## 2025 PROJECT SCREENING
STIP # | SPOT ID | Division | Route | From / Cross Street | To | Description | County | Previous ID / Work Completed | SCREENING DATE | FSU Proposed Recommendations | Reason for Recommendation | PEF (PDN Stage 1) | FSU PM | COMMENTS/NOTES | EXPRESS DESIGN COMPLETED | EXPRESS DESIGN COMPLETION DATE | CONNECT SCOPING SITE LINK | PROJECT SCOPING REPORT COMPLETED | Scoping Documentation Type | PROJECT SCOPING REPORT DOC DATE | PROJECT SCOPING REPORT DOC LINK | PRECON STAGE II WORK COMPLETED | LAST UPDATE - PRECON STAGE II WORK | CONNECT PRECONSTRUCTION SITE LINK | Env Features Map Available on Scoping Site? | ENVIRONMENTAL DOCUMENT TYPE | Environmental Document Type Reason | ENVIRONMENTAL DOCUMENT TYPE SCREENING | CONSTRUCTION DECISION MATRIX COMPLETED? | CONSTRUCTION DECISION MATRIX DATE | CONSTRUCTION DECISION MATRIX LINK | CONSTRUCTION PROCUREMENT METHOD (RECOMMENDED) | RESPONSIBLE GROUP (RECOMMENDED) | PROPOSED FY TO BEGIN PE | REVIEWER'S NOTES - RISK ASSESSMENT | REVIEWER - RISK CATEGORIES | PURPOSE & NEED STAKEHOLDERS - NCDOT PMU | PMU VERIFICATION DATE | PURPOSE & NEED STAKEHOLDERS - DIVISION | DIVISION VERIFICATION DATE | PURPOSE & NEED STAKEHOLDERS - LOCAL GOV | LOCAL GOV VERIFICATION DATE | PREFERRED CONCEPT LINK | REVIEWER'S NOTES - P&N | IS TRAFFIC DEMAND/CAPACITY A PRIMARY NEED? | HAS AN EDTE BEEN COMPLETED? | EDTE DATE | REVIEWER'S NOTES - TRAFFIC | REVIEWER'S NOTES - CONSTRUCTION | RISK ASSESSMENT WORKSHEET COMPLETED | RISK ASSESSMENT WORKSHEET DATE | RISK ASSESSMENT WORKSHEET LINK | # YEARS BETWEEN ROW Plans Completed (RPC) & LET | PROJECT BREAK POSSIBILITY | PROJECT BREAK COMMENTS | REVIEWER'S NOTES - PROJECT BREAKS | SUBMITTER/PROJECT MANAGER | SUBMITTER/PM EMAIL | OTHER PURPOSE & NEED NOTES | REVIEWER - RESPONSIBLE GROUP DECISION | REVIEWER - LET TYPE DECISION | REVIEWER - SME ENGAGEMENT CATEGORIES | REVIEWER - CANDIDATE FOR IN-HOUSE PRODUCTION | REVIEWER'S NOTES - GENERAL COMMENTS | CON Estimate (Alt 1) | CON Estimate (Alt 2) | STIP Tier
HP-0003 | H192736 | 05 | I-40 | Cary Towne Boulvard | N/A | Modify auxiliary lanes along I-40 between EB from NC 54 to Cary Towne Blvd, and WB from NC 54 to Wade, with ramp improvements at Cary Towne Blvd including traffic signals | Wake |  | 2025-03-05 | No Action Needed | PIF and environmental checklist completed, no PSR is needed | RK&K | Matt/Rupal |  | YES | 2024-01-24 | https://connect.ncdot.gov/site/scoping/Div05/H192736/Forms/By%20Topic.aspx | YES | Project Initiation Form | 2024-01-24 |  | NO |  |  | Yes | CE (Type I or II) | No major impacts anticipated and staying within current ROW. However, noise walls or additional Y-line improvements may change this. | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | CENTRAL | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-12-02 |  |  | NO | [14 empty] | 78300000 | 90000000
HP-0005 | H193009 | 05 | Division 5 Non-Municipal Division wide Signal System | N/A | N/A | Division-wide signal system to provide communication and cameras to improve signal timing. | Wake |  | 2025-03-05 | No Action Needed | Citywide Signal Project | n/a |  |  | Not Applicable |  |  | Not Applicable | Not Applicable |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 |  |  |  | Design Bid Build | CENTRAL | FUNDED FOR PE ONLY
HP-0007 | H231793 | 05 | US 70 Business | Raynor Road | Guy Road | Convert intersections at Raynor and Guy to RCI. This is an interim project pending U-6113. | Wake | H171592 (U-6113): Project Scoping Report (Same PEF - Accelerate) | 2025-03-05 | No Action Needed |  | Accelerate | Jennifer | The two RCIs were analyzed in the U-6113 / H171592 Express Design Traffic Evaluation (EDTE) using the U-6113 Traffic Forecast dated January 2021. | YES | 2025-02-07 | https://connect.ncdot.gov/site/scoping/Div05/H231793/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2025-03-28 | https://connect.ncdot.gov/site/scoping/Div04/H171592/H171592_ProjectScopingReport.pdf | NO |  |  | Yes | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | YES | 2025-03-28 | https://connect.ncdot.gov/site/scoping/Div05/H231793/HP0007_Contract%20Type%20Decision%20Tool.pdf | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO | [14 empty] | 78600000 | 104000000
HP-0008 | H172068 | 05 | Holly Springs Citywide Signal System | N/A | N/A | Install fiber to connect existing Town fiber to intersections, upgrade existing infrastructure including cabinets, controllers, and software. | Wake |  | 2025-03-05 | No Action Needed | Citywide Signal Project | n/a |  |  | Not Applicable |  |  | Not Applicable | Not Applicable |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 |  |  |  | Design Bid Build | CENTRAL | FUNDED FOR PE ONLY
HP-0009 | H184375 | 05 | US 401, US 70 Business | Tryon Road | N/A | Improve intersection signals and merging along 70/401 between Tryon and Mechanical Blvd. Study recommendations provided by VHB in recent Hot Spot study and any other recommendations by NCDOT. | Wake |  | 2025-03-05 | Express Design In Progress |  | VHB | Sonya | PEF is VHB "hotstudy" project, only kmz design files on scoping site | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div05/H184375/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | No | To be Determined | Is dependent on alternatives | To be Determined | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2025-01-07 |  |  | NO
HP-0010 | H231864 | 05 | Cary Citywide Signal System | N/A | N/A | Upgrade existing infrastructure, install new fiber, controllers, signals, connected vehicle technology and other equipment as necessary | Wake |  | 2025-03-05 | No Action Needed | Citywide Signal Project | n/a |  |  | Not Applicable |  |  | Not Applicable | Not Applicable |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 |  |  |  | Design Bid Build | CENTRAL | FUNDED FOR PE ONLY
HP-0012 | H231762 | 05 | US 401, SR 2684 (Tryon Road) | Tryon Road | N/A | Convert to Median U-Turn. Could also consider RCI. Complete streets improvements. | Wake |  | 2025-03-05 | Express Design In Progress |  | VHB | Sonya | PEF is VHB, complete streets project | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div05/H231762/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | No | CE (Type I or II) | Decision based on little to no information, 404 approval not likely | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | NO | NO |  |  |  | NO
HP-0013 | H170486 | 05 | US 1 (Raleigh Road) | Belmont Drive (Old County Home Road)/Raleigh Road (US 1)/Welcome Avenue | N/A | Improve intersection where Belmont Drive and Welcome Avenue meet | Vance |  | 2025-03-05 | TBD - Coordinate with Stakeholders | Older EXD (EXD summary complete) | Accelerate | Jennifer |  | YES | 2017-11-20 | https://connect.ncdot.gov/site/scoping/Div05/H170486/Forms/By%20Topic.aspx | YES | Project Screening Checklist |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-12 |  |  | NO | [14 empty] | 900000 | -
HP-0014 | H193266 | 05 | NC 55 | South Main Street | Holly Springs Road | Upgrade NC 55 corridor to 6 lane expressway/superstreet | Wake | H150718B: Express Design (Different PEF - RK&K) | 2025-03-05 | TBD - Coordinate with Stakeholders |  | VHB | Sonya |  | YES | 2025-03-27 | https://connect.ncdot.gov/site/scoping/Div05/H193266/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0016 | H231697 | 05 | US 70 (Glenwood Avenue) | NC 50 (Creedmoor Road) | N/A | Convert intersection to Median U-Turn. Open to other alternatives if suggested by Congestion Management Team. | Wake |  | 2025-03-05 | Express Design In Progress |  | Accelerate | Jennifer | PEF for ED is Accelerate EDTA recommends further ED work be explored | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div05/H231697/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Yes | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-10-15 |  |  | NO
HP-0017 | H140492 | 05 | NC 55 Bypass | SR 1144 (Main Street) | N/A | Upgrade existing at grade intersection to interchange. | Wake | Different PEF - RK&K | 2025-03-05 | TBD - Coordinate with Stakeholders | Older EXD (EXD summary complete) | VHB | Sonya | Original PEF was RK&K, but it is now being updated by VHB Feb 2022. | YES | 2018-05-30 | https://connect.ncdot.gov/site/scoping/Div05/H140492/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [15 empty] | NO
HP-0018 | H231717 | 05 | NC 55 (Apex Highway) | Cornwallis Road | N/A | Improve intersection to enhance safety and provide multimodal accommodations along both sides of all roadways within the project limits. | Durham |  | 2025-03-05 | TBD - Coordinate with Stakeholders | Review of Draft ED needed | JMT | Jennifer |  | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div05/H231717/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-05 |  |  | NO
HP-0021 | H231861 | 05 | Henderson Citywide Signal System | N/A | N/A | Install Citywide Signal System | Vance |  | 2025-03-05 | No Action Needed | Citywide Signal Project | n/a |  |  | Not Applicable |  |  | Not Applicable | Not Applicable |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | CENTRAL | FUNDED FOR PE ONLY
HP-0024 | H150744 | 05 | US 401 | Judd Parkway | US 401, NC 55, NC 42 interchange east of Fuquay Varina | Construct a median throughout the corridor with other access management improvements. Median is shown in the CAMPO 2040 MTP from Judd Parkway to the Five Points interchange east of town. | Wake | H150744 / U-5980: Express Design / PSR equivalent (Different PEF - Pinecone) | 2025-03-05 | TBD - Coordinate with Stakeholders | Older EXD | Benesch | Shane | Pinecone is PEF. Project goes by U-5980 also. PEC completed, note in FSU DB: "CAMPO desiring the Alt 3, FV desiring 10' SUP. Options to be evaluated with next SPOT submittal in P 7.0 " | YES | 2022-02-23 | https://connect.ncdot.gov/site/scoping/Div05/H150744/Forms/By%20Topic.aspx | YES | Project Screening Checklist | 2022-01-31 |  | NO |  |  | Yes | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0025 | H171610 | 05 | NC 98 | Six Forks Road | N/A | Upgrade intersection. | Wake |  | 2025-03-05 | No Action Needed |  | HNTB | Jennifer |  | YES | 2025-03-28 | https://connect.ncdot.gov/site/scoping/Div05/H171610/Forms/By%20Topic.aspx | Currently Under Development |  | 2025-06-20 | https://connect.ncdot.gov/site/scoping/Div05/H171610/Forms/By%20Topic.aspx | NO |  |  | Yes | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-27 |  |  | NO
BP-0001 | B141302 | 06 | Blounts Creek Phase III | Russell St | Cool Spring St | Construct multiuse path from Russell St to Cool Spring St | Cumberland |  | 2025-03-05 | No Action Needed |  | GPI | Rupal |  | YES | 2025-04-14 | https://connect.ncdot.gov/site/scoping/Div06/B141302/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Yes | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | NO |  |  |  |  | NO
HP-0011 | H191800 | 06 | NC 24, NC 87 | SR 1117 (Nursery Road) | N/A | Upgrade at-grade intersection to an interchange. | Harnett |  | 2025-03-05 | TBD - Coordinate with Stakeholders | No stakeholder coordination is documented. Coordinate with H150694-B as both EDTEs imply overdesign is possible | STV | Sonya | PEF is STV. Regroup with stakeholders to review results of ED/PSR | YES | 2023-07-31 | https://connect.ncdot.gov/site/scoping/Div06/H191800/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2024-10-01 | https://connect.ncdot.gov/site/scoping/Div06/H191800/H191800_ProjectScopingReport.pdf | NO |  |  | Yes | CE (Type III) | A CE level project but we would want to document more than a Type I CE due to some new location. | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2023-03-13 |  |  | NO
HP-0015 | H192435 | 06 | US 401 Bypass (Pamalee Drive) | NC 24/87 (Bragg Boulevard) | NC 210 (Murchison Road) | Upgrade multi-lane facility w/TWLTL to add raised center median with access management improvements. Include bicycle and pedestrian accommodations and bus pullouts. | Cumberland |  | 2025-03-05 | TBD - Coordinate with Stakeholders | EDTE may be appropriate now that project is funded for PE. Do express design alt showing thru-cut intersections instead of RCIs? | WSP | Sonya | PEF is WSP PSR updated Oct 2023, extensive documentation during ED from Rail division, Division 6, and MPO, City | YES | 2024-10-09 | https://connect.ncdot.gov/site/scoping/Div06/H192435/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2023-05-17 | https://connect.ncdot.gov/site/scoping/Div06/H192435/H192435_ProjectScopingReport.pdf | NO |  |  | Yes | EA | Community impacts and relocations. If some impacts can be avoided ahead of time and no significant opposition, a Type III CE may suffice. | Screened through ATLAS in PDN Stage 1 | YES | 2023-05-17 | https://connect.ncdot.gov/site/scoping/Div06/H192435/H192435_ConstructionTypeDecisionTool.pdf |  |  | FUNDED FOR PE ONLY |  |  | Documented verification in an ED | 2023-03-09 | Documented verification in an ED | 2023-03-09 | Documented verification in an ED | 2023-03-09 |  |  | YES | NO |  |  |  | NO
HP-0019 | H190797 | 06 | NC 211 (N Roberts Avenue) | SR 1531 (Saddletree Road / Clybourn Church Road) | N/A | Construct a Round About at the intersection. | Robeson |  | 2025-03-05 | No Action Needed | Streamlined PSR may be appropriate | In-House (design); RS&H (traffic) | Shane | ED done FSU in-house, EDTE done by RS&H confirms design will work. | YES | 2022-10-06 | https://connect.ncdot.gov/site/scoping/Div06/H190797/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | No | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-04 |  |  | NO
HP-0020 | H150694-B | 06 | NC 24, NC 87 | SR 1117 (Nursery Road) | SR 1451 (Manchester Road) | Widen to 6 lanes with median | Cumberland, Harnett | H191800: Project Scoping Report (Same PEF - STV) | 2025-03-05 | TBD - Coordinate with Stakeholders | Older EXD (EXD summary complete) | STV | MGH? | Draft PSR summary and PEC completed, EDTA should be reviewed prior to undertaking PSR, coordinate with EDTA for H191800, PEF is STV | YES | 2018-12-10 | https://connect.ncdot.gov/site/scoping/Div06/H150694B/Forms/By%20Topic.aspx | YES | Project Screening Checklist | 2018-12-10 |  | NO |  |  | Yes | CE (Type III) | Adding through lanes but no major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2025-01-17 |  |  | NO
HP-0033 | H184395 | 06 | NC 55, NC 210 | NC 210 | N/A | Add turning lanes and extend existing turning lanes or other improvements recommended by NCDOT | Harnett |  | 2025-03-05 | Express Design In Progress |  | HDR | Sonya | HDR is PEF, Final ED completed | YES | 2025-01-21 | https://connect.ncdot.gov/site/scoping/Div06/H184395/Forms/By%20Topic.aspx | YES | Project Initiation Form | 2025-01-21 |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0034 | H184385 | 06 | NC 55 | Broad Street | N/A | Construct roundabout at the intersection of NC 55 and North Broad Street in Angier, NC. | Harnett |  | 2025-05-21 | Express Design In Progress |  | HDR | Sonya | HDR is PEF, Final ED completed | YES | 2025-01-15 | https://connect.ncdot.gov/site/scoping/Div06/H184385/Forms/By%20Topic.aspx | YES | Project Initiation Form | 2025-01-15 |  | NO |  |  | Not Applicable | CE (Type I or II) | Residential relocations would require FHWA approval and likely a Type IIB CE | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0022 | H230379 | 07 | NC 49 | Plaza Drive | NC 54 | Relocation of Maple Avenue on new alignment from I-85/I-40 access ramps to NC 54. Due to realignment will also include relocation of Plaza Drive with a new signalized four-legged intersection at Plaza Drive to connect with relocated Plantation Drive. Landscaped medians, multi-use paths. | Alamance |  | 2025-03-05 | Express Design In Progress | Scaling back design | WGI | Jennifer | WGI is PEF | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div07/H230379/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Yes | CE (Type I or II) | No major impacts but a business relocation would require FHWA approval and likely a Type IIB CE | Screened through ATLAS in PDN Stage 1 | [5 empty] | FUNDED FOR PE ONLY | [10 empty] | NO | YES | 2025-04-23 |  |  | NO
HP-0030 | H191526 | 07 | US 70 (Church Street) | NC 62 | N/A | Intersection improvements to include dual lefts on all approaches, MUP on both sides, crosswalks and ped signals, limit to Overbrook and right turn lane onto Overbrook, improve intersection so that S. O'Neal has a through movement onto and off of NC 54 north and south, NC 54 from US 70 will then T into O'Neal Street. Project includes improvements to NC 62. Will go down to Trail Tow intersection at O'Neal Street. | Alamance |  | 2025-03-05 | Express Design In Progress |  | Michael Baker | Sonya | Michael Baker is PEF, newly assigned for ED | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div07/H191526/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | No | To be Determined | No project information available | To be Determined | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0023 | H185121 | 09 | US 158 | NC 801 | N/A | Upgrade intersection of US 158 & NC 801 by adding left turn lane on US 158 EB to achieve dual lefts onto NC 801 north. Also add right thru lane and right turn lane on NC 801 at intersection of US 158. | Davie |  | 2025-03-05 | No Action Needed | EXD summary complete | Exult | Jennifer | Exult is PEF | YES | 2022-12-20 | https://connect.ncdot.gov/site/scoping/Div09/H185121/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-11 |  |  | NO
HP-0026 | H170705 | 09 | I-40 | US 158 (Stratford Road) | N/A | Add Lanes to I-40 WB exit loop, modify traffic signal at intersection of US 158. Extend decel lane on I-40 WB. | Forsyth |  | 2025-03-05 | TBD - Coordinate with Stakeholders | Due to results of EDTA, stakeholders may want to expand alternatives in express design | STV | Sonya | STV is PEF, EDTA indicates current designs do not improve operations | YES | 2023-09-12 | https://connect.ncdot.gov/site/scoping/Div09/H170705/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-10-10 |  |  | NO
HP-0027 | H190716 | 09 | US 52 (Future I-285) | US 421 (Salem Parkway) - Exit 109 | SR 2264 (Akron Drive) - Exit 112 | Upgrade US 52 to interstate standards (I-285) by widening existing 4-lane facility to 6-lanes, widen paved shoulders, upgrade bridges / interchanges. Y-lines have been evaluated with the complete streets methodology and will include bike-ped accommodations as part of this project. | Forsyth | H090370 / U-2826: Project Scoping Report (Same PEF - KCA) | 2025-03-05 | TBD - Coordinate with Stakeholders | May be opportune time to conduct EDTE for interchanges or begin pre-NEPA studies | KCA | Matt | KCA is PEF, project also known as U-2826D, U-2826, and H090370 | YES | 2024-11-07 | https://connect.ncdot.gov/site/scoping/Div09/H190716/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2020-12-16 | https://connect.ncdot.gov/site/scoping/Div09/H090370/H90370_U-2826_Project%20Scoping%20Summary_12162020.pdf | NO |  |  | Yes | EA | Impacts to historic district/4f resources and public opposition. If impacts can be avoided ahead of time, a Type III may suffice. Merger screening is recommended. | Screened through ATLAS in PDN Stage 1 | NO |  |  | Alternative Delivery | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0028 | H230391 | 09 | NC 152, SR 1509 (Miller Road) | SR 1509 (Miller Road) | N/A | Construct a roundabout at the intersection of Miller Road and NC 152 west | Rowan |  | 2025-03-05 | Express Design In Progress |  | DRMP | Sonya |  | YES | 2025-03-11 | https://connect.ncdot.gov/site/scoping/Div09/H230391/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-19 |  |  | NO
HP-0029 | H190960 | 09 | NC 150 | SR 1526 (Rowan Mill Road), SR 1526 (Sherrills Ford Road) | N/A | Add storage and turn lanes per the road plans for the U-5900 TIP project. | Rowan |  | 2025-03-05 | TBD - Coordinate with Stakeholders | EDTE could be performed to confirm conceptual design alternatives | HNTB | Rupal |  | YES | 2024-04-04 | https://connect.ncdot.gov/site/scoping/Div09/H190960/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2024-04-04 | https://connect.ncdot.gov/site/scoping/Div09/H190960/REVISED%20Project%20Scoping%20Technical%20Report%2004-04-2024/H190960%20Revised%20PSTR.docx | NO |  |  | Not Applicable | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0031 | H150249 | 09 | US 421 | SR 1122 (Jonestown Road) | N/A | Upgrade the existing interchange by constructing additional travel and turn lanes on US 421 SB Ramp-Loop and Hanes Mall Blvd at intersection of Jonestown Rd. Revise TLs and storage on Jonestown Rd between Hanes Mall Blvd and US 421 NB Ramps. Remove two-way traffic from 421 NB On-ramp. Add lane to 421 NB On-ramp, extend accel lane distance onto mainline. Construct connector road from Benton Dr to Southwin Dr to accommodate access due to NB ramp revisions. Widen Jonestown Rd bridge. Add sidewalk. | Forsyth | H150249: Cost Update (Different PEF - Michael Baker); U-6074: Express Design / PE (Different PEF - HNTB) | 2025-03-05 | TBD - Coordinate with Stakeholders | Per PSR and EDTA, additional alternatives should be explored | Michael Baker | Rupal | HNTB did ED, PSR, Michael Baker did recent cost update known as H150249. Project also known as U-6074, EDTA indicates current alts do not solve the problem efficiently | YES | 2023-12-19 | https://connect.ncdot.gov/site/scoping/Div09/H150249/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2024-12-09 | https://connect.ncdot.gov/site/scoping/Div09/H150249/U6074_Scoping%20Report_2024.pdf | YES - Older than 2 Years | 2019-07-22 | https://connect.ncdot.gov/site/Preconstruction/division/div09/U-6074%20US%20421%20INTERCHNG/Project%20Development/Forms/AllItems.aspx | Yes | CE (Type III) | No major impacts but residential and commercial displacements will require FHWA signature | Screened through ATLAS in PDN Stage 1 | NO |  |  | Design Bid Build | DIVISION | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-10-16 |  |  | NO
HP-0001 | H230518 | 10 | US 74 (Andrew Jackson Highway) | Indian Trail-Fairview Road | North Rocky River Road | Widen 4 to 6 lanes | Union | F102023E: Express Design (Same PEF - MS Consultants) | 2025-03-05 | PSR Completed Already - do supplemental activities | PSR recently completed. Need to do pre-screening and other reviews. | MS Consultants | Ashley | PEF is ms consultants, final conceptual designs are complete. Also studied under F-102023E | YES | 2024-07-16 | https://connect.ncdot.gov/site/scoping/Div10/H230518/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2025-02-01 | https://connect.ncdot.gov/site/scoping/Div10/H230518/HP-0001%20(H230518)_Project%20Scoping%20Technical%20Report.pdf | NO |  |  | Yes | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-10-29 |  |  | NO
HP-0002 | H171622 | 10 | I-485 | I-77 - Exit 67 | I-85 - Exit 10 | Construct one Express Lane in each direction (in the median) on I-485 between I-77 and I-85 in southwest Charlotte [TOLL PROJECT] | Mecklenburg | Same ID: I-485 Express Lane Study (Different PEF - AECOM) | 2025-03-05 | No Action Needed | NCTA is currently working on planning-level activities. | STV | n/a | Previous I-485 Express Lane Study by AECOM (2021) | YES | 2024-03-20 | https://connect.ncdot.gov/site/scoping/Div10/H171622/Forms/By%20Topic.aspx | YES | Project Scoping Technical Report | 2023-11-16 | https://connect.ncdot.gov/site/scoping/Div10/H171622/I-6025%20H171622-Project%20Scoping%20Technical%20Report.pdf | NO |  |  | Not Applicable | CE (Type III) | Adding through lanes on an interstate, particularly managed lanes, typically requires a Type III at the least. Merger screening is recommended. | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | NO |  |  |  | NO
HP-0004 | H190784 | 10 | I-85 | SR 1291 (Billy Graham Parkway) | N/A | Improve Interchange | Mecklenburg |  | 2025-03-05 | TBD - Coordinate with Stakeholders | Recommend completing express design and PSR | RS&H | Matt | EDTA shows minimal improvement for either alternative. Might need to transition from EDTA to PE work. | Currently under development |  | https://connect.ncdot.gov/site/scoping/Div10/H190784/Forms/By%20Topic.aspx | NO |  |  |  | NO |  |  | No | CE (Type I or II) | No major impacts anticipated | Screened through ATLAS in PDN Stage 1 | NO |  |  |  |  | FUNDED FOR PE ONLY | [10 empty] | YES | YES | 2024-11-08 |  |  | NO
HP-0006 | H231862 | 05 07 | Chapel Hill Citywide Signal System | N/A | N/A | Plan and implement an improved signal system for the Town of Chapel Hill and the Town of Carrboro including transit signal priority. | Orange, Durham |  | 2025-03-05 | No Action Needed | Citywide Signal Project | n/a |  |  | Not Applicable |  |  | Not Applicable | Not Applicable |  |  | NO |  |  | Not Applicable | CE (Type I or II) | No major impact are anticipated | Screened through ATLAS in PDN Stage 1 |  |  |  | Design Bid Build | CENTRAL | FUNDED FOR PE ONLY

## Comments
Row 1 | Have reached out to Brian Peeler | ext-jdmartin4@ncdot.gov | 03/14/25 10:16 AM
| Doesn't appear to need more than a PIF/PEC | ext-jdmartin4@ncdot.gov | 03/17/25 12:32 PM
Row 3 | Gavin said PSR for this single intersection will be done by the end of march and can be updated quickly with new costs | ext-jdmartin4@ncdot.gov | 03/14/25 10:08 AM
Row 8 | Per Gavin, there are two alternatives. The first one has an ED but the second does not. His recommendation depends on whether or not the Division prefers alt 1 or wants to also explore ED for alt 2 | ext-jdmartin4@ncdot.gov | 03/14/25 10:11 AM
Row 11 | I have reached out to Brian Peeler on this one too | ext-jdmartin4@ncdot.gov | 03/14/25 10:18 AM
| Is there someone at VHB we can check with to see if they have done any work on this project within the past two or three years? | ext-jdmartin4@ncdot.gov | 03/17/25 12:38 PM
Row 20 | Shane requesting updated con, util, r/w estimates | ext-jdmartin4@ncdot.gov | 03/14/25 10:03 AM
Row 24 | Hold off for now because we are currently pushing WGI on completing the express design. But bring up once it is completed. | Matthew Quesenberry | 03/13/25 12:36 PM
Row 26 | Hold off for now because we are currently pushing PEF on completing the express design. But bring up once it is completed. | Matthew Quesenberry | 03/13/25 12:39 PM