## 2026 PSE_FUND AUTH DATES
2026 PS&E AND CENTRAL LETTING TIMELINES
PS&E MEETING DATES (WK16/Last Tues.) | PS&E COVERS (2-6 Wks prior to Turn-In) | PS&E TURN-IN DATES TO CONTRACT STANDARDS (WK14) | Agenda Cutoff Dates (by noon) (No AFRA Request required for STIP projects on the 12MLL) (Last Fri. every Month) | 2025 Item Due Dates | 2026 NCBOT MEETING DATES | Agenda Review | Turn In Date to BOT | NCBOT AGENDA COVERS | Bid Ad Shown on C7 due dates for Funding Help | 12MLL COVRES | 12MLL DELIVERY DATES (Prior to the 3rd Mon of Each Month) | 15MLL MEETING DATES (1st Thu) | 15MLL Covers | 2025 BOT MEETING DATES | Funding Status Report Due (Column 10) to CSDU Covering | STANDARD 4 WEEK ADVERTISEMENT (Request 1 Month Earlier For 8-Week Advertisement) | CENTRAL LETTING DATES (3rd Tues.)
2025-10-28 | Feb 2026- Mar 2026 | 2025-11-11 |  |  | 2026-01-08 |  |  | Jan Bid Ad for Feb Let => Jan Agenda |  | Jan 2026 - Dec 2026 | 2025-12-12 | 2026-01-08 | 2027-04-01 |  |  | 2026-01-20 | 2026-02-17
2025-11-25 | Mar 2026 - Apr 2026 | 2025-12-09 |  |  | 2026-02-05 |  |  | Feb Bid Ad for Mar Let =>Feb Agenda |  | Feb 2026 - Jan 2027 | 2026-01-16 | 2026-02-05 | 2027-05-01 |  |  | 2026-02-17 | 2026-03-17
2025-12-30 | Apr 2026 - May 2026 | 2026-01-13 |  |  | 2026-03-05 |  |  | Mar Bid Ad for Apr Let => Mar Agenda |  | Mar 2026 - Feb 2027 | 2026-02-13 | 2026-03-05 | 2027-06-01 |  |  | 2026-03-24 | 2026-04-21
2026-01-27 | May 2026 - Jun 2026 | 2026-02-10 |  |  | 2026-04-02 |  |  | Apr Bid Ad for May Let => Apr Agenda |  | Apr 2026 - Mar 2027 | 2026-03-13 | 2026-04-02 | 2027-07-01 |  |  | 2026-04-21 | 2026-05-19
2026-02-24 | Jun 2026 - Jul 2026 | 2026-03-10 |  |  | 2026-05-07 |  |  | May Bid Ad for Jun Let => May Agenda |  | May 2026 - Apr 2027 | 2026-04-17 | 2026-05-07 | 2027-08-01 |  |  | 2026-05-19 | 2026-06-16
2026-03-31 | Jul 2026 - Aug 2026 | 2026-04-14 |  |  | 2026-06-04 |  |  | Jun Bid Ad for Jul Let => Jun Agenda |  | Jun 2026 - May 2027 | 2026-05-15 | 2026-06-04 | 2027-09-01 |  |  | 2026-06-23 | 2026-07-21
2026-04-28 | Aug 2026 - Sept 2026 | 2026-05-12 |  |  | 2026-07-09 |  |  | Jul Bid Ad for Aug Let => Jul Agenda |  | Jul 2026 - Jun 2027 | 2026-06-12 | 2026-07-02 | 2027-10-01 |  |  | 2026-07-21 | 2026-08-18
2026-05-26 | Sept 2026 - Oct 2026 | 2026-06-09 |  |  | 2026-08-06 |  |  | Aug Bid Ad for Sept Let => Aug Agenda |  | Aug 2026 - Jul 2027 | 2026-07-17 | 2026-08-06 | 2027-11-01 |  |  | 2026-08-18 | 2026-09-15
2026-06-30 | Oct 2026 - Nov 2026 | 2026-07-14 |  |  | 2026-09-03 |  |  | Sept Bid Ad for Oct Let => Sept Agenda |  | Sept 2026 - Aug 2027 | 2026-08-14 | 2026-09-03 | 2027-12-01 |  |  | 2026-09-22 | 2026-10-20
2026-07-28 | Nov 2026 - Dec 2026 | 2026-08-11 |  |  | 2026-10-08 |  |  | Oct Bid Ad for Nov Let => Oct Agenda |  | Oct 2026 - Sept 2027 | 2026-09-18 | 2026-10-01 | 2028-01-01 |  |  | 2026-10-20 | 2026-11-17
2026-08-25 | Dec 2026 - Jan 2027 | 2026-09-08 |  |  | 2026-11-05 |  |  | Nov Bid Ad for Dec Let => Nov Agenda |  | Nov 2026 - Oct 2027 | 2026-10-16 | 2026-11-05 | 2028-02-01 |  |  | 2026-11-17 | 2026-12-15
2026-09-29 | Jan 2027 - Feb 2027 | 2026-10-13 |  |  | 2026-12-03 |  |  | Dec Bid Ad for Jan Let => Dec Agenda |  | Dec 2026 - Nov 2027 | 2026-11-13 | 2026-12-03 | 2028-03-01 |  |  | 2026-12-22 | 2027-01-19
Related to the covering materials
Related to the letting/funding process