## 36MLL-Central & Alternative
36 MONTH CENTRAL & ALTERNATIVE DELIVERY LET LIST (APRIL 2026 - MARCH 2029)
Let Date | Project ID | Let Type Description | WBS Element | Div | County | Project Description | CON Estimate | Combined with
2026-04-21 | I-6001 | Division Design Raleigh Let (DDRL) | 47956.3.1 | 5 | WAKE, FRANKLIN | I-87 /FUTURE I-87 /US 64/ US 264 FRANKLIN/WAKE COUNTIES FROM SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | $39,400,000
2026-04-21 | U-4753 | Division Design Raleigh Let (DDRL) | 39927.3.1 | 4 | WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) FROM SR 1003 (NEW HOPE ROAD)TO I-42 (FORMERLY US-70) IN GOLDSBORO. WIDEN TO FOUR LANES. | $21,900,000
2026-04-21 | W-5704E | Division Design Raleigh Let (DDRL) | 44850.3.5 | 4 | JOHNSTON | SR 1700 (COVERED BRIDGE ROAD) FROM EAST OF SR 1003 (BUFFALOROAD) TO WEST OF SR 2685 (HELENA LANE). | $16,100,000
2026-05-19 | A-0009CD | Division Design Raleigh Let (DDRL) | 32572.3.19 | 14 | GRAHAM | NC 28, FROM WEST OF SR 1228 (STECOAH ROAD) TO SR 1235 (GUNTERS GAP ROAD). UPGRADE ROADWAY. | $48,900,000
2026-05-19 | B-5833 | Raleigh Letting (LET) | 45786.3.1 | 11 | YADKIN | REPLACE BRIDGE 980029 OVER I-77 ON US 21 BUSINESS NEAR JONESVILLE. | $19,300,000
2026-05-19 | B-6047 | Division Design Raleigh Let (DDRL) | 48390.3.1 | 13 | RUTHERFORD | REPLACE BRIDGE 800145 OVER FLOYDS CREEK ON SR 2125 (HARRIS HENRIETTA ROAD). | $3,000,000
2026-05-19 | B-6051 | Raleigh Letting (LET) | 48708.3.1 | 12 | GASTON | US 29 / US 74 REPLACE BRIDGE 350091 OVER CATAWBA RIVER. | $76,600,000 | LET COMB. W/U-6143
2026-05-19 | BR-0004 | Division Design Raleigh Let (DDRL) | 67004.3.1 | 2 | HYDE, BEAUFORT | BRIDGE 060066 ON US 264 OVER PUNGO RIVER | $18,600,000
2026-05-19 | BR-0168 | Raleigh Letting (LET) | 67168.3.1 | 9 | FORSYTH | REPLACE BRIDGE 330289 ON SR4000 OVER US52 | $19,800,000
2026-05-19 | HS-2401P | Division Design Raleigh Let (DDRL) | 50973.3.17 | 1 | HERTFORD | US 158 / US 258 AT SR 1157 (CHARLIE POWELL ROAD), AT SR 1230 (CLOVER CIRCLE), AND AT SR 1160 (BENTHALL BRIDGE ROAD) NEAR MURFREESBORO. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | $5,100,000
2026-05-19 | I-5405D | Division Design Raleigh Let (DDRL) | 45454.3.12 | 10 | IREDELL, MECKLENBURG | PAVEMENT RECONSTRUCTION AND RESURFACING ON I-77 RAMPS AT US 21 (SUNSET BOULEVARD) SR 2143 (HARRIS BOULEVARD.), NC 73 (SAM FURR ROAD), SR 2158 (GRIFFITH STREET) AND SR 1109 (WILLIAMSON ROAD). | $10,600,000
2026-05-19 | U-6143 | Raleigh Letting (LET) | 48326.3.1 | 12 | GASTON | NC 7 (EAST CATAWBA STREET) AT US 29/74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7(EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 29/74 (WILKINSON BOULEVARD).(COMB W/ B-6051). | $7,300,000 | LET COMB. W/B-6051
2026-06-16 | B-5995 | Division Design Raleigh Let (DDRL) | 48190.3.1 | 2 | PAMLICO | REPLACE BRIDGE 680057 OVER DAWSON CREEK ON SR 1302 (JANIEROROAD) IN ARAPAHOE. | $6,300,000
2026-06-16 | BP7-R001 | Division Design Raleigh Let (DDRL) | BP7.R001.3 | 7 | ROCKINGHAM | REPLACE ROCKINGHAM BR780023 | $15,200,000
2026-06-16 | HE-0016 | Division Design Raleigh Let (DDRL) | 51325.3.1 | 3 | BRUNSWICK | NEW ROUTE ALONG NORTH SIDE OF US 74 FROM 0.5 MILES EAST OF BRUNSWICK COUNTY LINE TO 1.5 MILES EAST OF BRUNSWICK COUNTY LINE. CONSTRUCT ROAD ON NEW LOCATION AND CONSTRUCT INTERSECTIONS WITH US 74 ON EAST AND WEST TERMINI. | $11,400,000
2026-06-16 | R-5858 | Division Design Raleigh Let (DDRL) | 47546.3.1 | 2 | CARTERET | NC 24 CARTERET COUNTY. AT NC 58 INTERSECTION IN CAPE CARTERET. INTERSECTION IMPROVEMENTS. | $10,600,000
2026-06-16 | U-5743 | Division Design Raleigh Let (DDRL) | 50165.3.1 | 8 | RANDOLPH | NC 42 FROM SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64/ NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | $13,700,000
2026-07-21 | BR-0019 | Raleigh Letting (LET) | 67019.3.1 | 12 | GASTON | BRIDGE 350056 ON NC 275 OVER SF CATAWBA RIVER | $13,700,000
2026-07-21 | BR-0099 | Division Design Raleigh Let (DDRL) | 67099.3.1 | 13 | RUTHERFORD | REPLACE BRIDGE 800012 ON NC 120 OVER US 74 BYP | $8,200,000
2026-07-21 | HB-0035 | Raleigh Letting (LET) | 50639.3.1 | 7 | ROCKINGHAM | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK ON SR 1535 (PRICE ROAD) IN EDEN | $4,900,000
2026-07-21 | I-5716 | Raleigh Letting (LET) | 50133.3.1 | 12 | CATAWBA | I-40 AT SR 1007 (LENOIR RHYNE BOULEVARD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | $13,300,000
2026-07-21 | I-5934 | Division Design Raleigh Let (DDRL) | 45876.3.1 | 4 | NASH | I-95 FROM SR 1770 (SUNSET AVENUE)(MILEMARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD)(MILEMARKER 142.1); BRIDGE 630218 ON SR 1604 OVER I-95; BRIDGE 630220 ON SR 1524 OVER I-95; BRIDGE 630219 ON SR 1544 OVER I-95; | $6,500,000
2026-07-21 | U-4714AC | Raleigh Letting (LET) | 39078.3.9 | 10 | MECKLENBURG, UNION | SR 1009 (JOHN STREET / OLD MONROE ROAD), FROM EAST OF I-485TO WEST OF MORNINGSIDE MEADOW LANE IN MATTHEWS. WIDEN TO MULTI-LANES. (COMBINED WITH U-4714BA) | $40,700,000 | LET COMB. W/U-4714BA
2026-07-21 | U-4714BA | Raleigh Letting (LET) | 39078.3.10 | 10 | UNION | SR 1009 (JOHNSTREET / OLD MONROE ROAD) WEST OF MORNINGSIDE MEADOW LANE TO INDIAN TRAIL ROAD IN MATTHEWS. WIDEN TO MULTI-LANES. (COMB W/U-4714AC) | $22,555,000 | LET COMB. W/U-4714AC
2026-08-18 | 17BP.7.R.114 | Division Design Raleigh Let (DDRL) | 17BP.7.R.114 | 7 | GUILFORD | REPLACE GUILFORD BR400052 | $5,500,000
2026-08-18 | BR-0092 | Raleigh Letting (LET) | 67092.3.1 | 7 | ORANGE | REPLACE BRIDGE 670037 ON NC 86 OVER NEW HOPE CREEK | $5,600,000
2026-08-18 | HL-0065 | Division Design Raleigh Let (DDRL) | 50685.3.1 | 13 | RUTHERFORD | US 221A (CHARLOTTE ROAD/MAIN STREET) CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | $23,800,000
2026-08-18 | I-6011A | Division Design Raleigh Let (DDRL) | 48690.3.2 | 6 | ROBESON | US 74 (FUTURE I-74) AT SR 2225(CREEK ROAD) NORTH OF ORRUM. UPGRADE AT-GRADE INTERSECTION AT INTERCHANGE. | $9,200,000
2026-08-18 | P-5717 | Raleigh Letting (LET) | 46929.3.1 | 5 | DURHAM | NORFOLK SOUTHERN H LINE CROSSING NO. 734 742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | $41,500,000
2026-08-18 | U-4700CA | Division Design Raleigh Let (DDRL) | 35993.3.5 | 11 | CALDWELL | US 321 FROM SR 1160 (MOUNT HERMAN ROAD.UPGRADE INTERSECTIONTO SUPERSTREET DESIGN. | $8,200,000 | LET COMB. W/U-4700CB
2026-08-18 | U-4700CB | Division Design Raleigh Let (DDRL) | 35993.3.9 | 11 | CALDWELL | US 321-AT SR 1809/1952 (PINE MOUNTAIN ROAD) IN HUDSON. UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700C. | $16,400,000 | LET COMB. W/U-4700CA
2026-08-18 | U-5810 | Division Design Raleigh Let (DDRL) | 44383.3.1 | 11 | WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE). FROM US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | $56,800,000
2026-08-18 | U-6043 | Division Design Raleigh Let (DDRL) | 46984.3.1 | 12 | GASTON | US 29 / US 74 (FRANKLIN BOULEVARD) FROM SR 2200 (COX ROAD) TO EAST OF LINEBERGER ROAD IN GASTONIA. CONSTRUCT ADDITIONALEASTBOUND LANE AND EXTEND EXISTING CULVERT. | $7,900,000
2026-09-15 | B-4676A | Division Design Raleigh Let (DDRL) | 33831.3.3 | 11 | WILKES | SR 1001 (OAKWOODS RD.) FROM FOREST HILL DRIVE TO NC 268 (E.MAIN ST.). PROPOSED ROADWAY WIDENING; MULTIUSE PATHS; AND NEW BRIDGE OVER CUB CREEK | $8,400,000
2026-09-15 | HN-0033 | Division Design Raleigh Let (DDRL) | 51515.3.1 | 4 | WAYNE | NC 55 AND SR 1744 (OLD SEVEN SPRINGS ROAD/INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. | $4,500,000
2026-09-15 | HN-0040 | Division Design Raleigh Let (DDRL) | 51758.3.1 | 4 | JOHNSTON | SR 1908 (FIRE DEPT. ROAD) AT BUFFALO ROAD INTERSECTION NORTH OF WILSON'S MILLS. CONSTRUCT ROUNDABOUT. | $5,000,000
2026-09-15 | I-4409A | Division Design Raleigh Let (DDRL) | 38714.3.3 | 13 | BUNCOMBE | REPLACE BRIDGE 100488 ON I-40 OVER SR 2500 (BLUE RIDGE ROAD) IN BLACK MOUNTAIN. | $7,000,000
2026-09-15 | I-5995 | Division Design Raleigh Let (DDRL) | 47950.3.1 | 5 | WAKE, DURHAM | I-40 - DURHAM/WAKE COUNTIES FROM EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | $44,900,000
2026-09-15 | R-5100B | Division Design Raleigh Let (DDRL) | 41890.3.4 | 12 | IREDELL | SR 1109 (WILLIAMSON ROAD) FROM SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | $10,500,000
2026-09-15 | U-5711 | Division Design Raleigh Let (DDRL) | 50160.3.1 | 8 | RANDOLPH | SR 1712 (PINEVIEW STREET) FROM WEST OF SYLVAN DRIVE TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | $9,700,000
2026-09-15 | U-5728 | Division Design Raleigh Let (DDRL) | 54019.3.1 | 3 | ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) AT SR 1308 (BELL FORK ROAD)IN JACKSONVILLE IMPROVE INTERSECTION | $6,800,000
2026-09-15 | U-5834 | Division Design Raleigh Let (DDRL) | 50226.3.1 | 13 | BUNCOMBE | SR 3116 (MILLS GAP ROAD) FROM US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | $37,600,000
2026-09-15 | U-5965 | Division Design Raleigh Let (DDRL) | 45979.3.1 | 12 | GASTON | US 29 (FRANKLIN BOULEVARD) AND NC 274 CONSTRUCT INTERSECTION IMPROVEMENTS | $5,300,000
2026-10-20 | BL-0080 | Raleigh Letting (LET) | 50808.3.1 | 10 | MECKLENBURG | HUNTERSVILLE CONSTRUCT GREENWAY CULVERT UNDER US 21. (COMB W/U-5771). | $3,250,000 | LET COMB. W/U-5771
2026-10-20 | BL-0119 | Raleigh Letting (LET) | 51704.3.1 | 10 | MECKLENBURG | MCDOWELL CREEK GREENWAY FROM NC 73 IN HUNTERSVILLE. CONSTRUCT PEDESTRIAN BRIDGE OVER NC 73 NEAR LINDHOLM DRIVE. | $6,100,000 | LET COMB. W/U-5765
2026-10-20 | BP13-R052 | Design Build Let (DBL) | BP13.R052.3 | 13 | RUTHERFORD | EXPRESS DESIGN BUILD - REPLACEMENT OF RUTHERFORD STRUCTURE 800239 ON SR-1325 (NANNYTOWN RD.) | $0
2026-10-20 | BR-0174 | Division Design Raleigh Let (DDRL) | 52219.3.1 | 3 | PENDER | REPLACE BRIDGE 700037 ON NC 53 OVER ANGOLA CREEK. | $8,900,000
2026-10-20 | HB-0001A | Design Build Let (DBL) | 49475.3.2 | 18 | DARE, EDGECOMBE, NASH, TYRRELL, WASHINGTON, MARTIN | US 64 BROADBAND FOR TRAVELER INFORMATION SYSTEMS AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | $29,700,000
2026-10-20 | HB-0020 | Division Design Raleigh Let (DDRL) | 50351.3.1 | 11 | WILKES | REPLACE BRIDGE 960730 OVER YADKIN RIVER ON SR 1185 (CURTIS BRIDGE ROAD) | $13,100,000
2026-10-20 | HL-0007 | Division Design Raleigh Let (DDRL) | 49366.3.1 | 5 | WAKE | NC 55 AT SR 1191 (TECHNOLOGY DRIVE)/SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION | $28,000,000
2026-10-20 | I-5715 | Raleigh Letting (LET) | 50128.3.1 | 10 | MECKLENBURG | I-77 AT NC 73. UPGRADE INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | $79,900,000 | LET COMB. W/BL-0119 & U-5765
2026-10-20 | P-5707 | Raleigh Letting (LET) | 44643.3.1 | 5 | WAKE | CSX S LINE, CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | $39,800,000
2026-10-20 | R-5796 | Division Design Raleigh Let (DDRL) | 46881.3.1 | 1 | HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) FROM PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | $20,300,000
2026-10-20 | R-5810 | Division Design Raleigh Let (DDRL) | 46978.3.1 | 1 | MARTIN | US 17 FROM SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | $13,100,000
2026-10-20 | U-5765 | Raleigh Letting (LET) | 50178.3.1 | 10 | MECKLENBURG | NC 73 (SAM FURR ROAD) FROM SR 5544 (WEST CATAWBA AVENUE) TOSR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | $44,300,000 | LET COMB. W/BL-0119
2026-10-20 | U-5771 | Raleigh Letting (LET) | 50183.3.1 | 10 | MECKLENBURG | US 21 FROM SR 2136 (GILEAD ROAD) TO SR 6028 (HOLLY POINT DRIVE) IN HUNTERSVILLE. WIDEN TO FOUR LANES. | $32,100,000 | LET COMB. W/ BL-0080
2026-11-17 | 17BP.13.R.184 | Division Design Raleigh Let (DDRL) | 17BP.13.R.184 | 13 | MITCHELL | REPLACE BRIDGE 101 ON SR1002 OVER BIG CRABTREE CREEK IN MITCHELL COUNTY | $6,000,000
2026-11-17 | B-5857 | Division Design Raleigh Let (DDRL) | 45810.3.1 | 12 | GASTON | REPLACE BRIDGE 82 OVER A SOUTH FORK OF CATAWBA RIVER ON US 29/US 74.(COMB W/U-6146). | $11,800,000 | LET COMB. W/U-6146 & WBS 47897
2026-11-17 | BR-0140 | Division Design Raleigh Let (DDRL) | 67140.3.1 | 9 | DAVIDSON | REPLACE 280087 AND 280089 ON I85BUSN,US29,US70 OVER WSSB RAILROAD | $14,900,000
2026-11-17 | HB-0038 | Division Design Raleigh Let (DDRL) | 50636.3.1 | 4 | NASH | SR 1745 (BEND OF THE RIVER ROAD) REPLACE BRIDGE 630110 OVER THE TAR RIVER RESERVOIR. | $6,500,000
2026-11-17 | HE-0017 | Division Design Raleigh Let (DDRL) | 51679.3.1 | 6 | CUMBERLAND | SR 1711 (BETHUNE DRIVE) AT EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). | $7,300,000
2026-11-17 | I-2513AC | Raleigh Letting (LET) | 34165.3.8 | 13 | BUNCOMBE | I-26, I-240 WIDEN TO SIX LANE FREEWAY. | $284,200,000
2026-11-17 | I-5958 | Division Design Raleigh Let (DDRL) | 45910.3.1 | 7 | ORANGE | I-40/I-85 FROM WEST OF SR 1114(BUCKHORN ROAD)TO WEST OF SR 1006 (ORANGE GROVE ROAD) PAVEMENT REHABILITATION | $26,000,000
2026-11-17 | P-5709 | Raleigh Letting (LET) | 46920.3.1 | 7 | GUILFORD | GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A), AND CLOSE O'FERRELL STREET CROSSING (722961B) AT NCRR/NSR-NCLINE IN GREENSBORO. | $27,300,000
2026-11-17 | R-5759 | Division Design Raleigh Let (DDRL) | 44691.3.1 | 11 | WILKES | NC 115 FROM US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | $69,100,000
2026-11-17 | U-6078 | Division Design Raleigh Let (DDRL) | 47525.3.1 | 12 | GASTON | NC 275 AT INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR1456 (WHITE JENKINS ROAD), AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND | $7,600,000
2026-11-17 | U-6146 | Division Design Raleigh Let (DDRL) | 48392.3.2 | 12 | GASTON | US 29/US 74 (WILKINSON BOULEVARD)FROM MARKET STREET TO SR 2015 (ALBERTA AVENUE). (COMB W/B-5857). | $46,100,000 | LET COMB. W/B-5857 & WBS 47897
2026-12-15 | B-5876 | Raleigh Letting (LET) | 48070.3.1 | 13 | RUTHERFORD | REPLACE BRIDGE 83 AND 84 OVER SECOND BROAD RIVER ON US 74 BYPASS | $18,700,000
2026-12-15 | BR-0101 | Division Design Raleigh Let (DDRL) | 67101.3.1 | 13 | RUTHERFORD | REPLACE BRIDGE 800104 ON US 64 OVER COVE CREEK | $7,800,000
2026-12-15 | HB-0069 | Division Design Raleigh Let (DDRL) | 50739.3.1 | 11 | WILKES | REPLACE BRIDGE 960012 OVER REDDIES RIVER ON US 421 BUSINESS(D STREET) | $21,100,000
2026-12-15 | I-5701 | Design Build Let (DBL) | 50119.3.1 | 5 | WAKE | I-40/US 64; FROM I-440/US 1/US 64 TO SR 1009 (LAKE WHEELER ROAD) IN RALEIGH WIDEN FROM SIX TO EIGHT LANES. (COMB W/I-5703). | $163,100,000 | LET COMB. W/I-5703
2026-12-15 | I-5703 | Design Build Let (DBL) | 50120.3.GV1 | 5 | WAKE | I-40 AND I-440/US 1/US 64 INTERSECTION RECONSTRUCT INTERCHANGE. (COMB W/I-5701). | $330,900,000 | LET COMB. W/I-5701
2026-12-15 | I-5993 | Division Design Raleigh Let (DDRL) | 47948.3.GV1 | 5 | DURHAM | I-40 - DURHAM COUNTY FROM US 15/US 501 TO EAST OF NC 147 (INCLUDES I-5994).PAVEMENT REHABILITAION. | $50,700,000
2026-12-15 | R-5826B | Division Design Raleigh Let (DDRL) | 47098.3.3 | 8 | MONTGOMERY | NC 109 FROM SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). UPGRADE ROADWAY. | $13,600,000
2026-12-15 | U-3422B | Division Design Raleigh Let (DDRL) | 39001.3.3 | 6 | CUMBERLAND | SR 1003 (CAMDEN ROAD) FROM JUST WEST OF SR 1112 (ROACKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | $54,000,000
2027-01-19 | BR-0147 | Raleigh Letting (LET) | 67147.3.1 | 4 | NASH | REPLACE 630205 ON US64BUS OVER TAR RIVER OVERFLOW | $3,200,000
2027-01-19 | FF-0001 | Raleigh Letting (LET) | 50801.3.1 | 1 | HYDE | REPLACE STRUCTURES 470114 AND 470115 (FERRY RAMPS) OVER SILVER LAKE ON NC 12 AT THE OCRACOKE FERRY TERMINAL. | $19,400,000
2027-01-19 | I-3306AC | Raleigh Letting (LET) | 34178.3.9 | 7 | ORANGE | I-40 AT NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTION FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | $7,300,000
2027-01-19 | I-5900 | Division Design Raleigh Let (DDRL) | 45867.3.1 | 13 | MCDOWELL | I-40 FROM MILE MARKER 73 TO MILE MARKER 86. PAVEMENT REHABILITATION. | $30,100,000
2027-01-19 | I-5901 | Division Design Raleigh Let (DDRL) | 45868.3.1 | 13 | BUNCOMBE | I-240, FROM MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | $21,000,000
2027-01-19 | I-5998 | Division Design Raleigh Let (DDRL) | 47953.3.1 | 5 | WAKE, DURHAM | I-540 FROM I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | $24,900,000
2027-02-16 | BR-0005 | Raleigh Letting (LET) | 67005.3.1 | 2 | BEAUFORT | BRIDGE 060075 ON NC 33 OVER CHOCOWINITY CREEK | $13,200,000
2027-02-16 | HB-0016 | Raleigh Letting (LET) | 50923.3.1 | 1 | WASHINGTON | NC 32 PRESERVATION OF BRIDGE 930015 ON NC 32 OVER ALBEMARLESOUND. | $60,900,000
2027-02-16 | I-5888B | Division Design Raleigh Let (DDRL) | 46408.3.3 | 13 | BUNCOMBE | I - 40, REHABILITATE BRIDGES 100024, 100071, 100156, 100164, 100210, AND 100215 FROM MILE POINT 37 TO MILE POINT 44 AT HAYWOOD/BUNCOMBE COUNTY LINE. | $8,900,000
2027-02-16 | I-5947A | Division Design Raleigh Let (DDRL) | 45894.3.2 | 8 | MONTGOMERY | I-73/ I-74/ US220 FROM RICHMOND COUNTY LINE TO NC 211. | $19,800,000
2027-02-16 | R-5717 | Division Design Raleigh Let (DDRL) | 50213.3.1 | 1 | CURRITUCK, CAMDEN | SR 1227/SR 1208 (S. MILLS ROAD) SR 1224/SR1223 (OLD SWAMP ROAD) AT NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. (COMB W/R-5717B). WIDEN AND INTERSECTION IMPROVEMENTS. | $38,100,000 | LET COMB. W/R-5717B
2027-02-16 | R-5717B | Division Design Raleigh Let (DDRL) | 50213.3.3 | 1 | CURRITUCK, CAMDEN | REPLACE BRIDGE 140013 OVER JOYCE CREEK. (COMB W/R-5717). | $2,200,000 | LET COMB. W/R-5717
2027-02-16 | R-5718 | Division Design Raleigh Let (DDRL) | 50472.3.1 | 4 | JOHNSTON | SR 1003 (BUFFALO ROAD) FROM US 70 TO SR 1934 (OLD BEULAH ROAD) IN SELMA. WIDEN TO THREE LANES | $25,700,000
2027-02-16 | U-5753 | Raleigh Letting (LET) | 51078.3.1 | 8 | HOKE | SR 1305, US 401 TO PLANK ROAD; AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD) WIDEN TO MULTILANES. | $62,100,000
2027-02-16 | U-6014 | Division Design Raleigh Let (DDRL) | 47159.3.1 | 7 | ALAMANCE | SR 1716 (GRAHAM-HOPEDALE ROAD) FROM SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BICYCLE/PEDESTRIAN ACCOMMODATIONS. | $19,200,000
2027-03-16 | HI-0013 | Division Design Raleigh Let (DDRL) | 49984.3.1 | 4 | NASH | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | $32,700,000
2027-03-16 | I-5921 | Division Design Raleigh Let (DDRL) | 45928.3.1 | 12 | GASTON | I-85 - GASTON COUNTY FROM CLEVELAND COUNTY TO MILEMARKER 14. PAVEMENT REHABILITATION. | $26,400,000
2027-03-16 | I-5925 | Division Design Raleigh Let (DDRL) | 45934.3.1 | 14 | HENDERSON | I-26 IN HENDERSON COUNTY FROM MILEMARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | $25,800,000
2027-03-16 | I-5926 | Division Design Raleigh Let (DDRL) | 45935.3.1 | 14 | POLK | I-26 POLK COUNTY FROM HENDERSON COUNTY LINE TO MILEMARKER 65. PAVEMENT REHABILITATION. | $19,700,000
2027-03-16 | U-5844 | Division Design Raleigh Let (DDRL) | 50234.3.1 | 7 | ALAMANCE | NC 62 FROM SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON, WIDEN TO A THREE-LANE FACILITY. | $18,500,000
2027-03-16 | U-6110 | Division Design Raleigh Let (DDRL) | 48334.3.1 | 4 | WAYNE | US 70 AT SR 1711(NORTH OAK FOREST ROAD) | $13,600,000
2027-04-20 | BF-0002 | Division Design Raleigh Let (DDRL) | 50701.3.1 | 14 | TRANSYLVANIA | ECUSTA TRAIL, TRANSYLVANIA COUNTY LINE TO LAMB CREEK. CONSTRUCT GREENWAY. | $29,100,000
2027-04-20 | P-5725 | Raleigh Letting (LET) | 47603.3.1 | 10 | CABARRUS | NORFOLK SOUTHERN RAILROAD COMPANY, VARIOUS LOCATIONS IN KANNAPOLIS. CONSTRUCT TRACK IMPROVMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, REATINING WALL AND SIGNALING EQUIPMENT. | $13,900,000
2027-04-20 | R-5724B | Division Design Raleigh Let (DDRL) | 50217.3.3 | 8 | CHATHAM | US 15/US 501 FROM NORTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | $27,200,000
2027-04-20 | U-5911 | Division Design Raleigh Let (DDRL) | 44642.3.1 | 4 | NASH | NC 48 AT NC 4 IN ROCKY MOUNT. CONSTRUCT ROUNDABOUT. | $8,500,000
2027-05-18 | BR-0141 | Division Design Raleigh Let (DDRL) | 51604.3.1 | 7 | ROCKINGHAM | SR 2150 (RIVER ROAD) REPLACE BRIDGE 780123 OVER US 220 / US 311. | $4,100,000
2027-05-18 | R-5899 | Division Design Raleigh Let (DDRL) | 48355.3.1 | 3 | PENDER | NC 210 AT SR 1560 (WATTS LANDING ROAD) INTERSECTION IN SURFCITY. IMPROVE INTERSECTION. | $7,500,000
2027-06-15 | HB-0039 | Design Build Let (DBL) | 50603.3.1 | 3 | NEW HANOVER | US 17/US 76/US 421. REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. | $1,002,300,000
2027-06-15 | HL-0006 | Division Design Raleigh Let (DDRL) | 49365.3.1 | 5 | WAKE | US 401 AT SR 1393 (HILLTOP-NEEDMORE ROAD)SR 2751 (HILLTOP ROAD)/ SR 2752 (AIR PARK ROAD) AND SR 1375 (LAKE WHEELER ROAD)IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONSAND REALIGN SR 2751 TO INTERSECTION OPPOSITE SR 1375. | $42,400,000
2027-06-15 | I-5707 | Raleigh Letting (LET) | 50123.3.1 | 5 | DURHAM | I-40 FROM NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY/TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | $9,300,000
2027-06-15 | I-5718 | Design Build Let (DBL) | 49020.3.7 | 10 | MECKLENBURG | I-77 FROM THE SOUTH CAROLINA STATE LINE TO I-277 / NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT THE I-277 INTERCHANGES. | $2,658,900,000
2027-06-15 | P-5748B | Raleigh Letting (LET) | 48336FRA.3.1 | 10 | UNION | CSX SG LINE AT SR 1300(HELMS ROAD) INTERSECTION CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432(TORY PATH). | $24,200,000
2027-06-15 | R-2822BB | Division Design Raleigh Let (DDRL) | 34508.2.6 | 14 | GRAHAM | NC 143 FROM WEST BUFFALO CREEK OVER NC 143 BUSINESS. REPLACE BRIDGE 370013. | $33,500,000
2027-06-15 | R-5772 | Division Design Raleigh Let (DDRL) | 44692.3.1 | 11 | WILKES | SR 1001 (OAKWOODS ROAD) FROM US 421 TO FOREST HILL DRIVE. UPGRADE EXISTING ROADWAY. | $16,800,000
2027-06-15 | U-2817 | Division Design Raleigh Let (DDRL) | 34868.3.4 | 2 | PITT | SR 1700 (EVANS STREET / OLD TAR ROAD) FROM SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE | $123,300,000
2027-07-20 | B-5950 | Division Design Raleigh Let (DDRL) | 45985.3.1 | 9 | FORSYTH | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK ON NC 67(WESTBOUND SILAS CREEK PARKWAY) IN WINSTON-SALEM. | $8,700,000
2027-07-20 | B-6040 | Division Design Raleigh Let (DDRL) | 48389.3.1 | 13 | MCDOWELL | US 70 REPLACE BRIDGE 580127 OVER SOUTHERN RAILROAD. | $4,200,000
2027-07-20 | BR-0018 | Raleigh Letting (LET) | 67018.3.1 | 9 | FORSYTH | BRIDGE 330048 ON NC 8 OVER US 52 | $17,200,000
2027-07-20 | BR-0040 | Raleigh Letting (LET) | 52189.3.1 | 14 | POLK | NC 9 BRIDGE 740037 OVER GREEN RIVER. REPLACE BRIDGE. | $5,700,000
2027-07-20 | BR-0049 | Raleigh Letting (LET) | 67049.3.1 | 10 | UNION | BRIDGE 890034 ON CONCORD AVE OVER US 74, NC 200 | $9,100,000
2027-07-20 | BR-0074 | Raleigh Letting (LET) | 67074.3.1 | 2 | CRAVEN | REPLACE BRIDGE 240091 AND 240092 ON US 70 OVER S. PR. SLOCUM CREEK | $9,400,000
2027-07-20 | BR-0171 | Raleigh Letting (LET) | 67171.3.1 | 13 | MCDOWELL | REPLACE BRIDGE 580096 ON US70 OVER CATAWBA RIVER OVER FLOW | $8,000,000
2027-07-20 | P-5726 | Raleigh Letting (LET) | 47604.3.1 | 9 | ROWAN | RAILROAD NORFOLK SOUTHERN NORFOLK SOUTHERN MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS,SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | $13,600,000
2027-07-20 | P-5731 | Raleigh Letting (LET) | 47610.3.1 | 9 | DAVIDSON | ENORFOLK SOUTHERN, CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | $72,000,000
2027-07-20 | P-5737 | Raleigh Letting (LET) | 48153.3.1 | 5 | WAKE | CSX S LINE AT SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | $29,200,000
2027-07-20 | R-5721B | Raleigh Letting (LET) | 50215.3.2 | 10 | MECKLENBURG | NC 73 FROM VANCE ROAD EXTENSION / SR 2128/SR 2196 (BEATTIESFORD ROAD) TO SR 5544(WEST CATAWBA AVENUE). WIDEN TO MULTILANES. | $59,300,000
2027-07-20 | U-3467 | Raleigh Letting (LET) | 39019.3.1 | 10 | UNION | NC 84 (WEDDINGTON ROAD) FROM NC 16 (PROVIDENCE ROAD) TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | $103,300,000
2027-07-20 | U-5747A | Division Design Raleigh Let (DDRL) | 50167.3.2 | 5 | WAKE | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. (COMB W/U-5747B & U-5750). | $26,000,000 | LET COMB. W/U-5747B & U-5750
2027-07-20 | U-5747B | Division Design Raleigh Let (DDRL) | 50167.3.3 | 5 | WAKE | SR 1635 AT NC 54 - CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. (COMB W/U-5747A & U-5750). | $38,200,000 | LET COMB. W/U-5747A & U-5750
2027-07-20 | U-5750 | Division Design Raleigh Let (DDRL) | 50170.3.1 | 5 | WAKE | NC 54 FROM NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. CONSTRUCT ADDITIONAL LANES. (COMB W/U-5747A & U-5747B). | $30,100,000 | LET COMB. W/U-5747 A & B
2027-08-17 | BP5-R115 | Division Design Raleigh Let (DDRL) | BP5.R115.3 | 5 | GRANVILLE | REPLACE BRIDGE 144 OVER JOHN KERR RESERVOIR ON SR 1443 (HARRY DAVIS ROAD) | $5,900,000
2027-08-17 | BR-0031 | Raleigh Letting (LET) | 67031.3.1 | 14 | MACON | REPLACE BRIDGE 550227 OVER NANTAHALA RIVER ON SR 1310 (WAYAH ROAD). | $3,100,000 | LET COMB. W/BR-0052 & BR-0053
2027-08-17 | BR-0052 | Raleigh Letting (LET) | 67052.3.1 | 14 | MACON | REPLACE BRIDGE 550227 OVER NANTAHALA RIVER ON SR 1310 (WAYAH ROAD). | $3,000,000 | LET COMB. W/BR-0031 & BR-0053
2027-08-17 | BR-0053 | Raleigh Letting (LET) | 67053.3.1 | 14 | MACON | REPLACE BRIDGE 550228 OVER NANTAHALA RIVER ON SR 1310 (WAYAH ROAD). | $3,600,000 | LET COMB. W/BR-0031 & BR-0052
2027-08-17 | HE-0010 | Division Design Raleigh Let (DDRL) | 50610.3.1 | 5 | WAKE | INTERCHANGE IMPROVEMENTS AT US 1 AND SR 1127 (NEW HILL-HOLLEMANN ROAD); AND INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) AND SR 1149 (FRIENDSHIP ROAD); AND SR 1149 (FRIENDSHIP ROAD) AND SR 1152 (OLD HOLLY SPRINGS-NEWHILL ROAD). CONSTRUCT INTERCHANGE AND INTERSECTION IMPROVEME | $9,300,000
2027-08-17 | HL-0008J | Division Design Raleigh Let (DDRL) | 49367.3.7 | 5 | WAKE | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | $17,300,000
2027-08-17 | HO-0014 | Division Design Raleigh Let (DDRL) | 51176.3.1 | 6 | ROBESON | NC 72 FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETESTREET IMPROVEMENTS. | $12,300,000
2027-08-17 | I-5987AA | Division Design Raleigh Let (DDRL) | 47533.3.4 | 6 | ROBESON | I-95 CONSTRUCT WEIGH IN MOTION STATION. | $4,500,000
2027-08-17 | U-4700A | Division Design Raleigh Let (DDRL) | 35993.3.6 | 12 | BURKE, CATAWBA | US 321 FROM US 70 IN HICKORY TO US 321A (COMBINED WITH B-4450: TO REPLACE BRIDGE 367 OVER CATAWBA RIVER ON US 321) | $282,400,000
2027-08-17 | U-5821 | Division Design Raleigh Let (DDRL) | 44393.3.1 | 12 | GASTON | NC 279 (NEW HOPE ROAD) FROM SR 2478 (TITMAN ROAD) TO SR 2435 (UNION NEW HOPE ROAD). WIDEN TO 4-LANES. | $109,800,000
2027-08-17 | U-5998 | Division Design Raleigh Let (DDRL) | 47135.3.1 | 4 | JOHNSTON | NC 42, FROM SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | $26,900,000
2027-08-17 | U-6006 | Division Design Raleigh Let (DDRL) | 47141.3.1 | 8 | RANDOLPH | US 220 BUSINESS, FROM SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | $17,800,000
2027-09-21 | BR-0077 | Raleigh Letting (LET) |  | 7 |  | REPLACE BRIDGE 400131 ON SR 2770 OVER US 70 | $18,701,000
2027-09-21 | BR-0151 | Division Design Raleigh Let (DDRL) | 52146.3.1 | 13 | BURKE | SR 1002 (HENERY RIVER ROAD),SR 1002 (HENRY RIVER ROAD) OVERI-40. REPLACE BRIDGE. | $12,400,000 | LET COMB. W/ I-5990
2027-09-21 | BR-0177 | Raleigh Letting (LET) | 67177.3.1 | 11 | YADKIN | REPLACE BRIDGE 980186 ON SR1605 OVER YADKIN RIVER | $16,800,000
2027-09-21 | HB-0036 | Division Design Raleigh Let (DDRL) | 50946.3.1 | 9 | FORSYTH | REPLACE BRIDGE 330390 OVER RAIL CORRIDOR AND BRIDGE 330244 OVER US 52/ NC 8 ON 16TH STREET IN WINSTON-SALEM. | $9,800,000
2027-09-21 | HI-0005A | Division Design Raleigh Let (DDRL) | 49996.3.2 | 9 | FORSYTH, DAVIDSON | I-85. I-285 / US 52 / NC 8. PRESERVE BRIDGES 280147, 280152, 280513, 280515, 280516, 280136, 330027, 330028, 330053, AND 330054 | $0
2027-09-21 | HO-0027 | Raleigh Letting (LET) | 51910.3.1 | 1 | DARE | US 64 WILDLIFE CROSSING GRANT PROJECT TO INSTALL WILDLIFE CROSSINGS, UNDERPASS STRUCTURES, AND FENCING ALONG US 64 FROMEAST OF THE EAST LAKE COMMUNITY TO WEST OF SR 1169 (ROBERTSON LANDING ROAD). | $30,800,000
2027-09-21 | I-5990 | Division Design Raleigh Let (DDRL) | 47536.3.1 | 13 | BURKE | I-40 AT EXIT 118 - SR 1761 (OLD NC 10). (COMB W/BR-0151). CONSTRUCT INTERCHANGE IMPROVEMENTS. | $19,800,000 | LET COMB. W/BR-0151
2027-09-21 | R-2527 | Raleigh Letting (LET) | 35572.3.1 | 8 | MONTGOMERY | NC 24-27 FROM NC 73 TO THE TROY BYPASS. | $131,500,000
2027-09-21 | R-5100A | Raleigh Letting (LET) | 41890.3.3 | 12 | IREDELL | SR 1109 (WILLIAMSON ROAD) FROM I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD) IN MOORESVILLE. WIDEN TO FOUR LANES. | $74,300,000
2027-09-21 | U-5709 | Division Design Raleigh Let (DDRL) | 50159.3.1 | 8 | LEE | SR 1237 (CARTHAGE STREET) FROM SR 1152 (FIRE TOWER ROAD) TONC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO-LANE DIVIDED FACILITY WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | $22,200,000
2027-09-21 | U-5710 | Division Design Raleigh Let (DDRL) | 50115.3.1 | 3 | NEW HANOVER | US 74 (EASTWOOD ROAD) SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION - CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE | $60,500,000
2027-09-21 | U-5761 | Division Design Raleigh Let (DDRL) | 50174.3.1 | 10 | CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) AT THE INTERSECTION OF NC3 AND US 29/601 (CANNON BOULEVARD) IN KANNAPOLIS. CONSTRUCT INTERSECTION IMPROVEMENTS. | $20,600,000
2027-09-21 | U-5817 | Raleigh Letting (LET) | 44389.3.1 | 12 | IREDELL | SR 1246 (FAIRVIEW ROAD) EXTENSION OVER I-77 TO CONNECT WITHSR 1206 (ALCOVE ROAD). CONSTRUCT ROADWAY EXTENSION AND PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | $25,200,000
2027-10-19 | B-5531 | Raleigh Letting (LET) | 55031.3.1 | 12 | CLEVELAND | BRIDGE 76 OVER BUFFALO CREEK ON NC 150 | $8,100,000
2027-10-19 | BR-0028 | Raleigh Letting (LET) | 67028.3.1 | 14 | MACON | BRIDGE 550023 ON US 64 OVER NANTAHALA RIVER | $11,700,000
2027-10-19 | BR-0080 | Raleigh Letting (LET) | 51602.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400331 OVER US 29 / US 70 / US 220 ON SULLIVAN STREET. | $7,400,000
2027-10-19 | BR-0145 | Raleigh Letting (LET) | 52145.3.1 | 13 | MADISON | NC 208, BRIDGE 560033 OVER SHELTON LAUREL CREEK. REPLACE BRIDGE. | $2,200,000
2027-10-19 | HB-0026 | Division Design Raleigh Let (DDRL) | 50645.3.1 | 14 | TRANSYLVANIA | SR 1533 (EVERETT ROAD) REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | $7,200,000
2027-10-19 | I-4409B | Division Design Raleigh Let (DDRL) | 38714.3.4 | 13 | BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) AT I-40 FROM US 70 TO SOUTH OF I-40 AND FROM SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). UPGRADE TO INTERCHANGE AND WIDEN TO THREE LANES. | $23,700,000
2027-10-19 | R-2632AB | Raleigh Letting (LET) | 38824.3.2 | 10 | MECKLENBURG | NC 73 (SAM FURR ROAD) FROM NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | $68,100,000
2027-10-19 | R-5853 | Division Design Raleigh Let (DDRL) | 47541.3.1 | 4 | WAYNE | US 13 FROM SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | $8,800,000
2027-10-19 | R-5959 | Division Design Raleigh Let (DDRL) | 48593.3.1 | 8 | LEE | SR 1521 (KELLY DRIVE) FROM SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | $7,900,000
2027-10-19 | U-5308 | Division Design Raleigh Let (DDRL) | 47028.3.2 | 8 | RANDOLPH | SR 1547 (FINCH FARM ROAD) FROM SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | $50,100,000
2027-10-19 | U-6117 | Raleigh Letting (LET) | 48370.3.1 | 5 | WAKE | APEX TOWNWIDE SIGNAL SYSTEM | $8,500,000
2027-11-16 | U-5952 | Raleigh Letting (LET) | 44996.3.1 | 2 | PITT | GREENVILLE - SIGNAL SYSTEM | $13,100,000
2027-12-21 | HL-0133I | Division Design Raleigh Let (DDRL) | 51367.3.10 | 5 | WAKE | US 64 BUSINESS AND DUCKLING WAY INSTALL DIRECTIONAL CROSSOVER ON US 64 BUSINESS AT DUCKLING WAY. | $400,000 | LET COMB. W/HL-0133J
2027-12-21 | HL-0133J | Division Design Raleigh Let (DDRL) | 51367.3.11 | 5 | WAKE | US 64 BUSINESS AND FREEDOM DRIVE 3RD EAST BOUND THRU LANE ON US 64 BUSINESS NEW FREEDOM DRIVE WITH PEDESTRIAN ACCOMMODATIONS. | $4,100,000 | LET COMB. W/HL-0133I
2027-12-21 | R-2555B | Division Design Raleigh Let (DDRL) | 34462.3.7 | 10 | MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) FROM NC 73 (SAM FURR ROAD) TOSR 2151 (JETTON ROAD) IN CORNELIUS. WIDEN TO FOUR-LANES DIVIDED. | $34,600,000
2027-12-21 | R-5807 | Division Design Raleigh Let (DDRL) | 46969.3.1 | 1 | CAMDEN | NC 343 FROM US 158 TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH, MODERNIZE ROADWAY | $27,600,000
2027-12-21 | U-4900 | Division Design Raleigh Let (DDRL) | 40231.3.1 | 6 | CUMBERLAND | NC 210 (MURCHISON ROAD) FROM I-295 TO SOUTH OF US 401 BYPASS | $34,500,000
2028-01-18 | BR-0061 | Raleigh Letting (LET) | 67061.3.1 | 12 | ALEXANDER | REPLACE BRIDGE 010005 ON NC127 OVER DUCK CREEK. | $1,500,000
2028-01-18 | HI-0011 | Division Design Raleigh Let (DDRL) | 49924.3.1 | 3 | SAMPSON | I-40 FROM THE JOHNSTON VOUNTY LINE (MILE MARKER 340) TO THEDUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | $22,400,000
2028-01-18 | U-5727 | Division Design Raleigh Let (DDRL) | 54018.3.1 | 8 | LEE | US 1/US 15/US 501 FROM SOUTH OF SR 1198 (BRYAN DRIVE) TO SR1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. (COMB W/U-5727). | $29,700,000 | LET COMB. W/U-5975
2028-01-18 | U-5975 | Division Design Raleigh Let (DDRL) | 45963.3.1 | 8 | LEE | US 1/US 15/US 501 INTERSECTIONS FROM US 15/US 501 (WHITE HILL ROAD)/SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE) SOUTH OF SANFORD. CONSTRUCT REDUCED CONFLICTINTERSECTIONS. (COMB. W/U-5727). | $40,900,000 | LET COMB. W/U-5727
2028-02-15 | BR-0030 | Raleigh Letting (LET) | 67030.3.1 | 14 | MACON | BRIDGE 550085 ON NC 28 OVER COWEE CREEK | $4,100,000
2028-02-15 | I-5920 | Division Design Raleigh Let (DDRL) | 45927.3.1 | 12 | IREDELL | I-77 FROM MILEMARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | $24,300,000
2028-02-15 | I-5947C | Division Design Raleigh Let (DDRL) | 45894.3.4 | 8 | MONTGOMERY | I-73 /I-74 / US 220 FROM NC 24/27 TO RANDOLPH COUNTY LINE. | $17,600,000
2028-02-15 | I-5948 | Division Design Raleigh Let (DDRL) | 45895.3.1 | 8 | RANDOLPH | I-73/I-74/US 220 FROM MONTGOMERY COUNTY LINE TO NORTH OF SR1462(PARK DRIVE) IN ASHEBORO PAVEMENT REHABILITATION | $26,700,000
2028-02-15 | I-6037 | Division Design Raleigh Let (DDRL) | 47986.3.1 | 3 | NEW HANOVER | I-140 NEWHANOVER COUNTY FROM US 421 TO 1.45 MILES EAST I-40. PAVEMENT AND BRIDGE REHABILITATION. | $7,300,000
2028-02-15 | R-5824 | Division Design Raleigh Let (DDRL) | 47096.3.1 | 8 | MOORE | NC 690 (LOBELIA ROAD)FROM US 1 IN VASS TO CUMBERLAND COUNTYLINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | $14,300,000
2028-02-15 | U-4714BB | Raleigh Letting (LET) | 39078.3.11 | 10 | UNION | SR 1009 (JOHNSTREET / OLD MONROE ROAD) INDIAN TRAIL ROAD TOEAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | $77,765,000
2028-03-21 | BR-0183 | Division Design Raleigh Let (DDRL) | 67183.3.1 | 1 | CHOWAN | REPLACE BRIDGE 200002 ON US17BUS OVER PEMBROKE CREEK | $11,500,000
2028-03-21 | HP-0008 | Raleigh Letting (LET) | 51892.3.1 | 5 | WAKE | HOLLY SPRINGS, INSTALL FIBER TO CONNECT EXISTING TOWN FIBER TO INTERSECTIONS, UPGRADE EXISTINGINFRASTRUCTURE INCLUDINGCABINETS, CONTROLLERS, AND SOFTWARE. | $3,085,000
2028-03-21 | I-5924 | Division Design Raleigh Let (DDRL) | 45933.3.1 | 14 | HAYWOOD | I-40 - HAYWOOD COUNTY FROM MILEMARKER 15 TO MILEMARKER 20.5. PAVEMENT REHABILITATION. | $14,500,000
2028-03-21 | R-5822 | Division Design Raleigh Let (DDRL) | 47094.3.1 | 7 | CASWELL | NC 86 FROM US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCTTURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | $26,600,000
2028-03-21 | U-2561C | Division Design Raleigh Let (DDRL) | 34835.3.5 | 4 | NASH | NC 43 FROM SR 1613 (WOODRUFF AVENUE)TO I-95 WIDEN TO MULTI-LANES | $13,600,000
2028-03-21 | U-5770B | Division Design Raleigh Let (DDRL) | 54036.3.3 | 8 | RANDOLPH | SR 1009 (SOUTH MAIN STREET) FROM WEST OF COLUMBUS AVENUE TOSR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCIIMPROVEMENTS. | $25,600,000
2028-03-21 | U-5917 | Division Design Raleigh Let (DDRL) | 44679.3.1 | 2 | PITT | SR 1704 (FOURTEENTH STREET) FROM RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES | $24,700,000
2028-03-21 | U-5939 | Division Design Raleigh Let (DDRL) | 46887.3.1 | 1 | PASQUOTANK | US 17 BUSINESS TO SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | $17,300,000
2028-03-21 | U-5967 | Raleigh Letting (LET) | 45981.3.1 | 5 | WAKE | TOWN OF MORRISVILLE CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM | $560,000
2028-03-21 | U-6161 | Division Design Raleigh Let (DDRL) | 48472.3.1 | 11 | CALDWELL | US 321 FROM SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | $6,300,000
2028-04-18 | BR-0075 | Division Design Raleigh Let (DDRL) | 51605.3.1 | 9 | FORSYTH | REPLACE BRIDGE 330135 OVER I-40 ON SR 1109 (KINNAMON ROAD) | $12,000,000
2028-04-18 | BR-0079 | Raleigh Letting (LET) | 51601.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400302 OVER US29 / US 70 / US 220 ON TUSCALOOSA STREET IN GREENSBORO. | $7,700,000
2028-04-18 | I-5864 | Division Design Raleigh Let (DDRL) | 53067.3.1 | 11 | YADKIN | I-77 FROM MILEMARKER 71.8 TO MILEMARKER 75.8 PAVEMENT REHABILITATION | $6,285,000
2028-04-18 | R-2233BA | Raleigh Letting (LET) | 34400.3.3 | 13 | RUTHERFORD | US 221 FROM NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS. | $145,200,000
2028-04-18 | R-5836 | Division Design Raleigh Let (DDRL) | 47106.3.1 | 11 | SURRY | US 601 FROM I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4 LANES. | $143,800,000
2028-05-16 | U-6013 | Division Design Raleigh Let (DDRL) | 47158.3.1 | 7 | ALAMANCE | NC 119 FROM SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126(OLD HILLSBOROUGH ROAD) TO LOWES BOULEVARD IN MEBANE. WIDENTO MULTILANES. | $10,400,000
2028-06-20 | B-5925 | Division Design Raleigh Let (DDRL) | 48057.3.1 | 14 | CHEROKEE | REPLACE BRIDGE 223 OVER HIWASSEE RIVER ON SR 1548 | $6,900,000
2028-06-20 | B-5953 | Division Design Raleigh Let (DDRL) | 47217.3.1 | 13 | BUNCOMBE | SR 1002 (OLD LEICESTER HWY) REPLACE BRIDGE 100649 OVER FRENCH BROAD RIVER AND SOUTHERN RAILROAD. | $28,400,000
2028-06-20 | B-6037 | Division Design Raleigh Let (DDRL) | 48404.3.1 | 7 | ORANGE | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILWAY ON NC 86. | $11,400,000
2028-06-20 | BR-0193 | Division Design Raleigh Let (DDRL) | 52220.3.1 | 3 | ONSLOW | REPLACE BRIDGE 660007 ON NC 24 WEST OVER NORTHEAST CREEK. | $12,100,000
2028-06-20 | R-2576 | Design Build Let (DBL) | 34470.3.GV3 | 1 | CURRITUCK | MID-CURRITUCK BRIDGE, FROM COINJOCK TO COROLLA NCTA PROJECT | $1,062,200,000
2028-06-20 | R-5830 | Division Design Raleigh Let (DDRL) | 47102.3.1 | 11 | WATAUGA | SR 1522 (DEERFIELD ROAD), FROM STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD) IN BOONE. UPGRADE ROADWAY. | $16,000,000
2028-06-20 | R-5943 | Division Design Raleigh Let (DDRL) | 48561.3.1 | 2 | GREENE | US 13 AT SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | $10,500,000
2028-06-20 | U-5860 | Division Design Raleigh Let (DDRL) | 46386.3.1 | 2 | BEAUFORT | SR 1306 (15TH STREET),FROM US 17 BUSINESS (CAROLINA AVENUE)TO BROWN STREET, WIDEN TO MULTI-LANES | $33,600,000
2028-06-20 | U-6027 | Division Design Raleigh Let (DDRL) | 47152.3.1 | 8 | RICHMOND | US 1 (PROPOSED) / SR 1516 (GREENE STREET) FROM US 220 TO US1 IN ROCKINGHAM. WIDEN TO THREE-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | $8,100,000
2028-07-18 | B-5983 | Raleigh Letting (LET) | 47815.3.1 | 10 | MECKLENBURG | NC 160,REPLACE BRIDGE 590054 OVER NORFOLK SOUTHERN RAILROAD. | $8,200,000
2028-07-18 | BP5-R102 | Division Design Raleigh Let (DDRL) | BP5.R102.3 | 5 | GRANVILLE | BRIDGE 74 OVER TAR RIVER ON SR 1133 (BELLTOWN ROAD) | $7,200,000
2028-07-18 | BR-0021 | Raleigh Letting (LET) | 67021.3.1 | 4 | HALIFAX | BRIDGE 410051 ON NC 48 OVER ROANOKE RIVER | $35,100,000
2028-07-18 | BR-0083 | Design Build Let (DBL) | 67083.3.1 | 14 | HENDERSON | REPLACE BRIDGES 440057 AND 440115 ON US 64 OVER FRENCH BROAD RIVER OVERFLOW | $26,600,000
2028-07-18 | BR-0154 | Raleigh Letting (LET) | 52218.3.1 | 14 | HAYWOOD | REPLACE BRIDGE 430128 ON NC 209 OVER COVE CREEK. | $1,600,000
2028-07-18 | BR-0178 | Raleigh Letting (LET) | 67178.3.1 | 11 | ASHE | REPLACE BRIDGE 40056 ON SR1340 OVER NORTH FORK NEW RIVER | $5,200,000
2028-07-18 | F-5704 | Division Design Raleigh Let (DDRL) | 47550.3.1 | 1 | CARTERET, HYDE | SILVER LAKE REPLACEMENT VESSEL. NC 12 CEDAR ISLAND-OCRACOKEFERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY. | $25,600,000
2028-07-18 | HI-0009 | Division Design Raleigh Let (DDRL) | 49997.3.1 | 13 | MCDOWELL | SR 1001 (SUGAR HILL ROAD) FROM SR 1001 (SURGAR HILL ROAD) MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | $8,400,000
2028-07-18 | R-5913 | Division Design Raleigh Let (DDRL) | 48468.3.1 | 11 | SURRY, YADKIN | NC 67, COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY. CONSTRUCT ROUNDABOUTS AT WEST MAINSTREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET. IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS; US 21 BUSINESS, BRIDGE 850021 OVER YADKIN RIVER. REHABILITATE BRIDGE AND W | $10,500,000
2028-07-18 | U-2901BA | Division Design Raleigh Let (DDRL) | 34877.3.7 | 5 | WAKE | NC 55 (WILLIAMS STREET), CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | $30,600,000
2028-07-18 | U-5974 | Division Design Raleigh Let (DDRL) | 45962.3.1 | 7 | GUILFORD | NC 68 FROM SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | $51,800,000
2028-07-18 | U-6204 | Division Design Raleigh Let (DDRL) | 48664.3.1 | 4 | WAYNE | SR SR 1556 (WAYNE MEMORIAL DRIVE) FROM SR 1569 (COUNTRY DAY ROAD) TO SR 1003 (NEW HOPE ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $25,100,000
2028-08-15 | B-6038 | Raleigh Letting (LET) | 48405.3.1 | 7 | ROCKINGHAM | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD ON NC 14/NC 87. | $7,600,000
2028-08-15 | HB-0025 | Division Design Raleigh Let (DDRL) | 50644.3.1 | 14 | POLK | SR 1004 (POORS FORD ROAD) REPLACE BRIDGE 740087 OVER BROAD RIVER. | $13,900,000
2028-08-15 | HL-0024 | Division Design Raleigh Let (DDRL) | 49490.3.1 | 10 | MECKLENBURG | SR 3468 (WEDDINGTON ROAD) AT SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | $11,200,000
2028-08-15 | R-2588B | Division Design Raleigh Let (DDRL) | 34473.3.5 | 14 | HENDERSON | NC 191 FROM SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | $148,300,000
2028-08-15 | R-5757A | Division Design Raleigh Let (DDRL) | 44709.3.2 | 1 | NORTHAMPTON | NC 305 FROM HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | $25,600,000
2028-08-15 | R-5757B | Division Design Raleigh Let (DDRL) | 44709.3.3 | 1 | NORTHAMPTON | NC 305 FROM NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWNLIMITS. UPGRADE ROADWAY. | $29,100,000
2028-08-15 | R-5809B | Division Design Raleigh Let (DDRL) | 46976.3.3 | 1 | BERTIE | NC 45 FROM US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | $33,000,000
2028-08-15 | R-5832 | Division Design Raleigh Let (DDRL) | 47104.3.1 | 11 | ASHE | NC 88, FROM NC 88 TO NC 194. UPGRADE ROADWAY. | $68,000,000
2028-08-15 | U-6059A | Division Design Raleigh Let (DDRL) | 47483.3.2 | 9 | FORSYTH | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD ON SR 2662 (OLD GREENSBORO ROAD) IN WINSTON-SALEM. | $15,400,000
2028-09-19 | BR-0050 | Raleigh Letting (LET) | 67050.3.1 | 5 | WAKE | BRIDGE 910172 AND 910175 ON US 401 OVER ATLANTIC AVE. | $18,900,000
2028-09-19 | BR-0076 | Division Design Raleigh Let (DDRL) | 67076.3.1 | 14 | GRAHAM | REPLACE BRIDGE 9 OVER LITTLE TENNESSEE RIVER ON NC 28 IN GRAHAM COUNTY | $21,300,000
2028-09-19 | HS-2001F | Division Design Raleigh Let (DDRL) | 49296.3.7 | 1 | CURRITUCK | US 158 CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | $4,300,000
2028-09-19 | R-5763 | Division Design Raleigh Let (DDRL) | 44638.3.1 | 14 | TRANSYLVANIA | SR 1540 (WILSON ROAD)FROM SR 1504 (OLD US 64) TO US 276.UPGRADE ROADWAY | $58,100,000
2028-09-19 | U-6086 | Division Design Raleigh Let (DDRL) | 47881.3.1 | 10 | MECKLENBURG | NC 51 FROM PARK ROAD TO CARMEL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $14,500,000
2028-10-17 | B-6044 | Division Design Raleigh Let (DDRL) | 48330.3.1 | 4 | JOHNSTON | I-95 REPLACE BRIDGES 500082 AND 500085 OVER BLACK CREEK ANDBRIDGES 500100 AND 500101 OVER THE NEUSE RIVER. | $62,300,000 | LET COMB. W/ I-5974 AND HB-0042
2028-10-17 | BR-0023 | Raleigh Letting (LET) | 67023.3.1 | 12 | IREDELL | REPLACE BRIDGE 480090 OVER I 40 ON SR 1005. | $22,100,000
2028-10-17 | BR-0169 | Raleigh Letting (LET) | 52143.3.1 | 5 | FRANKLIN | NC 561, BRIDGE 340024 OVER SANDY CREEK. REPLACE BRIDGE. | $4,000,000
2028-10-17 | HB-0029 | Raleigh Letting (LET) | 50637.3.1 | 5 | WAKE | SR 1179 (BRIDGE STREET) REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | $3,300,000
2028-10-17 | HB-0031 | Division Design Raleigh Let (DDRL) | 50945.3.1 | 9 | FORSYTH | BRIDGES 330185, 330191 AND 330203 OVER US 52 (FUTURE I-285)/ US 311 ON THIRD STREET, FOURTH STREET, AND FIFTH STREET IN WINSTON-SALEM. REPLACE BRIDGES. | $9,500,000
2028-10-17 | HB-0042 | Division Design Raleigh Let (DDRL) | 50740.3.1 | 4 | JOHNSTON | US 301 REPLACE BRIDGE 56 OVER HOLT LAKE. | $11,300,000 | LET COMB. W/ I-5974 AND B-6044
2028-10-17 | I-5974 | Division Design Raleigh Let (DDRL) | 44993.3.1 | 4 | JOHNSTON | I-95 AT US 701 / NC 96. CONSTRUCT INTERCHANGE. | $76,000,000 | LET COMB. W/ HB-0042 & B-6044
2028-10-17 | U-4407 | Division Design Raleigh Let (DDRL) | 39051.3.1 | 4 | WAYNE | US 70 BUSINESS (EAST ASH STREET) FROM SR 1711 (SOUTH OAK FOREST ROAD) TO US 70. WIDEN TO FOUR LANES. | $31,300,000
2028-10-17 | U-5301A | Raleigh Letting (LET) | 47018.3.5 | 5 | WAKE | APEX/CARY - US 64 AT SR 1306 (LAURA DUNCAN ROAD) | $32,300,000
2028-10-17 | U-5886 | Division Design Raleigh Let (DDRL) | 44710.3.1 | 14 | HENDERSON | SR 1170 (WHITE STREET) FROM SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). (COMB W/U-6049). REALIGN AND EXTEND ROADWAY. | $18,200,000 | LET COMB. W/U-6049
2028-10-17 | U-6049 | Division Design Raleigh Let (DDRL) | 46995.3.1 | 14 | HENDERSON | BRIDGE 440143 OVER MUD CREEK ON US 25 BUSINESS (SOUTH MAIN STREET) AND US 25 BUSINESS FROM SOUTH MAIN STREET / SOUTH KING STREET TO US 276 IN HENDERSONVILLE. WIDEN BRIDGE TO FIVE LANES. | $8,800,000 | LET COMB. W/U-5886
2028-10-17 | U-6157 | Division Design Raleigh Let (DDRL) | 48471.3.1 | 11 | CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) FROM SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | $45,100,000
2028-11-21 | BR-0163 | Division Design Raleigh Let (DDRL) | 52144.3.1 | 10 | ANSON | NC 742, BRIDGE 030084 OVER LANES CREEK. REPLACE BRIDGE. | $4,448,000
2028-11-21 | I-5719A | Design Build Let (DBL) | 50135.3.GV1 | 12 | GASTON | I-85, FROM US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET).WIDEN TO EIGHT LANES.(COMB W/U-6044). | $498,200,000 | LET COMB. W/U-6044
2028-11-21 | I-6000 | Division Design Raleigh Let (DDRL) | 47955.3.1 | 5 | WAKE, DURHAM | I-540 - DURHAM/WAKE COUNTIES FROM I-40 IN DURHAM TO US 1 INRALEIGH. BRIDGE PRESERVATION/REHABILITATION. COORDINATE WITH I-5998 & I-5999. | $7,610,000
2028-11-21 | U-6034 | Division Design Raleigh Let (DDRL) | 46968.3.1 | 11 | CALDWELL | US 321 ALTERNATE FROM SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | $27,300,000
2028-11-21 | U-6044 | Design Build Let (DBL) | 46986.3.1 | 12 | GASTON | SR 2200 (COX ROAD)FROM I-85 TO US 29/74 SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS (COMB W/I-5719 AND U-5800). | $14,300,000 | LET COMB. W/I-5719A
2029-01-16 | B-5680 | Raleigh Letting (LET) | 45635.3.1 | 5 | WAKE | REMOVE BRIDGE 449 OVER THE CSX RAILROAD IN CARY ON SR 1633 | $700,000
2029-01-16 | BR-0022 | Division Design Raleigh Let (DDRL) | 67022.3.1 | 14 | HAYWOOD | BRIDGE 430122 ON US 19,23,74 SBL OVER NC 209 | $11,000,000
2029-01-16 | BR-0078 | Raleigh Letting (LET) | 67078.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400292 AND 400467 ON US 220 OVER US 220 SBL AND SR 1452 | $28,100,000
2029-01-16 | EB-5732 | Division Design Raleigh Let (DDRL) | 51055.3.1 | 10 | CABARRUS | SR 2894 (BRUTON SMITH BOULEVARD / CONCORD MILLS BOULEVARD),US 29 TO JOHN Q. HAMMONDS DRIVE IN CONCORD. CONSTRUCT SHARED USE PATH ON NORTH SIDE OF ROAD. | $10,500,000
2029-01-16 | I-5828 | Division Design Raleigh Let (DDRL) | 50471.3.1 | 10 | MECKLENBURG | I-485 FROM I-77 TO NC 49. PAVEMENT REHABILITATION. REHABILITATE BRIDGES 590661, 590662, 590663, 590664, AND 590643. | $7,730,000
2029-01-16 | U-4405C | Raleigh Letting (LET) | 39049.3.4 | 6 | CUMBERLAND | US 401 (RAEFORD ROAD) FROM EAST OF SR 1596 (GLENSFORD DRIVE) TO EAST OF ROBESON STREET. | $63,400,000
2029-01-16 | U-5787 | Division Design Raleigh Let (DDRL) | 44359.3.1 | 3 | ONSLOW | SR 2715 (TRADE STREET)FROM NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | $7,600,000
2029-02-20 | B-5976 | Division Design Raleigh Let (DDRL) | 47239.3.1 | 8 | LEE | SR 1400 (CUMNOCK RD.), REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | $11,500,000
2029-02-20 | BR-0081 | Raleigh Letting (LET) | 52216.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400283 AND BRIDGE 400342 ON PHILLIPS AVENUE OVER US 29, US 70, US 220. | $0
2029-02-20 | HI-0021 | Division Design Raleigh Let (DDRL) | 49992.3.1 | 6 | CUMBERLAND | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | $8,000,000
2029-02-20 | HL-0133A | Division Design Raleigh Let (DDRL) | 51367.3.2 | 5 | WAKE | POOLE ROAD / HODGE ROAD INTERSECTION IMPROVEMENTS. | $2,500,000 | LET COMB. W/HL-0133L
2029-02-20 | HL-0133L | Division Design Raleigh Let (DDRL) | 51367.3.13 | 5 | WAKE | POOLE ROAD / BARWELL TO HODGE ROAD CONSTRUCT SECOND 2-LANE BRIDGE OVER NEUSE AND WIDEN POOLE TO TIE INTO 4-LANE SECTIONS TO WEST AND EAST. | $23,000,000 | LET COMB. W/HL-0133A
2029-03-20 | B-5926 | Division Design Raleigh Let (DDRL) | 46369.3.1 | 12 | GASTON | NC 273, REPLACE BRIDGE 22 OVER DUKE POWER FEEDER CANAL | $12,000,000
2029-03-20 | B-6052 | Raleigh Letting (LET) | 48709.3.1 | 7 | ALAMANCE | REPLACE BRIDGE 68 OVER NCRR / NORFOLK SOUTHERN RAILROAD ON SR 1928 (TROLLINGWOOD ROAD) IN HAW RIVER | $2,500,000
2029-03-20 | BR-0180 | Division Design Raleigh Let (DDRL) | 67180.3.1 | 13 | BURKE | REPLACE BRIDGE 110346 ON SR1002 OVER HENRY FORK CREEK | $6,500,000
2029-03-20 | HI-0003 | Division Design Raleigh Let (DDRL) | 49994.3.1 | 8 | RANDOLPH | I-73/US 220 FROM SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | $8,120,000
2029-03-20 | HI-0022 | Division Design Raleigh Let (DDRL) | 49993.3.1 | 6 | CUMBERLAND | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | $5,800,000
2029-03-20 | I-5891B | Division Design Raleigh Let (DDRL) | 46411.3.3 | 13 | BURKE | I-40 FROM MILE MARKER 105 TO MILE MARKER 112 PAVEMENT REHABILITATION AND BRIDGE REHABILITATION | $4,000,000
2029-03-20 | U-2530A | Division Design Raleigh Let (DDRL) | 34824.3.3 | 12 | CATAWBA | NC 127 FROM SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD) | $59,700,000
2029-03-20 | U-5726 | Division Design Raleigh Let (DDRL) | 54017.3.1 | 4 | JOHNSTON | US 301/NC 39/NC 96 FROM SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $29,100,000
2029-03-20 | U-5790 | Division Design Raleigh Let (DDRL) | 44362.3.1 | 3 | NEW HANOVER | US 421 (CAROLINA BEACH ROAD)FROM NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONTRUCT FLYOVERS AT US 421 AND NC 132. INCLUDES U-5859 | $39,300,000
2029-03-20 | U-5951 | Division Design Raleigh Let (DDRL) | 45870.3.1 | 3 | ONSLOW | US 17 AT US 17 BUSINESS (MARINE BOULEVARD. UPGRADE AT-GRADEINTERSECTION TO PARTIAL INTERCHANGE. | $27,200,000
2029-03-20 | U-6032 | Division Design Raleigh Let (DDRL) | 46965.3.1 | 10 | MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD) FROM I-485 TO THE CABARRUS COUNTY LINE AND SR 1445 (DERITA ROAD) FROM THE COUNTY LINE TO SR 2894 (CONCORD MILLS BOULEVARD) IN CHARLOTTE. WIDEN TO SIX LANES. | $41,400,000
2029-03-20 | U-6205 | Division Design Raleigh Let (DDRL) | 48665.3.1 | 4 | WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) FROM US 70 BYPASS TO SR 1547(STONEY CREEK ROAD). WIDEN ROADWAY. | $2,500,000