## 36MLL-Central & Alternative
36 MONTH CENTRAL & ALTERNATIVE DELIVERY LET LIST (SEPTEMBER 2026 - AUGUST 2029)
Let Date | Project ID | Let Type Description | WBS Element | Div | County | Project Description | CON Estimate | Combined with
2026-09-15 | B-4676A | Division Design Raleigh Let (DDRL) | 33831.3.3 | 11 | WILKES | REPLACE BRIDGE 960029 OVER CUB CREEK ON SR 1001 (OAKWOODS ROAD). | $8,400,000
2026-09-15 | HN-0033 | Division Design Raleigh Let (DDRL) | 51515.3.1 | 4 | WAYNE | NC 55 AND SR 1744 (OLD SEVEN SPRINGS ROAD/INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. | $4,500,000
2026-09-15 | I-5995 | Division Design Raleigh Let (DDRL) | 47950.3.1 | 5 | WAKE, DURHAM | I-40 FROM EAST OF I-885 / NC 885 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION AND SIGNING. | $44,900,000
2026-09-15 | U-4700CA | Division Design Raleigh Let (DDRL) | 35993.3.5 | 11 | CALDWELL | US 321 AT SR 1160 (MOUNT HERMAN ROAD) IN HUDSON. CONSTRUCT REDUCED CONFLICT INTERSECTION (RCI). | $8,200,000 | LET COMB. W/U-4700CB
2026-09-15 | U-4700CB | Division Design Raleigh Let (DDRL) | 35993.3.9 | 11 | CALDWELL | US 321 AT SR 1809 / SR 1952 (PINE MOUNTAIN ROAD)IN HUDSON. CONSTRUCT REDUCED CONFLICT INTERSECTION (RCI). | $16,400,000 | LET COMB. W/U-4700CA
2026-09-15 | U-5711 | Division Design Raleigh Let (DDRL) | 50160.3.1 | 8 | RANDOLPH | SR 1712 (PINEVIEW STREET) FROM WEST OF SYLVAN DRIVE TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | $9,700,000
2026-09-15 | U-5728 | Division Design Raleigh Let (DDRL) | 54019.3.1 | 3 | ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) AT SR 1308 (BELL FORK ROAD/GUM BRANCH ROAD)IN JACKSONVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS. | $6,800,000
2026-10-20 | BL-0119 | Raleigh Letting (LET) | 51704.3.1 | 10 | MECKLENBURG | MCDOWELL CREEK GREENWAY. CONSTRUCT PEDESTRIAN BRIDGE OVER NC 73 NEAR LINDHOLM DRIVE IN HUNTERSVILLE. | $6,500,000 | LET COMB. W/U-5765 & I-5715
2026-10-20 | BR-0174 | Division Design Raleigh Let (DDRL) | 52219.3.1 | 3 | PENDER | REPLACE BRIDGE 700037 ON NC 53 OVER ANGOLA CREEK. | $8,900,000
2026-10-20 | I-5715 | Raleigh Letting (LET) | 50128.3.1 | 10 | MECKLENBURG | I-77 AT NC 73. UPGRADE INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | $83,700,000 | LET COMB. W/BL-0119 & U-5765
2026-10-20 | P-5707 | Raleigh Letting (LET) | 44643.3.1 | 5 | WAKE | CSX S-LINE AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING 633905Y IN WAKE FOREST. CONSTRUCT GRADE SEPARATION. | $39,800,000
2026-10-20 | R-5810 | Division Design Raleigh Let (DDRL) | 46978.3.1 | 1 | MARTIN | US 17 FROM 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEKBOULEVARD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $13,100,000
2026-10-20 | U-5765 | Raleigh Letting (LET) | 50178.3.1 | 10 | MECKLENBURG | NC 73 (SAM FURR ROAD) FROM SR 5544 (WEST CATAWBA AVENUE) TOSR 2316 / SR 2141 (NORTHCROSS DRIVE) IN HUNTERSVILLE. WIDENTO SIX LANES. | $61,900,000 | LET COMB. W/BL-0119 & I-5715
2026-11-17 | B-5857 | Division Design Raleigh Let (DDRL) | 45810.3.1 | 12 | GASTON | REPLACE BRIDGE 82 OVER A SOUTH FORK OF CATAWBA RIVER ON US 29/US 74.(COMB W/U-6146). | $17,200,000 | LET COMB. W/U-6146 & WBS 47897
2026-11-17 | BR-0140 | Division Design Raleigh Let (DDRL) | 67140.3.1 | 9 | DAVIDSON | REPLACE 280087 AND 280089 ON US 29/64/70 OVER WSSB RAILROAD. | $20,900,000
2026-11-17 | I-2513AC | Raleigh Letting (LET) | 34165.3.8 | 13 | BUNCOMBE | I-26 / I-240 FROM NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | $284,200,000
2026-11-17 | I-5958 | Division Design Raleigh Let (DDRL) | 45910.3.2 | 7 | ORANGE | I-40 / I-85 FROM WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OFSR 1006 (ORANGE GROVE ROAD). PAVEMENT AND BRIDGE REHABILITATION. | $26,000,000
2026-11-17 | R-5759 | Division Design Raleigh Let (DDRL) | 44691.3.1 | 11 | WILKES | NC 115 / US 421 BUSINESS (STATESVILLE ROAD) FROM US 421 TO NC 18 (2ND STREET) IN NORTH WILKESBORO. WIDEN TO TWO LANES WITH MEDIAN AND PEDESTRIAN ACCOMMODATIONS. | $69,100,000
2026-11-17 | U-6146 | Division Design Raleigh Let (DDRL) | 48392.3.2 | 12 | GASTON | US 29 / US 74 (WILKINSON BOULEVARD) FROM SR 2209 (MARKET STREET) TO SR 2015 (ALBERTA AVENUE) IN GASTONIA. WIDEN TO SIX LANES. | $32,000,000 | LET COMB. W/B-5857 & WBS 47897
2026-12-15 | R-5711 | Division Design Raleigh Let (DDRL) | 50207.3.1 | 12 | IREDELL | US 21 AT SR 2375 (HOUSTON ROAD) / SR 1312 (FLOWER HOUSE ROAD) IN TROUTMAN. REALIGN AND SIGNALIZE INTERSECTION. | $5,200,000
2026-12-15 | U-3422B | Division Design Raleigh Let (DDRL) | 39001.3.3 | 6 | CUMBERLAND | SR 1003 (CAMDEN ROAD) FROM JUST WEST OF SR 1112 (ROCKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | $54,000,000
2027-01-19 | 15BPR.116 | Raleigh Letting (LET) | 15BPR.116.3 | 10 | MECKLENBURG | BRIDGE 590363 OVER CATAWBA RIVER ON NC 16 NB BRIDGE 590541OVER CATAWBA RIVER ON NC 16 SB. | $5,000,000
2027-01-19 | BR-0147 | Raleigh Letting (LET) | 67147.3.1 | 4 | NASH | REPLACE 630205 ON US64BUS OVER TAR RIVER OVERFLOW | $3,200,000
2027-01-19 | FF-0001 | Raleigh Letting (LET) | 50801.3.1 | 1 | HYDE | REPLACE STRUCTURES 470114 AND 470115 (FERRY RAMPS) OVER SILVER LAKE ON NC 12 AT THE OCRACOKE FERRY TERMINAL. | $19,600,000
2027-01-19 | HB-0001A | Design Build Let (DBL) | 49475.3.2 | 1 | DARE, EDGECOMBE, NASH, TYRRELL, WASHINGTON, MARTIN | US 64 BROADBAND FOR TRAVELER INFORMATION SYSTEMS AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | $29,700,000
2027-01-19 | HN-0040 | Division Design Raleigh Let (DDRL) | 51758.3.1 | 4 | JOHNSTON | SR 1908 (FIRE DEPT ROAD) AT SR 1003 (BUFFALO ROAD) NORTH OFWILSON'S MILLS. CONSTRUCT ROUNDABOUT. | $5,000,000
2027-01-19 | I-5900 | Division Design Raleigh Let (DDRL) | 45867.3.2 | 13 | MCDOWELL | I-40 FROM WEST OF SR 1103 (CATAWBA AVENUE / BAT CAVE ROAD) AT THE OLD FORT EXIT (EXIT 73) TO EAST OF SR 1001 (SUGAR HILL ROAD) AT THE MARION EXIT (EXIT 81). REHABILITATE PAVEMENT. | $30,100,000
2027-01-19 | I-5901 | Division Design Raleigh Let (DDRL) | 45868.3.1 | 13 | BUNCOMBE | I-240, FROM MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | $21,000,000
2027-01-19 | U-4714AC | Raleigh Letting (LET) | 39078.3.9 | 10 | MECKLENBURG, UNION | SR 1010 (JOHN STREET) / SR 1009 (OLD MONROE ROAD) FROM EASTOF I-485 TO WEST OF MORNINGSIDE MEADOW LANE IN MATTHEWS. WIDEN TO MULTI-LANES. | $48,600,000 | LET COMB. W/U-4714BA
2027-01-19 | U-4714BA | Raleigh Letting (LET) | 39078.3.10 | 10 | UNION | SR 1009 (OLD MONROE ROAD) FROM WEST OF MORNINGSIDE MEADOW LANE TO INDIAN TRAIL ROAD IN MATTHEWS. WIDEN TO MULTI-LANES. | $39,500,000 | LET COMB. W/U-4714AC
2027-02-16 | 15BPR.103 | Raleigh Letting (LET) | 15BPR.103.3 | 5 | WAKE | BRIDGE 269 OVER I-440 ON LASSITER MILL ROAD AND BRIDGE 270OVER I-440 ON SR 1005 (SIX FORKS ROAD) IN WAKE COUNTY. BRIDGE PRESERVATION. | $2,500,000
2027-02-16 | BR-0005 | Raleigh Letting (LET) | 67005.3.1 | 2 | BEAUFORT | BRIDGE 060075 ON NC 33 OVER CHOCOWINITY CREEK | $13,200,000
2027-02-16 | BR-0101 | Division Design Raleigh Let (DDRL) | 67101.3.1 | 13 | RUTHERFORD | REPLACE BRIDGE 800104 ON US 64 OVER COVE CREEK | $6,700,000
2027-02-16 | I-5888B | Division Design Raleigh Let (DDRL) | 46408.3.3 | 13 | BUNCOMBE | REHABILITATE SIX BRIDGES ON I - 40 BETWEEN MILE POINT 37 AND MILE POINT 44 AT THE HAYWOOD-BUNCOMBE COUNTY LINE: BRIDGES100024, 100071, 100156 ,100164, 100210, AND 100215. | $8,900,000
2027-02-16 | I-5947A | Division Design Raleigh Let (DDRL) | 45894.3.2 | 8 | MONTGOMERY | I-73/ I-74/ US220 FROM RICHMOND COUNTY LINE TO NC 211. | $19,800,000
2027-02-16 | P-5717 | Raleigh Letting (LET) | 46929.3.1 | 5 | DURHAM | NORFOLK SOUTHERN H LINE CROSSING NO. 734 742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | $41,500,000
2027-02-16 | R-5100B | Division Design Raleigh Let (DDRL) | 41890.3.4 | 12 | IREDELL | SR 1109 (WILLIAMSON ROAD) FROM SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | $13,600,000
2027-02-16 | R-5717 | Division Design Raleigh Let (DDRL) | 50213.3.1 | 1 | CURRITUCK, CAMDEN | SR 1224/SR 1223 (OLD SWAMP ROAD) FROM NC 343 TO THE CAMDEN-CURRITUCK COUNTY LINE, AND SR 1218 / SR 1227 (SOUTH MILLS ROAD) FROM THE COUNTY LINE TO US 168 IN MOYOCK. (COMB W/R-5717B). WIDEN AND INTERSECTION IMPROVEMENTS. | $38,100,000 | LET COMB. W/R-5717B
2027-02-16 | R-5717B | Division Design Raleigh Let (DDRL) | 50213.3.3 | 1 | CURRITUCK, CAMDEN | REPLACE BRIDGE 140013 OVER JOYCE CREEK. (COMB W/R-5717). | $2,200,000 | LET COMB. W/R-5717
2027-02-16 | R-5718 | Division Design Raleigh Let (DDRL) | 50472.3.1 | 4 | JOHNSTON | SR 1003 (BUFFALO ROAD) FROM US 70 TO SR 1934 (OLD BEULAH ROAD) IN SELMA. WIDEN TO THREE LANES | $25,700,000
2027-02-16 | U-6014 | Division Design Raleigh Let (DDRL) | 47159.3.1 | 7 | ALAMANCE | SR 1716 (GRAHAM-HOPEDALE ROAD) FROM SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BICYCLE/PEDESTRIAN ACCOMMODATIONS. | $19,200,000
2027-03-09 | F-5704 | CMGC PRECON AWARD | 47550.3.1 | 1 | CARTERET, HYDE | SILVER LAKE REPLACEMENT VESSEL. NC 12 CEDAR ISLAND-OCRACOKEFERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY. | $25,600,000
2027-03-16 | 15BPR.132 | Raleigh Letting (LET) | 15BPR.132.3 | 10 | MECKLENBURG | BRIDGE 459 AND BRIDGE 460 OVER US 74 / US 29 ON SR 5901 (BILLY GRAHAM PARKWAY); AND BRIDGE 489 OVER I-277 ON SR 3998 (SOUTH BOULEVARD) IN MECKLENBURG COUNTY | $4,300,000
2027-03-16 | BL-0080 | Raleigh Letting (LET) | 50808.3.1 | 10 | MECKLENBURG | HUNTERSVILLE CONSTRUCT GREENWAY CULVERT UNDER US 21. (COMB W/U-5771). | $3,250,000 | LET COMB. W/U-5771
2027-03-16 | HB-0016 | Raleigh Letting (LET) | 50923.3.1 | 1 | WASHINGTON | NC 32 PRESERVATION OF BRIDGE 930015 ON NC 32 OVER ALBEMARLESOUND. | $60,900,000
2027-03-16 | HB-0020 | Division Design Raleigh Let (DDRL) | 50351.3.1 | 11 | WILKES | REPLACE BRIDGE 960730 OVER YADKIN RIVER ON SR 1185 (CURTIS BRIDGE ROAD) | $13,100,000
2027-03-16 | HE-0017 | Division Design Raleigh Let (DDRL) | 51679.3.1 | 6 | CUMBERLAND | SR 1711 (BETHUNE DRIVE) AT EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). | $6,400,000
2027-03-16 | HI-0013 | Division Design Raleigh Let (DDRL) | 49984.3.1 | 4 | NASH | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | $32,700,000
2027-03-16 | HL-0007 | Division Design Raleigh Let (DDRL) | 49366.3.1 | 5 | WAKE | NC 55 AT SR 1191 (TECHNOLOGY DRIVE)/SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION | $28,000,000
2027-03-16 | I-5701 | Design Build Let (DBL) | 50119.3.1 | 5 | WAKE | I-40/US 64; FROM I-440/US 1/US 64 TO SR 1009 (LAKE WHEELER ROAD) IN RALEIGH WIDEN FROM SIX TO EIGHT LANES. (COMB W/I-5703). | $163,100,000 | LET COMB. W/I-5703
2027-03-16 | I-5703 | Design Build Let (DBL) | 50120.3.GV1 | 5 | WAKE | I-40 AND I-440/US 1/US 64 INTERSECTION RECONSTRUCT INTERCHANGE. (COMB W/I-5701). | $330,900,000 | LET COMB. W/I-5701
2027-03-16 | I-5921 | Division Design Raleigh Let (DDRL) | 45928.3.1 | 12 | GASTON | I-85 FROM THE CLEVELAND COUNTY LINE TO MILE MARKER 14.0. REHABILITATE PAVEMENT. | $26,400,000
2027-03-16 | I-5925 | Division Design Raleigh Let (DDRL) | 45934.3.1 | 14 | HENDERSON | I-26 IN HENDERSON COUNTY FROM MILEMARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | $34,200,000
2027-03-16 | I-5926 | Division Design Raleigh Let (DDRL) | 45935.3.1 | 14 | POLK | I-26 POLK COUNTY FROM HENDERSON COUNTY LINE TO MILEMARKER 65. PAVEMENT REHABILITATION. | $29,300,000
2027-03-16 | R-5826B | Division Design Raleigh Let (DDRL) | 47098.3.3 | 8 | MONTGOMERY | NC 109 FROM SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). UPGRADE ROADWAY. | $13,600,000
2027-03-16 | U-5771 | Raleigh Letting (LET) | 50183.3.1 | 10 | MECKLENBURG | US 21 FROM SR 2136 (GILEAD ROAD) TO SR 6028 (HOLLY POINT DRIVE) IN HUNTERSVILLE. WIDEN TO FOUR LANES. | $44,700,000 | LET COMB. W/ BL-0080
2027-03-16 | U-5844 | Division Design Raleigh Let (DDRL) | 50234.3.1 | 7 | ALAMANCE | NC 62 FROM SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON, WIDEN TO A THREE-LANE FACILITY. | $18,500,000
2027-04-20 | 15BPR.118 | Raleigh Letting (LET) | 15BPR.118.3 | 12 | GASTON | REHAB BRG 350159 ON I85 OVER CATAWBA RIVER | $2,900,000
2027-04-20 | 15BPR.150 | Raleigh Letting (LET) | 15BPR.150.3 | 7 | ALAMANCE | BRIDGE PRESERVATION. BRIDGE 000075 OVER I-40 & I-85 ON SR 1158; BRIDGE 000379 OVER HAW RIVER ON US 70. | $3,200,000
2027-04-20 | B-5876 | Raleigh Letting (LET) | 48070.3.1 | 13 | RUTHERFORD | REPLACE BRIDGE 800083 AND BRIDGE 800084 OVER SECOND BROAD RIVER ON US 74 BYPASS NEAR RUTHERFORDTON. | $18,700,000
2027-04-20 | BF-0002 | Division Design Raleigh Let (DDRL) | 50701.3.1 | 14 | TRANSYLVANIA | ECUSTA TRAIL, TRANSYLVANIA COUNTY LINE TO LAMB CREEK. CONSTRUCT GREENWAY. | $29,100,000
2027-04-20 | BR-0074 | Raleigh Letting (LET) | 67074.3.1 | 2 | CRAVEN | REPLACE BRIDGE 240091 AND 240092 ON US 70 OVER S. PR. SLOCUM CREEK | $9,400,000
2027-04-20 | BR-0092 | Raleigh Letting (LET) | 67092.3.1 | 7 | ORANGE | REPLACE BRIDGE 670037 ON NC 86 OVER NEW HOPE CREEK | $5,600,000
2027-04-20 | HB-0069 | Division Design Raleigh Let (DDRL) | 50739.3.1 | 11 | WILKES | REPLACE BRIDGE 960012 OVER REDDIES RIVER ON US 421 BUSINESS(D STREET) | $21,100,000
2027-04-20 | I-5993 | Division Design Raleigh Let (DDRL) | 47948.3.GV1 | 5 | DURHAM | I-40 - DURHAM COUNTY FROM US 15/US 501 TO EAST OF NC 147 (INCLUDES I-5994).PAVEMENT REHABILITAION. | $50,700,000
2027-04-20 | P-5706A | Raleigh Letting (LET) | 46918.3.2 | 5 | DURHAM | NORFOLK SOUTHERN H LINE,CROSSING AT GLOVER ROAD (734735L). CONSTRUCT GRADE SEPARATION. | $28,500,000
2027-04-20 | R-5724B | Division Design Raleigh Let (DDRL) | 50217.3.3 | 8 | CHATHAM | US 15/US 501 FROM NORTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | $24,200,000
2027-04-20 | R-5899 | Division Design Raleigh Let (DDRL) | 48355.3.1 | 3 | PENDER | NC 210 AT SR 1560 (WATTS LANDING ROAD) INTERSECTION IN SURFCITY. IMPROVE INTERSECTION. | $7,500,000
2027-04-20 | U-5911 | Division Design Raleigh Let (DDRL) | 44642.3.1 | 4 | NASH | NC 48 AT NC 4 IN ROCKY MOUNT. CONSTRUCT ROUNDABOUT. | $8,500,000
2027-04-20 | U-5965 | Division Design Raleigh Let (DDRL) | 45979.3.1 | 12 | GASTON | US 29 (FRANKLIN BOULEVARD) AT NC 274 (BESSEMER CITY ROAD) /SR 2466 (WEST GARRISON BOULEVARD) IN GASTONIA. CONSTRUCT INTERSECTION IMPROVEMENTS. | $5,300,000
2027-05-18 | 15BPR.153 | Raleigh Letting (LET) | 15BPR.153.3 | 8 | MOORE | BRIDGES 74 & 257 IN MOORE CO. | $1,600,000
2027-05-18 | BR-0141 | Division Design Raleigh Let (DDRL) | 51604.3.1 | 7 | ROCKINGHAM | SR 2150 (RIVER ROAD) REPLACE BRIDGE 780123 OVER US 220 / US 311. | $7,800,000
2027-05-18 | I-5998 | Division Design Raleigh Let (DDRL) | 47953.3.1 | 5 | WAKE, DURHAM | I-540 FROM I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | $24,900,000
2027-05-18 | P-5709 | Raleigh Letting (LET) | 46920.3.1 | 7 | GUILFORD | GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A), AND CLOSE O'FERRELL STREET CROSSING (722961B) AT NCRR/NSR-NCLINE IN GREENSBORO. | $27,300,000
2027-06-15 | HB-0039 | Design Build Let (DBL) | 50603.3.1 | 3 | NEW HANOVER | US 17/US 76/US 421. REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. | $1,002,300,000
2027-06-15 | I-5707 | Raleigh Letting (LET) | 50123.3.1 | 5 | DURHAM | I-40 FROM NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY/TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | $11,700,000
2027-06-15 | I-5718 | Design Build Let (DBL) | 49020.3.8 | 10 | MECKLENBURG | I-77 FROM THE SOUTH CAROLINA STATE LINE TO I-277 / NC 16 (BROOKSHIRE FREEWAY). WIDEN FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT THE I-277 INTERCHANGES. | $2,658,900,000
2027-06-15 | R-5796 | Division Design Raleigh Let (DDRL) | 46881.3.1 | 1 | HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) FROM PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | $20,300,000
2027-06-15 | U-5753 | Raleigh Letting (LET) | 51078.3.1 | 8 | HOKE | SR 1305, US 401 TO PLANK ROAD; AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD) WIDEN TO MULTILANES. | $62,100,000
2027-06-15 | U-6043 | Division Design Raleigh Let (DDRL) | 46984.3.1 | 12 | GASTON | US 29 / US 74 (FRANKLIN BOULEVARD) FROM SR 2200 (COX ROAD) TO EAST OF LINEBERGER ROAD IN GASTONIA. CONSTRUCT ADDITIONALEASTBOUND LANE. | $8,100,000
2027-07-20 | B-5950 | Division Design Raleigh Let (DDRL) | 45985.3.1 | 9 | FORSYTH | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK ON NC 67(WESTBOUND SILAS CREEK PARKWAY) IN WINSTON-SALEM. | $9,000,000
2027-07-20 | BR-0018 | Raleigh Letting (LET) | 67018.3.1 | 9 | FORSYTH | BRIDGE 330048 ON NC 8 OVER US 52 | $21,000,000
2027-07-20 | BR-0019 | Raleigh Letting (LET) | 67019.3.1 | 12 | GASTON | BRIDGE 350056 ON NC 275 OVER SF CATAWBA RIVER | $12,500,000
2027-07-20 | BR-0040 | Raleigh Letting (LET) | 52189.3.1 | 14 | POLK | NC 9 BRIDGE 740037 OVER GREEN RIVER. REPLACE BRIDGE. | $5,700,000
2027-07-20 | BR-0049 | Raleigh Letting (LET) | 67049.3.1 | 10 | UNION | BRIDGE 890034 ON CONCORD AVE OVER US 74, NC 200 | $9,000,000
2027-07-20 | P-5737 | Raleigh Letting (LET) | 48153.3.1 | 5 | WAKE | CSX S LINE AT SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | $29,800,000
2027-07-20 | U-3467 | Raleigh Letting (LET) | 39019.3.1 | 10 | UNION | NC 84 (WEDDINGTON ROAD) FROM NC 16 (PROVIDENCE ROAD) TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | $103,300,000
2027-07-20 | U-6078 | Division Design Raleigh Let (DDRL) | 47525.3.1 | 12 | GASTON | NC 275 AT NC 274 (BESSEMER CITY ROAD); NC 275 AT SR 1327 (FAIRVIEW ROAD) AND SR 1456 (WHITE JENKINS ROAD) IN GASTONIA.CONSTRUCT INTERSECTION IMPROVEMENTS AND CLOSE INTERSECTION AT NC 275 AND SR 1456 (WHITE JENKINS ROAD). | $7,400,000
2027-08-17 | U-4700A | Division Design Raleigh Let (DDRL) | 35993.3.6 | 12 | BURKE, CALDWELL, CATAWBA | US 321 FROM US 70 IN HICKORY TO US 321A (COMBINED WITH B-4450: TO REPLACE BRIDGE 367 OVER CATAWBA RIVER ON US 321) | $287,400,000
2027-08-17 | U-5998 | Division Design Raleigh Let (DDRL) | 47135.3.1 | 4 | JOHNSTON | NC 42, FROM SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | $30,100,000
2027-08-17 | U-6013 | Division Design Raleigh Let (DDRL) | 47158.3.1 | 7 | ALAMANCE | NC 119 FROM SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126(OLD HILLSBOROUGH ROAD) TO LOWES BOULEVARD IN MEBANE. WIDENTO MULTILANES. | $10,600,000
2027-08-17 | U-6110 | Division Design Raleigh Let (DDRL) | 48334.3.1 | 4 | WAYNE | US 70 AT SR 1711(NORTH OAK FOREST ROAD) IN GOLDSBORO. CONSTRUCT INTERSECTION IMPROVEMENTS. | $13,600,000
2027-09-21 | BR-0177 | Raleigh Letting (LET) | 67177.3.1 | 11 | YADKIN | REPLACE BRIDGE 980186 ON SR1605 OVER YADKIN RIVER | $16,800,000
2027-09-21 | HB-0036 | Division Design Raleigh Let (DDRL) | 50946.3.1 | 9 | FORSYTH | REPLACE TWO BRIDGES ON SIXTEENTH STREET IN WINSTON-SALEM. BRIDGE 330390 OVER THE RAIL CORRIDOR AND BRIDGE 330244 OVER US 52 / NC 8. | $10,900,000
2027-09-21 | HI-0005A | Division Design Raleigh Let (DDRL) | 49996.3.2 | 9 | FORSYTH, DAVIDSON | I-85. I-285 / US 52 / NC 8. PRESERVE BRIDGES 280147, 280152, 280513, 280515, 280516, 280136, 330027, 330028, 330053, AND 330054 | $15,400,000
2027-09-21 | U-5710 | Division Design Raleigh Let (DDRL) | 50115.3.1 | 3 | NEW HANOVER | US 74 (EASTWOOD ROAD) SR 1409 (MILITARY CUTOFF ROAD) IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | $60,200,000
2027-09-21 | U-5761 | Division Design Raleigh Let (DDRL) | 50174.3.1 | 10 | CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) AT US 29 / US 601 (CANNON BOULEVARD) IN KANNAPOLIS. CONSTRUCT INTERSECTION IMPROVEMENTS. | $20,600,000
2027-10-19 | B-5531 | Raleigh Letting (LET) | 55031.3.1 | 12 | CLEVELAND | BRIDGE 76 OVER BUFFALO CREEK ON NC 150 | $8,100,000
2027-10-19 | B-6040 | Division Design Raleigh Let (DDRL) | 48389.3.1 | 13 | MCDOWELL | US 70 REPLACE BRIDGE 580127 OVER SOUTHERN RAILROAD. | $4,200,000
2027-10-19 | BR-0028 | Raleigh Letting (LET) | 67028.3.1 | 14 | MACON | BRIDGE 550023 ON US 64 OVER NANTAHALA RIVER | $11,700,000
2027-10-19 | BR-0080 | Raleigh Letting (LET) | 51602.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400331 OVER US 29 / US 70 / US 220 ON SULLIVAN STREET. | $9,700,000
2027-10-19 | BR-0145 | Raleigh Letting (LET) | 52145.3.1 | 13 | MADISON | NC 208, BRIDGE 560033 OVER SHELTON LAUREL CREEK. REPLACE BRIDGE. | $2,200,000
2027-10-19 | HL-0006 | Division Design Raleigh Let (DDRL) | 49365.3.1 | 5 | WAKE | US 401 AT SR 1393 (HILLTOP-NEEDMORE ROAD)SR 2751 (HILLTOP ROAD)/ SR 2752 (AIR PARK ROAD) AND SR 1375 (LAKE WHEELER ROAD)IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONSAND REALIGN SR 2751 TO INTERSECTION OPPOSITE SR 1375. | $53,100,000
2027-10-19 | R-5959 | Division Design Raleigh Let (DDRL) | 48593.3.1 | 8 | LEE | SR 1521 (KELLY DRIVE) FROM SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | $7,900,000
2027-10-19 | U-6117 | Raleigh Letting (LET) | 48370.3.1 | 5 | WAKE | APEX TOWNWIDE SIGNAL SYSTEM | $8,500,000
2027-11-16 | 15BPR.104 | Raleigh Letting (LET) | 15BPR.104.3 | 2 | CRAVEN | BRIDGE PRESERVATION OF: BRIDGES 83, 84, 231 & 222 IN CRAVEN COUNTY BRIDGES 60 AND 65 IN CRAVEN COUNTY BRIDGE 83, 84 & 222 OVER TRENT RIVER ON US 17 / US 70 / US 55 BRIDGE 231 OVER NEUSE RIVER / US 70 ON US 17 / NC 55 BRIDGE 240060 OVER TRENT RIVERON US 70B BRIDGE 240065 OVER UPPER BROAD CREEK ON | $14,500,000
2027-11-16 | HL-0008J | Division Design Raleigh Let (DDRL) | 49367.3.7 | 5 | WAKE | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | $17,300,000
2027-11-16 | U-5952 | Raleigh Letting (LET) | 44996.3.1 | 2 | PITT | GREENVILLE - SIGNAL SYSTEM | $13,100,000
2027-12-21 | 15BPR.112 | Raleigh Letting (LET) | 15BPR.112.3 | 6 | CUMBERLAND | REHAB BRG 250085 & 250061 ON I95BUS.LOOP,US301 OVER SR1738, SR1739, CAPE FEAR RIVER | $1,200,000
2027-12-21 | 15BPR.114 | Raleigh Letting (LET) | 15BPR.114.3 | 9 | FORSYTH | BRIDGE PRESERVATION OF BRIDGES 345 AND 259 IN FORSYTH COUNTY BRIDGE 330345 ON US 421/ I40 BUS OVER SALEM AVENUE AND NSRR BRIDGE 330259 ON US 421/ I40 BUS OVER EDEN, HAWTHORN, ANDCLOVERDALE STREETS | $8,300,000
2027-12-21 | 15BPR.142 | Raleigh Letting (LET) | 15BPR.142.3 | 3 | BRUNSWICK | BRIDGE PRESERVATION. BRIDGE 090096 OVER US 74 & US 76 ON US 17; BRIDGE 090198 OVER ICW & NC 179 ON SR 1172 | $2,800,000
2027-12-21 | 15BPR.152 | Raleigh Letting (LET) | 15BPR.152.3 | 12 | LINCOLN | BRIDGE PRESERVATION. BRIDGE 540050 OVER CATAWBA RIVER ON NC 73. | $2,700,000
2027-12-21 | 15BPR.155 | Raleigh Letting (LET) | 15BPR.155.3 | 10 | MECKLENBURG | BRIDGE PRESERVATION OF BRIDGES 23 & 120 IN MECKLENBURG CO. | $2,300,000
2027-12-21 | HE-0010 | Division Design Raleigh Let (DDRL) | 50610.3.1 | 5 | WAKE | INTERCHANGE IMPROVEMENTS AT US 1 AND SR 1127 (NEW HILL-HOLLEMANN ROAD); AND INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) AND SR 1149 (FRIENDSHIP ROAD); AND SR 1149 (FRIENDSHIP ROAD) AND SR 1152 (OLD HOLLY SPRINGS-NEWHILL ROAD). CONSTRUCT INTERCHANGE AND INTERSECTION IMPROVEME | $9,300,000
2027-12-21 | HO-0014 | Division Design Raleigh Let (DDRL) | 51176.3.1 | 6 | ROBESON | NC 72 FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETESTREET IMPROVEMENTS. | $12,300,000
2027-12-21 | I-4409B | Division Design Raleigh Let (DDRL) | 38714.3.4 | 13 | BUNCOMBE | BLUE RIDGE ROAD IMPROVEMENT PROJECT. SR 2500 (BLUE RIDGE ROAD) AT I-40, AND SR 2500 FROM US 70 TO SR 2713 (SOUTH BLUE RIDGE ROAD)IN BLACK MOUNTAIN. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE AND WIDEN TO THREE LANES. | $23,700,000
2027-12-21 | R-2555B | Division Design Raleigh Let (DDRL) | 34462.3.7 | 10 | MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) FROM NC 73 (SAM FURR ROAD) TOEAST OF SR 2151 (JETTON ROAD) IN CORNELIUS. WIDEN TO FOUR-LANES DIVIDED. | $40,900,000
2027-12-21 | R-5807 | Division Design Raleigh Let (DDRL) | 46969.3.1 | 1 | CAMDEN | NC 343 FROM US 158 TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH, MODERNIZE ROADWAY | $27,600,000
2027-12-21 | U-4900 | Division Design Raleigh Let (DDRL) | 40231.3.1 | 6 | CUMBERLAND | NC 210 (MURCHISON ROAD) FROM I-295 TO SOUTH OF US 401 BYPASS | $35,000,000
2028-01-18 | 15BPR.151 | Raleigh Letting (LET) | 15BPR.151.3 | 12 | CATAWBA | BRIDGE PRESERVATION OF BRIDGES 3 & 5 IN CATAWBA CO. | $5,500,000
2028-01-18 | BR-0061 | Raleigh Letting (LET) | 67061.3.1 | 12 | ALEXANDER | REPLACE BRIDGE 010005 ON NC127 OVER DUCK CREEK. | $1,500,000
2028-01-18 | HI-0011 | Division Design Raleigh Let (DDRL) | 49924.3.1 | 3 | SAMPSON | I-40 FROM THE JOHNSTON VOUNTY LINE (MILE MARKER 340) TO THEDUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | $27,700,000
2028-01-18 | U-5727 | Division Design Raleigh Let (DDRL) | 54018.3.1 | 8 | LEE | US 1/US 15/US 501 FROM SOUTH OF SR 1198 (BRYAN DRIVE) TO SR1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. (COMB W/U-5727). | $30,500,000 | LET COMB. W/U-5975
2028-01-18 | U-5834 | Division Design Raleigh Let (DDRL) | 50226.3.1 | 13 | BUNCOMBE | SR 3116 (MILLS GAP ROAD) FROM US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD) IN ASHEVILLE. UPGRADE ROADWAY. | $37,600,000
2028-01-18 | U-5975 | Division Design Raleigh Let (DDRL) | 45963.3.1 | 8 | LEE | US 1 / US 15 / US 501 INTERSECTIONS FROM US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE) SOUTH OF SANFORD. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | $40,900,000 | LET COMB. W/U-5727
2028-02-15 | 15BPR.111 | Raleigh Letting (LET) | 15BPR.111.3 | 5 | DURHAM | REHAB BRGS 310132, 310179, 310185, 310048 AND 310422 | $5,600,000
2028-02-15 | BR-0171 | Raleigh Letting (LET) | 67171.3.1 | 13 | MCDOWELL | REPLACE BRIDGE 580096 ON US70 OVER CATAWBA RIVER OVER FLOW | $7,500,000
2028-02-15 | I-5920 | Division Design Raleigh Let (DDRL) | 45927.3.1 | 12 | IREDELL | I-77 FROM MILEMARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | $32,300,000
2028-02-15 | I-5947C | Division Design Raleigh Let (DDRL) | 45894.3.4 | 8 | MONTGOMERY | I-73 /I-74 / US 220 FROM NC 24/27 TO RANDOLPH COUNTY LINE. | $16,500,000
2028-02-15 | I-5948 | Division Design Raleigh Let (DDRL) | 45895.3.1 | 8 | RANDOLPH | I-73/I-74/US 220 FROM MONTGOMERY COUNTY LINE TO NORTH OF SR1462(PARK DRIVE) IN ASHEBORO PAVEMENT REHABILITATION | $28,400,000
2028-02-15 | I-5987AA | Division Design Raleigh Let (DDRL) | 47533.3.4 | 6 | ROBESON | I-95 CONSTRUCT WEIGH IN MOTION STATION. | $4,500,000
2028-02-15 | I-6037 | Division Design Raleigh Let (DDRL) | 47986.3.1 | 3 | NEW HANOVER | I-140 NEWHANOVER COUNTY FROM US 421 TO 1.45 MILES EAST I-40. PAVEMENT AND BRIDGE REHABILITATION. | $12,600,000
2028-02-15 | U-2817 | Division Design Raleigh Let (DDRL) | 34868.3.4 | 2 | PITT | SR 1700 (EVANS STREET / OLD TAR ROAD) FROM SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | $117,700,000
2028-02-15 | U-4714BB | Raleigh Letting (LET) | 39078.3.11 | 10 | UNION | SR 1009 (JOHNSTREET / OLD MONROE ROAD) INDIAN TRAIL ROAD TOEAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | $77,765,000
2028-03-21 | 15BPR.154 | Raleigh Letting (LET) | 15BPR.154.3 | 8 | CHATHAM | BRIDGE PRESERVATION. BRIDGE 180025 OVER HAW RIVER ON US 15/US 501 SBL; BRIDGE 180510 OVER HAW RIVER ON US 15/US 501 NBL. | $1,400,000
2028-03-21 | BR-0183 | Division Design Raleigh Let (DDRL) | 67183.3.1 | 1 | CHOWAN | REPLACE BRIDGE 200002 ON US17BUS OVER PEMBROKE CREEK | $11,500,000
2028-03-21 | HP-0008 | Raleigh Letting (LET) | 51892.3.1 | 5 | WAKE | HOLLY SPRINGS CITYWIDE SIGNAL SYSTEM. INSTALL FIBER TO CONNECT EXISTING TOWN FIBER TO INTERSECTIONS, UPGRADE EXISTING INFRASTRUCTURE INCLUDING CABINETS, CONTROLLERS, AND SOFTWARE. | $3,085,000
2028-03-21 | I-3306AC | Raleigh Letting (LET) | 34178.3.9 | 7 | ORANGE | I-40 AT NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTION FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | $7,300,000
2028-03-21 | I-5924 | Division Design Raleigh Let (DDRL) | 45933.3.1 | 14 | HAYWOOD | I-40 IN HAYWOOD COUNTY FROM MILE MARKER 15 TO MILE MARKER 20.5. REHABILITATE PAVEMENT. | $14,500,000
2028-03-21 | P-5725 | Raleigh Letting (LET) | 47603.3.1 | 10 | CABARRUS | KANNAPOLIS TRAIN STATION IMPROVEMENTS. CONSTRUCT VARIOUS TRACK AND SAFETY IMPROVEMENTS. | $13,900,000
2028-03-21 | R-5100A | Raleigh Letting (LET) | 41890.3.3 | 12 | IREDELL | SR 1109 (WILLIAMSON ROAD) FROM I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD) IN MOORESVILLE. WIDEN TO FOUR LANES. | $74,300,000
2028-03-21 | U-2561C | Division Design Raleigh Let (DDRL) | 34835.3.5 | 4 | NASH | NC 43 FROM SR 1613 (WOODRUFF AVENUE)TO I-95 WIDEN TO MULTI-LANES | $16,400,000
2028-03-21 | U-5709 | Division Design Raleigh Let (DDRL) | 50159.3.1 | 8 | LEE | SR 1237 (CARTHAGE STREET) FROM SR 1152 (FIRE TOWER ROAD) TONC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO-LANE DIVIDED FACILITY WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | $23,200,000
2028-03-21 | U-5821 | Division Design Raleigh Let (DDRL) | 44393.3.1 | 12 | GASTON | NC 279 (NEW HOPE ROAD) FROM SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD) IN GASTONIA. WIDEN TO FOUR LANES. | $122,700,000
2028-03-21 | U-5917 | Division Design Raleigh Let (DDRL) | 44679.3.1 | 2 | PITT | SR 1704 (FOURTEENTH STREET) FROM RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES | $24,700,000
2028-03-21 | U-5939 | Division Design Raleigh Let (DDRL) | 46887.3.1 | 1 | PASQUOTANK | US 17 BUSINESS TO SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | $19,200,000
2028-03-21 | U-5967 | Raleigh Letting (LET) | 45981.3.1 | 5 | WAKE | TOWN OF MORRISVILLE CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM | $560,000
2028-03-21 | U-6161 | Division Design Raleigh Let (DDRL) | 48472.3.1 | 11 | CALDWELL | US 321 FROM SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | $6,300,000
2028-04-18 | 15BPR.140 | Raleigh Letting (LET) | 15BPR.140.3 | 2 | PAMLICO | BRIDGE PRESERVATION. BRIDGE 680053 OVER SMITH CREEK ON SR 1308 AND BRIDGE 680015 OVER ICWW ON NC 33 | $7,000,000
2028-04-18 | BR-0075 | Division Design Raleigh Let (DDRL) | 51605.3.1 | 9 | FORSYTH | REPLACE BRIDGE 330135 OVER I-40 ON SR 1109 (KINNAMON ROAD) | $12,000,000
2028-04-18 | BR-0077 | Raleigh Letting (LET) | 52072.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400131 OVER US 70 (EAST WENDOVER AVENUE) ON SR 2770 (HUFFINE MILL ROAD) IN GREENSBORO | $18,701,000
2028-04-18 | BR-0079 | Raleigh Letting (LET) | 51601.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400302 OVER US29 / US 70 / US 220 ON TUSCALOOSA STREET IN GREENSBORO. | $7,700,000
2028-04-18 | I-5864 | Division Design Raleigh Let (DDRL) | 53067.3.1 | 11 | YADKIN | I-77 FROM MILEMARKER 71.8 TO MILEMARKER 75.8 PAVEMENT REHABILITATION | $10,100,000
2028-04-18 | P-5731 | Raleigh Letting (LET) | 47610.3.1 | 9 | DAVIDSON | NORFOLK SOUTHERN, CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREETAND CLOSE CROSSING 722306Y. | $72,000,000
2028-04-18 | R-2233BA | Raleigh Letting (LET) | 34400.3.3 | 13 | RUTHERFORD | US 221 FROM NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS. | $145,200,000
2028-05-16 | R-5824 | Division Design Raleigh Let (DDRL) | 47096.3.1 | 8 | MOORE | NC 690 (LOBELIA ROAD)FROM US 1 IN VASS TO CUMBERLAND COUNTYLINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | $14,300,000
2028-05-16 | U-4913AA | Division Design Raleigh Let (DDRL) | 40543.3.4 | 10 | MECKLENBURG | SR 3174 (IDLEWILD ROAD), I-485 INTERCHANGE. CONSTRUCTION INTERCHANGE IMPROVEMENTS. | $5,000,000
2028-05-16 | U-5747A | Division Design Raleigh Let (DDRL) | 50167.3.2 | 5 | WAKE | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. (COMB W/U-5747B & U-5750). | $28,500,000 | LET COMB. W/U-5747B & U-5750
2028-05-16 | U-5747B | Division Design Raleigh Let (DDRL) | 50167.3.3 | 5 | WAKE | SR 1635 AT NC 54 - CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. (COMB W/U-5747A & U-5750). | $44,500,000 | LET COMB. W/U-5747A & U-5750
2028-05-16 | U-5750 | Division Design Raleigh Let (DDRL) | 50170.3.1 | 5 | WAKE | NC 54 FROM NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. CONSTRUCT ADDITIONAL LANES. (COMB W/U-5747A & U-5747B). | $28,300,000 | LET COMB. W/U-5747 A & B
2028-06-20 | 15BPR.117 | Raleigh Letting (LET) | 15BPR.117.3 | 11 | SURRY | REHAB BRG 850013 ON I77 SB OVER NC268, NSRR, YADKIN RIVER | $1,100,000
2028-06-20 | B-5925 | Division Design Raleigh Let (DDRL) | 48057.3.1 | 14 | CHEROKEE | REPLACE BRIDGE 223 OVER HIWASSEE RIVER ON SR 1548 | $6,900,000
2028-06-20 | B-5953 | Division Design Raleigh Let (DDRL) | 47217.3.1 | 13 | BUNCOMBE | REPLACE BRIDGE 100649 OVER FRENCH BROAD RIVER AND SOUTHERNRAILROAD ON SR 1002 (OLD LEICESTER HIGHWAY) IN ASHEVILLE. | $28,400,000
2028-06-20 | BR-0031 | Raleigh Letting (LET) | 67031.3.1 | 14 | MACON | REPLACE BRIDGE 550227 OVER NANTAHALA RIVER ON SR 1310 (WAYAH ROAD). | $3,400,000 | LET COMB. W/BR-0052 & BR-0053
2028-06-20 | BR-0052 | Raleigh Letting (LET) | 67052.3.1 | 14 | MACON | REPLACE BRIDGE 550227 OVER NANTAHALA RIVER ON SR 1310 (WAYAH ROAD). | $3,300,000 | LET COMB. W/BR-0031 & BR-0053
2028-06-20 | BR-0053 | Raleigh Letting (LET) | 67053.3.1 | 14 | MACON | REPLACE BRIDGE 550228 OVER NANTAHALA RIVER ON SR 1310 (WAYAH ROAD). | $3,900,000 | LET COMB. W/BR-0031 & BR-0052
2028-06-20 | BR-0193 | Division Design Raleigh Let (DDRL) | 52220.3.1 | 3 | ONSLOW | REPLACE BRIDGE 660007 ON NC 24 WEST OVER NORTHEAST CREEK. | $12,100,000
2028-06-20 | HO-0027 | Raleigh Letting (LET) | 51910.3.1 | 1 | DARE | US 64 WILDLIFE CROSSING GRANT PROJECT TO INSTALL WILDLIFE CROSSINGS, UNDERPASS STRUCTURES, AND FENCING ALONG US 64 FROMEAST OF THE EAST LAKE COMMUNITY TO WEST OF SR 1169 (ROBERTSON LANDING ROAD). | $30,800,000
2028-06-20 | R-2576 | Design Build Let (DBL) | 34470.3.GV3 | 1 | CURRITUCK | MID-CURRITUCK BRIDGE, FROM COINJOCK TO COROLLA NCTA PROJECT | $1,062,200,000
2028-06-20 | R-5830 | Division Design Raleigh Let (DDRL) | 47102.3.1 | 11 | WATAUGA | SR 1522 (DEERFIELD ROAD), FROM STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD) IN BOONE. UPGRADE ROADWAY. | $16,000,000
2028-06-20 | R-5853 | Division Design Raleigh Let (DDRL) | 47541.3.1 | 4 | WAYNE | US 13 FROM SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | $10,100,000
2028-06-20 | U-6006 | Division Design Raleigh Let (DDRL) | 47141.3.1 | 8 | RANDOLPH | US 220 BUSINESS, FROM SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | $18,100,000
2028-06-20 | U-6027 | Division Design Raleigh Let (DDRL) | 47152.3.1 | 8 | RICHMOND | WIDEN AND ENHANCE SR 1516 (GREENE STREET) FROM US 220 TO US1 AND RE-ROUTE US 1 ONTO GREEN STREET TO REDUCE HEAVY TRUCKTRAFFIC IN DOWNTOWN ROCKINGHAM. | $8,100,000
2028-07-18 | B-5983 | Raleigh Letting (LET) | 47815.3.1 | 10 | MECKLENBURG | NC 160,REPLACE BRIDGE 590054 OVER NORFOLK SOUTHERN RAILROAD. | $8,200,000
2028-07-18 | BR-0021 | Raleigh Letting (LET) | 67021.3.1 | 4 | HALIFAX | BRIDGE 410051 ON NC 48 OVER ROANOKE RIVER | $35,100,000
2028-07-18 | BR-0083 | Design Build Let (DBL) | 67083.3.1 | 14 | HENDERSON | REPLACE BRIDGES 440057 AND 440115 ON US 64 OVER FRENCH BROAD RIVER OVERFLOW | $26,600,000
2028-07-18 | BR-0178 | Raleigh Letting (LET) | 67178.3.1 | 11 | ASHE | REPLACE BRIDGE 40056 ON SR1340 OVER NORTH FORK NEW RIVER | $5,200,000
2028-07-18 | HI-0009 | Division Design Raleigh Let (DDRL) | 49997.3.1 | 13 | MCDOWELL | SR 1001 (SUGAR HILL ROAD) FROM SR 1001 (SURGAR HILL ROAD) MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | $8,400,000
2028-07-18 | R-5772 | Division Design Raleigh Let (DDRL) | 44692.3.1 | 11 | WILKES | SR 1001 (OAKWOODS ROAD) FROM US 421 TO FOREST HILL DRIVE. UPGRADE EXISTING ROADWAY. | $16,800,000
2028-07-18 | R-5913 | Division Design Raleigh Let (DDRL) | 48468.3.1 | 11 | SURRY, YADKIN | US 21 BUSINESS WIDENING AND PEDESTRIAN IMPROVEMENT PROJECT IN JONESVILLE AND ELKIN. REHABILIATE BRIDGE 850021 OVER THE YADKIN RIVER AND WIDEN US 21 BUSINESS FROM COMMERCE STREET IN ELKIN TO SR 1402 / US 21 BUSINESS (NORTH BRIDGE STREET) INJONESVILLE. CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET / ELM | $10,500,000
2028-07-18 | U-6204 | Division Design Raleigh Let (DDRL) | 48664.3.1 | 4 | WAYNE | SR SR 1556 (WAYNE MEMORIAL DRIVE) FROM SR 1569 (COUNTRY DAY ROAD) TO SR 1003 (NEW HOPE ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $25,100,000
2028-08-15 | 15BPR.113 | Raleigh Letting (LET) | 15BPR.113.3 | 7 | GUILFORD | REHAB BRG 400875 ON I73 OVER I85 REHAB BRG 400524 ON NC62 OVER I85 | $2,800,000
2028-08-15 | B-6038 | Raleigh Letting (LET) | 48405.3.1 | 7 | ROCKINGHAM | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD ON NC 14/NC 87. | $13,300,000
2028-08-15 | HB-0025 | Division Design Raleigh Let (DDRL) | 50644.3.1 | 14 | POLK | REPLACE BRIDGE 740087 OVER THE BROAD RIVER ON SR 1004 (POORS FORD ROAD) SOUTH OF RUTHERFORDTON. | $10,600,000
2028-08-15 | HL-0024 | Division Design Raleigh Let (DDRL) | 49490.3.1 | 10 | MECKLENBURG | SR 3468 (WEDDINGTON ROAD) AT SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | $11,500,000
2028-08-15 | R-2588B | Division Design Raleigh Let (DDRL) | 34473.3.5 | 14 | HENDERSON | NC 191 FROM SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | $153,900,000
2028-08-15 | R-5757A | Division Design Raleigh Let (DDRL) | 44709.3.2 | 1 | NORTHAMPTON | NC 305 FROM HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | $25,600,000
2028-08-15 | R-5757B | Division Design Raleigh Let (DDRL) | 44709.3.3 | 1 | NORTHAMPTON | NC 305 FROM NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWNLIMITS. UPGRADE ROADWAY. | $32,500,000
2028-08-15 | R-5809B | Division Design Raleigh Let (DDRL) | 46976.3.3 | 1 | BERTIE | NC 45 FROM US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | $33,000,000
2028-08-15 | R-5832 | Division Design Raleigh Let (DDRL) | 47104.3.1 | 11 | ASHE | NC 88, FROM NC 88 TO NC 194. UPGRADE ROADWAY. | $68,000,000
2028-08-15 | U-6059A | Division Design Raleigh Let (DDRL) | 47483.3.2 | 9 | FORSYTH | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD ON SR 2662 (OLD GREENSBORO ROAD) IN WINSTON-SALEM. | $15,400,000
2028-09-19 | 15BPR.147 | Raleigh Letting (LET) | 15BPR.147.3 | 6 | BLADEN | BRIDGE PRESERVATION. BRIDGE 080030 OVER CAPE FEAR RIVER OVERFLOW ON US 701 NBL/NC 41 EB; BRIDGE 080199 OVER CAPE FEAR RIVER OVERFLOW ON US 701 SBL/NC 41 WB. | $2,700,000
2028-09-19 | BR-0076 | Division Design Raleigh Let (DDRL) | 67076.3.1 | 14 | GRAHAM | REPLACE BRIDGE 9 OVER LITTLE TENNESSEE RIVER ON NC 28 IN GRAHAM COUNTY | $21,300,000
2028-09-19 | HS-2001F | Division Design Raleigh Let (DDRL) | 49296.3.7 | 1 | CURRITUCK | US 158 CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | $4,300,000
2028-09-19 | R-2527 | Raleigh Letting (LET) | 35572.3.1 | 8 | MONTGOMERY | NC 24-27 FROM NC 73 TO THE TROY BYPASS. | $157,200,000
2028-09-19 | R-5763 | Division Design Raleigh Let (DDRL) | 44638.3.1 | 14 | TRANSYLVANIA | SR 1540 (WILSON ROAD)FROM SR 1504 (OLD US 64) TO US 276.UPGRADE ROADWAY | $62,000,000
2028-09-19 | U-5308 | Division Design Raleigh Let (DDRL) | 47028.3.2 | 8 | RANDOLPH | SR 1547 (FINCH FARM ROAD) FROM SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | $50,100,000
2028-09-19 | U-6086 | Division Design Raleigh Let (DDRL) | 47881.3.1 | 10 | MECKLENBURG | NC 51 FROM PARK ROAD TO CARMEL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $14,500,000
2028-10-17 | 15BPR.156 | Raleigh Letting (LET) | 15BPR.156.3 | 13 | RUTHERFORD | BRIDGE PRESERVATION. BRIDGE 800646 OVER BROAD RIVER & SR 1005 ON US 74; BRIDGE 800647 OVER BROAD RIVER & SR 1005 ON US74 EBL. | $3,200,000
2028-10-17 | B-6044 | Division Design Raleigh Let (DDRL) | 48330.3.1 | 4 | JOHNSTON | I-95 REPLACE BRIDGES 500082 AND 500085 OVER BLACK CREEK ANDBRIDGES 500100 AND 500101 OVER THE NEUSE RIVER. | $62,300,000 | LET COMB. W/ I-5974 AND HB-0042
2028-10-17 | BR-0169 | Raleigh Letting (LET) | 52143.3.1 | 5 | FRANKLIN | NC 561, BRIDGE 340024 OVER SANDY CREEK. REPLACE BRIDGE. | $4,000,000
2028-10-17 | HB-0031 | Division Design Raleigh Let (DDRL) | 50945.3.1 | 9 | FORSYTH | REPLACE THREE BRIDGES OVER US 52 / US 311 / NC 8 IN WINSTON-SALEM. BRIDGE 330185 ON THIRD STREET, BRIDGE 330191 ON FOURTH STREET AND BRIDGE 330203 ON FIFTH STREET. | $9,500,000
2028-10-17 | HB-0042 | Division Design Raleigh Let (DDRL) | 50740.3.1 | 4 | JOHNSTON | US 301 REPLACE BRIDGE 56 OVER HOLT LAKE. | $11,300,000 | LET COMB. W/ I-5974 AND B-6044
2028-10-17 | I-5974 | Division Design Raleigh Let (DDRL) | 44993.3.1 | 4 | JOHNSTON | I-95 AT US 701 / NC 96. CONSTRUCT INTERCHANGE. | $76,000,000 | LET COMB. W/ HB-0042 & B-6044
2028-10-17 | R-2632AB | Raleigh Letting (LET) | 38824.3.2 | 10 | MECKLENBURG | NC 73 (SAM FURR ROAD) FROM NC 115 (OLD STATESVILLE ROAD) TOSR 2693 (DAVIDSON-CONCORD ROAD) IN HUNTERSVILLE. WIDEN TO FOUR LANES. | $68,100,000
2028-10-17 | R-5721B | Raleigh Letting (LET) | 50215.3.2 | 10 | MECKLENBURG | NC 73 FROM VANCE ROAD EXTENSION / SR 2128/SR 2196 (BEATTIESFORD ROAD) TO SR 5544(WEST CATAWBA AVENUE). WIDEN TO MULTILANES. | $76,400,000
2028-10-17 | U-4407 | Division Design Raleigh Let (DDRL) | 39051.3.1 | 4 | WAYNE | US 70 BUSINESS (EAST ASH STREET) FROM SR 1711 (SOUTH OAK FOREST ROAD) TO US 70. WIDEN TO FOUR LANES. | $29,500,000
2028-10-17 | U-5301A | Raleigh Letting (LET) | 47018.3.5 | 5 | WAKE | APEX/CARY - US 64 AT SR 1306 (LAURA DUNCAN ROAD) | $32,300,000
2028-10-17 | U-5886 | Division Design Raleigh Let (DDRL) | 44710.3.1 | 14 | HENDERSON | SR 1170 (WHITE STREET) FROM SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). (COMB W/U-6049). REALIGN AND EXTEND ROADWAY. | $18,200,000 | LET COMB. W/U-6049
2028-10-17 | U-6049 | Division Design Raleigh Let (DDRL) | 46995.3.1 | 14 | HENDERSON | BRIDGE 440143 OVER MUD CREEK ON US 25 BUSINESS (SOUTH MAIN STREET) AND US 25 BUSINESS FROM SOUTH MAIN STREET / SOUTH KING STREET TO US 276 IN HENDERSONVILLE. WIDEN BRIDGE TO FIVE LANES. | $8,800,000 | LET COMB. W/U-5886
2028-10-17 | U-6157 | Division Design Raleigh Let (DDRL) | 48471.3.1 | 11 | CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) FROM SR 1001 (CONNELLY SPRINGS ROAD) TO US 321 ALTERNATE IN SAWMILLS. MODERNIZE ROADWAY. | $45,100,000
2028-11-21 | 15BPR.127 | Raleigh Letting (LET) | 15BPR.127.3 | 10 | MECKLENBURG | BRIDGE PRESERVATION FOR BRIDGE 294 OVER I-85 ON NC 24 (WTHARRIS BOULEVARD) IN MECKLENBURG COUNTY | $2,800,000
2028-11-21 | 15BPR.160 | Raleigh Letting (LET) | 15BPR.160.3 | 19 | STATE WIDE | BRIDGE PRESERVATION FOR BRIDGES 19 AND 27 IN PASQUOTANK COUNTY 690019 CARRYING US 158 EB OVER PASQUOTANK RIVER 690027 CARRYING US 158 WB OVER PASQUOTANK RIVER | $2,400,000
2028-11-21 | B-6037 | Division Design Raleigh Let (DDRL) | 48404.3.1 | 7 | ORANGE | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILWAY ON NC 86. | $11,400,000
2028-11-21 | BR-0163 | Division Design Raleigh Let (DDRL) | 52144.3.1 | 10 | ANSON | NC 742, BRIDGE 030084 OVER LANES CREEK. REPLACE BRIDGE. | $4,448,000
2028-11-21 | I-5719A | Design Build Let (DBL) | 50135.3.GV1 | 12 | GASTON | I-85, FROM US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET).WIDEN TO EIGHT LANES.(COMB W/U-6044). | $498,200,000 | LET COMB. W/U-6044
2028-11-21 | I-6000 | Division Design Raleigh Let (DDRL) | 47955.3.1 | 5 | WAKE, DURHAM | I-540 - DURHAM/WAKE COUNTIES FROM I-40 IN DURHAM TO US 1 INRALEIGH. BRIDGE PRESERVATION/REHABILITATION. COORDINATE WITH I-5998 & I-5999. | $7,610,000
2028-11-21 | U-6034 | Division Design Raleigh Let (DDRL) | 46968.3.1 | 11 | CALDWELL | US 321 ALTERNATE FROM SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET) IN GRANITE FALLS. UPGRADE ROADWAY. | $29,400,000
2028-11-21 | U-6044 | Design Build Let (DBL) | 46986.3.1 | 12 | GASTON | SR 2200 (COX ROAD)FROM I-85 TO US 29/74 SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS (COMB W/I-5719 AND U-5800). | $14,300,000 | LET COMB. W/I-5719A
2029-01-16 | 15BPR.109 | Raleigh Letting (LET) | 15BPR.109.3 | 4 | NASH | REHAB BRG 630162 ON US64 E OVER I95 REHAB BRG 630163 ON US64 W OVER I95 | $6,900,000
2029-01-16 | 15BPR.110 | Raleigh Letting (LET) | 15BPR.110.3 | 5 | WAKE | REHAB BRG 910293 ON I40 OVER SR1564 (S.WILMINGTON STREET) REHAB BRG 910572 ON I40E, US64 OVER SR2026 (S. SAUNDERS ST.) | $2,200,000
2029-01-16 | 15BPR.135 | Raleigh Letting (LET) | 15BPR.135.3 | 10 | MECKLENBURG | BRIDGE PRESERVATION. BRIDGE 664 OVER I-485 / I-77 / SUGERCREEK ON THE I-77 RAMP | $4,600,000
2029-01-16 | B-5680 | Raleigh Letting (LET) | 45635.3.1 | 5 | WAKE | REMOVE BRIDGE 449 OVER THE CSX RAILROAD IN CARY ON SR 1633 | $580,000
2029-01-16 | BR-0022 | Division Design Raleigh Let (DDRL) | 67022.3.1 | 14 | HAYWOOD | BRIDGE 430122 ON US 19,23,74 SBL OVER NC 209 | $11,000,000
2029-01-16 | BR-0030 | Raleigh Letting (LET) | 67030.3.1 | 14 | MACON | BRIDGE 550085 ON NC 28 OVER COWEE CREEK | $4,100,000
2029-01-16 | BR-0078 | Raleigh Letting (LET) | 67078.3.1 | 7 | GUILFORD | REPLACE BRIDGE 400292 AND 400467 ON US 220 OVER US 220 SBL AND SR 1452 | $32,200,000
2029-01-16 | EB-5732 | Division Design Raleigh Let (DDRL) | 51055.3.1 | 10 | CABARRUS | SR 2894 (BRUTON SMITH BOULEVARD / CONCORD MILLS BOULEVARD),US 29 TO JOHN Q. HAMMONDS DRIVE IN CONCORD. CONSTRUCT SHARED USE PATH ON NORTH SIDE OF ROAD. | $10,400,000
2029-01-16 | I-5828 | Division Design Raleigh Let (DDRL) | 50471.3.1 | 10 | MECKLENBURG | I-485 FROM I-77 TO NC 49. PAVEMENT REHABILITATION. REHABILITATE BRIDGES 590661, 590662, 590663, 590664, AND 590643. | $21,600,000
2029-01-16 | P-5726 | Raleigh Letting (LET) | 47604.3.1 | 9 | ROWAN | RAILROAD NORFOLK SOUTHERN NORFOLK SOUTHERN MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS,SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | $13,600,000
2029-01-16 | U-4405C | Raleigh Letting (LET) | 39049.3.6 | 6 | CUMBERLAND | US 401 (RAEFORD ROAD) FROM EAST OF SR 1596 (GLENSFORD DRIVE) TO EAST OF ROBESON STREET. | $63,400,000
2029-01-16 | U-5770B | Division Design Raleigh Let (DDRL) | 54036.3.3 | 8 | RANDOLPH | SR 1009 (SOUTH MAIN STREET) FROM WEST OF COLUMBUS AVENUE TOSR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCIIMPROVEMENTS. | $25,600,000
2029-02-20 | 15BPR.145 | Raleigh Letting (LET) | 15BPR.145.3 | 5 | WAKE | BRIDGE PRESERVATION ON BRIDGE 228 IN WAKE COUNTY | $1,000,000
2029-02-20 | B-5976 | Division Design Raleigh Let (DDRL) | 47239.3.1 | 8 | LEE | SR 1400 (CUMNOCK RD.), REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | $11,500,000
2029-02-20 | HI-0021 | Division Design Raleigh Let (DDRL) | 49992.3.1 | 6 | CUMBERLAND | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | $19,000,000
2029-02-20 | R-5822 | Division Design Raleigh Let (DDRL) | 47094.3.1 | 7 | CASWELL | NC 86 FROM US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCTTURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | $26,600,000
2029-03-20 | 15BPR.120 | Raleigh Letting (LET) | 15BPR.120.3 | 14 | SWAIN | REHAB BRG 860023 AND 860022 ON US74 OVER SR1173,RR,TUCKASEGEE RVR | $2,700,000
2029-03-20 | BR-0180 | Division Design Raleigh Let (DDRL) | 67180.3.1 | 13 | BURKE | REPLACE BRIDGE 110346 ON SR1002 OVER HENRY FORK CREEK | $6,500,000
2029-03-20 | HI-0003 | Division Design Raleigh Let (DDRL) | 49994.3.1 | 8 | RANDOLPH | I-73/US 220 FROM SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | $12,600,000
2029-03-20 | HI-0022 | Division Design Raleigh Let (DDRL) | 49993.3.1 | 6 | CUMBERLAND | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | $12,000,000
2029-03-20 | I-5891B | Division Design Raleigh Let (DDRL) | 46411.3.3 | 13 | BURKE | I-40 FROM MILE MARKER 105 TO MILE MARKER 112 PAVEMENT REHABILITATION AND BRIDGE REHABILITATION | $4,000,000
2029-03-20 | U-2530A | Division Design Raleigh Let (DDRL) | 34824.3.3 | 12 | CATAWBA | NC 127 FROM SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). WIDEN TO MULTI-LANES. | $59,700,000
2029-03-20 | U-5726 | Division Design Raleigh Let (DDRL) | 54017.3.1 | 4 | JOHNSTON | US 301/NC 39/NC 96 FROM SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | $29,100,000
2029-03-20 | U-5790 | Division Design Raleigh Let (DDRL) | 44362.3.1 | 3 | NEW HANOVER | US 421 (CAROLINA BEACH ROAD)FROM NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONTRUCT FLYOVERS AT US 421 AND NC 132. INCLUDES U-5859 | $39,300,000
2029-03-20 | U-5817 | Raleigh Letting (LET) | 44389.3.1 | 12 | IREDELL | SR 1246 (FAIRVIEW ROAD) EXTENSION OVER I-77 TO CONNECT WITHSR 1206 (ALCOVE ROAD). CONSTRUCT ROADWAY EXTENSION AND PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | $25,200,000
2029-03-20 | U-5951 | Division Design Raleigh Let (DDRL) | 45870.3.1 | 3 | ONSLOW | US 17 AT US 17 BUSINESS (MARINE BOULEVARD) IN JACKSONVILLE.UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | $27,200,000
2029-03-20 | U-6032 | Division Design Raleigh Let (DDRL) | 46965.3.1 | 10 | MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD) FROM I-485 TO THE CABARRUS COUNTY LINE AND SR 1445 (DERITA ROAD) FROM THE COUNTY LINE TO SR 2894 (CONCORD MILLS BOULEVARD) IN CHARLOTTE. WIDEN TO SIX LANES. | $38,200,000
2029-03-20 | U-6205 | Division Design Raleigh Let (DDRL) | 48665.3.1 | 4 | WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) FROM US 70 BYPASS TO SR 1547(STONEY CREEK ROAD). WIDEN ROADWAY. | $2,500,000
2029-04-17 | 15BPR.106 | Raleigh Letting (LET) | 15BPR.106.3 | 2 | PITT | BRIDGES 455 & 456 OVER TAR RIVER ON US 264 IN PITT COUNTY.BRIDGE REHABILITATION. | $1,900,000
2029-04-17 | 15BPR.134 | Raleigh Letting (LET) | 15BPR.134.3 | 7 | GUILFORD, ORANGE, ALAMANCE | BRIDGE PRESERVATION. BRIDGE 197 OVER I-85 BUSINESS ON SR 1117 (SOUTH HOLDEN ROAD) IN GUILFORD COUNTY; BRIDGE 148 OVER HAW RIVER ON I-40 IN ALAMANCE COUNTY | $6,900,000
2029-04-17 | B-5681 | Raleigh Letting (LET) | 45636.3.1 | 5 | WAKE | REPLACE BRIDGE 258 OVER US 70 IN GARNER ON SR 2713 | $14,900,000
2029-04-17 | BR-0088 | Raleigh Letting (LET) | 67088.3.1 | 14 | MACON | REPLACE BRIDGE 550104 ON US 64 OVER CULLASAJA RIVER | $14,200,000
2029-04-17 | BR-0192 | Division Design Raleigh Let (DDRL) | 67192.3.1 | 4 | NASH | REPLACE BRIDGE 630038 ON NC43 BUS; NC48 OVER TAR RIVER | $8,000,000
2029-04-17 | BR-0194 | Division Design Raleigh Let (DDRL) | 67194.3.1 | 3 | ONSLOW | REPLACE BRIDGE 660029 ON US17 OVER CHANEY CREEK | $5,100,000
2029-04-17 | HB-0029 | Raleigh Letting (LET) | 50637.3.1 | 5 | WAKE | SR 1179 (BRIDGE STREET) REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | $3,300,000
2029-04-17 | HL-0133A | Division Design Raleigh Let (DDRL) | 51367.3.2 | 5 | WAKE | POOLE ROAD / HODGE ROAD INTERSECTION IMPROVEMENTS. | $2,500,000 | LET COMB. W/HL-0133L
2029-04-17 | HL-0133L | Division Design Raleigh Let (DDRL) | 51367.3.13 | 5 | WAKE | POOLE ROAD / BARWELL TO HODGE ROAD CONSTRUCT SECOND 2-LANE BRIDGE OVER NEUSE AND WIDEN POOLE TO TIE INTO 4-LANE SECTIONS TO WEST AND EAST. | $23,000,000 | LET COMB. W/HL-0133A
2029-04-17 | R-5836 | Division Design Raleigh Let (DDRL) | 47106.3.1 | 11 | SURRY | US 601 (ROCKFORD STREET) FROM I-74 TO SR 1104 (CODY TRAIL) SOUTH OF DOBSON. WIDEN TO FOUR LANES. | $143,800,000
2029-05-15 | B-5926 | Division Design Raleigh Let (DDRL) | 46369.3.1 | 12 | GASTON | NC 273, REPLACE BRIDGE 22 OVER DUKE POWER FEEDER CANAL | $12,000,000
2029-05-15 | I-5708 | Raleigh Letting (LET) | 50124.3.1 | 5 | WAKE | I-440/US 1 AT SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | $23,000,000
2029-05-15 | U-5816 | Division Design Raleigh Let (DDRL) | 44388.3.1 | 12 | IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) FROM US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | $50,200,000
2029-06-19 | BR-0151 | Division Design Raleigh Let (DDRL) | 52146.3.1 | 13 | BURKE | SR 1002 (HENERY RIVER ROAD),SR 1002 (HENRY RIVER ROAD) OVERI-40. REPLACE BRIDGE. | $12,400,000
2029-06-19 | HL-0133D | Division Design Raleigh Let (DDRL) | 51367.3.5 | 5 | WAKE | US 70 BUS AT AUBURN KNIGHTDALE ROAD, CONVERT INTERSECTION TO REDUCED CONFLICT INTERSERCTION. | $10,900,000
2029-06-19 | HL-0133F | Division Design Raleigh Let (DDRL) | 51367.3.7 | 5 | WAKE | US 70 BUSINESS AND GUY ROAD CONVERT INTERSECTION TO REDUCEDCONFLICT INTERSECTION. | $8,700,000
2029-06-19 | I-5990 | Division Design Raleigh Let (DDRL) | 47536.3.1 | 13 | BURKE | I-40 AT EXIT 118 - SR 1761 (OLD NC 10). (COMB W/BR-0151). CONSTRUCT INTERCHANGE IMPROVEMENTS. | $19,800,000
2029-06-19 | I-6065 | Division Design Raleigh Let (DDRL) | 48856.3.1 | 10 | IREDELL, MECKLENBURG | I-77 FROM I-485 TO NC 150, CONSTRUCT PEAK PERIOD SHOULDER LANES. | $45,762,000
2029-06-19 | P-5713 | Raleigh Letting (LET) | 46925.3.1 | 7 | GUILFORD | NORTH CAROLINA RAILROAD (NCRR)/NORFOLKSOUTHERNRAILROAD, SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSINGTO GRADE SEPARATION. | $20,200,000
2029-06-19 | P-5744 | Raleigh Letting (LET) | 48159FRA.3.2 | 10 | UNION | CSX SF LINE UNION COUNTY AT 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. | $23,100,000
2029-06-19 | P-5748B | Raleigh Letting (LET) | 48336FRA.3.1 | 10 | UNION | CSX SG RAILWAY LINE AT SR 1300 (HELMS ROAD) CONSTRUCT GRADESEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TROY PATH). | $25,000,000
2029-06-19 | R-5709B | Raleigh Letting (LET) | 50205.3.3 | 8 | MOORE, HOKE | NC 211, FROM US 15 / US 501 IN ABERDEEN TO 0.40 MILES NORTH OF SR 1225 (ASHEMONT ROAD). WIDEN TO MULTI-LANES. | $121,500,000
2029-06-19 | R-5905 | Division Design Raleigh Let (DDRL) | 48463.3.1 | 11 | SURRY | NC 89 (WEST PINE STREET) FROM SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | $53,400,000
2029-06-19 | R-5929 | Division Design Raleigh Let (DDRL) | 48547.3.1 | 8 | MOORE | NC 24 / NC 27 AT SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15/ US 501. | $4,900,000
2029-06-19 | R-5943 | Division Design Raleigh Let (DDRL) | 48561.3.1 | 2 | GREENE | US 13 AT SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | $10,600,000
2029-06-19 | U-2307B | Raleigh Letting (LET) | 34791.3.9 | 12 | CATAWBA | EAST SIDE THOROUGHFARE FROM SR 1453 (SPRINGS ROAD) TO NC 127 | $64,700,000
2029-06-19 | U-5734 | Division Design Raleigh Let (DDRL) | 54024.3.1 | 3 | NEW HANOVER | US 421 (SOUTH FRONT STREET) FROM US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD).WIDEN TO MULTI-LANES. | $37,500,000
2029-06-19 | U-5769A | Division Design Raleigh Let (DDRL) | 50182.3.1 | 10 | UNION | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCHRD). WIDEN TO MULTI-LANES. | $71,000,000 | LET COMB. W/U-5769B
2029-06-19 | U-5769B | Division Design Raleigh Let (DDRL) | 50182.3.2 | 10 | UNION | NC 16 (PROVIDENCE ROAD SOUTH) FROM SR 1321 (CUTHBERTSON ROAD) IN WEDDINGTON TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW WIDENTO MULTILANES | $80,900,000 | LET COMB. W/U-5769A
2029-06-19 | U-5791A | Division Design Raleigh Let (DDRL) | 44363.3.2 | 3 | ONSLOW | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) FROM NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). WIDEN TO MULTILANES, | $0
2029-06-19 | U-5792 | Division Design Raleigh Let (DDRL) | 54038.3.1 | 3 | NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) FROM US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | $241,900,000
2029-07-10 | BP12-R047 | Division Design Raleigh Let (DDRL) | BP12.R047.3 | 12 | CLEVELAND | REPLACE CLEVELAND BRIDGE 3 ON SR 1305 (WALMART ROAD) OVERBRUSHY CREEK | $6,400,000
2029-07-17 | B-5148 | Raleigh Letting (LET) | 42309.3.1 | 9 | FORSYTH | REPLACE BRIDGE 276 OVER NC 67 ON SR 1001 | $8,000,000
2029-07-17 | B-5729 | Division Design Raleigh Let (DDRL) | 45685.3.1 | 7 | ROCKINGHAM | REPLACE BRIDGE 134 OVER THE DAN RIVER IN EDEN ON NC 700 | $12,300,000
2029-07-17 | BR-0006 | Raleigh Letting (LET) | 67006.3.1 | 2 | BEAUFORT | REPLACE BRIDGES 060321 AND 060322 ON NC 306 OVER PAMLICO SOUND | $26,000,000
2029-07-17 | BR-0016 | Division Design Raleigh Let (DDRL) | 67016.3.1 | 9 | DAVIDSON | BRIDGE 280150 ON I-85 BUS OVER SR 2123W | $10,800,000 | LET COMB. W/HS-2009C
2029-07-17 | BR-0197 | Raleigh Letting (LET) | 67197.3.1 | 11 | SURRY | REPLACE BRIDGES 850097 AND 850100 ON US 52 OVER SOU. RR, HEATHERLY CREEK. | $20,500,000
2029-07-17 | HS-2009C | Division Design Raleigh Let (DDRL) | 49321.3.4 | 9 | DAVIDSON | US 29-70 AT LITWIN DRIVE/SR 2123 (OLD US 29). INSTALL DIRECTIONAL LEFTOVERS. | $500,000 | LET COMB. W/BR-0016
2029-07-17 | U-5785 | Raleigh Letting (LET) | 44357.3.1 | 2 | PITT | SR 1708 (FIRETOWER ROAD) FROM WEST OF SR 1725 (COUNTY HOME ROAD)/EAST ARLINGTON BOULEVARD TO SR 1726 (PORTERTOWN ROAD);AND SR 1726 (PORTERTOWN ROAD) FROM FIRETOWER ROAD TO NC 33 IN GREENVILLE. WIDEN TO FOUR LANES. | $109,400,000
2029-07-17 | U-5811 | Raleigh Letting (LET) | 44384.3.1 | 5 | WAKE | SR 1002 (AVIATION PARKWAY) FROM NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | $42,200,000
2029-08-21 | 15BPR.115 | Raleigh Letting (LET) | 15BPR.115.3 | 9 | ROWAN | REHAB BRG 790137 AND 790465 ON I85 OVER YADKIN RIVER | $6,900,000
2029-08-21 | 15BPR.136 | Raleigh Letting (LET) | 15BPR.136.3 | 1 | BERTIE, PASQUOTANK, TYRRELL, PERQUIMANS | BRIDGE PRESERVATION. BRIDGES 14 & 80 OVER PERQUIMANS RIVER ON US 17 IN PERQUIMANS COUNTY | $7,500,000
2029-08-21 | BR-0154 | Raleigh Letting (LET) | 52218.3.1 | 14 | HAYWOOD | REPLACE BRIDGE 430128 ON NC 209 OVER COVE CREEK. | $1,600,000
2029-08-21 | HB-0024 | Raleigh Letting (LET) | 50643.3.1 | 5 | FRANKLIN | US 401 REPLACE BRIDGE 340056 OVER SANDY CREEK. | $4,000,000
2029-08-21 | R-2822BB | Division Design Raleigh Let (DDRL) | 34508.2.6 | 14 | GRAHAM | NC 143 FROM WEST BUFFALO CREEK OVER NC 143 BUSINESS. REPLACE BRIDGE 370013. | $33,500,000
2029-08-21 | R-5840 | Division Design Raleigh Let (DDRL) | 47083.3.1 | 14 | POLK | NC 9 FROM US 74 TO NC 108. CONSTRUCT PAVED SHOULDERS. | $19,400,000