## Project Close Out List
TIP / Proj #: | WBS #: |  | Federal Aid #:
Municipality: | Project Description:
Contractor: | CEI Representative: |  | Division:
NTP: | Date Work Started:
Contract Completion Date: | Actual Completion Date:
DBE Commitment Amount: | Actual DBE Amount Paid:
ALL INVOICES ASSOCIATED WITH THE PROJECT MUST BE SUBMITTED WITHIN SIX (6) MONTHS OF THE COMPLETION OF CONSTRUCTION AND ACCEPTANCE OF THE PROJECT TO BE ELIGIBLE FOR REIMBURSEMENT BY THE DEPARTMENT. ANY INVOICES SUBMITTED AFTER THIS TIME WILL NOT BE ELIGIBLE FOR REIMBURSEMENT.
| Date (MM/DD/YYYY) | Punchlist Complete? (Y/N) | Date Punchlist Complete
Final Inspection with NCDOT Present
Project Final Est Process Mtg with NCDOT (review this doc and process)
| Date Written | Date Submitted to NCDOT | Date Received from NCDOT
Copy of NTP/Project Start letter
Copy of Division Project Documentation Review(s)
Project Acceptance Letter from Municipality to Contractor
Request for Concurrence in Construction from Municipality to NCDOT (including date of Acceptance)
Concurrence in Construction Letter from NCDOT (send to Div LAP Manager)
| Date reviewed by NCDOT | Materials Certification Date
Materials and Test Review (NCDOT)
| Totaled (Y/N) | Comp'd (Y/N) | Checked (Y/N) | Received from Testing firm? (Y/N)
As-built drawings
Pay Record Books for Final estimate
Ticket Books
Materials Receipts
Concrete Reports (903, 250)
Asphalt Reports (605)
Test Results Received for:
Density/Test Results
Asphalt (Core or Nuclear? Circle Appropriate)
Concrete
ABC Roadway(For Pavement, not Class IV, CL IV to be subgrade or emb)
Roadway Subgrade
Roadway Embankment
Samples
Roadway Embankment
Roadway Subgrade
Roadway ABC
| Fully Executed (Reviewed and signed by NCDOT) (Y/N) | Reviewed and verified against the FHWA 1273 (Y/N) | Completed & Signed by CEI/RE (Y/N) | Completed/Signed/ Notarized by Contractor/Employee (Y/N)
Pay Applications
DBE-IS Form (Can be included in pay app)
Certified Payrolls
Sales Tax Reports
SAFs (to include prime and sub agr, FHWA 1273, Title VI)
Buy America Cert
Daily Reports
Weekly Summaries
Wage Rate Interviews
DBE-IS Contract Goal & Commitment Payment Summary Form
| Written/Drafted? | Approved/Executed? (Contractor, Muni, NCDOT) | Total Additional Time &/OR Money
Claims (time, money, final)
Claim 1 - Description
Select this row and Insert additional lines as necessary
Force Account (Form 480 w/ Supporting Documentation) to be paid as a SA
FA 1 - Description
Select this row and Insert additional lines as necessary
Supplemental Agreement(s)
SA 1 - Description
Select this row and Insert additional lines as necessary
| Approved & Executed (Y/N) | Written (Y/N) | Submitted to Contractor | Received from Contractor
Final Pay Application/Estimate (Include with other pay applications)
Pay Adjustments or 105-3 Acceptance Letters
Ex. Asphalt Letter
Ex. Asphalt Letter
Ex. Asphalt Letter
Consent of Surety from Contractor, 109-10(A)
Affidavit of Debts from Contractor, 190-10(B)
Release of Claim from Contractor, 109-10(C)
Any other document required by contract for compliance with applicable labor regulations of FHWA, 109-10(D)
| Created/Drafted (Y/N) | Date Records Delivered to NCDOT Facility For Review | Completed and Signed off by NCDOT Checker
Final Estimate Transmittal to Division Final Estimate Checker -to include a copy of this completed checklist with the Final Estimate

## Pro-rata and LD Calc
PRO-RATA Calculation |  |  | Project TIP Number |  | X-0000
Cells highlighted in yellow are to be filled in. All other cells are calculated by a formula. Do not modify cells with formulas, except to copy to inserted rows.
Supplemental Agreements that Grant Time
SA # | Description | Original Amount | Final Amount | Days Granted by SA | Pro-rata Days for Overrun of SA | Total SA Time
1 |  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
Select the row above and Insert additional lines as neeeded. Copy formulas to every inserted row.
SA's that Grant Time Final Amount Correction Total |  |  | 0 |  | Total SA Days | 0
Claims that Grant Time - Not Project Final Claim
Claim # | Description | Days Granted by Claim
Select the row above and Insert additional lines as neeeded. Copy formulas to every inserted row.
Total Claim Time Granted |  | 0
Pay Factor Price Adjustment Correction (Asphalt density, 105-3, or permitted by Standard Specs)
LI # | Description | Original Unit Price | Adjusted Unit Price | Adjusted Quantity | Pay Factor Total Amount
0
0
Select the row above and Insert additional lines as neeeded. Copy formulas to every inserted row.
Final Amount Correction Total |  |  |  |  | 0
AC Price Adjustment Correction
AC Line Item Unit Price |  | Total Tons of AC Adjusted | Total Value of AC Adjustment | AC Adjusment Correction Total
0
Fuel Price Adjustment Correction
Total Value of Fuel Adjustment |  | Fuel Adjusment Correction Total
0
Contract Time, Pro-rata, and LD Days Calculation
| Use either time calcultor, depending on known values | Calculated Completion Date |  |  | Calculated Duration
| Contract Start / NTP Date |  |  | Contract Start / NTP Date
| Contract Duration (Days) |  |  | Contract Completion Date
| Contract Completion Date | -1 |  | Contract Duration (Days) | 1
Original Contract Amount
Final Paid Amount
| Total Adjustment Amount | 0
| Adj Contract Final Amount | 0
| Amount Difference | 0
| % Overrun | #DIV/0!
| Pro-rata Days | #DIV/0!
Original Contract Days
| Pro-rata Days | #DIV/0!
| Additional Days Granted By SA's | 0
| Additional Days Granted By Claims | 0
| Total Adjustment Days | #DIV/0!
| Total Adjusted Contact Days | #DIV/0!
Contract Start / NTP
Date Work Started
Contract Completion Date
| Revised Contract Completion Date | #DIV/0!
Actual Construction Completion Date
| Contract Days Overrun | #DIV/0!
LD Calculations - Day UoM
| ICT # | Unit of Measure | LD Rate | Original Amount | Final Amount | ICT Days | Pro-rata Days | Total ICT Time | Actual ICT | LD Days | LD Amount
| Contract |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 1 | #DIV/0! | #DIV/0!
| 1 | [5 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0!
0
Select the row above and Insert additional lines as neeeded. Copy formulas to every inserted row.
LD Calculations - Time UoM
| ICT # | Unit of Measure | LD Rate | # of Violations | [6 empty] | LD Amount
0
0
Select the row above and Insert additional lines as neeeded. Copy formulas to every inserted row. | [9 empty] | Total LD | #DIV/0!
Formulas:
Original Amount = C34+[Original Amount, row above]-1