## Coversheet
The following checklist is to act as a guide to support you – the project manager - and design teams to include constructability issues during design development. The first step is to review the checklist and begin to identify which issues may impact your project. Refer back to this checklist as you move through the various stages of your project. When you get to a point and you are unsure of how to include the constructability issues, reach out to your Division Construction Engineer (DCE) or Area Construction Engineer (ACE) for support and guidance.
Should you and/or the DCE/ACE determine an informal constructability review is needed, you are welcome to contact the Value Management Office to plan, facilitate, and share the meeting outcomes with everyone. The informal constructability review only includes internal NCDOT personnel and can also include the Private Engineering Firm working on the project.
Should you and/or the DCE/ACE determine a formal constructability review is needed, contact the Value Management Office. This is only permissible on a Design-Bid-Build project. A formal review allows contractors from the AGC to participate in the review. It is important that the Value Management Office organize and conduct these reviews and be the contact for the AGC to eliminate the potential for contractor bias. Contractor’s who participate are not disqualified from participating in bidding the project.
Keep this checklist as a part of the design development record.
Project Number (TIP): | Division:
PM Contact Name: | PM Contact email:
PEF Contact name: | PEF Contact email:

## Overall
Overall Checklist |  | If you answer yes to any of these questions and are unsure of how to address the construction impacts,
please contact the Area Construction Engineer for your division.
https://apps.ncdot.gov/dot/directory/authenticated/UnitPage.aspx?id=2821
Yes - on any of these items may warrant an internal or external CR. Contact your ACE and/or VMO.
Item | Description |  | Yes | No | Not Yet Defined
A | General
A-1a | If there is a Local Agreement, is it related to the construction footprint, construction hours, hauling routes, or another construction impact? i.e, holiday events that may result in road closures.
A-1b | If there is a Local Agreement, is it related to a unique feature to be construction - i.e., pedestrian bridge never constructed in the State?
A-1c | Does the MPO/RPO etc not understand the construction impacts? A CR can be helpful to provide back-up documentation.
A-1d | Overall -were any agreements made with the town that may impact Construction?
A-2 | Is it anticipated that this project construction will need to be accelerated?
B | Traffic Management
B-1 | Has sufficient construction easement been obtained for temporary work zone? Including traffic shifts, temporary bridges, temporary signage, etc.
B-2a | Do bike and pedestrians need to be accomodated during construction?
B-2b | Has this safety measure been taken into consideration?
B-3 | Has the phasing of the earthwork, hydraulics, etc been reviewed to consider the construction phasing?
B-4a | Are detours required?
B-4b | If so, have the detours been approved by the town?
B-4c | Is justification needed for the easements?
B-5a | Timing of highway closure for blasting and clearing?
B-5b | Does this project include blasting?
B-6a | Is the ground water level high?
B-6b | Will this impact the construction?
B-6c | Has how it will be handled been addressed?
B-7 | Is specialized equipment needed to complete any part of the project?
B-8 | If shoulders are required to carry traffic during staging, are shoulders sufficiently designed for that?
B-9 | Is there sufficient room to install shoring for the maintenance of traffic and construct the project?
B-10 | If no reasonable detour is available, will lane closures result in significant backups and/or create safety issues?
C | Project Complexity
C-1a | Will businesses or residences impacted during construction?
C-1b | Has access been provided?
C-1c | Will this impact the construction footbring and access?
C-2a | Will construction impact emergency services, schools, etc?
C-2b | Have access roads been provided for these and will it impact the construction access?
C-3a | Will detour be required?
C-3b | Has traffic analysis been conducted on the traffic for the detour?
C-3c | Have the construction impacts been considered for the detour?
C-4 | Has the phasing of the earthwork, hydraulics, etc been reviewed to consider the construction phasing?
C-5 | Is the project located in an area with limited laydown and staging areas?
C-6 | Can easements be obtained for detours?
C-7a | Is there sufficient construction easement?
C-7b | Are there locations where sufficient construction easement will not be able to be found?
C-8 | Are the potential hauling routes acceptable to carry the loads of the construction equipment?
C-9 | Is site-access for hauling materials an issue?
C-10 | Are the potential hauling routes acceptable to carry the loads of the construction equipment?
C-11 | Are there any deep excavations that require special site considerations?
C-11a | Sufficient ROW for staging?
C-12 | Will project create any long term maintenance issues?
C-13 | Is there any directional drilling required for drainage or ITS?
C-13a | Is there sufficient room for TDE and bore pit locations?
C-14a | Will the construction methods likely to be used impact the environment in a way that would need to be included in the permitting?
C-14b | Will this require barge work in an area with moratoriums or will the detour route cross a jurisdictional stream?
D | Structure Issues
D-1 | Does this project include any special provisions that would impact the construction means and methods?
D-2 | Is there a need, based on the permitting, for any cofferdams, submerged pumping, or specialized construction means?
D-3 | Does the structure consider an innovative approach - i.e. unusally long spans, special material, etc. ?
D-4 | Are there any materials that may require a long lead time or advanced delivery consideration?
D-5 | Is the structure subject to any historic preservation?
D-6 | Will barges be required for any reason during Construction?
D-7 | Will the project require a temporary structure?
D-8 | Will the structure be constructed adjacent or above traffic?
D-9 | Are as builts of the existing structure available?
D-10 | Do railroad or coast guard permits include the impacts of construction and not just the permanent structure?
D-11 | Does the project require structural remove over protected waterways, during certain times of the year, adjacent to OH utilities or any utilities?
D-12a | Does the structure cross any navigable waters requiring a FERC permit?
D-12b | Does the FERC regulated entity( i.e. power company) have any requirements?
D-13 | Is there sufficient access available to construct the bridges, sufficient room to stage cranes for construction, is top down construction required?
D-14 | Are there any in-water moratoriums that will extend the construction schedule?
D-15 | Are areas vailable for crane operations and their swing diameters?
D-16 | Does your structure include two of the following? Skew less than 75 degrees or more than 105 degrees, a vertical curve, transitionaing superelevation, or crown?
E | Right of Way (ROW)
E-1a | Have all ROW purchases and negotiations been made?
E-1b | Has this considered the construction impact (versus the permanent impact)?
E-1c | Will any negotiations not be complete prior to construction?
E-2a | Are there any complex relocations within proposed ROW?
E-2b | Does business relocations involve moving specialized equipment, very large equipment, or lengthy move times that would adversely disrupt the business?
E-3 | Are there any contaminated sites within the ROW that would require remediation?
E-4 | Are there any unusually high ROW estimates for property that may warrant a design change?
F | Unfamiliar Construction Practices
F-1a | Are there protected environmental species (flora or fauna) that need to be considered during construction?
F-1b | Will the clearing adversely impact wetlands?
F-1c | Or cause slope stabilization issues?
F-2 | Does the project require specialized disposal per the environmental permit??
F-3 | Is there anything that might require a specialized construction safety plan?
F-4a | Are there any moritoriums to consider?
F-4b | Are any ICTs (Intermediate Contract Times) needed for portions of the work?
F-5 | Are there any time restrictions for work to stop at (holidays, storm/hurricane season, etc.)
F-6 | Is noise ordinance (heavy equipment) respected (specific working hours)?
F-7 | Are sediment and erosion control devices designed and located correctly during different phases of construction?
G | Cost
G-1 | Construction cost of 10 Million Dollar Cost?
G-2 | Are all the utility costs known?
H | Utility Issues or Relocation
H-1a | Are utilities being done by others?
H-1b | Have they been scheduled?
H-1c | Will utilities be relocated prior to letting?
H-2 | If utilities will not be relocated before construction starts, has the phasing been included in the contract?
H-3a | Does any soil need to be removed from site due to contamination?
H-3b | Do the soil conditions require an unusual construction method?
H-4a | Is boring or drilling (trenchless technology) a part of the project?
H-4b | Has sufficient construction easement been included?
H-5a | Are utility relocations going to impact the construction?
H-5b | Are temporary utilities needed?
H-6 | Any close-by high voltage lines?
H-7 | Has sufficient construction easement been obtained for temporary work zone the is needed? Including traffic shifts, temporary bridges, temporary signage, etc.
H-8 | Have utility relocation plans been completed and is sufficient PUE shown to accommodate the relocation?
H-9 | Do utility owners need specialized equipment or permits to complete their work?
H-10a | Does project cross any power transmission easements/RW?
H-10b | Does plans meet utility owner's requirements regarding slopes, walls, excavation limits, etc.
H-11a | Does project cross any transcontinental gas lines?
H-11b | Can utility owner's conditions be satisfied regarding excavation, loading, etc.
H-13a | Do any wet utilities require complex or phased installation?
H-13b | Has this been accounted for in TMP?
H-14 | Will grading work need to be performed before water and sewer line relocation can occur?
H-15 | Does phasing need to consider delayed utility relocation? Can delays in relocation be mitigated through phasing?
Comments