## How to fill out the Worksheet
How to fill out the Cost Containment Worksheet
General
This worksheet will be used to record and review the Cost Containment recommendations. One worksheet can be used for each project and every recommendation developed for that project can be listed within the sheet.
Roles and Responsibilities
Project Design Teams develop cost containment recommendations and document on the form. Applicable disciplines can also provide comments on the Conceptual Review Coordination Tab.
Project Managers comments, decision and "sign off" in the Summary of Recommendation Review Section.
* Project Managers will also provide comments and "sign off" in Implementation Section once Rec. has been implemented.
Division Engineers provide comments and "sign off" in the Division Engineer Comment Section.
Project Detail/Description
Project Information should be provided here based on following. This information should be populated by the design team.
| STIP Number | Project STIP number
| Division | Division number, where the project is located
| County | County name where the project is located
| Let Date | Let date of the project
| Total Est. | Total estimated cost of project (including Construction, design, ROW, utility, etc.)
| Project Lead | Project Lead/Manager name
| Project Lead Email | Project Lead/Manager email
| Project Description | Brief explanation of the Project in more detail
Recommendation Description
Project recommendation will be provided here with extra information. This information should be populated by the design team.
| 1. Rec # | Identifier for each cost containment recommendation. This column should consist of a number. (1,2,3…)
| 2. Recommendation Type | Drop down to select between three options: CC (Cost Containment), PI (Project Improvement), and DC (Design Consideration)
- CC: Indicates the recommendation will provide cost savings for the project.
- PI: Indicates the recommendation may improve the project (safety, maintenance, construction, etc.).
- DC: Indicates the recommendation may identify a design discrepancy, constructability concern, risk, or other factor to be brought to attention of project design team and project manager.
| 3. Existing Condition | Current design of the project that relates to that specific recommendations
| 4. Recommendation Description | Provide a detailed explanation of the recommended cost savings. Additional documents can be added in new tabs.
| 5. Reference | Any reference that might be associated with the recommendation, such as link, Tab name, plan sheet number, detail, etc.
| 6. Applicable Discipline | Select the disciplines from the drop down that are most related (or should review) the recommendation. If applicable Disciplies does not exist, select other and write the name. Note:Multiple disciplines could be chosen.
Cost Analysis
Project cost analysis will provide more in depth information about the current cost estimate and potential savings that could be made by implementing the recommendation. Provide as many details as possible. This information should be populated by the design team.
| 1. Original | Current quantitiy and cost estimate related to what is currently designed.
| 2. VE Recommendation | Quantities and Costs of the specific recommendation
| 3. Saving | The total amount of savings if the recommendation were implemented into the project instead of the currently designed condition.
Recommendation Back-up
The "Recommendation Back-up" tab includes a table for showing derivations of the component quantities, which are then transferred into the cost estimate, and also includes a table for developing the cost estimate from itemized line items. Include construction, right-of-way and utilities costs (also include re-design costs if possible).
| Calculations Table | This table allows the design team to show how the quantities for each component of the estimate are derived. Complete the measurement quantities, and then add the formula that applies to that component in the "Area" or "Volume/Weight" column. Clearly indicate which items are "current design" line items and "recommended change" line items where needed. These entries can be revised as needed to fit the project features.
| Cost Estimate Table | Transfer the line items from the quantity derivations table to the cost estimate table, insert the unit cost using the current project cost estimate or NCDOT bid tabs. Apply the mark-up (revise the excel formula) based on whether they are roadway or structures line items; if you have both roadway and structures items and need to apply different markups then revise the spreadsheet as needed to derive different subtotals and apply separate mark-ups.
| Sketch | For recommendations requiring a sketch to clearly present the idea, insert this here. Sketches can be generated from snapshots of the current design documents, with additional content and descriptive notes added to clarify the intention.
*Check the formulas in Excel closely during a QC review of the worksheet to ensure costs are derived accurately
Conceptual Review Coordination
Conceptual Review is in different tab for more in depth analysis by subject matter experts who can provide their comments in this section. Each recommendation from the first tab should populate into this tab with a row for each reviewer to add their comments. Extra row could be added to each recommendation if necessary. This information should be populated by the Project Teams.
| 1. Applicable Discipline | Select your discipline from the drop down. If applicable discipline does not exist, select other and write the name. Each row should contain only one reviewers comments.
| 2. Name | Name of reviewer
| 3. Contact | Reviewer Email
| 4. Comments | An area for comments and analysis by subject matter experts who could be from project manager's team, consulting firm, etc.
Summary of Recommendation Review
This section is to be completed after review of recommendations and comments by project team. This information should be populated by the Project Manager.
| NC Project Manager/Lead | Typing your name in this block is your "sign off" that each idea has been vetted and you made the decisions for each recommendation. Note there is one total and not one per idea.
| 1. Decision | Drop down to select between three option as follow:
Accepted: The project manager agrees to implement the recommendation into the project.
Accepted as Modified: The project manager agrees to implement the recommendation with some modification.
Rejected: The project manager decides not to implement the recommendation into the project.
| 2. Comments | This is an area for the Project Manager to provide justification and reseanong for his/her decision regarding the recommendation.
Division Engineer Comments
This section is availble for Division Engineers to provide comments upon their review of the recommendations, comments and decision by the PM. This section should be filled out by Division Engineer.
| Division Engineer Name | By typing your name you are indicating that you reviewed the information for this worksheet.
| Comments | This is an area for Division Engineer to provide comments about the decision and recommendation.
Implementation Check
The implementation check occurs once the cost containment recommendation has been implemented into the project. This information should be populated by the Project Manager.
| 1. Decision | There is a drop down to select between two choices:
- Implemented: The recommendation has been implemented in the project
- Not Implemented: The recommendation has not been implemented in the project
| 2. Comments if Not Implemented | An area for the Project Manager to provide comments, argument and reseanong why the recommendation has not been implemented. This should only be filled in if the decision is different from the previous decision (i.e. accepted or accepted with modification that was not implemented.

## Recommendation Form
VA Worksheet |  |  | STIP Number:
|  | Project Details |  | Project Description
Division
County
Let Date
Total Est.
|  | Project Lead Name | [7 empty] | NCDOT Project Manager/Lead |  | Division Engineer Name | NCDOT Project Manager/Lead
Project Lead Email
`
| Recommendation Description | [5 empty] | Cost Analysis |  |  | Summary of Recommendation Review |  | Division Engineer Comments | Implementation Check
| Rec # | Recommendation Type | Existing Condition | Recommendation Description | Reference | Applicable Discipline | Original | VE Reccomendation | Savings | Decision | Comments | Comments | Decision | Comments if Not Implemented

## Rec# Backup
Recommendation #:
Calculations:
Component | Unit | EA | Beg Sta | End Sta | Length | Width | Depth | Area | Vol/Wt
Category Title
Insert calculations as appropriate for component being calculated
Category Title
Category Title
Cost Estimate
|  |  | Original |  | Recommendation
Component | Unit | $/Unit | Quantity | Total | Quantity | Total
Category
|  |  |  | 0 |  | 0
Category
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
Category
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
Subtotal |  |  |  | 0 |  | 0
X% Mark-up |  |  |  | 0 |  | 0 | Note: revise mark-up calculations based on if roadway or structures components
Total |  |  |  | 0 |  | 0 | Also, right-of-way costs may need to be added at the end if no ROW mark-up is desired.
Sketch
[Add sketch here if needed to clarify recommended change]

## Conceptual Review Coordination
Conceptual Review Coordination
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments
-
Recommendation | 0
Applicable Discipline | Name | Email | Comments