## MODEL
COST MODEL / DISTRIBUTION
TIP No. U-3318
Upgrade Main Street
Wake County, NC
|  | COST | % OF
| ITEM | $ | TOTAL
Steps to utilize cost model template
| RIGHT-OF-WAY | 5100000 | 26.58% | 0 | 1. Enter right-of-way costs directly in column C
| ASPHALT CONCRETE PAVING | 4847603.75 | 25.27% | 3039250 | 2. Include costs for other category totals in Column F
| EARTHWORK | 2380920.3 | 12.41% | 1492740 | 3. Revise formula in Column C cells to cover any mark-ups;
| GRASSING/EROSION CONTROL | 1507275 | 7.856% | 945000 | note, structures mark-ups may be different than roadway items
| DRAINAGE SYSTEM | 1201832.5 | 6.264% | 753500 | 4. Sort data on Column C and highlight top 80% of project costs
| BRIDGES | 1138500 | 5.934% | 900000 | 5. Revise notes at bottom of table regarding cost basis.
| CLEAR & GRUB | 843755 | 4.398% | 529000
| SIGNALS | 717750 | 3.741% | 450000
| CONCRETE MEDIANS | 472758 | 2.464% | 296400
| TRAFFIC CONTROL | 344679.5 | 1.797% | 216100
| CURB & GUTTER | 208530.3 | 1.087% | 130740
| SIGNAGE/MARKING | 169708 | 0.8846% | 106400
| GUARDRAILS | 113213.1 | 0.5901% | 70980
| FENCING | 110493.625 | 0.5759% | 69275
| CONCRETE SLABS/APRONS/MEDIANS | 28462.5 | 0.1484% | 22500
| PAVEMENT DEMOLITION | 0 | 0% | 0
| SOUND BARRIERS | 0 | 0% | 0
| SOD/LANDSCAPING | 0 | 0% | 0
| CONCRETE BARRIER | 0 | 0% | 0
| UTILITY RELOCATIONS | 0 | 0% | 0
| DEMOLITION | 0 | 0% | 0
| RETAINING WALLS | 0 | 0% | 0
| SIDEWALKS | 0 | 0% | 0
| *TOTAL - PROJECT | 19185481.575 | 100%
*Based on 10/3/18 construction estimate; ROW amount based on 10/3/18 ROW estimate
Shaded area represents 80% of project costs
X