## Ferry
[50 empty] | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74
| Reference / Comments |  |  | Basic Information | [8 empty] | Location | [25 empty] | Cost | [8 empty] | Details |  | 59: Data - Replacement; 68: Data - Expansion | Project Info
SPOT ID - to use for P8 | SPOT ID - initial | Ferry Div List ID | SPOT / Ferry Division Comments | Mode | TIP | Project Category | Route / Facility Name (or Project Name) | Location | Description | Specific Improvement Type | Primary Purpose | Comments / Notes | MPO(s) / RPO(s) | First MPO/RPO | First MPO/RPO % | Second MPO/RPO | Second MPO/RPO % | Third MPO/RPO | Third MPO/RPO % | Total MPO/RPO % (CHECK) | Division(s) | First Division | First Division % | Second Division | Second Division % | Third Division | Third Division % | Total Division % (CHECK) | County(ies) | First County | First County % | Second County | Second County % | Third County | Third County % | Fourth County | Fourth County % | Total County % (CHECK) | Source of Cost Estimation | ROW Cost [not needed] | Utilities Cost [not needed] | Construction Cost | Total Project Cost [CALC] | Other Funds - Source (1) | Other Funds - Amount (1) | Other Funds - Total Amount | Cost To NCDOT [CALC] | Included In Plans (Yes/No) | Name of Plans | 6-Year Planned and Corrective Maintenance Cost | Vessel plus Facility Cost | Useful Life (New) | Age | Usefule Life (Old) | Condition Score | Vessel Down Days, Missed Sailings, Used Capacity for the year | Days in the Year, Scheduled Sailings or Total Capacity |  | Demand at 85th Percentile | Total Vessel / Facility Capacity | Purchase Price | Usefule Life (New) | New Vehicle or Passenger Trips with Project in Place | Total Vehicle or Passenger Trips with Project in Place | Existing Capacity | P8 Submitter (Owner) | Carryover or Submittal | Original Submitter (first cycle) | Project Local ID
F130006 | F250801 | 57 | Changed SPOT ID Changed from Regional Impact to Division Needs (replacement vessel) | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | Replace a smaller Hatteras Class Vessel with a new and larger River Class vessel (MV Kinnakeet) | 6 - Expand Vehicle Vessel | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT Type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 17 | 30 | 35000000 | 30 | 19756.6667 | 79026.6667 | 158370 | Albemarle RPO | Submittal | Albemarle RPO
F130007 | F250796 | 52 | Changed SPOT ID | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | Replace a smaller Hatteras Class Vessel with a new and larger River Class vessel (MV Chicomicomico) | 6 - Expand Vehicle Vessel | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 25 | 30 | 35000000 | 30 | 9183.6667 | 36734.6667 | 48300 | Albemarle RPO | Submittal | Albemarle RPO
F130008 | F130008 | 53 |  | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | Replace a smaller Hatteras Class Vessel with a new and larger River Class vessel (MV Frisco) | 6 - Expand Vehicle Vessel | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT Type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 25 | 30 | 35000000 | 30 | 8005.3333 | 32021.3333 | 44100 | Albemarle RPO | Submittal | Division 1
F130012 | F250807 | 54 | Changed SPOT ID Changed from Regional Impact to Division Needs (replacement vessel) | Ferry |  | Division Needs | Currituck - Knotts Island | Currituck - Knotts Island route | Replace a smaller Hatteras Class Vessel with a new and larger River Class vessel (MV Hunt) | 6 - Expand Vehicle Vessel | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT Type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 9 | 30 | 35000000 | 30 | 5551.6667 | 22206.6667 | 58560 | Albemarle RPO | Submittal | Albemarle RPO
F150235 | F250414 | 40 | Changed SPOT ID | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport - Ft Fisher route | Additional River Class vessel | 6 - Expand Vehicle Vessel | Increase capacity and improve safety, mobility, and reliability. | P8 Notes. Ferry ID #40 on 9/15/2025. SIT 6. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 33 | 40 | 35000000 | 30 | 27600.3636 | 331204.3636 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F192296 | F192296 | 36 |  | Ferry |  | Regional Impact | Cherry Branch - Minnesott | Cherry Branch terminal | Replace the seawall and bulkhead at Cherry Branch | 4 - Replace Facility | Replacing the decrepit seawall and bulkhead will improve the safety of the structure and allow for safer operations of vessels as they traverse through the terminal |  | Down-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Capital Plan | 7500000 | 28000000 | 40 | 55 | 40 | 4 | 365 | 365 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Down East RPO | Submittal | Down East RPO (P6)
F192613 | F250798 | 25 | Changed SPOT ID | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Expand vessel basin at Hatteras | 8 - Expand Facility | Increase capacity, mobility, and reliability. Allow longer vessels to be docked. Larger vessels will increase the carrying capacity along the route. | SIT Type Expand Facility | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 4 | 2 | 13500000 | 40 | 182936.8 | 640278.8 | 1270034 | Albemarle RPO | Submittal | Albemarle RPO
F192621 | F250800 | 55 | Changed SPOT ID Changed from Regional Impact to Division Needs (replacement vessel) | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | Replace a smaller Hatteras Class Vessel with a new and larger River Class vessel (MV Ocracoke) | 6 - Expand Vehicle Vessel | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT Type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 25 | 30 | 35000000 | 30 | 6155.6667 | 24622.6667 | 31080 | Albemarle RPO | Submittal | Albemarle RPO
F192751 | F250370 | 31 | Changed SPOT ID | Ferry |  | Regional Impact | Manns Harbor Shipyard | Manns Harbor Shipyard | Synchrolift Refurbishment. Includes equipment upgrades, retrofits, and dredging. | 8 - Expand Facility | Refurbishment of the aging synchro-lift will increase reliability and ensure haul out capabilities. The synchro-lift at the Manns Harbor Shipyard is aging and needs replacement in order to be reliable and efficient in hauling out ferry vessels in order to perform needed corrective and preventative maintenance. |  | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO |  | 0 |  | 0 |  | 0 |  | 1 2 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 23 | 18 | TBD | 30 | 53384.05 | 209630.05 | 371600 | Division 1 | Submittal | TBD
F230645 | F230645 | 12 |  | Ferry |  | Division Needs | Southport - Ft Fisher | Southport - Ft Fisher route | Replace a River Class Vessel with a new River Class (MV Fort Fisher) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | P8 Notes. Ferry ID #12 on 9/15/2025. SIT 2. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | 1183730 | 30000000 | 30 | 25 | 30 | 1.8 | 27 | 3212 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Cape Fear RPO | Submittal | Cape Fear RPO
F230647 | F230647 | 11 |  | Ferry |  | Division Needs | Southport - Ft Fisher | Southport - Ft Fisher route | Replace a River Class Vessel with a new River Class (MV Southport) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | P8 Notes. Ferry ID #11 on 9/15/2025. SIT 2. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | 1357894 | 30000000 | 30 | 28 | 30 | 1.8 | 27 | 4148 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Cape Fear RPO | Submittal | Cape Fear RPO
F230648 | F230648 | 46 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport and Ft Fisher terminals | Replace and expand Operations Buildings / Visitor Centers at Southport and Fort Fisher | 8 - Expand Facility | Larger buildings will accommodate increased working area, offices, storage, and improve customer experience. | P8 Notes. Ferry ID #46 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 6355 | 4355 | 4448500 | 40 | 161579.3734 | 465183.3734 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F230649 | F230649 | 49 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport terminal | Additional (second) ramp at Southport | 8 - Expand Facility | Expand capacity to accommodate an additional vessel and provide redundancy along the route. | P8 Notes. Ferry ID #49 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2 | 1 | 18000000 | 40 | 333964.4 | 637568.4 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F230761 | F230761 | 50 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Ft Fisher terminal | Additional (second) ramp at Fort Fisher | 8 - Expand Facility | Expand capacity to accommodate an additional vessel and provide redundancy along the route. |  | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Cape Fear Moving Forward 2045 (Adopted in 2020) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2 | 1 | 18000000 | 40 | 333964.4 | 637568.4 | 554320 | Wilmington Urban Area MPO | Submittal | WMPO | F-22
F230763 | F230763 | (not in list) | Data still TBD | Ferry |  | Regional Impact | Southport - Ft Fisher | Ft Fisher terminal | Terminal improvement: install 5' sidewalk at Fort Fisher between ferry terminal building entrance and US 421 | TBD | Increase onsite pedestrian safety by providing separation between pedestrians, bicyclists, and vehicles. The East Coast Greenway alignment traverses the Cape Fear River via the Ft. Fisher to Southport Ferry Route. US 421 has dedicated bicycle lanes and proposed MUP. | P7 notes: Project is on ferry terminal property. Suggested by NCDOT Ferry staff and public - cyclists and pedestrians can and do access the ferry here. US 421 currently has dedicated bicycle lanes and an MUP is proposed and being studied through an NCDOT Feasibility Study grant. Ferry Div agreed to keep in Ferry scoring in P7 - was scored under "other infrastructure" SIT. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | Cape Fear Moving Forward 2045 (2020) |  |  | 39006 | [5 empty] | Y | Cape Fear Moving Forward 2045 (Adopted in 2020) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Wilmington Urban Area MPO | Submittal | WMPO | F-24
F231098 | F231098 | 56 | Changed from Regional Impact to Division Needs (replacement vessel) | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Southport - Ft Fisher route | Replace a smaller Hatteras Class Vessel with a new and larger River Class vessel (MV Cape Point) | 6 - Expand Vehicle Vessel | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 24 | 30 | 35000000 | 30 | 8853.3333 | 35413.3333 | 50670 | Albemarle RPO | Submittal | Albemarle RPO
F231100 | F250813 | 22 | Changed SPOT ID | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace Dorms 1 and 2 at Hatteras | 4 - Replace Facility | Replacing the aging dorms will provide safe, secure, and improved living conditions for employees working on shift. | SIT Type Replace Facility | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | 900000 | 14364000 | 30 | 28.5 | 30 | 3 | 8760 | 8760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F231101 | F250369 | 29 | Changed SPOT ID | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace and expand Operations Building / Visitor Center at Hatteras | 8 - Expand Facility | Provide safe, secure, and improved working conditions for employees working on shift. The operations building will also benefit the traveling public. |  | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 7603 | 6403 | 7603000 | 30 | 132949.0285 | 671678.0285 | 1270034 | Division 1 | Submittal | TBD
F231103 | F231103 | 1 |  | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Southport - Ft Fisher route | Replace a River Class Vessel with a new River Class (MV White) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | SIT type replace vehicle vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | 2389023 | 30000000 | 30 | 22 | 30 | 1.8 | 31 | 2553 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F231104 | F231104 | 2 |  | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Southport - Ft Fisher route | Replace a River Class Vessel with a new River Class (MV Croatoan) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | SIT type Replace Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | 2766607 | 30000000 | 30 | 21 | 30 | 1.8 | 21 | 2427 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F231105 | F231105 | 3 |  | Ferry |  | Division Needs | Hatteras - Ocracoke (South Dock) - vehicle | Southport - Ft Fisher route | Replace a River Class Vessel with a new River Class (MV Hatteras) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | 2390409 | 30000000 | 30 | 19 | 30 | 1.8 | 7 | 1935 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F231106 | Add 8 | 32 | Additional project entry | Ferry |  | Regional Impact | Manns Harbor Shipyard | Manns Harbor Shipyard | Replace and expand dorm facility at Manns Harbor Shipyard | 8 - Expand Facility | Increase capacity to provide modern and adequate lodging (single occupancy per room) and add administrative areas |  | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | [7 empty] | 1 2 3 | [28 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 6400 | 1599 | 4480000 | 40 | 4205372.2458 | 5518473.2458 | 3278334 | Division 2 | Submittal
F231109 | Add 4 | 15 | Additional project entry | Ferry |  | Regional Impact | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Support Vessel (Skyco) | 1 - Replace Support Vessel | Replacing the aging crane barge Skyco will ensure continued performance for piling, bulkhead, and ramp and gantry work at each Ferry terminal in the system. |  | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | [7 empty] | 1 2 3 | [28 empty] | 300462 | 40000000 | 40 | 16 | 40 | 1.9 | 387 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F231438 | F231438 | 39 |  | Ferry |  | Regional Impact | Aurora - Bayview | Aurora and Bayview terminals | Replace and expand Operations Building / Visitor Center at Bayview and Comfort Center at Aurora | 8 - Expand Facility | Increase office and operational space. | Submitted on behalf of the NCDOT Ferry Division. SIT has been changed to "1" per instructions. | Mid-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Capital Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 3660 | 3141 | 2379000 | 50 | 16197.851 | 88672.851 | 332940 | Mid-East RPO | Submittal | Mid-East RPO
F231469 | F231469 | 10 |  | Ferry |  | Division Needs | Aurora - Bayview | Aurora - Bayview route | Replace a River Class Vessel with a new River Class (MV Russell) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | Submitted on behalf of the NCDOT Ferry Division. SIT has been changed to "1" per instructions. | Mid-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Capital Plan | 1098182 | 30000000 | 30 | 33 | 30 | 1.8 | 104 | 4326 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Mid-East RPO | Submittal | Mid-East RPO
F231610 | F231610 | 9 |  | Ferry |  | Division Needs | Cherry Branch - Minnesott | Cherry Branch - Minnesott route | Replace a River Class Vessel with a new River Class (MV Lupton) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Down-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Long Range Plan | 1948717 | 30000000 | 30 | 25 | 30 | 3 | 46 | 3887 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Down East RPO | Submittal | Down East RPO
F231612 | F231612 | 8 |  | Ferry |  | Division Needs | Cherry Branch - Minnesott | Cherry Branch - Minnesott route | Replace a River Class Vessel with a new River Class (MV Neuse) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Down-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | 1355219 | 30000000 | 30 | 27 | 30 | 1.8 | 62 | 7144 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Down East RPO | Submittal | Down East RPO
F231623 | F231623 | 37 |  | Ferry |  | Regional Impact | Cherry Branch - Minnesott | Cherry Branch terminal | Replace and expand Maintenance Building at Cherry Branch | 8 - Expand Facility | Larger building will accommodate increased working area, offices, storage, and repair equipment. |  | Down-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Capital Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 8500 | 10000 | 6000000 | 40 | TBD | 286343 | 377449 | Down East RPO | Submittal | Down East RPO
F231633 | F231633 | 30 |  | Ferry |  | Regional Impact | Cedar Island - Ocracoke (Silver Lake) | Cedar Island - Ocracoke (Silver Lake) route | Additional Sound Class vessel | 6 - Expand Vehicle Vessel | Increase capacity and improve safety, mobility, and reliability. |  | Albemarle Down-East |  | 0 |  | 0 |  | 0 |  | 1 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Capital Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 33 | 50 | 40000000 | 30 | 31249.2 | 187495.2 | 371600 | Division 1 | Submittal | Down East RPO
F231635 | Add 1 | 4 | Additional project entry | Ferry |  | Division Needs | Cedar Island - Ocracoke (Silver Lake) | Cedar Island - Ocracoke (Silver Lake) route | Replace a Sound Class Vessel with a new Sound Class (MV Cedar Island) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Albemarle Down-East | [7 empty] | 1 2 | [28 empty] | 3152645 | 60000000 | 30 | 30 | 30 | 1.8 | 15 | 1113 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F231639 | Add 3 | 7 | Additional project entry | Ferry |  | Division Needs | Cedar Island - Ocracoke (Silver Lake) | Cedar Island - Ocracoke (Silver Lake) route | Replace a Sound Class Vessel with a new Sound Class (MV Carteret) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | F231639 (P7), F130014 (P5/P6) | Albemarle Down-East | [7 empty] | 1 2 | [28 empty] | 3176435 | 60000000 | 30 | 37 | 30 | 1.8 | 24 | 898 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F231640 | F250817 | 5 | Changed SPOT ID | Ferry |  | Division Needs | Swan Quarter - Ocracoke (Silver Lake) | Swan Quarter - Ocracoke (Silver Lake) route | Replace a Sound Class Vessel with a new Sound Class (MV Swan Quarter) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. | SIT Type Replace Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | 2931283 | 60000000 | 30 | 13 | 30 | 1.8 | 14 | 787 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F231641 | Add 2 | 6 | Additional project entry | Ferry |  | Division Needs | Cedar Island - Ocracoke (Silver Lake) | Cedar Island - Ocracoke (Silver Lake) route | Replace a Sound Class Vessel with a new Sound Class (MV Sea Level) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Albemarle Down-East | [7 empty] | 1 2 | [28 empty] | 3045561 | 60000000 | 30 | 13 | 30 | 1.8 | 28 | 777 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F231829 | F231829 | 33 |  | Ferry |  | Regional Impact | Cedar Island - Ocracoke (Silver Lake) | Cedar Island terminal | Replace and expand Maintenance Building and Operations Building / Visitor Center at Cedar Island | 8 - Expand Facility | Larger building will accommodate increased working area, offices, storage, and repair equipment. |  | Albemarle Down-East |  | 0 |  | 0 |  | 0 |  | 1 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Capital Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 8505 | 7105 | 6378750 | 40 | 21294.1552 | 104184.1552 | 184750 | Down East RPO | Submittal | Down East RPO | F192296
F250358 | F250358 | 26 |  | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace and expand Dorms 1 and 2 at Hatteras | 8 - Expand Facility | Replacing the aging dorms will provide safe, secure, and improved living conditions for employees working on shift. |  | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 34 | 24 | 7182000 | 30 | 262630.3875 | 262630.3875 | 1270034 | Division 1 | Submittal | Division 1
F250367 | F250367 | 27 |  | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace and expand Dorm 1 at Hatteras | 8 - Expand Facility | Replacing the aging dorm will provide safe, secure, and improved living conditions for employees working on shift. |  | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 17 | 12 | 3591000 | 30 | 131315.1938 | 131315.1938 | 1270034 | Division 1 | Submittal | TBD
F250368 | F250368 | 28 |  | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace and expand Dorm 2 at Hatteras | 8 - Expand Facility | Replacing the aging dorm will provide safe, secure, and improved living conditions for employees working on shift. |  | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 17 | 12 | 3591000 | 30 | 131315.1938 | 131315.1938 | 1270034 | Division 1 | Submittal | TBD
F250371 | F250371 | 59 | DELETE - DUPLICATE | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | DELETE Expand and Replace MV Croatoan |  | Replacing the aging vessel will increase capacity, safety, mobility, and reliability |  | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N | [17 empty] | Division 1 | Submittal | TBD
F250411 | F250411 | 47 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport - Ft Fisher route | Replace and expand Operations Building / Visitor Center at Southport | 8 - Expand Facility | Increase office and operational space. | P8 Notes. Ferry ID #47 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 4380 | 3380 | 3066000 | 40 | 109495.0521 | 413099.0521 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F250415 | F250415 | 41 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport - Ft Fisher route and terminals | Additional River Class vessel, additional (second) ramps at Southport and Fort Fisher, and replace/expand dorm at Southport | 6 - Expand Vehicle Vessel | Increase passenger carrying capacity and increase housing for employees to support additional operations. | P8 Notes. Ferry ID #41 on 9/15/2025. SIT 6. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 33 | 40 | 74591000 | 34.69 | 28980.3818 | 332584.3818 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F250416 | F250416 | 42 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport - Ft Fisher route and Southport terminal | Additional River Class vessel and additional (second) ramp at Southport | 6 - Expand Vehicle Vessel | Increase passenger carrying capacity. | P8 Notes. Ferry ID #42 on 9/15/2025. SIT 6. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 33 | 40 | 53000000 | 33.3333 | 28980.3818 | 332584.3818 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F250418 | F250418 | 44 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport - Ft Fisher route and Southport terminal | Additional River Class vessel, additional (second) ramp at Southport, and replace/expand dorm at Southport | 6 - Expand Vehicle Vessel | Increase passenger carrying capacity and increase housing for employees to support additional operations. | P8 Notes. Ferry ID #44 on 9/15/2025. SIT 6. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 33 | 40 | 56591000 | 33.81 | 28980.3818 | 332584.3818 | 554320 | Cape Fear RPO | Submittal | Cape
F250420 | F250420 | 48 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Ft Fisher terminal | Replace and expand Operations Building / Visitor Center at Fort Fisher | 8 - Expand Facility | Increase office and operational space. | P8 Notes. Ferry ID #48 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 1975 | 975 | 1382500 | 40 | 342138.3538 | 645742.3538 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F250422 | F250422 | 51 |  | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport and Ft Fisher terminals | Additional (second) ramps at Southport and Fort Fisher | 8 - Expand Facility | Expand capacity to accommodate an additional vessel and provide redundancy along the route. | P8 Notes. Ferry ID #51 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 4 | 2 | 36000000 | 40 | 333964.4 | 637568.4 | 554320 | Cape Fear RPO | Submittal | Cape Fear RPO
F250423 | F250423 | 61 | DELETE - DUPLICATE | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport-Ft. Fisher Ferry Route | DELETE Expand River Class Ferry, Ramps in 2 Localtions, and Dorms |  | Construct a new and addition river class vessel at Southport, build second ramps at Southport and Fort Fisher to increase passenger carrying capacity, and build a larger dorm at Southport to increase housing for employees to support additional operations. | P8 Notes. Ferry ID #61 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | #N/A |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | [16 empty] | Cape Fear RPO | Submittal | Cape Fear RPO
F250425 | F250425 | 62 | DELETE - DUPLICATE | Ferry |  | Regional Impact | Southport - Ft Fisher | Southport-Ft. Fisher Ferry Route | DELETE Expand River Class Ferry, Ramp, and Dorm at Southport |  | Construct a new and additional river class vessel at Southport, build a second ramp at Southport to increase passenger carrying capacity, and build a larger dorm to increase housing for employees to support additional operations. | P8 Notes. Ferry ID #62 on 9/15/2025. SIT 8. | Wilmington MPO Cape Fear |  | 0 |  | 0 |  | 0 |  | #N/A |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Long Range Plan | [16 empty] | Cape Fear RPO | Submittal | Cape Fear RPO
F250451 | F250451 | 17 |  | Ferry |  | Division Needs | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Tug Vessel (Wanchese) | 1 - Replace Support Vessel | Enhance operational capability, ensure continued reliability and efficiency, improve safety, and maintain essential harbor and towing services for maritime operations. | While the 2024 Ferry Vessel Replacement Plan document is not publicly available, the 2024 Ferry Division Maintenance Capacity Study indicates that the vessel replacement plan is currently underway. Therefore, the Wanchese tug replacement project is recognized in NCDOT's planning documents and is actively being addressed in the ongoing vessel replacement plan. | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO |  | 0 |  | 0 |  | 0 |  | 1 2 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Maintenance Capacity Study (2024) | 213148 | 5646459 | 40 | 4 | 40 | 1.1 | 418 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 1 | Submittal | Division 3
F250453 | F250453 | 20 |  | Ferry |  | Division Needs | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Tug Vessel (Hobucken) | 1 - Replace Support Vessel | Ensure safe, reliable ferry operations by reducing maintenance demands on aging vessels, supporting compliance with USCG standards, and enhancing operational efficiency. The new vessel aligns with long-term fleet modernization, eases stress on limited Manns Harbor resources, and sustains essential movement of goods, services, and people around the Outer Banks. | Please note that the location of this project is noted for Manns Harbor Shipyard, which is located within NCDOT Division 1, but NCDOT Ferry Division directed this project to be submitted by NCDOT Division "3". While the 2024 Ferry Vessel Replacement Plan document is not publicly available, the 2024 Ferry Division Maintenance Capacity Study indicates that the vessel replacement plan is currently underway. Therefore, the Wanchese tug replacement project is recognized in NCDOT's planning documents and is actively being addressed in the ongoing vessel replacement plan. | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO |  | 0 |  | 0 |  | 0 |  | 1 2 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | NCDOT Ferry Division Maintenance (2024) | 55466 | 1684280 | 40 | 4 | 40 | 1.1 | 9 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 1 | Submittal | Division 3
F250454 | F250454 | 21 |  | Ferry |  | Division Needs | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Tug Vessel (Manns Harbor) | 1 - Replace Support Vessel | Ensure safe, reliable ferry operations by reducing maintenance demands on aging vessels, supporting compliance with USCG standards, and enhancing operational efficiency. The new vessel aligns with long-term fleet modernization, eases stress on limited Manns Harbor resources, and sustains essential movement of goods, services, and people around the Outer Banks. | Please note that the location of this project is noted for Manns Harbor Shipyard, which is located within NCDOT Division 1, but NCDOT Ferry Division directed this project to be submitted by NCDOT Division "3". While the 2024 Ferry Vessel Replacement Plan document is not publicly available, the 2024 Ferry Division Maintenance Capacity Study indicates that the vessel replacement plan is currently underway. Therefore, the Manns Harbor tug replacement project is recognized in NCDOT's planning documents and is actively being addressed in the ongoing vessel replacement plan. | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO |  | 0 |  | 0 |  | 0 |  | 1 2 3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Maintenance Capacity Study (2024) | 4775 | 1684280 | 40 | 4 | 40 | 1.1 | 3 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 1 | Submittal | Division 3
F250646 | F250646 | 13 |  | Ferry |  | Division Needs | Cherry Branch - Minnesott | Cherry Branch - Minnesott route | Replace a River Class Vessel with a new River Class (MV Avon) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Down-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division | 722400 | 30000000 | 30 | 2 | 30 | 1 | 31 | 2097 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Down East RPO | Submittal | Down East RPO
F250648 | F250648 | 14 |  | Ferry |  | Division Needs | Cherry Branch - Minnesott | Cherry Branch - Minnesott route | Replace a River Class Vessel with a new River Class (MV Salvo) | 2 - Replace Vehicle Vessel | Replacing the aging vessel will improve safety, mobility, and reliability. |  | Down-East |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Plan | 1030381 | 30000000 | 30 | 2 | 30 | 1 | 152 | 2588 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Down East RPO | Submittal | Down East RPO
F250649 | F250649 | 34 |  | Ferry |  | Regional Impact | Cedar Island - Ocracoke (Silver Lake) | Cedar Island terminal | Replace and expand Maintenance Building at Cedar Island | 8 - Expand Facility | Increase capacity |  | Albemarle Down-East |  | 0 |  | 0 |  | 0 |  | 1 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Capital Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 3638 | 2938 | 2728500 | 40 | 24881.1065 | 107771.1065 | 184750 | Down East RPO | Submittal | Down East RPO
F250650 | F250650 | 35 |  | Ferry |  | Regional Impact | Cedar Island - Ocracoke (Silver Lake) | Cedar Island terminal | Replace and expand Operations Building / Visitor Center at Cedar Island | 8 - Expand Facility | Increase operational capacity |  | Albemarle Down-East |  | 0 |  | 0 |  | 0 |  | 1 2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | Y | Ferry Division Capital Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 4867 | 4167 | 3650250 | 40 | 18765.1263 | 101655.1263 | 184750 | Down East RPO | Submittal | Down East RPO
F250809 | F250809 | 24 |  | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace Dorm 2 at Hatteras | 4 - Replace Facility | Replacing the aging dorm will provide safe, secure, and improved living conditions for employees working on shift. | SIT Type Replace Facility | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | 425000 | 7182000 | 30 | 26 | 30 | 3 | 4380 | 4380 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F250811 | F250811 | 23 |  | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras terminal | Replace Dorm 1 at Hatteras | 4 - Replace Facility | Replacing the aging dorm will provide safe, secure, and improved living conditions for employees working on shift. | SIT type Replace Facility | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N |  | 475000 | 7182000 | 30 | 31 | 30 | 3 | 6205 | 6205 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Albemarle RPO | Submittal | Albemarle RPO
F250822 | F250822 | 60 | DELETE - DUPLICATE | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | DELETE Replace and expand a River Class vessel (MV Hatteras) for a new River Class vessel |  | Replacing the aging vessel will increase capacity, safety, mobility, and reliability | SIT Type Expand Vehicle Vessel | Albemarle |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | N | [17 empty] | Albemarle RPO | Submittal | Albemarle RPO
F251115 | Add 5 | 16 | Additional project entry | Ferry |  | Regional Impact | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Dredge (Manteo) | 1 - Replace Support Vessel | TBD |  | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | [7 empty] | 1 2 3 | [28 empty] | 374731 | 7909095 | 40 | 9 | 40 | 1.7 | 443 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F251117 | Add 6 | 18 | Additional project entry | Ferry |  | Regional Impact | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Tug Vessel (Morehead City) | 1 - Replace Support Vessel | Ensure safe, reliable ferry operations by reducing maintenance demands on aging vessels, supporting compliance with USCG standards, and enhancing operational efficiency. The new vessel aligns with long-term fleet modernization, eases stress on limited Manns Harbor resources, and sustains essential movement of goods, services, and people around the Outer Banks. |  | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | [7 empty] | 1 2 3 | [28 empty] | 22426 | 1684276 | 40 | 4 | 40 | 1.1 | 78 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F251118 | Add 7 | 19 | Additional project entry | Ferry |  | Regional Impact | Statewide: Support Vessel | Manns Harbor Shipyard | Replace Tug Vessel (Cape Fear) | 1 - Replace Support Vessel | Ensure safe, reliable ferry operations by reducing maintenance demands on aging vessels, supporting compliance with USCG standards, and enhancing operational efficiency. The new vessel aligns with long-term fleet modernization, eases stress on limited Manns Harbor resources, and sustains essential movement of goods, services, and people around the Outer Banks. |  | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | [7 empty] | 1 2 3 | [28 empty] | 17069 | 1684280 | 40 | 4 | 40 | 1.1 | 110 | 2190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Division 2 | Submittal
F251120 | Add 9 | 38 | Additional project entry | Ferry |  | Regional Impact | Aurora - Bayview | Bayview terminal | Replace and expand Operations Building / Visitor Center at Bayview | 8 - Expand Facility | Increase office and operational space. |  | Mid-East | [7 empty] | 2 | [28 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 3000 | 2581 | 1950000 | 50 | 15977.6346 | 88452.6346 | 332940 | Division 2 | Submittal
N/A | Add 10 | 58 | DELETE - DUPLICATE | Ferry |  | Regional Impact | Hatteras - Ocracoke (South Dock) - vehicle | Hatteras - Ocracoke (South Dock) route | DELETE Replace and expand a River Class vessel (MV White) for a new River Class vessel |  | Replacing the aging vessel will increase capacity, safety, mobility, and reliability |  | Albemarle | [7 empty] | 1
Note on AV3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only CON - not using ROW + UTL
Note on AZ3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assuming no Other Funds used
Note on N38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (single occupancy per room)

## Sheet1
1 | 1 - Replace Support Vessel
2 | 2 - Replace Vehicle Vessel
3 | 3 - Replace Passenger Vessel
4 | 4 - Replace Facility
5 | 5 - Expand Support Vessel
6 | 6 - Expand Vehicle Vessel
7 | 7 - Expand Passenger Vessel
8 | 8 - Expand Facility

## Ferry Div List
NCDOT Ferry Division Prioritization 8 Projects
ID | SPOT ID | Submitted? | Title | Route | Description | Project Type | SIT | MPO | RPO | Combined PO | Division | Regional or Division | Assigned Submitter | Comments | Ferry Div List ID | SIT | Submission Level
1 | F231103 | 1 | Replace MV White Vessel | Hatteras/Ocracoke | Replace a River Class Vessel - MV White with a River Class | Replace Vehicle Vessel | 2 |  | Albemarle | Albemarle | 1 | Division | Albemarle |  | 1 | 1 | Regional
2 | F231104 | 1 | Replace MV Croatoan Vessel | Hatteras/Ocracoke | Replace a River Class Vessel - MV Croatoan with a River Class | Replace Vehicle Vessel | 2 |  | Albemarle | Albemarle | 1 | Division | Albemarle |  | 2 | 2 | Division
3 | F231105 | 1 | Replace MV Hatteras Vessel | Hatteras/Ocracoke | Replace a River Class Vessel - MV Hatteras with a River Class | Replace Vehicle Vessel | 2 |  | Albemarle | Albemarle | 1 | Division | Albemarle |  | 3 | 3 | Regional
4 | F231635 | Confirmed - not submitted | Replace MV Cedar Island Vessel | Cedar Island/Ocracoke | Replace a Sound Class Vessel - MV Cedar Island with a Sound Class | Replace Vehicle Vessel | 2 |  | Down-East Albemarle | Down-East Albemarle | 1 2 | Division | 2 |  | 4 | 4 | Division
5 | F231640 | 1 | Replace MV Swan Quarter | Swan Quarter/Ocracoke | Replace a Sound Class Vessel - MV Swan Quarter with a Sound Class | Replace Vehicle Vessel | 2 |  | Albemarle | Albemarle | 1 | Division | Albemarle |  | 5 | 5 | Regional
6 | F231641 | Confirmed - not submitted | Replace MV Sea Level Vessl | Cedar Island/Ocracoke | Replace a Sound Class Vessel - MV Sea Level with a Sound Class | Replace Vehicle Vessel | 2 |  | Down-East Albemarle | Down-East Albemarle | 1 2 | Division | 2 |  | 6 | 6 | Regional
7 | F231639 | Confirmed - not submitted | Replace MV Carteret Vessl | Cedar Island/Ocracoke | Replace a Sound Class Vessel - MV Carteret with a Sound Class | Replace Vehicle Vessel | 2 |  | Down-East Albemarle | Down-East Albemarle | 1 2 | Division | 2 |  | 7 | 7 | Regional
8 | F231612 | 1 | Replace MV Neuse Vessel | Cherry Branch/Minnesott Beach | Replace a River Class Vessel - MV Neuse with a River Class | Replace Vehicle Vessel | 2 |  | Down-East | Down-East | 2 | Division | Down-East |  | 8 | 8 | Regional
9 | F231610 | 1 | Replace MV Lupton Vessel | Cherry Branch/Minnesott Beach | Replace a River Class Vessel - MV Lupton with a River Class | Replace Vehicle Vessel | 2 |  | Down-East | Down-East | 2 | Division | Down-East |  | 9
10 | F231469 | 1 | Replace MV Russell Vessel | Bayview/Aurora | Replace a River Class Vessel - MV Russell with a River Class | Replace Vehicle Vessel | 2 |  | Mid-East | Mid-East | 2 | Division | Mid-East |  | 10
11 | F230647 | 1 | Replace MV Southport Vessel | Southport/Fort Fisher | Replace a River Class Vessel - MV Southport with a River Class | Replace Vehicle Vessel | 2 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Division | Cape Fear |  | 11
12 | F230645 | 1 | Replace MV Fort Fisher Vessel | Southport/Fort Fisher | Replace a River Class Vessel - MV Fort Fisher with a River Class | Replace Vehicle Vessel | 2 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Division | Cape Fear |  | 12
13 | F250646 | 1 | Replace MV Avon Vessel | Cherry Branch/Minnesott Beach | Replace a River Class Vessel - MV Avon with a River Class | Replace Vehicle Vessel | 2 |  | Down-East | Down-East | 2 | Division | Down-East |  | 13
14 | F250648 | 1 | Replace MV Salvo Vessel | Cherry Branch/Minnesott Beach | Replace a River Class Vessel - MV Salvo with a River Class | Replace Vehicle Vessel | 2 |  | Down-East | Down-East | 2 | Division | Down-East |  | 14
15 | F231109 | Confirmed - not submitted | Replace Skyco Support Vessel | Manns Harbor Shipyard | Replace a Support Vessel - Skyco | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 3 |  | 15
16 |  | Confirmed - not submitted | Replace Manteo Dredge | Manns Harbor Shipyard | Replace Dredge Manteo | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 2 |  | 16
17 | F250451 | 1 | Replace Wanchese Tug | Manns Harbor Shipyard | Replace Tug Vessel Wanchese | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 | Regional | 3 |  | 17
18 |  | Confirmed - not submitted | Replace Morehead City Tug | Manns Harbor Shipyard | Replace Tug Vessel Morehead City | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 2 |  | 18
19 |  | Confirmed - not submitted | Replace Cape Fear Tug | Manns Harbor Shipyard | Replace Tug Cape Fear | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 2 |  | 19
20 | F250453 | 1 | Replace Hobucken Tug | Manns Harbor Shipyard | Replace Tug Hobucken | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 | Regional | 3 |  | 20
21 | F250454 | 1 | Replace Manns Harbor Tug | Manns Harbor Shipyard | Replace Tug Manns Harbor | Replace Support Vessel | 1 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 3 |  | 21
22 | F231100 | 1 | Replace Hatteras Dorms 1&2 | Hatteras/Ocracoke | Replacing the aging dorms (Dorm 1 & 2) at the Hatteras Ferry terminal to provide safe, secure, and improved living conditions for employees working on shift. | Replace Facility | 4 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 22
23 | F250811 | 1 | Replace Hatteras Dorm 1 | Hatteras/Ocracoke | Replacing of Dorm 1 at the Hatteras Ferry terminal to provide safe, secure, and improved living conditions for employees working on shift. | Replace Facility | 4 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 23
24 | F250809 | 1 | Replace Hatteras Dorm 2 | Hatteras/Ocracoke | Replacing of Dorm 2 at the Hatteras Ferry terminal to provide safe, secure, and improved living conditions for employees working on shift. | Replace Facility | 4 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 24
25 | F192613 | 1 | Expand Hatteras Dock Capacity (is this same as P7 basin project?) | Hatteras/Ocracoke | Expanding the docking capacity of the Hatteras Ferry Terminal to allow longer vessels to be docked. Larger vessel will increase the carrying capacity along the route | Expand Facility | 8 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 25
26 | F250358 | 1 | Expand and Replace Dorms 1&2 at Hatteras | Hatteras/Ocracoke | Replacing the aging dorms (Dorm 1 & 2) at the Hatteras Ferry terminal to provide safe, secure, and improved living conditions for employees working on shift. This may include expansion of existing. | Expand Facility | 8 |  | Albemarle | Albemarle | 1 | Regional | 1 |  | 26
27 | F250367 | 1 | Expand and Replace Dorm 1 at Hatteras | Hatteras/Ocracoke | Replacing of Dorm 1 at the Hatteras Ferry terminal to provide safe, secure, and improved living conditions for employees working on shift. This may include expansion of existing. | Expand Facility | 8 |  | Albemarle | Albemarle | 1 | Regional | 1 |  | 27
28 | F250368 | 1 | Expand and Replace Dorm 2 at Hatteras | Hatteras/Ocracoke | Replacing of Dorm 2 at the Hatteras Ferry terminal to provide safe, secure, and improved living conditions for employees working on shift. This may include expansion of existing. | Expand Facility | 8 |  | Albemarle | Albemarle | 1 | Regional | 1 |  | 28
29 | F231101 | 1 | Expand and Replace Facilities at Hatteras Terminal | Hatteras/Ocracoke | Replacing the aging facilities at the Hatteras Ferry terminal to provide safe, secure, and improved working conditions for employees working on shift. The operations building will also benefit the traveling public. This may include expansion of existing. | Expand Facility | 8 |  | Albemarle | Albemarle | 1 | Regional | 1 |  | 29
30 | F231633 | 1 | Expand Sound Class Ferry | Cedar Island/Swan Quarter/Ocracoke | Additional Sound Class vesssel to increase capacity and improve safety, mobility, and reliability. | Expand Vehicle Vessel | 6 |  | Albemarle Down-East | Albemarle Down-East | 1 2 | Regional | 3 |  | 30
31 | F192751 | 1 | Synchrolift Refurbishment (replacement in P7) | Manns Harbor Shipyard | Refurbishment of the aging synchro-Lift to increase reliability and ensure haul out capabilities. To include equipment upgrades, retrofits, and dredging | Expand Facility | 8 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 1 | Is this a replacement or expansion project? | 31
32 | F231106 | Confirmed - not submitted | Expand/New Dormitory at Manns Harbor | Manns Harbor Shipyard | Construction of a dorm facility at the Manns Harbor Shipyard | Expand Facility | 8 | Wilmington MPO | Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | Wilmington MPO Albemarle RPO Down-East RPO Mid-East RPO Cape Fear RPO | 1 2 3 | Regional | 2 |  | 32
33 | F231829 | 1 | Expand Cedar Island Maintenance and Visitor Facilities | Cedar Island/Ocracoke | Replace Cedar Island Maintenance Building and Visitor Center to increase capacity | Expand Facility | 8 |  | Albemarle Down-East | Albemarle Down-East | 1 2 | Regional | Down-East |  | 33
34 | F250649 | 1 | Expand Cedar Island Maintenance Facility | Cedar Island/Ocracoke | Replace Cedar Island Maintenance Building to increase capacity |  | 8 |  | Albemarle Down-East | Albemarle Down-East | 1 2 | Regional | Down-East |  | 34
35 | F250650 | 1 | Increase capacity at Cedar Island Visitor Center | Cedar Island/Ocracoke | Replace Cedar Island Visitor Center to increase operational capacity | Expand Facility | 8 |  | Down-East | Down-East | 2 | Regional | Down-East |  | 35
36 | F192296 | 1 | Replace Cherry Branch Seawall | Cherry Branch/Minnesott Beach | Project will be to replace the decrepit seawall at the Cherry Branch Ferry terminal. This will improve the safety of the structure and allow for safer operations of vessels as they traverse through the terminal | Replace Facility | 4 |  | Down-East | Down-East | 2 | Regional | Down-East |  | 36
37 | F231623 | 1 | Replace and Expand Cherry Branch Maintenance Facility | Cherry Branch/Minnesott Beach | Project will be to replace the existing maintenance Cherry Branch facility for a new building that is larger to accommodate increased working area, offices, storage, and repair equipment | Expand Facility | 8 |  | Down-East | Down-East | 2 | Regional | Down-East |  | 37
38 | NEEDS NEW | Confirmed - not submitted (1/21) | Replace and Expand Bayview Operations Facilities (not duplicate, but mixed up - need to figure out - only one was submitted) | Bayview/Aurora | Replace Bayview Operations Buildings / Comfort Centers to increase office and operational space | Expand Facility | 8 |  | Mid-East | Mid-East | 2 | Regional | Mid-East |  | 38
39 | F231438 | 1 | Replace and Expand Bayview and Aurora Operations Facilities (duplicate of what?) | Bayview/Aurora | Replace Bayview and Aurora Operations Buildings / Comfort Centers to increase office and operational space | Expand Facility | 8 |  | Mid-East | Mid-East | 2 | Regional | Mid-East | Duplicate. Instead, split into separate projects? | 39
40 | F150235 | 1 | Expand River Class Ferry | Southport/Fort Fisher | Project will be to construct a new and additional River Class vessel, resulting in an increase of capacity, at the Southport - Fort Fisher route. | Expand Vehicle Vessel | 6 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Wilmington |  | 40
41 | F250415 | 1 | Expand River Class Ferry, Ramp, and Dorms at Southport and Fort Fisher | Southport/Fort Fisher | Construct a new and addition river class vessel at Southport, build second ramps at Southport and Fort Fisher to increase passenger carrying capacity, and build a larger dorm at Southport to increase housing for employees to support additional operations | Expand Vehicle Vessel | 6 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Wilmington |  | 41
42 | F250416 | 1 | Expand River Class Ferry and Ramp | Southport/Fort Fisher | Construct a new and additional river class vessel at Southport and to build a second ramp to increase passenger carrying capacity | Expand Vehicle Vessel | 6 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Cape Fear |  | 42
44 | F250418 | 1 | Expand River Class Ferry, Ramp, and Dorm at Southport | Southport/Fort Fisher | Construct a new and addition river class vessel at Southport, build a second ramp at Southport to increase passenger carrying capacity, and build a larger dorm to increase housing for employees to support additional operations | Expand Vehicle Vessel | 6 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Cape Fear |  | 44
46 | F230648 | 1 | Replace and Expand Southport and Fort Fisher Visitor Centers | Southport/Fort Fisher | Replace the aging Southport & Fort Fisher Visitor Center to increase office and operational space | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Cape Fear |  | 46
47 | F250411 | 1 | Replace and Expand Southport Visitor Center (was listed as F230648 a second time in this doc but incorrect - that one is both locations) | Southport/Fort Fisher | Replace the Southport Visit Center to increase office and operational space | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | 3 |  | 47
48 | F250420 | 1 | Replace and Expand Fort Fisher Visitor Center | Southport/Fort Fisher | Replace the Fort Fisher Visitor Center to increase office and operational space | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Wilmington |  | 48
49 | F230649 | 1 | Expand Ramp and Gantry at Southport | Southport/Fort Fisher | Additional Ramp and Gantry system at Southport to expand capacity | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | 3 |  | 49
50 | F230761 | 1 | Expand Ramp and Gantry at Fort Fisher | Southport/Fort Fisher | Additional Ramp and Gantry system at Fort Fisher to expand capacity | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Wilmington |  | 50
51 | F250422 | 1 | Expand Ramp and Gantry at Southport and Fort Fisher | Southport/Fort Fisher | Additional ramps at Southport and Fort Fisher to increase capacity | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Wilmington |  | 51
52 | F130007 | 1 | Expand and Replace MV Chiconicomico Ferry | Hatteras/Ocracoke | This project will replace the aging and smaller Hatteras Class vessel (M/V Chicomicomico) with a new and larger River Class Ferry. This project will increase safety, capacity, mobility, and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 52
53 | F130008 | 1 | Expand and Replace MV Frisco Ferry | Hatteras/Ocracoke | This project will replace the aging and smaller Hatteras Class vessel (M/V Frisco) with new a larger River Class vessel that will increase safety, reliability, capacity, and mobility | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 53
54 | F130012 | 1 | Expand and Replace MV Hunt Ferry | Currituck/Knotts Island | This project will replace the aging and smaller Hatteras Class vessel (M/V Hunt) for a new River Class vessel that will increase capacity along with safety, mobility, and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 54
55 | F192621 | 1 | Expand and Replace MV Ocracoke | Hatteras/Ocracoke | This project will replace an aging and smaller Hatteras Class vessel (M/V Ocracoke) for a new and larger River Class vessel to increase safety, capacity, mobility and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 55
56 | F231098 | 1 | Expand and Replace MV Cape Point | Hatteras/Ocracoke | This project will replace an aging and smaller Hatteras Class vessel (M/V Cape Point) for a new and larger River Class vessel to increase safety, capacity, mobility and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 56
57 | F250801 | 0 | Expand and Replace MV Kinnakeet | Hatteras/Ocracoke | This project will replace an aging and smaller Hatteras Class vessel (M/V Kinnakeet) for a new and larger River Class vessel to increase safety, capacity, mobility and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 57
58 | - | Confirmed - not submitted | Expand and Replace MV White (this original doc had F231103 here incorrectly) | Hatteras/Ocracoke | This project will replace a River Class vessel (M/V White) for a new River Class vessel to increase safety, mobility and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | 1 |  | 58
59 | F250371 | 1 | Expand and Replace MV Croatoan (not sure this differs from F231104) | Hatteras/Ocracoke | This project will replace a River Class vessel (M/V Croatoan) for a new River Class vessel to increase safety, mobility and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | 1 |  | 59
60 | F250822 | 1 | Expand and Replace MV Hatteras (not sure this differs from F231105) | Hatteras/Ocracoke | This project will replace a River Class vessel (M/V Hatteras) for a new River Class vessel to increase safety, mobility and reliability | Expand Vehicle Vessel | 6 |  | Albemarle | Albemarle | 1 | Regional | Albemarle |  | 60
61 | F250423 | 1 | Expand River Class Ferry, Ramps in 2 locations, and Dorms (DELETE - we can't duplicate scopes to compete in different SITs) | Southport/Fort Fisher | Construct a new and addition river class vessel at Southport, build second ramps at Southport and Fort Fisher to increase passenger carrying capacity, and build a larger dorm at Southport to increase housing for employees to support additional operations | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Wilmington | Kai duplicated this project. It is the same as above, but competing in Facility section | 61
62 | F250425 | 1 | Expand River Class Ferry, Ramp, and Dorm at Southport (DELETE - we can't duplicate scopes to compete in different SITs) | Southport/Fort Fisher | Construct a new and additional river class vessel at Southport, build a second ramp at Southport to increase passenger carrying capacity, and build a larger dorm to increase housing for employees to support additional operations | Expand Facility | 8 | Wilmington MPO | Cape Fear | Wilmington MPO Cape Fear | 3 | Regional | Cape Fear | Kai duplicated this project. It is the same as above, but competing in Facility section | 62

## SPOT notes-questions
Questions
**confirm if expansion/replacement of vessel still = Regional or Divison
**need to update descriptions in Ferry Div file if it's the format being used for Thursday
removed most "aging" language
MV Hunt has no "only replace" project (FYI for P9)
MV Fort Fisher, Southport has no expansion project
Should Synchrolift be replacement project?