## 2026-2035 STIP
2026-2035 STATE TRANSPORTATION IMPROVEMENT PROGRAM As amended by the Board of Transportation and approved by FHWA (March 2026)
NOTE: ANY AMOUNTS PROGRAMMED FOR ACTIVITIES OTHER THAN RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION ARE INCLUDED UNDER "OTHER ACTIVITIES".
BASIC PROJECT INFORMATION | [12 empty] | FISCAL YEAR PROJECT PHASE SCHEDULED TO START
COUNTY(S) | ROUTE/CITY | RESPONSIBLE AGENCY | LOCATION DESCRIPTION | DESCRIPTION OF WORK | LENGTH (MILES) | MODE | FUNDING PROGRAM | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI CATEGORY FUNDED | FUNDING SOURCE (SEE FUNDING SOURCES TAB FOR MORE INFO) | RIGHT-OF-WAY PROJECTED SCHEDULE | FUNDS NEEDED FOR RIGHT-OF-WAY | UTILITIES PROJECTED SCHEDULE | FUNDS NEEDED FOR UTILITIES | CONSTRUCTION PROJECTED SCHEDULE | FUNDS NEEDED FOR CONSTRUCTION | PROJECTED SCHEDULE FOR OTHER ACTIVITIES | FUNDS FOR OTHER ACTIVITIES | TOTAL FUNDS NEEDED | COMMENT
Alamance | BUY | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | Burlington-Alamance Regional Airport | Construct 100 foot paved overrun and make safety enhancements. |  | Aviation | STI (Prioritization) | 7 | Burlington-Graham MPO | AV-5851 | Division 7 | T |  |  |  |  | 2029 | 6600000 |  |  | 6600000
Alamance | BUY | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | Burlington-Alamance Regional Airport | Obtain navigation easements and clear obstructions in the runway 24 approach. |  | Aviation | STI (Prioritization) | 7 | Burlington-Graham MPO | AV-5737 | Division 7 | L, T | 2027 | 1200000 | [6 empty] | 1200000
Alamance | Lee Avenue | ELON | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Bike & Ped | STI (Prioritization) | 7 | Burlington-Graham MPO | EB-5988 | Division 7 | L(M), TA50200 | 2030 | 40000 | 2030 | 280000 | 2032 | 310000 | 2024 | 30000 | 660000
Alamance | US 70 (North Church Street) | BURLINGTON | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Bike & Ped | STI (Prioritization) | 7 | Burlington-Graham MPO | EB-5885 | Division 7 | L(M), TA50200 | 2025 | 30000 | 2025 | 750000 | 2026 | 710000 |  |  | 1490000
Alamance | US 70 (North Church Street) | BURLINGTON | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Bike & Ped | STI (Prioritization) | 7 | Burlington-Graham MPO | EB-5879 | Division 7 | L(M), TA50200 | 2029 | 3300000 | 2029 | 950000 | 2032 | 930000 | 2024 | 16000 | 5196000
Alamance | I-40 / I-85 | NCDOT | Ramps at SR 1226, SR 1158, NC 62, NC 49, NC 87, NC 54, SR 1928, SR 1981, and NC 119 interchanges. | Upgrade traffic signals. | 12.4 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2407Q | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2027 | 179000 |  |  | 179000
Alamance | NC 119 | NCDOT | NC 54 to SR 2126 (Old Hillsbotough Road); SR 1921 (Mebane Rogers Road) to Caswell County line. | Install 6-inch rumble strips and long life pavement markings. | 13.3 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2407F | Region D | HSIP |  |  |  |  | 2027 | 960000 |  |  | 960000
Alamance | NC 87 | NCDOT | I-40 Eastbound on-ramp. | Install pedestrian accommodations. | 0.5 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2007F | Region D | HSIP, T(M) |  |  |  |  | 2024 | 87000 |  |  | 87000 | UNDER CONSTRUCTION
Alamance | NC 87 | NCDOT | SR 1005 (Greensboro Chapel Hill Road) to SR 2316 (Thompson Road). | Install rumble stripes with 6-inch long life pavement markings. | 11 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2407P | Region D | HSIP, T(M) |  |  |  |  | 2028 | 810000 |  |  | 810000
Alamance | SR 1005 (Greensboro-Chapel Hill Road) | NCDOT | Guilford County line to Orange County line. | Install 6-inch rumble strips and long life pavement markings. | 18.53 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2407E | Division 7 | HSIP |  |  |  |  | 2027 | 1285000 |  |  | 1285000
Alamance | SR 1301 (Boone Station Drive) | NCDOT | SR 1301 (Saint Marks Church Road) / Java Lane and Glidwell Drive / Tiki Lane in Burlington. | Install pedestrian signals, curb ramps, and revise pavement markings. | 0.5 | Highway | Safety | 7 | Burlington-Graham MPO | W-5807B | Division 7 | HSIP, T(M) |  |  |  |  | 2023 | 76000 |  |  | 76000
Alamance | Various | NCDOT | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2407K | Division 7 | HSIP, T(M) | 2027 | 2000000 | 2027 | 575000 | 2027 | 2680000 |  |  | 5255000
Alamance | Various | NCDOT | Routes in Burlington. | Upgraded traffic signals and install pedestrian accomodations at multiple signalized intersections. | 0.5 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2407J | Division 7 | HSIP |  |  |  |  | 2027 | 90000 |  |  | 90000
Alamance | I-40 / I-85 | NCDOT | SR 1007 (Mebane-Oaks Road) in Mebane. | Improve interchange. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | I-5711 | Statewide Mobility | NHP, T(M) |  |  |  |  | 2020 | 9830000 |  |  | 9830000 | UNDER CONSTRUCTION;
Alamance | I-40 / I-85 | NCDOT | SR 1158 (Huffman Mill Road) interchange in Burlington. | Construct additional left turn lane on I-40 westbound ramp and improve operations at SR 1308 (Garden Road) intersection. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | I-6009 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2400000 |  |  | 2940000
Alamance | I-40 / I-85 | NCDOT | SR 1981 (Trollingwood-Hawfields Road) in Mebane. | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | I-6059 | Division 7 | HF, T | 2025 | 5100000 | 2025 | 2500000 | 2025 | 32380000 |  |  | 39980000 | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE)
Alamance | NC 119 | NCDOT | I-40 / I-85 to north of SR 1921 (Mebane Rogers Road) | Relocate roadway. | 3.01 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-3109A | Region D | T |  |  |  |  | 2019 | 42967000 | 2021 | 360000 | 43327000 | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Alamance | NC 119 | NCDOT | NC 119 relocation, I-85 to south of SR 1918 (Mrs. White Road) in Mebane. | Four-to-six-lane facility on new location. | 4.2 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-3109
Alamance | NC 119 | NCDOT | North of SR 1921 (Mebane Rogers Road) to south of SR 1918 (Mrs. White Road). | Relocate roadway. | 1.49 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-3109B | Region D | T |  |  |  |  | 2021 | 5835000 |  |  | 5835000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.533 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Alamance | NC 119 | NCDOT | SR 1981 (Trollingwood-Hawfields Road) / SR 2126 (Old Hillsborough Road) to Lowes Boulevard in Mebane. | Widen to a four lane divided facility. | 0.52 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6013 | Division 7 | T | 2023 | 5500000 | 2023 | 900000 | 2028 | 10400000 |  |  | 16800000 | RIGHT-OF-WAY IN PROGRESS
Alamance | NC 49 (Maple Avenue) | NCDOT | I-85 / I-40 to NC 54 (Chapel Hill Road) intersection | Relocate NC 49 (Maple Avenue) on new alignment, and construct signalized intersection at Plaza Drive and Plantation Drive. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | HP-0022 | Region D | BG50200 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 |  |  | 6600000
Alamance | NC 54 | NCDOT | SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) to south of SR 2107 (Whittemore Road) in Graham. | Construct SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) intersection improvements, upgrade ramp intersections at I-40 / I-85, construct SR 2106 (Woody Road) intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115 | Region D
Alamance | NC 54 (East Harden Street) | NCDOT | I-40 / I-85 interchange | Upgrade ramp intersections. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115B | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 880000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10900000 |  |  | 12180000
Alamance | NC 54 (East Harden Street) | NCDOT | NC 49 (East Elm Street) intersection in Graham. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6017 | Division 7 | T | 2022 | 2000000 | 2022 | 550000 | 2024 | 2100000 |  |  | 4650000 | RIGHT-OF-WAY IN PROGRESS
Alamance | NC 54 (East Harden Street) | NCDOT | SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) intersection in Graham | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115A | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 520000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5200000 |  |  | 7720000
Alamance | NC 54 (East Harden Street) | NCDOT | SR 2106 (Woody Drive) intersection | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115C | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 340000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 |  |  | 7540000
Alamance | NC 54 (East Harden Street) | NCDOT | SR 2106 (Woody Drive) intersection and SR 2107 (Whittemore Road) intersection | Upgrade pipe culverts 000271 and 000297. |  | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115D | Not Funded | T | NOT FUNDED | 490000 | NOT FUNDED | 120000 | NOT FUNDED | 2100000 | NOT FUNDED |  | 2710000
Alamance | NC 54 (West Harden Street) | NCDOT | NC 49 (Maple Avenue) intersection in Burlington. | Install dual left turn lanes in westbound direction. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6131 | Region D | BG50200, T(M) | 2027 | 11700000 | 2027 | 1100000 | 2028 | 7400000 |  |  | 20200000
Alamance | NC 62 | NCDOT | SR 1430 (Ramada Road) to US 70 (Church Street) in Burlington. | Widen to a three lane facility. | 1.13 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-5844 | Division 7 | T | 2024 | 13300000 | 2025 | 1900000 | 2027 | 20895000 |  |  | 36095000 | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE)
Alamance | NC 62 (Alamance Road) | NCDOT | SR 1155 (Hatchery Road) / Bonnie Lane intersection in Burlington. | Install traffic signal and add turn lanes. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6114 | Region D | T | 2028 | 770000 | 2028 | 270000 | 2031 | 1800000 |  |  | 2840000
Alamance | SR 1716 (Graham- Hopedale Road) | NCDOT | SR 1720 (West Hanover Road) to Morningside Drive in Burlington. | Widen to a three lane facility with bike-ped accommodations. | 1.38 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6014 | Division 7 | T | 2024 | 1500000 | 2025 | 1200000 | 2027 | 19200000 |  |  | 21900000 | RIGHT-OF-WAY IN PROGRESS
Alamance | US 70 (Church Street) | NCDOT | NC 62 intersection | Construct intersection improvements. |  | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | HP-0030 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 |  |  | 2400000
Alamance | US 70 (North Church Street) | NCDOT | SR 1817 (Graham-Hopedale Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-5843 | Division 7 | T |  |  |  |  | 2019 | 2167000 | 2021 | 810000 | 2977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Alamance | US 70 (South Church Street) | NCDOT | SR 1158 (Huffman Mill Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6011 | Region D | T | 2022 | 3000000 | 2022 | 630000 | 2025 | 7080000 |  |  | 10710000 | Under construction.
Alamance | US 70 (South Church Street) | NCDOT | SR 1226 / SR 1311 (University Drive) intersection in Burlington. | Construct intersection improvements, to include widening of US 70 to maintain consistent cross-section with project U-5752 improvements. | 5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6010 | Region D | T | 2020 | 6000000 |  |  | 2022 | 16100000 |  |  | 22100000 | UNDER CONSTRUCTION
Alamance | US 70 (South Church Street) | NCDOT | Tarleton Avenue to Fifth Street in Burlington. | Widen and construct center turn lane. | 0.93 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6009 | Region D | T | 2028 | 2500000 | 2028 | 2100000 | 2030 | 23305000 |  |  | 27905000 | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
Alamance | Various | NCDOT | Routes in Burlington and Graham | Upgrade Burlington-Graham signal system. |  | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6015 | Division 7 | T |  |  |  |  | 2021 | 6125000 |  |  | 6125000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Alamance | City Of Burlington | BURLINGTON | Various locations | Funding for capital for pedestrian improvements for fixed route services. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Burlington-Graham MPO | TD-6322 | Public Transit | 5307, L | [6 empty] | 2025 | 1200000 | 1200000 | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
Alamance | Link Transit |  | Various locations | To provide fund for the design, engineering and construction of transit maintenance facility and transit transfer hub to support the link transit system. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Burlington-Graham MPO | TC-0034 | Public Transit | 5307, L, S | [6 empty] | 2024 | 1920000 | 1920000
Alamance | Link Transit | LINK TRANSIT | Various locations | Construct improvements and bus shelters. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Burlington-Graham MPO | TA-6322 | Public Transit | 5307, 5339, L | [6 empty] | 2023 | 1308000 | 1308000
Alamance | Link Transit | LINK TRANSIT | Various locations | Capital improvements for transit vehicles. |  | Public Transportation (Transit) | Locally Selected | 7 | Burlington-Graham MPO | TL-0029 | Public Transit | 5307, L | [6 empty] | 2022 | 1302000 | 1302000
Alamance | Alamance County Transportation Authority | ALAMANACE COUNTY TRANSPORTATION | Systemwide | Operating for Alamance county transportation in the Burlington urban area. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-5214 | Public Transit | 5307, L | [6 empty] | 2023 | 12318000 | 12318000 | FUNDS AUTHORIZED IN PROGRESS
Alamance | Link Transit | LINK TRANSIT | Various locations | ADA Service. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-6812A | Public Transit | 5307, L | [6 empty] | 2023 | 2041000 | 2041000
Alamance | Link Transit | LINK TRANSIT | Various locations | Operating assistance to maintain current level of service in addition to service expansion for weekend service |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-6170 | Public Transit | 5307, L | [6 empty] | 2023 | 11656000 | 11656000 | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO.
Alamance | Piedmont Regional Transport Authority | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-5134 | Public Transit | 5307, L | [6 empty] | 2023 | 10120000 | 10120000 | FUNDS AUTHORIZED IN PROGRESS
Alamance | Link Transit | LINK TRANSIT | Various location | Purchase two electric paratransit vehicles and install chargers. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 7 | Burlington-Graham MPO | TN-6134 | Exempt | CRPDA, L(M) | [6 empty] | 2025 | 560000 | 560000
Alamance | Burlington | BURLINGTON | Systemwide | Funding for ADA services. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TG-6812A | Public Transit | 5307, L | [6 empty] | 2025 | 1360000 | 1360000 | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
Alamance | City of Burlington/Link Transit | Link Transit | Systemwide | Administrative and Operations staff training. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0071 | Public Transit | 5307, L(M) | [6 empty] | 2026 | 72000 | 72000
Alamance | City of Burlington/Link Transit | Link Transit | Systemwide | Security enhancements. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0072 | Public Transit | 5307, L(M) | [6 empty] | 2026 | 252000 | 252000
Alamance | Link Transit | LINK TRANSIT | Systemwide | Preventative Maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0046 | Public Transit | 5307, L | [6 empty] | 2023 | 3962000 | 3962000
Alamance | Transportation Authority |  | Systemwide | Funding for rolling stock-shop vehicle. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0051 | Public Transit | 5307, L | [6 empty] | 2024 | 865000 | 865000
Alamance | Alamance County Transportation Authority |  | Various locations | Funding for ACTA planning and feasibility study |  | Public Transportation (Transit) | Planning | 7 | Burlington-Graham MPO | TU-0017 | Public Transit | 5307, L | [6 empty] | 2024 | 150000 | 150000
Alamance | Link Transit | LINK TRANSIT | Systemwide | Funding for planning for transit facility feasibility study and short range transit plan. |  | Public Transportation (Transit) | Planning | 7 | Burlington-Graham MPO | TA-6733 | Public Transit | 5307, 5309, L, S | [6 empty] | 2023 | 1453000 | 1453000 | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
Alamance |  | City of Burlington/Link Transit | City of Burlington/Link Transit | Shop truck replacement. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-0032 | Public Transit | 5307, L(M) | [6 empty] | 2026 | 120000 | 120000
Alamance | Piedmont Authority For Regional Transportation | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | Various locations | Funding for routine capital, preventative maintenance, passenger amenities, and mobility management. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-0012 | Public Transit | 5307, L | [6 empty] | 2023 | 875000 | 875000
Alamance | Piedmont Regional Transport Authority | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | Systemwide | Funding for routine capital, passenger amenities, parts, equipment, preventive maintenance, and capital cost of contracting. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-6137B | Public Transit | 5307, L | [6 empty] | 2020 | 2374000 | 2374000
Alamance | Piedmont Corridor | PIEDMONT CORRIDOR | Graham to Haw River. | Realign siding and curve. |  | Rail | Pre-STI (Historic) | 7 | Burlington-Graham MPO | P-5205 | Pre-STI (Transition) | [10 empty] | COMPLETE.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | BO-2407 | Division 7 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Locations in Division 7 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | R-5787 | Division 7 | HF, TA |  |  |  |  | 2020 | 4500000 |  |  | 4500000 | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Various locations in Division 7. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | BO-2607 | Division 7 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2007 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7 | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707DIV | Division 7 | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 556000 |  |  | 646000
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7 | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707SW | Statewide Mobility | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2407 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707 | [11 empty] | IN PROGRESS
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5807
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022DIV | Division 7 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022REG | Region D | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Secondary routes in Division 7. | Install long-life pavement markings. |  | Highway | Safety | 7 | Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, Piedmont Triad RPO | HS-2007C | Division 7 | HSIP, T(M) |  |  |  |  | 2021 | 1717000 |  |  | 1717000 | UNDER CONSTRUCTION
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Various locations in Division 7 | Safety Improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2607 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Locations in Division 7. | Implementation of traffic separation study and closures in Division 7. |  | Rail | Rail-Highway Grade Crossing Closure | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RC-2007 | Division 7 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Locations in Division 7. | Construct highway-rail grade crossing safety improvements in Division 7. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO, Piedmont Triad RPO, Piedmont Triad RPO, Triangle West TPO | RX-2607 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Locations in Division 7. | Construct highway-rail grade crossing safety improvements in Division 7. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RX-2007 | Division 7 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Guilford, Orange, Rockingham | Various | NCDOT | Locations in Division 7. | Construct highway-rail grade crossing safety improvements in Division 7. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RX-2407 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alamance, Caswell, Orange, Rockingham | Various | NCDOT | Routes in Division 7 | Construct safety improvements. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707REG | Region D | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 556000 |  |  | 646000
Alamance, Cumberland, Durham, Guilford, Wake, Caswell, Chatham, Granville, Harnett, Hoke, Lee, Montgomery, Moore, Orange, Person, Randolph, Richmond, Rockingham, Scotland | Various | NCDOT | Locations statewide. | Funding for lidar data collection. |  | Highway | Other | 5, 6, 7, 8 | Capital Area MPO, Fayetteville Area MPO, Greensboro Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Kerr-Tar RPO, Lumber River RPO, Mid-Carolina RPO, Northwest Piedmont RPO, Piedmont Triad RPO, Rock | M-0563D | Statewide Mobility | PROTCT, T(M) | [6 empty] | 2024 | 1285000 | 1285000
Alamance, Guilford, Orange | Various | NCDOT | Burlington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 7 | Burlington-Graham MPO | HL-0091 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 1708000 |  |  | 1708000
Alamance, Guilford, Orange | Alamance County Transportation Authority | ALAMANACE COUNTY TRANSPORTATION | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-6811B | Public Transit | 5307, L | [6 empty] | 2024 | 250000 | 250000
Alamance, Orange | GoTriangle | GOTRIANGLE | Systemwide. | Operating assistance. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0069 | Public Transit | 5307, L(M) | [6 empty] | 2026 | 144000 | 144000
Alamance, Orange | Orange County Public Transit |  | Systemwide | Operating assistance and purchase of charging stations. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0070 | Public Transit | 5307, L(M) | [6 empty] | 2026 | 818000 | 818000
Alamance, Orange | Orange County Public Transit | Orange County Public Transit | Systemwide. | Orange County Public Transit. Bus stop signage, lot improvements, and vehicle communications equipment procurement. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0073 | Public Transit | 5307, S | [6 empty] | 2026 | 350000 | 350000
Alexander | New Route | NCDOT | Alexander Industrial Park. | Construct access road. | 0.49 | Highway | Appalachian Development Highway System | 12 | Greater Hickory MPO | R-5870 | Exempt | ADHSL, T |  |  |  |  | 2021 | 1675000 |  |  | 1675000 | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING.
Alexander | SR 1348 (Old NC 90) | NCDOT | Bridge 010291 over Duck Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Greater Hickory MPO | BR-0201 | Highway Fund | HFB |  |  |  |  | 2021 | 1050000 |  |  | 1050000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88
Alexander | NC 16 | NCDOT | SR 1609 (County Home Road) intersection near Taylorsville. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-5762 | Division 12 | T | 2022 | 120000 |  |  | 2023 | 885000 |  |  | 1005000 | UNDER CONSTRUCTION.
Alexander | US 64 | NCDOT | SR 1124 (Church Road). | Construct left turn lane on westbound US 64 / NC 90. |  | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-6041 | Division 12 | BGLT5, T(M) | 2024 | 200000 | 2024 | 400000 | 2025 | 2700000 |  |  | 3300000 | UNDER CONSTRUCTION.
Alexander, Burke, Caldwell, Catawba | Western Piedmont Council of Governments | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | Systemwide | Funding for planning assistance. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TP-5106 | Public Transit | 5303, HF, L(M), S(M) | [6 empty] | 2024 | 466000 | 466000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority |  | Systemwide | Funding for routine capital. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TC-0032 | Public Transit | 5339, L | [6 empty] | 2024 | 240000 | 240000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority |  | Systemwide | Purchase rolling stock. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TC-0033 | Public Transit | 5309, L | [6 empty] | 2024 | 240000 | 240000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority |  | Various locations | Funding for vehicles and bus stops. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TC-0028 | Public Transit | 5339, L | [6 empty] | 2024 | 240000 | 240000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | REGIONAL TRANSPORTATION WESTERN PIEDMONT | Systemwide | Western Piedmont Transit Authority |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TA-6707 | Public Transit | 5307, L | [6 empty] | 2023 | 2520000 | 2520000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Funds for safety and security. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TS-7002 | Public Transit | 5307, L | [6 empty] | 2020 | 486000 | 486000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Purchase service vehicles. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TQ-9039 | Public Transit | 5310, L | [6 empty] | 2024 | 1300000 | 1300000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSPORTATION | Systemwide | Purchase bus for service expansion. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TA-4928 | Public Transit | 5307, L | [6 empty] | 2024 | 840000 | 840000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide. | Program administration. |  | Public Transportation (Transit) | Locally Selected | 11, 12, 13 | Greater Hickory MPO | TL-6110 | Public Transit | 5310 | [6 empty] | 2020 | 232000 | 232000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 11, 12, 13 | Greater Hickory MPO | TO-6162 | Public Transit | 5307, L | [6 empty] | 2020 | 19730000 | 19730000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | REGIONAL TRANSPORTATION WESTERN PIEDMONT | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-4774A | Public Transit | 5307, L | [6 empty] | 2023 | 740000 | 740000 | FUNDS AUTHORIZED IN PROGRESS
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-6801 | Public Transit | 5307, L | [6 empty] | 2024 | 1500000 | 1500000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Funding for operating assistance - elderly and disabled person. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TQ-6507 | Public Transit | 5310, L | [6 empty] | 2023 | 948000 | 948000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSPORTATION | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-6802 | Public Transit | 5310, L | [6 empty] | 2020 | 300000 | 300000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WPRTA | Systemwide. | Mobility management and operating assistance for elderly and disabled persons, and other ADA communities. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TM-0063 | Public Transit | 5310, L | [6 empty] | 2026 | 236000 | 236000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WPRTA | Systemwide. | Operational and capital cost of contracting, pass through, 3rd party contracts. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TM-0061 | Public Transit | 5310, L | [6 empty] | 2026 | 180000 | 180000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WPRTA | Systemwide. | Operational and capital cost of contracting, pass through, 3rd party contracts. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TM-0062 | Public Transit | 5310, L | [6 empty] | 2026 | 196000 | 196000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority |  | Systemwide | Purchase replacement buses. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-0023 | Public Transit | 5339, L | [6 empty] | 2025 | 125000 | 125000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority |  | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 11, 12, 13 | Greater Hickory MPO | TA-4774A | Public Transit | 5307, L(M) | [6 empty] | 2024 | 1875000 | 1875000
Alexander, Burke, Caldwell, Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, computer hardware and software, AVL software, etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-6800 | Public Transit | 5307, L | [6 empty] | 2024 | 1440000 | 1440000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
Alexander, Catawba | NC 127 | NCDOT | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3603A | Division 12 | BGANY, T(M) | 2030 | 19600000 | 2030 | 7300000 | 2034 | 115700000 |  |  | 142600000 | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040).
Alexander, Catawba | NC 127 | NCDOT | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.7 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3603
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | BO-2412 | Division 12 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 600000 | 6100000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | R-5792 | Division 12 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Various locations in Division 12. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | BO-2612 | Division 12 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2012 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2412 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712 | [11 empty] | IN PROGRESS
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712DIV | Division 12 | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712REG | Region F | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712SW | Statewide Mobility | HSIP, T(M) | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Construct safety improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5812 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027DIV | Division 12 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027REG | Region F | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5212 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. HF(M) IS SPOT SAFETY FUNDS.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Various locations in Division 12. | Safety Improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2612 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Locations in Division 12. | Traffic separation study implementation and closures. |  | Rail | Rail-Highway Grade Crossing Closure | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RC-2012 | Division 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Locations in Division 12. | Construct highway-rail grade crossing safety improvements in Division 12. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RX-2012 | Division 12 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Locations in Division 12. | Construct highway-rail grade crossing safety improvements in Division 12. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RX-2412 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | Various | NCDOT | Locations in Division 12. | Construct highway-rail grade crossing safety improvements in Division 12. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RX-2612 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Alexander, Catawba, Iredell | Various | NCDOT | Secondary routes in Division 12. | Install long life pavement markings. |  | Highway | Safety | 12 | Cabarrus-Rowan MPO, Charlotte Regional TPO | HS-2012D | Division 12 | HSIP, T(M) |  |  |  |  | 2023 | 3615000 |  |  | 3615000 | UNDER CONSTRUCTION.
Alleghany | SR 1422 (Fox Ridge Road) | NCDOT | Bridge 020035 over Glade Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0206 | Highway Fund | HFB |  |  |  |  | 2022 | 750000 |  |  | 750000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157
Alleghany | SR 1433 (Ridgeglen Road) | NCDOT | Bridge 020133 over Little River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0207 | Highway Fund | HFB |  |  |  |  | 2022 | 500000 |  |  | 500000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159
Alleghany | SR 1433 (Scenic Valley Road) | NCDOT | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0067 | Exempt | BGOFF, DP, HFB | 2025 | 200000 | 2025 | 10000 | 2026 | 1600000 | 2023 | 399000 | 2209000 | DP REPRESENTS RAISE GRANT FUNDS.
Alleghany | Alleghany County Transit | ALLEGHANY COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6105 | Public Transit | 5311, L, S | [6 empty] | 2020 | 620000 | 620000 | FUNDS AUTHORIZED IN PROGRESS
Anson | NC 742 | NCDOT | Bridge 030084 over Lanes Creek | Replace bridge. | 0.1 | Highway | Bridges | 10 | Rocky River RPO | BR-0163 | Region E | BFP, T(M) | 2029 | 445000 |  |  | 2029 | 4448000 |  |  | 4893000
Anson | SR 1627 (Pinkston River Road) | NCDOT | Bridge 030307 in the Town of Ansonville. | Install waterline per utility construction agreement. |  | Highway | Bridges | 10 | Rocky River RPO | B-4410A | Pre-STI (Transition) | L, T | 2022 | 25000 |  |  | 2027 | 1013000 |  |  | 1038000 | UNDER CONSTRUCTION.
Anson | SR 1627 (Pinkston River Road) | NCDOT | Bridge 030307 over WSSB Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-4410 | [11 empty] | COMPLETE. LOCAL FUNDING PROVIDED BY TOWN OF ANSONVILLE
Anson | SR 1812 (Diggs Road) | NCDOT | Bridge 030039 over Jones Creek. | Replace bridge. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-6048 | Division 10 | BGOFF | 2023 | 355000 |  |  | 2027 | 4100000 |  |  | 4455000 | RIGHT-OF-WAY IN PROGRESS.
Anson | US 74 | NCDOT | Anson High School Road | Intersection improvements | 0.1 | Highway | NCDOT Selected (Other Selection Process) | 10 | Rocky River RPO | HN-0042 | Statewide Mobility | CRPLT5, T(M) | 2026 | 194000 |  |  | 2026 | 2627000 | 2026 | 480000 | 3301000
Anson | SR 1110 (Mayesville Road) | NCDOT | NC 742 to South Carolina state line | Install rumble stripes with long life pavement markings. | 4.6 | Highway | Safety | 10 | Rocky River RPO | HS-2610V | Division 10 | HSIP, T(M) |  |  |  |  | 2027 | 26000 |  |  | 26000
Anson | US 52 | NCDOT | NC 742 to Ansonville town limits | Install rumble stripes with long life pavement markings. | 8.2 | Highway | Safety | 10 | Rocky River RPO | HS-2610U | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 242000 |  |  | 242000
Anson | US 74 | NCDOT | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Highway | Safety | 10 | Rocky River RPO | HS-2610J | Statewide Mobility | HSIP, T(M) | 2027 | 50000 | 2027 | 50000 | 2028 | 850000 |  |  | 950000
Anson | New Route (Wadesboro Bypass) | NCDOT | US 52 north of Wadesboro to US 74 east of Wadesboro. | Construct freeway on new location. | 6.44 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5878B | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 315700000 |  |  | 358800000
Anson | New Route (Wadesboro Bypass) | NCDOT | US 74 west of Wadesboro to US 52 north of Wadesboro. | Construct freeway on new location. |  | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5878A | Not Funded | NHP, T(M) | NOT FUNDED | 4000000 | NOT FUNDED | 600000 | NOT FUNDED | 104300000 | NOT FUNDED |  | 108900000
Anson | New Route (Wadesboro Bypass) | NCDOT | US 74 west of Wadesboro to US 74 east of Wadesboro. | Construct freeway on new location. | 11.3 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5878
Anson | US 74 (Andrew Jackson Highway) | NCDOT | Graham Street to SR 1749 (Allen Pond Road). | Construct median. | 2.87 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5798 | Statewide Mobility | BGLT5, T(M) | 2029 | 18500000 | 2029 | 5500000 | 2032 | 65100000 |  |  | 89100000
Anson | Anson County Transit | ANSON COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Rocky River RPO | TK-6106 | Public Transit | 5311, L, S | [6 empty] | 2020 | 820000 | 820000 | FUNDS AUTHORIZED IN PROGRESS
Anson | SR 1714 (Stanback Ferry Ice Plant Road) | NCDOT | CSX Crossing 631750C near Wadesboro. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO | RX-2010B | Division 10 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
Anson | CSX SF LINE | CSXT RR | Polkton. | Construct rail siding extension. |  | Rail | STI (Prioritization) | 10 | Rocky River RPO | P-5750A | Region E | DP, T |  |  |  |  | 2024 | 13037000 |  |  | 13037000
Anson | CSX SF LINE | NCDOT | Polkton. | Construct rail siding extension. |  | Rail | STI (Prioritization) | 10 | Rocky River RPO | P-5750 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
Anson | CSX SF LINE | NCDOT | SR 1469 (Freedom Road) intersection in Polkton. | Construct grade separation. |  | Rail | STI (Prioritization) | 10 | Rocky River RPO | P-5750B | Region E | T | 2029 | 2000000 | 2029 | 480000 | 2033 | 26400000 |  |  | 28880000
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | BO-2410 | Division 10 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 625000 | 6125000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Locations in Division 10 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | R-5790 | Division 10 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Various locations in Division 10. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | BO-2610 | Division 10 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2010 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2410 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710 | [11 empty] | HF(M) FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710DIV | Division 10 | HSIP, T(M) | 2020 | 410000 |  |  | 2020 | 2024000 |  |  | 2434000 | IN PROGRESS.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710REG | Region E | HSIP, T(M) | 2020 | 540000 |  |  | 2020 | 720000 |  |  | 1260000 | IN PROGRESS.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710SW | Statewide Mobility | HSIP, T(M) | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Construct safety improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5810 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025DIV | Division 10 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025REG | Region E | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Various locations in Division 10 | Safety Improvements. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2610 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Locations in Division 10. | Traffic separation study implementation and closures. |  | Rail | Rail-Highway Grade Crossing Closure | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RC-2010 | Division 10 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Locations in Division 10. | Construct highway-rail grade crossing safety improvements in Division 10. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RX-2010 | Division 10 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Locations in Division 10. | Construct highway-rail grade crossing safety improvements in Division 10. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RX-2410 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Cabarrus, Mecklenburg, Stanly, Union | Various | NCDOT | Locations in Division 10. | Construct highway-rail grade crossing safety improvements in Division 10. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RX-2610 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Anson, Robeson, Richmond, Scotland, Union | US 74 | NCDOT | Eastern end of Monroe Bypass to I-95 in Lumberton. | Install broadband and ITS for Traveler Information Systems. | 86.48 | Highway | Other | 6, 8, 10 | Lumber River RPO, Rocky River RPO, Charlotte Regional TPO | HO-0002B | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 14216000 |  |  | 14216000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION.
Ashe | GEV | ASHE COUNTY AIRPORT (GEV) | Ashe County Airport | Expand aprons. |  | Aviation | STI (Prioritization) | 11 | High Country RPO | AV-5848 | Division 11 | T |  |  |  |  | 2021 | 2700000 |  |  | 2700000 | UNDER CONSTRUCTION.
Ashe | Northwest Drive; AEV Lane | NCDOT | NC 88 to Benfield Drive; Northwest Drive to American Emergency Vehicles facility. | Widen road to 12-foot lanes. | 0.49 | Highway | Appalachian Development Highway System | 11 | High Country RPO | HA-0006 | Exempt | ADHSL | 2025 | 60000 |  |  | 2025 | 643000 | 2023 | 47000 | 750000 | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000
Ashe | SR 1104 (Brown Road) | NCDOT | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0052 | Exempt | BGOFF, DP, HFB | 2025 | 210000 | 2025 | 15000 | 2026 | 2398000 | 2023 | 381000 | 3004000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1105 (New River Bridge Road) | NCDOT | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0046 | Exempt | BGOFF, DP, HFB | 2025 | 220000 | 2025 | 10000 | 2026 | 2298000 | 2023 | 406000 | 2934000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1126 (Ed Little Road) | NCDOT | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0053 | Exempt | BGOFF, DP, HFB | 2025 | 280000 | 2025 | 40000 | 2026 | 1701000 | 2023 | 425000 | 2446000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1159 (Boggs Road) | NCDOT | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0051 | Exempt | BGOFF, DP, HFB | 2025 | 210000 | 2025 | 10000 | 2026 | 920000 | 2023 | 368000 | 1508000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1222 (Methodist Camp Road) | NCDOT | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0054 | Exempt | BGOFF, DP, HFB | 2025 | 150000 | 2025 | 30000 | 2026 | 3701000 | 2023 | 498000 | 4379000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1523 (Silas Creek Road) | NCDOT | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0043 | Exempt | BGOFF, DP, HFB | 2025 | 200000 | 2025 | 70000 | 2026 | 1501000 | 2023 | 398000 | 2169000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1527 (Helton Road) | NCDOT | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0068 | Exempt | BGOFF, DP, HFB | 2025 | 140000 | 2025 | 10000 | 2026 | 1501000 | 2023 | 289000 | 1940000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1528 (Jim Duvall Road) | NCDOT | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0047 | Exempt | BGOFF, DP, HFB | 2025 | 210000 | 2025 | 20000 | 2026 | 1600000 | 2023 | 436000 | 2266000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1563 (Clifton Road) | NCDOT | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0050 | Exempt | BGOFF, DP, HFB | 2025 | 1700000 | 2025 | 10000 | 2026 | 3200000 | 2023 | 403000 | 5313000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1602 (North Fulton Reeves Road) | NCDOT | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0049 | Exempt | BGOFF, DP, HFB | 2025 | 140000 | 2025 | 50000 | 2026 | 2301000 | 2023 | 408000 | 2899000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1606 (Double Springs Church Road) | NCDOT | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0048 | Exempt | BGOFF, DP, HFB | 2025 | 400000 | 2025 | 20000 | 2026 | 1301000 | 2023 | 364000 | 2085000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1609 (Upper Cranberry Creek Road) | NCDOT | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0045 | Exempt | BGOFF, DP, HFB | 2025 | 270000 | 2025 | 40000 | 2026 | 1500000 | 2023 | 379000 | 2189000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | SR 1644 (McNeil Road) | NCDOT | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0044 | Exempt | BGOFF, DP, HFB | 2025 | 290000 | 2025 | 10000 | 2026 | 2201000 | 2023 | 469000 | 2970000 | DP REPRESENTS RAISE GRANT FUNDS.
Ashe | NC 16 | NCDOT | US 221 to the Virginia state line. | Install new and upgrade existing guardrail. |  | Highway | Safety | 11 | High Country RPO | HS-2011E | Region F | HSIP |  |  |  |  | 2023 | 2200000 |  |  | 2200000 | UNDER CONSTRUCTION.
Ashe | NC 88 | NCDOT | NC 88 (West Main Street) in Warrensville to NC 194. | Upgrade roadway. | 3.76 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5832 | Division 11 | BGLT5, T(M) | 2025 | 16300000 | 2025 | 1700000 | 2028 | 67910000 |  |  | 85910000
Ashe | US 221 | NCDOT | North of South Fork New River to south of NC 194. | Widen to four lanes divided. | 4.2 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2915C | Division 11 | BGLT5, T(M) |  |  |  |  | 2017 | 19700000 |  |  | 19700000 | COMPLETE
Ashe | US 221 | NCDOT | US 221 Bypass to US 221 Business / NC 88 in Jefferson. | Widen to four lanes divided. | 3.55 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2915E | Division 11 | T |  |  |  |  | 2020 | 44684000 |  |  | 44684000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
Ashe | US 221 | NCDOT | 1003 (Idlewild Road) to North of South Fork New River. | Widen to four lanes divided. | 1 | Highway | Transition | 11 | High Country RPO | R-2915B | Pre-STI (Transition) | [10 empty] | COMPLETE
Ashe | US 221 | NCDOT | South of NC 194 to US 221 Bypass. | Widen to four lanes divided. | 3.8 | Highway | Transition | 11 | High Country RPO | R-2915D | Pre-STI (Transition) | [10 empty] | COMPLETE
Ashe | Ashe County Transportation | ASHE COUNTY TRANSPORTATION | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6108 | Public Transit | 5311, L, S | [6 empty] | 2020 | 784000 | 784000 | FUNDS AUTHORIZED IN PROGRESS
Ashe, Watauga | US 221 | NCDOT | US 421 in Watauga County to US 221 Business / NC 88 in Jefferson. | Widen to four lanes divided. | 16.1 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2915
Ashe, Watauga | US 221 | NCDOT | US 421 in Watauga County to SR 1003 (Idlewild Road) in Ashe County. | Widen to four lanes divided. | 3.6 | Highway | Transition | 11 | High Country RPO | R-2915A | Pre-STI (Transition) | [10 empty] | COMPLETE
Avery | SR 1306 (Hicks Hollow Road) | NCDOT | Bridge 050125 over Elk River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | B-5835 | Division 11 | BGOFF | 2025 | 150000 | 2025 | 160000 | 2025 | 2600000 |  |  | 2910000 | RIGHT-OF-WAY IN PROGRESS
Avery | SR 1326 (Puckett Road) | NCDOT | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0055 | Exempt | BGOFF, DP, HFB | 2025 | 270000 | 2025 | 10000 | 2026 | 3000000 | 2023 | 404000 | 3684000 | DP REPRESENTS RAISE GRANT FUNDS.
Avery | SR 1511 (Roseboro Road) | NCDOT | Mile marker 0.77 to mile marker 0.82 near Linville. | Install shoulder guardrail. | 0.05 | Highway | Safety | 11 | High Country RPO | HS-2011C | Division 11 | HSIP |  |  |  |  | 2021 | 20000 |  |  | 20000 | UNDER CONSTRUCTION.
Avery | US 19E | NCDOT | NC 194 intersection in Elk Park. | Construct right turn lane from US 19E northbound to NC 194 eastbound. | 0.5 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5911 | Division 11 | BGLT5, T(M) | 2022 | 200000 |  |  | 2023 | 1200000 |  |  | 1400000 | UNDER CONSTRUCTION.
Avery, Buncombe, Burke, Haywood, Henderson, Jackson, McDowell, Mitchell, Swain, Transylvania, Alleghany, Ashe, Caldwell, Watauga, Wilkes | Blue Ridge Parkway | NCDOT | Regionwide. | Marketing and branding for Blue Ridge Parkway Association. |  | Highway | Other | 11, 13, 14 | French Broad River MPO, Greater Hickory MPO, High Country RPO, Land-of-Sky RPO, Southwestern RPO, Foothills RPO | HO-0015 | Exempt | DP | [6 empty] | 2024 | 460000 | 460000 | DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING.
Avery, Watauga | NC 105 | NCDOT | US 221 in Avery County to SR 1136 (Clarks Creek Road) in Watauga County. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566A | Not Funded | T | NOT FUNDED | 1000000 | NOT FUNDED |  | NOT FUNDED | 60351000 | NOT FUNDED |  | 61351000
Beaufort | OCW | WARREN FIELD (OCW) | Warren Field Airport | Acquire land and construct runway 5-23 extension and taxiway. | 0 | Aviation | STI (Prioritization) | 2 | Mid-East RPO | AV-5743 | Division 2 | T | 2030 | 2200000 |  |  | 2032 | 7800000 |  |  | 10000000
Beaufort | SR 1112 (Mouth of the Creek Road) | NCDOT | Bridge 060009 over Blounts Creek. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Mid-East RPO | B-5614 | Division 2 | BGOFF | 2022 | 319000 | 2022 | 750000 | 2026 | 17200000 |  |  | 18269000 | RIGHT-OF-WAY IN PROGRESS.
Beaufort | US 17 Business (Carolina Avenue) | NCDOT | Washington Street intersection in Washington | Install channelization, pedestrian signals, and other accommodations. |  | Highway | Safety | 2 | Mid-East RPO | HS-2402K | Region B | HSIP, T(M) |  |  |  |  | 2025 | 97000 |  |  | 97000
Beaufort | US 264 | NCDOT | NC 32 to the western town limits of Pantego | Install rumble stripes. |  | Highway | Safety | 2 | Mid-East RPO | HS-2402W | Region B | HSIP |  |  |  |  | 2025 | 575000 |  |  | 575000
Beaufort | US 264 | NCDOT | SR 1410 (Voa Road) intersection. | Construct reduced conflict intersection. | 0.5 | Highway | Safety | 2 | Mid-East RPO | HS-2002D | Statewide Mobility | HSIP, T(M) | 2022 | 16000 |  |  | 2022 | 939000 |  |  | 955000 | UNDER CONSTRUCTION.
Beaufort | SR 1306 (15th Street) | NCDOT | US 17 Business (Carolina Avenue) to Brown Street. | Widen to multi-lanes. | 1.56 | Highway | STI (Prioritization) | 2 | Mid-East RPO | U-5860 | Division 2 | T | 2026 | 18100000 | 2026 | 4200000 | 2028 | 33600000 |  |  | 55900000
Beaufort | US 17 | NCDOT | SR 1130 (C.C. Road) to south of SR 1127 (Possum Track Road). | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 2 | Mid-East RPO | R-2513E | Not Funded | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 18300000 | NOT FUNDED |  | 23500000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | BO-2402 | Division 2 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Locations in Division 2 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | R-5782 | Division 2 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Various locations in Division 2. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | BO-2602 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Construct safety improvement. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702 | [11 empty] | IN PROGRESS
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Construct safety improvement. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702DIV | Division 2 | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 376000 |  |  | 406000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Construct safety improvement. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702REG | Region B | HSIP, T(M) | 2020 | 131000 |  |  | 2020 | 3126000 |  |  | 3257000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Construct safety improvement. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702SW | Statewide Mobility | HSIP, T(M) | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Construct safety improvements. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2002 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Construct safety improvements. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2402 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017DIV | Division 2 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017REG | Region B | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Routes in Division 2. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO | W-5202 | Region B | [10 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Various locations in Division 2 | Safety Improvements. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2602 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Locations in Division 2. | Implementation of traffic separation study and closures in Division 2. |  | Rail | Rail-Highway Grade Crossing Closure | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RC-2002 | Division 2
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Locations in Division 2. | Construct highway-rail grade crossing safety improvements in Division 2. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RX-2002 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Locations in Division 2. | Construct highway-rail grade crossing safety improvements in Division 2. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RX-2402 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | Various | NCDOT | Locations in Division 2. | Construct highway-rail grade crossing safety improvements in Division 2. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RX-2602 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Beaufort, Pitt, Edgecombe, Pamlico | NC 33 | NCDOT | SR 1240 (Mayo Road) to West of SR 1002 (Bay City Road) in Beaufort County; West of SR 1965 (Main Street Extension) to East of SR 1136 (Gray Road) in Chocowinity; West of SR 1143 (Taylor Road) to East of SR 1568 (Calvert Street in Pitt County | Install rumble stripes. | 56 | Highway | Safety | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Upper Coastal Plain RPO | HS-2402C | Region A, B | HSIP, T(M) |  |  |  |  | 2025 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION.
Bertie | NC 11 | NCDOT | Bridge 070024 over Cashie River | Replace bridge. |  | Highway | Bridges | 1 | Peanut Belt RPO | BR-0153 | Region A | BFP |  |  |  |  | 2025 | 4990000 |  |  | 4990000
Bertie | US 13 / US 17 (Future I-87) | NCDOT | Bridges 070155, 070156, 070158, and 070159 over Roanoke River overflow | Repair bridges. | 1 | Highway | Bridges | 1 | Peanut Belt RPO | HB-0070 | Statewide Mobility | BFP, T(M) |  |  |  |  | 2026 | 4300000 |  |  | 4300000
Bertie | US 13 / US 17 (Future I-87) | NCDOT | SR 1154 (Buds Lane) to US 13 Business Overpass | Rehabilitate pavement. | 2.18 | Highway | Interstate Maintenance | 1 | Peanut Belt RPO | HI-0024 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2029 | 2200000 |  |  | 2200000
Bertie | US 17 (Future I-87) | NCDOT | US 13 Business Overpass to pavement joint near US 17 | Rehabilitate open grade friction course pavement. | 6.48 | Highway | Interstate Maintenance | 1 | Peanut Belt RPO | HI-0025 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2029 | 2000000 |  |  | 2000000
Bertie | NC 45 | NCDOT | Hertford County line to Washington County line. | Modernize roadway. | 24.8 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809
Bertie | NC 45 | NCDOT | Southern city limits of Colerain to Hertford Count line. | Modernize roadway. | 3.15 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809C | Division 1 | [10 empty] | COMPLETE.
Bertie | NC 45 | NCDOT | US 17 at Midway to southern city limits of Colerain. | Modernize roadway. | 12.41 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809B | Division 1 | BGLT5, T(M) | 2025 | 6100000 | 2025 | 13000000 | 2028 | 33000000 |  |  | 52100000 | RIGHT-OF-WAY IN PROGRESS
Bertie | NC 45 | NCDOT | Washington County line to US 17 at Midway. | Modernize roadway. | 9.26 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809A | Division 1 | BGLT5, T | 2023 | 315000 | 2023 | 150000 | 2025 | 13670000 |  |  | 14135000 | UNDER CONSTRUCTION.
Bertie, Currituck | Various | NCDOT | Routes in Division 1. | Upgrade warning signs at curves. |  | Highway | Safety | 1 | Peanut Belt RPO, Albemarle RPO | HS-2001E | Division 1 | HSIP, T(M) |  |  |  |  | 2023 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Construct safety improvement. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701DIV | Division 1 | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 376000 |  |  | 406000
Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Construct safety improvement. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701REG | Region A | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 376000 |  |  | 406000
Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Construct safety improvement. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701SW | Statewide Mobility | HSIP, T(M) | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
Bertie, Hertford, Gates | US 13; NC 11 / SR 1212 (Shortcut Road) | NCDOT | SR 1302 (Lea Lumber Company Road) in Bertie County to north of SR 1418 (Arrow Road) in Hertford County, and SR 1212 (Shortcut Road) in Hertford County to US 158 in Gates County; 450 feet south of SR 1130 (Modlin Road) to US 13. | Install rumble stripes and pavement markings. | 22.2 | Highway | Safety | 1 | Peanut Belt RPO, Albemarle RPO | HS-2001G | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 896000 |  |  | 896000
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | BO-2401 | Division 1 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Locations in Division 1 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | R-5781 | Division 1 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Various locations in Division 1. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | BO-2601 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Construct safety improvements. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2001 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Construct safety improvements. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2401 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Construct safety improvements. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701 | [11 empty] | IN PROGRESS.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016DIV | Division 1 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016REG | Region A | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Routes in Division 1. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5201 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Locations in Division 1. | Implementation of traffic separation study and closures in Division 1. |  | Rail | Rail-Highway Grade Crossing Closure | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RC-2001 | Division 1 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Locations in Division 1. | Construct highway-rail grade crossing safety improvements in Division 1. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RX-2001 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Locations in Division 1. | Construct highway-rail grade crossing safety improvements in Division 1. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RX-2401 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Locations in Division 1. | Construct highway-rail grade crossing safety improvements in Division 1. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RX-2601 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Pasquotank, Perquimans, Tyrrell, Washington | Various | NCDOT | Various locations in Division 1 | Safety Improvements. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2601 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen | EYF | FIELD (EYF) CURTIS L BROWN JR | Curtis L Brown Jr. Field | Extend runway to 5500 feet and parallel taxiway. |  | Aviation | STI (Prioritization) | 6 | Mid-Carolina RPO | AV-5826 | Division 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 920000 | 10120000
Bladen | SR 1536 (James Porter Road) | NCDOT | Bridge 080198 over Kelly Canal. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Mid-Carolina RPO | B-6008 | Division 6 | [10 empty] | UNDER CONSTRUCTION.
Bladen | NC 87 | NCDOT | Smithfield Foods processing center north of Tar Heel. | Improve roadway. | 1.2 | Highway | Economic Development | 6 | Mid-Carolina RPO | R-5866 | Region C | T |  |  |  |  | 2018 | 1042000 |  |  | 1042000 | COMPLETE. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SMITHFIELD FOODS PROCESSING.
Bladen | NC 410 / NC 131 | DIVISION | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Mid-Carolina RPO | HN-0025 | Region C | CRPLT5, T(M) |  |  | 2025 | 20000 | 2025 | 2375000 | 2024 | 275000 | 2670000
Bladen | NC 41 (Broad Street) | NCDOT | SR 1150 (Peanut Road)/Newton Street | Revise traffic signal and install pedestrian signals and crosswalks. | 0.5 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406T | Region C | HSIP, T(M) |  |  | 2026 | 150000 | 2026 | 330000 |  |  | 480000
Bladen | NC 87 | NCDOT | Columbus County line to SR 1725 (Braddy Plantation Road) in Bladen County. | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406HB | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 300000 |  |  | 300000
Bladen | NC 87 | NCDOT | NC 131 intersection in Tarheel. | Install traffic signal. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406N | Region C | HSIP, T(M) | 2025 | 5000 | 2025 | 130000 | 2026 | 510000 |  |  | 645000
Bladen | NC 87 | NCDOT | SR 1004 (Tar Heel Road) / SR 1316 (Tar Heel Ferry Road) intersections. | Revise traffic signals. | 0.5 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006L | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 121000 |  |  | 121000 | UNDER CONSTRUCTION.
Bladen | NC 87 | NCDOT | SR 1725 (Braddy Plantation Road) to East of NC 87 Business. | Install centerline and shoulder sinusoidal rumble stripes. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406HA | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 340000 |  |  | 340000 | UNDER CONSTRUCTION.
Bladen | SR 1004 (Tar Heel Road) | NCDOT | NC 87 to Robeson County line | Install rumble strips and long life pavement markings and markers. | 2.6 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406X | Division 6 | HSIP, T(M) |  |  |  |  | 2026 | 170000 |  |  | 170000
Bladen | SR 1325 (Gum Springs Road) | NCDOT | Near SR 1327 (Live Oak Methodist Church Road). | Improve curve. | 0.25 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006M | Division 6 | HSIP, T(M) |  |  |  |  | 2024 | 174000 |  |  | 174000
Bladen | US 701 | NCDOT | SR 1806 (Mercer Mill Road), Swanzy Street, and King Street intersections in Elizabethtown | Install crosswalks, pedestrian signal heads, and upgrade traffic signals. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406E | Region C | HSIP, T(M) |  |  |  |  | 2025 | 716000 |  |  | 716000
Bladen | NC 87 | NCDOT | SR 1730 (Elwell Ferry Road) in Bladen County to NC 11 in Columbus County. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 6 | Cape Fear RPO, Mid-Carolina RPO | R-2561B | Not Funded | T | NOT FUNDED | 18800000 | NOT FUNDED | 6900000 | NOT FUNDED | 100800000 | NOT FUNDED |  | 126500000
Bladen, Columbus | NC 87 | NCDOT | Elizabethtown Bypass in Bladen County to US 74 / US 76 in Columbus County. | Widen to multi-lanes. | 30.2 | Highway | STI (Prioritization) | 6 | Cape Fear RPO, Mid-Carolina RPO | R-2561
Bladen, Columbus | NC 87 | NCDOT | Elizabethtown Bypass to SR 1730 (Elwell Ferry Road) in Bladen County. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | R-2561A | Not Funded | T | NOT FUNDED | 23000000 | NOT FUNDED | 8300000 | NOT FUNDED | 157400000 | NOT FUNDED |  | 188700000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | BO-2406 | Division 6 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Locations in Division 6 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | R-5786 | Division 6 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Various locations in Division 6. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | BO-2606 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6 | Construct safety improvements. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2006 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Construct safety improvement. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706 | [11 empty] | IN PROGRESS. "HF" FUNDING REPRESENTS HIGH IMPACT / LOW COST (HILC) FUNDS.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Construct safety improvement. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706DIV | Division 6 | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 376000 |  |  | 406000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Construct safety improvement. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706REG | Region C | HSIP, T(M) | 2020 | 134000 |  |  | 2020 | 519000 |  |  | 653000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Construct safety improvement. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706SW | Statewide Mobility | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 500000 |  |  | 590000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Construct safety improvement. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5806
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Construct safety improvements. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2406 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2021
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | HS-2021DIV | Division 6 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | HS-2021REG | Region C | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | HS-2021SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Various locations in Division 6 | Safety Improvements. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2606 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Locations in Division 6. | Implementation of traffic separation study and closures in Division 6. |  | Rail | Rail-Highway Grade Crossing Closure | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RC-2006 | Division 6 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Locations in Division 6. | Construct highway-rail grade crossing safety improvements in Division 6. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RX-2006 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Locations in Division 6. | Construct highway-rail grade crossing safety improvements in Division 6. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RX-2406 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Bladen, Columbus, Cumberland, Harnett, Robeson | Various | NCDOT | Locations in Division 6. | Construct highway-rail grade crossing safety improvements in Division 6. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RX-2606 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Brunswick | SUT | CAPE FEAR REGIONAL (SUT) | Cape Fear Regional Airport | Clear approach at runway 5 and runway 23. | 0 | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5739 | Division 3 | [10 empty] | UNDER CONSTRUCTION
Brunswick | Belville Elementary Multi-Use Path | BELVILLE | Along NC 133 connecting north and south entrances of Hawkeswater development to Belville Elementary School in Bellville | Construct multi-use path. | 0.37 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6026 | Division 3 | L(M), TADA |  |  |  |  | 2024 | 936000 | 2020 | 52000 | 988000 | UNDER CONSTRUCTION.
Brunswick | Gullah Geechee Heritage Trail Gap | BELVILLE | Along NC 133 south of Belville. | Construct multi-use path. | 0.22 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0153 | Division 3 | BGDA, L(M) |  |  |  |  | 2027 | 738000 | 2025 | 162000 | 900000
Brunswick | Rice Hope Multi-Use Path | BELVILLE | Along NC 133 from Morecamble Boulevard to Rice Hope Run in Belville | Construct multi-use path. | 0.17 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6025 | Division 3 | L(M), TADA |  |  |  |  | 2024 | 372000 | 2020 | 18000 | 390000 | UNDER CONSTRUCTION.
Brunswick | SR 1116 (Ocean Boulevard) | NCDOT | West of Shell Drive to Dunescape Drive in Holden Beach | Install bike lanes. | 6.14 | Bike & Ped | Locally Selected | 3 | Grand Strand Area Transportation Study | BL-0046 | Division 3 | BGDA, L(M) |  |  |  |  | 2022 | 1613000 |  |  | 1613000 | UNDER CONSTRUCTION.
Brunswick | SR 1144 (First Street) | OCEAN ISLE BEACH | East of West First Street Extension to east of Greensboro Street in Ocean Isle Beach | Construct bike lanes. | 2.88 | Bike & Ped | Locally Selected | 3 | Grand Strand Area Transportation Study | EB-6034 | Division 3 | BGDA, L(M) |  |  |  |  | 2021 | 1036000 |  |  | 1036000 | UNDER CONSTRUCTION.
Brunswick | US 17 | LELAND | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0074 | Statewide Mobility | L(M), TADA | 2025 | 25000 |  |  | 2025 | 625000 | 2023 | 183000 | 833000
Brunswick | Various | NCDOT | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 3 | Grand Strand Area Transportation Study | BL-0021 | Division 3 | TADA |  |  |  |  | 2022 | 1759000 |  |  | 1759000
Brunswick | Various | ST. JAMES | Various locations in St. James. | Replace street lights with LED lights. |  | Bike & Ped | Locally Selected | 3 | Cape Fear RPO | BN-0023 | Exempt | CRP550, L(M) |  |  |  |  | 2025 | 400000 |  |  | 400000
Brunswick | NC 211 (North Howe Street) | SOUTHPORT | East Owen Street to Dosher Hospital in Southport | Construct sidewalk. | 0.26 | Bike & Ped | STI (Prioritization) | 3 | Cape Fear RPO | EB-5982 | Division 3 | L, L(M), TA5T50 |  |  |  |  | 2025 | 195000 | 2025 | 30000 | 225000
Brunswick | SR 1300 (Ash-Little River Road Northwest) | NCDOT | Bridge 090126 over Cawcaw Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Grand Strand Area Transportation Study | B-5996 | Division 3 | BGOFF | 2022 | 100000 |  |  | 2022 | 2100000 |  |  | 2200000 | UNDER CONSTRUCTION.
Brunswick | SR 1342 (Makatoka Road Northwest) | NCDOT | Bridge 090100 over Muddy Branch. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Cape Fear RPO | B-4439 | Division 3 | BGOFF | 2022 | 550000 |  |  | 2022 | 1250000 |  |  | 1800000 | UNDER CONSTRUCTION.
Brunswick | SR 1515 (Old Mill Creek Road Southeast) | NCDOT | Bridge 090040 over Mill Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Cape Fear RPO | B-5629 | Division 3 | BGOFF | 2022 | 115000 |  |  | 2023 | 2759000 |  |  | 2874000 | UNDER CONSTRUCTION.
Brunswick | New Route | NCDOT | 0.5 miles east of Brunswick County line to 1.5 miles east of Brunswick County line on US 74. | Construct road on new location and intersecting roads with US 74 on east and west termini. | 1 | Highway | Economic Development | 3 | Cape Fear RPO | HE-0016 | Division 3 | O, T |  |  | 2025 | 40000 | 2025 | 9288000 | 2024 | 725000 | 10053000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. O FUNDS REPRESENT BRUNSWICK COUNTY PUBLIC UTILITY FUNDING.
Brunswick | I-140 | NCDOT | US 17 to north of US 74. | Rehabilitate pavement. | 5.08 | Highway | Interstate Maintenance | 3 | Wilmington Urban Area MPO | I-6036 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2024 | 11080000 |  |  | 11080000 | UNDER CONSTRUCTION.
Brunswick | NC 133 | BELVILLE | Belville Riverwalk Park entrance | Construct traffic signal and related pedestrian infrastructure |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0131 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 1458000 | 2025 | 81000 | 1539000
Brunswick | SR 1438 (Lanvale Road) | NCDOT | SR 1472 (Fletcher road / village road) intersection in Leland | Install traffic signal. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0179 | Division 3 | BGDA, HF, HF(M) |  |  |  |  | 2028 | 5330000 | 2026 | 44000 | 5374000
Brunswick | Various | NCDOT | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | HL-0103 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 342000 |  |  | 342000
Brunswick | Various | NCDOT | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | U-5990 | Division 3 | BGANY, BGDA |  |  |  |  | 2022 | 14631000 |  |  | 14631000
Brunswick | Various | NCDOT | Grand Strand Area Transportation Study Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | U-5910 | Division 3 | BGDA, L(M) | [6 empty] | 2023 | 540000 | 540000 | IN PROGRESS
Brunswick | Various | SHALLOTTE | Locations in Shallotte | Install adaptive signal system in Shallotte. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | HL-0132 | Division 3 | BGDA, CRPDA, HF(M) |  |  |  |  | 2024 | 398000 |  |  | 398000 | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS.
Brunswick | Leland | NCDOT | Piggly Wiggly. | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 3 | Cape Fear RPO | HV-0001G | Division 3 | NEVI, O(M), S(M) |  |  |  |  | 2025 | 1339000 |  |  | 1339000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM FRANCIS ENERGY CHARGING LLC
Brunswick | NC 130 | NCDOT | SR 1120 (Sabbath Home Road) / SR 1239 (Ocean View Avenue) intersection in Holden Beach. | Revise traffic signal and pavement markings. | 0.5 | Highway | Safety | 3 | Grand Strand Area Transportation Study | HS-2003G | Region B | HSIP, T(M) |  |  |  |  | 2024 | 101000 |  |  | 101000
Brunswick | NC 133 | NCDOT | SR 1518 (Daws Creek Road) to SR 1551 (Blackwell Road) | Install rumble strips. | 18.7 | Highway | Safety | 3 | Wilmington Urban Area MPO, Cape Fear RPO | HS-2403AW | Region B | HSIP |  |  |  |  | 2026 | 276000 |  |  | 276000
Brunswick | NC 133; NC 87 | NCDOT | SR 1100 (Country Club Drive) to north of Port Loop Road; South of NC 133 to north of SR 1729 (Van Galloway Trail). | Install rumble stripes and pavement markings. | 7.7 | Highway | Safety | 3 | Cape Fear RPO | HS-2403W | Region B | HSIP |  |  |  |  | 2027 | 765000 |  |  | 765000
Brunswick | SR 1300 (Ash-Little River Road) | NCDOT | NC 130 to SR 1303 (Hickman Road). | Install rumble stripes and pavement markings. | 11.02 | Highway | Safety | 3 | Cape Fear RPO, Grand Strand Area Transportation Study | HS-2403X | Division 3 | HSIP |  |  |  |  | 2027 | 630000 |  |  | 630000
Brunswick | US 17 (Future I-74) | NCDOT | SR 1130 (Mount Pisgah Road) / SR 1344 (Sellers Road) intersection. | Install signalized leftover. |  | Highway | Safety | 3 | Grand Strand Area Transportation Study | HS-2003D | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 269000 |  |  | 269000
Brunswick | US 17 (Future I-74) | NCDOT | SR 1136 (Red Bug Road) and SR 1345 (Royal Oak Road) intersections in Shallotte. | Construct reduced conflict intersection. | 0.5 | Highway | Safety | 3 | Grand Strand Area Transportation Study | HS-2003W | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION.
Brunswick | US 17 Business | NCDOT | NC 906 (Midway Road) intersection. | Install traffic signal. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003AR | Region B | HSIP, T(M) | 2025 | 48000 |  |  | 2026 | 257000 |  |  | 305000 | RIGHT-OF-WAY IN PROGRESS.
Brunswick | US 74 | NCDOT | I-140 ramp intersections in Leland. | Upgrade traffic signals and install advanced warning flasher. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AS | Statewide Mobility | HSIP |  |  |  |  | 2026 | 210000 |  |  | 210000
Brunswick | US 74 / US 76 | NCDOT | SR 1714 (Enterprise Drive) and SR 1494 (Wood Treatment Road) intersections in Leland. | Install traffic signals. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003O | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 533000 |  |  | 533000
Brunswick | US 74 / US 76 (Andrew Jackson Highway) | NCDOT | SR 1426 (Lanvale Road) eastbound ramp. | Install traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AS | Region B | HSIP, T(M) |  |  |  |  | 2025 | 450000 |  |  | 450000
Brunswick | I-74 (Carolina Bays Parkway Extension) | NCDOT | South Carolina state line to US 17 at NC 130. | Construct freeway on new location. |  | Highway | STI (Prioritization) | 3 | Cape Fear RPO, Grand Strand Area Transportation Study | R-5876 | Not Funded | O | NOT FUNDED | 179200000 | NOT FUNDED | 7500000 | NOT FUNDED | 623000000 | NOT FUNDED |  | 809700000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
Brunswick | NC 133 | NCDOT | US 17 / US 74 / US 76 to SR 1554 (Old River Road). | Modernize roadway. | 0.48 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5914 | Division 3 | T |  |  |  |  | 2023 | 6933000 |  |  | 6933000 | UNDER CONSTRUCTION.
Brunswick | NC 211 | NCDOT | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5021 | Division 3 | BGANY, T(M) |  |  | 2023 | 10850000 | 2022 | 239876000 |  |  | 250726000 | UNDER CONSTRUCTION.
Brunswick | US 17 (Future I-74) | NCDOT | US 17 Business south of Shallotte and US 17 Business north of Shallotte. | Construct reduced conflict intersections. | 1 | Highway | STI (Prioritization) | 3 | Grand Strand Area Transportation Study | R-5857 | Statewide Mobility | T | 2023 | 770000 | 2024 | 325000 | 2026 | 29810000 |  |  | 30905000 | RIGHT-OF-WAY IN PROGRESS.
Brunswick | US 17 (Future I-74; Shallotte Bypass) | NCDOT | SR 1357 (Smith Avenue) intersection in Shallotte | Upgrade intersection to interchange. | 1 | Highway | STI (Prioritization) | 3 | Grand Strand Area Transportation Study | U-5862 | Region B | T | 2028 | 8800000 | 2028 | 1900000 | 2031 | 43600000 |  |  | 54300000
Brunswick | US 17 Business (Main Street) | NCDOT | Wall Street / Shallotte Avenue intersection in Shallotte | Realign intersection. | 0.5 | Highway | STI (Prioritization) | 3 | Grand Strand Area Transportation Study | U-5788 | Division 3 | T |  |  |  |  | 2021 | 1964000 |  |  | 1964000 | UNDER CONSTRUCTION.
Brunswick | I-40 / US 17 (Wilmington Bypass) | NCDOT | US 74 / US 76 in Brunswick County to SR 1430 (Cedar Hill Road). | Construct new route. | 7.6 | Highway | Transition | 3 | Wilmington Urban Area MPO | R-2633BA | Pre-STI (Transition) | NHP |  |  |  |  | 2014 | 30750000 |  |  | 30750000 | COMPLETE. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK 2014 - 2025.
Brunswick | NC 113 (River Road) | NCDOT | Military Ocean Terminal Sunny Point Crossing 3101655V in Southport. | Improve highway-rail grade crossing safety. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO | RX-2403A | Division 3 | RR |  |  |  |  | 2031 | 750000 |  |  | 750000
Brunswick, New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | NC 87 south of Bishop to US 74 / US 76 east of Malmo in Brunswick County. | Construct four lane divided freeway on new location. |  | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633AB | [11 empty] | COMPLETE.
Brunswick, New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | NC 87 south of Bishop to US 74 / US 76 east of Malmo in Brunswick County. | Construct four lane divided freeway on new location. | 5.3 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633AA | Pre-STI (Transition) | NHP |  |  |  |  | 2010 | 6810000 |  |  | 6810000 | COMPLETE. GARVEE BOND FUNDING: $31.05M FOR CONSTRUCTION, PAYBACK 2010 - 2021.
Brunswick, New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | US 17 south of NC 87 in Brunswick County to I-40 in New Hanover County. | Construct four lane divided freeway on new location. | 20.2 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633
Brunswick, New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | US 17 south of NC 87 in Brunswick County to I-40 in New Hanover County. | Implementation of Intelligent Transportation Systems (ITS). | 20.13 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633D | Pre-STI (Transition) | [10 empty] | COMPLETE.
Brunswick, New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | US 74 / US 76 east of Malmo in Brunswick County to west of US 421 north of Wilmington. | Construct four-lane divided freeway on new location. |  | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633BC | [11 empty] | COMPLETE.
Brunswick, New Hanover | Cape Fear Public Transportation Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Various locations | Funding for the continuation of complimentary para transit service to two counties and four municipalities with in UAZ. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-5246 | Public Transit | 5307, L | [6 empty] | 2023 | 1093000 | 1093000
Brunswick, Onslow, New Hanover | Various | NCDOT | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO | W-5203SW | Statewide Mobility
Buncombe | AVL | ASHEVILLE REGIONAL AIRPORT (AVL) | Asheville Regional Airport | Modernize building. |  | Aviation | Other | 13 | French Broad River MPO | AO-0001 | Exempt | FED, HF, L |  |  |  |  | 2022 | 153808000 |  |  | 153808000 | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT
Buncombe | AVL | ASHEVILLE REGIONAL AIRPORT (AVL) | Asheville Regional Airport | Construct runway. |  | Aviation | STI (Prioritization) | 13 | French Broad River MPO | AV-5735 | Region G | [10 empty] | UNDER CONSTRUCTION
Buncombe | Beaverdam Creek Greenway | ASHEVILLE | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5774B | Division 13 | BGANY, BGDA, L(M), TADA | 2025 | 608000 |  |  | 2026 | 3450000 |  |  | 4058000
Buncombe | Bent Creek Greenway | BUNCOMBE COUNTY | Hominy Creek River Park to Western NC Farmers Market in Asheville | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5823 | Division 13 | BGDA, L(M) | [6 empty] | 2029 | 400000 | 400000
Buncombe | Black Mountain Riverwalk Greenway | BLACK MOUNTAIN | Black Mountain Avenue to Flat Creek Greenway in Black Mountain | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5547A | Division 13 | BGANY, L(M) |  |  |  |  | 2026 | 1599000 | 2023 | 290000 | 1889000
Buncombe | Black Mountain Riverwalk Greenway | BLACK MOUNTAIN | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5547B | Division 13 | BGANY, L(M) | 2025 | 20000 |  |  | 2026 | 1551000 | 2022 | 184000 | 1755000
Buncombe | Black Mountain Riverwalk Greenway | BLACK MOUNTAIN | Existing Flat Creek Greenway Trailhead north of US 70 to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5547 | Division 13 | [10 empty] | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.991M. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.915M.
Buncombe | Coxe Avenue | ASHEVILLE | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5831 | Division 13 | BGANY, BGDA, L(M), TADA | 2026 | 300000 |  |  | 2027 | 11003000 | 2023 | 900000 | 12203000 | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP.
Buncombe | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | NCDOT | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5824 | Division 13 | BGANY, BGDA, L(M) |  |  |  |  | 2027 | 3844000 | 2021 | 1310000 | 5154000 | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES.
Buncombe | NC 251 (Riverside Drive) | ASHEVILLE | US 19 / US 23 / US 70 (Exit 25) to the Mills at Riverside in Asheville | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5774A | Division 13 | BGDA, L(M), TADA | 2026 | 4259000 |  |  | 2027 | 6010000 |  |  | 10269000
Buncombe | NC 251 (Riverside Drive) | BUNCOMBE COUNTY | US 19 / US 23 / US 70 (Exit 25) to US 25 in Asheville | Construct multi-use path along Beaverdam Creek. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5774 | Division 13 | BGDA, L(M) | [6 empty] | 2020 | 2000000 | 2000000 | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION
Buncombe | NC 251 / SR 1781 (Broadway Street) | NCDOT | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0005 | Division 13 | BGDA, HF, HF(M), HSIP |  |  |  |  | 2022 | 1124000 | 2021 | 4000 | 1128000 | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID.
Buncombe | Reems Creek Greenway | BUNCOMBE COUNTY | Western edge of Weaverville to Karpen Soccer Fields in Weaverville | Construct multi-use path. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5821 | Division 13 | BGDA, L(M) | [6 empty] | 2029 | 600000 | 600000 | IN PROGRESS
Buncombe | SR 1319 (Johnston Boulevard) | ASHEVILLE | SR 3548 (Patton Avenue) to Iona Circle in Asheville | Construct sidewalks. | 0.95 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5944 | Division 13 | L, TAANY |  |  |  |  | 2025 | 2350000 |  |  | 2350000 | $1.88M OF STBG-DA FUNDS SWAPPED FOR $1.88M IN TAP-ANYAREA FUNDS ON 12-12-24.
Buncombe | SR 2002 (Riceville Road) | NCDOT | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0076 | Division 13 | HF(M), TADA | 2026 | 788000 |  |  | 2027 | 1951000 | 2024 | 374000 | 3113000 | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP
Buncombe | SR 2032 (New Haw Creek Road) | ASHEVILLE | Beverly Road to SR 2034 (Bell Road) in Asheville | Construct sidewalks. | 0.79 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5947 | Division 13 | BGANY, L(M) |  |  |  |  | 2024 | 2365000 | 2024 | 10000 | 2375000 | $1.9M IN BGANY USED AS PART OF FUND SWAP
Buncombe | SR 3075 (Onteora Boulevard) | ASHEVILLE | Lincoln Avenue to Raleigh Road in Asheville | Construct sidewalks. | 0.39 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5948 | Division 13 | BGDA, L(M), TADA |  |  |  |  | 2023 | 1140000 |  |  | 1140000 | UNDER CONSTRUCTION.
Buncombe | Various | ASHEVILLE | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5790 | Division 13 | BGDA, L, L(M), TAANY, TADA |  |  |  |  | 2024 | 1628000 | 2017 | 131000 | 1759000 | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23.
Buncombe | Various | NCDOT | Locations in Asheville | Construct pedestrian improvements. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0006 | Division 13 | BGDA, L, TAANY |  |  |  |  | 2027 | 750000 | 2026 | 75000 | 825000 | $501K OF STBG-DA FUNDS SWAPPED FOR $501K IN TAP-ANYAREA FUNDS ON 12-12-24.
Buncombe | Deaverview Road | ASHEVILLE | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Bike & Ped | STI (Prioritization) | 13 | French Broad River MPO | EB-5965 | Division 13 | L(M), TAANY | 2028 | 6100000 | 2028 | 1100000 | 2031 | 7000000 | 2026 | 710000 | 14910000
Buncombe | North Rad Greenway | NCDOT | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Bike & Ped | STI (Prioritization) | 13 | French Broad River MPO | EB-5822 | Division 13 | L(M), TAANY | 2026 | 2100000 | 2026 | 100000 | 2027 | 2200000 | 2019 | 600000 | 5000000 | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23.
Buncombe | New Leicester Highway | ASHEVILLE | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Bike & Ped | Transition | 13 | French Broad River MPO | U-5190 | Pre-STI (Transition) | BGANY, BGDA, L(M) | 2020 | 241000 |  |  | 2022 | 3322000 |  |  | 3563000 | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE
Buncombe | N/A | NCDOT | N/A | N/A |  | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | A-0010AA | Region G
Buncombe | New Route | NCDOT | Hakkon Industries in Enka Commerce Park. | Construct access road. | 0.3 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | U-6251 | Exempt | ADHSL, HF | [6 empty] | 2021 | 606000 | 606000 | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. HF REPRESENTS SPOT MOBILITY FUNDS.
Buncombe | New Route | NCDOT | US 19 / US 23 (Smokey Park Highway) to Walkoff Way. | Construct access road. | 0.3 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | U-6251A | Exempt | ADHSL, L |  |  |  |  | 2022 | 2850000 |  |  | 2850000 | UNDER CONSTRUCTION.
Buncombe | US 19 / US 23 (Smokey Park Highway) | NCDOT | SR 3688 (Enka Heritage Parkway) intersection. | Construct intersection improvements. | 0.5 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | U-6251B | Exempt | ADHSL, HF, L | 2022 | 133000 |  |  | 2023 | 395000 |  |  | 528000 | UNDER CONSTRUCTION.
Buncombe | SR 1296 (Brooks Branch Road) | NCDOT | Bridge 100536 over Newfound Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-6018 | Division 13 | BGOFF | 2021 | 55000 |  |  | 2021 | 872000 |  |  | 927000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION.
Buncombe | SR 2027 (Martins Creek Road) | NCDOT | Bridge 100142 over Martin Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Land-of-Sky RPO | B-6016 | Division 13 | BGOFF | 2022 | 50000 |  |  | 2022 | 500000 |  |  | 550000 | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014
Buncombe | US 19 / US 23 / US 25 / US 70 | NCDOT | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-4443 | Statewide Mobility | BFP, T(M) | 2028 | 700000 | 2028 | 660000 | 2031 | 50100000 |  |  | 51460000 | COORDINATE WITH A-0010A
Buncombe | US 19 / US 23 / US 25 / US 70 | NCDOT | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-4442 | Statewide Mobility | NHPB, T(M) | 2022 | 400000 |  |  | 2022 | 29996000 |  |  | 30396000 | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION.
Buncombe | I-26 | NCDOT | Mile marker 35. | Construct new interchange. |  | Highway | Economic Development | 13 | French Broad River MPO | HE-0001A | Exempt | DP, HF, HF(M) |  |  |  |  | 2024 | 45242000 |  |  | 45242000 | DP represents MPDG Rural Grant
Buncombe | I-26 | NCDOT | SR 3865 (Frederick Law Olmstead Way East) interchange | Construct new interchange near an access road near mile marker 35. | 1 | Highway | Economic Development | 13 | French Broad River MPO | HE-0001 | Exempt | HF | 2022 | 200000 |  |  |  |  | 2022 | 4659000 | 4859000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY.
Buncombe | New Route | NCDOT | Frederick Law Olmstead Way East to I-26 | Construct two lane road with sidewalk. Clearing for utilities. |  | Highway | Economic Development | 13 | French Broad River MPO | HE-0001BA | Exempt | HF |  |  |  |  | 2025 | 1400000 |  |  | 1400000
Buncombe | New Route | NCDOT | Frederick Law Olmstead Way East to I-26. | Construct two lane road with sidewalk. |  | Highway | Economic Development | 13 | French Broad River MPO | HE-0001B | Exempt | DP, HF(M) |  |  |  |  | 2026 | 15000000 |  |  | 15000000 | DP represents MPDG Rural Grant
Buncombe | SR 3684 (Walk Off Way) | NCDOT | Haakon Industries in Enka Commerce Park. | Extend roadway. | 0.27 | Highway | Economic Development | 13 | French Broad River MPO | U-6230 | Division 13 | T |  |  |  |  | 2021 | 1300000 |  |  | 1300000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR HAAKON INDUSTRIES. AWARD AMOUNT = $1,300,000 - COMPLETE.
Buncombe | I-240 | NCDOT | Mile marker 4.0 to mile marker 9.0. | Rehabilitate pavement. | 4.69 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5901 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 21000000 |  |  | 21000000
Buncombe | I-40 | NCDOT | East of SR 1224 (Monte Vista Road) to pavement joint west of SR 3412 (Sand Hill Road). | Reconstruct pavement. | 1.39 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-2513AA | Statewide Mobility | HP, NHFP, NHP | 2023 | 2000000 | 2023 | 100000 | 2024 | 82516000 |  |  | 84616000 | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS.
Buncombe | I-40 | NCDOT | Mile marker 37.0 to mile marker 44.0. | Rehabilitate bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 7.17 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5888B | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 6900000 |  |  | 6900000
Buncombe | I-40 | NCDOT | Mile marker 37.0 to mile marker 44.0. | Rehabilitate pavement and bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 6.5 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5888 | Statewide Mobility
Buncombe | I-40 | NCDOT | Mile marker 37.0 to mile marker 44.0. | Rehabilitate pavement and bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 6.73 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5888A | Statewide Mobility | [10 empty] | COMPLETE
Buncombe | I-40 | NCDOT | Mile marker 44.0 to mile marker 50.0. | Rehabilitate pavement and preserve bridges 100334, 100339, 100344, 100347, 100352, 100356, 100358, 10036, 100369, 100374, 100377, and 1000378. | 4 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5889
Buncombe | I-40 | NCDOT | Mile marker 44.0 to mile marker 50.0. | Rehabilitate pavement and preserve bridges 100334, 100339, 100344, 100347, 100352, and 100356. | 4.62 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5889B | Statewide Mobility | NHPIM, T |  |  |  |  | 2023 | 39936000 |  |  | 39936000 | UNDER CONSTRUCTION.
Buncombe | I-40 | NCDOT | Mile marker 46.0 to mile marker 50.0. | Preserve bridges 100334, 100339, 100344, 100347, 100352, 100356, 100358, 10036, 100369, 100374, 100377, and 1000378. | 4.65 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5889A | Statewide Mobility | [10 empty] | COMPLETE.
Buncombe | I-40 | NCDOT | Mile marker 50.0 to mile marker 55.0. | Rehabilitate pavement. | 4.96 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-6063 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 30222000 |  |  | 30222000 | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034
Buncombe | I-40 | NCDOT | Mile marker 55.0 to mile marker 67.5. | Rehabilitate pavement. | 11.99 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5890 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 23160000 |  |  | 23160000 | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033.
Buncombe | 9th Street | NCDOT | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Highway | Locally Selected | 13 | French Broad River MPO | HL-0013 | Division 13 | BGANY, BGDA, L(M) | 2025 | 120000 |  |  | 2026 | 1300000 | 2022 | 315000 | 1735000 | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
Buncombe | SR 3214 (Biltmore Avenue) | ASHEVILLE | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Highway | Locally Selected | 13 | French Broad River MPO | HL-0014 | Division 13 | BGANY, BGDA, L(M) | 2026 | 25000 |  |  | 2027 | 340000 | 2025 | 75000 | 440000 | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
Buncombe | US 19 / US 23 Business (Haywood Road) | NCDOT | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Highway | Locally Selected | 13 | French Broad River MPO | HL-0003 | Region G | BGANY, BGDA, HF, HF(M), L |  |  |  |  | 2025 | 8110000 | 2022 | 689000 | 8799000 | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
Buncombe | NC 63 (Leicester Highway) | NCDOT | SR 1615 (Gilbert Road) to west of SR 1004 (Newfound Road) in Asheville. | Widen to multi-lanes, some relocation. | 4.32 | Highway | Pre-STI (Historic) | 13 | French Broad River MPO | U-3301 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION - DESIGN BUILD PROJECT
Buncombe | US 25A (Sweeten Creek Road) | NCDOT | SR 3081 (Rock Hill Road) to SR 3079 (Roberts Road) | Widen to multi-lanes. | 1.473 | Highway | Pre-STI (Historic) | 13 | French Broad River MPO | U-2801B | [11 empty] | COMPLETE
Buncombe | NC 63 | NCDOT | SR 1220 (South Turkey Creek Road) intersection near Leicester. | Construct turn lane. | 0.5 | Highway | Safety | 13 | French Broad River MPO | HS-2013P | Region G | HSIP | 2026 | 5000 |  |  | 2027 | 715000 |  |  | 720000
Buncombe | SR 1002 (Old Leicester Highway) | NCDOT | NC 63 to SR 1607 (Bear Creek Road) near Leicester | Install guardrail. |  | Highway | Safety | 13 | French Broad River MPO | HS-2413I | Division 13 | HSIP |  |  |  |  | 2026 | 267000 |  |  | 267000
Buncombe | SR 1003 (Reems Creek Road) | NCDOT | SR 2106 (Parker Cove Road) to SR 2114 (Sugar Cove Road) near Weaverville. | Install guardrail. | 3.61 | Highway | Safety | 13 | French Broad River MPO | HS-2013K | Division 13 | HSIP |  |  |  |  | 2024 | 274000 |  |  | 274000
Buncombe | SR 1332 (North Louisiana Avenue) | NCDOT | SR 1338 (Emma Road) intersection near Asheville. | Install pedestrian signal phasing, high visibility crosswalks, sidewalk and curb ramps. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813C | Division 13 | HSIP, T(M) | 2022 | 2000 |  |  | 2023 | 156000 |  |  | 158000 | UNDER CONSTRUCTION.
Buncombe | SR 1727 (Monticello Road) | NCDOT | SR 1882 (New Stock Road) to east of NC 251 (Old Marshall Highway) | Install guardrail. |  | Highway | Safety | 13 | French Broad River MPO | HS-2413J | Division 13 | HSIP |  |  |  |  | 2026 | 300000 |  |  | 300000
Buncombe | SR 1781 (Broadway Street) | NCDOT | N. Lexington Avenue/I-240 westbound on-ramp in Asheville. | Install pedestrian signals and upgrade curb ramps. | 0.1 | Highway | Safety | 13 | French Broad River MPO | HS-2413W | Division 13 | HSIP |  |  |  |  | 2026 | 74000 |  |  | 74000
Buncombe | SR 2002 (Riceville Road) | NCDOT | North of US 70 to SR 2419 (Bull Creek Road) near Haw Creek. | Install 6" long life pavement markings. | 3.64 | Highway | Safety | 13 | French Broad River MPO | W-5213G | Division 13 | HSIP, T(M) |  |  |  |  | 2024 | 909000 |  |  | 909000 | UNDER CONSTRUCTION.
Buncombe | SR 2435 (Old US 70 Highway) | NCDOT | Woolwine Drive to the bus entrance at Owen Middle School | Construct pedestrian improvements. | 0.2 | Highway | Safety | 13 | French Broad River MPO | HS-2413O | Region G | HSIP | 2027 | 50000 | 2027 | 1000 | 2028 | 378000 |  |  | 429000
Buncombe | SR 2806 (Garren Creek Road) | NCDOT | SR 2815 (Village Road) to SR 2786 (Flat Creek Road / Morgan Hill Road) near Fairview. | Install shoulder guardrail. | 6.53 | Highway | Safety | 13 | Land-of-Sky RPO | W-5813I | Division 13 | HSIP, T(M) |  |  |  |  | 2022 | 460000 |  |  | 460000 | COMPLETE
Buncombe | SR 3075 (Onteora Boulevard) | NCDOT | Bridge 100460 over I-40. | Construct sidewalk and upgrade bridge rail. | 0.5 | Highway | Safety | 13 | French Broad River MPO | HS-2013O | Division 13 | HSIP |  |  |  |  | 2025 | 395000 |  |  | 395000
Buncombe | SR 3116 (Mills Gap Road) | NCDOT | SR 3157 (Weston Road) and SR 3136 (Cane Creek Road). | Install rumble stripes with long life pavement markings. | 2.3 | Highway | Safety | 13 | French Broad River MPO | HS-2413T | Division 13 | HSIP, T(M) |  |  |  |  | 2027 | 51000 |  |  | 51000
Buncombe | SR 3136 (Cane Creek Road) | NCDOT | SR 3116 (Mills Gap Road) to US 74 Alternate near Fairview | Install rumble stripes and long life pavement markings. |  | Highway | Safety | 13 | French Broad River MPO | HS-2413G | Division 13 | HSIP, T(M) |  |  |  |  | 2026 | 294000 |  |  | 294000
Buncombe | SR 3556 (Amboy Road) | NCDOT | Short Michigan Avenue intersection in Asheville. | Install Rectangular Rapid Flashing Beacon (RRFB) with crosswalk lighting, and upgrade curb ramps and sidewalk. | 0.1 | Highway | Safety | 13 | French Broad River MPO | HS-2413X | Division 13 | HSIP |  |  | 2026 | 25000 | 2026 | 29000 |  |  | 54000
Buncombe | US 19 / US 23 / US 74 ALT (Patton Avenue) | NCDOT | US 19 / US 23 Business (Haywood Road) / SR 1319 (Johnston Road) intersection in Asheville. | Install pedestrian signal phasing, high visibility crosswalks, and curb ramps. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813E | Region G | HSIP, T(M) |  |  |  |  | 2023 | 144000 |  |  | 144000 | UNDER CONSTRUCTION.
Buncombe | US 19 / US 23 / US 74 ALT (Smokey Park Highway) | NCDOT | I-40 to Cooper Boulevard | Install pedestrian signals and crosswalks, and construct sidewalks. | 26.2 | Highway | Safety | 13 | French Broad River MPO | HS-2413K | Region G | HSIP |  |  | 2025 | 25000 | 2025 | 905000 |  |  | 930000
Buncombe | US 19 / US 23 / US 74 ALT (Smokey Park Highway) | NCDOT | Old Haywood Road intersection in Asheville. | Install pedestrian signal phasing, high visibility crosswalks, and curb ramps. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813F | Region G | HSIP, T(M) |  |  |  |  | 2023 | 106000 |  |  | 106000 | UNDER CONSTRUCTION.
Buncombe | US 25 | NCDOT | US 25 (McDowell Street) at Doctor's Drive / Asheville High School entrance. | Install pedestrian signals, high visibility crosswalks, and curb ramps. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813A | Region G | HSIP, T(M) |  |  |  |  | 2022 | 64000 |  |  | 64000 | UNDER CONSTRUCTION.
Buncombe | US 70 (Tunnel Road); US 74 ALT (South Tunnel Road) | NCDOT | Old Chunns Cove Road intersection in Asheville; Main Mall Entrance (east leg) and Lower Mall entrance intersections in Asheville. | Install curb ramps, sidewalk, and signal upgrades. | 1 | Highway | Safety | 13 | French Broad River MPO | W-5813G | Region G | HSIP, T(M) |  |  |  |  | 2022 | 335000 |  |  | 335000 | UNDER CONSTRUCTION.
Buncombe | US 70 / US 74 ALT (College Street);US 70 / US 74 ALT (Tunnel Road) | NCDOT | SR 3284 (Charlotte Street); Kenilworth Road/Kenilworth Knolls | Construct pedestrian improvements. | 0.1 | Highway | Safety | 13 | French Broad River MPO | HS-2413N | Region G | HSIP, T(M) |  |  | 2027 | 105000 | 2027 | 175000 |  |  | 280000
Buncombe | Various | NCDOT | Routes in Division 13. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Highway | Safety | 13 | French Broad River MPO | W-5213DIV | Division 13 | HSIP, T(M) | 2020 | 50000 |  |  | 2020 | 700000 |  |  | 750000 | IN PROGRESS.
Buncombe | French Broad River West Greenway | NCDOT | French Broad River Park to Haywood Road. | Construct greenway. | 0.9 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019B | Division 13 | [10 empty] | UNDER CONSTRUCTION
Buncombe | I-26 | NCDOT | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513C | Not Funded | NHP, T(M) | NOT FUNDED | 8900000 | NOT FUNDED | 13400000 | NOT FUNDED | 261701000 | NOT FUNDED |  | 284001000
Buncombe | I-26 | NCDOT | NC 191 (Brevard Road). | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-5504 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT
Buncombe | I-26 (US 19 / US 23) | NCDOT | NC 251 / SR 1781 (Broadway Street) to US 25 / US 70 | Widen roadway to eight and six lanes. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AG | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 230000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 207600000 |  |  | 212430000
Buncombe | I-26 (US 19 / US 23) | NCDOT | SR 1882 (New Stock Road) interchange in Asheville | Construct interchange improvements and widen I-26 to north of SR 1720 (Aiken Road). |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AE | Region G | NHP | 2028 | 18600000 | 2028 | 3102000 | 2031 | 93900000 |  |  | 115602000
Buncombe | I-26 (US 19 / US 23) | NCDOT | SR 2207 (North Buncombe School Road) to south of SR 2148 (Stockton Road) | Upgrade roadway to interstate standards. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AK | Not Funded | T | NOT FUNDED | 700000 | NOT FUNDED |  | NOT FUNDED | 27001000 | NOT FUNDED |  | 27701000
Buncombe | I-26 (US 19 / US 23) | NCDOT | US 25 (Merrimon Avenue) interchange in Asheville | Construct interchange improvements. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AD | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 46300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74500000 |  |  | 122400000
Buncombe | I-26 (US 19 / US 23) | NCDOT | US 25 / US 70 interchange in Asheville | Construct interchange improvements. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AF | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4656000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 737000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36400000 |  |  | 41793000
Buncombe | I-26 (US 19 / US 23) | NCDOT | US 25 / US 70 to SR 2207 (North Buncombe School Road) | Upgrade roadway to interstate standards. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AJ | Not Funded | T | NOT FUNDED | 5600000 | NOT FUNDED |  | NOT FUNDED | 72001000 | NOT FUNDED |  | 77601000
Buncombe | I-26 (US 19/US 23) | NCDOT | NC 251 / SR 1781 (Broadway Street) interchange in Asheville. | Improve interchange. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AB | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26499000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 73600000 |  |  | 101899000
Buncombe | I-26 (US 19/US 23) | NCDOT | SR 1684 (Elk Mountain Road) interchange. | Improve interchange. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AC | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22106000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1697000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42700000 |  |  | 66503000
Buncombe | I-26 / I-240 | NCDOT | I-40 to US 19 / US 23. | Construct multi-lane freeway, part on new location. | 4.7 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513
Buncombe | I-26 / I-240 | NCDOT | North of I-40 to SR 3548 (Haywood Road). | Widen to six lane freeway. | 1.85 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513AC | Region G | T | 2023 | 41969000 | 2023 | 3750000 | 2027 | 244400000 |  |  | 290119000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE);
Buncombe | I-26 / I-40 | NCDOT | I-40 / US 19 / US 23 (Smokey Park Highway) interchanges. | Widen I-40 eastbound to I-26 eastbound ramp. Widen I-26 westbound between I-40 ramps. Construct new I-40 westbound to US 19 / US 23 (Smokey Park Highway) northbound ramp. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513AB | Region G | HP, NHP | 2023 | 3400000 | 2023 | 100000 | 2024 | 51207000 |  |  | 54707000 | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS.
Buncombe | I-26 / I-40 | NCDOT | SR 3548 (Haywood Road) to US 19 / US 23 at SR 1781 (Broadway Street). | Widen to six lane freeway. | 2.75 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513B | Statewide Mobility | NHP | 2024 | 150700000 | 2024 | 24100000 | 2024 | 1227188000 |  |  | 1401988000 | GARVEE BOND FUNDING: $60 M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $250M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $250M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D.
Buncombe | I-40 | NCDOT | Bridge 100488 over SR 2500 (Blue Ridge Road) | Replace bridge. | 0.25 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4409A | Division 13 | NHP | 2025 | 1000000 | 2025 | 900000 | 2026 | 7000000 |  |  | 8900000
Buncombe | I-40 | NCDOT | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4759 | Statewide Mobility | BGANY, BGDA | 2019 | 15582000 | 2019 | 700000 | 2030 | 88900000 |  |  | 105182000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033
Buncombe | I-40; SR 1228 (Liberty Road) | NCDOT | Various locations. | Clearing work. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4759A | Statewide Mobility | BGANY |  |  |  |  | 2029 | 500000 |  |  | 500000
Buncombe | Nasty Branch Greenway | NCDOT | Depot Street at Livingston Street Park to south of the intersection of Asheland Avenue and Phifer Street | Construct greenway. | 0.71 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019A | Division 13 | BGANY, L(M) |  |  |  |  | 2026 | 4200000 |  |  | 4200000
Buncombe | NC 112 (Sardis Road/ Sandhill Road) | NCDOT | NC 191 (Brevard Road) to US 19 / US 23 (Smokey Park Highway). | Widen roadway to multi-lanes. | 3.59 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-6047 | Division 13 | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 61100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 106800000 |  |  | 175800000
Buncombe | NC 146 (Long Shoals Road) | NCDOT | Schenck Parkway/Skyland Inn Drive intersection in Asheville. | Construct intersection improvements. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4700C | Region G | NHP |  |  | 2026 | 100000 | 2026 | 4100000 |  |  | 4200000
Buncombe | NC 81 (Swannanoa River Road) | NCDOT | SR 3214 (Biltmore Avenue) to US 74A (South Tunnel Road) in Asheville. | Widen existing roadway. | 1.62 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5832 | Division 13 | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 930000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 73200000 |  |  | 124130000
Buncombe | Riverway Multi-Modal Network | NCDOT | City of Asheville. | Construct interconnected network of pedestrian, bicycle, roadway, and streetscape improvements. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019 |  | BGANY, L(M) | [6 empty] | 2024 | 6870000 | 6870000 | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING
Buncombe | SR 1477 (Riverside Drive) | NCDOT | SR 1517 (Hill Street) to SR 1781 (Broadway Street). | Widen roadway to include bicycle lanes and construct multi-use path. | 1.44 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513D | Division 13 | BGANY | 2024 | 24900000 | 2024 | 3300000 | 2024 | 22822000 |  |  | 51022000 | TO BE LET WITH I-2513B.
Buncombe | SR 2500 (Blue Ridge Road) | NCDOT | I-40 grade separation; US 70 to south of I-40; south of I-40 to SR 2713 (South Blue Ridge Road) | Upgrade I-40 / SR 250 (Blue Ridge Road) grade separation to interchange; Widen to three lanes; Upgrade roadway. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4409 | Division 13
Buncombe | SR 2500 (Blue Ridge Road) | NCDOT | I-40 grade separation; US 70 to south of I-40; south of I-40 to SR 2713 (South Blue Ridge Road) | Upgrade I-40 / SR 250 (Blue Ridge Road) grade separation to interchange; Widen to three lanes; Upgrade roadway. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4409B | Division 13 | NHP | 2026 | 7700000 | 2026 | 1000000 | 2028 | 23700000 |  |  | 32400000
Buncombe | SR 3116 (Mills Gap Road) | NCDOT | SR 3136 (Cane Creek Road). | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-6163 | Division 13 | BGANY, HF | 2026 | 100000 | 2026 | 300000 | 2027 | 2400000 |  |  | 2800000 | HIGHWAY FUNDS ARE HIGH IMPACT/LOW COST FUNDS
Buncombe | SR 3116 (Mills Gap Road) | NCDOT | US 25 (Hendersonville Road) to SR 3157 (Weston Road) in Asheville. | Upgrade roadway. | 1.91 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5834 | Division 13 | BGANY, T | 2019 | 12333000 |  |  | 2026 | 37600000 |  |  | 49933000 | RIGHT-OF-WAY IN PROGRESS.
Buncombe | SR 3408 (Craven Street) | NCDOT | Bridge 100743 over French Broad River | Construct bridge improvements. | 0.11 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019E | Division 13 | BGANY, L(M) | 2027 | 1200000 | 2027 | 3800000 | 2028 | 5300000 | 2026 | 530000 | 10830000
Buncombe | SR 3556 (Amboy Road / Meadow Road) | NCDOT | I-240 to NC 81 / SR 3214 (Biltmore Avenue). | Upgrade roadway with new bridge over the French Broad River. | 2.87 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-4739 | Division 13 | BGANY, T | 2027 | 24100000 | 2027 | 5400000 | 2030 | 62205000 |  |  | 91705000 | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
Buncombe | US 19 (Patton Avenue) | NCDOT | NC 63 (New Leicester Highway) intersection in Asheville. | Construct drainage improvements. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971AA | Region G | T | 2021 | 100000 |  |  | 2022 | 550000 |  |  | 650000 | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION.
Buncombe | US 19 (Patton Avenue) | NCDOT | NC 63 (New Leicester Highway) intersection in Asheville. | Construct final intersection improvements. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971B | Not Funded | T | NOT FUNDED | 28900000 | NOT FUNDED | 200000 | NOT FUNDED | 12900000 | NOT FUNDED |  | 42000000
Buncombe | US 19 (Patton Avenue) | NCDOT | NC 63 (New Leicester Highway) intersection in Asheville. | Construct initial intersection improvements. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971A | Region G | [10 empty] | SUPPLEMENT WITH SPOT MOBILITY FUNDS. UNDER CONSTRUCTION
Buncombe | US 19 (Patton Avenue) | NCDOT | NC 63 (New Leicester Highway) intersection in Asheville. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971
Buncombe | US 25A (Sweeten Creek Road) | NCDOT | SR 3116 (Mills Gap Road) to SR 3081 (Rock Hill Road). | Widen to multi-lanes. | 2.68 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-2801AB | Region G | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8393000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 110998000 |  |  | 175991000
Buncombe | US 25A (Sweeten Creek Road) | NCDOT | US 25 (Hendersonville Road) to Roberts Road in Asheville. | Widen to multi-lanes. | 7.3 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-2801
Buncombe | US 25A (Sweeten Creek Road) | NCDOT | US 25 (Hendersonville Road) to SR 3116 (Mills Gap Road). | Widen to multi-lanes. | 2.77 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-2801AA | Not Funded | BGANY, T(M) | NOT FUNDED | 92500000 | NOT FUNDED | 8393000 | NOT FUNDED | 84598000 | NOT FUNDED |  | 185491000
Buncombe | Wilma Dykeman Riverway | NCDOT | Riverside Drive and Lyman Street intersection in Asheville; Five Points intersection in Asheville. | Construct roundabouts. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019C | Division 13 | [10 empty] | COMPLETE
Buncombe | Texas Road | NCDOT | Bridge 100528 over Flat Creek in Montreat. | Replace municipal bridge. | 0.25 | Highway | Transition | 13 | French Broad River MPO | B-5196 | Division 13 | [10 empty] | MUNICIPAL BRIDGE - COMPLETE
Buncombe | Asheville Redefines Transit | ASHEVILLE REDEFINES TRANSIT | Various locations | Funding for traditional projects - 5310 |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TQ-6186 | Public Transit
Buncombe | Buncombe County - Mountain Mobility | BUNCOMBE MOUNTAIN MOBILITY - | Systemwide | Purchase replacement vans. |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TA-6701 | Public Transit | 5307, L | [6 empty] | 2020 | 544000 | 544000
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Funding for agency administration for 5310 Program. |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TQ-7010 | Public Transit | 5310, L | [6 empty] | 2025 | 100000 | 100000
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Funding for planning assistance. |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TP-5113 | Public Transit | 5303 | [6 empty] | 2020 | 450000 | 450000 | FUNDS AUTHORIZED IN PROGRESS
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Purchase lo-no transit vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TA-6703 | Public Transit | 5307, L | [6 empty] | 2025 | 4936000 | 4936000
Buncombe | Buncombe County - Mountain Mobility | MOUNTAIN MOBILITY - BUNCOMBE | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 13 | French Broad River MPO | TO-6154 | Public Transit | 5307, L | [6 empty] | 2020 | 4502000 | 4502000
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Funding for transit operations. |  | Public Transportation (Transit) | Miscellaneous/Other | 13 | French Broad River MPO | TO-4075 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 1965000 | 1965000 | FUNDS AUTHORIZED IN PROGRESS
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Funding for 5310 other projects. |  | Public Transportation (Transit) | Operations and Maintenance | 13 | French Broad River MPO | TQ-6187 | Public Transit | 5310, L | [6 empty] | 2025 | 354000 | 354000
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Various locations | Funding for JARC operations. |  | Public Transportation (Transit) | Operations and Maintenance | 13 | French Broad River MPO | TM-5138 | Public Transit | 3037, L | [6 empty] | 2025 | 816000 | 816000
Buncombe | City of Asheville Transit |  | Various | FY 2021 AOPP - Areas of consistent poverty planning survey and engagement |  | Public Transportation (Transit) | Planning | 13 | French Broad River MPO | TU-0020 | Public Transit | DP, L | [6 empty] | 2025 | 335000 | 335000 | DP FUNDS REPRESENT FTA DISCRETIONARY GRANT.
Buncombe | Buncombe County - Mountain Mobility | MOUNTAIN MOBILITY - BUNCOMBE | Systemwide | Funding for contracts. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 13 | French Broad River MPO | TG-6786 | Public Transit | 5307, L | [6 empty] | 2021 | 1927000 | 1927000
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 13 | French Broad River MPO | TG-6183B | Public Transit | 5307, L | [6 empty] | 2024 | 9852000 | 9852000
Buncombe | City of Asheville Transit | CITY OF ASHEVILLE | Various locations | Funding for bus stop improvement program. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 13 | French Broad River MPO | TG-0011 | Public Transit | 5339, L | [6 empty] | 2025 | 1214000 | 1214000
Buncombe | Bear Creek Road | NCDOT | BLU Crossing 720397A in Asheville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413A | Division 13 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Buncombe | Black Mountain Avenue | NCDOT | Norfolk Southern Railroad Crossing 729428C in Black Mountain. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413E | Division 13 | RR |  |  |  |  | 2026 | 505000 |  |  | 505000
Buncombe | NC 9 (Broadway Street) | NCDOT | Norfolk Southern Crossing 726262P in Black Mountain. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2013B | Division 13 | RR |  |  |  |  | 2025 | 492000 |  |  | 492000
Buncombe | SR 1128 (Lindsey Road) | NCDOT | BLU Crossing 720381D in Candler. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413C | Division 13 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Buncombe | SR 1319 (Johnston Boulevard) | NCDOT | BLU Crossing 720399N in Asheville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2013A | Division 13 | RR |  |  |  |  | 2026 | 294000 |  |  | 294000
Buncombe | SR 1332 (Louisiana Avenue) | NCDOT | Blue Ridge Southern Railroad Crossing 720402U in Asheville. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413D | Division 13 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Buncombe | SR 3541 (Buck Shoals Road) | NCDOT | BLU Crossing 720637E in Asheville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413B | Division 13 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Buncombe, Alleghany, Jackson, Watauga, Ashe, Swain, Haywood, Avery, McDowell, Transylvania, Yancey, Mitchell, Henderson, Wilkes, Burke, Caldwell | Blue Ridge Parkway Association | BLUE RIDGE PARKWAY ASSOCIATION | Statewide. | Update Blue Ridge Parkway Association travel planner and map brochure. Redesign Blue Ridge Parkway website and mobile application. Implement marketing plan for Blue Ridge Parkway Association. |  | Highway | Other | 11, 13, 14 | High Country RPO, French Broad River MPO, Southwestern RPO, Land-of-Sky RPO, Foothills RPO, Greater Hickory MPO | HO-0012 | Exempt | DP, L | [6 empty] | 2024 | 575000 | 575000 | NATIONAL SCENIC BYWAYS GRANT AWARD: $460,000. DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. LOCAL MATCH PROVIDED BY BLUE RIDGE PARKWAYS ASSOCIATION.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | BO-2413 | Division 13 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | R-5793 | Division 13 | HF, TA |  |  |  |  | 2020 | 6404000 |  |  | 6404000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS. HSIP FUNDS TO BE USED ON R-5793KB.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Various locations in Division 13. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | BO-2613 | Division 13 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2013 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2413 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713 | [11 empty] | COMPLETE
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713DIV | Division 13 | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713REG | Region G | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713SW | Statewide Mobility | HSIP, T(M) | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Construct safety improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5813
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028DIV | Division 13 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028REG | Region G | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Routes in Division 13. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5213 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Various locations in Division 13. | Safety Improvements. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2613 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Locations in Division 13. | Traffic separation study implementation and closures. |  | Rail | Rail-Highway Grade Crossing Closure | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RC-2013 | Division 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Locations in Division 13. | Construct highway-rail grade crossing safety improvements in Division 13. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RX-2013 | Division 13 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Locations in Division 13. | Construct highway-rail grade crossing safety improvements in Division 13. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RX-2413 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | Various | NCDOT | Locations in Division 13. | Construct highway-rail grade crossing safety improvements in Division 13. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RX-2613 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Buncombe, Henderson | NC 191 | NCDOT | Blue Ridge Parkway in Buncombe County to NC 280 in Henderson County. | Install rumble stripes with long life pavement markings. | 7.3 | Highway | Safety | 13, 14 | French Broad River MPO | HS-2413S | Region G | HSIP, T(M) |  |  |  |  | 2027 | 150000 |  |  | 150000
Buncombe, Henderson | I-26 | NCDOT | NC 280 (Exit 40) to I-40 at Asheville. | Construct additional lanes. | 9.32 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | I-4700 | Statewide Mobility | NHP |  |  |  |  | 2019 | 62468000 |  |  | 62468000 | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033
Buncombe, Henderson, Haywood | Various | NCDOT | French Broad River Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 13, 14 | French Broad River MPO | U-5100 | Division 13, 14 | BGANY, BGDA, L |  |  |  |  | 2024 | 69405000 |  |  | 69405000
Buncombe, Henderson, Haywood, Madison | Various | NCDOT | French Broad River Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 13, 14 | French Broad River MPO | U-5535 | Division 13, 14 | L(M), TADA |  |  |  |  | 2024 | 925000 |  |  | 925000
Buncombe, Henderson, Haywood, Madison | Various | NCDOT | French Broad River Metropolitan Planning Organization (FBRMPO) area. | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 13, 14 | French Broad River MPO | HL-0090 | Exempt | CRPDA, L(M) |  |  |  |  | 2024 | 749000 |  |  | 749000
Buncombe, Henderson, Haywood, Madison | Various | NCDOT | French Broad River Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 13, 14 | French Broad River MPO | U-5616 | Division 13, 14 | BGDA, L(M) | [6 empty] | 2024 | 4472000 | 4472000
Buncombe, Madison | I-26 (US 19/US 23) | NCDOT | South of SR 2148 (Stockton Road) in Buncombe County to north of NC 213. | Widen to multi-lane freeway and construct new route. | 2.975 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO, French Broad River MPO | A-0010BA | [11 empty] | COMPLETE
Buncombe, Madison | I-26 (US 19/US 23) | NCDOT | SR 1781 (Broadway Street) in Asheville to Tennessee state line at Sams Gap. | Widen to multi-lane freeway and construct new route. | 28.3 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO, Land-of-Sky RPO | A-0010 | [11 empty] | COORDINATE WITH B-4442, B-4443, B-4444.
Buncombe, Madison, Rutherford | Various | NCDOT | Various locations in Division 13 | Install horizontal alignment warning signs. | 0.1 | Highway | Safety | 13 | French Broad River MPO, Land-of-Sky RPO, Foothills RPO | HS-2413R | Region G | HSIP |  |  |  |  | 2026 | 939000 |  |  | 939000
Buncombe, McDowell, Yancey, Madison, Burke, Rutherford, Mitchell | Various | NCDOT | Primary and secondary two-lane and four-lane roadways in Division 13. | Install long life pavement markings. |  | Highway | Safety | 13 | French Broad River MPO, Foothills RPO, High Country RPO, Land-of-Sky RPO, Greater Hickory MPO | HS-2013Q | Region G | HSIP |  |  |  |  | 2026 | 3337000 |  |  | 3337000
Burke | HKY | HICKORY REGIONAL AIRPORT (HKY) | Hickory Regional Airport | Extend Runway 6 by 600 feet. |  | Aviation | STI (Prioritization) | 13 | Greater Hickory MPO | AV-5741 | Division 13 | O, T |  |  |  |  | 2029 | 19609000 |  |  | 19609000 | "O" FUNDS REPRESENTS FUNDS FROM A LEGISLATIVE DIRECTIVE.
Burke | Massell Avenue |  | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0166 | Division 13 | L(M), TADA | 2028 | 75000 | 2028 | 25000 | 2029 | 675000 | 2026 | 175000 | 950000 | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25.
Burke | Morganton Downtown Greenway Connector, US 64 Bypass (Sanford Drive) | MORGANTON | Catawba River Greenway near Alphabet Lane to existing section of the Downtown Greenway at the intersection of College Street and NC 181 (North Green Street) in Morganton. | Construct greenway. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | EB-5807 | Division 13 | BGANY, BGDA, L(M) |  |  |  |  | 2021 | 1619000 |  |  | 1619000 | RIGHT-OF-WAY IN PROGRESS
Burke | NC 126 | NCDOT | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0141 | Division 13 | BGDA, L(M) | 2026 | 200000 |  |  | 2027 | 1250000 | 2025 | 100000 | 1550000
Burke | Riverwalk | HICKORY | Old Lenoir Road at City owned property to end of proposed Rosales Bridge in Hickory | Construct multi-use path. | 0.59 | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | EB-5939 | Division 13 | BGDA, L(M) |  |  |  |  | 2023 | 6500000 |  |  | 6500000 | UNDER CONSTRUCTION.
Burke | College Street | MORGANTON | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Bike & Ped | STI (Prioritization) | 13 | Greater Hickory MPO | EB-5978 | Division 13 | L(M), TAANY | 2026 | 200000 | 2026 | 10000 | 2026 | 7300000 |  |  | 7510000
Burke | New Route | NCDOT | Burke County Industrial Park. | Construct access road. | 0.36 | Highway | Appalachian Development Highway System | 13 | Greater Hickory MPO | HA-0001 | Exempt | ADHSL |  |  |  |  | 2025 | 1700000 | 2021 | 200000 | 1900000 | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000
Burke | SR 1687 (Goat Farm Road) | NCDOT | Industrial Park. | Improve access road. | 0.88 | Highway | Appalachian Development Highway System | 13 | Greater Hickory MPO | R-5967 | Exempt | ADHSL, L |  |  |  |  | 2023 | 2152000 |  |  | 2152000 | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION.
Burke | I-40 | NCDOT | Bridges 110114 and 110120 over Silver Creek. | Replace bridges. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | BR-0130 | Statewide Mobility | BFP, T(M) |  |  |  |  | 2031 | 11800000 |  |  | 11800000
Burke | SR 1001 (Connelly Springs Road) | NCDOT | Bridge 110010 over Catawba River. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | R-3430B | Highway Fund | HFB | 2022 | 880000 | 2022 | 370000 | 2026 | 22902000 |  |  | 24152000 | RIGHT-OF-WAY IN PROGRESS.
Burke | SR 1002 (Henry River Road). |  | SR1002 (Henry River Road) over I-40. | Replace bridge. |  | Highway | Bridges | 13 | Greater Hickory MPO | BR-0151 | Division 13 | BGDA, HFB, L, L(M) | 2027 | 500000 |  |  | 2028 | 12400000 |  |  | 12900000
Burke | SR 1430 (Harland Road) | NCDOT | Bridge 110145 over Bristol Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | B-6011 | Division 13 | BGOFF | 2022 | 65000 |  |  | 2022 | 725000 |  |  | 790000 | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION.
Burke | SR 1913 (Sugar Loaf Road) | NCDOT | Bridge 110237 over Rock Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | B-6015 | Division 13 | BGOFF | 2021 | 100000 |  |  | 2021 | 1369000 |  |  | 1469000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION.
Burke | US 64 / US 70 | NCDOT | Bridge 110099 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | B-5869 | Region G | BFP, BGDA | 2021 | 3200000 | 2021 | 270000 | 2023 | 25861000 |  |  | 29331000 | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION.
Burke | I-40 | NCDOT | Mile marker 93.0 to mile marker 119.0. | Rehabilitate bridges 110139, 110140, 10149, and 110150. | 26.03 | Highway | Interstate Maintenance | 13 | Greater Hickory MPO | I-5891B | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2029 | 4000000 |  |  | 4000000
Burke | I-40 | NCDOT | Mile marker 93.0 to mile marker 119.0. | Rehabilitate pavement and bridges 110139, 110140, 10149, and 110150. | 23.92 | Highway | Interstate Maintenance | 13 | Greater Hickory MPO | I-5891
Burke | I-40 | NCDOT | Mile marker 93.0 to mile marker 119.0. | Rehabilitate pavement. | 25.73 | Highway | Interstate Maintenance | 13 | Greater Hickory MPO | I-5891A | Statewide Mobility | [10 empty] | COMPLETE
Burke | NC 181 | NCDOT | SR 1414 (St Marys Church Road) and NC 183. | Install rumble stripes with long life pavement markings. | 24.6 | Highway | Safety | 13 | Greater Hickory MPO | HS-2413V | Region G | HSIP |  |  |  |  | 2026 | 550000 |  |  | 550000
Burke | NC 181 | NCDOT | US 64 to SR 1405 (Brown Mountain Beach Road). | Upgrade guardrail. | 11.35 | Highway | Safety | 13 | Greater Hickory MPO | HS-2013C | Region G | HSIP |  |  |  |  | 2021 | 195000 |  |  | 195000 | COMPLETE
Burke | SR 1786 (Miller Bridge Road) | NCDOT | NC 18 and SR 1761 (Old NC Highway 10) | Install rumble stripes with 6-inch long life pavement markings. | 5.9 | Highway | Safety | 13 | Greater Hickory MPO | HS-2413Q | Division 13 | HSIP |  |  |  |  | 2026 | 135000 |  |  | 135000
Burke | US 321 | NCDOT | Bridges 012366 and 012367 at the Catawba County line. | Install guardrail. | 0.19 | Highway | Safety | 13 | Greater Hickory MPO | HS-2013A | Statewide Mobility | HSIP |  |  |  |  | 2021 | 92000 |  |  | 92000 | COMPLETE
Burke | US 64 / NC 18 | NCDOT | NC 181 to Caldwell County line. | Upgrade guardrail. | 7.49 | Highway | Safety | 13 | Greater Hickory MPO | HS-2013E | Region G | HSIP |  |  |  |  | 2021 | 385000 |  |  | 385000 | COMPLETE
Burke | US 70 | NCDOT | Various locations | Install rumble stripes and 6" long life pavement markings. |  | Highway | Safety | 13 | Greater Hickory MPO | HS-2413E | Region G | HSIP, T(M) |  |  |  |  | 2026 | 230000 |  |  | 230000
Burke | Various | NCDOT | Primary and secondary routes in Division 13 | Install horizontal alignment warning signs. |  | Highway | Safety | 13 | Greater Hickory MPO | HS-2413H | Region G | HSIP, T(M) |  |  |  |  | 2026 | 438000 |  |  | 438000
Burke | I-40 | NCDOT | SR 1761 (Old NC 10) Exit 118 interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 13 | Greater Hickory MPO | I-5990 | Division 13 | NHP | 2027 | 2496000 | 2027 | 605000 | 2027 | 19800000 |  |  | 22901000
Burke | NC 181 | NCDOT | SR 1414 (St Mary's Church Road) to Morganton ETJ in Morganton. | Widen existing roadway. | 0.92 | Highway | STI (Prioritization) | 13 | Greater Hickory MPO | U-5836 | Region G | T | 2027 | 3000000 | 2027 | 2000000 | 2030 | 14190000 |  |  | 19190000 | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
Burke | SR 1001 (Malcolm Boulevard) | NCDOT | US 70 to Catawba River in Rutherford College. | Modernize roadway to include bicycle and pedestrian accommodations. |  | Highway | STI (Prioritization) | 13 | Greater Hickory MPO | R-3430A | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 1600000 | NOT FUNDED | 20000000 | NOT FUNDED |  | 31600000
Burke | Hogan Street | NCDOT | Norfolk Southern Crossing 729506G in Morganton. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | Greater Hickory MPO | RX-2013C | Division 13 | RR |  |  |  |  | 2026 | 451000 |  |  | 451000
Burke, Caldwell | US 321 | NCDOT | Bridge 130367 over Lake Hickory. | Construct interim structure improvements. | 0.5 | Highway | Bridges | 11, 13 | Greater Hickory MPO | U-4700AA | Statewide Mobility | NHP |  |  |  |  | 2022 | 2705000 |  |  | 2705000 | UNDER CONSTRUCTION.
Burke, Madison, Rutherford, McDowell | Various | NCDOT | Primary and secondary two-lane roadways in Division 13. | Install long life pavement markings. |  | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO, Land-of-Sky RPO, French Broad River MPO | HS-2013R | Region G | HSIP |  |  |  |  | 2024 | 2966000 |  |  | 2966000
Burke, Mitchell, Rutherford | US 321; US 70; US 19E; US 221A | NCDOT | Various locations. | Upgrade guardrail. |  | Highway | Safety | 13 | Greater Hickory MPO, Foothills RPO, High Country RPO | HS-2013F | Statewide Mobility | HSIP |  |  |  |  | 2021 | 348000 |  |  | 348000 | COMPLETE
Cabarrus | JQF | CONCORD REGIONAL AIRPORT (JQF) | Concord-Padgett Regional Airport | Expand commercial terminal apron. |  | Aviation | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | AV-5731 | Region E | O, T |  |  |  |  | 2027 | 8517000 | 2026 | 300000 | 8817000
Cabarrus | JQF | CONCORD REGIONAL AIRPORT (JQF) | Concord-Padgett Regional Airport | Expand north airport apron. |  | Aviation | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | AV-5892 | Region E | O, T |  |  |  |  | 2024 | 2170000 |  |  | 2170000 | COMPLETE. OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT
Cabarrus | JQF | CONCORD REGIONAL AIRPORT (JQF) | Concord-Padgett Regional Airport | Rehabilitate pavement on airport apron and taxiway. |  | Aviation | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | AV-5890 | Region E | T |  |  |  |  | 2020 | 300000 |  |  | 300000 | COMPLETE.
Cabarrus | Clarke Creek Greenway | CONCORD | Beginning at JE ‘Jim’ Ramseur Park near Cox Mill Elementary School, crossing Clarke Creek to the Highland Creek neighborhood and crossing back to a terminus at the Allen Mills neighborhood along Cox Mill Road | Construct greenway. | 3.6 | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0060 | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 4600000 | 2023 | 13000 | 4613000
Cabarrus | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | HARRISBURG | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0086 | Division 10 | L(M), TADA | 2026 | 172000 | 2026 | 56000 | 2027 | 1563000 | 2024 | 287000 | 2078000
Cabarrus | SR 2198 (Midlake Avenue) in Kannapolis | CRMPO | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0178 | Division 10 | BGDA, L(M) | 2027 | 300000 | 2027 | 75000 | 2029 | 4954000 | 2026 | 495000 | 5824000
Cabarrus | Union Street | CONCORD | Tulip Ave Southwest to NC 3 | Construct sidewalk extension. |  | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | EB-5903 | Division 10 | CMAQ, L(M), TADA |  |  |  |  | 2020 | 866000 |  |  | 866000 | COMPLETE.
Cabarrus | Various | CONCORD | Elm Street Avenue Northwest from Glenn Street Northwest to Alexander Street Northwest in Concord; Glenn Street Northwest from Elm Avenue Northwest to Academy Avenue Northwest in Concord; Crowell Drive Northwest from Clearwater Arts Center driveway to Ceda | Construct sidewalks. |  | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0087 | Division 10 | L(M), TADA |  |  |  |  | 2026 | 1615000 | 2024 | 10000 | 1625000
Cabarrus | SR 2154 (Little Texas Road) | KANNAPOLIS | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Bike & Ped | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | EB-5844 | Division 10 | CMAQ, HF(M), L, TAANY | 2024 | 400000 |  |  | 2026 | 4852000 | 2025 | 728000 | 5980000 | RIGHT-OF-WAY IN PROGRESS.
Cabarrus | SR 2894 (Bruton Smith Boulevard / Concord Mills Boulevard); Portion of Weddington Road | NCDOT | US 29 to John Q. Hammonds Drive in Concord | Construct shared use path on north side of road. | 1.71 | Bike & Ped | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | EB-5732 | Division 10 | L(M), TAANY | 2029 | 3405000 | 2029 | 187000 | 2029 | 10500000 |  |  | 14092000
Cabarrus | US 29 | NCDOT | Bridges 120014 and 120019 over Rocky River and Access Road. | Replace bridges. | 0.322 | Highway | Bridges | 10 | Cabarrus-Rowan MPO | B-5123 | Region E | [10 empty] | COMPLETE
Cabarrus | US 29 / US 601 | NCDOT | Bridges 120057 and 120059 over Irish Buffalo Creek. | Replace bridges. | 0.25 | Highway | Bridges | 10 | Cabarrus-Rowan MPO | B-5808 | Region E | BFP, NHPB | 2021 | 255000 | 2021 | 1156000 | 2023 | 10100000 |  |  | 11511000 | UNDER CONSTRUCTION.
Cabarrus | NC 49 | NCDOT | Prince Circle to West of General Services Drive Southwest. | Upgrade existing full access crossover to reduced conflict intersection with leftovers and signalized U-turn leftovers. |  | Highway | Economic Development | 10 | Cabarrus-Rowan MPO | HE-0015 | Division 10 | O, T |  |  |  |  | 2023 | 4091000 |  |  | 4091000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841.
Cabarrus | Various | KANNAPOLIS | NC 73 at SR 1430 and Access Road intersections; SR 1620 at SR 1621 (Barr Road) intersection; I-85 ramps at NC 73 interchange | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73; CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD); CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP |  | Highway | Economic Development | 10 | Cabarrus-Rowan MPO | U-6098 | Division 10 | T |  |  |  |  | 2019 | 1450000 |  |  | 1450000 | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION.
Cabarrus | I-85 | NCDOT | SR 1430 (George Liles Parkway) Interchange in Concord. | Install lighting at interchange. | 0.1 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0157 | Exempt | BGDA, HF(M), L(M) |  |  |  |  | 2025 | 1000000 |  |  | 1000000
Cabarrus | NC 3 | CRMPO | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0177 | Division 10 | BGDA, HF(M) | 2027 | 300000 | 2027 | 142000 | 2029 | 1810000 | 2026 | 280000 | 2532000 | HF(M) REPRESENTS SPOT SAFETY FUNDS.
Cabarrus | NC 49 | HARRISBURG | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0062 | Exempt | BGANY, BGDA, L | 2026 | 955000 | 2026 | 382000 | 2027 | 6445000 | 2023 | 1396000 | 9178000 | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
Cabarrus | SR 1173 (Caldwell Road) | HARRISBURG | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0063 | Division 10 | L, T(DA) | 2027 | 1108000 | 2027 | 10000 | 2028 | 4156000 | 2023 | 833000 | 6107000 | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24.
Cabarrus | SR 1394 (Poplar Tent Road) | CONCORD | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0001 | Division 10 | BGANY, BGDA, L(M) | 2026 | 5520000 |  |  | 2029 | 7850000 | 2022 | 1710000 | 15080000 | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022.
Cabarrus | SR 1431 (Weddington Road) | CONCORD | SR 1414 (Rock Hill Church Road) intersection in Concord | Construct roundabout | 0.1 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0178 | Division 10 | BGDA, L(M) |  |  |  |  | 2027 | 2990000 | 2026 | 10000 | 3000000
Cabarrus | SR 1445 (Derita Road) | NCDOT | SR 2894 (Concord Mills Boulevard) to Aviation Boulevard | Widen to 4-lanes divided. | 1 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | U-4910A | Division 10 | [10 empty] | UNDER CONSTRUCTION
Cabarrus | Various |  | Locations in Concord. | Upgrade software for Concord citywide signal system. |  | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0123 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 500000 | 2025 | 1000000 | 1500000
Cabarrus | Roberta Road | HARRISBURG | Main Street Intersection. | Construct roundabout. |  | Highway | NCDOT Selected (Other Selection Process) | 10 | Cabarrus-Rowan MPO | HN-0036 | Division 10 | CMAQ, L | 2027 | 250000 |  |  | 2028 | 1741000 | 2025 | 715000 | 2706000 | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225.
Cabarrus | SR 1643 (Bethpage Road) | KANNAPOLIS | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Highway | Other | 10 | Cabarrus-Rowan MPO | C-5603F | Exempt | CMAQ, L(M) | 2026 | 117000 |  |  | 2026 | 2365000 |  |  | 2482000
Cabarrus | US 601 | CONCORD | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Highway | Other | 10 | Cabarrus-Rowan MPO | C-5603I | Exempt | CMAQ, L(M) | 2026 | 250000 |  |  | 2026 | 4881000 |  |  | 5131000 | RIGHT-OF-WAY IN PROGRESS.
Cabarrus | George Liles Parkway | NCDOT | SR 1304 (Roberta Road) to SR 1431 (Weddington Road). | Widen to four lanes divided, some on new location. | 2.98 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | R-2246B | [11 empty] | COMPLETE
Cabarrus | George Liles Parkway | NCDOT | SR 1431 (Weddington Road) to south of I-85. | Widen to four lanes divided, some on new location. | 1.236 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | R-2246C | [11 empty] | COMPLETE
Cabarrus | I-85 | NCDOT | NC 73 (Exit 55) to SR 2180 (Lane Street). | Install ITS. | 7.35 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | I-3802AA | Pre-STI (Transition) | CMAQ, CRPDA, T(M) |  |  |  |  | 2023 | 2523000 |  |  | 2523000 | COMPLETE
Cabarrus | SR 1445 (Derita Road) | NCDOT | Aviation Boulevard to SR 1394 (Poplar Tent Road) | Widen to three lanes divided. | 1.54 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | U-4910B | Pre-STI (Transition) | BGDA, T(M) |  |  |  |  | 2024 | 1135000 |  |  | 1135000 | UNDER CONSTRUCTION
Cabarrus | NC 24 / NC 27 | NCDOT | SR 1100 (Pine Bluff Road / Reed Mine Road) intersection near Locust. | Construct a reduced conflict intersection. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010F | Region E | HSIP | 2023 | 5000 |  |  | 2024 | 1160000 |  |  | 1165000
Cabarrus | NC 24 / NC 27 | NCDOT | SR 1120 (Bethel School Road) intersection in Midland. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010D | Region E | HSIP | 2023 | 301000 |  |  | 2024 | 790000 |  |  | 1091000 | RIGHT-OF-WAY IN PROGRESS.
Cabarrus | NC 49 | NCDOT | SR 1155 (Zion Church Road) intersection near Concord. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010H | Statewide Mobility | HSIP | 2024 | 210000 | 2024 | 70000 | 2026 | 1949000 |  |  | 2229000
Cabarrus | NC 49 | NCDOT | SR 2635 (Old Airport Road) intersection in Concord. | Install directional crossover with U-turn bulb-out. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010Q | Statewide Mobility | HSIP | 2025 | 10000 | 2025 | 10000 | 2027 | 750000 |  |  | 770000
Cabarrus | NC 49; US 601; NC 3 | NCDOT | Mile marker 13.8 to mile marker 15.8; Mile marker 5.4 to mile marker 12.3; Mile marker 13.8 to mile marker 20.3. | Install rumble stripes and long life pavement markings. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010P | Region E | HSIP |  |  |  |  | 2024 | 885000 |  |  | 885000
Cabarrus | SR 1002 (Old Salisbury Concord Road) | NCDOT | SR 2400 (Irish Potato Road) near Kannapolis. | Construct safety improvements. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | W-5710AO | Division 10 | HSIP, T(M) |  |  |  |  | 2024 | 1296000 |  |  | 1296000
Cabarrus | SR 1168 (Robinson Church Road) | NCDOT | SR 1169 (Peach Orchard Road) intersection near Harrisburg. | Widen shoulders and improve superelevation. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010R | Division 10 | HSIP | 2026 | 50000 | 2027 | 25000 | 2027 | 730000 |  |  | 805000
Cabarrus | SR 1790 (Winecoff School Road) | NCDOT | Winecoff Elementary School in Concord | Install pedestrian accommodations. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2410A | Division 10 | HSIP, T(M) | 2026 | 10000 |  |  | 2029 | 97000 |  |  | 107000
Cabarrus | US 29 (Concord Parkway) | NCDOT | SR 2894 (Bruton Smith Boulevard) intersection in Concord | Install pedestrian signal upgrades. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2410D | Region E | HSIP, T(M) |  |  |  |  | 2025 | 29000 |  |  | 29000
Cabarrus | George Liles Parkway | NCDOT | NC 49 to south of I-85 in Concord. | Widen to four lanes divided, part on new location. | 6.5 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-2246
Cabarrus | George Liles Parkway | NCDOT | NC 49 to SR 1304 (Roberta Road) in Concord. | Widen to four lanes divided, part on new location. | 1.59 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-2246A | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42100000 |  |  | 57300000
Cabarrus | NC 3 (Dale Earnhardt Boulevard) | NCDOT | US 29 / US 601 (Cannon Boulevard) intersection. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-5761 | Region E | T |  |  | 2026 | 1800000 | 2027 | 8100000 |  |  | 9900000 | RIGHT-OF-WAY IN PROGRESS.
Cabarrus | NC 73 (Davidson Highway) | NCDOT | I-85 to US 29 in Cabarrus County. | Widen to multi-lanes. | 2.79 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-5706BB | Not Funded | NHP, T(M) | NOT FUNDED | 16500000 | NOT FUNDED | 8000000 | NOT FUNDED | 50700000 | NOT FUNDED |  | 75200000
Cabarrus | NC 73 (Davidson Highway) | NCDOT | SR 1394 (Popular Tent Road) to I-85 in Cabarrus County. | Widen to multi-lanes. | 6.07 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-5706BA | Not Funded | NHP, T(M) | NOT FUNDED | 26000000 | NOT FUNDED | 6500000 | NOT FUNDED | 139000000 | NOT FUNDED |  | 171500000
Cabarrus | SR 1394 (Poplar Tent Road) | NCDOT | Gable Oaks Lane/ Woodhaven Place to Seasons Place | Widen to multi-lanes. | 2.96 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-3415A | Division 10 | BGANY | 2029 | 12900000 | 2029 | 900000 | 2033 | 49400000 |  |  | 63200000
Cabarrus | SR 1394 (Poplar Tent Road) | NCDOT | George Liles Parkway to US 29 / US 601 Bypass. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-3415B | Not Funded | T | NOT FUNDED | 9900000 | NOT FUNDED | 13200000 | NOT FUNDED | 32900000 | NOT FUNDED |  | 56000000
Cabarrus | SR 1394 (Poplar Tent Road) | NCDOT | SR 1445 (Derita Road) to US 29 / US 601 Bypass. | Widen to multi-lanes. | 6.1 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-3415
Cabarrus | SR 2894 (Concord Mills Boulevard) | NCDOT | Kings Grant Pavilion (Entrance #1) intersection in Concord. | Construct two lane grade separated directional left flyover. | 1 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-5806 | Division 10 | T |  |  |  |  | 2021 | 10380000 | 2021 | 1755000 | 12135000 | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
Cabarrus | US 29 | NCDOT | Union Cemetery Road intersection in Concord; West of SR 1414 (Rock Hill Church Road) to east of SR 1414 (Rock Hill Church Road) in Concord. | Realign Union Cemetery Road to intersect with US 29 and SR 1414 (Rock Hill Church Road) intersection; Upgrade roadway. |  | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-5956 | Region E | T | 2022 | 5150000 | 2025 | 2550000 | 2026 | 16261000 |  |  | 23961000 | RIGHT-OF-WAY IN PROGRESS.
Cabarrus | NC 3 | NCDOT | West Side Bypass (U-2009) to SR 1691 (Loop Road) in Kannapolis. | Widen to four lanes divided. | 2.58 | Highway | Transition | 10 | Cabarrus-Rowan MPO | U-3440 | Pre-STI (Transition) | T | 2025 | 561000 |  |  | 2025 | 3100000 |  |  | 3661000 | UNDER CONSTRUCTION
Cabarrus | SR 1445 (Derita Road) | NCDOT | SR 2894 (Concord Mills Boulevard) to SR 1394 (Poplar Tent Road) in Concord. | Widen to three lanes divided. | 2.6 | Highway | Transition | 10 | Cabarrus-Rowan MPO | U-4910 | [11 empty] | SEGMENTS A AND B LET TOGETHER
Cabarrus | US 29 / US 601 | NCDOT | Bridges 120066 and 120069 over Southern Railroad. | Replace bridges. | 0.25 | Highway | Transition | 10 | Cabarrus-Rowan MPO | B-5136 | Region E | T |  |  |  |  | 2021 | 2790000 |  |  | 2790000 | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
Cabarrus | Cabarrus County Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for 5310 program projects - Operating |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5128B | Public Transit | 5310, L | [6 empty] | 2020 | 6300000 | 6300000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for 5310 program projects - Capital |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5128A | Public Transit | 5310, L | [6 empty] | 2020 | 9375000 | 9375000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for 5339 Program bus and bus facilities expansion vehicles. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5130B | Public Transit | 5339, L | [6 empty] | 2020 | 6600000 | 6600000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for agency administration for 5310 Program. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5128C | Public Transit | 5310 | [6 empty] | 2020 | 750000 | 750000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for planning assistance. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TP-5118 | Public Transit | 5303, L, S | [6 empty] | 2020 | 2031000 | 2031000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Safety and security minimum 1 % set aside |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TS-5116 | Public Transit | 5307 | [6 empty] | 2020 | 1200000 | 1200000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 10 | Cabarrus-Rowan MPO | TO-5138 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 47227000 | 47227000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus | Cabarrus County Transit | CABARRUS COUNTY | Various locations | Funding for capital for Cabarrus County through the City of Concord. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Cabarrus-Rowan MPO | TG-6789 | Public Transit | 5307, L | [6 empty] | 2020 | 2256000 | 2256000
Cabarrus | Norfolk Southern Mainline | NCDOT | SR 1766 (Rogers Lake Road Crossing) (724408Y) in Kannapolis. | Construct grade separation. |  | Rail | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | Y-4810K | Statewide Mobility | O, T |  |  |  |  | 2023 | 21260000 |  |  | 21260000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN
Cabarrus | Various | NCDOT | Locations in Kannapolis. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall, and signaling equipment. |  | Rail | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | P-5725 | Region E | T |  |  |  |  | 2027 | 3400000 |  |  | 3400000 | RIGHT-OF-WAY IN PROGRESS
Cabarrus, Mecklenburg | NC 73 (Davidson Highway) | NCDOT | East of SR 2693 (Davidson-Concord Road) to US 29. | Widen to multi-lanes. | 10.9 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | R-5706 | [11 empty] | COORDINATE WITH R-2632AB.
Cabarrus, Mecklenburg | Piedmont Corridor | NCDOT | Haydock to Junker | Restore double track |  | Rail | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | P-5208 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Cabarrus, Rowan | Various | NCDOT | Cabarrus Rowan Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | U-5545 | Division 9, 10 | L(M), TADA |  |  |  |  | 2024 | 7516000 |  |  | 7516000
Cabarrus, Rowan | Various | NCDOT | Cabarrus-Rowan Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | U-5614 | Division 9, 10 | BGANY, BGDA, L |  |  |  |  | 2024 | 76499000 |  |  | 76499000 | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP
Cabarrus, Rowan | Various | NCDOT | Cabarrus-Rowan Planning Organization (CRMPO) area. | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | HL-0093 | Exempt | CRPDA, L(M) |  |  |  |  | 2024 | 0
Cabarrus, Rowan | Various | CONCORD | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Highway | Other | 9, 10 | Cabarrus-Rowan MPO | C-5603 | Exempt | CMAQ, L(M) | 2020 | 309000 |  |  | 2020 | 1848000 | 2020 | 927000 | 3084000 | IN PROGRESS
Cabarrus, Rowan | I-85 | NCDOT | NC 73 (Exit 55) in Cabarrus County to US 29 / US 601 Connector (Exit 68) in Rowan County. | Widen to eight lanes. | 13.6 | Highway | STI (Prioritization) | 9, 10 | Cabarrus-Rowan MPO | I-3802 | [11 empty] | PROJECT COMPLETED. SEGMENT B INCLUDES B-5365 AND I-3610
Cabarrus, Rowan | I-85 | NCDOT | NC 73 intersection in Cabarrus County (Exit 55) to SR 2180 (Lane Street) in Cabarrus County. | Widen to eight lanes. | 7.35 | Highway | Transition | 9, 10 | Cabarrus-Rowan MPO | I-3802A | Pre-STI (Transition) | [10 empty] | COMPLETE
Cabarrus, Rowan | Concord Kannapolis Area Transit | CONCORD KANNAPOLIS AREA TRANSIT | Various locations | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, vehicles, etc. |  | Public Transportation (Transit) | Capital (Non-STI) | 9, 10 | Cabarrus-Rowan MPO | TA-5130A | Public Transit | 5339, L | [6 empty] | 2020 | 6000000 | 6000000
Cabarrus, Rowan | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for ADA services. |  | Public Transportation (Transit) | Operations and Maintenance | 9, 10 | Cabarrus-Rowan MPO | TG-5103B | Public Transit | 5307, L | [6 empty] | 2020 | 8563000 | 8563000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus, Rowan | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 9, 10 | Cabarrus-Rowan MPO | TG-5103C | Public Transit | 5307, L | [6 empty] | 2020 | 26250000 | 26250000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus, Rowan | Concord Kannapolis Area Transit | RIDER TRANSIT / CONCORD | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9, 10 | Cabarrus-Rowan MPO | TG-5103A | Public Transit | 5307, 5310, L | [6 empty] | 2020 | 9375000 | 9375000 | FUNDS AUTHORIZED IN PROGRESS
Cabarrus, Stanly | NC 73 | NCDOT | Mile marker 0 to mile marker 4.3, mile marker 13.1 to mile marker 18.9, mile marker 20.9 to mile marker 24.0 in Cabarrus County; Mile marker 0 to mile marker 8.1 in Stanly County. | Install rumble stripes and long life pavement markings. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO, Rocky River RPO | HS-2010O | Region E | HSIP |  |  |  |  | 2024 | 1400000 |  |  | 1400000
Caldwell | Hospital Avenue | LENOIR | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Bike & Ped | Locally Selected | 11 | Greater Hickory MPO | EB-5806 | Division 11 | BGANY, BGDA, L(M), TADA | 2021 | 120000 |  |  | 2024 | 3050000 |  |  | 3170000 | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION.
Caldwell | Hudson US 321A (Main Street) | NCDOT | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Bike & Ped | Locally Selected | 11 | Greater Hickory MPO | BL-0002 | Division 11 | BGDA, L(M), TAANY | 2026 | 24000 |  |  | 2026 | 390000 | 2024 | 130000 | 544000 | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22.
Caldwell | Lenior Greenway | LENOIR | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Bike & Ped | Locally Selected | 11 | Greater Hickory MPO | BL-0065 | Division 11 | BGDA, L(M) | 2026 | 281000 |  |  | 2027 | 1581000 | 2024 | 306000 | 2168000
Caldwell | SR 1356 (Old Johns River Road) | NCDOT | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0057 | Exempt | BGOFF, DP, HFB | 2025 | 290000 | 2025 | 10000 | 2026 | 1800000 | 2023 | 459000 | 2559000 | DP REPRESENTS RAISE GRANT FUNDS.
Caldwell | SR 1356 (Old Johns River Road) | NCDOT | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0058 | Exempt | BGOFF, DP, HFB | 2025 | 160000 | 2025 | 60000 | 2026 | 1600000 | 2023 | 459000 | 2279000 | DP REPRESENTS RAISE GRANT FUNDS.
Caldwell | SR 1356 (Old Johns River Road) | NCDOT | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0059 | Exempt | BGOFF, DP, HFB | 2025 | 120000 | 2025 | 40000 | 2026 | 1701000 | 2023 | 449000 | 2310000 | DP REPRESENTS RAISE GRANT FUNDS
Caldwell | SR 1356 (Old Johns River Road) | NCDOT | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0060 | Exempt | BGOFF, DP, HFB | 2025 | 270000 | 2025 | 60000 | 2026 | 1999000 | 2023 | 461000 | 2790000 | DP REPRESENTS RAISE GRANT FUNDS.
Caldwell | SR 1514 (Indian Grave Road) | NCDOT | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0056 | Exempt | BGOFF, DP, HFB | 2025 | 271000 | 2025 | 80000 | 2026 | 1799000 | 2023 | 539000 | 2689000 | DP REPRESENTS RAISE GRANT FUNDS.
Caldwell | SR 1574 (C C Camp Road) | NCDOT | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0061 | Exempt | BGOFF, DP, HFB | 2025 | 140000 | 2025 | 40000 | 2026 | 1501000 | 2023 | 411000 | 2092000 | DP REPRESENTS RAISE GRANT FUNDS
Caldwell | SR 1328 (Brown Mountain Beach Road) | NCDOT | Mile marker 5.3 to mile marker 7.5. | Install guardrail. | 2.19 | Highway | Federal Lands Access Program | 11 | Greater Hickory MPO | HF-0001 | Exempt | FLAP, HF(M) |  |  |  |  | 2022 | 235000 | 2022 | 5000 | 240000 | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION.
Caldwell | SR 1328 (Brown Mountain Beach Road) | NCDOT | Various locations along Wilson Creek. | Widen pavement. | 2.19 | Highway | Federal Lands Access Program | 11 | Greater Hickory MPO | HF-0003 | Exempt | FLAP, HF(M) |  |  |  |  | 2025 | 1575000 | 2022 | 175000 | 1750000 | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS.
Caldwell | US 321 | NCDOT | SR 1109 (Pinewoods Road) in Granite Falls. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 11 | Greater Hickory MPO | R-5775 | Exempt | BGDA, HF(M) |  |  |  |  | 2022 | 2735000 |  |  | 2735000 | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - HF(M) IS SPOT SAFETY (SS-4911 AL);
Caldwell | US 321 | NCDOT | SR 1370 (Kirby Mountain Road) to Green Hill Road. | Install rumble strips and pavement markings. |  | Highway | Safety | 11 | Greater Hickory MPO | HS-2411D | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 625000 |  |  | 625000
Caldwell | SR 1001 (Connelly Springs Road) | NCDOT | Cajah Mountain Road to SR 1933 (South-West Boulevard) in Cajah's Mountain. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | R-3430CA | Division 11 | BGANY | 2029 | 18942000 | 2029 | 2265000 | 2033 | 52300000 |  |  | 73507000
Caldwell | SR 1001 (Connelly Springs Road) | NCDOT | Catawba River to Cajah Mountain Road in Cajah's Mountain.. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.54 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | R-3430CB | Division 11 | BGANY | 2030 | 17857000 | 2030 | 2135000 | 2034 | 49300000 |  |  | 69292000
Caldwell | SR 1002 (Dudley Shoals Road) | NCDOT | Grace Chapel Road / Campground Road / SR 1752 (Peach Orchard Road) intersection in Granite Falls. | Construct roundabout. |  | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6035 | Division 11 | T |  |  | 2024 | 75000 | 2024 | 2900000 |  |  | 2975000 | RIGHT-OF-WAY IN PROGRESS
Caldwell | SR 1109 (Pinewood Road) | NCDOT | US 321 to SR 1931 (Bert Huffman Road). | Upgrade roadway. | 0.6 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6036 | Division 11 | T | 2019 | 1500000 | 2019 | 590000 | 2024 | 13317000 |  |  | 15407000 | RIGHT-OF-WAY IN PROGRESS
Caldwell | SR 1130 (Cajah Mountain Road) | NCDOT | SR 1001 (Connelly Springs Road) to US 321 Alternate. | Modernize roadway. | 3.39 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6157 | Division 11 | BGANY, T(M) | 2025 | 13000000 | 2025 | 7000000 | 2029 | 45100000 |  |  | 65100000 | RIGHT-OF-WAY IN PROGRESS.
Caldwell | US 321 | NCDOT | SR 1002 (Dudley Shoals Road) grade separation. | Construct ramp onto US 321 southbound. | 1 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6161 | Division 11 | NHP, T(M) | 2026 | 2000000 | 2026 | 270000 | 2028 | 6300000 |  |  | 8570000 | COORDINATE WITH U-4700A
Caldwell | US 321 | NCDOT | SR 1108 (Mission Road) intersection in Sawmills. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700CC | Statewide Mobility | NHP, T(M) | 2020 | 450000 | 2020 | 100000 | 2026 | 15490000 |  |  | 16040000 | RIGHT-OF-WAY IN PROGRESS.
Caldwell | US 321 | NCDOT | SR 1108 (Mission Road) to SR 1933 (Southwest Boulevard). | Widen to six lanes. | 0 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700C | Not Funded | NHP | NOT FUNDED | 5000000 | NOT FUNDED | 2000000 | NOT FUNDED | 12000000 | NOT FUNDED |  | 19000000
Caldwell | US 321 | NCDOT | SR 1160 (Mount Herman Road) intersection in Hudson. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700CA | Region F | NHP | 2020 | 420000 |  |  | 2026 | 8200000 |  |  | 8620000 | DESIGN BY DIVISION. UNDER CONSTRUCTION.
Caldwell | US 321 | NCDOT | SR 1809 / SR 1952 (Pine Mountain Road) intersection in Hudson. | Upgrade intersection to reduced conflict intersection within the limits of U-4700C. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700CB | Statewide Mobility | NHP, T(M) | 2020 | 1070000 | 2020 | 100000 | 2026 | 16400000 |  |  | 17570000 | RIGHT-OF-WAY IN PROGRESS.
Caldwell | US 321 | NCDOT | US 321A to SR 1108 (Mission Road). | Widen to six lanes. | 0 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700B | Not Funded | NHP | NOT FUNDED | 35000000 | NOT FUNDED | 4000000 | NOT FUNDED | 57500000 | NOT FUNDED |  | 96500000
Caldwell | US 321 Alternate | NCDOT | SR 1109 (Pinewood Road) to SR 1106 (Duke Street) | Upgrade roadway. | 1.33 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6034 | Division 11 | BGANY, T(M) | 2025 | 16000000 | 2025 | 3000000 | 2029 | 27300000 |  |  | 46300000
Caldwell | US 64 / NC 18 | NCDOT | SR 1142 (Callico Road) intersection. | Upgrade roadway. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6033 | Division 11 | T | 2019 | 400000 | 2019 | 668000 | 2023 | 4261000 |  |  | 5329000 | UNDER CONSTRUCTION.
Caldwell | US 64 / NC 90 / NC 18 (Wilkesboro Boulevard) | NCDOT | US 64 / NC 90 (Taylorsville Road) in Lenoir. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | R-5745 | Division 11 | T |  |  |  |  | 2019 | 1695000 |  |  | 1695000 | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE)
Caldwell, Burke | SR 1001 (Malcolm Boulevard / Connelly Springs Road) | NCDOT | US 70 to SR 1933 (South-West Boulevard) in Lenoir. | Modernize roadway to include bicycle and pedestrian accommodations. | 10 | Highway | STI (Prioritization) | 11, 13 | Greater Hickory MPO | R-3430
Caldwell, Catawba, Burke | US 321 | NCDOT | North of US 70 in Hickory to SR 1933 (Southwest Boulevard). | Widen to six lanes. | 13.3 | Highway | STI (Prioritization) | 11, 12, 13 | Greater Hickory MPO | U-4700 | [11 empty] | INCLUDES B-4450.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | BO-2411 | Division 11 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 7500000 | 2024 | 650000 | 8650000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Locations in Division 11 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | R-5791 | Division 11 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Various locations in Division 11. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (Ta) funds. |  | Bike & Ped | Other | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | BO-2611 | Division 11 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Construct safety improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2011 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Construct safety improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2411 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Construct safety improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Construct safety improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711DIV | Division 11 | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Construct safety improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711REG | Region F | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Construct safety improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711SW | Statewide Mobility | HSIP, T(M) | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026DIV | Division 11 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026REG | Region F | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Install long life pavement markings. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2011A | Division 11 | HSIP |  |  |  |  | 2021 | 1816000 |  |  | 1816000 | UNDER CONSTRUCTION.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Routes in Division 11. | Install long life pavement markings. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2011D | Division 11 | HSIP |  |  |  |  | 2021 | 855000 |  |  | 855000 | UNDER CONSTRUCTION.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Various locations in Division 11. | Safety Improvements. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2611 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Locations in Division 11. | Traffic separation study implementation and closures. |  | Rail | Rail-Highway Grade Crossing Closure | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RC-2011 | Division 11 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Locations in Division 11. | Construct highway-rail grade crossing safety improvements in Division 11. |  | Rail | Rail-Highway Grade Crossing Improvement | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RX-2011 | Division 11 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Locations in Division 11. | Construct highway-rail grade crossing safety improvements in Division 11. |  | Rail | Rail-Highway Grade Crossing Improvement | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RX-2411 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | Various | NCDOT | Locations in Division 11. | Construct highway-rail grade crossing safety improvements in Division 11. |  | Rail | Rail-Highway Grade Crossing Improvement | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RX-2611 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Camden | US 17 (Future I-87) | NCDOT | US 17 Business / NC 343 Intersection in South Mills | Modify the median opening and install traffic signal. | 0.5 | Highway | Safety | 1 | Albemarle RPO | HS-2401A | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 1500000 |  |  | 1500000
Camden | NC 343 | NCDOT | US 158 in Camden to SR 1119 (South Trotman Road) in Shiloh. | Modernize roadway and replace bridges 140017 and 140018 in Camden County. | 6.82 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5807 | Division 1 | BGANY, T | 2025 | 2000000 | 2025 | 9600000 | 2028 | 29705000 |  |  | 41305000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
Camden | SR 1224 (Old Swamp Road) | NCDOT | Bridge 140013 over Joyce Creek. | Replace bridge. |  | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5717B | Division 1 | T |  |  |  |  | 2027 | 2200000 |  |  | 2200000
Camden | SR 1224 (Old Swamp Road) | NCDOT | South of SR 1225 (Lilly Road) to north of SR 1225 (Lilly Road). | Widen existing lanes and shoulders, and construct intersection improvement. | 0.4 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5717A | Division 1 | [10 empty] | UNDER CONSTRUCTION.
Camden, Currituck | SR 1227 / SR 1208 (South Mills Road); SR 1224 / SR 1223 (Old Swamp Road) | NCDOT | NC 343 in Camden County to NC 168 in Currituck County. | Widen existing lanes and shoulders, and construct intersection improvement. | 11 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5717 | Division 1 | T |  |  |  |  | 2027 | 38100000 |  |  | 38100000 | RIGHT-OF-WAY IN PROGRESS.
Carteret | MRH | MICHAEL J. SMITH FIELD (MRH) | Michael J. Smith Field | Construct full parallel taxiway 8-26. |  | Aviation | STI (Prioritization) | 2 | Down East RPO | AV-5746 | Division 2 | [10 empty] | COMPLETE
Carteret | NC 58 | ATLANTIC BEACH | Bogue Shores Suites to Coral Bay Club in Atlantic Beach. | Construct sidewalk on north side of NC 58. | 2 | Bike & Ped | Locally Selected | 2 | Down East RPO | BN-0019 | Exempt | CRP550, L(M) |  |  |  |  | 2026 | 150000 | 2026 | 5000 | 155000
Carteret | NC 58 | NCDOT | Bridge 150006 over Bogue Sound | Rehabilitate bridge. | 0.75 | Highway | Bridges | 2 | Down East RPO | B-5939 | Region B | T |  |  |  |  | 2024 | 3000000 |  |  | 3000000 | UNDER CONSTRUCTION
Carteret | SR 1182 (Atlantic Beach Causeway) | NCDOT | Bridge 150068 over Bogue Sound | Rehabilitate bridge. | 0.75 | Highway | Bridges | 2 | Down East RPO | B-5938 | Division 2 | T |  |  |  |  | 2019 | 7995000 |  |  | 7995000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE)
Carteret | SR 1335 (Island Road) | NCDOT | Bridges 150073 and 150096 over the Straits at Harkers Island. | Replace lift spans. | 0.75 | Highway | Bridges | 2 | Down East RPO | B-4863 | Division 2 | DP, T |  |  |  |  | 2021 | 73735000 |  |  | 73735000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS.
Carteret | US 70 | NCDOT | Bridge 150033 over North River. | Repair bridge to serve as detour route for B-4722B. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4722A | [11 empty] | COMPLETE.
Carteret | US 70 | NCDOT | Bridge 150033 over North River. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4722 | Region B
Carteret | NC 58 | NCDOT | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Highway | NCDOT Selected (Other Selection Process) | 2 | Down East RPO | HN-0041 | Region B | CRP550, T(M) | 2026 | 100000 | 2026 | 150000 | 2026 | 1670000 | 2025 | 175000 | 2095000
Carteret | NC 101 | NCDOT | SR 1392 (Adams Creek Road) intersection | Improve intersection with channelization and supplemental stop sign installation. |  | Highway | Safety | 2 | Down East RPO | HS-2402P | Region B | HSIP |  |  |  |  | 2025 | 49000 |  |  | 49000
Carteret | NC 24 | NCDOT | SR 1259 (Taylor Notion Road) to US 70. | Install rumble stripes and pavement markings. | 15.07 | Highway | Safety | 2 | Down East RPO | HS-2002B | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 640000 |  |  | 640000 | COMPLETE.
Carteret | NC 58 | NCDOT | East of Lee Drive in Atlantic Beach. | Install rectangular rapid flashing beacons. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AA | Region B | HSIP, T(M) |  |  |  |  | 2024 | 32000 |  |  | 32000
Carteret | NC 58 | NCDOT | Loon Drive / Emerald Plantation Road; Mangrove Drive; Bogue Inlet Drive intersections in Emerald Isle. | Implement a leading pedestrian interval at the signalized intersections. |  | Highway | Safety | 2 | Down East RPO | HS-2402E | Region B | HSIP, T(M) |  |  |  |  | 2025 | 9000 |  |  | 9000 | UNDER CONSTRUCTION.
Carteret | NC 58 | NCDOT | West of Cedar Lane. | Install crosswalks, concrete pedestrian island, sidewalks, and rectangular rapid-flashing beacons. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002I | Region B | HSIP, T(M) |  |  |  |  | 2024 | 96000 |  |  | 96000
Carteret | NC 58 (Salter Path Road) | NCDOT | West of Tradewinds Drive. | Install crosswalk with rapid flashing beacons. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002G | Region B | HSIP, T(M) |  |  |  |  | 2022 | 24000 |  |  | 24000 | COMPLETE.
Carteret | NC 58 (West Fort Macon Road) | NCDOT | Atlantic Station Shopping Center / Atlantic Beach Town Park. | Install pedestrian heads and wheel chair ramp revisions. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002H | Region B | HSIP, T(M) |  |  |  |  | 2022 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
Carteret | SR 1310 (Lennoxville Road) | NCDOT | Carteret Avenue intersection in Beaufort. | Install crosswalk signalization. |  | Highway | Safety | 2 | Down East RPO | HS-2002U | Division 2 | HSIP, T(M) |  |  |  |  | 2024 | 24000 |  |  | 24000 | UNDER CONSTRUCTION.
Carteret | US 70 | NCDOT | NC 101 intersection in Beaufort. | Upgrade traffic signal. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AI | Region B | HSIP, T(M) |  |  |  |  | 2024 | 56000 |  |  | 56000
Carteret | US 70 | NCDOT | SR 1174 (Turner Street) intersection in Beaufort. | Install pedestrian signal heads at existing crosswalks. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AB | Region B | HSIP, T(M) |  |  |  |  | 2024 | 56000 |  |  | 56000
Carteret | US 70 | NCDOT | SR 1300 (Merrimon Road) intersection. | Upgrade traffic signal. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AC | Region B | HSIP, T(M) |  |  |  |  | 2024 | 24000 |  |  | 24000
Carteret | US 70 | NCDOT | SR 1429 (Olga Road) to NC 12; NC 12 from US 70 to SR 1388 (Lola Road) | Install rumble stripes. |  | Highway | Safety | 2 | Down East RPO | HS-2402T | Region B | HSIP |  |  |  |  | 2025 | 675000 |  |  | 675000
Carteret | US 70 (Arendell Street) | NCDOT | SR 1602 (35th Street) intersection in Morehead City. | Install pedestrian signals with other pedestrian accomodations. |  | Highway | Safety | 2 | Down East RPO | HS-2402Y | Statewide Mobility | HSIP |  |  |  |  | 2027 | 210000 |  |  | 210000
Carteret | US 70 (Future I-42) | NCDOT | Gladys Teasley Lane to SR 1753 (Arthur Farm Road) in Morehead City. | Construct reduced conflict intersection. | 0.65 | Highway | Safety | 2 | Down East RPO | HS-2002AF | Region B | HSIP, T(M) |  |  | 2025 | 150000 | 2025 | 1200000 |  |  | 1350000
Carteret | NC 24 | NCDOT | NC 58 intersection in Cape Carteret | Construct intersection improvements. | 1 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5858 | Statewide Mobility | NHP, T | 2021 | 750000 | 2024 | 670000 | 2026 | 10600000 |  |  | 12020000 | RIGHT-OF-WAY IN PROGRESS.
Carteret | NC 58 (Emerald Drive) | NCDOT | Mangrove Drive intersection in Emerald Isle | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5944 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 650000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 630000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5300000 |  |  | 6580000
Carteret | NC 58 (West Fort Macon Road) | NCDOT | Atlantic Beach Causeway. | Add right turn lane. |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-5816 | Region B | T | 2020 | 600000 |  |  | 2023 | 2170000 |  |  | 2770000 | UNDER CONSTRUCTION.
Carteret | SR 1176 (Bridges Street Extension) | NCDOT | SR 1738 (Bridges Street) to SR 1147 (McCabe Road). | Widen existing roadway and construct partially on new location. | 3.02 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5727 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 115000000 |  |  | 136200000
Carteret | SR 1176 (Bridges Street) | NCDOT | SR 1243 (Barbour Road) intersection in Morehead City | Realign intersection. | 1.3 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5941 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10701000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 930000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 |  |  | 15631000
Carteret | SR 1493 (Live Oak Street) | NCDOT | NC 101 intersection in Beaufort | Construct roundabout. |  | Highway | STI (Prioritization) | 2 | Down East RPO | U-6058 | Region B | BG5T50, T, T(M) | 2023 | 1359000 | 2024 | 1200000 | 2025 | 6300000 |  |  | 8859000 | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT.
Carteret | US 70 (Live Oak Street) | NCDOT | NC 101 to SR 1429 (Olga Road). | Manage Access. | 1.8 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5945 | Division 2 | BG5T50 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27700000 |  |  | 51800000
Carteret | US 70 (Live Oak Street) | NCDOT | SR 1310 (Lennoxville Road) intersection in Beaufort | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5946 | Division 2 | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21901000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 450000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 |  |  | 26851000
Carteret | US 70 | NCDOT | Bridge 150033 over North River. | Replace bridge. |  | Highway | Transition | 2 | Down East RPO | B-4722B | Region B | [10 empty] | COMPLETE.
Carteret, Craven | NC 101 | NCDOT | SR 1212 (Airport Road) near Beaufort to Outer Banks Drive near Havelock | Install rumble stripes and pavement markings. | 19.3 | Highway | Safety | 2 | Down East RPO | HS-2402L | Region B | HSIP, T(M) |  |  |  |  | 2025 | 350000 |  |  | 350000
Carteret, Craven | SR 1124 (Nine Mile Road); SR 1756 (Lake Road) | NCDOT | NC 24 to Parker Court in Newport; SR 1124 (Nine Mile Road / Nine Foot Road) in Carteret County to SR 1745 (Miller Boulevard) in Craven County | Install rumble stripes and pavement markings. | 13.5 | Highway | Safety | 2 | Down East RPO | HS-2402I | Division 2 | HSIP, T(M) |  |  |  |  | 2025 | 324000 |  |  | 324000
Carteret, Craven, Beaufort, Lenoir | Various | NCDOT | Primary routes throughout Division 2 | Replace guardrail end units. |  | Highway | Safety | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO, Eastern Carolina RPO | HS-2402M | Region B | HSIP, T(M) |  |  |  |  | 2025 | 504000 |  |  | 504000 | UNDER CONSTRUCTION.
Carteret, Hyde | Cedar Island to Ocracoke Ferry | NCDOT | Cedar Island to Ocracoke Ferry | Replace M/V Silver Lake Sound Class Ferry. |  | Ferry | STI (Prioritization) | 1, 2 | Albemarle RPO, Down East RPO | F-5704 | Division 1, 2 | FBP, T |  |  |  |  | 2028 | 25600000 | 2024 | 3031000 | 28631000
Caswell | SR 1710 (Griers Church Road) | NCDOT | Bridge 160007 over Hyco Creek. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5725 | Division 7 | BGOFF | 2030 | 30000 |  |  | 2031 | 2600000 |  |  | 2630000
Caswell | NC 86 | NCDOT | US 158 to Virginia State line. | Construct passing lanes and shoulder improvements at various locations, and construct turn lanes from SR 1300 (Park Springs Road) to solid waste convenience center. | 7.7 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | R-5822 | Region D | BGLT5 | 2026 | 440000 | 2026 | 1300000 | 2028 | 26600000 |  |  | 28340000 | SCOPE INCLUDES SPOT ID H170625
Catawba | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast |  | Various locations in Hickory | Construct sidewalk | 0.1 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0165 | Division 12 | CMAQ, L(M), TADA | 2027 | 400000 | 2027 | 350000 | 2028 | 2400000 | 2026 | 350000 | 3500000 | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25.
Catawba | 9th Street NW Connector | HICKORY | City Walk to Old Lenoir Road in Hickory | Construct multi-use path. | 0.27 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5977 | Division 12 | BGDA, CRPDA, L(M) | 2021 | 108000 |  |  | 2023 | 1460000 |  |  | 1568000 | UNDER CONSTRUCTION.
Catawba | Aviation Walk Connector | HICKORY | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0067 | Division 12 | BGDA, L, TAANY | 2025 | 250000 |  |  | 2026 | 1600000 | 2023 | 150000 | 2000000 | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24.
Catawba | Book Walk | HICKORY | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5937 | Division 12 | BGANY, BGDA, L(M), TADA | 2021 | 225000 |  |  | 2023 | 3388000 | 2019 | 500000 | 4113000 | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION.
Catawba | Book Walk South | HICKORY | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5938 | Division 12 | BGANY, L(M), TAANY, TADA | 2021 | 105000 |  |  | 2023 | 5095000 | 2019 | 800000 | 6000000 | UNDER CONSTRUCTION.
Catawba | Centennial Boulevard | CLAREMONT | North Lookout Street to Main Street in Claremont | Construct sidewalk. | 1.16 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5935 | Division 12 | BGANY, L(M) |  |  |  |  | 2025 | 590000 | 2024 | 10000 | 600000 | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
Catawba | Conover Boulevard East |  | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0164 | Division 12 | BGDA, L | 2028 | 50000 | 2028 | 25000 | 2029 | 607000 | 2026 | 150000 | 832000
Catawba | SR 1006 (Island Ford Road) | MAIDEN | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0068 | Division 12 | BGDA, L, TAANY | 2026 | 500000 |  |  | 2027 | 850000 | 2024 | 405000 | 1755000 | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24.
Catawba | SR 1371 (Clement Boulevard); 21st Street Northwest | HICKORY | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0115 | Division 12 | BGDA, CRPDA, L, TAANY | 2025 | 50000 |  |  | 2026 | 2650000 | 2024 | 300000 | 3000000 | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24.
Catawba | SR 1453 (Springs Road Northeast) | HICKORY | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0066 | Division 12 | BGDA, L, TAANY | 2025 | 250000 |  |  | 2026 | 2400000 | 2023 | 350000 | 3000000 | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24.
Catawba | Various | HICKORY | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-6038 | Exempt | DP, L | 2020 | 662000 |  |  | 2021 | 19216000 | 2020 | 2052000 | 21930000 | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT.
Catawba | Old Lenoir Road Multi-Use Path | HICKORY | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Bike & Ped | STI (Prioritization) | 12 | Greater Hickory MPO | EB-5911 | Division 12 | CRPDA, L(M), TAANY, TADA | 2021 | 1830000 |  |  | 2023 | 16025000 | 2019 | 1495000 | 19350000 | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP.
Catawba | SR 1124 (Main Avenue Northwest) | HICKORY | 7th Avenue NE to 9th Street Northwest in Newton | Construct greenway with park nodes and pedestrian bridge over NC 127. | 1.2 | Bike & Ped | STI (Prioritization) | 12 | Greater Hickory MPO | EB-5750 | Division 12 | L(M), TAANY |  |  |  |  | 2020 | 14100000 |  |  | 14100000
Catawba | Various | CLAREMONT | Locations in Claremont. | Construct sidewalk. |  | Bike & Ped | Transition | 12 | Greater Hickory MPO | C-5195 | Exempt | [10 empty] | UNDER CONSTRUCTION
Catawba | New Route |  | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Highway | Appalachian Development Highway System | 12 | Greater Hickory MPO | HA-0007 | Exempt | ADHS, HF, L |  |  |  |  | 2024 | 2019000 | 2023 | 332000 | 2351000 | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035.
Catawba | I-40 | NCDOT | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Highway | Bridges | 12 | Greater Hickory MPO | B-6041 | Statewide Mobility | BFP, T(M) | 2026 | 290000 |  |  | 2032 | 26900000 |  |  | 27190000
Catawba | SR 1709 (Rock Barn Road) | NCDOT | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Greater Hickory MPO | B-5847 | Division 12 | BFP, T(M) | 2023 | 1400000 |  |  | 2031 | 10300000 |  |  | 11700000
Catawba | Trivium Parkway / New Route | HICKORY | Trivium Corporate Center. | Extend roadway and construct new route. | 0.2 | Highway | Economic Development | 12 | Greater Hickory MPO | U-6238 | Division 12 | T |  |  |  |  | 2026 | 1316000 |  |  | 1316000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CATALER NORTH AMERICA. COMPLETED.
Catawba | 17th Street Northwest | HICKORY | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Highway | Locally Selected | 12 | Greater Hickory MPO | HL-0004 | Division 12 | BGANY, BGDA, L(M) | 2023 | 720000 |  |  | 2024 | 4800000 | 2021 | 480000 | 6000000 | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22.
Catawba | US 70 | HICKORY | SR 1358 (4th Street Drive Southwest) intersection in Hickory. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 12 | Greater Hickory MPO | HL-0002 | Exempt | BGANY, BGDA, L(M) | 2022 | 100000 |  |  | 2025 | 900000 |  |  | 1000000 | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
Catawba | Various | NCDOT | Locations in Hickory MPO. | Improve congestion and air quality. |  | Highway | Other | 12 | Greater Hickory MPO | C-5608 | Exempt | CMAQ, L(M) | 2020 | 51000 |  |  | 2020 | 303000 | 2020 | 153000 | 507000 | IN PROGRESS
Catawba |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AA | [11 empty] | COMPLETE
Catawba |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AB | [11 empty] | COMPLETE
Catawba |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AD | [11 empty] | COMPLETE
Catawba |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AE | [11 empty] | COMPLETE
Catawba |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307C | [11 empty] | COMPLETE
Catawba |  | NCDOT |  |  | 0.653 | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | R-3100C | [11 empty] | COMPLETE.
Catawba | NC 127 | NCDOT | US 321 / NC 127 interchange north of SR 1182. | Upgrade and extend. |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2530B | [11 empty] | COMPLETE
Catawba | NC 10 | NCDOT | Mile marker 11.9 to mile marker 15.0. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Greater Hickory MPO | HS-2012I | Region F | HSIP, T(M) |  |  |  |  | 2024 | 227000 |  |  | 227000
Catawba | NC 10 | NCDOT | Mile marker 19.8 to mile marker 27.1. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Greater Hickory MPO | HS-2012H | Region F | HSIP, T(M) |  |  |  |  | 2024 | 467000 |  |  | 467000
Catawba | SR 1844 (Slanting Bridge Road) | NCDOT | Bridge 018023 over Lake Norman. | Upgrade guardrail and end units. | 0.09 | Highway | Safety | 12 | Greater Hickory MPO | HS-2012B | Division 12 | HSIP, T(M) |  |  |  |  | 2021 | 372000 |  |  | 372000 | COMPLETE
Catawba | SR 1849 (Mount Pleasant Road) | NCDOT | Bridge 018163 over Mountain Creek portion on Lake Norman. | Install guardrail. | 0.05 | Highway | Safety | 12 | Greater Hickory MPO | HS-2012A | Division 12 | HSIP, T(M) |  |  |  |  | 2021 | 84000 |  |  | 84000 | COMPLETE
Catawba | 29th Avenue NE | NCDOT | SR 1453 (Springs Road) to NC 127. | Widen to multi-lanes. | 3.19 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2307B | Division 12 | BGANY, T(M) | 2026 | 53800000 | 2026 | 15700000 | 2029 | 64700000 |  |  | 134200000
Catawba | I-40 | NCDOT | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | I-5716 | Statewide Mobility | NHP, T(M) | 2019 | 280000 |  |  | 2026 | 12300000 |  |  | 12580000 | RIGHT-OF-WAY IN PROGRESS
Catawba | McDonald Parkway | NCDOT | US 70 / US 321 to NC 127 in Hickory. | Construct multi-lanes, part on new location. | 6.6 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2307
Catawba | NC 127 | NCDOT | 1st Avenue Southeast to 2nd Avenue Southeast in Hickory. | Construct turn lanes. |  | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-5777 | Region F | BGANY, T | 2019 | 2150000 | 2019 | 436000 | 2025 | 9900000 |  |  | 12486000 | UNDER CONSTRUCTION.
Catawba | NC 127 | NCDOT | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. | 3.14 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2530A | Division 12 | BGANY, T | 2025 | 25000000 | 2025 | 3900000 | 2029 | 66900000 |  |  | 95800000 | NC BUILD BONDS: $24M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
Catawba | NC 127 | NCDOT | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. Upgrade and extend SR 1213 and proposed US 321 / NC 127 interchange north of SR 1182. | 4.5 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2530
Catawba | NC 16 | NCDOT | SR 1814 (Caldwell Road) to SR 1801 (Claremont Road) southeast of Newton. | Widen to four lanes. | 3.75 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3100B | Division 12 | [10 empty] | COMPLETE.
Catawba | NC 16 | NCDOT | SR 1895 (Tower Road) to SR 1800 (Caleb Setzer Road) southeast of Newton. | Widen to four lanes. | 9.1 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3100
Catawba | NC 16 | NCDOT | SR 1895 (Tower Road) to SR 1814 (Caldwell Road) southeast of Newton. | Widen to four lanes. | 4.41 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3100A | Division 12 | T |  |  |  |  | 2021 | 42510000 |  |  | 42510000 | COMPLETE; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
Catawba | SR 1005 (Startown Road) | NCDOT | US 70 to NC 10 in Hickory. | Widen to multi-lanes. | 4.62 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-5113 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 99500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74500000 |  |  | 201800000
Catawba | SR 1124 (33rd Street Southwest) | NCDOT | SR 1642 (34th Street Northwest) intersection in Long View. | Realign intersection. | 0.5 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-6042 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 |  |  | 8800000
Catawba | 16th Street (Sandy Ridge Road) | HICKORY | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Highway | Transition | 12 | Greater Hickory MPO | C-5196 | Division 12 | BGANY, CMAQ, L(M) | 2026 | 1756000 | 2026 | 1100000 | 2027 | 4978000 | 2023 | 500000 | 8334000 | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP.
Catawba | Western Piedmont Regional Transit Authority |  | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Greater Hickory MPO | TM-6110 | Public Transit | 5310 | [6 empty] | 2020 | 232000 | 232000
Catawba | Western Piedmont Regional Transit Authority | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | Systemwide | Funding for mobility manager. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Greater Hickory MPO | TG-6798 | Public Transit | 5307, L | [6 empty] | 2020 | 970000 | 970000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
Catawba | Center Street | NCDOT | Norfolk Southern Crossing 729571M in Hickory. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2012C | Division 12 | RR |  |  |  |  | 2026 | 492000 |  |  | 492000
Catawba | NC 16 (First Avenue) | NCDOT | Norfolk Southern Railroad Crossing 729601C in Conover. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2412E | Division 12 | RR |  |  |  |  | 2026 | 570000 |  |  | 570000
Catawba | Sixty Street Place Southeast | NCDOT | Norfolk Southern Railroad Crossing 729574H in Hickory. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2412D | Division 12 | RR |  |  |  |  | 2026 | 440000 |  |  | 440000
Catawba | SR 1124 (Thirty-Third Street Southwest) | NCDOT | Norfolk Southern Railroad Crossing 729551B in Long View. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2412C | Division 12 | RR |  |  |  |  | 2026 | 440000 |  |  | 440000
Catawba | SR 1358 (Fourth Street Southwest) | NCDOT | Norfolk Southern Crossing 729568E in Hickory. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2012F | Division 12 | RR |  |  |  |  | 2026 | 775000 |  |  | 775000
Catawba | SR 1753 (Rankin Avenue / Mount Olive Church Road) | NCDOT | Norfolk Southern Crossing 729612P in Newton. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2012G | Division 12 | RR |  |  |  |  | 2027 | 492000 |  |  | 492000
Catawba | Twenty Seventh Street Northwest | NCDOT | Norfolk Southern Railroad Crossing 729556K in Long View. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2412B | Division 12 | RR |  |  |  |  | 2026 | 440000 |  |  | 440000
Catawba, Alexander, Burke, Caldwell | Various | NCDOT | Greater Hickory Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 11, 12, 13 | Greater Hickory MPO | U-5924 | Division 11, 12, 13 | BGDA, L(M) | [6 empty] | 2024 | 1750000 | 1750000
Catawba, Alexander, Burke, Caldwell | Various | NCDOT | Greater Hickory Planning Organization (GHMPO) area. | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 11, 12, 13 | Greater Hickory MPO | HL-0100 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 0
Catawba, Burke, Caldwell, Alexander | Various | NCDOT | Greater Hickory Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 11, 12, 13 | Greater Hickory MPO | U-5546 | Division 11, 12, 13 | L(M), TADA |  |  |  |  | 2024 | 4017000 |  |  | 4017000
Catawba, Burke, Caldwell, Alexander | Various | NCDOT | Greater Hickory Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 11, 12, 13 | Greater Hickory MPO | U-5615 | Division 11, 12, 13 | BGANY, BGDA, L |  |  |  |  | 2024 | 45073000 |  |  | 45073000
Catawba, Caldwell, Burke | US 321 | NCDOT | North of US 70 in Hickory to US 321A. | Widen to six lanes and replace bridges 130366 and 130367 over the Catawba River on US 321. | 3.35 | Highway | STI (Prioritization) | 11, 12, 13 | Greater Hickory MPO | U-4700A | Statewide Mobility | L, NHP, T(M) | 2021 | 75145000 |  |  | 2027 | 282400000 |  |  | 357545000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035
Catawba, Iredell, Lincoln | NC 150 | NCDOT | NC 16 interchange to US 21. | Widen to multi-lanes. | 14.8 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | R-2307 | [11 empty] | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717.
Catawba, Lincoln | NC 10 | NCDOT | Mile marker 0.0 to mile marker 2.2 in Lincoln County and mile marker 0.0 to mile marker 11.0 in Catawba County. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | HS-2012M | Region F | HSIP, T(M) |  |  |  |  | 2024 | 524000 |  |  | 524000
Catawba, Lincoln | NC 150 | NCDOT | Relocated NC 16 (STIP Project R-2206) to east of SR 1840 (Greenwood Road). | Widen to four lanes with a bypass of the Terrell Historic District. | 7.94 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | R-2307A | Region F | BGLT5, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 155000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 207200000 |  |  | 371700000
Chatham | SCR | SILER CITY MUNICIPAL AIRPORT (SCR) | Siler City Municipal Airport | Acquire navigation easements in runway 4 and runway 22 approaches, and remove obstructions in easements. |  | Aviation | STI (Prioritization) | 8 | Central Pines RPO | AV-5736 | Division 8 | T | 2024 | 365000 | [6 empty] | 365000
Chatham | Chatham Business Drive | PITTSBORO | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BL-0035 | Exempt | CMAQ, L(M) | 2022 | 10000 |  |  | 2023 | 160000 | 2022 | 40000 | 210000
Chatham | Pittsboro Elementary School Road | PITTSBORO | Farrell Street to McClehanan Street | Complete sidewalk gap. | 0.11 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BL-0062 | Exempt | CMAQ, L(M) |  |  |  |  | 2024 | 220000 | 2023 | 59000 | 279000
Chatham | Salisbury Street | PITTSBORO | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BN-0028 | Exempt | CRPANY, L(M) | 2026 | 28000 |  |  | 2026 | 254000 | 2025 | 119000 | 401000
Chatham | SR 1006 (North Second Avenue) | SILER CITY | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BN-0027 | Exempt | CRP550, L(M) | 2026 | 198000 |  |  | 2027 | 1517000 | 2025 | 235000 | 1950000
Chatham | SR 1008 (Mount Carmel Church Road); US 15 / US 501 | NCDOT | North side of Governors Drive to existing sidewalk and intersection of SR 1831 / 1848 (Village Park Drive); SR 1724 (Old Lystra Road) intersection in Chapel Hill | Install pedestrian signals and crosswalks. |  | Bike & Ped | Locally Selected | 8 | Triangle West TPO | BL-0070 | Division 8 | BGDA, BGDACV, HF, L(M) |  |  |  |  | 2023 | 175000 | 2023 | 5000 | 180000 | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS.
Chatham | SR 1107 (East Third Street) | SILER CITY | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BN-0026 | Exempt | CRP550, L(M) | 2026 | 184000 |  |  | 2027 | 2106000 | 2025 | 275000 | 2565000
Chatham | Pittsboro Lake Park | PITTSBORO | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Bike & Ped | NCDOT Selected (Other Selection Process) | 8 | Central Pines RPO | BN-0012 | Exempt | CRP550, L(M) | 2026 | 31000 |  |  | 2026 | 455000 | 2024 | 146000 | 632000
Chatham | Various | Town of Pittsboro | Routes in the Town of Pittsboro | Conduct a feasibility study for West Salisbury Street, The Village Apartments Connector, the Kiwanis Park Connector, the Town to Village Trail, the NC 87 to Central Carolina Community College (CCCC) Campus Sidewalk, and the Chatham Marketplace Connector. |  | Bike & Ped | Other | 8 | Central Pines RPO | BO-2615 | Exempt | DP | [6 empty] | 2026 | 996000 | 996000 | DP FUNDS REPRESENT RAISE GRANT FUNDING
Chatham | SR 1107 (West 3rd Street) | SILER CITY | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-6006 | Division 8 | L(M), TA5T50 | 2026 | 220000 | 2026 | 160000 | 2026 | 2000000 | 2025 | 333000 | 2713000
Chatham | SR 2103 (East Raleigh Street) | SILER CITY | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5734 | Division 8 | L(M), TA5T50 | 2024 | 205000 | 2024 | 143000 | 2026 | 2300000 |  |  | 2648000
Chatham | Triangle Innovation Point megasite | NCDOT | Locations in Division 8. | Construct roadway improvements near the triangle innovation point megasite. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006 | Highway Fund | [10 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
Chatham | US 64 | NCDOT | West of Siler City | Construct roadway improvements and industrial access road. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0011 | Division 8 | T | 2024 | 250000 | 2024 | 250000 | 2024 | 8500000 | 2023 | 1000000 | 10000000 | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED.
Chatham | Various | NCDOT | Site Design 1A | Resurface and strengthen roadways surrounding Triangle Innovation Point megasite. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006A | Highway Fund | HF |  |  |  |  | 2023 | 7000000 |  |  | 7000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
Chatham | Various | NCDOT | Site Design 1B and 1C | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006B | Highway Fund | HF | 2023 | 10000000 | 2023 | 5000000 | 2024 | 175000000 | 2023 | 3000000 | 193000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
Chatham | Various | NCDOT | Site Design 2A and 2B | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006C | Highway Fund | HF |  |  |  |  | 2025 | 50000000 |  |  | 50000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
Chatham | Various | CHATHAM COUNTY | Locations in Chatham County. | Purchase and install two electric vehicle charging stations. |  | Highway | Locally Selected | 8 | Triangle West TPO | HL-0156 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 266000 |  |  | 266000
Chatham | Various | CHATHAM COUNTY | Chatham County | Purchase and install four electric vehicle charging stations. |  | Highway | NCDOT Selected (Other Selection Process) | 8 | Central Pines RPO | HN-0035 | Exempt | CRPANY, L(M) |  |  |  |  | 2026 | 46000 | 2025 | 74000 | 120000
Chatham | Various | Town of Siler City | Locations in downtown Siler City | Complete final design for bus stops, streetscape elements, stormwater infrastructure, underground utility design, lighting, and flood mitigation with water quality improvements in Siler City’s downtown area. |  | Highway | Other | 8 | Central Pines RPO | HO-0034 | Exempt | DP | [6 empty] | 2026 | 6194000 | 6194000 | DP FUNDS REPRESENT RAISE GRANT FUNDING
Chatham | Various | Town of Siler City | Locations in the Loves Creek Tributary area around Raleigh Street | Complete final design for bus stops, streetscape improvements, stormwater infrastructure upgrades, underground utility design, lighting, and flood mitigation with water quality improvements in the Loves Creek Tributary area. |  | Highway | Other | 8 | Central Pines RPO | HO-0035 | Exempt | DP | [6 empty] | 2026 | 3995000 | 3995000 | DP FUNDS REPRESENT RAISE GRANT FUNDING
Chatham | NC 751; SR 1008 (Farrington Point Road) | NCDOT | NC 751 from US 64 to Durham County line; SR 1008 (Farrington Point Road) from SR 1972 (Pea Ridge Road) to Orange County line | Install rumble stripes. | 21.8 | Highway | Safety | 8 | Central Pines RPO, Triangle West TPO | HS-2408A | Region E | HSIP, T(M) |  |  |  |  | 2025 | 696000 |  |  | 696000
Chatham | US 421 | NCDOT | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Highway | Safety | 8 | Central Pines RPO | HS-2408F | Statewide Mobility | HSIP, T(M) | 2027 | 5000 | 2027 | 5000 | 2028 | 1060000 |  |  | 1070000
Chatham | US 421 (Future I-685) | NCDOT | NC 902 intersection. | Construct reduced conflict intersection. | 0.5 | Highway | Safety | 8 | Central Pines RPO | W-5808B | Statewide Mobility | HSIP, T(M) | 2024 | 100000 |  |  | 2025 | 1550000 |  |  | 1650000 | RIGHT-OF-WAY IN PROGRESS
Chatham | Chatham Park Way | NCDOT | Chatham Park Way to US 64 and realignment of Suttles Road to new intersection with Chatham Park Way | Construct new westbound on-ramp. | 0.5 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963D | Division 8 | T | 2024 | 500000 |  |  | 2024 | 6591000 |  |  | 7091000 | ROW BEING DONATED BY TOWN OF PITTSBORO
Chatham | NC 751 | NCDOT | SR 1731 (O'Kelly Chapel Road). | Upgrade and realign intersection. | 0.5 | Highway | STI (Prioritization) | 8 | Triangle West TPO | R-5825 | Division 8 | T |  |  |  |  | 2023 | 1264000 |  |  | 1264000 | RIGHT-OF-WAY IN PROGRESS
Chatham | New route | NCDOT | US 15 / US 501 / NC 87 to US 64 Business in Pittsboro. | Construct two lane roadway on new location. | 3.03 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963 | [11 empty] | Former R-5963B merged into R-5963A.
Chatham | New Route | NCDOT | US 15 / US 501 south of Pittsboro to US 64 Business | Construct roadway. | 1.33 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963A | Division 8 | T | 2025 | 6259000 | 2025 | 62000 | 2025 | 75424000 |  |  | 81745000 | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) AND $6M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
Chatham | New Route | NCDOT | US 64 Business to just north of US 64 | Construct roadway. | 1.22 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963C | Not Funded | T | NOT FUNDED |  | NOT FUNDED | 30000 | NOT FUNDED | 32100000 | NOT FUNDED |  | 32130000
Chatham | New Route - Chatham Park Way | NCDOT | North of proposed Grant Drive to US 15 / US 501 | Construct roadway. | 1.41 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5930B | Division 8 | T |  |  |  |  | 2025 | 17190000 |  |  | 17190000 | UNDER CONSTRUCTION
Chatham | New Route - Chatham Park Way | NCDOT | Northern terminus of existing Chatham Park Way just north of US 64 to north of proposed Grant Drive | Construct roadway. | 1.11 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5930A | Division 8 | O, T |  |  |  |  | 2024 | 19801000 |  |  | 19801000 | UNDER CONSTRUCTION
Chatham | New Route (Chatham Park Way) | NCDOT | US 64 Bypass in Pittsboro to US 15 / US 501. | Construct roadway on new location. | 2.52 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5930 | Division 8 | O, T | 2023 | 3693000 | 2023 | 360000 |  |  |  |  | 4053000 | "O" FUNDING REFLECTS LOCAL PARTICIPATION.
Chatham | US 15 / US 501 | NCDOT | South of US 64 Business to Powell Place Lane in Pittsboro. | Widen to multi-lanes, mill and resurface, and construct roadway and streetscape improvements at traffic circle. | 1.9 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5724
Chatham | US 15 / US 501 | NCDOT | US 15 / US 501, north of US 64 Business to Powell Place Lane | Mill and resurface from north of US 64 Business to Launis Street and widen from Launis Street to Powell Place Lane. | 1.79 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5724B | Division 8 | T | 2023 | 3900000 | 2023 | 1300000 | 2027 | 27200000 |  |  | 32400000 | RIGHT-OF-WAY IN PROGRESS
Chatham | US 15 / US 501 | NCDOT | US 15 / US 501, south of US 64 Business to north of US 64 Business | Construct roadway and streetscape improvements at traffic circle. |  | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5724A | Division 8 | T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION
Chatham | US 15 / US 501 | NCDOT | US 64 Bypass to SR 1919 (Smith Level Road). | Upgrade remaining non-synchronized sections of facility to synchronized street. | 10.46 | Highway | STI (Prioritization) | 8 | Central Pines RPO, Triangle West TPO | U-6192 | Division 8 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83300000 |  |  | 107000000
Chatham | US 64 | NCDOT | NC 751 intersection in Apex. | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 8 | Capital Area MPO | R-5887 | Region E | NHP, T(M) | 2028 | 6400000 | 2028 | 3000000 | 2032 | 62300000 |  |  | 71700000
Chatham | US 64 (East 11th Street) | NCDOT | North Glenn Avenue to US 421 (Future I-685) in Siler City. | Upgrade roadway to include median for access control, sidewalks, crosswalks, bicycle lanes and / or multi-use side path. | 2.64 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5737 | Region E | T | 2026 | 10800000 | 2026 | 3400000 | 2030 | 40300000 |  |  | 54500000
Chatham | Pittsboro | CHATHAM TRANSIT NETWORK | Pittsboro | Provide operating assistance for new transit service in the Town of Pittsboro. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 8 | Central Pines RPO | TN-6135 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 175000 | 175000
Chatham | SR 1916 (Corinth Road) | NCDOT | Crossing 630723C near Haywood | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Central Pines RPO | RX-2008A | Division 8 | RR |  |  |  |  | 2026 | 800000 |  |  | 800000
Chatham, Cumberland, Edgecombe, Gaston, Harnett, Henderson, Lee, Lincoln, Martin, Transylvania, Bertie, Hertford, Nash, Randolph, Wake | Various | NCDOT | Locations in Divisions 1, 4, 5, 6, 8, 12, and 14. | install EV chargers at multiple community colleges. |  | Highway | Other | 1, 4, 5, 6, 8, 12, 14 | Capital Area MPO, Central Pines RPO, Fayetteville Area MPO, French Broad River MPO, Gaston-Cleveland-Lincoln MPO, Land-of-Sky RPO, Mid-Carolina RPO, Peanut Belt RPO, Piedmont Triad RPO, Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | HO-0019 | Exempt | DP, HF(M) |  |  |  |  | 2026 | 1259000 |  |  | 1259000 | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. HF REPRESENT CONTINGENCY FUNDS.
Chatham, Hoke, Lee, Randolph, Scotland | Various | NCDOT | Secondary routes In Chatham, Lee, Hoke, Randolph and Scotland Counties. | Install long-life pavement markings. |  | Highway | Safety | 8 | Central Pines RPO, Lumber River RPO, Piedmont Triad RPO, High Point Urban Area MPO, Fayetteville Area MPO, Triangle West TPO | HS-2008C | Region E | HSIP, T(M) |  |  |  |  | 2022 | 1580000 |  |  | 1580000
Chatham, Lee | SR 1007 (Plank Road) | NCDOT | Bridge 180169 over Deep River. | Replace bridge. | 0.25 | Highway | Bridges | 8 | Central Pines RPO | HB-0034 | Division 8 | BGOFF | 2030 | 325000 | 2030 | 325000 | 2032 | 6500000 |  |  | 7150000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | BO-2408 | Division 8 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Locations in Division 8 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | R-5788 | Division 8 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Various locations in Division 8. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Triangle West TPO | BO-2608 | Division 8 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8 | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | W-5708DIV | Division 8 | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8 | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | W-5708REG | Region E | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8 | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | W-5708SW | Statewide Mobility | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | HS-2008 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | HS-2408 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | W-5708 | [11 empty] | IN PROGRESS
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Construct safety improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | W-5808
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | HS-2023
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | HS-2023DIV | Division 8 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | HS-2023REG | Region E | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | HS-2023SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Routes in Division 8. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | W-5208 | [11 empty] | UNDER CONSTRUCTION
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Various locations in Division 8 | Safety Improvements. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Triangle West TPO | HS-2608 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Locations in Division 8. | Implementation of traffic separation study and closures in Division 8. |  | Rail | Rail-Highway Grade Crossing Closure | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | RC-2008 | Division 8 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Locations in Division 8. | Construct highway-rail grade crossing safety improvements in Division 8. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | RX-2008 | Division 8 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Locations in Division 8. | Construct highway-rail grade crossing safety improvements in Division 8. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | RX-2408 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | Various | NCDOT | Locations in Division 8. | Construct highway-rail grade crossing safety improvements in Division 8. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Triangle West TPO | RX-2608 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Chatham, Orange | Various | NCDOT | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Highway | Other | 7, 8 | Central Pines RPO | C-5618 | Exempt | CMAQ, L(M) | 2020 | 45000 |  |  | 2020 | 255000 | 2020 | 135000 | 435000
Cherokee | SR 1326 (Joe Brown Highway) | NCDOT | Bridge 190159 over Hanging Dog Creek | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-4069 | Division 14 | BGOFF | 2025 | 295000 |  |  | 2027 | 1800000 |  |  | 2095000
Cherokee | SR 1548 (Old Highway 64) | NCDOT | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-5925 | Division 14 | BFP, T(M) | 2026 | 660000 | 2026 | 320000 | 2027 | 6500000 |  |  | 7480000
Cherokee | NC 141 | NCDOT | SR 1533 (Hendrix Road) intersection in Marble. | Construct left turn lane. |  | Highway | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | HN-0029 | Region G | CRPLT5, T(M) |  |  |  |  | 2024 | 600000 |  |  | 600000
Cherokee | SR 1564 (Brasstown Road) | NCDOT | John C. Campbell Folk School. | Install four rectangular flashing beacons and construct concrete landing pads. | 0.49 | Highway | Safety | 14 | Southwestern RPO | HS-2014V | Division 14 | HSIP, T(M) |  |  |  |  | 2024 | 150000 |  |  | 150000
Cherokee | US 19 | NCDOT | Various locations. | Upgrade guardrail end units. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414L | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 130000 |  |  | 130000
Cherokee | US 19 Business | NCDOT | SR 1424 (Connahetta Street) and Maple Street intersections | Install pedestrian rectangular rapid flashing beacons. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2414B | Region G | HSIP, T(M) |  |  |  |  | 2025 | 76000 |  |  | 76000
Cherokee | US 64 / US 74 | NCDOT | NC 60 near Murphy. | Construct directional leftover with U-turn bulb-outs. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014X | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 934000 |  |  | 934000
Cherokee | US 19 / US 129 | NCDOT | Georgia state line to US 64. | Modernize roadway to include additional paved shoulders and realignment to improve roadway geometry. | 3.8 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5861 | Division 14 | BGLT5, T | 2022 | 11400000 | 2022 | 2550000 | 2024 | 77933000 |  |  | 91883000 | RIGHT-OF-WAY IN PROGRESS.
Cherokee | US 19 / US 74 / US 64 / US 129 | NCDOT | Down Street to US 19 Business (Hiwassee Street). | Construct roadway improvements. | 0.07 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5735 | Division 14 | T | 2020 | 4815000 |  |  | 2020 | 15390000 | 2020 | 2700000 | 22905000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE)
Cherokee | US 19 / US 74 / US 64 / US 129 | NCDOT | Down Street to US 19 Business (Hiwassee Street). | Construct roadway improvements. | 0.73 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5735A | Division 14 | [10 empty] | CLEARING ONLY.
Cherokee | Cherokee County Transit | CHEROKEE COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6118 | Public Transit | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | BO-2414 | Division 14 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 600000 | 6100000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | R-5794 | Division 14 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Various locations in Division 14. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | BO-2614 | Division 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2014 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2414 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714 | [11 empty] | IN PROGRESS
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714DIV | Division 14 | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714REG | Region G | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714SW | Statewide Mobility | HSIP, T(M) | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Construct safety improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5814
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029DIV | Division 14 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029REG | Region G | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Various locations in Division 14. | Safety Improvements. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2614 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Locations in Division 14. | Traffic separation study implementation and closures. |  | Rail | Rail-Highway Grade Crossing Closure | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RC-2014 | Division 14 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Locations in Division 14. | Construct highway-rail grade crossing safety improvements in Division 14. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RX-2014 | Division 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Locations in Division 14. | Construct highway-rail grade crossing safety improvements in Division 14. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RX-2414 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | Various | NCDOT | Locations in Division 14. | Construct highway-rail grade crossing safety improvements in Division 14. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RX-2614 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Cherokee, Graham, Jackson, Swain | Federal Tribal Transportation Program (FTTP) | FHWA | Various tribal lands | Improve roads and bridges on transportation facilities that are owned by the Federal Government that provides access to tribal lands. |  | Highway | Other | 14 | Southwestern RPO | R-5966 | Exempt | FTTP |  |  |  |  | 2023 | 25490000 |  |  | 25490000 | PROGRAM IN PROGRESS
Cherokee, Graham, Jackson, Swain | Eastern Band Of Cherokee Indians | EASTERN BAND OF CHEROKE INDIANS | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6127 | Public Transit | 5311, L, S | [6 empty] | 2020 | 928000 | 928000 | FUNDS AUTHORIZED IN PROGRESS
Chowan | SR 1202 (Hickory Fork Road) | NCDOT | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Highway | Other | 1 | Albemarle RPO | HO-0023 | Exempt | DP, HF(M) | 2026 | 150000 |  |  | 2028 | 350000 | 2025 | 100000 | 600000 | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22
Clay | NC 69 | NCDOT | Georgia state line to US 64 (Hayesville Bypass). | Upgrade existing two-lanes. | 3.51 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011A | [11 empty] | COMPLETE
Clay | NC 69 | NCDOT | Georgia state line to US 64 (Hayesville Bypass). | Widen to four lanes. | 3.51 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011C | Exempt | ADHS |  |  |  |  | 2020 | 52600000 |  |  | 52600000 | UNDER CONSTRUCTION
Clay | US 64 | NCDOT | East of the Hiwassee River to east of NC 175. | Upgrade existing two-lanes. | 3.8 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011BB | [11 empty] | COMPLETE
Clay | US 64 | NCDOT | East of the Hiwassee River to east of NC 175. | Widen to four lanes. |  | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011D | Not Funded | ADHS | NOT FUNDED | 20845000 | NOT FUNDED | 378000 | NOT FUNDED | 52800000 | NOT FUNDED |  | 74023000
Clay | US 64 | NCDOT | NC 69 in Hayesville to east of the Hiwassee River. | Upgrade existing two-lanes. | 0.946 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011BA | [11 empty] | COMPLETE
Clay | US 64; NC 69 | NCDOT | NC 69 to east of NC 175; Georgia state line to US 64. | Widen to four lanes divided. Widen to multi-lanes. | 7.3 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011 | [11 empty] | APD FUNDS ARE 100% FEDERAL
Clay | SR 1140 (Myers Chapel Road) | NCDOT | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Highway | Bridges | 14 | Southwestern RPO | HF-0005 | Exempt | FLAP, HF, HF(M) | 2024 | 310000 | 2024 | 286000 | 2025 | 4166000 | 2021 | 745000 | 5507000 | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS.
Clay | SR 1100 (Old Highway 64 West) | NCDOT | SR 1135 (Settawig Road) intersection near Brasstown. | Widen and install guardrail. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014F | Division 14 | HSIP, T(M) |  |  |  |  | 2023 | 45000 |  |  | 45000 | UNDER CONSTRUCTION.
Clay | US 64 | NCDOT | SR 1147 (Oak Forest Road) intersection near Hayesville. | Extend two-way left lane. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014AA | Region G | HSIP, T(M) |  |  |  |  | 2024 | 51000 |  |  | 51000
Clay | US 64 | NCDOT | Various locations. | Upgrade guardrail end units. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414M | Region G | HSIP, T(M) |  |  |  |  | 2025 | 750000 |  |  | 750000
Clay | NC 175 | NCDOT | Georgia state line to US 64. | Upgrade roadway. | 4.15 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5742 | Division 14 | T | 2020 | 540000 |  |  | 2020 | 32847000 | 2020 | 2505000 | 35892000 | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
Clay | NC 175 | NCDOT | Georgia state line to US 64. | Upgrade roadway. | 4.15 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5742A | Division 14 | [10 empty] | CLEARING ONLY.
Clay | US 64 Business | NCDOT | US 64 to SR 1307 (Main Street). | Upgrade roadway. | 1.19 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5863 | Division 14 | T | 2022 | 4200000 |  |  | 2026 | 19371000 |  |  | 23571000 | RIGHT-OF-WAY IN PROGRESS.
Clay | Clay County Transit | CLAY COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6120 | Public Transit | 5311, L, S | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
Cleveland | Shelby Rail Trail | SHELBY | South Dekab Street to Gardner Street in Shelby. Graham Street to West Marion Street in Shelby | Construct multi-use path. | 10.41 | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO | EB-6037A | Division 12 | L(M), TAANY |  |  |  |  | 2025 | 5198000 | 2024 | 10000 | 5208000
Cleveland | SR 1607 (Eastridge Drive) | NCDOT | Bridge 220392 over Buffalo Creek. | Replace bridge. |  | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | B-5858 | Division 12 | BGOFF | 2027 | 20000 | 2027 | 225000 | 2029 | 1500000 |  |  | 1745000
Cleveland | US 74 | NCDOT | Bridges 220048 and 220049 over Sandy Run. | Replace bridges. | 0.25 | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | BR-0012 | Highway Fund | HFB | 2022 | 42000 |  |  | 2024 | 61591000 |  |  | 61633000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045
Cleveland | New Route | NCDOT | SR 1313 (Washburn Switch Road) to new industrial sites in Cleveland County | Construct improvements on SR 1313 (Washburn Switch Road) and a new 3-lane road. |  | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-5849 | Division 12 | [10 empty] | UNDER CONSTRUCTION
Cleveland | US 74 (Shelby Bypass) | NCDOT | East of SR 1318 (Kimbrell Road) to east of NC 226 | Construct four lane divided freeway on new location. | 5.27 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707F | Pre-STI (Transition) | [10 empty] | COMPLETE
Cleveland | US 74 (Shelby Bypass) | NCDOT | West of SR 1162 (Peachtree Road) to east of SR 1315 (Plato Road). | Acquire right-of-way. | 3.9 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707A | [11 empty] | COMPLETE
Cleveland | US 74 (Shelby Bypass) | NCDOT | West of SR 1162 (Peachtree Road) to east of SR 1318 (Kimbrell Road). | Construct four lane divided freeway on new location. | 1.88 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707AA | [11 empty] | COMPLETE
Cleveland | NC 10 | NCDOT | Mile Marker 7.7 to Mile Marker 15.4 | Install rumble strips. | 7.7 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2412A | Region F | HSIP |  |  |  |  | 2026 | 305000 |  |  | 305000
Cleveland | NC 18 | NCDOT | Mile marker 0.0 to mile marker 6.0. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012G | Region F | HSIP, T(M) |  |  |  |  | 2024 | 451000 |  |  | 451000
Cleveland | NC 18 | NCDOT | Mile marker 13.5 to mile marker 18.6. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012L | Region F | HSIP, T(M) |  |  |  |  | 2024 | 186000 |  |  | 186000
Cleveland | US 74 | NCDOT | SR 1168 (Lattimore Road) intersection in Mooresboro; West of US 74 Business (Ellenboro Road) to east of Bridges 023048 and 023049 over Sandy Run. | Upgrade at-grade intersection to interchange; Upgrade US 74 to full control of access. | 1.35 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-4045 | Region F | DP, T | 2023 | 16000000 | 2023 | 5600000 | 2023 | 61591000 |  |  | 83191000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION.
Cleveland | US 74 | NCDOT | US 74 Business to NC 226. | Construct access management improvements. | 5.96 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-5713 | Region F | NHP, T(M) |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 |  |  | 3200000
Cleveland | US 74 (Dixon Boulevard) | NCDOT | NC 150 (Dekalb Street) intersection in Shelby. | Construct interchange. | 1 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-2567 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21199000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48400000 |  |  | 70899000 | TO BE LET WITH U-5929
Cleveland | US 74 (Dixon Boulevard) | NCDOT | NC 226 (Earl Road) intersection in Shelby. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5929 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13600000 |  |  | 22500000 | TO BE LET WITH U-2567
Cleveland | US 74 (Shelby Bypass) | NCDOT | East of NC 150 to existing US 74 west of SR 2238 (Long Branch Road). | Construct four lane divided freeway on new location. | 4.26 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707D | Region F | T | 2019 | 20684000 |  |  | 2024 | 207397000 |  |  | 228081000 | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE);
Cleveland | US 74 (Shelby Bypass) | NCDOT | East of NC 226 to east of NC 150. | Construct four lane divided freeway on new location. | 5.42 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707C | Region F | T |  |  |  |  | 2020 | 40335000 | 2021 | 75000 | 40410000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
Cleveland | US 74 (Shelby Bypass) | NCDOT | US 74 west of SR 2238 (Long Branch Road) to west of SR 1001 (Stoney Point Road). | Construct four lane divided freeway on new location. | 3.03 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707E | Region F | T | 2019 | 35532000 | 2023 | 5300000 |  |  |  |  | 40832000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D.
Cleveland | US 74 (Shelby Bypass) | NCDOT | West of SR 1162 (Peachtree Road) to west of SR 1001 (Stoney Point Road). | Construct four lane divided freeway on new location. | 18.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707
Cleveland | US 74 Business (Marion Street) | NCDOT | NC 150 (Cherryville Road) intersection in Shelby. | Realign intersection. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5775 | Region F | L, T |  |  |  |  | 2022 | 10366000 |  |  | 10366000 | UNDER CONSTRUCTION. $702,705 FROM CITY OF SHELBY
Cleveland | US 74 (Shelby Bypass) | NCDOT | East of SR 1315 (Plato Lee Road) to east of NC 226. | Construct four lane divided freeway on new location. | 2.58 | Highway | Transition | 12 | Gaston-Cleveland-Lincoln MPO | R-2707B | Pre-STI (Transition) | [10 empty] | COMPLETE
Cleveland | US 74 (Shelby Bypass) | NCDOT | East of SR 1318 (Kimbrell Road) to east of SR 1315 (Plato Lee Road). | Construct four lane divided freeway on new location. | 2.68 | Highway | Transition | 12 | Gaston-Cleveland-Lincoln MPO | R-2707AB | Pre-STI (Transition) | [10 empty] | COMPLETE
Cleveland | Transportation Administration of Cleveland County | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TK-6166 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1196000 | 1196000 | FUNDS AUTHORIZED IN PROGRESS
Cleveland | Lineberger Street | NCDOT | CSX Crossing 631872G in Shelby. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO | RX-2012A | Division 12 | RR |  |  |  |  | 2026 | 474000 |  |  | 474000
Cleveland | SR 2263 (Margrace Road) | NCDOT | Norfolk Southern Crossing 716273A in Kings Mountain. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO | RX-2012E | Division 12 | RR |  |  |  |  | 2026 | 555000 |  |  | 555000
Cleveland, Gaston | NC 150 |  | North of SR 2068 (Troy Road) to SR 1651 (Delview Road) | Install rumble strips with six inch long life pavement markings. | 7.3 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2412B | Region F | HSIP |  |  |  |  | 2026 | 389000 |  |  | 389000
Cleveland, Gaston | I-85 | NCDOT | South Carolina state line to US 74. | Install broadband for Traveler Information Systems. | 9.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FC | Statewide Mobility | DP, HSIP, L(M), T(M) |  |  |  |  | 2025 | 7650000 |  |  | 7650000 | DP REPRESENTS 2022 INFRA GRANT.
Cleveland, Gaston | Kings Mountain |  | Five locations | Funding to install 20 new EV chargers |  | Public Transportation (Transit) | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | TO-6813 | Exempt | DP, L |  |  |  |  | 2024 | 1029000 |  |  | 1029000 | DP REPRESENTS CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT
Cleveland, Polk, Gaston, Henderson, Rutherford, Mecklenburg, Buncombe | U 74 | NCDOT | I-40 in Asheville to I-77 at I-485 (south) in Charlotte. | Install broadband for Traveler Information Systems. | 123.09 | Highway | Other | 10, 12, 13, 14 | Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Charlotte Regional TPO | HO-0002A | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 18435000 |  |  | 18435000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C.
Columbus | CPC | COLUMBUS COUNTY AIRPORT (CPC) | Columbus County Airport | Construct apron expansion. |  | Aviation | STI (Prioritization) | 6 | Cape Fear RPO | AV-5748 | Division 6 | T |  |  |  |  | 2024 | 3000000 |  |  | 3000000
Columbus | CPC | CPC | Columbus County Municipal Airport. | Extend runway. |  | Aviation | STI (Prioritization) | 6 | Cape Fear RPO | AP-0006 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 248000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3677000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 390000 | 4315000
Columbus | CPC | CPC | Columbus County Municipal Airport. | Improve runway safety area and widen runway. |  | Aviation | STI (Prioritization) | 6 | Cape Fear RPO | AP-0007 | Division 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10536000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1054000 | 11590000
Columbus | US 701 Business (East 5th Street) |  | West of Lynwood Norris Road to US 701 Bypass in Tabor City. | Construct sidewalk and signalized pedestrian crossing. | 0.2 | Bike & Ped | NCDOT Selected (Other Selection Process) | 6 | Cape Fear RPO | BN-0006 | Exempt | CRPLT5, HF(M) |  |  |  |  | 2025 | 250000 |  |  | 250000 | UNDER CONSTRUCTION. HF(M) FUNDING REPRESENT LEGISLATIVE CONTINGENCY FUNDS.
Columbus | SR 1800 (Blacksmith Road) | NCDOT | Bridge 230250 over Ricefield Branch. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Cape Fear RPO | HB-0009 | Division 6 | BGOFF | 2029 | 140000 | 2029 | 130000 | 2030 | 1600000 |  |  | 1870000
Columbus | US 74 (Future I-74) | NCDOT | East of NC 214 to west of SR 1824 (Water Tank Road). | Rehabilitate pavement. | 7 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0015 | Statewide Mobility | BGLT5 |  |  |  |  | 2024 | 10300000 |  |  | 10300000
Columbus | US 74 (Future I-74) | NCDOT | Robeson County line to west of SR 1585 (Union Valley Road). | Rehabilitate pavement. | 13.86 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0020 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2031 | 15000000 |  |  | 15000000
Columbus | US 74 (Future I-74) | NCDOT | West of SR 1585 (Union Valley Road) to west of US 701 Business. | Rehabilitate pavement. | 6.54 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0019 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2031 | 5400000 |  |  | 5400000
Columbus | US 74 (Future I-74) | NCDOT | West of US 701 Business to west of NC 214. | Rehabilitate pavement. | 17.59 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0018 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2025 | 26630000 |  |  | 26630000 | UNDER CONSTRUCTION.
Columbus | US 701 Business (Madison Street) |  | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Cape Fear RPO | HN-0023 | Region C | CRPANY, T(M) | 2025 | 100000 |  |  | 2026 | 2200000 | 2024 | 400000 | 2700000 | RIGHT-OF-WAY IN PROGRESS
Columbus | NC 11 | NCDOT | SR 1740 (Old Lake Road) intersection. | Construct roundabout. | 0.5 | Highway | Safety | 6 | Cape Fear RPO | W-5806A | Region C | HSIP, T(M) |  |  |  |  | 2025 | 50000 |  |  | 50000 | UNDER CONSTRUCTION.
Columbus | NC 130; NC 410 | NCDOT | Mile marker 0 to mile marker 17.04; Mile marker 2.62 to 13.6 | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Cape Fear RPO | HS-2406J | Region C | HSIP, T(M) |  |  |  |  | 2025 | 890000 |  |  | 890000 | UNDER CONSTRUCTION.
Columbus | NC 211 | NCDOT | Brunswick County line to NC 214. | Install rumble stripes. | 9.48 | Highway | Safety | 6 | Cape Fear RPO | HS-2006F | Region C | HSIP, T(M) |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
Columbus | NC 410 (Brown Street) | NCDOT | First Avenue intersection in Chadbourn. | Upgrade traffic signal with pedestrian heads. |  | Highway | Safety | 6 | Cape Fear RPO | HS-2406Q | Region C | HSIP, T(M) |  |  |  |  | 2025 | 85000 |  |  | 85000
Columbus | NC 87 | NCDOT | Mile marker 1.033 to mile marker 6.933 near Riegelwood | Install rumble stripes and pavement markers. | 5.9 | Highway | Safety | 6 | Cape Fear RPO | HS-2406A | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 290000 |  |  | 290000 | UNDER CONSTRUCTION.
Columbus | SR 1004 (Rough and Ready Road) | NCDOT | SR 1415 (Dolph Lewis Road) to US 701 | Install rumble strips and long life pavement markings and markers. | 10.9 | Highway | Safety | 6 | Cape Fear RPO | HS-2406Y | Division 6 | HSIP, T(M) |  |  |  |  | 2026 | 460000 |  |  | 460000
Columbus | US 701 Bypass | NCDOT | Lewis Street intersection | Install crosswalk with Rectangular Rapid Flashing Beacons and median fencing. | 0.2 | Highway | Safety | 6 | Cape Fear RPO | HS-2406AB | Region C | HSIP, T(M) |  |  |  |  | 2026 | 325000 |  |  | 325000
Columbus | US 701 Bypass | NCDOT | Williamson Street intersection | Install sidewalk, crosswalk with Rectangular Rapid Flashing Beacons, and median fencing. | 0.1 | Highway | Safety | 6 | Cape Fear RPO | HS-2406AC | Region C | HSIP, T(M) |  |  |  |  | 2026 | 203000 |  |  | 203000
Columbus | NC 410 (N. Brown Street) | NCDOT | US 74 / 76 Business (E. Strawberry Boulevard) | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | HP-0037 | Division 6 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 |  |  | 4700000
Columbus | NC 87 | NCDOT | Columbus County. | Construct detour route ahead of R-2561CA. |  | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-2561CB | Region C | T |  |  |  |  | 2023 | 1756000 |  |  | 1756000 | UNDER CONSTRUCTION.
Columbus | NC 87 | NCDOT | NC 11 intersection in Sandyfield | Construct interchange. | 1 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-2561CA | Region C | BGLT5, T | 2020 | 3904000 | 2020 | 3000000 | 2023 | 41376000 |  |  | 48280000 | UNDER CONSTRUCTION.
Columbus | NC 87 | NCDOT | NC 11 to US 74 / US 76 in Columbus County. | Widen to multi-lanes. | 5.99 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-2561C | Not Funded | T | NOT FUNDED | 26511000 | NOT FUNDED | 4488000 | NOT FUNDED | 85799000 | NOT FUNDED |  | 116798000
Columbus | US 701 Business | NCDOT | South of SR 1920 (Mill Pond Road) | Replace culvert. | 0.5 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020AA | Region C | BG5T50 |  |  |  |  | 2027 | 2000000 |  |  | 2000000
Columbus | US 701 Bypass | NCDOT | SR 1166 (Pleasant Plains Church Road) to SR 1437 (Virgil Avenue). | Widen to multi-lane facility. | 2.18 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020A | Region C | BG5T50 |  |  |  |  | 2030 | 63600000 |  |  | 63600000 | RIGHT-OF-WAY IN PROGRESS.
Columbus | US 701 Bypass | NCDOT | SR 1437 (Virgil Avenue) to US 74 / US 76. | Widen to multi-lane facility. | 1.74 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020B | Division 6 | T |  |  |  |  | 2022 | 32485000 |  |  | 32485000 | UNDER CONSTRUCTION.
Columbus | US 701 Bypass (Madison Street - Powell Boulevard) | NCDOT | South of SR 1166 (Pleasant Plains Road) to north of US 74 / US 76 Bypass in Whiteville. | Widen to multi-lane facility. | 3.92 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020 | [11 empty] | RIGHT-OF-WAY IN PROGRESS.
Columbus | US 74 | NCDOT | SR 1506 (Boardman Road) intersection in Boardman | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5797 | Region C | T |  |  |  |  | 2021 | 18620000 |  |  | 18620000 | UNDER CONSTRUCTION.
Columbus | US 74 | NCDOT | SR 1800 (Blacksmith Road) intersection | Convert at-grade intersection to grade separation. | 2 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | HP-0038 | Division 6 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 |  |  | 9000000
Columbus | US 74 (Future I-74) / US 76 | NCDOT | SR 1735 (Chauncey Town Road) intersection in Waccamaw | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5820 | Region C | T | 2021 | 1184000 | 2021 | 1297000 | 2022 | 50713000 |  |  | 53194000 | COMBINE WITH R-5819. UNDER CONSTRUCTION.
Columbus | US 74 (Future I-74) / US 76 | NCDOT | SR 1740 (Old Lake Road) intersection in Lake Waccamaw | Upgrade at-grade intersection to interchange. | 3 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5819 | Region C | T | 2021 | 346000 | 2021 | 129000 | 2022 | 11665000 |  |  | 12140000 | COMBINE WITH R-5820. UNDER CONSTRUCTION.
Columbus | US 74 / US 76 | NCDOT | SR 1735 (Chauncey Town Road) and SR 1740 (Old Lake Road) intersection in Waccamaw | Construct reduced conflict intersections. | 0.5 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5819A | Region C | T |  |  |  |  | 2021 | 2300000 |  |  | 2300000 | UNDER CONSTRUCTION.
Columbus | SR 1305 (Complex Street / Sandy Bluff Road) | NCDOT | RJ Coleman Railroad Crossing 629312A in Tabor City. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Cape Fear RPO | RX-2406A | Division 6 | RR |  |  |  |  | 2026 | 425000 |  |  | 425000
Columbus, Bladen | US 701 | NCDOT | Mile marker 1.96 to 9.46 in Bladen County, mile marker 2.57 to 15.48 and mile marker 19.97 to 30.35 in Columbus County | Install rumble stripes and pavement markings. | 30.79 | Highway | Safety | 6 | Cape Fear RPO, Mid-Carolina RPO | HS-2406G | Region C | HSIP, T(M) |  |  |  |  | 2025 | 970000 |  |  | 970000 | UNDER CONSTRUCTION.
Columbus, Robeson | US 74 (Future I-74) | NCDOT | Near Lumberton to US 76 near Chadbourn. | Upgrade US 74 to interstate standards. | 22.71 | Highway | STI (Prioritization) | 6 | Cape Fear RPO, Lumber River RPO | I-6011 | Not Funded | T | NOT FUNDED | 179000 | NOT FUNDED | 1469000 | NOT FUNDED | 169100000 | NOT FUNDED |  | 170748000
Columbus, Robeson, Anson, Scotland, Richmond, Brunswick, Union | US 74 | NCDOT | Eastern end of Monroe Bypass to I-140 in Wilmington. | Install flood gates and flood monitoring. | 156.15 | Highway | Other | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO | HO-0002D | Statewide Mobility | DP, T | [6 empty] | 2022 | 2200000 | 2200000
Columbus, Robeson, Brunswick | US 74 | NCDOT | I-95 in Lumberton to I-140 in Wilmington. | Install broadband for Traveler Information Systems. | 69.67 | Highway | Other | 3, 6 | Cape Fear RPO, Lumber River RPO, Wilmington Urban Area MPO | HO-0002C | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 10455000 |  |  | 10455000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION.
Columbus, Robeson, Cleveland, Anson, Gaston, Polk, Scotland, Henderson, Richmond, Rutherford, Mecklenburg, Brunswick, Buncombe, Union | US 74 | NCDOT | I-40 in Asheville to I-140 in Wilmington. | Implement broadband, ITS, and resiliency improvements. | 279.24 | Highway | Other | 3, 6, 8, 10, 12, 13, 14 | Lumber River RPO, Cape Fear RPO, Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO | HO-0002 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS.
Craven | SR 1309 (Glenburnie Road) | New Bern | College Court to Greenbriar Parkway in New Bern | Construct sidewalk. |  | Bike & Ped | Locally Selected | 2 | New Bern Area MPO | BL-0167 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 97000 | 2026 | 5000 | 102000
Craven | Cherry Branch Ferry | NCDOT | Maintenance depot | Planning and design study. |  | Ferry | Other | 2 | Down East RPO | FO-0001 | Public Transit | FSRC, T | [6 empty] | 2024 | 500000 | 500000
Craven | SR 1470 (Maple Cypress Road) | NCDOT | Bridges 240138 and 240139 over Neuse River. | Replace bridges. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4484 | Division 2 | T |  |  |  |  | 2021 | 18700000 |  |  | 18700000 | UNDER CONSTRUCTION.
Craven | New Route | NCDOT | US 70 to NC 43 / NC 55. | Construct NC 43 connector with interchange at US 70. |  | Highway | Economic Development | 2 | New Bern Area MPO | R-4463B | [11 empty] | COMPLETE. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOSCH CORPORATION.
Craven | Various | NCDOT | New Bern Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 2 | New Bern Area MPO | HL-0104 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 899000 |  |  | 899000
Craven | New Bern | NCDOT | Piggly Wiggly | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 2 | Down East RPO | HV-0001H | Division 2 | NEVI, O, O(M), S(M) |  |  |  |  | 2025 | 885000 |  |  | 885000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY
Craven | NC 43 Connector | NCDOT | NC 43 / NC 55 to US 17 in New Bern. | Construct route on new location with interchange at US 70. | 4.2 | Highway | Pre-STI (Historic) | 2 | New Bern Area MPO | R-4463
Craven | US 17 | NCDOT | Mills Street in Bridgeton to north of C Street. | Widen to multi-lanes. |  | Highway | Pre-STI (Historic) | 2 | Down East RPO | R-3403AA | [11 empty] | COMPLETE.
Craven | US 17 | NCDOT | North C Street to north of SR 1433 (Antioch Road) | Widen to multi-lanes. |  | Highway | Pre-STI (Historic) | 2 | Down East RPO | R-3403AB | [11 empty] | COMPLETE.
Craven | NC 55 (Neuse Boulevard) | NCDOT | Fort Totten Drive and First Street intersections. | Upgrade traffic signals and install pedestrian heads. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002Y | Region B | HSIP, T(M) |  |  |  |  | 2024 | 76000 |  |  | 76000
Craven | NC 55 (Neuse Boulevard) | NCDOT | SR 1215 (Simmons Street) intersection in New Bern. | Install pedestrian signals and crosswalks. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002V | Region B | HSIP, T(M) |  |  |  |  | 2024 | 18000 |  |  | 18000
Craven | NC 55 (Neuse Boulevard) | NCDOT | SR 1309 / SR 1402 (Glenburnie Road) in New Bern. | Install pedestrian signals and crosswalks. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002W | Region B | HSIP, T(M) |  |  |  |  | 2024 | 18000 |  |  | 18000
Craven | SR 1001 / SR 1256 (Main Street) | NCDOT | SR 1005 (Sunset Boulevard) Intersection. | Install all way stop and channelization, and revise overhead flasher. | 1 | Highway | Safety | 2 | Down East RPO | HS-2002F | Division 2 | HF, HSIP, T(M) | 2022 | 16000 |  |  | 2026 | 113000 |  |  | 129000 | RIGHT-OF-WAY IN PROGRESS.
Craven | US 17 Business (Martin Luther King Jr. Boulevard) | NCDOT | Trent Creek Road Intersection. | Install Flasher. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002O | Region B | HSIP, T(M) |  |  |  |  | 2023 | 42000 |  |  | 42000 | UNDER CONSTRUCTION.
Craven | NC 101 / SR 1763 (Fontana Boulevard / Miller Boulevard); SR 1756 (Lake Road) | NCDOT | SR 1756 (Lake Road) to Outer Banks Drive; SR 1763 (Miller Boulevard) to Havelock Bypass. | Widen to multi-lanes and construct road improvements. | 3.05 | Highway | STI (Prioritization) | 2 | Down East RPO | U-3431 | Division 2 | T | 2026 | 26000000 | 2026 | 3500000 | 2030 | 96600000 |  |  | 126100000
Craven | NC 43 Connector | NCDOT | US 17 Business to south of US 17 / US 70. | Construct route on new location. | 2.29 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-4463A | Region B | T | 2020 | 8023000 | 2023 | 1350000 | 2026 | 36870000 | 2020 | 1725000 | 47968000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
Craven | NC 55 (Neuse Boulevard) | NCDOT | US 17 Business (MLK Boulevard) intersection in New Bern | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | U-5993 | Region B | T | 2027 | 790000 |  |  | 2029 | 5700000 |  |  | 6490000
Craven | US 17 | NCDOT | Mills Street in Bridgeton to NC 43. | Widen to multi-lanes. | 9.8 | Highway | STI (Prioritization) | 2 | Down East RPO, New Bern Area MPO | R-3403 | Region B
Craven | US 17 | NCDOT | NC 43 to SR 1438 (Spruill Town Road). | Widen to multi-lanes. | 15.2 | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513
Craven | US 17 | NCDOT | North of NC 43 to SR 1438 (Spruill Town Road). | Widen to multi-lanes. | 1.86 | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513A | Division 2 | T | 2030 | 4100000 | 2030 | 2400000 | 2033 | 26500000 |  |  | 33000000
Craven | US 17 | NCDOT | SR 1433 (Antioch Road) to north of NC 43. | Widen to multi-lanes. | 7.19 | Highway | STI (Prioritization) | 2 | Down East RPO, New Bern Area MPO | R-3403B | Region B | T | 2030 | 8900000 | 2030 | 4100000 | 2033 | 129100000 |  |  | 142100000
Craven | US 17 | NCDOT | SR 1438 (Spruill Town Road) to SR 1637 (Mill Pond Road). | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513B | Not Funded | T | NOT FUNDED | 5800000 | NOT FUNDED | 800000 | NOT FUNDED | 16300000 | NOT FUNDED |  | 22900000
Craven | US 17 | NCDOT | SR 1637 (Mill Pond Road) to SR 1646 (Mile Road). | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513C | Not Funded | T | NOT FUNDED | 2300000 | NOT FUNDED | 600000 | NOT FUNDED | 11300000 | NOT FUNDED |  | 14200000
Craven | US 17 | NCDOT | SR 1646 (Mile Road) in Craven County to SR 1130 (C.C. Road) in Beaufort County. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513D | Not Funded | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 21000000 | NOT FUNDED |  | 26200000
Craven | US 70 (Future I-42) | NCDOT | East of Thurman Road to Havelock Bypass. | Upgrade roadway to freeway and construct service roads. | 6.88 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777C | Statewide Mobility | T | 2023 | 49129000 | 2023 | 20586000 | 2023 | 278703000 |  |  | 348418000 | UNDER CONSTRUCTION.
Craven | US 70 (Future I-42) | NCDOT | SR 1124 (Grantham Road) to Neuse River Bridge. | Upgrade roadway to freeway. | 1.8 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | U-5713 | Statewide Mobility | T | 2020 | 88668000 | 2020 | 1000000 | 2020 | 152337000 |  |  | 242005000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B.
Craven | US 70 (Future I-42) | NCDOT | SR 1124 (Grantham Road) to proposed US 70 Havelock Bypass. | Upgrade roadway to freeway. | 8.6 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777
Craven | US 70 (Future I-42) | NCDOT | Taberna Way intersection in New Bern | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777A | Statewide Mobility | T | 2020 | 47438000 | 2020 | 300000 | 2020 | 50778000 |  |  | 98516000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713.
Craven | US 70 (Future I-42) | NCDOT | West Thurman Road / East Thurman Road intersection in New Bern | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777B | Region B | T | 2020 | 47447000 | 2020 | 300000 | 2020 | 50778000 | 2020 | 105000 | 98630000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
Craven | US 70 (Havelock Bypass) | NCDOT | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 10.1 | Highway | STI (Prioritization) | 2 | Down East RPO, New Bern Area MPO | R-1015 | [11 empty] | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8M FOR RIGHT-OF-WAY, $2.2M FOR UTILITIES, AND $100M FOR CONSTRUCTION, PAYBACK FY 2019 - 2033.
Craven | US 70 (Havelock Bypass) | NCDOT | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-1015DIV | Division 2 | NHP, T(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 114172000 |  |  | 118292000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
Craven | US 70 (Havelock Bypass) | NCDOT | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-1015REG | Region B | NHP, T(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 105707000 |  |  | 109827000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
Craven | NC 43 Connector | NCDOT | South of US 17 / US 70 to US 70. | Construct route on new location with interchange at US 70. | 2.5 | Highway | Transition | 2 | New Bern Area MPO | R-4463AA | [11 empty] | COMPLETE.
Craven | Craven Area Rural Transportation System | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | Systemwide | Purchase rural vehicle replacement. |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | New Bern Area MPO | TA-5165 | Public Transit | 5307, L | [6 empty] | 2020 | 919000 | 919000 | FUNDS AUTHORIZED IN PROGRESS
Craven | Transportation System Craven Area Rural | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | Systemwide | Funding for mobility management. |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | New Bern Area MPO | TC-5100 | Public Transit | 5307, L | [6 empty] | 2023 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
Craven | Craven Area Rural Transportation System | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 2 | New Bern Area MPO | TO-5024 | Public Transit | 5307, L | [6 empty] | 2023 | 3200000 | 3200000
Craven | Transportation system Craven Area Rural | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | Various locations | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | New Bern Area MPO | TG-5257 | Public Transit | 5307, L | [6 empty] | 2020 | 313000 | 313000 | FUNDS AUTHORIZED IN PROGRESS
Craven, Johnston, Wayne, Lenoir, Carteret, Wake | US 70 (Future I-42) | NCDOT | I-40 to Port of Morehead City. | Install broadband fiber along US 70 for traveler information systems. | 138.47 | Highway | STI (Prioritization) | 2, 4, 5 | Down East RPO, Eastern Carolina RPO, New Bern Area MPO, Upper Coastal Plain RPO, Goldsboro Urban Area MPO, Capital Area MPO | R-5777D | Statewide Mobility | DP, T |  |  |  |  | 2021 | 33500000 |  |  | 33500000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
Craven, Jones, Beaufort | US 17 | NCDOT | North of Onslow County line to South of NC 58 in Jones County; North of SR 1433 (Antioch Road) to North of SR 1134 (Old New Bern Road) in Beaufort County | Install rumble stripes and pavement markings. | 26.5 | Highway | Safety | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO | HS-2402B | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 656000 |  |  | 656000 | UNDER CONSTRUCTION.
Cumberland | FAY | FAYETTEVILLE REGIONAL AIRPORT | Fayetteville Regional Airport | Extend runway 10/28. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AP-0002 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | 2700000
Cumberland | FAY | FAYETTEVILLE REGIONAL AIRPORT | Fayetteville Regional Airport | Extend runway 4/22. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AP-0003 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | 2700000
Cumberland | FAY | FAYETTEVILLE REGIONAL AIRPORT | Fayetteville Regional Airport | Upgrade pavement and paint the general aviation apron on Control Tower Road. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AP-0004 | Region C | O, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | 2300000 | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT.
Cumberland | FAY | FAYETTEVILLE REGIONAL AIRPORT (FAY) | Fayetteville Regional Airport | Replace perimeter fencing and road. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AV-5734 | Region C | O, T |  |  |  |  | 2027 | 3740000 |  |  | 3740000
Cumberland | Big Cross Creek Greenway. | FAYETTEVILLE | Little Cross Creek to I-295. | Construct multi-use path. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-5541 | Not Funded | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS.
Cumberland | Cape Fear River Trail | FAYETTEVILLE | Along Milan Road and Eufaula Road in Fayetteville. | Construct extension to Cape Fear River Trail. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0133 | Division 6 | BGDA, L(M) |  |  |  |  | 2027 | 2051000 | 2026 | 145000 | 2196000
Cumberland | East Shore Trail | FAYETTEVILLE | Essex Place to intersection of Coley Drive and Murchison Road along Glenville Lake in Fayetteville; Matthews Street from Coley Drive to Murchison Road. | Construct 10 foot multi-use path; construct sidewalk. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0134 | Division 6 | BGDA, L(M) | 2027 | 77000 |  |  | 2028 | 2023000 |  |  | 2100000
Cumberland | Fayetteville | FAYETTEVILLE | Cape Fear River Trail | Construct 10 foot multi-use path. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0131 | Division 6 | L(M), TADA | [6 empty] | 2025 | 1370000 | 1370000
Cumberland | Fayetteville | FAYETTEVILLE | Cape Fear River Trailhead to Arnette Park. | Construct 10 foot multi-use path. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0132 | Division 6 | L(M), TADA | [6 empty] | 2025 | 1370000 | 1370000
Cumberland | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | FAYETTEVILLE | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0138 | Division 6 | BGDA, L(M) | 2027 | 200000 | 2027 | 20000 | 2028 | 2030000 | 2026 | 200000 | 2450000
Cumberland | NC 59 (Hope Mills Road) | FAYETTEVILLE | Fayetteville City limits to Sumac Circle in Fayetteville. | Construct sidewalk. | 1.32 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6032 | Division 6 | L(M), TADA |  |  |  |  | 2022 | 375000 |  |  | 375000 | COMPLETE.
Cumberland | Spring Lake | FAYETTEVILLE | Near the Little River in the Town of Spring Lake | Construct greenway trail. | 5 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6041 | Division 6 | BGDA, L(M) | 2025 | 128000 |  |  |  |  | 2025 | 238000 | 366000
Cumberland | SR 1131 (Cameron Road) | HOPE MILLS | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0130 | Division 6 | L(M), TADA | 2026 | 25000 |  |  | 2027 | 574000 | 2025 | 100000 | 699000
Cumberland | US 401 (Ramsey Street) | FAYETTEVILLE | Summerchase Drive to SR 1611 (Andrews Road) near Fayetteville. | Construct sidewalk. | 0.17 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6031 | Division 6 | L(M), TADA |  |  |  |  | 2021 | 85000 |  |  | 85000 | COMPLETE.
Cumberland | US 401 Bypass (Skibo Road) | FAYETTEVILLE | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6030 | Division 6 | BGDA, L(M), TADA | 2024 | 100000 |  |  | 2026 | 2076000 | 2022 | 230000 | 2406000 | RIGHT-OF-WAY IN PROGRESS
Cumberland | Various | FAYETTEVILLE | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0137 | Division 6 | BGDA, L(M) | 2027 | 350000 | 2027 | 40000 | 2028 | 2010000 | 2026 | 300000 | 2700000
Cumberland | Cape Fear River Greenway | FAYETTEVILLE | Clark Park South to the Cape Fear Botanical Gardens. Existing trail at Clark Park to the north side of CSX rail line | Construct second phase of an off-road multi-use trail. | 1.26 | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539BB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
Cumberland | Cape Fear River Greenway | FAYETTEVILLE | Clark Park South to the Cape Fear Botanical Gardens. I-95 Business / US 301 to the south side of CSX rail line. | Construct second phase of an off-road multi-use trail. | 1.23 | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539A | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
Cumberland | Cape Fear River Greenway | FAYETTEVILLE | Clark Park to the Cape Fear Botanical Gardens in Fayetteville | Construct second phase of an off-road multi-use trail. |  | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539 | Pre-STI (Transition)
Cumberland | Cape Fear River Greenway | FAYETTEVILLE | North of CSX rail line to south of CSX rail line in Fayetteville. | Construct second phase of an off-road multi-use trail. | 0.27 | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539BC | Pre-STI (Transition) | L(M), TAANY |  |  |  |  | 2020 | 951000 |  |  | 951000 | UNDER CONSTRUCTION.
Cumberland | Blounts Creek Greenway | NCDOT | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | BP-0001 | Division 6 | L(M), TAANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 86000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1195000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 253000 | 1544000 | BLOUNTS CREEK PHASE III
Cumberland | Cross Creek Parks Connector Trail | FAYETTEVILLE | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | EB-5907 | Division 6 | L(M), TAANY | 2026 | 630000 | 2026 | 220000 | 2028 | 1400000 | 2023 | 84000 | 2334000
Cumberland | Little Cross Creek Greenway Extension | FAYETTEVILLE | Filter Plant Drive to Rowan Street bridge in Fayetteville | Construct multi-use path. | 0.75 | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | EB-5540 | Division 6 | L(M), TAANY |  |  |  |  | 2027 | 750000 |  |  | 750000
Cumberland | NC 59 | NCDOT | Bridge 250022 over I-95 Business / US 301. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Fayetteville Area MPO | B-4491 | Region C | NHPB, T(M) |  |  |  |  | 2018 | 3533000 |  |  | 3533000 | COMPLETE.
Cumberland | SR 1716 (Jackie Lee Road) | NCDOT | Bridge 250091 over Wade Canal. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Fayetteville Area MPO | HB-0010 | Division 6 | BGOFF | 2028 | 120000 |  |  | 2030 | 1300000 |  |  | 1420000
Cumberland | New Route | NCDOT | New route in Fayetteville. | Construct new access road and improvements at SR 1838 (Dunn Road) intersection. | 0.2 | Highway | Economic Development | 6 | Fayetteville Area MPO | HE-0012 | Division 6 | T | 2023 | 20000 | 2023 | 50000 | 2023 | 1100000 |  |  | 1170000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC.
Cumberland | SR 1711 (Bethune Drive) | NCDOT | East of US 401 intersection in Fayetteville. | Install signal at US 401 (Ramsey Street) intersection and extend SR 1711 (Bethune Drive). |  | Highway | Economic Development | 6 | Fayetteville Area MPO | HE-0017 | Division 6 | T | 2026 | 300000 | 2026 | 700000 | 2027 | 8200000 | 2025 | 800000 | 10000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL.
Cumberland | I-95 | NCDOT | NC 53 to I-95 Business / US 301. | Rehabilitate pavement. | 8.92 | Highway | Interstate Maintenance | 6 | Fayetteville Area MPO | HI-0022 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2029 | 5800000 |  |  | 5800000
Cumberland | I-95 | NCDOT | Robeson County line to NC 53 / NC 210 | Rehabilitate pavement. | 10.28 | Highway | Interstate Maintenance | 6 | Fayetteville Area MPO | HI-0021 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2029 | 8000000 |  |  | 8000000
Cumberland | NC 24 | FAYETTEVILLE | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0143 | Region C | BGDA, HF(M) | 2026 | 200000 | 2026 | 100000 | 2028 | 350000 | 2025 | 75000 | 725000
Cumberland | NC 59 (North Main Street) | HOPE MILLS | Lakeview Road to second entrance of Lake Park Concession Stand at Boatmans Drive. | Design and construct 10 foot multi-use path. | 1.5 | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0036 | Division 6 | L(M), TADA |  |  |  |  | 2024 | 768000 | 2021 | 50000 | 818000
Cumberland | SR 1112 (Rockfish Road) | FAYETTEVILLE | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0145 | Division 6 | BGDA, HF(M) | 2026 | 100000 |  |  | 2028 | 2752000 | 2025 | 250000 | 3102000
Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | East of SR 1415 (Yadkin Road) to west of NC 24 / NC 87 (Bragg Boulvard) | Construct freeway on new location. |  | Highway | Pre-STI (Historic) | 6 | Fayetteville Area MPO | U-2519DA | [11 empty] | COMPLETE.
Cumberland | NC 24 | NCDOT | West of SR 1006 (Maxwell Road / Clinton Road) in Cumberland County to SR 1853 (John Nunnery Road) | Construct four lane divide freeway, partially on new location. | 6.15 | Highway | Pre-STI (Historic) | 6 | Mid-Carolina RPO, Fayetteville Area MPO | R-2303A | Pre-STI (Transition) | [10 empty] | COMPLETE.
Cumberland | I-95 Business / US 301 | NCDOT | NC 87 South to NC 59. | Construct safety improvements. | 7.29 | Highway | Safety | 6 | Fayetteville Area MPO | W-5519 | Region C | [10 empty] | COMPLETE.
Cumberland | NC 24 (Bragg Boulevard) | NCDOT | US 401 (Skibo Road) to Glenville Avenue. | Replace median and guardrail, add pedestrian signal, and resurface pavement. | 2.53 | Highway | Safety | 6 | Fayetteville Area MPO | U-6229 | Division 6 | HSIP, T |  |  | 2022 | 200000 | 2023 | 7672000 |  |  | 7872000 | UNDER CONSTRUCTION.
Cumberland | NC 53 | NCDOT | Bladen County to Fayetteville City limits | Install rumble strips and long life pavement markings and markers. | 12.9 | Highway | Safety | 6 | Fayetteville Area MPO, Mid-Carolina RPO | HS-2406U | Region C | HSIP, T(M) |  |  |  |  | 2026 | 480000 |  |  | 480000
Cumberland | NC 53 (Cedar Creek Road) | NCDOT | North of Plymouth Street to south of Troy Drive. | Install median, U-turn bulbout, sidewalk, and rectangular rapid flashing beacon crossing. | 0.21 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006C | Region C | HSIP, T(M) | 2023 | 208000 |  |  | 2024 | 1800000 |  |  | 2008000 | RIGHT-OF-WAY IN PROGRESS.
Cumberland | SR 1006 (Person Street) | NCDOT | US 301 / I-95 Business (Eastern Boulevard) to east of Water Street. | Upgrade section from four lanes to three lanes and construct intersection improvements. | 0.34 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006B | Division 6 | HSIP, T(M) |  |  |  |  | 2022 | 651000 |  |  | 651000 | UNDER CONSTRUCTION.
Cumberland | SR 1400 (Cliffdale Road) | NCDOT | SR 1593 (Hoke Loop Road) intersection | Install signalized pedestrian crossing. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406V | Division 6 | HSIP, T(M) |  |  |  |  | 2026 | 174000 |  |  | 174000
Cumberland | SR 1404 (Hay Street / Morganton Road) | NCDOT | SR 3578 (Fort Bragg Road), Oakridge Avenue, and Highland Avenue intersections in Fayetteville. | Upgrade traffic signals and improve pedestrian crossings. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | W-5706U | Division 6 | HSIP, T(M) |  |  |  |  | 2025 | 100000 |  |  | 100000 | UNDER CONSTRUCTION.
Cumberland | SR 1404 (Morganton Road) | NCDOT | McPherson Church Road. | Install/upgrade crosswalks, crosswalk ramps signalized pedestrian heads, and traffic signal. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406R | Division 6 | HSIP, T(M) |  |  |  |  | 2026 | 300000 |  |  | 300000
Cumberland | SR 1404 (Morganton Road) | NCDOT | SR 1596 (Glensford Drive)/Cross Creek Mall, Cross Point/Cross Creek Mall, and US 401 (Skibo Road) | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406AA | Division 6 | HSIP, T(M) | 2026 | 50000 |  |  | 2027 | 620000 |  |  | 670000
Cumberland | SR 1404 (Morganton Road) | NCDOT | Sycamore Dairy Road, SR 1007 (All American Expressway) Northbound Ramp, and Southbound Ramp | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406Z | Division 6 | HSIP, T(M) |  |  |  |  | 2026 | 580000 |  |  | 580000
Cumberland | SR 1414 (Broadfoot Road) | NCDOT | Arsenal Avenue intersection in Fayetteville. | Install crosswalks with pedestrian signal head. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006Z | Division 6 | HSIP, T(M) |  |  |  |  | 2024 | 390000 |  |  | 390000
Cumberland | SR 1415 (Yadkin Road) | NCDOT | US 401 (Skibo Road), SR 1437 (Sante Fe Drive), and Southwick Drive intersections. | Add signalized pedestrian crossings and upgrade signal. | 1 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006A | Division 6 | HSIP, TADA |  |  |  |  | 2024 | 567000 |  |  | 567000
Cumberland | SR 1596 (Glensford Drive) | NCDOT | Berean Baptist Academy Entrance and Chambersburg Road intersection. | Install Rectangular rapid flashing beacons with refuge islands. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006O | Division 6 | HSIP, T(M) |  |  |  |  | 2025 | 334000 |  |  | 334000 | UNDER CONSTRUCTION.
Cumberland | SR 1596 (Glensford Drive) | NCDOT | US 401 (Raeford Road) to SR 1400 (Cliffdale Road) in Fayetteville. | Install pavement markings and sign improvements. | 1.16 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006N | Division 6 | HSIP, T(M) |  |  |  |  | 2025 | 81000 |  |  | 81000 | UNDER CONSTRUCTION.
Cumberland | SR 1600 (McArthur Road) | NCDOT | SR 1615 (Rosehill Road / Stacy Weaver Road) in Fayetteville. | Construct signalized pedestrian accommodations. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006V | Division 6 | HSIP, T(M) |  |  |  |  | 2024 | 190000 |  |  | 190000
Cumberland | SR 1615 (Rosehill Road) | NCDOT | Tamarack Drive and Landau Road intersections. | Construct mini-roundabouts. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | W-5806C | Division 6 | HSIP, T(M) | 2021 | 76000 |  |  | 2023 | 3113000 |  |  | 3189000 | UNDER CONSTRUCTION.
Cumberland | SR 1835 (Rock Hill Road) | NCDOT | SR 1838 (Dunn Road) intersection in Eastover. | Realign intersection to form T-intersection. | 0.15 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006G | Division 6 | HSIP, T(M) |  |  |  |  | 2023 | 282000 |  |  | 282000 | UNDER CONSTRUCTION.
Cumberland | SR 3950 (Ramsey Street) | NCDOT | Bridge 250216 in Fayetteville. | Install Guardrail. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006P | Division 6 | HSIP, T(M) |  |  |  |  | 2025 | 250000 |  |  | 250000 | UNDER CONSTRUCTION.
Cumberland | US 401 (Pamalee Drive) | NCDOT | Cain Road and Helen Street intersections | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406W | Region C | HSIP, T(M) |  |  |  |  | 2026 | 335000 |  |  | 335000
Cumberland | US 401 (Ramsey Street) | NCDOT | At Northgate shopping center in Fayetteville | Install crosswalk, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406C | Region C | HSIP, T(M) |  |  |  |  | 2025 | 330000 |  |  | 330000
Cumberland | US 401 (Ramsey Street) | NCDOT | Treetop Drive intersection in Fayetteville | Install / upgrade crosswalks, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406F | Region C | HSIP, T(M) |  |  |  |  | 2025 | 200000 |  |  | 200000
Cumberland | US 401 (Skibo Road) | NCDOT | NC 24 / NC 87 (Bragg Boulevard) eastbound ramps (Swain Street). | Install/upgrade crosswalks and traffic signal. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406S | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 730000 |  |  | 730000
Cumberland | US 401 (Skibo Road) | NCDOT | SR 1007 (All American Freeway) northbound and southbound ramps in Fayetteville. | Install signalized pedestrian accommodations. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006X | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 880000 |  |  | 880000
Cumberland | US 401 (Skibo Road) | NCDOT | SR 1400 (Cliffdale Road) intersection in Fayetteville. | Revise traffic signal, and install crosswalks and pedestrian signal heads. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406O | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 260000 |  |  | 260000
Cumberland | US 401 Business (Ramsey Street) | NCDOT | Langdon street and Colonial Drive intersections in Fayetteville | Install crosswalk, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406D | Region C | HSIP, T(M) |  |  |  |  | 2025 | 280000 |  |  | 280000
Cumberland | US 401 Business (Robeson Street) | NCDOT | SR 1168 (Whitfield Street) intersection in Fayetteville. | Revise traffic signal, and install crosswalks and pedestrian signal heads. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406P | Region C | HSIP, T(M) |  |  |  |  | 2025 | 180000 |  |  | 180000
Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | South of SR 1003 (Camden Road) to south of SR 1104 (Strickland Bridge Road). | Construct freeway on new location. | 3.96 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519BA | Region C | NHP, T(M) |  |  |  |  | 2022 | 161113000 |  |  | 161113000 | UNDER CONSTRUCTION.
Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | South of SR 1104 (Strickland Bridge Road) to south of US 401. | Construct freeway on new location. | 0.79 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519BB | Region C | [10 empty] | UNDER CONSTRUCTION. FUNDING AUTHORIZED UNDER U-2519BA.
Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | South of SR 1118 (Parkton Road) to south of SR 1003 (Camden Road). | Construct freeway on new location. | 4.88 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519AB | Region C | [10 empty] | DESIGN BUILD PROJECT. WORK BEING ACCOMPLISHED UNDER U-2519AA.
Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | South of US 401 to south of SR 1400 (Cliffdale Road). | Construct freeway on new location. | 2.63 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519CA | Statewide Mobility | NHP, T(M) | 2024 | 10000 | [6 empty] | 10000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT.
Cumberland | NC 210 (Murchison Road) | NCDOT | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4900 | Exempt | BGDA, T(M) | 2023 | 10600000 | 2023 | 15000000 | 2026 | 34500000 |  |  | 60100000 | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT.
Cumberland | NC 24 (North Bragg Boulevard) | NCDOT | SR 1451 (Manchester Road) intersection in Spring Lake | Construct interchange. | 1 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5930 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 65800000 |  |  | 82500000
Cumberland | New Route | NCDOT | Camden Road to Hunting Ridge Road | Construct new facility. | 0.27 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0040 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9600000 |  |  | 10600000
Cumberland | New Route | NCDOT | Rockfish Road to NC 59 (North Main Street) | Construct new facility. | 0.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0041 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17700000 |  |  | 23300000
Cumberland | SR 1003 (Camden Road) | NCDOT | Fayetteville Outer Loop (U-2519) to SR 1596 (Hope Mills Road) in Fayetteville. | Widen to four lanes. | 3.52 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-3422 | Division 6 | BGANY, T(M) | 2021 | 16175000 | 2021 | 5225000 |  |  |  |  | 21400000 | RIGHT-OF-WAY IN PROGRESS.
Cumberland | SR 1003 (Camden Road) | NCDOT | Proposed Fayetteville Outer Loop (U-2519) to just west of SR 1112 (Rockfish Road). | Widen to four-lanes. | 1.53 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-3422A | Division 6 | O, T |  |  |  |  | 2025 | 25875000 |  |  | 25875000 | UNDER CONSTRUCTION. O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE).
Cumberland | SR 1003 (Camden Road) | NCDOT | West of SR 1112 (Rockfish Road) to SR 1596 (Hope Mills Road). | Widen to four-lanes. | 1.99 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-3422B | Division 6 | O, T |  |  |  |  | 2027 | 61109000 |  |  | 61109000 | O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BULD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
Cumberland | SR 1102 (Gillis Hill Road) | NCDOT | North of SR 1112 (Stoney Point Road) to US 401 (Raeford Road). | Widen to four lanes and replace bridge 250075 over Little Rockfish Creek. | 1.07 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5798A | Division 6 | T | 2020 | 9322000 | 2020 | 475000 | 2022 | 26036000 |  |  | 35833000 | UNDER CONSTRUCTION.
Cumberland | SR 1107 (Fisher Road) | NCDOT | SR 1104 (Strickland Bridge Road) to NC 162 (Bingham Drive). | Widen to multi-lanes. | 2.1 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6073 | Division 6 | BGANY, T(M) | 2030 | 22500000 | 2030 | 2400000 | 2033 | 25100000 |  |  | 50000000
Cumberland | SR 1112 (Rockfish Road) | NCDOT | SR 1003 (Camden Road) to SR 1115 (Golfview Road) | Widen to multi-lanes. | 1.55 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6072B | Division 6 | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8500000 |  |  | 19400000
Cumberland | SR 1112 (Rockfish Road) | NCDOT | SR 1102 (Gillis Hill Road) to Camden Road | Widen to multi-lanes. | 4.8 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6072A | Not Funded | T | NOT FUNDED | 14900000 | NOT FUNDED | 4600000 | NOT FUNDED | 24500000 | NOT FUNDED |  | 44000000
Cumberland | SR 1112 (Rockfish Road) | NCDOT | SR 1140 (Strickland Bridge Road) to SR 1115 (Golfview Road). | Widen to multi-lanes. | 5.8 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6072
Cumberland | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | NCDOT | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4709 | Division 6 | O, T | 2022 | 9556000 | 2022 | 1575000 | 2024 | 25080000 |  |  | 36211000 | UNDER CONSTRUCTION. O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC.
Cumberland | SR 1400 (Cliffdale Road) | NCDOT | McPherson Church Road to SR 1404 (Morganton Road). | Widen roadway. | 0.94 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4404 | Division 6 | T | 2029 | 5800000 | 2029 | 5400000 | 2032 | 10800000 |  |  | 22000000
Cumberland | SR 1400 (Cliffdale Road) | NCDOT | Two Bale Lane to SR 1102 (Gillis Hill Road) | Widen roadway and extend on new location. | 1.08 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0042 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40100000 |  |  | 44600000
Cumberland | SR 1437 (Shaw Road) | NCDOT | NC 24 (Bragg Boulevard) to NC 210 (Murchison Road). | Widen roadway and construct partially on new location. | 1.89 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5101A | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39000000 |  |  | 58200000
Cumberland | SR 1437 (Shaw Road); SR 1614 (Shaw Mill Road); SR 1615 (Rosehill Road / Stacey Weaver Drive) | NCDOT | NC 24 (Bragg Boulevard) to US 401 (Ramsey Street). | Widen roadway and construct partially on new location. | 3.6 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5101 | Division 6
Cumberland | SR 1596 (South Main Street) | NCDOT | SR 1243 (Shipman Road) to SR 1118 (Parkton Road). | Widen to multi-lanes. | 1.19 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6001 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17900000 |  |  | 24000000
Cumberland | SR 1614 (Shaw Mill Road)-SR 1615 (Rosehill Road / Stacey Weaver Drive) | NCDOT | NC 210 (Murchison Road) to US 401 (Ramsey Street). | Widen roadway and construct partially on new location. |  | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5101B | Not Funded | T | NOT FUNDED | 38500000 | NOT FUNDED | 21445000 | NOT FUNDED | 36300000 | NOT FUNDED |  | 96245000
Cumberland | US 401 | NCDOT | US 401 Bypass to north of Slocumb Road. | Widen to multi-lanes. | 5.08 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403C | Division 6 | T | 2030 | 23400000 | 2030 | 20900000 | 2033 | 55300000 |  |  | 99600000
Cumberland | US 401 (Raeford Road) | NCDOT | East of Brighton Road to east of Glensford Drive in Fayetteville. | Construct access management improvements. | 1.61 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405B | Division 6 | BGANY, L |  |  |  |  | 2025 | 66957000 |  |  | 66957000 | UNDER CONSTRUCTION.
Cumberland | US 401 (Raeford Road) | NCDOT | East of SR 1596 (Glensford Drive) to east of Robeson Street in Fayetteville. | Construct access management improvements. | 2.38 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405C | Division 6 | T |  |  |  |  | 2029 | 67000000 |  |  | 67000000 | BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
Cumberland | US 401 (Raeford Road) | NCDOT | Old Raeford Road to east of Brighton Road in Fayetteville. | Construct access management improvements. | 2.22 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405A | Division 6 | BGANY, T(M) |  |  |  |  | 2022 | 35403000 |  |  | 35403000 | UNDER CONSTRUCTION.
Cumberland | US 401 (Raeford Road) | NCDOT | SR 3569 (Old Raeford Road) to east of SR 3828 (Robeson Street) in Fayetteville. | Construct access management improvements. | 6 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405 | Division 6 | [10 empty] | RIGHT-OF-WAY IN PROGRESS.
Cumberland | US 401 (Ramsey Street) | NCDOT | US 401 Business (Martin Luther King, Jr. Freeway) to north of Slocumb Road. | Widen to multi-lanes. | 8.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403
Cumberland | US 401 (Robeson Street) | NCDOT | US 401 (Raeford Road) to Saint Avold Avenue | Construct access management. | 2.09 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6152 | Region C | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 37200000 |  |  | 62000000
Cumberland | US 401 Business | NCDOT | NC 24 / NC 210 (Grove Street) to US 401 Business (Martin Luther King, Jr. Freeway). | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403A | Not Funded | T | NOT FUNDED | 3121000 | NOT FUNDED |  | NOT FUNDED | 7400000 | NOT FUNDED |  | 10521000
Cumberland | US 401 Business | NCDOT | US 401 Business (Martin Luther King, Jr. Freeway) to US 401 Bypass. | Widen to multi-lanes. | 2.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403B | Region C | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56500000 |  |  | 89300000
Cumberland | US 401 Business (Skibo Road) | NCDOT | SR 1400 (Cliffdale Road) intersection in Fayetteville | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6133 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8200000 |  |  | 17400000
Cumberland | US 401 Bypass (Pamalee Drive) | NCDOT | NC 24 / NC 87 (Bragg Boulevard) to NC 210 (Murchison Road). | Construct raised center median with access management improvements. | 2.32 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0015 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36000000 |  |  | 89400000
Cumberland | Various | NCDOT | Routes in Fayetteville. | Install computerized traffic signal system. | 0 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5742 | Region C | T |  |  |  |  | 2019 | 735000 |  |  | 735000 | COMPLETE. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | South of SR 1400 (Cliffdale Road) to east of SR 1415 (Yadkin Road). | Construct freeway on new location. | 4.69 | Highway | Transition | 6 | Fayetteville Area MPO | U-2519CB | Pre-STI (Transition) | [10 empty] | COMPLETE.
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Funding for planning assistance - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TP-5103 | Public Transit | 5303, L, S | [6 empty] | 2020 | 768000 | 768000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Funding for technology replacement upgrades |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TT-5204 | Public Transit | 5307, L, S | [6 empty] | 2022 | 350000 | 350000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Replace bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-4948A | Public Transit | 5307, 5339, L, S | [6 empty] | 2020 | 22350000 | 22350000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Replace light transit vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-4743A | Public Transit | 5307, L, S | [6 empty] | 2021 | 225000 | 225000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Replace light transit vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-4743B | Public Transit | 5307, L, S | [6 empty] | 2021 | 4420000 | 4420000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Safety and security minimum 1 % set aside |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TS-5109 | Public Transit | 5307, L | [6 empty] | 2020 | 300000 | 300000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Various locations | Funding for elderly and disabled projects (non traditional). |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-5139 | Public Transit | 5310, L | [6 empty] | 2020 | 1125000 | 1125000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE | Various locations | Funding to implement cashless fare system across the fixed route and paratransit fleet. |  | Public Transportation (Transit) | Locally Selected | 6 | Fayetteville Area MPO | TL-0060 | Exempt | CRPDA, L(M) |  |  |  |  | 2025 | 156000 |  |  | 156000
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 6 | Fayetteville Area MPO | TO-5132 | Public Transit | SMAP | [6 empty] | 2020 | 7656000 | 7656000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 6 | Fayetteville Area MPO | TO-5144 | Public Transit | 5307, L | [6 empty] | 2020 | 10800000 | 10800000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Funding for planning assistance - 5303 |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Fayetteville Area MPO | TP-5103B | Public Transit | 5307, L, S | [6 empty] | 2020 | 4200000 | 4200000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Various locations | Funding for elderly and disabled projects (traditional). |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Fayetteville Area MPO | TQ-6514 | Public Transit | 5310, L | [6 empty] | 2020 | 1584000 | 1584000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | SYSTEM TRANSIT FAYETTEVILLE AREA | Various locations | Funding for preventive maintenance along fixed route. |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Fayetteville Area MPO | TG-5224A | Public Transit | 5307, L | [6 empty] | 2020 | 18000000 | 18000000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | SYSTEM TRANSIT FAYETTEVILLE AREA | Various locations | Funding for ADA services. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6 | Fayetteville Area MPO | TG-5224E | Public Transit | 5307, L | [6 empty] | 2020 | 2841000 | 2841000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | SYSTEM TRANSIT FAYETTEVILLE AREA | Various locations | Funding for routine capital. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6 | Fayetteville Area MPO | TG-5224C | Public Transit | 5307, 5339, L | [6 empty] | 2020 | 1470000 | 1470000 | FUNDS AUTHORIZED IN PROGRESS
Cumberland | Fayetteville Area System of Transit (FAST) | SYSTEM TRANSIT FAYETTEVILLE AREA | Various locations | Funding for support vehicle. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6 | Fayetteville Area MPO | TG-5224D | Public Transit | 5307, L | [6 empty] | 2022 | 720000 | 720000
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM OF TRANSIT | Route 3. | Add shelter packages to existing stops. |  | Public Transportation (Transit) | STI (Prioritization) | 6 | Fayetteville Area MPO | TP-0005 | Division 6 | T |  |  |  |  | 2028 | 43000 |  |  | 43000
Cumberland | Fayetteville Area System of Transit (FAST) | FAYETTEVILLE AREA SYSTEM TRANSIT | Systemwide | Purchase expansion bus. |  | Public Transportation (Transit) | STI (Prioritization) | 6 | Fayetteville Area MPO | TA-6685 | Division 6 | FEDT, L, T |  |  |  |  | 2026 | 490000 |  |  | 490000
Cumberland | SR 1714 (Church Street) | NCDOT | CSX Crossing 629869Y in Wade. | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006A | Division 6 | RR |  |  |  |  | 2026 | 800000 |  |  | 800000
Cumberland | SR 2311 (Gillespie Street) | NCDOT | Aberdeen & Rockfish Railroad Crossing 847218L in Fayetteville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Fayetteville Area MPO | RX-2406C | Division 6 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Cumberland | Winslow | NCDOT | Aberdeen & Rockfish Railroad Crossing 847215R in Fayetteville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Fayetteville Area MPO | RX-2406D | Division 6 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Cumberland | CSX A Line |  | Hay Street Crossing 629881F in Fayetteville. | Construct grade separation and close at-grade crossing. |  | Rail | STI (Prioritization) | 6 | Fayetteville Area MPO | RP-0002 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34000000 |  |  | 49200000
Cumberland, Columbus, Bladen | Various | NCDOT | Routes in Bladen, Columbus, and Cumberland Counties | Upgrade 60 guardrail end units. |  | Highway | Safety | 6 | Fayetteville Area MPO, Cape Fear RPO, Mid-Carolina RPO | HS-2406I | Region C | HSIP, T(M) |  |  |  |  | 2025 | 609000 |  |  | 609000
Cumberland, Harnett | NC 210 | NCDOT | Bladen County line to NC 53 in Cumberland County, and Cumberland County line to Lillington city limits in Harnett County. | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO | HS-2006AC | Region C | HSIP, T(M) |  |  |  |  | 2024 | 1170000 |  |  | 1170000
Cumberland, Harnett | I-95 | NCDOT | I-95 Business / US 301 (Exit 56) to SR 1001 (Long Branch Road) (Exit 71). | Widen to eight lanes. | 15.76 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO, Fayetteville Area MPO | I-5986A | Statewide Mobility | NHP, PROTCT, T | 2019 | 21073000 | 2023 | 2000000 | 2019 | 425400000 |  |  | 448473000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
Cumberland, Harnett | NC 24 / NC 87 | NCDOT | SR 1117 (Nursery Road) to SR 1451 (Manchester Road). | Widen roadway. | 3.23 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0020 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33300000 |  |  | 64200000
Cumberland, Harnett, Hoke, Robeson | Various | NCDOT | Fayetteville Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 6, 8 | Fayetteville Area MPO | U-5528 | Division 6, 8 | TADA |  |  |  |  | 2020 | 21515000 |  |  | 21515000 | IN PROGRESS.
Cumberland, Harnett, Hoke, Robeson | Various | NCDOT | Fayetteville Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 6, 8 | Fayetteville Area MPO | HL-0095 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 5490000 |  |  | 5490000
Cumberland, Harnett, Hoke, Robeson | Various | NCDOT | Fayetteville Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 6, 8 | Fayetteville Area MPO | U-5207 | Division 6, 8 | BGDA, L(M) | [6 empty] | 2020 | 11860000 | 11860000 | IN PROGRESS.
Cumberland, Harnett, Hoke, Robeson | Various | NCDOT | Fayetteville Urban Area Metropolitan Planning Organization. | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 6, 8 | Fayetteville Area MPO | HL-0026 | Division 6, 8 | BGANY, BGDA |  |  |  |  | 2022 | 86582000 |  |  | 86582000
Cumberland, Harnett, Johnston | I-95 | NCDOT | I-95 Business / US 301 (Exit 56) to I-40 (Exit 81). | Widen to eight lanes. | 26 | Highway | STI (Prioritization) | 4, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Upper Coastal Plain RPO | I-5986
Cumberland, Hoke | SR 1102 (Gillis Hill Road) | NCDOT | SR 1418 (Lindsay Road) to north of SR 1112 (Stoney Point Road). | Widen to four lanes. | 1.21 | Highway | STI (Prioritization) | 6, 8 | Fayetteville Area MPO | U-5798B | Division 6, 8 | T | 2024 | 3700000 | 2024 | 710000 | 2026 | 17400000 |  |  | 21810000 | RIGHT-OF-WAY IN PROGRESS.
Cumberland, Hoke | SR 1102 (Gillis Hill Road) | NCDOT | US 401 (Raeford Road) to SR 1418 (Lindsay Road). | Widen to four lanes. | 2.4 | Highway | STI (Prioritization) | 6, 8 | Fayetteville Area MPO | U-5798 | Division 6, 8 | [10 empty] | COORDINATE WITH U-5753, U-5857, AND U-5858.
Cumberland, Robeson | I-295 (Fayetteville Outer Loop) | NCDOT | Fayetteville outer loop. | Install ITS for Fayetteville outer loop. | 34 | Highway | Pre-STI (Historic) | 6 | Fayetteville Area MPO, Lumber River RPO | U-2519F | Statewide Mobility | NHP, T(M) |  |  |  |  | 2026 | 11600000 |  |  | 11600000
Cumberland, Robeson | I-295 (Fayetteville Outer Loop) | NCDOT | I-95 south of Fayetteville to west of NC 24 / NC 87 (Bragg Boulevard). | Construct freeway on new location. | 22.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO, Lumber River RPO | U-2519
Cumberland, Robeson, Columbus, Harnett | Various | NCDOT | Routes in Division 6. | Install pavement markings in freeway / expressway ramps. |  | Highway | Safety | 6 | Lumber River RPO, Fayetteville Area MPO, Mid-Carolina RPO, Cape Fear RPO | HS-2006AB | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 200000 |  |  | 200000
Currituck | US 158 | NCDOT | Bridge 260016 over Currituck Sound. | Rehabilitate bridge. | 3.16 | Highway | Bridges | 1 | Albemarle RPO | B-5937 | Statewide Mobility | [10 empty] | COMPLETE.
Currituck | NC 615 (Marsh Causeway) | NCDOT | HQ / VC Entrance Road to west of Knotts Island Road. | Improve corridor at various locations. | 3.89 | Highway | Federal Lands Access Program | 1 | Albemarle RPO | HF-0008 | Exempt | FLAP |  |  |  |  | 2025 | 650000 | 2023 | 50000 | 700000 | FLAP PROJECT NC 71. AWARDED $700K. RIGHT-OF-WAY IN PROGRESS
Currituck | NC 168 | NCDOT | SR 1229 (Baxter Lane) intersection and Currituck Sand Company access north of Moyock | Install traffic signal. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401N | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 500000 |  |  | 500000 | UNDER CONSTRUCTION.
Currituck | US 158 | NCDOT | NC 168 to Wright Brothers Memorial Bridge, and US 158 to north of Lark Drive | Install rumble stripes and pavement markings. | 40 | Highway | Safety | 1 | Albemarle RPO | HS-2401K | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 632000 |  |  | 632000 | UNDER CONSTRUCTION.
Currituck | US 158 | NCDOT | SR 1186 (Walnut Island Boulevard) to SR 1131 (Poplar Branch Road) in Grandy | Install pedestrian signal heads, crosswalks, and sidewalks. | 0.25 | Highway | Safety | 1 | Albemarle RPO | HS-2401J | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 184000 |  |  | 184000
Currituck | US 158 | NCDOT | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Highway | Safety | 1 | Albemarle RPO | HS-2001F | Region A | HSIP, T | 2028 | 950000 | 2028 | 60000 | 2028 | 4300000 |  |  | 5310000
Currituck | US 158 | NCDOT | US 158 and SR 1147 (Indiantown Road) Intersection. | Construct roundabout. | 0.5 | Highway | Safety | 1 | Albemarle RPO | HS-2001A | Region A | HSIP, T(M) |  |  |  |  | 2023 | 44000 |  |  | 44000 | UNDER CONSTRUCTION.
Currituck | New Route | NCDOT | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-2576 | Division 1 | BGANY, BOND R, O, T(M) | 2027 | 42500000 | 2027 | 13000000 | 2027 | 1101205000 |  |  | 1156705000 | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041.
Currituck, Camden | NC 34 | NCDOT | US 158 in Camden County to NC 168 in Currituck County | Install rumble stripes and pavement markings. | 9 | Highway | Safety | 1 | Albemarle RPO | HS-2401O | Region A | HSIP, T(M) |  |  |  |  | 2025 | 286000 |  |  | 286000 | UNDER CONSTRUCTION.
Dare | US 158 | NCDOT | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Bike & Ped | STI (Prioritization) | 1 | Albemarle RPO | EB-5848 | Division 1 | L(M), TA5T50 |  |  | 2026 | 10000 | 2027 | 7200000 | 2024 | 100000 | 7310000
Dare | Hatteras to Ocracoke Ferry - Loading Facility | NCDOT | Loading facility | Improve parking lot and construct connectivity measures. |  | Ferry | Other | 1 | Albemarle RPO | F-5702A | Division 1 | [10 empty] | COMPLETE. WORK ACCOMPLISHED UNDER F-5702B.
Dare | NC 12 | NCDOT | Bridge 270008 over canal of Pamlico Sound in Hatteras. | Replace bridge. | 0.25 | Highway | Bridges | 1 | Albemarle RPO | B-5610 | Region A | BGLT5, NHPB | 2021 | 520000 | 2021 | 460000 | 2024 | 5220000 |  |  | 6200000 | RIGHT-OF-WAY IN PROGRESS.
Dare | US 64 | NCDOT | Bridge 270009 over Croatan Sound in Manns Harbor. | Preserve bridge. | 2.85 | Highway | Bridges | 1 | Albemarle RPO | HB-0017 | Region A | BFP, T(M) |  |  |  |  | 2022 | 55023000 |  |  | 55023000 | UNDER CONSTRUCTION.
Dare | NC 12 | NCDOT | Rodanthe to Oregon inlet. | Conduct planning study for the long-term operation of the roadway during major storm events. |  | Highway | Other | 1 | Albemarle RPO | HO-0020 | Exempt | DP | [6 empty] | 2025 | 1865000 | 1865000 | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT AWARD.
Dare | US 64 | NCDOT | East of the East Lake Community to west of SR 1169 (Robertson Landing Road). | Install wildlife underpasses and fencing. | 2.5 | Highway | Other | 1 | Albemarle RPO | HO-0027 | Exempt | DP, HF(M), O(M) |  |  |  |  | 2027 | 30550000 | 2026 | 700000 | 31250000 | DP funds represent Wildlife Crossings Pilot Program Grant. O(M) funds represent private donations. O phase represents Education / Outreach and Monitoring activities.
Dare | Various | NCDOT | Wright Brothers National Memorial. | Deployment of automated shuttle at Wright Brothers National Memorial. |  | Highway | Other | 1 | Albemarle RPO | R-5753A | Exempt | FLTP | [6 empty] | 2021 | 95000 | 95000
Dare | NC 12 | NCDOT | Bridge 270011 (Herbert C. Bonner Bridge) over Oregon Inlet. | Construct short-term improvements at Pea Island. |  | Highway | Pre-STI (Historic) | 1 | Albemarle RPO | B-2500AB | Pre-STI (Transition) | [10 empty] | COMPLETE.
Dare | NC 12 | NCDOT | Bridge 270011 (Herbert C. Bonner Bridge) over Oregon Inlet. | Replace bridge and construct NC 12 improvements. | 2.7 | Highway | Pre-STI (Historic) | 1 | Albemarle RPO | B-2500 | Pre-STI (Transition)
Dare | NC 12 (Virginia Dare Trail) | NCDOT | Neptune Drive intersection in Kill Devil Hills | Remove existing crosswalk, install new crosswalk with pedestrian heads, and revise signal. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401L | Region A | HSIP, T(M) |  |  |  |  | 2025 | 100000 |  |  | 100000
Dare | US 158 | NCDOT | SR 1206 (The Woods Road) / Dogwood Trail intersection in Kitty Hawk | Install curb, gutter, ramps and crosswalks. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401I | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 113000 |  |  | 113000
Dare | SR 1208 (West Kitty Hawk Road) | NCDOT | SR 1210 (Bob Perry Road) to Ivy Lane. | Upgrade facility and replace bridge 270040. | 1.01 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5738 | Division 1 | T |  |  |  |  | 2019 | 4646000 |  |  | 4646000 | COMPLETE. BUILD NC BOND FUNDING: $3,561,232 FOR CONSTRUCTION PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
Dare | SR 1217 (Collington Road) | NCDOT | Dead end to US 158 (Croatan Highway) in Kill Devil Hills. | Construct operational safety improvements. | 4.35 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5014 | Division 1 | BGANY, T(M) |  |  |  |  | 2022 | 22368000 |  |  | 22368000 | UNDER CONSTRUCTION.
Dare | NC 12 | NCDOT | Rodanthe. | Improve NC 12. |  | Highway | Transition | 1 | Albemarle RPO | B-2500B | Pre-STI (Transition) | BGLT5, T(M) |  |  |  |  | 2023 | 1300000 |  |  | 1300000 | COMPLETE.
Dare, Halifax | Hatteras to Ocracoke Ferry | NCDOT | Hatteras and Ocracoke terminals | Construct dock improvements. |  | Ferry | Other | 1, 4 | Albemarle RPO | F-5702E | Division 1, 4 | [10 empty] | COMPLETE. WORK ACCOMPLISHED UNDER F-5702B.
Dare, Hyde | Hatteras to Ocracoke Ferry | NCDOT | Hatteras and Ocracoke Island terminals | Construct ferry ramp and dock improvements. |  | Ferry | Federal Lands Access Program | 1 | Albemarle RPO | FF-0001 | Exempt | FLAP, HFB |  |  | 2026 | 10000 | 2027 | 20000000 | 2023 | 1070000 | 21080000 | FLAP PROJECT NC 62. AWARDED $3.5M. PREVIOUSLY BR-0170.
Dare, Hyde | Hatteras to Ocracoke Ferry | NCDOT | Hatteras to Ocracoke Ferry | Construct two passenger ferries to be used along new route from Hatteras in Dare County to Ocracoke in Hyde County. Implement transit system to aid passengers on Ocracoke Island. |  | Ferry | Other | 1 | Albemarle RPO | F-5702 | Division 1 | [10 empty] | OTHER FUNDS ARE FROM STATE APPROPRIATION 7355.
Dare, Hyde | Hatteras to Ocracoke Ferry | NCDOT | Hatteras to Ocracoke Ferry | Construct two passenger ferries. |  | Ferry | Other | 1 | Albemarle RPO | F-5702C | Division 1 | [10 empty] | UNDER CONSTRUCTION.
Dare, Hyde | Hatteras Ferry | NCDOT | Hatteras to Ocracoke Ferry | Purchase river class ferry. |  | Ferry | STI (Prioritization) | 1 | Albemarle RPO | F-5700 | Division 1 | [10 empty] | COMPLETE
Dare, Hyde | NC 12 | NCDOT | Ocracoke and Hatteras Ferry terminals | Replace passenger ferry docks. |  | Highway | Federal Lands Access Program | 1 | Albemarle RPO | FF-0001A | Exempt | FLAP |  |  |  |  | 2026 | 3250000 |  |  | 3250000
Davidson | EXX | DAVIDSON COUNTY AIRPORT (EXX) | Davidson County Airport | Upgrade and strengthen runway to accommodate larger private aircraft. |  | Aviation | STI (Prioritization) | 9 | High Point Urban Area MPO | AV-5831 | Division 9 | T |  |  |  |  | 2022 | 14551000 |  |  | 14551000 | UNDER CONSTRUCTION. TO BE LET WITH AV-5900.
Davidson | EXX | DAVIDSON COUNTY AIRPORT (EXX) | Davidson County Airport | Upgrade taxiway and apron. |  | Aviation | STI (Prioritization) | 9 | High Point Urban Area MPO | AV-5900 | Division 9 | [10 empty] | UNDER CONSTRUCTION, LET WITH AV-5831. FUNDING SHOWN UNDER PROJECT AV-5831
Davidson | I-85 | NCDOT | Bridges 280181 and 280182 over US 64 near Lexington. | Rehabilitate bridges. | 0.25 | Highway | Bridges | 9 | High Point Urban Area MPO | I-5740A | Statewide Mobility | [10 empty] | COMPLETE
Davidson | US 29 / US 70 / Business 85 | NCDOT | Bridges 280164 and 280168 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Highway | Bridges | 9 | High Point Urban Area MPO | B-5783 | Region D | BFP, T(M) |  |  |  |  | 2023 | 5778000 |  |  | 5778000 | UNDER CONSTRUCTION
Davidson | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | NCDOT | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Highway | Bridges | 9 | High Point Urban Area MPO | B-5779 | Region D | BFP, T(M) | 2031 | 110000 | 2031 | 350000 | 2032 | 11800000 |  |  | 12260000
Davidson | SR 1104 (Old Linwood Road) | NCDOT | North of SR 1254 (Brown Street). | Construct new access road and improvements to SR 1104 (Old Linwood Road). |  | Highway | Economic Development | 9 | High Point Urban Area MPO | HE-0014 | Division 9 | T |  |  | 2024 | 10000 | 2024 | 8590000 | 2023 | 400000 | 9000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY.
Davidson | US 64 | NCDOT | Across from SR 2112 (Decker Road). | Extend left turn lane and construct right turn lane at proposed new access road and widen rail crossing 836515Y. | 0.09 | Highway | Economic Development | 9 | High Point Urban Area MPO | HE-0008 | Division 9 | T |  |  |  |  | 2023 | 1500000 | 2022 | 300000 | 1800000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR.
Davidson | I-85 | NCDOT | I-285 / US 29 / US 52 / US 70 to north of US 64. | Rehabilitate pavement. | 9.58 | Highway | Interstate Maintenance | 9 | High Point Urban Area MPO | I-5950 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 28542000 |  |  | 28542000
Davidson | I-85 | NCDOT | SR 2205 (Old US 64) to 0.4 miles north of US 64. | Rehabilitate pavement. | 2.6 | Highway | Interstate Maintenance | 9 | High Point Urban Area MPO | I-5740 | Statewide Mobility | [10 empty] | COMPLETE
Davidson | NC 109 | NCDOT | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Highway | Locally Selected | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | HL-0061 | Exempt | BGDA, CMAQ, CRPDA, HF(M), L(M) | 2026 | 1982000 | 2026 | 518000 | 2027 | 2007000 | 2024 | 400000 | 4907000
Davidson | I-85 | NCDOT | North Carolina Railroad mile marker 326.4. | Realign curve at Duke South of Linwood Yard. |  | Highway | Pre-STI (Historic) | 9 | High Point Urban Area MPO | I-2304AE | [11 empty] | COMPLETE
Davidson | I-85 | NCDOT | North of NC 150 to US 29 / US 70 / US 52 / I-85 Business | Reconstruct bridge. |  | Highway | Pre-STI (Historic) | 9 | High Point Urban Area MPO | I-2304AD | Pre-STI (Transition) | NHP | 2009 | 984000 | [6 empty] | 984000 | COMPLETE; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021
Davidson | NC 109 | NCDOT | Denton northern municipal boundary to SR 2067 (Lambeth Road). Also, SR 1798 (Old Greensboro Road) / SR 1756 (West Lexington Avenue Extension) to SR 1711 (Gumtree Road). | Install rumble stripes and long-life pavement markings. | 15.99 | Highway | Safety | 9 | High Point Urban Area MPO | W-5809A | Region D | HSIP, T(M) |  |  |  |  | 2022 | 1100000 |  |  | 1100000 | UNDER CONSTRUCTION
Davidson | NC 109 | NCDOT | SR 2335 (Canaan Church Road) / Snyder Station Road intersection near Denton. | Install turn lanes. | 0.5 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009K | Region D | CRPLT5, T(M) |  |  |  |  | 2024 | 670000 |  |  | 670000
Davidson | NC 62 (Cloninger Drive) | NCDOT | SR 2055 (Liberty Drive) intersection in Thomasville. | Improve vertical alignment. | 0.5 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009L | Region D | HSIP, T(M) |  |  |  |  | 2025 | 530000 |  |  | 530000
Davidson | US 29 / US 70 | NCDOT | Vicinity of Fleet Darr Road west of SR 2123 (Lexington Avenue) Connector. | Install directional leftovers. | 0.5 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009C | Region D | HSIP, T(M) |  |  |  |  | 2029 | 500000 |  |  | 500000
Davidson | US 64 | NCDOT | SR 2782 (Bowers Road) to east of SR 2012 (Heath Church Road) / SR 2227 (New Bowers Road). | Construct four reduced conflict intersections and leftover with U-turn bulb. | 0.61 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009B | Region D | HSIP, T(M) |  |  | 2023 | 20000 | 2023 | 2687000 |  |  | 2707000 | UNDER CONSTRUCTION
Davidson | NC 8 (Winston Road) | NCDOT | 9th Street to SR 1408 (Biesecker Road) in Lexington. | Widen to four lane divided facility with bike-ped accommodations. | 0.51 | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | U-5757 | Region D | T | 2019 | 17575000 |  |  | 2025 | 15620000 |  |  | 33195000 | RIGHT-OF-WAY IN PROGRESS
Davidson | SR 1508 (Hickory Tree Road) | NCDOT | US 52 / NC 8 / Future I-285 to NC 150. | Widen to multi-lanes. | 2.91 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5786 | Division 9 | BGANY, T | 2030 | 12700000 | 2030 | 5200000 | 2034 | 45700000 |  |  | 63600000
Davidson | US 29 / US 70 / BUSINESS 85 | NCDOT | SR 1798 (Old Greensboro Road) intersection near Lexington . | Upgrade at grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | R-5737 | Division 9 | T |  |  |  |  | 2022 | 29777000 |  |  | 29777000 | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE
Davidson | US 64 | NCDOT | I-85 Business in Lexington to east of I-85. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | R-2220A | [11 empty] | COMPLETE
Davidson | US 64 | NCDOT | I-85 east of Lexington to NC 109. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | R-2220B | Not Funded | T | NOT FUNDED | 30992000 | NOT FUNDED | 5635000 | NOT FUNDED | 40572000 | NOT FUNDED |  | 77199000
Davidson | Davidson County Transportation System | DAVIDSON COUNTY TRANSPORTATION SYSTEM | Systemwide | Installing covered bus shelters with ADA access to major stops such as Walmart and Big lots. Install Simme seats at the remainder of bus stops. Simme seats provide two seats attached to the bus stip sign pole. |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0014 | Division 9 | BGDA, L | [6 empty] | 2021 | 140000 | 140000
Davidson | Davidson County Transportation system |  | Various locations | Operate our deviated fixed routes based in Thomasville, NC along with demand response trips. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | High Point Urban Area MPO | TM-0048 | Public Transit | 5317, L | [6 empty] | 2024 | 3300000 | 3300000
Davidson | Davidson County Transportation System |  | Various locations | Funding for routine maintenance for operations in Thomasville. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | High Point Urban Area MPO | TG-0021 | Public Transit | 5317, L | [6 empty] | 2024 | 360000 | 360000
Davidson | North Carolina Railroad | LEXINGTON | Lexington train station. | Construct track improvements and multi-modal passenger rail and bus station in the Lexington depot district. |  | Rail | Other | 9 | High Point Urban Area MPO | P-5732 | Exempt | DP, L, O |  |  |  |  | 2026 | 15700000 |  |  | 15700000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
Davidson | LS (First Street) | NCDOT | Crossing 849955C in Denton | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2009A | Division 9 | RR |  |  |  |  | 2026 | 303000 |  |  | 303000
Davidson | SR 1101 (Wildlife Recreation Area Access Road) | NCDOT | WSS Crossing 849835L in Southmont | Improve crossing. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2409D | Division 9 | RR |  |  |  |  | 2031 | 400000 | 2031 | 40000 | 440000
Davidson | SR 1101 (Wildlife Recreation Area Access Road) | NCDOT | WSS Crossing 849835L in Southmont | Improve crossing. | 0.25 | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2409A | Division 9 | RR |  |  |  |  | 2026 | 475000 |  |  | 475000
Davidson | SR 1821 (Hinkle Lane) | NCDOT | Winston Salem Southbound Railway Crossing 836380V. | Improve highway-rail grade crossing safety. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2409B | Division 9 | RR |  |  |  |  | 2031 | 400000 | 2031 | 40000 | 440000
Davidson | SR 2289 (Holloway Church Road) | NCDOT | Winston Salem Southbound Railway Crossing 849838G. | Improve highway-rail grade crossing safety. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2409C | Division 9 | RR |  |  |  |  | 2031 | 450000 | 2031 | 45000 | 495000
Davidson | Norfolk Southern | LEXINGTON | Kimberly Clark in Lexington. | Construct lead. |  | Rail | STI (Prioritization) | 9 | High Point Urban Area MPO | P-5722 | Region D | O, T |  |  |  |  | 2027 | 2038000 |  |  | 2038000 | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION.
Davidson | Norfolk Southern | NCDOT | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Rail | STI (Prioritization) | 9 | High Point Urban Area MPO | P-5731 | Division 9 | DP, L, T | 2025 | 8900000 | 2025 | 10000 | 2026 | 72000000 |  |  | 80910000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS
Davidson | North Carolina Railroad / Norfolk Southern Main Line | NCDOT | SR 2165 (Turner Street) in Thomasville. | Construct grade separation and close crossing 722327S. |  | Rail | STI (Prioritization) | 9 | High Point Urban Area MPO | P-5751 | Division 9 | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31387000 |  |  | 61987000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
Davidson, Alamance, Cabarrus, Durham, Guilford, Mecklenburg, Orange, Rowan, Wake | Piedmont Corridor | NCDOT | Regionwide | Purchase new trains and upgrade maintenance facility. |  | Rail | STI (Prioritization) | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Greensboro Urban Area MPO, Triangle West TPO | P-5719C | Region C, D, E | DP, T |  |  |  |  | 2026 | 212529000 |  |  | 212529000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | BO-2409 | Division 9 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Locations in Division 9 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | R-5789 | Division 9 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Various locations in Division 9. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | BO-2609 | Division 9 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9 | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709DIV | Division 9 | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 556000 |  |  | 646000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9 | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709REG | Region D | HSIP, T(M) | 2020 | 90000 |  |  | 2020 | 556000 |  |  | 646000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9 | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709SW | Statewide Mobility | HSIP, T(M) | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2009 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2409 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709 | [11 empty] | IN PROGRESS; $2.5M NHP FUNDING APPLIED TO W-5709E.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Construct safety improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5809
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024DIV | Division 9 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024REG | Region D | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Secondary routes in Division 9. | Install long-life pavement markings. |  | Highway | Safety | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO | HS-2009A | Division 9 | HSIP, T(M) |  |  |  |  | 2021 | 1900000 |  |  | 1900000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Various locations in Division 9 | Safety Improvements. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2609 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Locations in Division 9. | Implementation of traffic separation study and closures in Division 9. |  | Rail | Rail-Highway Grade Crossing Closure | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RC-2009 | Division 9 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | SR 1002 (Bringle Ferry Road) |  | Winston Salem Southbound Railway Crossing 849833X. | Improve highway-rail grade crossing safety. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2409E | Division 9 | RR |  |  |  |  | 2031 | 400000 | 2031 | 40000 | 440000
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Locations in Division 9. | Construct highway-rail grade crossing safety improvements in Division 9. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RX-2009 | Division 9 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Locations in Division 9. | Construct highway-rail grade crossing safety improvements in Division 9. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RX-2409 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Davie, Forsyth, Rowan, Stokes | Various | NCDOT | Locations in Division 9. | Construct highway-rail grade crossing safety improvements in Division 9. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RX-2609 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Davidson, Forsyth | NC 109 | NCDOT | Mile marker 0.256 in Forsyth County to mile marker 38.367 in Davidson County. | Install centerline and edgeline sinusoidal rumble stripes. | 0.48 | Highway | Safety | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | HS-2009F | Region D | HSIP, T(M) |  |  |  |  | 2023 | 238000 |  |  | 238000 | UNDER CONSTRUCTION
Davidson, Guilford, Forsyth | Various | HIGH POINT | Locations in High Point MPO. | Improve congestion and air quality. |  | Highway | Other | 7, 9 | High Point Urban Area MPO | C-5609 | Exempt | CMAQ, L(M) | 2020 | 243000 |  |  | 2020 | 1455000 | 2020 | 729000 | 2427000 | IN PROGRESS
Davidson, Guilford, Randolph | High Point Transit System | HIGH POINT TRANSIT SYSTEM / HI-TRAN | Systemwide | Funding for safety and security, minimum set 1 % aside. |  | Public Transportation (Transit) | Capital (Non-STI) | 7, 8, 9 | High Point Urban Area MPO | TS-5113 | Public Transit | 5307, L | [6 empty] | 2020 | 144000 | 144000 | FUNDS AUTHORIZED IN PROGRESS
Davidson, Guilford, Randolph, Forsyth | Various | NCDOT | High Point Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 7, 8, 9 | High Point Urban Area MPO | HL-0101 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 2366000 |  |  | 2366000
Davidson, Randolph | US 64 | NCDOT | East of I-85 Business in Lexington to Asheboro Bypass. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 8, 9 | High Point Urban Area MPO, Piedmont Triad RPO | R-2220
Davidson, Rowan | I-85 | NCDOT | North of SR 2120 (Long Ferry Road) in Rowan County to North of NC 150 in Davidson County, including Yadkin River Bridge. | Reconstruct bridge. |  | Highway | Pre-STI (Historic) | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | I-2304AC | Exempt | NHP | 2009 | 1066000 |  |  | 2010 | 8220000 |  |  | 9286000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC
Davidson, Rowan | I-85 | NCDOT | North of SR 2120 (Long Ferry Road) in Rowan County to US 29 / US 52 / US 70 / I-85 Business in Davidson County. | Construct additional lanes, and reconstruct Bridges 790137 and 790465 (Yadkin River Bridge). | 6.8 | Highway | Pre-STI (Historic) | 9 | High Point Urban Area MPO, Cabarrus-Rowan MPO | I-2304 | Pre-STI (Transition) | [10 empty] | INCLUDES B-3833; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION; GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
Davidson, Rowan | I-85 | NCDOT | In Division 9. | Implement intelligent transportation system (ITS). |  | Highway | Transition | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | I-2304AF | Pre-STI (Transition) | [10 empty] | COMPLETE
Davie | Blue Heron Trail | BERMUDA RUN | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0146 | Division 9 | L(M), TADA | 2026 | 110000 | 2026 | 13000 | 2026 | 647000 | 2025 | 275000 | 1045000
Davie | Blue Heron Trail | BERMUDA RUN | Twins Way near intersection with US 158 to pedestrian tunnel under I-40 in Bermuda Run | Construct section of multi-use path. | 1 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5958 | Division 9 | BGANY, BGDA, L(M) |  |  |  |  | 2022 | 3693000 |  |  | 3693000 | UNDER CONSTRUCTION
Davie | NC 801 | BERMUDA RUN | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0144 | Division 9 | BGDA, L(M) | 2026 | 145000 | 2026 | 13000 | 2026 | 647000 | 2025 | 248000 | 1053000
Davie | SR 1436 (Pinebrook School Road) | NCDOT | Bridge 290076 over I-40 | Replace bridge. |  | Highway | Bridges | 9 | Northwest Piedmont RPO | BR-0152 | Division 9 | BGOFF |  |  |  |  | 2025 | 4910000 |  |  | 4910000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM. UNDER CONSTRUCTION
Davie | I-40 | NCDOT | SR 1436 (Pinebrook School Road) to west of NC 801. | Rehabilitate pavement. | 4.76 | Highway | Interstate Maintenance | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | I-6003 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2021 | 7677000 |  |  | 7677000 | UNDER CONSTRUCTION
Davie | Various | NCDOT | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Highway | Other | 9 | Northwest Piedmont RPO | C-5614 | Exempt | CMAQ, L(M) | 2020 | 12000 |  |  | 2020 | 57000 | 2020 | 36000 | 105000
Davie | NC 801 | NCDOT | I-40 to US 601 | Install rumble strips. | 10.7 | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | HS-2409I | Region D | HSIP |  |  |  |  | 2026 | 800000 |  |  | 800000
Davie | US 158 | NCDOT | East of Crowe Street to east of R.R. Gerald Lane | Install rumble strips. | 7.2 | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | HS-2409J | Region D | HSIP |  |  |  |  | 2026 | 575000 |  |  | 575000
Davie | US 601 | NCDOT | Rowan County line to north of Crepe Myrtle Lane | Install rumble strips. | 6.9 | Highway | Safety | 9 | Northwest Piedmont RPO | HS-2409H | Region D | HSIP |  |  |  |  | 2026 | 560000 |  |  | 560000
Davie | US 601 | NCDOT | SR 1414 (Angell Road) intersection | Improve sight distance. | 0.5 | Highway | Safety | 9 | Northwest Piedmont RPO | HS-2409E | Region D | HSIP, T(M) |  |  |  |  | 2026 | 791000 |  |  | 791000
Davie | US 64 | NCDOT | Iredell County line to I-40 | Install rumble strips. | 7.1 | Highway | Safety | 9 | Northwest Piedmont RPO | HS-2409G | Region D | HSIP |  |  |  |  | 2026 | 575000 |  |  | 575000
Davie | New Route | NCDOT | SR 1630 (Baltimore Road) to I-40. | Construct 2-lane extension of Baltimore road and interchange at I-40. | 0.71 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6187 | Division 9 | BGANY, T | 2024 | 4000000 | 2025 | 1000000 | 2026 | 41890000 |  |  | 46890000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE)
Davie | SR 1410 (Farmington Road) | NCDOT | US 158 intersection in Mocksville. | Construct roundabout. | 1 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5854 | Division 9 | T | 2023 | 100000 | 2023 | 200000 | 2025 | 1500000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
Davie | US 158 | NCDOT | NC 801 Intersection in Bermuda Run | Upgrade intersection with left turn lane on eastbound US 158, right thru lane, and right turn lane on NC 801. | 0.5 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0023 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 |  |  | 7300000
Davie | US 601 | NCDOT | South Salisbury Street intersection in Mocksville. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5728 | Region D | [10 empty] | UNDER CONSTRUCTION
Davie | US 601 | NCDOT | SR 1301 (Madison Road) to SR 1408 (Cana Road). | Widen to multi-lanes. | 1.52 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5736 | Division 9 | BGANY, T(M) | 2030 | 6400000 | 2030 | 800000 | 2033 | 32100000 |  |  | 39300000
Davie | Wilkesboro Street | NCDOT | Yadkinville Road intersection in Mocksville. | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | U-6002 | Division 9 | T |  |  |  |  | 2022 | 1800000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
Davie, Forsyth | I-40 | NCDOT | West of NC 801 in Davie County to SR 1101 (Harper Road) in Forsyth County. | Add lanes. | 2.33 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-0911A | Region D | T |  |  |  |  | 2021 | 35894000 |  |  | 35894000 | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Davie, Stokes, Surry, Yadkin | Yadkin Valley Economic Development District | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 9, 11 | Northwest Piedmont RPO | TK-6174 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1704000 | 1704000 | FUNDS AUTHORIZED IN PROGRESS
Duplin | NC 11 | NCDOT | Bridge 300036 over Maxwell Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5639 | Highway Fund | HFB | 2020 | 56000 |  |  | 2021 | 3422000 |  |  | 3478000 | UNDER CONSTRUCTION.
Duplin | SR 1135 (Providence Church Road) | NCDOT | Bridge 300052 over Rockfish Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5647 | Division 3 | BGOFF | 2023 | 60000 | 2023 | 25000 | 2024 | 1150000 |  |  | 1235000 | RIGHT-OF-WAY IN PROGRESS.
Duplin | SR 1162 (Bay Road) | NCDOT | Bridge 300045 over Island Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | BR-0243 | Highway Fund | HFB |  |  |  |  | 2022 | 1700000 |  |  | 1700000 | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.83 PROJECT.
Duplin | SR 1828 (Cypress Creek Road) | NCDOT | Bridge 300187 over Back Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5632 | Division 3 | BGOFF | 2023 | 190000 |  |  | 2023 | 5186000 |  |  | 5376000 | UNDER CONSTRUCTION.
Duplin | US 117 NBL | NCDOT | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5981 | Statewide Mobility | BGLT5, T(M) | 2022 | 443000 |  |  | 2024 | 10866000 |  |  | 11309000 | RIGHT OF WAY IN PROGRESS
Duplin | I-40 | NCDOT | Sampson County line to Pender County line. | Rehabilitate pavement. | 28 | Highway | Interstate Maintenance | 3 | Eastern Carolina RPO | HI-0012 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2030 | 31100000 |  |  | 31100000
Duplin | Warsaw | NCDOT | Pilot Travel Center. | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 3 | Eastern Carolina RPO | HV-0001C | Division 3 | NEVI, O, O(M), S(M) |  |  |  |  | 2025 | 774000 |  |  | 774000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC
Duplin | NC 111 | NCDOT | Onslow County line to NC 41; NC 41 / NC 241 in Beulaville to NC 11; NC 11 / NC 903 to Wayne County line | Install centerline rumble stripes & shoulder rumble strips. | 27.8 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2403C | Region B | HSIP |  |  |  |  | 2026 | 1360000 |  |  | 1360000
Duplin | NC 24 Business (Routeledge Road) | NCDOT | NC 24 / NC 903 (South Kenansville Bypass) intersection in Kenansville. | Revise traffic signal. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003N | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 252000 |  |  | 252000
Duplin | NC 403 | NCDOT | SR 1306 (Beautancus Road) intersection. | Construct safety improvements. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003I | Region B | HSIP, T(M) |  |  |  |  | 2025 | 70000 |  |  | 70000
Duplin | NC 41 | NCDOT | North of NC 50 to Beulaville city limits | Widen roadway and install rumble strips. | 23 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2403AX | Region B | HSIP |  |  |  |  | 2026 | 718000 |  |  | 718000
Duplin | NC 41 / SR 1163 (Teachey Road) | NCDOT | NC 41 (Southerland Street) / SR 1173 (East Southerland Street) intersection in Wallace. | Upgrade traffic signal. |  | Highway | Safety | 3 | Eastern Carolina RPO | HS-2403AQ | Region B | HSIP |  |  |  |  | 2026 | 17000 |  |  | 17000
Duplin | SR 1501 (Garner Chapel Road) | NCDOT | NC 403 to SR 1306 / SR 1522 (Red Hill Road / Washboard Road) east of Mt. Olive | Install rumble stripes. | 9.41 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2403S | Division 3 | HSIP |  |  |  |  | 2027 | 368000 |  |  | 368000
Duplin | SR 1535 (Liddell Road) | NCDOT | SR 1534 (Drummersville Road) intersection. | Install all way stop. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003C | Division 3 | HSIP, T(M) |  |  |  |  | 2025 | 20000 |  |  | 20000
Duplin | US 117 | NCDOT | SR 1150 (Lodge/High School Road) intersection in Teachey | Install traffic signal. |  | Highway | Safety | 3 | Eastern Carolina RPO | HS-2403L | Region B | HSIP |  |  |  |  | 2026 | 161000 |  |  | 161000
Duplin | US 117 (Norwood Street) | NCDOT | SR 1173 (Southerland Street) intersection in Wallace. | Revise traffic signal. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003M | Region B | HSIP, T(M) |  |  |  |  | 2025 | 44000 |  |  | 44000 | UNDER CONSTRUCTION.
Duplin | US 117 (Sycamore Street) | NCDOT | SR 1102 (Charity Road) intersection in Rose Hill. | Revise traffic signal and pavement markings. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003E | Region B | HSIP, T(M) |  |  |  |  | 2025 | 102000 |  |  | 102000 | UNDER CONSTRUCTION.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | BO-2403 | Division 3 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Locations in Division 3 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | R-5783 | Division 3 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Various locations in Division 3. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | BO-2603 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3 | Construct safety improvements. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | HS-2003 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Construct safety improvement. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703 | [11 empty] | IN PROGRESS
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Construct safety improvement. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703DIV | Division 3 | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 376000 |  |  | 406000
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Construct safety improvement. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703REG | Region B | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 376000 |  |  | 406000
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Construct safety improvement. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703SW | Statewide Mobility | HSIP, T(M) | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Construct safety improvement. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5803
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Construct safety improvements. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | HS-2403 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018DIV | Division 3 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018REG | Region B | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO | W-5203 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Various locations in Division 3 | Safety Improvements. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | HS-2603 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Locations in Division 3. | Implementation of traffic separation study and closures in Division 3. |  | Rail | Rail-Highway Grade Crossing Closure | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | RC-2003 | Division 3 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Locations in Division 3. | Construct highway-rail grade crossing safety improvements in Division 3. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | RX-2003 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Locations in Division 3. | Construct highway-rail grade crossing safety improvements in Division 3. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | RX-2403 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | Various | NCDOT | Locations in Division 3. | Construct highway-rail grade crossing safety improvements in Division 3. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | RX-2603 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Duplin, Pender | I-40 | NCDOT | Duplin County line (mile marker 360) to west of US 117 (mile marker 390). | Rehabilitate bridge and pavement. | 35.89 | Highway | Interstate Maintenance | 3 | Eastern Carolina RPO, Cape Fear RPO | I-5940 | Statewide Mobility | BGIM |  |  |  |  | 2019 | 29576000 |  |  | 29576000 | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION.
Duplin, Sampson | US 117 (Future I-785) | NCDOT | I-40 in Sampson County to Wayne County line. | Install guardrail. | 6.95 | Highway | Safety | 3 | Eastern Carolina RPO, Mid-Carolina RPO | HS-2003AH | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 507000 |  |  | 507000
Duplin, Sampson | Various | NCDOT | Routes in Division 3. | Install pavement markings. |  | Highway | Safety | 3 | Eastern Carolina RPO, Mid-Carolina RPO | HS-2003B | Division 3 | HSIP, T(M) |  |  |  |  | 2021 | 3432000 |  |  | 3432000 | UNDER CONSTRUCTION.
Duplin, Sampson | US 117 (Future I-795) | NCDOT | I-40 to SR 1006 (West Trade Road). | Upgrade roadway to interstate standards, partially on new location. | 5.31 | Highway | STI (Prioritization) | 3 | Eastern Carolina RPO, Mid-Carolina RPO | U-3125A | Not Funded | NHP, T(M) | NOT FUNDED | 7300000 | NOT FUNDED | 1200000 | NOT FUNDED | 219400000 | NOT FUNDED |  | 227900000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
Durham | Carpenter Fletcher Road | DURHAM | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Bike & Ped | Locally Selected | 5 | Triangle West TPO | U-4726HO | Division 5 | BGANY, L(M), TADA | 2026 | 27000 |  |  | 2026 | 8252000 | 2023 | 10000 | 8289000
Durham | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | DURHAM | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Bike & Ped | Locally Selected | 5 | Triangle West TPO | BL-0028 | Division 5 | BGDA, CMAQ, L, L(M) |  |  |  |  | 2026 | 1217000 | 2024 | 175000 | 1392000
Durham | SR 1321 (Hillandale Road) | DURHAM | I-85 to NC 147 (Durham Freeway) in Durham | Install pedestrian improvements. |  | Bike & Ped | Locally Selected | 5 | Triangle West TPO | U-4726HN | Division 5 | BGDA, L |  |  |  |  | 2026 | 5244000 |  |  | 5244000
Durham | SR 1443 (Horton Road) | DURHAM | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Bike & Ped | Locally Selected | 5 | Triangle West TPO | BL-0063 | Exempt | BGDA, CMAQ, L(M) | 2028 | 571000 |  |  | 2029 | 924000 | 2024 | 1205000 | 2700000
Durham | SR 1945 (South Alston Avenue) | DURHAM | SR 1171 (Riddle Road) to Capps Street in Durham | Construct sidewalk. | 0.44 | Bike & Ped | Locally Selected | 5 | Triangle West TPO | C-5183B | Exempt | BGDA, CMAQ, L(M), TADA |  |  |  |  | 2023 | 1795000 |  |  | 1795000 | UNDER CONSTRUCTION
Durham | SR 1999 (Davis Drive) | RESEARCH TRIANGLE PARK | I-40 to SR 1121 (Cornwallis Road) | Reconstruct multi-use path. | 0.63 | Bike & Ped | Locally Selected | 5 | Triangle West TPO | BL-0152 | Division 5 | L(M), TADA |  |  |  |  | 2026 | 1211000 | 2025 | 10000 | 1221000
Durham | Various | DURHAM | Locations in Durham | Construct sidewalks. |  | Bike & Ped | Locally Selected | 5 | Triangle West TPO | C-5183 | Division 5
Durham | Bryant Bridge North / Goose Creek West Trail | DURHAM | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5720 | Division 5 | HP, L(M), TAANY | 2026 | 1800000 | 2026 | 1100000 | 2027 | 4600000 |  |  | 7500000 | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200.
Durham | Durham Rail Trail | DURHAM | Pettigrew Street to Avondale Drive in Durham | Construct multi-use trail on former rail corridor. | 1.75 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5904 | Division 5 | BGDA, DP, L(M), TAANY, TADA |  |  |  |  | 2026 | 20800000 |  |  | 20800000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT
Durham | Lasalle Street | DURHAM | Kangaroo Drive to Sprunt Avenue in Durham | Construct sidewalks on both sides from Kangaroo Drive to US 70 Business (Hillsborough Road) and on one side from Hillsborough Road to Sprunt Avenue. | 0.69 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5703 | Division 5 | L(M), TAANY | 2022 | 515000 |  |  | 2026 | 1800000 |  |  | 2315000 | RIGHT-OF-WAY IN PROGRESS
Durham | NC 157 / SR 1322 (Guess Road) | DURHAM | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5834 | Division 5 | L, L(M), TAANY | 2026 | 204000 | 2026 | 420000 | 2030 | 9701000 |  |  | 10325000
Durham | NC 54 | DURHAM | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5708 | Division 5 | L(M), SRTS, TAANY | 2021 | 177000 |  |  | 2025 | 1100000 |  |  | 1277000 | RIGHT-OF-WAY IN PROGRESS
Durham | NC 55 (Apex Highway) | DURHAM | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5835 | Division 5 | L(M), TAANY | 2030 | 350000 | 2030 | 250000 | 2031 | 10600000 | 2023 | 105000 | 11305000
Durham | Raynor Street | DURHAM | North Miami Boulevard to North Hardee Street in Durham | Construct sidewalk on one side of street. | 0.35 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5704 | Division 5 | L(M), TAANY | 2022 | 169000 |  |  | 2025 | 800000 |  |  | 969000 | RIGHT-OF-WAY IN PROGRESS
Durham | Third Fork Creek Trail | DURHAM | Southern Boundaries Park to American Tobacco Trail in Durham | Construct shared use path and sidewalks, and install beacon at SR 1158 (Cornwallis Road) crossing. | 1.6 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5837 | Division 5 | L(M), TAANY | 2026 | 980000 |  |  | 2027 | 5800000 |  |  | 6780000
Durham | US 501 Bypass (North Duke Street) | DURHAM | Murray Avenue to US 501 Business (North Roxboro Road) in Durham | Construct sidewalk on east side to fill in existing gaps. | 2.42 | Bike & Ped | STI (Prioritization) | 5 | Triangle West TPO | EB-5715 | Division 5 | L(M), TAANY | 2021 | 296000 |  |  | 2026 | 3400000 |  |  | 3696000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM
Durham | SR 1158 (Cornwallis Road) | DURHAM | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Bike & Ped | Transition | 5 | Triangle West TPO | U-4724 | Pre-STI (Transition) | BGANY, BGDA, L(M) | 2024 | 2400000 |  |  | 2026 | 12400000 |  |  | 14800000 | RIGHT-OF-WAY IN PROGRESS
Durham | SR 1317 (Morreene Road) | DURHAM | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Bike & Ped | Transition | 5 | Triangle West TPO | C-4928 | Division 5 | BGANY, BGDA, CMAQ, L(M) | 2023 | 1338000 |  |  | 2026 | 13000000 | 2015 | 994000 | 15332000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS
Durham | US 15 / US 501 Northbound | NCDOT | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Triangle West TPO | B-5674 | Statewide Mobility | BFP, T(M) | 2027 | 8400000 |  |  | 2030 | 36800000 |  |  | 45200000
Durham | SR 1004 (Old Oxford Road) | NCDOT | First Avenue (Merck Driveway) | Construct right turn lane. | 0.1 | Highway | Economic Development | 5 | Triangle West TPO | HE-0007A | Division 5 | T |  |  |  |  | 2026 | 165000 | 2023 | 25000 | 190000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
Durham | SR 1004 (Old Oxford Road); SR 1794 (Teknika Parkway); SR 2635 (International Drive) | NCDOT | North of Redmill Road; SR 1632 (Red Mill Road) intersection; End of road to SR 1004 (Old Oxford Road). | Construct access road and intersection improvements. |  | Highway | Economic Development | 5 | Triangle West TPO | HE-0007 | Division 5 | [10 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
Durham | SR 1631 (Snow Hill Road) | NCDOT | SR 1004 (Old Oxford Road) | Construct a left turn lane and signalize intersection. | 0.5 | Highway | Economic Development | 5 | Triangle West TPO | HE-0007D | Division 5 | T | 2026 | 50000 | 2026 | 75000 | 2027 | 700000 | 2025 | 200000 | 1025000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
Durham | SR 1794 (Teknika Parkway) | NCDOT | SR 1632 (Red Mill Road) | Construct roundabout. | 0.5 | Highway | Economic Development | 5 | Triangle West TPO | HE-0007B | Division 5 | T | 2024 | 195000 |  |  | 2026 | 815000 | 2023 | 90000 | 1100000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS.
Durham | SR 2635 (International Drive) | NCDOT | SR 1004 (Old Oxford Road) to new location | Construct new lanes. | 0.49 | Highway | Economic Development | 5 | Triangle West TPO | HE-0007C | Division 5 | T | [6 empty] | 2023 | 600000 | 600000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
Durham | I-40 | NCDOT | US 15 / US 501 to east of NC 147. | Rehabilitate pavement. | 9.24 | Highway | Interstate Maintenance | 5 | Triangle West TPO | I-5993 | Statewide Mobility | NHPIM |  |  |  |  | 2026 | 50700000 |  |  | 50700000 | TO BE LET WITH I-5994
Durham | I-85 | NCDOT | Orange County line to US 15 / US 501 in Durham. | Rehabilitate pavement. | 2.49 | Highway | Interstate Maintenance | 5 | Triangle West TPO | I-5941 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2024 | 13489000 |  |  | 13489000
Durham | I-885 | NCDOT | I-40 to 0.4 miles north of TW Alexander Drive. | Rehabilitate pavement. | 2.28 | Highway | Interstate Maintenance | 5 | Triangle West TPO | HI-0023 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2024 | 4363000 |  |  | 4363000
Durham | SR 1121 (Cornwallis Road) |  | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Triangle West TPO | HN-0014 | Exempt | CMAQ, HF(M) | 2026 | 20000 |  |  | 2027 | 870000 | 2025 | 248000 | 1138000
Durham | SR 1306 (Erwin Road) |  | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Triangle West TPO | HN-0013 | Exempt | CMAQ, T(M) | 2026 | 120000 |  |  | 2027 | 1200000 | 2025 | 258000 | 1578000
Durham | Durham | DURHAM | Bridge 310246 - Pettigrew Street over Campus Drive; bridge 310280 - Ramseur Street over South Roxboro Street. | Conduct Planning and Environmental Linkages (PEL) study for the replacement of two bridges. |  | Highway | Other | 5 | Triangle West TPO | HO-0026 | Exempt | DP, O(M) | [6 empty] | 2025 | 625000 | 625000 | "DP" FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM (BIP) GRANT AWARD AND "O(M)" FUNDS REPRESENT AN IN-KIND MATCH.
Durham | Durham | NCDOT | I-85, US 70, and possibly I-40. | Construct ev charging stations. |  | Highway | Other | 5 | Triangle West TPO | HO-0017 | Exempt | DP, L(M) |  |  |  |  | 2026 | 6080000 |  |  | 6080000 | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT
Durham | Durham | NCDOT | Various locations in the City of Durham. | Install ev charging equipment to support equitable electrification. |  | Highway | Other | 5 | Triangle West TPO | HO-0022 | Exempt | DP, L |  |  |  |  | 2026 | 5000000 |  |  | 5000000 | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT
Durham | Various | DURHAM | Locations in Durham | Design and install pedestrian and vehicle wayfinding signage for points of interest and parking. |  | Highway | Other | 5 | Triangle West TPO | C-5605H | Exempt | CMAQ, L(M) |  |  |  |  | 2024 | 984000 |  |  | 984000
Durham | I-40 | NCDOT | Orange County line to NC 147 (Durham Freeway / Triangle Expressway) in Durham | Widen roadway | 10.626 | Highway | Pre-STI (Historic) | 5 | Triangle West TPO | I-3306B | [11 empty] | COMPLETE
Durham | NC 157 (Guess Road) | NCDOT | Durham municipal limits to Orange County line. | Install long-life pavement markings. |  | Highway | Safety | 5 | Triangle West TPO | HS-2405B | Region C | HSIP, T(M) |  |  |  |  | 2025 | 223000 |  |  | 223000 | UNDER CONSTRUCTION
Durham | NC 54 | NCDOT | NC 55 intersection in Durham. | Install concrete pedestrian refuge islands in all quadrants. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005C | Region C | HSIP, T(M) |  |  |  |  | 2026 | 75000 |  |  | 75000
Durham | NC 54 (Miami Boulevard) | NCDOT | SR 1978 (Hopson Road) intersection | Construct Multi-use path |  | Highway | Safety | 5 | Triangle West TPO | HS-2405AH | Division 5 | HSIP |  |  |  |  | 2026 | 150000 |  |  | 150000
Durham | NC 55 (Alston Avenue) | NCDOT | SR 1670 (Geer Street) intersection in Durham. | Revise traffic signal and install pedestrian signal heads. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005M | Region C | HSIP, T(M) |  |  |  |  | 2026 | 62000 |  |  | 62000
Durham | NC 751 (Academy Road) | NCDOT | Pinecrest Road intersection | Install pedestiran and bicycle improvements. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2405AY | Region C | HSIP |  |  |  |  | 2026 | 60000 |  |  | 60000
Durham | NC 98 | NCDOT | SR 1815 (Mineral Springs Road) intersection. | Construct right turn lanes and sidewalk. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005S | Region C | HSIP, T(M) |  |  |  |  | 2026 | 1200000 |  |  | 1200000 | RIGHT-OF-WAY IN PROGRESS
Durham | SR 1110 (Barbee Chapel Road) | NCDOT | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2405I | Division 5 | HSIP, T(M) | 2026 | 2000 | 2026 | 2000 | 2026 | 120000 |  |  | 124000
Durham | SR 1303 (Pickett Road) | NCDOT | SR 1116 (Garrett Road) / Luna Lane intersection in Durham. | Install traffic signal. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005D | Division 5 | HSIP, T(M) | 2024 | 2000 |  |  | 2024 | 40000 |  |  | 42000 | UNDER CONSTRUCTION
Durham | SR 1327 (Gregson Street) | NCDOT | Knox Street intersection. | Install traffic signal. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005L | Division 5 | HSIP, T(M) |  |  | 2026 | 16000 | 2026 | 110000 |  |  | 126000
Durham | SR 1973 (Page Road) | NCDOT | Churchill Hall / Arby's / McDonalds Driveway. | Install directional crossover. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005H | Division 5 | HSIP, T(M) |  |  |  |  | 2025 | 20000 |  |  | 20000
Durham | US 15 / US 501 Business | NCDOT | NC 751 (Academy Road) interchange in Durham. | Install guardrail. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2005E | Region C | HSIP, T(M) |  |  |  |  | 2025 | 176000 |  |  | 176000 | UNDER CONSTRUCTION
Durham | US 501 (Roxboro Road) | NCDOT | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2405P | Region C | HSIP, T(M) | 2026 | 5000 | 2026 | 5000 | 2027 | 123000 |  |  | 133000
Durham | US 501 Business (Roxboro Street) | NCDOT | Maynard Avenue intersection | Install traffic signal with pedestrian accommodations and connect to the Durham signal system. | 0.5 | Highway | Safety | 5 | Triangle West TPO | HS-2405M | Region C | HSIP, T(M) | 2026 | 24000 |  |  | 2026 | 178000 |  |  | 202000
Durham | US 501 Business (Roxboro Street) | NCDOT | SR 1443 (Horton Road) / SR 1641 (Denfield Street) intersection. | Construct left turn lanes. | 0.5 | Highway | Safety | 5 | Triangle West TPO | W-5705AI | Region C | HSIP, T(M) |  |  |  |  | 2026 | 1700000 |  |  | 1700000
Durham | I 40 | NCDOT | NC 54 interchange | Construct interchange improvements, including upgrade of NC 54 from east of Little Creek to east of I-40. | 1 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774F | Statewide Mobility | NHP, T(M) | 2030 | 117800000 | 2030 | 5500000 | 2033 | 156100000 |  |  | 279400000
Durham | I-40 | NCDOT | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Highway | STI (Prioritization) | 5 | Triangle West TPO | I-5707 | Statewide Mobility | NHP, T(M) | 2025 | 800000 | 2025 | 190000 | 2027 | 9300000 |  |  | 10290000 | RIGHT-OF-WAY IN PROGRESS
Durham | I-885 | NCDOT | I-40 to NC 147 in Durham. | Add lanes, rehabilitate pavement, and prioritize the addition of transit accommodations. | 4.82 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5934 | Statewide Mobility | NHP, T(M) | 2028 | 10000 | 2028 | 300000 | 2030 | 142300000 |  |  | 142610000
Durham | NC 54 | NCDOT | East of I-40 to east of NC 751 | Upgrade roadway corridor. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774G | Not Funded | T | NOT FUNDED | 1800000 | NOT FUNDED | 800000 | NOT FUNDED | 16901000 | NOT FUNDED |  | 19501000
Durham | NC 54 | NCDOT | East of NC 751 to east of SR 1118 (Fayetteville Road) | Upgrade roadway corridor. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774H | Not Funded | T | NOT FUNDED | 5900000 | NOT FUNDED | 726000 | NOT FUNDED | 17999000 | NOT FUNDED |  | 24625000
Durham | NC 54 | NCDOT | East of SR 1106 (Barbee Road) to NC 55 | Upgrade roadway corridor. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774J | Not Funded | T | NOT FUNDED | 3200000 | NOT FUNDED | 420000 | NOT FUNDED | 17100000 | NOT FUNDED |  | 20720000
Durham | NC 54 | NCDOT | East of SR 1110 (Barbee Chapel Road) to east of Little Creek | Upgrade roadway corridor. | 1.64 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774C | Not Funded | T | NOT FUNDED | 610000 | NOT FUNDED | 4400000 | NOT FUNDED | 23001000 | NOT FUNDED |  | 28011000
Durham | NC 54 | NCDOT | East of SR 1118 (Fayetteville Road) to east of SR 1106 (Barbee Road) | Upgrade roadway corridor. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774I | Not Funded | T | NOT FUNDED | 2500000 | NOT FUNDED | 617000 | NOT FUNDED | 12300000 | NOT FUNDED |  | 15417000
Durham | NC 54 | NCDOT | Falconbridge Road intersection | Convert at-grade intersection to interchange. | 0.5 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774D | [11 empty] | SCOPE INCLUDED IN U-5774F
Durham | NC 54 | NCDOT | SR 1110 (Farrington Road) intersection | Convert at-grade intersection to grade separation. | 0.5 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5774E | [11 empty] | SCOPE INCLUDED IN U-5774F
Durham | NC 55 | NCDOT | Meridian Parkway to I-40 interchange in Durham. | Construct third southbound lane, upgrade ramp terminals, and include bike-ped facilities. | 2 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-6118 | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 350000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6800000 |  |  | 7550000
Durham | NC 55 (Apex Highway) | NCDOT | SR 1121 (Cornwallis Road) intersection | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 5 | Triangle West TPO | HP-0018 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | 3000000
Durham | NC 751 (Hope Valley Road) | NCDOT | SR 1183 (University Drive) intersection in Durham. | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5745 | Region C | T | 2019 | 435000 |  |  | 2019 | 1313000 | 2019 | 624000 | 2372000 | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT-OF-WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
Durham | NC 98 (Holloway Street) | NCDOT | SR 1838 (Junction Road) to west of SR 1919 (Lynn Road) | Construct safety improvements and widen to add median. Include shared use paths on both sides of the roadway, transit stop improvements, and traffic signals where needed. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-6120A | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9451000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17800000 |  |  | 28951000
Durham | NC 98 (Holloway Street) | NCDOT | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-6120B | Division 5 | HSIP, L, T | 2028 | 700000 | 2028 | 0 | 2030 | 9145000 |  |  | 9845000 | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE).
Durham | NC 98 (Holloway Street) | NCDOT | SR 1938 (Junction Road) to SR 1919 (Lynn Road) in Durham. | Construct safety improvements and widen to add median, bicycle lanes, sidewalks, transit stop improvements, and traffic signals where needed. | 0.83 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-6120
Durham | SR 1978 (Hopson Road) | NCDOT | East of SR 1999 (Davis Drive) to NC 54 | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-4716D | Not Funded | O | NOT FUNDED | 1126000 | NOT FUNDED |  | NOT FUNDED | 3160000 | NOT FUNDED |  | 4286000
Durham | US 15 / US 501 | NCDOT | SR 1116 (Garrett Road) in Durham. | Upgrade at-grade intersection to an interchange. | 1 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5717 | Statewide Mobility | NHP, T(M) |  |  |  |  | 2030 | 62200000 |  |  | 62200000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067
Durham | Various | NCDOT | Locations in the City of Durham. | Upgrade ITS / signal system. |  | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5968 | Region C | T |  |  |  |  | 2021 | 13000000 |  |  | 13000000 | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Durham | Woodcroft Parkway Extension | DURHAM | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Highway | STI (Prioritization) | 5 | Triangle West TPO | U-5823 | Division 5 | BGANY, L(M) | 2026 | 1400000 | 2026 | 1800000 | 2027 | 6000000 |  |  | 9200000 | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM
Durham | NC 55 (Alston Avenue) | NCDOT | NC 147 (Durham Freeway) to US 70 Business / NC 98 (Holloway Street) in Durham. | Widen to four-lane divided facility from NC 147 to Main Street and replace Norfolk Southern Railroad bridges. Modernize from Main Street to US 70 Business / NC 98 (Holloway Street) | 0.9 | Highway | Transition | 5 | Triangle West TPO | U-3308 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Durham | New Route | NCDOT | East End Connector, NC 147 (Durham Freeway) to north of NC 98 in Durham. | Construct four-lane divided freeway with auxiliary lanes, part on new location. | 2.52 | Highway | Transition | 5 | Triangle West TPO | U-0071 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Durham | SR 2220 (Old Chapel Hill Road) | NCDOT | SR 1113 (Pope Road) to SR 1116 (Garrett Road). | Construct bicycle, pedestrian, and transit improvements and construct roundabout. | 2.63 | Highway | Transition | 5 | Triangle West TPO | EB-4707B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Durham | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Purchase paratransit vehicles, bus refurbishment, and bus shelters. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TA-5019A | Division 5 | 5339(b), S | [6 empty] | 2025 | 5440000 | 5440000 | IN PROGRESS BY CHAPEL HILL TRANSIT
Durham | GoDurham |  | Fayetteville Road Transit Corridor | Construct access and bus stop improvements. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TC-0046 | Public Transit | 5339(b), L(M) |  |  |  |  | 2025 | 19384000 |  |  | 19384000
Durham | GoDurham |  | Systemwide. | GoDurham transit corridors. Improvement of Roxboro Transit Corridor from Denfield Street to Pettigrew Street, Durham access, stop improvements, and bus shelters. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TG-0031 | Public Transit | 5307, L, T |  |  |  |  | 2026 | 1590000 |  |  | 1590000
Durham | GoDurham | GODURHAM | Systemwide | Purchase replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TA-4923 | Division 5 | 5307, 5339, L | [6 empty] | 2021 | 12183000 | 12183000 | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY
Durham | GoDurham | GODURHAM | Various locations | Acquisition Of Six (6) Electric Transit Buses. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TM-0043 | Public Transit | 5339(b), L | [6 empty] | 2026 | 21283000 | 21283000
Durham | GoDurham | GODURHAM | Various locations | Funding for planning assistance -5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TP-5108 | Public Transit | 5303, L, S | [6 empty] | 2020 | 560000 | 560000 | FUNDS AUTHORIZED IN PROGRESS
Durham | GoTriangle | GO TRIANGLE | NC 98 (Holloway Street) transit corridor | Construct access and bus stop improvements. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Triangle West TPO | TD-5294 | Public Transit | DP, L | [6 empty] | 2025 | 17385000 | 17385000 | UNDER CONSTRUCTION BY GO TRIANGLE
Durham | GoDurham | GODURHAM | Systemwide. | Purchase battery electric buses. |  | Public Transportation (Transit) | Locally Selected | 5 | Triangle West TPO | TL-0065 | Division 5
Durham | GoTriangle |  | Various locations | This transit project will improve 13 stops on the Go triangle 805 coridor on Woodcroft parkway plus two stops on NC 54. 12 stops will add ADA compliant landing pad and continuous pedestrian connectivity to the existing sidewalk/sidepath netwok. |  | Public Transportation (Transit) | Locally Selected | 5 | Triangle West TPO | TL-0052 | Public Transit | BGDA, L(M) |  |  |  |  | 2024 | 782000 |  |  | 782000
Durham | GoTriangle |  | Various locations | The NC 54 Falconbridge construction project aims to address critical transit access and transit operations safety concerns along NC 54 in the Falconbridge area in Southwestern Durham County, thereby increasing transit ridership and reducing emissions. |  | Public Transportation (Transit) | Locally Selected | 5 | Triangle West TPO | TL-0027 | Public Transit | CMAQ, L(M) |  |  |  |  | 2025 | 940000 |  |  | 940000
Durham | GoTriangle | GOTRIANGLE | Systemwide. | Purchase two 40 foot busses. |  | Public Transportation (Transit) | Locally Selected | 5 | Triangle West TPO | TL-6111 | Division 5 | BGDA, L, L(M) | [6 empty] | 2025 | 1360000 | 1360000
Durham | Triangle Mobility hub | GOTRIANGLE | Various locations | Purchase battery electric bus. |  | Public Transportation (Transit) | Locally Selected | 5 | Triangle West TPO | TL-0064 | Exempt | BGDA, DP, L, L(M) |  |  |  |  | 2026 | 34500000 | 2025 | 17500000 | 52000000 | "DP" FUNDING REFLECTS RAISE GRANT AWARD.
Durham | GoDurham | GODURHAM | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Triangle West TPO | TO-5130 | Public Transit | L, SMAP | [6 empty] | 2025 | 28060000 | 28060000 | FUNDS AUTHORIZED IN PROGRESS
Durham | GoDurham | GODURHAM | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Triangle West TPO | TG-4738A | Public Transit | 5307, L | [6 empty] | 2023 | 22500000 | 22500000 | FUNDS AUTHORIZED IN PROGRESS
Durham | GoDurham | GODURHAM | Systemwide | Purchase service for passengers who are eligible for ADA services outside of the 3/4 mile ADA service area of GoDurham. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Triangle West TPO | TM-0067 | Public Transit | 5310, L | [6 empty] | 2025 | 500000 | 500000
Durham | GoDurham | GODURHAM | Systemwide. | Operating expenses for GoDurham fixed route. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Triangle West TPO | TM-0060 | Public Transit | 5307, L | [6 empty] | 2025 | 36182000 | 36182000
Durham | GoDurham | CITY OF DURHAM | Systemwide | Fund planning assistance for GoDurham. |  | Public Transportation (Transit) | Planning | 5 | Triangle West TPO | TU-0019 | Public Transit | 5303, L, S | [6 empty] | 2025 | 1108000 | 1108000
Durham | GoDurham | GODURHAM | Durham Station | Improvements to Durham station to expand equitable access to transit, improve station amenities, increase connection to employment, health care and educational opportunities and construct 8 bus bays, redesigned bus lanes and placed new pavement. |  | Public Transportation (Transit) | Planning | 5 | Triangle West TPO | TU-0013 | Public Transit | 5339(b), L | [6 empty] | 2023 | 34195000 | 34195000
Durham | GoDurham | GODURHAM | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Triangle West TPO | TG-4738 | Public Transit | 5307, L | [6 empty] | 2023 | 5594000 | 5594000 | FUNDS AUTHORIZED IN PROGRESS
Durham | GoDurham | GODURHAM | Systemwide. | Purchase 18 battery electric buses. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Triangle West TPO | TG-0029 | Public Transit | 5339(b), L | [6 empty] | 2026 | 21282000 | 21282000
Durham | GoDurham | GODURHAM | Systemwide. | Purchase replacement light transit vehicles for godurham access. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Triangle West TPO | TG-0030 | Public Transit | 5339(b), L | [6 empty] | 2025 | 2726000 | 2726000
Durham | SR 1978 (Hopson Road) | NCDOT | 0.2 miles west of NC 54 | Construct railroad grade separation and shift rail line. |  | Rail | Other | 5 | Triangle West TPO | U-4716A | [11 empty] | PROJECT COMPLETE
Durham | SR 1980 (Church Street) | NCDOT | 0.1 miles west of NC 54 | Realign and close crossing 734748M of the Norfolk Southern NC Railroad. |  | Rail | Pre-STI (Historic) | 5 | Triangle West TPO | U-4716B | Pre-STI (Transition) | [10 empty] | PROJECT COMPLETE
Durham | Norfolk Southern H Line | NCDOT | Crossing 734742W at SR 1121 (Cornwallis Road) in Durham. | Construct grade separation. |  | Rail | STI (Prioritization) | 5 | Triangle West TPO | P-5717 | Region C | T | 2022 | 4378000 | 2022 | 1878000 | 2026 | 41600000 |  |  | 47856000 | RIGHT-OF-WAY IN PROGRESS.
Durham | Norfolk Southern H Line | NCDOT | East Durham between CP Nelson and CP East Durham. | Construct East Durham railroad safety improvements. Project will straighten existing railroad curvature between CP Nelson and CP East Durham and includes a combination of grade separations and closures at Ellis Road South End (734737A), Glover Road (73473 | 6.9 | Rail | STI (Prioritization) | 5 | Triangle West TPO | P-5706 | Statewide Mobility | T | 2023 | 9328000 |  |  | 2030 | 66000000 |  |  | 75328000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS.
Durham, Orange | SR 2220 (Old Chapel Hill Road) SR 1838 (Old Durham Road) | DURHAM | US 15 / US 501 in Orange County to SR 1116 (Garrett Road) in Durham County | Construct bicycle, pedestrian, and transit improvements and roundabout. | 2.7 | Bike & Ped | Pre-STI (Historic) | 5, 7 | Triangle West TPO | EB-4707 | Pre-STI (Transition)
Durham, Orange | Central Pines Regional Council |  | Central Pines | Transportation Demand Management Program For Organizations In Triangle West TPO |  | Highway | NCDOT Selected (Other Selection Process) | 5, 7 | Triangle West TPO | HN-0026B | Exempt | CMAQ, L(M) | [6 empty] | 2024 | 3065000 | 3065000
Durham, Orange | NC 54 | NCDOT | US 15 / US 501 in Chapel Hill to NC 55 in Durham. | Upgrade roadway corridor. | 8.4 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | U-5774 | [11 empty] | PARTS A THROUGH F ON EXPANDED NHS
Durham, Orange | GoTriangle | GOTRIANGLE | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Triangle West TPO | TS-5119 | Public Transit | 5307, L | [6 empty] | 2020 | 156000 | 156000 | FUNDS AUTHORIZED IN PROGRESS
Durham, Orange | GoTriangle | GOTRIANGLE | Systemwide | Purchase expansion bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Triangle West TPO | TA-5123B | Public Transit | 5307, L, S | [6 empty] | 2020 | 4863000 | 4863000 | FUNDS AUTHORIZED IN PROGRESS
Durham, Orange | GoTriangle | GOTRIANGLE | Systemwide | Purchase replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Triangle West TPO | TA-4818B | Public Transit | 5307, 5309, 5339, L, L(M), S | [6 empty] | 2024 | 17130000 | 17130000
Durham, Orange | GoTriangle | GOTRIANGLE | Systemwide | Funding for planning assistance |  | Public Transportation (Transit) | Planning | 5, 7 | Triangle West TPO | TP-4732A | Public Transit | 5307, L, S | [6 empty] | 2020 | 6642000 | 6642000 | FUNDS AUTHORIZED IN PROGRESS
Durham, Orange | GoTriangle | GO TRIANGLE | Route 800. | Purchase 3 vehicles, construct stop and access improvements, and improve existing facility at Southpoint Transit Center. |  | Public Transportation (Transit) | STI (Prioritization) | 5, 7 | Triangle West TPO | TP-0001 | Region C, D | BGANY, L |  |  |  |  | 2030 | 14500000 |  |  | 14500000
Durham, Orange | GoTriangle | GO TRIANGLE | US 15 / US 501 from Durham to Carrboro. | Construct bus rapid transit lanes. |  | Public Transportation (Transit) | STI (Prioritization) | 5, 7 | Triangle West TPO | TP-0004 | Region C, D | BGANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40000000 |  |  | 40000000
Durham, Orange, Chatham | Various | NCDOT | Locations in Triangle West Transportation Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 5, 7, 8 | Triangle West TPO | U-6219 | Division 5, 7, 8 | TADA |  |  |  |  | 2031 | 3803000 |  |  | 3803000
Durham, Orange, Chatham | Various | NCDOT | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Bike & Ped | Locally Selected | 5, 7, 8 | Triangle West TPO | U-4726 | Division 5, 7, 8 | BGANY, BGDA, L(M) | 2021 | 1909000 |  |  | 2021 | 11766000 |  |  | 13675000 | IN PROGRESS
Durham, Orange, Chatham | Various | NCDOT | Triangle West Transportation Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 5, 7, 8 | Triangle West TPO | HL-0094 | Exempt | CRPDA, L(M) |  |  |  |  | 2025 | 2295000 |  |  | 2295000
Durham, Orange, Chatham | Various | NCDOT | Triangle West Transportation Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 5, 7, 8 | Triangle West TPO | U-5023 | Division 5, 7, 8 | BGANY, BGDA |  |  |  |  | 2028 | 34650000 |  |  | 34650000 | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726.
Durham, Orange, Chatham | Various. | NCDOT | Triangle West Transportation Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 5, 7, 8 | Triangle West TPO | U-4727 | Division 5, 7, 8 | BGDA, L(M) | [6 empty] | 2024 | 27694000 | 27694000 | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT
Durham, Orange, Chatham | Various | NCDOT | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Highway | Other | 5, 7, 8 | Triangle West TPO | C-5605 | Exempt | CMAQ, L(M) | 2020 | 447000 |  |  | 2020 | 5490000 | 2020 | 2051000 | 7988000 | IN PROGRESS
Durham, Person | Durham to Roxboro Rail Trail | NCDOT | NC 55 (Avondale Drive) in Durham to Patterson Drive / Somerset Church Road in Roxboro | Construct greenway. |  | Bike & Ped | Locally Selected | 5 | Triangle West TPO, Kerr-Tar RPO | BL-0168 | Division 5 | BGDA, CMAQ, L, L(M), S(M) | 2026 | 14240000 | [6 empty] | 14240000
Durham, Person | US 501 (Roxboro Road / Durham Road) | NCDOT | SR 1002 (Mason Road); SR 1631 (Snow Hill Road) in Durham County to 1,100 feet south of SR 1147 (Bessie Daniel Road) in Person County, excluding five lane sections. | Install rumble stripes. | 16 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AD | Region C | HSIP, T(M) |  |  |  |  | 2026 | 116000 |  |  | 116000
Durham, Wake | GoTriangle | CAPITAL AREA TRANSIT | Durham to North Hils in Raleigh. | Construct bus rapid transit lanes and purchase 24 vehicles. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO, Triangle West TPO | TP-0002 | Region C | BGANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000000 |  |  | 100000000
Durham, Wake | GoTriangle | GO TRIANGLE | DRX Route. | Purchase two vehicles and install electric charging infrastructure. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO, Triangle West TPO | TP-0003 | Region C | BGANY, L |  |  |  |  | 2027 | 3000000 |  |  | 3000000
Durham, Wake | Norfolk-Southern Railroad / NC Railroad | NCDOT | Clegg to Nelson | Construct passing siding. |  | Rail | Other | 5 | Capital Area MPO, Triangle West TPO | U-4716C | [11 empty] | PROJECT COMPLETE
Durham, Wake | Various | NCDOT | Routes and Norfolk Southern Railroad / North Carolina Railroad in Durham and Morrisville. South of I-40 to north of McCrimmon Parkway. | Construct a grade separation at SR 1978 (Hopson Road), extend Church Street to Hopson Road, close Church Street crossing |  | Rail | Other | 5 | Triangle West TPO, Capital Area MPO | U-4716
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | BO-2405 | Division 5 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Locations in Division 5 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | R-5785 | Division 5 | HF, TA |  |  |  |  | 2023 | 1100000 |  |  | 1100000 | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Various locations in Division 5. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | BO-2605 | Division 5 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | All freeway ramp locations in Division 5 | Bring wrong way driver deterrence markings up to standard. |  | Highway | Safety | 5 | Capital Area MPO, Triangle West TPO, Kerr-Tar RPO | HS-2405L | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 1093000 |  |  | 1093000 | UNDER CONSTRUCTION
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5 | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2005 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5 | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5705DIV | Division 5 | HSIP, T(M) | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5 | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5705REG | Region C | HSIP, T(M) | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5 | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5705SW | Statewide Mobility | HSIP, T(M) | 2020 | 137000 |  |  | 2020 | 720000 |  |  | 857000
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2405 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5705 | [11 empty] | IN PROGRESS; $150K NHP FUNDING APPLIED TO W-5705S.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Construct safety improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5805 | [11 empty] | W-5805B PROJECT DELETED AT REQUEST OF DIVISION; WORK TO BE ACCOMPLISHED UNDER U-6023.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2020
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2020DIV | Division 5 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2020REG | Region C | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2020SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Routes in Division 5. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5205 | [11 empty] | UNDER CONSTRUCTION
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Various locations in Division 5 | Safety Improvements. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | HS-2605 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Locations in Division 5. | Implementation of traffic separation study and closures in Division 5. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | RC-2005 | Division 5 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Locations in Division 5. | Construct highway-rail grade crossing safety improvements in Division 5. |  | Rail | Rail-Highway Grade Crossing Improvement | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | RX-2005 | Division 5 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Locations in Division 5. | Construct highway-rail grade crossing safety improvements in Division 5. |  | Rail | Rail-Highway Grade Crossing Improvement | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | RX-2405 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Durham, Wake, Franklin, Granville, Person, Vance, Warren | Various | NCDOT | Locations in Division 5. | Construct highway-rail grade crossing safety improvements in Division 5. |  | Rail | Rail-Highway Grade Crossing Improvement | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | RX-2605 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe | SR 1164 (Cokey Road); Rex Street | ROCKY MOUNT | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Bike & Ped | Locally Selected | 4 | Rocky Mount Urban Area MPO | BL-0032 | Exempt | CMAQ, L(M) | 2026 | 10000 |  |  | 2026 | 340000 | 2024 | 100000 | 450000
Edgecombe | US 64 West Alternate | TARBORO | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Bike & Ped | Locally Selected | 4 | Upper Coastal Plain RPO | BL-0064 | Exempt | CMAQ, L(M) | 2026 | 51000 |  |  | 2027 | 586000 | 2023 | 134000 | 771000
Edgecombe | East Raleigh Boulevard | ROCKY MOUNT | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5984 | Division 4 | L(M), TA50200 | 2029 | 500000 | 2029 | 100000 | 2031 | 3700000 | 2027 | 300000 | 4600000
Edgecombe | NC 111 / NC 122 | NCDOT | Bridge 320011 over Town Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5655 | Highway Fund | HFB |  |  |  |  | 2021 | 1950000 |  |  | 1950000 | COMPLETE.
Edgecombe | NC 33 | NCDOT | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4933 | Region A | BFP, T(M) | 2027 | 180000 | 2027 | 550000 | 2031 | 18315000 |  |  | 19045000
Edgecombe | NC 97 | NCDOT | Bridge 320087 over Swift Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5671 | Highway Fund | HFB |  |  |  |  | 2021 | 2279000 |  |  | 2279000 | COMPLETE.
Edgecombe | SR 1126 (Faith Baptist Church Road) | NCDOT | Bridge 320064 over Town Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6002 | Highway Fund | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | COMPLETE.
Edgecombe | SR 1243 (Leggett Road) | NCDOT | Bridge 320054 over Tar River. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Rocky Mount Urban Area MPO | BR-0241 | Highway Fund | HFB |  |  |  |  | 2021 | 3600000 |  |  | 3600000 | COMPLETE. PROJECT REPRESENTS HFB 4.R.101 PROJECT.
Edgecombe | SR 1404 (Seven Bridges Road) | NCDOT | Bridges 320003, 320004, and 320005 over Swift Creek. | Replace bridges. | 0.5 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0111 | Division 4 | DP | 2020 | 420000 | 2020 | 56000 | 2021 | 5450000 |  |  | 5926000 | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
Edgecombe | SR 1616 (Sharp Point Road) | NCDOT | Bridge 320035 over Otter Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0112 | Division 4 | DP |  |  |  |  | 2021 | 1112000 |  |  | 1112000 | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
Edgecombe | US 258 | NCDOT | Bridge 320022 over Town Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4931 | Highway Fund | HFB |  |  |  |  | 2021 | 2129000 |  |  | 2129000 | COMPLETE.
Edgecombe | New Route | NCDOT | SR 1252 (Dunbar Road) to SR 1225 (Kingsboro Road). | Construct 2-lane road and improve existing road. | 2.5 | Highway | Economic Development | 4 | Upper Coastal Plain RPO | R-5868 | Division 4 | [10 empty] | UNDER CONSTRUCTION. THIS IN AN ECONOMIC DEVELOPMENT PROJECT FOR TRIANGLE TYRE.
Edgecombe | US 64 (Future I-87) | NCDOT | Bridges 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, and 320326. | Rehabilitate Bridges. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6041A | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION.
Edgecombe | US 64 (Future I-87) | NCDOT | Bridges 320327 and 320328. | Rehabilitate Bridges. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6042A | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 300000 |  |  | 300000 | UNDER CONSTRUCTION.
Edgecombe | US 64 (Future I-87) | NCDOT | NC 33 to Martin County line. | Rehabilitate pavement. | 10.45 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6042 | Statewide Mobility | HP, NHPIM, T(M) |  |  |  |  | 2023 | 19700000 |  |  | 19700000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196.
Edgecombe | US 64 (Future I-87) | NCDOT | SR 1225 (Kingsboro Road) to NC 33. | Rehabilitate pavement. | 10.18 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6041 | Statewide Mobility | HP, NHPIM, T(M) |  |  |  |  | 2023 | 20659000 |  |  | 20659000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196.
Edgecombe | NC 111 | NCDOT | SR 1109 (Fountain Road) | Construct mini-roundabout with lighting. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404L | Region A | HSIP, T(M) |  |  | 2026 | 90000 | 2026 | 635000 |  |  | 725000
Edgecombe | NC 42 / NC 43 | NCDOT | SR 1162 (Sally Jenkins Street) to ECU Health Driveway in Pinetops. | Install pedestrian improvement. | 0.1 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404H | Region A | HSIP, T(M) | 2026 | 50000 |  |  | 2027 | 290000 |  |  | 340000
Edgecombe | NC 43 |  | Northern Pinetops municipal limit to SR 1232 (Meadowbrook Road) | Install 6-inch pavement markings and pavement markers. | 13.7 | Highway | Safety | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | HS-2404N | Region A | HSIP, T(M) |  |  |  |  | 2026 | 172000 |  |  | 172000
Edgecombe | US 64 Business (Raleigh Boulevard) | NCDOT | NC 43 (Fairview Road) intersection in Rocky Mount. | Install pedestrian signal heads. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004AB | Region A | HSIP, T(M) |  |  |  |  | 2024 | 128000 |  |  | 128000
Edgecombe | US 64 Business E (Tarboro Street) |  | NC 97 (Atlantic Avenue/Arlington Street) | Upgrade traffic signal, ramps, and crosswalks and install pedestrian signal heads. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2404M | Region A | HSIP, T(M) |  |  |  |  | 2026 | 152000 |  |  | 152000
Edgecombe | NC 111 (Wilson Street) | NCDOT | US 64 Alternate (Western Boulevard) to NC 122 (McNair Road). | Widen to three lanes. | 2.28 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-4424 | Division 4 | T |  |  |  |  | 2023 | 21645000 |  |  | 21645000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
Edgecombe | SR 1250 (Springfield Road) | NCDOT | US 64 Alternate to SR 1243 (Leggett Road). | Widen to three lanes. | 1.26 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-4762 | Division 4 | T |  |  |  |  | 2019 | 6255000 | 2021 | 1995000 | 8250000 | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Edgecombe | US 258 | NCDOT | SR 1601 (Colonial Road) to US 64. | Widen roadway. | 1.77 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5949 | Division 4 | T | 2030 | 8500000 | 2030 | 2600000 | 2033 | 54000000 |  |  | 65100000
Edgecombe | CSX A Line | CSXT RR | National Gateway Corridor | Improve CSX intermodal terminal and track. |  | Rail | Other | 4 | Rocky Mount Urban Area MPO | P-5711A | Statewide Mobility | T |  |  |  |  | 2020 | 43100000 |  |  | 43100000 | UNDER CONSTRUCTION.
Edgecombe, Halifax | US 258 | NCDOT | Pitt County line to US 64 in Edgecombe County, and Princeville to SR 1102 (Mullin Road) in Halifax County. | Install pavement markings and rumble stripes. | 31.69 | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | HS-2004R | Region A | HSIP, T(M) |  |  |  |  | 2023 | 780000 |  |  | 780000 | UNDER CONSTRUCTION.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | BO-2404 | Division 4 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Locations in Division 4 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | R-5784 | Division 4 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Various locations in Division 4. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bike & Ped | Other | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | BO-2604 | Division 4 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4 | Construct safety improvement. |  | Highway | Safety | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO | W-5704REG | Region A | HSIP, T(M) | 2022 | 30000 |  |  | 2020 | 456000 |  |  | 486000
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4 | Construct safety improvement. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5704DIV | Division 4 | HSIP, T(M) | 2020 | 144000 |  |  | 2022 | 360000 |  |  | 504000
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4 | Construct safety improvement. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5704SW | Statewide Mobility | HSIP, T(M) | 2022 | 40000 |  |  | 2022 | 480000 |  |  | 520000
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Construct safety improvement. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5704 | [11 empty] | IN PROGRESS
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Construct safety improvement. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5804
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Construct safety improvements. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2004 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Construct safety improvements. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2404 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | HS-2019DIV | Division 4 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | HS-2019REG | Region A | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | HS-2019SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2019
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Routes in Division 4. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5204 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Various locations in Division 4 | Safety Improvements. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2604 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Locations in Division 4. | Implementation of traffic separation study and closures in Division 4. |  | Rail | Rail-Highway Grade Crossing Closure | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RC-2004 | Division 4
Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | Various | NCDOT | Locations in Division 4. | Construct highway-rail grade crossing safety improvements in Division 4. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RX-2004 | Division 4 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Wayne, Wilson, Halifax, Nash | Various | NCDOT | Locations in Division 4. | Construct highway-rail grade crossing safety improvements in Division 4. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RX-2404 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Johnston, Wayne, Wilson, Halifax, Nash | Various | NCDOT | Locations in Division 4. | Construct highway-rail grade crossing safety improvements in Division 4. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RX-2604 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Edgecombe, Nash | US 64 Business (Thomas Street) |  | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Bike & Ped | Other | 4 | Rocky Mount Urban Area MPO | BO-2417 | Exempt | HP, L, L(M) | 2026 | 390000 |  |  | 2027 | 5803000 | 2025 | 1248000 | 7441000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198.
Edgecombe, Nash | US 301 Business (Church Street) | ROCKY MOUNT | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5763 | Division 4 | L(M), TA50200 | 2027 | 75000 |  |  | 2028 | 3000000 | 2024 | 200000 | 3275000
Edgecombe, Nash | US 64 (Future I-87) | NCDOT | SR 1603 (Old Carriage Road) to SR 1225 (Kingsboro Road). | Rehabilitate bridge. | 12.63 | Highway | Interstate Maintenance | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | I-6046 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 24006000 |  |  | 24006000 | UNDER CONSTRUCTION.
Edgecombe, Nash | Various | NCDOT | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Highway | Other | 4 | Rocky Mount Urban Area MPO | C-5616 | Exempt | CMAQ, L(M) | 2020 | 116000 |  |  | 2020 | 910000 | 2020 | 348000 | 1374000
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Purchase 4 replacement 25-foot light transit vehicles and 2 replacement 30- foot vehicles. |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Rocky Mount Urban Area MPO | TC-0041 | Public Transit | 5307, L | [6 empty] | 2025 | 2250000 | 2250000
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Purchase 4 replacement 30- foot vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Rocky Mount Urban Area MPO | TC-0039 | Public Transit | 5307, L | [6 empty] | 2026 | 3000000 | 3000000
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Purchase one expansion 25-foot vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Rocky Mount Urban Area MPO | TC-0040 | Public Transit | 5307, L | [6 empty] | 2026 | 188000 | 188000
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Rocky Mount Urban Area MPO | TO-5127 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 6000000 | 6000000 | FUNDS AUTHORIZED IN PROGRESS
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Rocky Mount Urban Area MPO | TG-4785A | Public Transit | 5307, L | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Rocky Mount Urban Area MPO | TG-4785B | Public Transit | 5307, L | [6 empty] | 2020 | 3600000 | 3600000 | FUNDS AUTHORIZED IN PROGRESS
Edgecombe, Nash | Tar River Transit | TAR RIVER TRANSIT | Various locations | Administration. |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Rocky Mount Urban Area MPO | TK-5180 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1170000 | 1170000 | FUNDS AUTHORIZED IN PROGRESS
Edgecombe, Nash | CSX A Line | CSXT RR | National Gateway Corridor | Construct freight rail and intermodal terminal infrastructure (CCX). | 12 | Rail | Other | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | P-5711 | Statewide Mobility
Edgecombe, Nash | CSX A Line | NCDOT | National Gateway Corridor | Construct highway improvements |  | Rail | Other | 4 | Rocky Mount Urban Area MPO | P-5711C | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
Forsyth | Doris Street |  | Closure of Doris Street at NS (Crossing 470 215U, MP R 121.8) in Winston-Salem | Closure of crossing. |  |  |  | 9 | Winston-Salem Area TPO | RC-2009A | Division 9 | RR | 2026 | 500000 | 2026 | 120000 | 2028 | 2000000 | 2026 | 150000 | 2770000
Forsyth | INT | SMITH REYNOLDS AIRPORT (INT) | Smith Reynolds Airport | Acquire land and clear terrain obstructions east of runway 15-33 to drain and grade material in place. |  | Aviation | STI (Prioritization) | 9 | Winston-Salem Area TPO | AV-5738 | Division 9 | T |  |  |  |  | 2031 | 6000000 |  |  | 6000000 | RIGHT-OF-WAY IN PROGRESS BY AIRPORT
Forsyth | INT | SMITH REYNOLDS AIRPORT (INT) | Smith Reynolds Airport | Construct new taxilane. |  | Aviation | STI (Prioritization) | 9 | Winston-Salem Area TPO | AV-5832 | Division 9 | T |  |  |  |  | 2028 | 15700000 |  |  | 15700000
Forsyth | Brewer Road | WINSTON-SALEM | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0018 | Division 9 | BGANY, BGDA, L(M) | 2026 | 513000 |  |  | 2028 | 2326000 | 2025 | 205000 | 3044000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
Forsyth | Broad Street | KERNERSVILLE | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0015 | Division 9 | BGDA, L(M) | 2026 | 99000 | 2026 | 334000 | 2027 | 630000 | 2025 | 155000 | 1218000
Forsyth | Brushy Fork Greenway | WINSTON-SALEM | Old Greensboro Road to Lowery Street | Construct paved multi-use trail. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-4020B | [11 empty] | COMPLETE
Forsyth | Brushy Fork Greenway | WINSTON-SALEM | Waterworks Road to Old Greensboro Road | Construct paved multi-use trail. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-4020A | [11 empty] | COMPLETE
Forsyth | Brushy Fork Greenway | WINSTON-SALEM | Waterworks Road to Reynolds Park Road in Winston-Salem | Construct paved multi-use trail. | 2.2 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-4020 | Pre-STI (Transition)
Forsyth | Depot Street | WALKERTOWN | US 311 (Main Street) to SR 1992 (Sullivantown Road) in Walkertown | Construct sidewalk. | 0.22 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0020 | Division 9 | BGDA, L(M) |  |  |  |  | 2026 | 1061000 |  |  | 1061000
Forsyth | Fairlawn Drive | WINSTON-SALEM | NC 67 (Reynolda Road) to SR 1528 (Silas Creek Parkway) in Winston-Salem | Construct sidewalk. | 0.39 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5952 | Division 9 | BGANY, BGDA, L(M) | 2022 | 248000 |  |  | 2025 | 741000 |  |  | 989000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | Friendly Road; Ruxton Drive | WALKERTOWN | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0143 | Division 9 | L(M), TADA | 2026 | 13000 | 2026 | 13000 | 2027 | 568000 | 2026 | 13000 | 607000
Forsyth | Griffith Road | WINSTON-SALEM | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5954 | Division 9 | BGANY, L(M) | 2026 | 293000 |  |  | 2028 | 3680000 | 2025 | 40000 | 4013000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | Harmon Lane | KERNERSVILLE | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0016 | Division 9 | BGANY, BGDA, L(M) | 2026 | 79000 | 2026 | 19000 | 2027 | 346000 | 2024 | 216000 | 660000
Forsyth | Long Branch Trail Phase II | WINSTON-SALEM | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0019 | Division 9 | BGDA, DP, L(M) | 2026 | 70000 | 2026 | 30000 | 2026 | 7500000 | 2024 | 1000000 | 8600000 | DP REPRESENT RAISE GRANT FUNDS
Forsyth | Piedmont Regional Greenway | WINSTON-SALEM | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | U-4741OK | Division 9 | BGANY, L(M), TADA | 2025 | 900000 |  |  | 2027 | 5703000 | 2025 | 783000 | 7386000
Forsyth | Salem Creek Greenway Bridge | WINSTON-SALEM | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0072 | Division 9 | BGDA, L(M) | 2028 | 115000 |  |  | 2029 | 575000 | 2023 | 322000 | 1012000
Forsyth | Southern Street Greenway | KERNERSVILLE | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0017 | Division 9 | BGDA, L(M) | 2026 | 50000 | 2026 | 203000 | 2027 | 648000 | 2025 | 146000 | 1047000
Forsyth | SR 1101 (Harper Road) | CLEMMONS | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5960 | Division 9 | BGANY, L | 2025 | 257000 | 2025 | 200000 | 2026 | 2671000 | 2021 | 125000 | 3253000 | IN PROGRESS
Forsyth | SR 1101 (Harper Road) | CLEMMONS | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-6040 | Division 9 | BGDA, L(M) | 2025 | 112000 | 2025 | 20000 | 2026 | 1455000 | 2022 | 66000 | 1653000
Forsyth | SR 1103 (Lewisville-Clemmons Road) | CLEMMONS | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0142 | Division 9 | L(M), TADA | 2025 | 44000 |  |  | 2026 | 263000 | 2025 | 13000 | 320000
Forsyth | SR 1261 (Marty Lane) | CLEMMONS | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0145 | Division 9 | BGDA, L(M) | 2027 | 197000 | 2027 | 13000 | 2028 | 1444000 | 2026 | 236000 | 1890000
Forsyth | SR 1348 (Robinhood Road) | WINSTON-SALEM | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5955 | Division 9 | BGANY, BGDA, L(M) | 2022 | 66000 |  |  | 2025 | 828000 | 2025 | 53000 | 947000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | SR 1992 (Sullivantown Road) | WALKERTOWN | US 311 at Harley Drive to Walkertown High / Middle School in Walkertown | Install bicycle and pedestrian facilities and construct sidewalk. | 0.44 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5956 | Division 9 | BGDA, L(M) |  |  |  |  | 2026 | 868000 |  |  | 868000
Forsyth | SR 3000 (Idols Road) | CLEMMONS | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5959 | Division 9 | BGANY, L | 2025 | 245000 | 2025 | 420000 | 2027 | 150000 | 2025 | 192000 | 1007000 | IN PROGRESS
Forsyth | SR 4000 (University Parkway) | WINSTON-SALEM | SR 1686 (Shattalon Drive) to Robin Wood Lane in Winston-Salem | Construct sidewalk. | 0.3 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5953 | Division 9 | BGDA, L(M) |  |  |  |  | 2028 | 635000 |  |  | 635000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM
Forsyth | SR 4278 (South Cherry Street) | KERNERSVILLE | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0014 | Division 9 | BGANY, BGDA, L(M) | 2026 | 145000 | 2026 | 765000 | 2027 | 1492000 | 2025 | 361000 | 2763000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
Forsyth | Winston-Salem | WINSTON-SALEM | Various routes | Purchase and install streetlights |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0162 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 1000000 |  |  | 1000000
Forsyth | Various | WINSTON-SALEM | Greenways in Winston-Salem. | Install wayfinding signs. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 9 | Winston-Salem Area TPO | BN-0030 | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 630000 | 2025 | 10000 | 640000
Forsyth | Barbara Jane Avenue | WINSTON-SALEM | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5810 | Division 9 | BGDA, L(M), TAANY | 2025 | 5000 |  |  | 2026 | 671000 | 2025 | 10000 | 686000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | NC 67 (Silas Creek Parkway) | WINSTON-SALEM | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5722 | Division 9 | BGANY, BGDA, L(M), TAANY, TADA | 2022 | 1340000 |  |  | 2026 | 8318000 | 2025 | 40000 | 9698000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | Salem Creek Greenway | WINSTON-SALEM | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5812 | Division 9 | L(M), TAANY | 2028 | 130000 | 2028 | 150000 | 2030 | 10400000 | 2020 | 150000 | 10830000
Forsyth | SR 1122 (Jonestown Road) | WINSTON-SALEM | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5920 | Division 9 | L(M), TAANY | 2027 | 200000 | 2027 | 800000 | 2028 | 900000 | 2025 | 200000 | 2100000
Forsyth | US 158 / US 421 (Salem Parkway) | WINSTON-SALEM | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-6008 | Division 9 | CMAQ, L(M), TAANY | 2027 | 408000 |  |  | 2028 | 5444000 | 2020 | 339000 | 6191000
Forsyth | US 158 / US 421 / NC 150 (Salem Parkway) | WINSTON-SALEM | NC 150 (Peters Creek Parkway) to the Strollway in Winston-Salem | Construct multi-use path. | 0.52 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5840 | Division 9 | BGDA, L(M), TAANY, TADA |  |  |  |  | 2024 | 3730000 |  |  | 3730000 | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION
Forsyth | Brushy Fork Greenway | WINSTON-SALEM | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Bike & Ped | Transition | 9 | Winston-Salem Area TPO | EB-4020C | Pre-STI (Transition) | BGANY, L(M) |  |  | 2026 | 194000 | 2027 | 2429000 | 2026 | 625000 | 3248000 | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
Forsyth | NC 67 (Silas Creek Parkway) Westbound | NCDOT | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | B-5950 | Region D | BFP, T(M) | 2026 | 990000 | 2026 | 490000 | 2027 | 8700000 |  |  | 10180000
Forsyth | Polo Road | NCDOT | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | HB-0033 | Division 9 | BFP, T(M) | 2029 | 300000 | 2029 | 300000 | 2031 | 8049000 |  |  | 8649000
Forsyth | Salisbury Ridge Road | NCDOT | Bridge 330243 over NC 150 in Winston-Salem. | Replace bridge. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | B-5770 | Division 9 | BGOFF |  |  |  |  | 2022 | 6001000 |  |  | 6001000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | Sixteenth Street | NCDOT | Bridge 330390 over rail corridor and Bridge 330244 over US 52( Future I-285) / NC 8 in Winston-Salem. | Replace bridge. | 0.5 | Highway | Bridges | 9 | Winston-Salem Area TPO | HB-0036 | Division 9 | BGOFF | 2026 | 1300000 | 2026 | 850000 | 2027 | 4200000 |  |  | 6350000
Forsyth | SR 1109 (Kinnamon Road) | NCDOT | Bridge 330135 over I-40 | Replace bridge. |  | Highway | Bridges | 9 | Winston-Salem Area TPO | BR-0075 | Division 9 | BGOFF | 2026 | 700000 | 2026 | 100000 | 2028 | 12000000 |  |  | 12800000
Forsyth | SR 2377 (Old Greensboro Road NE) | NCDOT | Bridge 330211 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | U-6059A | Division 9 | BGOFF | 2026 | 880000 | 2026 | 710000 | 2028 | 15400000 |  |  | 16990000
Forsyth | Third Street, Fourth Street, Fifth Street | NCDOT | Bridges 330185, 330191, and 330203 over US 52 (Future I-285) / US 311 in downtown Winston-Salem. | Replace bridges. | 0.5 | Highway | Bridges | 9 | Winston-Salem Area TPO | HB-0031 | Division 9 | BGOFF | 2027 | 950000 | 2027 | 50000 | 2029 | 9500000 |  |  | 10500000
Forsyth | New Route | NCDOT | SR 4001 (Reynolds Boulevard) to SR 2264 (Akron Drive) at intersection of SR 1763 (Indiana Avenue). | Construct access road. | 0.34 | Highway | Economic Development | 9 | Winston-Salem Area TPO | U-6231 | Division 9 | L, T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL.
Forsyth | I-40 | NCDOT | 0.3 mile east of SR 3153 (Hanes Mall Boulevard) to 0.9 mile east of NC 150 (Peters Creek Parkway) in Winston-Salem and SR 2747 (Clemmonsville Road) in Winston-Salem to Guilford County line. | Pavement rehabilitation and rehabilitation of bridges 330161, 330162, 330444, 330448, 330449,330508, and 330509. | 13.66 | Highway | Interstate Maintenance | 9 | Winston-Salem Area TPO | I-5795 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2020 | 23814000 |  |  | 23814000 | UNDER CONSTRUCTION
Forsyth | NC 66 / SR 4309 (West Mountain Street) | KERNERSVILLE | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0015 | Exempt | BGANY, BGDA, L(M) | 2026 | 282000 | 2026 | 288000 | 2027 | 3125000 | 2022 | 821000 | 4516000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
Forsyth | NC 8 (Germanton Road) | NCDOT | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0059 | Exempt | BGDA, CMAQ, HF | 2024 | 1059000 | 2024 | 570000 | 2026 | 3036000 | 2023 | 151000 | 4816000 | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS
Forsyth | New Route | WINSTON-SALEM | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) | Improve landscaping and lighting. | 1.09 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-2925C | Division 9 | BGANY, BGDA, L(M) |  |  |  |  | 2025 | 1358000 | 2021 | 453000 | 1811000 | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
Forsyth | SR 1173 (Williams Road) | LEWISVILLE | Roundabout west of bridge to roundabout east of bridge. | Improve roundabouts west & east of bridge over US 421, and widen to multi-lanes from roundabout east of bridge to west of SR 1001 (Shallowford Road). | 0.28 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-5617 | Division 9 | BGANY, L(M) |  |  |  |  | 2023 | 2109000 |  |  | 2109000 | UNDER CONSTRUCTION.
Forsyth | SR 1308 (Lewisville-Vienna Road) | LEWISVILLE | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-6154 | Division 9 | BGANY, BGDA, CMAQ, CRPDA, L, L(M) | 2023 | 474000 |  |  | 2025 | 4950000 | 2023 | 341000 | 5765000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS
Forsyth | Sullivantown Road | WALKERTOWN | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0153 | Division 9 | BGDA, L(M) | 2026 | 13000 | 2026 | 13000 | 2027 | 1475000 | 2026 | 13000 | 1514000
Forsyth | US 311; SR 4394 (Martin Luther King Jr. Boulevard) | WINSTON-SALEM | US 158 / US 421 / NC 150 / I-40 Business to US 52 (Future I-285) / NC 8 | Construct streetscape improvements. | 1.01 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-5539A | Division 9 | BGANY, L(M) | 2026 | 600000 |  |  | 2027 | 2188000 |  |  | 2788000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
Forsyth | US 421 (Salem Parkway) | WINSTON-SALEM | Silas Creek Parkway to Martin Luther King Jr Drive | Replace existing lighting with LED lighting |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0154 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 960000 | 2025 | 40000 | 1000000
Forsyth | Old Greensboro Road | WINSTON-SALEM | Bridge 330330 over Brushy Fork Creek | Replace bridge. | 0.25 | Highway | Municipal Bridge | 9 | Winston-Salem Area TPO | HM-0004 | Division 9 | BFPOFF | 2027 | 300000 | 2027 | 475000 | 2028 | 2800000 | 2026 | 1240000 | 4815000
Forsyth | West First Street | WINSTON-SALEM | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Highway | Municipal Bridge | 9 | Winston-Salem Area TPO | B-5007 | Division 9 | BFPOFF, BGANY, BGOFF, L(M) | 2023 | 600000 |  |  | 2026 | 8833000 | 2026 | 211000 | 9644000
Forsyth | New Route | NCDOT | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) in Winston-Salem. | Construct multi-lane facility on new location. | 1.81 | Highway | Pre-STI (Historic) | 9 | Winston-Salem Area TPO | U-2925 | Pre-STI (Transition) | [10 empty] | DESIGN-BUILD PROJECT COMPLETE
Forsyth | SR 2667 (Hastings Hill Road) | NCDOT | Winston-Salem Northern Beltway, Eastern Section, Bridge No. 366 over US 421 / NC 150 / I-40 Business | Replace bridge. |  | Highway | Pre-STI (Historic) | 9 | Winston-Salem Area TPO | U-2579G | [11 empty] | PROJECT COMPLETE
Forsyth | NC 150 | NCDOT | SR 2983 (Fishel Road) intersection | Construct reduced conflict intersection. | 0.5 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2409A | Region D | HSIP, T(M) |  |  | 2025 | 50000 | 2025 | 1100000 |  |  | 1150000 | UNDER CONSTRUCTION
Forsyth | SR 1528 (North Point Boulevard) | NCDOT | University Plaza Shopping Center main driveway and BP filling station driveway intersection. Also, Northcliffe Drive intersection. | Construct two reduced conflict intersections. | 1 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2009H | Division 9 | HSIP, T(M) |  |  | 2024 | 24000 | 2025 | 1010000 |  |  | 1034000
Forsyth | SR 1725 (University Parkway) | NCDOT | West 14th Street intersection in Winston-Salem. | Upgrade traffic signal, install pedestrian signals and crosswalks, and modify sidewalk and median. | 0.5 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2409C | Division 9 | HSIP |  |  |  |  | 2025 | 645000 |  |  | 645000
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, I-40 to US 421 / NC 150 / I-40 Business | Construct multi-lane freeway. | 3.27 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579AB | Region D | NHP, T(M) |  |  |  |  | 2022 | 310367000 |  |  | 310367000 | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, I-74 / US 311 to I-40 | Construct multi-lane freeway. | 0.87 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579AA | Region D | BGDA, NHP, T |  |  |  |  | 2023 | 149165000 |  |  | 149165000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $20M CONSTRUCTION PAYBACK FY 2026-2040 (SALE 6 / 2026).
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, eastern section, I-74 / US 311 to US 52 (Future I-285). | Multi-lane freeway on new location. | 17.1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579 |  | T | 2025 | 175000 | [6 empty] | 175000 | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, NC 8 to west of NC 66 (University Parkway) | Construct multi-lane freeway. | 2.44 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579F | Statewide Mobility | NHP |  |  |  |  | 2018 | 26767000 |  |  | 26767000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, SR 2211 (Baux Mountain Road) to NC 8 | Construct multi-lane freeway. | 2.21 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579E | Statewide Mobility | NHP |  |  |  |  | 2018 | 33462000 |  |  | 33462000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, US 158 to US 311 | Construct multi-lane freeway. | 1.41 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579C | Region D | NHP, T | 2016 | 6138000 |  |  | 2018 | 27222000 |  |  | 33360000 | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, US 311 to SR 2211 (Baux Mountain Road) | Construct multi-lane freeway. | 3.2 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579D | Statewide Mobility | NHP |  |  |  |  | 2018 | 42380000 |  |  | 42380000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, US 311 to SR 2211 (Baux Mountain Road) | Construct noise wall. | 0.5 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579DA | Statewide Mobility | NHP, T(M) |  |  |  |  | 2025 | 6000000 |  |  | 6000000 | RIGHT-OF-WAY IN PROGRESS.
Forsyth | I 40 | NCDOT | US 158 (Stratford Road) | Improve westbound exit loop. |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0026 | Region D | BGANY |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 |  |  | 3800000
Forsyth | I-40 | NCDOT | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-5981A | Not Funded | NHP, T(M) | NOT FUNDED | 1200000 | NOT FUNDED | 21700000 | NOT FUNDED | 87001000 | NOT FUNDED |  | 109901000
Forsyth | I-40 | NCDOT | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-5981B | Not Funded | NHP, T(M) | NOT FUNDED | 200000 | NOT FUNDED | 600000 | NOT FUNDED | 44000000 | NOT FUNDED |  | 44800000
Forsyth | I-40 / US 311 | NCDOT | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-5880 | Region D | NHP, T(M) | 2023 | 3600000 | 2023 | 1400000 | 2025 | 45000000 |  |  | 50000000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | Kernersville Southern Loop | NCDOT | US 421 / I-40 Business to NC 66 (West Mountain Street) in Kernersville. interchange at US 421 / NC 150. | Widen Big Mill Farm Road and SR 2649 (Hopkins Road) to a two lane divided facility and construct interchange at US 421 / NC 150. | 2.05 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5760 | Division 9 | T | 2022 | 11500000 | 2022 | 4000000 | 2026 | 92850000 |  |  | 108350000 | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE)
Forsyth | NC 65 (Bethania-Rural Hall Road) | NCDOT | SR 1647 (Glade Street) to NC 66 in Rural Hall. | Widen to 3 lanes. | 0.25 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6190 | Division 9 | T | 2028 | 2900000 | 2028 | 900000 | 2030 | 3800000 |  |  | 7600000
Forsyth | NC 65 (Bethania-Rural Hall Road) | NCDOT | US 52 to SR 3983 (Northridge Drive) in Rural Hall. | Widen to two lane divided facility with bike-ped accommodations. | 1.17 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6005 | Division 9 | T | 2023 | 3800000 | 2023 | 900000 | 2026 | 15800000 |  |  | 20500000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE)
Forsyth | NC 66 (Old Hollow Road) | NCDOT | Harley Drive to US 158 in Walkertown. | Widen to a multi-lane divided facility. | 1.61 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5824 | Division 9 | T | 2021 | 18798000 |  |  | 2024 | 23205000 |  |  | 42003000 | UNDER CONSTRUCTION; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE)
Forsyth | New Route | NCDOT | Forum Parkway connector, SR 3955 (Forum Parkway) to NC 66 (University Parkway) in Rural Hall. | Construct 2-lane roadway on new location. | 0.44 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5899 | Division 9 | T | 2022 | 4300000 | 2022 | 1300000 | 2025 | 16000000 |  |  | 21600000 | RIGHT-OF-WAY IN PROGRESS
Forsyth | New Route | NCDOT | Proposed Great Wagon Road from SR 1001 (Shallowford Road) to SR 1308 (Lewisville-Vienna Road) in Lewisville. | Construct two lane facility on new location with bicycle and pedestrian accommodations. | 0.88 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5536 | Division 9 | T | 2022 | 14792000 | 2025 | 1300000 | 2025 | 23800000 |  |  | 39892000 | UNDER CONSTRUCTION. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE)
Forsyth | New Route | NCDOT | SR 1969 (Piney Grove Road) to NC 150 (North Main Street) in Kernersville. | Construct two-lane divided facility with bicycle / pedestrian accommodations. | 0.94 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6003 | Division 9 | T |  |  |  |  | 2024 | 12400000 |  |  | 12400000 | UNDER CONSTRUCTION
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, bridges 330221 and 330222 over Muddy Creek. | Replace bridges. |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CC | [11 empty] | COMPLETE - WORK ACCOMPLISHED UNDER B-4507
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, I-40 to US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 17.4 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, interchange at US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 2.3 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247EB | Statewide Mobility | BGDA, NHP, T | 2025 | 517000 |  |  | 2018 | 86737000 |  |  | 87254000 | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, interchange with US 421 and interchange with SR 1140 (Peace Have Road). | Construct four lane expressway on new location, including ITS deployment. | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CA | Region D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 261000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 140900000 |  |  | 141661000
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, NC 67 to south of US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 4.53 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247EA | Region D | NHP, T | 2027 | 3800000 | 2027 | 6700000 | 2030 | 278500000 |  |  | 289000000 | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE)
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, north of SR 1348 (Meadowlark Drive / Robinhood Road) to NC 67. | Construct four lane expressway on new location, including ITS deployment. | 4.61 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247D | Region D | T | 2028 | 2100000 | 2028 | 6500000 | 2032 | 159100000 |  |  | 167700000
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, north of US 421 interchange to SR 1348 (Robinhood Road). | Construct four lane expressway on new location, including ITS deployment. | 3.24 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CB | Region D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92001000 |  |  | 117001000
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, south of I-40 to south of US 421 interchange. | Construct four lane expressway on new location, including ITS deployment. | 1.43 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247B | Region D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 149500000 |  |  | 184400000
Forsyth | New Route (Future NC 452 / Future I-274) | NCDOT | Winston-Salem Northern Beltway, western section, US 158 to south of I-40 | Construct four lane expressway on new location, including ITS deployment. | 1.95 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247A | Not Funded | NHP, T | NOT FUNDED | 13200000 | NOT FUNDED | 18900000 | NOT FUNDED | 39101000 | NOT FUNDED |  | 71201000
Forsyth | New Route (Macy Grove Road Extension) | NCDOT | SR 1005 (East Mountain Street) to NC 150 (North Main Street) in Kernersville. | Four-lane divided facility on new location. | 1.52 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-4734 | Division 9 | T |  |  |  |  | 2019 | 11172000 |  |  | 11172000 | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
Forsyth | SR 1103 (Lewisville-Clemmons Road) | NCDOT | US 158 to SR 1891 (Peace Haven Road) in Clemmons. | Construct access management and operational improvements. | 1.43 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6004 | Division 9 | BGANY, T | 2024 | 33600000 | 2026 | 2975000 | 2030 | 35400000 |  |  | 71975000 | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE)
Forsyth | SR 1156 (Lewisville- Clemmons Road) | NCDOT | SR 1103 (Styers Ferry Road) to SR 1101 (Shallowford Road) in Lewisville. | Widen to 3 lanes with bicycle and pedestrian accommodations. | 2.31 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6189 | Division 9 | T | 2030 | 14600000 | 2030 | 3300000 | 2033 | 27000000 |  |  | 44900000
Forsyth | SR 1672 (Hanes Mill Road) | NCDOT | Museum Drive to SR 4000 (University Parkway) in Winston-Salem. | Widen to multi-lane divided facility. | 0.42 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2729 | Division 9 | T | 2019 | 686000 |  |  | 2023 | 20226000 | 2020 | 1092000 | 22004000 | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE)
Forsyth | SR 1891 (Peace Haven Road / Future I-274) | NCDOT | US 421 Interchange and approaches in Winston-Salem. | Construct interchange. | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CD | Statewide Mobility | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247EC
Forsyth | SR 1969 (Piney Grove Road) | NCDOT | North of Nelson Street to SR 2031 (Brown Road) in Kernersville. | Widen to 3 lanes with bicycle / pedestrian accommodations. | 0.52 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6188 | Division 9 | T | 2028 | 2200000 | 2028 | 500000 | 2030 | 6800000 |  |  | 9500000
Forsyth | US 158 | NCDOT | Multi-lanes north of US 421 / I-40 Business to SR 1965 (Belews Creek Road). | Widen to a four lane divided facility. | 5.21 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2577A | Region D | T | 2021 | 36300000 | 2021 | 469000 | 2024 | 116750000 |  |  | 153519000 | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
Forsyth | US 158 | NCDOT | SR 1965 (Belews Creek Road) in Forsyth County to SR 2034 (Anthony Road) in Guilford County. | Widen to multi-lanes. | 7.53 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2577B | Not Funded | T | NOT FUNDED | 38800000 | NOT FUNDED | 9700000 | NOT FUNDED | 60300000 | NOT FUNDED |  | 108800000
Forsyth | US 421 | NCDOT | SR 1122 (Jamestown Road) intersection in Winston-Salem | Upgrade intersection, remove two-way traffic from US 421 Northbound on-ramp, and extend acceleration lane distance onto mainline. |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0031 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 |  |  | 20700000
Forsyth | US 421 (Salem Parkway) | NCDOT | Interchange at SR 2662 (Linville Road) and Bridge 330211 on SR 2237 (Old Greensboro Road Northeast) over Norfolk Southern Railroad In Winston-Salem. | Upgrade interchange and replace bridge. | 1.5 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6059
Forsyth | US 421 (Salem Parkway) | NCDOT | SR 2662 (Linville Road) interchange | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6059B | Not Funded | T | NOT FUNDED | 12600000 | NOT FUNDED | 800000 | NOT FUNDED | 42900000 | NOT FUNDED |  | 56300000 | COORDINATE WITH U-6068
Forsyth | US 52 (Future I-285) | NCDOT | US 421 (Salem Parkway) - Exit 109 to Exit 112 | Upgrade US 52 to Interstate standards (I-285) by widening existing facilities. |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0027 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 317100000 |  |  | 377700000
Forsyth | US 52 / Future I-74 | NCDOT | NC 65 interchange in Winston-Salem. | Reconstruct interchange. | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247EC | Statewide Mobility | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247CD
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Construct multi-lane freeway. | 2.92 | Highway | Transition | 9 | Winston-Salem Area TPO | U-2579B | Pre-STI (Transition) | NHP |  |  |  |  | 2015 | 68971000 |  |  | 68971000 | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Construct noise wall. | 2.92 | Highway | Transition | 9 | Winston-Salem Area TPO | U-2579BB | Pre-STI (Transition) | T |  |  | 2022 | 234000 | 2023 | 2855000 |  |  | 3089000 | UNDER CONSTRUCTION
Forsyth | Future I-74 | NCDOT | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Relocate stream. | 2.92 | Highway | Transition | 9 | Winston-Salem Area TPO | U-2579BA | Pre-STI (Transition) | NHP, T(M) |  |  |  |  | 2021 | 9300000 |  |  | 9300000 | UNDER CONSTRUCTION
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Systemwide | FTA Section 5339 bus and bus facilities grant. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TD-5303 | Public Transit | 5339, L | [6 empty] | 2024 | 2915000 | 2915000
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Systemwide | Funding for planning assistance - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TP-5105 | Public Transit | 5303, L, S | [6 empty] | 2020 | 618000 | 618000 | FUNDS AUTHORIZED IN PROGRESS
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TS-5120 | Public Transit | 5307, L | [6 empty] | 2024 | 127000 | 127000
Forsyth | Winston-Salem Transit Authority | WINSTON-SALEM TRANSIT AUTHORITY | Systemwide. | Purchase one large hybrid-diesel replacement bus and one small hybrid-diesel replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TC-0025 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 1230000 | 1230000
Forsyth | Piedmont Authority for Regional Transportation | PART | Various locations | Purchase cutaway vehicles and heavy duty buses. |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0063 | Division 9 | BGDA, L(M) | [6 empty] | 2025 | 2063000 | 2063000
Forsyth | Winston Salem Transit Authority | WINSTON SALEM TRANSIT AUTHORITY | Various locations | Improve paratransit tracking and accessibility through GPS and notification services, as well as provide mobile ticketing options for Winston-Salem area transportation planning organization (WSATPO) fixed route bus services by using ICAM (Innovative coor |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0025 | Public Transit | 5307, L | [6 empty] | 2023 | 700000 | 700000
Forsyth | Winston Salem Transit Authority | WSTA | Systemwide | Replace bus |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0054 | Division 9 | BGANY, BGDA, L(M) | [6 empty] | 2024 | 13199000 | 13199000
Forsyth | Piedmont Authority for Regional Transportation | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Winston-Salem Area TPO | TO-6150 | Public Transit | 5307, L | [6 empty] | 2022 | 5610000 | 5610000
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Winston-Salem Area TPO | TO-5126 | Public Transit | 5307, L, SMAP | [6 empty] | 2024 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
Forsyth | Winston Salem Transit |  | Systemwide | Purchase of five (5) hybrid-electric buses |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TM-0055 | Public Transit | 5339(b), L, S | [6 empty] | 2024 | 11198000 | 11198000
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Systemwide | FTA Section 5310 Winston-Salem allocation set aside for competitive grant to eligible agencies to assist in meeting the transportation needs of low income, disabled, and elderly populations. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TQ-6702 | Public Transit | 5310, L | [6 empty] | 2024 | 1904000 | 1904000
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Systemwide | Funding set aside for COMPETE Grant to eligible agencies to assist in meeting the needs of low income, disabled and elderly populations |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TQ-6782 | Public Transit | 5310, L | [6 empty] | 2020 | 3607000 | 3607000
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Various locations | Funding for Job access reverse commute (JARC) - Non urban. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TM-5309 | Public Transit | 5316, L | [6 empty] | 2020 | 660000 | 660000
Forsyth | Winston Salem transit | WINSTON SALEM TRANSIT | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TG-5126 | Public Transit | 5307, L | [6 empty] | 2024 | 9284000 | 9284000
Forsyth | Winston-Salem Transit Authority | WINSTON-SALEM TRANSIT AUTHORITY | Systemwide. | Continuation of night, Saturday, and Sunday services. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TM-0037 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 1013000 | 1013000
Forsyth | Piedmont Authority For Regional Transportation | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | Various locations | Funding for routine capital including passenger shelters, passenger amenities, shop equipment, and spare parts. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Winston-Salem Area TPO | TG-6783 | Public Transit | 5307, L | [6 empty] | 2022 | 1111000 | 1111000
Forsyth | Winston Salem Transit | WINSTON SALEM TRANSIT | Various locations | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Winston-Salem Area TPO | TG-5241 | Public Transit | 5307, L | [6 empty] | 2024 | 12110000 | 12110000 | FUNDS AUTHORIZED IN PROGRESS
Forsyth | SR 1686 (Shattalon Drive) | NCDOT | Crossing 722024H in Winston-Salem | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Winston-Salem Area TPO | RX-2009D | Division 9 | RR |  |  |  |  | 2027 | 492000 |  |  | 492000
Forsyth | SR 2381 (Willston Road) | NCDOT | Crossing 470210K in Walkertown | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Winston-Salem Area TPO | RX-2009C | Division 9 | RR |  |  |  |  | 2026 | 601000 |  |  | 601000
Forsyth | SR 2385 (Walkertown-Guthrie Road) | NCDOT | Crossing 722063Y in Walktertown | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Winston-Salem Area TPO | RX-2009B | Division 9 | RR |  |  |  |  | 2026 | 411000 |  |  | 411000
Forsyth, Davidson | I-285 / US 52 (Future I-74) / NC 8 | NCDOT | SR 4205 (S. Main Street) in Forsyth County to SR 3010 (Old US 52) in Davidson County. | Rehabilitate pavement. | 18.55 | Highway | Interstate Maintenance | 9 | Winston-Salem Area TPO | HI-0005 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2026 | 14200000 |  |  | 14200000
Forsyth, Davidson | I-85 | DIVISION | I-285 / US 52 / NC 8 | Preserve Bridges 280147, 280152, 280513, 280515, 280516, 280136, 330027, 330028, 330053, and 330054. |  | Highway | Interstate Maintenance | 9 | Winston-Salem Area TPO | HI-0005A | Statewide Mobility | NHPIM |  |  |  |  | 2026 | 13000000 |  |  | 13000000
Forsyth, Davidson, Davie | Various | WINSTON-SALEM | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Highway | Other | 9 | Winston-Salem Area TPO | C-5620 | Exempt | CMAQ, L(M) | 2020 | 366000 |  |  | 2020 | 5331000 | 2020 | 1098000 | 6795000 | IN PROGRESS
Forsyth, Davidson, Davie | Various | NCDOT | Multiple freeway and expressway ramps in Division 9. | Install long-life wrong way pavement markings. |  | Highway | Safety | 9 | Winston-Salem Area TPO, High Point Urban Area MPO, Northwest Piedmont RPO | HS-2009J | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 524000 |  |  | 524000
Forsyth, Davidson, Stokes, Davie | Various | NCDOT | Winston-Salem Area Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | U-4741 | Division 9 | BGANY, BGDA, L(M), TADA | 2022 | 788000 |  |  | 2020 | 2953000 |  |  | 3741000
Forsyth, Davidson, Stokes, Davie | Various | NCDOT | Winston-Salem Area Transportation Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | U-6221 | Division 9 | TADA |  |  |  |  | 2029 | 6149000 |  |  | 6149000
Forsyth, Davidson, Stokes, Davie | Various | NCDOT | Routes in Winston-Salem Area Transportation Planning Organization | Construct intersection improvements. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-4742 | Division 9 | BGDA, L(M) |  |  |  |  | 2020 | 875000 |  |  | 875000
Forsyth, Davidson, Stokes, Davie | Various | NCDOT | Routes in Winston-Salem Area Transportation Planning Organization | Planning (PL) Supplement. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-4951 | Division 9 | BGDA, L(M) | [6 empty] | 2024 | 6058000 | 6058000 | FORMERLY U-9999D - IN PROGRESS
Forsyth, Davidson, Stokes, Davie | Various | NCDOT | Winston-Salem Area Transportation Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-5022 | Division 9 | BGANY, BGDA |  |  |  |  | 2028 | 91644000 |  |  | 91644000
Forsyth, Davidson, Stokes, Davie | Winston-Salem Planning Organization | NCDOT | Routes in Winston-Salem Area Transportation Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0108 | Exempt | CRPDA, L(M) |  |  |  |  | 2024 | 0
Forsyth, Davie | I-40 | NCDOT | West of NC 801 in Bermuda Run to west of SR 1122 (Jonestown Road) in Winston-Salem. | Add lanes. | 7 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-0911 | [11 empty] | PARTS B AND C COMPLETE
Forsyth, Guilford | I-40 | NCDOT | I -74 / US 311 in Winston-Salem to US 421 (Future I-685) / I-40 Business in Guilford County. | Widen to six lanes. | 10.1 | Highway | STI (Prioritization) | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO | I-5981
Forsyth, Guilford | US 158 | NCDOT | Multi-lanes north of US 421 / I-40 Business in Winston-Salem to US 220 in Stokesdale. | Widen to a four lane divided facility. | 18.8 | Highway | STI (Prioritization) | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | R-2577
Forsyth, Guilford | Piedmont Authority for Regional Transportation | Piedmont Authority for Regional Transportation | Systemwide | Fund the operation of express bus service. |  | Public Transportation (Transit) | Locally Selected | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO | TL-0069 | Exempt | CMAQ, L(M) | [6 empty] | 2026 | 2250000 | 2250000
Franklin | LHZ | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | Triangle North Executive Airport | Extend runway including relocation of utilities, navigation aids, and roadways. |  | Aviation | STI (Prioritization) | 5 | Capital Area MPO | AV-5819 | Division 5 | T | 2026 | 3500000 |  |  | 2031 | 26000000 | 2025 | 770000 | 30270000
Franklin | Franklin County Rails To Trails | FRANKLINTON | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0053 | Exempt | CMAQ, L(M) | 2025 | 120000 |  |  | 2025 | 3000000 | 2024 | 600000 | 3720000
Franklin | Main Street | FRANKLINTON | Various | Upgrade crosswalks along Main Street, add a new mid-block crossing at the intersection of Water Street and Main Street, and an improved crossing configuration for the Franklinton to Novozymes Rail Trail. | 0.5 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0127 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 750000 | 2025 | 85000 | 835000
Franklin | Smoke Tree Way, North Main Street, Hospital Drive |  | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | C-5610E | Exempt | CMAQ, L(M) | 2026 | 157000 |  |  | 2026 | 550000 | 2024 | 148000 | 855000
Franklin | NC 561 | NCDOT | Bridge 340024 over Sandy Creek | Replace bridge. |  | Highway | Bridges | 5 | Kerr-Tar RPO | BR-0169 | Region C | BFP |  |  |  |  | 2029 | 4000000 |  |  | 4000000
Franklin | SR 1600 (East River Road) | NCDOT | Bridge 340076 over Sycamore Creek. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Kerr-Tar RPO | B-5210 | Division 5 | [10 empty] | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC)
Franklin | SR 1609 (Baptist Church Road) | NCDOT | Bridge 340078 over Tar River. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-6003 | Division 5 | BGOFF | 2029 | 430000 |  |  | 2031 | 7600000 |  |  | 8030000
Franklin | US 401 | NCDOT | Bridge 340056 over Sandy Creek. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | HB-0024 | Division 5 | BFP | 2027 | 60000 | 2027 | 180000 | 2029 | 3700000 |  |  | 3940000
Franklin | SR 1230 (Bunn Road) | LOUISBURG | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Highway | Locally Selected | 5 | Kerr-Tar RPO | HL-0044 | Exempt | CMAQ, L(M) | 2027 | 38000 |  |  | 2027 | 462000 | 2026 | 106000 | 606000
Franklin | US 401 | NCDOT | SR 1700 (Fox Park Road) south of Louisburg to NC 39 in Louisburg | Widen to four-lane median divided facility. | 1.022 | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | R-2814E | [11 empty] | COMPLETE
Franklin | NC 96; SR 1100 (East Main Street) | NCDOT | Cross Street intersection | Upgrade traffic signal and install pedestrian signals | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AL | Region C | HSIP | 2026 | 10000 | 2026 | 10000 | 2027 | 165000 |  |  | 185000
Franklin | SR 1229 (Main Street) | NCDOT | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405BF | Division 5 | HSIP, T(M) | 2027 | 25000 | 2027 | 5000 | 2028 | 340000 |  |  | 370000
Franklin | NC 56 | NCDOT | SR 1114 (Peach Orchard Road) to US 401 in Louisburg. | Widen to four lanes. | 2.28 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | R-5893 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36300000 |  |  | 45500000
Franklin | US 401 | NCDOT | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Highway | STI (Prioritization) | 5 | Capital Area MPO, Kerr-Tar RPO | R-2814D | Division 5 | BGLT5, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 82300000 |  |  | 95900000
Franklin | US 401 / NC 39 | NCDOT | NC 56 / NC 581 (Nash Street) to SR 1229 (Main Street). | Widen to multi-lanes. | 1.36 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | R-3608 | Region C | T | 2030 | 8500000 | 2030 | 3400000 | 2033 | 38800000 |  |  | 50700000 | COORDINATE WITH U-6024
Franklin | US 401 / NC 39 (Bickett Boulevard) | NCDOT | Burke Boulevard to NC 56 / NC 581 (Nash Street) in Louisburg. | Upgrade 5-lane section to 4-lane divided facility with bicycle/pedestrian accommodations. | 1.38 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-6024 | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 37800000 |  |  | 49600000 | COORDINATE WITH R-3608
Franklin | CXS S Line | NCDOT | Various | Construct NC 96 / Main Street bypass grade separation and Youngsville roadway improvements. |  | Rail | Other | 5 | Capital Area MPO | P-5753BE | Statewide Mobility
Franklin | CXS S Line | NCDOT | Various | Holding Avenue grade separation, Elm Avenue improvements, and Brick Street pedestrian crossing. |  | Rail | Other | 5 | Capital Area MPO | P-5753BD | Statewide Mobility
Franklin | CXS S Line | NCDOT | Various | SR 1133 (Bert Winston Road) and SR 1125 (Cedar Creek Road) grade separation and Franklinton roadway improvements. |  | Rail | Other | 5 | Capital Area MPO | P-5753BF | Statewide Mobility
Franklin, Lee, Vance, Warren, Wake | Integrated Mobility Division | LINK TRANSIT | Various locations | This planning project will fund the planning of mobility hubs in seven communities along the S-line passenger rail corridor. Participating communities include Sanford, Apex, Wake Forest, Youngsville, Henderson, Franklinton, and Norlina. |  | Public Transportation (Transit) | Planning | 5, 8 | Statewide Project | TU-0016 | Public Transit | 5307, DP, L | [6 empty] | 2023 | 5170000 | 5170000 | DP FUNDING REPRESENTS RAISE GRANT FUNDS
Franklin, Vance | US 1 | NCDOT | NC 96 to Chappell Lane | Install rumble stripes. | 12.7 | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | HS-2405AF | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 77000 |  |  | 77000
Franklin, Vance | CXS S Line | NCDOT | South Kitrell | Improve roadway. |  | Rail | Other | 5 | Capital Area MPO, Kerr-Tar RPO | P-5753BG | Statewide Mobility
Franklin, Vance, Wake, Warren | CSX S Line | NCDOT | CSX S Line from Raleigh to Virginia State line and CSX SA Line from Raleigh to Weldon. | Acquire right of way, upgrade existing track and construct new track. | 50 | Rail | Other | 5 | Capital Area MPO, Kerr-Tar RPO | P-5753 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
Franklin, Wake | US 401 | NCDOT | NC 96 to SR 1103 (Flat Rock Church Road / Clifton Pond Road). | Widen to four-lane median divided facility. | 5.98 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2814C | Division 5 | BGLT5 |  |  |  |  | 2018 | 36803000 |  |  | 36803000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032
Franklin, Wake | US 401 | NCDOT | North of SR 2044 (Ligon Mill Road) to NC 39 in Louisburg. | Widen to four-lane median divided facility, some new location. | 18.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO, Kerr-Tar RPO | R-2814 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
Gaston | Cramerton-McAdenville Greenway Connector | CRAMERTON | Paved trail at South Fork Village in Cramerton to Riverside Drive in McAdenville, following South Fork of Catawba River. | Construct greenway. | 0.37 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5704 | Exempt | CMAQ, CRPDA, L(M) |  |  |  |  | 2026 | 1163000 | 2021 | 317000 | 1480000 | CMAQ AWARD AMOUNT IS $1,183,200
Gaston | Highland Branch Greenway | GASTON COUNTY | Sims Legion Park to Bulb Avenue in Gastonia. | Construct greenway. | 0.62 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5622 | Exempt | CMAQ, L(M) |  |  |  |  | 2017 | 1335000 |  |  | 1335000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $1,068,204.
Gaston | Leisure Lane | GASTONIA | NC 275 to trailhead for Gaston Technology Park Greenway near Sportsman Drive in Dallas | Construct greenway. |  | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | BL-0105 | Exempt | CMAQ, L(M) |  |  |  |  | 2027 | 424000 | 2026 | 155000 | 579000
Gaston | NC 161 | BESSEMER CITY | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606B | Exempt | CMAQ, L(M) | 2026 | 5000 |  |  | 2026 | 529000 | 2018 | 214000 | 748000 | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847.
Gaston | NC 274 (Tryon Courthouse Road) | GASTON COUNTY | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | BL-0033 | Exempt | CMAQ, L(M) | 2026 | 50000 |  |  | 2028 | 1449000 | 2023 | 188000 | 1687000
Gaston | New Route | GASTON COUNTY | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606K | Exempt | CMAQ, L(M) | 2026 | 15000 |  |  | 2026 | 1570000 | 2023 | 275000 | 1860000 | CMAQ AWARD AMOUNT IS $757,478.
Gaston | New Route | GASTON COUNTY | Technology Park to Gaston College near Gastonia. | Construct greenway. | 0.63 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606E | Exempt | CMAQ, L(M) |  |  |  |  | 2025 | 588000 |  |  | 588000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $513,300.
Gaston | SR 2201 (Lowell Spencer Mountain Road) | GASTON COUNTY | George Poston Parkway to end of park limits near Gastonia. | Construct sidewalk. | 0.26 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606J | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 186000 |  |  | 186000 | CMAQ AWARD AMOUNT IS $334,379.
Gaston | SR 2400 (Neal Hawkins Road) | GASTON COUNTY | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606M | Exempt | CMAQ, L(M) | 2026 | 19000 |  |  | 2027 | 1364000 | 2023 | 477000 | 1860000 | CMAQ AWARD AMOUNT IS $1,488,462.
Gaston | Various | DALLAS | Locations along US 321 Business and NC 275 / NC 279 near Gaston College | Construct sidewalks. Install crosswalk across NC 275 / NC 279. |  | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606D | Exempt | CMAQ, L(M) |  |  |  |  | 2025 | 393000 |  |  | 393000 | CMAQ AWARD AMOUNT IS $383,779.
Gaston | NC 7 (Riverside Drive) | Cramerton | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Bike & Ped | NCDOT Selected (Other Selection Process) | 12 | Gaston-Cleveland-Lincoln MPO | BN-0029 | Exempt | CMAQ, L, L(M) | 2026 | 44000 |  |  | 2026 | 2490000 | 2025 | 61000 | 2595000 | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR.
Gaston | NC 279 (New Hope Road) | GASTONIA | US 29 / US 74 (Franklin Boulevard) to Hunt Avenue in Gastonia | Construct sidewalk on east side of NC 279 (New Hope Road) from US 29 / US 74 (Franklin Boulevard) to Court Drive and west side of NC 279 (New Hope Road) from Court Drive to Hunt Avenue. | 1.03 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5975 | Division 12 | L(M), TA50200 |  |  |  |  | 2027 | 2065000 | 2023 | 516000 | 2581000
Gaston | NC 279 (South New Hope Road) | GASTONIA | SR 2200 (Armstrong Park Road) to SR 1255 (Hudson Boulevard) in Cramerton | Construct missing sidewalk on south side of NC 279. | 1.12 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5743 | Division 12 | L(M), TA50200 |  |  |  |  | 2027 | 800000 | 2023 | 321000 | 1121000
Gaston | South Marietta Street / SR 1877 (Hilltop Drive) | GASTONIA | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5768 | Division 12 | L(M), TA50200 | 2026 | 1200000 | 2026 | 800000 | 2026 | 1000000 | 2023 | 350000 | 3350000
Gaston | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | GASTONIA | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5745 | Division 12 | L(M), TA50200 | 2026 | 900000 | 2026 | 600000 | 2027 | 3400000 | 2023 | 308000 | 5208000
Gaston | SR 2014 (Lakewood Road) | CRAMERTON | SR 2565 (Eagle Road) to Lake Drive in Cramerton | Construct sidewalk and pedestrian bridge over South Fork River Inlet. | 0.14 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5913 | Division 12 | L(M), TA50200 |  |  |  |  | 2026 | 354000 | 2023 | 164000 | 518000
Gaston | SR 2044 (Tuckaseegee Road) | MOUNT HOLLY | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5912 | Division 12 | L(M), TA50200, TAANY | 2027 | 2500000 | 2027 | 430000 | 2028 | 4500000 | 2026 | 436000 | 7866000
Gaston | SR 2200 (Cox Road) | GASTONIA | I-85 to Court Drive in Gastonia | Construct sidewalk on both sides. | 0.6 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5976 | Division 12 | L(M), TA50200 |  |  |  |  | 2027 | 1400000 | 2023 | 350000 | 1750000
Gaston | SR 2439 (Beaty Road) | MOUNT HOLLY | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5748 | Division 12 | L(M), TA50200 | 2026 | 231000 |  |  | 2027 | 800000 | 2022 | 10000 | 1041000
Gaston | US 29 / US 74 (East Franklin Boulevard) | GASTONIA | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5701 | Division 12 | L(M), TA50200 | 2026 | 800000 | 2026 | 75000 | 2027 | 880000 |  |  | 1755000
Gaston | 12th Street; Yellow Jacket Lane / SR 1446 (Bess Town Road) | BESSEMER CITY | Chadwick Court to Kaiser Road; 12th Street to 14th Street (NC 274) in Bessemer City | Construct sidewalks. | 0.4 | Bike & Ped | Transition | 12 | Gaston-Cleveland-Lincoln MPO | EB-5531 | Pre-STI (Transition) | BGANY, T(M) |  |  |  |  | 2026 | 300000 |  |  | 300000
Gaston | Gastonia | GASTONIA | Poston Park to South Fork River Greenway in Gastonia. | Construct trail. |  | Bike & Ped | Transition | 12 | Gaston-Cleveland-Lincoln MPO | EB-5533 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Gaston | Rail Trail | BELMONT | SR 1923 (Woodlawn Avenue) to Belmont Abbey College and Downtown. | Upgrade abandoned railroad to pedestrian trail. |  | Bike & Ped | Transition | 12 | Gaston-Cleveland-Lincoln MPO | C-5505 | Exempt | [10 empty] | IN PROGRESS
Gaston | SR 1421 (Marys Grove Road) | NCDOT | Bridge 350097 over Unnamed Tributary of Muddy Fork Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | B-5961 | Division 12 | BGOFF | 2021 | 67000 |  |  | 2022 | 705000 |  |  | 772000 | UNDER CONSTRUCTION.
Gaston | US 29 / US 74 | NCDOT | BRIDGE 350091 OVER CATAWBA RIVER | REPLACE BRIDGE. | 0.25 | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | B-6051 | Region F | HFB, HIB, T(M) | 2023 | 4000000 |  |  | 2026 | 76600000 |  |  | 80600000 | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143.
Gaston | I-85 | NCDOT | Cleveland County line to mile marker 14.0. | Rehabilitate pavement. | 5.91 | Highway | Interstate Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | I-5921 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 26400000 |  |  | 26400000
Gaston | NC 275 / NC 279 |  | US 321 to US 321 Business. | Extend right turn lane. Add right turn lane on southbound off ramp from US 321. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 12 | Gaston-Cleveland-Lincoln MPO | HN-0027 | Exempt | CRPANY, HF(M) |  |  |  |  | 2026 | 1040000 | 2024 | 205000 | 1245000 | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS
Gaston | Gastonia | NCDOT | Citywide. | Upgrade citywide signal system. |  | Highway | Other | 12 | Gaston-Cleveland-Lincoln MPO | C-5703 | Region F | CMAQ, L(M), T(M) | 2022 | 750000 |  |  | 2022 | 11363000 |  |  | 12113000 | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1).
Gaston |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | U-2523A | [11 empty] | COMPLETE
Gaston | NC 279 (New Hope Road) | NCDOT | Burtonwood Drive to SR 2466 (Garrison Boulevard) in Gastonia. | Construct turn lanes. | 0.53 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | C-4934 | Exempt | [10 empty] | UNDER CONSTRUCTION
Gaston | NC 274 | NCDOT | SR 1443 (Dameron Road) to SR 1405 (Ramseur Road). | Install rumble stripes. | 0.5 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5601R | Region F | HSIP, T(M) |  |  |  |  | 2023 | 90000 |  |  | 90000
Gaston | NC 275 | NCDOT | Mile marker 5.1 to mile marker 9.7. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012J | Region F | HSIP, T(M) |  |  |  |  | 2024 | 152000 |  |  | 152000
Gaston | NC 279 (Dallas Cherryville Highway) | NCDOT | South of SR 1438 (St. Mark's Church Road) to north of NC 275. | Construct safety improvements including passing zones. | 8.02 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5212N | Region F | T |  |  |  |  | 2021 | 12750000 |  |  | 12750000 | COMPLETE; BUILD NC BOND FUNDING: $9.912 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
Gaston | I-85 | NCDOT | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719B | Statewide Mobility | DP, NHP, T(M) | 2025 | 38400000 | 2025 | 47900000 | 2025 | 461505000 |  |  | 547805000 | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043.
Gaston | I-85 | NCDOT | NC 7 (McAdenville Road / Main Street) to NC 273. | Install and implement Intelligent Transportation System (ITS) components including Active Traffic Management and Incident Management. | 3.4 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FB | Statewide Mobility | DP, T(M) |  |  |  |  | 2025 | 7150000 |  |  | 7150000 | DP REPRESENTS 2022 INFRA GRANT.
Gaston | I-85 | NCDOT | South Carolina state line to NC 273 | Piedmont Northern Railroad bridge, two Norfolk Southern Railroad bridges, and Bridge 350142 over SR 2213 (Grove Street) within the limits of I-5719A |  | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719C | Statewide Mobility | NHP, T | 2026 | 3531000 | 2026 | 2600000 | 2026 | 232400000 |  |  | 238531000
Gaston | I-85 | NCDOT | US 321 interchange. | Construct geometric safety improvements to interchange. | 0.17 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5000 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Gaston | I-85 | NCDOT | US 321 to NC 273. | Widen to eight lanes. | 9.8 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719 | Statewide Mobility | [10 empty] | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT.
Gaston | I-85 | NCDOT | US 321 to NC 7 (McAdenville Road / Main Street) | Widen to eight lanes. | 6.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719A | Statewide Mobility | NHP, T | 2029 | 47200000 | 2029 | 12300000 | 2029 | 528205000 |  |  | 587705000 | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043.
Gaston | I-85 | NCDOT | US 321 to NC 7 (McAdenville Road / Main Street). | Install and implement Intelligent Transportation System (ITS) components including Active Traffic Management and Incident Management. | 6.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FA | Statewide Mobility | NHP, T(M) |  |  |  |  | 2028 | 4100000 |  |  | 4100000
Gaston | NC 27 (West Charlotte Avenue) | NCDOT | SR 2534 (Hawthorne Street) intersection in Mount Holly. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5819 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5200000 |  |  | 7600000
Gaston | NC 273 (South Main Street) | NCDOT | Tuckaseegee Road to A & E Drive in Mount Holly. | Widen to four lanes divided. | 1.1 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-3633 | Region F | T |  |  |  |  | 2021 | 6315000 |  |  | 6315000 | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746
Gaston | NC 274 (Union Road) | NCDOT | Osceola Street to Niblick Drive in Gastonia. | Upgrade roadway. | 1.02 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5961 | Region F | BG50200, O | 2028 | 25500000 | 2028 | 4100000 | 2031 | 24000000 |  |  | 53600000 | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA
Gaston | NC 275; SR 1327 (Fairview Road) | NCDOT | NC 274 and SR 1327 (Fairview Road) intersections in Gastonia; SR 1456 (White Jenkins Road) intersection in Gastonia. | Construct intersection improvements and close intersection of NC 275 and SR 1456 (White Jenkins Road). | 1.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6078 | Division 12 | BGANY | 2025 | 1400000 | 2025 | 780000 | 2027 | 7600000 |  |  | 9780000
Gaston | NC 279 | NCDOT | NC 7 to west of NC 275 in Dallas. | Widen to multi-lanes. | 3.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-2523 | Region F
Gaston | NC 279 | NCDOT | North of SR 2275 (Robinson-Clemmer Road) to west of NC 275 in Dallas. | Widen to multi-lanes. | 1.94 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-2523B | Region F | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39100000 |  |  | 60900000 | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778).
Gaston | NC 279 (New Hope Road) | NCDOT | SR 2478 (Titman Road) to SR 2435 (Union-New Hope Road) in Gastonia. | Widen to four lanes. | 0 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5821 | Division 12 | T | 2024 | 51200000 | 2026 | 17000000 | 2028 | 109800000 |  |  | 178000000 | RIGHT-OF-WAY IN PROGRESS.
Gaston | NC 279 (North New Hope Road) | NCDOT | US 29 / US 74 (Franklin Boulevard) intersection in Gastonia. | Construct right turn lane from NC 279 (North New Hope Road) to US 29 / US 74 (Franklin Boulevard). | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6138 | Region F | BG50200, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 880000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 70000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 2950000
Gaston | NC 7 | NCDOT | US 74 and US 29 intersections in Belmont. | Construct northbound through lane and intersection improvements. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5800 | Region F | BG50200 | 2025 | 18600000 | 2025 | 3700000 | 2025 | 19600000 |  |  | 41900000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. TO BE LET WITH I-5719B.
Gaston | NC 7 (East Catawba Street) | NCDOT | US 74 (Wilkinson Boulevard) intersection in Belmont. | Construct northbound right-turn lane on NC 7 (East Catawba Street) and extend existing westbound left-turn lane on US 74 (Wilkinson Boulevard). | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6143 | Region F | CRPDA, L, NHP | 2023 | 630000 | 2023 | 280000 | 2026 | 7300000 |  |  | 8210000 | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS.
Gaston | SR 2200 (Cox Road) | NCDOT | I-85 to US 29 / US 74. | Widen road and construct operational improvements. | 0.27 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6044 | Division 12 | BG50200, T(M) | 2029 | 49500000 | 2029 | 1500000 | 2029 | 14300000 |  |  | 65300000 | TO BE LET WITH I-5719.
Gaston | US 29 (Franklin Boulevard) | NCDOT | US 29 (Franklin Boulevard) and NC 274. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5965 | Region F | BG50200, T | 2023 | 6900000 | 2023 | 300000 | 2026 | 7200000 |  |  | 14400000 | RIGHT-OF-WAY IN PROGRESS.
Gaston | US 29 / US 74 (Franklin Boulevard) | NCDOT | SR 2200 (Cox Road) to 400 feet east of Lineberger Road. | Construct additional lane in the eastbound direction. | 1.06 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6043 | Division 12 | BG50200, T | 2023 | 1340000 | 2023 | 957000 | 2026 | 7900000 |  |  | 10197000 | RIGHT-OF-WAY IN PROGRESS.
Gaston | US 29 / US 74 (Wilkinson Boulevard) | NCDOT | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6146 | Region F | HFB, T | 2022 | 11780000 | 2021 | 5500000 | 2026 | 43500000 |  |  | 60780000 | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
Gaston | US 74 (Wilkinson Boulevard) | NCDOT | NC 7 (Catawba Street) to SR 2209 (Wesleyan Drive). | Implement adaptive signal system. | 3.87 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6038 | Division 12 | T |  |  |  |  | 2019 | 600000 |  |  | 600000 | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
Gaston | Gastonia Transit Authority |  | Various locations | Funding for capital rolling stock. |  | Public Transportation (Transit) | Capital (Non-STI) | 12 | Gaston-Cleveland-Lincoln MPO | TM-0047 | Public Transit | 5307, L | [6 empty] | 2025 | 1000000 | 1000000
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Gaston-Cleveland-Lincoln MPO | TO-5142 | Public Transit | SMAP | [6 empty] | 2020 | 1068000 | 1068000 | FUNDS AUTHORIZED IN PROGRESS
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Systemwide | Funding for operating expenses. |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Gaston-Cleveland-Lincoln MPO | TO-6061 | Public Transit | 5307, L | [6 empty] | 2025 | 4594000 | 4594000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Gastonia. | Purchase an electric ADA van. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TM-0058 | Public Transit | 5307, L |  |  |  |  | 2025 | 266000 |  |  | 266000
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6183A | Public Transit | 5307, L | [6 empty] | 2025 | 1250000 | 1250000
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Systemwide | Funding for Gastonia Transit payment kiosk. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TM-0045 | Public Transit | 5307, L | [6 empty] | 2023 | 219000 | 219000
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6184B | Public Transit | 5307, L | [6 empty] | 2025 | 427000 | 427000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
Gaston | Gastonia Transit Authority | GASTONIA TRANSIT | Systemwide | Funding for transit app. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6804 | Public Transit | 5307, L | [6 empty] | 2020 | 63000 | 63000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
Gaston | Gastonia Transit Authority | GASTON TRANSIT | Various locations | Improve pedestrian walkways. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6792 | Public Transit | 5307, L |  |  |  |  | 2024 | 458000 |  |  | 458000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
Gaston | Piedmont and Northern Railroad | NCDOT | Various locations | Construct crossing signal. |  | Rail | Other | 12 | Gaston-Cleveland-Lincoln MPO | P-5200A | [11 empty] | COMPLETE
Gaston | Piedmont and Northern Railroad | NCDOT | Various locations | Install crossing sign/pavement marking. |  | Rail | Other | 12 | Gaston-Cleveland-Lincoln MPO | P-5200B | [11 empty] | COMPLETE
Gaston | Piedmont and Northern Railroad | NCDOT | Various locations | Rail track construction engineering oversight. |  | Rail | Other | 12 | Gaston-Cleveland-Lincoln MPO | P-5200C | [11 empty] | COMPLETE
Gaston | SR 2412 (Little Mountain Road) | NCDOT | Norfolk Southern Crossing 729966J in Gastonia. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO | RX-2012H | Division 12 | RR |  |  |  |  | 2027 | 556000 |  |  | 556000
Gaston | Piedmont and Northern Railroad | NCDOT | Belmont Spur. | Reactivate rail corridor. |  | Rail | Transition | 12 | Gaston-Cleveland-Lincoln MPO | P-5200D | Pre-STI (Transition) | BGANY, T(M) | 2025 | 50000 |  |  | 2025 | 850000 |  |  | 900000
Gaston, Cleveland | I-85 | NCDOT | South Carolina state line to NC 273. | Implement Intelligent Transportation System (ITS) Statewide Resilience, connected vehicle technology, and traveler information. | 26.8 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FD | Statewide Mobility | DP, T(M) |  |  |  |  | 2025 | 6970000 |  |  | 6970000 | DP REPRESENTS 2022 INFRA GRANT.
Gaston, Cleveland | I-85 | NCDOT | Various locations. | Implement flood risk, vulnerability assessment, and flood warning system along the I-85 corridor. |  | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719D | Statewide Mobility | DP, T(M) | [6 empty] | 2025 | 200000 | 200000 | DP REPRESENTS 2022 INFRA GRANT.
Gaston, Cleveland, Lincoln | Various | NCDOT | Gaston Cleveland Lincoln Planning Organization (GCLMPO) area. | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | HL-0096 | Exempt | CRPDA, L(M) |  |  |  |  | 2024 | 1540000 |  |  | 1540000
Gaston, Cleveland, Lincoln | Various | NCDOT | Locations in Gaston-Cleveland-Lincoln MPO. | Improve congestion and air quality. |  | Highway | Other | 12 | Gaston-Cleveland-Lincoln MPO | C-5606 | Exempt | [10 empty] | "HF" FUNDS ON SEGMENT I REPRESENT CONTIGENCY FUNDS
Gaston, Iredell, Catawba | Various | NCDOT | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO, Greater Hickory MPO | W-5212REG | Region F
Gaston, Mecklenburg | Piedmont and Northern Railroad | NCDOT | Gastonia and Mount Holly, including the Belmont Spur. | Reactivate rail corridor. |  | Rail | Other | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO | P-5200
Gates, Chowan | NC 32 | NCDOT | NC 37 (Gliden Road) to Virginia State line. | Modernize roadway. | 17.27 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5938 | Division 1 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 49000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 160600000 |  |  | 225300000
Gates, Pasquotank | US 158 | NCDOT | SR 1002 (Acorn Hill Road) to Pasquotank County line. | Modernize roadway. | 3.99 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5808 | Division 1 | BGLT5, NHP | 2022 | 143000 |  |  | 2024 | 19701000 |  |  | 19844000 | UNDER CONSTRUCTION.
Graham | NC 143 | NCDOT | SR 1223 (Beech Creek Road) to north of Appalachian Trail. | Upgrade roadway. | 3.91 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CB | Exempt | ADHS | 2021 | 3300000 | 2021 | 1300000 | 2022 | 133871000 |  |  | 138471000 | UNDER CONSTRUCTION.
Graham | NC 143; NC 28 | NCDOT | North of Appalachian Trail to NC 28; NC 143 to west of SR 1228 (Stecoah Road). | Upgrade roadway. | 2.4 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CC | Exempt | ADHS | 2021 | 2300000 | 2021 | 550000 | 2023 | 77500000 |  |  | 80350000 | UNDER CONSTRUCTION.
Graham | NC 28 | NCDOT | Edwards Gap to east of SR 1231 (Tobacco Branch Road) | Upgrade roadway. | 2.859 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DD | [11 empty] | COMPLETE
Graham | NC 28 | NCDOT | West of SR 1228 (Stecoah Road) to existing four lanes east of SR 1235 (Gunter Gap Road) | Upgrade roadway. | 1.42 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CD | Exempt | ADHS, DP |  |  |  |  | 2026 | 48900000 |  |  | 48900000 | DP REPRESENTS FEDERAL NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS (NSFLTP) GRANT.
Graham | NC 28 | NCDOT | West of SR 1231 (Tobacco Branch Road) to Calfpen Gap. | Upgrade roadway. | 2.337 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DC | [11 empty] | COMPLETE
Graham | US 129; NC 143 | NCDOT | South of SR 1275 (Five Point Road) to NC 143; US 129 to SR 1223 (Beech Creek Road). | Upgrade roadway. | 4.14 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CA | Exempt | ADHS | 2021 | 1900000 | 2021 | 528000 | 2022 | 54624000 |  |  | 57052000 | UNDER CONSTRUCTION.
Graham | NC 28 | NCDOT | SR 1238 (Bill Crisp Road) to SR 1230 (Hyde Town Road). | Construct multi-use path. | 0.6 | Highway | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | A-0009CE | Exempt | CRPLT5 |  |  |  |  | 2024 | 5000000 |  |  | 5000000 | USE TOLL CREDITS ON A-0009CE.
Graham |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 14 | Southwestern RPO | R-2822A | [11 empty] | COMPLETE
Graham | NC 143 | NCDOT | Long Hungry Road intersection near Robbinsville. | Improve alignment and superelevation. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014G | Region G | HSIP, T(M) | 2024 | 2000 |  |  | 2025 | 516000 |  |  | 518000
Graham | NC 143 | NCDOT | Bridge 370013 over Santeetlah Lake. | Replace bridge. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822BB | Region G | T |  |  |  |  | 2027 | 33500000 |  |  | 33500000
Graham | NC 143 | NCDOT | West Buffalo Creek to NC 143 Business. | Upgrade corridor. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822
Graham | NC 143 | NCDOT | West Buffalo Creek to NC 143 Business. | Upgrade corridor. | 4.94 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822B | Region G | T | 2023 | 1100000 | 2023 | 1900000 |  |  |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS.
Graham | NC 143 | NCDOT | West Buffalo Creek to NC 143 Business. | Upgrade corridor. | 4.94 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822BA | Region G | T |  |  |  |  | 2030 | 40000000 |  |  | 40000000
Graham | NC 28 (Fontana Road) | NCDOT | East of SR 1245 (Fontana Dam Road) to SR 1287 (Cable Cove Road). | Upgrade roadway. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839C | Not Funded | T | NOT FUNDED | 90000 | NOT FUNDED | 20000 | NOT FUNDED | 58300000 | NOT FUNDED |  | 58410000
Graham | NC 28 (Fontana Road) | NCDOT | SR 1242 (Lower Tuskeegee Road) to NC 143. | Upgrade roadway. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839E | Not Funded | T | NOT FUNDED | 60000 | NOT FUNDED | 100000 | NOT FUNDED | 22000000 | NOT FUNDED |  | 22160000
Graham | NC 28 (Fontana Road) | NCDOT | SR 1287 (Cable Cove Road) to SR 1242 (Lower Tuskeegee Road). | Upgrade roadway. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839D | Not Funded | T | NOT FUNDED | 730000 | NOT FUNDED | 80000 | NOT FUNDED | 57500000 | NOT FUNDED |  | 58310000
Graham | NC 28 (Fontana Road) | NCDOT | Swain County / Graham County line at Little Tennessee River to Woods Road at Fontana Dam Village. | Upgrade roadway. | 1.14 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839BA | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17800000 |  |  | 18100000
Graham | NC 28 (Fontana Road) | NCDOT | Woods Road at Fontana Dam Village to east of SR 1245 (Fontana Dam Road). | Upgrade roadway. Realign intersection at NC 28 and SR 1245 (Fontana Dam Road). |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839BB | Not Funded | T | NOT FUNDED | 46332000 | NOT FUNDED | 80000 | NOT FUNDED | 37000000 | NOT FUNDED |  | 83412000
Graham | New Route | NCDOT | US 129 (Rodney Orr Bypass) to Robbinsville High School and Middle School in Robbinsville. | Construct new route including bridge over Cheoah River. | 0.31 | Highway | STI (Prioritization) | 14 | Southwestern RPO | U-5866 | Division 14 | [10 empty] | UNDER CONSTRUCTION
Graham, Cherokee | US 19/US 74/US 129; US 129 (Tallulah Road) | NCDOT | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009A | Not Funded | NHP, T(M) | NOT FUNDED | 14300000 | NOT FUNDED | 925000 | NOT FUNDED | 366000000 | NOT FUNDED |  | 381225000
Graham, Clay, Cherokee | Various | NCDOT | US, NC, and SR routes. | Install curve warning signs on multiple routes. |  | Highway | Safety | 14 | Southwestern RPO, Land-of-Sky RPO, Foothills RPO | HS-2414S | Region G | HSIP, T(M) |  |  |  |  | 2026 | 1575000 |  |  | 1575000
Graham, Swain | SR 1286 / SR 1383 (Tsali Road) | NCDOT | NC 28 to End of Maintenance. | Resurface and repair corridor. | 1.85 | Highway | Federal Lands Access Program | 14 | Southwestern RPO | HF-0007 | Exempt | FLAP, HF |  |  |  |  | 2025 | 3790000 | 2023 | 150000 | 3940000 | FLAP PROJECT NC 65. AWARDED $1.2M.
Graham, Swain | NC 28 (Fontana Road) | NCDOT | US 129 to NC 143. | Upgrade roadway. | 20.4 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839
Graham, Swain, Cherokee | US 19; US 74; US 129; NC 28; NC 143 | NCDOT | Corridor "K" in Andrews to NC 28 east of Almond. | Upgrade roadway to include existing facilities and construct new location. | 27.1 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009
Granville | NC 56 | CREEDMOOR | Greenway along NC 56 in Creedmoor | Construct bike-pedestrian trail system. | 2.76 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | C-5166 | Exempt | [10 empty] | PROJECT COMPLETE BY TOWN OF CREEDMOOR; LET WITH EB-5513
Granville | NC 56 | CREEDMOOR | Greenway in Creedmoor - Western section. | Construct bicycle-pedestrian trail system. | 1.15 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | C-5166B | Exempt | [10 empty] | PROJECT COMPLETE
Granville | SR 1646 (East Industry Drive) |  | 250 feet west of the intersection of US 15 (Lewis Street) and SR 1646 (East Industry Drive) to Speed EEZ Carwash driveway | Construct sidewalk. | 0.85 | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | C-5610B | Exempt | CMAQ, L(M) |  |  |  |  | 2025 | 961000 |  |  | 961000
Granville | NC 56 | CREEDMOOR | Greenway in Creedmoor - Eastern section. | Construct bicycle-pedestrian trail system. | 1.61 | Bike & Ped | Transition | 5 | Capital Area MPO | C-5166A | Exempt | [10 empty] | PROJECT COMPLETE
Granville | SR 1442 (Dave Winston Road) | NCDOT | Bridge 380143 over Johnson Creek. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Kerr-Tar RPO | B-5323 | Division 5 | BFPOFF |  |  |  |  | 2023 | 4183000 |  |  | 4183000 | UNDER CONSTRUCTION
Granville | SR 1629 (Flat Rock Road) | NCDOT | Bridge 380199 over Fork Creek | Replace bridge. |  | Highway | Bridges | 5 | Capital Area MPO | HB-0072 | Division 5 | BGOFF, HP, T(M) |  |  |  |  | 2026 | 2201000 |  |  | 2201000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077.
Granville | SR 1120 (Veazey Road) |  | SR 1239 (Central Avenue) and SR 1174 (Westbrook Drive) intersection in Butner. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | HN-0024 | Exempt | CRPLT5, HF(M), L(M), T(M) |  |  |  |  | 2026 | 2009000 | 2024 | 700000 | 2709000 | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS
Granville | US 15 |  | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0017 | Exempt | CMAQ, HF(M) | 2026 | 140000 |  |  | 2027 | 1636000 | 2024 | 442000 | 2218000 | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS
Granville | US 158 |  | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | HN-0015 | Region C | CMAQ, CRPLT5, T(M) | 2026 | 156000 |  |  | 2027 | 1945000 | 2024 | 700000 | 2801000
Granville | NC 96 (Martin Luther King Jr. Avenue) | NCDOT | SR 1646 (East Industry Drive) intersection | Install/upgrade pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405N | Region C | HSIP, T(M) |  |  |  |  | 2026 | 284000 |  |  | 284000
Granville | SR 1602 (Main Street) | NCDOT | SR 1207 (Spring Street) intersection in Oxford. | Construct mini-roundabout. |  | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005A | Division 5 | HSIP, T(M) |  |  |  |  | 2021 | 100000 |  |  | 100000 | UNDER CONSTRUCTION
Granville | US 15 | NCDOT | I-85 to Virginia state line | Install rumble stripes. | 37 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AE | Region C | HSIP, T(M) |  |  |  |  | 2026 | 1104000 |  |  | 1104000
Granville | US 158 (Oxford Loop Road) | NCDOT | US 158 Business (Williamsboro Street) / SR 1646 (Southeast Industry Drive) intersection. | Upgrade traffic signal. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405A | Region C | HSIP, T(M) |  |  |  |  | 2025 | 43000 |  |  | 43000 | UNDER CONSTRUCTION
Granville | NC 56 | NCDOT | US 15 and NC 50 intersections in Creedmoor. | Realign intersections. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-5707 | Region C | T |  |  |  |  | 2019 | 4988000 | 2021 | 989000 | 5977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Granville | NC 56 (East C Street) | NCDOT | SR 1215 (West Lyon Station Road) intersection in Butner. | Realign intersection. | 0.5 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-6020 | Division 5 | L, T | 2024 | 100000 |  |  | 2025 | 8200000 |  |  | 8300000 | UNDER CONSTRUCTION; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER
Granville | Church Street | NCDOT | Norfolk Southern crossing 734 896G in Stem | Close railway-highway crossing. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Kerr-Tar RPO | Y-5500ED | Division 5 | RR |  |  |  |  | 2025 | 300000 |  |  | 300000
Granville | SR 1136 (Tally Ho Road) | NCDOT | Norfolk Southern crossing 734 895A in Stem | Close railway-highway crossing. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Kerr-Tar RPO | Y-5500EC | Division 5 | RR |  |  |  |  | 2025 | 150000 |  |  | 150000
Granville, Durham | I-85 / US 15 | NCDOT | North of SR 1637 (Redwood Road) in Durham County to south of US 15 / SR 1100 (Gate One Road) in Granville County. | Rehabilitate pavement. | 2.03 | Highway | Interstate Maintenance | 5 | Triangle West TPO, Capital Area MPO, Kerr-Tar RPO | HI-0001 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 5665000 |  |  | 5665000 | UNDER CONSTRUCTION
Granville, Franklin, Person | Various | HENDERSON COUNTY | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Highway | Other | 5 | Kerr-Tar RPO | C-5610 | Exempt | CMAQ, L(M) | 2020 | 105000 |  |  | 2020 | 618000 | 2020 | 315000 | 1038000 | IN PROGRESS
Granville, Person | US 158 | NCDOT | Hardwood Drive in Person County to US Tobacco Cooperative driveway in Granville County. | Install rumble stipes. | 3.7 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AM | Statewide Mobility | HSIP |  |  |  |  | 2026 | 1331000 |  |  | 1331000
Granville, Vance, Person | Various | NCDOT | Secondary routes in Division 5 | Install long life pavement markings. |  | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405F | Division 5 | HSIP, T(M) |  |  |  |  | 2024 | 1850000 |  |  | 1850000
Greene | US 264 (Future I-587) | NCDOT | Pitt County line to Wilson County line. | Rehabilitate pavement. | 4.18 | Highway | Interstate Maintenance | 2 | Eastern Carolina RPO | I-6032 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 4830000 |  |  | 4830000 | COMPLETE. LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033.
Greene | US 13 | NCDOT | SR 1104 (Hull Road) intersection in Snow Hill | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5943 | Division 2 | BGLT5, T(M) | 2028 | 4700000 | 2026 | 600000 | 2028 | 10500000 |  |  | 15800000
Greene | US 13 Bypass | NCDOT | NC 58 (Kingold Boulevard) to NC 91. | Widen to three lanes with center turn lane. | 1.18 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5812 | Division 2 | L, T |  |  |  |  | 2020 | 9165000 | 2020 | 1290000 | 10455000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Greene, Lenoir | NC 58 | NCDOT | North of SR 1745 (Cunningham Road) in Lenoir County to northwest of Carolina Drive in Greene County; Northwestern intersection of US 13 to Wilson County line in Greene County | Install rumble stripes. |  | Highway | Safety | 2 | Eastern Carolina RPO | HS-2402V | Region B | HSIP |  |  |  |  | 2025 | 660000 |  |  | 660000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Construct northwest apron to increase capacity for future expansion. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5802 | Statewide Mobility | O, T |  |  |  |  | 2028 | 11000000 |  |  | 11000000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Construct taxiway F including bridge over Ted Johnson Parkway. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5803 | Statewide Mobility | O, T |  |  |  |  | 2028 | 28000000 |  |  | 28000000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Construct Taxiway G. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5707 | Statewide Mobility | O, T |  |  |  |  | 2026 | 16900000 |  |  | 16900000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Construct taxiway over future I-73 east of SR 2085 (Bryan Boulevard). |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5708 | Statewide Mobility | T |  |  |  |  | 2020 | 1500000 |  |  | 1500000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Extend runway 5R-23L. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5701 | Statewide Mobility | O, T |  |  |  |  | 2026 | 21000000 |  |  | 21000000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Extend taxiway J from taxiway D to taxiway J2. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5800 | Statewide Mobility | O, T |  |  |  |  | 2027 | 7000000 |  |  | 7000000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | High speed taxiway to runway 5R-23L. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5718 | Statewide Mobility | O, T |  |  |  |  | 2026 | 4000000 |  |  | 4000000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Runway 5R-23L group VI upgrade. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5715 | Statewide Mobility | O, T |  |  |  |  | 2028 | 11000000 |  |  | 11000000
Guilford | GSO | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | Piedmont Triad International Airport | Surface Movement Guidance and Control System (SMGSC) update. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5711 | Statewide Mobility | O, T |  |  |  |  | 2027 | 9000000 |  |  | 9000000 | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY
Guilford | A & Y Greenway | GREENSBORO | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0117 | Division 7 | L(M), TAANY | 2026 | 10000 |  |  | 2025 | 2428000 | 2024 | 110000 | 2548000
Guilford | A & Y Greenway | GREENSBORO | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0116 | Division 7 | HP, L(M), TAANY | 2026 | 938000 | 2026 | 10000 | 2027 | 5813000 | 2024 | 1100000 | 7861000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205.
Guilford | A&Y Greenway | City of Greensboro | Old Lake Brandt to Bur-Mil Park | Repair greenway surface. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0169 | Division 7 | BGDA, L(M) | 2026 | 53000 |  |  | 2027 | 3590000 |  |  | 3643000
Guilford | Big Tree Way; Shelby Drive; Hewitt Street; Bridford Parkway and Hornaday Road | GREENSBORO | Wendover Avenue to Elkhound Trail; Big Tree Way to Edith Lane; Norwolk Street to Merritt Drive; Wendover Avenue to existing west of Nicholas Road | Construct sidewalks. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532E | Division 7 | L(M), TADA |  |  |  |  | 2023 | 2436000 |  |  | 2436000 | UNDER CONSTRUCTION
Guilford | Elm Street | HIGH POINT | Sunset Drive to Commerce Avenue. | Construct pedestrian, bicycle, roadway, and streetscape improvements. |  | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | BL-0071B | Exempt | DP, L, O |  |  |  |  | 2026 | 13864000 |  |  | 13864000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING.
Guilford | High Point | HIGH POINT | Harvell Park to Goldston Park; Sunset Drive to Commerce Avenue | Construct greenway on new location connecting Harvell Park and Goldston Park; Construct pedestrian, bicycle, roadway, and streetscape improvements. | 4.3 | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | BL-0071 | Exempt | DP | 2026 | 2000000 |  |  |  |  | 2023 | 5000000 | 7000000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING.
Guilford | Latham Park Greenway; Lake Daniel Greenway | GREENSBORO | Friendly Avenue to Josephine Boyd Street; Tennis courts near Wendover Avenue in Greensboro | Repair surfaces. | 1.33 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0041 | Division 7 | L(M), TAANY, TAP |  |  |  |  | 2026 | 1133000 |  |  | 1133000 | Under Construction
Guilford | Murrow Boulevard | GREENSBORO | Murrow Boulevard bridge over Church Street | Repair bridge deck and complete greenway across structure. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | EL-5101DR | Division 7 | BGDA, L(M) |  |  |  |  | 2023 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION
Guilford | Rudd Station Road | GREENSBORO | Scott Road to Townsend Road near Greensboro. | Construct sidewalk. | 0.63 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532C | Division 7 | L(M), TAANY |  |  |  |  | 2026 | 370000 |  |  | 370000
Guilford | Southwest Heritage Greenway | HIGH POINT | Harvell Park to Goldston Park in High Point. | Construct greenway on new location. | 0.72 | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | BL-0071A | Exempt | DP, HF, L |  |  |  |  | 2026 | 7826000 |  |  | 7826000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS.
Guilford | SR 1352 (Oakdale Road) | JAMESTOWN | Existing sidewalk east of East Main Street to Chimney Court in Jamestown | Extend sidewalk. | 0.53 | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | C-5700 | Exempt | CMAQ, L(M) |  |  |  |  | 2025 | 170000 | 2024 | 10000 | 180000
Guilford | Vance Arlington Greenway | GREENSBORO | North of Florida Street to Bragg Street in Greensboro | Construct greenway and side path. | 0.81 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0042 | Division 7 | L(M), TAANY |  |  |  |  | 2026 | 1200000 |  |  | 1200000
Guilford | Various | GREENSBORO | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532 | Division 7 | BGANY, BGDA, L(M), TAANY, TADA | 2021 | 748000 |  |  | 2021 | 16154000 | 2023 | 100000 | 17002000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Various | GREENSBORO | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532I | Division 7 | L(M), TADA | 2026 | 400000 |  |  | 2027 | 1168000 | 2024 | 90000 | 1658000
Guilford | Various | GREENSBORO | Holden Road from Walker Avenue to Spring Garden Street - both sides, Holden Road from Darden Road to Vandalia Road - west side, Holden Road from Madison Avenue to Walker Avenue - both sides, Rankin Road / Martin Avenue | Install sidewalk. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532F | Division 7 | L(M), TADA |  |  |  |  | 2026 | 1898000 |  |  | 1898000
Guilford | Various | GREENSBORO | Locations in Greensboro | Construct sidewalk improvements. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532G | Division 7 | L(M), TADA | 2022 | 70000 | 2022 | 5000 | 2026 | 1150000 |  |  | 1225000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Various | GREENSBORO | North side of Seminole Drive from Josephine Boyd Street; north side of Whippoorwill Drive from Pennydale Drive to Jane Street; and north side of West Bessemer Avenue from Grecade Street to Hill Street. | Install sidewalk. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532H | Division 7 | L(M), TADA |  |  |  |  | 2026 | 670000 |  |  | 670000
Guilford | Various | GREENSBORO | SR 1546 (College Road) and SR 2179 (New Garden Road) in Greensboro. | Construct sidewalks. | 0.86 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | C-5555E | Exempt | BGDA, CMAQ, L(M) |  |  |  |  | 2022 | 1153000 |  |  | 1153000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Various | NCDOT | Greensboro Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-6220 | Division 7 | TADA |  |  |  |  | 2024 | 3332000 |  |  | 3332000
Guilford | A&Y Greenway | GREENSBORO | Spring Garden Street to South of Rollins Road in Greensboro. | Construct multi-use path. | 3.08 | Bike & Ped | Other | 7 | Greensboro Urban Area MPO | EB-6037C | Division 7 | BGANY, L(M), TAANY |  |  |  |  | 2023 | 8936000 |  |  | 8936000
Guilford | Various | GREENSBORO | Locations in the Greensboro Urban Area MPO | Pedestrian and bicycle projects in the Greensboro Urban Area Metropolitan Planning Organization (GUAMPO). |  | Bike & Ped | Other | 7 | Greensboro Urban Area MPO | EL-5101 | Division 7 | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS
Guilford | Various | GREENSBORO | Locations in Greensboro | Construct sidewalks. |  | Bike & Ped | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | C-5555 | Exempt | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO
Guilford | Benjamin Parkway | GREENSBORO | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5986 | Division 7 | L(M), TAANY | 2028 | 1700000 | 2028 | 10000 | 2031 | 5200000 | 2024 | 40000 | 6950000
Guilford | Cedrow Drive | HIGH POINT | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5989 | Division 7 | L(M), TA50200 | 2029 | 160000 | 2029 | 80000 | 2031 | 3800000 | 2025 | 120000 | 4160000
Guilford | Cone Boulevard | GREENSBORO | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5985 | Division 7 | L(M), TAANY | 2028 | 500000 | 2028 | 10000 | 2031 | 6900000 | 2022 | 150000 | 7560000
Guilford | Farmington Drive | GREENSBORO | Holden Road to SR 4121 (West Gate City Boulevard) in Greensboro | Construct sidewalks. | 0.97 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5877 | Division 7 | L(M), TAANY | 2022 | 25000 |  |  | 2026 | 1200000 |  |  | 1225000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Green Valley Road | GREENSBORO | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5997 | Division 7 | L(M), TAANY | 2028 | 2500000 | 2028 | 1400000 | 2031 | 1900000 | 2025 | 263000 | 6063000
Guilford | Holden Road | GREENSBORO | SR 4121 (West Gate City Boulevard) to Isler Street in Greensboro | Construct sidewalks. | 1.56 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5876 | Division 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
Guilford | Holden Road; East Lindsay Street | GREENSBORO | South of Meadowview Road to Spring Garden Road; Murrow Boulevard to Bessemer Avenue in Greensboro | Construct sidewalk. | 0.89 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5716 | Division 7 | [10 empty] | UNDER CONSTRUCTION
Guilford | Lawndale Drive | GREENSBORO | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5995 | Division 7 | L(M), TAANY | 2028 | 2300000 | 2028 | 60000 | 2031 | 1800000 | 2024 | 60000 | 4220000
Guilford | NC 68 (Eastchester Drive) | HIGH POINT | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5922 | Division 7 | L(M), TA50200 | 2027 | 130000 | 2027 | 460000 | 2027 | 540000 |  |  | 1130000
Guilford | NC 68 (Eastchester Drive) | HIGH POINT | Johnson Street to SR 1278 (University Parkway) in High Point | Construct sidewalk. | 0.65 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5874 | Division 7 | L(M), TA50200 |  |  |  |  | 2025 | 850000 |  |  | 850000
Guilford | Old Battleground Road | GREENSBORO | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5987 | Division 7 | L(M), TAANY | 2028 | 870000 | 2028 | 10000 | 2031 | 4300000 | 2024 | 99000 | 5279000
Guilford | SR 1001 (North Church Street) | GREENSBORO | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5996 | Division 7 | L(M), TAANY | 2026 | 100000 | 2026 | 10000 | 2027 | 4500000 |  |  | 4610000
Guilford | SR 1278 (University Parkway) | HIGH POINT | SR 1300 (East Green Drive) to SR 1113 (East Martin Luther King Jr. Drive) in High Point | Construct sidewalk. | 0.6 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5873 | Division 7 | L(M), TA50200 |  |  |  |  | 2025 | 430000 |  |  | 430000
Guilford | SR 1486 (West Main Street); SR 1539 (Penny Road) | JAMESTOWN | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5889 | Division 7 | L(M), TA50200 | 2027 | 2500000 | 2027 | 1900000 | 2030 | 4101000 |  |  | 8501000
Guilford | Summerfield South Greenway | SUMMERFIELD | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5900 | Division 7 | L(M), TAANY | 2025 | 540000 | 2026 | 180000 | 2026 | 6800000 |  |  | 7520000
Guilford | US 220 (Wendover Avenue) | GREENSBORO | Grecade Street to SR 1001 (North Church Street) and SR 2526 (Summit Avenue) to US 29 (North O'Henry Boulevard) in Greensboro | Construct sidewalks. | 2.21 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5883 | Division 7 | L(M), TAANY | 2026 | 296000 |  |  | 2028 | 2811000 |  |  | 3107000
Guilford | West Meadowview Road | GREENSBORO | SR 1007 (Randleman Road) to South Elm-Eugene Street in Greensboro | Construct sidewalks. | 0.47 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5878 | Division 7 | L(M), TAANY | 2022 | 50000 |  |  | 2026 | 950000 |  |  | 1000000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Latham Park Greenway | GREENSBORO | Battleground Avenue to Mendenhall Street in Greensboro | Remove through lane on Hill Street and construct multi-use path. | 0.11 | Bike & Ped | Transition | 7 | Greensboro Urban Area MPO | EB-5518 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
Guilford | New Pedestrian Bridge And Approaches | HIGH POINT | Existing sidewalk to Piedmont Environmental Center entrance in High Point and Jamestown | Construct pedestrian bridge over east fork of Deep River. | 0.5 | Bike & Ped | Transition | 7 | High Point Urban Area MPO | EB-5517 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
Guilford | SR 4121 (East Main Street) | JAMESTOWN | Existing sidewalk near Jamestown Municipal Building to Yorkleigh Lane near Guilford Technical Community College Jamestown Campus / Ragsdale High School complex in Jamestown | Construct sidewalk. | 0.57 | Bike & Ped | Transition | 7 | High Point Urban Area MPO | EB-5519 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
Guilford | I-40 / Business 85 / US 29 / US 70 / US 220 | NCDOT | Bridge 400299 over South Buffalo Creek in Greensboro. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5356 | Statewide Mobility | BFP, T(M) |  |  |  |  | 2032 | 11700000 |  |  | 11700000 | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965
Guilford | Patton Avenue | NCDOT | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5718 | Division 7 | BFP, T(M) | 2027 | 218000 |  |  | 2028 | 3350000 |  |  | 3568000 | COORDINATEWITH I-5965
Guilford | Phillips Avenue | NCDOT | Bridges 400283 and 400342 over US 29 / US 70 / US 220 | Replace bridge. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0081 | Division 7 | BFP, T(M) | 2027 | 1150000 |  |  | 2029 | 11500000 |  |  | 12650000
Guilford | SR 1158 (Jackson Lake Road) | NCDOT | Bridge 400054 over Richland Creek in High Point. | Replace bridge. | 0.25 | Highway | Bridges | 7 | High Point Urban Area MPO | B-5723 | Division 7 | BGOFF | 2030 | 30000 | 2030 | 570000 | 2031 | 3100000 |  |  | 3700000
Guilford | SR 2128 (Bunch Road) | NCDOT | Bridge 400106 over Reedy Fork Creek in Oak Ridge. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-4958 | Division 7 | [10 empty] | UNDER CONSTRUCTION
Guilford | SR 2770 (Huffine Mill Road) over US 70 (East Wendover Avenue) |  | Bridge 400131 | Replace bridge. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0077 | Division 7 | HFB, T(DA) | 2025 | 5567000 | 2025 | 560000 | 2028 | 18701000 |  |  | 24828000
Guilford | SR 4240 (Gate City Boulevard) | NCDOT | Bridges 400109 and 400121 over South Buffalo Creek in Greensboro. | Replace bridges. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5717 | Division 7 | BFP, HF | 2021 | 710000 | 2021 | 165000 | 2022 | 8957000 |  |  | 9832000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
Guilford | Sullivan Street | NCDOT | Bridge 400331 over US 29 / US 70 / US 220 | Replace bridge. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0080 | Division 7 | BGOFF | 2025 | 805000 | 2025 | 100000 | 2028 | 7400000 |  |  | 8305000
Guilford | Tuscaloosa Street | NCDOT | Bridge 400302 over US 29 / US 70 / US 220 | Replace bridge. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0079 | Division 7 | BGOFF | 2026 | 1200000 | 2026 | 2000000 | 2028 | 7700000 |  |  | 10900000
Guilford | Willow Road | NCDOT | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5713 | Division 7 | BFP, T(M) | 2028 | 510000 | 2028 | 1200000 | 2031 | 15200000 |  |  | 16910000
Guilford | NC 61 |  | Guilford County | NC 61 road widening, turn lanes and installation of two signals. NCDOT will add a right turn lane on the I-40 / I-85 north-bound exit ramp plus signal modifications and install left turn lane on I-40 / I-85 south-bound exit ramp and add signal. |  | Highway | Economic Development | 7 | Burlington-Graham MPO | HE-0019 | Division 7 | T |  |  |  |  | 2026 | 500000 |  |  | 500000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AHOLD DELHAIZE USA.
Guilford | Piedmont Triad International Airport manufacturing site | NCDOT | Piedmont Triad International Airport manufacturing site in Greensboro. | Construct road improvements. |  | Highway | Economic Development | 7 | Greensboro Urban Area MPO | HE-0005 | Exempt | HF | 2022 | 1000000 | 2022 | 500000 | 2023 | 30000000 |  |  | 31500000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION
Guilford | I-40 | NCDOT | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate bridges 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, and 400285. | 5.01 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5955A | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2024 | 8300000 |  |  | 8300000
Guilford | I-40 | NCDOT | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate pavement. | 5 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5955 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2023 | 13224000 |  |  | 13224000 | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356
Guilford | I-73 | NCDOT | I-85 to SR 2085 (Bryan Boulevard) in Greensboro. | Rehabilitate pavement and bridge. | 10.7 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5852
Guilford | I-73 / I-840 | NCDOT | I-40 to SR 2085 (Bryan Boulevard). | Rehabilitate pavement. | 3.26 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5852B | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Guilford | I-73 / US 421 | NCDOT | I-85 to I-40. | Rehabilitate pavement. | 6.62 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5852A | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Guilford | I-785 / I-840 | NCDOT | I-85 to US 70. | Rehabilitate pavement. | 2.14 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5953 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Guilford | I-85 | NCDOT | Randolph County line to SR 1113 (Kivett Drive). | Rehabilitate pavement. | 4.5 | Highway | Interstate Maintenance | 7 | High Point Urban Area MPO | I-5821 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789
Guilford | Lindley Road | GREENSBORO | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0126 | Division 7 | BGANY, L(M) |  |  | 2024 | 10000 | 2026 | 2304000 | 2024 | 10000 | 2324000
Guilford | Murrow Boulevard | City of Greensboro | Bridge #400462 | Rehabilitate bridge. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0168 | Division 7 | BGDA, L(M) |  |  |  |  | 2026 | 5840000 |  |  | 5840000
Guilford | SR 1001 (Church Street) | NCDOT | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0164 | Division 7 | HF, HSIP, T(DA) | 2027 | 750000 | 2027 | 750000 | 2028 | 2750000 | 2025 | 500000 | 4750000 | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS.
Guilford | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | GREENSBORO | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0047 | Division 7 | BGANY, BGDA, L | 2026 | 70000 |  |  | 2027 | 750000 | 2024 | 10000 | 830000
Guilford | SR 4240 (East Gate City Boulevard) | GREENSBORO | Willow Road to Florida Street in Greensboro. | Modernize roadway, add curb and gutter, and construct sidewalks. | 0.91 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0046 | Division 7 | BGDA, L(M), T(DA) | 2023 | 250000 | 2026 | 100000 | 2026 | 4500000 |  |  | 4850000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Various | GREENSBORO | Locations in Greensboro. | Pedestrian signal installation, accessible ramp construction, and traffic signal replacement at various intersections in Greensboro. | 0.5 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0048 | Division 7 | BGDA, BGDACV, L(M) | 2026 | 10000 |  |  | 2027 | 1000000 | 2022 | 255000 | 1265000
Guilford | Various | HIGH POINT | Routes in High Point | High Point signal system retiming study. |  | Highway | Locally Selected | 7 | High Point Urban Area MPO | HL-0060 | Exempt | CMAQ, L(M) | [6 empty] | 2023 | 1523000 | 1523000
Guilford | Various | NCDOT | Greensboro Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0098 | Exempt | CRPDA, L(M) |  |  |  |  | 2025 | 1840000 |  |  | 1840000
Guilford | Various | NCDOT | Greensboro Urban Area Metropolitan Planning Organization (GUAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | U-5021 | Division 7 | BGANY, BGDA |  |  |  |  | 2025 | 73005000 |  |  | 73005000 | STBG-ANYAREA FUNDS PROVIDED AS PART OF FUNDING SWAP. STATE TRUST FUNDS COULD BE USED IN LIEU OF STBG-ANYAREA ON AN ELIGIBLE STI HIGHWAY PROJECT IF DESIRED.
Guilford | Various | NCDOT | Greensboro Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | U-6085 | Division 7 | BGDA, L(M) | [6 empty] | 2022 | 9106000 | 9106000 | IN PROGRESS
Guilford | Various Routes | City of Greensboro | in Greensboro | Upgrade signal system, Phase 1. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0165 | Division 7 | BGDA, L(M), T(DA) |  |  |  |  | 2027 | 2055000 | 2026 | 875000 | 2930000
Guilford | I-85 |  | Triad Traffic Management Center | Upgrade traffic management center. |  | Highway | Other | 7 | Greensboro Urban Area MPO | C-5600U | Exempt | CMAQ, T(M) |  |  |  |  | 2025 | 1648000 |  |  | 1648000
Guilford | I-85 | NCDOT | Guilford County | Extend traffic management system. |  | Highway | Other | 7 | Greensboro Urban Area MPO | C-5600E | Exempt | CMAQ, T(M) |  |  |  |  | 2025 | 1661000 |  |  | 1661000
Guilford | SR 1352 (Oakdale Road) | JAMESTOWN | Chimney Court to Jamestown Oaks Drive in Jamestown. | Construct sidewalks and pedestrian improvements. |  | Highway | Other | 7 | High Point Urban Area MPO | C-5609F | Exempt | CMAQ, L(M) | 2026 | 40000 |  |  | 2026 | 550000 |  |  | 590000
Guilford | Various | GREENSBORO | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Highway | Other | 7 | Greensboro Urban Area MPO | C-5607 | Exempt | CMAQ, L(M) | 2020 | 360000 |  |  | 2020 | 2154000 | 2020 | 1080000 | 3594000
Guilford | Various | HIGH POINT | Locations in High Point MPO. | Construct sidewalks. |  | Highway | Other | 7 | High Point Urban Area MPO | C-5609L | Exempt | CMAQ, HSIP, L(M) |  |  |  |  | 2026 | 1860000 | 2026 | 50000 | 1910000 | RIGHT-OF-WAY IN PROGRESS
Guilford | Various | HIGH POINT | Routes in High Point. | Expand and upgrade signal system in High Point. |  | Highway | Other | 7 | High Point Urban Area MPO | C-5558 | Exempt | [10 empty] | UNDER CONSTRUCTION
Guilford | Future I-840 | NCDOT | Greensboro Western Loop, north of SR 2176 (Bryan Boulevard) to US 220 (Battleground Avenue) | Construct roadway. | 3.54 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524C | Pre-STI (Transition) | NHP |  |  |  |  | 2013 | 54285000 |  |  | 54285000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING $105.9 MILLION; PAYBACK FY 2013-2024
Guilford | I-73 / I-840 | NCDOT | Greensboro Western Loop | Install ITS. |  | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524E | [11 empty] | COMPLETE
Guilford | I-73 / I-840 | NCDOT | Greensboro Western Loop, north of SR 2147 (West Friendly Avenue) to north of SR 2176 (Bryan Boulevard) | Construct roadway. | 1.872 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524BB | [11 empty] | COMPLETE
Guilford | I-73 / I-840 | NCDOT | Greensboro Western Loop, south of I-40 to north of SR 2147 (West Friendly Avenue) | Construct roadway. | 2.429 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524BA | [11 empty] | COMPLETE
Guilford | I-73 / US 421 | NCDOT | Greensboro Western Loop, interchange at proposed SR 4121 (High Point Road) relocation | Construct interchange. | 1 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AE | [11 empty] | UNDER CONSTRUCTION
Guilford | I-73 / US 421 | NCDOT | Greensboro Western Loop, north of I-85 near SR 1129 (Groometown Road) to north of SR 4121 (High Point Road) | Construct roadway. | 4.207 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AB | [11 empty] | COMPLETE
Guilford | I-73 / US 421 | NCDOT | Greensboro Western Loop, north of SR 4121 (High Point Road) to south of I-40 | Construct roadway. | 3.471 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AC | [11 empty] | COMPLETE
Guilford | I-785 / I-840 | NCDOT | Greensboro Eastern Loop, south of SR 3041 (Clapp Farms Road) to US 70 relocation | Relocate roadway. | 1.809 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2525A | [11 empty] | COMPLETE
Guilford | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | NCDOT | SR 4228 (Vickrey Chapel Road) to SR 1424 (Hilltop Road) | Widen roadway. | 4.35 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | U-2412B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Guilford | SR 1546 (Guilford College Road) | NCDOT | South of SR 1541 (Wendover Avenue) to north of SR 1560 (Sapp Road) | Construct roadway. | 1.244 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AA | [11 empty] | COMPLETE
Guilford | SR 1556 (Gallimore Dairy Road) | NCDOT | Airpark Road to SR 1008 (West Market Street) in Greensboro | Widen to multi-lanes. |  | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-4015B | [11 empty] | COMPLETE
Guilford | US 220 (Battleground Avenue) | NCDOT | Brassfield Road intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-5306D | [11 empty] | PROJECT COMPLETE
Guilford | US 421 | NCDOT | SR 3389 (Woody Mill Road) intersection south of Greensboro. | Upgrade at-grade intersections to interchanges. | 0.702 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | R-2612A | [11 empty] | COMPLETE
Guilford | US 421 (Future I-685) | NCDOT | SR 3389 (Woody Mill Road) and SR 3418 (Neelley Road) south of Greensboro. | Upgrade at-grade intersections to interchanges. | 2 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | R-2612 | Exempt
Guilford | I-40 | NCDOT | Buffalo Creek Bridge east For 1,550 feet and I-40 Exit 219 to US 29 South. | Install guardrail. | 0.4 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007K | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 325000 |  |  | 325000
Guilford | I-74 | NCDOT | US 29 / US 70 (I-85 Business) interchange. | Upgrade signals, pavement markings, and signing. | 1 | Highway | Safety | 7 | High Point Urban Area MPO | HS-2007D | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 400000 |  |  | 400000
Guilford | I-85 Business / US 29 / US 70 | NCDOT | Randolph County line to north of SR 1145 (Riverdale Drive) in High Point. | Install guardrail. | 6.52 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007A | Region D | HSIP, T(M) |  |  |  |  | 2021 | 540000 |  |  | 540000 | UNDER CONSTRUCTION
Guilford | I-85 Business / US 29 / US 70 Northbound | NCDOT | North of SR 1145 (Riverdale Drive) to I-85 in High Point. | Install guardrail. | 3.13 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007B | Region D | HSIP, T(M) |  |  |  |  | 2021 | 270000 |  |  | 270000 | UNDER CONSTRUCTION
Guilford | NC 62 | NCDOT | West of SR 1138 (Tom Ball Road) to west of the Alamance County line. | Install pavement markings. | 20.69 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007E | Division 7 | HSIP, T(M) |  |  |  |  | 2023 | 401000 |  |  | 401000 | UNDER CONSTRUCTION
Guilford | SR 1007 (Randleman Road) | NCDOT | Webster Road intersection | Install traffic signal. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2407B | Division 7 | HSIP | 2025 | 5000 | 2025 | 40000 | 2026 | 145000 |  |  | 190000
Guilford | SR 2526 (Summit Avenue) | NCDOT | Textile Drive intersection | Install pedestrian signal heads, crosswalks, and other intersection improvements. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2407A | Division 7 | HSIP, T(M) |  |  | 2024 | 4000 | 2025 | 70000 |  |  | 74000
Guilford | SR 4240 (East Gate City Boulevard) / Lee Street | NCDOT | I-40 Westbound ramp intersection. | Install traffic signal and turn lane improvements. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007I | Statewide Mobility | HSIP, T(M) |  |  | 2025 | 4000 | 2026 | 752000 |  |  | 756000
Guilford | US 220 Eastbound | NCDOT | SR 2526 (Summit Avenue) ramp terminals in Greensboro. | Modify channelization island, install traffic signal, pedestrian heads, and crosswalks. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | W-5807A | Region D | HSIP, VRU |  |  |  |  | 2025 | 870000 |  |  | 870000 | UNDER CONSTRUCTION
Guilford | US 29 | NCDOT | Brentwood Street to I-85. | Install median guardrail. | 6.24 | Highway | Safety | 7 | High Point Urban Area MPO | HS-2407D | Region D | HSIP |  |  |  |  | 2026 | 2780000 |  |  | 2780000
Guilford | US 29 | NCDOT | Lakeview Memorial Park Cemetery entrance intersection. | Construct directional crossover. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007G | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 410000 |  |  | 410000
Guilford | US 29 Northbound | NCDOT | SR 2613 (North O'Henry Boulevard) in the vicinity of Joe Brown Drive; SR 2937 (North O'Henry Boulevard) in the vicinity of the flea market; SR 2622 / SR 5235 (Corbin Road) | Close directional leftovers. | 0.9 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2407C | Statewide Mobility | HSIP |  |  |  |  | 2027 | 615000 |  |  | 615000
Guilford | Friendly Avenue | NCDOT | West of Green Valley Road to Lindell Road in Greensboro. | Widen roadway and construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5841 | Division 7 | T |  |  |  |  | 2026 | 3100000 |  |  | 3100000 | UNDER CONSTRUCTION
Guilford | Future I-840 | NCDOT | Greensboro Western Loop, US 220 (Battleground Avenue) to SR 2303 (Lawndale Drive) | Construct roadway. | 1.64 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2524D | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Guilford | I-40 / Business 85 / US 29 / US 70 / US 220 | NCDOT | Elm Eugene Street interchange in Greensboro. | Improve interchange. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-5964 | Statewide Mobility | NHP, T(DA), T(M) |  |  |  |  | 2025 | 1532000 |  |  | 1532000
Guilford | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-5965 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 245800000 |  |  | 295200000 | COORDINATE WITH B-5356 AND B-5718
Guilford | I-40 / I-85 | NCDOT | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-6004 | Division 7 | NHP, T(M) | 2026 | 5700000 | 2026 | 1100000 | 2031 | 23100000 |  |  | 29900000
Guilford | I-40 / US 421 | NCDOT | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-5712 | Statewide Mobility | NHP, T(M) | 2028 | 13900000 | 2028 | 1100000 | 2031 | 27600000 |  |  | 42600000
Guilford | I-73 / I-840 / Future I-840 / US 421 | NCDOT | Greensboro Western loop, north of I-85 to Lawndale Drive in Greensboro. | Construct freeway on new location. | 15 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2524 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
Guilford | I-74 / US 311 | NCDOT | NC 68 (Eastchester Drive) in High Point. | Reconstruct interchange and approaches. | 1 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-5169 | Region D | [10 empty] | UNDER CONSTRUCTION
Guilford | I-785 / I-840; Future I-785; Future I-840 | NCDOT | Greensboro Eastern Loop, Lawndale Drive to north of I-40 / I-85 in Greensboro. | Construct freeway on new location. | 12.6 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525
Guilford | I-840 | NCDOT | Greensboro Eastern Loop, US 29 north of Greensboro to SR 2303 (Lawndale Drive) | Construct roadway. | 1.89 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525C | Statewide Mobility | T |  |  |  |  | 2018 | 94831000 | 2021 | 8340000 | 103171000 | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Guilford | I-840 | NCDOT | Interchange at proposed Cone Boulevard extension | Construct interchange. | 15.4 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525D | Not Funded | T | NOT FUNDED |  | NOT FUNDED |  | NOT FUNDED | 15000000 | NOT FUNDED |  | 15000000
Guilford | NC 62 | NCDOT | SR 1154 (Kersey Valley Road) to SR 1162 (Weant Road) in Archdale. | Improve interchange and realign intersections. | 1 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-6018 | Division 7 | T | 2021 | 2600000 | 2021 | 2811000 | 2025 | 24100000 |  |  | 29511000 | UNDER CONSTRUCTION.
Guilford | NC 68 | NCDOT | SR 1523 (Hickswood Road) to SR 1823 (Williard Dairy Road) in High Point. | Construct reduced conflict intersections. | 2.92 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-5974 | Region D | T | 2027 | 16300000 | 2027 | 4700000 | 2029 | 56605000 |  |  | 77605000 | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE)
Guilford | NC 68 | NCDOT | SR 1556 (Gallimore Dairy Road) to Triad Center Drive in Greensboro. | Construct reduced conflict intersections. | 2.12 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | U-6122 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34200000 |  |  | 38300000 | COORDINATE WITH U-5974
Guilford | NC 68; NC 150 | NCDOT | Along NC 68 and NC 150 in Oak Ridge. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | R-5725 | Region D | T | 2022 | 1380000 | 2022 | 500000 | 2023 | 7300000 |  |  | 9180000 | COORDINATE WITH U-6127. UNDER CONSTRUCTION
Guilford | Pisgah Church Road | GREENSBORO | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5842 | Division 7 | BGANY, L(M) | 2028 | 1800000 | 2028 | 10000 | 2031 | 6400000 | 2024 | 750000 | 8960000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
Guilford | SR 1001 (Church Street) | NCDOT | US 220 (Wendover Avenue) to east Cone Boulevard in Greensboro. | Construct additional lanes. | 1.65 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5851 | Division 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18900000 |  |  | 109000000
Guilford | SR 1007 (Randleman Road) | NCDOT | Elmsley Drive to Glendale Drive in Greensboro. | Widen to multi-lanes. | 0.36 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5850 | Division 7 | T | 2022 | 600000 | 2022 | 400000 | 2026 | 4300000 |  |  | 5300000 | RIGHT-OF-WAY IN PROGRESS
Guilford | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | NCDOT | Proposed US 311 Bypass in High Point to SR 1424 (Hilltop Road) in Greensboro. | Widen to multi-lanes, part on new location. | 7.8 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | U-2412
Guilford | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | NCDOT | US 311 Bypass to SR 4228 (Vickrey Chapel Road) | Widen roadway. | 3.61 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-2412A | Division 7 | T |  |  |  |  | 2018 | 80599000 |  |  | 80599000 | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Guilford | SR 1556 (Gallimore Dairy Road) | NCDOT | NC 68 to Airpark Road in Greensboro | Widen to multilane. | 1.17 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-4015A | Division 7 | T |  |  |  |  | 2025 | 20590000 |  |  | 20590000 | UNDER CONSTRUCTION
Guilford | SR 1556 (Gallimore Dairy Road) | NCDOT | NC 68 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 1.6 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-4015
Guilford | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | NCDOT | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-4758 | Division 7 | BGANY, HP, T(M) | 2022 | 13221000 | 2022 | 7200000 | 2025 | 74901000 |  |  | 95322000 | RIGHT-OF-WAY IN PROGRESS
Guilford | SR 1850 (Sandy Ridge Road) | NCDOT | I-40 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 0.69 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6045 | Division 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 590000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40100000 |  |  | 49790000
Guilford | SR 2085 (Bryan Boulevard) | NCDOT | New Garden Road at Horsepen Creek Road in Greensboro. | Interchange improvements, including new ramp from westbound new garden road to westbound SR 2085 (Bryan Boulevard). | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6008 | Division 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 290000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7600000 |  |  | 9990000
Guilford | SR 2124 (Lewiston Road) | NCDOT | SR 2136 (Fleming Road) intersection in Greensboro. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6016 | Division 7 | T | 2022 | 836000 | 2022 | 302000 | 2025 | 2049000 |  |  | 3187000 | RIGHT-OF-WAY IN PROGRESS
Guilford | SR 2334 (Air Harbor Road) | NCDOT | SR 2347 (Lake Brandt Road) | Construct turn lanes and sidewalks. |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6019 | Division 7 | T |  |  |  |  | 2022 | 1586000 |  |  | 1586000 | UNDER CONSTRUCTION
Guilford | US 220 (Battleground Avenue) | NCDOT | Cone Boulevard / Benjamin Parkway, Westridge Road, New Garden Road, and Brassfield Road intersections in Greensboro. | Construct intersection improvements and sidewalk improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5306
Guilford | US 220 (Battleground Avenue) | NCDOT | Westridge Road intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5306B | Region D | [10 empty] | UNDER CONSTRUCTION
Guilford | US 220 (Battleground Avenue) | NCDOT | Westridge Road to Cotswold Avenue in Greensboro. | Construct additional lanes. | 1.42 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5892 | Region D | NHP, T(M) | 2025 | 7531000 | 2025 | 1472000 | 2028 | 12400000 |  |  | 21403000
Guilford | US 29 (Future I-785) | NCDOT | North of I-785 to NC 150 | Upgrade corridor to interstate standards. | 4.48 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | R-5889A | Region D | T | 2027 | 17066000 | 2027 | 1876000 | 2030 | 137400000 |  |  | 156342000
Guilford | US 29 / US 70 / I-85 Business | NCDOT | SR 1009 (South Main Street) in High Point. | Reconstruct interchange. | 1 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-5896 | Division 7 | T | 2019 | 8834000 |  |  | 2022 | 15400000 | 2019 | 1820000 | 26054000 | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
Guilford | US 29 / US 70 / US 220 | NCDOT | SR 4240 (Gate City Boulevard) to south of I-785 in Greensboro. | Construct access management improvements and safety enhancements, including ramp closures and consolidations, reconfigure SR 2526 (Summit Avenue) / Phillips Avenue interchange, and replace bridges 400283 and 400342. | 5.09 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6100 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28400000 |  |  | 36300000
Guilford | US 29 / US 70 / US 220 (O'Henry Boulevard) | NCDOT | I-40 /I-85 Business to south of Florida Street in Greensboro. | Construct additional lane on I-40 / I-85 Business eastbound ramp onto northbound US 29 / US 70 / US 220 and extend US 29 / US 70 / US 220 southbound ramp onto SR 3762 (Martin Luther King, Jr. Drive) | 0.69 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5754 | Region D | T |  |  |  |  | 2022 | 6750000 |  |  | 6750000 | UNDER CONSTRUCTION
Guilford | US 29; SR 4771 (Reedy Fork Parkway) | NCDOT | US 29 / SR 4771 (Reedy Fork Parkway) interchange improvements in Greensboro. | Improve roadway, modify interchange, and replace bridge 400360. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | R-4707 | Region D | T | 2019 | 5824000 |  |  | 2021 | 62104000 | 2019 | 4019000 | 71947000 | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE)
Guilford | US 70 | NCDOT | SR 2826 (Birch Creek Road) to SR 3051 (Knox Road) | Widen roadway. |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581BB | Not Funded | T | NOT FUNDED | 2113000 | NOT FUNDED | 626000 | NOT FUNDED | 8200000 | NOT FUNDED |  | 10939000
Guilford | US 70 | NCDOT | SR 2851 (Penry Road) to SR 2828 (Willowlake Road) | Widen roadway. |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581A | [11 empty] | PROJECT COMPLETE
Guilford | US 70 | NCDOT | SR 3045 (Mount Hope Church Road) to SR 2826 (Birch Creek Road) | Widen roadway. | 1.15 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581BA | Division 7 | T | 2020 | 2618000 |  |  | 2020 | 15535000 | 2020 | 1609000 | 19762000 | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Guilford | US 70 | NCDOT | SR 3045 (Mount Hope Church Road) to SR 3056 (Rock Creek Dairy Road). | Widen to multi-lanes, part on new location. | 4.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581
Guilford | US 70 | NCDOT | SR 3051 (Knox Road) to SR 3056 (Rock Creek Dairy Road) | Widen roadway. |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581BC | Not Funded | T | NOT FUNDED | 3040000 | NOT FUNDED | 901000 | NOT FUNDED | 11799000 | NOT FUNDED |  | 15740000
Guilford | US 70 (Wendover Avenue) | NCDOT | US 70 (Wendover Avenue) at US 29 Interchange | Replace and upgrade overhead signs. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525CA | Statewide Mobility | T |  |  |  |  | 2025 | 1550000 | 2024 | 100000 | 1650000 | UNDER CONSTRUCTION
Guilford | Future I 73 | NCDOT | SR 2011 (Edgefield Road) to SR 2127 (Brook Bank Road) | Construct roadway. | 4 | Highway | Transition | 7 | Greensboro Urban Area MPO | R-2413A | Pre-STI (Transition) | T |  |  |  |  | 2024 | 55000 |  |  | 55000 | COMBINED WITH I-5110 AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
Guilford | Future I 73 | NCDOT | SR 2127 (Brook Bank Road) to Haw River | Construct roadway. | 4.4 | Highway | Transition | 7 | Greensboro Urban Area MPO | R-2413B | Pre-STI (Transition) | [10 empty] | COMBINED WITH I-5110 AND R-2413A FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
Guilford | Future I-73 | NCDOT | NC 68 to Greensboro Western Loop. | Construct six-lane freeway on new location. | 3 | Highway | Transition | 7 | Greensboro Urban Area MPO | I-5110 | Pre-STI (Transition) | [10 empty] | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
Guilford | I-73 / I-840 | NCDOT | SR 2085 (Bryan Boulevard) Interchange | Modify interchange, including auxiliary lanes, ITS, and Inman Road bridge replacement | 2 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-2524BC | Pre-STI (Transition) | [10 empty] | COMPLETE
Guilford | I-785 / I-840 | NCDOT | Greensboro Eastern Loop, US 70 relocation to US 29 north of Greensboro | Relocate roadway. | 4.59 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-2525B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Guilford | SR 3058 (Judge Adams Road) | NCDOT | Bridge 400214 over Little Alamance Creek. | Replace bridge. | 0.25 | Highway | Transition | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO | B-4960 | Division 7 | [10 empty] | UNDER CONSTRUCTION
Guilford | US 220 (Battleground Avenue) | NCDOT | Benjamin Parkway; Cone Boulevard intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-5306A | Pre-STI (Transition) | [10 empty] | PROJECT COMPLETE
Guilford | US 220 (Battleground Avenue) | NCDOT | New Garden Road intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-5306C | Pre-STI (Transition) | [10 empty] | PROJECT COMPLETE
Guilford | US 421 (Future I-685) | NCDOT | SR 3418 (Neelley Road) intersection south of Greensboro | Convert at-grade intersections to interchanges. | 0.901 | Highway | Transition | 7 | Greensboro Urban Area MPO | R-2612B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Guilford | Gastonia Transit Authority | GTA | Systemwide | Funding for electric vehicle and charging infrastructure. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-6714 | Public Transit | 5339, CMAQ, L, S | [6 empty] | 2023 | 4685000 | 4685000 | "S" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AUTHORITY | Systemwide | Safety and security. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TS-4758 | Public Transit | 5307, L | [6 empty] | 2025 | 699000 | 699000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AUTHORITY | Various locations | Funding for section 5310 for Capital project. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TQ-6783 | Public Transit | 5310, L | [6 empty] | 2025 | 3620000 | 3620000
Guilford | Greensboro Transit Authority | GTA | Systemwide | Purchase clean diesel replacement buses. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-4771 | Public Transit | CMAQ, L | [6 empty] | 2022 | 8914000 | 8914000
Guilford | Greensboro Transit Authority | GTA | Systemwide | Purchase paratransit vehicle replacement. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-4767 | Public Transit | 5309, L | [6 empty] | 2022 | 4844000 | 4844000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
Guilford | High point Transit System | HIGH POINT TRANSIT SYSTEM / HI-TRAN | Systemwide | Funding for planning assistance - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | High Point Urban Area MPO | TP-5104 | Public Transit | 5303, L, S | [6 empty] | 2020 | 396000 | 396000 | FUNDS AUTHORIZED IN PROGRESS
Guilford | High Point Transit System | SYSTEM / HI-TRAN HIGH POINT TRANSIT | Systemwide | Purchase replacement buses. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | High Point Urban Area MPO | TA-6729 | Public Transit | 5307, CMAQ, L | [6 empty] | 2022 | 1250000 | 1250000
Guilford | Piedmont Authority for Regional Transportation (PART) | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | Systemwide | Purchase replacement vehicles. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-6690 | Public Transit | 5339, L | [6 empty] | 2024 | 227000 | 227000
Guilford | Greensboro Transit Authority |  | Systemwide | Route 15 new service. |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0048 | Public Transit | CMAQ, L | [6 empty] | 2023 | 3624000 | 3624000
Guilford | Greensboro Transit Authority |  | Various locations | New crosstown new route. |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0050 | Public Transit | CMAQ, L | [6 empty] | 2024 | 7680000 | 7680000
Guilford | Greensboro Transit Authority | Greensboro Transit Authority | Systemwide | Fund study and design of Crossmax purple corridor. |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0068 | Exempt | DP, L(M) | [6 empty] | 2026 | 2500000 | 2500000 | "DP" FUNDS REPRESENT FEDERAL RAISE GRANT AWARD.
Guilford | GTA | GTA | J. Douglas Gaylon Depot | Renovation phase 3. |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0055 | Public Transit | 5339, BGDA, L(M) |  |  |  |  | 2026 | 3063000 |  |  | 3063000
Guilford | Burlington Fixed Route Service | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | Burlington fixed route | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-6151 | Public Transit | 5307, L | [6 empty] | 2025 | 3102000 | 3102000
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AUTHORITY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-4971 | Public Transit | 5307, L, SMAP | [6 empty] | 2022 | 56225000 | 56225000 | FUNDS AUTHORIZED IN PROGRESS
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AUTHORITY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-6139 | Public Transit | 5310, L | [6 empty] | 2025 | 870000 | 870000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBORO MPO
Guilford | Guilford County Transportation | GUILFORD COUNTY TRANSPORTATION | Systemwide | Funding for operating rural transit. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-5221 | Public Transit | 5307, L | [6 empty] | 2024 | 140000 | 140000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
Guilford | Guilford County Transportation | GUILFORD COUNTY TRANSPORTATION | Systemwide | Operating funding for Guilford county through High point MPO. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | High Point Urban Area MPO | TO-5216 | Public Transit | 5307, L | [6 empty] | 2020 | 1330000 | 1330000 | FUNDS AUTHORIZED IN PROGRESS
Guilford | Piedmont Authority For Regional Transport | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | Systemwide | Funding for operating Fixed route. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-5209 | Public Transit | 5307, L, SMAP | [6 empty] | 2024 | 8520000 | 8520000 | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY
Guilford | Piedmont Authority For Regional Transportation | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | High Point Urban Area MPO | TO-5134C | Public Transit | 5307, L | [6 empty] | 2023 | 16910000 | 16910000
Guilford | Gastonia Transit Authority |  | Systemwide | Operate micro transit. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TM-0053 | Public Transit | 5307, L | [6 empty] | 2025 | 6294000 | 6294000
Guilford | Greensboro Transit Authority |  | Systemwide | Fund operating expenses for Greensboro Transit Authority fixed routes. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TG-4971 | Public Transit | 5307, L |  |  |  |  | 2025 | 22430000 |  |  | 22430000
Guilford | Greensboro Transit Authority | AUTHORITY GREENSBORO TRANSIT | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TG-4957 | Public Transit | 5307, L | [6 empty] | 2025 | 4139000 | 4139000 | FUNDS AUTHORIZED IN PROGRESS
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AUTHORITY | Systemwide | Funding for section 5310 for project administration. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TQ-7000 | Public Transit | 5310 | [6 empty] | 2024 | 56000 | 56000
Guilford | Greensboro Transit Authority | GTA | Regionwide. | Install battery-electric and hybrid diesel buses and charging infrastructure. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TM-0057 | Public Transit | 5339(b), L(M) | [6 empty] | 2026 | 28014000 | 28014000
Guilford | Greensboro Transit Authority |  | Systemwide | Transit planning |  | Public Transportation (Transit) | Planning | 7 | Greensboro Urban Area MPO | TU-0021 | Public Transit | 5303, L, S | [6 empty] | 2025 | 2084000 | 2084000
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AUTHORITY | J. Douglas Galyon Depot area. | Conduct transit oriented development study. |  | Public Transportation (Transit) | Planning | 7 | Greensboro Urban Area MPO | TU-0018 | Public Transit | 20005(b) | [6 empty] | 2025 | 500000 | 500000
Guilford | Greensboro Transit Authority | AUTHORITY GREENSBORO TRANSIT | Systemwide | Funding for routine capital. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-5105 | Public Transit | 5339, L | [6 empty] | 2025 | 1063000 | 1063000 | FUNDS AUTHORIZED IN PROGRESS
Guilford | Greensboro Transit Authority | GREENSBORO TRANSIT AGENCY | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-4759 | Public Transit | 5307, L | [6 empty] | 2025 | 11637000 | 11637000
Guilford | Greensboro Transit Authority | GTA | Various locations | Funding for routine capital including fareboxes, camera systems, APCs and delivery for asset transfer of used buses, depot ticket machine, realtime shelter signage, and bus shelters. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-0019 | Public Transit | 5309, 5339, L | [6 empty] | 2025 | 5590000 | 5590000
Guilford | High Point Transit System |  | Systemwide | Purchase new spare paratransit buses. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-0025 | Public Transit | 5307, L | [6 empty] | 2024 | 275000 | 275000
Guilford | High Point Transit System |  | Systemwide | Replace paratransit buses. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-0024 | Public Transit | 5307, L | [6 empty] | 2024 | 1375000 | 1375000
Guilford | High Point Transit System | NT TRANSIT SYSTEM | Various locations | Renovate maintenance facility. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-0022 | Public Transit | 5339, L |  |  |  |  | 2024 | 1568000 |  |  | 1568000
Guilford | Piedmont Authority | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | Various locations | Funding for routine capital, preventive maintenance, security and passenger amenities. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-6173B | Public Transit | 5307, L | [6 empty] | 2023 | 2053000 | 2053000
Guilford | Piedmont Authority For Regional Transportation | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | Systemwide | Funding for routine capital. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-6185 | Public Transit | 5307, L | [6 empty] | 2024 | 1067000 | 1067000 | FUNDS AUTHORIZED IN PROGRESS
Guilford | Lowdermilk Street / Sykes Avenue / Pine Street | NCDOT | SR 3163 (East Market Street) intersections in Greensboro | Realign Lowdermilk Street and Sykes Avenue including relocation of crossing (#722958T) and close Pine Street crossing (#722957L). |  | Rail | Rail-Highway Grade Crossing Closure | 7 | Greensboro Urban Area MPO | Y-4807B | Division 7 | RR |  |  |  |  | 2024 | 5000000 |  |  | 5000000 | UNDER CONSTRUCTION
Guilford | SR 2531 (Hillcroft Road) | GREENSBORO | Crossing 722545Y near Greensboro | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Greensboro Urban Area MPO | RX-2007C | Division 7 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000 | UNDER CONSTRUCTION
Guilford | SR 2748 (Springwood Avenue) | GIBSONVILLE | Crossing 722990L in Gibsonville | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Burlington-Graham MPO | RX-2007A | Division 7 | RR |  |  |  |  | 2023 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
Guilford | NC Railroad / NS Main Line | NCDOT | SR 1332 (Scientific Street) intersection in Jamestown | Construct grade separation and close existing at-grade crossing (#722352a). |  | Rail | STI (Prioritization) | 7 | High Point Urban Area MPO | RP-0004 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17000000 |  |  | 22200000
Guilford | NC Railroad / NS NC Line | NCDOT | SR 1549 (Mackay Road) intersection in Greensboro | Construct grade separation and close existing at-grade crossing (#722359x). Includes relocating Atwater Drive. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | RP-0003 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21000000 |  |  | 30400000
Guilford | Norfolk Southern | JAMESTOWN | Jamestown siding in Jamestown. | Construct extension. |  | Rail | STI (Prioritization) | 7 | High Point Urban Area MPO | P-5721 | Statewide Mobility | O, T |  |  |  |  | 2026 | 4070000 |  |  | 4070000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
Guilford | Norfolk Southern H Line | NCDOT | Franklin Boulevard Crossing (722959A) in Greensboro and O'Ferrell Street Crossing. | Construct grade separation at Franklin Boulevard crossing (722959A) in Greensboro, and close O'Ferrell Street crossing (722961B). |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5709 | Region D | O, T | 2022 | 3484000 | 2022 | 2016000 | 2027 | 27010000 |  |  | 32510000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS
Guilford | Norfolk Southern Main Line | NCDOT | SR 1584 (Yanceyville Street) crossing in Greensboro. | Construct grade separation and close crossing 722542d. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5735 | Region D | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21801000 |  |  | 28801000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
Guilford | Norfolk Southern Mainline | NSR RR | Norfolk Southern "Roundhouse" property in Division 7. | Construct parking lot with space for international containers, including security fence, pole-mounted lighting, and paved entrance. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5700 | Division 7 | O, T |  |  |  |  | 2026 | 1700000 |  |  | 1700000 | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION
Guilford | North Carolina Railroad (NCRR) / Norfolk Southern | NCDOT | SR 1424 (Hilltop Road) in Greensboro. | Upgrade at-grade crossing to grade separation. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5713 | Statewide Mobility | O, T | 2026 | 9100000 | 2026 | 1600000 | 2027 | 20200000 |  |  | 30900000 | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION
Guilford | North Carolina Railroad / Norfolk Southern H Line | NCDOT | South English Street crossing in Greensboro. | Construct grade separation and close crossing 722955X. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5747 | Region D | O, T | 2026 | 8800000 | 2026 | 720000 | 2028 | 24901000 |  |  | 34421000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
Guilford | North Carolina Railroad / Norfolk Southern Main Line | NCDOT | SR 1352 (Oakdale Road). | Construct grade separation and close crossing #722355v. |  | Rail | STI (Prioritization) | 7 | High Point Urban Area MPO | RP-0007 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30000000 |  |  | 43400000
Guilford | North Carolina Railroad Norfolk Southern | NCDOT | Pomona Yard. | Extend auxiliary track and add power turnouts. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5714 | Region D | O, T |  |  |  |  | 2027 | 6600000 |  |  | 6600000 | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION
Guilford, Alamance | Piedmont Authority For Regional Transportation |  | Various locations | Funding for capital projects. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO, High Point Urban Area MPO | TG-0014B | Public Transit | 5307, 5339, L | [6 empty] | 2024 | 2149000 | 2149000
Guilford, Davidson, Randolph | High Point Transit System | SYSTEM / HI-TRAN HIGH POINT TRANSIT | Systemwide | Funding for routine capital - bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7, 8, 9 | High Point Urban Area MPO | TG-4814 | Public Transit | 5307, L | [6 empty] | 2024 | 2229000 | 2229000 | FUNDS AUTHORIZED IN PROGRESS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Equip 9 stations and platforms with ADA/FRA Passenger Information Display Systems. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918I | [11 empty] | IN PROGRESS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Passenger train security system, CCTV data network and generators. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918E | [11 empty] | IN PROGRESS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Purchase 2 used locomotives. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918B | [11 empty] | COMPLETE
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Purchase 4 used passenger cars and rehabilitate 7 passenger cars. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918G | [11 empty] | IN PROGRESS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Rebuild 2 F59PHI locomotives. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918A | [11 empty] | IN PROGRESS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Rehabilitate equipment - 3 locomotives. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918C | [11 empty] | IN PROGRESS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | - | Rehabilitate equipment - 3 passenger cars. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918D | [11 empty] | COMPLETE
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | Regionwide | Train 74 / 75 operations between Charlotte and Raleigh, equipment and capital yard maintenance facility. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918 | Exempt | CMAQ, HF(M) | [6 empty] | 2021 | 61393000 | 61393000 | "HF" FUNDING REFLECTS STATE RAIL FUNDS
Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | Piedmont Corridor | NCDOT | Regionwide | Purchase and refurbish rail cars for Piedmont Service expansion. |  | Rail | STI (Prioritization) | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-5719 | [11 empty] | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT
Guilford, Forsyth | I-40 | NCDOT | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Highway | STI (Prioritization) | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO | I-5981C | Not Funded | NHP, T(M) | NOT FUNDED | 3200000 | NOT FUNDED | 900000 | NOT FUNDED | 112500000 | NOT FUNDED |  | 116600000
Guilford, Forsyth | US 158 | NCDOT | North of SR 2034 (Anthony Road) to US 220. | Widen to multi-lanes. | 5.89 | Highway | STI (Prioritization) | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO | R-2577C | Not Funded | T | NOT FUNDED | 74608000 | NOT FUNDED | 625000 | NOT FUNDED | 48400000 | NOT FUNDED |  | 123633000
Guilford, Orange | Various | BURLINGTON | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Highway | Other | 7 | Burlington-Graham MPO | C-5602 | Exempt | CMAQ, L(M) | 2020 | 18000 |  |  | 2020 | 99000 | 2020 | 54000 | 171000
Guilford, Rockingham | Future I-73 | NCDOT | NC 68 at SR 2011 (Edgefield Road) in Guilford County to US 220 / NC 68 intersection in Rockingham County. | Construct four lane freeway, on new location, and four lanes along us 220 to NC 68 in Rockingham County. | 12.1 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO | R-2413 | Pre-STI (Transition)
Guilford, Wake, Mecklenburg | Piedmont Corridor | NCDOT | - | Acquire and rebuild two additional locomotives. |  | Rail | STI (Prioritization) | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-5719A | Exempt | [10 empty] | COMPLETE
Guilford, Wake, Mecklenburg | Piedmont Corridor | NCDOT | - | Acquire and rebuild two coach and one lounge/baggage rail cars. |  | Rail | STI (Prioritization) | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-5719B | Exempt | [10 empty] | IN PROGRESS
Halifax | IXA | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | Halifax Northampton Regional Airport | Construct taxi lane and preparation for additional T-hangars. |  | Aviation | STI (Prioritization) | 4 | Peanut Belt RPO | AV-5822 | Division 4 | T |  |  |  |  | 2024 | 1400000 |  |  | 1400000
Halifax | IXA | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | Halifax Northampton Regional Airport | Construct taxi lanes and apron. |  | Aviation | STI (Prioritization) | 4 | Peanut Belt RPO | AV-5833 | Division 4 | T |  |  |  |  | 2026 | 2500000 | 2025 | 221000 | 2721000
Halifax | NC 561 | NCDOT | Bridge 410093 over Conoconnara Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Peanut Belt RPO | B-5662 | Highway Fund | HFB |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | COMPLETE.
Halifax | SR 1601 (Sledge Road) | NCDOT | Bridge 410115 over Rocky Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Peanut Belt RPO | BR-0113 | Division 4 | DP, HFB | 2020 | 130000 |  |  | 2021 | 796000 |  |  | 926000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
Halifax | SR 1710 (Grace Drive / Watkins Drive); SR 1737 (Power Place) | NCDOT | US 158 to north of SR 1734 (Kennametal Drive); US 158 intersection | Widen to 4-lanes; Realign intersection. | 0.72 | Highway | Economic Development | 4 | Peanut Belt RPO | HE-0003 | Division 4 | T |  |  |  |  | 2022 | 2050000 |  |  | 2050000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR ROSEBURG FOREST PRODUCTS.
Halifax | I-95 | NCDOT | NC 481 (mile marker 154) to mile marker 167. | Rehabilitate pavement. | 18 | Highway | Interstate Maintenance | 4 | Peanut Belt RPO | I-5932
Halifax | I-95 | NCDOT | NC 481 (mile marker 154) to NC 561 (mile marker 160) | Rehabilitate pavement. | 6.83 | Highway | Interstate Maintenance | 4 | Peanut Belt RPO | I-5932B | Statewide Mobility | BGLT5, T(M) |  |  |  |  | 2021 | 8223000 |  |  | 8223000 | UNDER CONSTRUCTION.
Halifax | I-95 | NCDOT | NC 561 (mile marker 160) to mile marker 167. | Rehabilitate pavement. | 7.19 | Highway | Interstate Maintenance | 4 | Peanut Belt RPO | I-5932A | Statewide Mobility | BGLT5, T(M) |  |  |  |  | 2021 | 9593000 |  |  | 9593000 | UNDER CONSTRUCTION.
Halifax | NC 48 | NCDOT | NC 903 intersection. | Install all way stop and revise existing overhead and shoulder-mounted flashers. | 0.5 | Highway | Safety | 4 | Peanut Belt RPO | HS-2004G | Region A | HSIP, T(M) |  |  |  |  | 2022 | 50000 |  |  | 50000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H.
Halifax | US 158 | NCDOT | Eastern Littleton Town limits to West of SR 1432 (Everetts School Road). | Install rumble stripes and pavement markings. | 9.41 | Highway | Safety | 4 | Peanut Belt RPO | HS-2004T | Region A | HSIP, T(M) |  |  |  |  | 2024 | 230000 |  |  | 230000 | UNDER CONSTRUCTION.
Halifax | NC 125 | NCDOT | I-95 to SR 1745 (Old Farm Road). | Widen to four lanes. | 1.63 | Highway | STI (Prioritization) | 4 | Peanut Belt RPO | U-5725 | Division 4 | T |  |  |  |  | 2019 | 27240000 | 2021 | 2130000 | 29370000 | COMPLETE. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3).
Halifax | New Route | NCDOT | NC 125 to south of US 158. | Construct three lane facility on new location. | 1.49 | Highway | STI (Prioritization) | 4 | Peanut Belt RPO | R-3822 | Division 4 | [10 empty] | COMPLETE. COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725.
Halifax, Johnston | Various | NCDOT | Routes in Division 4. | Construct safety improvements. |  | Highway | Safety | 4 | Peanut Belt RPO, Upper Coastal Plain RPO | HS-2004J | Division 4 | HSIP, T(M) |  |  |  |  | 2022 | 5246000 |  |  | 5246000 | UNDER CONSTRUCTION.
Harnett | HRJ | HRJ | Harnett County Airport | Widen existing runway from 75 feet to 100 feet. |  | Aviation | STI (Prioritization) | 6 | Capital Area MPO | AP-0005 | Division 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3697000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 370000 | 4067000
Harnett | North Willow Street; South Park Street | ANGIER | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Bike & Ped | Locally Selected | 6 | Capital Area MPO | EB-6020 | Division 6 | BGDA, L, L(M) | 2024 | 150000 |  |  | 2025 | 3455000 | 2021 | 175000 | 3780000 | RIGHT-OF-WAY IN PROGRESS
Harnett | SR 1500 (East Mclver Street); South Wilma Street | ANGIER | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Bike & Ped | Locally Selected | 6 | Capital Area MPO | BL-0090 | Division 6 | BGDA, L(M) | 2025 | 50000 |  |  | 2026 | 898000 | 2024 | 150000 | 1098000
Harnett | Campbell University sidewalk | BUIES CREEK | Wade Steward Circle to Pearson Road in Buies Creek | Construct sidewalk. | 0.81 | Bike & Ped | STI (Prioritization) | 6 | Capital Area MPO | EB-6014 | Division 6 | L(M), TAANY | 2021 | 35000 |  |  | 2021 | 630000 |  |  | 665000 | UNDER CONSTRUCTION.
Harnett | SR 1210 (Hoover Road) | NCDOT | Bridge 420234 over Barbeque Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Fayetteville Area MPO | B-6005 | Division 6 | [10 empty] | COMPLETE.
Harnett | SR 1214 (Mount Pisgah Church Road) | NCDOT | Bridge 420034 over Upper Little River. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Fayetteville Area MPO | HB-0008 | Division 6 | BGOFF | 2026 | 330000 | 2026 | 100000 | 2028 | 2700000 |  |  | 3130000
Harnett | (New Route) Highland School Road | HARNETT COUNTY | SR 1115 (Buffalo Lake Road) to SR 1139 (Tingen Road) south of Highland Elementary and Middle School campuses | Construct two-lane minor thoroughfare partially on new ground. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0155 | Division 6 | L(M), T(DA) |  |  |  |  | 2028 | 3079000 | 2025 | 400000 | 3479000
Harnett | SR 1115 (Buffalo Lake Road) | FAYETTEVILLE | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0146 | Division 6 | BGDA, HF(M) | 2026 | 160000 | 2026 | 300000 | 2028 | 2500000 | 2025 | 500000 | 3460000
Harnett | I-95 | NCDOT | Cumberland County line to Johnston County line. | Repair pavement. | 8.8 | Highway | Pre-STI (Historic) | 6 | Mid-Carolina RPO | I-4906 | Pre-STI (Transition) | [10 empty] | COMPLETE. GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019.
Harnett | NC 27 | NCDOT | SR 1581 (Bailey's Crossroads) / SR 1705 (Fairground Road) intersection. | Realign and construct intersection improvements. | 0.5 | Highway | Safety | 6 | Capital Area MPO | W-5806D | Region C | HSIP, T(M) | 2021 | 100000 |  |  | 2022 | 606000 |  |  | 706000 | UNDER CONSTRUCTION.
Harnett | NC 27 | NCDOT | Moore County line to NC 24 / NC 27 split, NC 24 to Lillington, US 421 to Coats, and Coats to Johnston County line. | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006H | Region C | HSIP, T(M) |  |  |  |  | 2024 | 1064000 |  |  | 1064000 | UNDER CONSTRUCTION.
Harnett | NC 27 / SR 1006 (Old Stage Road) | NCDOT | SR 2084 (Leslies Campbell Avenue) intersection in Buise Creek. | Construct roundabout. | 0.5 | Highway | Safety | 6 | Capital Area MPO | W-5706L | Region C | HF, HSIP |  |  | 2024 | 278000 | 2024 | 3150000 |  |  | 3428000 | RIGHT-OF-WAY IN PROGRESS.
Harnett | SR 1115 (Buffalo Lake Road) | NCDOT | NC 27 to NC 87. | Install rumble stripes and pavement markings. | 4.57 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006Y | Division 6 | HSIP, T(M) |  |  |  |  | 2024 | 236000 |  |  | 236000 | UNDER CONSTRUCTION.
Harnett | SR 1117 (Nursery Road); SR 3242 (Overhills Road); SR 1121 (Ray Road) | NCDOT | NC 27 to SR 3242 (Overhills Road); NC 24 / NC 87 to SR 1117 (Nursery Road); SR 1117 (Nursery Road) to SR 3242 (Overhills Road) | Widen curves and install rumble stripes. | 11.01 | Highway | Safety | 6 | Fayetteville Area MPO, Mid-Carolina RPO | W-5806B | Division 6 | HSIP, T(M) |  |  |  |  | 2022 | 400000 |  |  | 400000 | UNDER CONSTRUCTION.
Harnett | SR 1441 (Chalybeate Springs Road) | NCDOT | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Highway | Safety | 6 | Capital Area MPO | HS-2006K | Division 6 | HSIP, T(M) | 2024 | 44000 | 2025 | 24000 | 2025 | 1150000 |  |  | 1218000 | RIGHT-OF-WAY IN PROGRESS
Harnett | SR 1532 (Langdon Road) | NCDOT | Bridge 420015. | Upgrade guardrail. | 0.5 | Highway | Safety | 6 | Capital Area MPO | HS-2006Q | Division 6 | HSIP, T(M) | 2023 | 40000 |  |  | 2023 | 1767000 |  |  | 1807000 | UNDER CONSTRUCTION.
Harnett | I-95 | NCDOT | SR 1808 (Jonesboro Road) (Exit 75) and SR 1709 (Hodges Chapel Road) (Exit 77). | Improve interchanges. | 1 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5883 | Statewide Mobility | T |  |  |  |  | 2022 | 100613000 |  |  | 100613000 | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION.
Harnett | I-95 | NCDOT | SR 1811 (Bud Hawkins Road) (Exit 70) and SR 1001 (Long Beach Road) (Exit 71). | Improve interchanges. | 1 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO, Mid-Carolina RPO | I-5877 | Statewide Mobility | T | 2023 | 3304000 |  |  | 2020 | 69733000 |  |  | 73037000 | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION.
Harnett | I-95 | NCDOT | US 421 (Exit 73) and SR 1793 (Pope Road) (Exit 72). | Clear for utilities. |  | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5878A | Statewide Mobility | T |  |  |  |  | 2020 | 139000 |  |  | 139000 | COMPLETE.
Harnett | I-95 | NCDOT | US 421 (Exit 73) and SR 1793 (Pope Road) (Exit 72). | Improve interchanges. | 1 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5878 | Statewide Mobility | T |  |  |  |  | 2022 | 78860000 |  |  | 78860000 | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION.
Harnett | NC 24 / NC 87 | NCDOT | SR 1117 (Nursery Road) intersection in Fayetteville | Upgrade at-grade intersection to interchange. | 2 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0011 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33400000 |  |  | 34200000
Harnett | NC 55 | NCDOT | Just south of SR 1532 (Oak Grove Church Road) to NC 210 in Angier. | Widen to multi-lanes, partially on new location. | 4.02 | Highway | STI (Prioritization) | 6 | Capital Area MPO | R-5705A | Division 6 | T | 2021 | 36835000 | 2021 | 3800000 | 2024 | 53392000 |  |  | 94027000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
Harnett | NC 55 | NCDOT | NC 210 intersection in Angier | Construct turn lanes. | 0.1 | Highway | STI (Prioritization) | 6 | Capital Area MPO | HP-0033 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 |  |  | 3800000
Harnett | NC 55 | NCDOT | North Broad Street intersection in Angier | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 6 | Capital Area MPO | HP-0034 | Division 6 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4400000 |  |  | 7700000
Harnett | NC 82 | NCDOT | Norris Road / Antioch Road intersection | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | HP-0039 | Division 6 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 |  |  | 6100000
Harnett | NC 87 / NC 24 | NCDOT | SR 1117 (Nursery Road) intersection north of Fayetteville | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5933 | Statewide Mobility | BGDA, T, T(M) | 2023 | 17000 | 2023 | 23000 | 2023 | 3345000 |  |  | 3385000 | UNDER CONSTRUCTION.
Harnett | SR 1117 (Nursery Road) | NCDOT | SR 3242 (Overhills Road) intersection | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0035 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 |  |  | 6100000
Harnett | US 401 | NCDOT | SR 1414 (Piney Grove Rawls Road) to SR 1443 (Lafayette Road) | Install traffic signals, restrict turns at Chalybeate Road, close Lafayette School Road. | 4.46 | Highway | STI (Prioritization) | 6 | Capital Area MPO | HP-0036 | Division 6 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 |  |  | 5100000
Harnett | US 401 (North Main Street) | NCDOT | Parker Lane to McKinney Parkway | Construct median. | 0.23 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | R-5890 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8700000 |  |  | 14700000
Harnett | Harnett Area Rural Transit System | HARNETT AREA RURAL TRANSIT SYSTEM | Systemwide. | Purchase two expansion vehicles to support on demand services. |  | Public Transportation (Transit) | STI (Prioritization) | 6 | Fayetteville Area MPO, Capital Area MPO, Mid-Carolina RPO | TP-0006 | Division 6 | T | [6 empty] | 2028 | 260000 | 260000
Harnett | Edgerton Street | NCDOT | CSX Crossing 629752R in Dunn. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006D | Division 6 | RR |  |  |  |  | 2026 | 446000 |  |  | 446000
Harnett | Harnett Street | NCDOT | CSX Crossing 629751J in Dunn | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006C | Division 6 | RR |  |  |  |  | 2026 | 446000 |  |  | 446000
Harnett | US 401 | NCDOT | Raleigh & Fayetteville Railroad Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Capital Area MPO | RX-2406B | Division 6 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Harnett | US 401 (Main Street) | NCDOT | Raleigh & Fayetteville Railroad Crossing 465860F in Lillington. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Capital Area MPO | RX-2006F | Division 6 | RR |  |  |  |  | 2025 | 345000 |  |  | 345000 | UNDER CONSTRUCTION.
Harnett, Bladen, Cumberland, Columbus | Various | NCDOT | Routes in Division 6. | Install long life pavement markings. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO | HS-2006E | Division 6 | HSIP, T(M) |  |  |  |  | 2022 | 4715000 |  |  | 4715000 | UNDER CONSTRUCTION.
Harnett, Cumberland | US 301 | NCDOT | Mile marker 0 to 1.674 in Cumberland County and mile marker 6.171 to 9.703 in Harnett County | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406K | Region C | HSIP, T(M) |  |  |  |  | 2025 | 280000 |  |  | 280000 | UNDER CONSTRUCTION.
Harnett, Cumberland | US 401 | NCDOT | Fayetteville to Cumberland County line, Harnett County line to Lillington, and Lillington to Wake County line. | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Mid-Carolina RPO, Capital Area MPO, Fayetteville Area MPO | HS-2006W | Region C | HSIP, T(M) |  |  |  |  | 2024 | 976000 |  |  | 976000 | UNDER CONSTRUCTION.
Harnett, Johnston | I-95 | NCDOT | SR 1001 (Long Branch Road) (Exit 71) to I-40 (Exit 81). | Clear for utilities. | 10.72 | Highway | STI (Prioritization) | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | I-5986BA | Statewide Mobility | T |  |  |  |  | 2020 | 144000 |  |  | 144000 | UNDER CONSTRUCTION.
Harnett, Johnston | I-95 | NCDOT | SR 1002 (Long Branch Road) (Exit 71) to I-40 (Exit 81). | Widen to eight lanes. | 10.72 | Highway | STI (Prioritization) | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | I-5986B | Statewide Mobility | T | 2020 | 42400000 | 2020 | 700000 | 2022 | 92456000 |  |  | 135556000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883.
Harnett, Wake | NC 55 | NCDOT | South of SR 1532 (Oak Grove Church Road) to NC 42 in Fuquay-Varina. | Widen to multi-lanes, partially on new location. | 10 | Highway | STI (Prioritization) | 5, 6 | Capital Area MPO | R-5705
Haywood | Hazelwood Avenue (Plott Creek Road) | NCDOT | Richland Creek Bridge to Will Hyatt Road in Waynesville | Construct pedestrian improvements. | 0.56 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5859 | Division 14 | [10 empty] | UNDER CONSTRUCTION
Haywood | US 19 (Soco Road) | NCDOT | US 276 to Fie Top Road in Maggie Valley | Construct bicycle and pedestrian improvements. |  | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5926 | Division 14 | BGANY, BGDA, L(M) |  |  |  |  | 2022 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP
Haywood | I-40 | NCDOT | Bridge 430057 over US Forest Service Road / Cold Springs Creek at Harmon's Den. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054A | Statewide Mobility | T |  |  |  |  | 2022 | 22898000 | 2020 | 500000 | 23398000 | UNDER CONSTRUCTION.
Haywood | I-40 | NCDOT | Bridge 430124 over SR 1338 (White Oak Road) and Fines Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054D | Statewide Mobility | T | 2024 | 5000 | 2024 | 5000 | 2024 | 25800000 | 2021 | 500000 | 26310000
Haywood | I-40 | NCDOT | Bridge 430142 over Pigeon River. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054E | Statewide Mobility | T | 2023 | 50000 | 2023 | 5000 | 2024 | 81650000 | 2021 | 2000000 | 83705000 | RIGHT-OF-WAY IN PROGRESS.
Haywood | I-40 | NCDOT | Bridge 430159 over SR 1338 (White Oak Road). | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054B | Statewide Mobility | T |  |  | 2022 | 5000 | 2023 | 25000000 | 2020 | 500000 | 25505000 | UNDER CONSTRUCTION.
Haywood | I-40 | NCDOT | Bridge 430171 over SR 1338 (White Oak Road) and Jonathan Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054C | Statewide Mobility | T | 2022 | 47000 | 2022 | 5000 | 2022 | 79725000 | 2020 | 2500000 | 82277000 | UNDER CONSTRUCTION.
Haywood | I-40 | NCDOT | Bridge 430236 over SR 1513. | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-5541 | Highway Fund | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY.
Haywood | I-40 | NCDOT | Bridge 430239 over SR 1550 (Incinerator Road). | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0003 | Statewide Mobility | BFP, HFB | 2023 | 1000000 | 2024 | 30000 | 2024 | 27600000 |  |  | 28630000
Haywood | I-40 | NCDOT | Bridge 430243 over NC 215 (Champion Drive). | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0004 | Statewide Mobility | BFP, HFB | 2024 | 1100000 | 2024 | 360000 | 2024 | 32860000 |  |  | 34320000
Haywood | I-40 | NCDOT | Bridges 430057, 430159, 430171, 430124, and 430142 on I-40. | Replace bridges. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054 | Statewide Mobility
Haywood | I-40 | NCDOT | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | HB-0005 | Statewide Mobility | BFP, T(M) | 2026 | 2000000 | 2026 | 170000 | 2032 | 25501000 |  |  | 27671000
Haywood | I-40 | NCDOT | Bridges 430248 and 430249 over SR 1613 (Beaverdam Road). | Replace bridges. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0002 | Statewide Mobility | BFP, HIB | 2023 | 2000000 | 2024 | 390000 | 2024 | 38276000 |  |  | 40666000 | RIGHT-OF-WAY IN PROGRESS.
Haywood | NC 209 | NCDOT | Bridge 430128 over Cove Creek | Replace bridge. | 0.5 | Highway | Bridges | 14 | Land-of-Sky RPO | BR-0154 | Region G | BFP |  |  |  |  | 2028 | 1600000 |  |  | 1600000
Haywood | SR 1216 (Steel Bridge Road) | NCDOT | Bridge 430246 over West Fork Pigeon Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-5920 | Division 14 | BGOFF | 2026 | 90000 | 2026 | 80000 | 2026 | 1800000 |  |  | 1970000
Haywood | SR 1355 (Panther Creek Road) | NCDOT | Bridge 430206 over Fines Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | HB-0027 | Division 14 | BGOFF | 2026 | 70000 | 2026 | 40000 | 2028 | 2400000 |  |  | 2510000
Haywood | SR 1876 (Sonoma Road / Max Thompson Road) | NCDOT | Bridge 430169 over West Fork Pigeon River and bridge 430170 over East Fork Pigeon River. | Replace bridges. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0023 | Division 14 | BGOFF | 2024 | 320000 | 2025 | 300000 | 2025 | 5000000 |  |  | 5620000 | UNDER CONSTRUCTION.
Haywood | US 19 / US 23 / US 74 | NCDOT | Bridge 430133 over SR 1527 (Jones Cove Road). | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0015 | Highway Fund | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY
Haywood | US 23 / US 74 | NCDOT | Bridge 430168 over US 19 and US 23. | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-5898 | Statewide Mobility | BG5T50 | 2021 | 150000 |  |  | 2024 | 20253000 |  |  | 20403000 | UNDER CONSTRUCTION. TO BE LET WITH B-3186.
Haywood | US 23 / US 74 | NCDOT | Bridges 430155 and 430158 over Richland Creek. | Replace bridges. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-3186 | Statewide Mobility | BG5T50 | 2021 | 800000 |  |  | 2024 | 29145000 |  |  | 29945000 | UNDER CONSTRUCTION. TO BE LET WITH B-5898.
Haywood | US 74 | NCDOT | Bridge 430126 over I-40. | Replace bridge. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0006 | Statewide Mobility | BFP, T(M) | 2028 | 1000000 |  |  | 2034 | 9000000 |  |  | 10000000
Haywood | I-40 | NCDOT | Mile marker 15.0 to mile marker 20.5. | Rehabilitate pavement. | 5.5 | Highway | Interstate Maintenance | 14 | Land-of-Sky RPO | I-5924 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 10900000 |  |  | 10900000
Haywood | I-40 | NCDOT | Mile marker 27.0 to mile marker 30.0. | Rehabilitate pavement. | 3 | Highway | Interstate Maintenance | 14 | French Broad River MPO, Land-of-Sky RPO | I-5834A | Statewide Mobility | BGDA, NHPIM |  |  |  |  | 2021 | 7299000 |  |  | 7299000 | UNDER CONSTRUCTION.
Haywood | I-40 | NCDOT | Mile marker 27.0 to mile marker 34.0. | Rehabilitate pavement. | 7 | Highway | Interstate Maintenance | 14 | French Broad River MPO, Land-of-Sky RPO | I-5834 | [11 empty] | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP.
Haywood | I-40 | NCDOT | Mile marker 30.0 to mile marker 34.0 | Rehabilitate pavement. | 4 | Highway | Interstate Maintenance | 14 | French Broad River MPO | I-5834B | Statewide Mobility | NHPIM, PROTCT |  |  |  |  | 2022 | 13958000 |  |  | 13958000 | UNDER CONSTRUCTION.
Haywood | I-40 | NCDOT | Mile marker 34.0 to Buncombe County line. | Rehabilitate pavement. | 2.74 | Highway | Interstate Maintenance | 14 | French Broad River MPO | I-5928 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 8749000 |  |  | 8749000
Haywood | Depot Street | WAYNESVILLE | Bridge 430262 over Richland Creek in Waynesville. | Replace Bridge. | 0.25 | Highway | Municipal Bridge | 14 | French Broad River MPO | B-5013 | Division 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY THE TOWN OF WAYNESVILLE - MUNICIPAL BRIDGE
Haywood | Great Smoky Mountains National Park | NCDOT | Regionwide | Funding for regional outreach and educational program. |  | Highway | Other | 14 | Land-of-Sky RPO | HO-0003 | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 250000 | 250000 | IN PROGRESS
Haywood | I-40 | NCDOT | Mile marker 9.5 | Install LED chevrons and flatten shoulder. | 0.1 | Highway | Safety | 14 | Land-of-Sky RPO | HS-2414P | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 591000 |  |  | 591000
Haywood | US 19 | NCDOT | Holston Village Road and SR 1197 (Golf Course Road) intersections near Waynesville. | Construct intersection improvements. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014K | Region G | HSIP, T(M) |  |  |  |  | 2025 | 110000 |  |  | 110000 | UNDER CONSTRUCTION.
Haywood | US 19 | NCDOT | Jackson County to Maggie Valley. | Install long life pavement markings. | 3.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014S | Region G | HSIP, T(M) |  |  |  |  | 2024 | 263000 |  |  | 263000
Haywood | US 19 (Dellwood Road) | NCDOT | North Lakeshore Drive. | Install traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014Y | Region G | HSIP, T(M) |  |  | 2025 | 140000 | 2025 | 410000 |  |  | 550000
Haywood | US 19/US 23 (Carolina Boulevard) | NCDOT | Waitsel Way (Midway Medical Center). | Install directional left over with bulb-out. | 0.1 | Highway | Safety | 14 | French Broad River MPO | HS-2414U | Region G | HSIP, T(M) |  |  |  |  | 2027 | 460000 |  |  | 460000
Haywood | US 276 | NCDOT | Near Laurel Brook Drive to the Waynesville city limit. | Install rumble stripes with long life pavement markings. | 15.3 | Highway | Safety | 14 | Foothills RPO | HS-2414T | Region G | HSIP, T(M) |  |  |  |  | 2026 | 440000 |  |  | 440000
Haywood | US 276 | NCDOT | South of SR 1326 (Bob Boyd Road). | Construct left turn lane. | 0.5 | Highway | Safety | 14 | Land-of-Sky RPO | W-5814A | Region G | HSIP, T(M) |  |  |  |  | 2022 | 380000 |  |  | 380000 | UNDER CONSTRUCTION.
Haywood | US 23 Business (North Main Street) | NCDOT | Walnut Street intersection in Waynesville. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5888 | Division 14 | T |  |  |  |  | 2022 | 8751000 |  |  | 8751000 | UNDER CONSTRUCTION. TO BE LET WITH U-5839.
Haywood | US 23 Business (South Main Street) | NCDOT | SR 1164 (Hyatt Creek Road) to US 276 (Pigeon Street). | Widen to multi-lanes. | 2.09 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-4712 | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25501000 |  |  | 57401000
Haywood | US 276 | NCDOT | SR 1134 (Crymes Cove Road) and SR 1812 (Raccoon Road) intersection east of Waynesville. | Realign intersection. | 0.5 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-6158 | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6200000 |  |  | 6500000
Haywood | US 276 (Jonathan Creek) | NCDOT | US 19 to I-40. | Modernize roadway. | 5.87 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO, French Broad River MPO | R-5921 | Division 14 | BGANY | 2023 | 8400000 | 2023 | 3200000 | 2025 | 44750000 |  |  | 56350000 | RIGHT-OF-WAY IN PROGRESS. FUND CONSTRUCTION WITH TOLL CREDITS.
Haywood | US 276 (Russ Avenue) | NCDOT | US 23 / US 74 (Great Smokey Mountain Expressway) to US 19 (Dellwood Road). | Construct access management. | 1.32 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-6159 | Division 14 | BG5T50, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25200000 |  |  | 38900000
Haywood | US 276 (Russ Avenue) | NCDOT | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5839 | Division 14 | T | 2019 | 6830000 | 2020 | 1250000 | 2024 | 55127000 | 2020 | 3330000 | 66537000 | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888.
Haywood | Haywood County |  | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | French Broad River MPO | TM-0054 | Public Transit | 5307, L | [6 empty] | 2024 | 984000 | 984000
Haywood | City of Asheville Transit | CITY OF ASHEVILLE | Haywood County mountain projects | Funding for deviated fixed route capital and CARES funds. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 14 | French Broad River MPO | TG-6788 | Public Transit | 5307, L | [6 empty] | 2024 | 1034000 | 1034000
Haywood | NC 215 (Blackwell Drive) | NCDOT | BLU Crossing 720349K in Canton. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2014A | Division 14 | RR |  |  |  |  | 2025 | 400000 |  |  | 400000
Haywood | SR 1173 (Hazelwood Avenue) | NCDOT | BLU Crossing 720305K in Waynesville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414K | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Haywood, Buncombe | US 19 / US 23 | NCDOT | SR 1836 (Chestnut Mountain Road) to SR 1200 (Wiggins Road). | Upgrade roadway. | 3.85 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | U-6048 | Division 13, 14 | T | 2030 | 1000000 | 2030 | 700000 | 2033 | 41600000 |  |  | 43300000
Haywood, Henderson, Jackson, Polk, Transylvania | Various | NCDOT | Primary and secondary routes in Division 14. | Install long life pavement markings. |  | Highway | Safety | 14 | Foothills RPO, French Broad River MPO, Land-of-Sky RPO, Southwestern RPO | HS-2014R | Region G | HSIP, T(M) |  |  |  |  | 2023 | 1224000 |  |  | 1224000 | UNDER CONSTRUCTION.
Haywood, Henderson, Macon, Polk, Swain | Various | NCDOT | Freeway ramps in Division 14 | Install snowplowable markers and pavement markings for wrong way ramp arrows. | 0.5 | Highway | Safety | 14 | Southwestern RPO, Foothills RPO, French Broad River MPO | HS-2014C | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 52000 |  |  | 52000 | UNDER CONSTRUCTION.
Haywood, Jackson | US 74 | NCDOT | SR 1392 (Barkers Creek Road) to east of SR 1388 (Dicks Creek Road) and from Jackson County line to Bridges 050107 and 050110. | Improve pavement. | 9.77 | Highway | Safety | 14 | French Broad River MPO, Southwestern RPO | HS-2014E | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 975000 |  |  | 975000 | UNDER CONSTRUCTION.
Haywood, Macon, Jackson, Transylvania, Swain | Various | NCDOT | Two lane primary and secondary routes. | Install long life pavement markings. |  | Highway | Safety | 14 | Southwestern RPO, Land-of-Sky RPO | HS-2414Q | Region G | HSIP, T(M) |  |  |  |  | 2026 | 3000000 |  |  | 3000000
Haywood, Polk | Various | NCDOT | Secondary routes in Division 14. | Install long life pavement markings. |  | Highway | Safety | 14 | French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2014J | Division 14 | HSIP, T(M) |  |  |  |  | 2023 | 2570000 |  |  | 2570000 | UNDER CONSTRUCTION.
Haywood, Robeson | I-40; I-95 | NCDOT | Tennessee state line to mile marker 20; Exit 13 to south of proposed I-295. | Implement system to provide real time alerts in vehicles when drivers encounter a road anomaly requiring them to take driving action. | 40 | Highway | Other | 6, 14 | Land-of-Sky RPO, Lumber River RPO | HO-0011 | Statewide Mobility | DP, O | [6 empty] | 2024 | 1972000 | 1972000 | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH.
Haywood, Swain | Various | NCDOT | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Highway | Other | 14 | Land-of-Sky RPO, Southwestern RPO | C-5612 | Exempt | CMAQ, L(M) | 2020 | 4000 |  |  | 2020 | 19000 | 2020 | 12000 | 35000 | IN PROGRESS
Henderson | Clear Creek Greenway | HENDERSONVILLE | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | BL-0008 | Division 14 | BGANY, BGDA, L, L(M) |  |  |  |  | 2026 | 3576000 | 2022 | 900000 | 4476000 | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23.
Henderson | Ecusta Rail Trail | NCDOT | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | BL-0007 | Division 14 | BGDA, CRPDA, DP, L(M), TADA |  |  |  |  | 2023 | 12001000 | 2022 | 683000 | 12684000 | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS.
Henderson | Ecusta Trail | HENDERSON COUNTY | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Bike & Ped | Locally Selected | 14 | French Broad River MPO | BL-0078 | Division 14 | BGDA, DP, L, L(M) |  |  |  |  | 2025 | 34000000 | 2024 | 1800000 | 35800000 | DP REPRESENTS NSFLTP GRANT OF $15.707M.
Henderson | NC 280 | MILLS RIVER | French Broad River to NC 191 (Haywood Road) in Mills River | Construct multi-use path. | 3.09 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5946 | Division 14 | L(M), TADA | [6 empty] | 2026 | 375000 | 375000
Henderson | SR 1764 (South Grove Street) | NCDOT | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Bike & Ped | STI (Prioritization) | 14 | French Broad River MPO | EB-5963 | Division 14 | L(M), TAANY | 2025 | 220000 | 2025 | 240000 | 2031 | 3600000 | 2024 | 157000 | 4217000
Henderson | SR 2162 (Blythe Street) | NCDOT | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Bike & Ped | STI (Prioritization) | 14 | French Broad River MPO | EB-5860 | Division 14 | L(M), TAANY | 2026 | 230000 | 2026 | 160000 | 2030 | 2400000 | 2024 | 267000 | 3057000
Henderson | SR 1970 (Commercial Boulevard) | NCDOT | Industrial Park. | Construct road extension. | 0.38 | Highway | Appalachian Development Highway System | 14 | French Broad River MPO | HA-0003 | Exempt | ADHSL | 2021 | 70000 |  |  | 2021 | 1830000 |  |  | 1900000 | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000
Henderson | I-26 | NCDOT | Mile marker 50.0 to Polk County line. | Rehabilitate pavement. | 7.96 | Highway | Interstate Maintenance | 14 | French Broad River MPO | I-5925 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 15200000 |  |  | 15200000
Henderson | Tracy Grove Road | NCDOT | Bridge 440350 over Devils Fork Creek. | Replace Bridge. | 0.25 | Highway | Municipal Bridge | 14 | French Broad River MPO | B-5929 | Division 14 | BFPOFF, BGOFF |  |  |  |  | 2026 | 2400000 | 2025 | 125000 | 2525000 | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE
Henderson | NC 191 (Haywood Road) | NCDOT | Ridgewood Boulevard / Whitmire Street intersection in Hendersonville | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Highway | Safety | 14 | French Broad River MPO | HS-2414F | Region G | HSIP, T(M) |  |  |  |  | 2025 | 65000 |  |  | 65000
Henderson | SR 1793 (Tracy Grove Road) | NCDOT | SR 1525 (Dana Road) to SR 1006 (Howard Gap Road) | Install rumble stripes with 6" long life pavement markings. | 3.07 | Highway | Safety | 14 | French Broad River MPO | HS-2414R | Division 14 | HSIP, T(M) |  |  |  |  | 2026 | 115000 |  |  | 115000
Henderson | US 25 Business (Asheville Highway) | NCDOT | Hendersonville City limit to SR 1534 (Naples Road). | Install rumble stripes and long life pavement markings. | 4.3 | Highway | Safety | 14 | French Broad River MPO | HS-2014I | Region G | HSIP, T(M) |  |  |  |  | 2024 | 349000 |  |  | 349000
Henderson | US 64 | NCDOT | SR 1574 (Fruitland Road), SR 1006 (Howard Gap Road), SR 1519 (Thompson Street) / SR 1751 (Freeman Street), and SR 1749 (Orr's Camp Road) / SR 1634 (Carolina Avenue) intersections in Hendersonville. | Construct intersection improvements. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014L | Region G | HSIP, T(M) |  |  |  |  | 2023 | 570000 |  |  | 570000 | UNDER CONSTRUCTION.
Henderson | US 64 | NCDOT | SR 1586 (South Mills Gap Road) / Tuttle Road intersection near Edneyville. | Install traffic signal. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014O | Region G | HSIP, T(M) | 2023 | 20000 |  |  | 2023 | 76000 |  |  | 96000
Henderson | US 64 (6th Avenue West) | NCDOT | North Oak Street intersection in Hendersonville | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Highway | Safety | 14 | French Broad River MPO | HS-2414C | Region G | HSIP, T(M) |  |  |  |  | 2025 | 65000 |  |  | 65000
Henderson | US 64; US 25 Business | NCDOT | Various locations. | Upgrade signal system. |  | Highway | Safety | 14 | French Broad River MPO | HS-2014Q | Region G | HSIP, T(M) |  |  |  |  | 2023 | 224000 |  |  | 224000 | UNDER CONSTRUCTION.
Henderson | I-26 | NCDOT | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Highway | STI (Prioritization) | 14 | French Broad River MPO | I-4400A | Not Funded | NHP, T(M) | NOT FUNDED | 1600000 | NOT FUNDED | 500000 | NOT FUNDED | 114800000 | NOT FUNDED |  | 116900000
Henderson | I-26 | NCDOT | US 64 Interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 14 | French Broad River MPO | I-4400BA | Division 14 | T |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 350000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 106600000 |  |  | 106950000
Henderson | I-26 | NCDOT | US 64 to US 25 Business. | Widen to add additional lanes. | 5.73 | Highway | STI (Prioritization) | 14 | French Broad River MPO | I-4400BB | Statewide Mobility | NHP |  |  |  |  | 2019 | 52752000 |  |  | 52752000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033
Henderson | NC 191 | NCDOT | SR 1381 (Mountain Road) to NC 280 south of Mills River. | Widen to multi-lanes. | 4.41 | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588B | Division 14 | NHP, T | 2021 | 9500000 | 2022 | 15500000 | 2029 | 148300000 |  |  | 173300000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901).
Henderson | NC 191 | NCDOT | SR 1381 (Mountain Road) to NC 280. | Clear for utilities. |  | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588BA | Division 14 | T |  |  |  |  | 2025 | 220000 |  |  | 220000
Henderson | NC 191 | NCDOT | US 25 in Hendersonville to NC 280 south of Mills River. | Widen to multi-lanes. | 7.2 | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588
Henderson | NC 191 | NCDOT | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588A | Not Funded | BGANY, T(M) | NOT FUNDED | 15200000 | NOT FUNDED | 1800000 | NOT FUNDED | 18800000 | NOT FUNDED |  | 35800000
Henderson | NC 225 (South Main Street) | NCDOT | South Main Street at South King Street to US 176. | Widen bridge 440143 to five lanes. | 0.24 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-6049 | Region G | BGANY, T | 2023 | 3400000 | 2023 | 400000 | 2029 | 8800000 |  |  | 12600000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886
Henderson | SR 1170 (White Street) | NCDOT | SR 1171 (Willow Road) to US 176 (Spartanburg Highway) in Hendersonville. | Realign and extend roadway. | 0.42 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5886 | Division 14 | T | 2023 | 21700000 | 2023 | 2600000 | 2029 | 21702000 |  |  | 46002000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049.
Henderson | SR 1547 (Old Airport Road) | NCDOT | US 25 to Mills Gap Road in Fletcher. | Widen existing roadway. | 0.89 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5840 | Division 14 | T | 2020 | 855000 |  |  | 2020 | 12150000 | 2020 | 1575000 | 14580000 | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE).
Henderson | SR 1783 (Highland Lake Road) | NCDOT | NC 225 to US 176 in Flat Rock. | Upgrade roadway. | 1.07 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5887 | Division 14 | T | 2020 | 2295000 |  |  | 2021 | 9026000 |  |  | 11321000 | UNDER CONSTRUCTION.
Henderson | US 64 | NCDOT | SR 1180 (Blythe Street) to SR 1173 (White Pine Drive) / SR 1186 (Daniel Drive) in Laurel Park. | Modernize roadway with bike lanes and paved shoulders. | 0.99 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5783 | Region G | T | 2022 | 19900000 | 2022 | 3900000 | 2025 | 32740000 |  |  | 56540000 | RIGHT-OF-WAY IN PROGRESS.
Henderson | NC 225 / SR 1164 (Erkwood Drive) | NCDOT | SR 1779 (Shepherd Street) intersection in Hendersonville. | Construct intersection improvements. | 0.5 | Highway | Transition | 14 | French Broad River MPO | U-5105 | Pre-STI (Transition) | [10 empty] | DIVISION PROJECT - UNDER CONSTRUCTION
Henderson | Apple Country Transit | APPLE COUNTRY TRANSIT | Systemwide | Purchase replacement transit vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 14 | French Broad River MPO | TA-5229 | Public Transit | 5307, L(M) | [6 empty] | 2024 | 2022000 | 2022000
Henderson | Apple Country Transit | APPLE COUNTRY TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 14 | French Broad River MPO | TO-6106 | Public Transit | 5307, L | [6 empty] | 2024 | 1410000 | 1410000
Henderson | Apple Country Transit | APPLE COUNTRY TRANSIT | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | French Broad River MPO | TK-5176 | Public Transit | 5311, L, S | [6 empty] | 2020 | 540000 | 540000 | FUNDS AUTHORIZED IN PROGRESS
Henderson | Apple Country Transit | APPLE COUNTRY TRANSIT | Systemwide | Funding for contracts. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | French Broad River MPO | TG-4951 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 3841000 | 3841000 | FUNDS AUTHORIZED IN PROGRESS
Henderson | Apple Country Transit | APPLE COUNTRY TRANSIT | Various | Funding for program support. |  | Public Transportation (Transit) | Planning | 14 | French Broad River MPO | TU-0010 | Public Transit | 5307, L | [6 empty] | 2025 | 300000 | 300000
Henderson | Apple Country Transit | APPLE COUNTRY TRANSIT | Systemwide | Funding for contracts. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 14 | French Broad River MPO | TG-6181 | Public Transit | 5307, L | [6 empty] | 2024 | 1380000 | 1380000
Henderson | City of Asheville Transit | CITY OF ASHEVILLE | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, and service new technology for system with Cares 2021 funding. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 14 | French Broad River MPO | TG-6143 | Public Transit | 5307, L | [6 empty] | 2023 | 858000 | 858000 | FUNDS AUTHORIZED IN PROGRESS
Henderson | Fifth Avenue | NCDOT | BLU Crossing 720654V in Hendersonville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414A | Division 14 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Henderson | Fourth Avenue | NCDOT | BLU Crossing 720655C in Hendersonville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414J | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Henderson | Ray Avenue | NCDOT | BLU Crossing 729542C in Hendersonville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414C | Division 14 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Henderson | Seventh Avenue | NCDOT | BLU Crossing 720651A in Hendersonville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414E | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Henderson | SR 1503 (Main Street) | NCDOT | BLU Crossing 729541V in Hendersonville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414H | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Henderson | SR 1527 (Jones Cove Road) | NCDOT | BLU Crossing 720335C in Clyde. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414G | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Henderson | SR 1633 (Industrial Park Road) | NCDOT | BLU Crossing 729533D in Balfour. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414B | Division 14 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Henderson | SR 1695 (Naples Road) | NCDOT | BLU Crossing 720650T in Naples. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414I | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Henderson, Buncombe | I-26 | NCDOT | US 25 Business to NC 280. | Widen to add additional lanes. | 3.29 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | I-4400C | Region G | NHP |  |  |  |  | 2019 | 61776000 |  |  | 61776000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035
Henderson, Buncombe | I-26 | NCDOT | US 25 to NC 280. | Widen to add additional lanes. | 13.6 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | I-4400
Henderson, Polk | I-26; US 74; US 25 | NCDOT | Various locations. | Upgrade guardrail end units. |  | Highway | Safety | 14 | French Broad River MPO, Foothills RPO | HS-2414I | Region G | HSIP, T(M) |  |  |  |  | 2026 | 350000 |  |  | 350000
Henderson, Transylvania | Ecusta Trail | NCDOT | Brevard Bike Path in Brevard to Kangua Road in Hendersonville | Construct multi-use path. | 19.57 | Bike & Ped | Other | 14 | French Broad River MPO, Land-of-Sky RPO | EB-6037B | Division 14 | L(M), TAANY | 2021 | 8000000 | [6 empty] | 8000000 | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE.
Hertford | NC 11 | NCDOT | SR 1212 (Short Cut Road) to US 158 | Install rumble stripes and pavement markers. |  | Highway | Safety | 1 | Peanut Belt RPO | HS-2401D | Region A | HSIP, T(M) |  |  |  |  | 2025 | 272000 |  |  | 272000 | UNDER CONSTRUCTION.
Hertford | US 158 / US 258 | NCDOT | SR 1157 (Charlie Powell Road), SR 1230 (Clover Circle), and SR 1160 (Benthall Bridge Road) intersections near Murfreesboro | Upgrade roadway to reduced conflict intersections. | 2 | Highway | Safety | 1 | Peanut Belt RPO | HS-2401P | Region A | HF, HSIP |  |  |  |  | 2025 | 5100000 |  |  | 5100000 | HF FUNDS REPRESENT HIGH IMPACT-LOW COST DIVISION FUNDS ($1,421,000) AND RESURFACING FUNDS ($2,000,000).
Hertford | NC 461 | NCDOT | NC 45 to end of state maintenance. | Modernize roadway. | 4.05 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5811 | Division 1 | T |  |  |  |  | 2023 | 5252000 |  |  | 5252000 | UNDER CONSTRUCTION.
Hertford | US 13 / NC 11 | NCDOT | NC 11 / NC 561 intersection in Ahoskie to US 13 / US 158 / NC 45 intersection near Winton | Widen to multi-lanes. | 7.8 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5311
Hertford | US 13 / NC 11 | NCDOT | NC 11 / NC 561 intersection near Ahoskie to US 13 / US 158 / NC 45 intersection near Winton. | Widen to multi-lanes. | 7.77 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5311B | Region A | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 193400000 |  |  | 199300000
Hertford | US 13 / NC 11 | NCDOT | West of Modlin Road to east of NC 11 / SR 1213 (Old NC 11 Road). | Construct grade separation. | 1 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5311A | Statewide Mobility | [10 empty] | COMPLETE.
Hertford | US 13 / NC 42 / NC 561 (Memorial Drive) | NCDOT | Peachtree Street to NC 42 | Widen to three lanes. | 0.78 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5796 | Region A | T | 2024 | 2574000 | 2024 | 2000000 | 2027 | 22695000 |  |  | 27269000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE).
Hertford | SR 1101 (Main Street) | NCDOT | North Carolina & Virginia Railroad Crossing 629828U in Ahoskie. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 1 | Peanut Belt RPO | RX-2401A | Division 1 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Hertford | SR 1409 (Hall Siding Road) | NCDOT | North Carolina & Virginia Railroad Crossing 642347G in Ahoskie. | Construct highway-rail grade crossing safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Peanut Belt RPO | RX-2001A | Division 1 | RR |  |  |  |  | 2025 | 355000 | 2025 | 20000 | 375000 | UNDER CONSTRUCTION.
Hertford, Currituck, Martin, Dare, Gates, Bertie, Northampton, Camden | Various | NCDOT | Primary routes in Division 1 | Upgrade guardrail end units. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2401B | Region A | HSIP, T(M) |  |  |  |  | 2025 | 491000 |  |  | 491000 | UNDER CONSTRUCTION.
Hoke | Hoke Trail | FAYETTEVILLE | Near James A. Leach Aquatic & Recreation Center in Hoke County. | Construct county-operated trail system. |  | Bike & Ped | Locally Selected | 8 | Fayetteville Area MPO | BL-0135 | Division 8 | L(M), TADA |  |  |  |  | 2026 | 429000 |  |  | 429000
Hoke | US 401 | HOKE COUNTY | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Bike & Ped | Locally Selected | 8 | Fayetteville Area MPO | BL-0136 | Division 8 | BGDA, L(M) | 2026 | 40000 | 2026 | 32000 | 2027 | 649000 | 2025 | 50000 | 771000
Hoke | US 401 / NC 211 | HOKE COUNTY | Various locations along routes in Raeford | Install and maintain 5 electric vehicle DC fast chargers. |  | Highway | Locally Selected | 8 | Fayetteville Area MPO | HL-0142 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 580000 | 2025 | 50000 | 630000
Hoke | NC 211 | NCDOT | 0.40 miles north of SR 1225 (Ashemont Road) to east of SR 1244 (West Palmer Street) / SR 1311 (Mockingbird Hill Road) in Raeford | Widen to multi-lanes. | 9.46 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Fayetteville Area MPO | R-5709C | Region E | T |  |  |  |  | 2025 | 104580000 |  |  | 104580000 | UNDER CONSTRUCTION
Hoke | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | NCDOT | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Highway | STI (Prioritization) | 8 | Fayetteville Area MPO | U-5753 | Division 8 | BGANY, BGDA, T | 2022 | 42100000 | 2022 | 5000000 | 2027 | 68110000 |  |  | 115210000 | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE)
Hoke | SR 1406 (Rockfish Road); New Route (Gillis Hill Road) | NCDOT | SR 1003 (Camden Road) to north of Westfield Drive; North of Westfield Drive to SR 1418 (Lindsay Road). | Widen to multi-lanes, part on new location. | 3.19 | Highway | STI (Prioritization) | 8 | Fayetteville Area MPO | U-5857 | Division 8 | T | 2030 | 38200000 | 2030 | 4600000 | 2034 | 86400000 |  |  | 129200000 | COORDINATE WITH U-5753 AND U-5798.
Hoke | SR 1003 (Arabia Road) | NCDOT | Crossing 847348H in Dundarrach | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Fayetteville Area MPO | RX-2008D | Division 8 | RR |  |  |  |  | 2026 | 345000 |  |  | 345000
Hoke, Moore | NC 211 | NCDOT | US 15 / US 501 in Aberdeen to 0.40 miles north of SR 1225 (Ashemont Road) | Widen to multi-lanes. | 5.9 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Central Pines RPO, Fayetteville Area MPO | R-5709B | Region E | T |  |  |  |  | 2029 | 114200000 |  |  | 114200000
Hoke, Moore | NC 211 | NCDOT | US 15 / US 501 in Aberdeen to east of SR 1244 (West Palmer Street) / SR 1311 (Mockingbird Hill Road) in Raeford | Clearing, grubbing, and erosion control. | 15.36 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Fayetteville Area MPO, Central Pines RPO | R-5709A | Region E | T |  |  |  |  | 2022 | 30625000 |  |  | 30625000 | UNDER CONSTRUCTION.
Hoke, Moore | NC 211 | NCDOT | US 15 / US 501 in Aberdeen to east of SR 1244 (West Palmer Street) / SR 1311 (Mockingbird Hill Road) in Raeford. | Widen to a four lane divided facility. | 15.36 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Fayetteville Area MPO, Central Pines RPO | R-5709 | Region E | T | 2021 | 59423000 | 2021 | 4976000 |  |  |  |  | 64399000 | RIGHT-OF-WAY IN PROGRESS
Hyde | 7W6 | HYDE COUNTY AIRPORT (7W6) | Hyde County Airport | Extend runway to 5500 feet. |  | Aviation | STI (Prioritization) | 1 | Albemarle RPO | AV-5812 | Division 1 | T |  |  |  |  | 2023 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION.
Hyde | Hatteras to Ocracoke Ferry | NCDOT | Ocracoke Terminal - Silver Lake | Construct Ocracoke pedestrian waiting and access accommodations. |  | Ferry | Other | 1 | Albemarle RPO | F-5702B | Division 1 | [10 empty] | COMPLETE.
Iredell | SVH | STATESVILLE REGIONAL AIRPORT (SVH) | Statesville Regional Airport | Relocate East Aviation Drive to allow for future runway extension. |  | Aviation | STI (Prioritization) | 12 | Charlotte Regional TPO | AV-5896 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4700000 |  |  | 11700000
Iredell | Bellingham Park Greenway | MOORESVILLE | Bellingham Park to SR 1142 (Johnson Dairy Road) in Mooresville | Extend greenway. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5787 | Division 12 | L(M), TADA |  |  |  |  | 2023 | 4444000 |  |  | 4444000 | UNDER CONSTRUCTION.
Iredell | Moore Avenue | MOORESVILLE | South Church Street to North Academy Street in Mooresville | Construct pedestrian improvements. | 0.22 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0013 | Division 12 | L(M), TAANY |  |  |  |  | 2026 | 1990000 | 2024 | 10000 | 2000000 | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23.
Iredell | NC 115 | MOORESVILLE | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0082 | Division 12 | L, TAANY, TADA | 2027 | 700000 |  |  | 2029 | 3829000 | 2025 | 344000 | 4873000 | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24.
Iredell | NC 152 (North Main Street) | MOORESVILLE | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0160 | Division 12 | BGDA, L(M) | 2027 | 666000 | 2027 | 10000 | 2029 | 599000 | 2026 | 290000 | 1565000
Iredell | NC 152 (North Main Street) | MOORESVILLE | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0009 | Division 12 | BGDA, L(M) | 2026 | 617000 |  |  | 2027 | 729000 | 2026 | 138000 | 1484000
Iredell | New Route | MOORESVILLE | South Elementary School to Mooresville Middle School in Mooresville | Construct greenway connectors. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0055 | Division 12 | L(M), TAANY |  |  |  |  | 2026 | 2081000 | 2025 | 363000 | 2444000 | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23
Iredell | Patterson Heights | MOORESVILLE | West Moore Avenue to West Iredell Avenue in Mooresville | Construct greenway. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0122 | Division 12 | BGDA, L(M) |  |  |  |  | 2028 | 3148000 | 2025 | 10000 | 3158000
Iredell | Richardson Greenway South, US 21 / NC 115 (South Main Street) | TROUTMAN | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5932 | Division 12 | L(M), TADA | 2026 | 217000 |  |  | 2027 | 1250000 | 2021 | 122000 | 1589000
Iredell | Rumple Street; Wagner Street | TROUTMAN | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5930 | Division 12 | L(M), TADA | 2026 | 199000 |  |  | 2026 | 1623000 | 2021 | 312000 | 2134000
Iredell | Shelton Avenue Multi-Use Path | STATESVILLE | Garner Bagnal Boulevard to SR 2342 (Amity Hill Road) in Statesville | Construct greenway. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5788 | Division 12 | BGDA, L(M) | 2023 | 251000 | [6 empty] | 251000 | RIGHT-OF-WAY IN PROGRESS
Iredell | SR 1306 (Rinehardt Road) | MOORESVILLE | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0159 | Division 12 | BGDA, L(M) | 2027 | 1105000 | 2027 | 10000 | 2029 | 1493000 | 2026 | 580000 | 3188000
Iredell | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | MOORESVILLE | Various locations in Mooresville | Construct sidewalks. | 0.69 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0056 | Division 12 | BGDA, L(M) | 2027 | 104000 |  |  | 2029 | 1972000 | 2024 | 563000 | 2639000
Iredell | US 21 (Turnersburg Highway) | STATESVILLE | Statesville Greenway - Gregory Creek Segment to Statesville Greenway - Fourth Creek Greenway Segment near Statesville. | Construct greenway connector under US 21. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5818 | Division 12 | BGDA, L(M), TAANY |  |  |  |  | 2026 | 2432000 |  |  | 2432000 | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23
Iredell | Various | MOORESVILLE | SR 1148 (Kistler Farm Road); Briarcliff Road; Bellingham Drive; White Oak Road in Mooresville | Construct sidewalks. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | C-5531 | Exempt | BGDA, L(M) |  |  |  |  | 2020 | 801000 |  |  | 801000 | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
Iredell | I-40 | NCDOT | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | HB-0018 | Statewide Mobility | BFP, T(M) | 2026 | 710000 | 2026 | 660000 | 2030 | 59900000 |  |  | 61270000
Iredell | I-77 | NCDOT | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | HB-0041 | Statewide Mobility | BFP, T(M) | 2026 | 370000 | 2026 | 320000 | 2030 | 23900000 |  |  | 24590000
Iredell | SR 1004 (Hudson Chapel Road) | NCDOT | Bridge 480081 over Catawba River. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | HB-0032 | Division 12 | BGOFF | 2025 | 1000000 | 2025 | 10000 | 2028 | 20400000 |  |  | 21410000
Iredell | SR 1577 (Pisgah Ridge Circle) | NCDOT | Bridge 480131 over Unnamed Tributary to Snow Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0107 | Highway Fund | HFB |  |  |  |  | 2022 | 800000 |  |  | 800000 | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
Iredell | SR 1595 (Coolbrook Road) | NCDOT | Bridge 480166 on SR 1595 over Rocky Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0115 | Division 12 | DP, HFB | 2020 | 170000 |  |  | 2021 | 1600000 |  |  | 1770000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Iredell | SR 1601 (Branton Road) | NCDOT | Bridge 480165 on SR 1601 over Rocky Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0114 | Division 12 | DP, HFB | 2020 | 150000 |  |  | 2021 | 1150000 |  |  | 1300000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Iredell | SR 1639 (Meacham Road) | NCDOT | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0025 | Division 12 | BFP, T(M) | 2029 | 80000 | 2029 | 10000 | 2031 | 4200000 |  |  | 4290000
Iredell | SR 1892 (Jennings Road) | NCDOT | Bridge 480189 over South Yadkin River. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | B-5846 | Division 12 | BGOFF | 2022 | 85000 | 2022 | 325000 | 2023 | 5615000 |  |  | 6025000 | UNDER CONSTRUCTION.
Iredell | SR 1892 (Jennings Road) | NCDOT | Bridge 480212 over Patterson Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0202 | Highway Fund | HFB |  |  |  |  | 2021 | 1250000 |  |  | 1250000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49
Iredell | SR 1892 (Jennings Road) | NCDOT | Bridge 480219 over Olin Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0204 | Highway Fund | HFB |  |  |  |  | 2021 | 900000 |  |  | 900000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51
Iredell | SR 1896 (Friendship Road) | NCDOT | Bridge 480214 over Patterson Creek | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0203 | Highway Fund | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50
Iredell | SR 2402 (Hoover Road) | NCDOT | Bridge 480020 over I-L Creek. | Replace bridge. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | B-5843 | Division 12 | BGOFF | 2028 | 67000 |  |  | 2030 | 1500000 |  |  | 1567000
Iredell | I-40 | NCDOT | SR 2158 (Old Mocksville Road) to Davie County line. | Rehabilitate pavement. | 8.26 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5805 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2030 | 53000000 |  |  | 53000000
Iredell | I-77 | NCDOT | Mile marker 36.5 to mile marker 50.0. | Rehabilitate pavement. | 13.55 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5918 | Statewide Mobility | NHFP, NHPIM, PROTCT |  |  |  |  | 2024 | 30201000 |  |  | 30201000
Iredell | I-77 | NCDOT | Mile marker 52.6 to mile marker 56.8. | Rehabilitate pavement. | 3.1 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5919 | Statewide Mobility | NHPIM |  |  |  |  | 2025 | 8773000 |  |  | 8773000
Iredell | I-77 | NCDOT | Mile marker 58.4 to Yadkin County line. | Rehabilitate pavement. | 10.41 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5920 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2028 | 24302000 |  |  | 24302000
Iredell | Langtree Road | MOORESVILLE | Pin Oak Lane to Mount Mourne Loop. | Widen roadway. | 1.21 | Highway | Locally Selected | 12 | Charlotte Regional TPO | HL-0114 | Division 12 | L, T(DA) | [6 empty] | 2024 | 1091000 | 1091000 | $873K IN STBG-DA FUNDS SWAPPED FOR $873K IN STATE FUNDS ON 5-17-23
Iredell | NC 115 | MOORESVILLE | Faith Road / Campus Lane intersection in Mooresville. | Realign Faith Road to tie into existing NC 115 / Campus Lane intersection. Construct dedicated turn lanes on Faith Road and Campus Lane at intersection. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | C-5529 | Exempt | BGDA, L(M) |  |  |  |  | 2023 | 1128000 | 2023 | 259000 | 1387000 | UNDER CONSTRUCTION
Iredell | NC 115 | MOORESVILLE | NC 150 intersection in Mooresville. | Construct southbound right turn lane on NC 115 and westbound shared through-right lane on NC 150. |  | Highway | Locally Selected | 12 | Charlotte Regional TPO | C-5200 | Exempt | BGDA, L(M) |  |  |  |  | 2020 | 1514000 |  |  | 1514000 | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
Iredell | NC 115 | MOORESVILLE | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6249 | Exempt | BGDA, L, L(M), T(DA) | 2026 | 500000 |  |  | 2028 | 4006000 | 2021 | 560000 | 5066000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23
Iredell | NC 801 | MOORESVILLE | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | C-5701 | Region F | BA, BGDA, CMAQ, L(M) | 2020 | 324000 |  |  | 2020 | 3236000 |  |  | 3560000 | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Iredell | New Route | MOORESVILLE | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6239 | Division 12 | BGDA, DP, L(M) | 2022 | 5555000 |  |  | 2022 | 32014000 | 2021 | 1268000 | 38837000 | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORSVILLE.
Iredell | SR 1363 (Bethlehem Road) | STATESVILLE | Aviation Drive to Bethlehem Road. | Relocate roadway adjacent to Statesville Regional Airport. | 0.76 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6153 | Division 12 | BA, O, T |  |  |  |  | 2029 | 4648000 | 2020 | 452000 | 5100000 | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT.
Iredell | US 21 / NC 115 (Main Street) | TROUTMAN | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | HL-0134 | Region F | BGANY, L | 2027 | 1582000 |  |  | 2029 | 3295000 | 2025 | 580000 | 5457000 | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24.
Iredell | Various | NCDOT | Routes in Division 12. | Perform various maintenance activities including resurfacing and pavement restriping. |  | Highway | Locally Selected | 12 | Charlotte Regional TPO | HL-0037 | Division 12 | BGDACV |  |  |  |  | 2023 | 975000 |  |  | 975000
Iredell | I-40 | NCDOT | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | I-3819A | Pre-STI (Transition) | NHP |  |  |  |  | 2012 | 4388000 |  |  | 4388000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
Iredell | I-77 | NCDOT | Mile marker 57.83 to mile marker 61.74. | Rehabilitate pavement. | 3.9 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | I-5106 | Pre-STI (Transition) | NHP |  |  |  |  | 2009 | 439000 |  |  | 439000 | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020
Iredell | SR 1100 (Brawley School Road) | NCDOT | SR 1109 (Centre Church Road) to I-77 | Widen to multi-lanes. | 1.1 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | R-3833B | [11 empty] | COMPLETE
Iredell | SR 1100 (Brawley School Road) | NCDOT | SR 1177 (Chuckwood Road) to SR 1109 (Centre Church Road). | Widen to multi-lanes. | 3.9 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | R-3833A | [11 empty] | COMPLETE
Iredell | NC 150 | NCDOT | Mile marker 11.4 to mile marker 11.9. | Install centerline and shoulder rumble stripes. |  | Highway | Safety | 12 | Charlotte Regional TPO | HS-2012K | Region F | HSIP, T(M) |  |  |  |  | 2024 | 24000 |  |  | 24000
Iredell | NC 150 | NCDOT | NC 152 (western intersection) in Mooresville. | Install rumble stripes, guardrail, safety and lighting improvements. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | W-5601U | Region F | HF, HSIP | 2022 | 472000 |  |  | 2025 | 1965000 |  |  | 2437000 | RIGHT-OF-WAY IN PROGRESS.
Iredell | SR 1005 (Old Mountain Road) | NCDOT | Alexander County line to south of SR 1498 (Southwood Drive) | Install rumble strips. | 12.1 | Highway | Safety | 12 | Charlotte Regional TPO | HS-2612D | Division 12 | HSIP, T(M) |  |  |  |  | 2026 | 443000 |  |  | 443000
Iredell | SR 1125 (Shearers Road) | NCDOT | SR 1147 (Rocky River Road) intersection near Mooresville. | Install traffic signal. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | HS-2012C | Division 12 | HSIP, T(M) |  |  |  |  | 2023 | 204000 | 2022 | 20000 | 224000 | UNDER CONSTRUCTION.
Iredell | SR 1303 (Perth Road) | NCDOT | SR 1302 (Cornelius Road) intersection near Mooresville. | Install signal and turn lanes. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | W-5212JB | Division 12 | BGANY, HF(M) | 2022 | 125000 |  |  | 2023 | 1091000 |  |  | 1216000 | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP.
Iredell | SR 1303 (Perth Road) | NCDOT | SR 1378 (Judas Road) intersection near Mooresville. | Install signal. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | W-5212JA | Division 12 | BGANY, BGDA, HF(M) | 2020 | 25000 |  |  | 2022 | 125000 |  |  | 150000 | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION.
Iredell | I-40 | NCDOT | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | I-3819 | [11 empty] | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023
Iredell | I-40 | NCDOT | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | I-3819B | Statewide Mobility | T |  |  |  |  | 2019 | 360365000 |  |  | 360365000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
Iredell | I-77 | NCDOT | SR 1302 (Cornelius Road). | Upgrade grade separation to an interchange. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | I-5962 | Statewide Mobility | NHP | 2028 | 7000000 | 2028 | 630000 | 2031 | 58960000 |  |  | 66590000
Iredell | NC 150 | NCDOT | Good Luck Lane to Morrison Plantation Parkway in Mooresville. | Extend eastbound right and through lane. | 0.28 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-2307BA | Region F | T |  |  |  |  | 2023 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
Iredell | NC 150 | NCDOT | SR 2399 (Wiggins Road) intersection in Mooresville. | Realign intersection. | 0.5 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5780 | Region F | T | 2019 | 605000 | 2025 | 865000 | 2025 | 4520000 |  |  | 5990000 | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U.
Iredell | SR 1100 (Brawley School Road) | NCDOT | I-77 to US 21 in Mooresville | Widen to multi-lanes. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-3833C | Division 12 | L, T | 2019 | 5610000 | 2019 | 1950000 | 2024 | 43837000 |  |  | 51397000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE.
Iredell | SR 1100 (Brawley School Road) | NCDOT | SR 1177 (Chuckwood Road) to US 21 in Mooresville. | Widen to multi-lanes with interchange at I-77. | 5.9 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-3833 | [11 empty] | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE.
Iredell | SR 1109 (Williamson Road) | NCDOT | I-77 to NC 150 in Mooresville. | Widen to four lanes. | 3.2 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5100 | [11 empty] | COORDINATE WITH U-5817.
Iredell | SR 1109 (Williamson Road) | NCDOT | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5100A | Division 12 | T | 2020 | 11700000 | 2022 | 5300000 | 2027 | 77305000 | 2020 | 600000 | 94905000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE).
Iredell | SR 1109 (Williamson Road) | NCDOT | SR 1100 (Brawley School Road) to NC 150 in Mooresville. | Widen to four lanes. | 0.87 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5100B | Division 12 | BGANY, T | 2019 | 10340000 | 2026 | 1300000 | 2026 | 10500000 |  |  | 22140000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
Iredell | SR 1246 (Fairview Road) | NCDOT | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5817 | Division 12 | BA, BGANY, BGDA, T, T(M), TADA | 2019 | 9299000 | 2019 | 1900000 | 2027 | 25200000 | 2015 | 2694000 | 39093000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100.
Iredell | SR 1305 (Oates Road / Midnight Lane) | NCDOT | US 21 (Charlotte Highway) to SR 1474 (Bluefield Road) in Mooresville. | Widen to three lanes with overpass over I-77. | 1.56 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5816 | Division 12 | T | 2026 | 25700000 | 2026 | 3200000 | 2029 | 52805000 |  |  | 81705000 | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
Iredell | SR 2321 (East Broad Street) | NCDOT | Vine Street to SR 2422 (Signal Hill Drive). | Upgrade roadway and implement access management solutions. | 0.68 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-6039 | Division 12 | T |  |  |  |  | 2019 | 5350000 |  |  | 5350000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B
Iredell | US 21 | NCDOT | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5799 | Region F | T | 2020 | 22360000 | 2023 | 4000000 | 2031 | 29400000 | 2020 | 2265000 | 58025000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
Iredell | US 21 | NCDOT | SR 2375 (Houston Road) / SR 1312 (Flower House Road) intersection in Troutman. | Realign and signalize intersection. | 0.5 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5711 | Region F | T | 2024 | 100000 | 2025 | 600000 | 2026 | 5200000 |  |  | 5900000 | RIGHT-OF-WAY IN PROGRESS
Iredell | US 21 (Charlotte Highway) | NCDOT | NC 150 (Plaza Drive) to SR 1245 (Medical Park Road). | Widen to four lanes divided. | 2.64 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-6037 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 77000000 |  |  | 119400000
Iredell | US 64 (Davie Avenue) | NCDOT | US 21 (Sullivan Road) intersection in Statesville. | Upgrade 5-approach intersection to a single lane roundabout. | 0.5 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5964 | Region F | T | 2024 | 3800000 | 2024 | 700000 | 2026 | 4500000 |  |  | 9000000
Iredell | SR 1302 (Perth Road) | NCDOT | SR 1378 (Judas Road) and SR 1302 (Cornelius Road) intersections near Mooresville. | Construct intersection improvements. | 0.5 | Highway | Transition | 12 | Charlotte Regional TPO | W-5212J | Division 12 | BGANY, HF(M) | [6 empty] | 2020 | 356000 | 356000 | $178K IN BGANY USED AS PART OF FUND SWAP.
Iredell | Iredell County Area Transportation System (ICATS) | IREDELL COUNTY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Charlotte Regional TPO | TO-5149 | Public Transit | 5307, L | [6 empty] | 2020 | 687000 | 687000 | FUNDS AUTHORIZED IN PROGRESS
Iredell | Iredell County Area Transportation System (ICATS) | IREDELL COUNTY | Systemwide | Funding for operations. |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Charlotte Regional TPO | TO-6158 | Public Transit | 5307, 5316, L, L(M) |  |  |  |  | 2026 | 500000 | 2020 | 4372000 | 4872000
Iredell | Iredell County Area Transportation System (ICATS) | IREDELL COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Charlotte Regional TPO | TK-6179 | Public Transit | 5311 | [6 empty] | 2020 | 1040000 | 1040000 | FUNDS AUTHORIZED IN PROGRESS
Iredell | SR 2395 (Mazeppa Road) | NCDOT | NC 115 intersection in Mooresville. | Construct grade separation over Norfolk Southern railroad and NC 115. | 0.3 | Rail | Locally Selected | 12 | Charlotte Regional TPO | RL-0001 | Region F | BGDA, DP, L(M) | 2025 | 320000 |  |  | 2026 | 12633000 | 2021 | 1298000 | 14251000 | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT.
Iredell | Opal Street | NCDOT | Norfolk Southern Crossing 729684T in Statesville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Charlotte Regional TPO | RX-2012D | Division 12 | RR |  |  |  |  | 2025 | 611000 |  |  | 611000
Iredell | SR 1639 (Meacham Road) | NCDOT | ARC Crossing 865740U in Statesville. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 12 | Charlotte Regional TPO | RX-2412A | Division 12 | RR |  |  |  |  | 2026 | 560000 |  |  | 560000
Iredell | Wall Street | NCDOT | Norfolk Southern Crossing 729686G in Statesville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Charlotte Regional TPO | RX-2012B | Division 12 | RR |  |  |  |  | 2025 | 650000 |  |  | 650000
Iredell, Catawba | I-40 | NCDOT | East of SR 1007 (1st Street West) to East of NC 115. | Rehabilitate bridge. |  | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO, Greater Hickory MPO | I-5915B | Statewide Mobility | BGDA, NHPIM, T(M) |  |  |  |  | 2023 | 12240000 |  |  | 12240000 | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION.
Iredell, Catawba | I-40 | NCDOT | East of SR 1007 (1st Street West) to East of NC 115. | Rehabilitate pavement. | 32.62 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO, Greater Hickory MPO | I-5915A | Statewide Mobility | [10 empty] | COMPLETE
Iredell, Catawba | I-40 | NCDOT | Mile marker 130.7 to mile marker 150.2. | Rehabilitate pavement and bridge. | 19.5 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO, Greater Hickory MPO | I-5915
Iredell, Catawba | Various | NCDOT | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Highway | Safety | 12 | Charlotte Regional TPO, Greater Hickory MPO | W-5212DIV | Division 12 | HSIP, T(M) | 2020 | 50000 |  |  | 2020 | 2500000 |  |  | 2550000 | IN PROGRESS.
Iredell, Catawba | NC 150 | NCDOT | SR 1840 (Greenwood Road) in Catawba County to west of SR 1303 / SR 1180 (Perth Road / Doolie Road) in Iredell County; SR 1383 / SR 1180 to US 21 in Iredell County | Widen to four lanes; Widen to six lanes. | 6.9 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO, Greater Hickory MPO | R-2307B | Region F | NHP |  |  |  |  | 2025 | 289272000 |  |  | 289272000 | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION FUNDED WITH TOLL CREDITS. BUILD NC BONDS: $50M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); $22.5M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE)
Iredell, Mecklenburg | I-77 | NCDOT | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Highway | STI (Prioritization) | 10, 12 | Charlotte Regional TPO | I-4750AB | Not Funded | NHP, T(M) | NOT FUNDED | 10500000 | NOT FUNDED | 675000 | NOT FUNDED | 133000000 | NOT FUNDED |  | 144175000
Iredell, Mecklenburg | I-77 | NCDOT | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Widen and reconstruct roadway. | 23 | Highway | STI (Prioritization) | 10, 12 | Charlotte Regional TPO | I-4750 | [11 empty] | FUNDING FOR I-4750 AA INCLUDED IN I-5405
Iredell, Mecklenburg | I-77 | NCDOT | SR 5544 (West Catawba Avenue) to NC 150. | Construct high occupancy/toll (hot) lanes. | 7.79 | Highway | Transition | 10, 12 | Charlotte Regional TPO | I-4750AA | [11 empty] | COMPLETE - UNDER CONSTRUCTION WITH PROJECT I-5405
Jackson | SR 1737 (Caney Fork Road), SR 1432 (Skyland Drive) | NCDOT | Various locations | Construct bicycle pullouts. |  | Bike & Ped | Federal Lands Access Program | 14 | Southwestern RPO | BF-0001 | Exempt | FLAP, HF(M) |  |  |  |  | 2022 | 190000 | 2022 | 10000 | 200000 | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION.
Jackson | Monteith Greenway | NCDOT | Great Smoky Mountain Railroad | Construct pedestrian bridge over Great Smoky Mountain Railroad. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | BN-0003A | Exempt
Jackson | Monteith Greenway | NCDOT | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | BN-0003 | Exempt | CRP550, L, L(M), O, TAP |  |  |  |  | 2026 | 2030000 | 2024 | 500000 | 2530000 | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO.
Jackson | NC 107 | NCDOT | SR 1330 (Forest Hills Road / North Country Club Road) to the Jackson County Recreation Complex near the intersection of SR 1545 (Wisdom Drive) and Cullowhee Mountain Road near Cullowhee. | Construct multi-use path on west side. | 0.3 | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | BN-0015 | Exempt | CRP550, L(M) |  |  |  |  | 2026 | 1647000 | 2025 | 440000 | 2087000
Jackson | SR 1432 (Skyland Drive) | NCDOT | SR 1429 (Chipper Curve Road) to US 23 Business in Sylva | Construct sidewalk. | 0.72 | Bike & Ped | STI (Prioritization) | 14 | Southwestern RPO | EB-5923 | Division 14 | L(M), TALT5 |  |  |  |  | 2023 | 960000 |  |  | 960000 | UNDER CONSTRUCTION.
Jackson | SR 1120 (Cedar Creek Road) | NCDOT | Bridge 490008 over Cedar Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-5921 | Division 14 | BGOFF | 2024 | 410000 |  |  | 2025 | 2900000 |  |  | 3310000 | RIGHT-OF-WAY IN PROGRESS
Jackson | SR 1300 (Pumpkintown Road) | NCDOT | Bridge 490065 over Savannah Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6034 | Division 14 | BGOFF | 2024 | 70000 |  |  | 2026 | 1800000 |  |  | 1870000
Jackson | SR 1300 (Pumpkintown Road) | NCDOT | Bridge 490069 over Savannah Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6031 | Division 14 | BGOFF, T(M) | 2024 | 80000 |  |  | 2029 | 2400000 |  |  | 2480000
Jackson | SR 1397 (Thomas Valley Road) | NCDOT | Bridge 490144 over Nations Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6032 | Division 14 | BGOFF | 2021 | 50000 |  |  | 2022 | 983000 |  |  | 1033000 | UNDER CONSTRUCTION. 80 2019 BGOFF R 0
Jackson | SR 1445 (Lee Bumgarner Road) | NCDOT | Bridge 490129 over Scott Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6033 | Division 14 | BGOFF, T(M) |  |  |  |  | 2029 | 3000000 |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS
Jackson | SR 1737 (Caney Fork Road) | NCDOT | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6036 | Division 14 | BGOFF, T(M) | 2026 | 410000 | 2026 | 60000 | 2027 | 1900000 |  |  | 2370000
Jackson | SR 1738 (Hooper Cemetery Road) | NCDOT | Bridge 490203 over Caney Fork. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6035 | Division 14 | BGOFF | 2021 | 70000 |  |  | 2022 | 1495000 |  |  | 1565000 | UNDER CONSTRUCTION.
Jackson | SR 1157 (Cullowhee Mountain Road) | NCDOT | Mile marker 2.6 to mile marker 6.6 near Cullowhee. | Install guardrail. | 4.02 | Highway | Safety | 14 | Southwestern RPO | HS-2014B | Division 14 | HSIP, T(M) |  |  |  |  | 2022 | 110000 |  |  | 110000 | UNDER CONSTRUCTION.
Jackson | SR 1325 (Centennial Drive) | NCDOT | Three midblock crossings near SR 1169 (Central Drive). | Install rectangular flashing beacons. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014D | Division 14 | HSIP, T(M) |  |  |  |  | 2022 | 59000 |  |  | 59000 | UNDER CONSTRUCTION.
Jackson | SR 1356 (Savannah Drive) | NCDOT | US 23 Business to Nicol Arms Road. | Construct sidewalk. | 0.12 | Highway | Safety | 14 | Southwestern RPO | HS-2014AD | Division 14 | HSIP, T(M) |  |  |  |  | 2025 | 146000 |  |  | 146000
Jackson | US 23 / US 441 | NCDOT | SR 1320 (Greens Creek Road). | Install a Directional Leftover with one bulb-out (RCI). |  | Highway | Safety | 14 | Southwestern RPO | HS-2414N | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 970000 |  |  | 970000
Jackson | US 23 Business (Haywood Road); SR 1557 (Front Street) | NCDOT | Church Street intersection in Dillsboro; SR 1558 (Depot Street) intersection in Dillsboro. | Install rectangular rapid flashing beacon and upgrade curb ramps. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014H | Region G | HSIP, T(M) |  |  |  |  | 2023 | 107000 |  |  | 107000
Jackson | US 64 | NCDOT | SR 1119 (Sapphire Post Office Road) at Chrysler Curve near Sapphire. | Construct safety improvements. | 0.68 | Highway | Safety | 14 | Southwestern RPO | W-5714E | Region G | HSIP, T(M) |  |  |  |  | 2024 | 974000 |  |  | 974000
Jackson | NC 107 | NCDOT | SR 1002 (Old Cullowhee Road) to NC 281. | Upgrade existing roadway. | 4.01 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-4753 | Division 14 | [10 empty] | UNDER CONSTRUCTION
Jackson | NC 107; US 23 Business | NCDOT | US 23 Business to NC 116 (Webster Road); SR 1432 (Skyland Drive) to west of Municipal Drive in Sylva. | Construct access management improvements. | 1.85 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5600 | Region G | BG5T50, T, T(M) | 2022 | 70440000 | 2022 | 7200000 | 2026 | 119893000 |  |  | 197533000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE).
Jackson | US 64 | NCDOT | NC 107 intersection in Cashiers. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5881 | Region G | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 |  |  | 15100000
Jackson | US 74 (Great Smokey Mountains Expressway) | NCDOT | US 441 Gateway interchange to SR 1391 (West Piney Mountain Road). | Modernize roadway, including replacement of Bridge 490043 over the Tuckasegee River. | 2.81 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5907 | Division 14 | BGLT5, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 420000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35000000 |  |  | 38920000
Jackson | Jackson County Transit | JACKSON COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6137 | Public Transit | 5311, L, S | [6 empty] | 2020 | 752000 | 752000 | FUNDS AUTHORIZED IN PROGRESS
Jackson | SR 1429 (Chipper Curve Road) | NCDOT | Blue Ridge Southern Railroad Crossing 720247S in Sylva. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO | RX-2414M | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Jackson | SR 1513 (Grindstaff Cove Road) | NCDOT | Blue Ridge Southern Railroad Crossing 720244W in Sylva. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO | RX-2414L | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Jackson, Swain | Indian Reservation Road (IRR) Program. | NCDOT | Various locations. | Improve roads and bridges. Constructed by Eastern Band of Cherokee Indians. |  | Highway | Other | 14 | Southwestern RPO | R-5500 | Exempt | [10 empty] | PROGRAM IN PROGRESS
Jackson, Swain | US 441; US 19 | NCDOT | Various locations. | Upgrade guardrail end units. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414J | Region G | HSIP, T(M) |  |  |  |  | 2025 | 110000 |  |  | 110000
Johnston | JNX | JOHNSTON COUNTY AIRPORT (JNX) | Johnston County Airport | Acquire and clear land. |  | Aviation | STI (Prioritization) | 4 | Upper Coastal Plain RPO | AV-5745 | Division 4 | T |  |  |  |  | 2023 | 2664000 | 2024 | 195000 | 2859000 | UNDER CONSTRUCTION
Johnston | Main Street | CLAYTON | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Bike & Ped | Locally Selected | 4 | Capital Area MPO | BL-0125 | Division 4 | L, L(M), TADA | 2027 | 50000 |  |  | 2027 | 1490000 | 2026 | 10000 | 1550000
Johnston | Neuse River | JOHNSTON COUNTY | From proposed residential development to future school complex near SR 2589 (Clearwater Drive) in Wilson's Mills | Construct multi-use path along Neuse River. |  | Bike & Ped | Locally Selected | 4 | Upper Coastal Plain RPO | BN-0024 | Exempt | CRPANY, L(M) |  |  |  |  | 2026 | 4011000 | 2025 | 200000 | 4211000
Johnston | SR 1004 (East Main Street) | CLAYTON | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Bike & Ped | Locally Selected | 4 | Capital Area MPO | BL-0050 | Exempt | CMAQ, L(M) | 2024 | 200000 |  |  | 2026 | 440000 | 2024 | 10000 | 650000 | RIGHT-OF-WAY IN PROGRESS.
Johnston | SR 2130 (West Main Street) | MICRO | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Bike & Ped | Locally Selected | 4 | Upper Coastal Plain RPO | BN-0025 | Exempt | CRP550, L(M) | 2025 | 175000 |  |  | 2026 | 870000 | 2025 | 175000 | 1220000
Johnston | US 70 Business (West Market Street) | SMITHFIELD | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Bike & Ped | NCDOT Selected (Other Selection Process) | 4 | Upper Coastal Plain RPO | BN-0001 | Exempt | CMAQ, CRP550, L(M) | 2026 | 100000 |  |  | 2026 | 2344000 | 2024 | 225000 | 2669000 | WEST MARKET STREET MULTI-USE PATH
Johnston | Venture Drive | Smithfield | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Bike & Ped | NCDOT Selected (Other Selection Process) | 4 | Upper Coastal Plain RPO | BN-0032 | Exempt | CMAQ, L(M) | 2027 | 180000 |  |  | 2028 | 1170000 | 2026 | 175000 | 1525000
Johnston | East Clayton Connector Greenway | CLAYTON | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Bike & Ped | STI (Prioritization) | 4 | Capital Area MPO | EB-6016 | Division 4 | L(M), TAANY | 2029 | 720000 | 2029 | 1200000 | 2031 | 3800000 | 2027 | 258000 | 5978000
Johnston | Mountains to Sea Trail | CLAYTON | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Bike & Ped | STI (Prioritization) | 4 | Capital Area MPO | EB-6017 | Division 4 | L(M), TAANY | 2030 | 1500000 | 2030 | 10000 | 2032 | 2100000 | 2028 | 83000 | 3693000
Johnston | I-95 | NCDOT | Bridges 500082 and 500085 over Black Creek and bridges 500100 and 500101 over Neuse River. | Replace bridges. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6044 | Statewide Mobility | BFP, HFB | 2023 | 110000 |  |  | 2029 | 53900000 |  |  | 54010000 | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH HB-0042 AND I-5974.
Johnston | I-95 | NCDOT | Bridges 500118 and 500119 over CSX railroad. | Replace bridges. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4937 | Statewide Mobility | T | 2030 | 9399000 | 2030 | 300000 | 2034 | 34400000 |  |  | 44099000
Johnston | SR 1555 (Barbour Mill Road) | NCDOT | Bridge 500145 over Swift Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Capital Area MPO | B-5664 | Division 4 | [10 empty] | UNDER CONSTRUCTION.
Johnston | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | NCDOT | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6050 | Division 4 | BFP, T(M) | 2025 | 2100000 | 2025 | 6100000 | 2031 | 91600000 |  |  | 99800000
Johnston | SR 2143 (Beulahtown Road) | NCDOT | Bridge 500216 over Little Buffalo Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4562 | Division 4 | [10 empty] | UNDER CONSTRUCTION. DESIGN BUILD PROJECT.
Johnston | I-95 | NCDOT | Bridge 500117 on SR 2399 (Truck Stop Road) over I-95. | Replace bridge and adjust service roads and approaches. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-5786A | Statewide Mobility
Johnston | I-95 | NCDOT | Mile marker 97 to mile marker 101. | Rehabilitate pavement. | 4.01 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0008 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 7229000 |  |  | 7229000 | UNDER CONSTRUCTION.
Johnston | I-95 | NCDOT | South of SR 1001 (Lizzie Mill Road) to Johnston/Wilson County line north of NC 222. | Rehabilitate pavement. | 11.75 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-5786 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
Johnston | I-95 | NCDOT | US 70 to US 301. | Rehabilitate pavement. | 10.7 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-3318
Johnston | I-95 | NCDOT | US to north of mile marker 100. | Rehabilitate bridge and pavement. | 2.859 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-3318A | [11 empty] | COMPLETE.
Johnston | US 70 (Future I-42) | NCDOT | SR 1003 (Buffalo Road) to Wayne County line. | Rehabilitate pavement. | 13.32 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6044 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 6090000 |  |  | 6090000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033.
Johnston | SR 1552 (South Robertson Street / Amelia Church Road); SR 1004 (Main Street) |  | Kenmore Drive to SR 1004 (Main Street); SR 1552 (South Robertson Street) to South Moore Street in Clayton. | Install curb and gutter, construct sidewalks, and construct intersection improvements. |  | Highway | Locally Selected | 4 | Capital Area MPO | HL-0129 | Division 4 | L(M), TADA | 2026 | 550000 |  |  |  |  | 2024 | 700000 | 1250000
Johnston | SR 1560 (Ranch Road Extension) | NCDOT | US 70 Business / NC 42 to SR 1560 (Ranch Road) in Clayton. | Construct roadway extension on new location. | 0.4 | Highway | Locally Selected | 4 | Capital Area MPO | U-6223 | Division 4 | BGDA, HF, HF(M), L(M) | 2021 | 2169000 |  |  | 2022 | 11250000 |  |  | 13419000 | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS.
Johnston | US 70 Business | NCDOT | SR 1553 (Shotwell Road) intersection in Clayton. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 4 | Capital Area MPO | HL-0127 | Exempt | CRPDA, HF(M) |  |  |  |  | 2024 | 5751000 |  |  | 5751000 | HF(M) REPRESENTS HIGH-IMPACT LOW-COST FUNDS
Johnston | SR 1908 (Fire Dept Road) | JOHNSTON COUNTY | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Highway | NCDOT Selected (Other Selection Process) | 4 | Capital Area MPO, Upper Coastal Plain RPO | HN-0040 | Exempt | CRPLT5, T(M) | 2026 | 1000000 |  |  | 2026 | 6800000 | 2025 | 1000000 | 8800000
Johnston | NC 42 | NCDOT | US 70 in Clayton to east of SR 1902 (Glen Laurel Road) | Widen to multi-lanes. | 1.5 | Highway | Pre-STI (Historic) | 4 | Capital Area MPO | R-3825A | [11 empty] | COMPLETE.
Johnston | NC 210 | NCDOT | Harnett County line to NC 50 and SR 1382 (North Pleasant-Coates Road) to SR 1010 (Cleveland Road). | Install rumble stripes and snowplowable pavement markers | 17 | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | HS-2404B | Region A | HSIP, T(M) |  |  |  |  | 2026 | 567000 |  |  | 567000
Johnston | NC 242 | NCDOT | Benson town limits to I-40. | Install rumble stripes with 6-inch pavement markings and snowplowable pavement markers. | 2.22 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404U | Region A | HSIP, T(M) |  |  |  |  | 2026 | 49000 |  |  | 49000
Johnston | NC 242 | NCDOT | North of SR 1116 (Godwin Lake Road) to North of SR 1116 (Godwin Lake Road). | Construct curve improvement. | 0.23 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004L | Region A | HSIP, T(M) | 2023 | 272000 |  |  | 2023 | 684000 |  |  | 956000 | UNDER CONSTRUCTION.
Johnston | NC 39 | NCDOT | US 301 north of Selma to Wake County line. | Install rumble stripes and pavement markings. | 18.5 | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | HS-2004AD | Region A | HSIP, T(M) |  |  |  |  | 2024 | 490000 |  |  | 490000
Johnston | SR 1007 (Brogden Road) | NCDOT | US 301 to Wayne County line. | Construct paved shoulders, resurface, and install rumble stripes and pavement markings. | 14.6 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404G | Division 4 | HSIP, T(M) |  |  |  |  | 2026 | 1350000 |  |  | 1350000
Johnston | SR 1010 (Cleveland Road) |  | NC 210 to the Wake County line. | Install 6-inch pavement markings and markers. | 13.7 | Highway | Safety | 4 | Capital Area MPO | HS-2404Q | Division 4 | HSIP, T(M) |  |  |  |  | 2026 | 86000 |  |  | 86000
Johnston | SR 1524 (Old Drug Store Road) | NCDOT | SR 1525 (Cornwallis Road) intersection. | Install signal and improve curve. | 0.5 | Highway | Safety | 4 | Capital Area MPO | W-5204E | Division 4 | HSIP, T(M) | 2023 | 200000 |  |  | 2024 | 998000 |  |  | 1198000 | RIGHT-OF-WAY IN PROGRESS.
Johnston | SR 1555 (Barber Mill Road) |  | SR 1010 (Cleveland Road) to SR 3908 (Veterans Parkway) | Install 6-inch pavement markings. | 5.7 | Highway | Safety | 4 | Capital Area MPO | HS-2404P | Division 4 | HSIP, T(M) |  |  |  |  | 2026 | 70000 |  |  | 70000
Johnston | SR 1700 (Covered Bridge Road) | NCDOT | West of SR 2685 (Helena Lane) to east of SR 1003 (Buffalo Road) | Construct safety improvement. | 1.41 | Highway | Safety | 4 | Capital Area MPO | W-5704E | Division 4 | HSIP, T, T(M) | 2023 | 1800000 |  |  | 2026 | 16100000 |  |  | 17900000 | RIGHT-OF-WAY IN PROGRESS
Johnston | SR 1902 (Glen Laurel Road) | NCDOT | SR 1903 (Vinson Road) intersection. | Install traffic signal. | 0.5 | Highway | Safety | 4 | Capital Area MPO | HS-2004S | Division 4 | HSIP, T(M) |  |  |  |  | 2023 | 350000 |  |  | 350000 | UNDER CONSTRUCTION.
Johnston | US 301 (Brightleaf Boulevard) | NCDOT | North Street intersection in Smithfield. | Install crosswalks, pedestrian improvements, and traffic signals. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004P | Region A | HSIP, T(M) |  |  |  |  | 2023 | 350000 |  |  | 350000 | UNDER CONSTRUCTION.
Johnston | US 301 / NC 96 (Brightleaf Boulevard) | NCDOT | SR 1921 (Hospital Road) intersection in Smithfield. | Update traffic signal and install pedestrian improvements. |  | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404J | Region A | HSIP, T(M) |  |  |  |  | 2026 | 45000 |  |  | 45000
Johnston | US 70 (Future I-42) | NCDOT | US 70 Alternate / SR 2532 (West Edwards Street) and SR 2314 (Pondfield Road) intersections in Princeton. | Construct reduced conflict intersection with westbound U-turn. | 0.38 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004W | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 800000 |  |  | 800000
Johnston | US 70 Business (Market Street) | NCDOT | Front Street to US 301 (Brightleaf Boulevard). | Install raised concrete median, crosswalks, and pedestrian signal heads, revise street parking, and widen lanes. | 0.6 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404V | Region A | HSIP, T(M) |  |  |  |  | 2026 | 1000000 |  |  | 1000000
Johnston | US 701 | NCDOT | SR 1143 (Stricklands Crossroads Road) intersection north of Newton Grove. | Install left turn lanes. |  | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404K | Region A | HSIP, T(M) |  |  | 2026 | 103000 | 2026 | 446000 |  |  | 549000
Johnston | I-40 | NCDOT | I-40 / NC 42 Interchange (Exit 312). | Improve access. | 1 | Highway | STI (Prioritization) | 4 | Capital Area MPO | I-4739 | Statewide Mobility | NHP | 2019 | 19305000 |  |  | 2018 | 40137000 |  |  | 59442000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033.
Johnston | I-40 | NCDOT | Wake County line to NC 42. | Add two general purpose lanes in each direction. | 1.55 | Highway | STI (Prioritization) | 4 | Capital Area MPO | I-5111REG | Region A | NHP | 2019 | 3479000 |  |  | 2018 | 23795000 |  |  | 27274000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
Johnston | I-95 | NCDOT | SR 1007 (Brogden Road) interchange. | Improve interchange. | 1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | I-6061 | Division 4 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26300000 |  |  | 30300000
Johnston | I-95 | NCDOT | US 70 Business interchange. | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | I-5972 | Region A | NHP |  |  |  |  | 2024 | 43182000 |  |  | 43182000 | RIGHT-OF-WAY IN PROGRESS
Johnston | I-95 | NCDOT | US 701 / NC 96 intersection in Four Oaks | Construct interchange. | 1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | I-5974 | Region A | NHFP, NHP | 2026 | 5300000 | 2026 | 1700000 | 2029 | 76000000 |  |  | 83000000 | PROJECT TO BE LET WITH B-6044 AND HB-0042.
Johnston | NC 210 | NCDOT | NC 50 to SR 1330 (Raleigh Road). | Construct reduced conflict intersections. | 2.06 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-6203 | Division 4 | T | 2027 | 12800000 | 2027 | 4000000 | 2030 | 71600000 |  |  | 88400000
Johnston | NC 242 | NCDOT | SR 1168 (Tarheel Road) to I-40. | Widen roadway. | 0.65 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5761 | Division 4 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 740000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20800000 |  |  | 23040000
Johnston | NC 42 | NCDOT | East of SR 1902 (Glen Laurel Road) to SR 1003 (Buffalo Road). | Widen to multi-lanes. | 4.35 | Highway | STI (Prioritization) | 4 | Capital Area MPO | R-3825B | Division 4 | T |  |  |  |  | 2019 | 68448000 |  |  | 68448000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Johnston | NC 42 | NCDOT | NC 50 to US 70 Business. | Widen to multi-lanes. | 8.64 | Highway | STI (Prioritization) | 4 | Capital Area MPO | R-3410 | Region A | BGANY, T | 2027 | 61895000 | 2027 | 10500000 | 2031 | 156900000 |  |  | 229295000 | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
Johnston | NC 42 | NCDOT | SR 1003 (Buffalo Road) to Wilson County line. | Modernize roadway. | 11.43 | Highway | STI (Prioritization) | 4 | Capital Area MPO, Upper Coastal Plain RPO | U-5998 | Division 4 | BGANY, T | 2025 | 3300000 | 2025 | 2100000 | 2027 | 29905000 |  |  | 35305000 | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
Johnston | NC 42 | NCDOT | US 70 to SR 1003 (Buffalo Road). | Widen to multi-lanes. | 6.1 | Highway | STI (Prioritization) | 4 | Capital Area MPO | R-3825
Johnston | New Route | NCDOT | SR 1010 (Cleveland Road) to NC 42. | Construct roadway on new location. | 1.46 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-6208 | Division 4 | T | 2030 | 19500000 | 2030 | 3900000 | 2034 | 33100000 |  |  | 56500000
Johnston | SR 1003 (Buffalo Road) | NCDOT | US 70 to SR 1934 (Old Beulah Road). | Widen to three lanes. | 1.27 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5718 | Division 4 | T | 2022 | 8537000 | 2022 | 1190000 | 2027 | 27195000 |  |  | 36922000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE).
Johnston | SR 1010 (Cleveland Road) | NCDOT | North of SR 2231 (Southfort Drive) to SR 1555 (Barber Mill Road). | Widen to multi-lanes. | 4.2 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-6216 | Division 4 | BGANY, T(M) | 2030 | 36600000 | 2030 | 6300000 | 2035 | 100900000 |  |  | 143800000
Johnston | SR 1501 (Swift Creek Road) | NCDOT | Airport Industrial Drive to just north of Johnston County Airport. | Widen roadway. | 0.29 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5950 | Division 4 | T | 2029 | 2000000 | 2029 | 1700000 | 2031 | 5600000 |  |  | 9300000
Johnston | US 301 / NC 39 / NC 96 | NCDOT | SR 1623 (Booker Dairy Road) to SR 2302 (Ricks Road). | Construct access management improvements. | 1.58 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-5726 | Division 4 | BG5T50, T(M) | 2026 | 13900000 | 2026 | 4300000 | 2029 | 29100000 |  |  | 47300000
Johnston | US 70 | NCDOT | West of SR 2372 (Edwards Road / North Pearl Street) to east of SR 2314 (Pondfield Road). | Upgrade roadway to freeway standards. | 2.22 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5829B | Not Funded | T | NOT FUNDED | 17600000 | NOT FUNDED | 14600000 | NOT FUNDED | 100100000 | NOT FUNDED |  | 132300000
Johnston | US 70 (Future I-42) | NCDOT | US 301 to I-95. | Construct access management improvements. | 0.69 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5795 | Region A | T | 2030 | 2800000 | 2030 | 7200000 | 2033 | 13400000 |  |  | 23400000
Johnston | US 70 (Future I-42) | NCDOT | US 70 Business to Neuse River Bridge. | Construct freeway with interchanges at SR 1501 (Swift Creek Road) and SR 1919 (Wilson's Mills Road). | 5.63 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | W-5600 | Region A | NHP, T(M) |  |  |  |  | 2021 | 87693000 |  |  | 87693000 | UNDER CONSTRUCTION.
Johnston | Various | NCDOT | Routes in Clayton, north of North Carolina Railroad. | Upgrade signal system. Includes rail encroachments. |  | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-5943B | Region A | BG50200, T(M) |  |  |  |  | 2026 | 890000 |  |  | 890000
Johnston | Various | NCDOT | Routes in Clayton, south of North Carolina Railroad. | Upgrade signal system. |  | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-5943A | Region A | BG50200 |  |  |  |  | 2025 | 4140000 |  |  | 4140000
Johnston | Various | NCDOT | Routes in Clayton. | Upgrade signal system. | 6.2 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-5943 | Region A | BG50200, T(M) |  |  | 2025 | 260000 |  |  |  |  | 260000 | RIGHT-OF-WAY IN PROGRESS.
Johnston | I-95 | NCDOT | Bridges 500114 and 500116 over Little River. | Replace bridges and approaches. |  | Highway | Transition | 4 | Upper Coastal Plain RPO | I-3318BB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
Johnston | Johnston County | JOHNSTON COUNTY (JCATS) | Systemwide | Purchase electric transit vehicles. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 4 | Upper Coastal Plain RPO | TN-6132 | Exempt | CRPANY, L(M) | [6 empty] | 2025 | 510000 | 510000
Johnston | Johnston County | JOHNSTON COUNTY | Systemwide | Purchase expansion vehicle. |  | Public Transportation (Transit) | STI (Prioritization) | 4 | Upper Coastal Plain RPO, Capital Area MPO | TA-6720 | Division 4 | 5311, L, T |  |  |  |  | 2026 | 330000 |  |  | 330000
Johnston | SR 2383 (Preston Street) | NCDOT | CSX Crossing 629 950L | Close SR 2383 (Preston Street) Crossing in Selma |  | Rail | Rail-Highway Grade Crossing Closure | 4 | Upper Coastal Plain RPO | RC-2004B | Division 4 | RR | 2026 | 50000 | 2026 | 20000 | 2026 | 500000 |  |  | 570000
Johnston | Lee Street | NCDOT | CSX Crossing 629964U in Smithfield. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004K | Division 4 | RR |  |  |  |  | 2026 | 388000 |  |  | 388000
Johnston | Parrish Drive | NCDOT | CSX Crossing 629739C in Benson. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004D | Division 4 | RR |  |  |  |  | 2026 | 500000 |  |  | 500000
Johnston | SR 1709 (Stallings Street) | NCDOT | Norfolk Southern Crossing 735396M in Clayton. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Capital Area MPO | RX-2004H | Division 4 | RR |  |  |  |  | 2025 | 474000 |  |  | 474000
Johnston | SR 2130 (Main Street) | NCDOT | CSX Crossing 629943B in Micro. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004G | Division 4 | RR |  |  |  |  | 2026 | 417000 |  |  | 417000
Johnston | SR 2339 (Bagley Road) | NCDOT | CSX Crossing 629939L in Kenly. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004J | Division 4 | RR |  |  |  |  | 2026 | 450000 |  |  | 450000
Johnston | SR 2500 (Wallpat Road) | NCDOT | CSX Crossing 629966H in Smithfield. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004L | Division 4 | RR |  |  |  |  | 2027 | 388000 |  |  | 388000
Johnston, Edgecombe, Nash | Various | NCDOT | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Highway | Other | 4 | Upper Coastal Plain RPO | C-5619 | Exempt | CMAQ, L(M) | 2020 | 420000 |  |  | 2020 | 2495000 | 2020 | 1260000 | 4175000
Johnston, Nash, Wayne, Wilson, Edgecombe, Halifax | Various | NCDOT | Ramps in Division 4 | Install wrong way pavement markings and signs. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2004Y | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 1550000 |  |  | 1550000 | UNDER CONSTRUCTION.
Johnston, Wake | Various | GO RALEIGH | Various locations | Construct infrastructure, purchase vehicles and establish service for bus rapid transit from Garner to Clayton | 15.03 | Public Transportation (Transit) | STI (Prioritization) | 4, 5 | Capital Area MPO | TO-6166D | Region A, C | T | 2028 | 2000000 | 2028 | 1000000 | 2030 | 17000000 |  |  | 20000000
Johnston, Wilson | Various | NCDOT | Routes in Division 4. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | W-5204DIV | Division 4
Johnston, Wilson | Various | NCDOT | Routes in Division 4. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | W-5204REG | Region A
Jones | US 17 Business (Main Street) |  | NC 58 to SR 1366 (East Street) in Pollocksville | Construct pedestrian improvements. | 0.83 | Bike & Ped | NCDOT Selected (Other Selection Process) | 2 | Down East RPO | BN-0005 | Exempt | CRPLT5, L(M) |  |  |  |  | 2025 | 455000 | 2024 | 75000 | 530000
Jones | US 70 (Future I-42) | NCDOT | SR 1002 (Wyse Fork Road) / SR 1309 (Caswell Station Road) intersection. | Construct reduced conflict intersection. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AG | Region B | HSIP, T(M) |  |  | 2024 | 30000 | 2024 | 964000 |  |  | 994000
Jones | US 17 | NCDOT | North of Maysville to south of NC 58. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 5.66 | Highway | Transition | 2 | Down East RPO | R-2514C | Pre-STI (Transition) | [10 empty] | COMPLETE.
Jones | US 17 | NCDOT | South of NC 58 to the New Bern Bypass. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 5.8 | Highway | Transition | 2 | Down East RPO | R-2514D | Pre-STI (Transition) | [10 empty] | COMPLETE.
Jones, Lenoir, Carteret | NC 58 | NCDOT | North of Camp Peletier Road in Carteret County Maysville in Jones County; East of SR 1338 (Goshen Lane) to Trenton in Jones County; East of SR 1124 (Greentown Road) in Jones County to SR 1900 (Collier Loftin Road) in Lenoir County | Install rumble stripes. |  | Highway | Safety | 2 | Down East RPO | HS-2402S | Region B | HSIP |  |  |  |  | 2025 | 1115000 |  |  | 1115000
Jones, Onslow | US 17 | NCDOT | North of Jacksonville to New Bern Bypass. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 22.1 | Highway | Pre-STI (Historic) | 2, 3 | Down East RPO, Jacksonville Urban Area MPO | R-2514
Lee | TTA | RALEIGH EXECUTIVE JETPORT (TTA) | Raleigh Executive Sanford - Lee County Airport | Construct airplane run-up lane at each end of runway 21 and runway 3 bypass taxiway. |  | Aviation | STI (Prioritization) | 8 | Central Pines RPO | AV-5899 | Division 8 | T |  |  |  |  | 2024 | 4199000 |  |  | 4199000
Lee | TTA | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | Raleigh Executive Sanford - Lee County Airport | Construct corporate area apron phase I. |  | Aviation | STI (Prioritization) | 8 | Central Pines RPO | AV-5762 | Division 8 | [10 empty] | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING
Lee | NC 42 (Wicker Street) | SANFORD | SR 1190 (Legion Drive) to north of High Ridge Drive at Kiwanis Family Park in Sanford | Construct multi-use path. | 0.42 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5742 | Division 8 | L(M), TA5T50 |  |  |  |  | 2027 | 1010000 | 2022 | 77000 | 1087000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS
Lee | SR 1002 (Charlotte Avenue) | SANFORD | Chatham Street to SR 1002 (11th Street) in Sanford | Construct sidewalks and implement road diet with bicycle lanes. | 0.95 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-6002 | Division 8 | L(M), TA5T50 |  |  |  |  | 2026 | 1400000 | 2023 | 191000 | 1591000
Lee | SR 1107 (Fields Drive) | SANFORD | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5867 | Division 8 | L(M), TA5T50 | 2026 | 620000 | 2026 | 600000 | 2027 | 1015000 | 2024 | 149000 | 2384000
Lee | US 1 Business (Carthage Street) | SANFORD | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5863 | Division 8 | L(M), TA5T50 | 2026 | 150000 |  |  | 2027 | 1469000 | 2021 | 295000 | 1914000
Lee | Woodland Street | SANFORD | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5868 | Division 8 | L(M), TA5T50 | 2026 | 111000 | 2026 | 100000 | 2027 | 1105000 | 2023 | 116000 | 1432000
Lee | SR 1400 (Cumnock Road) | NCDOT | Bridges 520069 and 520070 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Highway | Bridges | 8 | Central Pines RPO | B-5976 | Division 8 | BGOFF | 2026 | 210000 | 2026 | 510000 | 2029 | 11500000 |  |  | 12220000
Lee | US 421 | NCDOT | SR 1531 (Swanns Station Road) intersection | Install traffic signal and turn lanes. | 0.5 | Highway | Safety | 8 | Central Pines RPO | HS-2408C | Region E | HSIP |  |  | 2026 | 15000 | 2027 | 550000 |  |  | 565000
Lee | NC 42 | NCDOT | Various | Mitigate railroad. |  | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-3830A | Division 8 | T |  |  |  |  | 2021 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION
Lee | NC 42; SR 1579 (Bradfway Road / North Main Street) | NCDOT | NC 42, US 421 (Future I-685 / Horner Boulevard) in Sanford to SR 1579 (Broadway Road) and SR 1579 (Broadway Road / North Main Street), NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue) in Broadway. | Widen to a four lane divided facility from US 421 (Future I-685) to NC 42 (Avents Ferry Road) and widen to three lanes from NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue). | 5.57 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-3830 | Division 8 | T | 2019 | 10228000 |  |  | 2023 | 92194000 |  |  | 102422000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE)
Lee | SR 1237 (Carthage Street) | NCDOT | SR 1152 (Fire Tower Road) to NC 42 (Wicker Street) in Sanford. | Widen roadway to a two lane divided facility with bike-ped accommodations. | 0.85 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5709 | Division 8 | T | 2022 | 3427000 | 2022 | 1700000 | 2027 | 23395000 |  |  | 28522000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE).
Lee | SR 1521 (Kelly Drive) | NCDOT | SR 1519 (Nash Street) to Northeast of Central Carolina Community College. | Construct 3-lane realignment of Kelly Drive. | 0.5 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5959 | Division 8 | T | 2025 | 1900000 | 2025 | 660000 | 2027 | 7900000 |  |  | 10460000 | RIGHT-OF-WAY IN PROGRESS
Lee | US 1 / US 15 / US 501 | NCDOT | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Clearing, grubbing, and erosion control. | 2.17 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5975A | Region E | T |  |  |  |  | 2026 | 2500000 |  |  | 2500000
Lee | US 1 / US 15 / US 501 | NCDOT | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Construct reduced conflict intersections. | 2.17 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5975 | Region E | T | 2023 | 4100000 | 2023 | 3300000 | 2027 | 42000000 |  |  | 49400000 | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE);
Lee | US 1 / US 15 / US 501 | NCDOT | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Clearing, grubbing, and erosion control. | 0.8 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5727A | Region E | T |  |  |  |  | 2026 | 2000000 |  |  | 2000000
Lee | US 1 / US 15 / US 501 | NCDOT | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Construct reduced conflict intersection and relocate NC 78 (Tramway Road). | 0.8 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5727 | Region E | NHP, T | 2023 | 12300000 | 2023 | 1500000 | 2027 | 31300000 |  |  | 45100000 | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE);
Lee | US 421 Business / NC 87 | NCDOT | US 1 / US 15 / US 501 to former Atlantic Coast Line Railroad crossing east of Washington Avenue in Sanford. | Reconstruct as a "complete street" with improvements such as medians, sidewalks, bicycle facilities, and streetscaping. | 3.4 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5722 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19500000 |  |  | 56900000
Lee | US 1 Business (Carthage Street / Charlotte Avenue) | NCDOT | Crossing 721059F in Sanford | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Central Pines RPO | RX-2008E | Division 8 | RR |  |  |  |  | 2026 | 450000 |  |  | 450000
Lenoir | Kinston Riverwalk | KINSTON | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Bike & Ped | NCDOT Selected (Other Selection Process) | 2 | Eastern Carolina RPO | BN-0008 | Exempt | CRP550, L(M) | 2026 | 214000 |  |  | 2026 | 3040000 | 2024 | 305000 | 3559000 | KINSTON RIVERWALK PHASE 2
Lenoir | Kinston | NCDOT | Various locations in Kinston | Funding for multi-modal planning. |  | Bike & Ped | Other | 2 | Eastern Carolina RPO | M-0570M | Exempt | CRPANY, HF(M), L | [6 empty] | 2025 | 68000 | 68000
Lenoir | NC 903 | NCDOT | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Eastern Carolina RPO | B-4566 | Region B | BFP, T(M) | 2027 | 262000 | 2027 | 129000 | 2030 | 6500000 |  |  | 6891000
Lenoir | SR 1389 (Hardy Bridge Road) | NCDOT | Bridge 530052 over Neuse River and bridge 530152 over Neuse River Overflow. | Replace bridges. | 0.25 | Highway | Bridges | 2 | Eastern Carolina RPO | B-5619 | Division 2 | BGOFF | 2020 | 500000 |  |  | 2021 | 9170000 |  |  | 9670000 | UNDER CONSTRUCTION.
Lenoir | NC 11 | NCDOT | South of SR 1143 (Liddell Road) to north of SR 1144 (Tulls Mill Road / South Lenoir Drive). | Install two reduced conflict intersections. | 0.7 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2402AA | Region B | HSIP |  |  |  |  | 2026 | 1400000 |  |  | 1400000
Lenoir | NC 11 | NCDOT | SR 1716 (Harvey Rouse Road), NC 118 / SR 1091 (Grifton-Hugo Road), and SR 1714 (Creek Road) intersections. | Construct reduced conflict intersection. | 0.68 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002K | Region B | HSIP, T(M) |  |  | 2023 | 80000 | 2023 | 1236000 |  |  | 1316000 | UNDER CONSTRUCTION.
Lenoir | SR 1395 (West Vernon Avenue) | NCDOT | Greenbriar Road Intersection in Kinston | Install / upgrade pedestrian signals and other pedestrian accommodations. |  | Highway | Safety | 2 | Eastern Carolina RPO | HS-2402J | Division 2 | HSIP, T(M) | 2025 | 8000 |  |  | 2026 | 113000 |  |  | 121000 | RIGHT-OF-WAY IN PROGRESS
Lenoir | US 258 | NCDOT | SR 1120 (Nobles Mill Road) and SR 1908 (Bill Stroud Road) intersections. | Construct turn lanes. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002P | Region B | HSIP, T(M) |  |  | 2024 | 150000 | 2024 | 661000 |  |  | 811000 | UTILITY RELOCATION IN PROGRESS.
Lenoir | US 258 | NCDOT | SR 1342 (Will Baker Road / Central Avenue) intersection. | Upgrade traffic signal and install flasher. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002N | Region B | HSIP, T(M) |  |  |  |  | 2023 | 86000 |  |  | 86000 | UNDER CONSTRUCTION.
Lenoir | US 70 (Future I-42) | NCDOT | SR 1324 (Kennedy Home Road) / SR 1519 (Eason Road) intersection and adjacent crossover to the west. | Construct restricted crossing intersections. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002C | Statewide Mobility | HSIP, T(M) |  |  | 2022 | 20000 | 2022 | 250000 |  |  | 270000 | UNDER CONSTRUCTION.
Lenoir | US 70 (Future I-42) / US 258 (West Vernon Avenue) | NCDOT | East of US 258 in Kinston. | Remove eastbound left-over. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002AE | Region B | HSIP, T(M) |  |  |  |  | 2024 | 204000 |  |  | 204000
Lenoir | NC 148 (CF Harvey Parkway) | NCDOT | NC 58 to NC 11. | Construct multi-lane facility on new location. | 4.07 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5703 | Region B | T |  |  |  |  | 2018 | 74609000 |  |  | 74609000 | COMPLETE. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
Lenoir | SR 1569 (Carey Road Extension) | NCDOT | SR 1572 (Rouse Road) to US 258. | Construct multi-lanes on new location. | 1.81 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | U-3618 | Division 2 | BG5T50 | 2028 | 3200000 | 2028 | 2900000 | 2031 | 50300000 |  |  | 56400000
Lenoir | US 70 | NCDOT | SR 1227 (Jim Sutton Road) / SR 1252 (Willie Measley Road) intersection near La Grange | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5813 | Not Funded | NHP, T(M) | NOT FUNDED | 13200000 | NOT FUNDED | 7000000 | NOT FUNDED | 69900000 | NOT FUNDED |  | 90100000 | NOT FUNDED
Lenoir | US 70 (Future I-42) | NCDOT | Existing freeway near Lagrange to existing freeway near Dover. | Upgrade roadway to freeway, partially on new location. | 18.7 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-2553 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
Lenoir | Lincoln Street | NCDOT | Norfolk Southern Crossing 722766G in Kinston. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Eastern Carolina RPO | RX-2002D | Division 2 | RR |  |  |  |  | 2025 | 411000 |  |  | 411000
Lenoir, Greene | US 258 | NCDOT | SR 1101 (Browntown Road) to SR 2010 (C.F. Harvey parkway). | Widen to multi-lanes. | 4.79 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5814 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 67700000 |  |  | 87900000
Lenoir, Onslow, Jones | US 258 | NCDOT | NC 24 to US 70 in Kinston. | Install rumble stripes. | 25.07 | Highway | Safety | 2, 3 | Eastern Carolina RPO, Jacksonville Urban Area MPO, Down East RPO | HS-2002Q | Region B | HSIP, T(M) |  |  |  |  | 2025 | 585000 |  |  | 585000
Lenoir, Wayne | NC 55 | NCDOT | West of NC 903 to NC 11. | Install rumble stripes. | 11.76 | Highway | Safety | 2, 4 | Eastern Carolina RPO | HS-2002AD | Region A, B | HSIP, T(M) |  |  |  |  | 2025 | 380000 |  |  | 380000 | UNDER CONSTRUCTION.
Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | Various |  | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Bike & Ped | Other | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | BO-2419 | Division 2, 4, 5, 6, 8, 9 | DP, HF, HSIP | 2025 | 122000 | 2025 | 122000 | 2025 | 10647000 | 2024 | 1409000 | 12300000 | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS.
Lincoln | IPJ | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | Lincolnton-Lincoln County Airport | Acquire land for Runway 5 approach. |  | Aviation | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | AV-5755 | Division 12 | T | 2024 | 176000 | [6 empty] | 176000
Lincoln | IPJ | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | Lincolnton-Lincoln County Airport | Remove obstructions on Runway 5 approach. |  | Aviation | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | AV-5753 | Division 12 | T | 2024 | 295000 | [6 empty] | 295000
Lincoln | NC 27 | LINCOLNTON | Locations along NC 27 in Lincolnton | Construct sidewalks in gaps. | 0.09 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606I | Exempt | CMAQ, HF, L(M) |  |  |  |  | 2025 | 700000 |  |  | 700000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000.
Lincoln | SR 1003 (Buffalo Shoals Road) | NCDOT | SR 1343 (Ivey Church Road). | Construct safety improvements. | 0.5 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5712R | Division 12 | HSIP, T(M) | 2024 | 42000 | 2024 | 4000 | 2025 | 610000 |  |  | 656000
Lincoln | SR 1360 (Beth Haven Church Road) | NCDOT | SR 1373 (Wingate Hill Road / Forney Hill Road) intersection near Denver. | Install all-way stop, upgrade signs and pavement markings, and improve shoulders. | 0.5 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012F | Division 12 | HSIP, T(M) |  |  |  |  | 2023 | 24000 |  |  | 24000 | UNDER CONSTRUCTION.
Lincoln | NC 16 Business | NCDOT | SR 1373 (Campground Road) and SR 1386 (Will Proctor Road) intersections. | Realign intersections. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5962 | Region F | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16799000 |  |  | 35499000 | OTHER FUNDING PROVIDED BY LINCOLN COUNTY
Lincoln | NC 16 Business | NCDOT | SR 1439 (Unity Church Road) / SR 1387 (Triangle Circle) intersection near Denver. | Construct turn lanes. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-5712 | Region F | T |  |  | 2025 | 1200000 | 2025 | 4500000 |  |  | 5700000 | UNDER CONSTRUCTION.
Lincoln | NC 16 Bypass | NCDOT | SR 1380 (Optimist Club Road) intersection near Denver. | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6134 | Region F | BGLT5, T(M) | 2024 | 500000 | 2024 | 100000 | 2031 | 46800000 |  |  | 47400000
Lincoln | Lincoln County Transit | LINCOLN COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Eastern Carolina RPO | TK-6141 | Public Transit | 5311, L, S | [6 empty] | 2020 | 876000 | 876000 | FUNDS AUTHORIZED IN PROGRESS
Lincoln, Cleveland, Gaston | Various | NCDOT | Secondary routes in Division 12. | Install long life pavement markings. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012E | Division 12 | HSIP, T(M) |  |  |  |  | 2023 | 2675000 |  |  | 2675000 | UNDER CONSTRUCTION.
Lincoln, Mecklenburg | NC 73 | NCDOT | NC 16 to Vance Road Extension / Beatties Ford Road in Huntersville. | Widen to multi-lanes. | 5.57 | Highway | STI (Prioritization) | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO | R-5721A | Region E, F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 69900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 189600000 |  |  | 268800000
Macon | 1A5 | MACON COUNTY AIRPORT | Macon County Airport | Extend runway. |  | Aviation | STI (Prioritization) | 14 | Southwestern RPO | AV-5850 | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 430000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13400000 |  |  | 13830000
Macon | SR 1729 (Depot Street) | NCDOT | US 441 Business (East Main Street) to SR 1667 (Wayah Street) in Franklin | Construct missing sections of sidewalk along west side and construct new sidewalk on east side. | 0.63 | Bike & Ped | STI (Prioritization) | 14 | Southwestern RPO | EB-5756 | Division 14 | L(M), TAANY |  |  |  |  | 2023 | 326000 | 2022 | 18000 | 344000 | UNDER CONSTRUCTION.
Macon | Various | NCDOT | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Bike & Ped | STI (Prioritization) | 14 | Southwestern RPO | EB-5964 | Division 14 | L(M), TA5T50 | 2026 | 25000 | 2026 | 60000 | 2027 | 1600000 | 2024 | 225000 | 1910000
Macon | US 441 | NCDOT | SR 1515 (Hyatt Road) intersection. | Construct intersection improvements and right-in / right-out at Ingles Development site. | 0.5 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | HA-0004 | Exempt | ADHSL |  |  |  |  | 2022 | 1900000 |  |  | 1900000 | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION.
Macon | SR 1001 (Ellijay Road) | NCDOT | Bridge 550009 over North Prong Ellijay Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6029 | Division 14 | BGOFF |  |  |  |  | 2026 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION.
Macon | SR 1114 (Shope Road) | NCDOT | Bridge 550244 over North Fork Coweeta Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6025 | Division 14 | BGOFF |  |  |  |  | 2024 | 1700000 |  |  | 1700000 | UNDER CONSTRUCTION.
Macon | SR 1351 (Matlock Creek Road) | NCDOT | Bridge 550220 over Matlock Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6030 | Division 14 | BGOFF |  |  |  |  | 2029 | 1301000 |  |  | 1301000 | RIGHT-OF-WAY IN PROGRESS
Macon | SR 1500 (Watauga Road) | NCDOT | Bridge 550214 over Watauga Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6026 | Division 14 | BGOFF | 2024 | 50000 |  |  | 2028 | 500000 |  |  | 550000
Macon | SR 1528 (Little Ellijay Road) | NCDOT | Bridge 550150 over Ellijay Creek. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6028 | Division 14 | BGOFF |  |  |  |  | 2022 | 2600000 |  |  | 2600000 | UNDER CONSTRUCTION.
Macon | SR 1679 (Gold Mine Road) | NCDOT | Bridge 550056 over Cullasaja River. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | HB-0037 | Division 14 | BGOFF | 2026 | 50000 | 2026 | 50000 | 2027 | 1000000 |  |  | 1100000
Macon | SR 1679 (Peeks Creek Road) | NCDOT | Bridge 550055 over Cullasaja River. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | HB-0030 | Division 14 | BGOFF | 2025 | 480000 | 2025 | 360000 | 2026 | 3200000 |  |  | 4040000 | RIGHT-OF-WAY IN PROGRESS.
Macon | US 64 | NCDOT | Dry Falls Recreation Area. | Improve parking area, construct pedestrian bridge, and construct observation platform. | 0.2 | Highway | Federal Lands Access Program | 14 | Southwestern RPO | HF-0006 | Exempt | FLAP | [6 empty] | 2023 | 500000 | 500000 | FLAP PROJECT NC 64. AWARDED $1.0M.
Macon | SR 1372 (Lower Burningtown Road) | NCDOT | SR 1474 (Saldeer Mountain Road) to SR 1392 (Middle Burningtown Road) near Franklin | Install guardrail. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414E | Division 14 | HSIP, T(M) |  |  |  |  | 2025 | 375000 |  |  | 375000
Macon | SR 1668 (Fulton Road) | NCDOT | US 64 to SR 1667 (Wells Grove Road) near Franklin | Install guardrail. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414D | Division 14 | HSIP, T(M) |  |  |  |  | 2025 | 190000 |  |  | 190000
Macon | US 19 | NCDOT | Cherokee County line to Swain County line. | Install rumble stripes and long life pavement markings. | 2.61 | Highway | Safety | 14 | Southwestern RPO | HS-2014U | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 176000 |  |  | 176000
Macon | US 19; US 23; US 64 | NCDOT | Various locations. | Upgrade guardrail end units. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414K | Region G | HSIP, T(M) |  |  |  |  | 2025 | 850000 |  |  | 850000
Macon | US 64 (Murphy Road) | NCDOT | SR 1146 (Patton Road) and SR 1442 (Old Murphy Road) intersections near Franklin. | Construct directional leftover with U-turn bulb-outs. |  | Highway | Safety | 14 | Southwestern RPO | HS-2014W | Region G | HSIP, T(M) |  |  |  |  | 2026 | 1455000 |  |  | 1455000
Macon | US 64 / NC 28 | NCDOT | SR 1560 (Rogers Road) to SR 1533 (Walnut Creek Road) near Franklin. | Install centerline rumble stripes, long life pavement markings, and intermittent paved shoulders. | 5.76 | Highway | Safety | 14 | Southwestern RPO | HS-2014A | Region G | HSIP, T(M) |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION.
Macon | US 23 / US 441 | NCDOT | SR 1649 (Prentiss Bridge Road) to Georgia state line. | Implement access management strategies. | 9 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734C | Not Funded | T | NOT FUNDED | 5000000 | NOT FUNDED | 600000 | NOT FUNDED | 53600000 | NOT FUNDED |  | 59200000
Macon | US 23 / US 441 | NCDOT | SR 1652 (Wide Horizon Drive) / SR 1152 (Belden Circle) to SR 1649 (Prentiss Bridge Road). | Implement access management strategies. | 2.42 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734B | Not Funded | T | NOT FUNDED | 13800000 | NOT FUNDED | 3200000 | NOT FUNDED | 26600000 | NOT FUNDED |  | 43600000
Macon | US 23 / US 441 | NCDOT | US 64 to SR 1649 (Prentiss Bridge Road). | Implement access management strategies. | 3.2 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734 | [11 empty] | SEGMENT A INCLUDES THE REPLACEMENT OF BRIDGE 314 FORMERLY SCHEDULED TO BE REPLACED UNDER 17BP.14.R.154
Macon | US 23 / US 441 | NCDOT | US 64 to SR 1652 (Wide Horizon Drive) / SR 1152 (Belden Circle). | Implement access management strategies. | 0.82 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734A | Division 14 | T |  |  |  |  | 2021 | 12600000 | 2021 | 2310000 | 14910000 | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $7.066 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
Macon | Various | NCDOT | US 23 / US 64 / US 441 and Womack Street intersection in Franklin; US 23 / US 64 / US 441 and Maple Street intersection in Franklin; US 23 / US 64 / US 441 and Porter Street intersection in Franklin; US 441 / Main Street and Depot Street intersection in F | Construct intersection improvements. | 1.4 | Highway | STI (Prioritization) | 14 | Southwestern RPO | U-5604 | Region G | T |  |  |  |  | 2020 | 7080000 | 2021 | 1830000 | 8910000 | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE).
Macon | Integrated Mobility Division |  | Various | Funding for Macon County Areas of Persistent Poverty (AoPP) Grant. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TM-0049 | Public Transit | DP, L | [6 empty] | 2024 | 525000 | 525000
Macon | Macon County Transit | MACON COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6142 | Public Transit | 5311, L, S | [6 empty] | 2020 | 764000 | 764000 | FUNDS AUTHORIZED IN PROGRESS
Macon, Cherokee, Jackson | Various | NCDOT | Primary and secondary routes in Division 14. | Install long life pavement markings. |  | Highway | Safety | 14 | Southwestern RPO | HS-2014P | Region G | HSIP, T(M) |  |  |  |  | 2024 | 2955000 |  |  | 2955000 | UNDER CONSTRUCTION.
Madison | I-26 (US 19/US 23) | NCDOT | North of NC 213 to north of US 19. | Widen to multi-lane freeway and construct new route. | 1.762 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO | A-0010BB | [11 empty] | COMPLETE
Madison | I-26 (US 19/US 23) | NCDOT | North of US 19 to SR 1318 (Big Laurel Road) at Laurel Creek. | Widen to multi-lane freeway and construct new route. | 6.08 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO | A-0010C | [11 empty] | COMPLETE
Madison | I-26 (US 19/US 23) | NCDOT | SR 1318 (Big Laurel Road) at Laurel Creek to the Tennessee state line at Sams Gap. | Widen to multi-lane freeway and construct new route. | 2.98 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO | A-0010D | [11 empty] | COMPLETE
Madison | NC 208 | NCDOT | Bridge 560033 over Shelton Laurel Creek | Replace bridge. |  | Highway | Bridges | 13 | Foothills RPO | BR-0145 | Region G | BFP |  |  |  |  | 2027 | 2200000 |  |  | 2200000
Madison | SR 1341 (Foster Creek Road) | NCDOT | Bridge 560073 over Foster Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-6012 | Division 13 | T |  |  |  |  | 2019 | 4828000 |  |  | 4828000 | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
Madison | SR 1395 (Walnut Creek Road) | NCDOT | Bridge 560071 over Big Laurel Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Land-of-Sky RPO | B-5989 | Division 13 | BGOFF | 2022 | 13000 | 2023 | 130000 | 2023 | 7406000 |  |  | 7549000 | UNDER CONSTRUCTION.
Madison | SR 1503 (Laurel Valley) | NCDOT | Bridge 560246 over Laurel Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | French Broad River MPO, Land-of-Sky RPO | B-4182 | Division 13 | [10 empty] | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105)
Madison | I-26 | NCDOT | Tennessee state line to mile marker 9.0. | Rehabilitate bridges 560540, 560541, 560547, 560548, 560549. 560550, and 560551 and replace curb and drainage boxes. | 9.04 | Highway | Interstate Maintenance | 13 | Land-of-Sky RPO | I-5831A | Statewide Mobility | BGLT5, T(M) |  |  |  |  | 2022 | 10054000 |  |  | 10054000 | UNDER CONSTRUCTION.
Madison | I-26 | NCDOT | Tennessee state line to mile marker 9.0. | Rehabilitate pavement and bridges 560540, 560541, 560547, 560548, 560549. 560550, and 560551. | 9 | Highway | Interstate Maintenance | 13 | Land-of-Sky RPO | I-5831
Madison | I-26 | NCDOT | Tennessee state line to mile marker 9.0. | Rehabilitate pavement. | 9.04 | Highway | Interstate Maintenance | 13 | Land-of-Sky RPO | I-5831B | Statewide Mobility | BGLT5, T(M) |  |  |  |  | 2026 | 29490000 |  |  | 29490000
Madison | SR 1318 (Big Laurel Road) | NCDOT | SR 1340 (Pine Branch Road) to US 23 near Mars Hill. | Install guardrail. | 8.59 | Highway | Safety | 13 | Land-of-Sky RPO | HS-2013I | Division 13 | HSIP |  |  |  |  | 2024 | 520000 |  |  | 520000
Madison | SR 1631 (Crossroads Parkway) | NCDOT | SR 1631 (Crossroads Parkway) end point to SR 1632. | Extend roadway. | 0.31 | Highway | STI (Prioritization) | 13 | French Broad River MPO | R-5779 | Division 13 | ADHSL, O, T |  |  |  |  | 2021 | 4071000 |  |  | 4071000 | COMPLETE. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170)
Madison | Madison County Transportation | MADISON COUNTY TRANSPORTATION | Systemwide | Purchase two transit vehicles. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | Land-of-Sky RPO | TN-6130 | Exempt | CRPLT5, L(M) | [6 empty] | 2025 | 246000 | 246000
Madison | US 25 / US 70 | MADISON COUNTY TRANSPORTATION | US 25 / US 70 | Construct park and ride at US 25 Business / US 70 Business intersection. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | Land-of-Sky RPO | TN-6128 | Exempt | CRPLT5, T(M) |  |  |  |  | 2026 | 376000 | 2025 | 28000 | 404000
Madison | Madison County Transportation | MADISON COUNTY TRANSPORTATION | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 13 | Land-of-Sky RPO | TK-6143 | Public Transit | 5311, L, S | [6 empty] | 2020 | 548000 | 548000 | FUNDS AUTHORIZED IN PROGRESS
Martin | MCZ | MARTIN COUNTY AIRPORT (MCZ) | Martin County Airport | Construct taxi lanes and apron. |  | Aviation | STI (Prioritization) | 1 | Mid-East RPO | AV-5788 | Division 1 | T |  |  |  |  | 2023 | 1250000 |  |  | 1250000 | UNDER CONSTRUCTION.
Martin | US 17 BUS (East Main Street) | WILLIAMSTON | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Bike & Ped | STI (Prioritization) | 1 | Mid-East RPO | EB-5979 | Division 1 | L, L(M), TAANY, TAP | 2026 | 20000 | 2026 | 20000 | 2027 | 280000 | 2026 | 10000 | 330000
Martin | US 13/US 64 (Future I-87) | NCDOT | Edgecombe County line to US 13 / 17 and US 64 interchange. | Rehabilitate pavement. | 18.56 | Highway | Interstate Maintenance | 1 | Mid-East RPO | I-6028 | Statewide Mobility | [10 empty] | "A" BREAK DELETED, WORK WAS COMPLETED WITH CONTRACT RESURFACING.
Martin | US 64 (Future I-87) | NCDOT | NC 125 to US 13 / 17 and US 64 interchange. | Rehabilitate pavement. | 4.11 | Highway | Interstate Maintenance | 1 | Mid-East RPO | I-6028C | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 6000000 |  |  | 6000000 | UNDER CONSTRUCTION.
Martin | US 64 (Future I-87) | NCDOT | US 64 Alternate to NC 125 | Rehabilitate pavement. | 4.7 | Highway | Interstate Maintenance | 1 | Mid-East RPO | I-6028B | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 6073000 |  |  | 6073000 | COMPLETE.
Martin | Williamston | NCDOT | Publix | Install 6 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 1 | Mid-East RPO | HV-0001I | Division 1 | NEVI, O(M), S(M) |  |  |  |  | 2025 | 871000 |  |  | 871000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE
Martin | US 17 Business | NCDOT | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Highway | Safety | 1 | Mid-East RPO | HS-2401H | Region A | HSIP, T(M) | 2027 | 100000 | 2027 | 30000 | 2027 | 1050000 |  |  | 1180000
Martin | SR 1142 (Prison Camp Road) | NCDOT | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Highway | STI (Prioritization) | 1 | Mid-East RPO | R-4705 | Division 1 | BGANY, T(M) | 2022 | 200000 | 2023 | 2100000 | 2022 | 48147000 |  |  | 50447000 | UNDER CONSTRUCTION.
Martin | US 13 / US 17 (Future I-87) | NCDOT | Main Street intersection in Williamston | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 1 | Mid-East RPO | R-5879 | Region A | NHP, T(M) | 2028 | 140000 | 2028 | 970000 | 2031 | 5000000 |  |  | 6110000
Martin | US 17 | NCDOT | SR 1119 (Ralph Taylor Road) to SR 1205 (Holly Creek Road). | Manage Access. | 2.01 | Highway | STI (Prioritization) | 1 | Mid-East RPO | R-5810 | Division 1 | NHP, T | 2025 | 250000 | 2025 | 80000 | 2027 | 13100000 |  |  | 13430000 | RIGHT-OF-WAY IN PROGRESS
Martin, Beaufort | US 17 | NCDOT | Washington Bypass north of NC 171 to multi-lanes south of Williamston. | Widen to four lanes. | 10.01 | Highway | STI (Prioritization) | 1, 2 | Mid-East RPO | R-2511 | Division 1, 2 | T | 2019 | 10471000 | 2019 | 2200000 | 2022 | 99343000 |  |  | 112014000 | UNDER CONSTRUCTION.
Martin, Bertie | US 13; US 17; NC 171 | NCDOT | Various locations. | Upgrade curve warning signs. |  | Highway | Safety | 1 | Mid-East RPO, Peanut Belt RPO | HS-2001B | Region A | HSIP, T(M) |  |  |  |  | 2023 | 36000 |  |  | 36000 | UNDER CONSTRUCTION.
Martin, Edgecombe, Washington, Dare, Tyrrell, Nash | US 64 (Future I-87) | NCDOT | I-95 interchange to NC 12. | Install broadband fiber and ITS for traveler information systems. | 145.54 | Highway | Other | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | HB-0001A | Statewide Mobility | DP, HSIP, T(M) |  |  |  |  | 2027 | 26500000 |  |  | 26500000
McDowell | Fonta Flora Trail | MCDOWELL COUNTY | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5916 | Division 13 | L, TA5200, TA5T50 | 2026 | 60000 |  |  | 2026 | 4700000 | 2021 | 560000 | 5320000
McDowell | SR 1703 (Baldwin Avenue) | MARION | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5753 | Division 13 | L(M), TA5T50, TAANY | 2026 | 160000 | 2026 | 760000 | 2027 | 4000000 | 2024 | 463000 | 5383000
McDowell | New Route | NCDOT | Universal Property. | Construct access road. | 0.17 | Highway | Appalachian Development Highway System | 13 | Foothills RPO | R-5964 | Exempt | ADHSL |  |  |  |  | 2021 | 922000 |  |  | 922000 | UNDER CONSTRUCTION. ARC # 19098; AWARD AMOUNT = $987,112
McDowell | SR 1781 (Polly Spout Road) | NCDOT | Bridge 580312 over Second Broad River. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Foothills RPO | B-6014 | Division 13 | BGOFF | 2022 | 100000 |  |  | 2022 | 3027000 |  |  | 3127000 | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION.
McDowell | I-40 | NCDOT | Mile marker 67 to mile marker 73 (Old Fort Mountain). | Construct safety and drainage improvements, rehabilitate pavement, and reconstruct median barrier. | 5.95 | Highway | Interstate Maintenance | 13 | Foothills RPO | HI-0010 | Statewide Mobility | NHP, PROTCT, T(M) |  |  |  |  | 2023 | 21500000 |  |  | 21500000 | UNDER CONSTRUCTION.
McDowell | I-40 | NCDOT | Mile marker 73.0 to mile marker 86.0. | Rehabilitate pavement. | 12.99 | Highway | Interstate Maintenance | 13 | Foothills RPO | I-5900 | Statewide Mobility | NHFP, NHPIM, T(M) |  |  |  |  | 2027 | 25100000 |  |  | 25100000
McDowell | I-40 | NCDOT | Mile marker 81 / SR 1001 (Sugar Hill Road) to mile marker 86 / NC 226. | Rehabilitate pavement. | 4.97 | Highway | Interstate Maintenance | 13 | Foothills RPO | HI-0009 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 14900000 |  |  | 14900000
McDowell | Marion | NCDOT | Loves Marion Travel Stop #308. | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 13 | Foothills RPO | HV-0001B | Division 13 | NEVI, O, O(M), S(M) |  |  |  |  | 2025 | 1336000 |  |  | 1336000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM LOVE'S TRAVEL STOPS & COUNTY STORES INC
McDowell | US 221 (Marion Bypass) | NCDOT | South of Southern Railway to US 221 / NC 226 intersection south of Marion. | Widen to multi-lanes, with a bypass of Marion. | 0.5 | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-0204C | [11 empty] | COMPLETE
McDowell | US 221 (Marion Bypass) | NCDOT | US 221 / NC 226 Business to south of Southern Railway. | Widen to multi-lanes, with a bypass of Marion. |  | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-0204B | [11 empty] | COMPLETE
McDowell | US 221 / NC 226 | NCDOT | SR 1434 (Toms Creek Road) north of Marion to US 221 / NC 226 Business. | Widen to multi-lanes, with a bypass of Marion. |  | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-0204A | [11 empty] | COMPLETE
McDowell | I-40 | NCDOT | Buncombe County Line to Burke County Line. | Upgrade guardrail end units. |  | Highway | Safety | 13 | Foothills RPO | HS-2413L | Statewide Mobility | HSIP |  |  |  |  | 2025 | 285000 |  |  | 285000
McDowell | SR 1135 (Old Fort / Sugar Hill Road) | NCDOT | SR 1103 (Bat Cave Road) to SR 1001 (Sugar Hill Road / Montford Cove Road) near Old Fort. | Install guardrail. | 8.95 | Highway | Safety | 13 | Foothills RPO | HS-2013M | Division 13 | HSIP |  |  |  |  | 2023 | 890000 |  |  | 890000
McDowell | US 221 | NCDOT | NC 226 / US 221 BUS to US 70. | Improve pavement. | 2.49 | Highway | Safety | 13 | Foothills RPO | HS-2013H | Statewide Mobility | HSIP |  |  |  |  | 2023 | 530000 |  |  | 530000 | UNDER CONSTRUCTION.
McDowell | US 221 | NCDOT | Rutherford County Line to Avery County Line. | Upgrade guardrail end units. |  | Highway | Safety | 13 | Foothills RPO | HS-2413M | Statewide Mobility | HSIP |  |  |  |  | 2026 | 645000 |  |  | 645000
McDowell | US 221 | NCDOT | US 221 Business to north of NC 226 near Marion. | Install rumble stripes and 6" long life pavement markings. |  | Highway | Safety | 13 | Foothills RPO | HS-2413C | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 444000 |  |  | 444000
McDowell | US 70 | NCDOT | Mile marker 7.0 to mile marker 15.0 and mile marker 20.0 to mile marker 27.0 near Marion. | Install rumble stripes and 6" long life pavement markings. |  | Highway | Safety | 13 | Foothills RPO | HS-2413D | Region G | HSIP, T(M) |  |  |  |  | 2026 | 600000 |  |  | 600000
McDowell | SR 1001 (Sugar Hill Road) | NCDOT | I-40 westbound ramps to 0.3 mile west of I-40 eastbound ramps in Marion. | Widen roadway. | 0.36 | Highway | STI (Prioritization) | 13 | Foothills RPO | U-5818 | Division 13 | T | 2020 | 75000 |  |  | 2020 | 13230000 | 2020 | 1710000 | 15015000 | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $55,995 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
McDowell | US 221 | NCDOT | I-40 interchange. | Construct interchange improvements. | 2.13 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204EA | Division 13 | NHP | 2026 | 20100000 | 2026 | 1600000 | 2029 | 42700000 |  |  | 64400000
McDowell | US 221 | NCDOT | NC 266 south of Marion to north of I-40. | Widen to multi-lanes with a bypass of Marion. | 0.5 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204D | Not Funded | T | NOT FUNDED | 3000000 | NOT FUNDED | 500000 | NOT FUNDED | 32500000 | NOT FUNDED |  | 36000000
McDowell | US 221 | NCDOT | North of I-40 to SR 1153 (Goose Creek Road). | Widen to multi-lanes. | 2.13 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204EB | Division 13 | NHP | 2030 | 4000000 | 2030 | 2200000 | 2033 | 33400000 |  |  | 39600000
McDowell | US 221 / NC 226 | NCDOT | SR 1434 (Toms Creek Road) to SR 1153 (Goose Creek Road / Old Glenwood Road). | Widen to multi-lanes with a bypass of Marion. | 12.4 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204
McDowell | US 221 Business | NCDOT | US 221 / NC 226 to Georgia Avenue in Marion. | Widen existing roadway. | 1.48 | Highway | STI (Prioritization) | 13 | Foothills RPO | U-5835 | Division 13 | BG5T50 | 2024 | 6600000 | 2024 | 2000000 | 2031 | 26300000 |  |  | 34900000 | RIGHT-OF-WAY IN PROGRESS.
McDowell | NC 126 | NCDOT | Norfolk Southern Railroad Crossing 729481N in Marion. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | Foothills RPO | RX-2413F | Division 13 | RR |  |  |  |  | 2026 | 440000 |  |  | 440000
McDowell | SR 1103 (Catawba Avenue) | NCDOT | Norfolk Southern Railroad Crossing 729447G in Old Fort. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | Foothills RPO | RX-2413G | Division 13 | RR |  |  |  |  | 2026 | 560000 |  |  | 560000
McDowell, Mitchell | Primary and secondary routes | NCDOT | Various locations in Division 13 | Construct pedestrian improvements. | 20 | Highway | Safety | 13 | Foothills RPO, High Country RPO | HS-2413P | Region G | HSIP |  |  |  |  | 2026 | 373000 |  |  | 373000
McDowell, Rutherford | US 221 | NCDOT | US 64 in Rutherford County to the McDowell County line; Rutherford County line to I-40. | Install sinusoidal centerline rumble stripes and long life pavement markings. | 18.99 | Highway | Safety | 13 | Foothills RPO | W-5813J | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2022 | 500000 |  |  | 500000 | UNDER CONSTRUCTION.
Mecklenburg | CLT | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Charlotte Douglas International Airport | Construct end around taxiway on west side of proposed fourth parallel runway. |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AP-0001 | Statewide Mobility | T |  |  |  |  | 2029 | 2000000 |  |  | 2000000
Mecklenburg | CLT | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | Charlotte Douglas International Airport | Construct fourth parallel runway. |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AV-5879 | Statewide Mobility | O, T |  |  |  |  | 2025 | 609000000 |  |  | 609000000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
Mecklenburg | CLT | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | Charlotte Douglas International Airport | Expand west ramp near Concourse A. |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AV-5881 | Statewide Mobility | O, T |  |  |  |  | 2021 | 40100000 |  |  | 40100000 | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
Mecklenburg | Albemarle Road; Wilora Lake Road | CHARLOTTE | Redman Road to Nevin Road in Charlotte; Albemarle Road to 100 feet north of Barr Drive in Charlotte | Construct sidewalk; Construct sidewalk and pedestrian improvements at various intersections. | 0.93 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0084 | Division 10 | L(M), TADA |  |  |  |  | 2027 | 3182000 | 2025 | 10000 | 3192000
Mecklenburg | Beaty Street | DAVIDSON | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0096 | Division 10 | L(M), TADA | 2026 | 601000 |  |  | 2028 | 2561000 | 2024 | 330000 | 3492000
Mecklenburg | Davidson-Concord Road | DAVIDSON | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0161 | Division 10 | BGDA, L(M) | 2028 | 473000 | 2028 | 10000 | 2030 | 1880000 | 2027 | 440000 | 2803000
Mecklenburg | Four Mile Creek Greenway | MATTHEWS | SR 3448 (South Trade Street) in Matthews | Construct greenway crossing under roadway. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5829 | Division 10 | L(M), TADA |  |  |  |  | 2022 | 2899000 | 2019 | 141000 | 3040000 | UNDER CONSTRUCTION.
Mecklenburg | Hornets Nest Park | CHARLOTTE | SR 2025 (Oakdale Road / Miranda Road) to Kiev Drive in Charlotte. | Construct sidewalks on the north side. | 2.83 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-6036 | Division 10 | BGDA, L(M) |  |  |  |  | 2025 | 3158000 | 2020 | 5000 | 3163000
Mecklenburg | Huntersville | HUNTERSVILLE | US 21 in Huntersville. | Construct greenway culvert under roadway. | 0.21 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0080 | Division 10 | L(M), TADA |  |  |  |  | 2025 | 3240000 | 2024 | 10000 | 3250000
Mecklenburg | Irwin Creek Greenway | MECKLENBURG COUNTY | Clanton Road to Lester Street in Charlotte | Construct greenway. | 1.3 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0057 | Division 10 | BGDA, CMAQ, L(M) |  |  |  |  | 2030 | 6081000 | 2024 | 10000 | 6091000 | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
Mecklenburg | Kincaid Multi-Use Path | DAVIDSON | Eugenia Street and Spring Street to South Prong Rocky River Greenway near Davidson Elementary in Davidson | Construct multi-use path. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5933 | Division 10 | L(M), TAANY |  |  |  |  | 2026 | 878000 | 2024 | 219000 | 1097000 | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23
Mecklenburg | McDowell Creek Greenway | CORNELIUS | Magnolia Plaza to SR 2147 (Westmoreland Road) in Cornelius | Construct greenway. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5817 | Division 10 | BGDA, L(M), TADA |  |  |  |  | 2020 | 3882000 |  |  | 3882000 | COMPLETE.
Mecklenburg | McDowell Creek Greenway | NCDOT | NC 73 near Lindholm Drive in Huntersville | Construct pedestrian bridge. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0119 | Division 10 | BGDA, L(M) |  |  |  |  | 2027 | 6100000 |  |  | 6100000
Mecklenburg | McDowell Creek Tributary Greenway | CORNELIUS | Smithville Park at Catawba Avenue to SR 2147 (Westmoreland Road); SR 2147 (Westmoreland Road) from east of Amberwood Glen Drive to SR 2600 (Washam Potts Road) in Cornelius | Construct shared-use path. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5777 | Division 10 | CMAQ, L(M) | 2021 | 960000 |  |  | 2026 | 2040000 |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Mecklenburg | NC 24 (W.T. Harris Boulevard) | CHARLOTTE | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-6052 | Division 10 | L(M), TADA | 2025 | 400000 |  |  | 2026 | 1252000 | 2023 | 10000 | 1662000
Mecklenburg | NC 51 | PINEVILLE | Johnston Drive intersection in Pineville | Relocate Johnston Drive to align with existing Church Street intersection. | 0.06 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5949 | Division 10 | BGDA, L(M), O |  |  |  |  | 2022 | 4404000 |  |  | 4404000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 OF NC194 EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH
Mecklenburg | Rail Trail Pedestrian Bridge | CHARLOTTE | SR 3815 (East Morehead Street) to Brooklyn Village Light Rail Station over I-277 (Belk Freeway) in Charlotte | Construct rail trail pedestrian bridge. | 0.11 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0058 | Division 10 | L(M), TAANY |  |  |  |  | 2025 | 6343000 |  |  | 6343000 | $1.903M IN STBG-DA FUNDS SWAPPED FOR $1.903M IN TAP-ANYAREA FUNDS ON 5-17-23
Mecklenburg | South McDowell Street | CHARLOTTE | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5929 | Division 10 | BGANY, BGDA, L, TADA | 2021 | 517000 |  |  | 2026 | 1669000 | 2019 | 265000 | 2451000 | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE.
Mecklenburg | SR 1004 (Bain School Road) | MINT HILL | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0120 | Division 10 | BGDA, L(M) | 2028 | 220000 |  |  | 2030 | 1100000 | 2026 | 469000 | 1789000
Mecklenburg | SR 2840 (Rocky River Road) | CHARLOTTE | Rockland Drive to SR 2939 (Old Concord Road) in Charlotte | Construct shared-use path. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0123 | Division 10 | BGDA, L(M) |  |  |  |  | 2027 | 3952000 | 2025 | 10000 | 3962000
Mecklenburg | SR 3128 (Lawyers Road) | MINT HILL | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0121 | Division 10 | BGDA, L(M) | 2028 | 236000 |  |  | 2030 | 774000 | 2026 | 319000 | 1329000
Mecklenburg | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | MINT HILL | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0081 | Division 10 | L(M), TADA | 2028 | 133000 |  |  | 2029 | 1081000 | 2025 | 434000 | 1648000
Mecklenburg | SR 3168 (Sam Newell Road) | MATTHEWS | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5783 | Division 10 | BGANY, BGDA, L, L(M) | 2022 | 335000 |  |  | 2026 | 2023000 | 2018 | 381000 | 2739000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP.
Mecklenburg | SR 3178 (Moore Road) | MATTHEWS | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0158 | Division 10 | BGDA, L(M) | 2028 | 152000 | 2028 | 10000 | 2030 | 323000 | 2026 | 92000 | 577000
Mecklenburg | Sugar Creek Road | CHARLOTTE | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0083 | Division 10 | DP, L(M), TADA | 2026 | 686000 |  |  | 2027 | 20262000 | 2025 | 10000 | 20958000 | DP REPRESENTS FY 23 RAISE GRANT FUNDS.
Mecklenburg | The Park - Huntersville Greenway | HUNTERSVILLE | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0010 | Division 10 | BGDA, L(M), TAANY, TADA | 2026 | 516000 |  |  | 2027 | 2600000 | 2023 | 376000 | 3492000 | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23
Mecklenburg | Truelight Church Road | MINT HILL | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0124 | Division 10 | BGDA, L(M) | 2028 | 124000 |  |  | 2030 | 1216000 | 2026 | 500000 | 1840000
Mecklenburg | Upper McDowell Creek Greenway | HUNTERSVILLE | Chilgrove Lane to NC 73 in Huntersville | Construct greenway. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5785 | Division 10 | CMAQ, L(M) |  |  |  |  | 2025 | 5339000 |  |  | 5339000 | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
Mecklenburg | Various | CHARLOTTE | Locations in Charlotte | Expand bicycle routes. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5820 | Division 10 | [10 empty] | UNDER CONSTRUCTION
Mecklenburg | Various | MINT HILL | Lawyers Road from Lebanon Road / Wilson Grove Road to Apple Creek Drive in Mint Hill; Wilgrove-Mint Hill Road from Jim Harper Lane to Wilson Grove Road in Mint Hill; Wilson Grove Road from Wilgrove-Mint Hill Road to Central Drive in Mint Hill | Extend sidewalks. | 3.37 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-6051 | Division 10 | L(M), TADA | 2026 | 60000 |  |  |  |  | 2022 | 376000 | 436000
Mecklenburg | West Branch Nature Preserve | DAVIDSON | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0003 | Division 10 | BGDA, L, L(M), TADA | 2028 | 10000 | 2028 | 10000 | 2028 | 1558000 | 2023 | 537000 | 2115000 | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD
Mecklenburg | Charlotte | CHARLOTTE | East Charlotte Connector Trail | Funding for Albemarle Corridor Cultural Trail Framework Plan |  | Bike & Ped | Other | 10 | Charlotte Regional TPO | BO-0001 | Exempt | DP, L(M) | [6 empty] | 2026 | 1800000 | 1800000
Mecklenburg | Charlotte | CHARLOTTE | Rozzelles Ferry Mobility Path | Funding for Advance planning of the Rozzelles Ferry Mobility Path. |  | Bike & Ped | Other | 10 | Charlotte Regional TPO | BO-0002 | Exempt | DP, L(M) | [6 empty] | 2026 | 1624000 | 1624000
Mecklenburg | North Davidson Street | NCDOT | East 37th Street to Bearwood Avenue in Charlotte | Construct sidewalk. | 0.59 | Bike & Ped | Other | 10 | Charlotte Regional TPO | U-5008A | Pre-STI (Transition) | DP | 2022 | 1000000 | 2022 | 25000 | 2023 | 1200000 |  |  | 2225000 | UNDER CONSTRUCTION.
Mecklenburg | Irwin Creek Greenway | MECKLENBURG COUNTY | Existing Irwin Creek Greenway to Hamilton Street in Charlotte | Construct greenway. | 0.55 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5970 | Division 10 | L(M), TAANY |  |  |  |  | 2028 | 4636000 |  |  | 4636000
Mecklenburg | McAlpine Creek Greenway | MECKLENBURG COUNTY | NC 51 to Four Mile Creek Greenway in Charlotte | Construct greenway. | 1.65 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5782 | Division 10 | L(M), TAANY, TADA |  |  |  |  | 2023 | 7218000 |  |  | 7218000
Mecklenburg | NC 51 | NCDOT | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5969 | Division 10 | L(M), TAANY, TADA | 2026 | 960000 |  |  | 2028 | 1300000 | 2023 | 464000 | 2724000
Mecklenburg | SR 2833 (Mallard Creek Church Road) | CHARLOTTE | SR 2472 (Mallard Creek Road) to SR 2746 (Claude Freeman Drive) in Charlotte | Construct multi-use trail on south side of road. | 0.62 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5832 | Division 10 | BGDA, L(M), TAANY |  |  |  |  | 2022 | 1678000 |  |  | 1678000 | UNDER CONSTRUCTION.
Mecklenburg | Stewart Creek Greenway | CHARLOTTE | State Street to Rozzelles Ferry Road in Charlotte | Construct greenway. |  | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5781 | Division 10 | CMAQ, CRPDA, L(M) |  |  |  |  | 2021 | 3159000 |  |  | 3159000 | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Mecklenburg | NC 16 (Brookshire Boulevard) | NCDOT | SR 2004 (Mount Holly Huntersville Road) intersection. | Construct intersection improvements. | 0.5 | Highway | Economic Development | 10 | Charlotte Regional TPO | U-6084 | Region E | T |  |  |  |  | 2018 | 1963000 |  |  | 1963000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE.
Mecklenburg | I-277 | NCDOT | I-77 to East 10th Street. | Resurface roadway and rehabilitate bridges. | 3.5 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746
Mecklenburg | I-277 (Belk Freeway) | NCDOT | East Stonewall Street to East 10th Street. | Rehabilitate bridges 590047, 590309, 590315, 590316, 590448, 590449, 590450, 590451, 590452, 590478, 590479, 590487, 590488, and 590522. |  | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746B | Statewide Mobility | [10 empty] | COMPLETE
Mecklenburg | I-277 (Belk Freeway) | NCDOT | I-77 to East Stonewall Street. | Rehabilitate bridges 590078, 590118, 590505, 590506, 590507, 590508, 590509, and 590510. |  | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746A | Statewide Mobility | [10 empty] | COMPLETE
Mecklenburg | I-277 (Brookshire Freeway) | NCDOT | I-77 to East 10th Street. | Resurface roadway and rehabilitate bridges 590044, 590048, 590138, 590320, 590322, 590326, 590327, 590328, 590330, and 590332. | 1.75 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746C | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 44017000 |  |  | 44017000 | UNDER CONSTRUCTION.
Mecklenburg | I-277 (Brookshire Freeway) | NCDOT | West of I-77 to east of I-77. | Rehabilitate bridges 590339, 590337, 590338, 590341, 590342, 590281, 590282, and 590283 . | 0.32 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-6052 | Statewide Mobility | BGDA, NHPIM, T, T(M) |  |  |  |  | 2023 | 16660000 |  |  | 16660000 | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION.
Mecklenburg | I-485 | NCDOT | Blair Road to Idlewild Road. | Rehabilitate pavement. | 6.19 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5904 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 9801000 |  |  | 9801000 | COMPLETE - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034
Mecklenburg | I-485 | NCDOT | I-77 to NC 49; Bridges 590661, 590662, 590663, 590664, and 590643 | Rehabilitate pavement; Rehabilitate bridges. | 56.03 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5828 | Statewide Mobility | HFB, NHPIM |  |  |  |  | 2029 | 11950000 |  |  | 11950000 | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS
Mecklenburg | I-485 | NCDOT | Oakdale Road Interchange at mile marker 17.2. | Rehabilitate pavement and bridges 590955 and 590956. | 1 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5861 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2023 | 1256000 |  |  | 1256000 | UNDER CONSTRUCTION.
Mecklenburg | I-485 | NCDOT | SR 1786 (Old Gum Branch Road) to NC 27. | Rehabilitate bridges 590945, 590946, and 590947. | 0.65 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5902 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 1600000 |  |  | 1600000
Mecklenburg | I-77 | NCDOT | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 1.11 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5769 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 17532000 |  |  | 17532000 | COMPLETE - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034
Mecklenburg | I-85 | NCDOT | Concrete pavement joint at US 29 / NC 49 connector to concrete pavement joint north of NC 73. | Preserve pavement and bridge 590296. | 13.93 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5826 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 8940000 |  |  | 8940000 | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034
Mecklenburg | I-85 | NCDOT | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 2.92 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5796 | Statewide Mobility | [10 empty] | TO BE LET WITH I-5770 - UNDER CONSTRUCTION
Mecklenburg | I-85 | NCDOT | West of NC 16 (Brookshire Boulevard) to concrete pavement joint at US 29 / NC 49 Connector. | Rehabilitate pavement. | 2 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5905 | Statewide Mobility | BGDA, NHPIM, T(M) |  |  |  |  | 2021 | 19588000 |  |  | 19588000 | COMBINED WITH I-5906. UNDER CONSTRUCTION.
Mecklenburg | Beaty Street | DAVIDSON | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0111 | Exempt | CMAQ, L(M) | 2027 | 339000 |  |  | 2029 | 2742000 | 2025 | 358000 | 3439000
Mecklenburg | Brown-Grier Road; Sandy Porter Road | CHARLOTTE | NC 160 to I-485; William Glen to Brown-Grier Road | Improve corridors. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0138 | Division 10 | BGANY, L |  |  |  |  | 2027 | 31751000 | 2025 | 10000 | 31761000 | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24.
Mecklenburg | Davidson-Concord Road | NCDOT | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6092 | Exempt | BGDA, CMAQ, L(M) | 2022 | 795000 |  |  | 2025 | 2472000 | 2020 | 150000 | 3417000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Mecklenburg | Greylock Ridge Road | NCDOT | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0025 | Division 10 | BA, L, L(M), T(DA) | 2023 | 701000 | 2024 | 500000 | 2026 | 7900000 | 2022 | 1173000 | 10274000 | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25.
Mecklenburg | I-485 | NCDOT | Various locations along interstate. | Replace overhead signs. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038D | Exempt | BGDACV |  |  |  |  | 2022 | 705000 |  |  | 705000 | UNDER CONSTRUCTION.
Mecklenburg | Lancaster Highway | CHARLOTTE | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0113 | Exempt | CMAQ, HF, HF(M), L |  |  | 2026 | 400000 | 2027 | 3535000 | 2025 | 313000 | 4248000 | HF represents SPOT Mobility funds
Mecklenburg | Main Street | HUNTERSVILLE | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5908 | [11 empty] | UNDER CONSTRUCTION; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP.
Mecklenburg | Main Street | HUNTERSVILLE | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5908A | Division 10 | BGANY, BGDA, L(M) | 2020 | 825000 |  |  | 2021 | 4075000 | 2021 | 12000 | 4912000 | UNDER CONSTRUCTION.
Mecklenburg | NC 115 | HUNTERSVILLE | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0056 | Exempt | L, T(DA) | 2027 | 2852000 |  |  | 2029 | 4938000 | 2024 | 751000 | 8541000 | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP.
Mecklenburg | NC 115 | HUNTERSVILLE | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5908B | Exempt | BGANY, BGDA, L(M) | 2020 | 2895000 |  |  | 2021 | 12249000 |  |  | 15144000 | UNDER CONSTRUCTION.
Mecklenburg | NC 115 | NCDOT | Hickory Street intersection in Cornelius. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5613J | Exempt | BGDA, CMAQ, L(M) | 2022 | 675000 |  |  | 2026 | 3469000 |  |  | 4144000 | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265
Mecklenburg | NC 115 | NCDOT | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5873 | Exempt | BA, CMAQ, CRPDA, L, L(M), T(DA), T(M) | 2018 | 4254000 |  |  | 2024 | 16992000 | 2017 | 1404000 | 22650000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP.
Mecklenburg | NC 16 | CHARLOTTE | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0161 | Region E | BGDA, L(M) | 2028 | 38000 | 2028 | 10000 | 2029 | 3166000 | 2026 | 596000 | 3810000
Mecklenburg | NC 24 (W.T. Harris Boulevard) | CHARLOTTE | SR 2004 (Mount Holly-Huntersville Road) to I-85 North ramp. | Install overhead street lights. | 7.92 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0057 | Division 10 | BA, L, T(DA) |  |  |  |  | 2026 | 1522000 | 2024 | 10000 | 1532000 | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024.
Mecklenburg | NC 27 (Freedom Drive); Eastway Drive | MECKLENBURG COUNTY | Valerie C. Woodard Center and Ella B. Scarborough Community Resource Center. | Install electric vehicle fast charging stations. | 0.1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0163 | Exempt | CMAQ, CRPDA, L(M) |  |  |  |  | 2027 | 784000 | 2027 | 50000 | 834000
Mecklenburg | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | CHARLOTTE | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0152 | Exempt | BGDA, CRPANY, CRPDA, L |  |  |  |  | 2027 | 4040000 | 2025 | 857000 | 4897000 | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24.
Mecklenburg | NC 51 | NCDOT | Park Road to Carmel Road. | Construct access management improvements. | 1.46 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6086 | Region E | BGANY, L(M) |  |  |  |  | 2026 | 7553000 |  |  | 7553000 | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP
Mecklenburg | New Route | NCDOT | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5907 | Division 10 | BA, L, T(DA) | 2019 | 1798000 |  |  | 2024 | 10645000 | 2019 | 1853000 | 14296000 | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907.
Mecklenburg | North University Research Park I-85 Overpass | CHARLOTTE | SR 2722 (Louis Rose Place) to Doug Mayes Place. | Construct roadway. | 0.3 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5874 | Division 10 | BGANY, BGDA, L(M) | 2020 | 3500000 |  |  | 2022 | 19883000 |  |  | 23383000 | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES.
Mecklenburg | Rea Road | CHARLOTTE | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0023 | Division 10 | BA, HF, O, T(DA) | 2023 | 816000 |  |  | 2026 | 6185000 | 2024 | 24000 | 7025000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23.
Mecklenburg | SR 1138 (Arrowood Road) | CHARLOTTE | NC 49 (South Tryon) to South Boulevard. | Install ITS upgrades. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5613BD | Exempt | CMAQ, L(M) |  |  |  |  | 2022 | 614000 |  |  | 614000 | UNDER CONSTRUCTION.
Mecklenburg | SR 1662 (Tuckaseegee Road) | CHARLOTTE | Berryhill Road / Thrift Road intersection in Charlotte. | Construct a roundabout. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5538 | Division 10 | CMAQ, L(M) |  |  |  |  | 2021 | 3676000 |  |  | 3676000 | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Mecklenburg | SR 2112 (Lakeview Road) | CHARLOTTE | NC 24 (Harris Boulevard) and US 21 (Statesville Road) intersections in Charlotte. | Construct intersection improvements. | 1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5905B | Exempt | BA, BGDA |  |  |  |  | 2021 | 3162000 |  |  | 3162000
Mecklenburg | SR 2112 (Lakeview Road) | CHARLOTTE | Reames Road to NC 115. | Upgrade roadway. | 1.72 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5905A | Division 10 | BA, BGDA |  |  |  |  | 2021 | 8661000 |  |  | 8661000 | RIGHT-OF-WAY IN PROGRESS
Mecklenburg | SR 2112 (Lakeview Road) | CHARLOTTE | Reames Road to NC 115. | Upgrade roadway. | 2.1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5905 |  | BA | 2019 | 1500000 |  |  |  |  | 2017 | 1500000 | 3000000 | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
Mecklenburg | SR 2136 (Gilead Road) | HUNTERSVILLE | SR 2120 (McCoy Road) to Wynfield Creek Parkway. | Widen to 4-lanes divided. | 0.47 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6106 | Division 10 | BGANY, BGDA, L(M) | 2022 | 3134000 |  |  | 2026 | 10684000 |  |  | 13818000 | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP.
Mecklenburg | SR 2137 (Ervin Cook Road) | CHARLOTTE | South Birkdale Commons Parkway to Whitaker Pointe Drive. | Extend roadway. Construct roundabout at Whitaker Pointe Drive and South Birkdale Commons Parkway. | 0.4 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0162 | Division 10 | L(M), T(DA) | [6 empty] | 2026 | 812000 | 812000 | $406K IN BGDA FUNDS SWITCHED WITH $406K IN T(DA) FUNDS AS PART OF FUND SWAP.
Mecklenburg | SR 2195 (Torrence Chapel Road) / Liverpool Parkway | NCDOT | Various intersections in Cornelius. | Construct intersection improvements. Realign Knox Road and One Norman Boulevard intersection. Rehabilitate Knox Road. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5906 | Division 10 | BA, BGDA, L, L(M), O, T, T(DA) | 2020 | 10838000 |  |  | 2026 | 21501000 | 2017 | 2367000 | 34706000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION.
Mecklenburg | SR 2415 (Bailey Road) | NCDOT | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6105 | Division 10 | BGANY, BGDA, L(M) | 2023 | 2064000 |  |  | 2025 | 4632000 |  |  | 6696000 | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP
Mecklenburg | SR 2467 (Mallard Creek Road) | CHARLOTTE | NC 24 (Harris Boulevard) to Governor Hunt Road. | Install ITS and traffic management upgrades. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5613BE | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 200000 |  |  | 200000 | UNDER CONSTRUCTION.
Mecklenburg | SR 2479 (Dearmon Road) | CHARLOTTE | SR 2475 (Benfield Road) to SR 2480 (Browne Road). | Construct complete street improvements. | 0.78 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0112 | Division 10 | L, T(DA) |  |  |  |  | 2028 | 15665000 | 2024 | 10000 | 15675000 | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23
Mecklenburg | SR 2822 (Robinson Church Road) | CHARLOTTE | NC 24 to Plott Road. | Widen to three lanes. | 0.58 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0053 | Division 10 | L, T(DA) |  |  |  |  | 2028 | 12444000 | 2026 | 10000 | 12454000 | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
Mecklenburg | SR 3156 (Margaret Wallace Road) | NCDOT | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-2509EA | Division 10 | L, T(DA) | 2026 | 8568000 | 2025 | 910000 | 2028 | 4887000 |  |  | 14365000 | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP.
Mecklenburg | SR 3468 (Weddington Road) | NCDOT | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0024 | Division 10 | BA, T(DA) | 2024 | 2300000 | 2024 | 1200000 | 2029 | 4723000 | 2021 | 1211000 | 9434000 | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22.
Mecklenburg | Stumptown Road | HUNTERSVILLE | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0118 | Region E | L, L(M), T(DA) | 2027 | 4042000 | 2028 | 603000 | 2029 | 16873000 | 2026 | 185000 | 21703000 | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25.
Mecklenburg | US 21 | NCDOT | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5621 | Region E | BA, BGDA, CMAQ, L, T(M) | 2020 | 6183000 |  |  | 2024 | 23823000 | 2020 | 1916000 | 31922000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP.
Mecklenburg | US 29 / US 74 (Wilkinson Boulevard); US 29 (North Tryon Street) | NCDOT | Gaston County line to Field Ridge Road; West Sugar Creek Road to Old Concord Road. | Resurface roadways. | 3.46 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038A | Exempt | BGDACV |  |  |  |  | 2022 | 2596000 |  |  | 2596000 | COMPLETE.
Mecklenburg | Various | NCDOT | Routes in Division 10. | Perform various maintenance activities including resurfacing, traffic signal loop replacement, pavement restriping and markers, and sign replacement. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038 |  | BGDACV | [6 empty] | 2022 | 5000 | 5000
Mecklenburg | Various | NCDOT | Routes in Division 10. | Replace pavement markings and snow plowable markers. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038B | Exempt | BGDACV |  |  |  |  | 2022 | 2318000 |  |  | 2318000 | UNDER CONSTRUCTION.
Mecklenburg | Various | NCDOT | Routes in Division 10. | Replace traffic signal loops. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038C | Exempt | BGDACV |  |  |  |  | 2022 | 90000 |  |  | 90000 | COMPLETE.
Mecklenburg | WT Harris Boulevard | CHARLOTTE | Sugar Creek intersection in Charlotte | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0137 | Exempt | BGANY, L |  |  |  |  | 2028 | 1901000 | 2025 | 10000 | 1911000 | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24.
Mecklenburg | Morris Field Drive | CHARLOTTE | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Highway | Municipal Bridge | 10 | Charlotte Regional TPO | B-5931 | Division 10 | BGANY, BGDA, BGOFF, L, L(M) |  |  |  |  | 2026 | 6204000 | 2024 | 20000 | 6224000 | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION.
Mecklenburg | Sardis Lane | CHARLOTTE | Bridge 590433 over McAlpine Creek. | Replace Bridge. | 0.25 | Highway | Municipal Bridge | 10 | Charlotte Regional TPO | B-5930 | Division 10 | BGOFF, L(M) |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | PROJECT ADMINISTERED BY CITY OF CHARLOTTE
Mecklenburg | Charlotte | NCDOT | Northlake Mall. | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 10 | Charlotte Regional TPO | HV-0001F | Division 10 | NEVI, O(M), S(M) |  |  |  |  | 2025 | 1473000 |  |  | 1473000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM SCHNEIDER ELECTRIC BUILDINGS AMERICAS INC
Mecklenburg | Charlotte | CHARLOTTE | Freedom Drive/Ashely Road/Tuckaseegee Road | Construct complete street, traffic safety, and transit access/mobility service improvements. |  | Highway | Other | 10 | Charlotte Regional TPO | HO-0030 | Exempt | DP, L(M) |  |  |  |  | 2026 | 33692000 |  |  | 33692000
Mecklenburg | Huntersville | CHARLOTTE | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Highway | Other | 10 | Charlotte Regional TPO | HO-0033 | Exempt | DP, L(M) | [6 empty] | 2026 | 300000 | 300000
Mecklenburg | I-85 | NCDOT | I-485 interchange west of Charlotte | Improve interchange. Clearing work only. | 1 | Highway | Other | 10 | Charlotte Regional TPO | I-6016A | Highway Fund | HF |  |  |  |  | 2024 | 200000 |  |  | 200000
Mecklenburg | Mooresville | CHARLOTTE | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Highway | Other | 10 | Charlotte Regional TPO | HO-0031 | Exempt | DP, L(M) | [6 empty] | 2026 | 180000 | 180000
Mecklenburg | Various | CHARLOTTE | Charlotte Regional Transportation Planning Organization - Making Our Roads SAFER: A Cross-Jurisdictional Study (aka RAISE) | Fund planning activities by comprehensively examining prevailing transportation issues throughout the MPO's planning area. |  | Highway | Other | 10 | Charlotte Regional TPO | HO-0029 | Exempt | DP | [6 empty] | 2026 | 5000000 | 5000000
Mecklenburg |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | R-2632AC | Pre-STI (Transition) | [10 empty] | COMPLETE
Mecklenburg |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-0209B | Pre-STI (Transition) | NHP | 2010 | 10968000 |  |  | 2013 | 1025000 |  |  | 11993000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
Mecklenburg |  | NCDOT |  |  |  | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-0209BA | Pre-STI (Transition) | [10 empty] | WORK TO BE CONSTRUCTED BY PROJECT U-6103
Mecklenburg |  | NCDOT |  |  | 1.945 | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-2507B | [11 empty] | COMPLETE
Mecklenburg | SR 2467 (Mallard Creek Road) | NCDOT | SR 2480 (Sugar Creek Road) to SR 2472 (Mallard Creek Church Road) in Charlotte. | Widen to multi-lanes, part on new location. | 4.1 | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-2507
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | Brookshire Freeway to Idlewild Road in Charlotte. | Construct additional lanes and interchanges with Sharon Amity Road and Idlewild Road and safety improvements. | 1.4 | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-0209 | [11 empty] | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024
Mecklenburg | I-277 | NCDOT | Multiple exits | Install smart cushions. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 144000 |  |  | 144000
Mecklenburg | NC 16 (Providence Road) | NCDOT | High Ridge Drive/Greyson Ridge Drive. | Install pedestrian signals and upgrade pedestrian accommodations. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410O | Region E | HSIP |  |  |  |  | 2026 | 116000 |  |  | 116000
Mecklenburg | NC 24 / NC 27 | NCDOT | SR 3110 (Arlington Church Road) intersection near Charlotte. | Construct intersection improvements. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010A | Region E | HSIP | 2022 | 4000 |  |  | 2023 | 2025000 |  |  | 2029000 | UNDER CONSTRUCTION.
Mecklenburg | NC 49 (South Tryon Street) | NCDOT | General Drive; SR 1347 (Nevada Boulevard) intersections in Charlotte. | Install traffic signal at NC 49 and General Drive, and convert NC 49 at SR 1347 (Nevada Boulevard) to a directional crossover. | 0.42 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010E | Region E | HSIP |  |  | 2025 | 25000 | 2025 | 1470000 |  |  | 1495000
Mecklenburg | NC 49 (University City Boulevard) | NCDOT | Oak Leigh Drive intersection in Charlotte. | Install a directional crossover with a half signal for lefts onto Oak Leigh Drive. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410P | Statewide Mobility | HSIP | 2027 | 1000 | 2028 | 1000 | 2029 | 983000 |  |  | 985000
Mecklenburg | NC 51 | NCDOT | Palomino Drive / Hoods Village Drive intersection in Mint Hill | Construct directional crossover. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410H | Region E | HSIP | 2026 | 260000 | 2026 | 15000 | 2028 | 848000 |  |  | 1123000
Mecklenburg | NC 51 | NCDOT | SR 4982 (Polk Street) intersection in Charlotte. | Install pedestrian signals and accommodations. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010G | Region E | HSIP | 2025 | 70000 |  |  | 2025 | 410000 |  |  | 480000
Mecklenburg | NC 51 (Matthews Township Parkway) | NCDOT | Fullwood Lane intersection in Matthews | Construct pedestrian improvements. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410J | Region E | HSIP | 2026 | 15000 | 2026 | 5000 | 2027 | 277000 |  |  | 297000
Mecklenburg | NC 73 (Sam Furr Road) | NCDOT | SR 5544 (Catawba Avenue) and Glenfurness Drive intersections in Huntersville. | Install pedestrian accommodations. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010J | Region E | HSIP |  |  |  |  | 2024 | 865000 |  |  | 865000 | UNDER CONSTRUCTION.
Mecklenburg | SR 2025 (Oakdale Road) | NCDOT | SR 2108 (Sunset Road) / SR 2025 (Miranda Road) / SR 2041 (Simpson Road) / SR 2040 (Lawing Road) intersections near Charlotte. | Construct roundabouts. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710X | Division 10 | BGANY, BGDA, CMAQ, HSIP, L, L(M), O, T(M) | 2021 | 4288000 |  |  | 2026 | 6235000 | 2021 | 1021000 | 11544000 | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP.
Mecklenburg | SR 2935 (The Plaza) | NCDOT | Cove Creek Drive intersection in Charlotte | Construct directional crossover. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410G | Division 10 | HSIP |  |  |  |  | 2025 | 513000 |  |  | 513000
Mecklenburg | SR 3300 (7th Street) | NCDOT | Bascom Street / Cameron Avenue in Charlotte | Install traffic signal with pedestrian accommodations. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410B | Division 10 | HSIP, T(M) | 2026 | 24000 |  |  | 2028 | 233000 |  |  | 257000
Mecklenburg | SR 3448 (Pleasant Plains Road) | NCDOT | Squirrel Lake Park entrance intersection in Matthews. | Construct sidewalks and install pedestrian improvements. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410K | Division 10 | HSIP |  |  | 2026 | 10000 | 2026 | 101000 |  |  | 111000
Mecklenburg | SR 3468 (Weddington Road) | NCDOT | Vicinity of Socrates Academy | Construct pedestrian improvements. | 0.1 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410N | Division 10 | HSIP | 2025 | 10000 | 2025 | 5000 | 2026 | 115000 |  |  | 130000
Mecklenburg | SR 3624 (Rea Road) | NCDOT | Piper Glen Drive and Bevington Place intersections in Charlotte | Upgrade the traffic signals and install pedestrian accommodations. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410C | Division 10 | HSIP, T(M) | 2026 | 1000 |  |  | 2028 | 317000 |  |  | 318000
Mecklenburg | SR 3687 (Park Road) | NCDOT | Jim Hynes Circle intersection in Charlotte. | Install pedestrian signal. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410E | Division 10 | HSIP, T(M) |  |  |  |  | 2025 | 56000 |  |  | 56000
Mecklenburg | SR 5901 (Billy Graham Parkway) | NCDOT | NC 49 (Tryon Road) to I-85. | Install guardrail. | 5.1 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010L | Statewide Mobility | HSIP |  |  |  |  | 2023 | 960000 |  |  | 960000
Mecklenburg | Various | NCDOT | Various locations. | Install signal at various location on secondary routes. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410L | Division 10 | HSIP |  |  |  |  | 2026 | 1153000 |  |  | 1153000
Mecklenburg | I-485 |  | I-77 to I-85 in southwest Charlotte. | Construct one express lane in each direction. This is a toll project (express lanes only). |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | HP-0002 | Statewide Mobility | BOND R, NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 246200000 |  |  | 271500000
Mecklenburg | I-485 | NCDOT | I-77 south of Charlotte to US 74 (Independence Boulevard). | Construct one express lane in each direction. This is a toll project (express lanes only). | 16.62 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5507 | Statewide Mobility | T |  |  |  |  | 2019 | 504856000 |  |  | 504856000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT
Mecklenburg | I-485 | NCDOT | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5973 | Region E | T |  |  | 2022 | 195000 | 2023 | 6810000 |  |  | 7005000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE)
Mecklenburg | I-485 | NCDOT | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6019 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20700000 |  |  | 40300000
Mecklenburg | I-485 | NCDOT | NC 51 (Pineville-Matthews Road) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6015 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 840000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 720000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 |  |  | 15560000
Mecklenburg | I-485 (Charlotte Southern Outer Loop) | NCDOT | SR 3468 (Weddington Road) in Matthews. | Construct interchange. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-0211EC | Division 10 | T |  |  |  |  | 2019 | 9000000 |  |  | 9000000 | UNDER CONSTRUCTION. PROJECT LET WITH I-5507.
Mecklenburg | I-485 (Charlotte Southern Outer Loop) | NCDOT | West of I-77 to US 74. | Construct multi-lane freeway on new location. | 24.18 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-0211
Mecklenburg | I-77 | NCDOT | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5715 | Statewide Mobility | NHP, T(M) | 2023 | 21000000 | 2023 | 3000000 | 2027 | 79900000 |  |  | 103900000 | RIGHT-OF-WAY IN PROGRESS.
Mecklenburg | I-77 | NCDOT | South Carolina state line to I-277 / NC 16 (Brookshire Freeway). | Widen freeway to ten lanes by constructing managed lanes and reconstruct I-277 interchanges. This is a toll project (managed lanes only). | 11.2 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5718 | Statewide Mobility | BOND R, NHP | 2029 | 1508000000 | 2029 | 42000000 | 2029 | 2763315000 |  |  | 4313315000 | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049.
Mecklenburg | I-77 | NCDOT | SR 2136 (Gilead Road) interchange. | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5714 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Mecklenburg | I-85 |  | SR 1291 (Billy Graham Parkway) interchange in Charlotte. | Construct interchange improvements. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | HP-0004 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38700000 |  |  | 47800000
Mecklenburg | I-85 | NCDOT | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6012 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 47000000 |  |  | 52100000
Mecklenburg | I-85 | NCDOT | I-485 interchange west of Charlotte. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6016 | Statewide Mobility | HF, T | 2024 | 2000000 | 2024 | 970000 | 2026 | 41400000 |  |  | 44370000 | HF FUNDS ARE CONTINGENCY FUNDS.
Mecklenburg | I-85 | NCDOT | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6020 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 72900000 |  |  | 132100000
Mecklenburg | I-85 | NCDOT | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6013 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 590000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 390000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23000000 |  |  | 23980000
Mecklenburg | I-85 | NCDOT | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6053 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26973000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 655000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24300000 |  |  | 51928000
Mecklenburg | Independence Pointe Parkway | NCDOT | Sardis Road to SR 3474 (Sam Newell Road). | Construct roadway on new location. | 0.63 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509EB | Division 10 | T | 2028 | 1200000 | 2028 | 190000 | 2031 | 12000000 |  |  | 13390000 | SEGMENT C9
Mecklenburg | Independence Pointe Parkway | NCDOT | Windsor Square Drive to NC 51. | Construct roadway on new location. | 0.7 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AC | Statewide Mobility | NHP, T(M) | 2030 | 5799000 | 2030 | 3500000 | 2033 | 20400000 |  |  | 29699000 | 0
Mecklenburg | NC 115 (Old Statesville Road) | NCDOT | NC 24 (Harris Boulevard) to I-485 in Charlotte. | Widen to multi-lanes. | 2.16 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5772 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85900000 |  |  | 119700000
Mecklenburg | NC 16 (Brookshire Boulevard) | NCDOT | I-85 northbound ramp to eastbound NC 16 in Charlotte. | Improve I-85 northbound ramp to eastbound NC 16. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5955A | Region E | T |  |  |  |  | 2023 | 3000000 |  |  | 3000000 | UNDER CONSTRUCTION.
Mecklenburg | NC 16 (Brookshire Boulevard) | NCDOT | I-85 to Idaho Drive in Charlotte. | Construct additional westbound through lane west of Idaho Drive and I-85. Improve I-85 northbound ramp to eastbound NC 16. | 0.38 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5955 | Region E
Mecklenburg | NC 16 (Brookshire Boulevard) | NCDOT | Idaho Drive intersection in Charlotte. | Upgrade intersection to an interchange. | 0.38 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5955B | Region E | NHP, T(M) | 2030 | 4300000 | 2030 | 345000 | 2033 | 12700000 |  |  | 17345000
Mecklenburg | NC 160 | NCDOT | NC 49 (South Tryon Road) to I-485. | Widen to multi-lanes. | 4.31 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5766B | Region E | O, T | 2027 | 61890000 | 2027 | 42200000 | 2030 | 137400000 |  |  | 241490000 | BUILD NC BOND FUNDING: $12.3M FOR ROW, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE).
Mecklenburg | NC 160 | NCDOT | South Carolina line to I-485. | Widen to multi-lanes. | 6.8 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5766 | [11 empty] | "O" FUNDS REPRESENT CITY OF CHARLOTTE
Mecklenburg | NC 160 | NCDOT | South Carolina line to NC 49 (South Tryon Road). | Widen to multi-lanes. | 2.04 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5766A | Region E | T | 2025 | 26600000 | 2026 | 10700000 | 2030 | 35600000 |  |  | 72900000
Mecklenburg | NC 27 (Freedom Drive) | NCDOT | SR 1644 (Toddville Road) to SR 1600 (Moores Chapel Road) in Charlotte. | Widen to four lanes. | 1.25 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5957 | Region E | T | 2030 | 15900000 | 2030 | 2200000 | 2034 | 28800000 |  |  | 46900000
Mecklenburg | NC 49; SR 2827 (Back Creek Church Road) | NCDOT | John Kirk Drive to I-485; Existing SR 2827 (Back Creek Church Road) and NC 49 and SR 5394 (Mallard Creek Church Road)intersection in Harrisburg. | Widen to six lanes; Realign roadway on new location. Close existing grade rail crossing at NC 49 and SR 2827 (Back Creek Church Road). | 2.13 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5768 | Region E | L, T | 2030 | 37900000 | 2030 | 7500000 | 2034 | 80400000 |  |  | 125800000 | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE
Mecklenburg | NC 51 (Matthews Township Parkway) | NCDOT | SR 3356 (Sardis Road) to SR 1010 (East John Street / Monroe Road). | Widen to six lanes. | 0.75 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5763 | Region E | T | 2030 | 40100000 | 2030 | 5800000 | 2034 | 43000000 |  |  | 88900000
Mecklenburg | NC 73 | NCDOT | NC 115 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 2.67 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2632AB | Region E | BGDA, NHP, T(M) | 2023 | 8300000 | 2023 | 5100000 | 2028 | 68100000 |  |  | 81500000 | RIGHT-OF-WAY IN PROGRESS.
Mecklenburg | NC 73 | NCDOT | US 21 to NC 115. | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2632AA | [11 empty] | COMPLETE
Mecklenburg | NC 73 | NCDOT | US 21 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 4.3 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2632 | [11 empty] | COORDINATE WITH R-5706A & B. $7.273M IN NHP FUNDS SWITCHED WITH $7.237M IN BGDA AS PART OF FUND SWAP 8-9-22.
Mecklenburg | NC 73 | NCDOT | Vance Road Extension / Beatties Ford Road to SR 5544 (West Catawba Avenue) in Huntersville. | Widen to multi-lanes. | 1.88 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-5721B | Region E | BA, T | 2024 | 30401000 | 2024 | 3000000 | 2028 | 59300000 |  |  | 92701000 | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22.
Mecklenburg | NC 73 (Sam Furr Road) | NCDOT | SR 5544 (West Catawba Avenue) to SR 2316 (Northcross Drive). | Widen to six lanes. | 1.12 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5765 | Region E | T | 2023 | 58430000 | 2023 | 7500000 | 2027 | 49700000 |  |  | 115630000 | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE);
Mecklenburg | New route | NCDOT | SR 3457 (Campus Ridge Road) to SR 3448 (Pleasant Plains Road) in Matthews. | Construct two lane roadway on new location. | 1.1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4713
Mecklenburg | SR 1009 (John Street / Old Monroe Road) | NCDOT | I-485 interchange in Matthews | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714AB | Division 10 | [10 empty] | UNDER CONSTRUCTION. LET WITH I-5507.
Mecklenburg | SR 1009 (John Street / Old Monroe Road) | NCDOT | SR 3348 / SR 3474 (Trade Street) to west of I-485. | Widen to multi-lanes. | 1.01 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714AA | Not Funded | BGANY, T | NOT FUNDED | 19700000 | NOT FUNDED | 1600000 | NOT FUNDED | 30600000 | NOT FUNDED |  | 51900000
Mecklenburg | SR 1009 (Monroe Road) | NCDOT | Rama Road / Idlewild Road intersection in Charlotte. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5805 | Division 10 | BGANY, L(M), T, T(M) | 2020 | 1386000 |  |  | 2026 | 7440000 |  |  | 8826000 | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP.
Mecklenburg | SR 2467 (Mallard Creek Road) | NCDOT | SR 2472 (Mallard Creek Church Road) to Breezewood Drive. | Widen to four lanes. | 1.48 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6028 | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30000000 |  |  | 57000000
Mecklenburg | SR 2940 (Eastway Drive) | NCDOT | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5803 | Division 10 | L(M), NHP, O | 2026 | 6000000 |  |  | 2027 | 59519000 |  |  | 65519000 | LOCAL CONTRIBUTION OF $35.9M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP.
Mecklenburg | SR 3174 (Idlewild Road) | NCDOT | I-485 interchange. | Construct interchange improvements. | 0.1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913AA | Division 10 | T |  |  |  |  | 2028 | 5000000 |  |  | 5000000
Mecklenburg | SR 3174 (Idlewild Road) | NCDOT | SR 3175 (Stallings Road) to I-485. | Widen to four lanes. | 0.53 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913A | Division 10 | T | 2025 | 570000 | 2025 | 180000 | 2028 | 10678000 |  |  | 11428000 | RIGHT-OF-WAY IN PROGRESS.
Mecklenburg | SR 3440 (McKee Road) Extension | NCDOT | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4713A | Division 10 | L, T | 2020 | 2680000 | 2021 | 1100000 | 2025 | 15616000 | 2020 | 1155000 | 20551000 | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS
Mecklenburg | SR 3448 (South Trade Street) | NCDOT | Four Mile Creek to Weddington Road in Matthews. | Widen to four lanes. | 0.13 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5804B | Division 10 | T |  |  |  |  | 2019 | 1470000 |  |  | 1470000 | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE).
Mecklenburg | SR 3448 (South Trade Street) | NCDOT | Fullwood Lane to Four Mile Creek in Matthews. | Widen to four lanes. | 0.43 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5804A | [11 empty] | COMPLETE - BY TOWN OF MATTHEWS USING TOWN FUNDS.
Mecklenburg | SR 3448 (South Trade Street) | NCDOT | Fullwood Lane to Weddington Road in Matthews. | Widen to four lanes. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5804
Mecklenburg | SR 5544 (West Catawba Avenue) | NCDOT | NC 73 (Sam Furr Road) to east of SR 2151 (Jetton Road) in Cornelius. | Widen to four lanes divided. | 2.35 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2555B | Division 10 | L, T | 2018 | 5000000 | 2026 | 4000000 | 2028 | 37605000 |  |  | 46605000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028 / YR 8 SALE).
Mecklenburg | SR 5544 (West Catawba Avenue) | NCDOT | NC 73 (Sam Furr Road) to east of SR 2195 (Torrence Chapel Road) in Cornelius. | Widen to four lanes divided. | 3.4 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2555
Mecklenburg | SR 5544 (West Catawba Avenue) | NCDOT | SR 2151 (Jetton Road) to SR 2195 (Torrence Chapel Road). | Widen to four lanes divided. | 0.9 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2555A | [11 empty] | COMPLETE
Mecklenburg | US 21 | NCDOT | SR 2136 (Gilead Road) to SR 6028 (Holly Point Drive) in Huntersville. | Widen to four lanes. | 2.21 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5771 | Region E | BA, L, T, T(DA) | 2022 | 53050000 | 2022 | 1600000 | 2027 | 39809000 |  |  | 94459000 | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE);
Mecklenburg | US 21 (Statesville Road) | NCDOT | Northcross Center Court to SR 2147 (Westmoreland Road). | Widen to multi-lanes. | 1.22 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5767 | Region E | T | 2030 | 88500000 | 2030 | 2700000 | 2034 | 44300000 |  |  | 135500000
Mecklenburg | US 521 (Lancaster Highway / Johnston Road) | NCDOT | South Carolina State Line to SR 4979 (Ballantyne Commons Parkway). | Widen to multi-lanes. | 2.95 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6109 | Region E | NHP, T(M) | 2030 | 11900000 | 2030 | 2100000 | 2034 | 52900000 |  |  | 66900000
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | I-277 to west of Idlewild Road. | Widen roadway to allow for two-way express lane. This is a toll project (express lanes only). | 4.85 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6103 | Statewide Mobility | NHP, T(M) | 2030 | 12000000 | 2030 | 8100000 | 2033 | 248500000 |  |  | 268600000
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | Matthews-Mint Hill Road intersection in Charlotte. | Construct interchange at Matthews-Mint Hill Road. Extend Northeast Parkway from Overcash Drive to Waiting Street. | 0.23 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AD | Statewide Mobility | NHP, T(M) | 2026 | 46800000 | 2026 | 2600000 | 2029 | 35700000 |  |  | 85100000 | SEGMENT C10, C13
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | Sardis Road and SR 3473 (Sam Newell Road) intersections in Charlotte. | Construct interchanges at Sardis Road North and Sam Newell Road. Construct extension of Sardis Road North from US 74 to Arequipa Drive Extension and construct extension of Arequipa Drive from Sardis Road North Extension to Sam Newell Road. | 0.59 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AB | Statewide Mobility | NHP, T(M) | 2026 | 40700000 | 2026 | 5700000 | 2030 | 76000000 |  |  | 122400000 | SEGMENTS C6, C7A, C8
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | Sharon Forest Drive and Harris Boulevard / Village Lake Drive intersections in Charlotte. | Construct grade separation at Sharon Forest Drive and construct interchange at Village Lake Drive. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AA | Statewide Mobility | NHP, T(M) | 2026 | 85100000 | 2026 | 6500000 | 2031 | 78500000 |  |  | 170100000 | SEGMENTS C1, C2
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | SR 3356 (Sardis Road) to I-485. | Construct additional general purpose and express lanes. Construct express lane interchanges at I-485 and east side of Conference Drive, and reconstruct interchange at NC 51 (Matthews Township Parkway). This is a toll project (express lanes only). | 3.23 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509D | Not Funded | NHP, T(M) | NOT FUNDED | 92299000 | NOT FUNDED | 10300000 | NOT FUNDED | 202205000 | NOT FUNDED |  | 304804000 | SEGMENTS C14, M3
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | Wallace Lane to SR 3356 (Sardis Road). | Construct additional general purpose and express lanes. Construct express lane interchange at Sardis Road. This is a toll project (express lanes only). | 2.45 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509C | Not Funded | NHP, T(M) | NOT FUNDED | 39199000 | NOT FUNDED | 5600000 | NOT FUNDED | 70349000 | NOT FUNDED |  | 115148000 | SEGMENT M2
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | West of Idlewild Road to I-485. | Upgrade roadway to expressway with express lanes and construct improvements on parallel routes. | 6.62 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509
Mecklenburg | US 74 (Independence Boulevard) | NCDOT | West of SR 3143 (Idlewild Road) to Wallace Lane. | Construct additional general purpose and express lanes. Construct express lane interchange on west side of Conference Drive. This is a toll project (express lanes only). | 0.95 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509B | Statewide Mobility | NHP, T(M) | 2030 | 8499000 | 2030 | 2100000 | 2033 | 75100000 |  |  | 85699000 | SEGMENT M1
Mecklenburg | Various | NCDOT | Krefeld Drive, Arequipa Drive, and Independence Pointe Parkway. | Construct roadway improvements, part on new location. | 3.39 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509E | Not Funded | T | NOT FUNDED | 43200000 | NOT FUNDED | 3500000 | NOT FUNDED | 69400000 | NOT FUNDED |  | 116100000 | SEGMENTS C3, C4, C5, C7B, C12
Mecklenburg |  | NCDOT |  |  |  | Highway | Transition | 10 | Charlotte Regional TPO | U-2507AA | Pre-STI (Transition) | [10 empty] | IMPROVEMENTS CONSTRUCTED UNDER U-2507A
Mecklenburg |  | NCDOT |  |  | 1.1 | Highway | Transition | 10 | Charlotte Regional TPO | U-4713B | Pre-STI (Transition) | [10 empty] | COMPLETE
Mecklenburg | I-77 | NCDOT | Griffth Street (Exit 30) interchange. | Construct roundabouts at northbound and southbound ramp termini. | 1 | Highway | Transition | 10 | Charlotte Regional TPO | I-4750AC | Exempt | [10 empty] | COMPLETE
Mecklenburg | Northcross Drive Extension | NCDOT | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Highway | Transition | 10 | Charlotte Regional TPO | U-5108 | Pre-STI (Transition) | BA, BGANY, BGDA, L(M), T(M) | 2020 | 3500000 |  |  | 2024 | 17642000 | 2020 | 960000 | 22102000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP.
Mecklenburg | SR 2975 (Sugar Creek Road) | NCDOT | North Carolina Railroad / Norfolk Southern Railway Crossing 715 352H in Charlotte. | Construct grade separation. Close Craighead Road Crossing 715 352H. |  | Highway | Transition | 10 | Charlotte Regional TPO | U-5008 | [11 empty] | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS
Mecklenburg | SR 4979 (Ballantyne Commons Parkway-McKee Road) | CHARLOTTE | NC 16 (Providence Road) intersection in Charlotte. | Construct additional left turn lane on SR 4979 (Ballantyne Commons Parkway-McKee Road) and a second left turn lane on southbound NC 16. |  | Highway | Transition | 10 | Charlotte Regional TPO | C-5534 | Exempt | BGDA, T(M) |  |  |  |  | 2020 | 640000 |  |  | 640000 | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES.
Mecklenburg | US 21 | NCDOT | SR 2136 (Gilead Road) intersection in Huntersville. | Construct intersection improvements, including bicycle and pedestrian accommodations. | 0.5 | Highway | Transition | 10 | Charlotte Regional TPO | U-5114 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Mecklenburg | Charlotte Area Transit System (CATS) |  | Systemwide | Acquire battery-electric buses, hybrid buses, bus charges, management systems, training, and equipment. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0035 | Public Transit | 5339(b), L | [6 empty] | 2025 | 12759000 | 12759000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Lynx Blue Line near Iverson Way in South Charlotte | Add a light rail station. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TP-5156 | Public Transit | L | [6 empty] | 2021 | 7582000 | 7582000 | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION.
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | South Tryon Street Garage | Funding to service debt. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TD-4701 | Public Transit | 5307, L, S |  |  |  |  | 2025 | 12658000 |  |  | 12658000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for city lynx gold line - American rescue plan small starts. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0024 | Public Transit | 5309 | [6 empty] | 2022 | 11122000 | 11122000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TQ-9033 | Public Transit | 5310, L, L(M) | [6 empty] | 2025 | 15759000 | 15759000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding to purchase electric buses. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TM-0042 | Public Transit | CMAQ, L, S | [6 empty] | 2023 | 5480000 | 5480000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Purchase expansion vanpool. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0014 | Public Transit | 5307, L, S | [6 empty] | 2021 | 174000 | 174000 | "L" REFLECTS CATS CAPITAL FUND
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Purchase replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-4710 | Public Transit | 5307, 5339, L, S | [6 empty] | 2026 | 80212000 | 80212000 | "L" REFLECTS CATS CAPITAL PROGRAM
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Purchase replacement paratransit vehicle. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-4711 | Public Transit | 5307, L, S | [6 empty] | 2025 | 12427000 | 12427000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Purchase replacement van for vanpool. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-4960 | Public Transit | 5307, L, S | [6 empty] | 2020 | 3279000 | 3279000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Safety and security minimum 1 % set aside |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TS-5107 | Public Transit | 5307, L | [6 empty] | 2025 | 6165000 | 6165000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Transit Center | Upgrade facility. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TD-4702 | Public Transit | 5307, L, S |  |  |  |  | 2020 | 720000 |  |  | 720000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Various locations | Construct fixed guideway. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TE-4901 | Public Transit | 5309, L, S |  |  |  |  | 2020 | 112368000 |  |  | 112368000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Various locations | Perform rapid transit corridor studies. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TE-4902 | Public Transit | [10 empty] | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | NCDOT | Fixed guideway | Funding for bridge inspections and emergency repairs. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-5102B | Public Transit | FMOD, L |  |  |  |  | 2020 | 4123000 |  |  | 4123000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | NCDOT | Systemwide | Funding for bridge inspections and repairs. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-5102A | Public Transit | 5307, L, S |  |  |  |  | 2025 | 2120000 |  |  | 2120000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | NCDOT | Systemwide | Major investment study/alternative analysis for bus rapid transit extension to Research Triangle Park (RTP) and Clayton. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-4901 | Public Transit | 5337, L, S | [6 empty] | 2020 | 7854000 | 7854000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | NCDOT | Systemwide | STATE OF GOOD REPAIR - BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-5104B | Public Transit | 5307, 5337, L, S | [6 empty] | 2020 | 15882000 | 15882000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE | Systemwide | Purchase two electric buses for Ballantyne - I-485 service. |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0056 | Exempt | CRPDA, L |  |  |  |  | 2026 | 2188000 |  |  | 2188000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | North Davidson and South Tryon bus garages | Install electric bus chargers. |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0032 | Exempt | CRPDA, L |  |  |  |  | 2025 | 200000 |  |  | 200000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 10 | Charlotte Regional TPO | TO-5137 | Public Transit | SMAP | [6 empty] | 2020 | 75312000 | 75312000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CATS | Systemwide. | Acquire new light rail vehicles. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0065 | Public Transit | 5307, DP, L | [6 empty] | 2027 | 51350000 | 51350000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Charlotte Transportation Center in Uptown Charlotte | Rebuild CATS main transit hub. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0041 | Public Transit | CMAQ, DP, L |  |  |  |  | 2024 | 85718000 | 2023 | 2708000 | 88426000 | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000.
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for agency administration for 5310 Program. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TQ-7009 | Public Transit | 5310 | [6 empty] | 2026 | 1246000 | 1246000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Plan new and replacement circulator routes with new on-demand strategy of micro-transit zones to reduce travel times and improve connectivity to high-frequency routes at mobility hubs. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0040 | Public Transit | ARP | [6 empty] | 2023 | 1500000 | 1500000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE REGIONAL | Various locations | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TQ-6597 | Public Transit | 5310, L | [6 empty] | 2020 | 3720000 | 3720000 | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
Mecklenburg | Mecklenburg Transit System |  | Systemwide | Funding for demand response vendor trips, preventative maintenance expenses and security related software. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0056 | Public Transit | 5307, L | [6 empty] | 2024 | 1243000 | 1243000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Lynx Silver Line light rail | Funding for planning. | 28.84 | Public Transportation (Transit) | Planning | 10 | Charlotte Regional TPO | TU-0001 | Public Transit | 5307, L | [6 empty] | 2019 | 55000000 | 55000000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for Lynx Silver Line TOD planning in cooperation with CATS, CRTPO, and GCLMPO. |  | Public Transportation (Transit) | Planning | 10 | Charlotte Regional TPO | TP-5159 | Public Transit | 5303, L | [6 empty] | 2023 | 1909000 | 1909000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for planning assistance. |  | Public Transportation (Transit) | Planning | 10 | Charlotte Regional TPO | TP-5114 | Public Transit | 5303, 5307, L, S | [6 empty] | 2020 | 3235000 | 3235000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engineers, farebox, etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-4726 | Public Transit | 5307, 5337, FMOD, L | [6 empty] | 2025 | 6703000 | 6703000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Funding to service vehicles. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-4827 | Public Transit | [10 empty] | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Various locations | Funding for light rail vehicle overhaul. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-5118B | Public Transit | 5307, 5337, L | [6 empty] | 2025 | 58995000 | 58995000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Various locations | Funding for preventative maintenance for rail, bus, and facilities. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-5119 | Public Transit | 5307, L | [6 empty] | 2025 | 10211000 | 10211000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Various locations | Funding for state of good repair - rail. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-5118A | Public Transit | 5337, L, S | [6 empty] | 2025 | 26315000 | 26315000 | FUNDS AUTHORIZED IN PROGRESS
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Various locations | Purchase battery electric buses and charging stations. Funding for onsite training and startup support and testing. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-0010 | Public Transit | 5339, L | [6 empty] | 2021 | 14896000 | 14896000
Mecklenburg | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | I-77 and Hambright Road Park | Construct park and ride lot and transfer facility. |  | Public Transportation (Transit) | STI (Prioritization) | 10 | Charlotte Regional TPO | TA-6724 | Division 10 | BGDA, CMAQ, L(M), T(M) | 2025 | 1262000 |  |  | 2025 | 9906000 | 2025 | 1513000 | 12681000 | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS
Mecklenburg | Mecklenburg Transportation | MECKLENBURG COUNTY | Systemwide | Expand paratransit fleet by purchasing additional buses. |  | Public Transportation (Transit) | STI (Prioritization) | 10 | Charlotte Regional TPO | TA-6673 | Division 10 | O, T | [6 empty] | 2021 | 5000000 | 5000000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
Mecklenburg | Various | CHARLOTTE | Mecklenburg County Air Quality - Grants to Replace Aging Diesel Engines (GRADE). | Replace, repower, or retrofit aging diesel vehicles and equipment. |  | Public Transportation (Transit) | Transition | 10 | Charlotte Regional TPO | C-5536 | Exempt | CMAQ |  |  |  |  | 2021 | 139000 |  |  | 139000 | COMPLETE.
Mecklenburg | Various | NCDOT | Charlotte Railyard; Pineville Railyard. | Implement Grants to Replace Aging Diesel Engines (GRADE). |  | Rail | Locally Selected | 10 | Charlotte Regional TPO | RL-0002 | Exempt | CMAQ, L(M) |  |  |  |  | 2025 | 5450000 |  |  | 5450000
Mecklenburg | Charlotte | CHARLOTTE | Orr Road | Close and replace existing Orr Road at-grade rail crossing and replace with a new grade-separated crossing. |  | Rail | Other | 10 | Charlotte Regional TPO | RO-0001 | Exempt | DP, L(M) | [6 empty] | 2026 | 4630000 | 4630000
Mecklenburg | Piedmont and Northern Railroad | NCDOT | Various locations | Relocate thrift depot. |  | Rail | Other | 10 | Charlotte Regional TPO | P-5200EA | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Mecklenburg | Piedmont and Northern Railroad | NCDOT | Various locations | Stabilize thrift depot. |  | Rail | Other | 10 | Charlotte Regional TPO | P-5200EB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Mecklenburg | Piedmont Corridor | NCDOT | CRISP Charlotte Maintenance Facility. | Track extension and shop building. |  | Rail | Other | 10 | Charlotte Regional TPO | P-2918F | [11 empty] | IN PROGRESS
Mecklenburg | SR 2623 (Trailer Drive) | NCDOT | Norfolk Southern (Crossing Number 910 618A, MP O4.11) | Construct at grade crossing improvements. |  | Rail | Other | 10 | Charlotte Regional TPO | P-5754 | Exempt | O |  |  |  |  | 2022 | 1200000 | 2020 | 50000 | 1250000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN
Mecklenburg | Pecan Avenue | NCDOT | CSX Crossing 631391N in Charlotte. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010D | Division 10 | RR |  |  |  |  | 2026 | 388000 |  |  | 388000
Mecklenburg | Pecan Avenue | NCDOT | Norfolk Southern Crossing 716055T in Pineville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010E | Division 10 | RR |  |  |  |  | 2027 | 451000 |  |  | 451000
Mecklenburg | SR 2805 (Harrisburg Road) | NCDOT | ACWR Crossing 726808Y in Charlotte. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2410C | Division 10 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Mecklenburg | SR 2940 (Eastway Drive) | NCDOT | ACWR Crossing 726797N in Charlotte. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2410B | Division 10 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Mecklenburg | Tipperary Place | NCDOT | ACWR Crossing 726798V in Charlotte. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2410D | Division 10 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Mecklenburg | Charlotte Gateway Station | NCDOT | Charlotte | Update and maintain Charlotte Gateway Station. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705 | [11 empty] | DP REPRESENTS FEDERAL PRIIA GRANT AWARD = $2,578,000
Mecklenburg | Charlotte Gateway Station | NCDOT | Charlotte Junction. | Construct WYE connection track. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705A | Statewide Mobility | DP, T | 2021 | 500000 |  |  | 2023 | 13000000 |  |  | 13500000 | UNDER CONSTRUCTION.
Mecklenburg | Charlotte Gateway Station | NCDOT | Various locations | Acquire right-of-way. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705B | Region E | [10 empty] | UNDER CONSTRUCTION.
Mecklenburg | Charlotte Gateway Station | NCDOT | Various locations | Install platform and canopy. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705BB | Region E | [10 empty] | UNDER CONSTRUCTION.
Mecklenburg | Charlotte Gateway Station | NCDOT | Various locations | Install track, structure, and signals. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705BA | Region E | [10 empty] | UNDER CONSTRUCTION.
Mecklenburg | Clanton Road | NCDOT | End point of Clanton Road to US 29 / US 74 (Wilkinson Boulevard). | Extend roadway. Construct grade separation of Norfolk Southern Railroad and close the Donald Ross Road crossing. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5730 | Region E | O, T | 2030 | 13600000 | 2030 | 1200000 | 2034 | 62801000 |  |  | 77601000 | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN.
Mecklenburg, Cabarrus | I-85; I-77; I-277; I-485; and US 74 | NCDOT | Various locations. | Install wrong way pavement markings and signs. |  | Highway | Safety | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2010M | Statewide Mobility | HSIP |  |  |  |  | 2024 | 783000 |  |  | 783000
Mecklenburg, Cabarrus | NC 73 (Davidson Highway) | NCDOT | East of SR 2693 (Davidson-Concord Road) to east of SR 1394 (Popular Tent Road) in Mecklenburg County. | Widen to multi-lanes. | 2.35 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | R-5706A | Region E | NHP, T(M) | 2025 | 12000000 | 2025 | 6200000 | 2029 | 53100000 |  |  | 71300000
Mecklenburg, Cabarrus | SR 2467 (Mallard Creek Road) / SR 1445 (Derita Road) | NCDOT | I-485 to SR 2894 (Concord Mills Boulevard) | Widen to six lanes. | 0.87 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | U-6032 | Division 10 | T | 2022 | 14500000 | 2025 | 2514000 | 2029 | 45595000 |  |  | 62609000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $14M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
Mecklenburg, Cabarrus | Charlotte Area Transit System (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | Systemwide | Purchase six buses. |  | Public Transportation (Transit) | STI (Prioritization) | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | TA-6672 | Region E | O, T | [6 empty] | 2020 | 6000000 | 6000000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
Mecklenburg, Iredell | I-77 | NCDOT | Mile marker 11.0 to mile marker 20.0 and mile marker 24.5 to mile marker 37. | Rehabilitate pavement. | 21.27 | Highway | Interstate Maintenance | 10, 12 | Charlotte Regional TPO | I-5992 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Mecklenburg, Iredell | I-77 | NCDOT | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | I-6065 | Exempt | BA, BGDA, T(DA), T(M) | 2027 | 100000 |  |  | 2029 | 45080000 | 2020 | 1820000 | 47000000 | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
Mecklenburg, Iredell, Union | Various | NCDOT | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | C-5613 | Exempt | CMAQ, L(M) | 2020 | 518000 |  |  | 2020 | 3108000 | 2020 | 1554000 | 5180000 | IN PROGRESS.
Mecklenburg, Lincoln | NC 73 | NCDOT | NC 16 in Lincoln County to SR 5544 (West Catawba Avenue) in Huntersville. | Widen to multi-lanes. | 9.7 | Highway | STI (Prioritization) | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | R-5721 | [11 empty] | COORDINATE WITH U-5765.
Mecklenburg, Union, Iredell | Various | NCDOT | Locations in the Charlotte Regional Transportation Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 10, 12 | Charlotte Regional TPO | U-5544 | Division 10, 12 | L(M), TADA |  |  |  |  | 2024 | 24694000 |  |  | 24694000
Mecklenburg, Union, Iredell | Various | NCDOT | Charlotte Regional Transportation Planning Organization (CRTPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | U-4744 | Division 10, 12 | BGDA, L(M) |  |  |  |  | 2024 | 194877000 |  |  | 194877000
Mecklenburg, Union, Iredell | Various | NCDOT | Charlotte Regional Transportation Planning Organization (CRTPO) area. | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | HL-0092 | Exempt | CRPDA, L(M) |  |  |  |  | 2024 | 1433000 |  |  | 1433000
Mecklenburg, Union, Iredell | Various | NCDOT | Charlotte Regional Transportation Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | U-4950 | Division 10, 12 | BGDA, L(M) | [6 empty] | 2024 | 18629000 | 18629000 | FORMERLY U-9999C - IN PROGRESS
Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Lincoln, Nash, Chatham, Davie, Edgecombe, Franklin, Granville, Haywood, Person, Swain | North Carolina Department of Environment and Natural Resources | NCDOT | Statewide | North Carolina air awareness outreach program to provide education and produce daily air quality forecasts. |  | Highway | Other | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban Area MPO, Roc | HO-0009 | Exempt | CMAQ, L(M), O | [6 empty] | 2022 | 1604000 | 1604000 | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS
Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Nash, Davie, Edgecombe, Granville, Haywood | Various | NCDOT | Locations in Divisions 4, 5, 7, 9, and 10. | Install statewide ITS devices. |  | Highway | Other | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Winston-Salem Area TPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MPO, Kerr-Tar RPO, Lan | HO-0005 | Exempt | CMAQ, T(M) |  |  |  |  | 2022 | 21605000 |  |  | 21605000 | UNDER CONSTRUCTION.
Mitchell | SR 1193 (Ledger School Road) | MITCHELL COUNTY | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 13 | High Country RPO | BN-0016 | Exempt | CRPLT5, HF(M) | 2026 | 10000 |  |  | 2028 | 1840000 | 2025 | 315000 | 2165000 | HIGHWAY FUNDS ARE CONTIGENCY FUNDS
Mitchell | SR 1260 (South Mitchell Avenue) | BAKERSVILLE | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 13 | High Country RPO | BN-0017 | Exempt | CRPLT5, HF(M) | 2026 | 110000 | 2026 | 80000 | 2028 | 1100000 | 2025 | 291000 | 1581000 | HIGHWAY FUNDS ARE CONTIGENCY FUNDS
Mitchell | SR 1106 (Lynn Gap Road) | NCDOT | Bridge 600207 over Grassy Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | High Country RPO | B-6013 | Division 13 | BGOFF | 2022 | 40000 |  |  | 2022 | 800000 |  |  | 840000 | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016
Mitchell | NC 226 | NCDOT | SR 1250 (Snow Creek Road) to NC 261. | Upgrade guardrail. | 3.36 | Highway | Safety | 13 | High Country RPO | HS-2013D | Region G | HSIP |  |  |  |  | 2021 | 272000 |  |  | 272000 | COMPLETE
Mitchell | NC 226 | NCDOT | US 19E to NC 261 near Spruce Pine. | Install guardrail. | 9.4 | Highway | Safety | 13 | High Country RPO | HS-2013L | Region G | HSIP |  |  |  |  | 2023 | 590000 |  |  | 590000
Mitchell | NC 226 | NCDOT | US 19E to SR 1250 (Snow Creek Road). | Upgrade guardrail. | 6.04 | Highway | Safety | 13 | High Country RPO | HS-2013B | Region G | HSIP |  |  |  |  | 2021 | 290000 |  |  | 290000 | COMPLETE
Mitchell | NC 226 | NCDOT | Various locations in Bakersville and Spruce Pine | Install rumble stripes and 6" long life pavement markings. |  | Highway | Safety | 13 | High Country RPO | HS-2413F | Region G | HSIP, T(M) |  |  |  |  | 2026 | 345000 |  |  | 345000
Mitchell | Mitchell County Transit |  | Mitchell County Transit | Construct new facility. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | High Country RPO | TN-0002 | Exempt | CRPLT5, L(M) | [6 empty] | 2025 | 5000000 | 5000000
Mitchell | Mecklenburg Transportation | MITCHELL COUNTY TRANSPORTATION | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 13 | High Country RPO | TK-6146 | Public Transit | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
Montgomery | NC 731 (East Allenton Street) | MOUNT GILEAD | Existing sidewalk on NC 731 to Stanbeck Park in Mt. Gilead | Construct sidewalk. | 0.19 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5899 | Division 8 | L(M), TALT5 |  |  |  |  | 2023 | 277000 |  |  | 277000
Montgomery | NC 134 (North Main Street); SR 1005 (South Main Street) | TROY | SR 1323 (Okeewemee Road) to Barnhill Street in Troy | Construct sidewalks. | 2.37 | Bike & Ped | Transition | 8 | Piedmont Triad RPO | EB-5521 | Pre-STI (Transition) | BGANY, T |  |  |  |  | 2026 | 2200000 |  |  | 2200000 | UNDER CONSTRUCTION BY TOWN OF TROY
Montgomery | I-73 / I-74 | NCDOT | Montgomery County line to NC 211. | Rehabilitate pavement. | 8.92 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947A | Statewide Mobility | BGIM, T(M) |  |  |  |  | 2027 | 19800000 |  |  | 19800000
Montgomery | I-73 / I-74 | NCDOT | NC 211 to NC 24 / NC 27. | Rehabilitate pavement. | 5.05 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947B | Statewide Mobility | BGIM, T(M) |  |  |  |  | 2023 | 6900000 |  |  | 6900000 | UNDER CONSTRUCTION - LET WITH I-5946A
Montgomery | I-73 / I-74 | NCDOT | NC 24 / NC 27 to Randolph County line. | Rehabilitate pavement. | 10.51 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947C | Statewide Mobility | BGIM, T(M) |  |  |  |  | 2028 | 17600000 |  |  | 17600000
Montgomery | I-73 / I-74 / US 220 | NCDOT | Montgomery County line To Randolph County line. | Rehabilitate pavement. | 24.5 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947
Montgomery | Candor | NCDOT | Pilot Travel Center | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 8 | Piedmont Triad RPO | HV-0001D | Division 8 | NEVI, O, O(M), S(M) |  |  |  |  | 2025 | 741000 |  |  | 741000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC
Montgomery | NC 109 | NCDOT | NC 73 (North Main Street) in Mt. Gilead to NC 24 / NC 27. | Upgrade roadway, including paved shoulders, turn lanes and signals. | 8 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826
Montgomery | NC 109 | NCDOT | NC 73 (North Main Street) in Mt. Gilead to SR 1127 (Hearne Farm Road) | Upgrade roadway, including paved shoulders, turn lanes, and signals. |  | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826A | Not Funded | T | NOT FUNDED | 3700000 | NOT FUNDED | 250000 | NOT FUNDED | 9200000 | NOT FUNDED |  | 13150000
Montgomery | NC 109 | NCDOT | SR 1127 (Hearne Farm Road) to SR 1174 (Pee Dee Road) | Upgrade roadway. | 2.61 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826B | Division 8 | BGLT5, T, T(M) | 2023 | 438000 | 2024 | 240000 | 2027 | 14035000 |  |  | 14713000 | RIGHT-OF-WAY IN PROGRESS
Montgomery | NC 109 | NCDOT | SR 1174 (Pee Dee Road) to NC 24 / NC 27 | Upgrade roadway, including paved shoulders, turn lanes, and signals. |  | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826C | Not Funded | T | NOT FUNDED | 3000000 | NOT FUNDED | 299000 | NOT FUNDED | 18000000 | NOT FUNDED |  | 21299000
Montgomery | NC 24 / NC 27 | NCDOT | NC 73 to Troy Bypass. | Widen to a four lane divided facility. | 9.1 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-2527 | Region E | BGLT5, T | 2019 | 854000 |  |  | 2027 | 131500000 | 2019 | 7802000 | 140156000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
Montgomery | NC 24 / NC 27 | NCDOT | Troy Bypass, west of SR 1138 (Dairy Road) to east of Little River. | Widen to four lanes, part on new location. | 5.42 | Highway | Transition | 8 | Piedmont Triad RPO | R-0623 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Montgomery | Eldorado Street | NCDOT | ACWR Crossing 728934A in Troy. | Improve crossing. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Piedmont Triad RPO | RX-2408B | Division 8 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Montgomery | US 220 Alternate (Main Street) | NCDOT | ACWR Crossing 466027X in Star. | Improve crossing. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Piedmont Triad RPO | RX-2408A | Division 8 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Moore | SOP | MOORE COUNTY AIRPORT (SOP) | Moore County Airport | Construct hangar taxiways and internal airfield service road. |  | Aviation | STI (Prioritization) | 8 | Sandhills MPO | AV-5855 | Division 8 | T |  |  |  |  | 2021 | 2900000 |  |  | 2900000 | UNDER CONSTRUCTION
Moore | Aberdeen | SANDHILLS MPO | Poplar Street from Peach Avenue to Providence Place/Johnson Street | Construct sidewalk. |  | Bike & Ped | Locally Selected | 8 | Sandhills MPO | BL-0176 | Exempt | CRPDA, L(M) | [6 empty] | 2026 | 118000 | 118000
Moore | Knoll Road | SOUTHERN PINES | NC 2 (Midland Road) to SR 1843 (Airport Road) near Southern Pines. | Construct multi-use path along Knoll Road to connect with existing Southern Pines Greenway on Midland Road. | 1.44 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-5864 | Division 8 | L(M), TA50200 |  |  |  |  | 2026 | 3600000 | 2023 | 190000 | 3790000
Moore | SR 1203 (Johnson Street) | ABERDEEN | US 15 / US 501 to Mike Place in Aberdeen | Construct sidewalks. | 0.39 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-5869 | Division 8 | L(M), TA50200 | 2023 | 30000 |  |  | 2027 | 300000 |  |  | 330000
Moore | SR 2055 (North Poplar Street) | ABERDEEN | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-6001 | Division 8 | L(M), TA50200 | 2024 | 34000 |  |  | 2027 | 340000 | 2023 | 26000 | 400000 | COORDINATE WITH U-5815
Moore | US 1 / US 15 / US 501 (Sandhills Boulevard) | NCDOT | Maple Avenue in Aberdeen. | Construct mid-block crosswalk, median refuge island, and install pedestrian signal. | 0.26 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-5741 | Division 8 | L(M), TA50200 |  |  |  |  | 2023 | 312000 |  |  | 312000
Moore | NC 22 | NCDOT | Bridge 620062 over Nicks Creek in Carthage. | Replace bridge. | 0.25 | Highway | Bridges | 8 | Sandhills MPO | BR-0035 | Region E | NHPB, T(M) |  |  |  |  | 2022 | 4100000 |  |  | 4100000 | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION
Moore | Airport Road | SANDHILLS MPO | Thorne Road to Knoll Road in Southern Pines | Improve roadway. |  | Highway | Locally Selected | 8 | Sandhills MPO | HL-0175 | Exempt | CRPDA, L(M) | [6 empty] | 2026 | 293000 | 293000
Moore | NC 5 | NCDOT | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Highway | Safety | 8 | Sandhills MPO | HS-2008F | Region E | HSIP, T | 2026 | 500000 | 2027 | 250000 | 2028 | 3550000 |  |  | 4300000
Moore | SR 2055 (North Poplar Street) | NCDOT | West Maple Avenue intersection in Aberdeen. | Install all-way stop. | 0.5 | Highway | Safety | 8 | Sandhills MPO | W-5808C | Division 8 | HSIP, T(M) | 2021 | 2000 |  |  | 2021 | 16000 |  |  | 18000 | UNDER CONSTRUCTION.
Moore | US 1 | NCDOT | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Highway | Safety | 8 | Central Pines RPO | HS-2408B | Statewide Mobility | HSIP, T(M) | 2026 | 24000 | 2026 | 24000 | 2027 | 824000 |  |  | 872000
Moore | NC 211 | NCDOT | NC 73 in West End to west of SR 1241 (Holly Grove School Road) | Clearing, grubbing, and erosion control. | 4.09 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5726A | Region E | T |  |  |  |  | 2022 | 5679000 |  |  | 5679000
Moore | NC 211 | NCDOT | NC 73 in west end to west of SR 1241 (Holly Grove School Road). | Widen to a four lane divided facility. | 4.09 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5726 | Region E | T |  |  |  |  | 2025 | 49520000 |  |  | 49520000 | UNDER CONSTRUCTION
Moore | NC 24 / NC 27 | NCDOT | Courthouse west of NC 22 (McNeill Street) to US 15 / US 501 in Carthage. | Widen to three lanes with curb and gutter and bicycle / pedestrian accommodations. | 1.35 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-3628 | Region E | NHP, T | 2023 | 2275000 |  |  | 2025 | 6900000 |  |  | 9175000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929
Moore | NC 24 / NC 27 | NCDOT | SR 1006 (Glendon-Carthage Road) intersection in Carthage. | Construct intersection improvements at US 15 / US 501 and each adjacent intersections of each facility | 0.5 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5929 | Division 8 | T | 2027 | 500000 | 2027 | 300000 | 2029 | 4900000 |  |  | 5700000 | COORDINATE WITH U-3628
Moore | NC 5 | NCDOT | US 1 in Aberdeen to the intersection of Trotter Drive / Blake Boulevard in Pinehurst. | Widen to four lane divided facility from US 1 to Linden Road and a three lane facility from Linden Road to Trotter Drive. | 3.94 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5756 | Region E | T | 2023 | 8600000 | 2023 | 13200000 | 2025 | 119700000 |  |  | 141500000 | RIGHT-OF-WAY IN PROGRESS
Moore | NC 5 (Beulah Hill Road) | NCDOT | Trotter Drive / Blake Boulevard to NC 211 in Pinehurst. | Add turn lane, signal improvements, and other operational improvements along corridor as appropriate. | 2.76 | Highway | STI (Prioritization) | 8 | Sandhills MPO | R-5892 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1892000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43200000 |  |  | 53292000
Moore | NC 690 (Lobelia Road) | NCDOT | US 1 in Vass to Cumberland County line. | Upgrade roadway, to include turn lanes at various locations and some realignment. | 11.75 | Highway | STI (Prioritization) | 8 | Fayetteville Area MPO, Central Pines RPO | R-5824 | Region E | BGLT5, T(M) | 2025 | 1800000 | 2026 | 1500000 | 2028 | 14300000 |  |  | 17600000 | RIGHT-OF-WAY IN PROGRESS
Moore | US 1 (Sandhills Boulevard) | NCDOT | Knight Street in Aberdeen to SR 2080 (Old US 1) in Southern Pines | Relocate water transmission line. | 2.36 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815BA | Region E | T |  |  |  |  | 2023 | 17900000 |  |  | 17900000 | UNDER CONSTRUCTION
Moore | US 1 (Sandhills Boulevard) | NCDOT | Knight Street in Aberdeen to SR 2080 (Old US 1) in Southern Pines, to include SR 1112 (Roseland Road) realignment at US 1 and radii improvement at US 15 / US 501 / NC 211 | Construct access management improvements, realignment, and radii improvements. | 2.36 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815B | Region E | T | 2023 | 6650000 |  |  | 2025 | 154300000 |  |  | 160950000 | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION INCLUDES U-5814.
Moore | US 1 (Sandhills Boulevard) | NCDOT | SR 1112 (Roseland Road) in Aberdeen to old US 1 in Southern Pines. | Improve access management. | 2.9 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815 | Region E
Moore | US 1 (Sandhills Boulevard) | NCDOT | SR 1112 (Roseland Road) to Knight Street | Construct access management improvements. | 0.58 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815A | Region E | BGANY, T(M) | 2029 | 4700000 | 2029 | 3200000 | 2032 | 12700000 |  |  | 20600000
Moore | US 15 / US 501 | NCDOT | NC 2 and NC 211 traffic circle in Pinehurst to NC 73. | Widen to multi-lanes. | 3.7 | Highway | STI (Prioritization) | 8 | Sandhills MPO, Central Pines RPO | R-5927 | Division 8 | T | 2028 | 1300000 | 2028 | 3900000 | 2031 | 48100000 |  |  | 53300000
Moore | US 15 / US 501 | NCDOT | SR 1905 (Voit Gilmore Lane) in Southern Pines to SR 1208 (Page Road) in Pinehurst. | Upgrade SR 1208 (Page Road) intersection and construct improvements to Pinehurst traffic circle and approaches. | 2.3 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5976 | Division 8 | T | 2028 | 28900000 | 2028 | 970000 | 2031 | 51100000 |  |  | 80970000
Moore | US 15 / US 501 / NC 211 | NCDOT | SR 1205 / SR 1309 (Morganton Road) in Southern Pines. | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 8 | Sandhills MPO | R-5891 | Region E | BG50200, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39400000 |  |  | 44200000
Moore | US 15 / US 501 / NC 211 | NCDOT | US 1 (Sandhills Boulevard) in Aberdeen to Brucewood Road in Southern Pines. | Improve access management. | 1.24 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5814 | Region E | T | 2023 | 11500000 | 2023 | 1250000 |  |  |  |  | 12750000 | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING.
Moore | LS (South Street) | NCDOT | Crossing 722526U in Aberdeen | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Sandhills MPO | RX-2008B | Division 8 | RR |  |  |  |  | 2026 | 1832000 |  |  | 1832000
Moore, Hoke, Lee | Various | NCDOT | National Highway System and primary routes in Division 8 District 2. | Upgrade guardrail. |  | Highway | Safety | 8 | Central Pines RPO, Lumber River RPO, Sandhills MPO | HS-2008B | Region E | HSIP, T(M) |  |  |  |  | 2021 | 250000 |  |  | 250000 | UNDER CONSTRUCTION
Nash | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | ROCKY MOUNT | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Bike & Ped | Locally Selected | 4 | Rocky Mount Urban Area MPO | C-5549 | Exempt | CMAQ, CRPDA, L(M) | 2026 | 200000 |  |  | 2027 | 1373000 |  |  | 1573000
Nash | US 301 Business (Church Street) |  | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5761B | Division 4 | L(M), TA50200 | 2030 | 181000 | 2030 | 619000 | 2031 | 4000000 | 2029 | 150000 | 4950000
Nash | US 301 Business (Church Street) and US 301 Business (Franklin Street) |  | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5761A | Division 4 | L(M), TA50200 | 2027 | 269000 | 2027 | 181000 | 2028 | 8500000 | 2026 | 150000 | 9100000
Nash | US 301 Business (Church Street) and US 301 Business (Franklin Street) | ROCKY MOUNT | NC 97 (Raleigh Boulevard) to US 64 in Rocky Mount. | Construct streetscape improvements including sidewalk and bike lanes. | 1.69 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5761 | Division 4
Nash | US 64 Business (Sunset Avenue) | ROCKY MOUNT | SR 1836 (May Drive) to Northbound US 301 Business (Church Street) in Rocky Mount. | Install pedestrian signals. | 1.7 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5711 | Division 4 | L(M), TA50200 |  |  |  |  | 2024 | 580000 |  |  | 580000
Nash | US 64 Business (Thomas Street) | ROCKY MOUNT | SR 1005 (East Raleigh Boulevard) to US 64 Business (Sunset Avenue) in Rocky Mount | Add pedestrian signals. |  | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5905 | Division 4 | BG50200, L(M) |  |  |  |  | 2027 | 1400000 |  |  | 1400000
Nash | NC 33 | NCDOT | Bridge 630041 over I-95 | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0036 | Highway Fund | HFB |  |  |  |  | 2021 | 4700000 |  |  | 4700000 | UNDER CONSTRUCTION.
Nash | NC 581 | NCDOT | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5947 | Region A | NHPB, T(M) | 2021 | 400000 | 2021 | 138000 | 2023 | 7162000 |  |  | 7700000 | UNDER CONSTRUCTION.
Nash | SR 1403 (Cooper Road) | NCDOT | Bridge 630080 over Gideon Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0116 | Highway Fund | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
Nash | SR 1510 | NCDOT | Bridge 630224 over I-95 | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0039 | Highway Fund | HFB |  |  |  |  | 2021 | 5200000 |  |  | 5200000 | UNDER CONSTRUCTION.
Nash | SR 1522 (Halifax Road) | NCDOT | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5980 | Statewide Mobility | NHPB, T(M) | 2020 | 2100000 |  |  | 2021 | 18000000 |  |  | 20100000 | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039.
Nash | SR 1745 (Bend of the River Road) | NCDOT | Bridge 630110 over Tar River Reservoir. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Rocky Mount Urban Area MPO | HB-0038 | Division 4 | BGOFF |  |  |  |  | 2027 | 6500000 |  |  | 6500000
Nash | I-95 | NCDOT | Mile marker 137.4 to mile marker 142.1. | Rehabilitate bridge and pavement. | 3.92 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | I-5934 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2026 | 5500000 |  |  | 5500000
Nash | US 64 (Future I-87) | NCDOT | Bridges 630072 and 630074. | Rehabilitate bridge. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | I-6045A | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 520000 |  |  | 520000 | UNDER CONSTRUCTION.
Nash | US 64 (Future I-87) | NCDOT | SR 1306 (South Old Franklin Road) to SR 1603 (Old Carriage Road). | Rehabilitate pavement. | 11.12 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | I-6045 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2023 | 16660000 |  |  | 16660000 | UNDER CONSTRUCTION.
Nash | NC 43 | NCDOT | SR 1500 (Swift Creek School Road) intersection. | Realign intersection. | 0.75 | Highway | Safety | 4 | Upper Coastal Plain RPO | W-5804B | Region A | HSIP, T(M) | 2023 | 44000 |  |  | 2023 | 891000 |  |  | 935000 | UNDER CONSTRUCTION.
Nash | NC 48 | NCDOT | Waterloo Drive / Roundtree Drive and Greyson Road / Cunningham Drive intersections. | Install mini roundabouts. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004M | Region A | HSIP, T(M) |  |  |  |  | 2023 | 441000 |  |  | 441000 | UNDER CONSTRUCTION.
Nash | NC 97 | NCDOT | SR 1603 (Old Carriage Road) intersection. | Install left turn lane. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004B | Region A | HSIP, T(M) | 2022 | 86000 |  |  | 2022 | 204000 |  |  | 290000 | UNDER CONSTRUCTION.
Nash | SR 1001 (Old Bailey Highway) | NCDOT | SR 1717 (Macedonia Road / Sandy Cross Road) intersection. | Install all way stop. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004H | Division 4 | HSIP, T(M) |  |  |  |  | 2022 | 24000 |  |  | 24000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G.
Nash | SR 1544 (Halifax Road) | NCDOT | NC 97 to SR 1770 (Sunset Avenue) | Install 6-inch pavement markings and snowplowable pavement markers. | 5.22 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2404T | Division 4 | HSIP, T(M) |  |  |  |  | 2026 | 78000 |  |  | 78000
Nash | SR 1700 (Oak Level Road) | NCDOT | SR 1603 (Old Carriage Road) intersection. | Revise traffic signal. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004N | Division 4 | HSIP, T(M) |  |  |  |  | 2023 | 351000 |  |  | 351000 | UNDER CONSTRUCTION.
Nash | US 301 |  | Northern Rocky Mount Municipal limit to SR 1516 (Johnston Road) | Install 6-inch pavement markings and pavement markers. | 3.1 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2404O | Region A | HSIP, T(M) |  |  |  |  | 2026 | 48000 |  |  | 48000
Nash | US 64 (Future I-87) | NCDOT | Bridges 630019 and 630020 over Tar River. | Improve pavement. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004Q | Region A | HSIP, T(M) |  |  |  |  | 2023 | 900000 |  |  | 900000 | UNDER CONSTRUCTION.
Nash | US 64 Business (Sunset Avenue) | NCDOT | River Drive / Lake Drive intersection in Rocky Mount. | Construct various pedestrian and safety improvements. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004AA | Region A | HSIP, T(M) |  |  |  |  | 2026 | 216000 |  |  | 216000
Nash | Various | NCDOT | Secondary roads in Nash County. | Install long life pavement markings. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | HS-2404E | Division 4 | HSIP |  |  |  |  | 2025 | 2170000 |  |  | 2170000
Nash | Various | NCDOT | Various secondary roads. | Install long life pavement markings. |  | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2404R | Division 4 | HSIP, T(M) |  |  |  |  | 2027 | 1940000 |  |  | 1940000
Nash | Various | NCDOT | Various secondary roads. | Install long life pavement markings. |  | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2404S | Division 4 | HSIP, T(M) |  |  |  |  | 2027 | 1940000 |  |  | 1940000
Nash | I-95 | NCDOT | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5026 | Division 4 | L, T | 2020 | 34686000 | 2020 | 336000 | 2020 | 87636000 |  |  | 122658000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Nash | NC 43 | NCDOT | SR 1613 (Woodruff Avenue) to I-95. | Widen to multi-lanes. | 0.61 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-2561 | Division 4
Nash | NC 43 | NCDOT | SR 1613 (Woodruff Avenue) to I-95. | Widen to multi-lanes. | 1.65 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-2561C | Division 4 | BGLT5, T(M) | 2026 | 4400000 | 2026 | 3100000 | 2028 | 13600000 |  |  | 21100000
Nash | NC 43 (Benvenue Road) | NCDOT | US 64 Bypass offramp intersection in Rocky Mount | Construct roundabout. | 1 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5947 | Region A | T | 2022 | 80000 | 2022 | 800000 | 2022 | 5725000 |  |  | 6605000 | UNDER CONSTRUCTION.
Nash | NC 48 | NCDOT | NC 4 Intersection in Rocky Mount | Construct roundabout. | 0.42 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5911 | Division 4 | CRPLT5 | 2025 | 30000 | 2025 | 360000 | 2027 | 3900000 |  |  | 4290000
Nash | SR 1603 (Old Carriage Road) | NCDOT | Green Hills Road to SR 1770 (Eastern Avenue). | Widen to four lanes from Green Hills Road through US 64 bridge; widen to three lanes from south of US 64 bridge to SR 1770 (Eastern Avenue). | 1.33 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5996 | Division 4 | T | 2020 | 529000 |  |  | 2022 | 23940000 |  |  | 24469000 | UNDER CONSTRUCTION.
Nash | SR 1770 (Eastern Avenue) | NCDOT | SR 1003 (Red Oak Road) to SR (Old Carriage Road) in Rocky Mount. | Widen to multi-lanes. | 2.41 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | R-5720 | Division 4 | T | 2020 | 12252000 | 2020 | 1470000 |  |  |  |  | 13722000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026.
Nash | NC 43 / NC 48 (Benvenue Road) | ROCKY MOUNT | Jeffrey's Road Intersection in Rocky Mount. | Construct intersection improvements. | 0.5 | Highway | Transition | 4 | Rocky Mount Urban Area MPO | C-5546 | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 130000 |  |  | 130000
Nash | Tar River Transit | TAR RIVER TRANSIT | Systemwide | Construct improvements to driver's break room. |  | Public Transportation (Transit) | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | TD-5281 | Division 4 | T | [6 empty] | 2025 | 15000 | 15000
Nash, Edgecombe, Wilson | Various | NCDOT | Rocky Mount Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 4 | Rocky Mount Urban Area MPO | HL-0106 | Exempt | BGANY, CRPDA, L |  |  |  |  | 2023 | 1306000 |  |  | 1306000
Nash, Halifax | NC 43 | NCDOT | North of SR 1425 (Castalia Road) in Nash County to NC 561 in Halifax County. | Install rumble stripes. | 13.51 | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | HS-2004X | Region A | HSIP, T(M) |  |  |  |  | 2024 | 361000 |  |  | 361000 | UNDER CONSTRUCTION.
Nash, Wake, Johnston | US 264 (Future I-587) | NCDOT | The US 64 / US 264 split to the Wilson County line. | Rehabilitate pavement. | 14.27 | Highway | Interstate Maintenance | 4, 5 | Upper Coastal Plain RPO, Capital Area MPO | HI-0013 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 16500000 |  |  | 16500000
Nash, Wilson | NC 58 | NCDOT | Northern Statonsburg town limits to 0.3 miles north of SR 1622 (Evansdale Road) in Wilson County, south of SR 1314 (Thompson Chapel Church Road) in Wilson County to southern Nashville town limits in Nash County, and south of SR 1004 (Taylors Store Road) t | Install rumble stripes and pavement markings. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | HS-2004U | Region A | HSIP, T(M) |  |  |  |  | 2024 | 690000 |  |  | 690000 | UNDER CONSTRUCTION.
New Hanover | ILM | WILMINGTON INTERNATIONAL AIRPORT (ILM) | Wilmington International Airport | Expand air carrier apron. |  | Aviation | STI (Prioritization) | 3 | Wilmington Urban Area MPO | AV-5801 | Statewide Mobility | O, T |  |  |  |  | 2021 | 3940000 |  |  | 3940000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM.
New Hanover | ILM | WILMINGTON INTERNATIONAL AIRPORT (ILM) | Wilmington International Airport | Improve taxiways. |  | Aviation | STI (Prioritization) | 3 | Wilmington Urban Area MPO | AV-5798 | Statewide Mobility | O, T |  |  |  |  | 2028 | 5600000 |  |  | 5600000 | OTHER FUNDS PROVIDED BY ILM.
New Hanover | ILM | WILMINGTON INTERNATIONAL AIRPORT (ILM) | Wilmington International Airport | Rehabilitate runway. |  | Aviation | STI (Prioritization) | 3 | Wilmington Urban Area MPO | AV-5885 | Statewide Mobility | O, T |  |  |  |  | 2027 | 7500000 |  |  | 7500000 | OTHER FUNDS PROVIDED BY ILM.
New Hanover | US 76 (Causeway Drive); US 74 (West Salisbury Street) | WRIGHTSVILLE BEACH | Along US 76 (Causeway Drive) and US 74 (West Salisbury Street) in Wrightsville Beach | Install on-street bicycle lanes and pedestrian crosswalks. | 2.1 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0075 | Division 3 | BGDA, L(M) |  |  |  |  | 2024 | 2291000 | 2024 | 10000 | 2301000
New Hanover | Brooklyn Street; Navassa Park | NAVASSA | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534U | Division 3 | BGANY, BGDA, L(M) | 2025 | 40000 |  |  | 2026 | 1449000 | 2025 | 40000 | 1529000 | RIGHT-OF-WAY IN PROGRESS
New Hanover | Kerr Avenue Trail | Wilmington | Begins at Kerr Avenue and Patrick Avenue intersection heading south to Fountain drive then east to South College Road and north to Hoggard Drive in Wilmington. | Construct mult-use path. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0180 | Division 3 | BGDA, L(M) |  |  |  |  | 2027 | 3352000 |  |  | 3352000
New Hanover | NC 132 (South College Road) | New Hanover County | 17th Street to SR 1521 (Piner Road / Carolina Beach Road) | Construct multi-use path. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0181 | Division 3 | BGDA, L(M) |  |  |  |  | 2026 | 3328000 |  |  | 3328000
New Hanover | SR 1403 (Middle Sound Loop) | New Hanover County | South of Market Street from Red Cedar Road to existing trail at corner of Market Street and Middle Sound Loop Road near Wilmington. | Construct multi-use path. | 6.73 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6027 | Division 3 | L | 2021 | 500000 |  |  | 2025 | 1000000 |  |  | 1500000 | RIGHT OF WAY IN PROGRESS.
New Hanover | SR 1573 (K Avenue) | KURE BEACH | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0059 | Division 3 | BGDACV, L(M), TADA | 2025 | 270000 |  |  | 2025 | 520000 | 2023 | 423000 | 1213000
New Hanover | St. Joseph Avenue / Lewis Drive | CAROLINA BEACH | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6039 | Division 3 | BGDA, L(M), TADA | 2025 | 60000 |  |  | 2025 | 1231000 | 2021 | 747000 | 2038000
New Hanover | US 117 (College Road) | BELVILLE | SR 2048 (Gordon Road) to SR 2206 (Northchase Parkway). | Construct bicycle and pedestrian improvements. | 2.5 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0118 | Division 3 | BGDA, L, L(M) | 2025 | 513000 |  |  | 2026 | 2300000 |  |  | 2813000
New Hanover | US 17 Business (Market Street) | WILMINGTON | 21st Street in Wilmington | Construct signalized pedestrian crossing. | 0 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6028 | Division 3 | L(M), TADA |  |  |  |  | 2023 | 164000 |  |  | 164000 | UNDER CONSTRUCTION
New Hanover | Various | NEW HANOVER COUNTY | Middle Sound Loop Connector to Porters Neck Walmart Connector | Construct multi-use path. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0040 | Division 3 | L(M), TADA |  |  |  |  | 2025 | 1574000 |  |  | 1574000
New Hanover | Wilmington Rail Trail | WILMINGTON | 3rd Street to Love Grove Bridge multi-use path facility in Wilmington | Construct multi-use path. | 1.36 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0045 | Division 3 | BGDA, BGDACV, L(M) | [6 empty] | 2022 | 1219000 | 1219000
New Hanover | UNC Wilmington | NCDOT | Various locations at UNC Wilmington | Funding for multi-modal planning. |  | Bike & Ped | Other | 3 | Wilmington Urban Area MPO | M-0570S | Exempt | CRPANY, HF(M), L | [6 empty] | 2025 | 68000 | 68000
New Hanover | SR 1219 (South 17th Street) | WILMINGTON | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | Bike & Ped | STI (Prioritization) | 3 | Wilmington Urban Area MPO | EB-5600 | Division 3 | BGANY, BGDA, L(M) | 2024 | 30000 |  |  | 2027 | 3738000 | 2022 | 150000 | 3918000 | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON.
New Hanover | US 76 / US 74 | NCDOT | Bridges 640021, 640022, and 64024 in New Hanover County. | Replace bridges. | 0.9 | Highway | Bridges | 3 | Wilmington Urban Area MPO | HB-0040 | Region B | HFB | 2026 | 32200000 | 2026 | 2000000 | 2026 | 48100000 |  |  | 82300000 | PROJECT BEING DELIVERED THROUGH STRUCTURES MANAGEMENT HIGH FUND BRIDGE PROGRAM.
New Hanover | SR 1302 (North 23rd Street) | NCDOT | US 74 (Martin Luther King Jr. Parkway) to Airport Boulevard. | Widen Northbound Lane. | 0.6 | Highway | Economic Development | 3 | Wilmington Urban Area MPO | HE-0018 | Division 3 | O, T | 2025 | 400000 | 2025 | 500000 | 2027 | 1900000 | 2025 | 560000 | 3360000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FRONTIER SCIENTIFIC SOLUTIONS. O FUNDS REPRESENT WILMINGTON INTERNATIONAL AIRPORT (ILM) FUNDING.
New Hanover | I-140 | NCDOT | US 421 to I-40. | Rehabilitate bridge and pavement. | 6.79 | Highway | Interstate Maintenance | 3 | Wilmington Urban Area MPO | I-6037 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2028 | 7300000 |  |  | 7300000
New Hanover | Greenville Avenue | NCDOT | SR 1411 (Wrightsville Avenue) to Hinton Avenue in Wilmington | Realign intersection and construct bike lanes and sidewalk along Greenville avenue. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534C | Division 3 | BGDA, L(M) |  |  |  |  | 2025 | 1076000 |  |  | 1076000 | UNDER CONSTRUCTION.
New Hanover | Hinton Avenue | NCDOT | Park Avenue to Greenville Avenue in Wilmington. | Construct a 10 foot multi-use path. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534H | Division 3 | BGDA, L(M) |  |  |  |  | 2025 | 983000 |  |  | 983000 | UNDER CONSTRUCTION.
New Hanover | Hooker Road | NCDOT | SR 1411 (Wrightsville Avenue) to Mallard Drive / Rose Avenue intersection in Wilmington. | Construct a 10 foot multi-use path. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534G | Division 3 | BGDA, L(M) |  |  |  |  | 2025 | 2395000 |  |  | 2395000 | UNDER CONSTRUCTION.
New Hanover | North Carolina Port Authority | WILMINGTON | Wilmington. | Construct new north gate on North Carolina Port Authority property. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0040 | Division 3 | CRPDA, L(M) | [6 empty] | 2022 | 313000 | 313000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY.
New Hanover | South 3rd Street | WILMINGTON | Ann Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0109 | Division 3 | BGDA, L(M) |  |  |  |  | 2025 | 664000 | 2024 | 489000 | 1153000
New Hanover | South 3rd Street | WILMINGTON | Orange Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0110 | Division 3 | BGANY, HF, L |  |  |  |  | 2025 | 286000 | 2023 | 69000 | 355000 | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY.
New Hanover | US 421 (Lake Park Boulevard) | CAROLINA BEACH | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-6233 | Division 3 | BGDA, HF | 2022 | 40000 |  |  | 2024 | 256000 | 2021 | 18000 | 314000 | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS.
New Hanover | US 421 (Lake Park Boulevard) | NCDOT | Federal Point Shopping Center Driveway intersection north of Bennet Lane in Carolina Beach. | Install traffic signal. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0181 | Region B
New Hanover | Various | WILMINGTON | Routes in Wilmington | Traffic signal pre-emption for emergency vehicles project. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-6235 | Division 3 | BGDA, L(M) |  |  |  |  | 2026 | 1206000 | 2020 | 224000 | 1430000
New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | US 117 to east of I-40 south of Castle Hayne. | Construct four-lane divided freeway on new location. | 0.85 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633CC | [11 empty] | COMPLETE.
New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | West of NC 133 to US 117. | Construct four-lane divided freeway on new location. | 3.544 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633CB | [11 empty] | COMPLETE.
New Hanover | I-140/US 17 (Wilmington Bypass). | NCDOT | West of US 421 north of Wilmington to west of NC 133. | Construct four-lane divided freeway on new location. | 3.6 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633CA | [11 empty] | COMPLETE.
New Hanover | US 17 Business (Market Street) | NCDOT | SR 1272 (New Centre Drive) to Martin Luther King Jr., Boulevard | Construct access management improvements. | 0.089 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | U-4902A | [11 empty] | COMPLETE.
New Hanover | SR 1175(Kerr Avenue) | NCDOT | SR 2048 (Gordon Road) / SR 1327 (Farley Drive) intersection. | Upgrade traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AO | Division 3 | HSIP, T(M) |  |  |  |  | 2024 | 33000 |  |  | 33000
New Hanover | SR 1216 (16th Street); SR 1217 (17th Street) | NCDOT | Queen Street and Castle Street intersections; Queen Street intersection in Wilmington | Install crosswalks and other pedestrian improvements. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403A | Division 3 | HSIP, T(M) |  |  |  |  | 2025 | 811000 |  |  | 811000
New Hanover | SR 1217 (17th Street) | NCDOT | Dock Street intersection in Wilmington. | Install signal heads. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003A | Division 3 | HSIP, T(M) |  |  |  |  | 2025 | 83000 |  |  | 83000
New Hanover | SR 1301 (Princess Place Drive) | NCDOT | North 30th Street intersection in Wilmington. | Construct safety improvements. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AK | Division 3 | HSIP, T(M) | 2024 | 16000 |  |  | 2026 | 151000 |  |  | 167000 | RIGHT-OF-WAY IN PROGRESS.
New Hanover | SR 1302 (23rd Street) | NCDOT | NC 133 (Castle Hayne Road) to US 74 east ramp. | Upgrade traffic signal and add pedestrian accomodations. | 0.6 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AO | Division 3 | HSIP |  |  |  |  | 2026 | 280000 |  |  | 280000
New Hanover | SR 1302 (23rd Street) | NCDOT | SR 1301 (Princess Place Drive) intersection in Wilmington. | Upgrade traffic signals and install pedestrian signals. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AP | Region B | HSIP, T(M) |  |  |  |  | 2025 | 196000 |  |  | 196000 | UNDER CONSTRUCTION.
New Hanover | SR 1318 (Blue Clay Road) | NCDOT | SR 1302 (N. 23rd Street) to SR 1336 (Sidbury Road). | Install rumble strips. | 4.7 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AL | Division 3 | HSIP |  |  |  |  | 2026 | 271000 |  |  | 271000
New Hanover | SR 1520 (Grissom Road) | NCDOT | SR 1492 (Myrtle Grove Road) to SR 1521 (Piner Road). | Install rumble strips. | 0.4 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AM | Division 3 | HSIP |  |  |  |  | 2026 | 27000 |  |  | 27000
New Hanover | SR 2048 (Gordon Road) | NCDOT | West of I-40. | Install pavement markings. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003U | Division 3 | HSIP, T(M) |  |  |  |  | 2023 | 37000 |  |  | 37000 | UNDER CONSTRUCTION.
New Hanover | SR 2817 (17th Street) | NCDOT | Castle Street intersection in Wilmington. | Upgrade traffic signals and install pedestrian signals. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AQ | Division 3 | HSIP, T(M) |  |  |  |  | 2025 | 380000 |  |  | 380000
New Hanover | US 117 | NCDOT | South of SR 2160 (Long Ridge Road) to south of NC 133 intersection north of Wilmington. | Widen road and install center and edgeline sinusoidal rumble strips. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AF | Region B | HSIP |  |  |  |  | 2026 | 406000 |  |  | 406000
New Hanover | US 117 | NCDOT | SR 1209 (Independence Boulveard) intersection in Wilmington. | Upgrade traffic singal and install signalized pedestrian crodding and pavement markings. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AC | Statewide Mobility | HSIP |  |  |  |  | 2026 | 136000 |  |  | 136000
New Hanover | US 117 (Shipyard Boulevard) | NCDOT | Converse Road / Longstreet Drive intersection in Wilmington. | Upgrade traffic signal and add pedestrian accommodations. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003P | Statewide Mobility | HSIP, T(M) | 2025 | 30000 |  |  | 2026 | 271000 |  |  | 301000
New Hanover | US 117 / NC 132 | NCDOT | SR 2206 (West Northchase Parkway) / SR 2257 (Southeast Northchase Parkway) intersection north of Wilmington | Upgrade traffic signal. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403N | Region B | HSIP |  |  |  |  | 2026 | 113000 |  |  | 113000
New Hanover | US 117 / NC 132 (College Road) | NCDOT | Crews Drive intersection. | Upgrade traffic signal and install signalized pedestrian crossings. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AD | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 246000 |  |  | 246000
New Hanover | US 117 / NC 132 (College Road) | NCDOT | Lake Avenue-Hugh McRae Park in Wilmington. | Revise traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003H | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 66000 |  |  | 66000
New Hanover | US 117 / NC 132 (College Road) | NCDOT | SR 1411 (Wrightsville Avenue) intersection in Wilmington. | Install Crosswalks and pedestrian countdown heads. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AE | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 110000 |  |  | 110000
New Hanover | US 117 / NC 132 (College Road) | NCDOT | SR 2313 (Wilshire Boulevard) intersection in Wilmington. | Install pedestrian countdown heads. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003Y | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 63000 |  |  | 63000
New Hanover | US 117/NC 132 (College Road) | NCDOT | SR 2160 (Long Ridge Road) intersection. | Install traffic signal with pedestrian accommodations. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AI | Region B | HSIP, T(M) |  |  |  |  | 2026 | 576000 |  |  | 576000
New Hanover | US 17 (Dawson Street) | NCDOT | US 421 (3rd Street) intersection in Wilmington. | Upgrade traffic signal, pavement markings, and add pedestrian accommodations. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003Q | Region B | HSIP, T(M) |  |  |  |  | 2026 | 184000 |  |  | 184000
New Hanover | US 17 (Market Street) | NCDOT | SR 1402 (Porters Neck Road) intersection in Wilmington. | Upgrade traffic signal. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AR | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 11000 |  |  | 11000
New Hanover | US 17 (Oleander Drive) | NCDOT | 42nd Street intersection in Wilmington. | Revise traffic signal and pavement markings. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003J | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 70000 |  |  | 70000
New Hanover | US 17 / US 76 (Dawson Street and Wooster Street) | NCDOT | SR 1216 (16th Street) and SR 1217 (17th Street) intersections in Wilmington. | Upgrade traffic signal, crosswalks, and pedestrian signals. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AN | Region B | HSIP, T(M) |  |  |  |  | 2025 | 147000 |  |  | 147000
New Hanover | US 17 / US 76 (Oleander Drive) | NCDOT | SR 1209 (Independence Boulevard) intersection in Wilmington. | Upgrade traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003V | Statewide Mobility | HSIP, T(M) | 2025 | 30000 |  |  | 2026 | 50000 |  |  | 80000 | RIGHT-OF-WAY IN PROGRESS.
New Hanover | US 17 / US 76 (Oleander Drive) | NCDOT | SR 1421 (Greenville Loop Road / Greenville Avenue) intersection in Wilmington. | Revise traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003L | Region B | HSIP, T(M) |  |  |  |  | 2025 | 84000 |  |  | 84000
New Hanover | US 17 / US 76 (Wooster Street) | NCDOT | SR 1217 (17th Street) intersection in Wilmington. | Revise traffic signal and install pedestrian countdown heads. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003Z | Region B | HSIP, T(M) |  |  |  |  | 2026 | 114000 |  |  | 114000
New Hanover | US 17 Business (Market Street) | NCDOT | 10th Street intersection in Wilmington | Upgrade traffic signal and install pedestrian signals. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403O | Region B | HSIP |  |  |  |  | 2026 | 82000 |  |  | 82000
New Hanover | US 17 Business (Market Street) | NCDOT | 5th Avenue intersection in Wilmington | Upgrade traffic signal with pedestrian accommodations. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403P | Region B | HSIP |  |  |  |  | 2026 | 47000 |  |  | 47000
New Hanover | US 17 Business (Market Street) | NCDOT | Lullwater Drive intersection in Wilmington | Upgrade signing and traffic signal with pedestrian accommodations. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403Q | Region B | HSIP |  |  |  |  | 2026 | 51000 |  |  | 51000
New Hanover | US 17 Business (Market Street) | NCDOT | SR 1216 (16th Street) intersection in Wilmington. | Upgrade traffic signal and construct curb bump-outs. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AG | Region B | HSIP | 2026 | 6000 | 2026 | 2000 | 2026 | 261000 |  |  | 269000
New Hanover | US 17 Business (Market Street) | NCDOT | SR 1272 (New Centre Drive) intersection in Wilmington. | Install crosswalks. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003S | Region B | HSIP, T(M) | 2025 | 58000 |  |  | 2026 | 114000 |  |  | 172000
New Hanover | US 17 Business (Market Street) | NCDOT | SR 2219 (Green Meadows Drive) intersection in Wilmington. | Upgrade traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003T | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 63000 |  |  | 63000
New Hanover | US 17/ US 76 (Oleander Drive) | NCDOT | Country Club Road intersection in Wilmington | Install near side signal head and upgrade traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403G | Region B | HSIP |  |  |  |  | 2026 | 51000 |  |  | 51000
New Hanover | US 421 | NCDOT | Independence Boulevard intersection in Wilmington. | Upgrade traffic signal and add pedestrian accomodations. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AN | Statewide Mobility | HSIP |  |  |  |  | 2026 | 38000 |  |  | 38000
New Hanover | US 421 | NCDOT | SR 1573 (Dow Road) intersection in Carolina Beach. | Upgrade traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003R | Region B | HSIP, T(M) |  |  |  |  | 2026 | 23000 |  |  | 23000
New Hanover | US 421 (Carolina Beach Road) | NCDOT | SR 1276 (Cathay Road) intersection in Wilmington. | Upgrade traffic signal. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AT | Region B | HSIP |  |  |  |  | 2026 | 18000 |  |  | 18000
New Hanover | US 421 (Carolina Beach Road) | NCDOT | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | Highway | Safety | 3 | Wilmington Urban Area MPO | W-5703C | Region B | HSIP | 2023 | 363000 | 2023 | 127000 | 2026 | 3950000 |  |  | 4440000 | RIGHT-OF-WAY IN PROGRESS.
New Hanover | US 74 | NCDOT | SR 1627 (3rd Street / Martin Luther King, Jr. Boulevard) westbound on-ramp in Wilmington. | Revise traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003K | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 16000 |  |  | 16000 | UNDER CONSTRUCTION.
New Hanover | US 74 (Eastwood Road) | NCDOT | US 17 (Military Cutoff Road) and Cavalier Drive intersections in Wilmington. | Upgrade pedestrian signals. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | W-5803A | Region B | HSIP, T(M) |  |  |  |  | 2023 | 170000 |  |  | 170000 | UNDER CONSTRUCTION.
New Hanover | US 74 / US 76 (Eastwood Road) | NCDOT | Lumina Commons Driveway intersection in Wilmington. | Improve left turn lane offsets and pedestrian accommodations. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403AU | Statewide Mobility | HSIP | 2027 | 5000 | 2027 | 5000 | 2027 | 1150000 |  |  | 1160000
New Hanover | Lendire Road | NCDOT | West of US 17 Business (Market Street) to US 17 Business (Market Street) / SR 1403 (Middle Sound Loop Road). | Realign roadway. | 0.31 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4751A | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
New Hanover | NC 132 (College Road) | NCDOT | SR 1272 (New Centre Drive) to US 117 (Shipyard Boulevard). | Access management and travel time improvements. | 2.64 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5702A | Statewide Mobility | NHP, T(M) | 2030 | 29800000 | 2030 | 12500000 | 2033 | 38900000 |  |  | 81200000 | PLANNING/DESIGN IN PROGRESS.
New Hanover | NC 132 (College Road) | NCDOT | SR 1272 (New Centre Drive) to US 421 (Carolina Beach Road). | Access management and travel time improvements. | 9.7 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5702
New Hanover | NC 132 (College Road) | NCDOT | US 117 (Shipyard Boulevard) to US 421 (Carolina Beach Road). | Access management and travel time improvements. | 4.23 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5702B | Not Funded | NHP, T(M) | NOT FUNDED | 30600000 | NOT FUNDED | 15000000 | NOT FUNDED | 50400000 | NOT FUNDED |  | 96000000
New Hanover | New Location | NCDOT | SR 1409 (Military Cutoff Road) at Drysdale Drive to US 74 (Eastwood Road). | Construct roadway on new location. | 0.3 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5710A | Statewide Mobility | BGANY, T | 2019 | 2575000 |  |  | 2022 | 8200000 |  |  | 10775000 | UNDER CONSTRUCTION.
New Hanover | SR 1175 (Kerr Avenue) | NCDOT | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Widen to multi-lanes. | 3.2 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-3338
New Hanover | SR 1175 (Kerr Avenue) | NCDOT | SR 1175 (Kerr Avenue) interchange at US 74 (Martin Luther King, Jr. Parkway). | Improve interchange. | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-3338C | Region B | BGANY, T(M) |  |  |  |  | 2030 | 39600000 |  |  | 39600000 | RIGHT-OF-WAY IN PROGRESS.
New Hanover | SR 1209 (Independence Boulevard Extension) | NCDOT | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Extend roadway on new location. | 1.81 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4434 | Division 3 | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 133500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 288800000 |  |  | 424600000
New Hanover | SR 1409 (Military Cutoff Road Extension) | NCDOT | SR 1409 (Military Cutoff Road) to US 17 (Market Street) in Wilmington. | Construct roadway on new location. | 3.61 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4751 | Statewide Mobility | T | 2009 | 355000 |  |  | 2018 | 85750000 | 2021 | 14850000 | 100955000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
New Hanover | SR 2048 (Gordon Road) | NCDOT | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6202 | Division 3 | T | 2022 | 17835000 | 2024 | 6651000 | 2025 | 65959000 |  |  | 90445000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S.
New Hanover | US 117 / NC 132 (College Road) | NCDOT | US 17 Business (Market Street) to SR 2048 (Gordon Road). | Upgrade roadway. | 1.9 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5792 | Division 3 | T | 2026 | 37899000 | 2026 | 2700000 | 2029 | 250900000 |  |  | 291499000 | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE).
New Hanover | US 17 / US 76 / US 421 | NCDOT | Bridge 640013 (Cape Fear Memorial Bridge) over Cape Fear River. | Replace bridge. This is a toll project. Wilmington MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 0.8 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | HB-0039 | Statewide Mobility | BOND R, DP, NHP | 2026 | 41000000 | 2026 | 3300000 | 2026 | 1002305000 |  |  | 1046605000 | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2031 - 2045.
New Hanover | US 17 Business (Market Street) | NCDOT | Colonial Drive to SR 1402 (Porters Neck Road). | Improve access management. | 8.6 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902
New Hanover | US 17 Business (Market Street) | NCDOT | CSX Railroad to Cinema Drive; Jacksonville Street to north of US 117 / NC 132 (College Road). | Construct access management improvements. | 1.4 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902B | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 2900000 | NOT FUNDED | 9700000 | NOT FUNDED |  | 22600000
New Hanover | US 17 Business (Market Street) | NCDOT | North of US 117 / NC 132 (College Road) to Station Road. | Construct access management improvements. | 2.19 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902C | Statewide Mobility | T | 2030 | 50358000 | 2030 | 5862000 | 2033 | 112900000 |  |  | 169120000 | INCLUDES U-5880.
New Hanover | US 17 Business (Market Street) | NCDOT | SR 1403 (Middle Sound Loop Road) to SR 2290 (Mendenhall Drive) / SR 2734 (Marsh Oaks Drive). | Construct access management improvements. | 1.66 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902D | Statewide Mobility | T |  |  |  |  | 2019 | 27609000 | 2021 | 4290000 | 31899000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
New Hanover | US 421 | NCDOT | US 117 (Shipyard Boulevard) intersection in Wilmington | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5729SW | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4620000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1640000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7160000 |  |  | 13420000
New Hanover | US 421 | NCDOT | US 421 (Burnett Boulevard) to US 117 (Shipyard Boulevard) in Wilmington. | Upgrade roadway. | 1.54 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5729REG | Region B | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18480000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6560000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28640000 |  |  | 53680000
New Hanover | US 421 (Carolina Beach Road) | NCDOT | NC 132 (South College Road) to Sanders Road in Wilmington. | Widen existing roadway and construct flyovers at US 421 and NC 132. | 1.03 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5790 | Division 3 | T | 2027 | 12000000 | 2027 | 3200000 | 2029 | 39300000 |  |  | 54500000
New Hanover | US 421 (Carolina Beach Road) | NCDOT | US 421 (Burnett Boulevard) to US 117 (Shipyard Boulevard) in Wilmington. | Upgrade roadway. | 1.6 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5729
New Hanover | US 421 (South Front Street) | NCDOT | US 17 Business / US 76 / US 421 (Cape Fear Memorial Bridge) to US 421 (Burnett Boulevard) in Wilmington. | Widen to multi-lanes. | 0.99 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5734 | Region B | NHP, T(M) | 2026 | 35800000 | 2026 | 3200000 | 2029 | 37500000 |  |  | 76500000
New Hanover | US 74 | NCDOT | US 17 / US 421 in Wilmington. | Construct a fly-over and free flow ramp at interchange. | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5731 | Statewide Mobility | BGLT5, T(M) | 2028 | 6100000 | 2028 | 590000 | 2030 | 48700000 |  |  | 55390000
New Hanover | US 74 (Eastwood Road) | NCDOT | SR 1409 (Military Cutoff Road) intersection in Wilmington | Upgrade at-grade intersection to an interchange. | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5710 | Statewide Mobility | NHP, T(M) | 2023 | 16900000 | 2025 | 4000000 | 2027 | 60500000 |  |  | 81400000 | RIGHT-OF-WAY IN PROGRESS.
New Hanover | US 76 (Oleander Drive) | NCDOT | Greenville Loop Road and Greenville Avenue intersections Wilmington | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6128 | Region B | BGANY, T(M) | 2027 | 3700000 | 2027 | 600000 | 2030 | 6800000 |  |  | 11100000
New Hanover | Various | NCDOT | Routes in Wilmington | Improve signal system. | 39.2 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6199 | Division 3 | T | 2028 | 10000 | 2028 | 1100000 | 2030 | 15500000 |  |  | 16610000
New Hanover | SR 1175 (Kerr Avenue) | NCDOT | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway). | Widen to multi-lanes. | 1.49 | Highway | Transition | 3 | Wilmington Urban Area MPO | U-3338B | Pre-STI (Transition) | [10 empty] | COMPLETE.
New Hanover | Cape Fear Public Transportation Authority - Wave Transit |  | Cape Fear Public Transportation Authority - Wave Transit | PURCHASE OF 2 SUPPORT VEHICLES PAST THEIR USEFUL LIFE, PARA VEHICLE CAMERAS, BUS SHELTERS, CNG FUELING STATION EQUIPMENT, TELECOMMUNICATIONS HARDWARE, AND BUS FACILITIES EMERGENCY OPERATIONS EQUIPMENT. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TC-0047 | Public Transit | 5339, L(M) | [6 empty] | 2026 | 362000 | 362000
New Hanover | Cape Fear Public Transportation Authority - Wave Transit |  | Systemwide. | Capital investments for the demolition, purchase, and installation of bus shelters throughout New Hanover County. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TC-0045 | Public Transit | 5307, L | [6 empty] | 2025 | 1530000 | 1530000
New Hanover | Cape Fear Public Transportation Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Systemwide | Funding for organizations to remove transportation barriers and connect elders and individuals with disabilities to needed resources. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TQ-9001 | Public Transit | 5310, L | [6 empty] | 2022 | 568000 | 568000
New Hanover | Cape Fear Public Transportation Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Systemwide | Funding for Section 5310 funds to administer program. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TQ-8019 | Public Transit | 5310, L | [6 empty] | 2023 | 371000 | 371000 | FUNDS AUTHORIZED IN PROGRESS
New Hanover | Cape Fear Public Transportation Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | Various locations | Install transit shelters. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TC-0027 | Public Transit | 5309, 5339, BGDA, L | [6 empty] | 2023 | 664000 | 664000
New Hanover | Wave Transit | Wave Transit | Systemwide | Purchase of CNG buses that will replace buses past their useful life. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TC-0050 | Not Funded | 5339, L | NOT FUNDED |  | NOT FUNDED |  | NOT FUNDED |  | NOT FUNDED | 1200000 | 1200000
New Hanover | Cape Fear Public Transit Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 3 | Wilmington Urban Area MPO | TO-4751 | Public Transit | 5307, L, SMAP | [6 empty] | 2022 | 17437000 | 17437000 | FUNDS AUTHORIZED IN PROGRESS
New Hanover | Cape Fear Public Transportation Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Route 205 | Provide Operating Support For Fixed Bus Route 205 Long Leaf Park Which Services Novant Hospital And The Medical Center. |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Wilmington Urban Area MPO | TQ-6513 | Public Transit | 5310, L | [6 empty] | 2023 | 866000 | 866000 | FUNDS AUTHORIZED IN PROGRESS
New Hanover | Cape Fear PublicTransportation Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Systemwide | Funding for Section 5310 Program. |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Wilmington Urban Area MPO | TQ-7005 | Public Transit | 5310 | [6 empty] | 2021 | 180000 | 180000
New Hanover | Cape Fear Public Transit Authority |  | Various locations | Acquire or replace bus facilities capital improvements- acquire or replace equipment and systems in Wave transit operation and maintenance facility. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-0020 | Public Transit | 5309, L | [6 empty] | 2024 | 239000 | 239000
New Hanover | Cape Fear Public Transit Authority (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | Systemwide | Purchase CNG buses. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-0026 | Public Transit | 5339(b), L | [6 empty] | 2025 | 3432000 | 3432000
New Hanover | Cape Fear Public Transportation Authority (WAVE) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | Various locations | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-5245 | Public Transit | 5307, L | [6 empty] | 2020 | 2464000 | 2464000
New Hanover | Wilmington | NC STATE PORTS AUTHORITY | Port of Wilmington | Operation of new intermodal container shipping facility. |  | Rail | NCDOT Selected (Other Selection Process) | 3 | Wilmington Urban Area MPO | RN-0001 | Exempt | CMAQ, S(M) | [6 empty] | 2025 | 2475000 | 2475000 | PROJECT BENEFITS THE QUEEN CITY EXPRESS AND WILMINGTON MIDWEST EXPRESS LINES PROVIDING AN AIR QUALITY BENEFIT TO THE CHARLOTTE AND ROCKY MOUNT AREAS. NON-FEDERAL MATCH PROVIDED BY THE NC STATE PORTS AUTHORITY.
New Hanover | CSX SE Line | NCDOT | Wilmington. | Close and improve various at-grade crossings. |  | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740B | Statewide Mobility | DP, T | 2023 | 2600000 | 2025 | 270000 | 2026 | 4200000 |  |  | 7070000 | RIGHT-OF-WAY IN PROGRESS.
New Hanover, Brunswick | I-140/US 17 (Wilmington Bypass). | NCDOT | SR 1430 (Cedar Hill Road) to West of US 421 north of Wilmington. | Construct four-lane divided freeway on new location. |  | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633BB | Pre-STI (Transition) | NHP |  |  |  |  | 2013 | 51250000 |  |  | 51250000 | COMPLETE. GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK 2013 - 2024.
New Hanover, Brunswick | CSX SE Line | WILMINGTON | Wilmington. | Install railroad grade crossing signals and gates at various at-grade crossings. |  | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740C | Statewide Mobility | DP, T |  |  |  |  | 2026 | 8300000 |  |  | 8300000
New Hanover, Brunswick | CSX SE Line | WILMINGTON | Wilmington. | Rehabilitate ties and curves, realign curve, upgrade bridges. |  | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740A | Statewide Mobility | DP, T |  |  |  |  | 2023 | 33000000 |  |  | 33000000 | UNDER CONSTRUCTION.
New Hanover, Brunswick | CSX Southeast Line | CSXT RR | Wilmington. | Construct Wilmington Beltline Speed Improvements | 13 | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740 | Statewide Mobility | [10 empty] | DP FUNDS REPRESENT FEDERAL CRISI GRANT.
New Hanover, Brunswick, Pender | Various | NCDOT | Wilmington Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | U-5527 | Division 3 | TADA |  |  |  |  | 2022 | 16694000 |  |  | 16694000 | IN PROGRESS.
New Hanover, Brunswick, Pender | Various | NCDOT | Wilmington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0107 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 3727000 |  |  | 3727000
New Hanover, Brunswick, Pender | Various | NCDOT | Wilmington Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5525 | Division 3 | BGDA, L(M) | [6 empty] | 2020 | 19840000 | 19840000
New Hanover, Brunswick, Pender | Various | NCDOT | Wilmington Urban Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5989 | Division 3 | BGANY, BGDA |  |  |  |  | 2022 | 127394000 |  |  | 127394000
New Hanover, Brunswick, Pender | Wilmington Urban Area Metropolitan Planning Organization | NCDOT | Various | Wilmington Urban Area MPO STP-DA Program. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534 | Division 3 | BGANY, BGDA, L, L(M) | 2022 | 220000 | 2024 | 420000 | 2020 | 15092000 |  |  | 15732000 | IN PROGRESS
New Hanover, Pender | I-40 | NCDOT | End I-40 (mile marker 420) to NC 210 (mile marker 408). | Rehabilitate pavement. | 11.88 | Highway | Interstate Maintenance | 3 | Wilmington Urban Area MPO | I-6039 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2023 | 23004000 |  |  | 23004000 | UNDER CONSTRUCTION.
New Hanover, Pender | SR 1336 (Sidbury Road) | NCDOT | SR 1318 (Blue Clay Road) to US 17 North of Wilmington | Install centerline and shoulder sinusoidal rumble stripes with bicycle pattern. | 7.2 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403D | Division 3 | HSIP |  |  |  |  | 2025 | 421000 |  |  | 421000 | UNDER CONSTRUCTION.
New Hanover, Pender | US 17 (Hampstead Bypass) | NCDOT | US 17 Bypass south of Hampstead to US 17 North of Hampstead. | Construct freeway on new location. | 12.3 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | R-3300
Northampton | NC 186 | NCDOT | Garysburg to the Virginia State line, excluding the seaboard town limits | Install rumble stripes and pavement markings. |  | Highway | Safety | 1 | Peanut Belt RPO | HS-2401E | Region A | HSIP, T(M) |  |  |  |  | 2025 | 457000 |  |  | 457000 | UNDER CONSTRUCTION.
Northampton | NC 305 | NCDOT | Hertford County line to north of SR 1503 (Lasker Road). | Upgrade roadway. | 10.33 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5757A | Division 1 | BGLT5, T(M) |  |  |  |  | 2027 | 25600000 |  |  | 25600000
Northampton | NC 305 | NCDOT | North of SR 1503 (Lasker Road) to Seaboard Town limits. | Upgrade roadway. | 13.97 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5757B | Division 1 | BGLT5, T(M) |  |  |  |  | 2027 | 29100000 |  |  | 29100000
Northampton | NC 305 | NCDOT | Seaboard Town limits to Hertford County line. | Upgrade roadway. | 24.3 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5757 | Division 1 | BGLT5, T(M) | 2023 | 3200000 | 2024 | 4122000 |  |  |  |  | 7322000 | RIGHT-OF-WAY IN PROGRESS.
Northampton | NC 46 | NCDOT | NC 48 in Gaston to the Virginia State line. | Upgrade and widen existing lanes and shoulders. | 10.41 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5739 | Division 1 | T | 2022 | 5065000 | 2022 | 2300000 | 2026 | 48955000 |  |  | 56320000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
Northampton | US 158 / NC 46 | NCDOT | I-95 / NC 46 in Roanoke Rapids to SR 1312 (St. John Church Road) in Northampton County. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.94 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-2582A | Division 1 | T | 2020 | 3345000 |  |  | 2020 | 106809000 | 2020 | 8820000 | 118974000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Northampton | US 158 / NC 46 | NCDOT | I-95 / NC 46 in Roanoke Rapids to SR 1333 (Mount Carmel Church Road) east of Jackson. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 15.2 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-2582
Northampton | US 158 / NC 46 | NCDOT | SR 1312 (St. John Church Road) to SR 1333 (Mount Carmel Church Road) east of Jackson. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.4 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-2582B | Not Funded | T | NOT FUNDED | 5400000 | NOT FUNDED |  | NOT FUNDED | 61400000 | NOT FUNDED |  | 66800000
Northampton, Chowan, Gates, Tyrrell | US 64; US 158; NC 32 | NCDOT | Various locations | Install rumble stripes and snow plowable pavement markers. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO | HS-2401Q | Region A | HSIP, T(M) |  |  |  |  | 2026 | 1950000 |  |  | 1950000
Onslow | OAJ | ALBERT J. ELLIS AIRPORT (OAJ) | Albert J. Ellis Airport | Acquire land for highway relocation. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5805 | Region B | O, T | 2026 | 661000 | [6 empty] | 661000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS.
Onslow | OAJ | ALBERT J. ELLIS AIRPORT (OAJ) | Albert J. Ellis Airport | Acquire land for runway 5 protection zone extension. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5804 | Region B | O, T | 2026 | 697000 | [6 empty] | 697000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS.
Onslow | OAJ | ALBERT J. ELLIS AIRPORT (OAJ) | Albert J. Ellis Airport | Design and construct runway 23 holding apron. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5733 | Region B | O, T |  |  |  |  | 2022 | 750000 |  |  | 750000 | UNDER CONSTRUCTION.
Onslow | OAJ | ALBERT J. ELLIS AIRPORT (OAJ) | Albert J. Ellis Airport | Extend runway 23 and taxiway A. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5806 | Region B | O, T |  |  |  |  | 2026 | 13180000 | 2025 | 300000 | 13480000 | OTHER FUNDS ARE AIRPORT FUNDS
Onslow | SR 1308 (Gum Branch Road) | JACKSONVILLE | Nottingham Road to north Onsville Drive intersection in Jacksonville. | Construct pedestrian improvements. | 1.49 | Bike & Ped | Locally Selected | 3 | Jacksonville Urban Area MPO | BL-0073 | Exempt | CRPDA, L(M) | [6 empty] | 2024 | 320000 | 320000
Onslow | Downtown Greenway | JACKSONVILLE | Chaney Avenue to Wardola Drive in Jacksonville | Construct multi-use path. | 0.58 | Bike & Ped | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | EB-6012 | Division 3 | L(M), TA50200 |  |  |  |  | 2022 | 1367000 |  |  | 1367000 | UNDER CONSTRUCTION.
Onslow | NC 24 | NCDOT | Bridge 660007 over Northeast Creek | Replace bridge. |  | Highway | Bridges | 3 | Jacksonville Urban Area MPO | BR-0193 | Statewide Mobility | BFP |  |  |  |  | 2028 | 9600000 |  |  | 9600000
Onslow | NC 24 (West Corbett Avenue) | NCDOT | East of West Shore Drive. | Replace culvert east of West Shore Drive. |  | Highway | Bridges | 3 | Jacksonville Urban Area MPO | R-5885A | Region B | NHP, T(M) | 2025 | 350000 | 2025 | 90000 | 2027 | 2700000 |  |  | 3140000 | RIGHT-OF-WAY IN PROGRESS
Onslow | SR 1509 (Queens Creek Road) | NCDOT | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Jacksonville Urban Area MPO | B-5944 | Division 3 | BFP, T(M) | 2031 | 1600000 | 2031 | 1200000 | 2033 | 30100000 |  |  | 32900000
Onslow | Various | NCDOT | Jacksonville Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 3 | Jacksonville Urban Area MPO | HL-0102 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 2902000 |  |  | 2902000
Onslow | Jacksonville Parkway | NCDOT | Country Club Road to SR 1470 (Western Boulevard) | Add lanes and construct routes on new location. | 0 | Highway | Pre-STI (Historic) | 3 | Jacksonville Urban Area MPO | U-4007B | [11 empty] | COMPLETE.
Onslow | SR 1702 (West Huff Drive) | NCDOT | SR 1308 (Bell Fork Road) to east of SR 1470 (Western Boulevard) | Add lanes and construct routes on new location. | 1.4 | Highway | Pre-STI (Historic) | 3 | Jacksonville Urban Area MPO | U-4007A | [11 empty] | COMPLETE.
Onslow | US 17 | NCDOT | Multi-lane section north of Jacksonville to South of Belgrade. | Widen to multi-lanes with bypass of Belgrade, Maysville and Pollocksville on new location. | 6.17 | Highway | Pre-STI (Historic) | 3 | Jacksonville Urban Area MPO | R-2514A | Pre-STI (Transition) | [10 empty] | COMPLETE.
Onslow | NC 111 | NCDOT | West of US 258 to Onslow County line. | Widen road and install center and edgeline sinusoidal rumble strips. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AD | Region B | HSIP |  |  |  |  | 2026 | 445000 |  |  | 445000
Onslow | NC 172 | NCDOT | Camp Lejeune Gate to NC 210. | Upgrade two lane roadway to three lane roadway with two way left turn lane. | 3.74 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5602 | Region B | T |  |  |  |  | 2019 | 12183000 |  |  | 12183000 | COMPLETE. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
Onslow | NC 172 | NCDOT | SR 1500 (Starling Road) near Hubert | Install traffic signal. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403I | Region B | HSIP |  |  |  |  | 2026 | 450000 |  |  | 450000
Onslow | NC 172; NC 24 | NCDOT | US 17 to SR 1678 (Old Ferry Road); NC 53 to SR 1406 (Piney Green Road). | Install rumble strips and pavement markings. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AJ | Region B | HSIP |  |  |  |  | 2026 | 438000 |  |  | 438000
Onslow | NC 24 | NCDOT | SR 1445 (Norris Road) intersection in Swansboro. | Install ramps and pedestrian accommodations. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AT | Region B | HSIP, T(M) | 2025 | 124000 |  |  | 2026 | 324000 |  |  | 448000 | RIGHT-OF-WAY IN PROGRESS.
Onslow | NC 24 | NCDOT | SR 1514 (Phillips Loop Road) intersection in Swansboro. | Install crosswalks with pedestrian signals and advance flashers. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003X | Statewide Mobility | HSIP, T(M) | 2026 | 184000 |  |  | 2026 | 202000 |  |  | 386000 | RIGHT-OF-WAY IN PROGRESS.
Onslow | NC 24 (West Corbett Avenue) | NCDOT | SR 1512 (Old Hammock Road) intersection. | Upgrade pedestrian signals. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5803D | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2022 | 17000 |  |  | 17000 | COMPLETE.
Onslow | NC 53 (Western Boulevard) | NCDOT | Carolina Forest Boulevard and North Plain Road intersections in Jacksonville | Install near side signal heads. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403F | Region B | HSIP |  |  |  |  | 2026 | 35000 |  |  | 35000
Onslow | NC 53 (Western Boulevard) | NCDOT | Center Street / Liberty Drive intersection. | Upgrade traffic signal and add additional speed limit signs. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5803E | Region B | HSIP, T(M) |  |  |  |  | 2022 | 57000 |  |  | 57000 | COMPLETE.
Onslow | NC 53 (Western Boulevard) | NCDOT | Forum Road / Marty Goldman Way intersection in Jacksonville. | Install Crosswalks and pedestrian signals. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AM | Region B | HSIP, T(M) |  |  |  |  | 2025 | 178000 |  |  | 178000 | UNDER CONSTRUCTION.
Onslow | NC 53 (Western Boulevard) | NCDOT | SR 1308 (Gum Branch Road) intersection in Jacksonville. | Upgrade traffic signal. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AA | Region B | HSIP |  |  |  |  | 2026 | 13000 |  |  | 13000
Onslow | SR 1308 (Bell Fork Road) | NCDOT | Brynn Marr Road intersection. | Upgrade traffic signal, signing, and pavement markings. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AA | Division 3 | HSIP, T(M) | 2024 | 126000 |  |  | 2026 | 246000 |  |  | 372000 | RIGHT-OF-WAY IN PROGRESS.
Onslow | SR 1308 (Gum Branch Road) | NCDOT | SR 1903 (Ramsey Drive) / SR 1944 (Hunting Green Drive) and SR 1920 (Raintree Road) intersections in Jacksonville | Install traffic signals. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403R | Division 3 | HSIP | 2026 | 55000 | 2026 | 2000 | 2027 | 625000 |  |  | 682000
Onslow | SR 1308 (Gumbranch Road) | NCDOT | Nottingham Road to Plaza drive in Jacksonville | Improve pedestrian accommodations. | 1 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AV | Division 3 | HSIP |  |  |  |  | 2026 | 1047000 |  |  | 1047000
Onslow | SR 1336 (Henderson Drive) | NCDOT | SR 1308 (Gum Branch Road) intersection and intersection south of SR 1308 (Gum Branch Road) in Jacksonville. | Upgrade traffic signals and install accessible pedestrian signals. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AI | Division 3 | HSIP |  |  |  |  | 2026 | 60000 |  |  | 60000
Onslow | SR 1403 (Country Club Road) | NCDOT | Academic Drive intersection in Jacksonville | Install traffic signal, pedestrian signals, and pedestrian accommodations. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403J | Division 3 | HSIP | 2026 | 10000 | 2026 | 2000 | 2026 | 505000 |  |  | 517000
Onslow | SR 1428 (Riggs Road) | NCDOT | Nautical Wave Road to SR 1744 (Hubert Boulevard). | Install pavement markings. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AB | Division 3 | HSIP, T(M) |  |  |  |  | 2024 | 71000 |  |  | 71000
Onslow | SR 1532 (Flokstone Road) | NCDOT | US 17 to SR 1531 (Tar Landing Road). | Install center and edgeline sinusoidal rumble strips. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AE | Division 3 | HSIP |  |  |  |  | 2025 | 93000 |  |  | 93000
Onslow | US 17 | NCDOT | NC 210 intersection east of Holly Ridge. | Install signal heads. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AH | Statewide Mobility | HSIP |  |  |  |  | 2026 | 21000 |  |  | 21000
Onslow | US 17 (Marine Boulevard) | NCDOT | Henderson Drive intersection in Jacksonville. | Construct safety improvements. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AJ | Region B | HSIP, T(M) | 2025 | 51000 |  |  | 2026 | 159000 |  |  | 210000
Onslow | US 17 Business (Marine Boulevard) | NCDOT | SR 1308 (Gum Branch Road / Bell Fork Road) intersection in Jacksonville. | Construct safety improvements. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AF | Region B | HSIP, T(M) |  |  |  |  | 2025 | 82000 |  |  | 82000 | UNDER CONSTRUCTION.
Onslow | US 17 Business (Marine Boulevard) | NCDOT | SR 1336 (Onslow Drive) intersection in Jacksonville. | Construct safety improvements. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AG | Region B | HSIP, T(M) |  |  |  |  | 2025 | 144000 |  |  | 144000 | UNDER CONSTRUCTION.
Onslow | US 17 Business (Marine Boulevard) | NCDOT | SR 1402 (Old Bridge Street) intersection. | Upgrade traffic signal, install pavement markings, and improve sight distance. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5803C | Region B | HSIP, T(M) |  |  |  |  | 2023 | 84000 |  |  | 84000 | UNDER CONSTRUCTION.
Onslow | US 17 Business (North Marine Boulevard) | NCDOT | McDaniel Drive and Workshop Lane intersections in Jacksonville | Install near side signal heads. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403H | Region B | HSIP |  |  |  |  | 2026 | 23000 |  |  | 23000
Onslow | US 258 / NC 24 | NCDOT | SR 1320 (Wells Road) to SR 1238 (Koonce Fork Road) south of Richlands | Install rumble stripes. | 7.34 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403T | Statewide Mobility | HSIP |  |  |  |  | 2026 | 292000 |  |  | 292000
Onslow | Various | NCDOT | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5203REG | Region B
Onslow | Various | NCDOT | Routes in Onslow County | Install rumble strips. | 17.25 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403AK | Division 3 | HSIP |  |  |  |  | 2026 | 1136000 |  |  | 1136000
Onslow | Commerce Drive Extension | NCDOT | Commerce Drive to SR 1406 (Piney Green Road). | Construct roadway on new location. | 0.24 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5878 | Division 3 | T |  |  |  |  | 2022 | 3698000 |  |  | 3698000 | UNDER CONSTRUCTION.
Onslow | NC 210 | NCDOT | US 17 to south of SR 1518 (Old Folkstone Road). | Widen to multi-lanes. | 5.76 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5949 | Region B | T | 2030 | 33198000 | 2030 | 15400000 | 2034 | 115400000 |  |  | 163998000
Onslow | NC 24 | NCDOT | US 258 (Richlands Highway) intersection in Jacksonville | Upgrade at-grade intersection to an interchange. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5716 | Statewide Mobility | T | 2022 | 35672000 | 2028 | 3900000 | 2031 | 66400000 |  |  | 105972000 | PROJECT BEING LET WITH U-5739. RIGHT-OF-WAY BEGAN IN 2022 AND THEN PAUSED. SCHEDULED TO RESUME IN 2028.
Onslow | NC 24 (Lejeune Boulevard) | NCDOT | NC 53 (Western Boulevard) in Jacksonville. | Upgrade intersection and drainage. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5508 | Statewide Mobility | BG50200, T(M) | 2027 | 1100000 | 2027 | 280000 | 2030 | 3100000 |  |  | 4480000
Onslow | NC 24 (West Corbett Avenue) | NCDOT | Belgrade-Swansboro Road to Front Street. | Construct reduced conflict intersection. | 2.91 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | R-5885 | Not Funded | NHP, T(M) | NOT FUNDED | 61900000 | NOT FUNDED | 5200000 | NOT FUNDED | 47400000 | NOT FUNDED |  | 114500000
Onslow | NC 53 | NCDOT | US 17 (Marine Boulevard) to SR 2716 (Exchange Drive). | Add additional lanes and construct routes on new location. | 0.7 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007E | Statewide Mobility | BG50200, T(M) | 2028 | 8900000 | 2028 | 420000 | 2031 | 12600000 |  |  | 21920000 | COMBINED WITH U-5736.
Onslow | NC 53 (Western Boulevard) | NCDOT | SR 2714 (Jacksonville Parkway) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5789 | Region B | BG50200, T(M) |  |  |  |  | 2025 | 9910000 |  |  | 9910000 | RIGHT-OF-WAY IN PROGRESS.
Onslow | NC 53 (Western Boulevard) | NCDOT | US 17 (Marine Boulevard) to NC 24 (Lejeune Boulevard) in Jacksonville. | Construct access management improvements. | 2.55 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5736 | Region B | BG50200, T(M) | 2028 | 16100000 | 2028 | 1600000 | 2031 | 54700000 |  |  | 72400000 | COMBINED WITH U-4007E.
Onslow | SR 1308 (Bell Fork Road) | NCDOT | SR 1403 (Country Club Road / Hargett Street). | Construct intersection improvements. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-6082 | Division 3 | BG50200, T(M) | 2025 | 2800000 | 2025 | 1100000 | 2028 | 12900000 |  |  | 16800000
Onslow | SR 1336 (Henderson Road) | NCDOT | SR 1308 (Gum Branch Road) to NC 53 (Western Boulevard). | Upgrade to reduced conflict intersections. | 1.13 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5903 | Division 3 | T | 2030 | 5900000 | 2030 | 4200000 | 2033 | 38500000 |  |  | 48600000
Onslow | SR 2714 (Jacksonville Parkway Extension) | NCDOT | NC 53 (Western Boulevard) to US 17 (New Bern Highway). | Widen to multi-lanes, partially on new location. | 3.83 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5791 | Division 3
Onslow | SR 2714 (Jacksonville Parkway) | NCDOT | NC 53 (Western Boulevard) to SR 1324 (Ramsey Road). | Widen to multi-lanes, partially on new location. | 1.55 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5791A | Division 3 | T | 2027 | 20900000 | 2027 | 1200000 | 2029 | 86000000 |  |  | 108100000 | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
Onslow | SR 2714 (Jacksonville Parkway) | NCDOT | SR 1324 (Ramsey Road) to US 17 (New Bern Highway). | Widen to multi-lanes, partially on new location. |  | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5791B | Not Funded | T | NOT FUNDED | 17600000 | NOT FUNDED | 4200000 | NOT FUNDED | 51400000 | NOT FUNDED |  | 73200000
Onslow | SR 2715 (Trade Street) | NCDOT | NC 53 (Western Boulevard) to McDaniel Drive in Jacksonville. | Construct roadway on new location. | 0.28 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5787 | Division 3 | T | 2026 | 2600000 | 2026 | 890000 | 2029 | 7600000 |  |  | 11090000
Onslow | US 17 | NCDOT | Fairway Drive to Drummer Kellum Road. | Add additional lanes and construct routes on new location. | 0 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007D | Not Funded | NHP, T(M) | NOT FUNDED | 32345000 | NOT FUNDED |  | NOT FUNDED | 16600000 | NOT FUNDED |  | 48945000
Onslow | US 17 | NCDOT | NC 172 (Sneads Ferry Road) and SR 1518 (Old Folkstone Road) intersections | Upgrade existing signal and NC 172 intersection and install signal at SR 1518 (Old Folkstone Road) intersection. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-6065 | Statewide Mobility | BGLT5, HSIP |  |  |  |  | 2025 | 2000000 |  |  | 2000000
Onslow | US 17 | NCDOT | US 17 Business (Marine Boulevard) intersection in Jacksonville | Upgrade at-grade intersection to partial interchange. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5951 | Region B | BG50200, T(M) | 2027 | 350000 | 2027 | 330000 | 2029 | 22600000 |  |  | 23280000
Onslow | US 17 | NCDOT | US 17 Business to SR 1326 (Drummer Kellum Road) in Jacksonville. | Add additional lanes and construct routes on new location. | 1.4 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007
Onslow | US 17 | NCDOT | Western Boulevard to Fairway Drive. | Add additional lanes and construct routes on new location. | 0 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007C | Not Funded | NHP, T(M) | NOT FUNDED | 34775000 | NOT FUNDED |  | NOT FUNDED | 26300000 | NOT FUNDED |  | 61075000
Onslow | US 17 (Wilmington Highway) | NCDOT | MCAS New River Main Gate | Improve roadway to Douglas Gate Entrance. |  | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5735A | Exempt | O |  |  |  |  | 2021 | 1075000 |  |  | 1075000 | COMPLETE. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS.
Onslow | US 17 (Wilmington Highway) | NCDOT | SR 1130 (Old Maplehurst Road) in Jacksonville. | Construct interchange and associated improvements to MCAS New River main gate. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5735 | Region B | BG50200, T(M) | 2028 | 38102000 | 2028 | 6300000 | 2032 | 109400000 |  |  | 153802000
Onslow | US 17 Business (Marine Boulevard) | NCDOT | SR 1308 (Bell Fork Road) in Jacksonville. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5728 | Region B | BG50200, T | 2024 | 590000 |  |  | 2026 | 6900000 |  |  | 7490000 | RIGHT-OF-WAY IN PROGRESS.
Onslow | US 17 Business (Marine Boulevard) | NCDOT | SR 1336 (Henderson Drive) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5950 | Region B | BG50200, T(M) | 2025 | 100000 | 2025 | 200000 | 2026 | 1500000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
Onslow | US 258 / NC 24 (Richlands Highway) | NCDOT | SR 1212 (Pony Farm Road) to SR 1213 (Blue Creek Road). | Construct reduced conflict intersections. | 2.16 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5739 | Region B | T | 2028 | 2600000 | 2028 | 3200000 | 2031 | 31600000 |  |  | 37400000 | PROJECT BEING LET WITH WITH U-5716.
Onslow | NC 53 (Western Boulevard) | NCDOT | SR 1336 (Henderson Drive) intersection in Jacksonville. | Construct intersection improvements. | 0.5 | Highway | Transition | 3 | Jacksonville Urban Area MPO | W-5203U | Region B | HF(M), HSIP |  |  | 2023 | 61000 | 2023 | 2363000 |  |  | 2424000 | UNDER CONSTRUCTION.
Onslow | SR 1308 (Gum Branch Road) | NCDOT | West of SR 1313 (Mills Fields Road) to east of SR 1324 (Ramsey Road) in Jacksonville. | Modernize roadway, provide paved shoulders, and construct intersection improvements. | 7.42 | Highway | Transition | 3 | Jacksonville Urban Area MPO | U-4906 | Pre-STI (Transition) | BGANY, T(M) |  |  |  |  | 2021 | 16095000 |  |  | 16095000 | UNDER CONSTRUCTION.
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for Technology upgrade such as vehicle tracking, passenger information, data communication, traffic signal priority |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TT-4907 | Public Transit | 5307, L | [6 empty] | 2020 | 1140000 | 1140000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Expansion bus fixed route. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TA-4943 | Public Transit | 5307, L, S | [6 empty] | 2020 | 1587000 | 1587000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for safety and security, minimum set 1 % aside. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TS-5114 | Public Transit | 5307 | [6 empty] | 2020 | 116000 | 116000 | FUNDS AUTHORIZED IN PROGRESS
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Replace bus fixed route. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TA-4944 | Public Transit | 5307, L | [6 empty] | 2020 | 2516000 | 2516000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Various locations | Construct An Urban Fixed-Route Satellite Transfer Facility For Jacksonville Transit To Include Public Parking, Shelters, Restroom And Passenger Terminal. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TL-0001 | Public Transit | 5307 |  |  |  |  | 2020 | 8000000 |  |  | 8000000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Various locations | Retrofitting of Existing Side Walk and Constructing New Side Walk. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TL-0002 | Public Transit | 5307 |  |  |  |  | 2020 | 1230000 |  |  | 1230000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 3 | Jacksonville Urban Area MPO | TO-4923 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 7990000 | 7990000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for planning assistance - 5303 |  | Public Transportation (Transit) | Planning | 3 | Jacksonville Urban Area MPO | TP-5102 | Public Transit | 5303, L, S | [6 empty] | 2020 | 335000 | 335000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for planning assistance -5307 |  | Public Transportation (Transit) | Planning | 3 | Jacksonville Urban Area MPO | TP-4908 | Public Transit | 5307, L, S | [6 empty] | 2020 | 745000 | 745000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-4952 | Public Transit | 5307, L | [6 empty] | 2020 | 761000 | 761000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for preventive maintenance along fixed route. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5109 | Public Transit | 5307, L | [6 empty] | 2020 | 2076000 | 2076000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Various locations | Funding for Jacksonville Transit mobility management. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5220 | Public Transit | 5307, L, S | [6 empty] | 2020 | 311000 | 311000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Various locations | Funding for mobility management. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5225C | Public Transit | 5307, L | [6 empty] | 2020 | 653000 | 653000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Various locations | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5225 | Public Transit | 5307, L | [6 empty] | 2020 | 149000 | 149000
Onslow | Jacksonville Transit | JACKSONVILLE TRANSIT | Systemwide | Funding for downtown transit center. |  | Public Transportation (Transit) | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | TD-4904 | Public Transit | 5307, L(M) |  |  |  |  | 2025 | 2654000 |  |  | 2654000
Onslow, Brunswick, New Hanover | Various | NCDOT | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO | W-5203DIV | Division 3
Onslow, Duplin, Brunswick, New Hanover, Pender, Sampson | US 17; US 258; US 421; NC 24; NC 87 | NCDOT | Various locations in Division 3 | Upgrade guardrail end units. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Cape Fear RPO, Mid-Carolina RPO, Grand Strand Area Transportation Study | HS-2403E | Region B | HSIP |  |  |  |  | 2025 | 352000 |  |  | 352000 | UNDER CONSTRUCTION.
Onslow, Jones | US 17 | NCDOT | South of Belgrade to north of Maysville. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 4.36 | Highway | Transition | 2, 3 | Jacksonville Urban Area MPO, Down East RPO | R-2514B | Pre-STI (Transition) | T |  |  |  |  | 2023 | 6000 |  |  | 6000 | COMPLETE.
Onslow, Pender | US 17 | NCDOT | Pender County line to mile marker 19.3 in Onslow County. | Install shoulder rumble stripes. | 34.89 | Highway | Safety | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Cape Fear RPO | W-5803B | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 476000 |  |  | 476000 | COMPLETE.
Onslow, Pender, Sampson, Duplin, New Hanover | NC 53; US 117 (Future I-795); US 701 | NCDOT | Various locations along routes | Install center and edgeline sinusoidal rumble stripes. | 63.83 | Highway | Safety | 3 | Cape Fear RPO, Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO | HS-2403B | Region B | HSIP, T(M) |  |  |  |  | 2026 | 3760000 |  |  | 3760000
Orange | Bolin Creek Greenway Phase Two | CARRBORO | Lake Hogan Greenway to Jones Creek/Twin Creeks greenways. | Construct greenway. |  | Bike & Ped | Locally Selected | 7 | Triangle West TPO | BL-0151 | Division 7 | L(M), TADA | [6 empty] | 2027 | 400000 | 400000
Orange | Cameron Avenue | CHAPEL HILL | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Bike & Ped | Locally Selected | 7 | Triangle West TPO | BL-0101 | Division 7 | BGDA, L(M) | 2026 | 175000 |  |  | 2027 | 725000 | 2024 | 50000 | 950000
Orange | NC 54 | NCDOT | Westbrook Drive in Carrboro to west of US 15 / US 501 / NC 86 (South Columbia Street) interchange in Chapel Hill | Construct sidewalk and install pedestrian signals, crosswalks, and refuge islands at selected locations. | 1.55 | Bike & Ped | Locally Selected | 7 | Triangle West TPO | BL-0044 | Division 7 | BGDA, HF, HF(M), L(M) |  |  |  |  | 2025 | 1939000 | 2022 | 175000 | 2114000 | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION.
Orange | Shelton Street; East Poplar Avenue; Maple Avenue | CARRBORO | Hillsborough Road to North Greensboro Street; West Main Street to North Greensbor Street; East Braxton Foushee Street to end of Maple Avenue | Install pavement markings on Shelton Street, construct pedestrian lane on East Poplar Avenue, and construct contraflow lane on Maple Avenue. |  | Bike & Ped | Locally Selected | 7 | Triangle West TPO | BL-0149 | Division 7 | BGDA, L(M) |  |  |  |  | 2026 | 1112000 |  |  | 1112000
Orange | SR 1006 (Orange Grove Road) |  | Hillsborough | Construct transit access sidewalk. | 0.5 | Bike & Ped | Locally Selected | 7 | Triangle West TPO | BL-0139 | Division 7 | L(M), TADA | [6 empty] | 2025 | 450000 | 450000
Orange | SR 1750 (North Estes Drive) | CHAPEL HILL | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Bike & Ped | Locally Selected | 7 | Triangle West TPO | C-5179 | Exempt | BGDA, BGDACV, CMAQ, L, L(M) |  |  |  |  | 2020 | 6433000 |  |  | 6433000 | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
Orange | SR 1777 (Homestead Road) | DURHAM | SR 1843 (Seawell School Road) to SR 1733 (Weaver Dairy Road Extension) | Construct sidewalks. |  | Bike & Ped | Locally Selected | 7 | Triangle West TPO | U-4726IK | Division 7 | BGDA, L(M) |  |  |  |  | 2023 | 2000000 |  |  | 2000000
Orange | SR 1919 (Smith Level Road / South Greensboro Street) | CARRBORO | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Bike & Ped | Locally Selected | 7 | Triangle West TPO | C-5650 | Division 7 | BGANY, CMAQ, L(M) | 2026 | 125000 |  |  | 2027 | 2676000 | 2023 | 10000 | 2811000
Orange | Various | CHAPEL HILL | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Bike & Ped | Locally Selected | 7 | Triangle West TPO | BL-0150 | Division 7 | L(M), TADA | 2027 | 176000 |  |  | 2027 | 2935000 | 2026 | 359000 | 3470000
Orange | Various | DURHAM | Various | Install bicycle detection at signalized intersections. |  | Bike & Ped | Locally Selected | 7 | Triangle West TPO | U-4726DF | Exempt | BGDA, CMAQ, L(M) |  |  |  |  | 2024 | 156000 |  |  | 156000
Orange | Ephesus Church Road | TOWN OF CHAPEL HILL | US 15 / US 501 Bypass (Fordham Boulevard) to Pope Road near Chapel Hill. | Construct sidewalks and bike lanes to fill in gaps. | 1.6 | Bike & Ped | Other | 7 | Triangle West TPO | BO-2421 | Exempt | HP, L(M) | 2026 | 70000 | 2026 | 150000 | 2026 | 800000 | 2025 | 80000 | 1100000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204.
Orange | Morgan Creek Greenway | CHAPEL HILL | Existing Morgan Creek Greenway to SR 1919 (Smith Level Road) in Chapel Hill | Construct greenway and connections. |  | Bike & Ped | Other | 7 | Triangle West TPO | BO-2415 | Division 7 | BGDA, L(M), TADA | 2023 | 1173000 |  |  | 2024 | 1197000 |  |  | 2370000
Orange | Barnes Street | CARRBORO | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5890 | Division 7 | L(M), TAANY | 2027 | 420000 | 2027 | 230000 | 2028 | 450000 | 2026 | 46000 | 1146000
Orange | Orange County Bicycle Route 1 | CHAPEL HILL | Cleland Drive to Willow Drive in Chapel Hill | Upgrade existing off-road path and construct new section of path. | 0.67 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5721 | Division 7 | BGDA, L(M), TADA |  |  |  |  | 2026 | 2700000 |  |  | 2700000
Orange | SR 1005 (Jones Ferry Road) | CARRBORO | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5880 | Division 7 | L(M), TAANY | 2027 | 80000 | 2027 | 180000 | 2028 | 690000 | 2026 | 89000 | 1039000
Orange | SR 1780 (Estes Drive) | CHAPEL HILL | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5886B | Division 7 | L(M), TAANY | 2028 | 864000 |  |  | 2031 | 3104000 | 2022 | 534000 | 4502000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7.
Orange | SR 1780 (Estes Drive) | CHAPEL HILL | SR 1772 (North Greensboro Street) in Carrboro to NC 86 (Martin Luther King, Jr. Boulevard) in Chapel Hill | Construct bicycle and pedestrian improvements. | 1.7 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5886 | Division 7
Orange | SR 1780 (Estes Drive) | CHAPEL HILL | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5886A | Division 7 | L(M), TAANY | 2030 | 900000 | 2030 | 1100000 | 2033 | 7000000 | 2025 | 170000 | 9170000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7.
Orange | US 15 / US 501 | CHAPEL HILL | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Bike & Ped | STI (Prioritization) | 7 | Triangle West TPO | EB-5998 | Division 7 | L(M), TAANY | 2028 | 480000 | 2028 | 1100000 | 2031 | 7200000 | 2026 | 204000 | 8984000 | COORDINATE WITH U-5304
Orange | Jones Creek Greenway | CARRBORO | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Bike & Ped | Transition | 7 | Triangle West TPO | C-5181 | Exempt | BGDA, CMAQ, L(M) |  |  |  |  | 2026 | 1300000 | 2022 | 12000 | 1312000
Orange | Morgan Creek Greenway | CARRBORO | Phase 1 - Abbey Lane to SR 1919 (Smith Level Road) in Carrboro and Piedmont EMC utility easement to SR 1919 (Smith Level Road) in Carrboro | Construct greenway and connections. | 0.29 | Bike & Ped | Transition | 7 | Triangle West TPO | EL-4828A | Pre-STI (Transition) | BGDA, L(M), TADA |  |  |  |  | 2026 | 1992000 |  |  | 1992000
Orange | Morgan Creek Greenway | CARRBORO | SR 1919 (Smith Level road) to University Lake in Carrboro | Construct greenway and connections. | 1.7 | Bike & Ped | Transition | 7 | Triangle West TPO | EL-4828 | Pre-STI (Transition) | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO
Orange | Riverwalk Trail | HILLSBOROUGH | Along Eno River connecting River Park, Gold Park, and Occoneechee Mountain State Natural Area in Hillsborough. | Construct paved off-road trail and sidewalk to provide pedestrian and bicycle connections. | 2.17 | Bike & Ped | Transition | 7 | Triangle West TPO | C-5184 | Exempt | [10 empty] | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH
Orange | NC 86 | NCDOT | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Triangle West TPO | B-6037 | Region D | BFP, T(M) | 2025 | 2700000 | 2025 | 970000 | 2027 | 11400000 |  |  | 15070000
Orange | SR 1146 (West Ten Road) | NCDOT | SR 1114 (Buckhorn Road) to West of SR 1137 (Bushy Cook Road) in Mebane. | Construct overlay, paved shoulders and turn lanes. | 1.68 | Highway | Economic Development | 7 | Triangle West TPO | U-6245 | Division 7 | T |  |  |  |  | 2021 | 829000 | 2020 | 109000 | 938000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE
Orange | I-40 / I-85 | NCDOT | West of SR 1114 (Buckhorn Road) to west of SR 1006 (Orange Grove Road). | Rehabilitate pavement. | 6.74 | Highway | Interstate Maintenance | 7 | Triangle West TPO, Burlington-Graham MPO | I-5958 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2027 | 9500000 |  |  | 9500000
Orange | Exchange Park Lane | HILLSBOROUGH | Faribault Lane to US 70 Business (South Churton Street) in Hillsborough. | Repair bridge 670241 over Eno River. | 0.13 | Highway | Locally Selected | 7 | Triangle West TPO | HL-0045 | Division 7 | BGDA, L(M) |  |  |  |  | 2026 | 401000 |  |  | 401000
Orange | SR 1010 (Franklin Street); Rosemary Street |  | Merritt Mill Road to Henderson Street, and connecting streets in Downtown Chapel Hill. | Install new mast arm and curb and sidewalk improvements. | 2 | Highway | Other | 7 | Triangle West TPO | HO-0013 | Exempt | DP, L | 2026 | 250000 | 2026 | 550000 | 2026 | 1300000 | 2024 | 400000 | 2500000 | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. DEMO ID NC201.
Orange | US 15 / US 501 | NCDOT | SR 1742 (Ephesus Church Road) intersection | Improve intersection. | 0.5 | Highway | Pre-STI (Historic) | 7 | Triangle West TPO | U-5304C | [11 empty] | WORK COMPLETED UNDER U-5550.
Orange | NC 86 (Martin Luther King Boulevard) | NCDOT | Critz Drive intersection. | Install pedestrian improvements. | 0.5 | Highway | Safety | 7 | Triangle West TPO | HS-2007J | Region D | HSIP, T(M) |  |  |  |  | 2025 | 510000 |  |  | 510000 | UNDER CONSTRUCTION
Orange | SR 1009 (Old NC 86) | NCDOT | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Highway | Safety | 7 | Triangle West TPO | HS-2007H | Division 7 | HSIP, T(M) | 2025 | 10000 | 2025 | 4000 | 2026 | 137000 |  |  | 151000
Orange | Various | NCDOT | Routes in Chapel Hill and Carrboro. | Install pedestrian accommodations at multiple signalized intrsections. | 0.5 | Highway | Safety | 7 | Triangle West TPO | HS-2407G | Division 7 | HSIP | 2027 | 600000 | 2027 | 170000 | 2027 | 840000 |  |  | 1610000
Orange | Various | NCDOT | Routes in Chapel Hill. | Upgraded traffic signals and install pedestrian accomodations at multiple signalized intersections. | 0.5 | Highway | Safety | 7 | Triangle West TPO | HS-2407H | Division 7 | HSIP |  |  |  |  | 2027 | 350000 |  |  | 350000
Orange | I-40 | NCDOT | I-85 interchange in Orange County to Durham County line. | Towing contract for I-3306A construction. |  | Highway | STI (Prioritization) | 7 | Triangle West TPO | I-3306AD | Statewide Mobility | T |  |  |  |  | 2023 | 2280000 |  |  | 2280000 | UNDER CONSTRUCTION
Orange | I-40 | NCDOT | I-85 interchange in Orange County to Durham County line. | Widen to six lanes, improve NC 86 interchange, and install ITS. | 11.73 | Highway | STI (Prioritization) | 7 | Triangle West TPO | I-3306A | Statewide Mobility | NHP, T(M) | 2021 | 10724000 | 2021 | 628000 | 2021 | 303565000 |  |  | 314917000 | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035
Orange | I-85 | NCDOT | NC 86 in Hillsborough | Upgrade interchange. | 1 | Highway | STI (Prioritization) | 7 | Triangle West TPO | I-0305C | Not Funded | NHP, T(M) | NOT FUNDED | 11800000 | NOT FUNDED | 3100000 | NOT FUNDED | 56500000 | NOT FUNDED |  | 71400000 | SCOPE PREVIOUSLY INCLUDED UNDER I-5984.
Orange | I-85 | NCDOT | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 7 | Triangle West TPO | I-0305B | Statewide Mobility | NHP, T(M) | 2030 | 67100000 | 2030 | 1200000 | 2034 | 96200000 |  |  | 164500000 | SCOPE PREVIOUSLY INCLUDED UNDER I-5967.
Orange | NC 54 | NCDOT | SR 1006 (Orange Grove Road) | Improve intersection. | 0.5 | Highway | STI (Prioritization) | 7 | Triangle West TPO | R-5821B | Division 7 | [10 empty] | UNDER CONSTRUCTION
Orange | NC 54 | NCDOT | SR 1006 (Orange Grove Road) to SR 1107 / SR 1937 (Old Fayetteville Road) | Construct operational improvements, including bicycle/pedestrian accommodations. | 6.07 | Highway | STI (Prioritization) | 7 | Triangle West TPO | R-5821A | Not Funded | T | NOT FUNDED | 11600000 | NOT FUNDED | 350000 | NOT FUNDED | 9700000 | NOT FUNDED |  | 21650000
Orange | NC 54 | NCDOT | SR 1006 (Orange Grove Road) to SR 1107 / SR 1937 (Old Fayetteville Road). | Construct operational improvements, including bicycle/pedestrian accommodations, and improve SR 1006 (Orange Grove Road)intersection. | 6.1 | Highway | STI (Prioritization) | 7 | Triangle West TPO, Central Pines RPO | R-5821
Orange | NC 54 | NCDOT | US 15/ US 501 interchange | Upgrade interchange | 1 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5774A | Not Funded | T | NOT FUNDED | 4800000 | NOT FUNDED | 720000 | NOT FUNDED | 28600000 | NOT FUNDED |  | 34120000
Orange | NC 86 | NCDOT | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Highway | STI (Prioritization) | 7 | Triangle West TPO | I-3306AC | Region D | NHP, T(M) | 2025 | 1400000 | 2025 | 670000 | 2027 | 7300000 |  |  | 9370000
Orange | SR 1009 (South Churton Street) | NCDOT | I-40 to Eno River in Hillsborough. | Widen to multi-lanes. | 2.22 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5845 | Division 7 | T | 2030 | 19700000 | 2030 | 7200000 | 2034 | 50500000 |  |  | 77400000 | COMBINED LET WITH I-0305B
Orange | SR 1772 (Greensboro Street) | NCDOT | SR 1780 (Estes Drive) intersection in Carrboro. | Construct roundabout. |  | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5846 | Division 7 | [10 empty] | UNDER CONSTRUCTION
Orange | US 15 / US 501 | NCDOT | NC 54 (Raleigh Road) to SR 1742 (Ephesus Church Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 1.92 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5304D | Not Funded | T | NOT FUNDED | 5000000 | NOT FUNDED | 344000 | NOT FUNDED | 30001000 | NOT FUNDED |  | 35345000
Orange | US 15 / US 501 | NCDOT | NC 86 (North Columbia Street) to NC 54 (Raleigh Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 2.13 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5304B | Not Funded | T | NOT FUNDED | 6000000 | NOT FUNDED | 285000 | NOT FUNDED | 22001000 | NOT FUNDED |  | 28286000
Orange | US 15 / US 501 | NCDOT | NC 86 (South Columbia Street) | Improve interchange. | 1 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5304A | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 1040000 | NOT FUNDED | 22001000 | NOT FUNDED |  | 33041000
Orange | US 15 / US 501 | NCDOT | SR 1902 (Manning Drive) intersection | Convert at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5304E | Not Funded | T | NOT FUNDED | 12000000 | NOT FUNDED | 446000 | NOT FUNDED | 25000000 | NOT FUNDED |  | 37446000
Orange | US 15 / US 501 (Fordham Boulevard) | NCDOT | SR 1742 (Ephesus Church Road) in Chapel Hill. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 7 | Triangle West TPO | U-5550 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Fund Ex rider senior shuttle 5310 grant. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TC-0043 | Public Transit | 5310, L | [6 empty] | 2025 | 548000 | 548000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Fund mobilty management under 5310 grant. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TC-0042 | Public Transit | 5307, S | [6 empty] | 2025 | 75000 | 75000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Purchase paratransit vehicle replacement. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TA-4748 | Public Transit | 5307, 5339(b), L | [6 empty] | 2020 | 2273000 | 2273000 | FUNDS AUTHORIZED IN PROGRESS
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Purchase replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TA-4726 | Public Transit | 5307, CMAQ, CPF, L | [6 empty] | 2020 | 18123000 | 18123000 | FUNDS AUTHORIZED IN PROGRESS
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Replace van. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TA-4979 | Public Transit | 5307, L, S | [6 empty] | 2023 | 1584000 | 1584000 | FUNDS AUTHORIZED IN PROGRESS
Orange | GoTriangle | GO TRIANGLE | Town of Hillsborough | Construct park and ride lot. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TD-5295 | Public Transit | 5307, L, S |  |  |  |  | 2023 | 2640000 |  |  | 2640000 | UNDER CONSTRUCTION BY GO TRIANGLE
Orange | GoTriangle | GOTRIANGLE | Systemwide | Access improvements at the intersection of US 15 -501 and Eastowne drive. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TL-0018 | Public Transit | CMAQ, L |  |  |  |  | 2023 | 400000 | 2023 | 100000 | 500000
Orange | Orange Public Transit | ORANGE PUBLIC TRANSIT | Systemwide | Purchase new bus of less than 30-feet long. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Triangle West TPO | TA-6731 | Public Transit | L | [6 empty] | 2025 | 56000 | 56000
Orange | Chapel Hill Transit |  | Various locations | Purchase 2 ADA accessible mini vans. |  | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TL-0049 | Exempt | CMAQ, L | [6 empty] | 2024 | 187000 | 187000
Orange | Chapel hill Transit | CHAPEL HILL TRANSIT | Systemwide | Funding to acquire five new transit electric vehicles |  | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TL-0034 | Exempt | CMAQ, L(M) | [6 empty] | 2024 | 2708000 | 2708000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide. | Purchase electric bus |  | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TL-0066 | Division 7 | BGDA, L(M) | [6 empty] | 2027 | 1150000 | 1150000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Various locations | Improve all bus stops. |  | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TL-0062 | Division 7 | CPF, L(M) |  |  |  |  | 2026 | 850000 |  |  | 850000
Orange | Chapel Hill Transit | TOWN OF CHAPEL HILL | Southern Village park and ride lot to Eubanks Road park and ride lot. | Construct North-South Bus Rapid Transit (NSBRT) system. | 8.2 | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TL-0035 | Public Transit | 5307, L |  |  |  |  | 2027 | 201548000 | 2024 | 10737000 | 212285000
Orange | GoTriangle |  | Various locations | Improve three bus stops in Orange county at sites 701, 705, and 706. |  | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TL-0051 | Public Transit | 5307, L(M) |  |  |  |  | 2024 | 250000 |  |  | 250000
Orange | Orange County Transit |  | Systemwide | Funding for 2 ADA accessible mini vans. Expand micro transit. |  | Public Transportation (Transit) | Locally Selected | 7 | Central Pines RPO | TN-6126 | Exempt | 5307, L | [6 empty] | 2024 | 188000 | 188000
Orange | Orange Public Transit | ORANGE PUBLIC TRANSIT | Systemwide | Funding for one replacement LTV (25') and radio, vehicle lettering and logos, and on board camera. |  | Public Transportation (Transit) | Locally Selected | 7 | Triangle West TPO | TD-5155 | Division 7 | BGDA, L | [6 empty] | 2022 | 154000 | 154000 | IN PROGRESS BY ORANGE PUBLIC TRANSIT
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Triangle West TPO | TO-5133 | Public Transit | SMAP | [6 empty] | 2020 | 28560000 | 28560000 | FUNDS AUTHORIZED IN PROGRESS
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Purchase five electric transit buses. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 7 | Triangle West TPO | TN-6133 | Exempt | CMAQ, L, L(M) | [6 empty] | 2025 | 2708000 | 2708000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Triangle West TPO | TG-4731B | Public Transit | 5307, L | [6 empty] | 2020 | 20372000 | 20372000 | FUNDS AUTHORIZED IN PROGRESS
Orange | Orange county public transit |  | Systemwide | Operating assistance |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Triangle West TPO | TM-0066 | Public Transit | 5307, L | [6 empty] | 2025 | 1716000 | 1716000
Orange | Orange County STEAM | Orange County | Systemwide | Funding for education program, expand and manage a volunteer driver program, and purchase service for transportation operators. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Triangle West TPO | TM-0068 | Public Transit | 5310, L | [6 empty] | 2025 | 480000 | 480000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Regionwide. | Expand facility. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Triangle West TPO | TG-0028 | Public Transit | 5339(b), L | [6 empty] | 2025 | 21384000 | 21384000
Orange | Chapel Hill Transit | CHAPEL HILL TRANSIT | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Triangle West TPO | TG-4732A | Public Transit | 5307, S | [6 empty] | 2020 | 2880000 | 2880000 | FUNDS AUTHORIZED IN PROGRESS
Orange | Orange Public Transit | ORANGE PUBLIC TRANSIT | Systemwide | Purchase two light transit vehicles. |  | Public Transportation (Transit) | STI (Prioritization) | 7 | Central Pines RPO, Triangle West TPO | TA-6721 | Division 7 | BGANY, L | [6 empty] | 2022 | 218000 | 218000
Orange | SR 1120 (Mount Willing Road) | NCDOT | Crossing 735145T near Efland | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Triangle West TPO | RX-2007B | Division 7 | RR |  |  |  |  | 2025 | 800000 |  |  | 800000 | UNDER CONSTRUCTION
Orange | NC Railroad / NS NC Line | NCDOT | SR 1120 (Mt. Willing Road) intersection in Efland. | Realign SR 1120 (Mt. Willing Road) to line up with Efland - Cedar Grove Road at US 70, construct grade separation, and close existing at-grade crossing (#735145t). |  | Rail | STI (Prioritization) | 7 | Triangle West TPO | RP-0005 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 |  |  | 18300000
Orange | Norfolk Southern H Line | NCDOT | Mile marker 41.7 in Hillsborough. | Construct platform, passenger rail station building, site access, utilities, and parking. |  | Rail | STI (Prioritization) | 7 | Triangle West TPO | P-5701 | Division 7 | [10 empty] | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT.
Orange | Norfolk Southern H Line | NCDOT | Milepost 41.7 in Hillsborough. | Construct passenger rail station building, site access, utilities, and parking. |  | Rail | STI (Prioritization) | 7 | Triangle West TPO | P-5701A | Division 7 | O, T |  |  |  |  | 2022 | 6860000 |  |  | 6860000
Orange | Norfolk Southern H Line | NCDOT | Milepost 41.7 in Hillsborough. | Construct station platform and realign curve at Milepost 41.4. |  | Rail | STI (Prioritization) | 7 | Triangle West TPO | P-5701B | Division 7 | T |  |  |  |  | 2025 | 1000000 |  |  | 1000000
Orange, Alamance | NC 49 | NCDOT | NC 62 in Alamance County to NC 86 in Orange County. | Install rumble strips and 6-inch long life pavement markings. | 9 | Highway | Safety | 7 | Central Pines RPO, Burlington-Graham MPO | HS-2407S | Region D | HSIP, T(M) |  |  |  |  | 2027 | 700000 |  |  | 700000
Orange, Durham | I-40 | NCDOT | I-85 in Orange County to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Widen to six lanes and install ITS. | 20.7 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | I-3306
Orange, Durham | I-85 | NCDOT | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | I-0305A | Not Funded | NHP, T(M) | NOT FUNDED | 17900000 | NOT FUNDED | 1200000 | NOT FUNDED | 120898000 | NOT FUNDED |  | 139998000
Orange, Durham | I-85 | NCDOT | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County. | Construct additional lanes. | 7.8 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | I-0305 | [11 empty] | COMBINED LET WITH U-5845
Orange, Durham | NC 54 | NCDOT | West of US 15 / US 501 in Orange County to east of SR 1110 (Barbee Chapel Road) in Durham County | Upgrade roadway corridor. | 1.22 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | U-5774B | Not Funded | T | NOT FUNDED | 31300000 | NOT FUNDED | 7600000 | NOT FUNDED | 54100000 | NOT FUNDED |  | 93000000
Orange, Durham | US 15 / US 501 | NCDOT | SR 1742 (Ephesus Church Road) to I-40 | Construct corridor capacity improvements. | 1.75 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | U-5304F | Region C, D | T | 2028 | 4400000 | 2028 | 1700000 | 2030 | 77500000 |  |  | 83600000
Orange, Durham | US 15 / US 501 (Fordham Boulevard) | NCDOT | NC 86 (South Columbia Street) to I-40 in Chapel Hill. | Upgrade corridor. | 6 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | U-5304 | [11 empty] | COORDINATE WITH EB-5998 AND U-5774
Orange, Durham | Various | NCDOT | Chapel Hill Carrboro | Implement an improved signal system for the Town of Chapel Hill and Town of Carrboro. | 14.79 | Highway | STI (Prioritization) | 5, 7 | Triangle West TPO | HP-0006 | Region C, D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13910000 |  |  | 15610000
Orange, Durham | SR 1838 (Old Durham) / SR 2220 (Old Chapel Hill Road) | NCDOT | US 15 / US 501 in Orange County to SR 1113 (Pope Road) in Durham County. | Construct bicycle, pedestrian, and transit improvements and construct roundabout. | 1 | Highway | Transition | 5, 7 | Triangle West TPO | EB-4707A | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Pamlico | Vandemere | NCDOT | Various locations in Vandemere | Funding for bicycle and pedestrian project acceleration plan. |  | Bike & Ped | Other | 2 | Down East RPO | M-0570N | Exempt | CRPLT5, HF(M), L | [6 empty] | 2025 | 48000 | 48000
Pamlico | NC 306 | NCDOT | Structure 680078 (Ferry Ramp) over the Neuse River at the Minnesott Beach Ferry Terminal. | Replace Structure. | 0.1 | Highway | Bridges | 2 | Down East RPO | BR-0173 | Region B | FBP |  |  |  |  | 2025 | 9100000 |  |  | 9100000
Pamlico | NC 55 | NCDOT | Bridge 680038 over Trent Creek. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4593 | Region B | NHPB, T(M) |  |  |  |  | 2022 | 6137000 |  |  | 6137000 | UNDER CONSTRUCTION.
Pamlico | SR 1302 (Janiero Road) | NCDOT | Bridge 680057 over Dawson Creek. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-5995 | Division 2 | BGOFF | 2022 | 600000 |  |  | 2026 | 6300000 |  |  | 6900000
Pasquotank | NC 344 (Weeksville Road) |  | Various locations in Elizabeth City | Accessibility and connectivity plan. | 3.6 | Bike & Ped | Locally Selected | 1 | Albemarle RPO | BO-2420 | Exempt | DP | [6 empty] | 2024 | 2000000 | 2000000 | 'DP' FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS.
Pasquotank | US 17 (Future I-87) | NCDOT | Perquimans County line to north end of US 17 (Elizabeth City) Bypass. | Rehabilitate pavement. | 10.29 | Highway | Interstate Maintenance | 1 | Albemarle RPO | I-6029 | Statewide Mobility | NHP, NHPIM, T(M) |  |  |  |  | 2020 | 11886000 |  |  | 11886000 | COMPLETE. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034.
Pasquotank | Elizabeth City | NCDOT | Firehouse Subs. | Install 4 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 1 | Albemarle RPO | HV-0001A | Division 1 | NEVI, O, S(M) |  |  |  |  | 2025 | 871000 |  |  | 871000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE
Pasquotank | NC 344 | NCDOT | South of airport entrance to SR 1100 (Sawmill Road). | Install rumble stripes and pavement markings. | 3.72 | Highway | Safety | 1 | Albemarle RPO | HS-2001I | Region A | HSIP, T(M) |  |  |  |  | 2024 | 160000 |  |  | 160000
Pasquotank | NC 344 | NCDOT | Tanglewood Parkway to Mount Everest Drive in Elizabeth City. | Remove portion of median island and install pedestrian accommodations. | 0.36 | Highway | Safety | 1 | Albemarle RPO | HS-2401M | Region A | HSIP, T(M) |  |  |  |  | 2025 | 90000 |  |  | 90000
Pasquotank | SR 1333 (West Main Street Extension) | NCDOT | 0.6 miles north of SR 1338 (Berea Church Road) to 0.2 miles south of SR 1338 (Berea Church Road). | Improve horizontal alignment with curve improvements. | 0.8 | Highway | Safety | 1 | Albemarle RPO | W-5701C | Division 1 | HSIP, T(M) | 2024 | 170000 |  |  | 2025 | 2165000 |  |  | 2335000 | UNDER CONSTRUCTION.
Pasquotank | SR 1354 (Millpond Road) | NCDOT | US 158 to SR 1001 (Turnpike Road). | Upgrade pavement markings. | 4.42 | Highway | Safety | 1 | Albemarle RPO | HS-2001C | Division 1 | HSIP, T(M) |  |  |  |  | 2024 | 40000 |  |  | 40000
Pasquotank | US 17 Business (Ehringhaus Street) | NCDOT | NC 344 (Halstead Boulevard) intersection in Elizabeth City | Install audible pedestrian signals. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401F | Region A | HSIP, T(M) |  |  |  |  | 2025 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
Pasquotank | US 17 (Hughes Boulevard) | NCDOT | SR 1308 (Church Street) to US 17 Business (North Road Street). | Construct access management improvements. | 1.49 | Highway | STI (Prioritization) | 1 | Albemarle RPO | U-5940 | Region A | NHP, T(M) | 2027 | 18700000 | 2027 | 4700000 | 2030 | 21100000 |  |  | 44500000
Pasquotank | US 17 Business (Future I-87) | NCDOT | SR 1145 (Oak Stump Road). | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 1 | Albemarle RPO | U-5939 | Region A | BG5T50, T(M) | 2025 | 5400000 | 2025 | 530000 | 2028 | 17300000 |  |  | 23230000 | RIGHT-OF-WAY IN PROGRESS
Pasquotank | Various | NCDOT | Routes in Elizabeth City. | Upgrade signal system. | 20 | Highway | STI (Prioritization) | 1 | Albemarle RPO | U-5942 | Region A | BG5T50, HP |  |  |  |  | 2021 | 5359000 |  |  | 5359000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368.
Pasquotank, Camden, Perquimans | Various | NCDOT | Routes in Division 1. | Upgrade warning signs at curves. |  | Highway | Safety | 1 | Albemarle RPO | HS-2001D | Division 1 | HSIP, T(M) |  |  |  |  | 2023 | 41000 |  |  | 41000 | UNDER CONSTRUCTION.
Pender | ACZ | HENDERSON FIELD (ACZ) | Henderson Field Airport | Acquire land (phase IV) for roadway relocation; relocate SR 1307 (Wallace Airport Road) and SR 1306 (Old Mill Road); extend runway (phase I). | 0 | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5744 | Division 3 | T | 2022 | 2113000 |  |  | 2024 | 8700000 |  |  | 10813000 | UNDER CONSTRUCTION.
Pender | ACZ | HENDERSON FIELD (ACZ) | Henderson Field Airport | Expand apron. |  | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5815 | Division 3 | T |  |  |  |  | 2027 | 8900000 |  |  | 8900000
Pender | ACZ | HENDERSON FIELD (ACZ) | Henderson Field Airport | Extend runway to 5500 feet |  | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5744A | Division 3 | T |  |  |  |  | 2027 | 4405000 |  |  | 4405000
Pender | Country Club multi-use path | PENDER COUNTY | Adjacent to SR 1565 (Country Club Drive) and SR 1593 (Jenkins Road) from SR 1563 (Sloop Point Loop Road) to SR 1592 (North St. Johns Church Road). | Construct multi-use path. | 3.91 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0154 | Division 3 | BGDA, L(M) | [6 empty] | 2026 | 886000 | 886000
Pender | SR 1510 (East Wilmington Street) |  | US 117 Business to US 117 Bypass Corridor in Burgaw | Construct eight foot multi-use path. | 0.67 | Bike & Ped | NCDOT Selected (Other Selection Process) | 3 | Cape Fear RPO | BN-0007 | Exempt | CRPLT5, L(M) |  |  |  |  | 2024 | 867000 | 2024 | 50000 | 917000
Pender | Burgaw | NCDOT | Various locations in Burgaw | Funding for bicycle and pedestrian project acceleration plan. |  | Bike & Ped | Other | 3 | Cape Fear RPO | M-0570Q | Exempt | CRPLT5, HF(M), L | [6 empty] | 2025 | 48000 | 48000
Pender | NC 53 | NCDOT | Bridge 700037 over Angola Creek | Replace bridge. | 0.1 | Highway | Bridges | 3 | Cape Fear RPO | BR-0174 | Region B | BFP |  |  |  |  | 2027 | 3000000 |  |  | 3000000
Pender | I-40 | NCDOT | West of US 117 (mile marker 388) to NC 210 (mile marker 408). | Rehabilitate pavement. | 15.05 | Highway | Interstate Maintenance | 3 | Cape Fear RPO | I-6040 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 19768000 |  |  | 19768000 | UNDER CONSTRUCTION.
Pender | SR 1563 (Sloop Point Road) | NCDOT | SR 1565 (Country Club Drive) intersection in Hampstead. | Install traffic signal. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0180 | Division 3
Pender | NC 50 (Roland Avenue) | NCDOT | NC 210 / SR 1534 (Belt Road) intersection in Surf City | Upgrade traffic signal and pavement markings. |  | Highway | Safety | 3 | Cape Fear RPO | HS-2403M | Region B | HSIP |  |  |  |  | 2027 | 40000 |  |  | 40000
Pender | SR 1114 (Blueberry Road) | NCDOT | SR 1113 (Montague Road) to NC 210 North of Wilmington. | Install rumble stripes. | 2.71 | Highway | Safety | 3 | Cape Fear RPO | HS-2403V | Division 3 | HSIP |  |  |  |  | 2027 | 162000 |  |  | 162000
Pender | SR 1216 (Piney Woods Road); SR 1002 (Island Creek Road); US 421 | NCDOT | US 421 to SR 1336 (Horse Branch Road); NC 210 to New Hanover County line; North of SR 1217 (Teddar Road) to New Hanover County line. | Install rumble stripes. | 13.41 | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO | HS-2403U | Division 3 | HSIP |  |  |  |  | 2025 | 1038000 |  |  | 1038000
Pender | US 117 | NCDOT | NC 53 intersection in Burgaw. | Upgrade traffic signal. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003AL | Region B | HSIP, T(M) |  |  |  |  | 2024 | 12000 |  |  | 12000
Pender | US 117 | NCDOT | SR 1411 (Ashton Road / Old River Road) intersection. | Install traffic signal. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003AC | Region B | HSIP, T(M) |  |  |  |  | 2025 | 324000 |  |  | 324000
Pender | US 117 | NCDOT | SR 1412 (New Road) intersection in Saint Helena. | Install traffic signal. |  | Highway | Safety | 3 | Cape Fear RPO | HS-2403AP | Region B | HSIP, T(M) |  |  |  |  | 2027 | 360000 |  |  | 360000
Pender | US 17 | NCDOT | NC 210 intersection in Surf City. | Revise traffic signal and install traffic signs. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003F | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 271000 |  |  | 271000
Pender | US 17 | NCDOT | SR 1561 (Sloop Point Road) northeast of Hampstead | Install traffic signal. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403K | Statewide Mobility | HSIP | 2026 | 10000 | 2026 | 2000 | 2026 | 300000 |  |  | 312000
Pender | US 421 | NCDOT | SR 1114 (Blueberry Road) north of NC 210 | Install rumble strips. | 8.9 | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO | HS-2403AY | Region B | HSIP |  |  |  |  | 2026 | 210000 |  |  | 210000
Pender | Dan Owen Drive Extension | NCDOT | SR 1570 (Factory Road) to Dan Owen Drive. | Construct reduced conflict intersections. |  | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5732A | Region B | [10 empty] | COMPLETE.
Pender | NC 210 | NCDOT | SR 1560 (Watts Landing Road) intersection in Surf City | Improve intersection. | 0.5 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5899 | Division 3 | BGANY, T(M) | 2025 | 820000 | 2025 | 210000 | 2027 | 7500000 |  |  | 8530000
Pender | NC 50 / NC 210 | NCDOT | SR 1534 (Belt Road) intersection Surf City | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5900 | Division 3 | T | 2026 | 4600000 | 2026 | 310000 | 2029 | 19500000 |  |  | 24410000
Pender | NC 53 | NCDOT | US 117 Business (Walker Street / Wilmington Street) intersection | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5701 | Region B | L, T | 2025 | 210000 | 2025 | 180000 | 2027 | 2800000 |  |  | 3190000 | L FUNDS REPRESENT PROPERTY DONATED BY THE TOWN OF BURGAW.
Pender | US 17 | NCDOT | NC 210 to US 17 north of Hampstead. | Construct freeway on new location. | 5.45 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | R-3300B | Region B | T | 2025 | 5000000 |  |  | 2022 | 229552000 |  |  | 234552000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE).
Pender | US 17 | NCDOT | SR 1582 (Washington Acres Road) to Vista Lane. | Construct reduced conflict intersections. | 5.51 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5732 | Statewide Mobility | T | 2029 | 25200000 | 2029 | 5100000 | 2032 | 60000000 |  |  | 90300000
Pender, New Hanover | US 17 | NCDOT | US 17 Bypass south of Hampstead to NC 210. | Construct freeway on new location. | 6.87 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | R-3300A | Region B | T | 2018 | 10000000 |  |  | 2026 | 234980000 |  |  | 244980000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
Pender, Onslow | Surf City | NCDOT | Various locations in Surf City | Funding for bicycle and pedestrian planning. |  | Bike & Ped | Other | 3 | Cape Fear RPO | M-0570P | Exempt | CRPANY, HF(M), L | [6 empty] | 2025 | 64000 | 64000
Pender, Onslow | Surf City | SURF CITY | Systemwide | Purchase two electric vehicles. |  | Public Transportation (Transit) | Locally Selected | 3 | Cape Fear RPO, Jacksonville Urban Area MPO | TN-6131 | Exempt | CRPANY, L(M) | [6 empty] | 2025 | 100000 | 100000
Perquimans | SR 1338 (Wynne Fork Road) | NCDOT | Bridge 710011 over Racoon Creek. | Replace bridge. | 0.25 | Highway | Bridges | 1 | Albemarle RPO | B-5606 | Division 1 | T |  |  |  |  | 2021 | 1545000 |  |  | 1545000 | COMPLETE. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
Perquimans | US 17 (Future I-87) | NCDOT | Bridges 710014 and 710080 over Perquimans River to SR 1304 (Cartwright Swamp Road) | Rehabilitate pavement. | 4.38 | Highway | Interstate Maintenance | 1 | Albemarle RPO | HI-0026 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2029 | 4400000 |  |  | 4400000
Perquimans | US 17 (Future I-87) | NCDOT | SR 1304 (Cartwright Swamp Road) to Pasquotank County line | Rehabilitate pavement. | 4.17 | Highway | Interstate Maintenance | 1 | Albemarle RPO | HI-0027 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2030 | 4200000 |  |  | 4200000
Perquimans | US 17 (Future I-87) | NCDOT | US 17 Business to bridges 710014 and 710080 over Perquimans River | Rehabilitate pavement. | 1.74 | Highway | Interstate Maintenance | 1 | Albemarle RPO | HI-0028 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2030 | 2000000 |  |  | 2000000
Perquimans | US 17 Business / NC 37 | NCDOT | South of Bridge 710008 (Perquimans River Bridge) to north of NC 37. | Replace bridge. | 0.82 | Highway | Pre-STI (Historic) | 1 | Albemarle RPO | R-4467 | Region A | T |  |  |  |  | 2019 | 65512000 | 2021 | 2415000 | 67927000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Perquimans | US 17 | NCDOT | West of SR 1220 (Wiggins Road) to east of SR 1227 (Swing Gate Road) / SR 1301 (Old Neck Road). | Close, modify, or install a crossover at three locations. | 0.8 | Highway | Safety | 1 | Albemarle RPO | HS-2401R | Statewide Mobility | HSIP | 2026 | 25000 | 2026 | 40000 | 2027 | 896000 |  |  | 961000
Perquimans | US 17 (Future I-87) | NCDOT | Chowan County line to SR 1101 (Bear Swamp Road) | Install rumble stripes. | 4 | Highway | Safety | 1 | Albemarle RPO | HS-2401G | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 160000 |  |  | 160000 | UNDER CONSTRUCTION.
Perquimans | SR 1300 (New Hope Road) | NCDOT | Woodland Church Road to SR 1329 (Woodville Road). | Modernize roadway. | 4.38 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5939 | Division 1 | T | 2028 | 1400000 | 2028 | 1700000 | 2030 | 26000000 |  |  | 29100000
Perquimans | SR 1329 (Woodville Road) | NCDOT | SR 1331 (Red Bank Road) to SR 1300 (New Hope Road). | Upgrade roadway. | 4.39 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5740 | Division 1 | T | 2019 | 765000 | 2023 | 140000 | 2021 | 5841000 | 2020 | 1035000 | 7781000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
Perquimans | SR 1336 (Harvey Point Road) | NCDOT | US 17 to SR 1350 (Churches Lane). | Modernize roadway. | 6.13 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5806 | Division 1 | BGLT5, T(M) |  |  |  |  | 2022 | 5170000 |  |  | 5170000 | UNDER CONSTRUCTION.
Perquimans | US 17 (Future I-87) | NCDOT | South of US 17 Business (Edenton Road) to north of SR 1220 (Wiggins Road). | Upgrade roadway and upgrade intersections to interchanges. | 6 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869
Perquimans | US 17 (Future I-87) | NCDOT | South of US 17 Business (Edenton Road) to north of SR 1220 (Wiggins Road). | Upgrade roadway. |  | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869C | Not Funded | NHP, T(M) | NOT FUNDED | 3500000 | NOT FUNDED | 1000000 | NOT FUNDED | 135000000 | NOT FUNDED |  | 139500000 | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY.
Perquimans | US 17 (Future I-87) | NCDOT | SR 1300 (New Hope Road) intersection in Winfall | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869B | Division 1 | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5301000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 880000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 53900000 |  |  | 60081000
Perquimans | US 17 (Future I-87) | NCDOT | SR 1336 (Harvey Point Road) and SR 1338 (Wynne Fork Road) intersections in Hertford | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869A | Division 1 | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 70800000 |  |  | 102700000
Person | TDF | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | Person County Executive Airport | Extend runway to total length of 7,000 feet, construct taxiway extension, and relocate SR 1311 (Cates Mill Road). |  | Aviation | STI (Prioritization) | 5 | Kerr-Tar RPO | AV-5818 | Division 5 | T |  |  |  |  | 2026 | 15200000 |  |  | 15200000
Person | NC 157 (Hurdle Mills Road); Southern Middle School | ROXBORO | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Bike & Ped | Locally Selected | 5 | Kerr-Tar RPO | BL-0061 | Exempt | CMAQ, L(M) | 2025 | 65000 |  |  | 2025 | 450000 | 2023 | 130000 | 645000
Person | US 501 | NCDOT | NC 57 (Hillsborough Road) intersection. | Install traffic signal. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005P | Region C | HSIP, T(M) |  |  | 2026 | 16000 | 2026 | 430000 |  |  | 446000
Person | Various | NCDOT | Intersections in Roxboro | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AO | Division 5 | HSIP | 2026 | 10000 | 2026 | 20000 | 2027 | 943000 |  |  | 973000
Person | US 501 | NCDOT | NC 157 to SR 1596 (West Morehead Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.03 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969B | Region C | T | 2029 | 7900000 | 2029 | 200000 | 2031 | 15100000 |  |  | 23200000
Person | US 501 | NCDOT | South of US 158 to NC 157 | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 0.88 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969A | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14400000 |  |  | 20300000
Person | US 501 | NCDOT | South of US 158 to SR 1601 (North Main Street) in Roxboro. | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 3 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969
Person | US 501 / NC 49 | NCDOT | SR 1596 (West Morehead Street) to SR 1601 (North Main Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.11 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969C | Not Funded | T | NOT FUNDED | 4400000 | NOT FUNDED | 250000 | NOT FUNDED | 6599000 | NOT FUNDED |  | 11249000
Person | Person County Transit | PERSON COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Kerr-Tar RPO | TK-6153 | Public Transit | 5311, L, S | [6 empty] | 2020 | 664000 | 664000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | Arlington Boulevard | GREENVILLE | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Bike & Ped | Locally Selected | 2 | Greenville Urban Area MPO | BL-0156 | Exempt | BGANY, L(M) | 2026 | 70000 | 2026 | 40000 | 2026 | 135000 | 2025 | 68000 | 313000
Pitt | Greenville Community Center Pathway | GREENVILLE | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Bike & Ped | Locally Selected | 2 | Greenville Urban Area MPO | BL-0155 | Exempt | BGANY, L(M) | 2026 | 20000 | 2026 | 3000 | 2026 | 226000 | 2025 | 81000 | 330000 | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE
Pitt | SR 1149 (Mill Street) | WINTERVILLE | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Bike & Ped | Locally Selected | 2 | Greenville Urban Area MPO | BL-0179 | Division 2 | BGANY, L(M) | 2026 | 45000 | 2026 | 25000 | 2027 | 66000 | 2026 | 35000 | 171000
Pitt | Various | GREENVILLE | Locations including along the Tar River, Moye Boulevard, the Norfolk Southern rail corridor, and Town Creek in Greenville | Construct multi-use path. | 2.27 | Bike & Ped | Locally Selected | 2 | Greenville Urban Area MPO | EB-6042 | Exempt | DP, L |  |  |  |  | 2022 | 8291000 |  |  | 8291000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS.
Pitt | SR 1531 (North Greene Street) |  | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Bike & Ped | Other | 2 | Greenville Urban Area MPO | BO-2418 | Exempt | HP, L, L(M) | 2026 | 25000 | 2026 | 100000 | 2026 | 3285000 | 2025 | 590000 | 4000000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199.
Pitt | South Tar River Greenway | GREENVILLE | Pitt Street to Nash Street in Greenville. | Construct greenway using existing sidewalks, roads and on new location along the river. | 0.89 | Bike & Ped | Transition | 2 | Greenville Urban Area MPO | EB-5539 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
Pitt | NC 222 | NCDOT | Bridge 730024 over Tar River. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Mid-East RPO | B-5612 | Region B | BFP | 2028 | 1200000 |  |  | 2031 | 14000000 |  |  | 15200000 | RIGHT-OF-WAY IN PROGRESS.
Pitt | US 13 | NCDOT | Bridge 730038 over Tar River in Greenville. | Replace bridge. | 0.25 | Highway | Bridges | 2 | Greenville Urban Area MPO | B-4786 | Region B | NHPB, T(M) |  |  |  |  | 2022 | 9700000 |  |  | 9700000 | UNDER CONSTRUCTION.
Pitt | US 264/US 258 (Future I-587) | NCDOT | Greene County line to SR 1467 (Stantonsburg Road) interchange (Greenville Southwest Bypass). | Rehabilitate pavement. | 13.19 | Highway | Interstate Maintenance | 2 | Mid-East RPO, Greenville Urban Area MPO | I-6035 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 14420000 |  |  | 14420000 | COMPLETE. LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033.
Pitt | SR 1571 (West 5th Street) | GREENVILLE | Cadillac Street to Reade Circle in Greenville. | Rehabilitate and realign roadway. | 1.07 | Highway | Locally Selected | 2 | Greenville Urban Area MPO | U-6240 | Exempt | DP, L |  |  |  |  | 2022 | 34077000 |  |  | 34077000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS.
Pitt | Various | NCDOT | Greenville Planning Metropolitan Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 2 | Greenville Urban Area MPO | HL-0099 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 3295000 |  |  | 3295000
Pitt | Oxford Road | NCDOT | Bridge 730419 over Meeting House Branch in Greenville. | Replace bridge. | 0.25 | Highway | Municipal Bridge | 2 | Greenville Urban Area MPO | HB-0021 | Division 2 | BFPOFF | 2024 | 50000 | 2024 | 143000 | 2024 | 1180000 |  |  | 1373000 | RIGHT-OF-WAY IN PROGRESS
Pitt | Rock Springs Road | NCDOT | Bridge 730096 over Greens Mill Run in Greenville. | Replace bridge. | 0.25 | Highway | Municipal Bridge | 2 | Greenville Urban Area MPO | HB-0022 | Division 2 | BFPOFF | 2029 | 100000 | 2029 | 126000 | 2030 | 1800000 |  |  | 2026000
Pitt | Various | GRIMESLAND | Routes in Grimeland. | Repave 22 sections of roadway. |  | Highway | Other | 2 | Mid-East RPO | HO-0028 | Exempt | DP, L(M) |  |  |  |  | 2026 | 1395000 |  |  | 1395000 | DP FUNDS REPRESENTS NC203 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $1,116,276.
Pitt | NC 11 / NC 903 (Greenville Southwest Bypass) | NCDOT | NC 11 to US 264 (Greenville Bypass) in Winterville. | Construct four lane divided facility on new location with bypass of Winterville. | 11.25 | Highway | Pre-STI (Historic) | 2 | Greenville Urban Area MPO | R-2250 | Pre-STI (Transition) | T |  |  |  |  | 2023 | 750000 |  |  | 750000 | UNDER CONSTRUCTION.
Pitt | NC 102 | NCDOT | NC 11 Bypass southbound ramps in Ayden. | Construct concrete islands to prevent left turns from NC 11 Bypass. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402X | Region B | HSIP |  |  |  |  | 2026 | 41000 |  |  | 41000
Pitt | NC 102 (Third Street); SR 1149 (Lee Street) | NCDOT | SR 1149 (Lee Street) intersection in Ayden; Second Street intersection in Ayden | Upgrade traffic signals and install / upgrade pedestrian signals and other accommodations. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402H | Region B | HSIP, T(M) |  |  |  |  | 2025 | 72000 |  |  | 72000 | UNDER CONSTRUCTION.
Pitt | NC 11 / NC 43 / NC 903 (Memorial Drive) | NCDOT | Arlington Boulevard Intersection in Greenville | Revise traffic signal and install pedestrian signals, crosswalks, and sidewalk. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402Q | Region B | HSIP, T(M) | 2025 | 6000 |  |  | 2026 | 142000 |  |  | 148000 | RIGHT-OF-WAY IN PROGRESS
Pitt | NC 33 | NCDOT | US 13 / NC 11 (Memorial Drive) to Daughtridge Drive in Greenville. | Install median island and revise pavement markings. | 0.07 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002J | Region B | HSIP, T(M) |  |  |  |  | 2023 | 120000 |  |  | 120000 | UNDER CONSTRUCTION.
Pitt | NC 43 | NCDOT | SR 2241 (Ivy Road) and SR 1753 (Stokestown St. John Road) intersections south of Greenville | Install traffic signals at both intersections and construct left turn lanes on SR 2241 (Ivy Road). |  | Highway | Safety | 2 | Greenville Urban Area MPO, Mid-East RPO | HS-2402F | Region B | HSIP, T(M) |  |  | 2025 | 500000 | 2026 | 370000 |  |  | 870000
Pitt | NC 43 | NCDOT | US 264 interchange ramps | Construct roundabouts. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402O | Region B | HF, HSIP, T(M) |  |  |  |  | 2026 | 1401000 |  |  | 1401000
Pitt | SR 1131 (Reedy Branch Road) | NCDOT | Bulldog Run and Eddie Smith Street intersections in Winterville. | Install rectangular rapid flashing beacons. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002Z | Division 2 | HSIP, T(M) |  |  |  |  | 2024 | 56000 |  |  | 56000
Pitt | SR 1598 (10th Street) | NCDOT | 5th Street intersection in Greenville. | Install / upgrade traffic signals, pavement markings, pedestrian signals, and other accommodations. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402N | Division 2 | HSIP, T(M) | 2025 | 3000 |  |  | 2025 | 253000 |  |  | 256000
Pitt | SR 1598 (10th Street) | NCDOT | Anderson Street intersection in Greenville | Install a pedestrian hybrid beacon. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402D | Division 2 | HSIP, T(M) |  |  |  |  | 2025 | 176000 |  |  | 176000 | UNDER CONSTRUCTION.
Pitt | SR 1598 (10th Street) | NCDOT | College Hill Drive and Elm Street intersections in Greenville. | Upgrade traffic signal. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002M | Division 2 | HSIP, T(M) |  |  |  |  | 2024 | 56000 |  |  | 56000 | RIGHT-OF-WAY IN PROGRESS.
Pitt | SR 1702 (Evans Street) | NCDOT | Howell Street intersection in Greenville. | Install traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002R | Division 2 | HSIP, T(M) |  |  | 2023 | 64000 | 2023 | 400000 |  |  | 464000 | UNDER CONSTRUCTION.
Pitt | SR 1703 (14th Street) | NCDOT | Haskett Way to Berkley Road. | Install crosswalk, wheelchair ramps, sidewalk, fence, and remove crosswalks. | 0.09 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002A | Division 2 | HSIP, T(M) |  |  |  |  | 2021 | 50000 |  |  | 50000 | COMPLETE.
Pitt | SR 1725 (County Home Road) | NCDOT | Crosswalk south of District Park Drive in Greenville. | Install rectangular rapid flashing beacons. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002X | Division 2 | HSIP, T(M) |  |  |  |  | 2024 | 36000 |  |  | 36000 | UNDER CONSTRUCTION.
Pitt | US 13 / US 264 | NCDOT | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Highway | Safety | 2 | Greenville Urban Area MPO, Mid-East RPO | HS-2402G | Region B | HSIP, T(M) | 2026 | 150000 | 2026 | 300000 | 2027 | 950000 |  |  | 1400000
Pitt | US 258 (Wesley Church Road) | NCDOT | US 264 to I-587 eastbound ramps. | Install rumble stripes. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402R | Region B | HSIP |  |  |  |  | 2025 | 80000 |  |  | 80000
Pitt | US 258 Business | NCDOT | Cooperative Way / Sharon Lane intersection in Farmville | Install all way stop. |  | Highway | Safety | 2 | Mid-East RPO | HS-2402A | Region B | HSIP, T(M) |  |  |  |  | 2024 | 124000 |  |  | 124000
Pitt | US 264 |  | SR 1565 (Grimesland Bridge Road) and the eastern intersection of SR 1564 (Old Washington Road) | Construct Reduced Conflict Intersection. | 0.5 | Highway | Safety | 2 | Mid-East RPO | HS-2402AC | Statewide Mobility | HSIP | 2027 | 175000 | 2027 | 200000 | 2028 | 950000 |  |  | 1325000
Pitt | US 264 | NCDOT | NC 30 intersection east of Greenville. | Close full movement crossover and install reduced conflict intersection. | 1 | Highway | Safety | 2 | Mid-East RPO | HS-2402Z | Statewide Mobility | HSIP | 2026 | 50000 | 2027 | 265000 | 2027 | 1020000 |  |  | 1335000
Pitt | US 264 Alternate (Greenville Boulevard) | NCDOT | NC 11 / NC 43 / NC 903 (Memorial Drive) intersection, and NC 11 / NC 903 (Memorial Drive) and Mall Drive intersection in Greenville. | Construct turn lanes. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002L | Region B | HSIP, T(M) |  |  |  |  | 2024 | 896000 |  |  | 896000
Pitt | US 264 Alternate (Greenville Boulevard) | NCDOT | South of Luci Drive to NC 33 (10th Street) in Greenville. | Construct pedestrian improvements. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002AH | Region B | HSIP, T(M) |  |  | 2024 | 124000 | 2024 | 320000 |  |  | 444000
Pitt | US 264 Alternate (Greenville Boulevard) | NCDOT | SR 1534 (Old Pactolus Road) intersection. | Construct restricted-crossing intersection. | 0.48 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002E | Region B | HSIP, T(M) |  |  |  |  | 2023 | 882000 |  |  | 882000 | UNDER CONSTRUCTION.
Pitt | NC 43 | NCDOT | SR 1708 (Fire Tower Road) to SR 1711 (Worthington Road). | Widen to multi-lanes. | 3.19 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5991 | Division 2 | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62400000 |  |  | 105100000
Pitt | SR 1203 (Allen Road) | NCDOT | SR 1467 (Stantonsburg Road) to US 13 (Dickinson Avenue Extension). | Widen to four lanes. | 2.33 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5875 | Division 2 | T | 2018 | 485000 | 2024 | 650000 | 2026 | 67905000 |  |  | 69040000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
Pitt | SR 1620 (Dickinson Avenue) | NCDOT | NC 11 to Reade Circle. | Improve roadway. | 1.34 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5606 | Division 2 | BG50200, T(M) |  |  |  |  | 2022 | 18365000 |  |  | 18365000 | UNDER CONSTRUCTION.
Pitt | SR 1700 (Evans Street / Old Tar Road) | NCDOT | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-2817 | Division 2 | BG50200, T, T(M) | 2019 | 22800000 | 2019 | 12972000 | 2027 | 138310000 |  |  | 174082000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
Pitt | SR 1704 (Fourteenth Street) | NCDOT | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5917 | Division 2 | T | 2019 | 952000 | 2024 | 2772000 | 2028 | 26950000 | 2020 | 1740000 | 32414000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
Pitt | SR 1708 (Firetower Road) | NCDOT | West of East Arlington Boulevard to NC 33 (East 10th Street) in Greenville. | Widen to four lanes. | 3.4 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5785 | Division 2 | T | 2024 | 58200000 | 2024 | 7500000 | 2030 | 109400000 |  |  | 175100000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES SCOPE OF U-5870.
Pitt | SR 1711 (Worthington Road) | NCDOT | SR 1725 (County Home Road) intersection in Greenville | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-6197 | Division 2 | T | 2027 | 1300000 | 2027 | 730000 | 2029 | 3100000 |  |  | 5130000
Pitt | US 13 (Memorial Drive) | NCDOT | NC 43 (5th Street) intersection in Greenville | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5730 | Region B | T |  |  | 2023 | 125000 | 2026 | 1400000 |  |  | 1525000 | RIGHT-OF-WAY IN PROGRESS.
Pitt | Various | NCDOT | Routes in Greenville | Upgrade signal system. | 25 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5952 | Region B | BG50200, T(M) |  |  | 2026 | 750000 | 2028 | 13100000 |  |  | 13850000
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Systemwide | Safety and security minimum 1 % set aside |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | Greenville Urban Area MPO | TS-5112 | Public Transit | 5307 | [6 empty] | 2020 | 34000 | 34000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Various locations | Fleet Service Building Expansion. |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | Greenville Urban Area MPO | TL-0009 | Public Transit | CARES, L |  |  |  |  | 2021 | 1826000 |  |  | 1826000
Pitt | Greenville Area Transit | GREENVILLE | Systemwide | Install bus shelters and benches as part of Greenville Area Transit's new routes for headway reduction. |  | Public Transportation (Transit) | Locally Selected | 2 | Greenville Urban Area MPO | TL-0067 | Exempt | BGANY, L(M) |  |  |  |  | 2025 | 303000 |  |  | 303000
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 2 | Greenville Urban Area MPO | TO-4726 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 11920000 | 11920000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Greenville Urban Area MPO | TG-5107C | Public Transit | 5307, L | [6 empty] | 2020 | 1350000 | 1350000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Greenville Urban Area MPO | TG-5107B | Public Transit | 5307, L | [6 empty] | 2020 | 6075000 | 6075000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Systemwide | Funding for planning assistance - 5303 |  | Public Transportation (Transit) | Planning | 2 | Greenville Urban Area MPO | TP-5107 | Public Transit | 5303, L, S | [6 empty] | 2020 | 472000 | 472000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | Greenville Area Transit | GREENVILLE AREA TRANSIT | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | Greenville Urban Area MPO | TG-4767 | Public Transit | 5307, L | [6 empty] | 2020 | 5409000 | 5409000 | FUNDS AUTHORIZED IN PROGRESS
Pitt | East Street | NCDOT | CSX Crossing 628 794Y | Close East Street crossing in Bethel. |  | Rail | Rail-Highway Grade Crossing Closure | 2 | Mid-East RPO | RC-2002A | Division 2 | RR |  |  |  |  | 2024 | 560000 |  |  | 560000
Pitt | SR 1139 (Wilson Street / Moye-Turnage Road) | NCDOT | Carolina Coastal Railway Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 2 | Mid-East RPO | RX-2402B | Division 2 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Pitt | SR 1530 (Airport Road) | NCDOT | CSX Crossing 641860P in Greenville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Greenville Urban Area MPO | RX-2002E | Division 2 | RR |  |  |  |  | 2027 | 530000 |  |  | 530000
Pitt | SR 1704 (Fourteenth Street) | NCDOT | Carolina Coastal Railway Crossing 465488D in Greenville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Greenville Urban Area MPO | RX-2002B | Division 2 | RR |  |  |  |  | 2026 | 345000 |  |  | 345000
Pitt | US 258 Business (Main Street) | NCDOT | Carolina Coastal Railway Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 2 | Mid-East RPO | RX-2402A | Division 2 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Pitt | US 264 (Marlboro Road) | NCDOT | Carolina Coastal Railway Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 2 | Mid-East RPO | RX-2402C | Division 2 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Pitt | US 264 ALT (Greenville Boulevard) | NCDOT | Carolina Coastal Railway Crossing 465489K in Greenville. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Greenville Urban Area MPO | RX-2002C | Division 2 | RR |  |  |  |  | 2026 | 345000 |  |  | 345000
Pitt, Craven, Edgecombe | NC 43 | NCDOT | NC 118 in Craven County to SR 1730 (Herman Garris Road) in Pitt County, and SR 1205 (Rock Spring Road) to southern limits of Falkland, and northern limits of Falkland in Pitt County to NC 42 in Edgecombe County. | Install rumble stripes and pavement markings. | 33.01 | Highway | Safety | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Down East RPO, Upper Coastal Plain RPO | HS-2002S | Region A, B | HSIP, T(M) |  |  |  |  | 2024 | 816000 |  |  | 816000
Pitt, Greene | US 264 | NCDOT | Wilson County line to SR 1128 (Davenport Farm Road) / SR 1206 (Bell Arthur Road) in Pitt County. | Install rumble stripes. | 11.76 | Highway | Safety | 2 | Mid-East RPO, Eastern Carolina RPO, Greenville Urban Area MPO | HS-2002T | Region B | HSIP, T(M) |  |  |  |  | 2024 | 378000 |  |  | 378000 | UNDER CONSTRUCTION.
Pitt, Greene, Lenoir | NC 903 | NCDOT | LaGrange Town limits in Lenoir County to SR 1104 (Hull Road) in Greene County; US 13/258 in Greene County to NC 11 in Pitt County; US 13 / NC 11 to Martin County line in Pitt County | Install rumble stripes. |  | Highway | Safety | 2 | Eastern Carolina RPO, Mid-East RPO | HS-2402U | Region B | HSIP |  |  |  |  | 2025 | 950000 |  |  | 950000
Polk | NC 9 | NCDOT | Bridge 740037 over Green River | Replace bridge. | 0.5 | Highway | Bridges | 14 | Foothills RPO | BR-0040 | Region G | BFP, HFB | 2025 | 330000 |  |  | 2028 | 5700000 |  |  | 6030000 | RIGHT-OF-WAY IN PROGRESS.
Polk | SR 1004 (Poors Ford Road) | NCDOT | Bridge 740087 over Broad River. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Foothills RPO | HB-0025 | Division 14 | BGOFF | 2026 | 310000 | 2026 | 600000 | 2028 | 13900000 |  |  | 14810000
Polk | I-26 | NCDOT | Henderson County line to mile marker 65.0. | Rehabilitate pavement. | 7.05 | Highway | Interstate Maintenance | 14 | Foothills RPO | I-5926 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 19700000 |  |  | 19700000
Polk | I-26 | NCDOT | Mile marker 65.0 to South Carolina state line. | Rehabilitate pavement. | 6.06 | Highway | Interstate Maintenance | 14 | Foothills RPO | I-5927 | Statewide Mobility | BGLT5, T(M) |  |  |  |  | 2023 | 21600000 |  |  | 21600000 | UNDER CONSTRUCTION.
Polk | NC 108 (Mills Street) | NCDOT | SR 1534 (Peak Street) intersection in Columbus. | Install pedestrian signals and upgrade curb ramp. | 0.5 | Highway | Safety | 14 | Foothills RPO | HS-2014AB | Region G | HSIP, T(M) |  |  |  |  | 2024 | 168000 |  |  | 168000
Polk | US 74 EB | NCDOT | I-26 to the Rutherford County line. | Upgrade guardrail end terminals to current standards. | 12.65 | Highway | Safety | 14 | Foothills RPO | W-5814C | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 179000 |  |  | 179000 | COMPLETE
Polk | US 74 WB | NCDOT | I-26 to the Rutherford County line. | Upgrade guardrail end terminals to current standards. | 12.65 | Highway | Safety | 14 | Foothills RPO | W-5814B | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 199000 |  |  | 199000 | COMPLETE
Polk | I-26 | NCDOT | NC 108 at Exit 67. | Construct improvements. |  | Highway | STI (Prioritization) | 14 | Foothills RPO | I-4729B | Region G | T | 2019 | 3200000 | 2020 | 2000000 | 2033 | 33600000 |  |  | 38800000 | RIGHT-OF-WAY IN PROGRESS
Polk | I-26 | NCDOT | US 74 / NC 108 interchange (Exit 67). | Construct interchange improvements and improvements on NC 108. |  | Highway | STI (Prioritization) | 14 | Foothills RPO | I-4729
Polk | I-26 | NCDOT | US 74 / NC 108 interchange (Exit 67). | Construct ramps from I-26 westbound to US 74 eastbound and from US 74 westbound to I-26 eastbound. | 1 | Highway | STI (Prioritization) | 14 | Foothills RPO | I-4729A | Region G | [10 empty] | COMPLETE
Polk | NC 9 | NCDOT | US 74 to NC 108. | Construct paved shoulders. | 3.07 | Highway | STI (Prioritization) | 14 | Foothills RPO | R-5840 | Division 14 | T | 2022 | 2200000 | 2024 | 1300000 | 2030 | 13800000 |  |  | 17300000 | RIGHT-OF-WAY IN PROGRESS.
Polk | Polk County Transportation | POLK COUNTY TRANSPORTATION | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Foothills RPO | TK-6155 | Public Transit | 5311, L, S | [6 empty] | 2020 | 736000 | 736000 | FUNDS AUTHORIZED IN PROGRESS
Randolph | SR 1009 (North Main Street) | HIGH POINT | Columbus Avenue to the Guilford County line | Construct sidewalk and curb ramps. | 1.1 | Bike & Ped | Locally Selected | 8 | High Point Urban Area MPO | BL-0163 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 10000 | 2026 | 894000 | 904000
Randolph | Industrial Park Avenue | ASHEBORO | Randolph Community College entrance to Continuing Education and Industrial Center in Asheboro | Construct sidewalk on south side. | 0.26 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5862 | Division 8 | L(M), TA5T50 |  |  |  |  | 2022 | 147000 |  |  | 147000
Randolph | SR 1950 (West Academy Street) | RANDLEMAN | SR 1952 (High Point Street) to Hillary Street in Randleman | Construct sidewalk on north side. | 1.04 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5744 | Division 8 | L(M), TA5T50 |  |  |  |  | 2027 | 800000 |  |  | 800000
Randolph | SR 1950 (West Naomi Street) | RANDLEMAN | West Academy Street to US 220 Business (South Main Street) in Randleman | Construct sidewalk, implement road diet, and install raised crosswalk and median. |  | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5898 | Division 8 | L(M), TA5T50 | 2026 | 1900000 |  |  | 2027 | 2900000 |  |  | 4800000
Randolph | US 64 / NC 49 (East Dixie Drive) | ASHEBORO | Executive Way to Centerpoint Plaza Shopping Center in Asheboro | Construct sidewalk. | 0.15 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-6004 | Division 8 | L(M), TA5T50 | 2027 | 340000 | 2027 | 90000 | 2027 | 2100000 |  |  | 2530000
Randolph | SR 2207 (Faith Rock Road) | NCDOT | Bridge 750176 over creek off Deep River. | Replace bridge. |  | Highway | Bridges | 8 | Piedmont Triad RPO | HB-0071 | Division 8 | BGOFF, HP, T(M) | 2025 | 20000 |  |  | 2026 | 800000 |  |  | 820000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. RIGHT-OF-WAY IN PROGRESS
Randolph | SR 2481 (Low Bridge Road) | NCDOT | Bridge 750307 over Mount Pleasant Creek. | Replace bridge. | 0.25 | Highway | Bridges | 8 | Piedmont Triad RPO | B-5546 | Highway Fund | [10 empty] | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT
Randolph | Various | NCDOT | Routes at the Randolph County Megasite near Liberty. | Construct road enhancements and wetland mitigation. | 3.18 | Highway | Economic Development | 8 | Piedmont Triad RPO | HE-0004 | Division 8 | HF | 2022 | 11000000 | 2022 | 1000000 | 2023 | 156350000 | 2023 | 4100000 | 172450000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
Randolph | I-73 / I-74 / US 220 | NCDOT | Montgomery County line to north of SR 1462 (Park Drive) in Asheboro. | Rehabilitate pavement. | 15.72 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5948 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2028 | 26700000 |  |  | 26700000
Randolph | I-73 / US 220 | NCDOT | SR 1009 (Old US Highway 311) to Guilford County line. | Rehabilitate pavement. | 7.69 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO, High Point Urban Area MPO | HI-0003 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2029 | 8121000 |  |  | 8121000
Randolph | I-74 | NCDOT | SR 1928 (Cedar Square Road) to I-73 / US 220. | Rehabilitate pavement. | 7.58 | Highway | Interstate Maintenance | 8 | High Point Urban Area MPO, Piedmont Triad RPO | HI-0004 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2031 | 8140000 |  |  | 8140000
Randolph | US 64 | NCDOT | Asheboro Southern Bypass, US 64 West to US 64 East. | Construct four lane freeway on new location with interchanges at US 220, NC 49 and zoo access at NC 159. | 12.76 | Highway | Pre-STI (Historic) | 8 | Piedmont Triad RPO | R-2536 | Pre-STI (Transition) | [10 empty] | COMPLETE.
Randolph | US 421 (Future I-685) | NCDOT | Chatham County line to the Guilford County line. | Install one mile and half mile markers and revise exit number signs. | 9.98 | Highway | Safety | 8 | Piedmont Triad RPO | HS-2008D | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2023 | 50000 |  |  | 50000
Randolph | I-85 | NCDOT | SR 1009 (South Main Street) intersection in Archdale. | Construct intersection improvements. | 1 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5770 | Region E | T | 2022 | 6358000 | 2022 | 2200000 |  |  |  |  | 8558000 | “HF” FUNDING REFLECTS CONTRACT RESURFACING FUNDS.
Randolph | NC 159 (Zoo Parkway) | NCDOT | Ridge Street intersection in Asheboro. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5958 | Division 8 | T | 2026 | 800000 | 2026 | 410000 | 2028 | 1900000 |  |  | 3110000
Randolph | NC 42 | NCDOT | SR 2237 (East Salisbury Street) to north of US 64 / NC 49 (Dixie Drive) in Asheboro. | Widen to three lanes. | 0.5 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-5743 | Region E | T | 2022 | 2006000 | 2022 | 897000 | 2026 | 13700000 |  |  | 16603000 | RIGHT-OF-WAY IN PROGRESS
Randolph | NC 62 | NCDOT | SR 3252 (Surrett Drive) in Trinity to SR 1009 (North Main Street) in Archdale. | Modernize roadway. | 3.18 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-6191 | Division 8 | T | 2029 | 21400000 | 2029 | 12400000 | 2033 | 30000000 |  |  | 63800000
Randolph | SR 1009 (South Main Street) | NCDOT | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Construct diverging diamond interchange and reduced conflict intersection improvements | 0.99 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5770B | Region E | T |  |  | 2026 | 2400000 | 2028 | 29795000 |  |  | 32195000 | NC BUILD BOND $8M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE).
Randolph | SR 1009 (South Main Street) | NCDOT | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Mill and resurface roadway. | 1.07 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5770A | Region E | HF, T |  |  |  |  | 2023 | 1693000 |  |  | 1693000 | UNDER CONSTRUCTION
Randolph | SR 1547 (Finch Farm Road) | NCDOT | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5308 | Division 8 | T | 2019 | 2459000 | 2026 | 3500000 | 2028 | 55900000 | 2020 | 2703000 | 64562000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE)
Randolph | SR 1712 (Pineview Street) | NCDOT | West of Sylvan Drive to US 220 Business in Asheboro. | Widen to a three lane facility. | 0.61 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-5711 | Division 8 | BG5T50, T(M) |  |  |  |  | 2026 | 9700000 |  |  | 9700000 | RIGHT-OF-WAY IN PROGRESS
Randolph | US 220 Business | NCDOT | SR 2123 (Caudle Road) to SR 2270 (US 311 extension) in Randleman. | Widen to 4-lane divided facility. | 0.72 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-6006 | Division 8 | BGANY, T | 2024 | 2050000 | 2024 | 2800000 | 2027 | 17800000 |  |  | 22650000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5956
Randolph | US 220 Business (North Fayetteville Street) | NCDOT | SR 2149 (Hub Morris Road) to SR 2123 (Caudle Road) | Widen roadway. | 1.27 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5956B | Not Funded | T | NOT FUNDED | 3200000 | NOT FUNDED | 6005000 | NOT FUNDED | 9399000 | NOT FUNDED |  | 18604000
Randolph | US 220 Business (North Fayetteville Street) | NCDOT | SR 2269 (Vision Drive) to SR 2123 (Caudle Road) in Asheboro. | Widen to multi-lanes. | 3.6 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5956 | Division 8 | [10 empty] | COORDINATE WITH U-6006
Randolph | US 220 Business (North Fayetteville Street) | NCDOT | SR 2269 (Vision Drive) to SR 2149 (Hub Morris Road) | Widen roadway. | 2.29 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5956A | Not Funded | T | NOT FUNDED | 4000000 | NOT FUNDED | 7900000 | NOT FUNDED | 31600000 | NOT FUNDED |  | 43500000
Randolph | US 220 Business (South Fayetteville Street) | NCDOT | South of SR 2915 (Ridge Street) to south of SR 1453 (Walker Avenue) in Asheboro. | Construct right turn lane on SR 2915, construct left-overs at SR 1154 (Country Club Drive) / SR 2800 (Atlantic Avenue), and reduce number of lanes from SR 2800 (Atlantic Avenue) to south of SR 1453 (Walker Avenue). | 0.47 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-6007 | Division 8 | T |  |  | 2022 | 300000 | 2024 | 1400000 |  |  | 1700000 | RIGHT-OF-WAY IN PROGRESS
Randolph | US 64 | NCDOT | Asheboro Bypass to east of I-73 / I-74 / US 220 in Asheboro. | Widen to a four lane divided facility, reconstruct interchange at NC 49, modify interchange at I-73 / I-74 / US 220 and replace bridge 750171 over US 64 and NC 49. | 2.31 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-5813 | Region E | NHP | 2021 | 7967000 | 2021 | 3000000 | 2024 | 68441000 |  |  | 79408000 | RIGHT OF WAY IN PROGRESS.
Randolph | US 64 | NCDOT | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-2220DA | Region E | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 117100000 |  |  | 133200000
Randolph | Coordinated Area Transportation System (RCATS) |  | Systemwide | Funding for Asheboro flexible route transit launch. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 8 | Piedmont Triad RPO | TN-0001 | Exempt | CRPANY, L(M) | [6 empty] | 2025 | 733000 | 733000
Randolph | SR 2502 (Julian Airport Road) | NCDOT | Crossing 720943W in Liberty | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Piedmont Triad RPO | RX-2008F | Division 8 | RR |  |  |  |  | 2026 | 411000 |  |  | 411000
Randolph, Davidson | I-85 | NCDOT | NC 109 in Thomasville to SR 1009 (South Main Street) in Archdale. | Pavement rehabilitation. | 7.61 | Highway | Interstate Maintenance | 8, 9 | High Point Urban Area MPO | HI-0002 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 15672000 |  |  | 15672000 | UNDER CONSTRUCTION
Randolph, Davidson | US 64 | NCDOT | NC 109 to SR 1409 (Lake Park Road). | Widen to multi-lanes. |  | Highway | STI (Prioritization) | 8, 9 | High Point Urban Area MPO | R-2220C | Not Funded | T | NOT FUNDED | 13746000 | NOT FUNDED | 1650000 | NOT FUNDED | 56452000 | NOT FUNDED |  | 71848000
Randolph, Davidson, Guilford | High Point Transit System | HIGH POINT TRANSIT SYSTEM / HI-TRAN | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 7, 8, 9 | High Point Urban Area MPO | TO-4790 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 29675000 | 29675000 | FUNDS AUTHORIZED IN PROGRESS
Randolph, Guilford | SR 1577 / SR 1004 (Archdale Road) | NCDOT | US 311 (Main Street) to east of Springwood Lane in Archdale. | Widen to multi-lanes. | 3.09 | Highway | STI (Prioritization) | 7, 8 | High Point Urban Area MPO | U-3400 | Division 7, 8 | T | 2024 | 7901000 | 2026 | 6300000 | 2030 | 43600000 |  |  | 57801000
Randolph, Guilford | SR 1595 / SR 4053 (Surrett Drive) | NCDOT | I-85 in Trinity to SR 1300 (West Fairfield Road) in High Point. | Widen to multi-lanes. | 3.22 | Highway | STI (Prioritization) | 7, 8 | High Point Urban Area MPO | U-5864 | Division 7, 8 | BGANY, T(M) | 2029 | 28300000 | 2029 | 6700000 | 2033 | 44500000 |  |  | 79500000
Richmond | RCZ | RICHMOND COUNTY AIRPORT (RCZ) | Richmond County Airport | Clear obstructions in runway 14 approach. |  | Aviation | STI (Prioritization) | 8 | Lumber River RPO | AV-5761 | Division 8 | T |  |  |  |  | 2026 | 570000 |  |  | 570000
Richmond | RCZ | RICHMOND COUNTY AIRPORT (RCZ) | Richmond County Airport | Construct east ramp expansion. |  | Aviation | STI (Prioritization) | 8 | Lumber River RPO | AV-5853 | Division 8 | T |  |  |  |  | 2026 | 2000000 |  |  | 2000000
Richmond | SR 1639 (Spring Street); SR 1615 (South Main Street) | HAMLET | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6018 | Division 8 | L(M), TA5T50 | 2026 | 320000 | 2026 | 160000 | 2028 | 2900000 | 2024 | 28000 | 3408000
Richmond | I-73 / I-74 | NCDOT | South of US 220 / SR 1446 (Haywood Cemetery Road) to Montgomery County line. | Rehabilitate pavement. | 10.5 | Highway | Interstate Maintenance | 8 | Lumber River RPO | I-5946
Richmond | I-73/I-74 | NCDOT | South of US 220 / SR 1446 (Haywood Cemetery Road) to SR 1455 (Fire Tower Road). | Rehabilitate pavement. | 3.23 | Highway | Interstate Maintenance | 8 | Lumber River RPO | I-5946A | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION - LET WITH I-5947B
Richmond | I-73/I-74 | NCDOT | SR 1455 (Fire Tower Road) to Montgomery County line. | Rehabilitate pavement. | 6.86 | Highway | Interstate Maintenance | 8 | Lumber River RPO | I-5946B | Statewide Mobility | BGIM, T(M) |  |  |  |  | 2022 | 6812000 |  |  | 6812000 | UNDER CONSTRUCTION
Richmond | New Route | NCDOT | US 74 Business to SR 1426 (Aberdeen Road). | Construct two lane facility utilizing sections of SR 1641 (Clemmer Road) and SR 1645 (Mt. Olive Church Road), remainder on new location. | 4.01 | Highway | STI (Prioritization) | 8 | Lumber River RPO | U-5706 | Division 8 | T | 2027 | 18200000 | 2027 | 2500000 | 2031 | 64300000 |  |  | 85000000
Richmond | US 1 | NCDOT | North of SR 1606 (Fox Road) to south of SR 1001 (Marston Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 3.43 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501C | Division 8 | T |  |  |  |  | 2019 | 12975000 | 2021 | 217000 | 13192000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Richmond | US 1 | NCDOT | South Carolina state line to SR 1001 (Marston Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 24.1 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501
Richmond | US 1 | NCDOT | South Carolina state line to SR 1104 (Osborne Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.089 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501A | Not Funded | T | NOT FUNDED | 4500000 | NOT FUNDED |  | NOT FUNDED | 25700000 | NOT FUNDED |  | 30200000 | SCHEDULED FOR REPRIORITIZATION
Richmond | US 1 | NCDOT | SR 1104 (Osborne Road) to US 74 Bypass. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.282 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501BA | Not Funded | T | NOT FUNDED | 5519000 | NOT FUNDED | 908000 | NOT FUNDED | 40501000 | NOT FUNDED |  | 46928000 | SCHEDULED FOR REPRIORITIZATION
Richmond | US 1 | NCDOT | US 74 Business to north of SR 1606 (Fox Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 7.15 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501BC | Not Funded | T | NOT FUNDED | 24248000 | NOT FUNDED | 6950000 | NOT FUNDED | 101101000 | NOT FUNDED |  | 132299000 | COORDINATE WITH R-5928
Richmond | US 1 | NCDOT | US 74 Bypass to US 74 Business. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 4.07 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501BB | Not Funded | T | NOT FUNDED | 13300000 | NOT FUNDED | 2523000 | NOT FUNDED | 67699000 | NOT FUNDED |  | 83522000 | SCHEDULED FOR REPRIORITIZATION
Richmond | US 1 (Proposed) / SR 1516 (Greene Street) | NCDOT | US 220 to US 1 in Rockingham. | Widen to 3-lane facility and re-route US 1 along project. | 0.54 | Highway | STI (Prioritization) | 8 | Lumber River RPO | U-6027 | Division 8 | T | 2025 | 2199000 | 2025 | 1300000 | 2028 | 8100000 |  |  | 11599000 | RIGHT-OF-WAY IN PROGRESS
Richmond | US 220 / Future I 73 / Future I 74 | NCDOT | SR 1336 (Billy Covington Road) | Construct roadway. |  | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421CA | Statewide Mobility | T | 2023 | 75000 | 2023 | 25000 | 2024 | 532000 |  |  | 632000 | UNDER CONSTRUCTION
Richmond | US 220 / Future I-73 / Future I-74 | NCDOT | Rockingham Bypass. | Four lanes divided on new location. | 10.5 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421 | [11 empty] | BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
Richmond | US 220 Bypass / Future I 73 / Future I 74 | NCDOT | South of SR 1140 (Old Charlotte Highway) to southwest of SR 1304 (Harrington Road) | Construct roadway. | 9.25 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421B | Region E | T |  |  |  |  | 2020 | 83679000 |  |  | 83679000 | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Richmond | US 220 Bypass / Future I 73 / Future I 74 | NCDOT | US 74 Bypass west of Rockingham at SR 1109 (Zion Church Road) to interchange to south of SR 1140 (Old Charlotte Highway) | Construct roadway. | 2.61 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421A | Region E | T | 2020 | 5495000 |  |  | 2020 | 106857000 |  |  | 112352000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Richmond | US 74 / Future I-74 | NCDOT | US 1 (Exit 311) interchange near Rockingham. | Improve interchange. | 1 | Highway | STI (Prioritization) | 8 | Lumber River RPO | I-5979 | Division 8 | NHP | 2022 | 500000 | 2022 | 210000 | 2025 | 9810000 |  |  | 10520000 | UNDER CONSTRUCTION
Richmond | US 220 Bypass / Future I 73 / Future I 74 | NCDOT | 0.2 miles southwest of SR 1304 (Harrington Road) to I-73 / I-74 Interchange south of Ellerbe | Construct roadway. | 0.84 | Highway | Transition | 8 | Lumber River RPO | R-3421C | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Richmond | SR 1925 (Biltmore Drive) | NCDOT | Crossing 630856U in Rockingham | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO | RX-2008C | Division 8 | RR |  |  |  |  | 2026 | 446000 |  |  | 446000
Robeson | Various | NCDOT | Locations in Lumberton | Develop drone disaster response and delivery network. |  | Aviation | Other | 6 | Lumber River RPO | AO-0002 | Exempt | DP | [6 empty] | 2025 | 1100000 | 1100000 | DP FUNDS REPRESENT 2024 SMART GRANT FUNDING.
Robeson | LBT | LUMBERTON REGIONAL AIRPORT (LBT) | Lumberton Regional Airport | Construct partial parallel taxiway. |  | Aviation | STI (Prioritization) | 6 | Lumber River RPO | AV-5747 | Division 6 | T |  |  |  |  | 2022 | 2600000 |  |  | 2600000 | UNDER CONSTRUCTION.
Robeson | NC 711 (Third Street) | PEMBROKE | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Bike & Ped | STI (Prioritization) | 6 | Lumber River RPO | EB-6013 | Division 6 | L, L(M), TAP | 2028 | 400000 | 2028 | 140000 | 2029 | 2500000 | 2027 | 170000 | 3210000
Robeson | NC 41 / NC 72 / SR 1600 | NCDOT | Bridge 770125 over Lumber River. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Lumber River RPO | B-5985A | Region C | BFP, T(M) |  |  |  |  | 2023 | 7915000 |  |  | 7915000 | UNDER CONSTRUCTION.
Robeson | NC 41 / NC 72 / SR 1600 | NCDOT | Bridge 770175 over Lumber River. | Replace bridge. | 0.25 | Highway | Bridges | 6 | Lumber River RPO | B-5985B | Region C | BFP, T(M) |  |  |  |  | 2026 | 9000000 |  |  | 9000000
Robeson | NC 41 / NC 72 / SR 1600 | NCDOT | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Highway | Bridges | 6 | Lumber River RPO | B-5985 | Region C | NHPB, T(M) | 2022 | 395000 | 2022 | 485000 |  |  |  |  | 880000 | RIGHT-OF-WAY IN PROGRESS.
Robeson | SR 1529 (Mount Olive Church Road) | NCDOT | Bridges 770299 and 770300 over Saddle Tree Swamp. | Replace bridges. | 0.5 | Highway | Bridges | 6 | Lumber River RPO | HB-0007 | Division 6 | BGOFF | 2023 | 77000 | 2023 | 185000 | 2024 | 1339000 |  |  | 1601000 | RIGHT-OF-WAY IN PROGRESS.
Robeson | I-95 | NCDOT | Mile marker 13 to mile marker 22. | Rehabilitate bridge. | 9 | Highway | Interstate Maintenance | 6 | Lumber River RPO | I-6064C | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2021 | 131492000 |  |  | 131492000 | UNDER CONSTRUCTION.
Robeson | I-95 | NCDOT | North of US 301 (mile marker 22) to Cumberland County line (mile marker 40). | Rehabilitate bridge and improve interstate. | 17.99 | Highway | Interstate Maintenance | 6 | Lumber River RPO, Fayetteville Area MPO | I-5850A | Statewide Mobility | [10 empty] | COMPLETE.
Robeson | I-95 | NCDOT | North of US 301 (mile marker 22) to Cumberland County line (mile marker 40). | Rehabilitate pavement. | 15.7 | Highway | Interstate Maintenance | 6 | Lumber River RPO, Fayetteville Area MPO | I-5850 | Statewide Mobility
Robeson | I-95 | NCDOT | North of US 301 (mile marker 22) to Cumberland County line (mile marker 40). | Rehabilitate pavement. | 18.97 | Highway | Interstate Maintenance | 6 | Lumber River RPO, Fayetteville Area MPO | I-5850B | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
Robeson | I-95 | NCDOT | South Carolina state line (mile marker 0.0) to I-74 (mile marker 13). | Rehabilitate pavement. | 5.49 | Highway | Interstate Maintenance | 6 | Lumber River RPO | I-5939 | Statewide Mobility | BGIM, T(M) |  |  |  |  | 2022 | 23898000 |  |  | 23898000 | UNDER CONSTRUCTION.
Robeson | US 74 (Future I-74) | NCDOT | East of NC 41 to east of Columbus County line. | Rehabilitate pavement. | 10.93 | Highway | Interstate Maintenance | 6 | Lumber River RPO | HI-0016 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 13100000 |  |  | 13100000 | TO BE LET WITH HI-0017.
Robeson | US 74 (Future I-74) | NCDOT | Scotland County line to I-74 / US 74 Business. | Rehabilitate pavement. | 3.44 | Highway | Interstate Maintenance | 6 | Lumber River RPO | HI-0017 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2024 | 8600000 |  |  | 8600000 | TO BE LET WITH HI-0016.
Robeson | NC 71 | FAYETTEVILLE | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0144 | Region C | BGDA, HF(M) | 2026 | 100000 | 2026 | 150000 | 2027 | 900000 | 2025 | 200000 | 1350000
Robeson | NC 711 (Third Street) | PEMBROKE | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Highway | Locally Selected | 6 | Lumber River RPO | HL-0009 | Exempt | DP, HF, L | 2022 | 100000 | 2022 | 930000 | 2023 | 8810000 | 2021 | 350000 | 10190000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS.
Robeson | NC 130 | NCDOT | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Lumber River RPO | HN-0022 | Region C | CRPLT5, T(M) | 2025 | 150000 | 2025 | 180000 | 2026 | 3700000 | 2024 | 608000 | 4638000 | RIGHT-OF-WAY IN PROGRESS
Robeson | NC 71 | NCDOT | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Lumber River RPO | HN-0020 | Region C | CRPLT5, T(M) | 2025 | 400000 | 2025 | 50000 | 2026 | 3400000 | 2024 | 462000 | 4312000
Robeson | I-95 | NCDOT | Mile marker 13 to mile marker 22. | Gauge installation, modeling / hydraulic studies, and stress testing along corridor. | 9.01 | Highway | Other | 6 | Lumber River RPO | I-6064D | Statewide Mobility | DP, T | [6 empty] | 2022 | 315000 | 315000
Robeson | NC 72 |  | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Highway | Other | 6 | Lumber River RPO | HO-0014 | Region C | DP, HF, HSIP | 2026 | 760000 | 2026 | 210000 | 2027 | 8600000 | 2024 | 1430000 | 11000000 | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH.
Robeson | US 74 (Future I-74) | NCDOT | Bridges 770466 and 770118 over the Lumber River | Reinforce shoulder embankments. |  | Highway | Other | 6 | Lumber River RPO | HO-0021 | Exempt | DP, S(M) |  |  |  |  | 2026 | 1950000 | 2025 | 305000 | 2255000 | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. S(M) FUNDS REPRESENT NC OFFICE OF STATE BUDGET AND MANAGEMENT FUNDING $225,000 AND NC DEPARTMENT OF ENVIRONMENTAL QUALITY FUNDING (UP TO $270,000).
Robeson | I-95 | NCDOT | Mile marker 2.0 to mile marker 12.45. | Install cable median barrier. | 10.45 | Highway | Safety | 6 | Lumber River RPO | HS-2006R | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 816000 |  |  | 816000
Robeson | NC 41 (Martin Luther King Jr Drive) | NCDOT | NC 72 (West Second Street) and SR 1599 (Martin Luther King Jr Drive) intersections. | Construct signalized pedestrian crossings. | 0.5 | Highway | Safety | 6 | Lumber River RPO | W-5806E | Region C | HSIP, T(M) |  |  |  |  | 2022 | 315000 |  |  | 315000 | UNDER CONSTRUCTION.
Robeson | NC 71 | NCDOT | Lumber Bridge city limits to Parkton city limits, and Parkton city limits to US 301. | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Lumber River RPO, Fayetteville Area MPO | HS-2006AD | Region C | HSIP, T(M) |  |  |  |  | 2024 | 320000 |  |  | 320000
Robeson | NC 710 | NCDOT | SR 1339 (Deep Branch Road) intersection in Pembroke. | Construct roundabout. | 0.5 | Highway | Safety | 6 | Lumber River RPO | W-5706N | Region C | CRPLT5, HF, L, T(M) |  |  |  |  | 2024 | 4728000 |  |  | 4728000 | RIGHT-OF-WAY IN PROGRESS.
Robeson | NC 710 | NCDOT | SR 1340 (Prospect Road) intersection. | Construct roundabout. | 0.5 | Highway | Safety | 6 | Lumber River RPO | HS-2006I | Region C | HSIP, T(M) | 2024 | 250000 |  |  | 2025 | 2200000 |  |  | 2450000 | RIGHT-OF-WAY IN PROGRESS
Robeson | NC 72 | NCDOT | NC 711 to NC 710. | Install rumble stripes and pavement markings. | 14.42 | Highway | Safety | 6 | Lumber River RPO | HS-2006U | Region C | HSIP, T(M) |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
Robeson | NC 72 | NCDOT | US 74 to NC 41 / NC 211. | Install rumble stripes and pavement markings. | 11.84 | Highway | Safety | 6 | Lumber River RPO | HS-2006T | Region C | HSIP, T(M) |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
Robeson | SR 1340 (Odom Street / Prospect Road) | NCDOT | NC 771 (Third Street) and SR 1566 (Corinth Road) in Pembroke. | Install crosswalks, pedestrian signal heads, refuge islands and rectangular rapid flashing beacons. Upgrade traffic signal. | 0.89 | Highway | Safety | 6 | Lumber River RPO | HS-2006AA | Region C | HSIP, T(M) |  |  |  |  | 2025 | 836000 |  |  | 836000 | UNDER CONSTRUCTION.
Robeson | SR 1561 (University Road) | NCDOT | NC 711 to Hawk Drive in Pembroke. | Install pedestrian signals and crosswalks. | 0.51 | Highway | Safety | 6 | Lumber River RPO | HS-2006AE | Division 6 | HSIP, T(M) |  |  |  |  | 2025 | 300000 |  |  | 300000 | UNDER CONSTRUCTION.
Robeson | SR 1935 (Howell Road) | NCDOT | SR 1924 (Barker Ten Mile Road) intersection, and north leg of SR 1005 (Tolarsville Road) intersection. | Upgrade intersection to all way stop, and realign intersection. | 0.5 | Highway | Safety | 6 | Lumber River RPO | HS-2006D | Division 6 | HSIP, T(M) | 2022 | 24000 |  |  | 2024 | 566000 |  |  | 590000 | UNDER CONSTRUCTION.
Robeson | US 301 | NCDOT | Mile marker 24.42 to 32.52 and mile marker 33.865 to 40.92 | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Lumber River RPO | HS-2406L | Region C | HSIP, T(M) |  |  |  |  | 2025 | 670000 |  |  | 670000 | UNDER CONSTRUCTION.
Robeson | US 301; SR 1003 (Chicken Road) | NCDOT | Mile marker 10.14 to 22.23; Mile marker 5.785 to 19.004 | Install rumble stripes and pavement markings. |  | Highway | Safety | 6 | Lumber River RPO | HS-2406M | Region C | HSIP, T(M) |  |  |  |  | 2025 | 240000 |  |  | 240000 | UNDER CONSTRUCTION.
Robeson | US 501 | NCDOT | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Highway | Safety | 6 | Lumber River RPO | HS-2406B | Region C | HSIP, T(M) | 2025 | 30000 | 2025 | 70000 | 2026 | 1250000 |  |  | 1350000
Robeson | US 501 | NCDOT | NC 130 to Scotland County line. | Install rumble stripes. | 5.41 | Highway | Safety | 6 | Lumber River RPO | HS-2006S | Region C | HSIP, T(M) |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
Robeson | US 501 / NC 130 | NCDOT | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Highway | Safety | 6 | Lumber River RPO | HS-2006J | Region C | HSIP, T(M) | 2024 | 68000 | 2025 | 70000 | 2025 | 990000 |  |  | 1128000 | RIGHT-OF-WAY IN PROGRESS
Robeson | I-95 | NCDOT | Carthage Road (Exit 19) to US 301 (Fayetteville Road) (Exit 22). | Widen to eight lanes. | 2.79 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6064B | Statewide Mobility | T | 2022 | 9788000 | 2022 | 3425000 | 2022 | 125846000 |  |  | 139059000 | UNDER CONSTRUCTION.
Robeson | I-95 | NCDOT | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6064A | Region C | DP, T | 2021 | 3087000 | 2021 | 6700000 | 2021 | 260685000 |  |  | 270472000 | UNDER CONSTRUCTION.
Robeson | I-95 | NCDOT | Mile marker 13 to mile marker 22. | Widen to eight lanes and rehabilitate pavement. | 9 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6064 | [11 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879.
Robeson | I-95 | NCDOT | North of Lumberton. | Construct weigh in motion station. | 2 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-5987AA | Region C | O |  |  |  |  | 2027 | 4500000 |  |  | 4500000 | O FUNDS REPRESENT STATE PRIMARY MAINTENANCE FUNDS FOR WEIGH STATIONS.
Robeson | I-95 | NCDOT | South of NC 20 to south of proposed I-295. | Widen to eight lanes. | 6.28 | Highway | STI (Prioritization) | 6 | Lumber River RPO, Fayetteville Area MPO | I-5987B | Region C | T | 2021 | 3581000 | 2021 | 2624000 | 2023 | 367456000 |  |  | 373661000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE)
Robeson | I-95 | NCDOT | South of US 301 to south of NC 20. | Widen to eight lanes. | 10.24 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-5987A | Region C | T | 2021 | 3395000 | 2022 | 3075000 | 2023 | 323869000 |  |  | 330339000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE)
Robeson | I-95 | NCDOT | South of US 301 to south of proposed I-295. | Install gauge, modeling / hydraulic studies, and stress testing along corridor. | 16.52 | Highway | STI (Prioritization) | 6 | Lumber River RPO, Fayetteville Area MPO | I-5987C | Region C | DP, T | [6 empty] | 2022 | 315000 | 315000
Robeson | I-95 | NCDOT | South of US 301 to south of proposed I-295. | Widen to eight lanes. | 15.7 | Highway | STI (Prioritization) | 6 | Lumber River RPO, Fayetteville Area MPO | I-5987 | Region C | [10 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. AA BREAK: O FUNDS REPRESENT WEIGH STATION FUNDING.
Robeson | I-95 | NCDOT | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-5879 | Division 6 | NHP, T(M) | 2026 | 8150000 |  |  | 2021 | 15028000 |  |  | 23178000 | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C.
Robeson | NC 211 (North Roberts Avenue) | NCDOT | SR 1531 (Saddletree Road / Clybourn Church Road) intersection in Lumberton | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 6 | Lumber River RPO | HP-0019 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 |  |  | 5300000
Robeson | NC 41 (East Elizabethtown Road) | NCDOT | SR 2110 (Snake Road) to Sycamore Lane. | Widen existing roadway. | 1.85 | Highway | STI (Prioritization) | 6 | Lumber River RPO | R-5888 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 |  |  | 7000000
Robeson | SR 1945 (Meadow Road) | NCDOT | SR 1984 (Linkhaw Road) intersection in Lumberton | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 6 | Lumber River RPO | R-5954 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3600000 |  |  | 4300000
Robeson | SR 1997 (Fayetteville Road) | NCDOT | Farrington Street to East 22nd Street. | Widen to six lanes and modernize roadway. | 1.26 | Highway | STI (Prioritization) | 6 | Lumber River RPO | U-5797 | Division 6 | T | 2023 | 8200000 | 2024 | 2600000 | 2026 | 48405000 |  |  | 59205000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE).
Robeson | US 74 (Future I-74) | NCDOT | NC 72 / NC 130 intersection north of Boardman | Upgrade at-grade intersection to interchange. | 1 | Highway | STI (Prioritization) | 6 | Lumber River RPO | R-5751 | Region C | T | 2021 | 325000 |  |  | 2023 | 28286000 |  |  | 28611000 | UNDER CONSTRUCTION.
Robeson | US 74 (Future I-74) | NCDOT | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6011A | Division 6 | BGLT5, T(M) | 2025 | 300000 | 2025 | 300000 | 2027 | 9200000 |  |  | 9800000 | RIGHT-OF-WAY IN PROGRESS
Robeson | NC 41 (Martin Luther King Jr. Drive) | NCDOT | CSX Crossing 631029P in Lumberton. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Lumber River RPO | RX-2006E | Division 6 | RR |  |  |  |  | 2026 | 446000 |  |  | 446000
Robeson | SR 1154 (Union School Road) | NCDOT | CSX Crossing 629606K near Pembroke. | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Lumber River RPO | RX-2006B | Division 6 | RR |  |  |  |  | 2024 | 1450000 |  |  | 1450000
Robeson | SR 1748 (Crenshaw Road) | NCDOT | CSX Crossing 629581S in Rex. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Lumber River RPO | RX-2006G | Division 6 | RR |  |  |  |  | 2027 | 417000 |  |  | 417000
Robeson, Cumberland | I-295 (Fayetteville Outer Loop) | NCDOT | I-95 in Robeson County to south of SR 1118 (Parkton Road) in Cumberland County. | Construct freeway on new location. | 1.88 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519AA | Region C | NHP, T(M) |  |  |  |  | 2018 | 260442000 |  |  | 260442000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032.
Robeson, Cumberland, Johnston, Nash, Halifax, Wilson, Harnett, Northampton | I-95 | NCDOT | South Carolina state line to Virginia state line. | Install broadband fiber for traveler information systems. | 181.34 | Highway | Other | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | I-5986C | Statewide Mobility | DP, T |  |  |  |  | 2021 | 42167000 |  |  | 42167000 | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
Rockingham | SIF | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | Rockingham County / NC Shiloh Airport | Construct t-hangar taxilanes for addition of t-hangars. |  | Aviation | STI (Prioritization) | 7 | Piedmont Triad RPO | AV-5898 | Division 7 | T |  |  |  |  | 2024 | 810000 |  |  | 810000
Rockingham | SR 1747 (East Stadium Drive) | NCDOT | SR 1962 (North Pierce Street) to Freedom Park in Eden | Construct sidewalk. | 0.57 | Bike & Ped | STI (Prioritization) | 7 | Piedmont Triad RPO | EB-5888 | Division 7 | L(M), TA5T50 |  |  |  |  | 2026 | 1901000 |  |  | 1901000
Rockingham | US 220 Business | MAYODAN | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Bike & Ped | STI (Prioritization) | 7 | Piedmont Triad RPO | EB-5891 | Division 7 | L(M), TALT5 | 2030 | 510000 | 2030 | 1300000 | 2032 | 6599000 | 2026 | 350000 | 8759000
Rockingham | NC 14 / NC 87 | NCDOT | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-6038 | Region D | BFP, T(M) | 2026 | 460000 | 2026 | 760000 | 2028 | 7603000 |  |  | 8823000
Rockingham | SR 1138 (Lindsey Bridge Road) | NCDOT | Bridge 780140 over Dan River. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5716 | Division 7 | BGOFF | 2023 | 610000 |  |  | 2025 | 15020000 |  |  | 15630000 | RIGHT-OF-WAY IN PROGRESS
Rockingham | SR 1169 (Island Drive) | NCDOT | Bridge 780277 over Big Beaver Island Creek. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5722 | Division 7 | BGOFF | 2023 | 200000 |  |  | 2025 | 2400000 |  |  | 2600000
Rockingham | SR 1535 (Price Road) | NCDOT | Bridge 780177 over Matrimony Creek in Eden. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | HB-0035 | Division 7 | BGOFF | 2025 | 410000 | 2025 | 300000 | 2026 | 4900000 |  |  | 5610000
Rockingham | SR 1700 (Fisher Hill Road) | NCDOT | Bridge 780176 over NC 14 / NC 87 | Replace bridge. |  | Highway | Bridges | 7 | Piedmont Triad RPO | BR-0096 | Division 7 | BGOFF |  |  |  |  | 2026 | 2300000 |  |  | 2300000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
Rockingham | SR 2150 (River Road) | NCDOT | Bridge 780123 over US 220 / US 311 | Replace bridge. |  | Highway | Bridges | 7 | Piedmont Triad RPO | BR-0141 | Division 7 | BGOFF |  |  |  |  | 2027 | 4100000 |  |  | 4100000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
Rockingham | SR 2177 (Dan Valley Road) | NCDOT | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5721 | Division 7 | BGLT5, T(M) | 2022 | 188000 | 2022 | 336000 | 2023 | 4853000 |  |  | 5377000 | UNDER CONSTRUCTION
Rockingham | US 220 / Future I 73 | NCDOT | NC 68 intersection | Convert at-grade intersection to interchange. | 1 | Highway | Pre-STI (Historic) | 7 | Piedmont Triad RPO | R-2413CA | Pre-STI (Transition) | [10 empty] | IN PROGRESS
Rockingham | NC 14 | NCDOT | 1050 feet North of Cox Street to NC 87. | Install rumble strips. | 3.91 | Highway | Safety | 7 | Piedmont Triad RPO | HS-2407I | Region D | HSIP |  |  |  |  | 2027 | 410000 |  |  | 410000
Rockingham | US 311 | NCDOT | SR 2141 (Young Road) to NC 14, south of Eden. | Install rumble strips and 6-inch long life pavement markings. | 8.4 | Highway | Safety | 7 | Piedmont Triad RPO | HS-2407R | Region D | HSIP, T(M) |  |  |  |  | 2027 | 660000 |  |  | 660000
Rockingham | Future I-73 / US 220 | NCDOT | US 311 / NC 135 interchange near Mayodan. | Replace bridge 780074 and upgrade interchange. | 1 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | I-5898 | Region D | T | 2022 | 1500000 | 2022 | 1600000 | 2026 | 20900000 |  |  | 24000000 | RIGHT-OF-WAY IN PROGRESS
Rockingham | NC 65 / NC 87 | NCDOT | West of SR 2371 (Old County Home Road) in Wentworth to US 158 / US 29 Business (Freeway Drive) in Reidsville. | Upgrade roadway. |  | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | R-5766 | Division 7 | BGANY | 2030 | 18600000 | 2030 | 4800000 | 2034 | 36800000 |  |  | 60200000
Rockingham | NC 87 | NCDOT | SR 1998 (Wentworth Street) / SR 1001 (Sandy Cross Road) intersection in Wentworth. | Realign intersections. | 0.5 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | R-5704 | Region D | [10 empty] | UNDER CONSTRUCTION
Rockingham, Guilford | US 220 / Future I 73 | NCDOT | Haw River to NC 68 / US 220 Intersection | Construct roadway. | 5.071 | Highway | Pre-STI (Historic) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-2413C | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Rockingham, Guilford | NC 65 / NC 68 | NCDOT | US 158 in Stokesdale in Guilford County to I-73 / US 220 in Rockingham County. | Construct multiple intersection improvements along corridor. | 3.61 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-5823 | Division 7 | BGLT5, T(M) | 2030 | 10500000 | 2030 | 3300000 | 2034 | 29200000 |  |  | 43000000
Rockingham, Guilford | US 29 (Future I-785) | NCDOT | NC 150 to US 158 / NC 14 in Reidsville | Upgrade corridor to interstate standards. | 11.12 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-5889B | Not Funded | T | NOT FUNDED | 9364000 | NOT FUNDED | 5430000 | NOT FUNDED | 116450000 | NOT FUNDED |  | 131244000
Rockingham, Guilford | US 29 (Future I-785) | NCDOT | North of I-785 in Greensboro to US 158 / NC 14 in Reidsville. | Upgrade corridor to interstate standards. | 15.59 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-5889 | Region D
Rowan | 8th Street Greenway HAWK | CRMPO | Kannapolis | Install pedestrian signal. | 0.1 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | BL-0177 | Exempt | BGDA, L(M) | 2027 | 35000 | 2027 | 63000 | 2027 | 435000 | 2026 | 70000 | 603000
Rowan | Arlington Avenue | SALISBURY | Salisbury. | Construct sidewalks. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908D | Exempt | [10 empty] | COMPLETE
Rowan | Grants Creek Greenway | SALISBURY | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | EB-5619B | Division 9 | BGDA, L(M) | 2020 | 825000 | 2025 | 10000 | 2026 | 1725000 |  |  | 2560000 | RIGHT-OF-WAY IN PROGRESS
Rowan | Grants Creek Greenway | SALISBURY | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | EB-5619C | Division 9 | BGDA, L(M), TADA | 2026 | 65000 | 2026 | 45000 | 2027 | 2044000 | 2024 | 675000 | 2829000
Rowan | Grants Creek Greenway | SALISBURY | Vicinity of Forestdale Drive to Catawba College in Salisbury. | Construct low-water bridge greenway connection. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | EB-5619A | Division 9 | [10 empty] | COMPLETE
Rowan | Kerns Street; North Oak Street; Crook Street | GRANITE QUARRY | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | BL-0088 | Division 9 | BGDA, L(M), TADA | 2025 | 90000 | 2025 | 35000 | 2026 | 790000 | 2024 | 85000 | 1000000
Rowan | Main Street | SALISBURY | D Avenue to Sunset Drive in Salisbury | Construct sidewalk. | 0.43 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908H | Exempt | [10 empty] | UNDER CONSTRUCTION
Rowan | Newsome Road | SALISBURY | SR 1002 (Bringle Ferry Road) to SR 1004 (Stokes Ferry Road) in Salisbury. | Construct sidewalks. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908F | Exempt | [10 empty] | PROJECT DELETED AT MPO REQUEST
Rowan | Various | SALISBURY | Locations in Salisbury | Construct sidewalks. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908 | Exempt
Rowan | Grants Creek Greenway | SALISBURY | Kelsey Scott Park to Catawba College in Salisbury | Construct multi-use path. |  | Bike & Ped | Other | 9 | Cabarrus-Rowan MPO | EB-5619 | Division 9 | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SALISBURY
Rowan | Various | SALISBURY | Ryan Street to Celebration Drive and South Boundary Street from Hillsboro Street to Hills Street in Salisbury. | Construct sidewalks. |  | Bike & Ped | Pre-STI (Historic) | 9 | Cabarrus-Rowan MPO | C-4908B | Exempt | [10 empty] | COMPLETE
Rowan | Various | SALISBURY | Various streets around Salisbury High School in Salisbury. | Construct sidewalk. |  | Bike & Ped | Pre-STI (Historic) | 9 | Cabarrus-Rowan MPO | C-4908C | Exempt | [10 empty] | COMPLETE
Rowan | SR 2739 (North Main Street) | KANNAPOLIS | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Bike & Ped | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | EB-5921 | Division 9 | L(M), TAANY | 2030 | 700000 | 2030 | 1100000 | 2033 | 2600000 | 2026 | 450000 | 4850000 | COORDINATE WITH U-6062
Rowan | Third Street Greenway | SPENCER | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Bike & Ped | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | EB-5861 | Division 9 | L(M), TAANY | 2026 | 10000 | 2026 | 10000 | 2026 | 4286000 | 2024 | 185000 | 4491000
Rowan | SR 1724 (Hurley School Road) | NCDOT | Bridge 790066 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 9 | Cabarrus-Rowan MPO | B-5772 | Division 9 | BGOFF | 2021 | 77000 | 2021 | 31000 | 2022 | 3009000 |  |  | 3117000 | UNDER CONSTRUCTION
Rowan | NC 152 | NCDOT | Intersection with Access Road east of I-85 / US 601 in China Grove. | Widen pavement and construct roundabout. |  | Highway | Economic Development | 9 | Cabarrus-Rowan MPO | HE-0009 | Division 9 | T |  |  |  |  | 2025 | 5411000 | 2022 | 1489000 | 6900000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS.
Rowan | NC 152 | NCDOT | NC 152, intersection with proposed access road east of I-85 / US 601 in China Grove | Construct intersection improvements. Widen pavement and construct turn lanes for Phase I of roadway improvements. | 0.4 | Highway | Economic Development | 9 | Cabarrus-Rowan MPO | HE-0009A | Division 9 | T |  |  |  |  | 2023 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION. CONSTRUCTION BY STATE FORCES. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS.
Rowan | SR 2120 (Long Ferry Road) | NCDOT | SR 2182 (I-85 Service Road) near Spencer. | Construct Right-turn lane on SR 2120, and remove residual pavement and strengthen remaining pavement on SR 2182 (I-85 Service Road). | 0.6 | Highway | Economic Development | 9 | Cabarrus-Rowan MPO | U-6237 | Division 9 | T |  |  | 2021 | 50000 | 2021 | 365000 |  |  | 415000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM
Rowan | I-85 | NCDOT | US 29 / US 601 in China Grove to US 601 (Jake Alexander Boulevard) in Salisbury and from south of US 52 in Salisbury to north of SR 2120 (Long Ferry Road) in Spencer. | Rehabilitate pavement. | 1.08 | Highway | Interstate Maintenance | 9 | Cabarrus-Rowan MPO | I-5858 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 12012000 |  |  | 12012000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
Rowan | Brenner Avenue | SALISBURY | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0049 | Division 9 | BGDA, L(M), TADA | 2026 | 14000 | 2026 | 200000 | 2027 | 3447000 | 2023 | 220000 | 3881000
Rowan | McCanless Road | CRMPO | I-85 | Construct interchange ramps. | 0.1 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0176 | Exempt | BGDA, L(M) | [6 empty] | 2026 | 4108000 | 4108000
Rowan | New Route | NCDOT | SR 1211 (Kimball Road) extension, SR 1242 (North Chapel Street) to SR 1221 (Bostian Road) in Landis. | Construct two-lane connector on new location. | 0.27 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | U-5608 | Division 9 | [10 empty] | PROJECT COMPLETED
Rowan | US 29 (Main Street) | SALISBURY | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0064 | Division 9 | BGDA, L(M) |  |  | 2026 | 3261000 | 2026 | 19221000 | 2024 | 10000 | 22492000
Rowan | Various | SALISBURY | Locations in Salisbury. | Upgrade signal System. |  | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0005 | Division 9 | BGDA, L(M) |  |  |  |  | 2022 | 429000 |  |  | 429000
Rowan | Brenner Avenue | SALISBURY | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Highway | Other | 9 | Cabarrus-Rowan MPO | C-5603H | Exempt | CMAQ, CRPANY, L, L(M) |  |  | 2025 | 275000 | 2026 | 1594000 |  |  | 1869000 | $676,032 IN CMAQ TRANSFERRED FROM BL-0034
Rowan | Horah Street | SALISBURY | Brenner Avenue to Partee Street in Salisbury. | Construct sidewalk. |  | Highway | Other | 9 | Cabarrus-Rowan MPO | C-4908A | Exempt | [10 empty] | PROJECT DELETED AT MPO REQUEST
Rowan | SR 1002 (Old Concord Road) | SALISBURY | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Highway | Other | 9 | Cabarrus-Rowan MPO | C-5603D | Exempt | CMAQ, L(M) | 2024 | 15000 |  |  | 2026 | 1950000 |  |  | 1965000
Rowan | NC 152 | NCDOT | Iredell County line to SR 1211 (Patterson Street/Brown Road) | Install rumble stripes and 6-inch long life pavement markings. | 7.9 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2409F | Region D | HSIP |  |  |  |  | 2026 | 620000 |  |  | 620000
Rowan | NC 152 | NCDOT | NC 153 intersection near China Grove. | Construct intersection improvements. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2009I | Region D | HSIP, T(M) | 2024 | 20000 |  |  | 2025 | 380000 |  |  | 400000
Rowan | NC 153 (Rice Street) | NCDOT | SR 1197 (Cannon Farm Road / Mt Moriah Church Road) in China Grove. | Construct roundabout. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | W-5709E | Region D | BGANY |  |  |  |  | 2024 | 2500000 |  |  | 2500000 | RIGHT-OF-WAY IN PROGRESS
Rowan | SR 1002 (Old Concord Road) | NCDOT | Jake Alexander Boulevard in Salisbury to the Cabarrus County line. | Install pavement markings. | 10.94 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2009E | Division 9 | HSIP, T(M) |  |  |  |  | 2023 | 396000 |  |  | 396000
Rowan | SR 1002 (Old Concord Road) | NCDOT | Martin Luther King Jr. Avenue South intersection | Upgrade traffic signal and install/upgrade pedestrian signals and other pedestrian accommodations. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2409B | Division 9 | HSIP, T(M) |  |  | 2025 | 30000 | 2026 | 160000 |  |  | 190000
Rowan | SR 1007 (Jake Alexander Boulevard) | NCDOT | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2009D | Division 9 | HSIP, T(M) | 2022 | 50000 | 2022 | 20000 | 2023 | 520000 |  |  | 590000 | UNDER CONSTRUCTION
Rowan | US 29-70/NC 150 (Salisbury Avenue); SR 1915 (Andrews Street/Jefferson Street) | NCDOT | SR 1915 (Jefferson Street), 4th Street, 5th Street, and 6th Street intersections; SR 2100 (Long Street) intersection | Upgrade traffic signals with pedestrian accommodations and upgrade curb ramps. | 2.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2409L | Region D | HSIP | 2026 | 5000 | 2026 | 5000 | 2026 | 270000 |  |  | 280000
Rowan | I-85 | NCDOT | SR 1221 (Old Beatty Ford Road) intersection near Landis. | Upgrade grade separation to interchange. | 1 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | I-3804 | Division 9 | [10 empty] | INCLUDED IN I-3802B - DESIGN-BUILD PROJECT
Rowan | I-85 | NCDOT | SR 2180 (Lane Street) in Cabarrus County to US 29 / US 601 connector in Rowan County. | Widen to eight lanes. | 6.49 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | I-3802B | Statewide Mobility | [10 empty] | COMPLETE - DESIGN-BUILD PROJECT
Rowan | NC 150 | NCDOT | SR 1526 (Rowan Mill Road) and SR 1526 (Sherrills Ford Road) intersections in Sherrills Ford and Salisbury | Add storage and turn lanes. |  | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | HP-0029 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 |  |  | 19900000
Rowan | NC 152 | NCDOT | SR 1509 (Miller Road) intersection in China Grove | Construct roundabout. |  | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | HP-0028 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 |  |  | 6100000
Rowan | New Route | NCDOT | Airport Parkway, SR 1710 (Harrison Road) near US 70 / US 601 (Jake Alexander Boulevard) to SR 2539 (Peach Orchard Road) at US 29 in Salisbury. | Construct 2-lane roadway. | 3.63 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5901 | Division 9 | BGANY, T(M) | 2030 | 19600000 | 2030 | 7900000 | 2034 | 52090000 |  |  | 79590000
Rowan | New Route | NCDOT | SR 1006 (Faith Road) to US 52 (East Innes Street) | Construct multi-lane roadway on new location. | 0.1 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5820B | Division 9 | T |  |  |  |  | 2020 | 1100000 |  |  | 1100000
Rowan | New Route | NCDOT | SR 2576 (Bendix Drive) to SR 1006 (Faith Road) | Construct multi-lane roadway on new location. | 0.42 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5820A | Division 9 | T |  |  |  |  | 2019 | 2609000 |  |  | 2609000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
Rowan | New Route | NCDOT | SR 2576 (Bendix Drive) to US 52 (East Innes Street) at Newsome Road in Salisbury. | Construct a new multi-lane roadway. | 0.6 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5820 | [11 empty] | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY
Rowan | SR 2528 (Julian Road) | NCDOT | US 601 (Jake Alexander Boulevard) to SR 2667 (Summit Park Drive) in Salisbury. | Widen to four lane divided facility with bike-ped accommodations. | 1.28 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5738 | Division 9 | T |  |  |  |  | 2022 | 14995000 |  |  | 14995000 | UNDER CONSTRUCTION
Rowan | SR 2739 (North Main Street / South Main Street) | NCDOT | SR 2000 (Jackson Park Road) / North Loop Road in Kannapolis to SR 1211 (Kimball Road) in China Grove | Upgrade roadway incorporating bicycle lanes and sidewalks. | 4.26 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-6062 | Division 9 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35800000 |  |  | 80400000 | COORDINATE WITH EB-5921
Rowan | US 52 | NCDOT | Proposed Granite Quarry bypass | Construct 3-lane facility on new location. | 4.63 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | R-5860C | Not Funded | NHP, T(M) | NOT FUNDED | 5500000 | NOT FUNDED | 900000 | NOT FUNDED | 36500000 | NOT FUNDED |  | 42900000
Rowan | US 52 | NCDOT | Proposed Rockwell bypass | Construct 3-lane facility on new location. | 3.63 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | R-5860B | Not Funded | NHP, T(M) | NOT FUNDED | 8200000 | NOT FUNDED | 500000 | NOT FUNDED | 22300000 | NOT FUNDED |  | 31000000
Rowan | SR 1002 (Bringley Ferry Road) | SALISBURY | Long Street to Newsome Road in Salisbury | Construct sidewalk. |  | Highway | Transition | 9 | Cabarrus-Rowan MPO | C-4908E | Exempt | [10 empty] | COMPLETE
Rowan | US 70 (Statesville Boulevard) | SALISBURY | US 601 (Jake Alexander Boulevard) | Construct sidewalk. |  | Highway | Transition | 9 | Cabarrus-Rowan MPO | C-4908G | Exempt | [10 empty] | UNDER CONSTRUCTION
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Funding for preventive maintenance for bus and bus facility, facility improvements and repairs, automatic bus washer, shop equipment, fueling system, security gate upgrade. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TD-5302 | Public Transit | 5339, L | [6 empty] | 2020 | 1720000 | 1720000
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TS-5133 | Public Transit | 5307 | [6 empty] | 2025 | 28000 | 28000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City of Salisbury | CITY OF SALISBURY | Systemwide | Purchase expansion vehicle (ADA paratransit, administration). |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TA-5182 | Public Transit | 5339, L | [6 empty] | 2022 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Purchase replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TA-5181 | Public Transit | 5307, L | [6 empty] | 2020 | 8235000 | 8235000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City Of Salisbury | SALISBURY TRANSIT ( CITY OF SALISBURY) | Systemwide | Replace four transit buses that have exceeded their useful life, and replace vehicle related equipment such as fare boxes, destination signs, camera systems and automated voice annunciation system. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TC-0023 | Public Transit | 5339(b), L | [6 empty] | 2021 | 4560000 | 4560000
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Cabarrus-Rowan MPO | TO-5135 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 3560000 | 3560000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Cabarrus-Rowan MPO | TO-5201 | Public Transit | SMAP | [6 empty] | 2020 | 1808000 | 1808000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Funding for operating free fare. |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Cabarrus-Rowan MPO | TO-5139 | Public Transit | CMAQ, L | [6 empty] | 2020 | 336000 | 336000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City of Salisbury | CITY OF SALISBURY | Systemwide | Funding for planning assistance -5303 |  | Public Transportation (Transit) | Planning | 9 | Cabarrus-Rowan MPO | TP-5150 | Public Transit | 5303, L | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City of Salisbury | CITY OF SALISBURY | Systemwide | Funding for AVL system. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-6179 | Public Transit | 5339, L | [6 empty] | 2020 | 1400000 | 1400000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City Of Salisbury | CITY OF SALISBURY | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-5233 | Public Transit | 5307, L | [6 empty] | 2020 | 1120000 | 1120000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City of Salisbury | CITY OF SALISBURY | Various locations | Funding for ADA services. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-5260 | Public Transit | 5307, L | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | City of Salisbury | CITY OF SALISBURY | Various locations | Funding for preventive maintenance on buses and facilities. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-5232 | Public Transit | 5307, L | [6 empty] | 2020 | 3336000 | 3336000 | FUNDS AUTHORIZED IN PROGRESS
Rowan | SR 1526 (Henderson Grove Church Road) | NCDOT | Railroad crossing 724 362M | Close railway-highway crossing and construct roadway on new location to Julian Road. |  | Rail | Rail-Highway Grade Crossing Closure | 9 | Cabarrus-Rowan MPO | Y-5500IA | Division 9 | RR |  |  |  |  | 2024 | 4900000 |  |  | 4900000
Rowan | Norfolk Southern | NCDOT | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5733 | Division 9 | CMAQ, T | 2026 | 5300000 |  |  | 2026 | 5699000 | 2024 | 720000 | 11719000 | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0.
Rowan | Norfolk Southern | NCDOT | Norfolk Southern mainline in Rowan County. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall and signal equipment. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5726 | Region D | T | 2019 | 1638000 |  |  | 2028 | 13600000 |  |  | 15238000
Rowan | Norfolk Southern Mainline | NCDOT | Salisbury Train Station | Construct second platform and pedestrian underpass. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5726A | Region D | T |  |  |  |  | 2027 | 2500000 |  |  | 2500000
Rowan | Norfolk Southern Mainline | SALISBURY | Salisbury Norfolk Southern Crossover. | Relocation. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5726B | Region D | T |  |  |  |  | 2026 | 4000000 |  |  | 4000000
Rowan | North Carolina Railroad / Norfolk Southern Main Line | NCDOT | SR 2120 (Long Ferry Rd). | Construct grade separation and close crossing #715307Nr. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | RP-0006 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15000000 |  |  | 20200000
Rowan, Cabarrus | US 52 | NCDOT | Proposed Misenheimer Bypass to Granite Quarry Bypass. | Widen to three lane roadway. | 4.54 | Highway | STI (Prioritization) | 9, 10 | Cabarrus-Rowan MPO | R-5860 | Division 9, 10
Rowan, Cabarrus | US 52 | NCDOT | Proposed Misenheimer Bypass to proposed Rockwell Bypass. | Widen to three lane roadway. | 4.54 | Highway | STI (Prioritization) | 9, 10 | Cabarrus-Rowan MPO | R-5860A | Division 9, 10 | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50500000 |  |  | 79800000
Rutherford | Thermal Belt Rail Trail | NCDOT | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5966 | Division 13 | L, TA5T50 | 2027 | 666000 | 2027 | 500000 | 2027 | 2100000 | 2024 | 150000 | 3416000
Rutherford | New Route | NCDOT | Rutherfordton Industrial Park. | Construct access road. | 0.14 | Highway | Appalachian Development Highway System | 13 | Foothills RPO | HA-0005 | Exempt | ADHSL | 2027 | 15000 |  |  | 2028 | 900000 | 2022 | 15000 | 930000 | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045
Rutherford | SR 1306 (Bills Creek Road) | NCDOT | Bridge 800628 over Lake Lure Dam and Broad River. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Foothills RPO | B-5871 | Division 13 | BGOFF | 2027 | 410000 |  |  | 2028 | 20800000 |  |  | 21210000
Rutherford | SR 2125 (Harris Henrietta Road) | NCDOT | Bridge 800145 over Floyds Creek. | Replace bridge. | 0.25 | Highway | Bridges | 13 | Foothills RPO | B-6047 | Division 13 | BGOFF | 2024 | 210000 |  |  | 2026 | 3000000 |  |  | 3210000 | RIGHT-OF-WAY IN PROGRESS.
Rutherford | US 221A (Charlotte Road) | NCDOT | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Highway | Locally Selected | 13 | Foothills RPO | HL-0065 | Division 13 | 5311, CRPANY, DP, HF(M), HSIP, L, T(M) | 2025 | 3550000 | 2025 | 2110000 | 2026 | 25950000 | 2023 | 3102000 | 34712000 | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT
Rutherford | Rutherfordton | RUTHERFORDTON | Systemwide | Purchase four electric vehicles |  | Highway | NCDOT Selected (Other Selection Process) | 13 | Foothills RPO | HN-0043 | Exempt | CRP550, L(M) | [6 empty] | 2026 | 291000 | 291000
Rutherford | US 64 / US 74A |  | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 13 | Foothills RPO | HN-0019 | Region G | CRP550, T(M) | 2026 | 3300000 | 2026 | 250000 | 2026 | 6000000 | 2024 | 650000 | 10200000
Rutherford | US 221 | NCDOT | South Carolina state line to south of Floyd's Creek. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 3.3 | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-2233AA | Division 13 | [10 empty] | COMPLETE
Rutherford | US 221 | NCDOT | South Carolina state line to south of Floyd's Creek. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 6.2 | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-2233AB | [11 empty] | COMPLETE
Rutherford | SR 1006 (Bostic Sunshine Highway) | NCDOT | North of Bostic municipal limit to NC 226. | Install rumble stripes with long life pavement markings. | 11.7 | Highway | Safety | 13 | Foothills RPO | HS-2413U | Division 13 | HSIP |  |  |  |  | 2026 | 237000 |  |  | 237000
Rutherford | SR 1006 (Bostic-Sunshine Highway) | NCDOT | SR 1007 (Andrews Mill Road / Piney Mountain Church Road) to NC 226 near Bostic. | Install guardrail. | 9.78 | Highway | Safety | 13 | Foothills RPO | HS-2013N | Division 13 | HSIP |  |  |  |  | 2024 | 875000 |  |  | 875000
Rutherford | SR 1510 (Hudlow Road) | NCDOT | US 221A to NC 64. | Upgrade guardrail. | 5.39 | Highway | Safety | 13 | Foothills RPO | HS-2013G | Division 13 | HSIP |  |  |  |  | 2023 | 497000 |  |  | 497000 | UNDER CONSTRUCTION.
Rutherford | SR 2241 (Oak Street) | NCDOT | SR 2159 (Pine Ridge Road) to US 74 in Forest City. | Widen existing roadway. | 0.64 | Highway | STI (Prioritization) | 13 | Foothills RPO | U-5833 | Division 13 | T | 2020 | 450000 |  |  | 2020 | 7530000 | 2020 | 1050000 | 9030000 | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $347,260 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
Rutherford | US 221 | NCDOT | North of US 74 Bypass in Rutherfordton to south of US 74 Business. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 4.52 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-2233BA | Division 13 | T | 2025 | 18100000 | 2025 | 3000000 | 2028 | 158700000 |  |  | 179800000 | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). $15M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE).
Rutherford | US 221 | NCDOT | South Carolina state line to north of SR 1366 (Roper Loop Road). | Widen to multi-lanes with bypass of Rutherfordton on new location. | 18.2 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-2233
Rutherford | US 221 | NCDOT | South of US 74 Business to north of SR 1366 (Roper Loop Road) in Rutherfordton. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 3.51 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-2233BB | Division 13 | T | 2021 | 20000000 |  |  | 2022 | 132797000 |  |  | 152797000 | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
Rutherford | Rutherfordton | RUTHERFORDTON | Systemwide | Purchase four vehicles |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | Foothills RPO | TN-6127 | Exempt | CRP550, L(M) | [6 empty] | 2025 | 291000 | 291000
Rutherford | Rutherford County Transit | RUTHERFORD COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 13 | Foothills RPO | TK-6161 | Public Transit | 5311, L, S | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
Rutherford, Burke | US 64 / NC 18; US 64 / US 74 | NCDOT | SR 1008 (Bills Creek Road) to Rutherfordton western municipal limit | Install long life pavement markings. | 17.46 | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO | HS-2413A | Region G | HSIP, T(M) |  |  |  |  | 2026 | 676000 |  |  | 676000
Rutherford, Burke, McDowell | US 64 | NCDOT | Rutherfordton Northeast Municipal Limit to Morganton Southwest Municipal Limit | Install long life pavement markings. | 28.03 | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO | HS-2413B | Region G | HSIP, T(M) |  |  |  |  | 2026 | 762000 |  |  | 762000
Rutherford, Burke, Mitchell, Yancey | Various | NCDOT | Secondary routes in Division 13. | Install long life pavement markings. |  | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO, High Country RPO | W-5813B | Division 13 | HSIP, T(M) |  |  |  |  | 2022 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
Sampson | CTZ | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | Clinton Sampson County Airport | Rehabilitate runway. |  | Aviation | STI (Prioritization) | 3 | Mid-Carolina RPO | AV-5823 | Division 3 | T |  |  |  |  | 2025 | 4400000 | 2024 | 232000 | 4632000
Sampson | NC 24 | NCDOT | Bridge 810056 over Six Runs Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-4636 | Statewide Mobility | BFP, HFB | 2020 | 390000 |  |  | 2031 | 9900000 |  |  | 10290000 | RIGHT-OF-WAY IN PROGRESS.
Sampson | SR 1206 (Wright Bridge Road) | NCDOT | Bridge 810072 over Great Coharie Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-6049 | Division 3 | BGOFF | 2023 | 340000 |  |  | 2024 | 1901000 |  |  | 2241000 | UNDER CONSTRUCTION.
Sampson | SR 1703 (Old Goldsboro Road) | NCDOT | Bridge 810348 over Beaverdam Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | BR-0122 | Division 3 | DP |  |  |  |  | 2021 | 727000 |  |  | 727000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
Sampson | SR 1804 (Houses Mill Road) | NCDOT | Bridge 810178 over Sevenmile Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | BR-0121 | Division 3 | DP |  |  |  |  | 2021 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
Sampson | SR 1817 (Bradshaw Road) | NCDOT | Bridge 810188 over Ward Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-5310 | Division 3 | BGOFF | 2023 | 100000 |  |  | 2024 | 1850000 |  |  | 1950000 | RIGHT-OF-WAY IN PROGRESS.
Sampson | SR 1904 (Pine Ridge Road) | NCDOT | Bridge 810248 over Six Runs Creek. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-5621 | Division 3 | BGOFF | 2021 | 154000 |  |  | 2022 | 2500000 |  |  | 2654000 | UNDER CONSTRUCTION.
Sampson | US 13 | NCDOT | Bridge 810009 over South River Overflow. | Replace bridge. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-4635 | Highway Fund | HFB |  |  |  |  | 2021 | 2250000 |  |  | 2250000 | UNDER CONSTRUCTION.
Sampson | I-40 | NCDOT | Johnston County line to Duplin County line. | Rehabilitate pavement. | 20.18 | Highway | Interstate Maintenance | 3 | Mid-Carolina RPO | HI-0011 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2028 | 22400000 |  |  | 22400000
Sampson | NC 24 | NCDOT | West of SR 1262 (Airport Road) to east of US 421 | Construct four lane divided highway, part on new location. |  | Highway | Pre-STI (Historic) | 3 | Mid-Carolina RPO | R-2303DA | [11 empty] | COMPLETED.
Sampson | NC 24 | NCDOT | Cumberland County line to east of SR 1292 (Dixie Road). | Install rumble stripes. | 17.25 | Highway | Safety | 3 | Mid-Carolina RPO | HS-2403Z | Region B | HSIP |  |  |  |  | 2027 | 439000 |  |  | 439000
Sampson | NC 41; NC 55 | NCDOT | Bladen County line to west of SR 1155 (Ward Road); East of NC 242 to east of Harnett County line. | Install rumble stripes and pavement markings. | 15.75 | Highway | Safety | 3 | Mid-Carolina RPO | HS-2403Y | Region B | HSIP |  |  |  |  | 2027 | 904000 |  |  | 904000
Sampson | US 421 | NCDOT | Pender County line to north of Pearson Road | Install rumble strips. | 22.1 | Highway | Safety | 3 | Mid-Carolina RPO | HS-2403AZ | Region B | HSIP |  |  |  |  | 2027 | 702000 |  |  | 702000
Sampson | US 421 | NCDOT | SR 1311 (Five Bridge Road) / SR 1356 (North Boulevard) intersection in Clinton. | Upgrade traffic signal. |  | Highway | Safety | 3 | Mid-Carolina RPO | HS-2403AB | Region B | HSIP |  |  |  |  | 2026 | 120000 |  |  | 120000
Sampson | NC 24 | NCDOT | US 421 / US 701 / SR 1296 (Sunset Avenue) to SR 1935 (Cecil Odie Road). | Construct four lane divide freeway, partially on new location. | 4.77 | Highway | STI (Prioritization) | 3 | Mid-Carolina RPO | R-2303E | Division 3 | T | 2020 | 4395000 |  |  | 2020 | 38396000 | 2020 | 5055000 | 47846000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Sampson | NC 24 | NCDOT | SR 1303 (Mitchell Loop Road) to US 421/ US 701 / SR 1296 (Sunset Avenue). | Construct four lane divided highway, part on new location. | 6.9 | Highway | Transition | 3 | Mid-Carolina RPO | R-2303D | Pre-STI (Transition) | [10 empty] | COMPLETE.
Sampson | NC 24 | NCDOT | SR 1404 (Sowdy Road) to SR 1303 (Mitchell Loop Road). | Construct four lane divided highway, part on new location. | 6.12 | Highway | Transition | 3 | Mid-Carolina RPO | R-2303C | Pre-STI (Transition) | [10 empty] | COMPLETE.
Sampson, Cumberland | NC 24 | NCDOT | SR 1853 (John Nunnery Road) in Cumberland County to SR 1404 (Dowdy Road) in Sampson County | Construct four lane divide freeway, partially on new location. | 6.95 | Highway | Pre-STI (Historic) | 3, 6 | Mid-Carolina RPO | R-2303B | Pre-STI (Transition) | [10 empty] | COMPLETE.
Sampson, Cumberland, Duplin | NC 24 | NCDOT | West of SR 1006 (Maxwell Road / Clinton Road) in Cumberland County to I-40 in Duplin County in Warsaw. | Construct four lane divide freeway, partially on new location. | 39.7 | Highway | STI (Prioritization) | 3, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Eastern Carolina RPO | R-2303
Sampson, Duplin | NC 24 | NCDOT | SR 1935 (Cecil Odie Road) in Sampson County to I-40 in Duplin County. | Construct four lane divide freeway, partially on new location. | 9.61 | Highway | STI (Prioritization) | 3 | Mid-Carolina RPO, Eastern Carolina RPO | R-2303F | Not Funded | T | NOT FUNDED | 35700000 | NOT FUNDED | 2300000 | NOT FUNDED | 338100000 | NOT FUNDED |  | 376100000 | PLANNING/DESIGN IN PROGRESS.
Scotland | SR 1108 (West Boulevard) | LAURINBURG | Glasgow Drive to east of US 15 / US 401 / US 501 (McColl Road) in Laurinburg. | Provide pedestrian accommodations at US 15 / US 401 / US 501 intersection and across US 74. |  | Bike & Ped | Locally Selected | 8 | Lumber River RPO | EB-5872B | Exempt
Scotland | SR 1107 (Atkinson Street) | NCDOT | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-5865 | Division 8 | L(M), TA5T50 | 2026 | 100000 | 2026 | 90000 | 2028 | 930000 | 2022 | 76000 | 1196000
Scotland | SR 1108 (West Boulevard) | LAURINBURG | SR 1105 (Turnpike Road) to Sunset Drive in Laurinburg | Construct sidewalk on west side, and provide pedestrian accommodations at US 15 / US 401 / US 501 intersection and across US 74. | 1.2 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-5872 | Division 8 | [10 empty] | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A.
Scotland | SR 1108 (West Boulevard) | NCDOT | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-5872A | Division 8 | L(M), TA5T50 | 2027 | 166000 |  |  | 2029 | 436000 | 2024 | 87000 | 689000
Scotland | US 401 Business (South Main Street) | NCDOT | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6015B | Division 8 | L(M), TA5T50 | 2027 | 30000 | 2027 | 290000 | 2028 | 1300000 | 2026 | 70000 | 1690000
Scotland | US 401 Business (South Main Street) | NCDOT | SR 1674 (Lauchwood Drive) to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 1 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6015
Scotland | US 401 Business (South Main Street) | NCDOT | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6015A | Division 8 | L(M), TA5T50 | 2026 | 76000 |  |  | 2028 | 660000 | 2022 | 66000 | 802000
Scotland | US 15 / US 501 | NCDOT | NC 144 intersection. | Construct roundabout. | 0.5 | Highway | Safety | 8 | Lumber River RPO | W-5208MA | Region E | [10 empty] | UNDER CONSTRUCTION
Scotland | US 74 (Future I-74) | NCDOT | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Highway | Safety | 8 | Lumber River RPO | HS-2008E | Statewide Mobility | HSIP, T | 2025 | 100000 | 2025 | 50000 | 2026 | 2940000 |  |  | 3090000 | RIGHT-OF-WAY IN PROGRESS
Scotland | US 74 (Future I-74) | NCDOT | Richmond County line to SR 1363. | Upgrade guardrail. | 4.33 | Highway | Safety | 8 | Lumber River RPO | HS-2008A | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2021 | 360000 |  |  | 360000 | UNDER CONSTRUCTION
Scotland | US 15 / US 401 | NCDOT | South Carolina state line to south of SR 1105 (Turnpike Road) in Laurinburg. | Widen to multi-lanes. | 3.44 | Highway | STI (Prioritization) | 8 | Lumber River RPO | U-5977 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22000000 |  |  | 29800000
Scotland | CSX | CSXT RR | Rail spur for industrial access near end of SR 1495 (Pell Drive) in Maxton. | Construct spine track and turnouts, and rehabilitate existing track sections. |  | Rail | Economic Development | 8 | Lumber River RPO | P-5724 | Division 8 | [10 empty] | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CSX; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM
Scotland | US 74 Business (Andrew Jackson Highway) | NCDOT | Carolina Coastal Railway Crossing 852590B. | Improve highway-rail grade crossing safety. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO | RX-2408C | Division 8 | RR |  |  |  |  | 2031 | 450000 | 2031 | 45000 | 495000
Scotland, Richmond | US 74 / Future I-74 | NCDOT | US 74 Business east of Hamlet to US 74 Business west of Laurinburg. | Upgrade corridor to interstate standards. | 9.84 | Highway | STI (Prioritization) | 8 | Lumber River RPO | I-6055 | Region E | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 224100000 |  |  | 275600000
Stanly | VUJ | STANLY COUNTY AIRPORT (VUJ) | Stanly County Airport | Acquire land for expansion and perform ESA to determine status of structures on property. Clear and grub land required for expansion and demolish houses on property acquired. |  | Aviation | STI (Prioritization) | 10 | Rocky River RPO | AV-5817 | Division 10 | T | 2025 | 3234000 |  |  | 2027 | 1500000 |  |  | 4734000
Stanly | NC 200 | NCDOT | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Bike & Ped | STI (Prioritization) | 10 | Rocky River RPO | EB-5857 | Division 10 | HF(M), L(M), TALT5 | 2024 | 196000 |  |  | 2025 | 1151000 | 2021 | 120000 | 1467000 | RIGHT-OF-WAY IN PROGRESS.
Stanly | North Second Avenue | ALBEMARLE | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Bike & Ped | STI (Prioritization) | 10 | Rocky River RPO | EB-5972 | Division 10 | L(M), TA5T50 | 2026 | 430000 | 2026 | 81000 | 2027 | 1200000 | 2024 | 300000 | 2011000
Stanly | SR 1434 (Rogers Road) | NCDOT | Bridge 830042 over Big Bear Creek. | Replace bridge. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-5811 | Division 10 | BGOFF | 2028 | 15000 |  |  | 2030 | 600000 |  |  | 615000
Stanly | SR 1917 (Bethlehem Church Road) | NCDOT | Bridge 830102 over Long Creek. | Replace bridge. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-6046 | Division 10 | BGOFF | 2022 | 145000 |  |  | 2024 | 2779000 |  |  | 2924000 | UNDER CONSTRUCTION.
Stanly | NC 205 | NCDOT | SR 1108 (Lighthouse Road) / SR 1109 (Buster Road) and SR 1110 (Swift Road) intersections at Charlotte Pipe facility. | Construct intersection improvements. | 0.5 | Highway | Economic Development | 10 | Rocky River RPO | R-5965A | Division 10 | T | 2021 | 120000 |  |  | 2021 | 2405000 |  |  | 2525000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION.
Stanly | SR 1107 (Silver Road) | NCDOT | SR 1108 (Lighthouse Road) and SR 1110 (Swift Road) intersections. | Construct intersection improvements. Improve roadway including full depth reclamation at various locations along SR 1107 (Silver Road), SR 1108 (Lighthouse Road), and SR 1110 (Swift Road). |  | Highway | Economic Development | 10 | Rocky River RPO | R-5965B | Division 10 | T | 2021 | 250000 |  |  | 2023 | 1586000 |  |  | 1836000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION.
Stanly | Various | NCDOT | Locations in the Town of Oakboro. | Improve transportation infrastructure. | 3.4 | Highway | Economic Development | 10 | Rocky River RPO | R-5965 | [11 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. TOTAL AWARD AMOUNT = $4,400,279
Stanly | NC 24 / NC 27 | NCDOT | Leonard Avenue intersection in Albemarle. | Install audible pedestrian signals. | 0.5 | Highway | Safety | 10 | Rocky River RPO | HS-2010K | Region E | HSIP |  |  |  |  | 2024 | 15000 |  |  | 15000
Stanly | NC 24 / NC 27 | NCDOT | SR 1963 (St. Martin Road) to Bird Road in Albemarle. | Widen to multi-lanes. |  | Highway | Safety | 10 | Rocky River RPO | R-2530A | [11 empty] | COMPLETE
Stanly | NC 73 | NCDOT | SR 1425 (Nelson Mountain Road) / SR 1243 (Cane Drive) intersection near Albemarle | Re-align intersection and construct turn lanes. |  | Highway | Safety | 10 | Rocky River RPO | HS-2410I | Region E | HSIP | 2026 | 125000 | 2026 | 65000 | 2028 | 912000 |  |  | 1102000
Stanly | US 52 | NCDOT | SR 1414 (Morton Street) to north of SR 1486 | Install rumble stripes with long life pavement markings. | 8.3 | Highway | Safety | 10 | Rocky River RPO | HS-2610A | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2027 | 353000 |  |  | 353000
Stanly | NC 24 / NC 27 | NCDOT | Bird Road in Albemarle to west of the Pee Dee River | Widen to multi-lanes. | 6.1 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-2530B | Region E | T | 2020 | 5700000 | 2020 | 3600000 | 2020 | 96961000 | 2020 | 8040000 | 114301000 | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Stanly | NC 24 / NC 27 | NCDOT | SR 1963 (St. Martin Road) in Albemarle to NC 73. | Widen to multi-lanes. | 8.9 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-2530
Stanly | NC 200 | NCDOT | Aberdeen Carolina and Western Railway crossing 728825W in Stanfield. Improve highway-rail grade crossing safety. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO | RX-2410E | Division 10 | RR |  |  |  |  | 2026 | 450000 |  |  | 450000
Stanly | Old Charlotte Highway | NCDOT | WSS Crossing 849910V in Albemarle. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO | RX-2410A | Division 10 | RR |  |  |  |  | 2026 | 450000 |  |  | 450000
Stanly, Anson | NC 740; US 52 | NCDOT | Mile marker 0 to mile marker 12.8 in Stanly County; Mile marker 4.9 to mile marker 10.5 in Anson County. | Install rumble stripes and long life pavement markings. |  | Highway | Safety | 10 | Rocky River RPO | HS-2010N | Region E | HSIP |  |  |  |  | 2024 | 636000 |  |  | 636000
Statewide | Various | NCDOT | Locations statewide. | Construct pedestrian safety improvements. | 0.1 | Bike & Ped | NCDOT Selected (Other Selection Process) | 99 | Statewide Project | BN-0031 | Division 99 | TAANY | 2026 | 1000000 | 2026 | 2000000 | 2026 | 21400000 | 2026 | 2600000 | 27000000
Statewide | Various |  | Systemwide | Funding for multi-modal planning. |  | Bike & Ped | Other | 99 | Statewide Project | M-0570
Statewide | Various |  | Locations statewide | Funding for national recreational trails. |  | Bike & Ped | Other | 99 | Statewide Project | M-0510 | Division 99 | T(M), TA |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide | Rails to trails program |  | Bike & Ped | Other | 99 | Statewide Project | EB-6037 | Division 99 | [10 empty] | LOCAL FUNDS REPRESENT LOCAL MATCH FOR RIGHT-OF-WAY AND CONSTRUCTION OF TRAILS BY LOCAL GOVERNMENTS.
Statewide | Various | NCDOT | Locations statewide | Safe routes to school education. |  | Bike & Ped | Other | 99 | Statewide Project | EB-6033 | Division 99 | [10 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Integrated Mobility Division bicycle and pedestrian coordination activities. |  | Bike & Ped | Other | 99 | Statewide Project | BO-2424 | Exempt | CMAQ | [6 empty] | 2025 | 1100000 | 1100000
Statewide | Various | NCDOT | Systemwide | Funding for safe routes to school program. Improve safety, reduce traffic, fuel consumption and air pollution in vicinity of schools. |  | Bike & Ped | Other | 99 | Statewide Project | SR-5001 | Division 99 | [10 empty] | IN PROGRESS - $200,800 IN STPDA FUNDS ALLOCATED TO SR-5001C
Statewide | Various | NCDOT | Locations statewide | Sidewalk program in all fourteen highway divisions. |  | Bike & Ped | Pre-STI (Historic) | 99 | Statewide Project | ER-2971 | Pre-STI (Transition) | [10 empty] | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E
Statewide | Various | NCDOT | Locations statewide | Statewide pedestrian facilities program. |  | Bike & Ped | Pre-STI (Historic) | 99 | Statewide Project | EB-3314 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Statewide | Various |  | Locations statewide | Municipal bridge inspection program. |  | Highway | Bridges | 99 | Statewide Project | HM-9999 | Division 99 | BGOFF | [6 empty] | 2025 | 13000000 | 13000000
Statewide | Various | NCDOT | Locations divisionwide | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | HB-8888DIV | Division 99 | BFP, T(M) |  |  |  |  | 2024 | 0
Statewide | Various | NCDOT | Locations regionwide | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | HB-8888REG | Region SW | BFP, T(M) |  |  |  |  | 2024 | 0
Statewide | Various | NCDOT | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Highway | Bridges | 99 | Statewide Project | HB-0088 | Division 99 | BGOFF |  |  |  |  | 2025 | 272854000 |  |  | 272854000
Statewide | Various | NCDOT | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Highway | Bridges | 99 | Statewide Project | HB-0088DIV | Division 99 | BFP |  |  |  |  | 2025 | 144938000 |  |  | 144938000
Statewide | Various | NCDOT | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Highway | Bridges | 99 | Statewide Project | HB-0088REG | Region SW | BFP |  |  |  |  | 2025 | 144938000 |  |  | 144938000
Statewide | Various | NCDOT | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Highway | Bridges | 99 | Statewide Project | HB-0088SW | Statewide Mobility | BFP |  |  |  |  | 2025 | 193250000 |  |  | 193250000
Statewide | Various | NCDOT | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Highway | Bridges | 99 | Statewide Project | HB-8888 | Division 99 | BGOFF |  |  |  |  | 2024 | 6844000 |  |  | 6844000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program analysis. |  | Highway | Bridges | 99 | Statewide Project | HB-0099C
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program analysis. |  | Highway | Bridges | 99 | Statewide Project | HB-0099CDIV | Division 99 | T | [6 empty] | 2025 | 8580000 | 8580000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program analysis. |  | Highway | Bridges | 99 | Statewide Project | HB-0099CREG | Region SW | T | [6 empty] | 2025 | 8580000 | 8580000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program analysis. |  | Highway | Bridges | 99 | Statewide Project | HB-0099CSW | Statewide Mobility | T | [6 empty] | 2025 | 11440000 | 11440000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program inspections. |  | Highway | Bridges | 99 | Statewide Project | HB-0099A
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program inspections. |  | Highway | Bridges | 99 | Statewide Project | HB-0099ADIV | Division 99 | T | [6 empty] | 2025 | 85800000 | 85800000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program inspections. |  | Highway | Bridges | 99 | Statewide Project | HB-0099AREG | Region SW | T | [6 empty] | 2025 | 85800000 | 85800000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program inspections. |  | Highway | Bridges | 99 | Statewide Project | HB-0099ASW | Statewide Mobility | T | [6 empty] | 2025 | 114400000 | 114400000
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program structure inventory and appraisal. |  | Highway | Bridges | 99 | Statewide Project | HB-0099B
Statewide | Various | NCDOT | Locations statewide | Funding for bridge inspection program structure inventory and appraisal. |  | Highway | Bridges | 99 | Statewide Project | HB-0099BDIV | Division 99 | T | [6 empty] | 2025 | 6600000 | 6600000
Statewide | Various | NCDOT | Locations statewide | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | HB-8888SW | Statewide Mobility | BFP, T(M) |  |  |  |  | 2024 | 0
Statewide | Various | NCDOT | Locations statewide. | Establish bridge management system. |  | Highway | Bridges | 99 | Statewide Project | BK-5100 | Division 99 | [10 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for scour evaluation program of existing bridges. |  | Highway | Bridges | 99 | Statewide Project | M-0379 | Division 99 | [10 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for storm water runoff. Research, design, construct, maintain and monitor storm water drainage from 50 bridges over waterways. |  | Highway | Bridges | 99 | Statewide Project | M-0418 | Division 99 | [10 empty] | UNDER CONSTRUCTION
Statewide | Various | NCDOT | Locations statewide. | Funding for the municipal bridge inspection program. |  | Highway | Bridges | 99 | Statewide Project | M-0414 | Division 99 | BGOFF, L | [6 empty] | 2020 | 5000000 | 5000000
Statewide | Various | NCDOT | Locations statewide. | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | B-8888 | Division 99 | BGOFF |  |  |  |  | 2022 | 0
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | B-8888DIV | Division 99 | BFP |  |  |  |  | 2022 | 0
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | B-8888REG | Region SW | BFP |  |  |  |  | 2022 | 0
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility finding. | Unprogrammed bridge replacement program balance. |  | Highway | Bridges | 99 | Statewide Project | B-8888SW | Statewide Mobility | BFP |  |  |  |  | 2022 | 0
Statewide | Various | NCDOT |  | Interstate maintenance program - unprogrammed balance. |  | Highway | Interstate Maintenance | 99 | Statewide Project | HI-9999 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2026 | 996742000 |  |  | 996742000
Statewide | Various | NCDOT | Locations statewide. | Construction of electric vehicle supply equipment along North Carolina's alternative corridors and NEVI planning. |  | Highway | National Electric Vehicle Infrastructure | 99 | Statewide Project | HV-0001 | Division 99 | NEVI, T(M) |  |  |  |  | 2024 | 91722000 | 2023 | 10910000 | 102632000
Statewide | Various | NCDOT | Locations statewide. | National Electric Vehicle Infrastructure Program (NEVI) - unprogrammed balance. |  | Highway | National Electric Vehicle Infrastructure | 99 | Statewide Project | HV-9999 | Division 99 | NEVI, T(M) |  |  |  |  | 2023 | 6925000 |  |  | 6925000
Statewide | North Carolina Clean Energy Technology Center | NCSU | Systemwide | Funding for Clean Fuels and Advanced Technologies (CFAT). |  | Highway | NCDOT Selected (Other Selection Process) | 99 | Statewide Project | HN-0039 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 5930000 | 5930000
Statewide | Statewide | NCDOT | Statewide | Develop Carbon Reduction Strategy and Emissions tool. |  | Highway | NCDOT Selected (Other Selection Process) | 99 | Statewide Project | HN-0037 | Exempt | CRPANY | [6 empty] | 2025 | 250000 | 250000
Statewide | Federal Lands Transportation Program (FLTP) and Emergency Relief For Federally Owned Roads (ERFO). | FHWA | Various federal lands | Improve roads and bridges on transportation facilities that are owned by the federal government that provide access to federal lands. |  | Highway | Other | 99 | Statewide Project | R-5753 | Exempt | ERFO, FLTP, O |  |  |  |  | 2020 | 400842000 |  |  | 400842000 | PROGRAM IN PROGRESS
Statewide | North Carolina Clean Energy Technology Center | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Highway | Other | 99 | Statewide Project | C-5702A | Exempt | [10 empty] | IN PROGRESS
Statewide | North Carolina Clean Energy Technology Center | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Highway | Other | 99 | Statewide Project | C-5702D | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 15023000 | 15023000
Statewide | North Carolina Clean Energy Technology Center | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program, including emissions-reducing sub-awards, in all CMAQ-eligible counties. |  | Highway | Other | 99 | Statewide Project | C-5702 | Exempt
Statewide | North Carolina Clean Energy Technology Center | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. |  | Highway | Other | 99 | Statewide Project | C-5702B | Exempt | [10 empty] | IN PROGRESS
Statewide | North Carolina Clean Energy Technology Center | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. |  | Highway | Other | 99 | Statewide Project | C-5702C | Exempt
Statewide | North Carolina Clean Energy Technology Center | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. Including education and outreach. |  | Highway | Other | 99 | Statewide Project | C-5702E | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 10084000 | 10084000
Statewide | North Carolina State University Solar Center Clean Transportation Program. | NORTH CAROLINA STATE UNIVERSITY | Systemwide | Develop and administer a seven year clean fuel-advanced technology rebate program in all CMAQ eligible counties to reduce emissions. |  | Highway | Other | 99 | Statewide Project | C-4902 | Exempt | [10 empty] | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY
Statewide | North Carolina State University Solar Center Clean Transportation Program. | NORTH CAROLINA STATE UNIVERSITY | Systemwide | Develop and administer a seven year clean fuel-advanced technology rebate program in all CMAQ eligible counties to reduce emissions. |  | Highway | Other | 99 | Statewide Project | C-4902A | Exempt
Statewide | Statewide | NCDOT | Statewide | Advanced Right-of-Way acquisition account. Revolving account to fund Advanced Right-of-Way acquisition. Funds to be repaid from the STIP project at the time the project is funded. |  | Highway | Other | 99 | Statewide Project | M-0556 | Statewide Mobility | T | 2023 | 6000000 | [6 empty] | 6000000
Statewide | Statewide | NCDOT | Statewide | Improve 1000 isolated closed-loop system signals. |  | Highway | Other | 99 | Statewide Project | HO-0024 | Exempt | DP, HF(M), O(M) | [6 empty] | 2025 | 15932000 | 15932000 | DP FUNDS REPRESENT FEDERAL ATTAIN GRANT FUNDING. HF(M) FUNDS REPRESENT NCDOT TRAFFIC SYSTEMS AND OPERATION FUNDING. O(M) FUNDS REPRESENT IN-KIND MATCH FROM VARIOUS PARTNERS AND MUNICIPALITIES.
Statewide | Statewide Traffic Operations | NCDOT | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management. |  | Highway | Other | 99 | Statewide Project | HO-0010
Statewide | Statewide Traffic Operations | NCDOT | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management. |  | Highway | Other | 99 | Statewide Project | HO-0010B | Exempt | CMAQ | [6 empty] | 2024 | 93220000 | 93220000
Statewide | Various |  | Locations statewide. | Funding for integrated project delivery. |  | Highway | Other | 99 | Statewide Project | M-0553A
Statewide | Various |  | Locations statewide. | Funding for training and special projects |  | Highway | Other | 99 | Statewide Project | M-0553B
Statewide | Various |  | Statewide | Funding for training, education, and workforce development. |  | Highway | Other | 99 | Statewide Project | M-0426 | [11 empty] | AUTHORIZED UNDER 23 U.S.C. 504e
Statewide | Various |  | Locations statewide. | Funding for protect formula planning for resilience program. |  | Highway | Other | 99 | Statewide Project | M-0563
Statewide | Various | NCDOT | Locations statewide | Manage vegetation and clear zones. |  | Highway | Other | 99 | Statewide Project | ER-5600 | Division 99 | STPE |  |  |  |  | 2022 | 9000000 | 2022 | 700000 | 9700000 | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide in the Division Needs category. | Funding for NPDES permit, retrofit 14 sites per year to protect water quality - Division Category. |  | Highway | Other | 99 | Statewide Project | R-5968DIV | Division 99 | BGANY, T(M) |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide in the Regional Impact category. | Funding for NPDES permit, retrofit 14 sites per year to protect water quality - Regional Category. |  | Highway | Other | 99 | Statewide Project | R-5968REG | Region SW | BGANY, T(M) |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide in the Statewide Mobility category. | Funding for NPDES permit, retrofit 14 sites per year to protect water quality - Statewide Category. |  | Highway | Other | 99 | Statewide Project | R-5968SW | Statewide Mobility | BGANY, T(M) |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Highway | Other | 99 | Statewide Project | M-0534 | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | M-0539
Statewide | Various | NCDOT | Locations statewide. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | R-9999WM | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | R-9999WMDIV | Division 99 | NHP, T | [6 empty] | 2020 | 300000 | 300000
Statewide | Various | NCDOT | Locations statewide. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | R-9999WMREG | Region SW | NHP, T | [6 empty] | 2020 | 300000 | 300000
Statewide | Various | NCDOT | Locations statewide. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | R-9999WMSW | Statewide Mobility | NHP, T | [6 empty] | 2020 | 400000 | 400000
Statewide | Various | NCDOT | Locations statewide. | Funding for federal state transportation innovation council (STIC) incentive funded projects |  | Highway | Other | 99 | Statewide Project | M-0482 | Exempt | DP, HF(M) | [6 empty] | 2023 | 500000 | 500000 | DP FUNDS REPRESENT FEDERAL STIC FUNDS.
Statewide | Various | NCDOT | Locations statewide. | Funding for Geotechnical Asset Management (GAM) database and landslide mitigation planning. |  | Highway | Other | 99 | Statewide Project | M-0563C | Statewide Mobility | PROTCT, T(M) | [6 empty] | 2023 | 2240000 | 2240000
Statewide | Various | NCDOT | Locations statewide. | Funding for hazard characterization and warning tools. |  | Highway | Other | 99 | Statewide Project | M-0563A | Statewide Mobility | PROTCT, T(M) | [6 empty] | 2023 | 3360000 | 3360000
Statewide | Various | NCDOT | Locations statewide. | Funding for hazard corridor vulnerability assessments. |  | Highway | Other | 99 | Statewide Project | M-0563B | Statewide Mobility | PROTCT, T(M) | [6 empty] | 2023 | 1400000 | 1400000
Statewide | Various | NCDOT | Locations statewide. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0392 | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Highway | Other | 99 | Statewide Project | M-0554
Statewide | Various | NCDOT | Locations statewide. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Highway | Other | 99 | Statewide Project | M-0219
Statewide | Various | NCDOT | Locations statewide. | Funding for resilience program reporting, management, and support. |  | Highway | Other | 99 | Statewide Project | M-0563E | Statewide Mobility | PROTCT, T(M) | [6 empty] | 2024 | 2550000 | 2550000
Statewide | Various | NCDOT | Locations statewide. | Funding for roadway design for open roads designer (ORD) training and development. |  | Highway | Other | 99 | Statewide Project | M-0552A
Statewide | Various | NCDOT | Locations statewide. | Funding for roadway design for training and development for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0552B
Statewide | Various | NCDOT | Locations statewide. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Highway | Other | 99 | Statewide Project | M-0376 | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for statewide landscape plans for STIP construction projects. |  | Highway | Other | 99 | Statewide Project | M-0451
Statewide | Various | NCDOT | Locations statewide. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Highway | Other | 99 | Statewide Project | M-0479A
Statewide | Various | NCDOT | Locations statewide. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0479B
Statewide | Various | NCDOT | Locations statewide. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Highway | Other | 99 | Statewide Project | M-0479
Statewide | Various | NCDOT | Locations statewide. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0391 | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for tolling/financial feasibility studies. |  | Highway | Other | 99 | Statewide Project | M-0452 | Statewide Mobility | T | [6 empty] | 2020 | 3200000 | 3200000
Statewide | Various | NCDOT | Locations statewide. | Funding for Transportation Program Management Unit (TPMU) oversight for locally-administered projects including preparation of agreements and funding authorization requests. |  | Highway | Other | 99 | Statewide Project | M-0505 | Division 99 | T | [6 empty] | 2020 | 5000000 | 5000000
Statewide | Various | NCDOT | Locations statewide. | Funding for utility encroachment and administrative activities. |  | Highway | Other | 99 | Statewide Project | M-0555
Statewide | Various | NCDOT | Locations statewide. | Retrofit 14 sites per year to protect water quality. |  | Highway | Other | 99 | Statewide Project | R-5968
Statewide | Various | NCDOT | Locations statewide. | Right-of-way branch, review of local public agency (LPA) projects by the appraisal section. |  | Highway | Other | 99 | Statewide Project | M-0515 | Division 99 | T | 2020 | 4000000 | [6 empty] | 4000000
Statewide | Various | NCDOT | Locations statewide. | Statewide CMAQ projects to improve air quality within nonattainment and maintenance areas. |  | Highway | Other | 99 | Statewide Project | C-5600 | Exempt
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Highway | Other | 99 | Statewide Project | M-0534DIV | Division 99 | T | [6 empty] | 2020 | 9600000 | 9600000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | M-0539DIV | Division 99 | T | [6 empty] | 2020 | 43200000 | 43200000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0392DIV | Division 99 | T | [6 empty] | 2020 | 1788000 | 1788000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Highway | Other | 99 | Statewide Project | M-0554DIV | Division 99 | T | [6 empty] | 2022 | 105000000 | 105000000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Highway | Other | 99 | Statewide Project | M-0219DIV | Division 99 | T | [6 empty] | 2020 | 1200000 | 1200000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for roadway design for open roads designer (ORD) training and development. |  | Highway | Other | 99 | Statewide Project | M-0552ADIV | Division 99 | T | [6 empty] | 2022 | 1650000 | 1650000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for roadway design for training and development for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0552BDIV | Division 99 | T | [6 empty] | 2022 | 1180000 | 1180000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Highway | Other | 99 | Statewide Project | M-0376DIV | Division 99 | T | [6 empty] | 2020 | 10620000 | 10620000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for statewide landscape plans for STIP construction projects. |  | Highway | Other | 99 | Statewide Project | M-0451DIV | Division 99 | T | [6 empty] | 2020 | 1203000 | 1203000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Highway | Other | 99 | Statewide Project | M-0479ADIV | Division 99 | T | [6 empty] | 2020 | 7200000 | 7200000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0479BDIV | Division 99 | T | [6 empty] | 2020 | 2400000 | 2400000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Highway | Other | 99 | Statewide Project | M-0479DIV | Division 99 | T | [6 empty] | 2020 | 24000000 | 24000000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0391DIV | Division 99 | T | [6 empty] | 2020 | 1920000 | 1920000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for utility encroachment and administrative activities. |  | Highway | Other | 99 | Statewide Project | M-0555DIV | Division 99 | T |  |  | 2023 | 2160000 |  |  |  |  | 2160000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Highway | Other | 99 | Statewide Project | M-0534REG | Region SW | T | [6 empty] | 2020 | 9600000 | 9600000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | M-0539REG | Region SW | T | [6 empty] | 2020 | 43200000 | 43200000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0392REG | Region SW | T | [6 empty] | 2020 | 1788000 | 1788000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Highway | Other | 99 | Statewide Project | M-0554REG | Region SW | T | [6 empty] | 2022 | 105000000 | 105000000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Highway | Other | 99 | Statewide Project | M-0219REG | Region SW | T | [6 empty] | 2020 | 1200000 | 1200000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for roadway design for open roads designer (ORD) training and development. |  | Highway | Other | 99 | Statewide Project | M-0552AREG | Region SW | T | [6 empty] | 2022 | 1650000 | 1650000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for roadway design for training and development for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0552BREG | Region SW | T | [6 empty] | 2022 | 1180000 | 1180000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Highway | Other | 99 | Statewide Project | M-0376REG | Region SW | T | [6 empty] | 2020 | 13500000 | 13500000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for statewide landscape plans for STIP construction projects. |  | Highway | Other | 99 | Statewide Project | M-0451REG | Region SW | T | [6 empty] | 2020 | 1203000 | 1203000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Highway | Other | 99 | Statewide Project | M-0479AREG | Region SW | T | [6 empty] | 2020 | 7200000 | 7200000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0479BREG | Region SW | T | [6 empty] | 2020 | 2400000 | 2400000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Highway | Other | 99 | Statewide Project | M-0479REG | Region SW | T | [6 empty] | 2020 | 24000000 | 24000000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0391REG | Region SW | T | [6 empty] | 2020 | 1920000 | 1920000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for utility encroachment and administrative activities. |  | Highway | Other | 99 | Statewide Project | M-0555REG | Region SW | T |  |  | 2023 | 2160000 |  |  |  |  | 2160000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Highway | Other | 99 | Statewide Project | M-0534SW | Statewide Mobility | T | [6 empty] | 2020 | 12800000 | 12800000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for environmental mitigation and minimization. |  | Highway | Other | 99 | Statewide Project | M-0539SW | Statewide Mobility | T | [6 empty] | 2020 | 57600000 | 57600000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0392SW | Statewide Mobility | T | [6 empty] | 2020 | 2384000 | 2384000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Highway | Other | 99 | Statewide Project | M-0554SW | Statewide Mobility | T | [6 empty] | 2022 | 140000000 | 140000000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Highway | Other | 99 | Statewide Project | M-0219SW | Statewide Mobility | T | [6 empty] | 2020 | 1600000 | 1600000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for roadway design for open roads designer (ORD) training and development. |  | Highway | Other | 99 | Statewide Project | M-0552ASW | Statewide Mobility | T | [6 empty] | 2022 | 2200000 | 2200000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for roadway design for training and development for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0552BSW | Statewide Mobility | T | [6 empty] | 2022 | 1572000 | 1572000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Highway | Other | 99 | Statewide Project | M-0376SW | Statewide Mobility | T | [6 empty] | 2020 | 14160000 | 14160000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for statewide landscape plans for STIP construction projects. |  | Highway | Other | 99 | Statewide Project | M-0451SW | Statewide Mobility | T | [6 empty] | 2020 | 1606000 | 1606000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Highway | Other | 99 | Statewide Project | M-0479ASW | Statewide Mobility | T | [6 empty] | 2020 | 9600000 | 9600000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0479BSW | Statewide Mobility | T | [6 empty] | 2020 | 3200000 | 3200000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Highway | Other | 99 | Statewide Project | M-0479SW | Statewide Mobility | T | [6 empty] | 2020 | 32000000 | 32000000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Highway | Other | 99 | Statewide Project | M-0391SW | Statewide Mobility | T | [6 empty] | 2020 | 2560000 | 2560000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for utility encroachment and administrative activities. |  | Highway | Other | 99 | Statewide Project | M-0555SW | Statewide Mobility | T |  |  | 2023 | 2880000 |  |  |  |  | 2880000
Statewide | Various | NCDOT | Statewide | Funding for Disadvantaged Business Enterprise (DBE) training and supportive services. |  | Highway | Other | 99 | Statewide Project | M-0480 | Exempt | FO | [6 empty] | 2024 | 3600000 | 3600000
Statewide | Various | NCDOT | Statewide | Funding for integrated project delivery. |  | Highway | Other | 99 | Statewide Project | M-0553ADIV | Exempt | T | [6 empty] | 2022 | 5250000 | 5250000
Statewide | Various | NCDOT | Statewide | Funding for integrated project delivery. |  | Highway | Other | 99 | Statewide Project | M-0553AREG | Exempt | T | [6 empty] | 2022 | 5250000 | 5250000
Statewide | Various | NCDOT | Statewide | Funding for integrated project delivery. |  | Highway | Other | 99 | Statewide Project | M-0553ASW | Exempt | T | [6 empty] | 2022 | 7000000 | 7000000
Statewide | Various | NCDOT | Statewide | Funding for National Summer Transportation Institute (NSTI). |  | Highway | Other | 99 | Statewide Project | M-0460 | Exempt | FO | [6 empty] | 2024 | 2400000 | 2400000
Statewide | Various | NCDOT | Statewide | Funding for on-the-job training program. |  | Highway | Other | 99 | Statewide Project | M-0478 | Exempt | FO | [6 empty] | 2024 | 6000000 | 6000000
Statewide | Various | NCDOT | Statewide | Funding for traIning and special projects. |  | Highway | Other | 99 | Statewide Project | M-0553BDIV | Exempt | T | [6 empty] | 2022 | 3180000 | 3180000
Statewide | Various | NCDOT | Statewide | Funding for training and special projects. |  | Highway | Other | 99 | Statewide Project | M-0553BREG | Exempt | T | [6 empty] | 2022 | 3180000 | 3180000
Statewide | Various | NCDOT | Statewide | Funding for training and special projects. |  | Highway | Other | 99 | Statewide Project | M-0553BSW | Exempt | T | [6 empty] | 2022 | 4240000 | 4240000
Statewide | Various | NCDOT | Statewide | Funding for training, education, and workforce development. |  | Highway | Other | 99 | Statewide Project | M-0426DIV | Division 99 | NHP | [6 empty] | 2024 | 1140000 | 1140000
Statewide | Various | NCDOT | Statewide | Funding for training, education, and workforce development. |  | Highway | Other | 99 | Statewide Project | M-0426REG | Region SW | NHP | [6 empty] | 2024 | 1140000 | 1140000
Statewide | Various | NCDOT | Statewide | Funding for training, education, and workforce development. |  | Highway | Other | 99 | Statewide Project | M-0426SW | Statewide Mobility | NHP | [6 empty] | 2024 | 1520000 | 1520000
Statewide | Various | NCDOT | Various | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Highway | Other | 99 | Statewide Project | M-0531 | Division 99
Statewide | Various | NCDOT | Various | Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Highway | Other | 99 | Southwestern RPO | M-0575 | Division 99 | BGANY | [6 empty] | 2025 | 103000 | 103000
Statewide | Various | NCDOT | Various Locations. | Funding for Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Highway | Other | 99 | Statewide Project | M-0575DIV | Division 99
Statewide | Various | NCDOT | Various Locations. | Funding for Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Highway | Other | 99 | Statewide Project | M-0575REG | Region SW
Statewide | Various | NCDOT | Various Locations. | Funding for Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Highway | Other | 99 | Statewide Project | M-0575SW | Statewide Mobility
Statewide | Various | NCDOT | Various Locations. | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Highway | Other | 99 | Statewide Project | M-0531DIV | Division 99 | BGANY | [6 empty] | 2025 | 4620000 | 4620000
Statewide | Various | NCDOT | Various Locations. | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Highway | Other | 99 | Statewide Project | M-0531REG | Region SW | BGANY | [6 empty] | 2025 | 4620000 | 4620000
Statewide | Various | NCDOT | Various Locations. | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Highway | Other | 99 | Statewide Project | M-0531SW | Statewide Mobility | BGANY | [6 empty] | 2025 | 6160000 | 6160000
Statewide | Various | NORTH CAROLINA CLEAN ENERGY | North Carolina Clean Energy Technology Center. | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Highway | Other | 99 | Statewide Project | HO-0025 | Exempt | [10 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
Statewide | Various |  | Locations statewide. | Funding for school traffic analysis for new, relocated and expanding schools. |  | Highway | Safety | 99 | Statewide Project | SM-6215
Statewide | Various | NCDOT | Locations statewide | Funding for highway safety improvement program balance. |  | Highway | Safety | 99 | Statewide Project | W-9999
Statewide | Various | NCDOT | Locations statewide | Funding for highway safety improvement program balance. |  | Highway | Safety | 99 | Statewide Project | W-9999DIV | Division 99 | HSIP, T(M) |  |  |  |  | 2020 | 45163000 |  |  | 45163000
Statewide | Various | NCDOT | Locations statewide | Funding for highway safety improvement program balance. |  | Highway | Safety | 99 | Statewide Project | W-9999REG | Region SW | HSIP, T(M) |  |  |  |  | 2020 | 55936000 |  |  | 55936000
Statewide | Various | NCDOT | Locations statewide | Funding for highway safety improvement program balance. |  | Highway | Safety | 99 | Statewide Project | W-9999SW | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2020 | 74580000 |  |  | 74580000
Statewide | Various | NCDOT | Locations statewide | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | W-5717
Statewide | Various | NCDOT | Locations statewide | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | W-5717DIV | Division 99 | HSIP, T(M) | [6 empty] | 2020 | 1350000 | 1350000
Statewide | Various | NCDOT | Locations statewide | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | W-5717REG | Region SW | HSIP, T(M) | [6 empty] | 2020 | 1350000 | 1350000
Statewide | Various | NCDOT | Locations statewide | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | W-5717SW | Statewide Mobility | HSIP, T(M) | [6 empty] | 2020 | 1800000 | 1800000
Statewide | Various | NCDOT | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | W-5715
Statewide | Various | NCDOT | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | W-5715DIV | Division 99 | HSIP, T(M) | [6 empty] | 2020 | 4230000 | 4230000
Statewide | Various | NCDOT | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | W-5715REG | Region SW | HSIP, T(M) | [6 empty] | 2020 | 4230000 | 4230000
Statewide | Various | NCDOT | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | W-5715SW | Statewide Mobility | HSIP, T(M) | [6 empty] | 2020 | 5640000 | 5640000
Statewide | Various | NCDOT | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on division category. |  | Highway | Safety | 99 | Statewide Project | W-5601DIV | Division 99 | HSIP, T(M) | 2021 | 68000 |  |  | 2020 | 3670000 |  |  | 3738000
Statewide | Various | NCDOT | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on regional category. |  | Highway | Safety | 99 | Statewide Project | W-5601REG | Region SW | HSIP, T(M) | 2021 | 68000 |  |  | 2021 | 6170000 |  |  | 6238000
Statewide | Various | NCDOT | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on statewide category. |  | Highway | Safety | 99 | Statewide Project | W-5601SW | Statewide Mobility | HSIP, T(M) | 2021 | 90000 |  |  | 2021 | 3360000 |  |  | 3450000
Statewide | Various | NCDOT | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations. |  | Highway | Safety | 99 | Statewide Project | W-5601 | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | HS-2422
Statewide | Various | NCDOT | Locations statewide. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Highway | Safety | 99 | Statewide Project | HS-2421
Statewide | Various | NCDOT | Locations statewide. | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | HS-2420
Statewide | Various | NCDOT | Locations statewide. | Highway safety improvement program - unprogrammed balance |  | Highway | Safety | 99 | Statewide Project | HS-9999
Statewide | Various | NCDOT | Locations statewide. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Highway | Safety | 99 | Statewide Project | HS-2015
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | HS-2422DIV | Division 99 | T | [6 empty] | 2024 | 18000000 | 18000000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Highway | Safety | 99 | Statewide Project | HS-2421DIV | Division 99 | T | [6 empty] | 2024 | 51000000 | 51000000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for school traffic analysis for new, relocated and expanding schools. |  | Highway | Safety | 99 | Statewide Project | SM-6215DIV | Division 99 | T | [6 empty] | 2024 | 3600000 | 3600000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | HS-2420DIV | Division 99 | T | [6 empty] | 2024 | 30600000 | 30600000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Highway safety improvement program - unprogrammed balance |  | Highway | Safety | 99 | Statewide Project | HS-9999DIV | Division 99 | HSIP, T(M) |  |  |  |  | 2024 | 287286000 |  |  | 287286000
Statewide | Various | NCDOT | Locations statewide. Division Needs funding. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Highway | Safety | 99 | Statewide Project | HS-2015DIV | Division 99 | VRU | [6 empty] | 2023 | 26805000 | 26805000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | HS-2422REG | Region SW | T | [6 empty] | 2024 | 21500000 | 21500000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Highway | Safety | 99 | Statewide Project | HS-2421REG | Region SW | T | [6 empty] | 2024 | 51000000 | 51000000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for school traffic analysis for new, relocated and expanding schools. |  | Highway | Safety | 99 | Statewide Project | SM-6215REG | Region SW | T | [6 empty] | 2024 | 3600000 | 3600000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | HS-2420REG | Region SW | T | [6 empty] | 2024 | 30600000 | 30600000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Highway safety improvement program - unprogrammed balance |  | Highway | Safety | 99 | Statewide Project | HS-9999REG | Region SW | HSIP, T(M) |  |  |  |  | 2024 | 287336000 |  |  | 287336000
Statewide | Various | NCDOT | Locations statewide. Regional Impact funding. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Highway | Safety | 99 | Statewide Project | HS-2015REG | Region SW | VRU | [6 empty] | 2023 | 26805000 | 26805000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility finding. | Funding for school traffic analysis for new, relocated and expanding schools. |  | Highway | Safety | 99 | Statewide Project | SM-6215SW | Statewide Mobility | T | [6 empty] | 2024 | 4800000 | 4800000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for highway system data collection. |  | Highway | Safety | 99 | Statewide Project | HS-2422SW | Statewide Mobility | T | [6 empty] | 2024 | 24000000 | 24000000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Highway | Safety | 99 | Statewide Project | HS-2421SW | Statewide Mobility | T | [6 empty] | 2024 | 68000000 | 68000000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Funding for signal retiming and signal operations software to improve safety. |  | Highway | Safety | 99 | Statewide Project | HS-2420SW | Statewide Mobility | T | [6 empty] | 2024 | 40800000 | 40800000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Highway safety improvement program - unprogrammed balance |  | Highway | Safety | 99 | Statewide Project | HS-9999SW | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2024 | 383102000 |  |  | 383102000
Statewide | Various | NCDOT | Locations statewide. Statewide Mobility funding. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Highway | Safety | 99 | Statewide Project | HS-2015SW | Statewide Mobility | VRU | [6 empty] | 2023 | 35740000 | 35740000
Statewide | NCDOT | NCDOT | Systemwide | Funding for 5310 capital projects for rural and urban areas. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0018 | Public Transit | 5310, L, L(M), S, S(M) | [6 empty] | 2022 | 39955000 | 39955000
Statewide | NCDOT | NCDOT | Systemwide | Funding for 5311 ADTAP capital funds for FTA grants. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0022 | Public Transit | ADTAP, L, S | [6 empty] | 2022 | 1880000 | 1880000
Statewide | NCDOT | NCDOT | Systemwide | Funding for 5311 capital funds For FTA grants. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0019 | Public Transit | 5311, L, S | [6 empty] | 2022 | 17147000 | 17147000
Statewide | NCDOT | NCDOT | Systemwide | Funding for 5339 statewide rural. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0021 | Public Transit | 5339, L, S | [6 empty] | 2023 | 90025000 | 90025000
Statewide | NCDOT | NCDOT | Various locations | Funding for 5311(b) capital funding for rural projects. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0003 | Public Transit | 5311, L, S | [6 empty] | 2023 | 1371000 | 1371000
Statewide | NCDOT | NCDOT | Various locations | Funding for 5339(b) discretionary grant for facility construction. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0011 | Public Transit | 5339, L |  |  |  |  | 2023 | 719000 | 2021 | 8689000 | 9408000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Systemwide | Funding for 5310 capital projects for rural areas and small urban areas. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TQ-9038 | Public Transit | 5310 | [6 empty] | 2021 | 2850000 | 2850000 | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | Statewide | FTA | Systemwide | Funding for 5311 capital projects for rural areas. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TA-6665 | Public Transit | 5311, L, L(M), S, S(M) | [6 empty] | 2023 | 194050000 | 194050000
Statewide | Statewide | FTA | Systemwide | Funding for 5339 bus and bus facilities. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TA-6666 | Public Transit | 5339 | [6 empty] | 2021 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
Statewide | Statewide | FTA | Various locations | Funding for 5310 discretionary grant awarded by FTA. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0013 | Public Transit | 5310, S | [6 empty] | 2021 | 350000 | 350000
Statewide | Statewide | FTA | Various locations | Funding for 5339(b) discretionary grant for facility construction. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0005 | Public Transit | 5339, L |  |  |  |  | 2022 | 3750000 |  |  | 3750000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Various locations | Funding for 5339(b) discretionary grant for facility construction. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0006 | Public Transit | 5339, L |  |  |  |  | 2021 | 1819000 |  |  | 1819000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Various locations | Funding for 5339(b) discretionary grant for facility construction. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0007 | Public Transit | 5339, L | [6 empty] | 2021 | 3976000 | 3976000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Various locations | Funding for 5339(b) discretionary grant for facility construction. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0008 | Public Transit | 5339, L |  |  |  |  | 2025 | 500000 | 2023 | 8325000 | 8825000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Various locations | Funding for 5339(b) discretionary grant for facility construction. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0010 | Public Transit | 5339, L |  |  |  |  | 2023 | 15100000 |  |  | 15100000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Various locations | Funding for 5339(b) discretionary grant to purchase electric buses and charging stations. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | Statewide Project | TC-0012 | Public Transit | 5339, L | [6 empty] | 2024 | 3125000 | 3125000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
Statewide | Statewide | FTA | Statewide | 5311 Operating funds for FTA grants. |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | Statewide Project | TO-6135 | Public Transit | 5311 | [6 empty] | 2021 | 947000 | 947000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | Statewide | FTA | Statewide | Funding for Urbanized formula program. |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO | TO-6142 | Public Transit | 5307, L | [6 empty] | 2020 | 11230000 | 11230000
Statewide | Statewide | FTA | Systemwide | System safety oversight grant for Rail division NCDOT. |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | Statewide Project | TO-0004 | Public Transit | S, SSO | [6 empty] | 2021 | 7680000 | 7680000 | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD.
Statewide | NCDOT | NCDOT |  | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-6112 | Public Transit | 5311, L, S | [6 empty] | 2026 | 33000000 | 33000000
Statewide | NCDOT | NCDOT |  | RTAP STATEWIDE FUNDS FOR FTA GRANTS. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-6113 | Public Transit | RTAP, S | [6 empty] | 2026 | 1200000 | 1200000
Statewide | NCDOT | NCDOT | Statewide | NCDOT-IMD STATE ADMINISTRATION - FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORIING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR ELDERLY AND DISABLED. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-6111 | Public Transit | 5310 | [6 empty] | 2026 | 900000 | 900000
Statewide | NCDOT | NCDOT | Systemwide | NCDOT-IMD Section 5304 program funds to support the IMD urban transit technical assistance activities |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TU-0011 | Public Transit | 5303, L, S | [6 empty] | 2023 | 22070000 | 22070000
Statewide | NCDOT | NCDOT | Various locations | 5311 ADTAP state administrative funds. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0030 | Public Transit | ADTAP | [6 empty] | 2022 | 177000 | 177000
Statewide | NCDOT | NCDOT | Various locations | 5311 State administrative funds for FTA grants. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0029 | Public Transit | 5311 | [6 empty] | 2022 | 16361000 | 16361000
Statewide | NCDOT | NCDOT | Various locations | 5311(F) Intercity bus - state admin. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0033 | Public Transit | 5311 | [6 empty] | 2022 | 494000 | 494000
Statewide | NCDOT | NCDOT | Various locations | 5311(F) Intercity bus funds for FTA grants. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0032 | Public Transit | 5311, L, L(M), S, S(M) | [6 empty] | 2022 | 119441000 | 119441000
Statewide | NCDOT | NCDOT | Various locations | Funding for operating assistance for FTA grants. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0028 | Public Transit | 5311, L, L(M), S(M) | [6 empty] | 2023 | 64494000 | 64494000
Statewide | NCDOT | NCDOT | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0025 | Public Transit | 5310, L | [6 empty] | 2022 | 4212000 | 4212000
Statewide | Statewide | FTA | Statewide | 5311(F) Intercity bus funds for FTA grants. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TI-6109 | Public Transit | 5311 | [6 empty] | 2021 | 2698000 | 2698000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | Statewide | FTA | Statewide | Funding for 5311 State administration. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TK-4900Z | Public Transit | 5311 | [6 empty] | 2021 | 3080000 | 3080000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | Statewide | FTA | Statewide | Funding for state administration of Appalachian Development Transportation Assistance Program. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TK-4902 | Public Transit | ADTAP | [6 empty] | 2021 | 235000 | 235000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | Statewide | FTA | Systemwide | Funding 5329 State safety and oversight. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TS-7001 | Public Transit | FED, L, S | [6 empty] | 2020 | 4676000 | 4676000
Statewide | Statewide | FTA | Systemwide | Funding for 5310 state administrative funds. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TM-0036 | Public Transit | 5310 | [6 empty] | 2022 | 567000 | 567000
Statewide | Statewide | FTA | Systemwide | Funding for section 5310 for Rural project. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TQ-6954 | Public Transit | 5310, L | [6 empty] | 2021 | 31935000 | 31935000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | Statewide | FTA | Systemwide | Statewide RTAP. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | Statewide Project | TS-4900Z | Public Transit | RTAP | [6 empty] | 2021 | 480000 | 480000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
Statewide | NCDOT | NCDOT | Systemwide | 5303 Metropolitan Transportation Planning Funds For FTA Grants. |  | Public Transportation (Transit) | Planning | 99 | Statewide Project | TU-0005 | Public Transit | 5303, L, S | [6 empty] | 2022 | 10809000 | 10809000
Statewide | NCDOT | NCDOT | Various locations | H.O.P.E Grant opportunity from the FTA. Discretionary Grant awarded by FTA. Planning and design in preparation for electric vehicle deployment. |  | Public Transportation (Transit) | Planning | 99 | Statewide Project | TU-0003 | Public Transit | 5303, 5312, S | [6 empty] | 2021 | 222000 | 222000 | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD.
Statewide | Statewide | FTA | Systemwide | 5304 Planning. |  | Public Transportation (Transit) | Planning | 99 | Statewide Project | TP-5154 | Public Transit | 5303, L | [6 empty] | 2020 | 5136000 | 5136000
Statewide | Queen City Express | NCDOT | Wilmington to Charlotte | Subsidy for intermodal rail service between Port of Wilmington and Charlotte. |  | Rail | Other | 99 | Statewide Project | C-5600VA | Exempt | CMAQ | [6 empty] | 2025 | 250000 | 250000
Statewide | Various | NCDOT | Routes statewide in the Division Needs category. | Funding for statewide rail preliminary engineering. |  | Rail | Other | 99 | Statewide Project | P-5602DIV | Division 99 | T | [6 empty] | 2020 | 4800000 | 4800000
Statewide | Various | NCDOT | Routes statewide in the Regional Impact category | Funding for statewide rail preliminary engineering. |  | Rail | Other | 99 | Statewide Project | P-5602REG | Region SW | T | [6 empty] | 2020 | 4800000 | 4800000
Statewide | Various | NCDOT | Routes statewide in the Statewide Mobility category. | Funding for statewide rail preliminary engineering. |  | Rail | Other | 99 | Statewide Project | P-5602SW | Statewide Mobility | T | [6 empty] | 2020 | 6400000 | 6400000
Statewide | Various | NCDOT | Routes statewide. | Funding for statewide rail preliminary engineering. |  | Rail | Other | 99 | Statewide Project | P-5602 | [11 empty] | IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for traffic separation study implementation and closures program administration. |  | Rail | Rail-Highway Grade Crossing Closure | 99 | Statewide Project | RC-2000 | Statewide Mobility | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
Statewide | Various | NCDOT | Various locations | Funding for traffic separation study implementation and closures - unprogrammed balance. |  | Rail | Rail-Highway Grade Crossing Closure | 99 | Statewide Project | Y-5500 | Division 99 | RR | 2021 | 1500000 |  |  | 2020 | 7560000 |  |  | 9060000 | RIGHT-OF-WAY IN PROGRESS
Statewide | Various | NCDOT | Locations statewide. | Funding for highway-rail grade crossing safety improvements program administration. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | RX-2000 | Division 99 | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
Statewide | Various | NCDOT | Locations statewide. | Funding for passenger rail crossing safety improvement inventory program. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | RX-2100 | Division 99 | RR | [6 empty] | 2021 | 3000000 | 3000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY
Statewide | Various | NCDOT | Locations statewide. | Funding for railway-highway crossings program - unprogrammed balance. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | RX-9999 | Division 99 | RR |  |  |  |  | 2024 | 106260000 |  |  | 106260000
Statewide | Various | NCDOT | Various | Improve passenger rail crossing safety inventory program. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | RX-2600 | Division 99 | RR | [6 empty] | 2027 | 2000000 | 2000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY
Statewide | Various | NCDOT | Various locations | Construct highway-rail grade crossing safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | Z-5400 | Division 99 | [10 empty] | IN PROGRESS
Statewide | Various | NCDOT | Various locations | Construct highway-rail grade crossing safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | Z-5700 | Division 99 | [10 empty] | IN PROGRESS
Statewide | Various | NCDOT | Various locations | Construct highway-rail grade crossing safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | Statewide Project | Z-5800 | Division 99 | RR | 2021 | 500000 |  |  | 2020 | 3280000 |  |  | 3780000
Stokes | Ingram Drive | KING | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0148 | Exempt | BGDA, L(M) |  |  | 2027 | 13000 | 2027 | 200000 | 2025 | 38000 | 251000
Stokes | SR 1112 (Main Street) | KING | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0147 | Exempt | BGDA, L(M) | 2026 | 98000 | 2026 | 13000 | 2027 | 310000 | 2025 | 10000 | 431000
Stokes | Walnut Cove Greenway | PIEDMONT TRIAD REGIONAL COUNCIL | Walnut Cove | Construct greenway |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO | BO-2425 | Exempt | DP | [6 empty] | 2025 | 250000 | 250000 | DP FUNDS REPRESENT FEDERAL NEIGHBORHOOD ACCESS AND EQUITY (NAE) GRANT.
Stokes | SR 1112 (South Main Street) | NCDOT | West Dalton Road/East Dalton Road intersection | Install pedestrian signals. | 0.5 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2409K | Division 9 | HSIP |  |  |  |  | 2026 | 18000 |  |  | 18000
Stokes | US 311 | NCDOT | NC 65 in Walnut Cove. | Construct intersection improvements and improve railroad crossing. | 0.5 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5768 | Division 9 | BGLT5, T |  |  |  |  | 2023 | 6963000 |  |  | 6963000 | UNDER CONSTRUCTION
Stokes | US 311 (North Main Street) | NCDOT | SR 1918 (First Street) in Walnut Cove. | Construct roundabout. |  | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5828 | Division 9 | T |  |  |  |  | 2022 | 3050000 |  |  | 3050000 | UNDER CONSTRUCTION
Surry | MWK | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | Mount Airy-Surry County Airport | Construct general aviation apron and aircraft storage hangars. |  | Aviation | STI (Prioritization) | 11 | Northwest Piedmont RPO | AV-5859 | Division 11 | T |  |  |  |  | 2020 | 4000000 |  |  | 4000000 | COMPLETE.
Surry | Dobson School Greenway |  | Central Middle School to the Elementary School in Dobson. | Construct greenway. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 11 | Northwest Piedmont RPO | BN-0004 | Exempt | CRPLT5, L(M) | 2025 | 50000 |  |  | 2026 | 1485000 |  |  | 1535000
Surry | US 21 Business (North Bridge Street) | ELKIN | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Bike & Ped | STI (Prioritization) | 11 | Northwest Piedmont RPO | EB-5961 | Division 11 | L(M), TALT5 | 2026 | 53000 |  |  | 2027 | 175000 | 2022 | 63000 | 291000
Surry | Various | MOUNT AIRY | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Bike & Ped | STI (Prioritization) | 11 | Northwest Piedmont RPO | EB-5845 | Division 11 | L(M), TA5T50 | 2026 | 280000 |  |  | 2027 | 430000 | 2022 | 192000 | 902000
Surry | I-77 Northbound | NCDOT | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5831 | Statewide Mobility | BFP, T(M) | 2024 | 320000 |  |  | 2026 | 19470000 |  |  | 19790000 | RIGHT-OF-WAY IN PROGRESS.
Surry | SR 2080 (Quaker Church Road) | NCDOT | Bridge 850152 over Ararat River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5832 | Division 11 | BGOFF | 2029 | 250000 |  |  | 2030 | 4000000 |  |  | 4250000
Surry | SR 2081 (Hardy Road) | NCDOT | Bridge 850153 over Hogan Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0210 | Highway Fund | DP |  |  |  |  | 2020 | 875000 |  |  | 875000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Surry | I-74 | NCDOT | I-77 to US 601. | Rehabilitate pavement. | 6.28 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5907 | Statewide Mobility | BGLT5, T(M) |  |  |  |  | 2022 | 5543000 |  |  | 5543000 | UNDER CONSTRUCTION.
Surry | I-77 | NCDOT | Mile marker 91.0 to mile marker 95.0. | Perform diamond grinding. | 4.39 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5829A | Statewide Mobility | T |  |  |  |  | 2022 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION.
Surry | I-77 | NCDOT | Mile marker 91.0 to mile marker 95.0. | Rehabilitate pavement. | 4.39 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5829 | [11 empty] | UNDER CONSTRUCTION
Surry | NC 89 (Pine Street) | NCDOT | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Highway | Safety | 11 | Northwest Piedmont RPO | HS-2011G | Region F | HF, HSIP | 2026 | 425000 | 2026 | 25000 | 2027 | 1274000 | 2023 | 100000 | 1824000 | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS.
Surry | NC 89 (West Pine Street) | NCDOT | SR 1387 (Toast Road) to SR 1396 (Pine Ridge Road). | Modernize roadway and construct SR 1396 (Pine Ridge Road) intersection improvements. | 3.81 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5905 | Division 11 | BGLT5, T, T(M) | 2026 | 19400000 | 2026 | 5901000 | 2029 | 57505000 |  |  | 82806000 | NC BUILD BOND FUNDING: $13.7M FOR CONSTRUCTION PAYBACK 2030 - 2042 (FY 2030 / YR 10 SALE).
Surry | NC 89 (West Pine Street) | NCDOT | SR 1397 (Round Peak Church Road) intersection near Mount Airy. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5901 | Region F | BGLT5, T(M) | 2024 | 370000 | 2024 | 410000 | 2025 | 7900000 |  |  | 8680000 | RIGHT-OF-WAY IN PROGRESS.
Surry | US 21 Business (North Bridge Street) | NCDOT | NC 268 (CC Camp Road) intersection in Elkin. | Improve US 21 Business northbound to NC 268 eastbound movement. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5910 | Division 11 | BGLT5, T(M) | 2022 | 1175000 | 2022 | 400000 | 2023 | 2150000 |  |  | 3725000 | UNDER CONSTRUCTION.
Surry | US 601 | NCDOT | I-74 to SR 1104 (Cody Trail). | Widen to four lanes. | 7.19 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5836 | Division 11 | BGLT5, T | 2026 | 980000 | 2026 | 2200000 | 2028 | 159355000 |  |  | 162535000 | NC BUILD BOND FUNDING: $35.5M FOR CONSTRUCTION PAYBACK 2030 - 2042 (FY 2030 / YR 10 SALE).
Surry | US 601 | NCDOT | US 52 to SR 1365 (Forrest Drive). | Upgrade roadway. | 0.98 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5714 | Region F | T | 2019 | 10950000 | 2024 | 1200000 | 2031 | 29800000 |  |  | 41950000 | RIGHT-OF-WAY IN PROGRESS.
Surry | US 52 Bypass (Andy Griffith Parkway) | NCDOT | YVRR Crossing 721996Y in Mount Airy. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 11 | Northwest Piedmont RPO | RX-2411A | Division 11 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Swain | NC 28 | NCDOT | SR 1121 (Wattia Road) at Almond to existing US 19 / NC 28. | Upgrade roadway. | 1.517 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DA | [11 empty] | COMPLETE
Swain | Great Smoky Mountains National Park | NCDOT | Regionwide | Funding for sustainable transportation practices to reduce air pollution. |  | Highway | Other | 14 | Southwestern RPO | HO-0004 | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 375000 | 375000 | IN PROGRESS
Swain | SR 1337 (West Deep Creek Road) | NCDOT | SR 1338 (Deep Creek Cemetery Road) intersection in Bryson City. | Install pedestrian accommodations. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014Z | Division 14 | HSIP, T(M) |  |  |  |  | 2025 | 147000 |  |  | 147000
Swain | US 19 | NCDOT | SR 1336 (Old River Road / Deep Creek Street) to Jackson County. | Install rumble stripes and long life pavement markings. | 5.15 | Highway | Safety | 14 | Southwestern RPO | HS-2014T | Region G | HSIP, T(M) |  |  |  |  | 2024 | 364000 |  |  | 364000
Swain | US 19 / US 74 | NCDOT | Nantahala Outdoors Center / Appalachian Trail near SR 1103 (Silvermine Road) near Wesser | Install pedestrian rectangular rapid flashing beacons. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2414A | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 48000 |  |  | 48000
Swain | NC 28 (Fontana Road) | NCDOT | US 129 to Swain County / Graham County line at Little Tennessee River. | Upgrade roadway. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839A | Not Funded | T | NOT FUNDED | 1520000 | NOT FUNDED | 200000 | NOT FUNDED | 312700000 | NOT FUNDED |  | 314420000
Swain | Various | NCDOT | SR 1321 (Bryson Walk) from SR 1323 (Slope Street) to Everett Street; Everett Street from SR 1321 (Bryson Walk) to SR 1336 (Depot Street); SR 1336 (Depot Street) from Everett Street to SR 1336 (Deep Creek Road). | Construct intersection improvements. | 0.73 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5843 | Division 14 | T |  |  |  |  | 2022 | 3629000 |  |  | 3629000 | UNDER CONSTRUCTION.
Swain | Swain County Focal Point On Aging, Inc. | SWAIN COUNTY FOCAL POINT ON AGING, INC. | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6165 | Public Transit | 5311, L, S | [6 empty] | 2020 | 508000 | 508000 | FUNDS AUTHORIZED IN PROGRESS
Swain | SR 1176 (Whittier Depot Road) | NCDOT | GSM Crossing 720218G in Whittier. | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO | RX-2414F | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
Swain, Graham | NC 28 | NCDOT | East of Calfpen Gap in Graham County to SR 1121 (Wattia Road) at Almond in Swain County. | Upgrade roadway. | 2.381 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DB | [11 empty] | COMPLETE
Transylvania | Ecusta Trail | NCDOT | Transylvania County Line to Lamb Creek near Brevard. | Construct greenway. | 8 | Bike & Ped | Federal Lands Access Program | 14 | Land-of-Sky RPO | BF-0002 | Exempt | CRPANY, DP, FLAP, L(M) |  |  |  |  | 2026 | 25200000 | 2023 | 2875000 | 28075000 | FLAP PROJECT NC 61. PE AWARDED $1.0M. DP REPRESENTS RAISE GRANT OF $24.559M.
Transylvania | Estatoe Trail | NCDOT | SR 1344 (Cashiers Valley Road) to Silversteen Drive in Brevard. | Construct multi-use path. | 0.69 | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Land-of-Sky RPO | BN-0011 | Exempt | CRP550, L(M) |  |  | 2026 | 200000 | 2026 | 2100000 | 2024 | 150000 | 2450000
Transylvania | New Route | NCDOT | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Bike & Ped | STI (Prioritization) | 14 | Land-of-Sky RPO | EB-5858 | Division 14 | L(M), TA5200 | 2022 | 20000 | 2022 | 140000 | 2022 | 1200000 | 2022 | 820000 | 2180000 | UNDER CONSTRUCTION.
Transylvania | Mountain Industrial Drive | NCDOT | Jennings Industrial Park. | Construct road extension. | 0.41 | Highway | Appalachian Development Highway System | 14 | Land-of-Sky RPO | HA-0002 | Exempt | ADHSL | 2022 | 10000 |  |  | 2024 | 739000 | 2021 | 200000 | 949000 | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610
Transylvania | SR 1533 (Everett Road) | NCDOT | Bridge 870030 over French Broad River. | Replace bridge. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | HB-0026 | Division 14 | BGOFF | 2026 | 380000 | 2026 | 130000 | 2028 | 7200000 |  |  | 7710000
Transylvania | SR 1408 (Fish Hatchery Road) | NCDOT | West of US 276 to end of pavement. | Install guardrail. | 1.65 | Highway | Federal Lands Access Program | 14 | Land-of-Sky RPO | HF-0002 | Exempt | FLAP, HF(M) |  |  |  |  | 2023 | 230000 | 2022 | 10000 | 240000 | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS.
Transylvania | US 276 | NCDOT | US 64 to Avery Creek Trailhead. | Install guardrail and construct sidewalk. | 0.5 | Highway | Federal Lands Access Program | 14 | Land-of-Sky RPO | HF-0004 | Exempt | FLAP, HF(M) | [6 empty] | 2022 | 525000 | 525000 | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS.
Transylvania | US 276 | NCDOT | US 64 to Avery Creek Trailhead. | Widen to 3-lanes with bicycle lanes. | 2.2 | Highway | Federal Lands Access Program | 14 | Land-of-Sky RPO | R-5865 | Exempt | FLAP, HF(M) | [6 empty] | 2019 | 3400000 | 3400000 | HF(M) FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECTS NC 35 AND NC 63.
Transylvania | Railroad Avenue | BREVARD | Bridge 870102 over Kings Creek in Brevard. | Replace Bridge. | 0.25 | Highway | Municipal Bridge | 14 | Land-of-Sky RPO | B-5550 | Division 14 | BFPOFF |  |  |  |  | 2023 | 1586000 |  |  | 1586000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD
Transylvania | US 276 | NCDOT | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 14 | Land-of-Sky RPO | HN-0031 | Exempt | CRPLT5, T(M) | 2026 | 130000 |  |  | 2026 | 4200000 | 2024 | 744000 | 5074000
Transylvania | SR 1512 (Ecusta Road) | NCDOT | Ecusta Bypass intersection in Brevard | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Highway | Safety | 14 | Land-of-Sky RPO | HS-2414G | Division 14 | HSIP, T(M) |  |  |  |  | 2025 | 35000 |  |  | 35000
Transylvania | US 276 (Greenville Highway) | NCDOT | SR 1118 (Gallimore Road) intersection in Brevard. | Install traffic signal with pedestrian signals. | 0.5 | Highway | Safety | 14 | Land-of-Sky RPO | HS-2014AC | Region G | HSIP, T(M) |  |  |  |  | 2024 | 215000 |  |  | 215000
Transylvania | US 64 | NCDOT | Mile marker 5.0 to mile marker 13.0 and mile marker 25.0 to mile marker 31.0 near Brevard | Install rumble stripes with 6" long life pavement markings. |  | Highway | Safety | 14 | Land-of-Sky RPO | HS-2414H | Region G | HSIP, T(M) |  |  |  |  | 2025 | 580000 |  |  | 580000
Transylvania | US 64 (Asheville Highway) | NCDOT | SR 1592 (Hospital Drive) / Straus Parkway intersection in Brevard. | Construct intersection improvements. | 0.5 | Highway | Safety | 14 | Land-of-Sky RPO, French Broad River MPO | HS-2014M | Region G | HSIP, T(M) |  |  |  |  | 2024 | 225000 |  |  | 225000
Transylvania | US 64 (Rosman Highway) | NCDOT | Estatoe Trail Greenway Crossing near SR 1347 (Carolina Ave) (0.17 mile northeast of SR 1347 (Carolina Ave)). | Install a pedestrian hybrid beacon. |  | Highway | Safety | 14 | Land-of-Sky RPO | HS-2414O | Region G | HSIP, T(M) |  |  |  |  | 2025 | 170000 |  |  | 170000
Transylvania | Davidson River Village Connector | NCDOT | US 64 to US 276 / US 64 in Pisgah Forest. | Construct roadway on new location. | 0.75 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5605 | Division 14 | T |  |  |  |  | 2020 | 3345000 |  |  | 3345000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE)
Transylvania | SR 1540 (Wilson Road) | NCDOT | SR 1504 (Old US 64) to US 276 in Brevard. | Upgrade roadway. | 3.67 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5763 | Division 14 | T | 2022 | 17400000 | 2022 | 1200000 | 2029 | 63445000 |  |  | 82045000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $17.8M ON CONSTRUCTION PAYBACK 2029-2043 (SALE 9 / FY 2029).
Transylvania | US 64 | NCDOT | US 276 / NC 280 intersection in Pisgah Forest. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5799 | Region G | T | 2022 | 5890000 | 2022 | 600000 | 2024 | 23651000 |  |  | 30141000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
Transylvania | US 64 / US 276 | NCDOT | Fortune Cove Road to US 64 Business (North Caldwell Street). | Construct median and access control measures. | 1.17 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5800 | Region G | BG5T50, T | 2023 | 14800000 | 2023 | 4400000 | 2030 | 32500000 |  |  | 51700000 | RIGHT-OF-WAY IN PROGRESS
Transylvania | Transylvania County Transit | TRANSYLVANIA COUNTY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Land-of-Sky RPO | TK-6167 | Public Transit | 5311, L, S | [6 empty] | 2020 | 644000 | 644000 | FUNDS AUTHORIZED IN PROGRESS
Tyrrell | US 64 | NCDOT | Bridge 880007 over Alligator River | Replace bridge. | 4 | Highway | Bridges | 1 | Albemarle RPO | HB-0001 | Statewide Mobility | BFP, DP, HF(M), HFB, PROTCT, T | 2023 | 590000 | 2023 | 500000 | 2025 | 521740000 |  |  | 522830000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS.
Tyrrell | US 64 | NCDOT | East of SR 1326 (Keiser Drive) to SR 1229 (Old Highway 64) intersection. | Install rumble stripes. | 5.19 | Highway | Safety | 1 | Albemarle RPO | HS-2001H | Region A | HSIP, T(M) |  |  |  |  | 2024 | 250000 |  |  | 250000
Tyrrell | US 64 | NCDOT | Columbia to Alligator River Bridge. | Modernize roadway. | 14.34 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5940 | Division 1 | NHP, T(M) | 2028 | 1400000 | 2028 | 6000000 | 2032 | 64900000 |  |  | 72300000
Union | Marvin Loop Trail | MARVIN | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0012 | Division 10 | BGDA, L, TADA | 2026 | 157000 |  |  | 2027 | 1309000 | 2023 | 443000 | 1909000
Union | NC 205 (North Elm Street); East Union Street | MARSHVILLE | SR 1740 (Main Street) and SR 1735 (East Union Street) intersections in Marshville; N Cross Street intersection in Marshville | Construct pedestrian improvements and install pavement markings. | 0.55 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0011 | Division 10 | BGDA, L(M) |  |  |  |  | 2026 | 335000 | 2023 | 63000 | 398000
Union | NC 75 | NCDOT | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0157 | Division 10 | BGDA, L(M) | 2028 | 412000 | 2028 | 10000 | 2030 | 642000 | 2026 | 173000 | 1237000
Union | North Indian Trail Road | INDIAN TRAIL | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5931 | Division 10 | BGDA, CMAQ, L, L(M), TADA | 2023 | 1509000 |  |  | 2026 | 7391000 | 2020 | 25000 | 8925000 | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
Union | Various | WAXHAW | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5819 | Division 10 | BGDA, L(M), TADA |  |  |  |  | 2022 | 1738000 | 2016 | 258000 | 1996000 | UNDER CONSTRUCTION.
Union | US 74 | INDIAN TRAIL | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5723 | Division 10 | CMAQ, L(M), TAANY, TADA | 2026 | 125000 |  |  | 2026 | 3931000 | 2019 | 1191000 | 5247000 | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Union | NC 200 | NCDOT | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Highway | Bridges | 10 | Charlotte Regional TPO | B-5949 | Region E | BFP, T(M) | 2026 | 120000 |  |  | 2028 | 5400000 |  |  | 5520000
Union | SR 1681 (Old Camden Road) | NCDOT | Bridge 890021 over Stewarts Creek. | Replace bridge. | 0.25 | Highway | Bridges | 10 | Charlotte Regional TPO | B-5376 | Division 10 | BGOFF | 2024 | 210000 |  |  | 2028 | 3000000 |  |  | 3210000
Union | Indian Trail | INDIAN TRAIL | Crooked Creek Park, Chestnut Square Park, and Crossing Paths Park in Indian Trail. | Install Level 2 electric vehicle chargers. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0139 | Exempt | BGDA, L |  |  |  |  | 2026 | 784000 | 2025 | 5000 | 789000
Union | Indian Trail-Fairview Road | INDIAN TRIAL | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0160 | Division 10 | BGDA, L(M) | 2029 | 566000 | 2029 | 152000 | 2031 | 7498000 | 2027 | 2248000 | 10464000
Union | NC 16 (North Broome Street) | WAXHAW | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0115 | Region E | BGANY, BGDA, L | 2027 | 517000 |  |  | 2028 | 3099000 | 2025 | 461000 | 4077000 | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24.
Union | NC 218 | UNION COUNTY | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0117 | Exempt | CMAQ, HF(M) | 2025 | 308000 |  |  | 2027 | 2349000 | 2023 | 200000 | 2857000 | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY)
Union | NC 75 | NCDOT | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6248 | Exempt | L, T(DA) | 2027 | 1598000 |  |  | 2028 | 3544000 | 2021 | 200000 | 5342000 | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
Union | NC 84 | NCDOT | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6246 | Exempt | BGDA, HF(M), L, T(DA) | 2026 | 350000 |  |  | 2028 | 2080000 | 2022 | 200000 | 2630000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS.
Union | NC 84 | NCDOT | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6247 | Exempt | BGDA, HF, HF(M), L, L(M), T(DA) | 2027 | 540000 |  |  | 2029 | 6314000 | 2021 | 840000 | 7694000 | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
Union | North Charlotte Avenue; New Town Road | NCDOT | Walnut Street to NC 200; Cuthbertson Road to Ennis Road. | Resurface roadways. | 3.23 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039A | Division 10 | BGDACV |  |  |  |  | 2022 | 938000 |  |  | 938000 | UNDER CONSTRUCTION.
Union | SR 1305 (Kensington Drive) | WAXHAW | NC 16 to Sunset Hill Road in Waxhaw. | Improve corridor. | 0.24 | Highway | Locally Selected | 10 | Charlotte Regional TPO | EB-5950 | Division 10 | BGANY, BGDA, L(M) | 2022 | 591000 |  |  | 2026 | 4339000 |  |  | 4930000 | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23
Union | SR 1307 (Bonds Grove Church Road) | UNION COUNTY | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0116 | Exempt | CMAQ, L(M) | 2026 | 595000 |  |  | 2028 | 4426000 | 2024 | 438000 | 5459000
Union | SR 1315 (New Town Road) | NCDOT | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0135 | Division 10 | BGANY, HF(M), L(M) | 2026 | 447000 |  |  | 2027 | 3646000 | 2024 | 407000 | 4500000 | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24.
Union | SR 1346 (Potter Road) | NCDOT | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6087 | Division 10 | BGDA, CMAQ, CRPDA, HF, HF(M), L, L(M) | 2019 | 1258000 |  |  | 2018 | 2500000 | 2018 | 436000 | 4194000 | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP.
Union | SR 1357 (Potter Road) | NCDOT | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0055 | Division 10 | BGANY, HF, L, L(M), O, T(DA) | 2024 | 643000 |  |  | 2027 | 1773000 | 2023 | 475000 | 2891000 | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS.
Union | US 74 | MARSHVILLE | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0159 | Exempt | BGDA, L(M) | 2026 | 36000 | 2026 | 100000 | 2028 | 1677000 | 2025 | 203000 | 2016000
Union | Various | NCDOT | Routes in Division 10. | Perform various maintenance activities including resurfacing, traffic signal loop replacement, and pavement restriping. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039
Union | Various | NCDOT | Routes in Division 10. | Replace pavement markings. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039B | Exempt | BGDACV |  |  |  |  | 2022 | 126000 |  |  | 126000 | COMPLETE.
Union | Various | NCDOT | Routes in Division 10. | Replace traffic signal loops. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039C | Exempt | BGDACV |  |  |  |  | 2023 | 189000 |  |  | 189000 | UNDER CONSTRUCTION.
Union | Waxhaw Parkway West | WAXHAW | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0158 | Division 10 | L, L(M), T(DA) | 2027 | 1696000 | 2027 | 10000 | 2029 | 8130000 | 2026 | 760000 | 10596000 | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP.
Union | Marvin | CHARLOTTE | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Highway | Other | 10 | Charlotte Regional TPO | HO-0032 | Exempt | DP, L(M) | [6 empty] | 2026 | 72000 | 72000
Union | Various | NCDOT | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Highway | Other | 10 | Rocky River RPO | C-5617 | Exempt | CMAQ, L(M) | 2020 | 6000 |  |  | 2020 | 38000 | 2020 | 18000 | 62000
Union | NC 200 (Lancaster Highway) | NCDOT | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710Z | Region E | BGANY, BGDA, HF(M), HSIP, L(M) | 2020 | 35000 |  |  | 2022 | 2571000 | 2020 | 195000 | 2801000 | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP.
Union | NC 200 (Lancaster Highway) | NCDOT | SR 1137 (Potter Road) intersection near Waxhaw. | Construct safety improvements. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AH | Region E | HF(M), HSIP | 2022 | 650000 |  |  | 2024 | 2914000 |  |  | 3564000
Union | NC 218 | NCDOT | SR 1606 (Sikes Mills Road) intersection near Fairview. | Construct roundabout. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AI | Region E | HSIP, T(M) |  |  |  |  | 2024 | 1217000 |  |  | 1217000
Union | SR 1003 (White Store Road) | NCDOT | Anson County line to US 601 | Install rumble stripes with long life pavement markings. | 12.6 | Highway | Safety | 10 | Rocky River RPO | HS-2610B | Division 10 | HSIP, T(M) |  |  |  |  | 2027 | 417000 |  |  | 417000
Union | SR 1005 (Landsford Road) | NCDOT | SR 1937 (Old Pageland Marshville Road). | Install an all way stop. |  | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AD | Division 10 | HSIP, T(M) |  |  |  |  | 2024 | 30000 |  |  | 30000
Union | SR 1009 (Old Charlotte Highway) | NCDOT | Williams Road in Monroe. | Construct safety improvements. |  | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AN | Division 10 | HSIP, T(M) |  |  |  |  | 2024 | 952000 |  |  | 952000
Union | SR 1313 (Joe Kerr Road) | NCDOT | SR 3486 (Wheatfield Drive) intersection in Marvin. | Install pedestrian signs and crosswalk. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410M | Division 10 | HSIP |  |  | 2025 | 10000 | 2026 | 90000 | 2025 | 30000 | 130000
Union | SR 1315 (New Town Road) | NCDOT | SR 1008 (Waxhaw-Indian Trail Road) intersection in Wesley Chapel. | Construct safety improvements. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710Y | Division 10 | BGANY, HF(M), HSIP |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP.
Union | SR 1365 (Stallings Road) | NCDOT | Vicinity of Stallings Municipal Park | Install a Rectangular Rapid Flashing Beacon (RRFB) at the existing crosswalk and add yield bar pavement markings. | 0.1 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2610K | Division 10 | HSIP, T(M) |  |  |  |  | 2026 | 50000 |  |  | 50000
Union | SR 3286 (Tom Short Road) | NCDOT | SR 2968 (Carisbrooke Drive) intersection in Charlotte | Install a Rectangular Rapid Flashing Beacon (RRFB) at the existing crosswalk and add yield bar pavement markings. | 0.1 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2610L | Division 10 | HSIP, T(M) |  |  |  |  | 2026 | 50000 |  |  | 50000
Union | NC 16 (Providence Road South) | NCDOT | SR 1307 (Bonds Grove Church Road) intersection in Waxhaw. | Construct interim safety improvements. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769AA | Region E | HSIP, T | 2024 | 4150000 | 2025 | 1000000 | 2026 | 1225000 |  |  | 6375000
Union | NC 16 (Providence Road South) | NCDOT | SR 1307 (Bonds Grove Church Road) to SR 3530 (Waxhaw Parkway) in Waxhaw. | Widen to multi-lanes. | 1.73 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769B | Region E | T | 2026 | 18200000 | 2026 | 10000 | 2029 | 80900000 |  |  | 99110000
Union | NC 16 (Providence Road South) | NCDOT | SR 1316 (Rea Road extension) to SR 1307 (Bonds Grove Church Road) in Waxhaw. | Widen to multi-lanes. | 4.05 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769A | Region E | T | 2026 | 29800000 | 2026 | 10000 | 2029 | 71000000 |  |  | 100810000
Union | NC 16 (Providence Road South) | NCDOT | SR 1316 (Rea Road extension) to SR 3530 (Waxhaw Parkway) in Waxhaw. | Widen to multi-lanes. | 5.7 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769
Union | NC 84 | NCDOT | NC 16 to SR 1008 (Waxhaw-Indian Trail Road) in Wesley Chapel. | Construct four lane roadway, part on new location. | 4.02 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-3467 | Region E | BGANY, T | 2024 | 41000000 | 2025 | 5700000 | 2028 | 115595000 |  |  | 162295000 | NC BUILD BOND $41M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE);
Union | SR 1004 (Lawyers Road) | NCDOT | I-485 to SR 1524 (Stevens Mill Road). | Widen to four lanes. | 0.25 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6170 | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18700000 |  |  | 24600000
Union | SR 1009 (Charlotte Avenue) | NCDOT | Seymour Street to NC 200 (Dickerson Boulevard). | Widen to four lanes divided. | 0.37 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6031 | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18100000 |  |  | 25100000
Union | SR 1009 (Old Monroe Road) | NCDOT | Indian Trail Road to east of SR 1377 (Wesley Chapel-Stouts Road). | Widen to multi-lanes. | 3.16 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714BB | Division 10 | O, T |  |  |  |  | 2028 | 77765000 |  |  | 77765000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $35.2M ON CONSTRUCTION PAYBACK 2029-2043 (SALE 9 / FY 2029). OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL.
Union | SR 1009 (Old Monroe Road) | NCDOT | West of Morningside Meadow Lane to Indian Trail Road | Widen to multi-lanes. | 3.16 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714BA | Division 10 | T |  |  |  |  | 2027 | 22555000 |  |  | 22555000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. NC BUILD BONDS: $8.5M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028).
Union | SR 1362 (Chestnut Lane Connector) | NCDOT | SR 1367 (Matthews Indian Trail Road) to SR 1368 (Gribble Road) in Indian Trail. | Construct road on new location. | 0.39 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5808 | Division 10 | T | 2019 | 1615000 | 2019 | 1200000 | 2024 | 20041000 |  |  | 22856000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025);
Union | SR 1514 (Rocky River Road) | NCDOT | James Hamilton Road intersection in Monroe. | Realign James Hamilton Road to intersect with SR 1514 (Rocky River Road) and Myers Road. | 0.14 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5703B | Statewide Mobility | O, T | 2023 | 759000 | 2023 | 325000 | 2026 | 2590000 |  |  | 3674000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY THE CITY OF MONROE.
Union | US 601 | NCDOT | Existing US 74 to the Monroe Bypass. | Widen to multi-lanes. | 0.89 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4024 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 770000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27700000 |  |  | 29670000 | COORDINATE WITH U-5723
Union | US 74 | NCDOT | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | HP-0001 | Statewide Mobility | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 107300000 |  |  | 116000000
Union | US 74 | NCDOT | US 601 interchange in Monroe. | Construct interchange improvements. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5723 | Statewide Mobility | T |  |  | 2025 | 500000 | 2030 | 23100000 |  |  | 23600000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024
Union | US 74 (Andrew Jackson Highway) | NCDOT | NC 200 (Dickerson Boulevard) to SR 1007 (Rocky River Road). | Widen to six lanes. | 2.8 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5764 | Region E | NHP, T(M) | 2027 | 59248000 | 2027 | 7400000 | 2030 | 75298000 |  |  | 141946000 | COORDINATE WITH U-5931
Union | US 74 (Andrew Jackson Highway) | NCDOT | Secrest Shortcut Road intersection in Monroe. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5931 | Statewide Mobility | T | 2027 | 4531000 | 2027 | 520000 | 2030 | 8800000 |  |  | 13851000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764.
Union | US 74 (Roosevelt Boulevard) | NCDOT | SR 1514 (Rocky River Road) intersection in Monroe. | Construct reduced conflict intersection. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5703
Union | US 74 (Roosevelt Boulevard) | NCDOT | SR 1514 (Rocky River Road) intersection in Monroe. | Construct reduced conflict intersection. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5703A | Statewide Mobility | [10 empty] | COMPLETE
Union | SR 1364 (Pleasant Plains Road) | NCDOT | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Highway | Transition | 10 | Charlotte Regional TPO | U-5112 | Pre-STI (Transition) | BGANY, BGDA, CMAQ, HSIP, L, L(M), T(M) | 2021 | 676000 |  |  | 2024 | 10203000 |  |  | 10879000 | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
Union | Union County Transportation | UNION COUNTY TRANSPORTATION | Various | Facility renovations, preventive maintenance, and compliance with federal security and safety set-aside requirements. Operational funds will support urban passenger trips, the Union Express bus service to Charlotte, and other ongoing operating expenses. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0048 | Public Transit | 5307, L, L(M) | [6 empty] | 2025 | 3837000 | 3837000
Union | Union County Transportation | UNION COUNTY TRANSPORTATION | Union County Transportation motor pool facility | Implement low emission alternative fuel conversion. |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0031 | Exempt | CRPDA, L |  |  |  |  | 2024 | 200000 |  |  | 200000
Union | Union County Transportation |  | Various locations | Funding for operational expenses and routine capital. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0052 | Public Transit | 5307, L(M) | [6 empty] | 2024 | 1942000 | 1942000
Union | Union County Transportation | UNION COUNTY TRANSPORTATION | Systemwide | Operational expenses, routine capital, and planning. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0059 | Public Transit | 5307, L | [6 empty] | 2024 | 1938000 | 1938000
Union | CSX Railroad | NCDOT | SR 1758 (North Main Street) crossing; Stewart Street crossing; SR 1762 (Bivens Street) crossing. | Improve crossings at SR 1758 (North Main Street) and SR 1762 (Bivens Street). Close crossing at Stewart Street. |  | Rail | Rail-Highway Grade Crossing Closure | 10 | Charlotte Regional TPO | RC-2010A | Division 10 | RR | 2025 | 500000 |  |  | 2027 | 3000000 |  |  | 3500000
Union | SR 1008 (Indian Trail Road) | NCDOT | CSX Crossing 631928Y in Indian Trail. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010C | Division 10 | RR |  |  |  |  | 2026 | 388000 |  |  | 388000
Union | SR 3522 (Weddington Road) | NCDOT | CSX Crossing 631587H near Monroe. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010A | Division 10 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
Union | CSX SF Line | NCDOT | SR 1007 (Rockey River Road) and SR 1009 (Old Charlotte Highway) at-grade crossings in Monroe | Construct two rail-highway grade separations. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | RP-0001 | Statewide Mobility | BGANY, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 210000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34000000 |  |  | 42010000
Union | CSX SF LINE | NCDOT | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5744 | Statewide Mobility | DP, O, T | 2026 | 5848000 | 2026 | 826000 | 2028 | 23100000 |  |  | 29774000 | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX.
Union | CSX SG Line | CSXT RR | SR 1300 (Helms Road) in Waxhaw. | Construct rail siding. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5748A | Region E | T |  |  |  |  | 2022 | 5894000 |  |  | 5894000 | UNDER CONSTRUCTION.
Union | CSX SG Line | NCDOT | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct grade separation at SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5748B | Region E | DP, O, T | 2023 | 5000000 | 2023 | 378000 | 2026 | 24202000 |  |  | 29580000 | RIGHT-OF-WAY IN PROGRESS.
Union | CSX SG Line | NCDOT | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct rail siding and grade separation in vicinity of SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5748 | [11 empty] | DP REPRESENTS FEDERAL CRISI GRANT FUNDS; OTHER FUNDING PROVIDED BY CSX.
Union, Anson | SR 1901 (Hasty Road); SR 1238 (Hasty Road) | NCDOT | East of SR 1740 (Old Hwy 74) to Anson County line; Union County line to SR 1252 (Lower White Store Road). | Install rumble stripes with long life pavement markings. | 7 | Highway | Safety | 10 | Rocky River RPO | HS-2610I | Division 10 | HSIP, T(M) |  |  |  |  | 2027 | 148000 |  |  | 148000
Union, Anson, Mecklenburg | NC 218 | NCDOT | US 74 in Anson County to US 601 in Union County, and from Mill Grove Road in Union County to I-485 in Mecklenburg County. | Install milled rumble stripes. | 27.51 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010C | Region E | HSIP |  |  |  |  | 2022 | 616000 |  |  | 616000 | UNDER CONSTRUCTION.
Union, Mecklenburg | SR 1009 (John Street / Old Monroe Road) | NCDOT | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714AC | Division 10 | BGANY, BGDA, T, T(DA), T(M) | 2019 | 11780000 | 2019 | 2200000 | 2027 | 45200000 |  |  | 59180000 | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028).
Union, Mecklenburg | SR 1009 (John Street / Old Monroe Road) | NCDOT | SR 3348 / SR 3474 (Trade Street) to SR 1377 (Wesley Chapel-Stouts Road). | Widen to multi-lanes. | 6.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714
Union, Mecklenburg | SR 3174 / SR 1501 (Idlewild Road) | NCDOT | I-485 to SR 1524 (Stevens Mill Road). | Widen to six lanes. | 0.77 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913B | Not Funded | T | NOT FUNDED | 14947000 | NOT FUNDED | 646000 | NOT FUNDED | 21500000 | NOT FUNDED |  | 37093000
Union, Mecklenburg | SR 3174 / SR 1501 (Idlewild Road) | NCDOT | SR 3175 (Stallings Road) to SR 1524 (Stevens Mill Road). | Widen roadway. | 0.77 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913 | [11 empty] | PROJECT BEING ACCELERATED BY A LOAN PROVIDED BY THE TOWN OF MATTHEWS. LOAN TO BE PAID BACK TO THE TOWN WITH ROW/UTIL IN 2025 AND CON IN 2026. NCDOT TO BEGIN ROW IN 2024 AND CON IN 2026.
Vance | SR 1001 (Warrenton Road) | NCDOT | SR 1507 (Brookston Road) intersection. | Construct intersection improvements. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | W-5705G | Division 5 | HSIP, T(M) |  |  |  |  | 2026 | 1265000 |  |  | 1265000
Vance | US 1 | NCDOT | SR 1113 (Lake Lodge Road) intersection. | Construct unsignalized reduced conflict intersection. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | W-5805G | Statewide Mobility | CRPLT5, HF(M), HSIP, T(M) | 2024 | 100000 |  |  | 2026 | 1815000 |  |  | 1915000 | HF(M) funds represent High Impact/Low Cost funds.
Vance | Various | NCDOT | Intersections in Henderson | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AP | Division 5 | HSIP | 2027 | 10000 | 2027 | 20000 | 2028 | 1255000 |  |  | 1285000
Vance | SR 1162 (Dabney Drive) | NCDOT | South Cooper Drive to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5890 | Division 5 | T | 2027 | 41545000 | 2027 | 5000000 | 2030 | 44605000 |  |  | 91150000 | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE).
Vance | US 1 (Raleigh Road) | NCDOT | Belmont Drive (Old County Home Road) and Welcome Avenue intersection in Henderson | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | HP-0013 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 2800000
Vance | Various | NCDOT | Locations in Henderson | Install citywide signal system. | 9.71 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | HP-0021 | Region C | BGANY |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4736000 |  |  | 5036000
Vance | CXS S Line | NCDOT | Alexander Avenue | Construct Alexander Avenue grade separation and roadway improvements on SR 1267 (Dabney Drive) |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CF | Region C | T | 2030 | 9000000 | 2030 | 800000 | 2033 | 20000000 |  |  | 29800000
Vance | CXS S Line | NCDOT | Andrews | Construct grade separation and improve downtown roadways. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CG | Statewide Mobility
Vance | CXS S Line | NCDOT | Franklinton to Ridgeway | Improve S-line. | 36.46 | Rail | Other | 5 | Kerr-Tar RPO | P-5753CA | Statewide Mobility
Vance | CXS S Line | NCDOT | North Kitrell | Roadway improvements of North Kitrell Roadway including McClanahan Street grade separation and SR 1458 (Peter Gill Road). |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753BH | Statewide Mobility
Vance | CXS S Line | NCDOT | SR 1115 (Bear Pond Road) | Construct grade separation. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CD | Statewide Mobility
Vance | CXS S Line | NCDOT | SR 1139 (JP Taylor Road) | Construct grade separation and improve roadway. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CE | Statewide Mobility
Vance | CXS S Line | NCDOT | Various | Construct grade separation at SR 1507 (Brookston Road) and SR 1501 (South Carroll Street). |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CI | Statewide Mobility
Vance | CXS S Line | NCDOT | Various | Construct grade separation at SR 1508 (Greystone Road) and Warrenton roadway improvements. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CH | Statewide Mobility
Vance, Franklin, Wake | NC 39 | NCDOT | NC 97 in Wake County to Virginia state line | Install rumble stripes. | 22.5 | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO | HS-2405AG | Region C | HSIP, T(M) |  |  |  |  | 2026 | 1704000 |  |  | 1704000
Vance, Warren | I-85 | NCDOT | South of US 158 in Vance County to North of SR 1237 (Manson Drewry Road) in Warren County. | Rehabilitate pavement and upgrade signs. | 5.81 | Highway | Transition | 5 | Kerr-Tar RPO | I-0914BA | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Vance, Warren | CXS S Line | NCDOT | Franklinton to Ridgeway |  |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753C | Statewide Mobility
Wake | RDU | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | Raleigh Durham International Airport | Reconstruct runway 5L-23R. |  | Aviation | STI (Prioritization) | 5 | Capital Area MPO | AV-5700 | Statewide Mobility | O, T |  |  |  |  | 2024 | 104000000 |  |  | 104000000
Wake | Alston Ridge Greenway | FUQUAY-VARINA | Alston Ridge Greenway to Bass Lake Greenway in Fuquay-Varina. | Complete a gap of greenway trail. | 0.41 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0092 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 2231000 | 2024 | 17000 | 2248000 | Under Construction.
Wake | Beaver Creek Greenway Extension | APEX | Kelly Road Park to Apex Nature Park in Apex | Realign adjacent segment of existing Beaver Creek Greenway. | 1.21 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6021 | Division 5 | L, L(M), TADA |  |  |  |  | 2022 | 8201000 |  |  | 8201000
Wake | Bridge Street | CAMPO | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0174 | Division 5 | BGDA, L(M) | 2026 | 677000 | 2026 | 70000 | 2026 | 2811000 |  |  | 3558000
Wake | Crabtree Creek Greenway | CARY | Bond Park to SR 1615 (High House Road) in Cary | Construct greenway between Black Creek and White Oak Creek Greenways and between Bond Park and Preston Fields Park. | 0.53 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0036 | Exempt | CMAQ, L(M) |  |  |  |  | 2024 | 1402000 | 2024 | 248000 | 1650000
Wake | Crabtree Creek Greenway | CARY | Various locations in Cary and Morrisville | Connect existing greenway and replace train trestle. | 1.85 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | C-5168 | Exempt | [10 empty] | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE
Wake | Crabtree Creek Greenway | RALEIGH | Lassiter Mill Road to Hertford Street in Raleigh | Construct greenway trail. | 0.14 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0027 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 1627000 |  |  | 1627000
Wake | Crabtree Creek Greenway Connector | CARY | Crabtree Creek Greenway to Weston Greenway in Cary | Construct 10-foot greenway including grade separation under Weston Parkway. | 0.21 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0037 | Exempt | CMAQ, L(M) |  |  |  |  | 2025 | 2826000 | 2024 | 20000 | 2846000
Wake | East Jones Street | FUQUAY-VARINA | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0038 | Exempt | CMAQ, L, TADA | 2022 | 17000 | 2022 | 39000 | 2024 | 898000 | 2022 | 140000 | 1094000 | UNDER CONSTRUCTION
Wake | Higgins Greenway | CARY | Shirley Drive to north of intersection of Walnut Street and SR 1300 (Kildaire Farm Road) in Cary | Complete a gap of greenway trail. | 0.27 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0091 | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 2450000 | 2024 | 10000 | 2460000
Wake | Jenks Carpenter Road; Green level Church Road | CAMPO | High House Road to Deshire Mist Lane; Green Hope School Road to Brooks Park Lane. | Construct 10 foot wide street-side trails. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0172 | Division 5 | L(M), TADA |  |  |  |  | 2026 | 2500000 |  |  | 2500000
Wake | Little Drive | RALEIGH | SR 2153 (Louis Stephens Drive) to CSX Railroad crossing in Research Triangle Park | Construct greenway trail. | 0.24 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0026 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 2207000 | 2022 | 235000 | 2442000 | UNDER CONSTRUCTION
Wake | Optimist Farm Greenway | CARY | Existing segment of the greenway behind Truelove Drive South and west to West Lake Road in Cary. | Construct 10 foot wide greenway and 0.2 miles of sidewalk. Includes pedestrian improvements at one intersection and a mid-block crossing on Optimist Farm Road. | 1.2 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0126 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 5000000 |  |  | 5000000
Wake | Saunders Street | APEX | SR 1307 (West Chatham Street) to Hinton Street in Apex | Construct sidewalk extensions. | 0.4 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0095 | Division 5 | BGDA, L(M) |  |  |  |  | 2026 | 1344000 | 2024 | 20000 | 1364000
Wake | South Garner Greenway | GARNER | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0129 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 5300000 | 2025 | 16000 | 5316000
Wake | SR 1152 (Holly Springs Road) | HOLLY SPRINGS | Flint Point Lane to Middlecrest Way in Holly Springs | Construct pedestrian safety enhancements. | 0.41 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0023 | Division 5 | BGDA, L(M) |  |  |  |  | 2022 | 1115000 |  |  | 1115000 | UNDER CONSTRUCTION
Wake | SR 1307 (West Chatham Street) | APEX | Hunter Street to Saunder Street in Apex | Construct sidewalk extensions and improve safety of pedestrian crossing. | 0.31 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6046 | Division 5 | BGDA, L(M) |  |  |  |  | 2024 | 953000 | 2024 | 10000 | 963000
Wake | SR 1308 (Laura Duncan Road) | APEX | Community Park Drive to SR 5878 (North Salem Street) in Apex | Improve safety of pedestrian crossing. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6019 | Division 5 | BGDA, L(M) |  |  |  |  | 2021 | 544000 |  |  | 544000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION.
Wake | SR 1379 (Penny Road) | NCDOT | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0051 | Exempt | CMAQ, HF(M) | 2025 | 50000 |  |  | 2026 | 350000 | 2023 | 50000 | 450000 | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS
Wake | SR 1616 (Old Apex Road) | CARY | West Chatham Street to Murphy Drive in Cary, including CSX railroad crossing | Complete sidewalk gaps. | 1.29 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0048 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 1975000 | 2024 | 25000 | 2000000
Wake | SR 1632 (Louis Stephens Drive) | MORRISVILLE | Gray Marble Road to Addenbrock Drive and Northeast corner of Louis Stephens Drive and SR 1635 (McCrimmon Parkway) intersection in Morrisville | Complete sidewalk gaps. | 0.63 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0049 | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 550000 | 2025 | 10000 | 560000
Wake | SR 2000 (Wake Forest Road) | RALEIGH | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0025 | Division 5 | BGANY, L(M) | 2024 | 200000 |  |  | 2024 | 2679000 | 2022 | 150000 | 3029000 | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP
Wake | SR 2768 (Southeast Judd Parkway) | FUQUAY-VARINA | South of Logan Meadow Court to north of Oldwyck Drive in Fuquay-Varina | Complete sidewalk gaps. | 0.07 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0054 | Division 5 | BGDA, L(M) |  |  |  |  | 2024 | 728000 | 2023 | 60000 | 788000
Wake | SR 3112 (Northwest Cary Parkway) | CARY | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0024 | Division 5 | BGDA, L(M) | 2022 | 40000 | 2022 | 162000 | 2023 | 6744000 |  |  | 6946000 | UNDER CONSTRUCTION
Wake | SR 6107 (North Main Street) | HOLLY SPRINGS | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0052 | Exempt | CMAQ, L(M) | 2025 | 250000 |  |  | 2025 | 500000 | 2024 | 75000 | 825000 | RIGHT-OF-WAY IN PROGRESS
Wake | US 401 (South Saunders Street) | RALEIGH | SR 1009 (Lake Wheeler Road) to north of Dorothea Drive in Raleigh | Construct shared use path. | 0.12 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0089 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 1095000 | 2024 | 10000 | 1105000
Wake | US 64 Business (Wendell Boulevard) | WENDELL | North of SR 2346 (Hanor Lane) to east of SR 2353 (Old Wilson Road) in Wendell | Construct geometric improvements, sidewalk extension and install pedestrian crossing at SR 2329 (Marshburn Road). | 1.47 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6048 | Division 5 | BGDA, L(M) | 2023 | 75000 |  |  | 2023 | 1575000 |  |  | 1650000 | UNDER CONSTRUCTION
Wake | Utley Creek Greenway West | HOLLY SPRINGS | NC 55 to Holly Glen subdivision sidewalk in Holly Springs | Complete a gap of greenway trail. | 1.06 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0093 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 2750000 | 2024 | 20000 | 2770000
Wake | Vandora Springs Road; Woodland Road | NCDOT | Vandora Springs Elementary School to Woodland Road; Vandora Springs Road to Pineview Drive in Garner. | Construct sidewalk. | 0.15 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0128 | Division 5 | HF(M), TADA | 2026 | 73000 |  |  |  |  | 2025 | 234000 | 307000
Wake | Various | APEX | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0047 | Division 5 | L(M), TADA | 2024 | 221000 |  |  | 2025 | 1524000 | 2024 | 20000 | 1765000
Wake | Various | CAMPO | South side of Center Street from North Mason Street to Tunstall Avenue, one side of Tunstall Avenue from Center Street to East Williams Street, North side of East Williams Street from Tunstall Avenue to James Street, and North Side of J | Construct sidewalk. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0173 | Division 5 | L(M), TADA | 2026 | 536000 | [6 empty] | 536000
Wake | Various | FUQUAY-VARINA | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0022 | Division 5 | BGDA, L(M) | 2023 | 187000 | 2023 | 75000 | 2024 | 2305000 | 2022 | 164000 | 2731000 | UNDER CONSTRUCTION
Wake | SR 1011 (South Salem Street) | APEX | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Bike & Ped | Other | 5 | Capital Area MPO | BO-2422 | Exempt | HP, L, L(M) | 2027 | 890000 |  |  | 2028 | 2970000 | 2025 | 740000 | 4600000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206.
Wake | SR 1153 (Tingen Road) |  | CSX Railroad crossing north of James Street. | Construct a pedestrian bridge over CSX railroad within the existing alignment of SR 1153 (Tingen Road) in Apex. | 0.25 | Bike & Ped | Other | 5 | Capital Area MPO | BO-2416 | Exempt | HP, L(M) | 2025 | 48000 |  |  |  |  | 2024 | 640000 | 688000 | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC202. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME.
Wake | Walnut Creek Greenway | CARY | Downtown Cary Park to Buck Jones Road at I-40 in Cary. | Construct greenway. | 2.6 | Bike & Ped | Other | 5 | Capital Area MPO | BO-2423 | Exempt | HP, L(M) | [6 empty] | 2025 | 625000 | 625000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC207.
Wake | Black Creek Greenway | CARY | West Dynasty Drive to Old Reedy Creek Road in Cary | Construct greenway. | 2.74 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5894 | Division 5 | CMAQ, L(M), TAANY |  |  |  |  | 2023 | 15121000 |  |  | 15121000 | UNDER CONSTRUCTION
Wake | NC 55 (East Williams Street) | HOLLY SPRINGS | SR 1301 (Sunset Lake Road) to NC 55 in Holly Springs | Construct sidewalk. | 0.9 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5895 | Division 5 | L(M), TAANY |  |  |  |  | 2021 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
Wake | SR 1012 (Western Boulevard) | NCDOT | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5718 | Division 5 | L(M), TAANY | 2028 | 6200000 | 2028 | 310000 | 2030 | 5600000 |  |  | 12110000 | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166
Wake | SR 1637 (Church Street) | MORRISVILLE | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5838 | Division 5 | L(M), TAANY | 2026 | 250000 |  |  | 2026 | 1450000 | 2022 | 300000 | 2000000
Wake | NC 231 | NCDOT | Bridge 910034 over Norfolk Southern Railroad in Wendell. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5986 | Region C | BFP, HFB | 2027 | 1104000 | 2027 | 352000 | 2030 | 6100000 |  |  | 7556000
Wake | NC 50 | NCDOT | Bridge 910069 over US 70 in Garner. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-4654 | Region C | BFP, T(M) |  |  |  |  | 2024 | 13530000 |  |  | 13530000
Wake | SR 1179 (Bridge Street) | NCDOT | Bridge 910497 over Norfolk Southern Railroad in Fuquay-Varina. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | HB-0029 | Division 5 | BGOFF | 2027 | 100000 | 2027 | 100000 | 2029 | 2000000 |  |  | 2200000
Wake | SR 1321 (Avent Ferry Road) | NCDOT | Bridge 910318 over Lake Johnson in Raleigh. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5130 | Division 5 | BFP, T(M) |  |  |  |  | 2032 | 8000000 |  |  | 8000000 | RIGHT-OF-WAY IN PROGRESS.
Wake | SR 2044 (Ligon Mill Road) | NCDOT | Bridge 910126 over Smiths Creek in Wake Forest. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5318 | Division 5 | BFP, T(M) |  |  |  |  | 2023 | 11000000 |  |  | 11000000 | UNDER CONSTRUCTION
Wake | US 401 | NCDOT | Bridges 910115 and 910117 over Norfolk Southern Railroad and an unnamed tributary of Swift Creek. | Replace bridges. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5987 | Region C | BFP | 2027 | 640000 | 2027 | 640000 | 2030 | 24500000 |  |  | 25780000 | RIGHT OF WAY IN PROGRESS.
Wake | US 401 (Capital Boulevard) | NCDOT | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5684 | Region C | BFP, T(M) | 2031 | 4600000 | 2031 | 560000 | 2033 | 16700000 |  |  | 21860000
Wake | New Route; SR 1152 (Holly Springs - New Hill Road); SR 1153 (Old Holly Springs Apex Road) | NCDOT | Green Oaks Parkway near Irving Parkway intersection in Holly Springs; SR 1153 (Old Holly Springs Apex Road) intersection; Bennet Know Parkway intersection in Holly Springs. | Construct access road; Construct intersection improvements. | 1.55 | Highway | Economic Development | 5 | Capital Area MPO | HE-0002 | Division 5 | O, T |  |  |  |  | 2024 | 9690000 |  |  | 9690000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES. OTHER FUNDS REPRESENT STATE CONTINGENCY FUNDS.
Wake | SR 5220 (Jones Sausage Road) | NCDOT | SR 1004 (West Garner Road) to I-40 in Garner. | Widen roadway from south of SR 2585 (Wilmington Road) to I-40, including access point improvements, and construct improvements at SR 1004 intersection and I-40 interchange. | 1.44 | Highway | Economic Development | 5 | Capital Area MPO | U-6099 | Division 5 | [10 empty] | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMAZON
Wake | US 1; SR 1127 (New Hill - Holleman Road); SR 1149 (Friendship Road) | NCDOT | SR 1127 (New Hill - Holleman Road) interchange; SR 1149 (Friendship Road) intersection; SR 1152 (Old Holly Springs-New Hill Road) in Holly Springs. | Construct intersection improvements. |  | Highway | Economic Development | 5 | Capital Area MPO | HE-0010 | Division 5 | T | 2026 | 200000 |  |  | 2027 | 8675000 | 2023 | 1125000 | 10000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN.
Wake | I-40 | NCDOT | SR 1728 (Wade Avenue) to I-440 / US 1 in Raleigh. | Rehabilitate pavement and bridge. | 3.84 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5943 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 18419000 |  |  | 18419000 | UNDER CONSTRUCTION
Wake | I-440 / US 1 | NCDOT | SR 1728 (Wade Avenue) to SR 2000 (Wake Forest Road) in Raleigh. | Rehabilitate pavement. | 4.85 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5997 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2024 | 23100000 |  |  | 23100000
Wake | I-540 | NCDOT | Triangle Towne Center Boulevard in Raleigh to I-495 / US 64 / US 264 in Knightdale. | Rehabilitate pavement. | 8.97 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5945 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2031 | 27900000 |  |  | 27900000
Wake | I-540 | NCDOT | US 70 (Glenwood Avenue) to east of Triangle Town Boulevard in Raleigh. | Rehabilitate pavement. | 12.53 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5999 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2024 | 12511000 |  |  | 12511000 | COORDINATE WITH I-5998 AND I-6000;
Wake | I-87 / US 64 / US 264 | NCDOT | I-440 in Raleigh to SR 1003 (Rolesville Road). | Rehabilitate pavement. | 9.91 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5944 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2031 | 28600000 |  |  | 28600000
Wake | Apex Peakway | APEX | James Street to Towhee Drive. | Construct grade separated interchange for Apex Peakway at South Salem Street and CSX Railroad. | 0.25 | Highway | Locally Selected | 5 | Capital Area MPO | U-5928 | Division 5 | BGDA, L(M), RR |  |  |  |  | 2024 | 25000000 |  |  | 25000000
Wake | Blue Ridge Road | RALEIGH | Homewood Banks Drive to Crabtree Valley Avenue in Raleigh. | Add center turn lane, raised median, complete street improvements, and grade separation with House Creek Greenway Connections. | 0.32 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0052 | Division 5 | BGANY, BGDA, L(M) |  |  |  |  | 2025 | 7997000 | 2024 | 10000 | 8007000 | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP.
Wake | Bowling Road | Town of Fuquay-Varina | South Main Street | Operational improvements. Install traffic signal, curb and gutter, sidepath, and ADA-compliant ramps. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0172 | Division 5
Wake | Holly Springs Road | Town of Holly Springs | NC 55 to North Main Street | Widen to four lane divided facility with bike/ped accommodations. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0174 | Division 5 | BGDA, L(M) | [6 empty] | 2026 | 3000000 | 3000000
Wake | Lake Boone Trail | RALEIGH | I-440 to Ridge Road in Raleigh. | Upgrade roadway to complete street. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0032 | Division 5 | BGDA, L(M) |  |  |  |  | 2024 | 1712000 |  |  | 1712000
Wake | NC 42 | NCDOT | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0171 | Division 5 | BGDA, HF, HF(M) | 2026 | 860000 | 2026 | 10000 |  |  | 2026 | 381000 | 1251000 | HF FUNDS REPRESENT SPOT MOBILITY FUNDS
Wake | NC 42 | NCDOT | SR 2735 (Johnston Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008O | Exempt | BA | 2023 | 175000 | 2025 | 125000 | 2025 | 1300000 |  |  | 1600000 | RIGHT-OF-WAY IN PROGRESS
Wake | NC 50 |  | SR 2728 (Rand Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008J | Exempt | BGBA | 2025 | 1500000 | 2025 | 100000 | 2027 | 17200000 | 2024 | 10000 | 18810000 | RIGHT-OF-WAY IN PROGRESS
Wake | NC 50 | CREEDMOOR | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0121 | Division 5 | BGDA, HF(M) | 2025 | 103000 |  |  | 2026 | 778000 | 2024 | 266000 | 1147000 | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS
Wake | NC 50 | NCDOT | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0122 | Division 5 | BGDA, HF(M) | 2025 | 187000 |  |  | 2026 | 940000 | 2024 | 332000 | 1459000 | HF(M) REPRESENT SPOT MOBILITY FUNDING
Wake | NC 50 (Benson Road) | NCDOT | SR 2812 (Timber Drive) intersection in Garner. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008C | Exempt | BA | 2022 | 100000 |  |  | 2025 | 525000 |  |  | 625000 | UNDER CONSTRUCTION
Wake | NC 55 | HOLLY SPRINGS | SR 1115 (Avent Ferry Road) to South Main Street in Holly Springs. | Construct 3rd southbound lane. | 0.39 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0029 | Exempt | BGDA, L(M) | 2023 | 102000 |  |  | 2024 | 914000 |  |  | 1016000 | UNDER CONSTRUCTION
Wake | NC 55 | NCDOT | SR 1191 (Technology Drive) / SR 6107 (East Williams Street) intersection in Apex. | Upgrade intersection to interchange or alternative intersection. | 1 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0007 | Exempt | BA, NHPBA | 2024 | 9100000 | 2024 | 2900000 | 2026 | 27099000 | 2021 | 2615000 | 41714000
Wake | NC 96 (Arendell Avenue) | ZEBULON | North of Pearces Road to Dogwood Drive | Construc access management improvements. | 0.4 | Highway | Locally Selected | 5 | Capital Area MPO | U-5118FB | Region C | BGANY, BGDA, L(M) |  |  |  |  | 2025 | 1062000 |  |  | 1062000
Wake | NC 98 | WAKE FOREST | Camp Kanata Road intersection in Wake Forest. | Construct intersection improvements and add turn lanes on NC 98. | 0.75 | Highway | Locally Selected | 5 | Capital Area MPO | U-6222 | Exempt | BGDA, HF |  |  |  |  | 2021 | 1050000 | 2020 | 150000 | 1200000 | "HF" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION
Wake | Olive Chapel Road | NCDOT | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0173 | Division 5 | BGDA, L, L(M) | 2026 | 498000 | 2026 | 10000 |  |  | 2026 | 772000 | 1280000
Wake | South Main Street | HOLLY SPRINGS | SR 1152 (Holly Springs Road) to Earp Street in Holly Springs. | Construct intersection improvements, add turn lanes and sidewalk on northbound Main Street. | 0.12 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0030 | Division 5 | BGDA, L(M) | 2023 | 451000 |  |  | 2024 | 749000 |  |  | 1200000 | UNDER CONSTRUCTION
Wake | SR 1003 (Rolesville Road) |  | SR 2320 (Riley Hill Road) intersection in Wendell. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0128 | Division 5 | BGDA, HF(M) | 2025 | 90000 |  |  |  |  | 2024 | 197000 | 287000 | HF(M) FUNDING REPRESENTS SPOT MOBILITY FUNDS.
Wake | SR 1005 (Six Forks Road) | NCDOT | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0043 | Exempt | CMAQ, HF(M) | 2024 | 275000 | 2026 | 200000 | 2026 | 840000 | 2022 | 190000 | 1505000 | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS
Wake | SR 1005 (Six Forks Road) | RALEIGH | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0119 | Division 5 | BGANY, BGDA, L, L(M) |  |  |  |  | 2025 | 30998000 | 2025 | 51000 | 31049000 | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP
Wake | SR 1006 (Old Stage Road) |  | SR 2736 (Rock Service Station Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008I | Exempt | BA | 2024 | 3100000 | 2025 | 350000 | 2026 | 9300000 |  |  | 12750000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1007 (Poole Road) | NCDOT | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0031 | Division 5 | BGDA, HF(M) | 2022 | 340000 | 2022 | 150000 | 2025 | 1700000 |  |  | 2190000 | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION
Wake | SR 1010 (Ten Ten Road) |  | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008F | Exempt | BGBA, T(M) | 2025 | 510000 | 2025 | 50000 | 2025 | 2000000 |  |  | 2560000
Wake | SR 1010 (Ten Ten Road) | NCDOT | NC 50 (Benson Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008P | Exempt | BA, HSIP | 2023 | 370000 | 2025 | 240000 | 2028 | 2700000 |  |  | 3310000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1010 (Ten Ten Road) | NCDOT | SR 1386 (Bells Lake Road) / SR 1386 (Graham Newton Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008L | Exempt | BA | 2023 | 300000 | 2025 | 225000 | 2025 | 3000000 |  |  | 3525000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | FUQUAY-VARINA | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0042 | Exempt | BGDA, CMAQ, L(M) | 2023 | 140000 | 2023 | 260000 | 2025 | 2344000 | 2022 | 253000 | 2997000 | UNDER CONSTRUCTION
Wake | SR 1115 (Avent Ferry Road) | HOLLY SPRINGS | West of SR 1101 (Piney Grove - Wilbon Road) to Village Walk Drive in Holly Springs. | Construct operational improvements. | 0.25 | Highway | Locally Selected | 5 | Capital Area MPO | U-5529 | Division 5 | BGDA, L(M) |  |  |  |  | 2020 | 2330000 |  |  | 2330000 | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS
Wake | SR 1152 (Holly Springs Road) | HOLLY SPRINGS | Flint Point Lane to SR 1301 (Sunset Lake Road) in Holly Springs. | Widen to a four-lane median-divided facility and construct sidewalk. | 1.52 | Highway | Locally Selected | 5 | Capital Area MPO | U-6243 | Division 5 | BGDA, L(M) |  |  |  |  | 2022 | 18000000 |  |  | 18000000 | UNDER CONSTRUCTION
Wake | SR 1152 (Holly Springs Road) | HOLLY SPRINGS | North Main Street to Flint Point Lane in Holly Springs. | Widen from 2 to 4 lanes. | 0.83 | Highway | Locally Selected | 5 | Capital Area MPO | U-6094 | Division 5 | BGDA, L(M) | 2020 | 1480000 |  |  | 2025 | 1521000 |  |  | 3001000 | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS
Wake | SR 1152 (Holly Springs Road) | NCDOT | SR 1301 (Sunset Lake Road) intersection in Holly Springs. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008D | Exempt | BA | 2024 | 1330000 | 2025 | 170000 | 2026 | 3400000 |  |  | 4900000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1301 (Sunset Lake Road) | FUQUAY-VARINA | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0027 | Division 5 | BGDA, L(M) | 2023 | 1510000 | 2023 | 575000 | 2025 | 578000 | 2022 | 62000 | 2725000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1319 (Jones Franklin Road) | NCDOT | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0051 | Division 5 | BGDA, HF(M) | 2026 | 70000 | 2026 | 10000 | 2027 | 400000 | 2023 | 110000 | 590000 | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE.
Wake | SR 1349 (Dillard Drive) | NCDOT | Village Tavern Road to SR 1319 (Jones Franklin Road) in Raleigh. | Install two way left turn lane. | 0.15 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0050 | Division 5 | BGDA, HF | 2023 | 801000 |  |  | 2026 | 472000 |  |  | 1273000 | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS
Wake | SR 1371 (Lake Wheeler Road) / SR 1375 (Lake Wheeler Road) | NCDOT | SR 1375 (Simpkins Road) / Simpkins Farm Lane intersection in Raleigh. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008H | Exempt | BA | 2022 | 251000 | 2022 | 300000 | 2025 | 1750000 |  |  | 2301000 | UNDER CONSTRUCTION
Wake | SR 1375 (Lake Wheeler Road) | NCDOT | SR 1393 (Hilltop-Needmore Road) intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008G | Exempt | BA, BGBA | 2023 | 790000 | 2024 | 240000 | 2025 | 2000000 |  |  | 3030000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1379 (Penny Road) | NCDOT | SR 1382 (Olde South Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008S | Exempt | [10 empty] | DELETED
Wake | SR 1390 (Optimist Farm Road) | NCDOT | SR 1386 (Bells Lake Road) intersection in Apex. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008Q | Exempt | BA | 2024 | 360000 | 2025 | 60000 | 2026 | 3800000 | 2023 | 10000 | 4230000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1521 (Lake Pine Drive) | APEX | North of MacGregor Pines Road to north of Versailles Drive. | Widen to 3 lanes including 10 ft multi-use path on east side and 5 ft sidewalk west side. | 0.31 | Highway | Locally Selected | 5 | Capital Area MPO | U-5537 | Division 5 | BGDA, L(M) |  |  |  |  | 2021 | 585000 |  |  | 585000 | UNDER CONSTRUCTION BY TOWN OF APEX
Wake | SR 1624 (Carpenter Fire Station Road) | CARY | NC 55 to Cameron Pond Drive in Cary. | Widen to multi lanes. | 0.95 | Highway | Locally Selected | 5 | Capital Area MPO | U-6227 | Division 5 | BGANY, BGDA, L(M) | 2021 | 5629000 |  |  | 2026 | 8100000 |  |  | 13729000 | RIGHT-OF-WAY IN PROGRESS. $3,645,000 IN STBG-ANYAREA FUNDS RESULTING FROM FUND SWAPS
Wake | SR 1650 (Reedy Creek Road) | CARY | NC 54 (NE Maynard Road) to SR 1652 (Harrison Avenue) in Cary. | Widen from 2 to 3 lanes, to include roundabouts, as well as pedestrian and bicycle enhancements. | 1.2 | Highway | Locally Selected | 5 | Capital Area MPO | U-5501 | Division 5 | BGDA, L(M) |  |  |  |  | 2020 | 7692000 |  |  | 7692000 | UNDER CONSTRUCTION BY TOWN OF CARY
Wake | SR 1650 (Reedy Creek Road) | CARY | SR 1652 (Harrison Avenue) to south of Watts Pond Lane in Cary | Widen roadway. Install roundabouts and pedestrian enhancements. | 0.38 | Highway | Locally Selected | 5 | Capital Area MPO | U-5501A | Division 5
Wake | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | RALEIGH | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Highway | Locally Selected | 5 | Capital Area MPO | U-6242 | Division 5 | BGANY, BGDA, L(M) | 2023 | 1700000 | 2023 | 1100000 | 2025 | 11148000 |  |  | 13948000 | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP.
Wake | SR 2051 (Burlington Mills Road); US 401 Business (South Main Street) | ROLESVILLE | East of Rolesville Middle School to US 401 Business (South Main Street) in Rolesville; SR 2051 (Burlington Mills Road) to north of SR 1003 (East Young Street) / SR 1945 (West Young Street) in Rolesville. | Realign roadway and construct new intersection with south main street; Construct sidewalk extensions and complete street improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | U-6241 | Division 5 | BGDA, L(M) |  |  |  |  | 2022 | 20452000 |  |  | 20452000 | UNDER CONSTRUCTION
Wake | SR 2542 (Rock Quarry Road) | RALEIGH | Olde Birch Road to SR 2544 (Sunnybrook Road) in Raleigh. | Widen to 4-lane divided facility. | 0.83 | Highway | Locally Selected | 5 | Capital Area MPO | U-6093 | Division 5 | BGDA, L(M) | 2021 | 1891000 |  |  | 2022 | 11062000 |  |  | 12953000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 2700 (White Oak Road) | GARNER | SR 2709 (Ackerman Road) and SR 2547 (Hebron Church Road) intersection in Garner. | Construct intersection improvements and add multi-lane roundabout. | 1.06 | Highway | Locally Selected | 5 | Capital Area MPO | U-6225 | Division 5 | BGDA, L(M) | 2021 | 75000 |  |  | 2024 | 3441000 |  |  | 3516000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. UNDER CONSTRUCTION
Wake | SR 2765 (Old Honeycutt Road) | FUQUAY-VARINA | Intersection of Old Honeycutt Road and Kennebec Road (SR 2754) | Provide signalization at the intersection. Add curb, gutter, sidewalk and ADA ramps. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0141 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 1212000 | 2025 | 15000 | 1227000
Wake | SR 2768 (Judd Parkway) | FUQUAY-VARINA | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0041 | Exempt | CMAQ, HF(M) | 2022 | 63000 |  |  | 2023 | 2161000 | 2022 | 86000 | 2310000 | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION
Wake | SR 3014 (Morrisville-Carpenter Road) | MORRISVILLE | SR 1613 (Davis Drive) to west of NC 54 in Morrisville. | Widen to 4-lane divided facility. | 1.2 | Highway | Locally Selected | 5 | Capital Area MPO | U-5618 | Division 5 | BGDA, HF, L, L(M) |  |  |  |  | 2020 | 8495000 |  |  | 8495000 | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION
Wake | SR 3126 (Airport Boulevard) | NCDOT | Garden Square Lane to SR 1637 (Church Street) in Morrisville. | Construct roadway on new location. | 0.44 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0033 | Division 5 | BGDA, L, L(M) | 2022 | 600000 |  |  | 2026 | 11100000 |  |  | 11700000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 5220 (Jones Sausage Road) | GARNER | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0140 | Division 5 | BGDA, L(M) | 2025 | 2000000 | 2025 | 500000 | 2026 | 7090000 | 2025 | 10000 | 9600000
Wake | Ten-Ten Road | NCDOT | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0170 | Division 5 | BGDA, HF, HF(M) | 2026 | 34000 | 2026 | 10000 |  |  | 2026 | 338000 | 382000 | HF FUNDS REPRESENT SPOT SAFETY FUNDS
Wake | US 401 | FUQUAY-VARINA | SR 1404 (Mill Creek Drive) / Ideal Lane intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0028 | Exempt | BGDA, L, L(M) |  |  |  |  | 2024 | 3202000 | 2022 | 134000 | 3336000 | UNDER CONSTRUCTION
Wake | US 401 | NCDOT | SR 1393 (Hilltop-Needmore Road) / SR 2751 (Hilltop Road) / SR 2752 (Air Park Road) intersection and SR 1375 (Lake Wheeler Road) intersection in Fuquay-Varina. | Construct reduced conflict intersections and realign SR 2751 (Hilltop Road) to intersect opposite SR 1375 (Lake Wheeler Road). | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0006 | Exempt | NHPBA | 2024 | 2601000 | 2025 | 509000 | 2026 | 30500000 |  |  | 33610000 | RIGHT-OF-WAY IN PROGRESS
Wake | US 64 Business (Wendell Boulevard) | WENDELL | SR 1007 (Wendell Falls Parkway) in Wendell. | Construct intersection improvements and include closure of Wall Street. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | U-6244 | Exempt | BGDA, L(M) | 2022 | 110000 |  |  | 2024 | 2076000 |  |  | 2186000 | UNDER CONSTRUCTION
Wake | Various | NCDOT | Wake County | Construct congestion and safety improvements at various locations in Wake County. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0133 | Exempt | BA | [6 empty] | 2025 | 2500000 | 2500000
Wake | Cheswick Drive | RALEIGH | Bridge 910627 over Big Branch connecting Oakland Drive to Cheswick Drive. | Replace bridge. | 0.25 | Highway | Municipal Bridge | 5 | Capital Area MPO | HM-0003 | Division 5 | BFPOFF | 2025 | 250000 | 2025 | 250000 | 2025 | 1250000 | 2025 | 500000 | 2250000
Wake | Shelley Road | RALEIGH | Bridge 910378 over Mine Creek from Shadowbrook Drive to Forest Lawn Court. | Replace bridge. | 0.25 | Highway | Municipal Bridge | 5 | Capital Area MPO | HM-0002 | Division 5 | BFPOFF | 2026 | 300000 | 2026 | 250000 | 2026 | 2500000 |  |  | 3050000
Wake | Central Pines Regional Council | CAMPO | Central Pines | Transportation Demand Management Program For Organizations In Capital Area MPO |  | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0026A | Exempt | CMAQ, L(M) | [6 empty] | 2024 | 3146000 | 3146000
Wake | North Carolina State University | NORTH CAROLINA STATE UNIVERSITY (NCSU) | Clean Energy Technology Center. | Clean Fuels and Advanced Technologies (CFAT). |  | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0038 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 5930000 | 5930000
Wake | SR 1001 (Pearces Road) |  | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0018 | Exempt | CMAQ, T | 2026 | 40000 |  |  | 2027 | 1400000 | 2024 | 118000 | 1558000
Wake | SR 2697 (New Hope Road) |  | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0012 | Exempt | CMAQ, T | 2028 | 63000 |  |  | 2029 | 676000 | 2024 | 161000 | 900000
Wake | US 70 (Glenwood Avenue) |  | Cole Street / Wade Avenue eastbound ramps intersection in Raleigh. | Construct turn lanes. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0016 | Exempt | CMAQ, HF(M) |  |  |  |  | 2026 | 260000 | 2024 | 124000 | 384000 | HF(M) ARE SPOT SAFETY FUNDS.
Wake | Higgins Greenway | CARY | Higgins Greenway in Cary. | Improve congestion and air quality. |  | Highway | Other | 5 | Capital Area MPO | C-5604ID | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 1249000 |  |  | 1249000
Wake | Mingo Creek Greenway | KNIGHTDALE | Existing Greenway to Knightdale Station Park in Knightdale. | Improve congestion and air quality. |  | Highway | Other | 5 | Capital Area MPO | C-5604HA | Exempt | CMAQ, L(M) | 2024 | 300000 |  |  | 2023 | 3431000 |  |  | 3731000 | UNDER CONSTRUCTION
Wake | North Carolina State University | NCDOT | - | Before & after study, expansion feasibility study. |  | Highway | Other | 5 | Capital Area MPO | HO-0001C | Exempt | DP, HF(M) | [6 empty] | 2021 | 310000 | 310000
Wake | North Carolina State University | NCDOT | - | Install fiber optic cable. |  | Highway | Other | 5 | Capital Area MPO | HO-0001AB | Exempt | DP, HF(M) |  |  |  |  | 2026 | 168000 | 2022 | 150000 | 318000
Wake | North Carolina State University | NCDOT | - | NCDOT multi-modal connected vehicle infrastructure, connected vehicle applications, traffic signal improvements, project management. |  | Highway | Other | 5 | Capital Area MPO | HO-0001AA | Exempt | DP, HF(M) |  |  |  |  | 2023 | 2981000 | 2021 | 369000 | 3350000 | UNDER CONSTRUCTION
Wake | North Carolina State University | NCDOT | - | NCDOT multi-modal connected vehicle pilot program. |  | Highway | Other | 5 | Capital Area MPO | HO-0001 | Exempt | DP, HF(M) |  |  |  |  | 2022 | 227000 | 2021 | 311000 | 538000 | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS.
Wake | North Carolina State University | NCDOT | NCSU Campus | Systems engineering, grant administration. |  | Highway | Other | 5 | Capital Area MPO | HO-0001B | Exempt | DP, HF(M) | [6 empty] | 2021 | 200000 | 200000
Wake | I-40 | NCDOT | SR 1728 (Wade Avenue) US I-440 / US 1 / US 64. | Widen to six lanes. | 4 | Highway | Pre-STI (Historic) | 5 | Capital Area MPO | I-4744 | Pre-STI (Transition) | NHP |  |  |  |  | 2009 | 4635000 |  |  | 4635000 | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020
Wake | US 401 | NCDOT | Rolesville Bypass, north of SR 2225 (Louisbury Road) to NC 96 | Widen to four-lane median divided facility. | 6.401 | Highway | Pre-STI (Historic) | 5 | Capital Area MPO | R-2814B | Pre-STI (Transition) | BGANY | 2009 | 1727000 |  |  | 2011 | 7083000 |  |  | 8810000 | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022
Wake | US 401 | NCDOT | SR 2044 (Ligon Mill Road) to north of SR 2225 (Louisbury Road) | Widen to four-lane median divided facility. | 2.237 | Highway | Pre-STI (Historic) | 5 | Capital Area MPO | R-2814A | [11 empty] | COMPLETE
Wake | NC 42 | NCDOT | Bridge 910023 over Middle Creek. | Install guardrail. | 0.5 | Highway | Safety | 5 | Capital Area MPO | W-5805D | Region C | HSIP, T(M) |  |  |  |  | 2022 | 184000 |  |  | 184000 | UNDER CONSTRUCTION
Wake | NC 98 | NCDOT | SR 2057 / SR 4465 (Moores Pond Road) | Construct roundabout. |  | Highway | Safety | 5 | Capital Area MPO | W-5805E | Region C | BGDA, HF, HF(M), HSIP, T(M) | 2023 | 140000 | 2025 | 124000 | 2026 | 2400000 |  |  | 2664000 | RIGHT-OF-WAY IN PROGRESS
Wake | SR 1004 (Garner Road) | NCDOT | SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install pedestrian signals, curb ramps, and crosswalks. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AK | Division 5 | HSIP |  |  | 2025 | 8000 | 2026 | 145000 |  |  | 153000
Wake | SR 1004 (Garner Road); Timber Drive East | NCDOT | SR 2539 (Yeargan Road) intersection, SR 2564 (Creech Road) intersection, and Shenstone Boulevard intersection in Garner. | Upgrade traffic signals. | 1 | Highway | Safety | 5 | Capital Area MPO | W-5805H | Division 5 | HSIP, T(M) |  |  |  |  | 2021 | 75000 |  |  | 75000 | UNDER CONSTRUCTION
Wake | SR 1142 (Humie Olive Road) | NCDOT | Blazing Trail Drive / Driveway access to Apex Friendship High and Elementary Schools intersection. | Install traffic and pedestrian signals. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2005Q | Division 5 | HSIP, T(M) |  |  |  |  | 2024 | 130000 |  |  | 130000 | UNDER CONSTRUCTION
Wake | SR 1152 (Holly Springs Road) | NCDOT | SR 4089 (Winding Oak Way); YMCA Driveway | Install traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AJ | Division 5 | HSIP | 2026 | 12000 | 2026 | 6000 | 2027 | 248000 |  |  | 266000
Wake | SR 1349 (Dillard Drive) | NCDOT | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405G | Division 5 | HSIP, T(M) | 2026 | 8000 | 2026 | 30000 | 2027 | 297000 |  |  | 335000
Wake | SR 1615 (High House Road) | NCDOT | Cornerstone Drive intersection. | Upgrade traffic signal and intersection to include pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AV | Division 5 | HSIP |  |  | 2026 | 15000 | 2026 | 135000 |  |  | 150000
Wake | SR 1645 (Lumley Road) | NCDOT | I-540 westbound ramp / Arco Corporate Drive in Raleigh. | Upgrade traffic signal and construct turn lane. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2005I | Division 5 | HSIP, T(M) |  |  |  |  | 2025 | 240000 |  |  | 240000 | UNDER CONSTRUCTION
Wake | SR 1652 (Harrison Avenue) | NCDOT | SR 3081 (Chapel Hill Road) intersection | Upgrade traffic signal and install pedestrian signal and other pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405U | Division 5 | HSIP, T(M) |  |  |  |  | 2026 | 80000 |  |  | 80000
Wake | SR 1656 (Trinity Road) | NCDOT | SR 3009 (Edwards Mill Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405D | Division 5 | HSIP, T(M) |  |  | 2025 | 16000 | 2026 | 124000 |  |  | 140000
Wake | SR 1820 (Lead Mine Road) | NCDOT | SR 1827 (Lynn Road) intersection in Raleigh. | Construct pedestrian refuge islands, revise curb ramps, crosswalks, and other pavement markings. | 0.5 | Highway | Safety | 5 | Capital Area MPO | W-5805C | Division 5 | HSIP, T(M) |  |  |  |  | 2022 | 292000 |  |  | 292000 | UNDER CONSTRUCTION
Wake | SR 1822 (Leesville Road) | NCDOT | Country Trail/Tylerton Drive intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405BB | Division 5 | HSIP | 2026 | 10000 | 2026 | 10000 | 2027 | 475000 |  |  | 495000
Wake | SR 1827 (Lynn Road) | NCDOT | Glendower Road intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AW | Division 5 | HSIP | 2026 | 20000 | 2026 | 5000 | 2027 | 655000 |  |  | 680000
Wake | SR 1835 (Pinecrest Road) | NCDOT | Grove Barton Road; Toscana Drive intersection | Install traffic signal and intersection pedestrian improvements. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AQ | Division 5 | HSIP | 2026 | 30000 | 2026 | 5000 | 2027 | 340000 |  |  | 375000
Wake | SR 2000 (Falls Of Neuse Road) | NCDOT | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AC | Division 5 | HSIP, T(M) | 2025 | 2000 | 2025 | 3000 | 2026 | 136000 |  |  | 141000
Wake | SR 2000 (Falls Of Neuse Road) | NCDOT | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AB | Division 5 | HSIP, T(M) | 2025 | 2000 | 2025 | 3000 | 2026 | 114000 |  |  | 119000
Wake | SR 2000 (Wake Forest Road) | NCDOT | Hardimont Road/New Hope Church Road and Bland Road intersections | Update traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AZ | Division 5 | HSIP | 2026 | 10000 | 2026 | 15000 | 2027 | 360000 |  |  | 385000
Wake | SR 2026 (Hammond Road) | NCDOT | Rush Street intersection | Upgrade traffic signals and install/upgrade pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405Y | Division 5 | HSIP, T(M) |  |  |  |  | 2026 | 183000 |  |  | 183000
Wake | SR 2026 (North Person Street) | NCDOT | Polk street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405K | Division 5 | HSIP, T(M) | 2026 | 2000 |  |  | 2027 | 150000 |  |  | 152000
Wake | SR 2049 (Forestville Road) | NCDOT | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405H | Division 5 | HSIP, T(M) | 2026 | 2000 | 2026 | 20000 | 2027 | 243000 |  |  | 265000
Wake | SR 2215 (Buffaloe Road) | NCDOT | SR 2214 (Southhall Road) / Brintons Cottage Street and Valley Stream Drive intersections in Raleigh. | Revise traffic signals, curb ramps, and pavement markings. | 0.33 | Highway | Safety | 5 | Capital Area MPO | HS-2005G | Division 5 | HSIP, T(M) |  |  |  |  | 2024 | 147000 |  |  | 147000 | UNDER CONSTRUCTION
Wake | SR 2516 (Hodge Road) | NCDOT | Mingo Creek Trail crossing. | Relocate crosswalk. |  | Highway | Safety | 5 | Capital Area MPO | HS-2005J | Division 5 | HSIP, T(M) |  |  |  |  | 2024 | 190000 |  |  | 190000 | UNDER CONSTRUCTION
Wake | SR 2544 (Sunnybrook Road) | NCDOT | Middle Branch Road intersection. | Install traffic signal. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AT | Division 5 | HSIP |  |  | 2026 | 15000 | 2026 | 160000 |  |  | 175000
Wake | SR 2754 (Kennebec Road) | NCDOT | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405O | Division 5 | HSIP, T(M) | 2026 | 50000 | 2026 | 50000 | 2026 | 560000 |  |  | 660000
Wake | SR 2765 (Old Honeycutt Road) | NCDOT | Fitness Drive / Weststone Boulevard intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405BC | Division 5 | HSIP |  |  | 2026 | 50000 | 2026 | 300000 |  |  | 350000
Wake | SR 2765 (Old Honeycutt Road) | NCDOT | Fuquay-Varina Parkway intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AX | Division 5 | HSIP | 2026 | 8000 | 2026 | 10000 | 2027 | 382000 |  |  | 400000
Wake | SR 2921 (North Raleigh Boulevard) | NCDOT | Glascock Street intersection | Upgrade traffic signal and install pedestrian improvements. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405BJ | Division 5 | HSIP, T(M) | 2026 | 5000 |  |  | 2027 | 325000 |  |  | 330000
Wake | SR 3008 (Edenton Street) | NCDOT | Harrington Street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AI | Division 5 | HSIP | 2026 | 20000 | 2026 | 20000 | 2027 | 300000 |  |  | 340000
Wake | SR 3009 (Edwards Mill Road) | NCDOT | SR 1728 (Wade Avenue) ramp terminals | Upgrade traffic signal, install pedestrian signals, and install rectangular rapid flashing beacons at slip ramps. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AN | Division 5 | HSIP |  |  |  |  | 2026 | 185000 |  |  | 185000
Wake | SR 3067 (TW Alexander Drive) | NCDOT | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405R | Division 5 | HSIP, T(M) | 2025 | 8000 | 2025 | 3000 | 2026 | 124000 |  |  | 135000
Wake | SR 4363 (Martin Luther King Jr. Boulevard) | NCDOT | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Highway | Safety | 5 | Capital Area MPO | HS-2405S | Division 5 | HSIP, T(M) | 2026 | 3000 | 2026 | 5000 | 2027 | 440000 |  |  | 448000
Wake | SR 4363 (Martin Luther King Jr. Boulevard) | NCDOT | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405V | Division 5 | HSIP, T(M) | 2026 | 16000 | 2026 | 5000 | 2027 | 405000 |  |  | 426000
Wake | SR 4363 (Martin Luther King Jr. Boulevard) | NCDOT | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Highway | Safety | 5 | Capital Area MPO | HS-2405W | Division 5 | HSIP, T(M) | 2026 | 5000 | 2026 | 10000 | 2026 | 470000 |  |  | 485000
Wake | SR 4363 (Martin Luther King Jr. Boulevard) | NCDOT | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Highway | Safety | 5 | Capital Area MPO | HS-2405T | Division 5 | HSIP, T(M) | 2026 | 5000 | 2026 | 3000 | 2026 | 385000 |  |  | 393000
Wake | SR 5144 (Heritage Lake Road) | NCDOT | Heritage Heights Lane intersection | Construct crosswalk and sidewalk improvements. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405Q | Division 5 | HSIP, T(M) |  |  |  |  | 2026 | 150000 |  |  | 150000
Wake | US 1 (Capital Boulevard) | NCDOT | Calvary Drive intersection. | Construct signal and crosswalk upgrades and install median fence. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AS | Statewide Mobility | HSIP |  |  |  |  | 2025 | 395000 |  |  | 395000
Wake | US 401 | NCDOT | SR 2108 / SR 2036 (New Hope Road) intersection and US 401 at Calvary Drive intersection. | Install pedestrian signals and crosswalks. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2005K | Region C | HSIP, T(M) |  |  |  |  | 2024 | 487000 |  |  | 487000 | UNDER CONSTRUCTION
Wake | US 70 (Glenwood Avenue) | NCDOT | Hilburn Drive; Glenwood Forest Drive intersection | Install/upgrade crosswalks, pedestrian signals, and sidewalk. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405X | Region C | HSIP, T(M) |  |  | 2025 | 2000 | 2026 | 227000 |  |  | 229000
Wake | US 70 (Glenwood Road) | NCDOT | SR 1820 (Lead Mine Road) / SR 1670 (Blue Ridge Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405E | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 176000 |  |  | 176000
Wake | US 70 / US 401 (South Saunders Street) | NCDOT | I-40 / I-440 ramp terminals | Uprade ramp traffic signals. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405J | Region C | HSIP, T(M) |  |  |  |  | 2026 | 360000 |  |  | 360000
Wake | US 70 / US 401 / NC 50 (Wilmington Street) | NCDOT | Chapanoke Road intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405Z | Region C | HSIP, T(M) |  |  |  |  | 2026 | 89000 |  |  | 89000
Wake | US 70 / US 401 / NC 50 (Wilmington Street) | NCDOT | SR 1370/SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AA | Region C | HSIP, T(M) |  |  | 2025 | 2000 | 2026 | 270000 |  |  | 272000
Wake | Various | NCDOT | Downtown Raleigh | Construct pedestrian improvements at multiple existing crosswalks including pedestrian curb extensions, raised crosswalks, and median refuge islands. |  | Highway | Safety | 5 | Capital Area MPO | HS-2405AR | Division 5 | HSIP | 2026 | 5000 | 2026 | 5000 | 2027 | 1020000 |  |  | 1030000
Wake | Various | NCDOT | Downtown Raleigh Business District. | Revise traffic signals at various locations. |  | Highway | Safety | 5 | Capital Area MPO | HS-2005F | Division 5 | HSIP, T(M) |  |  |  |  | 2023 | 200000 |  |  | 200000 | UNDER CONSTRUCTION
Wake | Various | NCDOT | Routes in Division 5 | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 5 | Capital Area MPO | W-5205REG | Region C
Wake | Holly Springs | NCDOT | Holly Springs | Install fiber to connect existing town fiber to intersections, upgrade existing infrastructure including cabinets, controllers, and software. | 4.58 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0008 | Region C | T |  |  |  |  | 2028 | 3085000 |  |  | 3085000
Wake | I 40 |  | Cary Towne Boulevard to Wade Avenue | Construct operational improvements including auxiliary lanes between Wade Avenue and Cary Towne Boulevard and interchange improvements at Cary Towne Boulevard. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0003 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27500000 |  |  | 34000000
Wake | I-40 | NCDOT | I-440 / US 1 / US 64 interchange in Raleigh. | Reconstruct interchange. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5703 | Statewide Mobility | NHP | 2027 | 40800000 | 2027 | 2799000 | 2027 | 354895000 |  |  | 398494000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $80M FOR CONSTRUCTION, PAYBACK FY 2029-2043.
Wake | I-40 | NCDOT | I-440 / US 64 (Exit 301) to Johnston County line | Construct 2 lanes in each direction. | 9.18 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5111SW | Statewide Mobility | NHP | 2019 | 15826000 |  |  | 2018 | 128398000 |  |  | 144224000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
Wake | I-40 | NCDOT | NC 54 interchange in Raleigh. | Improve interchange. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5873 | Region C | [10 empty] | UNDER CONSTRUCTION
Wake | I-40 | NCDOT | SR 1002 (Aviation Parkway) interchange in Cary. | Improve interchange and construct auxiliary lane on I-40 westbound from SR 1002 (Aviation Parkway) to SR 3015 (Airport Boulevard). | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5506 | Statewide Mobility | [10 empty] | PROJECT COMPLETE.
Wake | I-40 | NCDOT | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5966 | Statewide Mobility | NHP, T(M) | 2029 | 430000 | 2029 | 200000 | 2032 | 73700000 |  |  | 74330000
Wake | I-40 | NCDOT | SR 3015 (Airport Boulevard) intersection in Cary/Morrisville. | Revise interchange; Construct auxiliary lanes on I-40 eastbound from I-540 to SR 3015 (Airport Boulevard) and from SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway), and construct auxiliary lane on I-40 westbound from SR 3015 (Airport Boulevard) t | 2.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5700 | Statewide Mobility | NHP, T(M) |  |  |  |  | 2020 | 51733000 |  |  | 51733000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034
Wake | I-40 / US 64 | NCDOT | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5701 | Statewide Mobility | NHP, T(M) |  |  | 2027 | 2300000 | 2027 | 163100000 |  |  | 165400000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703.
Wake | I-440 / US 1 | NCDOT | SR 2000 (Wake Forest Road) intersection in Raleigh. | Improve interchange. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5708 | Statewide Mobility | NHP | 2019 | 1736000 | 2024 | 2000000 | 2029 | 23000000 |  |  | 26736000 | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033
Wake | I-440 / US-1 | NCDOT | South of SR 1313 (Walnut Street) to north of SR 1728 (Wade Avenue) in Raleigh. | Widen from four to six lanes, improve storage at Lake Boone Trail interchange and install ramp meters. | 5.58 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2719 | Statewide Mobility | NHP | 2019 | 34749000 |  |  | 2019 | 158558000 |  |  | 193307000 | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT-OF-WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
Wake | I-540 | NCDOT | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5968 | Statewide Mobility | NHP, T(M) | 2028 | 4700000 | 2028 | 20000 | 2031 | 35700000 |  |  | 40420000
Wake | McCrimmon Parkway | NCDOT | SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway) in Morrisville. | Widen to a four lane divided facility, part on new location. | 1.42 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5828 | Division 5 | T |  |  |  |  | 2019 | 3097000 |  |  | 3097000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
Wake | NC 50 (Creedmoor Road) | NCDOT | I-540 to north of NC 98. | Widen to multi-lane divided roadway. | 5.12 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5891 | Region C | T | 2030 | 143200000 | 2030 | 2200000 | 2034 | 104200000 |  |  | 249600000
Wake | NC 54 | NCDOT | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5750 | Region C | T | 2019 | 3468000 | 2022 | 1700000 | 2027 | 33105000 | 2019 | 1620000 | 39893000 | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS
Wake | NC 54 | NCDOT | SR 1635 (Mccrimmon Parkway) intersection | Convert at-grade intersection to grade separation, including grade separation of North Carolina Railroad. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5747B | Region C | T | 2019 | 2072000 | 2024 | 620000 | 2027 | 41205000 |  |  | 43897000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE)
Wake | NC 54 (Hillsborough Street) | NCDOT | SR 1664 / SR 3074 (Blue Ridge Road) in vicinity of NC Railroad (CSX Corporation and Norfolk Southern) in Raleigh. | Construct grade separations and access road between NC 54 and SR 1664 / SR 3074. | 3 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-4437 | Division 5 | [10 empty] | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT
Wake | NC 54; SR 1635 (McCrimmon Parkway) | NCDOT | SR 1635 (McCrimmon Parkway) from west of SR 1613 (Davis Drive) to north of SR 1637 (Church Street); NC 54 at SR 1635 (McCrimmon Parkway) in Morrisville. | Widen SR 1635 and upgrade NC 54 at-grade intersection to grade separation, including grade separation. | 2 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5747 | Region C | T | [6 empty] | 2019 | 3001000 | 3001000 | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
Wake | NC 540 | NCDOT | East of SR 1152 (Holly Springs Road) to east of US 401. | Construct freeway on new location. This is a toll project. | 5.37 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2721B | Statewide Mobility | NHP, T(M) |  |  |  |  | 2019 | 63000000 |  |  | 63000000 | UNDER CONSTRUCTION
Wake | NC 540 | NCDOT | NC 55 Bypass to east of SR 1152 (Holly Springs Road). | Construct freeway on new location. This is a toll project. | 2.84 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2721A | Statewide Mobility | NHP, T(M) |  |  |  |  | 2019 | 79500000 |  |  | 79500000 | UNDER CONSTRUCTION
Wake | NC 55 | NCDOT | SR 1114 (South Main Street) to SR 1152 (New Hill Road); West Holly Springs Road | Upgrade corridor to six lane expressway. | 1.6 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0014 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 550000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44800000 |  |  | 48650000
Wake | NC 55 | NCDOT | SR 4809 (Jicarilla Lane) to NC 42 in Fuquay-Varina | Widen roadway. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-5705C | Not Funded | T | NOT FUNDED | 8170000 | NOT FUNDED | 1386000 | NOT FUNDED | 17900000 | NOT FUNDED |  | 27456000
Wake | NC 55 (Williams Street) | NCDOT | CSX Railroad bridge over NC 55 | Replace railroad bridge. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2901BA | Region C | T | 2026 | 830000 | 2026 | 140000 | 2028 | 30600000 |  |  | 31570000
Wake | NC 55 (Williams Street) | NCDOT | US 1 to north of SR 1160 (Olive Chapel Road) | Convert existing multilane to median divided section and widen remaining 2-lane sections to multilane. | 1.73 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2901B | Region C | T | 2027 | 12900000 | 2027 | 1700000 | 2030 | 40300000 |  |  | 54900000
Wake | NC 55 (Williams Street) | NCDOT | US 1 to north of SR 1160 (Olive Chapel Road) in Apex. | Widen to a multi-lane curb and gutter facility. | 2.8 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2901 | [11 empty] | PROJECTS U-2901AA AND AB COMPLETE
Wake | NC 55 Bypass | NCDOT | SR 1114 (South Main Street) intersection | Convert existing at-grade intersection to interchange. | 2 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0017 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24700000 |  |  | 55200000
Wake | NC 98 | NCDOT | SR 1907; SR 1005 (Six Forks Road) intersection | Construct intersection upgrades. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0025 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 11000000
Wake | New Route (Future NC 540) | NCDOT | Eastern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), I-40 to I-87 / US 64 / US 264 Bypass. | Construct freeway on new location. This is a toll project. | 10.8 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2829 | Statewide Mobility | T | 2025 | 1133000 | [6 empty] | 1133000
Wake | New Route (Future NC 540) | NCDOT | I 40 to south of SR 2542 (Rock Quarry Road) | Construct freeway on new location. This is a toll project. | 6.42 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2829A | Statewide Mobility | BOND R, NHP, T(M) | 2025 | 41809000 | 2025 | 3544000 | 2025 | 350563000 |  |  | 395916000 | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $125 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039
Wake | New Route (Future NC 540) | NCDOT | South of SR 2542 (Rock Quarry Road) to I-87 / US 64 / US 264 Bypass | Construct freeway on new location. This is a toll project. | 3.82 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2829B | Statewide Mobility | BOND R, NHP, T(M) | 2025 | 33806000 | 2025 | 500000 | 2025 | 525139000 |  |  | 559445000 | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $175 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039
Wake | New Route (Future NC 540) | NCDOT | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), NC 55 (South) to east of US 401 south. This is a toll project. | Freeway on new location. | 7.8 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2721 | Statewide Mobility | [10 empty] | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT
Wake | SR 1002 (Aviation Parkway) | NCDOT | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5811 | Division 5 | BGANY, T | 2026 | 13000000 | 2026 | 2100000 | 2030 | 46105000 |  |  | 61205000 | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
Wake | SR 1010 (Ten Ten Road) | NCDOT | Apex Peakwy to to SR 1306 (Schieffelin Road). | Widen to four lanes with reduced conflict intersections. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825A | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 3300000 | NOT FUNDED | 22000000 | NOT FUNDED |  | 35300000
Wake | SR 1010 (Ten Ten Road) | NCDOT | SR 4070 (Reliance Avenue) to SR 1300 (Kildaire Farm Road). | Widen to four lanes with reduced conflict intersections. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825C | Not Funded | T | NOT FUNDED | 11500000 | NOT FUNDED | 3300000 | NOT FUNDED | 59500000 | NOT FUNDED |  | 74300000
Wake | SR 1010 (Ten-Ten Road) | NCDOT | Apex Peakway in Apex to SR 1300 (Kildaire Farm Road) in Cary. | Widen to multi-lanes. | 3.3 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825 | [11 empty] | COORDINATE WITH U-6066
Wake | SR 1115 (Avent Ferry Road) | HOLLY SPRINGS | SR 1116 (Cass Holt Road) to NC 55 Bypass in Holly Springs. | Widen to multi-lanes, with intersection improvements at SR 1116 (Cass Holt Road), SR 1101 (Piney Grove-Wilbon Road) and NC 55 Bypass. | 1.02 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5889 | Division 5 | T | 2027 | 1400000 | 2028 | 500000 | 2029 | 17155000 |  |  | 19055000 | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
Wake | SR 1152 (Holly Springs Road) | NCDOT | SR 1010 (Ten-Ten Road) to SR 3977 (Cary Parkway). | Construct intersection improvements at SR 1010, SR 1379 (Penny Road), and SR 3977 (Cary Parkway). | 3.44 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6217 | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 49200000 |  |  | 68900000
Wake | SR 1632 (Louis Stephens Drive) | NCDOT | Poplar Pike Lane in Morrisville to SR 2153 (Little Drive) in Research Triangle Park. | Construct roadway on new location. | 0.55 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5827 | Division 5 | T | 2020 | 1340000 |  |  | 2020 | 7699000 | 2019 | 1231000 | 10270000 | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Wake | SR 1635 (McCrimmon Parkway) | NCDOT | SR 1613 (Davis Drive) to north of SR 1637 (Church Street) | Widen to four lane divided facility. | 1.07 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5747A | Division 5 | T | 2021 | 5000000 | 2021 | 500000 | 2027 | 32010000 |  |  | 37510000 | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $10,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE)
Wake | SR 2000 (Falls Of Neuse Road) | NCDOT | I-540 to SR 2006 (Durant Road). | Construct additional lanes. | 0.89 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5826 | Division 5 | T | 2024 | 280000 |  |  | 2023 | 30325000 |  |  | 30605000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
Wake | Town of Cary | NCDOT | Town of Cary | Upgrade existing infrastructure, install new fiber, controllers, signals, connected vehicle technology and other equipment as necessary. | 7.94 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0010 | Region C | L, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10000000 |  |  | 10000000
Wake | US 1 | NCDOT | I-540 to north of SR 2006 (Durant Road) | Upgrade roadway to controlled access facility. | 1.63 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307A | Statewide Mobility | NHP | 2026 | 128500000 | 2026 | 13400000 | 2031 | 338650000 |  |  | 480550000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047.
Wake | US 1 | NCDOT | North of SR 2006 (Durant Road) in Raleigh to north of SR 2045 (Burlington Mills Road) in Wake Forest | Upgrade roadway to controlled access facility. | 2.11 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307B | Statewide Mobility | NHP | 2026 | 119500000 | 2026 | 8200000 | 2031 | 191750000 |  |  | 319450000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2033-2047.
Wake | US 1 | NCDOT | North of SR 2045 (Burlington Mills Road) to south of NC 98 Business | Upgrade roadway to controlled access facility. | 3.83 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307C | Statewide Mobility | NHP | 2028 | 37700000 | 2028 | 6400000 | 2033 | 167250000 |  |  | 211350000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2035-2049.
Wake | US 1 | NCDOT | South of NC 98 Business to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to controlled access facility. | 2.33 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307D | Statewide Mobility | NHP | 2028 | 72000000 | 2028 | 10100000 | 2033 | 174850000 |  |  | 256950000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2035-2049.
Wake | US 1 | NCDOT | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0032 | Region C | T | 2027 | 21300000 | 2027 | 3300000 | 2030 | 20600000 |  |  | 45200000
Wake | US 1 | NCDOT | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825B | Region C | T | 2027 | 30300000 | 2027 | 2300000 | 2030 | 66900000 |  |  | 99500000
Wake | US 1 (Capital Boulevard) | NCDOT | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to controlled access facility | 10 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307 | Statewide Mobility
Wake | US 401 | NCDOT | NC 55 / NC 42 intersection in Fuquay-Varina. | Construct intersection improvements. Project will include improvements to NC 55 intersection with NC 42, and construction of connector from NC 55 to SR 5056 (Judd Parkway). | 3 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5751 | Region C | T | 2028 | 59900000 | 2028 | 3300000 | 2031 | 113300000 |  |  | 176500000
Wake | US 401 | NCDOT | South of SR 1006 (Old Stage Road) to south of SR 2538 (Mechanical Boulevard) / Garner Station Boulevard in Garner. | Construct reduced conflict intersections. | 1.05 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5302 | Region C | T | 2019 | 9931000 |  |  | 2026 | 27500000 | 2019 | 1801000 | 39232000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
Wake | US 401 | NCDOT | SR 1010 (Ten-Ten Road) intersection in Fuquay-Varina. | Upgrade existing signalized intersection to square-loop interchange. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6112 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30480000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6720000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33600000 |  |  | 70800000 | COORDINATE WITH R-2721 AND U-5746
Wake | US 401 | NCDOT | SR 1370 (Tryon Road) intersection in Raleigh | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0012 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 11000000
Wake | US 401 | NCDOT | SR 1467 / SR 2839 (Allen Street) to SR 1010 (Ten-Ten road). | Construct additional lanes. | 0.81 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5746 | Region C | T | 2022 | 2938000 | 2022 | 1310000 | 2025 | 7410000 |  |  | 11658000 | UNDER CONSTRUCTION
Wake | US 401 | NCDOT | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5748 | Region C | T | 2019 | 6840000 | 2021 | 212000 | 2024 | 22500000 | 2019 | 1921000 | 31473000 | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE).
Wake | US 401 | NCDOT | SR 5056 / SR 2768 (Judd Parkway) to NC 55 / NC 42 (Five Points inersection) | Construct access management improvements. | 1.18 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0024 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 470000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 |  |  | 9770000
Wake | US 401 / US 70 Business | NCDOT | SR 1370 (Tryon Road) intersection in Raleigh | Improve intersection signals and merging between Tryon Road and Mechanical Boulevard. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0009 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5500000 |  |  | 7500000
Wake | US 64 | NCDOT | CSX Railroad bridge over US 64. | Replace railroad bridge. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5301A | Statewide Mobility | NHP | 2027 | 5600000 | 2027 | 104000 | 2029 | 32300000 |  |  | 38004000
Wake | US 64 | NCDOT | West of SR 1308 (Laura Duncan Road) to US 1 in Apex and Cary. | Upgrade and improve corridor. | 3.2 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5301 | Statewide Mobility | NHP, T(M) | 2026 | 93000000 | 2026 | 4400000 | 2031 | 207100000 |  |  | 304500000
Wake | US 70 (Glenwood Avenue) | NCDOT | NC 50 (Creedmoor Road) intersection | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0016 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19800000 |  |  | 25900000
Wake | US 70 Business | NCDOT | Raynor Road and Guy Road intersection in Raleigh | Convert intersections to reduced conflict intersections. | 1.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0007 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1340000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 |  |  | 17840000
Wake | Various | NCDOT | Apex townwide signal system. | Upgrade existing infrastructure and install new fiber, controllers, signals, and other equipment as necessary. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6117 | Division 5 | BGANY, T |  |  | 2027 | 360000 | 2028 | 7100000 |  |  | 7460000 | BUILD NC BOND FUNDING: $3,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY2028/ YR 8 SALE).
Wake | Various | NCDOT | Division 5 | Provide communication and cameras to improve signal timing. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0005 | Region C | T |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15596000 |  |  | 16796000
Wake | Various | NCDOT | Locations in Garner | Improve citywide signal system in Garner. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6194 | Division 5 | BGANY, T(M) |  |  | 2030 | 480000 | 2031 | 6800000 |  |  | 7280000
Wake | Various | NCDOT | Locations in the Town of Morrisville. | Construct townwide ITS / signal system. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5967 | Region C | BGANY, T |  |  | 2027 | 33000 | 2028 | 953000 |  |  | 986000
Wake | Various | NCDOT | Raleigh citywide signal system. | Upgrade software for existing ITS system. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6119 | Division 5 | BGANY, T(M) |  |  |  |  | 2030 | 5400000 |  |  | 5400000
Wake | Various | NCDOT | Routes in the Town of Fuquay-Varina | Construct townwide ITS / signal system. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6022 | Region C | BGANY, T(M) |  |  | 2022 | 451000 | 2023 | 4092000 |  |  | 4543000 | UNDER CONSTRUCTION
Wake | Various | NCDOT | Routes in the Town of Knightdale | Construct townwide ITS / signal system. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6026 | Division 5 | BGANY, T(M) |  |  | 2022 | 450000 | 2023 | 2320000 |  |  | 2770000 | FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION. UNDER CONSTRUCTION
Wake | Various | NCDOT | Routes in the Town of Wake Forest | Construct townwide ITS / signal system. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6023 | Division 5 | BGANY, T(M) |  |  | 2022 | 250000 | 2023 | 4176000 |  |  | 4426000 | UNDER CONSTRUCTION
Wake | SR 2703 (New Bethel Church Road) | NCDOT | Bridge 910248 over Mahler's Creek in Garner. | Replace bridge. | 0.25 | Highway | Transition | 5 | Capital Area MPO | B-5237 | Division 5 | T |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
Wake | Capital Area Transit | CAPITAL AREA TRANSIT | Systemwide | Purchase ADA expansion bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5202 | Public Transit | 5307, 5339, L | [6 empty] | 2020 | 2400000 | 2400000 | FUNDS AUTHORIZED IN PROGRESS
Wake | Capital Area Transit | CAPITAL AREA TRANSIT | Systemwide | Safety and security minimum 1 % set aside |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TS-5104 | Public Transit | 5307, L | [6 empty] | 2021 | 1292000 | 1292000 | FUNDS AUTHORIZED IN PROGRESS
Wake | Cary Transit | CARY TRANSIT/C-TRAN | Systemwide | Funding for downtown Cary multi modal facility. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5305 | Public Transit | L |  |  |  |  | 2022 | 109200000 |  |  | 109200000
Wake | GoRaleigh |  | Systemwide. | Routine capital - shop equipment, spare parts, engines, farebox, service/support vehicles, computer hardware/sotware. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0044 | Public Transit | 5307, L | [6 empty] | 2025 | 1350000 | 1350000
Wake | GoRaleigh | GO RALEIGH | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TP-5160 | Public Transit
Wake | GoRaleigh | GO RALEIGH | Systemwide | Project development and final design of bus rapid transit in Wake Transit Western corridor (Downtown Raleigh to Downtown Cary). |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0006 | Public Transit | L |  |  |  |  | 2022 | 45168000 | 2022 | 1500000 | 46668000
Wake | GoRaleigh | GORALEIGH | Systemwide | 5310 Administration and Capital. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TQ-9037 | Public Transit | 5310, L | [6 empty] | 2021 | 17338000 | 17338000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoRaleigh | GORALEIGH | Systemwide | Build park and ride facility at Gorman street at I-40 in Raleigh. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0023 | Public Transit | L |  |  |  |  | 2027 | 1614000 | 2025 | 1432000 | 3046000
Wake | GoRaleigh | GORALEIGH | Systemwide | Construct bus stop improvements. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5304 | Public Transit | L | [6 empty] | 2022 | 6546000 | 6546000
Wake | GoRaleigh | GORALEIGH | Systemwide | Project development and final design of bus rapid transit in Wake transit Southern corridor ( Downtown Raleigh to Downtown Garner). |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0013 | Public Transit | L |  |  |  |  | 2022 | 40947000 | 2022 | 1500000 | 42447000
Wake | GoRaleigh | GORALEIGH | Systemwide | Purchase replacement bus and upgrade bus facilities. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-4903 | Public Transit | 5339, L | [6 empty] | 2021 | 32834000 | 32834000
Wake | GoRaleigh | GORALEIGH | Systemwide | Purchase replacement bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5140 | Public Transit | 5307, CPF, L, S | [6 empty] | 2021 | 6505000 | 6505000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoRaleigh | GORALEIGH | Various locations | Construct capital projects (passenger amenities, pedestrian connections, facility maintenance, upgrade and upkeeps etc). |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0015 | Public Transit | 5307, L | [6 empty] | 2021 | 12081000 | 12081000
Wake | GoRaleigh | GORALEIGH | Various locations | Construct coordinated ADA Facility. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5308 | Public Transit | 5339, DP, L | 2022 | 2750000 |  |  | 2023 | 79935000 | 2022 | 4000000 | 86685000 | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH.
Wake | GoRaleigh | GORALEIGH | Various locations | Construct new transit center at midtown area of Raleigh. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5318 | Public Transit | L | 2024 | 2249000 |  |  | 2025 | 2989000 | 2024 | 547000 | 5785000
Wake | GoRaleigh | GORALEIGH | Various locations | Funding for expansion and maintenance facilities. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TM-0039 | Public Transit | 5307, L |  |  |  |  | 2022 | 28000000 |  |  | 28000000
Wake | GoRaleigh | GORALEIGH | Various locations | Update transit center at the Crabtree valley mall. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5319 | Public Transit | L |  |  |  |  | 2022 | 648000 |  |  | 648000
Wake | GoRaleigh | GORALEIGH | Various locations | Update transit center at the Triangle Towne Center. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5320 | Public Transit | L |  |  |  |  | 2022 | 7527000 |  |  | 7527000
Wake | GoTriangle |  | Systemwide | Improve ten bus stop for route ZWX in Eastern Wake county. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0036 | Public Transit | CPF, L | [6 empty] | 2025 | 999000 | 999000
Wake | GoTriangle |  | Systemwide | Replace bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0037 | Public Transit | CPF, L | [6 empty] | 2025 | 2500000 | 2500000
Wake | GoTriangle |  | Systemwide | Replace bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0038 | Public Transit | CPF, L | [6 empty] | 2025 | 1250000 | 1250000
Wake | GoTriangle | GO TRIANGLE | Systemwide | Expand existing garage facility in Morrisville. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5285 | Public Transit | 5339(b), L |  |  |  |  | 2025 | 815000 | 2024 | 120000 | 935000 | IN PROGRESS
Wake | GoTriangle | GOTRIANGLE | Systemwide | Purchase bus for service expansion. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-4818A | Public Transit | 5307, 5339, L | [6 empty] | 2025 | 5541000 | 5541000
Wake | GoTriangle | GOTRIANGLE | Systemwide | Purchase expansion bus. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5123A | Public Transit | 5307, 5339, L, S | [6 empty] | 2025 | 3378000 | 3378000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoTriangle | GOTRIANGLE | Various locations | Construct improvements at existing bus stops. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0016 | Public Transit | 5307, L | 2026 | 12000 |  |  | 2026 | 550000 | 2025 | 110000 | 672000
Wake | GoTriangle | GOTRIANGLE | Various locations | Construct improvements at existing bus stops. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0017 | Public Transit | 5307, L | 2026 | 14000 |  |  | 2026 | 330000 | 2025 | 130000 | 474000
Wake | GoTriangle | GOTRIANGLE | Various locations | Construct improvements at existing park and ride. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5314 | Public Transit | L | [6 empty] | 2022 | 1105000 | 1105000
Wake | GoTriangle | GOTRIANGLE | Various locations | Construct new park and ride at Hillsborough Street and I-440 In Raleigh. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5315 | Public Transit | L |  |  |  |  | 2026 | 5200000 | 2025 | 2220000 | 7420000
Wake | New Bern Avenue | GO RALEIGH | New Bern Avenue. Downtown to New Hope Road | Betterment funding to construct bus rapid transit. | 3.54 | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TP-5160B | Division 5 | L |  |  |  |  | 2023 | 1628000 |  |  | 1628000
Wake | New Bern Avenue | GO RALEIGH | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TP-5160A | Division 5 | 5309, ARP, FUZ, L | 2021 | 3086000 |  |  | 2021 | 68507000 | 2020 | 20841000 | 92434000
Wake | GoCary | GOCARY | Various locations | Purchase and install new radios for the GOCARY bus system, Including equipment for a base console operation for a dispatch. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0059 | Division 5 | BGDA, L(M) | [6 empty] | 2025 | 339000 | 339000
Wake | GoRaleigh | GO RALEIGH TRANSIT | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TD-5309 | Division 5 | BGDA, L | [6 empty] | 2020 | 752000 | 752000
Wake | GoRaleigh | GO RALEIGH TRANSIT | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TD-5309A | Division 5 | BGDA, L | 2020 | 250000 | [6 empty] | 250000
Wake | GoRaleigh | GO RALEIGH TRANSIT | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TD-5309B | Division 5 | BGDA, L |  |  |  |  | 2020 | 1500000 |  |  | 1500000
Wake | GoRaleigh | GORALEIGH | Systemwide | Raleigh Union Station inter-city/commuter rail park and ride. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0020 | Public Transit | CMAQ, L(M), S(M) | [6 empty] | 2025 | 6250000 | 6250000 | S(M) REPRESENTS STATE RAIL FUNDS.
Wake | GoRaleigh | GORALEIGH | Various locations | Develop enhanced transfer points throughout Go Raleigh system in location with high ridership (75 + Boarding per day). |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TG-6816 | Division 5 | BGDA, L | [6 empty] | 2021 | 2371000 | 2371000
Wake | GoTriangle | GOTRIANGLE | Route 305 | Add a landing pad at 24 stops between existing sidewalk and back of curb. Trash can pads may be included as warranted. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0053 | Division 5 | BGDA, L |  |  |  |  | 2024 | 240000 | 2024 | 100000 | 340000
Wake | GoTriangle | GOTRIANGLE | Systemwide | Purchase and install new amenities at 13 bus stop locations along routes in Wake County. Upgrades include shelters, bench, or some combinations. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TG-6815 | Division 5 | 5307, BGDA, L | [6 empty] | 2021 | 1815000 | 1815000
Wake | GoTriangle | GOTRIANGLE | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0046 | Division 5 | 5307, L | 2026 | 15000 |  |  | 2026 | 250000 | 2025 | 60000 | 325000
Wake | GoTriangle | GOTRIANGLE | Various locations | Construct downtown Apex transfer points. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0011 | Public Transit | 5307, L | 2026 | 18000 |  |  | 2026 | 242000 | 2025 | 64000 | 324000
Wake | GoTriangle | GOTRIANGLE | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0058 | Division 5 | L(M), TADA | 2025 | 27000 |  |  | 2025 | 405000 | 2025 | 108000 | 540000
Wake | GoTriangle | GOTRIANGLE | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0057 | Division 5 | L(M), TADA | 2025 | 18000 |  |  | 2025 | 438000 | 2025 | 72000 | 528000
Wake | Capital Area Transit | CAPITAL AREA TRANSIT | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-5128 | Public Transit | 5307, L, SMAP | [6 empty] | 2021 | 152980000 | 152980000 | FUNDS AUTHORIZED IN PROGRESS
Wake | Cary Transit | CARY TRANSIT/C-TRAN | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-5129 | Public Transit | 5307, L, SMAP | [6 empty] | 2021 | 19401000 | 19401000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoRaleigh | GORALEIGH | Town of Wake Forest reverse circulator | Funding for operating assistance |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-6168 | Public Transit | L | [6 empty] | 2021 | 2283000 | 2283000
Wake | GoTriangle | GOTRIANGLE | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-5131 | Public Transit | L, SMAP | [6 empty] | 2021 | 37855000 | 37855000 | FUNDS AUTHORIZED IN PROGRESS
Wake | Cary Transit | CARY TRANSIT/C-TRAN | Systemwide | Funding for contracting costs. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TG-4935A | Public Transit | 5307, 5309, 5339, L | [6 empty] | 2023 | 18180000 | 18180000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoRaleigh | GORALEIGH | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TG-4729B | Public Transit | 5307, L | [6 empty] | 2021 | 32600000 | 32600000
Wake | GoRaleigh | GORALEIGH | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TG-4792B | Public Transit | 5307, L | [6 empty] | 2021 | 37600000 | 37600000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoTriangle | GOTRIANGLE | Various locations | Funding for operational assistance of Morrisville node based smart shuttle. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TM-0035 | Public Transit | L | [6 empty] | 2021 | 3621000 | 3621000
Wake | Wake Coordinated Transportation Service | WAKE COORDINATED TRANSIT SERVICE | Various locations | Funding for Transit service operating assistance. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TN-6116 | Public Transit | 5307, L | [6 empty] | 2021 | 8002000 | 8002000
Wake | Capital Area Transit | CAPITAL AREA TRANSIT | Various locations | Funding for planning assistance -5303 |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TP-5100A | Public Transit | 5303, L, S | [6 empty] | 2021 | 4404000 | 4404000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoRaleigh | GORALEIGH | Systemwide | Gotriangle Wake county bus plan update. |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TU-0007 | Public Transit | L | [6 empty] | 2021 | 860000 | 860000
Wake | GoRaleigh | GORALEIGH | Systemwide | Project development and final design on bus rapid transit in Wake transit plan Northern corridor. |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TL-0007 | Public Transit | L | [6 empty] | 2020 | 15540000 | 15540000
Wake | GoRaleigh | GORALEIGH | Various locations | Funding for planning assistance -5307 |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TP-5100B | Public Transit | 5307, L, S | [6 empty] | 2021 | 11326000 | 11326000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoTriangle | GOTRIANGLE | Systemwide | Funding 5329 State safety and oversight. |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TU-0006 | Public Transit | CMAQ, L | [6 empty] | 2021 | 740000 | 740000
Wake | GoTriangle | GOTRIANGLE | Systemwide | Funding for planning assistance |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TP-4732B | Public Transit | 5307, L, S | [6 empty] | 2020 | 6642000 | 6642000 | FUNDS AUTHORIZED IN PROGRESS
Wake | GoRaleigh | GORALEIGH | Various locations | Funding for capital projects. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-0015 | Public Transit | 5307, L | [6 empty] | 2021 | 5560000 | 5560000
Wake | GoRaleigh | GORALEIGH | Various locations | Funding for preventative maintenance. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-0013 | Public Transit | 5307, L | [6 empty] | 2021 | 26700000 | 26700000
Wake | GoTriangle | GOTRIANGLE | Systemwide. | Construct 11 bus stops. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-0027 | Public Transit | CPF, L | [6 empty] | 2025 | 1136000 | 1136000
Wake | GoCary | CARY TRANSIT / C-TRAN | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5264B | Division 5 | 5307, 5339(b), DP, L, T |  |  |  |  | 2023 | 76442000 | 2022 | 2500000 | 78942000 | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023
Wake | GoRaleigh | GO RALEIGH TRANSIT | South Wilmington Street at Pecan Road in Raleigh | Construct off street transfer facility. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5272 | Division 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
Wake | GoRaleigh | GO RALEIGH TRANSIT | US 64 Business at New Hope Road intersection | Funding to construct transit facility on New Hope Road in Raleigh. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-4912 | Division 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
Wake | GoTriangle | GO TRIANGLE | Union Station in Raleigh | Construct bus component. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5269 | Division 5 | 5339(b), DP, L, O, T |  |  |  |  | 2020 | 54185000 | 2024 | 130000 | 54315000 | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH
Wake | Various | GO RALEIGH | Triangle Town Center | Construct transit center and park and ride facility. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5307 | Division 5 | L, O, T | 2027 | 1500000 |  |  | 2028 | 6658000 |  |  | 8158000
Wake | Various | GO RALEIGH | Various locations | Funding to establish bus rapid transit service from Cary to Raleigh. Construct infrastructures, purchase vehicles | 9.19 | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TO-6166B | Region C | 5309, L(M), T |  |  |  |  | 2027 | 359990000 | 2026 | 35000000 | 394990000
Wake | Various | GO RALEIGH | Various locations | Funding to establish bus rapid transit service from Research Triangle Park to Cary. Construct infrastructures, purchase vehicles | 3.86 | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TO-6166A | Region C | T | 2028 | 2000000 | 2028 | 1000000 | 2030 | 27000000 |  |  | 30000000
Wake | Various | GO RALEIGH | Various locations | Funding to construct infrastructure, purchase vehicles and establish service for Bus rapid Transit from Raleigh to Garner | 5.93 | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TO-6166C | Region C | 5309, L(M), T |  |  |  |  | 2027 | 226642000 |  |  | 226642000
Wake | CXS S / SA Line | NCDOT | Raleigh to NC 98. | Acquire right of way, upgrade existing track, and construct new track. |  | Rail | Other | 5 | Capital Area MPO | P-5753A | Statewide Mobility
Wake | CXS S Line | NCDOT | Highwoods Boulevard Intersection | Construct grade separation. |  | Rail | Other | 5 | Capital Area MPO | P-5753AG | Statewide Mobility
Wake | CXS S Line | NCDOT | Ligon Mill Road; Seawell Drive; Friendship Chapel Road | Construct grade separation at Ligon Mill Road; Construct roadway improvements at Seawell Drive and Friendship Chapel Road. |  | Rail | Other | 5 | Capital Area MPO | P-5753AI
Wake | CXS S Line | NCDOT | Raleigh Union Station to NC 98. | Improve rail-line. | 28.66 | Rail | Other | 5 | Capital Area MPO | P-5753AA | Statewide Mobility
Wake | CXS S Line | NCDOT | Various | Construct Hargett Street, SR 5908 (Morgan Street), and US 401 (Capital Boulevard) roadway improvements and pedestrian overpass at Jones Street. |  | Rail | Other | 5 | Capital Area MPO | P-5753AE | Statewide Mobility
Wake | CXS S Line | NCDOT | Various | Construct SR 2013 (Gresham Lake Road) and SR 2044 (Ligon Mill Road) grade separations and roadway improvements at SR 2046 (Seawell Drive) and Friendship Chapel Road. |  | Rail | Other | 5 | Capital Area MPO | P-5753AH | Statewide Mobility | CMAQ | 2027 | 26920000 | 2027 | 580000 | 2030 | 21000000 | 2026 | 1500000 | 50000000
Wake | CXS S Line | NCDOT | Whitaker Mill Road | Improve roadway. |  | Rail | Other | 5 | Capital Area MPO | P-5753AF | Statewide Mobility
Wake | Piedmont Corridor | NCDOT | Capital Yard Phase 1 Improvements | Extend Tracks 1 and 2, perform major work on Track 3. |  | Rail | Other | 5 | Capital Area MPO | P-2918H | [11 empty] | IN PROGRESS
Wake | NC Railroad | NCDOT | Raleigh Union Station | Improve track. |  | Rail | Pre-STI (Historic) | 5 | Capital Area MPO | P-5500C | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Wake | NC Railroad | NCDOT | Raleigh Union Station | Station site work. |  | Rail | Pre-STI (Historic) | 5 | Capital Area MPO | P-5500B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Wake | Raleigh Union Station | NCDOT | North Carolina Railroad | Construct Raleigh train station and associated rail track and siding improvements to increase passenger and freight capacity. |  | Rail | Pre-STI (Historic) | 5 | Capital Area MPO | P-5500 | Pre-STI (Transition) | [10 empty] | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION
Wake | Carolina Coastal Railway | NCDOT | SR 2513 (Fayetteville Street) intersection in Knightdale | Close existing at-grade crossing (#465681P). |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Capital Area MPO | Y-4805F | Division 5 | RR |  |  |  |  | 2025 | 3000000 |  |  | 3000000
Wake | SR 1108 (Wake Chapel Road) | NCDOT | Raleigh Fayetville Railroad Crossing 465825S. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 5 | Capital Area MPO | RX-2405A | Division 5 | RR |  |  |  |  | 2031 | 650000 | 2031 | 65000 | 715000
Wake | CSX | NCDOT | Crossing 630601X at SR 2006 (Durant Road) in Raleigh. | Construct grade separation. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5720 | Region C | T |  |  |  |  | 2024 | 21910000 |  |  | 21910000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307
Wake | CSX | NCDOT | Crossing 630607N at New Hope Church Road in Raleigh. | Construct grade separation. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5715 | Region C | T |  |  |  |  | 2025 | 22780000 |  |  | 22780000 | RIGHT-OF-WAY IN PROGRESS
Wake | CSX | NCDOT | Crossing 643351A at SR 1415 (NE Maynard Road) in Cary. | Construct grade separation. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5718 | Region C | O, T | 2028 | 37300000 | 2028 | 4500000 | 2031 | 42001000 |  |  | 83801000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734.
Wake | CSX S Line | NCDOT | SR 2052 (Rogers Road Extension) crossing (633905Y) in Wake Forest. | Construct grade separation. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5707 | Region C | T | 2025 | 7000000 |  |  | 2026 | 39800000 |  |  | 46800000 | RIGHT-OF-WAY IN PROGRESS
Wake | CSX S Line | NCDOT | SR 2108 (Millbrook Road) in Raleigh. | Construct grade separation and close crossing 630605A. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5737 | Statewide Mobility | DP, T | 2022 | 6111000 | 2022 | 1228000 | 2027 | 26400000 |  |  | 33739000 | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT.
Wake | North Carolina Railroad / Norfolk Southern H Line | NCDOT | SR 1655 (Trinity Road) crossing in Cary. | Construct grade separation and close crossing 630657S. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5734 | Statewide Mobility | O, T | 2028 | 23400000 | 2028 | 960000 | 2031 | 29600000 |  |  | 53960000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718.
Wake | North Carolina Railroad; Norfolk Southern H Line | NCDOT | Beryl Road crossing in Raleigh. | Extend Beryl Road to Royal Avenue, and close crossing 630647L. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5736 | Statewide Mobility | O, T | 2030 | 3700000 | 2030 | 1700000 | 2033 | 5400000 |  |  | 10800000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
Wake | CSX S-Line | NCDOT | Raleigh Union Station | Improve track and signals. |  | Rail | Transition | 5 | Capital Area MPO | P-5500A | [11 empty] | DELETED - WORK TO BE ACCOMPLISHED UNDER P-5005D.
Wake, Durham | I-40 | NCDOT | East of NC 147 to SR 1728 (Wade Avenue). | Rehabilitate pavement. | 9.37 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Triangle West TPO | I-5995 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2026 | 54600000 |  |  | 54600000
Wake, Durham | I-540 | NCDOT | I-40 in Durham to US 1 in Raleigh. | Rehabilitate pavement and bridge preservation. | 16.34 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Triangle West TPO | I-6000 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2029 | 7610000 |  |  | 7610000 | COORDINATE WITH I-5998 AND I-5999
Wake, Durham | I-540 | NCDOT | I-40 in Durham to US 70 in Raleigh. | Rehabilitate pavement. | 4.25 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Triangle West TPO | I-5998 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2027 | 24900000 |  |  | 24900000 | COORDINATE WITH I-5999 AND I-6000
Wake, Durham | Various | NCDOT | Routes in Division 5 | Improve rumble stripes, guardrail, safety, and lighting. |  | Highway | Safety | 5 | Capital Area MPO, Triangle West TPO | W-5205DIV | Division 5
Wake, Durham | US 70 (Glenwood Avenue) | NCDOT | West of SR 3067 (T.W. Alexander Drive) to I-540 in Raleigh. | Upgrade roadway to improve capacity, safety and traffic operations including interchanges at various locations. | 1.26 | Highway | STI (Prioritization) | 5 | Capital Area MPO, Triangle West TPO | U-5518 | Statewide Mobility | NHP, T(M) | 2030 | 148600000 | 2030 | 21000000 | 2030 | 230000000 |  |  | 399600000 | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT
Wake, Durham, Orange | Central Pines Regional Council |  | - | Transportation demand management program for organizations. |  | Highway | NCDOT Selected (Other Selection Process) | 5, 7 | Capital Area MPO, Triangle West TPO | HN-0026 | Exempt
Wake, Durham, Orange | GoTriangle | GOTRIANGLE | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5, 7 | Capital Area MPO, Triangle West TPO | TG-4821B | Public Transit | 5307, 5339, L | [6 empty] | 2024 | 26745000 | 26745000 | FUNDS AUTHORIZED IN PROGRESS
Wake, Franklin | I-87 / US 64 (Future I-87) / US 264 (Future I-587) | NCDOT | SR 1003 (Rolesville Road) to Nash County line. | Rehabilitate pavement. | 13.38 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Kerr-Tar RPO | I-6001 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2026 | 39400000 |  |  | 39400000
Wake, Franklin | Various | NCDOT | Routes in Wake and Franklin counties | Install experimental pavement markings to evaluate wet retroreflectivity. |  | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | HS-2405BA | Division 5 | HSIP |  |  |  |  | 2026 | 2925000 |  |  | 2925000
Wake, Franklin | CXS S Line | NCDOT | NC 98 to Franklinton | Improve rail-line. | 16.88 | Rail | Other | 5 | Capital Area MPO | P-5753BA | Statewide Mobility
Wake, Franklin, Granville | Various | NCDOT | US 401 in Franklin County. NC 42 in Wake County. NC 56 in Franklin and Granville Counties. NC 96 in Wake and Granville Counties. SR 1006 in Wake County. NC 50 in Wake and Granville Counties. | Install long-life pavement markings. |  | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | HS-2405C | Region C | HSIP, T(M) |  |  |  |  | 2025 | 1315000 |  |  | 1315000 | UNDER CONSTRUCTION
Wake, Franklin, Vance | CXS S Line | NCDOT | NC 98 to Franklinton |  |  | Rail | Other | 5 | Capital Area MPO, Kerr-Tar RPO | P-5753B | Statewide Mobility
Wake, Franklin, Warren | Various | NCDOT | Secondary routes in Wake, Warren, and Franklin Counties. | Install long-life pavement markings. |  | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | W-5805F | Division 5 | HSIP, T(M) |  |  |  |  | 2021 | 2553000 |  |  | 2553000 | COMPLETE
Wake, Harnett | Various | NCDOT | SR 1119 (Buckhorn Duncan Road) from Harnett County line to SR 1116 (Cass Holt Road); SR 1371/SR 1375 (Lake Wheeler Road) from SR 1009 (Tryon Road) to SR 5411 (Lakewind Court); SE 14003 (Cokesbury Road) from Wake County line to NC 42 in Harnett County. | Install 6-inch edgeline pavement marking. | 4.9 | Highway | Safety | 5, 6 | Capital Area MPO | HS-2405AU | Division 5, 6 | HSIP |  |  |  |  | 2026 | 300000 |  |  | 300000
Wake, Harnett | NC 55 | NCDOT | NC 210 to SR 4809 (Jicarilla Lane). | Widen to multi-lanes, partially on new location. | 4.99 | Highway | STI (Prioritization) | 5, 6 | Capital Area MPO | R-5705B | Region C | T | 2021 | 35171000 | 2021 | 1300000 | 2023 | 70722000 |  |  | 107193000 | UNDER CONSTRUCTION.
Wake, Iredell, Mecklenburg, Rowan, Cleveland, Union, Cabarrus, Gaston, Johnston, Durham, Lincoln, Franklin, Orange, Chatham, Granville, Harnett | Statewide Traffic Operations | NCDOT | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management in the Triangle and Metrolina Areas. |  | Highway | Other | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Triangle West TPO | HO-0010A | Statewide Mobility | CRPANY, HF(M) | [6 empty] | 2023 | 4000000 | 4000000
Wake, Johnston | I-40 | NCDOT | I-440 / US 64 (Exit 301) to NC 42 (Exit 312). | Add two general purpose lanes in each direction. | 10.71 | Highway | STI (Prioritization) | 4, 5 | Capital Area MPO | I-5111 | [11 empty] | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK 2019-2033.
Wake, Johnston | New Route (Future NC 540) | NCDOT | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), east of US 401 to I-40. This is a toll project. | Construct freeway on new location. | 8.64 | Highway | STI (Prioritization) | 4, 5 | Capital Area MPO | R-2828 | Statewide Mobility | NHP, T(M) |  |  |  |  | 2019 | 135750000 |  |  | 135750000 | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT.
Wake, Johnston | GoRaleigh | GO RALEIGH | Various locations | Construct Infrastructure for rapid bus transit from Research Triangle Park to Clayton | 33.93 | Public Transportation (Transit) | STI (Prioritization) | 4, 5 | Capital Area MPO | TO-6166
Wake, Johnston, Franklin, Granville | Various | NCDOT | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Highway | Other | 4, 5 | Capital Area MPO | C-5604 | Exempt | BGDA, CMAQ, L(M) | 2020 | 1188000 |  |  | 2020 | 23622000 | 2020 | 4081000 | 28891000 | IN PROGRESS
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Capital Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Bike & Ped | Locally Selected | 4, 5, 6 | Capital Area MPO | U-5530 | Division 4, 5, 6 | BGDA, L(M), TADA |  |  |  |  | 2020 | 3500000 |  |  | 3500000
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Locations in the Capital Area MPO | Unallocated Transportation Alternatives Program Funds. |  | Bike & Ped | Locally Selected | 4, 5, 6 | Capital Area MPO | U-6218 | Division 4, 5, 6 | TADA |  |  |  |  | 2024 | 26579000 |  |  | 26579000
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Locations in the Capital Area MPO | Pedestrian, bicycle, and transit projects in the Capital Area Metropolitan Planning Organization (CAMPO). |  | Bike & Ped | Other | 4, 5, 6 | Capital Area MPO | EL-5100 | Division 4, 5, 6
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Capital Area Metropolitan Metropolitan Planning Organization (CAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | U-4735 | Division 4, 5, 6 | BGANY, BGDA |  |  |  |  | 2024 | 162642000 |  |  | 162642000
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Capital Area Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | HL-0105 | Exempt | CRPDA, L(M) |  |  |  |  | 2024 | 6008000 |  |  | 6008000
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Capital Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | U-4850 | Division 4, 5, 6 | BGDA, L(M) | [6 empty] | 2022 | 20336000 | 20336000 | FORMERLY U-9999B - IN PROGRESS
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Locations in Capital Area MPO (CAMPO). | Construct intersection improvements. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | HL-0008 | Exempt | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
Wake, Johnston, Franklin, Granville, Harnett | Various | NCDOT | Locations in Divisions 4, 5, and 6. | Operational improvements for safety and congestion mitigation. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | U-5118 | Division 4, 5, 6 | BGDA, L(M) |  |  |  |  | 2020 | 4477000 |  |  | 4477000 | UNDER CONSTRUCTION. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. $24,867 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP.
Wake, Lee, Vance | CSX S-LINE | CSX S-LINE | Sanford to Henderson | Transit oriented planning |  | Public Transportation (Transit) | Planning | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | TU-0004 | Public Transit | FED, L, S | [6 empty] | 2021 | 1505000 | 1505000 | UNDERWAY. "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS
Warren | NC 903 | NCDOT | NC 903 causeway on Eatons Ferry Bridge over Lake Gaston. | Upgrade guardrail. | 0.85 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005B | Region C | HSIP, T(M) |  |  |  |  | 2021 | 130000 |  |  | 130000 | UNDER CONSTRUCTION
Warren | US 1 / US 158 | NCDOT | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005O | Region C | HSIP, T(M) | 2025 | 31000 | 2025 | 80000 | 2026 | 424000 |  |  | 535000 | RIGHT-OF-WAY IN PROGRESS
Warren | I-85 | NCDOT | North of SR 1237 (Manson Drewry Road) to Virginia State line. | Rehabilitate pavement and upgrade signs. | 7.72 | Highway | Transition | 5 | Kerr-Tar RPO | I-0914BB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Warren | CXS S Line | NCDOT | Norlina | Construct roadway improvements. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753DD | Statewide Mobility
Warren | CXS S Line | NCDOT | Ridgeway to Paschall |  |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753D | Statewide Mobility
Warren | CXS S Line | NCDOT | Ridgeway to VA State Line | Improve rail-line. | 13.51 | Rail | Other | 5 | Kerr-Tar RPO | P-5753DA | Statewide Mobility
Warren | CXS S Line | NCDOT | SR 1101 (Kimball Road) | Construct grade separation. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CJ | Statewide Mobility
Warren | CXS S Line | NCDOT | Various | Construct grade separation in Drewry and roadway improvements on SR 1151 (Soul City Boulevard) |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753DC | Statewide Mobility
Warren | CXS S Line | NCDOT | Various | Construct roadway improvements in Wise and on SR 1302 (Felts Road) |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753DE | Statewide Mobility
Warren, Vance | I-85 | NCDOT | South of US 158 in Vance County to Virginia state line | ITS deployment for Parts BA and BB. |  | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | I-0914BC | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Warren, Vance | I-85 | NCDOT | South of US 158 in Vance County to Virginia state line | Refurbish signs and signposts. |  | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | I-0914A | [11 empty] | COMPLETE
Warren, Vance | I-85 | NCDOT | US 158 (mile marker 213.5) in Vance County to Virginia state line. | Rehabilitate pavement and upgrade signs. | 19 | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | I-0914 | Pre-STI (Transition)
Washington | NC 32 | NCDOT | Bridge 930015 over Albemarle Sound. | Preserve bridge. | 3.5 | Highway | Bridges | 1 | Albemarle RPO | HB-0016 | Region A | BFP, T(M) |  |  |  |  | 2027 | 50001000 |  |  | 50001000
Washington | SR 1106 (Morattock Road) | NCDOT | SR 1100 (Long Ridge Road) to NC 32 South. | Modernize roadway. | 2.12 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5937 | Division 1 | T | 2028 | 1400000 | 2028 | 340000 | 2032 | 21600000 |  |  | 23340000
Washington | SR 1126 (Newland Road) | NCDOT | SR 1128 (A Canal Road) to SR 1183 (Shore Drive). | Modernize roadway. | 4.19 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5936 | Division 1 | T | 2028 | 820000 | 2028 | 120000 | 2030 | 38000000 |  |  | 38940000
Washington, Martin, Pasquotank, Chowan, Tyrrell, Bertie, Hertford | US 64 (Future I-87); US 17 Bypass; US 17; NC 11; US 13 | NCDOT | Various locations in Division 1 | Install wrong way pavement markings, markers, and signs at ramps. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2401C | Region A | HSIP, T(M) |  |  |  |  | 2025 | 170000 |  |  | 170000 | UNDER CONSTRUCTION.
Watauga | New Route | BLOWING ROCK | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Bike & Ped | Locally Selected | 11 | High Country RPO | EB-5924 | Exempt | FLAP, HF, HF(M), L(M) |  |  |  |  | 2026 | 1626000 | 2019 | 603000 | 2229000 | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS.
Watauga | US 221 | BLOWING ROCK | Main Street to Moses H. Cone Memorial Park and Bass Lake in Blowing Rock | Construct sidewalk. | 0.6 | Bike & Ped | Locally Selected | 11 | High Country RPO | EB-5798 | Exempt | [10 empty] | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK
Watauga | US 421 / US 321 (West King Street) |  | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Bike & Ped | NCDOT Selected (Other Selection Process) | 11 | High Country RPO | BN-0010 | Exempt | CRP550, L(M) | 2026 | 50000 |  |  | 2027 | 656000 | 2024 | 150000 | 856000
Watauga | US 421 (KING STREET) | BOONE | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Bike & Ped | STI (Prioritization) | 11 | High Country RPO | EB-5983 | Division 11 | L, TA5T50 | 2027 | 2400000 | 2027 | 20000 | 2028 | 5300000 | 2026 | 500000 | 8220000
Watauga | SR 1594 (Aldridge Road) | NCDOT | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0062 | Exempt | BGOFF, DP, HFB | 2025 | 500000 | 2025 | 60000 | 2026 | 2000000 | 2023 | 414000 | 2974000 | DP REPRESENTS RAISE GRANT FUNDS.
Watauga | Hunting Hills Lane | BOONE | Bridge 940346 over South Fork of New River in Boone. | Replace Bridge. | 0.25 | Highway | Municipal Bridge | 11 | High Country RPO | B-5979 | Division 11 | BGOFF, L(M) |  |  |  |  | 2025 | 5222000 |  |  | 5222000 | Construction underway.
Watauga | US 221 / US 321 | NCDOT | Deerfield Road intersection to Boone Mall in Boone. | Install pedestrian countdown heads and flashing yellow arrows at various intersections. | 0.99 | Highway | Safety | 11 | High Country RPO | HS-2011B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 116000 |  |  | 116000 | UNDER CONSTRUCTION.
Watauga | US 221/ 421 | NCDOT | US 221/421 AND SR 1655 (LANDFILL ROAD) INTERSECTION AND ON INNOVATION DRIVE. | INSTALL REDUCED CONFLICT INTERSECTION RIGHT IN/ RIGHT OUT ONLY AND IMPROVEMENTS TO ADJACENT ROADWAY (INNOVATION DRIVE) FOR REDIRECTED TRAFFIC. |  | Highway | Safety | 11 | High Country RPO | HS-2411E | Statewide Mobility | HSIP, T(M) | 2025 | 100000 | 2025 | 150000 | 2026 | 1000000 |  |  | 1250000
Watauga | NC 105 | NCDOT | SR 1136 (Clarks Creek Road) to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 5.49 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566B | Region F | NHP, T | 2022 | 13270000 | 2022 | 13700000 | 2031 | 117200000 |  |  | 144170000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
Watauga | NC 105 | NCDOT | SR 1658 (Old Shulls Mill Road) intersection near Boone. | Realign roadway. | 0.5 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566BB | Region F | T |  |  |  |  | 2025 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION.
Watauga | NC 105 | NCDOT | Watauga River; SR 1112 (Broadstone Road) intersection near Boone. | Construct new bridge over Watauga River; Construct left turn lane at SR 1112 (Broadstone Road). |  | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566BA | Division 11 | T |  |  | 2019 | 2850000 | 2022 | 35330000 |  |  | 38180000 | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
Watauga | SR 1514 (Bamboo Road) / SR 1523 (Wilson Ridge) | NCDOT | US 421 / US 221 to SR 1522 (Deerfield Road). | Modernize roadway. | 1.88 | Highway | STI (Prioritization) | 11 | High Country RPO | U-5810 | Division 11 | BG5T50, T | 2022 | 19400000 | 2025 | 1300000 | 2026 | 54700000 |  |  | 75400000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
Watauga | SR 1522 (Deerfield Road) | NCDOT | State Farm Road to SR 1523 (Wilson Ridge Road) in Boone. | Upgrade roadway. | 0.87 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5830 | Division 11 | BG5T50 | 2026 | 6200000 | 2026 | 500000 | 2028 | 16000000 |  |  | 22700000
Watauga | US 421 (Daniel Boone Parkway) | NCDOT | NC 105 to US 221 / US 321 south of Boone. | Construct freeway on new location south of Boone. | 3.62 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915B | Division 11 | TA5T50 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 89100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 347499000 |  |  | 440699000
Watauga | US 421 (Daniel Boone Parkway) | NCDOT | US 221 / US 321 to US 221 / US 421 east of Boone. | Construct freeway on new location south of Boone. | 4.55 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915C | Not Funded | NHP, T(M) | NOT FUNDED | 133800000 | NOT FUNDED | 400000 | NOT FUNDED | 384600000 | NOT FUNDED |  | 518800000
Watauga | US 421 (Daniel Boone Parkway) | NCDOT | US 421 / US 321 west of Boone to NC 105. | Construct freeway on new location south of Boone. | 2.25 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915A | Not Funded | NHP, T(M) | NOT FUNDED | 81700000 | NOT FUNDED | 400000 | NOT FUNDED | 165600000 | NOT FUNDED |  | 247700000
Watauga | US 421 (Daniel Boone Parkway) | NCDOT | US 421 / US 321 west of Boone to US 421 east of Boone. | Construct freeway on new location south of Boone. | 10.42 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915 | Division 11
Watauga | US 421 / US 321 | NCDOT | US 421 / US 321 Junction near Vilas to SR 1107 (NC 105 Bypass). | Widen to multi-lanes. | 3.55 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2615 | Region F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 55000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 78300000 |  |  | 136200000
Watauga | Appalcart | APPALCART | Systemwide | Purchase three battery electric buses and associated charger, electric vehicle management and diagnostic tool |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 11 | High Country RPO | TN-6129 | Exempt | 5311, T(M) | [6 empty] | 2027 | 5003000 | 5003000
Watauga | Appalcart | APPALCART | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6107 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
Watauga, Avery | NC 105 | NCDOT | US 221 to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 14.8 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566
Watauga, Wilkes | US 421 | NCDOT | SR 1301 (Fall Creek Road) to East of SR 1461 (Old US Hwy 421), including ramps to US 421/US 221. | Install 6-inch rumble strips, thermo long life pavement markings, and three CCTV cameras. |  | Highway | Safety | 11 | High Country RPO | HS-2411C | Statewide Mobility | HSIP |  |  |  |  | 2025 | 600000 |  |  | 600000
Wayne | W40 | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | Mount Olive Municipal Airport | Extend runway to 5500 feet. |  | Aviation | STI (Prioritization) | 4 | Eastern Carolina RPO | AV-5811 | Division 4 | T |  |  |  |  | 2029 | 1200000 |  |  | 1200000
Wayne | Stoney Creek Greenway | GOLDSBORO | US 70 Bypass to SR 1560 (Royall Avenue) in Goldsboro. | Construct 10 foot wide asphalt greenway. | 0.39 | Bike & Ped | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | EB-5707 | Division 4 | L(M), SRTS |  |  |  |  | 2022 | 391000 |  |  | 391000 | UNDER CONSTRUCTION.
Wayne | SR 1958 (Bennetts Bridge Road) | NCDOT | Bridge 950117 over Northeast Cape Fear River. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Eastern Carolina RPO | B-4844 | Highway Fund | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS.
Wayne | I-795 | NCDOT | Wilson County line to SR 2075 (Ash Street). | Upgrade guardrail, shoulders, and median repairs. | 13.55 | Highway | Interstate Maintenance | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | I-6047 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 6893000 |  |  | 6893000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034.
Wayne | US 117 (Future I-795) | NCDOT | US 70 to Duplin County line. | Rehabilitate bridge and pavement. | 16.69 | Highway | Interstate Maintenance | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | I-6048 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2021 | 7942000 |  |  | 7942000 | UNDER CONSTRUCTION.
Wayne | Various | NCDOT | Goldsboro Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Highway | Locally Selected | 4 | Goldsboro Urban Area MPO | HL-0097 | Exempt | CRPDA, L(M) |  |  |  |  | 2023 | 1745000 |  |  | 1745000
Wayne | NC 55 | DIVISION | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Highway | NCDOT Selected (Other Selection Process) | 4 | Eastern Carolina RPO | HN-0033 | Exempt | CRPANY, T(M) | 2026 | 662000 |  |  | 2026 | 6318000 | 2024 | 1100000 | 8080000
Wayne | NC 111 | NCDOT | SR 1754 (Zion Church Road) intersection. | Install all way stop utilizing existing overhead flashers. | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2004E | Region A | HSIP, T(M) |  |  |  |  | 2022 | 152000 |  |  | 152000 | UNDER CONSTRUCTION.
Wayne | NC 55 | NCDOT | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2404A | Region A | HSIP, T(M) | 2027 | 76000 | 2027 | 96000 | 2028 | 524000 |  |  | 696000
Wayne | NC 55 | NCDOT | West of Lenoir County line to Mount Olive city limits and SR 1135 (Country Club Road) to Sampson County line | Install rumble stripes and pavement markings. | 23.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2404C | Region A | HSIP, T(M) |  |  |  |  | 2026 | 806000 |  |  | 806000
Wayne | SR 1002 (Pikeville-Princeton Road) | NCDOT | SR 1320 (Hinnant Road) intersection. | Install all way stop with island. | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2004D | Division 4 | HSIP, T(M) |  |  |  |  | 2022 | 64000 |  |  | 64000 | UNDER CONSTRUCTION.
Wayne | SR 1003 (New Hope Road) | NCDOT | US 13 (Berkley Boulevard) to SR 1719 (Beston Road) in Goldsboro. | Install pavement markings. | 5.5 | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2404I | Division 4 | HSIP, T(M) |  |  |  |  | 2026 | 89000 |  |  | 89000
Wayne | SR 1537 (Airport Road) | NCDOT | SR 1545 (Mt. Carmel Church Road) intersection | Install all way stop. | 0.5 | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2004C | Division 4 | HSIP, T(M) |  |  |  |  | 2022 | 66000 |  |  | 66000 | UNDER CONSTRUCTION.
Wayne | SR 1556 (Wayne Memorial Drive) | NCDOT | US 70 Bypass to Greene County line. | Install rumble stripes with pavement markings. | 7.3 | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2004AC | Division 4 | HSIP, T(M) |  |  |  |  | 2024 | 210000 |  |  | 210000
Wayne | SR 1744 (Indian Springs Road) | NCDOT | SR 1941 (Northeast Church Road) intersection. | Install all way stop. | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2004I | Division 4 | HSIP, T(M) |  |  |  |  | 2022 | 64000 |  |  | 64000 | UNDER CONSTRUCTION.
Wayne | SR 1927 (Genoa Road) | NCDOT | Crescent drive intersection | Construct intersection improvements. | 0.5 | Highway | Safety | 4 | Goldsboro Urban Area MPO | W-5704K | Division 4 | HSIP, T(M) | 2024 | 40000 |  |  | 2024 | 857000 |  |  | 897000 | UNDER CONSTRUCTION.
Wayne | US 70 Business / US 117 Business (Ash Street) | NCDOT | SR 1925 (John Street) and US 117 Business (William Street) intersections in Goldsboro. | Install / revise pedestrian accommodations including traffic signals, pedestrian signals, and crosswalk improvements. |  | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2404D | Region A | HSIP, T(M) |  |  |  |  | 2025 | 240000 |  |  | 240000 | UNDER CONSTRUCTION.
Wayne | NC 581 (Bill Lane Boulevard) | NCDOT | Neuse River south of SR 1919 (Westbrook Road) to NC 111. | Modernize roadway. | 4.5 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6207 | Division 4 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 740000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 460000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22000000 |  |  | 23200000
Wayne | SR 1556 (Wayne Memorial Drive) | NCDOT | Lockhaven Drive to Country Day Road. | Construct access management improvements. | 0.26 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-5994 | Division 4 | T |  |  |  |  | 2023 | 450000 |  |  | 450000 | UNDER CONSTRUCTION.
Wayne | SR 1556 (Wayne Memorial Drive) | NCDOT | SR 1003 (New Hope Road) to I-42 (formerly US 70) in Goldsboro. | Widen to four lanes. | 0.87 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-4753 | Division 4 | T | 2019 | 6180000 |  |  | 2026 | 21900000 |  |  | 28080000 | RIGHT-OF-WAY IN PROGRESS.
Wayne | SR 1556 (Wayne Memorial Drive) | NCDOT | SR 1569 (Country Day Road) to SR 1003 (New Hope Road). | Construct access management. | 1.08 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6204 | Division 4 | BG50200, T | 2026 | 4101000 | 2026 | 2000000 | 2028 | 27205000 |  |  | 33306000 | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
Wayne | SR 1556 (Wayne Memorial Drive) | NCDOT | US 70 Bypass to SR 1547 (Stoney Creek Church Road). | Widen roadway. | 2.79 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6205 | Division 4 | T | 2027 | 1200000 | 2027 | 1600000 | 2029 | 4400000 |  |  | 7200000
Wayne | SR 1713 (Miller's Chapel Road) | NCDOT | US 70 to SR 1712 (Thoroughfare Road). | Modernize roadway. | 1 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6206 | Division 4 | T | 2029 | 9200000 | 2029 | 2500000 | 2031 | 10900000 |  |  | 22600000
Wayne | US 117 (Future I-795) | NCDOT | North of NC 581 (Arrington Bridge Road) to I-795. | Upgrade roadway to interstate standards, partially on new location. | 3.48 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3125F | Not Funded | NHP, T(M) | NOT FUNDED | 20200000 | NOT FUNDED | 1600000 | NOT FUNDED | 116400000 | NOT FUNDED |  | 138200000
Wayne | US 117 (Future I-795) | NCDOT | North of SR 1135 (Country Club Road) to south of SR 1129 (South Landfill Road). | Upgrade roadway to interstate standards, partially on new location. | 3.61 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO | U-3125C | Region A | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 90000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35500000 |  |  | 38690000
Wayne | US 117 (Future I-795) | NCDOT | South of SR 1129 (South Landfill Road) to south of SR 1927 (Genoa Road). | Upgrade roadway to interstate standards, partially on new location. | 2.42 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3125D | Region A | NHP, T(M) | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 103100000 |  |  | 117900000
Wayne | US 117 (Future I-795) | NCDOT | South of SR 1927 (Genoa Road) to north of NC 581 (Arrington Bridge Road). | Upgrade roadway to interstate standards, partially on new location. | 1.82 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3125E | Not Funded | NHP, T(M) | NOT FUNDED | 30500000 | NOT FUNDED | 2600000 | NOT FUNDED | 234400000 | NOT FUNDED |  | 267500000
Wayne | US 117 Business / US 117 (North Williams Street) | NCDOT | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-2714 | Region A | L, T | 2020 | 3510000 |  |  | 2020 | 25087000 | 2020 | 4290000 | 32887000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
Wayne | US 13 | NCDOT | SR 1572 (Saulston Road) to SR 1700 (Rodell Barrow Road). | Modernize roadway. | 3.64 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | R-5853 | Division 4 | BGANY, T(M) | 2025 | 3500000 | 2025 | 1900000 | 2028 | 8800000 |  |  | 14200000
Wayne | US 13 (Berkeley Boulevard) | NCDOT | Hood Swamp Road. | Realignment of Hood Swamp Road. | 0.19 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3609BA | Region A | T |  |  |  |  | 2022 | 2030000 |  |  | 2030000 | UNDER CONSTRUCTION.
Wayne | US 13 (Berkeley Boulevard) | NCDOT | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3609B | Region A | T | 2020 | 23339000 | 2020 | 3750000 | 2026 | 35305000 | 2020 | 2400000 | 64794000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE).
Wayne | US 13 (Berkeley Boulevard) | NCDOT | SR 1560 (Royal Avenue) to north of SR 1572 (Saulston Road) in Goldsboro. | Widen to multi-lanes. | 3 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3609
Wayne | US 13 (Berkeley Boulevard) | NCDOT | SR 1709 (Central Heights Road) at Berkeley Boulevard in Goldsboro. | Realign roadway. | 0.62 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-5724 | Region A | T | 2019 | 1322000 |  |  | 2023 | 19839000 |  |  | 21161000 | UNDER CONSTRUCTION.
Wayne | US 70 | NCDOT | SR 1711 (North Oak Forest Road) intersection in Goldsboro | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6110 | Region A | NHP, T(M) | 2025 | 1300000 | 2025 | 280000 | 2027 | 14000000 |  |  | 15580000
Wayne | US 70 Business (East Ash Street) | NCDOT | SR 1711 (South Oak Forest Road) to US 70 | Widen to four lanes. | 1.88 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-4407 | Region A | T | 2026 | 4900000 | 2026 | 5300000 | 2029 | 34305000 |  |  | 44505000 | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 9 SALE).
Wayne | US 13 (Berkeley Boulevard) | NCDOT | SR 1560 (Royal Avenue) to SR 1003 (New Hope Road). | Widen to multi-lanes. | 1 | Highway | Transition | 4 | Goldsboro Urban Area MPO | U-3609A | Pre-STI (Transition) | [10 empty] | COMPLETE.
Wayne | Goldsboro - Wayne Transportation Authority | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | Various locations | Funding for planning assistance |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Goldsboro Urban Area MPO | TP-5116 | Public Transit | 5303, L, S | [6 empty] | 2020 | 392000 | 392000 | FUNDS AUTHORIZED IN PROGRESS
Wayne | Goldsboro - Wayne Transportation Authority | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | Systemwide | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Goldsboro Urban Area MPO | TO-6107 | Public Transit | 5311, L | [6 empty] | 2020 | 336000 | 336000 | FUNDS AUTHORIZED IN PROGRESS
Wayne | Goldsboro-Wayne Transportation Authority | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | Various locations | Funding for operating assistance. |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Goldsboro Urban Area MPO | TO-4719 | Public Transit | 5307, L, SMAP | [6 empty] | 2021 | 9240000 | 9240000 | FUNDS AUTHORIZED IN PROGRESS
Wayne | Transportation Authority of Goldsboro-Wayne | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | Systemwide | Funding for ADA paratransit service. |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Goldsboro Urban Area MPO | TG-4752C | Public Transit | 5307, L | [6 empty] | 2021 | 1225000 | 1225000 | FUNDS AUTHORIZED IN PROGRESS
Wayne | Transportation Authority of Goldsboro-Wayne | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | Systemwide | Funding for preventative maintenance. |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Goldsboro Urban Area MPO | TG-4752B | Public Transit | 5307, L | [6 empty] | 2020 | 2008000 | 2008000 | FUNDS AUTHORIZED IN PROGRESS
Wayne | Transportation Authority of Goldsboro-Wayne | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 4 | Goldsboro Urban Area MPO | TG-4752A | Public Transit | 5307, L | [6 empty] | 2020 | 260000 | 260000 | FUNDS AUTHORIZED IN PROGRESS
Wayne | Jefferson Street | NCDOT | Norfolk Southern Crossing 722868U in Goldsboro. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Goldsboro Urban Area MPO | RX-2004M | Division 4 | RR |  |  |  |  | 2025 | 411000 |  |  | 411000 | UNDER CONSTRUCTION.
Wayne, Duplin | US 117 (Future I-795) | NCDOT | SR 1006 (West Trade Street) to north of SR 1135 (Country Club Road). | Upgrade roadway to interstate standards, partially on new location. | 6.73 | Highway | STI (Prioritization) | 3, 4 | Eastern Carolina RPO | U-3125B | Not Funded | NHP, T(M) | NOT FUNDED | 39400000 | NOT FUNDED | 5000000 | NOT FUNDED | 173000000 | NOT FUNDED |  | 217400000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
Wayne, Duplin, Sampson | US 117 (Future I-795) | NCDOT | I-40 to I-795. | Upgrade roadway to interstate standards, partially on new location. | 24.3 | Highway | STI (Prioritization) | 3, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO, Mid-Carolina RPO | U-3125
Wayne, Edgecombe, Wilson | NC 111 | NCDOT | Multiple segments from Wayne / Duplin county line to Edgecombe / Martin county line. | Install rumble stripes and pavement markings. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Goldsboro Urban Area MPO | HS-2004V | Region A | HSIP, T(M) |  |  |  |  | 2024 | 2161000 |  |  | 2161000 | UNDER CONSTRUCTION.
Wayne, Johnston | US 70 | NCDOT | US 70 Bypass to east of SR 2314 (Pondfield Road). | Upgrade roadway to freeway standards. | 7.2 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO | R-5829
Wayne, Johnston | US 70 | NCDOT | US 70 Bypass to west of SR 2372 (Edwards Road / North Pearl Street). | Upgrade roadway to freeway standards. | 5.1 | Highway | STI (Prioritization) | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Upper Coastal Plain RPO | R-5829A | Not Funded | T | NOT FUNDED | 49399000 | NOT FUNDED | 14100000 | NOT FUNDED | 157200000 | NOT FUNDED |  | 220699000
Wilkes | UKF | WILKES COUNTY AIRPORT (UKF) | Wilkes County Airport | Extend runway to 7,000 feet. |  | Aviation | STI (Prioritization) | 11 | High Country RPO | AV-5894 | Division 11 | T | 2026 | 600000 |  |  | 2027 | 12300000 |  |  | 12900000
Wilkes | SR 1001 (Oakwoods Road) | NCDOT | Bridge 960029 over Cub Creek. | Replace bridge. |  | Highway | Bridges | 11 | High Country RPO | B-4676A | Division 11 | BGOFF |  |  |  |  | 2026 | 8800000 |  |  | 8800000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
Wilkes | SR 1002 (Traphill Road) | NCDOT | Bridge 960663 over East Prong Roaring River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0125 | Highway Fund | DP, HFB | 2020 | 280000 |  |  | 2021 | 2650000 |  |  | 2930000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Wilkes | SR 1148 (Red Top Road) | NCDOT | Bridge 960419 over Naked Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0209 | Highway Fund | HFB |  |  |  |  | 2021 | 650000 |  |  | 650000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153
Wilkes | SR 1170 (Casper Hawkins Road) | NCDOT | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0065 | Exempt | BGOFF, DP, HFB | 2025 | 280000 | 2025 | 20000 | 2026 | 1902000 | 2023 | 425000 | 2627000 | DP REPRESENTS RAISE GRANT FUNDS.
Wilkes | SR 1185 (Curtis Bridge Road) | NCDOT | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0020 | Exempt | BGOFF, DP, HF(M), HFB, T(M) | 2025 | 752000 | 2025 | 290000 | 2027 | 13098000 | 2023 | 1112000 | 15252000 | DP REPRESENTS RAISE GRANT FUNDS.
Wilkes | SR 1313 (Congo Road) | NCDOT | Bridge 960075 over Fish Dam Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | B-4977 | Highway Fund | HFB |  |  |  |  | 2021 | 700000 |  |  | 700000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
Wilkes | SR 1355 (White Oak Road) | NCDOT | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0066 | Exempt | BGOFF, DP, HFB | 2025 | 130000 | 2025 | 60000 | 2026 | 2100000 | 2023 | 439000 | 2729000 | DP REPRESENTS RAISE GRANT FUNDS.
Wilkes | SR 1559 (Colvard Road) | NCDOT | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0063 | Exempt | BGOFF, DP, HFB | 2025 | 70000 | 2025 | 20000 | 2026 | 1600000 | 2023 | 454000 | 2144000 | DP REPRESENTS RAISE GRANT FUNDS.
Wilkes | SR 1567 (Sheets Gap Road) | NCDOT | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0064 | Exempt | BGOFF, DP, HFB | 2025 | 130000 | 2025 | 40000 | 2026 | 1400000 | 2023 | 421000 | 1991000 | DP REPRESENTS RAISE GRANT FUNDS.
Wilkes | SR 1745 (Shumate Mountain Road) | NCDOT | Bridge 960166 on SR 1745 over West Prong Roaring River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0124 | Highway Fund | DP, HFB | 2020 | 40000 |  |  | 2021 | 2900000 |  |  | 2940000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Wilkes | SR 1749 (Austin Traphill Road) | NCDOT | Bridge 960667 over Sparks Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0126 | Highway Fund | DP, HFB | 2020 | 80000 |  |  | 2021 | 1550000 |  |  | 1630000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Wilkes | SR 2418 (South Windy Gap Road) | NCDOT | Bridge 960004 over Little Hunting Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0108 | Highway Fund | HFB |  |  |  |  | 2022 | 1200000 |  |  | 1200000 | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
Wilkes | SR 2516 (Industrial Park Road) | NCDOT | Bridge 960733 over Cub Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0208 | Highway Fund | HFB |  |  |  |  | 2022 | 600000 |  |  | 600000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154
Wilkes | US 421 Business | NCDOT | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0069 | Exempt | BFP, BGANY, DP, HF(M), HFB, T(M) | 2025 | 4001000 | 2025 | 1402000 | 2027 | 14640000 | 2023 | 1667000 | 21710000 | DP REPRESENTS RAISE GRANT FUNDS.
Wilkes | NC 268 | NCDOT | SR 1966 (Airport Road) to SR 2026 (Austin Traphill Road). | Install guardrail and pavement markings. | 13.75 | Highway | Safety | 11 | High Country RPO | W-5503A | Region F | HSIP, T(M) |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
Wilkes | SR 1143 (New Browns Ford Road) | NCDOT | Bridge 960093 over Yadkin River. | Install guardrail. |  | Highway | Safety | 11 | High Country RPO | HS-2411A | Division 11 | HSIP |  |  |  |  | 2025 | 76000 |  |  | 76000
Wilkes | US 421 | NCDOT | SR 2325 (Red White & Blue Road/Mathis Farm Road). | Install Open Graded Friction Course. |  | Highway | Safety | 11 | High Country RPO | HS-2411G | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2026 | 385000 |  |  | 385000
Wilkes | Various | NCDOT | Routes in Division 11. | Install rumble stripes and long life pavement markings. Install shoulder guardrail near SR 2329 (Woodhaven Road). |  | Highway | Safety | 11 | High Country RPO | HS-2011F | Division 11 | HSIP |  |  |  |  | 2023 | 420000 |  |  | 420000
Wilkes | NC 115 | NCDOT | US 421 to 2nd Street in North Wilkesboro. | Widen to two lanes with median. Construct bike lanes and sidewalks. | 2.98 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5759 | Division 11 | T | 2022 | 12615000 | 2022 | 900000 | 2027 | 55830000 | 2020 | 1365000 | 70710000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PE, PAYBACK 20-34 (FY 19 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR1 SALE); $17.42M FOR CON PAYBACK 29-43 (FY 29/ YR 9 SALE)
Wilkes | NC 268 | NCDOT | SR 1966 to four lanes west of SR 2026 (Austin Traphill Road). | Modernize roadway. | 13.52 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5906 | Division 11 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 118900000 |  |  | 160900000
Wilkes | SR 1001 (Oakwoods Road) | NCDOT | US 421 to Forest Hill Drive in Wilkesboro. | Upgrade roadway. | 1.27 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5772 | Division 11 | BG5T50, T, T(M) | 2026 | 4100000 | 2026 | 1700000 | 2027 | 16800000 |  |  | 22600000
Wilkes | US 421 | NCDOT | NC 16 to US 421 Business. | Construct reduced conflict intersections. | 2.64 | Highway | STI (Prioritization) | 11 | High Country RPO | U-5312 | Region F | NHP, T(M) | 2023 | 5100000 | 2023 | 1217000 | 2023 | 91349000 |  |  | 97666000 | UNDER CONSTRUCTION.
Wilkes | NC 268 | NCDOT | NC 18 to SR 1966 (Airport Road). | Construct sidewalk from NC 18 to Shaver Street. Widen to five lanes from Shaver Street to SR 1971 (Fairplains Road). Widen to four lanes divided from Fairplains Road to SR 1966 (Airport Road). | 3.27 | Highway | Transition | 11 | High Country RPO | R-2603 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
Wilkes | NC 268 | NCDOT | Various locations east of Wilkesboro. | Widen roadway, improve shoulders, and install guardrail, rumble stripes, and pavement markings. |  | Highway | Transition | 11 | High Country RPO | W-5503 | Region F | [10 empty] | PART COMPLETE
Wilkes | Wilkes Transportation Authority | WILKES TRANSPORTATION AUTHORITY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6172 | Public Transit | 5311, L, S | [6 empty] | 2020 | 912000 | 912000 | FUNDS AUTHORIZED IN PROGRESS
Wilkes, Ashe, Watauga | US 221; US 421 | NCDOT | Mile Marker 0.4 in Ashe County, Mile Marker 18.3 in Watauga County; Mile Marker 30.1 in Wilkes County. | Install Dynamic Message Signs. |  | Highway | Safety | 11 | High Country RPO | HS-2411F | Statewide Mobility | HSIP, T(M) |  |  | 2026 | 30000 | 2026 | 645000 |  |  | 675000
Wilson | Wilson | WILSON | Hominy Creek Greenway and Trail Network | Construct greenway. | 3.8 | Bike & Ped | Other | 4 | Upper Coastal Plain RPO | BL-0069 | Exempt | DP | [6 empty] | 2023 | 950000 | 950000 | DP FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT.
Wilson | SR 1339 (Sharpe Shore Road) | NCDOT | Bridge 970092 over Town Swamp. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5998 | Division 4 | [10 empty] | UNDER CONSTRUCTION
Wilson | SR 1400 (Rock Quarry Road) | NCDOT | Bridge 970096 over tributary of Town Creek. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6000 | Division 4 | [10 empty] | UNDER CONSTRUCTION
Wilson | US 117 | NCDOT | Bridge 970047 over Seaboard Coast Line Railroad. | Replace bridge. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5666 | Highway Fund | HFB |  |  |  |  | 2022 | 4469000 |  |  | 4469000 | UNDER CONSTRUCTION.
Wilson | US 264 (Future I-587) | NCDOT | I-795 to Toisnot Swamp. | Rehabilitate pavement. | 7.05 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0006 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 13706000 |  |  | 13706000 | UNDER CONSTRUCTION.
Wilson | US 264 (Future I-587) | NCDOT | Toisnot Swamp to the Greene County Line. | Rehabilitate pavement. | 8.23 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0007 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2022 | 11015000 |  |  | 11015000 | UNDER CONSTRUCTION.
Wilson | US 264 (Future I-587) | NCDOT | Wilson County line to I-95. | Rehabilitate pavement. | 4.55 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0014 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2026 | 10600000 |  |  | 10600000
Wilson | SR 1356 (Raleigh Road Parkway) | NCDOT | Atlantic Christian College Drive to NC 42 / NC 58 in Wilson. | Modernize roadway. | 0.47 | Highway | Locally Selected | 4 | Upper Coastal Plain RPO | HL-0034 | Exempt | BA |  |  | 2022 | 75000 | 2023 | 2357000 | 2021 | 45000 | 2477000 | UNDER CONSTRUCTION.
Wilson | SR 1103 (Wiggins Mill Road) | NCDOT | SR 1169 (Radford Road) intersection. | Install all way stop utilizing existing overhead flashers. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004F | Division 4 | HSIP, T(M) |  |  |  |  | 2022 | 30000 |  |  | 30000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H.
Wilson | SR 1192 (Hines Street) | NCDOT | Lodge Street intersection in Wilson. | Upgrade traffic signal to include pedestrian accommodations and install crosswalks. | 0 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2404F | Division 4 | HSIP, T(M) |  |  |  |  | 2027 | 80000 |  |  | 80000
Wilson | SR 1320 (Airport Boulevard) | NCDOT | Chelsea Drive and Jetstream Drive intersections in Wilson. | Install traffic signals. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004O | Division 4 | HSIP, T(M) |  |  | 2023 | 140000 | 2024 | 709000 |  |  | 849000 | UNDER CONSTRUCTION.
Wilson | US 301 | NCDOT | NC 581 intersection. | Construct reduced conflict intersection and adjacent bulbouts. | 1 | Highway | Safety | 4 | Upper Coastal Plain RPO | W-5804A | Region A | HSIP, T(M) | 2021 | 100000 |  |  | 2022 | 2584000 |  |  | 2684000 | UNDER CONSTRUCTION.
Wilson | NC 58 (Nash Street Northwest) | NCDOT | SR 1330 (Airport Road) / SR 1332 (Lake Wilson Road) intersection in Wilson | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-6111 | Region A | T | 2028 | 4800000 | 2028 | 720000 | 2031 | 8100000 |  |  | 13620000
Wilson | US 264 Alternate (Raleigh Road Parkway) | NCDOT | SR 1320 (Airport Boulevard) to east of SR 1165 (Forest Hills Road). | Construct safety improvements. | 1.12 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-5941 | Region A | BG5T50, T(M) | 2028 | 12600000 | 2028 | 4200000 | 2031 | 21300000 |  |  | 38100000
Wilson | Various | NCDOT | Routes in Wilson. | Upgrade signal system. | 26.1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-5945 | Division 4 | BG5T50, T(M) |  |  | 2025 | 2600000 | 2026 | 3600000 |  |  | 6200000
Wilson | Integrated Mobility Division |  | Various locations | Funding for City of Wilson Ride Microtransit Expansion. |  | Public Transportation (Transit) | Locally Selected | 4 | Upper Coastal Plain RPO | TL-0033 | Public Transit | CPF, L | [6 empty] | 2024 | 5000000 | 5000000
Wilson | SR 1163 (Goldsboro Street) | NCDOT | CSX Crossing 629 847Y | Improve at-grade crossing in Wilson. |  | Rail | Rail-Highway Grade Crossing Closure | 4 | Upper Coastal Plain RPO | RC-2004A | Division 4 | RR | 2024 | 50000 | 2025 | 50000 | 2026 | 1200000 |  |  | 1300000
Wilson | Green Street | NCDOT | CSX Crossing 629849M in Wilson. | Construct safety improvements. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004I | Division 4 | RR |  |  |  |  | 2026 | 417000 |  |  | 417000
Wilson | NC 58 | NCDOT | Carolina Coastal Railway Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404A | Division 4 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Wilson | SR 1100 (Chicopee Road) | NCDOT | CSX Crossing 629847Y in Wilson. | Install active warning devices. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004B | Division 4 | RR |  |  |  |  | 2023 | 650000 |  |  | 650000 | UNDER CONSTRUCTION.
Wilson | SR 1165 (Forest Hills Road) | NCDOT | Carolina Coastal Railway Crossing 465611A in Wilson. | Improve highway-rail grade crossing safety. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404D | Division 4 | RR |  |  |  |  | 2031 | 400000 |  |  | 400000
Wilson | SR 1607 (Charleston Street) | NCDOT | Carolina Coastal Railway Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404B | Division 4 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Wilson | Tarboro Street Annex | NCDOT | Carolina Coastal Railway Crossing | Construct highway-rail grade crossing safety improvements. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404C | Division 4 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
Wilson, Lee, Rowan, Brunswick, New Hanover, Pender, Johnston, Alamance, Rockingham, McDowell, Montgomery, Edgecombe, Franklin, Granville, Nash, Randolph, Vance, Warren | Integrated Mobility Division |  | Systemwide | Funding for turnkey project. |  | Public Transportation (Transit) | Capital (Non-STI) | 3, 4, 5, 7, 8, 9, 13 | Wilmington Urban Area MPO, Upper Coastal Plain RPO, Piedmont Triad RPO, Greensboro Urban Area MPO, Winston-Salem Area TPO, Kerr-Tar RPO, Foothills RPO | TC-0031 | Public Transit | L, RTAP, S | [6 empty] | 2024 | 25400000 | 25400000
Yadkin | NC 67 | NCDOT | Bridge 980035 over Yadkin River. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5825 | Region F | T |  |  |  |  | 2021 | 12440000 |  |  | 12440000 | UNDER CONSTRUCTION.
Yadkin | SR 1119 (Sloans Mill Road) | NCDOT | Bridge 980028 over North Little Hunting Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0205 | Highway Fund | HFB |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130
Yadkin | SR 1152 (Neelie Road) | NCDOT | Bridge 980020 over South Deep Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0200 | Highway Fund | HFB |  |  |  |  | 2019 | 850000 |  |  | 850000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183.
Yadkin | SR 1325 (Mountain View Church Road) | NCDOT | Bridge 980189 over South Deep Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0127 | Highway Fund | DP, HFB | 2020 | 45000 |  |  | 2021 | 850000 |  |  | 895000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
Yadkin | US 21 Business | NCDOT | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5833 | Region F | BFP, T(M) | 2021 | 2000000 |  |  | 2026 | 19300000 |  |  | 21300000 | RIGHT-OF-WAY IN PROGRESS.
Yadkin | US 21 Business | NCDOT | Bridge 980059 over Jonesville Creek. | Replace bridge. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-4979 | Highway Fund | HFB |  |  |  |  | 2021 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
Yadkin | I-77 | NCDOT | Mile marker 71.8 to mile marker 75.8. | Rehabilitate pavement. | 2.08 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5864 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2028 | 6285000 |  |  | 6285000 | COMBINE WITH I-5865 FOR LETTING.
Yadkin | I-77 | NCDOT | Mile marker 75.8 to US 21 (Exit 79). | Rehabilitate pavement. | 1.89 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5865 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 2990000 |  |  | 2990000 | COMBINE WITH I-5864 FOR LETTING.
Yadkin | Jonesville | NCDOT | Breakfastime. | Install 6 DC fast charging ports. |  | Highway | National Electric Vehicle Infrastructure | 11 | Northwest Piedmont RPO | HV-0001E | Division 11 | NEVI, O, O(M), S(M) |  |  |  |  | 2025 | 885000 |  |  | 885000 | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY
Yadkin | US 421 | NCDOT | SR 1710 (Speer Bridge Road) interchange in Yadkinville. | Construct roundabouts at ramp terminals. |  | Highway | NCDOT Selected (Other Selection Process) | 11 | Northwest Piedmont RPO | HN-0028 | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 4000000 |  |  | 4000000
Yadkin | I-77 | NCDOT | South of SR 1125 (Ashbury Church Road) (mile marker 71.0) to US 21 in Yadkin County (Exit 79) | Rehabilitate pavement. | 6.592 | Highway | Pre-STI (Historic) | 11 | Northwest Piedmont RPO | I-2808A | Pre-STI (Transition) | [10 empty] | COMPLETE
Yadkin | NC 67 | NCDOT | US 601 in Booneville to West Main Street in East Bend. | Modernize roadway with intersection improvements at Nebo Road. | 10.55 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5914 | Division 11 | BGLT5 | 2030 | 29000000 | 2030 | 14800000 | 2033 | 92100000 |  |  | 135900000
Yadkin | SR 1314 (East Main Street) | NCDOT | US 601 to SR 1765 (Unifi Industrial Road) in Yadkinville. | Modernize roadway, including improvements at the US 601 and Van Buren Street intersections. | 1.19 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5909 | Division 11 | T | 2027 | 10000000 | 2027 | 2300000 | 2030 | 12205000 |  |  | 24505000 | NC BUILD BONDS: $4M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
Yadkin | SR 1605 (Old US 421) | NCDOT | SR 1146 (Shacktown Road) to SR 1711 (Speer Bridge Road). | Construct new roadway to realign with SR 1605 (Old US 421) with SR 1711 (Speer Bridge Road) and construct a roundabout at the intersection with SR 1146 (Shacktown Road). | 0.18 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5730 | Division 11 | T |  |  |  |  | 2022 | 3216000 |  |  | 3216000 | UNDER CONSTRUCTION.
Yadkin | SR 1605 (Old US 421) | NCDOT | SR 1600 (Falcon Road) intersection near Yadkinville. | Construct roundabout. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5912 | Division 11 | T | 2023 | 600000 | 2023 | 400000 | 2024 | 1725000 |  |  | 2725000 | RIGHT-OF-WAY IN PROGRESS.
Yadkin | US 601 (Carolina Avenue) | NCDOT | NC 67 (Main Street) intersection in Boonville. | Construct intersection improvements. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5831 | Division 11 | T |  |  | 2023 | 750000 | 2026 | 5600000 |  |  | 6350000 | RIGHT-OF-WAY IN PROGRESS
Yadkin | US 601 (State Street) | NCDOT | SR 1742 (Sharon Drive) to SR 1146 (Lee Avenue) | Construct median and roundabouts. | 0.68 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | U-5809 | Division 11 | BGLT5, T | 2023 | 1700000 | 2024 | 800000 | 2024 | 23035000 |  |  | 25535000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894.
Yadkin, Surry | I-77 | NCDOT | South of SR 1125 (Mile Marker 71.0) in Yadkin County to US 21 Bypass (mile marker 83.5) in Surry County (Exit 83). | Rehabilitate pavement. | 12 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-2808 | [11 empty] | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
Yadkin, Surry | I-77 | NCDOT | US 21 in Yadkin County (Exit 79) to mile marker 83.4 in Surry County. | Rehabilitate pavement. | 4.36 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5912 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
Yadkin, Surry | I-77 | NCDOT | US 21 in Yadkin County (Exit 79) to US 21 Bypass (Exit 83) in Surry County. | Rehabilitate pavement. | 0 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-2808B | [11 empty] | SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
Yadkin, Surry | I-77 | NCDOT | Various locations. | Upgrade guardrail end units. |  | Highway | Safety | 11 | Northwest Piedmont RPO | HS-2411B | Statewide Mobility | HSIP |  |  |  |  | 2025 | 152000 |  |  | 152000
Yadkin, Surry | NC 67; US 21 Business | NCDOT | Commerce Street in Elkin to North Bridge Street in Jonesville; Bridge 850021 over Yadkin River. | Widen roadway. Construct roundabouts at West Main Street and Elm Street and Elm Street and North Bridge Street. Improve bicycle and pedestrian connections; Rehabilitate bridge and widen sidewalks. | 0.35 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5913 | Division 11 | BGLT5, HFB | 2026 | 2200000 | 2026 | 400000 | 2028 | 10500000 |  |  | 13100000
Yancey | US 19 W | NCDOT | Bridge 990012 over Bald Creek | Replace bridge. |  | Highway | Bridges | 13 | High Country RPO | BR-0162 | Statewide Mobility | BFP |  |  |  |  | 2030 | 1600000 |  |  | 1600000
Yancey | NC 197 | NCDOT | SR 1338 (Wilds Branch Road) to the Mitchell County line near Green Mountain. | Install shoulder guardrail. | 3.74 | Highway | Safety | 13 | High Country RPO | W-5813H | Region G | HSIP, T(M) |  |  |  |  | 2022 | 474000 |  |  | 474000 | COMPLETE
Yancey | US 19W | NCDOT | SR 1454 (Cane River School Road) to SR 1382 (Silver Gap Road) near Burnsville. | Install guardrail. | 5.07 | Highway | Safety | 13 | High Country RPO | HS-2013J | Region G | HSIP |  |  |  |  | 2024 | 731000 |  |  | 731000
Yancey | Yancey County Transportation Authority | YANCEY COUNTY TRANSPORTATION AUTHORITY | Systemwide | Funding for agency administration. |  | Public Transportation (Transit) | Operations and Maintenance | 13 | High Country RPO | TK-6175 | Public Transit | 5311, L, S | [6 empty] | 2020 | 580000 | 580000 | FUNDS AUTHORIZED IN PROGRESS
Yancey | Yancey County Transportation Authority | AUTHORITY YANCEY COUNTY TRANSPORTATION | Various locations | Construct office / training / maintenance facility. |  | Public Transportation (Transit) | STI (Prioritization) | 13 | High Country RPO | TA-6723 | Division 13 | L, T |  |  |  |  | 2023 | 2345000 | 2023 | 155000 | 2500000 | LOCAL FUNDING PROVIDED BY YANCEY COUNTY

## 2026-2035 STIP Funding Details
2026-2035 STATE TRANSPORTATION IMPROVEMENT PROGRAM As amended by the Board of Transportation and approved by FHWA (March 2026) | [15 empty] | 2026-2035 STIP WINDOW
PROJECT ID | MODE | FUNDING PROGRAM | ROUTE/CITY | LOCATION DESCRIPTION | DESCRIPTION OF WORK | LENGTH (MILES) | COUNTY(S) | DIVISION(S) | MPOs/RPOs | COMMENT | CATEGORY FUNDED | FUNDING COMMENT | FUND SOURCE | ACTIVITY | TOTAL FUNDED (MAY INCLUDE PREVIOUSLY AUTHORIZED FUNDS) | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | FY 2035 | AFTER 2035
A-0009 | Highway | Appalachian Development Highway System | US 19; US 74; US 129; NC 28; NC 143 | Corridor "K" in Andrews to NC 28 east of Almond. | Upgrade roadway to include existing facilities and construct new location. | 27.1 | Graham, Swain, Cherokee | 14 | Southwestern RPO | [5 empty] | 84907000
A-0009A | Highway | Appalachian Development Highway System | US 19/US 74/US 129; US 129 (Tallulah Road) | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Graham, Cherokee | 14 | Southwestern RPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 11440000 | [10 empty] | 11440000
A-0009A | Highway | Appalachian Development Highway System | US 19/US 74/US 129; US 129 (Tallulah Road) | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Graham, Cherokee | 14 | Southwestern RPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 2860000 | [10 empty] | 2860000
A-0009A | Highway | Appalachian Development Highway System | US 19/US 74/US 129; US 129 (Tallulah Road) | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Graham, Cherokee | 14 | Southwestern RPO |  | Not Funded |  | NHP | UTILITIES | 740000 | [10 empty] | 740000
A-0009A | Highway | Appalachian Development Highway System | US 19/US 74/US 129; US 129 (Tallulah Road) | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Graham, Cherokee | 14 | Southwestern RPO |  | Not Funded |  | T(M) | UTILITIES | 185000 | [10 empty] | 185000
A-0009A | Highway | Appalachian Development Highway System | US 19/US 74/US 129; US 129 (Tallulah Road) | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Graham, Cherokee | 14 | Southwestern RPO |  | Not Funded |  | NHP | CONSTRUCTION | 292799000 | [10 empty] | 292799000
A-0009A | Highway | Appalachian Development Highway System | US 19/US 74/US 129; US 129 (Tallulah Road) | US 19 Business in Andrews to US 129 (Tallulah Road); US 19/US 74/US 129 to south of SR 1275 (Five Point Road) in Robbinsville. | Upgrade roadway. | 7.71 | Graham, Cherokee | 14 | Southwestern RPO |  | Not Funded |  | T(M) | CONSTRUCTION | 73201000 | [10 empty] | 73201000
A-0009CA | Highway | Appalachian Development Highway System | US 129; NC 143 | South of SR 1275 (Five Point Road) to NC 143; US 129 to SR 1223 (Beech Creek Road). | Upgrade roadway. | 4.14 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | RIGHT-OF-WAY | 1900000
A-0009CA | Highway | Appalachian Development Highway System | US 129; NC 143 | South of SR 1275 (Five Point Road) to NC 143; US 129 to SR 1223 (Beech Creek Road). | Upgrade roadway. | 4.14 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | UTILITIES | 528000
A-0009CA | Highway | Appalachian Development Highway System | US 129; NC 143 | South of SR 1275 (Five Point Road) to NC 143; US 129 to SR 1223 (Beech Creek Road). | Upgrade roadway. | 4.14 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | CONSTRUCTION | 54624000
A-0009CB | Highway | Appalachian Development Highway System | NC 143 | SR 1223 (Beech Creek Road) to north of Appalachian Trail. | Upgrade roadway. | 3.91 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | RIGHT-OF-WAY | 3300000
A-0009CB | Highway | Appalachian Development Highway System | NC 143 | SR 1223 (Beech Creek Road) to north of Appalachian Trail. | Upgrade roadway. | 3.91 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | UTILITIES | 1300000
A-0009CB | Highway | Appalachian Development Highway System | NC 143 | SR 1223 (Beech Creek Road) to north of Appalachian Trail. | Upgrade roadway. | 3.91 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | CONSTRUCTION | 133871000 | FY 2026: 19198000
A-0009CC | Highway | Appalachian Development Highway System | NC 143; NC 28 | North of Appalachian Trail to NC 28; NC 143 to west of SR 1228 (Stecoah Road). | Upgrade roadway. | 2.4 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | RIGHT-OF-WAY | 2300000
A-0009CC | Highway | Appalachian Development Highway System | NC 143; NC 28 | North of Appalachian Trail to NC 28; NC 143 to west of SR 1228 (Stecoah Road). | Upgrade roadway. | 2.4 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | UTILITIES | 550000
A-0009CC | Highway | Appalachian Development Highway System | NC 143; NC 28 | North of Appalachian Trail to NC 28; NC 143 to west of SR 1228 (Stecoah Road). | Upgrade roadway. | 2.4 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | CONSTRUCTION | 77500000 | FY 2026: 13053000; FY 2027: 3622000
A-0009CD | Highway | Appalachian Development Highway System | NC 28 | West of SR 1228 (Stecoah Road) to existing four lanes east of SR 1235 (Gunter Gap Road) | Upgrade roadway. | 1.42 | Graham | 14 | Southwestern RPO | DP REPRESENTS FEDERAL NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS (NSFLTP) GRANT. | Exempt |  | ADHS | CONSTRUCTION | 28900000 | FY 2026: 28900000
A-0009CD | Highway | Appalachian Development Highway System | NC 28 | West of SR 1228 (Stecoah Road) to existing four lanes east of SR 1235 (Gunter Gap Road) | Upgrade roadway. | 1.42 | Graham | 14 | Southwestern RPO | DP REPRESENTS FEDERAL NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS (NSFLTP) GRANT. | Exempt |  | DP | CONSTRUCTION | 20000000 | FY 2026: 20000000
A-0009CE | Highway | NCDOT Selected (Other Selection Process) | NC 28 | SR 1238 (Bill Crisp Road) to SR 1230 (Hyde Town Road). | Construct multi-use path. | 0.6 | Graham | 14 | Southwestern RPO | USE TOLL CREDITS ON A-0009CE. | Exempt |  | CRPLT5 | CONSTRUCTION | 5000000
A-0009DA | Highway | Appalachian Development Highway System | NC 28 | SR 1121 (Wattia Road) at Almond to existing US 19 / NC 28. | Upgrade roadway. | 1.517 | Swain | 14 | Southwestern RPO | COMPLETE
A-0009DB | Highway | Appalachian Development Highway System | NC 28 | East of Calfpen Gap in Graham County to SR 1121 (Wattia Road) at Almond in Swain County. | Upgrade roadway. | 2.381 | Swain, Graham | 14 | Southwestern RPO | COMPLETE
A-0009DC | Highway | Appalachian Development Highway System | NC 28 | West of SR 1231 (Tobacco Branch Road) to Calfpen Gap. | Upgrade roadway. | 2.337 | Graham | 14 | Southwestern RPO | COMPLETE
A-0009DD | Highway | Appalachian Development Highway System | NC 28 | Edwards Gap to east of SR 1231 (Tobacco Branch Road) | Upgrade roadway. | 2.859 | Graham | 14 | Southwestern RPO | COMPLETE
A-0010 | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | SR 1781 (Broadway Street) in Asheville to Tennessee state line at Sams Gap. | Widen to multi-lane freeway and construct new route. | 28.3 | Buncombe, Madison | 13 | French Broad River MPO, Land-of-Sky RPO | COORDINATE WITH B-4442, B-4443, B-4444.
A-0010AA | Highway | Appalachian Development Highway System | N/A | N/A | N/A |  | Buncombe | 13 | French Broad River MPO |  | Region G
A-0010AB | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251 / SR 1781 (Broadway Street) interchange in Asheville. | Improve interchange. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 26499000
A-0010AB | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251 / SR 1781 (Broadway Street) interchange in Asheville. | Improve interchange. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1800000
A-0010AB | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251 / SR 1781 (Broadway Street) interchange in Asheville. | Improve interchange. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 73600000
A-0010AC | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1684 (Elk Mountain Road) interchange. | Improve interchange. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 22106000
A-0010AC | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1684 (Elk Mountain Road) interchange. | Improve interchange. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1697000
A-0010AC | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1684 (Elk Mountain Road) interchange. | Improve interchange. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 42700000
A-0010AD | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 (Merrimon Avenue) interchange in Asheville | Construct interchange improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 46300000
A-0010AD | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 (Merrimon Avenue) interchange in Asheville | Construct interchange improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1600000
A-0010AD | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 (Merrimon Avenue) interchange in Asheville | Construct interchange improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 74500000
A-0010AE | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | SR 1882 (New Stock Road) interchange in Asheville | Construct interchange improvements and widen I-26 to north of SR 1720 (Aiken Road). |  | Buncombe | 13 | French Broad River MPO |  | Region G |  | NHP | RIGHT-OF-WAY | 18600000 | FY 2028: 1860000; FY 2029: 6510000; FY 2030: 6510000; FY 2031: 1860000; FY 2032: 1860000
A-0010AE | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | SR 1882 (New Stock Road) interchange in Asheville | Construct interchange improvements and widen I-26 to north of SR 1720 (Aiken Road). |  | Buncombe | 13 | French Broad River MPO |  | Region G |  | NHP | UTILITIES | 3102000 | FY 2028: 1034000; FY 2029: 1034000; FY 2030: 1034000
A-0010AE | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | SR 1882 (New Stock Road) interchange in Asheville | Construct interchange improvements and widen I-26 to north of SR 1720 (Aiken Road). |  | Buncombe | 13 | French Broad River MPO |  | Region G |  | NHP | CONSTRUCTION | 93900000 | FY 2031: 23475000; FY 2032: 23475000; FY 2033: 23475000; FY 2034: 23475000
A-0010AF | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 / US 70 interchange in Asheville | Construct interchange improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4656000
A-0010AF | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 / US 70 interchange in Asheville | Construct interchange improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 737000
A-0010AF | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 / US 70 interchange in Asheville | Construct interchange improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 36400000
A-0010AG | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | NC 251 / SR 1781 (Broadway Street) to US 25 / US 70 | Widen roadway to eight and six lanes. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4600000
A-0010AG | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | NC 251 / SR 1781 (Broadway Street) to US 25 / US 70 | Widen roadway to eight and six lanes. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 230000
A-0010AG | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | NC 251 / SR 1781 (Broadway Street) to US 25 / US 70 | Widen roadway to eight and six lanes. |  | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 207600000
A-0010AJ | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 / US 70 to SR 2207 (North Buncombe School Road) | Upgrade roadway to interstate standards. |  | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5600000 | [10 empty] | 5600000
A-0010AJ | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | US 25 / US 70 to SR 2207 (North Buncombe School Road) | Upgrade roadway to interstate standards. |  | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 72001000 | [10 empty] | 72001000
A-0010AK | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | SR 2207 (North Buncombe School Road) to south of SR 2148 (Stockton Road) | Upgrade roadway to interstate standards. |  | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 700000 | [10 empty] | 700000
A-0010AK | Highway | STI (Prioritization) | I-26 (US 19 / US 23) | SR 2207 (North Buncombe School Road) to south of SR 2148 (Stockton Road) | Upgrade roadway to interstate standards. |  | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 27001000 | [10 empty] | 27001000
A-0010BA | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | South of SR 2148 (Stockton Road) in Buncombe County to north of NC 213. | Widen to multi-lane freeway and construct new route. | 2.975 | Buncombe, Madison | 13 | Land-of-Sky RPO, French Broad River MPO | COMPLETE
A-0010BB | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | North of NC 213 to north of US 19. | Widen to multi-lane freeway and construct new route. | 1.762 | Madison | 13 | Land-of-Sky RPO | COMPLETE
A-0010C | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | North of US 19 to SR 1318 (Big Laurel Road) at Laurel Creek. | Widen to multi-lane freeway and construct new route. | 6.08 | Madison | 13 | Land-of-Sky RPO | COMPLETE
A-0010D | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | SR 1318 (Big Laurel Road) at Laurel Creek to the Tennessee state line at Sams Gap. | Widen to multi-lane freeway and construct new route. | 2.98 | Madison | 13 | Land-of-Sky RPO | COMPLETE
A-0011 | Highway | Appalachian Development Highway System | US 64; NC 69 | NC 69 to east of NC 175; Georgia state line to US 64. | Widen to four lanes divided. Widen to multi-lanes. | 7.3 | Clay | 14 | Southwestern RPO | APD FUNDS ARE 100% FEDERAL |  |  |  |  | 47732000
A-0011A | Highway | Appalachian Development Highway System | NC 69 | Georgia state line to US 64 (Hayesville Bypass). | Upgrade existing two-lanes. | 3.51 | Clay | 14 | Southwestern RPO | COMPLETE
A-0011BA | Highway | Appalachian Development Highway System | US 64 | NC 69 in Hayesville to east of the Hiwassee River. | Upgrade existing two-lanes. | 0.946 | Clay | 14 | Southwestern RPO | COMPLETE
A-0011BB | Highway | Appalachian Development Highway System | US 64 | East of the Hiwassee River to east of NC 175. | Upgrade existing two-lanes. | 3.8 | Clay | 14 | Southwestern RPO | COMPLETE
A-0011C | Highway | Appalachian Development Highway System | NC 69 | Georgia state line to US 64 (Hayesville Bypass). | Widen to four lanes. | 3.51 | Clay | 14 | Southwestern RPO | UNDER CONSTRUCTION | Exempt |  | ADHS | CONSTRUCTION | 52600000
A-0011D | Highway | Appalachian Development Highway System | US 64 | East of the Hiwassee River to east of NC 175. | Widen to four lanes. |  | Clay | 14 | Southwestern RPO |  | Not Funded |  | ADHS | RIGHT-OF-WAY | 20845000 | [10 empty] | 20845000
A-0011D | Highway | Appalachian Development Highway System | US 64 | East of the Hiwassee River to east of NC 175. | Widen to four lanes. |  | Clay | 14 | Southwestern RPO |  | Not Funded |  | ADHS | UTILITIES | 378000 | [10 empty] | 378000
A-0011D | Highway | Appalachian Development Highway System | US 64 | East of the Hiwassee River to east of NC 175. | Widen to four lanes. |  | Clay | 14 | Southwestern RPO |  | Not Funded |  | ADHS | CONSTRUCTION | 52800000 | [10 empty] | 52800000
AO-0001 | Aviation | Other | AVL | Asheville Regional Airport | Modernize building. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | Exempt |  | FED | CONSTRUCTION | 2884000
AO-0001 | Aviation | Other | AVL | Asheville Regional Airport | Modernize building. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | Exempt |  | L | CONSTRUCTION | 136674000
AO-0001 | Aviation | Other | AVL | Asheville Regional Airport | Modernize building. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | Exempt |  | HF | CONSTRUCTION | 14250000
AO-0002 | Aviation | Other | Various | Locations in Lumberton | Develop drone disaster response and delivery network. |  | Robeson | 6 | Lumber River RPO | DP FUNDS REPRESENT 2024 SMART GRANT FUNDING. | Exempt |  | DP | IMPLEMENTATION | 1100000
AP-0001 | Aviation | STI (Prioritization) | CLT | Charlotte Douglas International Airport | Construct end around taxiway on west side of proposed fourth parallel runway. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | T | CONSTRUCTION | 2000000 | FY 2029: 500000; FY 2030: 500000; FY 2031: 500000; FY 2032: 500000
AP-0002 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Extend runway 10/28. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 600000 | FY 2030: 300000; FY 2031: 300000
AP-0002 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Extend runway 10/28. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
AP-0002 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Extend runway 10/28. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
AP-0003 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Extend runway 4/22. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 600000 | FY 2030: 300000; FY 2031: 300000
AP-0003 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Extend runway 4/22. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
AP-0003 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Extend runway 4/22. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
AP-0004 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Upgrade pavement and paint the general aviation apron on Control Tower Road. |  | Cumberland | 6 | Fayetteville Area MPO | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT. | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 600000 | FY 2032: 300000; FY 2033: 300000
AP-0004 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Upgrade pavement and paint the general aviation apron on Control Tower Road. |  | Cumberland | 6 | Fayetteville Area MPO | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT. | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 300000
AP-0004 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Upgrade pavement and paint the general aviation apron on Control Tower Road. |  | Cumberland | 6 | Fayetteville Area MPO | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT. | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 1400000
AP-0005 | Aviation | STI (Prioritization) | HRJ | Harnett County Airport | Widen existing runway from 75 feet to 100 feet. |  | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 370000 | FY 2033: 370000
AP-0005 | Aviation | STI (Prioritization) | HRJ | Harnett County Airport | Widen existing runway from 75 feet to 100 feet. |  | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3697000
AP-0006 | Aviation | STI (Prioritization) | CPC | Columbus County Municipal Airport. | Extend runway. |  | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 390000 | FY 2030: 390000
AP-0006 | Aviation | STI (Prioritization) | CPC | Columbus County Municipal Airport. | Extend runway. |  | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 248000
AP-0006 | Aviation | STI (Prioritization) | CPC | Columbus County Municipal Airport. | Extend runway. |  | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3677000
AP-0007 | Aviation | STI (Prioritization) | CPC | Columbus County Municipal Airport. | Improve runway safety area and widen runway. |  | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 1054000 | FY 2033: 1054000
AP-0007 | Aviation | STI (Prioritization) | CPC | Columbus County Municipal Airport. | Improve runway safety area and widen runway. |  | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 10536000
AV-5700 | Aviation | STI (Prioritization) | RDU | Raleigh Durham International Airport | Reconstruct runway 5L-23R. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 4500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
AV-5700 | Aviation | STI (Prioritization) | RDU | Raleigh Durham International Airport | Reconstruct runway 5L-23R. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 99500000
AV-5701 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Extend runway 5R-23L. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5701 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Extend runway 5R-23L. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 19500000 | FY 2026: 19500000
AV-5707 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct Taxiway G. |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2027: 500000; FY 2028: 500000; FY 2029: 500000
AV-5707 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct Taxiway G. |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | O | CONSTRUCTION | 15400000 | FY 2026: 15400000
AV-5708 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct taxiway over future I-73 east of SR 2085 (Bryan Boulevard). |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  |  |  | 525000
AV-5708 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct taxiway over future I-73 east of SR 2085 (Bryan Boulevard). |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | T | CONSTRUCTION | 1500000
AV-5711 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Surface Movement Guidance and Control System (SMGSC) update. |  | Guilford | 7 | Greensboro Urban Area MPO | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2027: 500000; FY 2028: 500000; FY 2029: 500000
AV-5711 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Surface Movement Guidance and Control System (SMGSC) update. |  | Guilford | 7 | Greensboro Urban Area MPO | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | O | CONSTRUCTION | 7500000 | FY 2027: 7500000
AV-5715 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Runway 5R-23L group VI upgrade. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2028: 500000; FY 2029: 500000; FY 2030: 500000
AV-5715 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Runway 5R-23L group VI upgrade. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 9500000 | FY 2028: 9500000
AV-5718 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | High speed taxiway to runway 5R-23L. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5718 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | High speed taxiway to runway 5R-23L. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 2500000 | FY 2027: 2500000
AV-5731 | Aviation | STI (Prioritization) | JQF | Concord-Padgett Regional Airport | Expand commercial terminal apron. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | T | ENGINEERING | 300000 | FY 2026: 300000
AV-5731 | Aviation | STI (Prioritization) | JQF | Concord-Padgett Regional Airport | Expand commercial terminal apron. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | T | CONSTRUCTION | 900000 | FY 2027: 300000; FY 2028: 300000; FY 2029: 300000
AV-5731 | Aviation | STI (Prioritization) | JQF | Concord-Padgett Regional Airport | Expand commercial terminal apron. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | O | CONSTRUCTION | 7617000 | FY 2027: 7617000
AV-5733 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Design and construct runway 23 holding apron. |  | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T | CONSTRUCTION | 300000
AV-5733 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Design and construct runway 23 holding apron. |  | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | O | CONSTRUCTION | 450000
AV-5734 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Replace perimeter fencing and road. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | T | CONSTRUCTION | 600000 | FY 2027: 300000; FY 2028: 300000
AV-5734 | Aviation | STI (Prioritization) | FAY | Fayetteville Regional Airport | Replace perimeter fencing and road. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | O | CONSTRUCTION | 3140000 | FY 2027: 3140000
AV-5735 | Aviation | STI (Prioritization) | AVL | Asheville Regional Airport | Construct runway. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION | Region G |  |  |  | 300000
AV-5736 | Aviation | STI (Prioritization) | SCR | Siler City Municipal Airport | Acquire navigation easements in runway 4 and runway 22 approaches, and remove obstructions in easements. |  | Chatham | 8 | Central Pines RPO |  | Division 8 |  | T | RIGHT-OF-WAY | 365000
AV-5737 | Aviation | STI (Prioritization) | BUY | Burlington-Alamance Regional Airport | Obtain navigation easements and clear obstructions in the runway 24 approach. |  | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  |  |  | 163000
AV-5737 | Aviation | STI (Prioritization) | BUY | Burlington-Alamance Regional Airport | Obtain navigation easements and clear obstructions in the runway 24 approach. |  | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 1080000 | FY 2027: 1080000
AV-5737 | Aviation | STI (Prioritization) | BUY | Burlington-Alamance Regional Airport | Obtain navigation easements and clear obstructions in the runway 24 approach. |  | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 120000 | FY 2027: 120000
AV-5738 | Aviation | STI (Prioritization) | INT | Smith Reynolds Airport | Acquire land and clear terrain obstructions east of runway 15-33 to drain and grade material in place. |  | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS BY AIRPORT | Division 9 |  |  |  | 363000
AV-5738 | Aviation | STI (Prioritization) | INT | Smith Reynolds Airport | Acquire land and clear terrain obstructions east of runway 15-33 to drain and grade material in place. |  | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS BY AIRPORT | Division 9 |  | T | CONSTRUCTION | 6000000 | FY 2031: 3000000; FY 2032: 3000000
AV-5739 | Aviation | STI (Prioritization) | SUT | Cape Fear Regional Airport | Clear approach at runway 5 and runway 23. | 0 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION | Division 3 |  |  |  | 1116000
AV-5741 | Aviation | STI (Prioritization) | HKY | Hickory Regional Airport | Extend Runway 6 by 600 feet. |  | Burke | 13 | Greater Hickory MPO | "O" FUNDS REPRESENTS FUNDS FROM A LEGISLATIVE DIRECTIVE. | Division 13 |  | T | RIGHT-OF-WAY | 3309000
AV-5741 | Aviation | STI (Prioritization) | HKY | Hickory Regional Airport | Extend Runway 6 by 600 feet. |  | Burke | 13 | Greater Hickory MPO | "O" FUNDS REPRESENTS FUNDS FROM A LEGISLATIVE DIRECTIVE. | Division 13 |  | T | CONSTRUCTION | 6175000 | FY 2029: 2058000; FY 2030: 2058000; FY 2031: 2059000
AV-5741 | Aviation | STI (Prioritization) | HKY | Hickory Regional Airport | Extend Runway 6 by 600 feet. |  | Burke | 13 | Greater Hickory MPO | "O" FUNDS REPRESENTS FUNDS FROM A LEGISLATIVE DIRECTIVE. | Division 13 |  | O | CONSTRUCTION | 13434000 | FY 2029: 13434000
AV-5743 | Aviation | STI (Prioritization) | OCW | Warren Field Airport | Acquire land and construct runway 5-23 extension and taxiway. | 0 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  |  |  | 300000
AV-5743 | Aviation | STI (Prioritization) | OCW | Warren Field Airport | Acquire land and construct runway 5-23 extension and taxiway. | 0 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 2200000 | FY 2030: 2200000
AV-5743 | Aviation | STI (Prioritization) | OCW | Warren Field Airport | Acquire land and construct runway 5-23 extension and taxiway. | 0 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  | T | CONSTRUCTION | 7800000 | FY 2032: 3900000; FY 2033: 3900000
AV-5744 | Aviation | STI (Prioritization) | ACZ | Henderson Field Airport | Acquire land (phase IV) for roadway relocation; relocate SR 1307 (Wallace Airport Road) and SR 1306 (Old Mill Road); extend runway (phase I). | 0 | Pender | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | T | RIGHT-OF-WAY | 2113000
AV-5744 | Aviation | STI (Prioritization) | ACZ | Henderson Field Airport | Acquire land (phase IV) for roadway relocation; relocate SR 1307 (Wallace Airport Road) and SR 1306 (Old Mill Road); extend runway (phase I). | 0 | Pender | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 8700000
AV-5744A | Aviation | STI (Prioritization) | ACZ | Henderson Field Airport | Extend runway to 5500 feet |  | Pender | 3 | Cape Fear RPO |  | Division 3 |  | T | CONSTRUCTION | 4405000 | FY 2027: 2205000; FY 2028: 2200000
AV-5745 | Aviation | STI (Prioritization) | JNX | Johnston County Airport | Acquire and clear land. |  | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | Division 4 |  | T | ENGINEERING | 195000
AV-5745 | Aviation | STI (Prioritization) | JNX | Johnston County Airport | Acquire and clear land. |  | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | Division 4 |  | T | CONSTRUCTION | 2664000
AV-5746 | Aviation | STI (Prioritization) | MRH | Michael J. Smith Field | Construct full parallel taxiway 8-26. |  | Carteret | 2 | Down East RPO | COMPLETE | Division 2 |  |  |  | 2621000
AV-5747 | Aviation | STI (Prioritization) | LBT | Lumberton Regional Airport | Construct partial parallel taxiway. |  | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 2600000
AV-5748 | Aviation | STI (Prioritization) | CPC | Columbus County Airport | Construct apron expansion. |  | Columbus | 6 | Cape Fear RPO |  | Division 6 |  | T | CONSTRUCTION | 3000000
AV-5753 | Aviation | STI (Prioritization) | IPJ | Lincolnton-Lincoln County Airport | Remove obstructions on Runway 5 approach. |  | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | RIGHT-OF-WAY | 295000
AV-5755 | Aviation | STI (Prioritization) | IPJ | Lincolnton-Lincoln County Airport | Acquire land for Runway 5 approach. |  | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | RIGHT-OF-WAY | 176000
AV-5761 | Aviation | STI (Prioritization) | RCZ | Richmond County Airport | Clear obstructions in runway 14 approach. |  | Richmond | 8 | Lumber River RPO |  | Division 8 |  | T | CONSTRUCTION | 570000 | FY 2026: 570000
AV-5762 | Aviation | STI (Prioritization) | TTA | Raleigh Executive Sanford - Lee County Airport | Construct corporate area apron phase I. |  | Lee | 8 | Central Pines RPO | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING | Division 8 |  |  |  | 3996000
AV-5788 | Aviation | STI (Prioritization) | MCZ | Martin County Airport | Construct taxi lanes and apron. |  | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | T | CONSTRUCTION | 1250000
AV-5798 | Aviation | STI (Prioritization) | ILM | Wilmington International Airport | Improve taxiways. |  | New Hanover | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | T | CONSTRUCTION | 500000 | FY 2028: 500000
AV-5798 | Aviation | STI (Prioritization) | ILM | Wilmington International Airport | Improve taxiways. |  | New Hanover | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | O | CONSTRUCTION | 5100000 | FY 2028: 5100000
AV-5800 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Extend taxiway J from taxiway D to taxiway J2. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1000000 | FY 2027: 500000; FY 2028: 500000
AV-5800 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Extend taxiway J from taxiway D to taxiway J2. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 6000000 | FY 2027: 6000000
AV-5801 | Aviation | STI (Prioritization) | ILM | Wilmington International Airport | Expand air carrier apron. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | T | CONSTRUCTION | 500000
AV-5801 | Aviation | STI (Prioritization) | ILM | Wilmington International Airport | Expand air carrier apron. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | O | CONSTRUCTION | 3440000
AV-5802 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct northwest apron to increase capacity for future expansion. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2028: 500000; FY 2029: 500000; FY 2030: 500000
AV-5802 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct northwest apron to increase capacity for future expansion. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 9500000 | FY 2028: 9500000
AV-5803 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct taxiway F including bridge over Ted Johnson Parkway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2028: 500000; FY 2029: 500000; FY 2030: 500000
AV-5803 | Aviation | STI (Prioritization) | GSO | Piedmont Triad International Airport | Construct taxiway F including bridge over Ted Johnson Parkway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 26500000 | FY 2028: 26500000
AV-5804 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Acquire land for runway 5 protection zone extension. |  | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | T | RIGHT-OF-WAY | 300000 | FY 2026: 300000
AV-5804 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Acquire land for runway 5 protection zone extension. |  | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | O | RIGHT-OF-WAY | 397000 | FY 2026: 397000
AV-5805 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Acquire land for highway relocation. |  | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | T | RIGHT-OF-WAY | 600000 | FY 2026: 300000; FY 2027: 300000
AV-5805 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Acquire land for highway relocation. |  | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | O | RIGHT-OF-WAY | 61000 | FY 2026: 61000
AV-5806 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Extend runway 23 and taxiway A. |  | Onslow | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | Region B |  | T | ENGINEERING | 300000
AV-5806 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Extend runway 23 and taxiway A. |  | Onslow | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | Region B |  | T | CONSTRUCTION | 600000 | FY 2026: 300000; FY 2027: 300000
AV-5806 | Aviation | STI (Prioritization) | OAJ | Albert J. Ellis Airport | Extend runway 23 and taxiway A. |  | Onslow | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | Region B |  | O | CONSTRUCTION | 12580000 | FY 2026: 12580000
AV-5811 | Aviation | STI (Prioritization) | W40 | Mount Olive Municipal Airport | Extend runway to 5500 feet. |  | Wayne | 4 | Eastern Carolina RPO |  | Division 4 |  | T | CONSTRUCTION | 1200000 | FY 2029: 1200000
AV-5812 | Aviation | STI (Prioritization) | 7W6 | Hyde County Airport | Extend runway to 5500 feet. |  | Hyde | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  |  |  | 200000
AV-5812 | Aviation | STI (Prioritization) | 7W6 | Hyde County Airport | Extend runway to 5500 feet. |  | Hyde | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | T | CONSTRUCTION | 1800000
AV-5815 | Aviation | STI (Prioritization) | ACZ | Henderson Field Airport | Expand apron. |  | Pender | 3 | Cape Fear RPO |  | Division 3 |  | T | CONSTRUCTION | 8900000 | FY 2027: 2848000; FY 2028: 4539000; FY 2029: 1513000
AV-5817 | Aviation | STI (Prioritization) | VUJ | Stanly County Airport | Acquire land for expansion and perform ESA to determine status of structures on property. Clear and grub land required for expansion and demolish houses on property acquired. |  | Stanly | 10 | Rocky River RPO |  | Division 10 |  | T | RIGHT-OF-WAY | 3234000
AV-5817 | Aviation | STI (Prioritization) | VUJ | Stanly County Airport | Acquire land for expansion and perform ESA to determine status of structures on property. Clear and grub land required for expansion and demolish houses on property acquired. |  | Stanly | 10 | Rocky River RPO |  | Division 10 |  | T | CONSTRUCTION | 1500000 | FY 2027: 1500000
AV-5818 | Aviation | STI (Prioritization) | TDF | Person County Executive Airport | Extend runway to total length of 7,000 feet, construct taxiway extension, and relocate SR 1311 (Cates Mill Road). |  | Person | 5 | Kerr-Tar RPO |  | Division 5 |  |  |  | 1123000
AV-5818 | Aviation | STI (Prioritization) | TDF | Person County Executive Airport | Extend runway to total length of 7,000 feet, construct taxiway extension, and relocate SR 1311 (Cates Mill Road). |  | Person | 5 | Kerr-Tar RPO |  | Division 5 |  | T | CONSTRUCTION | 15200000 | FY 2026: 6000000; FY 2027: 6000000; FY 2028: 3200000
AV-5819 | Aviation | STI (Prioritization) | LHZ | Triangle North Executive Airport | Extend runway including relocation of utilities, navigation aids, and roadways. |  | Franklin | 5 | Capital Area MPO |  | Division 5 |  | T | ENGINEERING | 770000
AV-5819 | Aviation | STI (Prioritization) | LHZ | Triangle North Executive Airport | Extend runway including relocation of utilities, navigation aids, and roadways. |  | Franklin | 5 | Capital Area MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 3500000 | FY 2026: 3500000
AV-5819 | Aviation | STI (Prioritization) | LHZ | Triangle North Executive Airport | Extend runway including relocation of utilities, navigation aids, and roadways. |  | Franklin | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 26000000 | FY 2031: 6500000; FY 2032: 6500000; FY 2033: 6500000; FY 2034: 6500000
AV-5822 | Aviation | STI (Prioritization) | IXA | Halifax Northampton Regional Airport | Construct taxi lane and preparation for additional T-hangars. |  | Halifax | 4 | Peanut Belt RPO |  | Division 4 |  | T | CONSTRUCTION | 1400000
AV-5823 | Aviation | STI (Prioritization) | CTZ | Clinton Sampson County Airport | Rehabilitate runway. |  | Sampson | 3 | Mid-Carolina RPO |  | Division 3 |  | T | ENGINEERING | 232000
AV-5823 | Aviation | STI (Prioritization) | CTZ | Clinton Sampson County Airport | Rehabilitate runway. |  | Sampson | 3 | Mid-Carolina RPO |  | Division 3 |  | T | CONSTRUCTION | 4400000 | FY 2026: 3400000
AV-5826 | Aviation | STI (Prioritization) | EYF | Curtis L Brown Jr. Field | Extend runway to 5500 feet and parallel taxiway. |  | Bladen | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY
AV-5826 | Aviation | STI (Prioritization) | EYF | Curtis L Brown Jr. Field | Extend runway to 5500 feet and parallel taxiway. |  | Bladen | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 920000 | FY 2032: 920000
AV-5826 | Aviation | STI (Prioritization) | EYF | Curtis L Brown Jr. Field | Extend runway to 5500 feet and parallel taxiway. |  | Bladen | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9200000
AV-5831 | Aviation | STI (Prioritization) | EXX | Davidson County Airport | Upgrade and strengthen runway to accommodate larger private aircraft. |  | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH AV-5900. | Division 9 |  |  |  | 600000
AV-5831 | Aviation | STI (Prioritization) | EXX | Davidson County Airport | Upgrade and strengthen runway to accommodate larger private aircraft. |  | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH AV-5900. | Division 9 |  | T | CONSTRUCTION | 14551000
AV-5832 | Aviation | STI (Prioritization) | INT | Smith Reynolds Airport | Construct new taxilane. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 4551000
AV-5832 | Aviation | STI (Prioritization) | INT | Smith Reynolds Airport | Construct new taxilane. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 15700000 | FY 2028: 2000000; FY 2029: 7000000; FY 2030: 6700000
AV-5833 | Aviation | STI (Prioritization) | IXA | Halifax Northampton Regional Airport | Construct taxi lanes and apron. |  | Halifax | 4 | Peanut Belt RPO |  | Division 4 |  | T | ENGINEERING | 221000
AV-5833 | Aviation | STI (Prioritization) | IXA | Halifax Northampton Regional Airport | Construct taxi lanes and apron. |  | Halifax | 4 | Peanut Belt RPO |  | Division 4 |  | T | CONSTRUCTION | 2500000 | FY 2026: 2500000
AV-5848 | Aviation | STI (Prioritization) | GEV | Ashe County Airport | Expand aprons. |  | Ashe | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | T | CONSTRUCTION | 2700000
AV-5850 | Aviation | STI (Prioritization) | 1A5 | Macon County Airport | Extend runway. |  | Macon | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 430000
AV-5850 | Aviation | STI (Prioritization) | 1A5 | Macon County Airport | Extend runway. |  | Macon | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 13400000
AV-5851 | Aviation | STI (Prioritization) | BUY | Burlington-Alamance Regional Airport | Construct 100 foot paved overrun and make safety enhancements. |  | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | T | CONSTRUCTION | 6600000 | FY 2029: 3300000; FY 2030: 3300000
AV-5853 | Aviation | STI (Prioritization) | RCZ | Richmond County Airport | Construct east ramp expansion. |  | Richmond | 8 | Lumber River RPO |  | Division 8 |  | T | CONSTRUCTION | 2000000 | FY 2026: 1600000; FY 2027: 400000
AV-5855 | Aviation | STI (Prioritization) | SOP | Moore County Airport | Construct hangar taxiways and internal airfield service road. |  | Moore | 8 | Sandhills MPO | UNDER CONSTRUCTION | Division 8 |  |  |  | 300000
AV-5855 | Aviation | STI (Prioritization) | SOP | Moore County Airport | Construct hangar taxiways and internal airfield service road. |  | Moore | 8 | Sandhills MPO | UNDER CONSTRUCTION | Division 8 |  | T | CONSTRUCTION | 2900000
AV-5859 | Aviation | STI (Prioritization) | MWK | Mount Airy-Surry County Airport | Construct general aviation apron and aircraft storage hangars. |  | Surry | 11 | Northwest Piedmont RPO | COMPLETE. | Division 11 |  |  |  | 2180000
AV-5859 | Aviation | STI (Prioritization) | MWK | Mount Airy-Surry County Airport | Construct general aviation apron and aircraft storage hangars. |  | Surry | 11 | Northwest Piedmont RPO | COMPLETE. | Division 11 |  | T | CONSTRUCTION | 4000000
AV-5879 | Aviation | STI (Prioritization) | CLT | Charlotte Douglas International Airport | Construct fourth parallel runway. |  | Mecklenburg | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | T | CONSTRUCTION | 2000000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5879 | Aviation | STI (Prioritization) | CLT | Charlotte Douglas International Airport | Construct fourth parallel runway. |  | Mecklenburg | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | O | CONSTRUCTION | 607000000
AV-5881 | Aviation | STI (Prioritization) | CLT | Charlotte Douglas International Airport | Expand west ramp near Concourse A. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | T | CONSTRUCTION | 500000
AV-5881 | Aviation | STI (Prioritization) | CLT | Charlotte Douglas International Airport | Expand west ramp near Concourse A. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | O | CONSTRUCTION | 39600000
AV-5885 | Aviation | STI (Prioritization) | ILM | Wilmington International Airport | Rehabilitate runway. |  | New Hanover | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | T | CONSTRUCTION | 500000 | FY 2027: 500000
AV-5885 | Aviation | STI (Prioritization) | ILM | Wilmington International Airport | Rehabilitate runway. |  | New Hanover | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | O | CONSTRUCTION | 7000000 | FY 2027: 7000000
AV-5890 | Aviation | STI (Prioritization) | JQF | Concord-Padgett Regional Airport | Rehabilitate pavement on airport apron and taxiway. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. | Region E |  | T | CONSTRUCTION | 300000
AV-5892 | Aviation | STI (Prioritization) | JQF | Concord-Padgett Regional Airport | Expand north airport apron. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT | Region E |  | T | CONSTRUCTION | 300000
AV-5892 | Aviation | STI (Prioritization) | JQF | Concord-Padgett Regional Airport | Expand north airport apron. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT | Region E |  | O | CONSTRUCTION | 1870000
AV-5894 | Aviation | STI (Prioritization) | UKF | Wilkes County Airport | Extend runway to 7,000 feet. |  | Wilkes | 11 | High Country RPO |  | Division 11 |  | T | RIGHT-OF-WAY | 600000 | FY 2026: 600000
AV-5894 | Aviation | STI (Prioritization) | UKF | Wilkes County Airport | Extend runway to 7,000 feet. |  | Wilkes | 11 | High Country RPO |  | Division 11 |  | T | CONSTRUCTION | 12300000 | FY 2027: 3000000; FY 2028: 6000000; FY 2029: 3300000
AV-5896 | Aviation | STI (Prioritization) | SVH | Statesville Regional Airport | Relocate East Aviation Drive to allow for future runway extension. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7000000
AV-5896 | Aviation | STI (Prioritization) | SVH | Statesville Regional Airport | Relocate East Aviation Drive to allow for future runway extension. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4700000
AV-5898 | Aviation | STI (Prioritization) | SIF | Rockingham County / NC Shiloh Airport | Construct t-hangar taxilanes for addition of t-hangars. |  | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | T | CONSTRUCTION | 810000
AV-5899 | Aviation | STI (Prioritization) | TTA | Raleigh Executive Sanford - Lee County Airport | Construct airplane run-up lane at each end of runway 21 and runway 3 bypass taxiway. |  | Lee | 8 | Central Pines RPO |  | Division 8 |  | T | CONSTRUCTION | 4199000
AV-5900 | Aviation | STI (Prioritization) | EXX | Davidson County Airport | Upgrade taxiway and apron. |  | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION, LET WITH AV-5831. FUNDING SHOWN UNDER PROJECT AV-5831 | Division 9
B-2500 | Highway | Pre-STI (Historic) | NC 12 | Bridge 270011 (Herbert C. Bonner Bridge) over Oregon Inlet. | Replace bridge and construct NC 12 improvements. | 2.7 | Dare | 1 | Albemarle RPO |  | Pre-STI (Transition) |  |  |  | 513209000
B-2500AB | Highway | Pre-STI (Historic) | NC 12 | Bridge 270011 (Herbert C. Bonner Bridge) over Oregon Inlet. | Construct short-term improvements at Pea Island. |  | Dare | 1 | Albemarle RPO | COMPLETE. | Pre-STI (Transition)
B-2500B | Highway | Transition | NC 12 | Rodanthe. | Improve NC 12. |  | Dare | 1 | Albemarle RPO | COMPLETE. | Pre-STI (Transition) |  | BGLT5 | CONSTRUCTION | 1040000
B-2500B | Highway | Transition | NC 12 | Rodanthe. | Improve NC 12. |  | Dare | 1 | Albemarle RPO | COMPLETE. | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 260000
B-3186 | Highway | Bridges | US 23 / US 74 | Bridges 430155 and 430158 over Richland Creek. | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-5898. | Statewide Mobility |  | BG5T50 | RIGHT-OF-WAY | 800000
B-3186 | Highway | Bridges | US 23 / US 74 | Bridges 430155 and 430158 over Richland Creek. | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-5898. | Statewide Mobility |  | BG5T50 | CONSTRUCTION | 29145000
B-4069 | Highway | Bridges | SR 1326 (Joe Brown Highway) | Bridge 190159 over Hanging Dog Creek | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  |  |  | 297000
B-4069 | Highway | Bridges | SR 1326 (Joe Brown Highway) | Bridge 190159 over Hanging Dog Creek | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 295000
B-4069 | Highway | Bridges | SR 1326 (Joe Brown Highway) | Bridge 190159 over Hanging Dog Creek | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2027: 1062000; FY 2028: 738000
B-4182 | Highway | Bridges | SR 1503 (Laurel Valley) | Bridge 560246 over Laurel Creek. | Replace bridge. | 0.25 | Madison | 13 | French Broad River MPO, Land-of-Sky RPO | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105) | Division 13 |  |  |  | 327000
B-4410 | Highway | Bridges | SR 1627 (Pinkston River Road) | Bridge 030307 over WSSB Railroad. | Replace bridge. | 0.25 | Anson | 10 | Rocky River RPO | COMPLETE. LOCAL FUNDING PROVIDED BY TOWN OF ANSONVILLE
B-4410A | Highway | Bridges | SR 1627 (Pinkston River Road) | Bridge 030307 in the Town of Ansonville. | Install waterline per utility construction agreement. |  | Anson | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | T | RIGHT-OF-WAY | 25000
B-4410A | Highway | Bridges | SR 1627 (Pinkston River Road) | Bridge 030307 in the Town of Ansonville. | Install waterline per utility construction agreement. |  | Anson | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | T | CONSTRUCTION | 945000 | FY 2027: 795000; FY 2028: 150000
B-4410A | Highway | Bridges | SR 1627 (Pinkston River Road) | Bridge 030307 in the Town of Ansonville. | Install waterline per utility construction agreement. |  | Anson | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | L | CONSTRUCTION | 68000 | FY 2029: 68000
B-4439 | Highway | Bridges | SR 1342 (Makatoka Road Northwest) | Bridge 090100 over Muddy Branch. | Replace bridge. | 0.25 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 179000
B-4439 | Highway | Bridges | SR 1342 (Makatoka Road Northwest) | Bridge 090100 over Muddy Branch. | Replace bridge. | 0.25 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 550000
B-4439 | Highway | Bridges | SR 1342 (Makatoka Road Northwest) | Bridge 090100 over Muddy Branch. | Replace bridge. | 0.25 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 1250000
B-4442 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 18000
B-4442 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 4000
B-4442 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | NHPB | RIGHT-OF-WAY | 320000
B-4442 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 80000
B-4442 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | NHPB | CONSTRUCTION | 23997000
B-4442 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100370 and 100373 over Reems Creek. | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 5999000
B-4443 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 560000 | FY 2028: 560000
B-4443 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 140000 | FY 2028: 140000
B-4443 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | BFP | UTILITIES | 528000 | FY 2028: 528000
B-4443 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | T(M) | UTILITIES | 132000 | FY 2028: 132000
B-4443 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | BFP | CONSTRUCTION | 40080000 | FY 2031: 5210000; FY 2032: 10020000; FY 2033: 9619000; FY 2034: 8417000; FY 2035: 6814000
B-4443 | Highway | Bridges | US 19 / US 23 / US 25 / US 70 | Bridges 100345 and 100346 over SR 1839 (Old Marshall Highway). | Replace bridges. | 0.25 | Buncombe | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | T(M) | CONSTRUCTION | 10020000 | FY 2031: 1303000; FY 2032: 2505000; FY 2033: 2405000; FY 2034: 2104000; FY 2035: 1703000
B-4484 | Highway | Bridges | SR 1470 (Maple Cypress Road) | Bridges 240138 and 240139 over Neuse River. | Replace bridges. | 0.25 | Craven | 2 | Down East RPO | UNDER CONSTRUCTION. | Division 2 |  | T | CONSTRUCTION | 18700000
B-4491 | Highway | Bridges | NC 59 | Bridge 250022 over I-95 Business / US 301. | Replace bridge. | 0.25 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Region C |  |  |  | 18036000
B-4491 | Highway | Bridges | NC 59 | Bridge 250022 over I-95 Business / US 301. | Replace bridge. | 0.25 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Region C |  | T(M) |  | 4509000
B-4491 | Highway | Bridges | NC 59 | Bridge 250022 over I-95 Business / US 301. | Replace bridge. | 0.25 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Region C |  | NHPB | CONSTRUCTION | 2826000
B-4491 | Highway | Bridges | NC 59 | Bridge 250022 over I-95 Business / US 301. | Replace bridge. | 0.25 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Region C |  | T(M) | CONSTRUCTION | 707000
B-4562 | Highway | Bridges | SR 2143 (Beulahtown Road) | Bridge 500216 over Little Buffalo Creek. | Replace bridge. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. | Division 4 |  |  |  | 3416000
B-4566 | Highway | Bridges | NC 903 | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | BFP | RIGHT-OF-WAY | 210000 | FY 2027: 210000
B-4566 | Highway | Bridges | NC 903 | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | T(M) | RIGHT-OF-WAY | 52000 | FY 2027: 52000
B-4566 | Highway | Bridges | NC 903 | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | BFP | UTILITIES | 103000 | FY 2027: 103000
B-4566 | Highway | Bridges | NC 903 | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | T(M) | UTILITIES | 26000 | FY 2027: 26000
B-4566 | Highway | Bridges | NC 903 | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | BFP | CONSTRUCTION | 5200000 | FY 2030: 2600000; FY 2031: 2600000
B-4566 | Highway | Bridges | NC 903 | Bridge 530045 over Neuse River. | Replace bridge. | 0.25 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | T(M) | CONSTRUCTION | 1300000 | FY 2030: 650000; FY 2031: 650000
B-4593 | Highway | Bridges | NC 55 | Bridge 680038 over Trent Creek. | Replace bridge. | 0.25 | Pamlico | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | NHPB | CONSTRUCTION | 4910000
B-4593 | Highway | Bridges | NC 55 | Bridge 680038 over Trent Creek. | Replace bridge. | 0.25 | Pamlico | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 1227000
B-4635 | Highway | Bridges | US 13 | Bridge 810009 over South River Overflow. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 2250000
B-4636 | Highway | Bridges | NC 24 | Bridge 810056 over Six Runs Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  |  |  | 135000
B-4636 | Highway | Bridges | NC 24 | Bridge 810056 over Six Runs Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HFB | RIGHT-OF-WAY | 390000
B-4636 | Highway | Bridges | NC 24 | Bridge 810056 over Six Runs Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | CONSTRUCTION | 9900000 | FY 2031: 990000; FY 2032: 4158000; FY 2033: 3168000; FY 2034: 1584000
B-4654 | Highway | Bridges | NC 50 | Bridge 910069 over US 70 in Garner. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | BFP | CONSTRUCTION | 10824000
B-4654 | Highway | Bridges | NC 50 | Bridge 910069 over US 70 in Garner. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 2706000
B-4676A | Highway | Bridges | SR 1001 (Oakwoods Road) | Bridge 960029 over Cub Creek. | Replace bridge. |  | Wilkes | 11 | High Country RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 11 |  | BGOFF | CONSTRUCTION | 8800000 | FY 2026: 88000; FY 2027: 3432000; FY 2028: 2992000; FY 2029: 2024000; FY 2030: 264000
B-4722 | Highway | Bridges | US 70 | Bridge 150033 over North River. | Replace bridge. | 0.25 | Carteret | 2 | Down East RPO |  | Region B |  |  |  | 17337000
B-4722A | Highway | Bridges | US 70 | Bridge 150033 over North River. | Repair bridge to serve as detour route for B-4722B. | 0.25 | Carteret | 2 | Down East RPO | COMPLETE.
B-4722B | Highway | Transition | US 70 | Bridge 150033 over North River. | Replace bridge. |  | Carteret | 2 | Down East RPO | COMPLETE. | Region B
B-4786 | Highway | Bridges | US 13 | Bridge 730038 over Tar River in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | NHPB | CONSTRUCTION | 7760000
B-4786 | Highway | Bridges | US 13 | Bridge 730038 over Tar River in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 1940000
B-4844 | Highway | Bridges | SR 1958 (Bennetts Bridge Road) | Bridge 950117 over Northeast Cape Fear River. | Replace bridge. | 0.25 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Highway Fund |  |  |  | 507000
B-4844 | Highway | Bridges | SR 1958 (Bennetts Bridge Road) | Bridge 950117 over Northeast Cape Fear River. | Replace bridge. | 0.25 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Highway Fund |  | HFB | CONSTRUCTION | 1200000
B-4863 | Highway | Bridges | SR 1335 (Island Road) | Bridges 150073 and 150096 over the Straits at Harkers Island. | Replace lift spans. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  |  |  | 7788000
B-4863 | Highway | Bridges | SR 1335 (Island Road) | Bridges 150073 and 150096 over the Straits at Harkers Island. | Replace lift spans. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  | T | BUILD NC CON | 21240000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000
B-4863 | Highway | Bridges | SR 1335 (Island Road) | Bridges 150073 and 150096 over the Straits at Harkers Island. | Replace lift spans. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  | DP | CONSTRUCTION | 1000000
B-4863 | Highway | Bridges | SR 1335 (Island Road) | Bridges 150073 and 150096 over the Straits at Harkers Island. | Replace lift spans. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  | T | CONSTRUCTION | 51495000
B-4931 | Highway | Bridges | US 258 | Bridge 320022 over Town Creek. | Replace bridge. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 2129000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  |  |  | 1028000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) |  | 257000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | BFP | RIGHT-OF-WAY | 144000 | FY 2027: 144000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | RIGHT-OF-WAY | 36000 | FY 2027: 36000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | BFP | UTILITIES | 440000 | FY 2027: 440000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | UTILITIES | 110000 | FY 2027: 110000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | BFP | CONSTRUCTION | 14652000 | FY 2031: 2664000; FY 2032: 5328000; FY 2033: 4292000; FY 2034: 2368000
B-4933 | Highway | Bridges | NC 33 | Bridge 320080 over Tar River and bridge 320049 over Tar River overflow. | Replace bridges. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 3663000 | FY 2031: 666000; FY 2032: 1332000; FY 2033: 1073000; FY 2034: 592000
B-4937 | Highway | Bridges | I-95 | Bridges 500118 and 500119 over CSX railroad. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 9399000 | FY 2030: 334000; FY 2031: 2005000; FY 2032: 2005000; FY 2033: 2005000; FY 2034: 3050000
B-4937 | Highway | Bridges | I-95 | Bridges 500118 and 500119 over CSX railroad. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T | UTILITIES | 300000 | FY 2030: 300000
B-4937 | Highway | Bridges | I-95 | Bridges 500118 and 500119 over CSX railroad. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T | CONSTRUCTION | 34400000 | FY 2034: 8600000; FY 2035: 17200000 | 8600000
B-4958 | Highway | Bridges | SR 2128 (Bunch Road) | Bridge 400106 over Reedy Fork Creek in Oak Ridge. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 1240000
B-4960 | Highway | Transition | SR 3058 (Judge Adams Road) | Bridge 400214 over Little Alamance Creek. | Replace bridge. | 0.25 | Guilford | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 3514000
B-4977 | Highway | Bridges | SR 1313 (Congo Road) | Bridge 960075 over Fish Dam Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | CONSTRUCTION | 700000
B-4979 | Highway | Bridges | US 21 Business | Bridge 980059 over Jonesville Creek. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | Highway Fund |  | HFB | CONSTRUCTION | 1600000
B-5007 | Highway | Municipal Bridge | West First Street | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 604000
B-5007 | Highway | Municipal Bridge | West First Street | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | ENGINEERING | 169000 | FY 2026: 169000
B-5007 | Highway | Municipal Bridge | West First Street | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 42000 | FY 2026: 42000
B-5007 | Highway | Municipal Bridge | West First Street | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | RIGHT-OF-WAY | 600000
B-5007 | Highway | Municipal Bridge | West First Street | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 7066000 | FY 2026: 7066000
B-5007 | Highway | Municipal Bridge | West First Street | Bridge 330296 over Norfolk Southern Railway in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 1767000 | FY 2026: 1767000
B-5013 | Highway | Municipal Bridge | Depot Street | Bridge 430262 over Richland Creek in Waynesville. | Replace Bridge. | 0.25 | Haywood | 14 | French Broad River MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY THE TOWN OF WAYNESVILLE - MUNICIPAL BRIDGE | Division 14
B-5123 | Highway | Bridges | US 29 | Bridges 120014 and 120019 over Rocky River and Access Road. | Replace bridges. | 0.322 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE | Region E |  |  |  | 10000000
B-5130 | Highway | Bridges | SR 1321 (Avent Ferry Road) | Bridge 910318 over Lake Johnson in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  |  |  | 391000
B-5130 | Highway | Bridges | SR 1321 (Avent Ferry Road) | Bridge 910318 over Lake Johnson in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T(M) |  | 98000
B-5130 | Highway | Bridges | SR 1321 (Avent Ferry Road) | Bridge 910318 over Lake Johnson in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BFP | CONSTRUCTION | 6400000 | FY 2032: 1792000; FY 2033: 2432000; FY 2034: 1600000; FY 2035: 576000
B-5130 | Highway | Bridges | SR 1321 (Avent Ferry Road) | Bridge 910318 over Lake Johnson in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T(M) | CONSTRUCTION | 1600000 | FY 2032: 448000; FY 2033: 608000; FY 2034: 400000; FY 2035: 144000
B-5136 | Highway | Transition | US 29 / US 601 | Bridges 120066 and 120069 over Southern Railroad. | Replace bridges. | 0.25 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Region E |  |  |  | 16557000
B-5136 | Highway | Transition | US 29 / US 601 | Bridges 120066 and 120069 over Southern Railroad. | Replace bridges. | 0.25 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Region E |  | T | BUILD NC CON | 2790000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000
B-5196 | Highway | Transition | Texas Road | Bridge 100528 over Flat Creek in Montreat. | Replace municipal bridge. | 0.25 | Buncombe | 13 | French Broad River MPO | MUNICIPAL BRIDGE - COMPLETE | Division 13 |  |  |  | 869000
B-5210 | Highway | Bridges | SR 1600 (East River Road) | Bridge 340076 over Sycamore Creek. | Replace bridge. | 0.25 | Franklin | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC) | Division 5 |  |  |  | 600000
B-5237 | Highway | Transition | SR 2703 (New Bethel Church Road) | Bridge 910248 over Mahler's Creek in Garner. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  |  |  | 4024000
B-5237 | Highway | Transition | SR 2703 (New Bethel Church Road) | Bridge 910248 over Mahler's Creek in Garner. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | BUILD NC CON | 2000000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 138000
B-5310 | Highway | Bridges | SR 1817 (Bradshaw Road) | Bridge 810188 over Ward Swamp. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  |  |  | 226000
B-5310 | Highway | Bridges | SR 1817 (Bradshaw Road) | Bridge 810188 over Ward Swamp. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 100000
B-5310 | Highway | Bridges | SR 1817 (Bradshaw Road) | Bridge 810188 over Ward Swamp. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | CONSTRUCTION | 1850000
B-5318 | Highway | Bridges | SR 2044 (Ligon Mill Road) | Bridge 910126 over Smiths Creek in Wake Forest. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BFP | CONSTRUCTION | 8800000
B-5318 | Highway | Bridges | SR 2044 (Ligon Mill Road) | Bridge 910126 over Smiths Creek in Wake Forest. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 2200000
B-5323 | Highway | Bridges | SR 1442 (Dave Winston Road) | Bridge 380143 over Johnson Creek. | Replace bridge. | 0.25 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Division 5 |  | BFPOFF | CONSTRUCTION | 4183000
B-5356 | Highway | Bridges | I-40 / Business 85 / US 29 / US 70 / US 220 | Bridge 400299 over South Buffalo Creek in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | Statewide Mobility |  |  |  | 224000
B-5356 | Highway | Bridges | I-40 / Business 85 / US 29 / US 70 / US 220 | Bridge 400299 over South Buffalo Creek in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | Statewide Mobility |  | T(M) |  | 56000
B-5356 | Highway | Bridges | I-40 / Business 85 / US 29 / US 70 / US 220 | Bridge 400299 over South Buffalo Creek in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | Statewide Mobility |  | BFP | CONSTRUCTION | 9360000 | FY 2032: 3463000; FY 2033: 3276000; FY 2034: 1685000; FY 2035: 936000
B-5356 | Highway | Bridges | I-40 / Business 85 / US 29 / US 70 / US 220 | Bridge 400299 over South Buffalo Creek in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | Statewide Mobility |  | T(M) | CONSTRUCTION | 2340000 | FY 2032: 866000; FY 2033: 819000; FY 2034: 421000; FY 2035: 234000
B-5376 | Highway | Bridges | SR 1681 (Old Camden Road) | Bridge 890021 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  |  |  | 200000
B-5376 | Highway | Bridges | SR 1681 (Old Camden Road) | Bridge 890021 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGOFF | RIGHT-OF-WAY | 210000
B-5376 | Highway | Bridges | SR 1681 (Old Camden Road) | Bridge 890021 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGOFF | CONSTRUCTION | 3000000 | FY 2028: 2190000; FY 2029: 810000
B-5541 | Highway | Bridges | I-40 | Bridge 430236 over SR 1513. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. | Highway Fund
B-5546 | Highway | Bridges | SR 2481 (Low Bridge Road) | Bridge 750307 over Mount Pleasant Creek. | Replace bridge. | 0.25 | Randolph | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT | Highway Fund |  |  |  | 123000
B-5550 | Highway | Municipal Bridge | Railroad Avenue | Bridge 870102 over Kings Creek in Brevard. | Replace Bridge. | 0.25 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD | Division 14 |  |  |  | 416000
B-5550 | Highway | Municipal Bridge | Railroad Avenue | Bridge 870102 over Kings Creek in Brevard. | Replace Bridge. | 0.25 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD | Division 14 |  | BFPOFF | CONSTRUCTION | 1586000
B-5606 | Highway | Bridges | SR 1338 (Wynne Fork Road) | Bridge 710011 over Racoon Creek. | Replace bridge. | 0.25 | Perquimans | 1 | Albemarle RPO | COMPLETE. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Division 1 |  |  |  | 1622000
B-5606 | Highway | Bridges | SR 1338 (Wynne Fork Road) | Bridge 710011 over Racoon Creek. | Replace bridge. | 0.25 | Perquimans | 1 | Albemarle RPO | COMPLETE. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Division 1 |  | T | BUILD NC CON | 1545000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000
B-5610 | Highway | Bridges | NC 12 | Bridge 270008 over canal of Pamlico Sound in Hatteras. | Replace bridge. | 0.25 | Dare | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  |  |  | 100000
B-5610 | Highway | Bridges | NC 12 | Bridge 270008 over canal of Pamlico Sound in Hatteras. | Replace bridge. | 0.25 | Dare | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | NHPB | RIGHT-OF-WAY | 520000
B-5610 | Highway | Bridges | NC 12 | Bridge 270008 over canal of Pamlico Sound in Hatteras. | Replace bridge. | 0.25 | Dare | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | NHPB | UTILITIES | 460000
B-5610 | Highway | Bridges | NC 12 | Bridge 270008 over canal of Pamlico Sound in Hatteras. | Replace bridge. | 0.25 | Dare | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | BGLT5 | CONSTRUCTION | 5220000 | FY 2026: 634000
B-5612 | Highway | Bridges | NC 222 | Bridge 730024 over Tar River. | Replace bridge. | 0.25 | Pitt | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 1120000
B-5612 | Highway | Bridges | NC 222 | Bridge 730024 over Tar River. | Replace bridge. | 0.25 | Pitt | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BFP | RIGHT-OF-WAY | 1200000 | FY 2028: 1200000
B-5612 | Highway | Bridges | NC 222 | Bridge 730024 over Tar River. | Replace bridge. | 0.25 | Pitt | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BFP | CONSTRUCTION | 14000000 | FY 2031: 140000; FY 2032: 5040000; FY 2033: 4480000; FY 2034: 2940000; FY 2035: 1400000
B-5614 | Highway | Bridges | SR 1112 (Mouth of the Creek Road) | Bridge 060009 over Blounts Creek. | Replace bridge. | 0.25 | Beaufort | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  |  |  | 100000
B-5614 | Highway | Bridges | SR 1112 (Mouth of the Creek Road) | Bridge 060009 over Blounts Creek. | Replace bridge. | 0.25 | Beaufort | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BGOFF | RIGHT-OF-WAY | 319000
B-5614 | Highway | Bridges | SR 1112 (Mouth of the Creek Road) | Bridge 060009 over Blounts Creek. | Replace bridge. | 0.25 | Beaufort | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BGOFF | UTILITIES | 750000
B-5614 | Highway | Bridges | SR 1112 (Mouth of the Creek Road) | Bridge 060009 over Blounts Creek. | Replace bridge. | 0.25 | Beaufort | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BGOFF | CONSTRUCTION | 17200000 | FY 2026: 3612000; FY 2027: 8772000; FY 2028: 4816000
B-5619 | Highway | Bridges | SR 1389 (Hardy Bridge Road) | Bridge 530052 over Neuse River and bridge 530152 over Neuse River Overflow. | Replace bridges. | 0.25 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 2 |  | BGOFF | RIGHT-OF-WAY | 500000
B-5619 | Highway | Bridges | SR 1389 (Hardy Bridge Road) | Bridge 530052 over Neuse River and bridge 530152 over Neuse River Overflow. | Replace bridges. | 0.25 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 2 |  | BGOFF | CONSTRUCTION | 9170000
B-5621 | Highway | Bridges | SR 1904 (Pine Ridge Road) | Bridge 810248 over Six Runs Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 100000
B-5621 | Highway | Bridges | SR 1904 (Pine Ridge Road) | Bridge 810248 over Six Runs Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 154000
B-5621 | Highway | Bridges | SR 1904 (Pine Ridge Road) | Bridge 810248 over Six Runs Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 2500000
B-5629 | Highway | Bridges | SR 1515 (Old Mill Creek Road Southeast) | Bridge 090040 over Mill Creek. | Replace bridge. | 0.25 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 200000
B-5629 | Highway | Bridges | SR 1515 (Old Mill Creek Road Southeast) | Bridge 090040 over Mill Creek. | Replace bridge. | 0.25 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 115000
B-5629 | Highway | Bridges | SR 1515 (Old Mill Creek Road Southeast) | Bridge 090040 over Mill Creek. | Replace bridge. | 0.25 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 2759000
B-5632 | Highway | Bridges | SR 1828 (Cypress Creek Road) | Bridge 300187 over Back Swamp. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 213000
B-5632 | Highway | Bridges | SR 1828 (Cypress Creek Road) | Bridge 300187 over Back Swamp. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 190000
B-5632 | Highway | Bridges | SR 1828 (Cypress Creek Road) | Bridge 300187 over Back Swamp. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 5186000
B-5639 | Highway | Bridges | NC 11 | Bridge 300036 over Maxwell Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | RIGHT-OF-WAY | 56000
B-5639 | Highway | Bridges | NC 11 | Bridge 300036 over Maxwell Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 3422000
B-5647 | Highway | Bridges | SR 1135 (Providence Church Road) | Bridge 300052 over Rockfish Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  |  |  | 100000
B-5647 | Highway | Bridges | SR 1135 (Providence Church Road) | Bridge 300052 over Rockfish Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 60000
B-5647 | Highway | Bridges | SR 1135 (Providence Church Road) | Bridge 300052 over Rockfish Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | UTILITIES | 25000
B-5647 | Highway | Bridges | SR 1135 (Providence Church Road) | Bridge 300052 over Rockfish Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | CONSTRUCTION | 1150000
B-5655 | Highway | Bridges | NC 111 / NC 122 | Bridge 320011 over Town Creek. | Replace bridge. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 1950000
B-5662 | Highway | Bridges | NC 561 | Bridge 410093 over Conoconnara Swamp. | Replace bridge. | 0.25 | Halifax | 4 | Peanut Belt RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 2581000
B-5664 | Highway | Bridges | SR 1555 (Barbour Mill Road) | Bridge 500145 over Swift Creek. | Replace bridge. | 0.25 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 4946000
B-5666 | Highway | Bridges | US 117 | Bridge 970047 over Seaboard Coast Line Railroad. | Replace bridge. | 0.25 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 4469000
B-5671 | Highway | Bridges | NC 97 | Bridge 320087 over Swift Creek. | Replace bridge. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 2279000
B-5674 | Highway | Bridges | US 15 / US 501 Northbound | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  |  |  | 80000
B-5674 | Highway | Bridges | US 15 / US 501 Northbound | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | T(M) |  | 20000
B-5674 | Highway | Bridges | US 15 / US 501 Northbound | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 6721000 | FY 2027: 202000; FY 2028: 2621000; FY 2029: 2554000; FY 2030: 672000; FY 2031: 672000
B-5674 | Highway | Bridges | US 15 / US 501 Northbound | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 1679000 | FY 2027: 50000; FY 2028: 655000; FY 2029: 638000; FY 2030: 168000; FY 2031: 168000
B-5674 | Highway | Bridges | US 15 / US 501 Northbound | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 29440000 | FY 2030: 294000; FY 2031: 8243000; FY 2032: 8243000; FY 2033: 7066000; FY 2034: 5594000
B-5674 | Highway | Bridges | US 15 / US 501 Northbound | Bridges 310080 and 310083 over SR 1308 (Cornwallis Road) in Durham. | Replace bridge. | 0.25 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 7360000 | FY 2030: 74000; FY 2031: 2061000; FY 2032: 2061000; FY 2033: 1766000; FY 2034: 1398000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  |  |  | 80000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) |  | 20000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | BFP | RIGHT-OF-WAY | 3680000 | FY 2031: 2103000; FY 2032: 841000; FY 2033: 368000; FY 2034: 368000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 920000 | FY 2031: 526000; FY 2032: 210000; FY 2033: 92000; FY 2034: 92000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | BFP | UTILITIES | 448000 | FY 2031: 448000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | UTILITIES | 112000 | FY 2031: 112000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | BFP | CONSTRUCTION | 13361000 | FY 2033: 134000; FY 2034: 4810000; FY 2035: 3607000 | 4810000
B-5684 | Highway | Bridges | US 401 (Capital Boulevard) | Bridge 910146 over Crabtree Creek in Raleigh. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 3339000 | FY 2033: 33000; FY 2034: 1202000; FY 2035: 902000 | 1202000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 80000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) |  | 20000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | RIGHT-OF-WAY | 409000 | FY 2028: 93000; FY 2029: 80000; FY 2030: 80000; FY 2031: 78000; FY 2032: 78000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | RIGHT-OF-WAY | 101000 | FY 2028: 23000; FY 2029: 20000; FY 2030: 20000; FY 2031: 19000; FY 2032: 19000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | UTILITIES | 960000 | FY 2028: 480000; FY 2029: 480000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | UTILITIES | 240000 | FY 2028: 120000; FY 2029: 120000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | CONSTRUCTION | 12160000 | FY 2031: 3040000; FY 2032: 4378000; FY 2033: 2675000; FY 2034: 1459000; FY 2035: 608000
B-5713 | Highway | Bridges | Willow Road | Bridge 400352 over I-40 / Business 85 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | CONSTRUCTION | 3040000 | FY 2031: 760000; FY 2032: 1094000; FY 2033: 669000; FY 2034: 365000; FY 2035: 152000
B-5716 | Highway | Bridges | SR 1138 (Lindsey Bridge Road) | Bridge 780140 over Dan River. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 950000
B-5716 | Highway | Bridges | SR 1138 (Lindsey Bridge Road) | Bridge 780140 over Dan River. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGOFF | RIGHT-OF-WAY | 610000
B-5716 | Highway | Bridges | SR 1138 (Lindsey Bridge Road) | Bridge 780140 over Dan River. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGOFF | CONSTRUCTION | 15020000 | FY 2026: 11874000; FY 2027: 3146000
B-5717 | Highway | Bridges | SR 4240 (Gate City Boulevard) | Bridges 400109 and 400121 over South Buffalo Creek in Greensboro. | Replace bridges. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | Division 7 |  | HF | RIGHT-OF-WAY | 710000
B-5717 | Highway | Bridges | SR 4240 (Gate City Boulevard) | Bridges 400109 and 400121 over South Buffalo Creek in Greensboro. | Replace bridges. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | Division 7 |  | HF | UTILITIES | 165000
B-5717 | Highway | Bridges | SR 4240 (Gate City Boulevard) | Bridges 400109 and 400121 over South Buffalo Creek in Greensboro. | Replace bridges. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | Division 7 |  | BFP | CONSTRUCTION | 8957000
B-5718 | Highway | Bridges | Patton Avenue | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  |  |  | 162000
B-5718 | Highway | Bridges | Patton Avenue | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | T(M) |  | 40000
B-5718 | Highway | Bridges | Patton Avenue | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | BFP | RIGHT-OF-WAY | 174000 | FY 2027: 174000
B-5718 | Highway | Bridges | Patton Avenue | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | T(M) | RIGHT-OF-WAY | 44000 | FY 2027: 44000
B-5718 | Highway | Bridges | Patton Avenue | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | BFP | CONSTRUCTION | 2680000 | FY 2028: 1715000; FY 2029: 965000
B-5718 | Highway | Bridges | Patton Avenue | Bridge 400329 over I-40 / Business 85 / US 29 / US 70 / US 220 in Greensboro. | Replace bridge. | 0.25 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | T(M) | CONSTRUCTION | 670000 | FY 2028: 429000; FY 2029: 241000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 160000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | T(M) |  | 40000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | BGLT5 | RIGHT-OF-WAY | 150000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | T(M) | RIGHT-OF-WAY | 38000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | BGLT5 | UTILITIES | 269000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | T(M) | UTILITIES | 67000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | BGLT5 | CONSTRUCTION | 3882000
B-5721 | Highway | Bridges | SR 2177 (Dan Valley Road) | Bridge 780124 over Mayo River in Madison. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | T(M) | CONSTRUCTION | 971000
B-5722 | Highway | Bridges | SR 1169 (Island Drive) | Bridge 780277 over Big Beaver Island Creek. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  |  |  | 575000
B-5722 | Highway | Bridges | SR 1169 (Island Drive) | Bridge 780277 over Big Beaver Island Creek. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 200000
B-5722 | Highway | Bridges | SR 1169 (Island Drive) | Bridge 780277 over Big Beaver Island Creek. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 2400000 | FY 2026: 1498000
B-5723 | Highway | Bridges | SR 1158 (Jackson Lake Road) | Bridge 400054 over Richland Creek in High Point. | Replace bridge. | 0.25 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2030: 30000
B-5723 | Highway | Bridges | SR 1158 (Jackson Lake Road) | Bridge 400054 over Richland Creek in High Point. | Replace bridge. | 0.25 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | BGOFF | UTILITIES | 570000 | FY 2030: 570000
B-5723 | Highway | Bridges | SR 1158 (Jackson Lake Road) | Bridge 400054 over Richland Creek in High Point. | Replace bridge. | 0.25 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 3100000 | FY 2031: 3100000
B-5725 | Highway | Bridges | SR 1710 (Griers Church Road) | Bridge 160007 over Hyco Creek. | Replace bridge. | 0.25 | Caswell | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2030: 30000
B-5725 | Highway | Bridges | SR 1710 (Griers Church Road) | Bridge 160007 over Hyco Creek. | Replace bridge. | 0.25 | Caswell | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 2600000 | FY 2031: 1300000; FY 2032: 1300000
B-5770 | Highway | Bridges | Salisbury Ridge Road | Bridge 330243 over NC 150 in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 366000
B-5770 | Highway | Bridges | Salisbury Ridge Road | Bridge 330243 over NC 150 in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGOFF | CONSTRUCTION | 6001000
B-5772 | Highway | Bridges | SR 1724 (Hurley School Road) | Bridge 790066 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  |  |  | 100000
B-5772 | Highway | Bridges | SR 1724 (Hurley School Road) | Bridge 790066 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | BGOFF | RIGHT-OF-WAY | 77000
B-5772 | Highway | Bridges | SR 1724 (Hurley School Road) | Bridge 790066 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | BGOFF | UTILITIES | 31000
B-5772 | Highway | Bridges | SR 1724 (Hurley School Road) | Bridge 790066 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | BGOFF | CONSTRUCTION | 3009000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  |  |  | 80000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) |  | 20000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | BFP | RIGHT-OF-WAY | 88000 | FY 2031: 88000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | RIGHT-OF-WAY | 22000 | FY 2031: 22000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | BFP | UTILITIES | 280000 | FY 2031: 280000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | UTILITIES | 70000 | FY 2031: 70000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | BFP | CONSTRUCTION | 9441000 | FY 2032: 1416000; FY 2033: 3210000; FY 2034: 2549000; FY 2035: 1794000 | 472000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / Business 85 NB | Bridge 280118 over SR 3346 (North Main Street) in Lexington. | Replace bridge. | 0.25 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | CONSTRUCTION | 2359000 | FY 2032: 354000; FY 2033: 802000; FY 2034: 637000; FY 2035: 448000 | 118000
B-5783 | Highway | Bridges | US 29 / US 70 / Business 85 | Bridges 280164 and 280168 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  |  |  | 80000
B-5783 | Highway | Bridges | US 29 / US 70 / Business 85 | Bridges 280164 and 280168 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T(M) |  | 20000
B-5783 | Highway | Bridges | US 29 / US 70 / Business 85 | Bridges 280164 and 280168 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | BFP | CONSTRUCTION | 4622000
B-5783 | Highway | Bridges | US 29 / US 70 / Business 85 | Bridges 280164 and 280168 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 1156000
B-5808 | Highway | Bridges | US 29 / US 601 | Bridges 120057 and 120059 over Irish Buffalo Creek. | Replace bridges. | 0.25 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  |  |  | 100000
B-5808 | Highway | Bridges | US 29 / US 601 | Bridges 120057 and 120059 over Irish Buffalo Creek. | Replace bridges. | 0.25 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  | NHPB | RIGHT-OF-WAY | 255000
B-5808 | Highway | Bridges | US 29 / US 601 | Bridges 120057 and 120059 over Irish Buffalo Creek. | Replace bridges. | 0.25 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  | NHPB | UTILITIES | 1156000
B-5808 | Highway | Bridges | US 29 / US 601 | Bridges 120057 and 120059 over Irish Buffalo Creek. | Replace bridges. | 0.25 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  | BFP | CONSTRUCTION | 10100000
B-5811 | Highway | Bridges | SR 1434 (Rogers Road) | Bridge 830042 over Big Bear Creek. | Replace bridge. | 0.25 | Stanly | 10 | Rocky River RPO |  | Division 10 |  |  |  | 237000
B-5811 | Highway | Bridges | SR 1434 (Rogers Road) | Bridge 830042 over Big Bear Creek. | Replace bridge. | 0.25 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | BGOFF | RIGHT-OF-WAY | 15000 | FY 2028: 15000
B-5811 | Highway | Bridges | SR 1434 (Rogers Road) | Bridge 830042 over Big Bear Creek. | Replace bridge. | 0.25 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | BGOFF | CONSTRUCTION | 600000 | FY 2030: 600000
B-5825 | Highway | Bridges | NC 67 | Bridge 980035 over Yadkin River. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Region F |  |  |  | 933000
B-5825 | Highway | Bridges | NC 67 | Bridge 980035 over Yadkin River. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 12440000
B-5831 | Highway | Bridges | I-77 Northbound | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  |  |  | 80000
B-5831 | Highway | Bridges | I-77 Northbound | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) |  | 20000
B-5831 | Highway | Bridges | I-77 Northbound | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 256000
B-5831 | Highway | Bridges | I-77 Northbound | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 64000
B-5831 | Highway | Bridges | I-77 Northbound | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | CONSTRUCTION | 15576000 | FY 2026: 3582000; FY 2027: 4206000; FY 2028: 3582000; FY 2029: 2648000; FY 2030: 1558000
B-5831 | Highway | Bridges | I-77 Northbound | Bridge 850006 over NC 268, Norfolk Southern Railroad, and the Yadkin River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | CONSTRUCTION | 3894000 | FY 2026: 896000; FY 2027: 1051000; FY 2028: 896000; FY 2029: 662000; FY 2030: 389000
B-5832 | Highway | Bridges | SR 2080 (Quaker Church Road) | Bridge 850152 over Ararat River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  |  |  | 100000
B-5832 | Highway | Bridges | SR 2080 (Quaker Church Road) | Bridge 850152 over Ararat River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGOFF | RIGHT-OF-WAY | 250000 | FY 2029: 250000
B-5832 | Highway | Bridges | SR 2080 (Quaker Church Road) | Bridge 850152 over Ararat River. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGOFF | CONSTRUCTION | 4000000 | FY 2030: 1880000; FY 2031: 2120000
B-5833 | Highway | Bridges | US 21 Business | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  |  |  | 80000
B-5833 | Highway | Bridges | US 21 Business | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T(M) |  | 20000
B-5833 | Highway | Bridges | US 21 Business | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | BFP | RIGHT-OF-WAY | 1600000 | FY 2026: 160000
B-5833 | Highway | Bridges | US 21 Business | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T(M) | RIGHT-OF-WAY | 400000 | FY 2026: 40000
B-5833 | Highway | Bridges | US 21 Business | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | BFP | CONSTRUCTION | 15441000 | FY 2026: 4561000; FY 2027: 6114000; FY 2028: 4122000; FY 2029: 644000
B-5833 | Highway | Bridges | US 21 Business | Bridge 980029 over I-77. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T(M) | CONSTRUCTION | 3859000 | FY 2026: 1140000; FY 2027: 1528000; FY 2028: 1030000; FY 2029: 161000
B-5835 | Highway | Bridges | SR 1306 (Hicks Hollow Road) | Bridge 050125 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  |  |  | 100000
B-5835 | Highway | Bridges | SR 1306 (Hicks Hollow Road) | Bridge 050125 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | BGOFF | RIGHT-OF-WAY | 150000
B-5835 | Highway | Bridges | SR 1306 (Hicks Hollow Road) | Bridge 050125 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | BGOFF | UTILITIES | 160000
B-5835 | Highway | Bridges | SR 1306 (Hicks Hollow Road) | Bridge 050125 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | BGOFF | CONSTRUCTION | 2600000 | FY 2026: 1106000
B-5843 | Highway | Bridges | SR 2402 (Hoover Road) | Bridge 480020 over I-L Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  |  |  | 226000
B-5843 | Highway | Bridges | SR 2402 (Hoover Road) | Bridge 480020 over I-L Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | RIGHT-OF-WAY | 67000 | FY 2028: 67000
B-5843 | Highway | Bridges | SR 2402 (Hoover Road) | Bridge 480020 over I-L Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2030: 790000; FY 2031: 710000
B-5846 | Highway | Bridges | SR 1892 (Jennings Road) | Bridge 480189 over South Yadkin River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  |  |  | 100000
B-5846 | Highway | Bridges | SR 1892 (Jennings Road) | Bridge 480189 over South Yadkin River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | RIGHT-OF-WAY | 85000
B-5846 | Highway | Bridges | SR 1892 (Jennings Road) | Bridge 480189 over South Yadkin River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | UTILITIES | 325000
B-5846 | Highway | Bridges | SR 1892 (Jennings Road) | Bridge 480189 over South Yadkin River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | CONSTRUCTION | 5615000
B-5847 | Highway | Bridges | SR 1709 (Rock Barn Road) | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  |  |  | 80000
B-5847 | Highway | Bridges | SR 1709 (Rock Barn Road) | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | T(M) |  | 20000
B-5847 | Highway | Bridges | SR 1709 (Rock Barn Road) | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BFP | RIGHT-OF-WAY | 1120000 | FY 2026: 112000
B-5847 | Highway | Bridges | SR 1709 (Rock Barn Road) | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | T(M) | RIGHT-OF-WAY | 280000 | FY 2026: 28000
B-5847 | Highway | Bridges | SR 1709 (Rock Barn Road) | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BFP | CONSTRUCTION | 8241000 | FY 2031: 989000; FY 2032: 3049000; FY 2033: 2390000; FY 2034: 1813000
B-5847 | Highway | Bridges | SR 1709 (Rock Barn Road) | Bridge 170173 over I-40. | Replace bridge. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | T(M) | CONSTRUCTION | 2059000 | FY 2031: 247000; FY 2032: 762000; FY 2033: 597000; FY 2034: 453000
B-5858 | Highway | Bridges | SR 1607 (Eastridge Drive) | Bridge 220392 over Buffalo Creek. | Replace bridge. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGOFF | RIGHT-OF-WAY | 20000 | FY 2027: 20000
B-5858 | Highway | Bridges | SR 1607 (Eastridge Drive) | Bridge 220392 over Buffalo Creek. | Replace bridge. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGOFF | UTILITIES | 225000 | FY 2027: 225000
B-5858 | Highway | Bridges | SR 1607 (Eastridge Drive) | Bridge 220392 over Buffalo Creek. | Replace bridge. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2029: 15000; FY 2030: 1215000; FY 2031: 270000
B-5869 | Highway | Bridges | US 64 / US 70 | Bridge 110099 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  |  |  | 471000
B-5869 | Highway | Bridges | US 64 / US 70 | Bridge 110099 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BFP | RIGHT-OF-WAY | 640000
B-5869 | Highway | Bridges | US 64 / US 70 | Bridge 110099 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BGDA | RIGHT-OF-WAY | 2560000
B-5869 | Highway | Bridges | US 64 / US 70 | Bridge 110099 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BFP | UTILITIES | 270000
B-5869 | Highway | Bridges | US 64 / US 70 | Bridge 110099 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BFP | CONSTRUCTION | 25861000
B-5871 | Highway | Bridges | SR 1306 (Bills Creek Road) | Bridge 800628 over Lake Lure Dam and Broad River. | Replace bridge. | 0.25 | Rutherford | 13 | Foothills RPO |  | Division 13 |  |  |  | 200000
B-5871 | Highway | Bridges | SR 1306 (Bills Creek Road) | Bridge 800628 over Lake Lure Dam and Broad River. | Replace bridge. | 0.25 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | BGOFF | RIGHT-OF-WAY | 410000 | FY 2027: 16000; FY 2028: 189000; FY 2029: 123000; FY 2030: 41000; FY 2031: 41000
B-5871 | Highway | Bridges | SR 1306 (Bills Creek Road) | Bridge 800628 over Lake Lure Dam and Broad River. | Replace bridge. | 0.25 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | BGOFF | CONSTRUCTION | 20800000 | FY 2028: 1872000; FY 2029: 6032000; FY 2030: 5200000; FY 2031: 4160000; FY 2032: 3536000
B-5898 | Highway | Bridges | US 23 / US 74 | Bridge 430168 over US 19 and US 23. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | Statewide Mobility |  |  |  | 100000
B-5898 | Highway | Bridges | US 23 / US 74 | Bridge 430168 over US 19 and US 23. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | Statewide Mobility |  | BG5T50 | RIGHT-OF-WAY | 150000
B-5898 | Highway | Bridges | US 23 / US 74 | Bridge 430168 over US 19 and US 23. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | Statewide Mobility |  | BG5T50 | CONSTRUCTION | 20253000
B-5920 | Highway | Bridges | SR 1216 (Steel Bridge Road) | Bridge 430246 over West Fork Pigeon Creek. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Division 14 |  |  |  | 100000
B-5920 | Highway | Bridges | SR 1216 (Steel Bridge Road) | Bridge 430246 over West Fork Pigeon Creek. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 90000 | FY 2026: 90000
B-5920 | Highway | Bridges | SR 1216 (Steel Bridge Road) | Bridge 430246 over West Fork Pigeon Creek. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | UTILITIES | 80000 | FY 2026: 80000
B-5920 | Highway | Bridges | SR 1216 (Steel Bridge Road) | Bridge 430246 over West Fork Pigeon Creek. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2026: 18000; FY 2027: 1782000
B-5921 | Highway | Bridges | SR 1120 (Cedar Creek Road) | Bridge 490008 over Cedar Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  |  |  | 100000
B-5921 | Highway | Bridges | SR 1120 (Cedar Creek Road) | Bridge 490008 over Cedar Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | BGOFF | RIGHT-OF-WAY | 410000
B-5921 | Highway | Bridges | SR 1120 (Cedar Creek Road) | Bridge 490008 over Cedar Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | BGOFF | CONSTRUCTION | 2900000 | FY 2026: 1624000; FY 2027: 1276000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  |  |  | 275000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | T(M) |  | 69000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | BFP | RIGHT-OF-WAY | 528000 | FY 2026: 528000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | T(M) | RIGHT-OF-WAY | 132000 | FY 2026: 132000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | BFP | UTILITIES | 256000 | FY 2026: 256000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | T(M) | UTILITIES | 64000 | FY 2026: 64000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | BFP | CONSTRUCTION | 5200000 | FY 2027: 5200000
B-5925 | Highway | Bridges | SR 1548 (Old Highway 64) | Bridge 190223 over Hiwassee River | Replace bridge. | 0.25 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 1300000 | FY 2027: 1300000
B-5929 | Highway | Municipal Bridge | Tracy Grove Road | Bridge 440350 over Devils Fork Creek. | Replace Bridge. | 0.25 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | Division 14 |  |  |  | 205000
B-5929 | Highway | Municipal Bridge | Tracy Grove Road | Bridge 440350 over Devils Fork Creek. | Replace Bridge. | 0.25 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | Division 14 |  | BGOFF | ENGINEERING | 125000
B-5929 | Highway | Municipal Bridge | Tracy Grove Road | Bridge 440350 over Devils Fork Creek. | Replace Bridge. | 0.25 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | Division 14 |  | BFPOFF | CONSTRUCTION | 2400000 | FY 2026: 2400000
B-5930 | Highway | Municipal Bridge | Sardis Lane | Bridge 590433 over McAlpine Creek. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | Division 10 |  |  |  | 300000
B-5930 | Highway | Municipal Bridge | Sardis Lane | Bridge 590433 over McAlpine Creek. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | Division 10 |  | BGOFF | CONSTRUCTION | 1600000
B-5930 | Highway | Municipal Bridge | Sardis Lane | Bridge 590433 over McAlpine Creek. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | Division 10 |  | L(M) | CONSTRUCTION | 400000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | BGANY | ENGINEERING | 480000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | BGOFF | ENGINEERING | 377000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | BGDA | ENGINEERING | 13000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | L(M) | ENGINEERING | 217000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | L | ENGINEERING | 4000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | BGOFF | RIGHT-OF-WAY | 280000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | L(M) | RIGHT-OF-WAY | 70000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | BGOFF | CONSTRUCTION | 2192000 | FY 2026: 2192000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 1732000 | FY 2026: 1732000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | L(M) | CONSTRUCTION | 981000 | FY 2026: 981000
B-5931 | Highway | Municipal Bridge | Morris Field Drive | Bridge 590443 over Southern Railroad. | Replace Bridge. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | PLANNING/DESIGN BY CITY OF CHARLOTTE. UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 1299000 | FY 2026: 1299000
B-5937 | Highway | Bridges | US 158 | Bridge 260016 over Currituck Sound. | Rehabilitate bridge. | 3.16 | Currituck | 1 | Albemarle RPO | COMPLETE. | Statewide Mobility |  |  |  | 30100000
B-5938 | Highway | Bridges | SR 1182 (Atlantic Beach Causeway) | Bridge 150068 over Bogue Sound | Rehabilitate bridge. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | Division 2 |  |  |  | 5592000
B-5938 | Highway | Bridges | SR 1182 (Atlantic Beach Causeway) | Bridge 150068 over Bogue Sound | Rehabilitate bridge. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | Division 2 |  | T | BUILD NC CON | 6195000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000
B-5938 | Highway | Bridges | SR 1182 (Atlantic Beach Causeway) | Bridge 150068 over Bogue Sound | Rehabilitate bridge. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | Division 2 |  | T | CONSTRUCTION | 1800000
B-5939 | Highway | Bridges | NC 58 | Bridge 150006 over Bogue Sound | Rehabilitate bridge. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION | Region B |  |  |  | 4560000
B-5939 | Highway | Bridges | NC 58 | Bridge 150006 over Bogue Sound | Rehabilitate bridge. | 0.75 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION | Region B |  | T | CONSTRUCTION | 3000000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 400000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T(M) |  | 100000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BFP | RIGHT-OF-WAY | 1280000 | FY 2031: 64000; FY 2032: 717000; FY 2033: 243000; FY 2034: 128000; FY 2035: 128000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T(M) | RIGHT-OF-WAY | 320000 | FY 2031: 16000; FY 2032: 179000; FY 2033: 61000; FY 2034: 32000; FY 2035: 32000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BFP | UTILITIES | 960000 | FY 2031: 960000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T(M) | UTILITIES | 240000 | FY 2031: 240000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BFP | CONSTRUCTION | 24079000 | FY 2033: 4334000; FY 2034: 6742000; FY 2035: 5538000 | 7465000
B-5944 | Highway | Bridges | SR 1509 (Queens Creek Road) | Bridge 660077 over Queen's Creek. | Replace bridge. | 0.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T(M) | CONSTRUCTION | 6021000 | FY 2033: 1084000; FY 2034: 1686000; FY 2035: 1385000 | 1866000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  |  |  | 8000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) |  | 2000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHPB | RIGHT-OF-WAY | 320000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | RIGHT-OF-WAY | 80000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHPB | UTILITIES | 110000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | UTILITIES | 28000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHPB | CONSTRUCTION | 5730000
B-5947 | Highway | Bridges | NC 581 | Bridge 630091 over Tar River. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 1432000
B-5949 | Highway | Bridges | NC 200 | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 8000
B-5949 | Highway | Bridges | NC 200 | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T(M) |  | 2000
B-5949 | Highway | Bridges | NC 200 | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Region E |  | BFP | RIGHT-OF-WAY | 96000 | FY 2026: 96000
B-5949 | Highway | Bridges | NC 200 | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T(M) | RIGHT-OF-WAY | 24000 | FY 2026: 24000
B-5949 | Highway | Bridges | NC 200 | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Region E |  | BFP | CONSTRUCTION | 4319000 | FY 2028: 43000; FY 2029: 2419000; FY 2030: 1382000; FY 2031: 475000
B-5949 | Highway | Bridges | NC 200 | Bridge 890053 over Stewarts Creek. | Replace bridge. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T(M) | CONSTRUCTION | 1081000 | FY 2028: 11000; FY 2029: 605000; FY 2030: 346000; FY 2031: 119000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  |  |  | 10000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | BFP | RIGHT-OF-WAY | 792000 | FY 2026: 792000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | T(M) | RIGHT-OF-WAY | 198000 | FY 2026: 198000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | BFP | UTILITIES | 392000 | FY 2026: 392000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | T(M) | UTILITIES | 98000 | FY 2026: 98000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | BFP | CONSTRUCTION | 6960000 | FY 2027: 1879000; FY 2028: 2645000; FY 2029: 1740000; FY 2030: 696000
B-5950 | Highway | Bridges | NC 67 (Silas Creek Parkway) Westbound | Bridges 330007 and 330295 over Salem Creek in Winston-Salem. | Replace bridges. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | T(M) | CONSTRUCTION | 1740000 | FY 2027: 470000; FY 2028: 661000; FY 2029: 435000; FY 2030: 174000
B-5961 | Highway | Bridges | SR 1421 (Marys Grove Road) | Bridge 350097 over Unnamed Tributary of Muddy Fork Creek. | Replace bridge. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  |  |  | 600000
B-5961 | Highway | Bridges | SR 1421 (Marys Grove Road) | Bridge 350097 over Unnamed Tributary of Muddy Fork Creek. | Replace bridge. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | RIGHT-OF-WAY | 67000
B-5961 | Highway | Bridges | SR 1421 (Marys Grove Road) | Bridge 350097 over Unnamed Tributary of Muddy Fork Creek. | Replace bridge. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | CONSTRUCTION | 705000
B-5976 | Highway | Bridges | SR 1400 (Cumnock Road) | Bridges 520069 and 520070 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  |  |  | 413000
B-5976 | Highway | Bridges | SR 1400 (Cumnock Road) | Bridges 520069 and 520070 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | RIGHT-OF-WAY | 210000 | FY 2026: 210000
B-5976 | Highway | Bridges | SR 1400 (Cumnock Road) | Bridges 520069 and 520070 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | UTILITIES | 510000 | FY 2026: 510000
B-5976 | Highway | Bridges | SR 1400 (Cumnock Road) | Bridges 520069 and 520070 over Norfolk Southern Railroad. | Replace bridges. | 0.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | CONSTRUCTION | 11500000 | FY 2029: 2415000; FY 2030: 3910000; FY 2031: 2990000; FY 2032: 2185000
B-5979 | Highway | Municipal Bridge | Hunting Hills Lane | Bridge 940346 over South Fork of New River in Boone. | Replace Bridge. | 0.25 | Watauga | 11 | High Country RPO | Construction underway. | Division 11 |  |  |  | 260000
B-5979 | Highway | Municipal Bridge | Hunting Hills Lane | Bridge 940346 over South Fork of New River in Boone. | Replace Bridge. | 0.25 | Watauga | 11 | High Country RPO | Construction underway. | Division 11 |  | BGOFF | CONSTRUCTION | 4178000 | FY 2026: 738000
B-5979 | Highway | Municipal Bridge | Hunting Hills Lane | Bridge 940346 over South Fork of New River in Boone. | Replace Bridge. | 0.25 | Watauga | 11 | High Country RPO | Construction underway. | Division 11 |  | L(M) | CONSTRUCTION | 1044000 | FY 2026: 184000
B-5980 | Highway | Bridges | SR 1522 (Halifax Road) | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  |  |  | 1290000
B-5980 | Highway | Bridges | SR 1522 (Halifax Road) | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | T(M) |  | 323000
B-5980 | Highway | Bridges | SR 1522 (Halifax Road) | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | NHPB | RIGHT-OF-WAY | 1680000
B-5980 | Highway | Bridges | SR 1522 (Halifax Road) | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 420000
B-5980 | Highway | Bridges | SR 1522 (Halifax Road) | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | NHPB | CONSTRUCTION | 14400000
B-5980 | Highway | Bridges | SR 1522 (Halifax Road) | Bridge 630203 over I-95. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | T(M) | CONSTRUCTION | 3600000
B-5981 | Highway | Bridges | US 117 NBL | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  |  |  | 88000
B-5981 | Highway | Bridges | US 117 NBL | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | T(M) |  | 22000
B-5981 | Highway | Bridges | US 117 NBL | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | BGLT5 | RIGHT-OF-WAY | 354000
B-5981 | Highway | Bridges | US 117 NBL | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 89000
B-5981 | Highway | Bridges | US 117 NBL | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 8694000 | FY 2026: 522000
B-5981 | Highway | Bridges | US 117 NBL | Bridges 300016 and 300017 over CSX Railroad. | Replace bridge 300016 and bridge preservation on bridge 300017. | 0.25 | Duplin | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | T(M) | CONSTRUCTION | 2172000 | FY 2026: 130000
B-5985 | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  |  |  | 88000
B-5985 | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) |  | 22000
B-5985 | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | NHPB | RIGHT-OF-WAY | 316000
B-5985 | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) | RIGHT-OF-WAY | 79000
B-5985 | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | NHPB | UTILITIES | 388000
B-5985 | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridges 770125 and 770175 over Lumber River. | Replace bridges. | 0.25 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) | UTILITIES | 97000
B-5985A | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridge 770125 over Lumber River. | Replace bridge. | 0.25 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | BFP | CONSTRUCTION | 6332000
B-5985A | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridge 770125 over Lumber River. | Replace bridge. | 0.25 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 1583000
B-5985B | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridge 770175 over Lumber River. | Replace bridge. | 0.25 | Robeson | 6 | Lumber River RPO |  | Region C |  | BFP | CONSTRUCTION | 7200000 | FY 2026: 2520000; FY 2027: 2808000; FY 2028: 1872000
B-5985B | Highway | Bridges | NC 41 / NC 72 / SR 1600 | Bridge 770175 over Lumber River. | Replace bridge. | 0.25 | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | CONSTRUCTION | 1800000 | FY 2026: 630000; FY 2027: 702000; FY 2028: 468000
B-5986 | Highway | Bridges | NC 231 | Bridge 910034 over Norfolk Southern Railroad in Wendell. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  |  |  | 110000
B-5986 | Highway | Bridges | NC 231 | Bridge 910034 over Norfolk Southern Railroad in Wendell. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | HFB | RIGHT-OF-WAY | 1104000 | FY 2027: 1104000
B-5986 | Highway | Bridges | NC 231 | Bridge 910034 over Norfolk Southern Railroad in Wendell. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | HFB | UTILITIES | 352000 | FY 2027: 352000
B-5986 | Highway | Bridges | NC 231 | Bridge 910034 over Norfolk Southern Railroad in Wendell. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Region C |  | BFP | CONSTRUCTION | 6100000 | FY 2030: 53000; FY 2031: 2597000; FY 2032: 1908000; FY 2033: 1542000
B-5987 | Highway | Bridges | US 401 | Bridges 910115 and 910117 over Norfolk Southern Railroad and an unnamed tributary of Swift Creek. | Replace bridges. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | Region C |  | BFP | RIGHT-OF-WAY | 640000 | FY 2027: 640000
B-5987 | Highway | Bridges | US 401 | Bridges 910115 and 910117 over Norfolk Southern Railroad and an unnamed tributary of Swift Creek. | Replace bridges. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | Region C |  | BFP | UTILITIES | 640000 | FY 2027: 640000
B-5987 | Highway | Bridges | US 401 | Bridges 910115 and 910117 over Norfolk Southern Railroad and an unnamed tributary of Swift Creek. | Replace bridges. | 0.25 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | Region C |  | BFP | CONSTRUCTION | 24500000 | FY 2030: 5429000; FY 2031: 9668000; FY 2032: 6706000; FY 2033: 2697000
B-5989 | Highway | Bridges | SR 1395 (Walnut Creek Road) | Bridge 560071 over Big Laurel Creek. | Replace bridge. | 0.25 | Madison | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  |  |  | 110000
B-5989 | Highway | Bridges | SR 1395 (Walnut Creek Road) | Bridge 560071 over Big Laurel Creek. | Replace bridge. | 0.25 | Madison | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 13000
B-5989 | Highway | Bridges | SR 1395 (Walnut Creek Road) | Bridge 560071 over Big Laurel Creek. | Replace bridge. | 0.25 | Madison | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  | BGOFF | UTILITIES | 130000
B-5989 | Highway | Bridges | SR 1395 (Walnut Creek Road) | Bridge 560071 over Big Laurel Creek. | Replace bridge. | 0.25 | Madison | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 7406000
B-5995 | Highway | Bridges | SR 1302 (Janiero Road) | Bridge 680057 over Dawson Creek. | Replace bridge. | 0.25 | Pamlico | 2 | Down East RPO |  | Division 2 |  | BGOFF | RIGHT-OF-WAY | 600000
B-5995 | Highway | Bridges | SR 1302 (Janiero Road) | Bridge 680057 over Dawson Creek. | Replace bridge. | 0.25 | Pamlico | 2 | Down East RPO |  | Division 2 |  | BGOFF | CONSTRUCTION | 6300000 | FY 2026: 819000; FY 2027: 3402000; FY 2028: 2079000
B-5996 | Highway | Bridges | SR 1300 (Ash-Little River Road Northwest) | Bridge 090126 over Cawcaw Swamp. | Replace bridge. | 0.25 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 100000
B-5996 | Highway | Bridges | SR 1300 (Ash-Little River Road Northwest) | Bridge 090126 over Cawcaw Swamp. | Replace bridge. | 0.25 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 2100000
B-5998 | Highway | Bridges | SR 1339 (Sharpe Shore Road) | Bridge 970092 over Town Swamp. | Replace bridge. | 0.25 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | Division 4 |  |  |  | 778000
B-6000 | Highway | Bridges | SR 1400 (Rock Quarry Road) | Bridge 970096 over tributary of Town Creek. | Replace bridge. | 0.25 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | Division 4 |  |  |  | 873000
B-6002 | Highway | Bridges | SR 1126 (Faith Baptist Church Road) | Bridge 320064 over Town Creek. | Replace bridge. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 1200000
B-6003 | Highway | Bridges | SR 1609 (Baptist Church Road) | Bridge 340078 over Tar River. | Replace bridge. | 0.25 | Franklin | 5 | Capital Area MPO |  | Division 5 |  |  |  | 200000
B-6003 | Highway | Bridges | SR 1609 (Baptist Church Road) | Bridge 340078 over Tar River. | Replace bridge. | 0.25 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | RIGHT-OF-WAY | 430000 | FY 2029: 430000
B-6003 | Highway | Bridges | SR 1609 (Baptist Church Road) | Bridge 340078 over Tar River. | Replace bridge. | 0.25 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | CONSTRUCTION | 7600000 | FY 2031: 2584000; FY 2032: 3344000; FY 2033: 1672000
B-6005 | Highway | Bridges | SR 1210 (Hoover Road) | Bridge 420234 over Barbeque Swamp. | Replace bridge. | 0.25 | Harnett | 6 | Fayetteville Area MPO | COMPLETE. | Division 6 |  |  |  | 1465000
B-6008 | Highway | Bridges | SR 1536 (James Porter Road) | Bridge 080198 over Kelly Canal. | Replace bridge. | 0.25 | Bladen | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  |  |  | 1190000
B-6011 | Highway | Bridges | SR 1430 (Harland Road) | Bridge 110145 over Bristol Creek. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | Division 13 |  |  |  | 265000
B-6011 | Highway | Bridges | SR 1430 (Harland Road) | Bridge 110145 over Bristol Creek. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 65000
B-6011 | Highway | Bridges | SR 1430 (Harland Road) | Bridge 110145 over Bristol Creek. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 725000
B-6012 | Highway | Bridges | SR 1341 (Foster Creek Road) | Bridge 560073 over Foster Creek. | Replace bridge. | 0.25 | Madison | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 13 |  |  |  | 908000
B-6012 | Highway | Bridges | SR 1341 (Foster Creek Road) | Bridge 560073 over Foster Creek. | Replace bridge. | 0.25 | Madison | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 4440000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000
B-6012 | Highway | Bridges | SR 1341 (Foster Creek Road) | Bridge 560073 over Foster Creek. | Replace bridge. | 0.25 | Madison | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 13 |  | T | CONSTRUCTION | 388000
B-6013 | Highway | Bridges | SR 1106 (Lynn Gap Road) | Bridge 600207 over Grassy Creek. | Replace bridge. | 0.25 | Mitchell | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | Division 13 |  |  |  | 200000
B-6013 | Highway | Bridges | SR 1106 (Lynn Gap Road) | Bridge 600207 over Grassy Creek. | Replace bridge. | 0.25 | Mitchell | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | Division 13 |  | BGOFF | RIGHT-OF-WAY | 40000
B-6013 | Highway | Bridges | SR 1106 (Lynn Gap Road) | Bridge 600207 over Grassy Creek. | Replace bridge. | 0.25 | Mitchell | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | Division 13 |  | BGOFF | CONSTRUCTION | 800000
B-6014 | Highway | Bridges | SR 1781 (Polly Spout Road) | Bridge 580312 over Second Broad River. | Replace bridge. | 0.25 | McDowell | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | Division 13 |  |  |  | 200000
B-6014 | Highway | Bridges | SR 1781 (Polly Spout Road) | Bridge 580312 over Second Broad River. | Replace bridge. | 0.25 | McDowell | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 100000
B-6014 | Highway | Bridges | SR 1781 (Polly Spout Road) | Bridge 580312 over Second Broad River. | Replace bridge. | 0.25 | McDowell | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 3027000
B-6015 | Highway | Bridges | SR 1913 (Sugar Loaf Road) | Bridge 110237 over Rock Creek. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | Division 13 |  |  |  | 200000
B-6015 | Highway | Bridges | SR 1913 (Sugar Loaf Road) | Bridge 110237 over Rock Creek. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 100000
B-6015 | Highway | Bridges | SR 1913 (Sugar Loaf Road) | Bridge 110237 over Rock Creek. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 1369000
B-6016 | Highway | Bridges | SR 2027 (Martins Creek Road) | Bridge 100142 over Martin Creek. | Replace bridge. | 0.25 | Buncombe | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | Division 13 |  |  |  | 200000
B-6016 | Highway | Bridges | SR 2027 (Martins Creek Road) | Bridge 100142 over Martin Creek. | Replace bridge. | 0.25 | Buncombe | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | Division 13 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6016 | Highway | Bridges | SR 2027 (Martins Creek Road) | Bridge 100142 over Martin Creek. | Replace bridge. | 0.25 | Buncombe | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | Division 13 |  | BGOFF | CONSTRUCTION | 500000
B-6018 | Highway | Bridges | SR 1296 (Brooks Branch Road) | Bridge 100536 over Newfound Creek. | Replace bridge. | 0.25 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | Division 13 |  |  |  | 200000
B-6018 | Highway | Bridges | SR 1296 (Brooks Branch Road) | Bridge 100536 over Newfound Creek. | Replace bridge. | 0.25 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 55000
B-6018 | Highway | Bridges | SR 1296 (Brooks Branch Road) | Bridge 100536 over Newfound Creek. | Replace bridge. | 0.25 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 872000
B-6025 | Highway | Bridges | SR 1114 (Shope Road) | Bridge 550244 over North Fork Coweeta Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 255000
B-6025 | Highway | Bridges | SR 1114 (Shope Road) | Bridge 550244 over North Fork Coweeta Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 1700000
B-6026 | Highway | Bridges | SR 1500 (Watauga Road) | Bridge 550214 over Watauga Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO |  | Division 14 |  |  |  | 200000
B-6026 | Highway | Bridges | SR 1500 (Watauga Road) | Bridge 550214 over Watauga Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6026 | Highway | Bridges | SR 1500 (Watauga Road) | Bridge 550214 over Watauga Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 500000 | FY 2028: 500000
B-6028 | Highway | Bridges | SR 1528 (Little Ellijay Road) | Bridge 550150 over Ellijay Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 250000
B-6028 | Highway | Bridges | SR 1528 (Little Ellijay Road) | Bridge 550150 over Ellijay Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 2600000
B-6029 | Highway | Bridges | SR 1001 (Ellijay Road) | Bridge 550009 over North Prong Ellijay Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 200000
B-6029 | Highway | Bridges | SR 1001 (Ellijay Road) | Bridge 550009 over North Prong Ellijay Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2026: 1389000; FY 2027: 611000
B-6030 | Highway | Bridges | SR 1351 (Matlock Creek Road) | Bridge 550220 over Matlock Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  |  |  | 262000
B-6030 | Highway | Bridges | SR 1351 (Matlock Creek Road) | Bridge 550220 over Matlock Creek. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | BGOFF | CONSTRUCTION | 1301000 | FY 2029: 949000; FY 2030: 352000
B-6031 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490069 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  |  |  | 200000
B-6031 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490069 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 64000
B-6031 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490069 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | T(M) | RIGHT-OF-WAY | 16000
B-6031 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490069 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1920000 | FY 2029: 1459000; FY 2030: 461000
B-6031 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490069 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 480000 | FY 2029: 365000; FY 2030: 115000
B-6032 | Highway | Bridges | SR 1397 (Thomas Valley Road) | Bridge 490144 over Nations Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | Division 14 |  |  |  | 200000
B-6032 | Highway | Bridges | SR 1397 (Thomas Valley Road) | Bridge 490144 over Nations Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6032 | Highway | Bridges | SR 1397 (Thomas Valley Road) | Bridge 490144 over Nations Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | Division 14 |  | BGOFF | CONSTRUCTION | 983000
B-6033 | Highway | Bridges | SR 1445 (Lee Bumgarner Road) | Bridge 490129 over Scott Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  |  |  | 320000
B-6033 | Highway | Bridges | SR 1445 (Lee Bumgarner Road) | Bridge 490129 over Scott Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | BGOFF | CONSTRUCTION | 2400000 | FY 2029: 1272000; FY 2030: 1128000
B-6033 | Highway | Bridges | SR 1445 (Lee Bumgarner Road) | Bridge 490129 over Scott Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | T(M) | CONSTRUCTION | 600000 | FY 2029: 318000; FY 2030: 282000
B-6034 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490065 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  |  |  | 200000
B-6034 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490065 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 70000
B-6034 | Highway | Bridges | SR 1300 (Pumpkintown Road) | Bridge 490065 over Savannah Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2026: 1080000; FY 2027: 720000
B-6035 | Highway | Bridges | SR 1738 (Hooper Cemetery Road) | Bridge 490203 over Caney Fork. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 200000
B-6035 | Highway | Bridges | SR 1738 (Hooper Cemetery Road) | Bridge 490203 over Caney Fork. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | RIGHT-OF-WAY | 70000
B-6035 | Highway | Bridges | SR 1738 (Hooper Cemetery Road) | Bridge 490203 over Caney Fork. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 1495000
B-6036 | Highway | Bridges | SR 1737 (Caney Fork Road) | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  |  |  | 200000
B-6036 | Highway | Bridges | SR 1737 (Caney Fork Road) | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 410000 | FY 2026: 410000
B-6036 | Highway | Bridges | SR 1737 (Caney Fork Road) | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | UTILITIES | 48000 | FY 2026: 48000
B-6036 | Highway | Bridges | SR 1737 (Caney Fork Road) | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | T(M) | UTILITIES | 12000 | FY 2026: 12000
B-6036 | Highway | Bridges | SR 1737 (Caney Fork Road) | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1520000 | FY 2027: 15000; FY 2028: 1505000
B-6036 | Highway | Bridges | SR 1737 (Caney Fork Road) | Bridge 490081 over Johns Creek. | Replace bridge. | 0.25 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 380000 | FY 2027: 4000; FY 2028: 376000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  |  |  | 80000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) |  | 20000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | BFP | RIGHT-OF-WAY | 2160000 | FY 2026: 576000; FY 2027: 216000; FY 2028: 216000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) | RIGHT-OF-WAY | 540000 | FY 2026: 144000; FY 2027: 54000; FY 2028: 54000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | BFP | UTILITIES | 776000 | FY 2026: 388000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) | UTILITIES | 194000 | FY 2026: 97000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | BFP | CONSTRUCTION | 9120000 | FY 2027: 1550000; FY 2028: 4013000; FY 2029: 2189000; FY 2030: 1368000
B-6037 | Highway | Bridges | NC 86 | Bridge 670049 over North Carolina Railroad / Norfolk Southern Railroad. | Replace bridge. | 0.25 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) | CONSTRUCTION | 2280000 | FY 2027: 388000; FY 2028: 1003000; FY 2029: 547000; FY 2030: 342000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  |  |  | 100000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | BFP | RIGHT-OF-WAY | 368000 | FY 2026: 368000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | T(M) | RIGHT-OF-WAY | 92000 | FY 2026: 92000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | BFP | UTILITIES | 608000 | FY 2026: 608000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | T(M) | UTILITIES | 152000 | FY 2026: 152000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | BFP | CONSTRUCTION | 6083000 | FY 2028: 1825000; FY 2029: 2615000; FY 2030: 1217000; FY 2031: 426000
B-6038 | Highway | Bridges | NC 14 / NC 87 | Bridge 780155 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | T(M) | CONSTRUCTION | 1520000 | FY 2028: 456000; FY 2029: 654000; FY 2030: 304000; FY 2031: 106000
B-6041 | Highway | Bridges | I-40 | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Statewide Mobility |  |  |  | 80000
B-6041 | Highway | Bridges | I-40 | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Statewide Mobility |  | T(M) |  | 20000
B-6041 | Highway | Bridges | I-40 | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 232000 | FY 2026: 232000
B-6041 | Highway | Bridges | I-40 | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 58000 | FY 2026: 58000
B-6041 | Highway | Bridges | I-40 | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 21520000 | FY 2032: 3874000; FY 2033: 5810000; FY 2034: 4950000; FY 2035: 3658000 | 3228000
B-6041 | Highway | Bridges | I-40 | Bridges 170177 and 170178 over Lyle Creek. | Replace bridges. | 0.25 | Catawba | 12 | Greater Hickory MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5380000 | FY 2032: 968000; FY 2033: 1453000; FY 2034: 1237000; FY 2035: 915000 | 807000
B-6044 | Highway | Bridges | I-95 | Bridges 500082 and 500085 over Black Creek and bridges 500100 and 500101 over Neuse River. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH HB-0042 AND I-5974. | Statewide Mobility |  |  |  | 100000
B-6044 | Highway | Bridges | I-95 | Bridges 500082 and 500085 over Black Creek and bridges 500100 and 500101 over Neuse River. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH HB-0042 AND I-5974. | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 110000
B-6044 | Highway | Bridges | I-95 | Bridges 500082 and 500085 over Black Creek and bridges 500100 and 500101 over Neuse River. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH HB-0042 AND I-5974. | Statewide Mobility |  | HFB | CONSTRUCTION | 53900000 | FY 2029: 8624000; FY 2030: 14553000; FY 2031: 12397000; FY 2032: 10241000; FY 2033: 8085000
B-6046 | Highway | Bridges | SR 1917 (Bethlehem Church Road) | Bridge 830102 over Long Creek. | Replace bridge. | 0.25 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  |  |  | 100000
B-6046 | Highway | Bridges | SR 1917 (Bethlehem Church Road) | Bridge 830102 over Long Creek. | Replace bridge. | 0.25 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | BGOFF | RIGHT-OF-WAY | 145000
B-6046 | Highway | Bridges | SR 1917 (Bethlehem Church Road) | Bridge 830102 over Long Creek. | Replace bridge. | 0.25 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | BGOFF | CONSTRUCTION | 2779000
B-6047 | Highway | Bridges | SR 2125 (Harris Henrietta Road) | Bridge 800145 over Floyds Creek. | Replace bridge. | 0.25 | Rutherford | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  |  |  | 100000
B-6047 | Highway | Bridges | SR 2125 (Harris Henrietta Road) | Bridge 800145 over Floyds Creek. | Replace bridge. | 0.25 | Rutherford | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 210000
B-6047 | Highway | Bridges | SR 2125 (Harris Henrietta Road) | Bridge 800145 over Floyds Creek. | Replace bridge. | 0.25 | Rutherford | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGOFF | CONSTRUCTION | 3000000 | FY 2026: 1320000; FY 2027: 1500000; FY 2028: 180000
B-6048 | Highway | Bridges | SR 1812 (Diggs Road) | Bridge 030039 over Jones Creek. | Replace bridge. | 0.25 | Anson | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  |  |  | 100000
B-6048 | Highway | Bridges | SR 1812 (Diggs Road) | Bridge 030039 over Jones Creek. | Replace bridge. | 0.25 | Anson | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGOFF | RIGHT-OF-WAY | 355000
B-6048 | Highway | Bridges | SR 1812 (Diggs Road) | Bridge 030039 over Jones Creek. | Replace bridge. | 0.25 | Anson | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGOFF | CONSTRUCTION | 4100000 | FY 2027: 1927000; FY 2028: 1927000; FY 2029: 246000
B-6049 | Highway | Bridges | SR 1206 (Wright Bridge Road) | Bridge 810072 over Great Coharie Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 100000
B-6049 | Highway | Bridges | SR 1206 (Wright Bridge Road) | Bridge 810072 over Great Coharie Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 340000
B-6049 | Highway | Bridges | SR 1206 (Wright Bridge Road) | Bridge 810072 over Great Coharie Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 1901000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 168000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T(M) |  | 42000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BFP | RIGHT-OF-WAY | 1681000 | FY 2026: 34000; FY 2027: 414000; FY 2028: 414000; FY 2029: 414000; FY 2030: 405000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T(M) | RIGHT-OF-WAY | 419000 | FY 2026: 9000; FY 2027: 103000; FY 2028: 103000; FY 2029: 103000; FY 2030: 101000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BFP | UTILITIES | 4880000 | FY 2026: 2440000; FY 2027: 2440000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T(M) | UTILITIES | 1220000 | FY 2026: 610000; FY 2027: 610000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BFP | CONSTRUCTION | 73280000 | FY 2031: 14656000; FY 2032: 17587000; FY 2033: 16122000; FY 2034: 13923000; FY 2035: 10992000
B-6050 | Highway | Bridges | SR 2137 (Pittman Road); SR 2130 (East Main Street); SR 2339 (Bagley Road) | Bridges 500109, 500110, 500112 over I-95. | Replace bridges. | 0.25 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T(M) | CONSTRUCTION | 18320000 | FY 2031: 3664000; FY 2032: 4397000; FY 2033: 4030000; FY 2034: 3481000; FY 2035: 2748000
B-6051 | Highway | Bridges | US 29 / US 74 | BRIDGE 350091 OVER CATAWBA RIVER | REPLACE BRIDGE. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region F |  | HIB | RIGHT-OF-WAY | 4000000
B-6051 | Highway | Bridges | US 29 / US 74 | BRIDGE 350091 OVER CATAWBA RIVER | REPLACE BRIDGE. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region F |  | HIB | CONSTRUCTION | 30201000 | FY 2026: 3130000; FY 2027: 17198000; FY 2028: 4079000; FY 2029: 5367000; FY 2030: 427000
B-6051 | Highway | Bridges | US 29 / US 74 | BRIDGE 350091 OVER CATAWBA RIVER | REPLACE BRIDGE. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region F |  | T(M) | CONSTRUCTION | 7551000 | FY 2026: 783000; FY 2027: 4299000; FY 2028: 1020000; FY 2029: 1342000; FY 2030: 107000
B-6051 | Highway | Bridges | US 29 / US 74 | BRIDGE 350091 OVER CATAWBA RIVER | REPLACE BRIDGE. | 0.25 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region F |  | HFB | CONSTRUCTION | 38848000 | FY 2026: 6196000; FY 2027: 5282000; FY 2028: 17164000; FY 2029: 8581000; FY 2030: 1625000
B-6054 | Highway | Bridges | I-40 | Bridges 430057, 430159, 430171, 430124, and 430142 on I-40. | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility
B-6054A | Highway | Bridges | I-40 | Bridge 430057 over US Forest Service Road / Cold Springs Creek at Harmon's Den. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 500000
B-6054A | Highway | Bridges | I-40 | Bridge 430057 over US Forest Service Road / Cold Springs Creek at Harmon's Den. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 22898000
B-6054B | Highway | Bridges | I-40 | Bridge 430159 over SR 1338 (White Oak Road). | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 500000
B-6054B | Highway | Bridges | I-40 | Bridge 430159 over SR 1338 (White Oak Road). | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 5000
B-6054B | Highway | Bridges | I-40 | Bridge 430159 over SR 1338 (White Oak Road). | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 25000000
B-6054C | Highway | Bridges | I-40 | Bridge 430171 over SR 1338 (White Oak Road) and Jonathan Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 2500000
B-6054C | Highway | Bridges | I-40 | Bridge 430171 over SR 1338 (White Oak Road) and Jonathan Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 47000
B-6054C | Highway | Bridges | I-40 | Bridge 430171 over SR 1338 (White Oak Road) and Jonathan Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 5000
B-6054C | Highway | Bridges | I-40 | Bridge 430171 over SR 1338 (White Oak Road) and Jonathan Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 79725000
B-6054D | Highway | Bridges | I-40 | Bridge 430124 over SR 1338 (White Oak Road) and Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | ENGINEERING | 500000
B-6054D | Highway | Bridges | I-40 | Bridge 430124 over SR 1338 (White Oak Road) and Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 5000
B-6054D | Highway | Bridges | I-40 | Bridge 430124 over SR 1338 (White Oak Road) and Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | UTILITIES | 5000
B-6054D | Highway | Bridges | I-40 | Bridge 430124 over SR 1338 (White Oak Road) and Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | CONSTRUCTION | 25800000 | FY 2026: 10551000
B-6054E | Highway | Bridges | I-40 | Bridge 430142 over Pigeon River. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | ENGINEERING | 2000000
B-6054E | Highway | Bridges | I-40 | Bridge 430142 over Pigeon River. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 50000
B-6054E | Highway | Bridges | I-40 | Bridge 430142 over Pigeon River. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 5000
B-6054E | Highway | Bridges | I-40 | Bridge 430142 over Pigeon River. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 81650000 | FY 2026: 44481000; FY 2027: 15096000; FY 2028: 4721000
B-8888 | Highway | Bridges | Various | Locations statewide. | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BGOFF | CONSTRUCTION | 0
B-8888DIV | Highway | Bridges | Various | Locations statewide. Division Needs funding. | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BFP | CONSTRUCTION | 0
B-8888REG | Highway | Bridges | Various | Locations statewide. Regional Impact funding. | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Region SW |  | BFP | CONSTRUCTION | 0
B-8888SW | Highway | Bridges | Various | Locations statewide. Statewide Mobility finding. | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | BFP | CONSTRUCTION | 0
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (Caney Fork Road), SR 1432 (Skyland Drive) | Various locations | Construct bicycle pullouts. |  | Jackson | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | ENGINEERING | 8000
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (Caney Fork Road), SR 1432 (Skyland Drive) | Various locations | Construct bicycle pullouts. |  | Jackson | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | ENGINEERING | 2000
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (Caney Fork Road), SR 1432 (Skyland Drive) | Various locations | Construct bicycle pullouts. |  | Jackson | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | CONSTRUCTION | 152000
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (Caney Fork Road), SR 1432 (Skyland Drive) | Various locations | Construct bicycle pullouts. |  | Jackson | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | CONSTRUCTION | 38000
BF-0002 | Bike & Ped | Federal Lands Access Program | Ecusta Trail | Transylvania County Line to Lamb Creek near Brevard. | Construct greenway. | 8 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. DP REPRESENTS RAISE GRANT OF $24.559M. | Exempt |  | FLAP | ENGINEERING | 1000000
BF-0002 | Bike & Ped | Federal Lands Access Program | Ecusta Trail | Transylvania County Line to Lamb Creek near Brevard. | Construct greenway. | 8 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. DP REPRESENTS RAISE GRANT OF $24.559M. | Exempt |  | CRPANY | ENGINEERING | 1500000
BF-0002 | Bike & Ped | Federal Lands Access Program | Ecusta Trail | Transylvania County Line to Lamb Creek near Brevard. | Construct greenway. | 8 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. DP REPRESENTS RAISE GRANT OF $24.559M. | Exempt |  | L(M) | ENGINEERING | 375000
BF-0002 | Bike & Ped | Federal Lands Access Program | Ecusta Trail | Transylvania County Line to Lamb Creek near Brevard. | Construct greenway. | 8 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. DP REPRESENTS RAISE GRANT OF $24.559M. | Exempt |  | DP | CONSTRUCTION | 24559000 | FY 2026: 24559000
BF-0002 | Bike & Ped | Federal Lands Access Program | Ecusta Trail | Transylvania County Line to Lamb Creek near Brevard. | Construct greenway. | 8 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. DP REPRESENTS RAISE GRANT OF $24.559M. | Exempt |  | L(M) | CONSTRUCTION | 641000 | FY 2026: 641000
BK-5100 | Highway | Bridges | Various | Locations statewide. | Establish bridge management system. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 2500000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | BGDA | ENGINEERING | 64000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | TAANY | ENGINEERING | 40000 | FY 2026: 40000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | L(M) | ENGINEERING | 26000 | FY 2026: 10000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | BGDA | RIGHT-OF-WAY | 19000 | FY 2026: 19000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | TAANY | CONSTRUCTION | 312000 | FY 2026: 312000
BL-0002 | Bike & Ped | Locally Selected | Hudson US 321A (Main Street) | SR 1952 (Cedar Valley Road) to SR 1156 (Legion Road) in Hudson | Construct pedestrian crossings improvements. | 0.23 | Caldwell | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | L(M) | CONSTRUCTION | 78000 | FY 2026: 78000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | BGDA | ENGINEERING | 251000 | FY 2027: 251000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | TADA | ENGINEERING | 121000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | L(M) | ENGINEERING | 93000 | FY 2027: 63000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | L | ENGINEERING | 72000 | FY 2027: 72000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | BGDA | RIGHT-OF-WAY | 6000 | FY 2028: 6000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2028: 4000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | BGDA | UTILITIES | 6000 | FY 2028: 6000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | L(M) | UTILITIES | 4000 | FY 2028: 4000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | BGDA | CONSTRUCTION | 1014000 | FY 2028: 1014000
BL-0003 | Bike & Ped | Locally Selected | West Branch Nature Preserve | Summers Walk Boulevard to end point near West Branch Rocky River in Davidson | Construct greenway. | 0.77 | Mecklenburg | 10 | Charlotte Regional TPO | WEST BRANCH NATURE PRESERVE - RIVER RUN NEIGHBORHOOD | Division 10 |  | L(M) | CONSTRUCTION | 544000 | FY 2028: 544000
BL-0005 | Bike & Ped | Locally Selected | NC 251 / SR 1781 (Broadway Street) | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Buncombe | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | BGDA | ENGINEERING | 3000
BL-0005 | Bike & Ped | Locally Selected | NC 251 / SR 1781 (Broadway Street) | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Buncombe | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HF(M) | ENGINEERING | 1000
BL-0005 | Bike & Ped | Locally Selected | NC 251 / SR 1781 (Broadway Street) | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Buncombe | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HSIP | CONSTRUCTION | 45000
BL-0005 | Bike & Ped | Locally Selected | NC 251 / SR 1781 (Broadway Street) | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Buncombe | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | BGDA | CONSTRUCTION | 749000
BL-0005 | Bike & Ped | Locally Selected | NC 251 / SR 1781 (Broadway Street) | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Buncombe | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HF | CONSTRUCTION | 142000
BL-0005 | Bike & Ped | Locally Selected | NC 251 / SR 1781 (Broadway Street) | US 19/ US 23 northbound exit ramp to north of SR 1477 (Riverside Drive) in Asheville | Construct pedestrian improvements. | 0.23 | Buncombe | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HF(M) | CONSTRUCTION | 188000
BL-0006 | Bike & Ped | Locally Selected | Various | Locations in Asheville | Construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | $501K OF STBG-DA FUNDS SWAPPED FOR $501K IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | BGDA | ENGINEERING | 60000 | FY 2026: 60000
BL-0006 | Bike & Ped | Locally Selected | Various | Locations in Asheville | Construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | $501K OF STBG-DA FUNDS SWAPPED FOR $501K IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | L | ENGINEERING | 15000 | FY 2026: 15000
BL-0006 | Bike & Ped | Locally Selected | Various | Locations in Asheville | Construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | $501K OF STBG-DA FUNDS SWAPPED FOR $501K IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | BGDA | CONSTRUCTION | 99000 | FY 2027: 99000
BL-0006 | Bike & Ped | Locally Selected | Various | Locations in Asheville | Construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | $501K OF STBG-DA FUNDS SWAPPED FOR $501K IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | TAANY | CONSTRUCTION | 501000 | FY 2027: 501000
BL-0006 | Bike & Ped | Locally Selected | Various | Locations in Asheville | Construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | $501K OF STBG-DA FUNDS SWAPPED FOR $501K IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | L | CONSTRUCTION | 150000 | FY 2027: 150000
BL-0007 | Bike & Ped | Locally Selected | Ecusta Rail Trail | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Henderson | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | BGDA | ENGINEERING | 546000
BL-0007 | Bike & Ped | Locally Selected | Ecusta Rail Trail | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Henderson | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L(M) | ENGINEERING | 137000
BL-0007 | Bike & Ped | Locally Selected | Ecusta Rail Trail | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Henderson | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | DP | CONSTRUCTION | 5705000
BL-0007 | Bike & Ped | Locally Selected | Ecusta Rail Trail | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Henderson | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | CRPDA | CONSTRUCTION | 1911000
BL-0007 | Bike & Ped | Locally Selected | Ecusta Rail Trail | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Henderson | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | TADA | CONSTRUCTION | 2618000
BL-0007 | Bike & Ped | Locally Selected | Ecusta Rail Trail | SR 1127 (Kanuga Road) to US 64 (Battle Creek) in Horse Shoe, Yale, and Laurel Park in Henderson. | Construct multi-use path. | 5.79 | Henderson | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L(M) | CONSTRUCTION | 1767000
BL-0008 | Bike & Ped | Locally Selected | Clear Creek Greenway | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Henderson | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGDA | ENGINEERING | 720000
BL-0008 | Bike & Ped | Locally Selected | Clear Creek Greenway | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Henderson | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L(M) | ENGINEERING | 180000
BL-0008 | Bike & Ped | Locally Selected | Clear Creek Greenway | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Henderson | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGANY | CONSTRUCTION | 2361000 | FY 2026: 2361000
BL-0008 | Bike & Ped | Locally Selected | Clear Creek Greenway | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Henderson | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGDA | CONSTRUCTION | 403000 | FY 2026: 403000
BL-0008 | Bike & Ped | Locally Selected | Clear Creek Greenway | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Henderson | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L(M) | CONSTRUCTION | 691000 | FY 2026: 691000
BL-0008 | Bike & Ped | Locally Selected | Clear Creek Greenway | Berkeley Mills Park to SR 1518 (Lakewood Road) in Hendersonville | Construct multi-use path. | 1.39 | Henderson | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | CONSTRUCTION | 121000 | FY 2026: 121000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 110000 | FY 2026: 110000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 28000 | FY 2026: 28000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 493000 | FY 2026: 493000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 124000 | FY 2026: 124000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 583000 | FY 2027: 583000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Pine Street to North Main Park in Hendersonville | Construct pedestrian improvements. | 1.68 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 146000 | FY 2027: 146000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TADA | ENGINEERING | 188000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | ENGINEERING | 188000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | RIGHT-OF-WAY | 77000 | FY 2026: 77000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | RIGHT-OF-WAY | 181000 | FY 2026: 181000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | RIGHT-OF-WAY | 258000 | FY 2026: 258000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | CONSTRUCTION | 1300000 | FY 2027: 1300000
BL-0010 | Bike & Ped | Locally Selected | The Park - Huntersville Greenway | Torrence Creek Greenway to SR 2004 (Mount Holly-Huntersville Road) in Huntersville | Construct greenway. | 1.55 | Mecklenburg | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | CONSTRUCTION | 1300000 | FY 2027: 1300000
BL-0011 | Bike & Ped | Locally Selected | NC 205 (North Elm Street); East Union Street | SR 1740 (Main Street) and SR 1735 (East Union Street) intersections in Marshville; N Cross Street intersection in Marshville | Construct pedestrian improvements and install pavement markings. | 0.55 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 50000
BL-0011 | Bike & Ped | Locally Selected | NC 205 (North Elm Street); East Union Street | SR 1740 (Main Street) and SR 1735 (East Union Street) intersections in Marshville; N Cross Street intersection in Marshville | Construct pedestrian improvements and install pavement markings. | 0.55 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 13000
BL-0011 | Bike & Ped | Locally Selected | NC 205 (North Elm Street); East Union Street | SR 1740 (Main Street) and SR 1735 (East Union Street) intersections in Marshville; N Cross Street intersection in Marshville | Construct pedestrian improvements and install pavement markings. | 0.55 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 268000 | FY 2026: 268000
BL-0011 | Bike & Ped | Locally Selected | NC 205 (North Elm Street); East Union Street | SR 1740 (Main Street) and SR 1735 (East Union Street) intersections in Marshville; N Cross Street intersection in Marshville | Construct pedestrian improvements and install pavement markings. | 0.55 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 67000 | FY 2026: 67000
BL-0012 | Bike & Ped | Locally Selected | Marvin Loop Trail | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 265000
BL-0012 | Bike & Ped | Locally Selected | Marvin Loop Trail | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 178000
BL-0012 | Bike & Ped | Locally Selected | Marvin Loop Trail | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 94000 | FY 2026: 94000
BL-0012 | Bike & Ped | Locally Selected | Marvin Loop Trail | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 63000 | FY 2026: 63000
BL-0012 | Bike & Ped | Locally Selected | Marvin Loop Trail | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 785000 | FY 2027: 785000
BL-0012 | Bike & Ped | Locally Selected | Marvin Loop Trail | SR 1315 (New Town Road) from west of SR 1307 (Waxhaw-Marvin Road) to SR 1316 (Marvin School Road). SR 1316 (Marvin School Road) from SR 1315 (New Town Road) to Yellow Jasmine Lane in Marvin. | Construct pedestrian improvements. | 1.16 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 524000 | FY 2027: 524000
BL-0013 | Bike & Ped | Locally Selected | Moore Avenue | South Church Street to North Academy Street in Mooresville | Construct pedestrian improvements. | 0.22 | Iredell | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23. | Division 12 |  | TAANY | ENGINEERING | 8000
BL-0013 | Bike & Ped | Locally Selected | Moore Avenue | South Church Street to North Academy Street in Mooresville | Construct pedestrian improvements. | 0.22 | Iredell | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23. | Division 12 |  | L(M) | ENGINEERING | 2000
BL-0013 | Bike & Ped | Locally Selected | Moore Avenue | South Church Street to North Academy Street in Mooresville | Construct pedestrian improvements. | 0.22 | Iredell | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23. | Division 12 |  | TAANY | CONSTRUCTION | 1192000 | FY 2026: 1192000
BL-0013 | Bike & Ped | Locally Selected | Moore Avenue | South Church Street to North Academy Street in Mooresville | Construct pedestrian improvements. | 0.22 | Iredell | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23. | Division 12 |  | L(M) | CONSTRUCTION | 798000 | FY 2026: 798000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 289000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | ENGINEERING | 72000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | RIGHT-OF-WAY | 116000 | FY 2026: 116000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | RIGHT-OF-WAY | 29000 | FY 2026: 29000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | UTILITIES | 612000 | FY 2026: 612000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | UTILITIES | 153000 | FY 2026: 153000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 889000 | FY 2027: 889000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | CONSTRUCTION | 305000 | FY 2027: 305000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (South Cherry Street) | Oakhurst Street to Holy Cross Church in Kernersville | Construct five-foot sidewalk. | 0.4 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | CONSTRUCTION | 298000 | FY 2027: 298000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 124000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 31000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 79000 | FY 2026: 79000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 268000 | FY 2026: 268000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 66000 | FY 2026: 66000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 503000 | FY 2027: 503000
BL-0015 | Bike & Ped | Locally Selected | Broad Street | SR 4309 (East Mountain Street) to Harmon Lane in Kernersville | Construct five-foot sidewalk. | 0.17 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 127000 | FY 2027: 127000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 45000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | ENGINEERING | 165000 | FY 2026: 165000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 8000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 43000 | FY 2026: 41000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 64000 | FY 2026: 64000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2026: 15000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 15000 | FY 2026: 15000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 4000 | FY 2026: 4000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 277000 | FY 2027: 277000
BL-0016 | Bike & Ped | Locally Selected | Harmon Lane | SR 4315 (South Main Street) to Broad Street in Kernersville | Construct five-foot sidewalk. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 69000 | FY 2027: 69000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 117000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 29000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 162000 | FY 2026: 162000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 41000 | FY 2026: 41000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 519000 | FY 2027: 519000
BL-0017 | Bike & Ped | Locally Selected | Southern Street Greenway | Southern Street to Kerners Mill Creek Greenway in Kernersville | Construct multi-use paved path. | 0.13 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 129000 | FY 2027: 129000
BL-0018 | Bike & Ped | Locally Selected | Brewer Road | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 164000
BL-0018 | Bike & Ped | Locally Selected | Brewer Road | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | ENGINEERING | 41000
BL-0018 | Bike & Ped | Locally Selected | Brewer Road | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | RIGHT-OF-WAY | 410000 | FY 2026: 410000
BL-0018 | Bike & Ped | Locally Selected | Brewer Road | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | RIGHT-OF-WAY | 103000 | FY 2026: 103000
BL-0018 | Bike & Ped | Locally Selected | Brewer Road | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1861000 | FY 2028: 1861000
BL-0018 | Bike & Ped | Locally Selected | Brewer Road | Buchanan Street to Clemmonsville Road in Winston-Salem | Construct five-foot sidewalk. | 0.76 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | CONSTRUCTION | 465000 | FY 2028: 465000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | BGDA | ENGINEERING | 800000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L(M) | ENGINEERING | 200000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | BGDA | RIGHT-OF-WAY | 56000 | FY 2026: 56000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L(M) | RIGHT-OF-WAY | 14000 | FY 2026: 14000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | BGDA | UTILITIES | 24000 | FY 2026: 24000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L(M) | UTILITIES | 6000 | FY 2026: 6000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | DP | CONSTRUCTION | 6000000 | FY 2026: 6000000
BL-0019 | Bike & Ped | Locally Selected | Long Branch Trail Phase II | SR 2516 (Martin Luther King, Jr. Drive) to 25th Street in Winston-Salem | Construct greenway. | 1.28 | Forsyth | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L(M) | CONSTRUCTION | 1500000 | FY 2026: 1500000
BL-0020 | Bike & Ped | Locally Selected | Depot Street | US 311 (Main Street) to SR 1992 (Sullivantown Road) in Walkertown | Construct sidewalk. | 0.22 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 849000 | FY 2026: 849000
BL-0020 | Bike & Ped | Locally Selected | Depot Street | US 311 (Main Street) to SR 1992 (Sullivantown Road) in Walkertown | Construct sidewalk. | 0.22 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 212000 | FY 2026: 212000
BL-0021 | Bike & Ped | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Division 3 |  | TADA | CONSTRUCTION | 1759000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 378000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | ENGINEERING | 131000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | ENGINEERING | 33000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 150000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | RIGHT-OF-WAY | 37000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | UTILITIES | 60000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | UTILITIES | 15000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 1844000
BL-0022 | Bike & Ped | Locally Selected | Various | Downtown Fuquay-Varina to Fuquay-Varina High School in Fuquay-Varina | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 461000
BL-0023 | Bike & Ped | Locally Selected | SR 1152 (Holly Springs Road) | Flint Point Lane to Middlecrest Way in Holly Springs | Construct pedestrian safety enhancements. | 0.41 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 558000
BL-0023 | Bike & Ped | Locally Selected | SR 1152 (Holly Springs Road) | Flint Point Lane to Middlecrest Way in Holly Springs | Construct pedestrian safety enhancements. | 0.41 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 557000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (Northwest Cary Parkway) | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 20000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (Northwest Cary Parkway) | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | RIGHT-OF-WAY | 20000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (Northwest Cary Parkway) | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | UTILITIES | 81000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (Northwest Cary Parkway) | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | UTILITIES | 81000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (Northwest Cary Parkway) | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 3372000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (Northwest Cary Parkway) | In the vicinity of Black Creek in Cary | Construct sidewalk extensions and improve safety of pedestrian crossings. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 3372000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (Wake Forest Road) | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Wake | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | BGANY | ENGINEERING | 120000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (Wake Forest Road) | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Wake | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | L(M) | ENGINEERING | 30000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (Wake Forest Road) | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Wake | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | BGANY | RIGHT-OF-WAY | 160000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (Wake Forest Road) | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Wake | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | L(M) | RIGHT-OF-WAY | 40000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (Wake Forest Road) | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Wake | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | BGANY | CONSTRUCTION | 2411000 | FY 2026: 1060000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (Wake Forest Road) | Forest Ridge Road to Ronald Drive in Raleigh | Extend sidewalks. | 0.12 | Wake | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | L(M) | CONSTRUCTION | 268000
BL-0026 | Bike & Ped | Locally Selected | Little Drive | SR 2153 (Louis Stephens Drive) to CSX Railroad crossing in Research Triangle Park | Construct greenway trail. | 0.24 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | ENGINEERING | 166000
BL-0026 | Bike & Ped | Locally Selected | Little Drive | SR 2153 (Louis Stephens Drive) to CSX Railroad crossing in Research Triangle Park | Construct greenway trail. | 0.24 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | ENGINEERING | 69000
BL-0026 | Bike & Ped | Locally Selected | Little Drive | SR 2153 (Louis Stephens Drive) to CSX Railroad crossing in Research Triangle Park | Construct greenway trail. | 0.24 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 1545000
BL-0026 | Bike & Ped | Locally Selected | Little Drive | SR 2153 (Louis Stephens Drive) to CSX Railroad crossing in Research Triangle Park | Construct greenway trail. | 0.24 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 662000
BL-0027 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Lassiter Mill Road to Hertford Street in Raleigh | Construct greenway trail. | 0.14 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 895000
BL-0027 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Lassiter Mill Road to Hertford Street in Raleigh | Construct greenway trail. | 0.14 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 732000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Durham | 5 | Triangle West TPO |  | Division 5 |  | CMAQ | ENGINEERING | 48000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Durham | 5 | Triangle West TPO |  | Division 5 |  | BGDA | ENGINEERING | 75000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | ENGINEERING | 52000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Durham | 5 | Triangle West TPO |  | Division 5 |  | CMAQ | CONSTRUCTION | 852000 | FY 2026: 852000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CONSTRUCTION | 213000 | FY 2026: 213000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (Chapel Hill Street); West Club Boulevard; Blackwell Street / Corcoran Street / Foster Street | Ramseur Street to Swift Avenue; Washington Street to SR 1322 (Broad Street); American Tobacco Trail trailhead to Washington Street in Durham | Construct buffered bicycle lanes. | 4.44 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | CONSTRUCTION | 152000 | FY 2026: 152000
BL-0032 | Bike & Ped | Locally Selected | SR 1164 (Cokey Road); Rex Street | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 80000
BL-0032 | Bike & Ped | Locally Selected | SR 1164 (Cokey Road); Rex Street | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 20000
BL-0032 | Bike & Ped | Locally Selected | SR 1164 (Cokey Road); Rex Street | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 8000 | FY 2026: 8000
BL-0032 | Bike & Ped | Locally Selected | SR 1164 (Cokey Road); Rex Street | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
BL-0032 | Bike & Ped | Locally Selected | SR 1164 (Cokey Road); Rex Street | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 272000 | FY 2026: 3000; FY 2027: 269000
BL-0032 | Bike & Ped | Locally Selected | SR 1164 (Cokey Road); Rex Street | CSX Railroad to Wintergreen Court; Old Wilson Road to SR 1164 (Cokey Road) | Construct sidewalk. | 0.58 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 68000 | FY 2026: 1000; FY 2027: 67000
BL-0033 | Bike & Ped | Locally Selected | NC 274 (Tryon Courthouse Road) | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | ENGINEERING | 150000
BL-0033 | Bike & Ped | Locally Selected | NC 274 (Tryon Courthouse Road) | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L(M) | ENGINEERING | 38000
BL-0033 | Bike & Ped | Locally Selected | NC 274 (Tryon Courthouse Road) | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BL-0033 | Bike & Ped | Locally Selected | NC 274 (Tryon Courthouse Road) | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0033 | Bike & Ped | Locally Selected | NC 274 (Tryon Courthouse Road) | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1159000 | FY 2028: 828000; FY 2029: 331000
BL-0033 | Bike & Ped | Locally Selected | NC 274 (Tryon Courthouse Road) | SR 1534 (Pine Springs Drive) to Tryon Elementary School in Tryon | Construct sidewalk on west side of roadway from Pine Springs to Court Terrace. Install mid-block crosswalk and construct sidewalk on east side of roadway to Tryon Elementary School. | 0.31 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L(M) | CONSTRUCTION | 290000 | FY 2028: 200000; FY 2029: 90000
BL-0035 | Bike & Ped | Locally Selected | Chatham Business Drive | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CMAQ | ENGINEERING | 32000
BL-0035 | Bike & Ped | Locally Selected | Chatham Business Drive | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 8000
BL-0035 | Bike & Ped | Locally Selected | Chatham Business Drive | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 8000
BL-0035 | Bike & Ped | Locally Selected | Chatham Business Drive | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 2000
BL-0035 | Bike & Ped | Locally Selected | Chatham Business Drive | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 128000
BL-0035 | Bike & Ped | Locally Selected | Chatham Business Drive | South of US 64 Business (East Street) to south of US 64 Business (East Street) in Pittsboro | Construct sidewalk segment to connect existing sidewalk. | 0.16 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 32000
BL-0036 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Bond Park to SR 1615 (High House Road) in Cary | Construct greenway between Black Creek and White Oak Creek Greenways and between Bond Park and Preston Fields Park. | 0.53 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 198000
BL-0036 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Bond Park to SR 1615 (High House Road) in Cary | Construct greenway between Black Creek and White Oak Creek Greenways and between Bond Park and Preston Fields Park. | 0.53 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 50000
BL-0036 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Bond Park to SR 1615 (High House Road) in Cary | Construct greenway between Black Creek and White Oak Creek Greenways and between Bond Park and Preston Fields Park. | 0.53 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1122000
BL-0036 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Bond Park to SR 1615 (High House Road) in Cary | Construct greenway between Black Creek and White Oak Creek Greenways and between Bond Park and Preston Fields Park. | 0.53 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 280000
BL-0037 | Bike & Ped | Locally Selected | Crabtree Creek Greenway Connector | Crabtree Creek Greenway to Weston Greenway in Cary | Construct 10-foot greenway including grade separation under Weston Parkway. | 0.21 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 16000
BL-0037 | Bike & Ped | Locally Selected | Crabtree Creek Greenway Connector | Crabtree Creek Greenway to Weston Greenway in Cary | Construct 10-foot greenway including grade separation under Weston Parkway. | 0.21 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 4000
BL-0037 | Bike & Ped | Locally Selected | Crabtree Creek Greenway Connector | Crabtree Creek Greenway to Weston Greenway in Cary | Construct 10-foot greenway including grade separation under Weston Parkway. | 0.21 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 2261000 | FY 2026: 346000
BL-0037 | Bike & Ped | Locally Selected | Crabtree Creek Greenway Connector | Crabtree Creek Greenway to Weston Greenway in Cary | Construct 10-foot greenway including grade separation under Weston Parkway. | 0.21 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 565000 | FY 2026: 86000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | ENGINEERING | 112000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | ENGINEERING | 28000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | RIGHT-OF-WAY | 14000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | RIGHT-OF-WAY | 3000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | UTILITIES | 31000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | UTILITIES | 8000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 568000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | TADA | CONSTRUCTION | 150000
BL-0038 | Bike & Ped | Locally Selected | East Jones Street | US 401 / NC 42 to North Woodrow Street in Fuquay-Varina | Construct sidewalks. | 0.29 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 180000
BL-0040 | Bike & Ped | Locally Selected | Various | Middle Sound Loop Connector to Porters Neck Walmart Connector | Construct multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | CONSTRUCTION | 1260000
BL-0040 | Bike & Ped | Locally Selected | Various | Middle Sound Loop Connector to Porters Neck Walmart Connector | Construct multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 314000
BL-0041 | Bike & Ped | Locally Selected | Latham Park Greenway; Lake Daniel Greenway | Friendly Avenue to Josephine Boyd Street; Tennis courts near Wendover Avenue in Greensboro | Repair surfaces. | 1.33 | Guilford | 7 | Greensboro Urban Area MPO | Under Construction | Division 7 |  | TAP | CONSTRUCTION | 400000 | FY 2026: 400000
BL-0041 | Bike & Ped | Locally Selected | Latham Park Greenway; Lake Daniel Greenway | Friendly Avenue to Josephine Boyd Street; Tennis courts near Wendover Avenue in Greensboro | Repair surfaces. | 1.33 | Guilford | 7 | Greensboro Urban Area MPO | Under Construction | Division 7 |  | TAANY | CONSTRUCTION | 506000 | FY 2026: 506000
BL-0041 | Bike & Ped | Locally Selected | Latham Park Greenway; Lake Daniel Greenway | Friendly Avenue to Josephine Boyd Street; Tennis courts near Wendover Avenue in Greensboro | Repair surfaces. | 1.33 | Guilford | 7 | Greensboro Urban Area MPO | Under Construction | Division 7 |  | L(M) | CONSTRUCTION | 227000 | FY 2026: 227000
BL-0042 | Bike & Ped | Locally Selected | Vance Arlington Greenway | North of Florida Street to Bragg Street in Greensboro | Construct greenway and side path. | 0.81 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 960000 | FY 2026: 960000
BL-0042 | Bike & Ped | Locally Selected | Vance Arlington Greenway | North of Florida Street to Bragg Street in Greensboro | Construct greenway and side path. | 0.81 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 240000 | FY 2026: 240000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | Westbrook Drive in Carrboro to west of US 15 / US 501 / NC 86 (South Columbia Street) interchange in Chapel Hill | Construct sidewalk and install pedestrian signals, crosswalks, and refuge islands at selected locations. | 1.55 | Orange | 7 | Triangle West TPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | HF | ENGINEERING | 175000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | Westbrook Drive in Carrboro to west of US 15 / US 501 / NC 86 (South Columbia Street) interchange in Chapel Hill | Construct sidewalk and install pedestrian signals, crosswalks, and refuge islands at selected locations. | 1.55 | Orange | 7 | Triangle West TPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | BGDA | CONSTRUCTION | 1521000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | Westbrook Drive in Carrboro to west of US 15 / US 501 / NC 86 (South Columbia Street) interchange in Chapel Hill | Construct sidewalk and install pedestrian signals, crosswalks, and refuge islands at selected locations. | 1.55 | Orange | 7 | Triangle West TPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | L(M) | CONSTRUCTION | 193000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | Westbrook Drive in Carrboro to west of US 15 / US 501 / NC 86 (South Columbia Street) interchange in Chapel Hill | Construct sidewalk and install pedestrian signals, crosswalks, and refuge islands at selected locations. | 1.55 | Orange | 7 | Triangle West TPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | HF(M) | CONSTRUCTION | 187000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | Westbrook Drive in Carrboro to west of US 15 / US 501 / NC 86 (South Columbia Street) interchange in Chapel Hill | Construct sidewalk and install pedestrian signals, crosswalks, and refuge islands at selected locations. | 1.55 | Orange | 7 | Triangle West TPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | HF | CONSTRUCTION | 38000
BL-0045 | Bike & Ped | Locally Selected | Wilmington Rail Trail | 3rd Street to Love Grove Bridge multi-use path facility in Wilmington | Construct multi-use path. | 1.36 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 431000
BL-0045 | Bike & Ped | Locally Selected | Wilmington Rail Trail | 3rd Street to Love Grove Bridge multi-use path facility in Wilmington | Construct multi-use path. | 1.36 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDACV | ENGINEERING | 680000
BL-0045 | Bike & Ped | Locally Selected | Wilmington Rail Trail | 3rd Street to Love Grove Bridge multi-use path facility in Wilmington | Construct multi-use path. | 1.36 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 108000
BL-0046 | Bike & Ped | Locally Selected | SR 1116 (Ocean Boulevard) | West of Shell Drive to Dunescape Drive in Holden Beach | Install bike lanes. | 6.14 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 913000
BL-0046 | Bike & Ped | Locally Selected | SR 1116 (Ocean Boulevard) | West of Shell Drive to Dunescape Drive in Holden Beach | Install bike lanes. | 6.14 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 700000
BL-0047 | Bike & Ped | Locally Selected | Various | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 16000
BL-0047 | Bike & Ped | Locally Selected | Various | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 4000
BL-0047 | Bike & Ped | Locally Selected | Various | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 177000
BL-0047 | Bike & Ped | Locally Selected | Various | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 44000
BL-0047 | Bike & Ped | Locally Selected | Various | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 1219000
BL-0047 | Bike & Ped | Locally Selected | Various | Routes in Apex | Complete sidewalk gaps in downtown Apex including crossing improvements at intersection of North Salem Street and Hunter Street. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 305000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (Old Apex Road) | West Chatham Street to Murphy Drive in Cary, including CSX railroad crossing | Complete sidewalk gaps. | 1.29 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 15000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (Old Apex Road) | West Chatham Street to Murphy Drive in Cary, including CSX railroad crossing | Complete sidewalk gaps. | 1.29 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 10000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (Old Apex Road) | West Chatham Street to Murphy Drive in Cary, including CSX railroad crossing | Complete sidewalk gaps. | 1.29 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1180000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (Old Apex Road) | West Chatham Street to Murphy Drive in Cary, including CSX railroad crossing | Complete sidewalk gaps. | 1.29 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 795000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (Louis Stephens Drive) | Gray Marble Road to Addenbrock Drive and Northeast corner of Louis Stephens Drive and SR 1635 (McCrimmon Parkway) intersection in Morrisville | Complete sidewalk gaps. | 0.63 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (Louis Stephens Drive) | Gray Marble Road to Addenbrock Drive and Northeast corner of Louis Stephens Drive and SR 1635 (McCrimmon Parkway) intersection in Morrisville | Complete sidewalk gaps. | 0.63 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (Louis Stephens Drive) | Gray Marble Road to Addenbrock Drive and Northeast corner of Louis Stephens Drive and SR 1635 (McCrimmon Parkway) intersection in Morrisville | Complete sidewalk gaps. | 0.63 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 385000 | FY 2026: 4000; FY 2027: 381000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (Louis Stephens Drive) | Gray Marble Road to Addenbrock Drive and Northeast corner of Louis Stephens Drive and SR 1635 (McCrimmon Parkway) intersection in Morrisville | Complete sidewalk gaps. | 0.63 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 165000 | FY 2026: 2000; FY 2027: 163000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (East Main Street) | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (East Main Street) | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | ENGINEERING | 2000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (East Main Street) | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 140000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (East Main Street) | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | RIGHT-OF-WAY | 60000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (East Main Street) | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | CONSTRUCTION | 307000 | FY 2026: 307000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (East Main Street) | Second Street to US 70 Business / NC 42 in Clayton | Complete sidewalk gap and include crossing improvements. | 0.35 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | CONSTRUCTION | 133000 | FY 2026: 133000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (Penny Road) | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | CMAQ | ENGINEERING | 39000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (Penny Road) | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | HF(M) | ENGINEERING | 11000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (Penny Road) | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | CMAQ | RIGHT-OF-WAY | 39000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (Penny Road) | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 11000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (Penny Road) | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 273000 | FY 2026: 273000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (Penny Road) | SR 4720 (Loch Highlands Drive) to east of entrance to Oak Grove Elementary School in Raleigh | Complete sidewalk gaps. | 0.28 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 77000 | FY 2026: 77000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (North Main Street) | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 60000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (North Main Street) | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 15000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (North Main Street) | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 200000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (North Main Street) | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 50000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (North Main Street) | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 400000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (North Main Street) | Trellis Pointe Drive to Arbor Creek Drive in Holly Springs | Complete sidewalk gaps. | 0.24 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 100000
BL-0053 | Bike & Ped | Locally Selected | Franklin County Rails To Trails | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Franklin | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 480000
BL-0053 | Bike & Ped | Locally Selected | Franklin County Rails To Trails | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Franklin | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 120000
BL-0053 | Bike & Ped | Locally Selected | Franklin County Rails To Trails | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Franklin | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 96000
BL-0053 | Bike & Ped | Locally Selected | Franklin County Rails To Trails | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Franklin | 5 | Capital Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 24000
BL-0053 | Bike & Ped | Locally Selected | Franklin County Rails To Trails | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Franklin | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 2400000
BL-0053 | Bike & Ped | Locally Selected | Franklin County Rails To Trails | Downtown Franklinton Train Depot to SR 1003 (Perry's Chapel Road) using abandoned rail corridor in Franklinton | Construct greenway. | 2.82 | Franklin | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 600000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (Southeast Judd Parkway) | South of Logan Meadow Court to north of Oldwyck Drive in Fuquay-Varina | Complete sidewalk gaps. | 0.07 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 48000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (Southeast Judd Parkway) | South of Logan Meadow Court to north of Oldwyck Drive in Fuquay-Varina | Complete sidewalk gaps. | 0.07 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 12000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (Southeast Judd Parkway) | South of Logan Meadow Court to north of Oldwyck Drive in Fuquay-Varina | Complete sidewalk gaps. | 0.07 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 582000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (Southeast Judd Parkway) | South of Logan Meadow Court to north of Oldwyck Drive in Fuquay-Varina | Complete sidewalk gaps. | 0.07 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 146000
BL-0055 | Bike & Ped | Locally Selected | New Route | South Elementary School to Mooresville Middle School in Mooresville | Construct greenway connectors. |  | Iredell | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | ENGINEERING | 272000
BL-0055 | Bike & Ped | Locally Selected | New Route | South Elementary School to Mooresville Middle School in Mooresville | Construct greenway connectors. |  | Iredell | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L(M) | ENGINEERING | 91000
BL-0055 | Bike & Ped | Locally Selected | New Route | South Elementary School to Mooresville Middle School in Mooresville | Construct greenway connectors. |  | Iredell | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | CONSTRUCTION | 1561000 | FY 2026: 1561000
BL-0055 | Bike & Ped | Locally Selected | New Route | South Elementary School to Mooresville Middle School in Mooresville | Construct greenway connectors. |  | Iredell | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L(M) | CONSTRUCTION | 520000 | FY 2026: 520000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | Various locations in Mooresville | Construct sidewalks. | 0.69 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 422000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | Various locations in Mooresville | Construct sidewalks. | 0.69 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 141000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | Various locations in Mooresville | Construct sidewalks. | 0.69 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 78000 | FY 2027: 78000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | Various locations in Mooresville | Construct sidewalks. | 0.69 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 26000 | FY 2027: 26000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | Various locations in Mooresville | Construct sidewalks. | 0.69 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 1479000 | FY 2029: 1479000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (White Oak Road); Maple Avenue; McNeely Avenue; Rocky River School Road | Various locations in Mooresville | Construct sidewalks. | 0.69 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 493000 | FY 2029: 493000
BL-0057 | Bike & Ped | Locally Selected | Irwin Creek Greenway | Clanton Road to Lester Street in Charlotte | Construct greenway. | 1.3 | Mecklenburg | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | ENGINEERING | 8000
BL-0057 | Bike & Ped | Locally Selected | Irwin Creek Greenway | Clanton Road to Lester Street in Charlotte | Construct greenway. | 1.3 | Mecklenburg | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L(M) | ENGINEERING | 2000
BL-0057 | Bike & Ped | Locally Selected | Irwin Creek Greenway | Clanton Road to Lester Street in Charlotte | Construct greenway. | 1.3 | Mecklenburg | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | CMAQ | CONSTRUCTION | 4484000 | FY 2030: 45000; FY 2031: 3254000; FY 2032: 1185000
BL-0057 | Bike & Ped | Locally Selected | Irwin Creek Greenway | Clanton Road to Lester Street in Charlotte | Construct greenway. | 1.3 | Mecklenburg | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | CONSTRUCTION | 381000 | FY 2030: 381000
BL-0057 | Bike & Ped | Locally Selected | Irwin Creek Greenway | Clanton Road to Lester Street in Charlotte | Construct greenway. | 1.3 | Mecklenburg | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L(M) | CONSTRUCTION | 1216000 | FY 2030: 1216000
BL-0058 | Bike & Ped | Locally Selected | Rail Trail Pedestrian Bridge | SR 3815 (East Morehead Street) to Brooklyn Village Light Rail Station over I-277 (Belk Freeway) in Charlotte | Construct rail trail pedestrian bridge. | 0.11 | Mecklenburg | 10 | Charlotte Regional TPO | $1.903M IN STBG-DA FUNDS SWAPPED FOR $1.903M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | CONSTRUCTION | 1903000
BL-0058 | Bike & Ped | Locally Selected | Rail Trail Pedestrian Bridge | SR 3815 (East Morehead Street) to Brooklyn Village Light Rail Station over I-277 (Belk Freeway) in Charlotte | Construct rail trail pedestrian bridge. | 0.11 | Mecklenburg | 10 | Charlotte Regional TPO | $1.903M IN STBG-DA FUNDS SWAPPED FOR $1.903M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | CONSTRUCTION | 4440000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDACV | ENGINEERING | 110000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | ENGINEERING | 250000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 63000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | RIGHT-OF-WAY | 216000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | RIGHT-OF-WAY | 54000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | CONSTRUCTION | 416000
BL-0059 | Bike & Ped | Locally Selected | SR 1573 (K Avenue) | Fort Fisher and North 3rd Street intersections in Kure Beach | Construct intersections including ADA crosswalks, pedestrian actuated push buttons, and sidewalk connections. | 0.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 104000
BL-0060 | Bike & Ped | Locally Selected | Clarke Creek Greenway | Beginning at JE ‘Jim’ Ramseur Park near Cox Mill Elementary School, crossing Clarke Creek to the Highland Creek neighborhood and crossing back to a terminus at the Allen Mills neighborhood along Cox Mill Road | Construct greenway. | 3.6 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 10000
BL-0060 | Bike & Ped | Locally Selected | Clarke Creek Greenway | Beginning at JE ‘Jim’ Ramseur Park near Cox Mill Elementary School, crossing Clarke Creek to the Highland Creek neighborhood and crossing back to a terminus at the Allen Mills neighborhood along Cox Mill Road | Construct greenway. | 3.6 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 3000
BL-0060 | Bike & Ped | Locally Selected | Clarke Creek Greenway | Beginning at JE ‘Jim’ Ramseur Park near Cox Mill Elementary School, crossing Clarke Creek to the Highland Creek neighborhood and crossing back to a terminus at the Allen Mills neighborhood along Cox Mill Road | Construct greenway. | 3.6 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 3680000 | FY 2026: 3680000
BL-0060 | Bike & Ped | Locally Selected | Clarke Creek Greenway | Beginning at JE ‘Jim’ Ramseur Park near Cox Mill Elementary School, crossing Clarke Creek to the Highland Creek neighborhood and crossing back to a terminus at the Allen Mills neighborhood along Cox Mill Road | Construct greenway. | 3.6 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 920000 | FY 2026: 920000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (Hurdle Mills Road); Southern Middle School | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Person | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 104000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (Hurdle Mills Road); Southern Middle School | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Person | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | ENGINEERING | 26000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (Hurdle Mills Road); Southern Middle School | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Person | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 52000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (Hurdle Mills Road); Southern Middle School | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Person | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 13000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (Hurdle Mills Road); Southern Middle School | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Person | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 360000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (Hurdle Mills Road); Southern Middle School | Sandstone Way to Cleveland Lane; NC 157 (Hurdle Mills Road) to Delta Drive; Southern Middle School Road intersection in Roxboro | Construct sidewalk, construct intersection improvements and crosswalks, and install accessible pedestrian signals and rectangular rapid flashing beacons across NC 157. | 0.44 | Person | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | CONSTRUCTION | 90000
BL-0062 | Bike & Ped | Locally Selected | Pittsboro Elementary School Road | Farrell Street to McClehanan Street | Complete sidewalk gap. | 0.11 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CMAQ | ENGINEERING | 47000
BL-0062 | Bike & Ped | Locally Selected | Pittsboro Elementary School Road | Farrell Street to McClehanan Street | Complete sidewalk gap. | 0.11 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 12000
BL-0062 | Bike & Ped | Locally Selected | Pittsboro Elementary School Road | Farrell Street to McClehanan Street | Complete sidewalk gap. | 0.11 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 176000
BL-0062 | Bike & Ped | Locally Selected | Pittsboro Elementary School Road | Farrell Street to McClehanan Street | Complete sidewalk gap. | 0.11 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 44000
BL-0063 | Bike & Ped | Locally Selected | SR 1443 (Horton Road) | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | ENGINEERING | 964000
BL-0063 | Bike & Ped | Locally Selected | SR 1443 (Horton Road) | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Durham | 5 | Triangle West TPO |  | Exempt |  | L(M) | ENGINEERING | 241000
BL-0063 | Bike & Ped | Locally Selected | SR 1443 (Horton Road) | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Durham | 5 | Triangle West TPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 457000 | FY 2028: 457000
BL-0063 | Bike & Ped | Locally Selected | SR 1443 (Horton Road) | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Durham | 5 | Triangle West TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 114000 | FY 2028: 114000
BL-0063 | Bike & Ped | Locally Selected | SR 1443 (Horton Road) | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Durham | 5 | Triangle West TPO |  | Exempt |  | BGDA | CONSTRUCTION | 739000 | FY 2029: 739000
BL-0063 | Bike & Ped | Locally Selected | SR 1443 (Horton Road) | NC 157 (Guess Road) to US 501 (Roxboro Road) in Durham | Construct multi-use path and complete sidewalk gaps. | 1.6 | Durham | 5 | Triangle West TPO |  | Exempt |  | L(M) | CONSTRUCTION | 185000 | FY 2029: 185000
BL-0064 | Bike & Ped | Locally Selected | US 64 West Alternate | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | ENGINEERING | 107000
BL-0064 | Bike & Ped | Locally Selected | US 64 West Alternate | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 27000
BL-0064 | Bike & Ped | Locally Selected | US 64 West Alternate | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 41000 | FY 2026: 41000
BL-0064 | Bike & Ped | Locally Selected | US 64 West Alternate | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0064 | Bike & Ped | Locally Selected | US 64 West Alternate | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 469000 | FY 2027: 261000; FY 2028: 208000
BL-0064 | Bike & Ped | Locally Selected | US 64 West Alternate | West Howard Street to NC 111 (West Wilson Street) in Tarboro | Construct 10 foot multi-use path along Western Boulevard. | 0.69 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 117000 | FY 2027: 65000; FY 2028: 52000
BL-0065 | Bike & Ped | Locally Selected | Lenior Greenway | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGDA | ENGINEERING | 245000
BL-0065 | Bike & Ped | Locally Selected | Lenior Greenway | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | L(M) | ENGINEERING | 61000
BL-0065 | Bike & Ped | Locally Selected | Lenior Greenway | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGDA | RIGHT-OF-WAY | 225000 | FY 2026: 225000
BL-0065 | Bike & Ped | Locally Selected | Lenior Greenway | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | L(M) | RIGHT-OF-WAY | 56000 | FY 2026: 56000
BL-0065 | Bike & Ped | Locally Selected | Lenior Greenway | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGDA | CONSTRUCTION | 1264000 | FY 2027: 1264000
BL-0065 | Bike & Ped | Locally Selected | Lenior Greenway | SR 1300 (Harper Avenue) to Morganton Boulevard in Lenoir | Extend multi-use path. | 0.84 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | L(M) | CONSTRUCTION | 317000 | FY 2027: 317000
BL-0066 | Bike & Ped | Locally Selected | SR 1453 (Springs Road Northeast) | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Catawba | 12 | Greater Hickory MPO | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | ENGINEERING | 280000
BL-0066 | Bike & Ped | Locally Selected | SR 1453 (Springs Road Northeast) | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Catawba | 12 | Greater Hickory MPO | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | ENGINEERING | 70000
BL-0066 | Bike & Ped | Locally Selected | SR 1453 (Springs Road Northeast) | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Catawba | 12 | Greater Hickory MPO | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | RIGHT-OF-WAY | 200000 | FY 2026: 200000
BL-0066 | Bike & Ped | Locally Selected | SR 1453 (Springs Road Northeast) | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Catawba | 12 | Greater Hickory MPO | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | RIGHT-OF-WAY | 50000
BL-0066 | Bike & Ped | Locally Selected | SR 1453 (Springs Road Northeast) | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Catawba | 12 | Greater Hickory MPO | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | CONSTRUCTION | 2050000 | FY 2026: 2050000
BL-0066 | Bike & Ped | Locally Selected | SR 1453 (Springs Road Northeast) | Sandy Ridge Road to SR 1005 (McDonald Parkway NE) in Hickory | Construct sidewalk. | 1.26 | Catawba | 12 | Greater Hickory MPO | $2.05M IN TADA FUNDS SWITCHED WITH $2.05M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | CONSTRUCTION | 350000 | FY 2026: 350000
BL-0067 | Bike & Ped | Locally Selected | Aviation Walk Connector | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | ENGINEERING | 120000
BL-0067 | Bike & Ped | Locally Selected | Aviation Walk Connector | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | ENGINEERING | 30000
BL-0067 | Bike & Ped | Locally Selected | Aviation Walk Connector | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | RIGHT-OF-WAY | 200000
BL-0067 | Bike & Ped | Locally Selected | Aviation Walk Connector | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | RIGHT-OF-WAY | 50000
BL-0067 | Bike & Ped | Locally Selected | Aviation Walk Connector | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | CONSTRUCTION | 1280000 | FY 2026: 1280000
BL-0067 | Bike & Ped | Locally Selected | Aviation Walk Connector | SR 1371 (Clement Boulevard NW) to 17th Street Northwest in Hickory | Extend multi-use path. | 0.26 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.28M IN BGDA FUNDS SWITCHED WITH $1.28M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | CONSTRUCTION | 320000 | FY 2026: 320000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | ENGINEERING | 324000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | ENGINEERING | 81000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | RIGHT-OF-WAY | 390000 | FY 2026: 390000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | RIGHT-OF-WAY | 100000 | FY 2026: 100000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | CONSTRUCTION | 680000 | FY 2027: 680000
BL-0068 | Bike & Ped | Locally Selected | SR 1006 (Island Ford Road) | Don's Grill to Living Word Church in Maiden | Construct sidewalks. | 0.56 | Catawba | 12 | Greater Hickory MPO | $390K IN BGDA FUNDS SWITCHED WITH $390K IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | CONSTRUCTION | 170000 | FY 2027: 170000
BL-0069 | Bike & Ped | Other | Wilson | Hominy Creek Greenway and Trail Network | Construct greenway. | 3.8 | Wilson | 4 | Upper Coastal Plain RPO | DP FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT. | Exempt |  | DP | ENGINEERING | 950000
BL-0070 | Bike & Ped | Locally Selected | SR 1008 (Mount Carmel Church Road); US 15 / US 501 | North side of Governors Drive to existing sidewalk and intersection of SR 1831 / 1848 (Village Park Drive); SR 1724 (Old Lystra Road) intersection in Chapel Hill | Install pedestrian signals and crosswalks. |  | Chatham | 8 | Triangle West TPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | BGDACV | ENGINEERING | 5000
BL-0070 | Bike & Ped | Locally Selected | SR 1008 (Mount Carmel Church Road); US 15 / US 501 | North side of Governors Drive to existing sidewalk and intersection of SR 1831 / 1848 (Village Park Drive); SR 1724 (Old Lystra Road) intersection in Chapel Hill | Install pedestrian signals and crosswalks. |  | Chatham | 8 | Triangle West TPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | BGDA | CONSTRUCTION | 140000
BL-0070 | Bike & Ped | Locally Selected | SR 1008 (Mount Carmel Church Road); US 15 / US 501 | North side of Governors Drive to existing sidewalk and intersection of SR 1831 / 1848 (Village Park Drive); SR 1724 (Old Lystra Road) intersection in Chapel Hill | Install pedestrian signals and crosswalks. |  | Chatham | 8 | Triangle West TPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | L(M) | CONSTRUCTION | 17000
BL-0070 | Bike & Ped | Locally Selected | SR 1008 (Mount Carmel Church Road); US 15 / US 501 | North side of Governors Drive to existing sidewalk and intersection of SR 1831 / 1848 (Village Park Drive); SR 1724 (Old Lystra Road) intersection in Chapel Hill | Install pedestrian signals and crosswalks. |  | Chatham | 8 | Triangle West TPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | HF | CONSTRUCTION | 18000
BL-0071 | Bike & Ped | Locally Selected | High Point | Harvell Park to Goldston Park; Sunset Drive to Commerce Avenue | Construct greenway on new location connecting Harvell Park and Goldston Park; Construct pedestrian, bicycle, roadway, and streetscape improvements. | 4.3 | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | DP | ENGINEERING | 5000000
BL-0071 | Bike & Ped | Locally Selected | High Point | Harvell Park to Goldston Park; Sunset Drive to Commerce Avenue | Construct greenway on new location connecting Harvell Park and Goldston Park; Construct pedestrian, bicycle, roadway, and streetscape improvements. | 4.3 | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | DP | RIGHT-OF-WAY | 2000000 | FY 2026: 2000000
BL-0071A | Bike & Ped | Locally Selected | Southwest Heritage Greenway | Harvell Park to Goldston Park in High Point. | Construct greenway on new location. | 0.72 | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. | Exempt |  | DP | CONSTRUCTION | 6626000 | FY 2026: 6626000
BL-0071A | Bike & Ped | Locally Selected | Southwest Heritage Greenway | Harvell Park to Goldston Park in High Point. | Construct greenway on new location. | 0.72 | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. | Exempt |  | L | CONSTRUCTION | 1000000 | FY 2026: 1000000
BL-0071A | Bike & Ped | Locally Selected | Southwest Heritage Greenway | Harvell Park to Goldston Park in High Point. | Construct greenway on new location. | 0.72 | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. | Exempt |  | HF | CONSTRUCTION | 200000 | FY 2026: 2000; FY 2027: 159000; FY 2028: 39000
BL-0071B | Bike & Ped | Locally Selected | Elm Street | Sunset Drive to Commerce Avenue. | Construct pedestrian, bicycle, roadway, and streetscape improvements. |  | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | DP | CONSTRUCTION | 6176000 | FY 2026: 6176000
BL-0071B | Bike & Ped | Locally Selected | Elm Street | Sunset Drive to Commerce Avenue. | Construct pedestrian, bicycle, roadway, and streetscape improvements. |  | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | O | CONSTRUCTION | 1500000 | FY 2026: 1500000
BL-0071B | Bike & Ped | Locally Selected | Elm Street | Sunset Drive to Commerce Avenue. | Construct pedestrian, bicycle, roadway, and streetscape improvements. |  | Guilford | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | L | CONSTRUCTION | 6188000 | FY 2026: 6188000
BL-0072 | Bike & Ped | Locally Selected | Salem Creek Greenway Bridge | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 258000
BL-0072 | Bike & Ped | Locally Selected | Salem Creek Greenway Bridge | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 64000
BL-0072 | Bike & Ped | Locally Selected | Salem Creek Greenway Bridge | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 92000 | FY 2028: 92000
BL-0072 | Bike & Ped | Locally Selected | Salem Creek Greenway Bridge | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 23000 | FY 2028: 23000
BL-0072 | Bike & Ped | Locally Selected | Salem Creek Greenway Bridge | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 460000 | FY 2029: 460000
BL-0072 | Bike & Ped | Locally Selected | Salem Creek Greenway Bridge | West of Salem Lake near Winston-Salem. | Construct greenway trail. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 115000 | FY 2029: 115000
BL-0073 | Bike & Ped | Locally Selected | SR 1308 (Gum Branch Road) | Nottingham Road to north Onsville Drive intersection in Jacksonville. | Construct pedestrian improvements. | 1.49 | Onslow | 3 | Jacksonville Urban Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 256000
BL-0073 | Bike & Ped | Locally Selected | SR 1308 (Gum Branch Road) | Nottingham Road to north Onsville Drive intersection in Jacksonville. | Construct pedestrian improvements. | 1.49 | Onslow | 3 | Jacksonville Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 64000
BL-0074 | Bike & Ped | Locally Selected | US 17 | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | TADA | ENGINEERING | 146000
BL-0074 | Bike & Ped | Locally Selected | US 17 | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | L(M) | ENGINEERING | 37000
BL-0074 | Bike & Ped | Locally Selected | US 17 | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | TADA | RIGHT-OF-WAY | 20000
BL-0074 | Bike & Ped | Locally Selected | US 17 | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | L(M) | RIGHT-OF-WAY | 5000
BL-0074 | Bike & Ped | Locally Selected | US 17 | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | TADA | CONSTRUCTION | 500000
BL-0074 | Bike & Ped | Locally Selected | US 17 | Ploof Road and Olde Waterford Way in Leland | Install signalized zebra-type pedestrian crossing. | 0.1 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | L(M) | CONSTRUCTION | 125000
BL-0075 | Bike & Ped | Locally Selected | US 76 (Causeway Drive); US 74 (West Salisbury Street) | Along US 76 (Causeway Drive) and US 74 (West Salisbury Street) in Wrightsville Beach | Install on-street bicycle lanes and pedestrian crosswalks. | 2.1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 8000
BL-0075 | Bike & Ped | Locally Selected | US 76 (Causeway Drive); US 74 (West Salisbury Street) | Along US 76 (Causeway Drive) and US 74 (West Salisbury Street) in Wrightsville Beach | Install on-street bicycle lanes and pedestrian crosswalks. | 2.1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 2000
BL-0075 | Bike & Ped | Locally Selected | US 76 (Causeway Drive); US 74 (West Salisbury Street) | Along US 76 (Causeway Drive) and US 74 (West Salisbury Street) in Wrightsville Beach | Install on-street bicycle lanes and pedestrian crosswalks. | 2.1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 1833000
BL-0075 | Bike & Ped | Locally Selected | US 76 (Causeway Drive); US 74 (West Salisbury Street) | Along US 76 (Causeway Drive) and US 74 (West Salisbury Street) in Wrightsville Beach | Install on-street bicycle lanes and pedestrian crosswalks. | 2.1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 458000
BL-0076 | Bike & Ped | Locally Selected | SR 2002 (Riceville Road) | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Buncombe | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | TADA | ENGINEERING | 187000
BL-0076 | Bike & Ped | Locally Selected | SR 2002 (Riceville Road) | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Buncombe | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | HF(M) | ENGINEERING | 187000
BL-0076 | Bike & Ped | Locally Selected | SR 2002 (Riceville Road) | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Buncombe | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | TADA | RIGHT-OF-WAY | 394000 | FY 2026: 394000
BL-0076 | Bike & Ped | Locally Selected | SR 2002 (Riceville Road) | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Buncombe | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | HF(M) | RIGHT-OF-WAY | 394000 | FY 2026: 394000
BL-0076 | Bike & Ped | Locally Selected | SR 2002 (Riceville Road) | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Buncombe | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | TADA | CONSTRUCTION | 917000 | FY 2027: 917000
BL-0076 | Bike & Ped | Locally Selected | SR 2002 (Riceville Road) | US 70 to north of the Veterans Affairs Hospital driveway in Asheville | Construct sidewalks and crossing improvements. | 0.16 | Buncombe | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | HF(M) | CONSTRUCTION | 1034000 | FY 2027: 1034000
BL-0078 | Bike & Ped | Locally Selected | Ecusta Trail | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Henderson | 14 | French Broad River MPO | DP REPRESENTS NSFLTP GRANT OF $15.707M. | Division 14 |  | BGDA | ENGINEERING | 1440000
BL-0078 | Bike & Ped | Locally Selected | Ecusta Trail | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Henderson | 14 | French Broad River MPO | DP REPRESENTS NSFLTP GRANT OF $15.707M. | Division 14 |  | L(M) | ENGINEERING | 360000
BL-0078 | Bike & Ped | Locally Selected | Ecusta Trail | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Henderson | 14 | French Broad River MPO | DP REPRESENTS NSFLTP GRANT OF $15.707M. | Division 14 |  | DP | CONSTRUCTION | 15707000
BL-0078 | Bike & Ped | Locally Selected | Ecusta Trail | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Henderson | 14 | French Broad River MPO | DP REPRESENTS NSFLTP GRANT OF $15.707M. | Division 14 |  | BGDA | CONSTRUCTION | 11746000 | FY 2026: 10714000
BL-0078 | Bike & Ped | Locally Selected | Ecusta Trail | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Henderson | 14 | French Broad River MPO | DP REPRESENTS NSFLTP GRANT OF $15.707M. | Division 14 |  | L(M) | CONSTRUCTION | 4682000 | FY 2026: 2679000
BL-0078 | Bike & Ped | Locally Selected | Ecusta Trail | US 64 to Transylvania County line near Etowah | Construct greenway. |  | Henderson | 14 | French Broad River MPO | DP REPRESENTS NSFLTP GRANT OF $15.707M. | Division 14 |  | L | CONSTRUCTION | 1865000 | FY 2026: 1865000
BL-0080 | Bike & Ped | Locally Selected | Huntersville | US 21 in Huntersville. | Construct greenway culvert under roadway. | 0.21 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 8000
BL-0080 | Bike & Ped | Locally Selected | Huntersville | US 21 in Huntersville. | Construct greenway culvert under roadway. | 0.21 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 2000
BL-0080 | Bike & Ped | Locally Selected | Huntersville | US 21 in Huntersville. | Construct greenway culvert under roadway. | 0.21 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 2592000
BL-0080 | Bike & Ped | Locally Selected | Huntersville | US 21 in Huntersville. | Construct greenway culvert under roadway. | 0.21 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 648000
BL-0081 | Bike & Ped | Locally Selected | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 347000
BL-0081 | Bike & Ped | Locally Selected | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 87000
BL-0081 | Bike & Ped | Locally Selected | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 106000 | FY 2028: 106000
BL-0081 | Bike & Ped | Locally Selected | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 27000 | FY 2028: 27000
BL-0081 | Bike & Ped | Locally Selected | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 865000 | FY 2029: 865000
BL-0081 | Bike & Ped | Locally Selected | SR 3135 (Lebanon Road); SR 3156 (Margaret Wallace Road) | SR 3156 (Margaret Wallace Road) to Gristmill Lane; SR 3143 (Idlewild Road) to SR 3135 (Lebanon Road) in Mint Hill | Construct sidewalks. | 0.99 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 216000 | FY 2029: 216000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | ENGINEERING | 172000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | ENGINEERING | 172000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | RIGHT-OF-WAY | 350000 | FY 2027: 350000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | RIGHT-OF-WAY | 350000 | FY 2027: 350000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TADA | CONSTRUCTION | 358000 | FY 2029: 358000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | CONSTRUCTION | 1556000 | FY 2029: 1556000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | SR 1246 (Fairview Road) to SR 1135 (Waterlynn Road) in Mooresville | Construct multi-use path. | 0.55 | Iredell | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | CONSTRUCTION | 1915000 | FY 2029: 1915000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | TADA | ENGINEERING | 6000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L(M) | ENGINEERING | 4000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | TADA | RIGHT-OF-WAY | 377000 | FY 2026: 377000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L(M) | RIGHT-OF-WAY | 309000 | FY 2026: 309000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | DP | CONSTRUCTION | 12000000 | FY 2027: 12000000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | TADA | CONSTRUCTION | 2040000 | FY 2027: 2040000
BL-0083 | Bike & Ped | Locally Selected | Sugar Creek Road | SR 2502 (Rumple Road) to Nevin Road, Roman Road to Graham Street in Charlotte. Merlane Drive to North Tryon Street in Charlotte | Construct sidewalk. Construct multi-use path. Install pedestrian improvements at Sofley Road. Improve transit stops at Sugar Creek Road, Merlane Drive, and Mallard Creek Road. | 1.07 | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L(M) | CONSTRUCTION | 6222000 | FY 2027: 6222000
BL-0084 | Bike & Ped | Locally Selected | Albemarle Road; Wilora Lake Road | Redman Road to Nevin Road in Charlotte; Albemarle Road to 100 feet north of Barr Drive in Charlotte | Construct sidewalk; Construct sidewalk and pedestrian improvements at various intersections. | 0.93 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 6000
BL-0084 | Bike & Ped | Locally Selected | Albemarle Road; Wilora Lake Road | Redman Road to Nevin Road in Charlotte; Albemarle Road to 100 feet north of Barr Drive in Charlotte | Construct sidewalk; Construct sidewalk and pedestrian improvements at various intersections. | 0.93 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 4000
BL-0084 | Bike & Ped | Locally Selected | Albemarle Road; Wilora Lake Road | Redman Road to Nevin Road in Charlotte; Albemarle Road to 100 feet north of Barr Drive in Charlotte | Construct sidewalk; Construct sidewalk and pedestrian improvements at various intersections. | 0.93 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 1750000 | FY 2027: 1750000
BL-0084 | Bike & Ped | Locally Selected | Albemarle Road; Wilora Lake Road | Redman Road to Nevin Road in Charlotte; Albemarle Road to 100 feet north of Barr Drive in Charlotte | Construct sidewalk; Construct sidewalk and pedestrian improvements at various intersections. | 0.93 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 1432000 | FY 2027: 1432000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | ENGINEERING | 230000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | ENGINEERING | 57000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 138000 | FY 2026: 138000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 34000 | FY 2026: 34000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | UTILITIES | 45000 | FY 2026: 45000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | UTILITIES | 11000 | FY 2026: 11000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | CONSTRUCTION | 1250000 | FY 2027: 1250000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (Hickory Ridge Road); SR 1161 (Stallings Road) | SR 1161 (Stallings Road) to Hickory Ridge Middle School; SR 1138 (Hickory Ridge Road) to SR 1304 (Harrisburg Veterans Road) in Charlotte. | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 313000 | FY 2027: 313000
BL-0087 | Bike & Ped | Locally Selected | Various | Elm Street Avenue Northwest from Glenn Street Northwest to Alexander Street Northwest in Concord; Glenn Street Northwest from Elm Avenue Northwest to Academy Avenue Northwest in Concord; Crowell Drive Northwest from Clearwater Arts Center driveway to Ceda | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | ENGINEERING | 8000
BL-0087 | Bike & Ped | Locally Selected | Various | Elm Street Avenue Northwest from Glenn Street Northwest to Alexander Street Northwest in Concord; Glenn Street Northwest from Elm Avenue Northwest to Academy Avenue Northwest in Concord; Crowell Drive Northwest from Clearwater Arts Center driveway to Ceda | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | ENGINEERING | 2000
BL-0087 | Bike & Ped | Locally Selected | Various | Elm Street Avenue Northwest from Glenn Street Northwest to Alexander Street Northwest in Concord; Glenn Street Northwest from Elm Avenue Northwest to Academy Avenue Northwest in Concord; Crowell Drive Northwest from Clearwater Arts Center driveway to Ceda | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | CONSTRUCTION | 1292000 | FY 2026: 1292000
BL-0087 | Bike & Ped | Locally Selected | Various | Elm Street Avenue Northwest from Glenn Street Northwest to Alexander Street Northwest in Concord; Glenn Street Northwest from Elm Avenue Northwest to Academy Avenue Northwest in Concord; Crowell Drive Northwest from Clearwater Arts Center driveway to Ceda | Construct sidewalks. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 323000 | FY 2026: 323000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | ENGINEERING | 12000 | FY 2026: 12000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | ENGINEERING | 56000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | ENGINEERING | 17000 | FY 2026: 3000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 72000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 18000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | UTILITIES | 20000 | FY 2026: 20000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | UTILITIES | 8000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | UTILITIES | 7000 | FY 2026: 5000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 328000 | FY 2026: 328000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | CONSTRUCTION | 304000 | FY 2026: 304000
BL-0088 | Bike & Ped | Locally Selected | Kerns Street; North Oak Street; Crook Street | SR 2300 (North Main Street) to US 52; Crook Street to Granite Civic Park; SR 2300 (North Main Street) to North Oak Street in Granite Quarry. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 158000 | FY 2026: 158000
BL-0089 | Bike & Ped | Locally Selected | US 401 (South Saunders Street) | SR 1009 (Lake Wheeler Road) to north of Dorothea Drive in Raleigh | Construct shared use path. | 0.12 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0089 | Bike & Ped | Locally Selected | US 401 (South Saunders Street) | SR 1009 (Lake Wheeler Road) to north of Dorothea Drive in Raleigh | Construct shared use path. | 0.12 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BL-0089 | Bike & Ped | Locally Selected | US 401 (South Saunders Street) | SR 1009 (Lake Wheeler Road) to north of Dorothea Drive in Raleigh | Construct shared use path. | 0.12 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 657000
BL-0089 | Bike & Ped | Locally Selected | US 401 (South Saunders Street) | SR 1009 (Lake Wheeler Road) to north of Dorothea Drive in Raleigh | Construct shared use path. | 0.12 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 164000
BL-0089 | Bike & Ped | Locally Selected | US 401 (South Saunders Street) | SR 1009 (Lake Wheeler Road) to north of Dorothea Drive in Raleigh | Construct shared use path. | 0.12 | Wake | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 274000
BL-0090 | Bike & Ped | Locally Selected | SR 1500 (East Mclver Street); South Wilma Street | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Harnett | 6 | Capital Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 120000
BL-0090 | Bike & Ped | Locally Selected | SR 1500 (East Mclver Street); South Wilma Street | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Harnett | 6 | Capital Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 30000
BL-0090 | Bike & Ped | Locally Selected | SR 1500 (East Mclver Street); South Wilma Street | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Harnett | 6 | Capital Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 40000
BL-0090 | Bike & Ped | Locally Selected | SR 1500 (East Mclver Street); South Wilma Street | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Harnett | 6 | Capital Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 10000
BL-0090 | Bike & Ped | Locally Selected | SR 1500 (East Mclver Street); South Wilma Street | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Harnett | 6 | Capital Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 718000 | FY 2026: 718000
BL-0090 | Bike & Ped | Locally Selected | SR 1500 (East Mclver Street); South Wilma Street | SR 1500 (East Mclver Street) and South Wilma Street in Angier | Construct sidewalk extensions and install crosswalk. | 0.37 | Harnett | 6 | Capital Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 180000 | FY 2026: 180000
BL-0091 | Bike & Ped | Locally Selected | Higgins Greenway | Shirley Drive to north of intersection of Walnut Street and SR 1300 (Kildaire Farm Road) in Cary | Complete a gap of greenway trail. | 0.27 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0091 | Bike & Ped | Locally Selected | Higgins Greenway | Shirley Drive to north of intersection of Walnut Street and SR 1300 (Kildaire Farm Road) in Cary | Complete a gap of greenway trail. | 0.27 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BL-0091 | Bike & Ped | Locally Selected | Higgins Greenway | Shirley Drive to north of intersection of Walnut Street and SR 1300 (Kildaire Farm Road) in Cary | Complete a gap of greenway trail. | 0.27 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1960000 | FY 2026: 1960000
BL-0091 | Bike & Ped | Locally Selected | Higgins Greenway | Shirley Drive to north of intersection of Walnut Street and SR 1300 (Kildaire Farm Road) in Cary | Complete a gap of greenway trail. | 0.27 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 490000 | FY 2026: 490000
BL-0092 | Bike & Ped | Locally Selected | Alston Ridge Greenway | Alston Ridge Greenway to Bass Lake Greenway in Fuquay-Varina. | Complete a gap of greenway trail. | 0.41 | Wake | 5 | Capital Area MPO | Under Construction. | Exempt |  | CMAQ | ENGINEERING | 10000
BL-0092 | Bike & Ped | Locally Selected | Alston Ridge Greenway | Alston Ridge Greenway to Bass Lake Greenway in Fuquay-Varina. | Complete a gap of greenway trail. | 0.41 | Wake | 5 | Capital Area MPO | Under Construction. | Exempt |  | L(M) | ENGINEERING | 7000
BL-0092 | Bike & Ped | Locally Selected | Alston Ridge Greenway | Alston Ridge Greenway to Bass Lake Greenway in Fuquay-Varina. | Complete a gap of greenway trail. | 0.41 | Wake | 5 | Capital Area MPO | Under Construction. | Exempt |  | CMAQ | CONSTRUCTION | 1269000 | FY 2026: 350000
BL-0092 | Bike & Ped | Locally Selected | Alston Ridge Greenway | Alston Ridge Greenway to Bass Lake Greenway in Fuquay-Varina. | Complete a gap of greenway trail. | 0.41 | Wake | 5 | Capital Area MPO | Under Construction. | Exempt |  | L(M) | CONSTRUCTION | 845000 | FY 2026: 233000
BL-0092 | Bike & Ped | Locally Selected | Alston Ridge Greenway | Alston Ridge Greenway to Bass Lake Greenway in Fuquay-Varina. | Complete a gap of greenway trail. | 0.41 | Wake | 5 | Capital Area MPO | Under Construction. | Exempt |  | L | CONSTRUCTION | 117000 | FY 2026: 117000
BL-0093 | Bike & Ped | Locally Selected | Utley Creek Greenway West | NC 55 to Holly Glen subdivision sidewalk in Holly Springs | Complete a gap of greenway trail. | 1.06 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 14000
BL-0093 | Bike & Ped | Locally Selected | Utley Creek Greenway West | NC 55 to Holly Glen subdivision sidewalk in Holly Springs | Complete a gap of greenway trail. | 1.06 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 6000
BL-0093 | Bike & Ped | Locally Selected | Utley Creek Greenway West | NC 55 to Holly Glen subdivision sidewalk in Holly Springs | Complete a gap of greenway trail. | 1.06 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1925000
BL-0093 | Bike & Ped | Locally Selected | Utley Creek Greenway West | NC 55 to Holly Glen subdivision sidewalk in Holly Springs | Complete a gap of greenway trail. | 1.06 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 481000
BL-0093 | Bike & Ped | Locally Selected | Utley Creek Greenway West | NC 55 to Holly Glen subdivision sidewalk in Holly Springs | Complete a gap of greenway trail. | 1.06 | Wake | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 344000
BL-0095 | Bike & Ped | Locally Selected | Saunders Street | SR 1307 (West Chatham Street) to Hinton Street in Apex | Construct sidewalk extensions. | 0.4 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 16000
BL-0095 | Bike & Ped | Locally Selected | Saunders Street | SR 1307 (West Chatham Street) to Hinton Street in Apex | Construct sidewalk extensions. | 0.4 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 4000
BL-0095 | Bike & Ped | Locally Selected | Saunders Street | SR 1307 (West Chatham Street) to Hinton Street in Apex | Construct sidewalk extensions. | 0.4 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1075000 | FY 2026: 1075000
BL-0095 | Bike & Ped | Locally Selected | Saunders Street | SR 1307 (West Chatham Street) to Hinton Street in Apex | Construct sidewalk extensions. | 0.4 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 269000 | FY 2026: 269000
BL-0096 | Bike & Ped | Locally Selected | Beaty Street | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 198000
BL-0096 | Bike & Ped | Locally Selected | Beaty Street | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 132000
BL-0096 | Bike & Ped | Locally Selected | Beaty Street | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 361000 | FY 2026: 361000
BL-0096 | Bike & Ped | Locally Selected | Beaty Street | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 240000 | FY 2026: 240000
BL-0096 | Bike & Ped | Locally Selected | Beaty Street | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 1537000 | FY 2028: 1537000
BL-0096 | Bike & Ped | Locally Selected | Beaty Street | NC 115 (North Main Street) to SR 2158 (Griffith Street) in Davidson | Construct shared use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 1024000 | FY 2028: 1024000
BL-0101 | Bike & Ped | Locally Selected | Cameron Avenue | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | ENGINEERING | 40000
BL-0101 | Bike & Ped | Locally Selected | Cameron Avenue | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 10000
BL-0101 | Bike & Ped | Locally Selected | Cameron Avenue | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 140000 | FY 2026: 140000
BL-0101 | Bike & Ped | Locally Selected | Cameron Avenue | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 35000 | FY 2026: 35000
BL-0101 | Bike & Ped | Locally Selected | Cameron Avenue | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 580000 | FY 2027: 580000
BL-0101 | Bike & Ped | Locally Selected | Cameron Avenue | SR 1927 (South Merritt Mill Road) to NC 86 (South Columbia Street) in Chapel Hill | Construct bike lanes and cycle path. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 145000 | FY 2027: 145000
BL-0105 | Bike & Ped | Locally Selected | Leisure Lane | NC 275 to trailhead for Gaston Technology Park Greenway near Sportsman Drive in Dallas | Construct greenway. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | ENGINEERING | 124000 | FY 2026: 124000
BL-0105 | Bike & Ped | Locally Selected | Leisure Lane | NC 275 to trailhead for Gaston Technology Park Greenway near Sportsman Drive in Dallas | Construct greenway. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L(M) | ENGINEERING | 31000 | FY 2026: 31000
BL-0105 | Bike & Ped | Locally Selected | Leisure Lane | NC 275 to trailhead for Gaston Technology Park Greenway near Sportsman Drive in Dallas | Construct greenway. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 339000 | FY 2027: 3000; FY 2028: 336000
BL-0105 | Bike & Ped | Locally Selected | Leisure Lane | NC 275 to trailhead for Gaston Technology Park Greenway near Sportsman Drive in Dallas | Construct greenway. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L(M) | CONSTRUCTION | 85000 | FY 2027: 85000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | CRPDA | ENGINEERING | 240000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | ENGINEERING | 60000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | CRPDA | RIGHT-OF-WAY | 40000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | RIGHT-OF-WAY | 10000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | BGDA | CONSTRUCTION | 765000 | FY 2026: 765000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | TAANY | CONSTRUCTION | 1355000 | FY 2026: 1355000
BL-0115 | Bike & Ped | Locally Selected | SR 1371 (Clement Boulevard); 21st Street Northwest | 21st Street Northwest to 19th Street Northwest in Hickory; SR 1371 (Clement Boulevard) to SR 1312 (9th Avenue Drive Northwest) in Hickory | Construct multi-use trails. | 0.31 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN TAANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 12 |  | L | CONSTRUCTION | 530000 | FY 2026: 530000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | TAANY | ENGINEERING | 880000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | ENGINEERING | 220000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | HP | RIGHT-OF-WAY | 750000 | FY 2026: 750000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | RIGHT-OF-WAY | 188000 | FY 2026: 188000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | TAANY | UTILITIES | 8000 | FY 2026: 8000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | UTILITIES | 2000 | FY 2026: 2000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | HP | CONSTRUCTION | 2970000 | FY 2027: 2970000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | TAANY | CONSTRUCTION | 1680000 | FY 2027: 1680000
BL-0116 | Bike & Ped | Locally Selected | A & Y Greenway | Hill Street to Rollins Road in Greensboro. | Extend greenway. |  | Guilford | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | CONSTRUCTION | 1163000 | FY 2027: 1163000
BL-0117 | Bike & Ped | Locally Selected | A & Y Greenway | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 88000
BL-0117 | Bike & Ped | Locally Selected | A & Y Greenway | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 22000
BL-0117 | Bike & Ped | Locally Selected | A & Y Greenway | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 8000 | FY 2026: 8000
BL-0117 | Bike & Ped | Locally Selected | A & Y Greenway | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
BL-0117 | Bike & Ped | Locally Selected | A & Y Greenway | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 1942000 | FY 2027: 1942000
BL-0117 | Bike & Ped | Locally Selected | A & Y Greenway | Bridge over Lake Brandt near Greensboro. | Replace bridge, improve greenway, and improve crossing at Strawberry Road. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 486000 | FY 2027: 486000
BL-0118 | Bike & Ped | Locally Selected | US 117 (College Road) | SR 2048 (Gordon Road) to SR 2206 (Northchase Parkway). | Construct bicycle and pedestrian improvements. | 2.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | RIGHT-OF-WAY | 513000
BL-0118 | Bike & Ped | Locally Selected | US 117 (College Road) | SR 2048 (Gordon Road) to SR 2206 (Northchase Parkway). | Construct bicycle and pedestrian improvements. | 2.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 1840000 | FY 2026: 1840000
BL-0118 | Bike & Ped | Locally Selected | US 117 (College Road) | SR 2048 (Gordon Road) to SR 2206 (Northchase Parkway). | Construct bicycle and pedestrian improvements. | 2.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 460000 | FY 2026: 460000
BL-0119 | Bike & Ped | Locally Selected | McDowell Creek Greenway | NC 73 near Lindholm Drive in Huntersville | Construct pedestrian bridge. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 3660000 | FY 2027: 3660000
BL-0119 | Bike & Ped | Locally Selected | McDowell Creek Greenway | NC 73 near Lindholm Drive in Huntersville | Construct pedestrian bridge. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 2440000 | FY 2027: 2440000
BL-0120 | Bike & Ped | Locally Selected | SR 1004 (Bain School Road) | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 305000 | FY 2026: 305000
BL-0120 | Bike & Ped | Locally Selected | SR 1004 (Bain School Road) | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 164000 | FY 2026: 164000
BL-0120 | Bike & Ped | Locally Selected | SR 1004 (Bain School Road) | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 143000 | FY 2028: 143000
BL-0120 | Bike & Ped | Locally Selected | SR 1004 (Bain School Road) | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 77000 | FY 2028: 77000
BL-0120 | Bike & Ped | Locally Selected | SR 1004 (Bain School Road) | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 715000 | FY 2030: 715000
BL-0120 | Bike & Ped | Locally Selected | SR 1004 (Bain School Road) | Gait Drive to SR 1004 (Philadelphia Church Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 385000 | FY 2030: 385000
BL-0121 | Bike & Ped | Locally Selected | SR 3128 (Lawyers Road) | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 255000 | FY 2026: 255000
BL-0121 | Bike & Ped | Locally Selected | SR 3128 (Lawyers Road) | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 64000 | FY 2026: 64000
BL-0121 | Bike & Ped | Locally Selected | SR 3128 (Lawyers Road) | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 189000 | FY 2028: 189000
BL-0121 | Bike & Ped | Locally Selected | SR 3128 (Lawyers Road) | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 47000 | FY 2028: 47000
BL-0121 | Bike & Ped | Locally Selected | SR 3128 (Lawyers Road) | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 619000 | FY 2030: 619000
BL-0121 | Bike & Ped | Locally Selected | SR 3128 (Lawyers Road) | Piaffe Avenue to SR 3125 (Thompson Road) in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 155000 | FY 2030: 155000
BL-0122 | Bike & Ped | Locally Selected | Patterson Heights | West Moore Avenue to West Iredell Avenue in Mooresville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 8000
BL-0122 | Bike & Ped | Locally Selected | Patterson Heights | West Moore Avenue to West Iredell Avenue in Mooresville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 2000
BL-0122 | Bike & Ped | Locally Selected | Patterson Heights | West Moore Avenue to West Iredell Avenue in Mooresville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 2518000 | FY 2028: 2518000
BL-0122 | Bike & Ped | Locally Selected | Patterson Heights | West Moore Avenue to West Iredell Avenue in Mooresville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 630000 | FY 2028: 630000
BL-0123 | Bike & Ped | Locally Selected | SR 2840 (Rocky River Road) | Rockland Drive to SR 2939 (Old Concord Road) in Charlotte | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 5000
BL-0123 | Bike & Ped | Locally Selected | SR 2840 (Rocky River Road) | Rockland Drive to SR 2939 (Old Concord Road) in Charlotte | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 5000
BL-0123 | Bike & Ped | Locally Selected | SR 2840 (Rocky River Road) | Rockland Drive to SR 2939 (Old Concord Road) in Charlotte | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 1976000 | FY 2027: 1976000
BL-0123 | Bike & Ped | Locally Selected | SR 2840 (Rocky River Road) | Rockland Drive to SR 2939 (Old Concord Road) in Charlotte | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 1976000 | FY 2027: 1976000
BL-0124 | Bike & Ped | Locally Selected | Truelight Church Road | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 400000 | FY 2026: 400000
BL-0124 | Bike & Ped | Locally Selected | Truelight Church Road | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 100000 | FY 2026: 100000
BL-0124 | Bike & Ped | Locally Selected | Truelight Church Road | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 99000 | FY 2028: 99000
BL-0124 | Bike & Ped | Locally Selected | Truelight Church Road | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 25000 | FY 2028: 25000
BL-0124 | Bike & Ped | Locally Selected | Truelight Church Road | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 973000 | FY 2030: 973000
BL-0124 | Bike & Ped | Locally Selected | Truelight Church Road | SR 5223 (Wilgrove-Mint Road) to Heather Nicole Lane in Mint Hill | Construct sidewalk. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 243000 | FY 2030: 243000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TADA | ENGINEERING | 7000 | FY 2026: 7000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 2000 | FY 2026: 2000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L | ENGINEERING | 1000 | FY 2026: 1000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TADA | RIGHT-OF-WAY | 35000 | FY 2027: 35000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 9000 | FY 2027: 9000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 6000 | FY 2027: 6000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TADA | CONSTRUCTION | 1043000 | FY 2027: 1043000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 261000 | FY 2027: 261000
BL-0125 | Bike & Ped | Locally Selected | Main Street | Moore Street to Smith Street in Clayton | Construct sidewalk on both sides of Main Street from Robertson Street to Moore Street. Add crosswalks, curb extensions, and pedestrian signals from Moore Street to Smith Street. | 1 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L | CONSTRUCTION | 186000 | FY 2027: 186000
BL-0126 | Bike & Ped | Locally Selected | Optimist Farm Greenway | Existing segment of the greenway behind Truelove Drive South and west to West Lake Road in Cary. | Construct 10 foot wide greenway and 0.2 miles of sidewalk. Includes pedestrian improvements at one intersection and a mid-block crossing on Optimist Farm Road. | 1.2 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 3250000
BL-0126 | Bike & Ped | Locally Selected | Optimist Farm Greenway | Existing segment of the greenway behind Truelove Drive South and west to West Lake Road in Cary. | Construct 10 foot wide greenway and 0.2 miles of sidewalk. Includes pedestrian improvements at one intersection and a mid-block crossing on Optimist Farm Road. | 1.2 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 813000
BL-0126 | Bike & Ped | Locally Selected | Optimist Farm Greenway | Existing segment of the greenway behind Truelove Drive South and west to West Lake Road in Cary. | Construct 10 foot wide greenway and 0.2 miles of sidewalk. Includes pedestrian improvements at one intersection and a mid-block crossing on Optimist Farm Road. | 1.2 | Wake | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 937000
BL-0127 | Bike & Ped | Locally Selected | Main Street | Various | Upgrade crosswalks along Main Street, add a new mid-block crossing at the intersection of Water Street and Main Street, and an improved crossing configuration for the Franklinton to Novozymes Rail Trail. | 0.5 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 68000
BL-0127 | Bike & Ped | Locally Selected | Main Street | Various | Upgrade crosswalks along Main Street, add a new mid-block crossing at the intersection of Water Street and Main Street, and an improved crossing configuration for the Franklinton to Novozymes Rail Trail. | 0.5 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 17000
BL-0127 | Bike & Ped | Locally Selected | Main Street | Various | Upgrade crosswalks along Main Street, add a new mid-block crossing at the intersection of Water Street and Main Street, and an improved crossing configuration for the Franklinton to Novozymes Rail Trail. | 0.5 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 600000
BL-0127 | Bike & Ped | Locally Selected | Main Street | Various | Upgrade crosswalks along Main Street, add a new mid-block crossing at the intersection of Water Street and Main Street, and an improved crossing configuration for the Franklinton to Novozymes Rail Trail. | 0.5 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 150000
BL-0128 | Bike & Ped | Locally Selected | Vandora Springs Road; Woodland Road | Vandora Springs Elementary School to Woodland Road; Vandora Springs Road to Pineview Drive in Garner. | Construct sidewalk. | 0.15 | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 187000
BL-0128 | Bike & Ped | Locally Selected | Vandora Springs Road; Woodland Road | Vandora Springs Elementary School to Woodland Road; Vandora Springs Road to Pineview Drive in Garner. | Construct sidewalk. | 0.15 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HF(M) | ENGINEERING | 47000
BL-0128 | Bike & Ped | Locally Selected | Vandora Springs Road; Woodland Road | Vandora Springs Elementary School to Woodland Road; Vandora Springs Road to Pineview Drive in Garner. | Construct sidewalk. | 0.15 | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 58000 | FY 2026: 58000
BL-0128 | Bike & Ped | Locally Selected | Vandora Springs Road; Woodland Road | Vandora Springs Elementary School to Woodland Road; Vandora Springs Road to Pineview Drive in Garner. | Construct sidewalk. | 0.15 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HF(M) | RIGHT-OF-WAY | 15000 | FY 2026: 15000
BL-0129 | Bike & Ped | Locally Selected | South Garner Greenway | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0129 | Bike & Ped | Locally Selected | South Garner Greenway | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BL-0129 | Bike & Ped | Locally Selected | South Garner Greenway | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Wake | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 6000
BL-0129 | Bike & Ped | Locally Selected | South Garner Greenway | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 2650000
BL-0129 | Bike & Ped | Locally Selected | South Garner Greenway | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 663000
BL-0129 | Bike & Ped | Locally Selected | South Garner Greenway | Vandora Springs Road and Buffaloe Road to Lake Benson Park in Garner. | Construct a multi-use path along the west/south side of Buffaloe Road. Includes a pedestrian bridge crossing and boardwalk segments. | 1.75 | Wake | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 1987000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (Cameron Road) | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 80000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (Cameron Road) | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 20000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (Cameron Road) | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (Cameron Road) | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (Cameron Road) | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 459000 | FY 2027: 459000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (Cameron Road) | Hope Mills Middle School to NC 59 (South Main Street) in Hope Mills. | Install new concrete sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 115000 | FY 2027: 115000
BL-0131 | Bike & Ped | Locally Selected | Fayetteville | Cape Fear River Trail | Construct 10 foot multi-use path. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 1096000
BL-0131 | Bike & Ped | Locally Selected | Fayetteville | Cape Fear River Trail | Construct 10 foot multi-use path. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 274000
BL-0132 | Bike & Ped | Locally Selected | Fayetteville | Cape Fear River Trailhead to Arnette Park. | Construct 10 foot multi-use path. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 1096000
BL-0132 | Bike & Ped | Locally Selected | Fayetteville | Cape Fear River Trailhead to Arnette Park. | Construct 10 foot multi-use path. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 274000
BL-0133 | Bike & Ped | Locally Selected | Cape Fear River Trail | Along Milan Road and Eufaula Road in Fayetteville. | Construct extension to Cape Fear River Trail. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 116000 | FY 2026: 116000
BL-0133 | Bike & Ped | Locally Selected | Cape Fear River Trail | Along Milan Road and Eufaula Road in Fayetteville. | Construct extension to Cape Fear River Trail. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 29000 | FY 2026: 29000
BL-0133 | Bike & Ped | Locally Selected | Cape Fear River Trail | Along Milan Road and Eufaula Road in Fayetteville. | Construct extension to Cape Fear River Trail. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1641000 | FY 2027: 1641000
BL-0133 | Bike & Ped | Locally Selected | Cape Fear River Trail | Along Milan Road and Eufaula Road in Fayetteville. | Construct extension to Cape Fear River Trail. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 410000 | FY 2027: 410000
BL-0134 | Bike & Ped | Locally Selected | East Shore Trail | Essex Place to intersection of Coley Drive and Murchison Road along Glenville Lake in Fayetteville; Matthews Street from Coley Drive to Murchison Road. | Construct 10 foot multi-use path; construct sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 62000 | FY 2027: 62000
BL-0134 | Bike & Ped | Locally Selected | East Shore Trail | Essex Place to intersection of Coley Drive and Murchison Road along Glenville Lake in Fayetteville; Matthews Street from Coley Drive to Murchison Road. | Construct 10 foot multi-use path; construct sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2027: 15000
BL-0134 | Bike & Ped | Locally Selected | East Shore Trail | Essex Place to intersection of Coley Drive and Murchison Road along Glenville Lake in Fayetteville; Matthews Street from Coley Drive to Murchison Road. | Construct 10 foot multi-use path; construct sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1618000 | FY 2028: 1618000
BL-0134 | Bike & Ped | Locally Selected | East Shore Trail | Essex Place to intersection of Coley Drive and Murchison Road along Glenville Lake in Fayetteville; Matthews Street from Coley Drive to Murchison Road. | Construct 10 foot multi-use path; construct sidewalk. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 405000 | FY 2028: 405000
BL-0135 | Bike & Ped | Locally Selected | Hoke Trail | Near James A. Leach Aquatic & Recreation Center in Hoke County. | Construct county-operated trail system. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | TADA | CONSTRUCTION | 343000 | FY 2026: 343000
BL-0135 | Bike & Ped | Locally Selected | Hoke Trail | Near James A. Leach Aquatic & Recreation Center in Hoke County. | Construct county-operated trail system. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 86000 | FY 2026: 86000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | BGDA | ENGINEERING | 40000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | ENGINEERING | 10000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | BGDA | RIGHT-OF-WAY | 32000 | FY 2026: 32000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 8000 | FY 2026: 8000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | BGDA | UTILITIES | 26000 | FY 2026: 26000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | UTILITIES | 6000 | FY 2026: 6000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | BGDA | CONSTRUCTION | 519000 | FY 2027: 519000
BL-0136 | Bike & Ped | Locally Selected | US 401 | Walmart to James A. Leach Aquatic & Recreation Center in Raeford. | Construct sidewalk. |  | Hoke | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 130000 | FY 2027: 130000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 240000 | FY 2026: 240000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 60000 | FY 2026: 60000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 280000 | FY 2027: 280000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 70000 | FY 2027: 70000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | UTILITIES | 32000 | FY 2027: 32000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | UTILITIES | 8000 | FY 2027: 8000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1608000 | FY 2028: 1608000
BL-0137 | Bike & Ped | Locally Selected | Various | Locations in Fayetteville. | Construct sidewalk, wheelchair ramps, retaining wall and bus pad upgrades. | 5.35 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 402000 | FY 2028: 402000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 160000 | FY 2026: 160000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 40000 | FY 2026: 40000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2027: 160000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2027: 40000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | UTILITIES | 16000 | FY 2027: 16000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | UTILITIES | 4000 | FY 2027: 4000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1624000 | FY 2028: 1624000
BL-0138 | Bike & Ped | Locally Selected | NC 162 (Bunce Road / Bingham Drive); SR 1400 (Cliffdale Road) | Raeford Road to Reilly Road; Lakeridge Drive to Raeford Road in West Fayetteville. | Construct sidewalk, wheelchair ramps and bus pad upgrades. | 4.9 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 406000 | FY 2028: 406000
BL-0139 | Bike & Ped | Locally Selected | SR 1006 (Orange Grove Road) | Hillsborough | Construct transit access sidewalk. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | ENGINEERING | 360000 | FY 2026: 200000
BL-0139 | Bike & Ped | Locally Selected | SR 1006 (Orange Grove Road) | Hillsborough | Construct transit access sidewalk. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 90000 | FY 2026: 50000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | ENGINEERING | 80000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | ENGINEERING | 20000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2026: 160000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 1000000 | FY 2027: 1000000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | Benefield's Landing Burke Road to Eastside Burke Avenue in Nebo | Construct sidewalk. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 250000 | FY 2027: 250000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (Lewisville-Clemmons Road) | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 10000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (Lewisville-Clemmons Road) | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 3000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (Lewisville-Clemmons Road) | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 35000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (Lewisville-Clemmons Road) | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 9000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (Lewisville-Clemmons Road) | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 210000 | FY 2026: 210000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (Lewisville-Clemmons Road) | August Drive to Brandon Farm Road at West Forsyth High School near Clemmons. | Construct and improve sidewalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 53000 | FY 2026: 53000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 10000 | FY 2026: 10000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 3000 | FY 2026: 3000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 3000 | FY 2026: 3000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | UTILITIES | 10000 | FY 2026: 10000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 3000 | FY 2026: 3000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 454000 | FY 2027: 454000
BL-0143 | Bike & Ped | Locally Selected | Friendly Road; Ruxton Drive | Main Street to York Place Drive NE; Walkertown Elementary School at Friendly Road in Walkertown. | Construct sidewalk on Ruxton Drive; Improve crosswalk. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 114000 | FY 2027: 114000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 198000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 50000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 132000 | FY 2026: 132000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 13000 | FY 2026: 13000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 10000 | FY 2026: 10000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 3000 | FY 2026: 3000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 518000 | FY 2026: 518000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 to Yadkin Valley Road at Atrium Wake Forest Baptist Hospital (Davie) in Bermuda Run. | Construct sidewalk. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 129000 | FY 2026: 129000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 189000 | FY 2026: 189000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 47000 | FY 2026: 47000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 159000 | FY 2027: 159000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 38000 | FY 2027: 38000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 10000 | FY 2027: 10000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 3000 | FY 2027: 3000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1155000 | FY 2028: 1155000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (Marty Lane) | SR 1103 (Lewisville-Clemmons Road) to King Richard Drive near Clemmons. | Construct sidewalk. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 289000 | FY 2028: 289000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 220000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 55000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 88000 | FY 2026: 88000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 22000 | FY 2026: 22000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | UTILITIES | 10000 | FY 2026: 10000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 3000 | FY 2026: 3000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 518000 | FY 2026: 518000
BL-0146 | Bike & Ped | Locally Selected | Blue Heron Trail | Royal Troon Drive to NC 801 in Bermuda Run | Construct Blue Heron Trail Phase III. |  | Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 129000 | FY 2026: 129000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | ENGINEERING | 8000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 78000 | FY 2026: 78000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | UTILITIES | 10000 | FY 2026: 10000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | UTILITIES | 3000 | FY 2026: 3000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | CONSTRUCTION | 248000 | FY 2027: 248000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (Main Street) | Kirby Road to King City Hall in King. | Construct ADA-compliant sidewalk. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 62000 | FY 2027: 62000
BL-0148 | Bike & Ped | Locally Selected | Ingram Drive | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | ENGINEERING | 30000
BL-0148 | Bike & Ped | Locally Selected | Ingram Drive | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 8000
BL-0148 | Bike & Ped | Locally Selected | Ingram Drive | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | UTILITIES | 10000 | FY 2027: 10000
BL-0148 | Bike & Ped | Locally Selected | Ingram Drive | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | UTILITIES | 3000 | FY 2027: 3000
BL-0148 | Bike & Ped | Locally Selected | Ingram Drive | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | CONSTRUCTION | 160000 | FY 2027: 160000
BL-0148 | Bike & Ped | Locally Selected | Ingram Drive | Campbell Drive to East of 5 Forks Street in King. | Construct ADA-compliant sidewalk connecting to existing sidewalks. |  | Stokes | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 40000 | FY 2027: 40000
BL-0149 | Bike & Ped | Locally Selected | Shelton Street; East Poplar Avenue; Maple Avenue | Hillsborough Road to North Greensboro Street; West Main Street to North Greensbor Street; East Braxton Foushee Street to end of Maple Avenue | Install pavement markings on Shelton Street, construct pedestrian lane on East Poplar Avenue, and construct contraflow lane on Maple Avenue. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 890000 | FY 2026: 890000
BL-0149 | Bike & Ped | Locally Selected | Shelton Street; East Poplar Avenue; Maple Avenue | Hillsborough Road to North Greensboro Street; West Main Street to North Greensbor Street; East Braxton Foushee Street to end of Maple Avenue | Install pavement markings on Shelton Street, construct pedestrian lane on East Poplar Avenue, and construct contraflow lane on Maple Avenue. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 222000 | FY 2026: 222000
BL-0150 | Bike & Ped | Locally Selected | Various | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | ENGINEERING | 287000 | FY 2026: 287000
BL-0150 | Bike & Ped | Locally Selected | Various | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 72000 | FY 2026: 72000
BL-0150 | Bike & Ped | Locally Selected | Various | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | RIGHT-OF-WAY | 141000 | FY 2027: 141000
BL-0150 | Bike & Ped | Locally Selected | Various | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 35000 | FY 2027: 35000
BL-0150 | Bike & Ped | Locally Selected | Various | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | CONSTRUCTION | 2348000 | FY 2027: 2348000
BL-0150 | Bike & Ped | Locally Selected | Various | Routes in Chapel Hill. | Construct sidewalks to fill in gaps. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 587000 | FY 2027: 587000
BL-0151 | Bike & Ped | Locally Selected | Bolin Creek Greenway Phase Two | Lake Hogan Greenway to Jones Creek/Twin Creeks greenways. | Construct greenway. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | ENGINEERING | 320000 | FY 2027: 320000
BL-0151 | Bike & Ped | Locally Selected | Bolin Creek Greenway Phase Two | Lake Hogan Greenway to Jones Creek/Twin Creeks greenways. | Construct greenway. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 80000 | FY 2027: 80000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (Davis Drive) | I-40 to SR 1121 (Cornwallis Road) | Reconstruct multi-use path. | 0.63 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TADA | ENGINEERING | 8000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (Davis Drive) | I-40 to SR 1121 (Cornwallis Road) | Reconstruct multi-use path. | 0.63 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | ENGINEERING | 2000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (Davis Drive) | I-40 to SR 1121 (Cornwallis Road) | Reconstruct multi-use path. | 0.63 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TADA | CONSTRUCTION | 969000 | FY 2026: 969000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (Davis Drive) | I-40 to SR 1121 (Cornwallis Road) | Reconstruct multi-use path. | 0.63 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CONSTRUCTION | 242000 | FY 2026: 242000
BL-0153 | Bike & Ped | Locally Selected | Gullah Geechee Heritage Trail Gap | Along NC 133 south of Belville. | Construct multi-use path. | 0.22 | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 130000
BL-0153 | Bike & Ped | Locally Selected | Gullah Geechee Heritage Trail Gap | Along NC 133 south of Belville. | Construct multi-use path. | 0.22 | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 32000
BL-0153 | Bike & Ped | Locally Selected | Gullah Geechee Heritage Trail Gap | Along NC 133 south of Belville. | Construct multi-use path. | 0.22 | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 590000 | FY 2027: 590000
BL-0153 | Bike & Ped | Locally Selected | Gullah Geechee Heritage Trail Gap | Along NC 133 south of Belville. | Construct multi-use path. | 0.22 | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 148000 | FY 2027: 148000
BL-0154 | Bike & Ped | Locally Selected | Country Club multi-use path | Adjacent to SR 1565 (Country Club Drive) and SR 1593 (Jenkins Road) from SR 1563 (Sloop Point Loop Road) to SR 1592 (North St. Johns Church Road). | Construct multi-use path. | 3.91 | Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 709000 | FY 2026: 709000
BL-0154 | Bike & Ped | Locally Selected | Country Club multi-use path | Adjacent to SR 1565 (Country Club Drive) and SR 1593 (Jenkins Road) from SR 1563 (Sloop Point Loop Road) to SR 1592 (North St. Johns Church Road). | Construct multi-use path. | 3.91 | Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 177000 | FY 2026: 177000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | BGANY | ENGINEERING | 65000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | L(M) | ENGINEERING | 16000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | BGANY | RIGHT-OF-WAY | 16000 | FY 2026: 16000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2026: 4000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | BGANY | UTILITIES | 2000 | FY 2026: 2000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | L(M) | UTILITIES | 1000 | FY 2026: 1000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | BGANY | CONSTRUCTION | 181000 | FY 2026: 181000
BL-0155 | Bike & Ped | Locally Selected | Greenville Community Center Pathway | 4th Street to 3rd Street; Along south side of 3rd Street to Memorial Drive | Construct multi-use path, sidewalk, and install roadway lighting. |  | Pitt | 2 | Greenville Urban Area MPO | LOCAL MATCH PROVIDED BY CITY OF GREENVILLE | Exempt |  | L(M) | CONSTRUCTION | 45000 | FY 2026: 45000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | BGANY | ENGINEERING | 54000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 14000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | BGANY | RIGHT-OF-WAY | 56000 | FY 2026: 56000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 14000 | FY 2026: 14000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | BGANY | UTILITIES | 32000 | FY 2026: 32000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | L(M) | UTILITIES | 8000 | FY 2026: 8000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | BGANY | CONSTRUCTION | 108000 | FY 2026: 108000
BL-0156 | Bike & Ped | Locally Selected | Arlington Boulevard | Hooker Road to Evans Park in Greenville. | Construct sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 27000 | FY 2026: 27000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 112000 | FY 2026: 112000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 61000 | FY 2026: 61000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 268000 | FY 2028: 268000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 144000 | FY 2028: 144000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | UTILITIES | 6000 | FY 2028: 6000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | UTILITIES | 4000 | FY 2028: 4000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 418000 | FY 2030: 418000
BL-0157 | Bike & Ped | Locally Selected | NC 75 | Potter Road Intersection in Mineral Springs. | Construct sidewalk and pedestrian improvements. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 224000 | FY 2030: 224000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 60000 | FY 2026: 60000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 32000 | FY 2026: 32000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 99000 | FY 2028: 99000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 53000 | FY 2028: 53000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | UTILITIES | 6000 | FY 2028: 6000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | UTILITIES | 4000 | FY 2028: 4000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 210000 | FY 2030: 210000
BL-0158 | Bike & Ped | Locally Selected | SR 3178 (Moore Road) | Chambers Drive to Royal Commons Lane in Matthews. | Construct sidewalk. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 113000 | FY 2030: 113000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 232000 | FY 2026: 232000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 348000 | FY 2026: 348000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 442000 | FY 2027: 442000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 663000 | FY 2027: 663000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | UTILITIES | 4000 | FY 2027: 4000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | UTILITIES | 6000 | FY 2027: 6000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 597000 | FY 2029: 597000
BL-0159 | Bike & Ped | Locally Selected | SR 1306 (Rinehardt Road) | Selma Burke Middle School (SMBS) to East Plaza Drive in Mooresville. | Construct sidewalk. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 896000 | FY 2029: 896000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 232000 | FY 2026: 232000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 58000 | FY 2026: 58000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 533000 | FY 2027: 533000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 133000 | FY 2027: 133000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | UTILITIES | 8000 | FY 2027: 8000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | UTILITIES | 2000 | FY 2027: 2000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 479000 | FY 2029: 479000
BL-0160 | Bike & Ped | Locally Selected | NC 152 (North Main Street) | Glastonbury Drive to East Mooresville Intermediate School (EIMS) in Mooresville. | Construct sidewalk and crossing. | 0.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 120000 | FY 2029: 120000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 273000 | FY 2027: 273000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 167000 | FY 2027: 167000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 293000 | FY 2028: 293000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 180000 | FY 2028: 180000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | UTILITIES | 6000 | FY 2028: 6000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | UTILITIES | 4000 | FY 2028: 4000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 1166000 | FY 2030: 1166000
BL-0161 | Bike & Ped | Locally Selected | Davidson-Concord Road | South Prong Rocky River Greenway to Davidson Place Drive in Davidson. | Construct side path. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 714000 | FY 2030: 714000
BL-0162 | Bike & Ped | Locally Selected | Winston-Salem | Various routes | Purchase and install streetlights |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 800000 | FY 2026: 800000
BL-0162 | Bike & Ped | Locally Selected | Winston-Salem | Various routes | Purchase and install streetlights |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 200000 | FY 2026: 200000
BL-0163 | Bike & Ped | Locally Selected | SR 1009 (North Main Street) | Columbus Avenue to the Guilford County line | Construct sidewalk and curb ramps. | 1.1 | Randolph | 8 | High Point Urban Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 745000 | FY 2026: 745000
BL-0163 | Bike & Ped | Locally Selected | SR 1009 (North Main Street) | Columbus Avenue to the Guilford County line | Construct sidewalk and curb ramps. | 1.1 | Randolph | 8 | High Point Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 149000 | FY 2026: 149000
BL-0163 | Bike & Ped | Locally Selected | SR 1009 (North Main Street) | Columbus Avenue to the Guilford County line | Construct sidewalk and curb ramps. | 1.1 | Randolph | 8 | High Point Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 8000 | FY 2026: 8000
BL-0163 | Bike & Ped | Locally Selected | SR 1009 (North Main Street) | Columbus Avenue to the Guilford County line | Construct sidewalk and curb ramps. | 1.1 | Randolph | 8 | High Point Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 2000 | FY 2026: 2000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | ENGINEERING | 120000 | FY 2026: 120000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | L | ENGINEERING | 30000 | FY 2026: 30000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 40000 | FY 2028: 40000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 10000 | FY 2028: 10000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | UTILITIES | 20000 | FY 2028: 20000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | L | UTILITIES | 5000 | FY 2028: 5000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | CONSTRUCTION | 485000 | FY 2029: 485000
BL-0164 | Bike & Ped | Locally Selected | Conover Boulevard East | Conover City Park to 1st Street Southeast | Construct corridor improvements including sidewalks, pedestrian signalization and turn lane improvements | 0.1 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | L | CONSTRUCTION | 122000 | FY 2029: 122000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | TADA | ENGINEERING | 280000 | FY 2026: 280000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | L(M) | ENGINEERING | 70000 | FY 2026: 70000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | CMAQ | RIGHT-OF-WAY | 320000 | FY 2027: 320000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | L(M) | RIGHT-OF-WAY | 80000 | FY 2027: 80000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | CMAQ | UTILITIES | 280000 | FY 2027: 280000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | L(M) | UTILITIES | 70000 | FY 2027: 70000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | CMAQ | CONSTRUCTION | 1920000 | FY 2028: 1920000
BL-0165 | Bike & Ped | Locally Selected | 10th Avenue Southeast; 3rd Street Southeast; 8th Avenue Southeast; 5th Street Southeast; 3rd Avenue Drive Southeast | Various locations in Hickory | Construct sidewalk | 0.1 | Catawba | 12 | Greater Hickory MPO | 280K OF STBG-DA SWITCHED WITH 280K OF TADA AREA AS PART OF FUND SWAP 5-25. | Division 12 |  | L(M) | CONSTRUCTION | 480000 | FY 2028: 480000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | TADA | ENGINEERING | 140000 | FY 2026: 140000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | L(M) | ENGINEERING | 35000 | FY 2026: 35000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | TADA | RIGHT-OF-WAY | 60000 | FY 2028: 60000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2028: 15000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | TADA | UTILITIES | 20000 | FY 2028: 20000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | L(M) | UTILITIES | 5000 | FY 2028: 5000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | TADA | CONSTRUCTION | 540000 | FY 2029: 540000
BL-0166 | Bike & Ped | Locally Selected | Massell Avenue | Rodoret Street to Carolina Street SE | Construct sidewalk. | 0.1 | Burke | 13 | Greater Hickory MPO | 760K OF STBG-DA SWITCHED WITH 760K OF TAANY AREA AS PART OF FUND SWAP 5-25. | Division 13 |  | L(M) | CONSTRUCTION | 135000 | FY 2029: 135000
BL-0167 | Bike & Ped | Locally Selected | SR 1309 (Glenburnie Road) | College Court to Greenbriar Parkway in New Bern | Construct sidewalk. |  | Craven | 2 | New Bern Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 4000 | FY 2026: 4000
BL-0167 | Bike & Ped | Locally Selected | SR 1309 (Glenburnie Road) | College Court to Greenbriar Parkway in New Bern | Construct sidewalk. |  | Craven | 2 | New Bern Area MPO |  | Exempt |  | L(M) | ENGINEERING | 1000 | FY 2026: 1000
BL-0167 | Bike & Ped | Locally Selected | SR 1309 (Glenburnie Road) | College Court to Greenbriar Parkway in New Bern | Construct sidewalk. |  | Craven | 2 | New Bern Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 78000 | FY 2026: 78000
BL-0167 | Bike & Ped | Locally Selected | SR 1309 (Glenburnie Road) | College Court to Greenbriar Parkway in New Bern | Construct sidewalk. |  | Craven | 2 | New Bern Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 19000 | FY 2026: 19000
BL-0168 | Bike & Ped | Locally Selected | Durham to Roxboro Rail Trail | NC 55 (Avondale Drive) in Durham to Patterson Drive / Somerset Church Road in Roxboro | Construct greenway. |  | Durham, Person | 5 | Triangle West TPO, Kerr-Tar RPO |  | Division 5 |  | CMAQ | RIGHT-OF-WAY | 3250000 | FY 2026: 3250000
BL-0168 | Bike & Ped | Locally Selected | Durham to Roxboro Rail Trail | NC 55 (Avondale Drive) in Durham to Patterson Drive / Somerset Church Road in Roxboro | Construct greenway. |  | Durham, Person | 5 | Triangle West TPO, Kerr-Tar RPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 7500000 | FY 2026: 7500000
BL-0168 | Bike & Ped | Locally Selected | Durham to Roxboro Rail Trail | NC 55 (Avondale Drive) in Durham to Patterson Drive / Somerset Church Road in Roxboro | Construct greenway. |  | Durham, Person | 5 | Triangle West TPO, Kerr-Tar RPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 1688000 | FY 2026: 1688000
BL-0168 | Bike & Ped | Locally Selected | Durham to Roxboro Rail Trail | NC 55 (Avondale Drive) in Durham to Patterson Drive / Somerset Church Road in Roxboro | Construct greenway. |  | Durham, Person | 5 | Triangle West TPO, Kerr-Tar RPO |  | Division 5 |  | L | RIGHT-OF-WAY | 802000 | FY 2026: 802000
BL-0168 | Bike & Ped | Locally Selected | Durham to Roxboro Rail Trail | NC 55 (Avondale Drive) in Durham to Patterson Drive / Somerset Church Road in Roxboro | Construct greenway. |  | Durham, Person | 5 | Triangle West TPO, Kerr-Tar RPO |  | Division 5 |  | S(M) | RIGHT-OF-WAY | 1000000 | FY 2026: 1000000
BL-0169 | Bike & Ped | Locally Selected | A&Y Greenway | Old Lake Brandt to Bur-Mil Park | Repair greenway surface. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 42000 | FY 2026: 42000
BL-0169 | Bike & Ped | Locally Selected | A&Y Greenway | Old Lake Brandt to Bur-Mil Park | Repair greenway surface. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 11000 | FY 2026: 11000
BL-0169 | Bike & Ped | Locally Selected | A&Y Greenway | Old Lake Brandt to Bur-Mil Park | Repair greenway surface. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 2872000 | FY 2027: 2872000
BL-0169 | Bike & Ped | Locally Selected | A&Y Greenway | Old Lake Brandt to Bur-Mil Park | Repair greenway surface. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 718000 | FY 2027: 718000
BL-0172 | Bike & Ped | Locally Selected | Jenks Carpenter Road; Green level Church Road | High House Road to Deshire Mist Lane; Green Hope School Road to Brooks Park Lane. | Construct 10 foot wide street-side trails. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 2000000 | FY 2026: 2000000
BL-0172 | Bike & Ped | Locally Selected | Jenks Carpenter Road; Green level Church Road | High House Road to Deshire Mist Lane; Green Hope School Road to Brooks Park Lane. | Construct 10 foot wide street-side trails. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 500000 | FY 2026: 500000
BL-0173 | Bike & Ped | Locally Selected | Various | South side of Center Street from North Mason Street to Tunstall Avenue, one side of Tunstall Avenue from Center Street to East Williams Street, North side of East Williams Street from Tunstall Avenue to James Street, and North Side of J | Construct sidewalk. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 429000 | FY 2026: 429000
BL-0173 | Bike & Ped | Locally Selected | Various | South side of Center Street from North Mason Street to Tunstall Avenue, one side of Tunstall Avenue from Center Street to East Williams Street, North side of East Williams Street from Tunstall Avenue to James Street, and North Side of J | Construct sidewalk. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 107000 | FY 2026: 107000
BL-0174 | Bike & Ped | Locally Selected | Bridge Street | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 542000 | FY 2026: 542000
BL-0174 | Bike & Ped | Locally Selected | Bridge Street | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 135000 | FY 2026: 135000
BL-0174 | Bike & Ped | Locally Selected | Bridge Street | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | UTILITIES | 56000 | FY 2026: 56000
BL-0174 | Bike & Ped | Locally Selected | Bridge Street | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | UTILITIES | 14000 | FY 2026: 14000
BL-0174 | Bike & Ped | Locally Selected | Bridge Street | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 2249000 | FY 2026: 2249000
BL-0174 | Bike & Ped | Locally Selected | Bridge Street | McLean Street to North Judd Parkway Northwest. | Install sidewalks, ADA-compliant ramps, improve existing drainage system, and add pavement markings. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 562000 | FY 2026: 562000
BL-0176 | Bike & Ped | Locally Selected | Aberdeen | Poplar Street from Peach Avenue to Providence Place/Johnson Street | Construct sidewalk. |  | Moore | 8 | Sandhills MPO |  | Exempt |  | CRPDA | ENGINEERING | 94000 | FY 2026: 94000
BL-0176 | Bike & Ped | Locally Selected | Aberdeen | Poplar Street from Peach Avenue to Providence Place/Johnson Street | Construct sidewalk. |  | Moore | 8 | Sandhills MPO |  | Exempt |  | L(M) | ENGINEERING | 24000 | FY 2026: 24000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | BGDA | ENGINEERING | 56000 | FY 2026: 56000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 14000 | FY 2026: 14000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 28000 | FY 2027: 28000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 7000 | FY 2027: 7000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | BGDA | UTILITIES | 50000 | FY 2027: 50000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | UTILITIES | 13000 | FY 2027: 13000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | BGDA | CONSTRUCTION | 348000 | FY 2027: 348000
BL-0177 | Bike & Ped | Locally Selected | 8th Street Greenway HAWK | Kannapolis | Install pedestrian signal. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 87000 | FY 2027: 87000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDA | ENGINEERING | 396000 | FY 2026: 396000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | ENGINEERING | 99000 | FY 2026: 99000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 240000 | FY 2027: 240000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 60000 | FY 2027: 60000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDA | UTILITIES | 60000 | FY 2027: 60000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | UTILITIES | 15000 | FY 2027: 15000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDA | CONSTRUCTION | 3963000 | FY 2029: 3963000
BL-0178 | Bike & Ped | Locally Selected | SR 2198 (Midlake Avenue) in Kannapolis | SR 2114 (Centergrove Rd) to Brantley Rd | Construct sidewalk | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 991000 | FY 2029: 991000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | ENGINEERING | 28000 | FY 2026: 28000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | L(M) | ENGINEERING | 7000 | FY 2026: 7000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | RIGHT-OF-WAY | 36000 | FY 2026: 36000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | L(M) | RIGHT-OF-WAY | 9000 | FY 2026: 9000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | UTILITIES | 20000 | FY 2026: 20000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | L(M) | UTILITIES | 5000 | FY 2026: 5000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | CONSTRUCTION | 53000 | FY 2027: 53000
BL-0179 | Bike & Ped | Locally Selected | SR 1149 (Mill Street) | SR 1133 (Main Street) to existing sidewalk north of Depot Street in Winterville | Construct sidewalk on western side of SR 1149 (Mill Street) | 0.1 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | L(M) | CONSTRUCTION | 13000 | FY 2027: 13000
BL-0180 | Bike & Ped | Locally Selected | Kerr Avenue Trail | Begins at Kerr Avenue and Patrick Avenue intersection heading south to Fountain drive then east to South College Road and north to Hoggard Drive in Wilmington. | Construct mult-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 2682000 | FY 2027: 2682000
BL-0180 | Bike & Ped | Locally Selected | Kerr Avenue Trail | Begins at Kerr Avenue and Patrick Avenue intersection heading south to Fountain drive then east to South College Road and north to Hoggard Drive in Wilmington. | Construct mult-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 670000 | FY 2027: 670000
BL-0181 | Bike & Ped | Locally Selected | NC 132 (South College Road) | 17th Street to SR 1521 (Piner Road / Carolina Beach Road) | Construct multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 2629000 | FY 2026: 2629000
BL-0181 | Bike & Ped | Locally Selected | NC 132 (South College Road) | 17th Street to SR 1521 (Piner Road / Carolina Beach Road) | Construct multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 699000 | FY 2026: 699000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CMAQ | ENGINEERING | 180000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | L(M) | ENGINEERING | 45000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CRP550 | RIGHT-OF-WAY | 80000 | FY 2026: 80000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CMAQ | CONSTRUCTION | 709000 | FY 2026: 321000; FY 2027: 388000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CRP550 | CONSTRUCTION | 1166000 | FY 2026: 397000; FY 2027: 769000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 70 Business (West Market Street) | SR 1913 (Wilson's Mills Road) to Neuse River Bridge in Smithfield | Construct eight foot multi-use path. | 1 | Johnston | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | L(M) | CONSTRUCTION | 469000 | FY 2026: 469000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | CRP550 | ENGINEERING | 400000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | O | ENGINEERING | 100000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | CRP550 | CONSTRUCTION | 1520000 | FY 2026: 1520000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | TAP | CONSTRUCTION | 104000 | FY 2026: 104000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | O | CONSTRUCTION | 200000 | FY 2026: 200000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | L(M) | CONSTRUCTION | 26000 | FY 2026: 26000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad near Cullowhee. | Construct pedestrian bridge. |  | Jackson | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. "L" FUNDS REPRESENT FUNDS FROM DILLSBORO. | Exempt |  | L | CONSTRUCTION | 180000 | FY 2026: 180000
BN-0003A | Bike & Ped | NCDOT Selected (Other Selection Process) | Monteith Greenway | Great Smoky Mountain Railroad | Construct pedestrian bridge over Great Smoky Mountain Railroad. |  | Jackson | 14 | Southwestern RPO |  | Exempt
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | Dobson School Greenway | Central Middle School to the Elementary School in Dobson. | Construct greenway. |  | Surry | 11 | Northwest Piedmont RPO |  | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 40000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | Dobson School Greenway | Central Middle School to the Elementary School in Dobson. | Construct greenway. |  | Surry | 11 | Northwest Piedmont RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 10000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | Dobson School Greenway | Central Middle School to the Elementary School in Dobson. | Construct greenway. |  | Surry | 11 | Northwest Piedmont RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 1188000 | FY 2026: 1188000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | Dobson School Greenway | Central Middle School to the Elementary School in Dobson. | Construct greenway. |  | Surry | 11 | Northwest Piedmont RPO |  | Exempt |  | L(M) | CONSTRUCTION | 297000 | FY 2026: 297000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 Business (Main Street) | NC 58 to SR 1366 (East Street) in Pollocksville | Construct pedestrian improvements. | 0.83 | Jones | 2 | Down East RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 60000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 Business (Main Street) | NC 58 to SR 1366 (East Street) in Pollocksville | Construct pedestrian improvements. | 0.83 | Jones | 2 | Down East RPO |  | Exempt |  | L(M) | ENGINEERING | 15000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 Business (Main Street) | NC 58 to SR 1366 (East Street) in Pollocksville | Construct pedestrian improvements. | 0.83 | Jones | 2 | Down East RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 364000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 Business (Main Street) | NC 58 to SR 1366 (East Street) in Pollocksville | Construct pedestrian improvements. | 0.83 | Jones | 2 | Down East RPO |  | Exempt |  | L(M) | CONSTRUCTION | 91000
BN-0006 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 701 Business (East 5th Street) | West of Lynwood Norris Road to US 701 Bypass in Tabor City. | Construct sidewalk and signalized pedestrian crossing. | 0.2 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. HF(M) FUNDING REPRESENT LEGISLATIVE CONTINGENCY FUNDS. | Exempt |  | CRPLT5 | CONSTRUCTION | 200000
BN-0006 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 701 Business (East 5th Street) | West of Lynwood Norris Road to US 701 Bypass in Tabor City. | Construct sidewalk and signalized pedestrian crossing. | 0.2 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. HF(M) FUNDING REPRESENT LEGISLATIVE CONTINGENCY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 50000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (East Wilmington Street) | US 117 Business to US 117 Bypass Corridor in Burgaw | Construct eight foot multi-use path. | 0.67 | Pender | 3 | Cape Fear RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 40000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (East Wilmington Street) | US 117 Business to US 117 Bypass Corridor in Burgaw | Construct eight foot multi-use path. | 0.67 | Pender | 3 | Cape Fear RPO |  | Exempt |  | L(M) | ENGINEERING | 10000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (East Wilmington Street) | US 117 Business to US 117 Bypass Corridor in Burgaw | Construct eight foot multi-use path. | 0.67 | Pender | 3 | Cape Fear RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 693000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (East Wilmington Street) | US 117 Business to US 117 Bypass Corridor in Burgaw | Construct eight foot multi-use path. | 0.67 | Pender | 3 | Cape Fear RPO |  | Exempt |  | L(M) | CONSTRUCTION | 174000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | Kinston Riverwalk | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Lenoir | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | CRP550 | ENGINEERING | 244000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | Kinston Riverwalk | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Lenoir | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | L(M) | ENGINEERING | 61000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | Kinston Riverwalk | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Lenoir | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | CRP550 | RIGHT-OF-WAY | 171000 | FY 2026: 171000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | Kinston Riverwalk | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Lenoir | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | L(M) | RIGHT-OF-WAY | 43000 | FY 2026: 43000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | Kinston Riverwalk | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Lenoir | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | CRP550 | CONSTRUCTION | 2432000 | FY 2026: 2432000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | Kinston Riverwalk | Caswell Memorial Park to Atlantic Avenue along Neuse River in Kinston | Construct 10 foot multi-use path. | 1.58 | Lenoir | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | L(M) | CONSTRUCTION | 608000 | FY 2026: 608000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421 / US 321 (West King Street) | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Watauga | 11 | High Country RPO |  | Exempt |  | CRP550 | ENGINEERING | 120000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421 / US 321 (West King Street) | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Watauga | 11 | High Country RPO |  | Exempt |  | L(M) | ENGINEERING | 30000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421 / US 321 (West King Street) | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Watauga | 11 | High Country RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421 / US 321 (West King Street) | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Watauga | 11 | High Country RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421 / US 321 (West King Street) | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Watauga | 11 | High Country RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 525000 | FY 2027: 525000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421 / US 321 (West King Street) | SR 1180 (Poplar Grove Connector Road) to Westwood Apartments in Boone | Construct sidewalk and other corridor improvements. | 0.42 | Watauga | 11 | High Country RPO |  | Exempt |  | L(M) | CONSTRUCTION | 131000 | FY 2027: 131000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | Estatoe Trail | SR 1344 (Cashiers Valley Road) to Silversteen Drive in Brevard. | Construct multi-use path. | 0.69 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | CRP550 | ENGINEERING | 130000 | FY 2026: 50000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | Estatoe Trail | SR 1344 (Cashiers Valley Road) to Silversteen Drive in Brevard. | Construct multi-use path. | 0.69 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | L(M) | ENGINEERING | 20000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | Estatoe Trail | SR 1344 (Cashiers Valley Road) to Silversteen Drive in Brevard. | Construct multi-use path. | 0.69 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | CRP550 | UTILITIES | 200000 | FY 2026: 200000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | Estatoe Trail | SR 1344 (Cashiers Valley Road) to Silversteen Drive in Brevard. | Construct multi-use path. | 0.69 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1988000 | FY 2026: 1988000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | Estatoe Trail | SR 1344 (Cashiers Valley Road) to Silversteen Drive in Brevard. | Construct multi-use path. | 0.69 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | L(M) | CONSTRUCTION | 112000 | FY 2026: 112000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | Pittsboro Lake Park | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | ENGINEERING | 117000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | Pittsboro Lake Park | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 29000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | Pittsboro Lake Park | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 25000 | FY 2026: 25000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | Pittsboro Lake Park | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 6000 | FY 2026: 6000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | Pittsboro Lake Park | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 364000 | FY 2026: 364000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | Pittsboro Lake Park | Town Lake Park in Pittsboro. | Install sidewalk along NC 87. | 0.33 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 91000 | FY 2026: 91000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (Forest Hills Road / North Country Club Road) to the Jackson County Recreation Complex near the intersection of SR 1545 (Wisdom Drive) and Cullowhee Mountain Road near Cullowhee. | Construct multi-use path on west side. | 0.3 | Jackson | 14 | Southwestern RPO |  | Exempt |  | CRP550 | ENGINEERING | 352000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (Forest Hills Road / North Country Club Road) to the Jackson County Recreation Complex near the intersection of SR 1545 (Wisdom Drive) and Cullowhee Mountain Road near Cullowhee. | Construct multi-use path on west side. | 0.3 | Jackson | 14 | Southwestern RPO |  | Exempt |  | L(M) | ENGINEERING | 88000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (Forest Hills Road / North Country Club Road) to the Jackson County Recreation Complex near the intersection of SR 1545 (Wisdom Drive) and Cullowhee Mountain Road near Cullowhee. | Construct multi-use path on west side. | 0.3 | Jackson | 14 | Southwestern RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1318000 | FY 2026: 1318000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (Forest Hills Road / North Country Club Road) to the Jackson County Recreation Complex near the intersection of SR 1545 (Wisdom Drive) and Cullowhee Mountain Road near Cullowhee. | Construct multi-use path on west side. | 0.3 | Jackson | 14 | Southwestern RPO |  | Exempt |  | L(M) | CONSTRUCTION | 329000 | FY 2026: 329000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (Ledger School Road) | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | ENGINEERING | 252000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (Ledger School Road) | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | ENGINEERING | 63000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (Ledger School Road) | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 8000 | FY 2026: 8000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (Ledger School Road) | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (Ledger School Road) | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | CONSTRUCTION | 1472000 | FY 2028: 1472000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (Ledger School Road) | NC 226 to Mitchell High School near Bakersville. | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 368000 | FY 2028: 368000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | ENGINEERING | 233000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | ENGINEERING | 58000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 88000 | FY 2026: 88000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 22000 | FY 2026: 22000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | UTILITIES | 64000 | FY 2026: 64000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | UTILITIES | 16000 | FY 2026: 16000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | CONSTRUCTION | 880000 | FY 2028: 880000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 (South Mitchell Avenue) | North of SR 1278 (Bakers Lane) to Willis Cove Road | Construct sidewalk. |  | Mitchell | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 220000 | FY 2028: 220000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | Bogue Shores Suites to Coral Bay Club in Atlantic Beach. | Construct sidewalk on north side of NC 58. | 2 | Carteret | 2 | Down East RPO |  | Exempt |  | CRP550 | ENGINEERING | 4000 | FY 2026: 4000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | Bogue Shores Suites to Coral Bay Club in Atlantic Beach. | Construct sidewalk on north side of NC 58. | 2 | Carteret | 2 | Down East RPO |  | Exempt |  | L(M) | ENGINEERING | 1000 | FY 2026: 1000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | Bogue Shores Suites to Coral Bay Club in Atlantic Beach. | Construct sidewalk on north side of NC 58. | 2 | Carteret | 2 | Down East RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 120000 | FY 2026: 120000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | Bogue Shores Suites to Coral Bay Club in Atlantic Beach. | Construct sidewalk on north side of NC 58. | 2 | Carteret | 2 | Down East RPO |  | Exempt |  | L(M) | CONSTRUCTION | 30000 | FY 2026: 30000
BN-0023 | Bike & Ped | Locally Selected | Various | Various locations in St. James. | Replace street lights with LED lights. |  | Brunswick | 3 | Cape Fear RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 320000
BN-0023 | Bike & Ped | Locally Selected | Various | Various locations in St. James. | Replace street lights with LED lights. |  | Brunswick | 3 | Cape Fear RPO |  | Exempt |  | L(M) | CONSTRUCTION | 80000
BN-0024 | Bike & Ped | Locally Selected | Neuse River | From proposed residential development to future school complex near SR 2589 (Clearwater Drive) in Wilson's Mills | Construct multi-use path along Neuse River. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | ENGINEERING | 160000
BN-0024 | Bike & Ped | Locally Selected | Neuse River | From proposed residential development to future school complex near SR 2589 (Clearwater Drive) in Wilson's Mills | Construct multi-use path along Neuse River. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 40000
BN-0024 | Bike & Ped | Locally Selected | Neuse River | From proposed residential development to future school complex near SR 2589 (Clearwater Drive) in Wilson's Mills | Construct multi-use path along Neuse River. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 3209000 | FY 2026: 3209000
BN-0024 | Bike & Ped | Locally Selected | Neuse River | From proposed residential development to future school complex near SR 2589 (Clearwater Drive) in Wilson's Mills | Construct multi-use path along Neuse River. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 802000 | FY 2026: 802000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (West Main Street) | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRP550 | ENGINEERING | 140000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (West Main Street) | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 35000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (West Main Street) | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 140000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (West Main Street) | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 35000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (West Main Street) | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 696000 | FY 2026: 696000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (West Main Street) | South of Fayetteville Street to Dwight Drive in Micro | Construct sidewalk. | 0.3 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 174000 | FY 2026: 174000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (East Third Street) | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | ENGINEERING | 220000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (East Third Street) | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 55000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (East Third Street) | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 147000 | FY 2026: 147000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (East Third Street) | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 37000 | FY 2026: 37000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (East Third Street) | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1685000 | FY 2027: 1685000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (East Third Street) | SR 1006 (North Second Avenue) to East Fifth Street in Siler City. | Construct sidewalk on north side. | 0.8 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 421000 | FY 2027: 421000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (North Second Avenue) | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | ENGINEERING | 188000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (North Second Avenue) | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 47000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (North Second Avenue) | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 158000 | FY 2026: 158000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (North Second Avenue) | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (North Second Avenue) | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1214000 | FY 2027: 1214000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (North Second Avenue) | East Fourth Street to US 64 (West Eleventh Street) in Siler City. | Construct sidewalk on west side. | 0.6 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 303000 | FY 2027: 303000
BN-0028 | Bike & Ped | Locally Selected | Salisbury Street | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRPANY | ENGINEERING | 95000
BN-0028 | Bike & Ped | Locally Selected | Salisbury Street | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 24000
BN-0028 | Bike & Ped | Locally Selected | Salisbury Street | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRPANY | RIGHT-OF-WAY | 22000 | FY 2026: 22000
BN-0028 | Bike & Ped | Locally Selected | Salisbury Street | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 6000 | FY 2026: 6000
BN-0028 | Bike & Ped | Locally Selected | Salisbury Street | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 203000 | FY 2026: 203000
BN-0028 | Bike & Ped | Locally Selected | Salisbury Street | Fayetteville Street to JA Farrell Street in Pittsboro. | Construct sidewalk. | 0.5 | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 51000 | FY 2026: 51000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (Riverside Drive) | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | CMAQ | ENGINEERING | 8000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (Riverside Drive) | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L(M) | ENGINEERING | 2000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (Riverside Drive) | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L | ENGINEERING | 51000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (Riverside Drive) | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L | RIGHT-OF-WAY | 44000 | FY 2026: 44000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (Riverside Drive) | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | CMAQ | CONSTRUCTION | 1992000 | FY 2026: 1992000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (Riverside Drive) | SR 2000 (Hickory Grove Road) to future Riverlink Trail Extension in Cramerton. | Construct sidewalk. | 0.2 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L(M) | CONSTRUCTION | 498000 | FY 2026: 498000
BN-0030 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Greenways in Winston-Salem. | Install wayfinding signs. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BN-0030 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Greenways in Winston-Salem. | Install wayfinding signs. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BN-0030 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Greenways in Winston-Salem. | Install wayfinding signs. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 504000 | FY 2026: 504000
BN-0030 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Greenways in Winston-Salem. | Install wayfinding signs. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 126000 | FY 2026: 126000
BN-0031 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Locations statewide. | Construct pedestrian safety improvements. | 0.1 | Statewide | 99 | Statewide Project |  | Division 99 |  | TAANY | ENGINEERING | 2600000 | FY 2026: 2600000
BN-0031 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Locations statewide. | Construct pedestrian safety improvements. | 0.1 | Statewide | 99 | Statewide Project |  | Division 99 |  | TAANY | RIGHT-OF-WAY | 1000000 | FY 2026: 1000000
BN-0031 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Locations statewide. | Construct pedestrian safety improvements. | 0.1 | Statewide | 99 | Statewide Project |  | Division 99 |  | TAANY | UTILITIES | 2000000 | FY 2026: 2000000
BN-0031 | Bike & Ped | NCDOT Selected (Other Selection Process) | Various | Locations statewide. | Construct pedestrian safety improvements. | 0.1 | Statewide | 99 | Statewide Project |  | Division 99 |  | TAANY | CONSTRUCTION | 21400000 | FY 2026: 21400000
BN-0032 | Bike & Ped | NCDOT Selected (Other Selection Process) | Venture Drive | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | ENGINEERING | 140000 | FY 2026: 140000
BN-0032 | Bike & Ped | NCDOT Selected (Other Selection Process) | Venture Drive | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 35000 | FY 2026: 35000
BN-0032 | Bike & Ped | NCDOT Selected (Other Selection Process) | Venture Drive | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 144000 | FY 2027: 144000
BN-0032 | Bike & Ped | NCDOT Selected (Other Selection Process) | Venture Drive | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 36000 | FY 2027: 36000
BN-0032 | Bike & Ped | NCDOT Selected (Other Selection Process) | Venture Drive | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 936000 | FY 2028: 936000
BN-0032 | Bike & Ped | NCDOT Selected (Other Selection Process) | Venture Drive | Outlet Center Drive to SR 2403 (Peedin Road) in Smithfield. | Construct five foot sidewalk along Venture Drive. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 234000 | FY 2028: 234000
BO-0001 | Bike & Ped | Other | Charlotte | East Charlotte Connector Trail | Funding for Albemarle Corridor Cultural Trail Framework Plan |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | DP | PLANNING | 1400000 | FY 2026: 1400000
BO-0001 | Bike & Ped | Other | Charlotte | East Charlotte Connector Trail | Funding for Albemarle Corridor Cultural Trail Framework Plan |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | PLANNING | 400000 | FY 2026: 400000
BO-0002 | Bike & Ped | Other | Charlotte | Rozzelles Ferry Mobility Path | Funding for Advance planning of the Rozzelles Ferry Mobility Path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | DP | PLANNING | 1291000 | FY 2026: 1291000
BO-0002 | Bike & Ped | Other | Charlotte | Rozzelles Ferry Mobility Path | Funding for Advance planning of the Rozzelles Ferry Mobility Path. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | PLANNING | 333000 | FY 2026: 333000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | ENGINEERING | 100000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | UTILITIES | 50000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | CONSTRUCTION | 1000000
BO-2401 | Bike & Ped | Other | Various | Locations in Division 1 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | ENGINEERING | 100000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | UTILITIES | 50000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2402 | Bike & Ped | Other | Various | Locations in Division 2 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | CONSTRUCTION | 1000000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | ENGINEERING | 100000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | UTILITIES | 50000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | CONSTRUCTION | 1000000
BO-2403 | Bike & Ped | Other | Various | Locations in Division 3 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | ENGINEERING | 100000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | UTILITIES | 50000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | CONSTRUCTION | 1000000
BO-2404 | Bike & Ped | Other | Various | Locations in Division 4 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | ENGINEERING | 100000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | UTILITIES | 50000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2405 | Bike & Ped | Other | Various | Locations in Division 5 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | CONSTRUCTION | 1000000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | ENGINEERING | 100000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | UTILITIES | 50000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2406 | Bike & Ped | Other | Various | Locations in Division 6 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | CONSTRUCTION | 1000000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | ENGINEERING | 100000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | UTILITIES | 50000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | CONSTRUCTION | 1000000
BO-2407 | Bike & Ped | Other | Various | Locations in Division 7 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | ENGINEERING | 100000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | UTILITIES | 50000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | CONSTRUCTION | 1000000
BO-2408 | Bike & Ped | Other | Various | Locations in Division 8 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | ENGINEERING | 100000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | UTILITIES | 50000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2409 | Bike & Ped | Other | Various | Locations in Division 9 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | CONSTRUCTION | 1000000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | ENGINEERING | 425000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | ENGINEERING | 200000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | UTILITIES | 50000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2410 | Bike & Ped | Other | Various | Locations in Division 10 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | CONSTRUCTION | 1000000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | ENGINEERING | 250000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | UTILITIES | 50000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2411 | Bike & Ped | Other | Various | Locations in Division 11 | Construct intersection improvements to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | CONSTRUCTION | 3500000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | ENGINEERING | 200000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | UTILITIES | 50000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2412 | Bike & Ped | Other | Various | Locations in Division 12 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | CONSTRUCTION | 1000000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | ENGINEERING | 100000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | UTILITIES | 50000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | CONSTRUCTION | 1000000
BO-2413 | Bike & Ped | Other | Various | Locations in Division 13 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | ENGINEERING | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | ENGINEERING | 200000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | RIGHT-OF-WAY | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | UTILITIES | 50000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | UTILITIES | 200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | CONSTRUCTION | 1000000
BO-2414 | Bike & Ped | Other | Various | Locations in Division 14 | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | CONSTRUCTION | 4000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2415 | Bike & Ped | Other | Morgan Creek Greenway | Existing Morgan Creek Greenway to SR 1919 (Smith Level Road) in Chapel Hill | Construct greenway and connections. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | RIGHT-OF-WAY | 623000
BO-2415 | Bike & Ped | Other | Morgan Creek Greenway | Existing Morgan Creek Greenway to SR 1919 (Smith Level Road) in Chapel Hill | Construct greenway and connections. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 550000
BO-2415 | Bike & Ped | Other | Morgan Creek Greenway | Existing Morgan Creek Greenway to SR 1919 (Smith Level Road) in Chapel Hill | Construct greenway and connections. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 647000
BO-2415 | Bike & Ped | Other | Morgan Creek Greenway | Existing Morgan Creek Greenway to SR 1919 (Smith Level Road) in Chapel Hill | Construct greenway and connections. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 550000
BO-2416 | Bike & Ped | Other | SR 1153 (Tingen Road) | CSX Railroad crossing north of James Street. | Construct a pedestrian bridge over CSX railroad within the existing alignment of SR 1153 (Tingen Road) in Apex. | 0.25 | Wake | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC202. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | HP | ENGINEERING | 520000
BO-2416 | Bike & Ped | Other | SR 1153 (Tingen Road) | CSX Railroad crossing north of James Street. | Construct a pedestrian bridge over CSX railroad within the existing alignment of SR 1153 (Tingen Road) in Apex. | 0.25 | Wake | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC202. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | L(M) | ENGINEERING | 120000
BO-2416 | Bike & Ped | Other | SR 1153 (Tingen Road) | CSX Railroad crossing north of James Street. | Construct a pedestrian bridge over CSX railroad within the existing alignment of SR 1153 (Tingen Road) in Apex. | 0.25 | Wake | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC202. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | HP | RIGHT-OF-WAY | 40000
BO-2416 | Bike & Ped | Other | SR 1153 (Tingen Road) | CSX Railroad crossing north of James Street. | Construct a pedestrian bridge over CSX railroad within the existing alignment of SR 1153 (Tingen Road) in Apex. | 0.25 | Wake | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC202. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | L(M) | RIGHT-OF-WAY | 8000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | HP | ENGINEERING | 998000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L(M) | ENGINEERING | 250000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | HP | RIGHT-OF-WAY | 312000 | FY 2026: 312000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L(M) | RIGHT-OF-WAY | 78000 | FY 2026: 78000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | HP | CONSTRUCTION | 1690000 | FY 2027: 1690000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L(M) | CONSTRUCTION | 423000 | FY 2027: 423000
BO-2417 | Bike & Ped | Other | US 64 Business (Thomas Street) | Main Street intersection in Rocky Mount. | Construct pedestrian bridge over Main Street. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L | CONSTRUCTION | 3690000 | FY 2027: 3690000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L | ENGINEERING | 590000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | HP | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | HP | UTILITIES | 80000 | FY 2026: 80000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L(M) | UTILITIES | 20000 | FY 2026: 20000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | HP | CONSTRUCTION | 2400000 | FY 2026: 2400000
BO-2418 | Bike & Ped | Other | SR 1531 (North Greene Street) | 1st Street to SR 1530 (Mumford Road) in Greenville | Construct greenway / side path using existing road and sidewalk. | 1.1 | Pitt | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L(M) | CONSTRUCTION | 885000 | FY 2026: 885000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | ENGINEERING | 1031000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | ENGINEERING | 344000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | ENGINEERING | 34000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | RIGHT-OF-WAY | 89000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | RIGHT-OF-WAY | 30000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | RIGHT-OF-WAY | 3000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | UTILITIES | 89000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | UTILITIES | 30000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | UTILITIES | 3000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | CONSTRUCTION | 7791000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | CONSTRUCTION | 2596000
BO-2419 | Bike & Ped | Other | Various | Locations in 15 municipalities in Divisions 2, 4, 5, 6, 8, and 9 | Construct pedestrian countdown signal heads, crosswalks and accessible routes at signalized intersections. |  | Lenoir, Wilson, Rowan, Davidson, Richmond, Robeson, Granville, Halifax, Johnston, Vance, Beaufort, Chatham | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | CONSTRUCTION | 260000
BO-2420 | Bike & Ped | Locally Selected | NC 344 (Weeksville Road) | Various locations in Elizabeth City | Accessibility and connectivity plan. | 3.6 | Pasquotank | 1 | Albemarle RPO | 'DP' FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 2000000
BO-2421 | Bike & Ped | Other | Ephesus Church Road | US 15 / US 501 Bypass (Fordham Boulevard) to Pope Road near Chapel Hill. | Construct sidewalks and bike lanes to fill in gaps. | 1.6 | Orange | 7 | Triangle West TPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | ENGINEERING | 80000
BO-2421 | Bike & Ped | Other | Ephesus Church Road | US 15 / US 501 Bypass (Fordham Boulevard) to Pope Road near Chapel Hill. | Construct sidewalks and bike lanes to fill in gaps. | 1.6 | Orange | 7 | Triangle West TPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | RIGHT-OF-WAY | 70000 | FY 2026: 70000
BO-2421 | Bike & Ped | Other | Ephesus Church Road | US 15 / US 501 Bypass (Fordham Boulevard) to Pope Road near Chapel Hill. | Construct sidewalks and bike lanes to fill in gaps. | 1.6 | Orange | 7 | Triangle West TPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | UTILITIES | 150000 | FY 2026: 150000
BO-2421 | Bike & Ped | Other | Ephesus Church Road | US 15 / US 501 Bypass (Fordham Boulevard) to Pope Road near Chapel Hill. | Construct sidewalks and bike lanes to fill in gaps. | 1.6 | Orange | 7 | Triangle West TPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | CONSTRUCTION | 200000 | FY 2026: 200000
BO-2421 | Bike & Ped | Other | Ephesus Church Road | US 15 / US 501 Bypass (Fordham Boulevard) to Pope Road near Chapel Hill. | Construct sidewalks and bike lanes to fill in gaps. | 1.6 | Orange | 7 | Triangle West TPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | L(M) | CONSTRUCTION | 600000 | FY 2026: 600000
BO-2422 | Bike & Ped | Other | SR 1011 (South Salem Street) | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L | ENGINEERING | 740000
BO-2422 | Bike & Ped | Other | SR 1011 (South Salem Street) | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | HP | RIGHT-OF-WAY | 712000 | FY 2027: 712000
BO-2422 | Bike & Ped | Other | SR 1011 (South Salem Street) | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L(M) | RIGHT-OF-WAY | 178000 | FY 2027: 178000
BO-2422 | Bike & Ped | Other | SR 1011 (South Salem Street) | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | HP | CONSTRUCTION | 138000 | FY 2028: 138000
BO-2422 | Bike & Ped | Other | SR 1011 (South Salem Street) | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L(M) | CONSTRUCTION | 35000 | FY 2028: 35000
BO-2422 | Bike & Ped | Other | SR 1011 (South Salem Street) | Pleasant Plains Road to Chatham Street near Apex. | Construct bicycle lanes and install shared lane markings. | 2.9 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L | CONSTRUCTION | 2797000 | FY 2028: 2797000
BO-2423 | Bike & Ped | Other | Walnut Creek Greenway | Downtown Cary Park to Buck Jones Road at I-40 in Cary. | Construct greenway. | 2.6 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC207. | Exempt |  | HP | ENGINEERING | 500000
BO-2423 | Bike & Ped | Other | Walnut Creek Greenway | Downtown Cary Park to Buck Jones Road at I-40 in Cary. | Construct greenway. | 2.6 | Wake | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC207. | Exempt |  | L(M) | ENGINEERING | 125000
BO-2424 | Bike & Ped | Other | Various | Locations statewide. | Integrated Mobility Division bicycle and pedestrian coordination activities. |  | Statewide | 99 | Statewide Project |  | Exempt |  | CMAQ | ENGINEERING | 1100000 | FY 2026: 367000; FY 2027: 366000
BO-2425 | Bike & Ped | Other | Walnut Cove Greenway | Walnut Cove | Construct greenway |  | Stokes | 9 | Northwest Piedmont RPO | DP FUNDS REPRESENT FEDERAL NEIGHBORHOOD ACCESS AND EQUITY (NAE) GRANT. | Exempt |  | DP | ENGINEERING | 250000
BO-2601 | Bike & Ped | Other | Various | Various locations in Division 1. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1
BO-2602 | Bike & Ped | Other | Various | Various locations in Division 2. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2
BO-2603 | Bike & Ped | Other | Various | Various locations in Division 3. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3
BO-2604 | Bike & Ped | Other | Various | Various locations in Division 4. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4
BO-2605 | Bike & Ped | Other | Various | Various locations in Division 5. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5
BO-2606 | Bike & Ped | Other | Various | Various locations in Division 6. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6
BO-2607 | Bike & Ped | Other | Various | Various locations in Division 7. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7
BO-2608 | Bike & Ped | Other | Various | Various locations in Division 8. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8
BO-2609 | Bike & Ped | Other | Various | Various locations in Division 9. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9
BO-2610 | Bike & Ped | Other | Various | Various locations in Division 10. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10
BO-2611 | Bike & Ped | Other | Various | Various locations in Division 11. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (Ta) funds. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11
BO-2612 | Bike & Ped | Other | Various | Various locations in Division 12. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12
BO-2613 | Bike & Ped | Other | Various | Various locations in Division 13. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13
BO-2614 | Bike & Ped | Other | Various | Various locations in Division 14. | Upgrade intersections to comply with the Americans with Disabilities Act (ADA) using Transportation Alternatives (TA) funds. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14
BO-2615 | Bike & Ped | Other | Various | Routes in the Town of Pittsboro | Conduct a feasibility study for West Salisbury Street, The Village Apartments Connector, the Kiwanis Park Connector, the Town to Village Trail, the NC 87 to Central Carolina Community College (CCCC) Campus Sidewalk, and the Chatham Marketplace Connector. |  | Chatham | 8 | Central Pines RPO | DP FUNDS REPRESENT RAISE GRANT FUNDING | Exempt |  | DP | ENGINEERING | 996000 | FY 2026: 996000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | ENGINEERING | 202000 | FY 2029: 202000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | ENGINEERING | 51000 | FY 2029: 51000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | RIGHT-OF-WAY | 67000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | RIGHT-OF-WAY | 19000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | UTILITIES | 8000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | UTILITIES | 2000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | CONSTRUCTION | 956000
BP-0001 | Bike & Ped | STI (Prioritization) | Blounts Creek Greenway | Russell Street to Cool Spring Street in Fayetteville. | Construct multi-use path. | 0.62 | Cumberland | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | CONSTRUCTION | 239000
BR-0012 | Highway | Bridges | US 74 | Bridges 220048 and 220049 over Sandy Run. | Replace bridges. | 0.25 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045 | Highway Fund |  | HFB | RIGHT-OF-WAY | 42000
BR-0012 | Highway | Bridges | US 74 | Bridges 220048 and 220049 over Sandy Run. | Replace bridges. | 0.25 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045 | Highway Fund |  | HFB | CONSTRUCTION | 61591000 | FY 2026: 20325000; FY 2027: 6775000
BR-0025 | Highway | Bridges | SR 1639 (Meacham Road) | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BFP | RIGHT-OF-WAY | 64000 | FY 2029: 64000
BR-0025 | Highway | Bridges | SR 1639 (Meacham Road) | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | T(M) | RIGHT-OF-WAY | 16000 | FY 2029: 16000
BR-0025 | Highway | Bridges | SR 1639 (Meacham Road) | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BFP | UTILITIES | 8000 | FY 2029: 8000
BR-0025 | Highway | Bridges | SR 1639 (Meacham Road) | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | T(M) | UTILITIES | 2000 | FY 2029: 2000
BR-0025 | Highway | Bridges | SR 1639 (Meacham Road) | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BFP | CONSTRUCTION | 3360000 | FY 2031: 1243000; FY 2032: 1579000; FY 2033: 538000
BR-0025 | Highway | Bridges | SR 1639 (Meacham Road) | Bridge 480118 over I-40. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | T(M) | CONSTRUCTION | 840000 | FY 2031: 311000; FY 2032: 395000; FY 2033: 134000
BR-0035 | Highway | Bridges | NC 22 | Bridge 620062 over Nicks Creek in Carthage. | Replace bridge. | 0.25 | Moore | 8 | Sandhills MPO | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION | Region E |  | NHPB | CONSTRUCTION | 3280000
BR-0035 | Highway | Bridges | NC 22 | Bridge 620062 over Nicks Creek in Carthage. | Replace bridge. | 0.25 | Moore | 8 | Sandhills MPO | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION | Region E |  | T(M) | CONSTRUCTION | 820000
BR-0036 | Highway | Bridges | NC 33 | Bridge 630041 over I-95 | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 4700000
BR-0039 | Highway | Bridges | SR 1510 | Bridge 630224 over I-95 | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 5200000
BR-0040 | Highway | Bridges | NC 9 | Bridge 740037 over Green River | Replace bridge. | 0.5 | Polk | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | HFB | RIGHT-OF-WAY | 330000
BR-0040 | Highway | Bridges | NC 9 | Bridge 740037 over Green River | Replace bridge. | 0.5 | Polk | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | BFP | CONSTRUCTION | 5700000 | FY 2028: 5700000
BR-0075 | Highway | Bridges | SR 1109 (Kinnamon Road) | Bridge 330135 over I-40 | Replace bridge. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 700000 | FY 2026: 700000
BR-0075 | Highway | Bridges | SR 1109 (Kinnamon Road) | Bridge 330135 over I-40 | Replace bridge. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 100000 | FY 2026: 100000
BR-0075 | Highway | Bridges | SR 1109 (Kinnamon Road) | Bridge 330135 over I-40 | Replace bridge. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 12000000 | FY 2028: 2880000; FY 2029: 3960000; FY 2030: 3000000; FY 2031: 2160000
BR-0077 | Highway | Bridges | SR 2770 (Huffine Mill Road) over US 70 (East Wendover Avenue) | Bridge 400131 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HFB | RIGHT-OF-WAY | 5567000
BR-0077 | Highway | Bridges | SR 2770 (Huffine Mill Road) over US 70 (East Wendover Avenue) | Bridge 400131 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HFB | UTILITIES | 560000
BR-0077 | Highway | Bridges | SR 2770 (Huffine Mill Road) over US 70 (East Wendover Avenue) | Bridge 400131 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(DA) | CONSTRUCTION | 301000 | FY 2028: 301000
BR-0077 | Highway | Bridges | SR 2770 (Huffine Mill Road) over US 70 (East Wendover Avenue) | Bridge 400131 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HFB | CONSTRUCTION | 18400000 | FY 2028: 18400000
BR-0079 | Highway | Bridges | Tuscaloosa Street | Bridge 400302 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 1200000 | FY 2026: 101000; FY 2027: 606000; FY 2028: 253000; FY 2029: 120000; FY 2030: 120000
BR-0079 | Highway | Bridges | Tuscaloosa Street | Bridge 400302 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | UTILITIES | 2000000 | FY 2026: 2000000
BR-0079 | Highway | Bridges | Tuscaloosa Street | Bridge 400302 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 7700000 | FY 2028: 2079000; FY 2029: 3619000; FY 2030: 1540000; FY 2031: 462000
BR-0080 | Highway | Bridges | Sullivan Street | Bridge 400331 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 805000
BR-0080 | Highway | Bridges | Sullivan Street | Bridge 400331 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | UTILITIES | 100000
BR-0080 | Highway | Bridges | Sullivan Street | Bridge 400331 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 7400000 | FY 2028: 814000; FY 2029: 3700000; FY 2030: 1998000; FY 2031: 888000
BR-0081 | Highway | Bridges | Phillips Avenue | Bridges 400283 and 400342 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | RIGHT-OF-WAY | 920000 | FY 2027: 920000
BR-0081 | Highway | Bridges | Phillips Avenue | Bridges 400283 and 400342 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | RIGHT-OF-WAY | 230000 | FY 2027: 230000
BR-0081 | Highway | Bridges | Phillips Avenue | Bridges 400283 and 400342 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | CONSTRUCTION | 9200000 | FY 2029: 4600000; FY 2030: 4600000
BR-0081 | Highway | Bridges | Phillips Avenue | Bridges 400283 and 400342 over US 29 / US 70 / US 220 | Replace bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | CONSTRUCTION | 2300000 | FY 2029: 1150000; FY 2030: 1150000
BR-0096 | Highway | Bridges | SR 1700 (Fisher Hill Road) | Bridge 780176 over NC 14 / NC 87 | Replace bridge. |  | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 7 |  | BGOFF | CONSTRUCTION | 2300000 | FY 2026: 1403000; FY 2027: 897000
BR-0107 | Highway | Bridges | SR 1577 (Pisgah Ridge Circle) | Bridge 480131 over Unnamed Tributary to Snow Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | Highway Fund |  | HFB | CONSTRUCTION | 800000
BR-0108 | Highway | Bridges | SR 2418 (South Windy Gap Road) | Bridge 960004 over Little Hunting Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | CONSTRUCTION | 1200000
BR-0111 | Highway | Bridges | SR 1404 (Seven Bridges Road) | Bridges 320003, 320004, and 320005 over Swift Creek. | Replace bridges. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  |  |  | 100000
BR-0111 | Highway | Bridges | SR 1404 (Seven Bridges Road) | Bridges 320003, 320004, and 320005 over Swift Creek. | Replace bridges. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | RIGHT-OF-WAY | 420000
BR-0111 | Highway | Bridges | SR 1404 (Seven Bridges Road) | Bridges 320003, 320004, and 320005 over Swift Creek. | Replace bridges. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | UTILITIES | 56000
BR-0111 | Highway | Bridges | SR 1404 (Seven Bridges Road) | Bridges 320003, 320004, and 320005 over Swift Creek. | Replace bridges. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | CONSTRUCTION | 5450000
BR-0112 | Highway | Bridges | SR 1616 (Sharp Point Road) | Bridge 320035 over Otter Creek. | Replace bridge. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  |  |  | 230000
BR-0112 | Highway | Bridges | SR 1616 (Sharp Point Road) | Bridge 320035 over Otter Creek. | Replace bridge. | 0.25 | Edgecombe | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | CONSTRUCTION | 1112000
BR-0113 | Highway | Bridges | SR 1601 (Sledge Road) | Bridge 410115 over Rocky Swamp. | Replace bridge. | 0.25 | Halifax | 4 | Peanut Belt RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  |  |  | 100000
BR-0113 | Highway | Bridges | SR 1601 (Sledge Road) | Bridge 410115 over Rocky Swamp. | Replace bridge. | 0.25 | Halifax | 4 | Peanut Belt RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | HFB | RIGHT-OF-WAY | 130000
BR-0113 | Highway | Bridges | SR 1601 (Sledge Road) | Bridge 410115 over Rocky Swamp. | Replace bridge. | 0.25 | Halifax | 4 | Peanut Belt RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | CONSTRUCTION | 796000
BR-0114 | Highway | Bridges | SR 1601 (Branton Road) | Bridge 480165 on SR 1601 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  |  |  | 250000
BR-0114 | Highway | Bridges | SR 1601 (Branton Road) | Bridge 480165 on SR 1601 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | HFB | RIGHT-OF-WAY | 150000
BR-0114 | Highway | Bridges | SR 1601 (Branton Road) | Bridge 480165 on SR 1601 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | DP | CONSTRUCTION | 300000
BR-0114 | Highway | Bridges | SR 1601 (Branton Road) | Bridge 480165 on SR 1601 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | HFB | CONSTRUCTION | 850000
BR-0115 | Highway | Bridges | SR 1595 (Coolbrook Road) | Bridge 480166 on SR 1595 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  |  |  | 270000
BR-0115 | Highway | Bridges | SR 1595 (Coolbrook Road) | Bridge 480166 on SR 1595 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | HFB | RIGHT-OF-WAY | 170000
BR-0115 | Highway | Bridges | SR 1595 (Coolbrook Road) | Bridge 480166 on SR 1595 over Rocky Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | DP | CONSTRUCTION | 1600000
BR-0116 | Highway | Bridges | SR 1403 (Cooper Road) | Bridge 630080 over Gideon Swamp. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  |  |  | 100000
BR-0116 | Highway | Bridges | SR 1403 (Cooper Road) | Bridge 630080 over Gideon Swamp. | Replace bridge. | 0.25 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 1000000
BR-0121 | Highway | Bridges | SR 1804 (Houses Mill Road) | Bridge 810178 over Sevenmile Swamp. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 3 |  |  |  | 250000
BR-0121 | Highway | Bridges | SR 1804 (Houses Mill Road) | Bridge 810178 over Sevenmile Swamp. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 3 |  | DP | CONSTRUCTION | 1400000
BR-0122 | Highway | Bridges | SR 1703 (Old Goldsboro Road) | Bridge 810348 over Beaverdam Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 3 |  |  |  | 150000
BR-0122 | Highway | Bridges | SR 1703 (Old Goldsboro Road) | Bridge 810348 over Beaverdam Creek. | Replace bridge. | 0.25 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 3 |  | DP | CONSTRUCTION | 727000
BR-0124 | Highway | Bridges | SR 1745 (Shumate Mountain Road) | Bridge 960166 on SR 1745 over West Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  |  |  | 100000
BR-0124 | Highway | Bridges | SR 1745 (Shumate Mountain Road) | Bridge 960166 on SR 1745 over West Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 40000
BR-0124 | Highway | Bridges | SR 1745 (Shumate Mountain Road) | Bridge 960166 on SR 1745 over West Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 2900000
BR-0125 | Highway | Bridges | SR 1002 (Traphill Road) | Bridge 960663 over East Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  |  |  | 380000
BR-0125 | Highway | Bridges | SR 1002 (Traphill Road) | Bridge 960663 over East Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 280000
BR-0125 | Highway | Bridges | SR 1002 (Traphill Road) | Bridge 960663 over East Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 2350000
BR-0125 | Highway | Bridges | SR 1002 (Traphill Road) | Bridge 960663 over East Prong Roaring River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | CONSTRUCTION | 300000
BR-0126 | Highway | Bridges | SR 1749 (Austin Traphill Road) | Bridge 960667 over Sparks Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  |  |  | 100000
BR-0126 | Highway | Bridges | SR 1749 (Austin Traphill Road) | Bridge 960667 over Sparks Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 80000
BR-0126 | Highway | Bridges | SR 1749 (Austin Traphill Road) | Bridge 960667 over Sparks Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 1550000
BR-0127 | Highway | Bridges | SR 1325 (Mountain View Church Road) | Bridge 980189 over South Deep Creek. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 45000
BR-0127 | Highway | Bridges | SR 1325 (Mountain View Church Road) | Bridge 980189 over South Deep Creek. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 850000
BR-0130 | Highway | Bridges | I-40 | Bridges 110114 and 110120 over Silver Creek. | Replace bridges. | 0.25 | Burke | 13 | Greater Hickory MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 9440000 | FY 2031: 4720000; FY 2032: 4720000
BR-0130 | Highway | Bridges | I-40 | Bridges 110114 and 110120 over Silver Creek. | Replace bridges. | 0.25 | Burke | 13 | Greater Hickory MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 2360000 | FY 2031: 1180000; FY 2032: 1180000
BR-0141 | Highway | Bridges | SR 2150 (River Road) | Bridge 780123 over US 220 / US 311 | Replace bridge. |  | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 7 |  | BGOFF | CONSTRUCTION | 4100000 | FY 2027: 615000; FY 2028: 2501000; FY 2029: 984000
BR-0145 | Highway | Bridges | NC 208 | Bridge 560033 over Shelton Laurel Creek | Replace bridge. |  | Madison | 13 | Foothills RPO |  | Region G |  | BFP | CONSTRUCTION | 2200000 | FY 2027: 2200000
BR-0151 | Highway | Bridges | SR 1002 (Henry River Road). | SR1002 (Henry River Road) over I-40. | Replace bridge. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | HFB | RIGHT-OF-WAY | 500000 | FY 2027: 500000
BR-0151 | Highway | Bridges | SR 1002 (Henry River Road). | SR1002 (Henry River Road) over I-40. | Replace bridge. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 416000 | FY 2028: 416000
BR-0151 | Highway | Bridges | SR 1002 (Henry River Road). | SR1002 (Henry River Road) over I-40. | Replace bridge. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 104000 | FY 2028: 104000
BR-0151 | Highway | Bridges | SR 1002 (Henry River Road). | SR1002 (Henry River Road) over I-40. | Replace bridge. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L | CONSTRUCTION | 312000 | FY 2028: 312000
BR-0151 | Highway | Bridges | SR 1002 (Henry River Road). | SR1002 (Henry River Road) over I-40. | Replace bridge. |  | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | HFB | CONSTRUCTION | 11568000 | FY 2028: 11568000
BR-0152 | Highway | Bridges | SR 1436 (Pinebrook School Road) | Bridge 290076 over I-40 | Replace bridge. |  | Davie | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM. UNDER CONSTRUCTION | Division 9 |  | BGOFF | CONSTRUCTION | 4910000 | FY 2026: 2320000; FY 2027: 270000
BR-0153 | Highway | Bridges | NC 11 | Bridge 070024 over Cashie River | Replace bridge. |  | Bertie | 1 | Peanut Belt RPO |  | Region A |  | BFP | CONSTRUCTION | 4990000 | FY 2026: 3382000; FY 2027: 998000
BR-0154 | Highway | Bridges | NC 209 | Bridge 430128 over Cove Creek | Replace bridge. | 0.5 | Haywood | 14 | Land-of-Sky RPO |  | Region G |  | BFP | CONSTRUCTION | 1600000 | FY 2028: 1600000
BR-0162 | Highway | Bridges | US 19 W | Bridge 990012 over Bald Creek | Replace bridge. |  | Yancey | 13 | High Country RPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 1600000 | FY 2030: 1600000
BR-0163 | Highway | Bridges | NC 742 | Bridge 030084 over Lanes Creek | Replace bridge. | 0.1 | Anson | 10 | Rocky River RPO |  | Region E |  | BFP | RIGHT-OF-WAY | 356000 | FY 2029: 356000
BR-0163 | Highway | Bridges | NC 742 | Bridge 030084 over Lanes Creek | Replace bridge. | 0.1 | Anson | 10 | Rocky River RPO |  | Region E |  | T(M) | RIGHT-OF-WAY | 89000 | FY 2029: 89000
BR-0163 | Highway | Bridges | NC 742 | Bridge 030084 over Lanes Creek | Replace bridge. | 0.1 | Anson | 10 | Rocky River RPO |  | Region E |  | BFP | CONSTRUCTION | 3558000 | FY 2029: 3558000
BR-0163 | Highway | Bridges | NC 742 | Bridge 030084 over Lanes Creek | Replace bridge. | 0.1 | Anson | 10 | Rocky River RPO |  | Region E |  | T(M) | CONSTRUCTION | 890000 | FY 2029: 890000
BR-0169 | Highway | Bridges | NC 561 | Bridge 340024 over Sandy Creek | Replace bridge. |  | Franklin | 5 | Kerr-Tar RPO |  | Region C |  | BFP | CONSTRUCTION | 4000000 | FY 2029: 4000000
BR-0173 | Highway | Bridges | NC 306 | Structure 680078 (Ferry Ramp) over the Neuse River at the Minnesott Beach Ferry Terminal. | Replace Structure. | 0.1 | Pamlico | 2 | Down East RPO |  | Region B |  | FBP | CONSTRUCTION | 9100000 | FY 2026: 4550000
BR-0174 | Highway | Bridges | NC 53 | Bridge 700037 over Angola Creek | Replace bridge. | 0.1 | Pender | 3 | Cape Fear RPO |  | Region B |  | BFP | CONSTRUCTION | 3000000 | FY 2027: 3000000
BR-0193 | Highway | Bridges | NC 24 | Bridge 660007 over Northeast Creek | Replace bridge. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 9600000 | FY 2028: 9600000
BR-0200 | Highway | Bridges | SR 1152 (Neelie Road) | Bridge 980020 over South Deep Creek. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183. | Highway Fund |  | HFB | CONSTRUCTION | 850000
BR-0201 | Highway | Bridges | SR 1348 (Old NC 90) | Bridge 010291 over Duck Creek. | Replace bridge. | 0.25 | Alexander | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88 | Highway Fund |  | HFB | CONSTRUCTION | 1050000
BR-0202 | Highway | Bridges | SR 1892 (Jennings Road) | Bridge 480212 over Patterson Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49 | Highway Fund |  | HFB | CONSTRUCTION | 1250000
BR-0203 | Highway | Bridges | SR 1896 (Friendship Road) | Bridge 480214 over Patterson Creek | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50 | Highway Fund |  | HFB | CONSTRUCTION | 1000000
BR-0204 | Highway | Bridges | SR 1892 (Jennings Road) | Bridge 480219 over Olin Creek. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51 | Highway Fund |  | HFB | CONSTRUCTION | 900000
BR-0205 | Highway | Bridges | SR 1119 (Sloans Mill Road) | Bridge 980028 over North Little Hunting Creek. | Replace bridge. | 0.25 | Yadkin | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130 | Highway Fund |  | HFB | CONSTRUCTION | 2000000
BR-0206 | Highway | Bridges | SR 1422 (Fox Ridge Road) | Bridge 020035 over Glade Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157 | Highway Fund |  | HFB | CONSTRUCTION | 750000
BR-0207 | Highway | Bridges | SR 1433 (Ridgeglen Road) | Bridge 020133 over Little River. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159 | Highway Fund |  | HFB | CONSTRUCTION | 500000
BR-0208 | Highway | Bridges | SR 2516 (Industrial Park Road) | Bridge 960733 over Cub Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154 | Highway Fund |  | HFB | CONSTRUCTION | 600000
BR-0209 | Highway | Bridges | SR 1148 (Red Top Road) | Bridge 960419 over Naked Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153 | Highway Fund |  | HFB | CONSTRUCTION | 650000
BR-0210 | Highway | Bridges | SR 2081 (Hardy Road) | Bridge 850153 over Hogan Creek. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  |  |  | 50000
BR-0210 | Highway | Bridges | SR 2081 (Hardy Road) | Bridge 850153 over Hogan Creek. | Replace bridge. | 0.25 | Surry | 11 | Northwest Piedmont RPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 875000
BR-0241 | Highway | Bridges | SR 1243 (Leggett Road) | Bridge 320054 over Tar River. | Replace bridge. | 0.25 | Edgecombe | 4 | Rocky Mount Urban Area MPO | COMPLETE. PROJECT REPRESENTS HFB 4.R.101 PROJECT. | Highway Fund |  | HFB | CONSTRUCTION | 3600000
BR-0243 | Highway | Bridges | SR 1162 (Bay Road) | Bridge 300045 over Island Creek. | Replace bridge. | 0.25 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.83 PROJECT. | Highway Fund |  | HFB | CONSTRUCTION | 1700000
C-4902 | Highway | Other | North Carolina State University Solar Center Clean Transportation Program. | Systemwide | Develop and administer a seven year clean fuel-advanced technology rebate program in all CMAQ eligible counties to reduce emissions. |  | Statewide | 99 | Statewide Project | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY | Exempt |  |  |  | 4694000
C-4902A | Highway | Other | North Carolina State University Solar Center Clean Transportation Program. | Systemwide | Develop and administer a seven year clean fuel-advanced technology rebate program in all CMAQ eligible counties to reduce emissions. |  | Statewide | 99 | Statewide Project |  | Exempt
C-4908 | Bike & Ped | Locally Selected | Various | Locations in Salisbury | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  |  |  | 1376000
C-4908A | Highway | Other | Horah Street | Brenner Avenue to Partee Street in Salisbury. | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO | PROJECT DELETED AT MPO REQUEST | Exempt
C-4908B | Bike & Ped | Pre-STI (Historic) | Various | Ryan Street to Celebration Drive and South Boundary Street from Hillsboro Street to Hills Street in Salisbury. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908C | Bike & Ped | Pre-STI (Historic) | Various | Various streets around Salisbury High School in Salisbury. | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908D | Bike & Ped | Locally Selected | Arlington Avenue | Salisbury. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908E | Highway | Transition | SR 1002 (Bringley Ferry Road) | Long Street to Newsome Road in Salisbury | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908F | Bike & Ped | Locally Selected | Newsome Road | SR 1002 (Bringle Ferry Road) to SR 1004 (Stokes Ferry Road) in Salisbury. | Construct sidewalks. |  | Rowan | 9 | Cabarrus-Rowan MPO | PROJECT DELETED AT MPO REQUEST | Exempt
C-4908G | Highway | Transition | US 70 (Statesville Boulevard) | US 601 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Exempt
C-4908H | Bike & Ped | Locally Selected | Main Street | D Avenue to Sunset Drive in Salisbury | Construct sidewalk. | 0.43 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Exempt
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | CMAQ | ENGINEERING | 795000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L(M) | ENGINEERING | 199000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | CMAQ | RIGHT-OF-WAY | 1070000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L(M) | RIGHT-OF-WAY | 268000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | CMAQ | CONSTRUCTION | 360000 | FY 2026: 360000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | BGANY | CONSTRUCTION | 3531000 | FY 2026: 3531000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 6509000 | FY 2026: 6509000
C-4928 | Bike & Ped | Transition | SR 1317 (Morreene Road) | Neal Road to SR 1320 (Erwin Road) in Durham. | Construct bike lanes and sidewalk. | 1.52 | Durham | 5 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L(M) | CONSTRUCTION | 2600000 | FY 2026: 2600000
C-4934 | Highway | Pre-STI (Historic) | NC 279 (New Hope Road) | Burtonwood Drive to SR 2466 (Garrison Boulevard) in Gastonia. | Construct turn lanes. | 0.53 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Exempt |  |  |  | 3917000
C-5166 | Bike & Ped | Locally Selected | NC 56 | Greenway along NC 56 in Creedmoor | Construct bike-pedestrian trail system. | 2.76 | Granville | 5 | Capital Area MPO | PROJECT COMPLETE BY TOWN OF CREEDMOOR; LET WITH EB-5513 | Exempt
C-5166A | Bike & Ped | Transition | NC 56 | Greenway in Creedmoor - Eastern section. | Construct bicycle-pedestrian trail system. | 1.61 | Granville | 5 | Capital Area MPO | PROJECT COMPLETE | Exempt
C-5166B | Bike & Ped | Locally Selected | NC 56 | Greenway in Creedmoor - Western section. | Construct bicycle-pedestrian trail system. | 1.15 | Granville | 5 | Capital Area MPO | PROJECT COMPLETE | Exempt
C-5168 | Bike & Ped | Locally Selected | Crabtree Creek Greenway | Various locations in Cary and Morrisville | Connect existing greenway and replace train trestle. | 1.85 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE | Exempt |  |  |  | 4247000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (North Estes Drive) | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  |  |  | 1149000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (North Estes Drive) | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | CMAQ | CONSTRUCTION | 3072000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (North Estes Drive) | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | BGDA | CONSTRUCTION | 1731000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (North Estes Drive) | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | BGDACV | CONSTRUCTION | 429000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (North Estes Drive) | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | L(M) | CONSTRUCTION | 275000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (North Estes Drive) | NC 86 (Martin Luther King Jr. Boulevard) to Caswell Drive in Chapel Hill; NC 86 (Martin Luther King Jr. Boulevard) to Elliott Road in Chapel Hill | Construct five foot sidewalks and five foot bike lanes; construct ten foot multi-use path. | 0.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | L | CONSTRUCTION | 926000
C-5181 | Bike & Ped | Transition | Jones Creek Greenway | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Orange | 7 | Triangle West TPO |  | Exempt |  |  |  | 100000
C-5181 | Bike & Ped | Transition | Jones Creek Greenway | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Orange | 7 | Triangle West TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 747000 | FY 2026: 747000
C-5181 | Bike & Ped | Transition | Jones Creek Greenway | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Orange | 7 | Triangle West TPO |  | Exempt |  | BGDA | CONSTRUCTION | 293000 | FY 2026: 293000
C-5181 | Bike & Ped | Transition | Jones Creek Greenway | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Orange | 7 | Triangle West TPO |  | Exempt |  | L(M) | CONSTRUCTION | 260000 | FY 2026: 260000
C-5181 | Bike & Ped | Transition | Jones Creek Greenway | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Orange | 7 | Triangle West TPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 10000
C-5181 | Bike & Ped | Transition | Jones Creek Greenway | Upper Bolin Trail to Twin Creeks Greenway in Carrboro. | Construct 100 foot bridge and 650 foot paved trail and implement program to support non-vehicle trips to Morris Grove Elementary School. | 0.12 | Orange | 7 | Triangle West TPO |  | Exempt |  | L(M) | IMPLEMENTATION | 2000
C-5183 | Bike & Ped | Locally Selected | Various | Locations in Durham | Construct sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  |  |  | 109000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (South Alston Avenue) | SR 1171 (Riddle Road) to Capps Street in Durham | Construct sidewalk. | 0.44 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 565000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (South Alston Avenue) | SR 1171 (Riddle Road) to Capps Street in Durham | Construct sidewalk. | 0.44 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 468000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (South Alston Avenue) | SR 1171 (Riddle Road) to Capps Street in Durham | Construct sidewalk. | 0.44 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Exempt |  | TADA | CONSTRUCTION | 403000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (South Alston Avenue) | SR 1171 (Riddle Road) to Capps Street in Durham | Construct sidewalk. | 0.44 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 359000
C-5184 | Bike & Ped | Transition | Riverwalk Trail | Along Eno River connecting River Park, Gold Park, and Occoneechee Mountain State Natural Area in Hillsborough. | Construct paved off-road trail and sidewalk to provide pedestrian and bicycle connections. | 2.17 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH | Exempt |  |  |  | 610000
C-5195 | Bike & Ped | Transition | Various | Locations in Claremont. | Construct sidewalk. |  | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION | Exempt |  |  |  | 395000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  |  |  | 8000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L(M) |  | 2000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | ENGINEERING | 400000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L(M) | ENGINEERING | 100000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | CMAQ | RIGHT-OF-WAY | 1405000 | FY 2026: 1405000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L(M) | RIGHT-OF-WAY | 351000 | FY 2026: 351000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | CMAQ | UTILITIES | 1100000 | FY 2026: 1100000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | CMAQ | CONSTRUCTION | 1992000 | FY 2027: 1992000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | CONSTRUCTION | 1990000 | FY 2027: 1990000
C-5196 | Highway | Transition | 16th Street (Sandy Ridge Road) | 21st Avenue NE intersection in Hickory. | Construct roundabout. |  | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L(M) | CONSTRUCTION | 996000 | FY 2027: 996000
C-5200 | Highway | Locally Selected | NC 115 | NC 150 intersection in Mooresville. | Construct southbound right turn lane on NC 115 and westbound shared through-right lane on NC 150. |  | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  |  |  | 1283000
C-5200 | Highway | Locally Selected | NC 115 | NC 150 intersection in Mooresville. | Construct southbound right turn lane on NC 115 and westbound shared through-right lane on NC 150. |  | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | BGDA | CONSTRUCTION | 1211000
C-5200 | Highway | Locally Selected | NC 115 | NC 150 intersection in Mooresville. | Construct southbound right turn lane on NC 115 and westbound shared through-right lane on NC 150. |  | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | L(M) | CONSTRUCTION | 303000
C-5505 | Bike & Ped | Transition | Rail Trail | SR 1923 (Woodlawn Avenue) to Belmont Abbey College and Downtown. | Upgrade abandoned railroad to pedestrian trail. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | IN PROGRESS | Exempt |  |  |  | 1900000
C-5529 | Highway | Locally Selected | NC 115 | Faith Road / Campus Lane intersection in Mooresville. | Realign Faith Road to tie into existing NC 115 / Campus Lane intersection. Construct dedicated turn lanes on Faith Road and Campus Lane at intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  |  |  | 1677000
C-5529 | Highway | Locally Selected | NC 115 | Faith Road / Campus Lane intersection in Mooresville. | Realign Faith Road to tie into existing NC 115 / Campus Lane intersection. Construct dedicated turn lanes on Faith Road and Campus Lane at intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | BGDA | ENGINEERING | 207000
C-5529 | Highway | Locally Selected | NC 115 | Faith Road / Campus Lane intersection in Mooresville. | Realign Faith Road to tie into existing NC 115 / Campus Lane intersection. Construct dedicated turn lanes on Faith Road and Campus Lane at intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | L(M) | ENGINEERING | 52000
C-5529 | Highway | Locally Selected | NC 115 | Faith Road / Campus Lane intersection in Mooresville. | Realign Faith Road to tie into existing NC 115 / Campus Lane intersection. Construct dedicated turn lanes on Faith Road and Campus Lane at intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 846000
C-5529 | Highway | Locally Selected | NC 115 | Faith Road / Campus Lane intersection in Mooresville. | Realign Faith Road to tie into existing NC 115 / Campus Lane intersection. Construct dedicated turn lanes on Faith Road and Campus Lane at intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 282000
C-5531 | Bike & Ped | Locally Selected | Various | SR 1148 (Kistler Farm Road); Briarcliff Road; Bellingham Drive; White Oak Road in Mooresville | Construct sidewalks. |  | Iredell | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  |  |  | 3552000
C-5531 | Bike & Ped | Locally Selected | Various | SR 1148 (Kistler Farm Road); Briarcliff Road; Bellingham Drive; White Oak Road in Mooresville | Construct sidewalks. |  | Iredell | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | BGDA | CONSTRUCTION | 641000
C-5531 | Bike & Ped | Locally Selected | Various | SR 1148 (Kistler Farm Road); Briarcliff Road; Bellingham Drive; White Oak Road in Mooresville | Construct sidewalks. |  | Iredell | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | L(M) | CONSTRUCTION | 160000
C-5534 | Highway | Transition | SR 4979 (Ballantyne Commons Parkway-McKee Road) | NC 16 (Providence Road) intersection in Charlotte. | Construct additional left turn lane on SR 4979 (Ballantyne Commons Parkway-McKee Road) and a second left turn lane on southbound NC 16. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | Exempt |  |  |  | 890000
C-5534 | Highway | Transition | SR 4979 (Ballantyne Commons Parkway-McKee Road) | NC 16 (Providence Road) intersection in Charlotte. | Construct additional left turn lane on SR 4979 (Ballantyne Commons Parkway-McKee Road) and a second left turn lane on southbound NC 16. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | Exempt |  | T(M) |  | 223000
C-5534 | Highway | Transition | SR 4979 (Ballantyne Commons Parkway-McKee Road) | NC 16 (Providence Road) intersection in Charlotte. | Construct additional left turn lane on SR 4979 (Ballantyne Commons Parkway-McKee Road) and a second left turn lane on southbound NC 16. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | Exempt |  | BGDA | CONSTRUCTION | 512000
C-5534 | Highway | Transition | SR 4979 (Ballantyne Commons Parkway-McKee Road) | NC 16 (Providence Road) intersection in Charlotte. | Construct additional left turn lane on SR 4979 (Ballantyne Commons Parkway-McKee Road) and a second left turn lane on southbound NC 16. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | Exempt |  | T(M) | CONSTRUCTION | 128000
C-5536 | Public Transportation (Transit) | Transition | Various | Mecklenburg County Air Quality - Grants to Replace Aging Diesel Engines (GRADE). | Replace, repower, or retrofit aging diesel vehicles and equipment. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  |  |  | 979000
C-5536 | Public Transportation (Transit) | Transition | Various | Mecklenburg County Air Quality - Grants to Replace Aging Diesel Engines (GRADE). | Replace, repower, or retrofit aging diesel vehicles and equipment. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | CMAQ | CONSTRUCTION | 139000
C-5538 | Highway | Locally Selected | SR 1662 (Tuckaseegee Road) | Berryhill Road / Thrift Road intersection in Charlotte. | Construct a roundabout. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  |  |  | 530000
C-5538 | Highway | Locally Selected | SR 1662 (Tuckaseegee Road) | Berryhill Road / Thrift Road intersection in Charlotte. | Construct a roundabout. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 2850000
C-5538 | Highway | Locally Selected | SR 1662 (Tuckaseegee Road) | Berryhill Road / Thrift Road intersection in Charlotte. | Construct a roundabout. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 826000
C-5546 | Highway | Transition | NC 43 / NC 48 (Benvenue Road) | Jeffrey's Road Intersection in Rocky Mount. | Construct intersection improvements. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  |  |  | 16000
C-5546 | Highway | Transition | NC 43 / NC 48 (Benvenue Road) | Jeffrey's Road Intersection in Rocky Mount. | Construct intersection improvements. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 104000 | FY 2026: 104000
C-5546 | Highway | Transition | NC 43 / NC 48 (Benvenue Road) | Jeffrey's Road Intersection in Rocky Mount. | Construct intersection improvements. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 26000 | FY 2026: 26000
C-5549 | Bike & Ped | Locally Selected | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  |  |  | 172000
C-5549 | Bike & Ped | Locally Selected | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CRPDA | RIGHT-OF-WAY | 160000 | FY 2026: 160000
C-5549 | Bike & Ped | Locally Selected | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2026: 40000
C-5549 | Bike & Ped | Locally Selected | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 688000 | FY 2027: 688000
C-5549 | Bike & Ped | Locally Selected | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 410000 | FY 2027: 410000
C-5549 | Bike & Ped | Locally Selected | NC 97 (Raleigh Street); SR 1613 (Winstead Avenue) | Kinchen Drive to Wilkins Street; Ridgecrest Drive to SR 1770 (Sunset Avenue) in Rocky Mount | Construct sidewalks. | 2.27 | Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 275000 | FY 2027: 275000
C-5555 | Bike & Ped | Pre-STI (Historic) | Various | Locations in Greensboro | Construct sidewalks. |  | Guilford | 7 | Greensboro Urban Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO | Exempt |  |  |  | 1029000
C-5555E | Bike & Ped | Locally Selected | Various | SR 1546 (College Road) and SR 2179 (New Garden Road) in Greensboro. | Construct sidewalks. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 200000
C-5555E | Bike & Ped | Locally Selected | Various | SR 1546 (College Road) and SR 2179 (New Garden Road) in Greensboro. | Construct sidewalks. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGDA | CONSTRUCTION | 722000
C-5555E | Bike & Ped | Locally Selected | Various | SR 1546 (College Road) and SR 2179 (New Garden Road) in Greensboro. | Construct sidewalks. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 231000
C-5558 | Highway | Other | Various | Routes in High Point. | Expand and upgrade signal system in High Point. |  | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | Exempt |  |  |  | 10232000
C-5600 | Highway | Other | Various | Locations statewide. | Statewide CMAQ projects to improve air quality within nonattainment and maintenance areas. |  | Statewide | 99 | Statewide Project |  | Exempt |  |  |  | 41540000
C-5600E | Highway | Other | I-85 | Guilford County | Extend traffic management system. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1312000 | FY 2026: 262000
C-5600E | Highway | Other | I-85 | Guilford County | Extend traffic management system. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | T(M) | CONSTRUCTION | 349000 | FY 2026: 70000
C-5600U | Highway | Other | I-85 | Triad Traffic Management Center | Upgrade traffic management center. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1318000
C-5600U | Highway | Other | I-85 | Triad Traffic Management Center | Upgrade traffic management center. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | T(M) | CONSTRUCTION | 330000
C-5600VA | Rail | Other | Queen City Express | Wilmington to Charlotte | Subsidy for intermodal rail service between Port of Wilmington and Charlotte. |  | Statewide | 99 | Statewide Project |  | Exempt |  | CMAQ | OTHER | 250000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | ENGINEERING | 15000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | ENGINEERING | 3000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 15000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 3000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 78000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | CONSTRUCTION | 21000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 15000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 3000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | OPERATIONS | 15000
C-5602 | Highway | Other | Various | Locations in Burlington-Graham MPO. | Improve congestion and air quality. |  | Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | OPERATIONS | 3000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  |  |  | 1590000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 246000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 63000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 246000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 63000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1479000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 369000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 246000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 63000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 246000
C-5603 | Highway | Other | Various | Locations in the Cabarrus-Rowan MPO. | Improve congestion and air quality. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 63000
C-5603D | Highway | Other | SR 1002 (Old Concord Road) | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 28000
C-5603D | Highway | Other | SR 1002 (Old Concord Road) | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 7000
C-5603D | Highway | Other | SR 1002 (Old Concord Road) | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 31000
C-5603D | Highway | Other | SR 1002 (Old Concord Road) | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 8000
C-5603D | Highway | Other | SR 1002 (Old Concord Road) | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1560000 | FY 2026: 1560000
C-5603D | Highway | Other | SR 1002 (Old Concord Road) | Ryan Street to SR 1007 (Jake Alexander Boulevard) | Construct sidewalk. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 390000 | FY 2026: 390000
C-5603F | Highway | Other | SR 1643 (Bethpage Road) | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 208000
C-5603F | Highway | Other | SR 1643 (Bethpage Road) | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 52000
C-5603F | Highway | Other | SR 1643 (Bethpage Road) | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 94000 | FY 2026: 94000
C-5603F | Highway | Other | SR 1643 (Bethpage Road) | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 23000 | FY 2026: 23000
C-5603F | Highway | Other | SR 1643 (Bethpage Road) | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1892000 | FY 2026: 1892000
C-5603F | Highway | Other | SR 1643 (Bethpage Road) | SR 1008 (South Main Street) to Leonard Avenue, and Westgreen Drive to Klondale Avenue in Kannapolis. | Construct sidewalk. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 473000 | FY 2026: 473000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | ENGINEERING | 44000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | ENGINEERING | 11000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | RIGHT-OF-WAY | 12000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | UTILITIES | 220000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | UTILITIES | 55000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | CONSTRUCTION | 970000 | FY 2026: 970000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CRPANY | CONSTRUCTION | 305000 | FY 2026: 305000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | CONSTRUCTION | 243000 | FY 2026: 243000
C-5603H | Highway | Other | Brenner Avenue | SR 2094 (Statesville Boulevard) to West Horah Street, and at Link Avenue in Salisbury. | Construct sidewalks and add turn lanes at Link Avenue. |  | Rowan | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L | CONSTRUCTION | 76000 | FY 2026: 76000
C-5603I | Highway | Other | US 601 | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | ENGINEERING | 400000
C-5603I | Highway | Other | US 601 | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | ENGINEERING | 100000
C-5603I | Highway | Other | US 601 | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2026: 200000
C-5603I | Highway | Other | US 601 | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | RIGHT-OF-WAY | 50000 | FY 2026: 50000
C-5603I | Highway | Other | US 601 | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | CONSTRUCTION | 3905000 | FY 2026: 3905000
C-5603I | Highway | Other | US 601 | SR 1132 (Flowes Store Road) to SR 1153 (Zion Church Road), and SR 1132 (Flowes Store Road) intersection in Concord. | Construct sidewalks and intersection improvements. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | CONSTRUCTION | 976000 | FY 2026: 976000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  |  |  | 18097000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 951000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 237000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 951000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 237000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 18897000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 4725000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 951000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 237000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 951000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | BGDA | OPERATIONS | 414000
C-5604 | Highway | Other | Various | Locations in Capital Area MPO. | Improve congestion and air quality. |  | Wake, Johnston, Franklin, Granville | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 340000
C-5604HA | Highway | Other | Mingo Creek Greenway | Existing Greenway to Knightdale Station Park in Knightdale. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | RIGHT-OF-WAY | 538000
C-5604HA | Highway | Other | Mingo Creek Greenway | Existing Greenway to Knightdale Station Park in Knightdale. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | RIGHT-OF-WAY | 134000
C-5604HA | Highway | Other | Mingo Creek Greenway | Existing Greenway to Knightdale Station Park in Knightdale. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 2745000
C-5604HA | Highway | Other | Mingo Creek Greenway | Existing Greenway to Knightdale Station Park in Knightdale. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 686000
C-5604ID | Highway | Other | Higgins Greenway | Higgins Greenway in Cary. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 1520000
C-5604ID | Highway | Other | Higgins Greenway | Higgins Greenway in Cary. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 380000
C-5604ID | Highway | Other | Higgins Greenway | Higgins Greenway in Cary. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 999000
C-5604ID | Highway | Other | Higgins Greenway | Higgins Greenway in Cary. | Improve congestion and air quality. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 250000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  |  |  | 2845000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 357000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 90000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 357000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 90000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 4392000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 1098000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 925000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 232000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 357000
C-5605 | Highway | Other | Various | Locations in Durham / Chapel Hill / Carrboro MPO. | Improve congestion and air quality. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 90000
C-5605H | Highway | Other | Various | Locations in Durham | Design and install pedestrian and vehicle wayfinding signage for points of interest and parking. |  | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 787000
C-5605H | Highway | Other | Various | Locations in Durham | Design and install pedestrian and vehicle wayfinding signage for points of interest and parking. |  | Durham | 5 | Triangle West TPO |  | Exempt |  | L(M) | CONSTRUCTION | 197000
C-5606 | Highway | Other | Various | Locations in Gaston-Cleveland-Lincoln MPO. | Improve congestion and air quality. |  | Gaston, Cleveland, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | "HF" FUNDS ON SEGMENT I REPRESENT CONTIGENCY FUNDS | Exempt
C-5606B | Bike & Ped | Locally Selected | NC 161 | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | CMAQ | ENGINEERING | 171000
C-5606B | Bike & Ped | Locally Selected | NC 161 | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | L(M) | ENGINEERING | 43000
C-5606B | Bike & Ped | Locally Selected | NC 161 | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | CMAQ | RIGHT-OF-WAY | 4000 | FY 2026: 4000
C-5606B | Bike & Ped | Locally Selected | NC 161 | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | L(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
C-5606B | Bike & Ped | Locally Selected | NC 161 | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | CMAQ | CONSTRUCTION | 423000 | FY 2026: 423000
C-5606B | Bike & Ped | Locally Selected | NC 161 | South 13th Street to South 14th Street in Bessemer City. | Construct sidewalks with crosswalks. | 0.47 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | L(M) | CONSTRUCTION | 106000 | FY 2026: 106000
C-5606D | Bike & Ped | Locally Selected | Various | Locations along US 321 Business and NC 275 / NC 279 near Gaston College | Construct sidewalks. Install crosswalk across NC 275 / NC 279. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $383,779. | Exempt |  | CMAQ | CONSTRUCTION | 314000
C-5606D | Bike & Ped | Locally Selected | Various | Locations along US 321 Business and NC 275 / NC 279 near Gaston College | Construct sidewalks. Install crosswalk across NC 275 / NC 279. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $383,779. | Exempt |  | L(M) | CONSTRUCTION | 79000
C-5606E | Bike & Ped | Locally Selected | New Route | Technology Park to Gaston College near Gastonia. | Construct greenway. | 0.63 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $513,300. | Exempt |  | CMAQ | CONSTRUCTION | 470000
C-5606E | Bike & Ped | Locally Selected | New Route | Technology Park to Gaston College near Gastonia. | Construct greenway. | 0.63 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $513,300. | Exempt |  | L(M) | CONSTRUCTION | 118000
C-5606I | Bike & Ped | Locally Selected | NC 27 | Locations along NC 27 in Lincolnton | Construct sidewalks in gaps. | 0.09 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | CMAQ | CONSTRUCTION | 358000
C-5606I | Bike & Ped | Locally Selected | NC 27 | Locations along NC 27 in Lincolnton | Construct sidewalks in gaps. | 0.09 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | L(M) | CONSTRUCTION | 92000
C-5606I | Bike & Ped | Locally Selected | NC 27 | Locations along NC 27 in Lincolnton | Construct sidewalks in gaps. | 0.09 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | HF | CONSTRUCTION | 250000
C-5606J | Bike & Ped | Locally Selected | SR 2201 (Lowell Spencer Mountain Road) | George Poston Parkway to end of park limits near Gastonia. | Construct sidewalk. | 0.26 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $334,379. | Exempt |  | CMAQ | CONSTRUCTION | 149000 | FY 2026: 149000
C-5606J | Bike & Ped | Locally Selected | SR 2201 (Lowell Spencer Mountain Road) | George Poston Parkway to end of park limits near Gastonia. | Construct sidewalk. | 0.26 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $334,379. | Exempt |  | L(M) | CONSTRUCTION | 37000 | FY 2026: 37000
C-5606K | Bike & Ped | Locally Selected | New Route | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | CMAQ | ENGINEERING | 220000
C-5606K | Bike & Ped | Locally Selected | New Route | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | L(M) | ENGINEERING | 55000
C-5606K | Bike & Ped | Locally Selected | New Route | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | CMAQ | RIGHT-OF-WAY | 12000 | FY 2026: 12000
C-5606K | Bike & Ped | Locally Selected | New Route | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | L(M) | RIGHT-OF-WAY | 3000 | FY 2026: 3000
C-5606K | Bike & Ped | Locally Selected | New Route | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | CMAQ | CONSTRUCTION | 1256000 | FY 2026: 1256000
C-5606K | Bike & Ped | Locally Selected | New Route | Rankin Lake to Tech Park Greenway near Gastonia. | Construct greenway. | 0.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | L(M) | CONSTRUCTION | 314000 | FY 2026: 314000
C-5606M | Bike & Ped | Locally Selected | SR 2400 (Neal Hawkins Road) | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | CMAQ | ENGINEERING | 382000
C-5606M | Bike & Ped | Locally Selected | SR 2400 (Neal Hawkins Road) | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | L(M) | ENGINEERING | 95000
C-5606M | Bike & Ped | Locally Selected | SR 2400 (Neal Hawkins Road) | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | CMAQ | RIGHT-OF-WAY | 15000 | FY 2026: 15000
C-5606M | Bike & Ped | Locally Selected | SR 2400 (Neal Hawkins Road) | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2026: 4000
C-5606M | Bike & Ped | Locally Selected | SR 2400 (Neal Hawkins Road) | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | CMAQ | CONSTRUCTION | 1091000 | FY 2027: 1091000
C-5606M | Bike & Ped | Locally Selected | SR 2400 (Neal Hawkins Road) | Existing sidewalk at Marth Rivers Park to existing sidewalk at Village of Parkside; South of SR 2420 (Forbes Road) intersection; South of SR 2420 (Forbes Road) intersection to Hawk Ridge Drive near Gastonia. | Construct sidewalk on south side of Neal Hawkins Road; Construct mid-block crossing; Construct sidewalk on north side of Neal Hawkins Road. | 1.82 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | L(M) | CONSTRUCTION | 273000 | FY 2027: 273000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 288000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 72000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 288000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 72000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1722000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 432000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 288000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 72000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | OPERATIONS | 288000
C-5607 | Highway | Other | Various | Locations in Greensboro Urban Area MPO. | Improve congestion and air quality. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | L(M) | OPERATIONS | 72000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  |  |  | 1023000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 41000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 10000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 41000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 10000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 242000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 61000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 41000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 10000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 41000
C-5608 | Highway | Other | Various | Locations in Hickory MPO. | Improve congestion and air quality. |  | Catawba | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 10000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  |  |  | 105000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 195000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 48000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 195000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 48000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1164000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 291000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 195000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 48000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 195000
C-5609 | Highway | Other | Various | Locations in High Point MPO. | Improve congestion and air quality. |  | Davidson, Guilford, Forsyth | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 48000
C-5609F | Highway | Other | SR 1352 (Oakdale Road) | Chimney Court to Jamestown Oaks Drive in Jamestown. | Construct sidewalks and pedestrian improvements. |  | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 32000 | FY 2026: 32000
C-5609F | Highway | Other | SR 1352 (Oakdale Road) | Chimney Court to Jamestown Oaks Drive in Jamestown. | Construct sidewalks and pedestrian improvements. |  | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 8000 | FY 2026: 8000
C-5609F | Highway | Other | SR 1352 (Oakdale Road) | Chimney Court to Jamestown Oaks Drive in Jamestown. | Construct sidewalks and pedestrian improvements. |  | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 440000 | FY 2026: 440000
C-5609F | Highway | Other | SR 1352 (Oakdale Road) | Chimney Court to Jamestown Oaks Drive in Jamestown. | Construct sidewalks and pedestrian improvements. |  | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 110000 | FY 2026: 110000
C-5609L | Highway | Other | Various | Locations in High Point MPO. | Construct sidewalks. |  | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | HSIP | ENGINEERING | 50000 | FY 2026: 50000
C-5609L | Highway | Other | Various | Locations in High Point MPO. | Construct sidewalks. |  | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 76000
C-5609L | Highway | Other | Various | Locations in High Point MPO. | Construct sidewalks. |  | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 19000
C-5609L | Highway | Other | Various | Locations in High Point MPO. | Construct sidewalks. |  | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1488000 | FY 2026: 1488000
C-5609L | Highway | Other | Various | Locations in High Point MPO. | Construct sidewalks. |  | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 372000 | FY 2026: 372000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  |  |  | 254000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 84000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 21000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 84000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 21000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 495000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 123000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 84000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 21000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 84000
C-5610 | Highway | Other | Various | Locations in Kerr-Tar RPO. | Improve congestion and air quality. |  | Granville, Franklin, Person | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 21000
C-5610B | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1646 (East Industry Drive) | 250 feet west of the intersection of US 15 (Lewis Street) and SR 1646 (East Industry Drive) to Speed EEZ Carwash driveway | Construct sidewalk. | 0.85 | Granville | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 769000
C-5610B | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1646 (East Industry Drive) | 250 feet west of the intersection of US 15 (Lewis Street) and SR 1646 (East Industry Drive) to Speed EEZ Carwash driveway | Construct sidewalk. | 0.85 | Granville | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | CONSTRUCTION | 192000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | Smoke Tree Way, North Main Street, Hospital Drive | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 118000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | Smoke Tree Way, North Main Street, Hospital Drive | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | ENGINEERING | 30000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | Smoke Tree Way, North Main Street, Hospital Drive | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 126000 | FY 2026: 126000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | Smoke Tree Way, North Main Street, Hospital Drive | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 31000 | FY 2026: 31000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | Smoke Tree Way, North Main Street, Hospital Drive | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 440000 | FY 2026: 440000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | Smoke Tree Way, North Main Street, Hospital Drive | Smoke Tree Way in Louisburg. | Construct 2245 feet of sidewalk. Projects to improve congestion and air quality in the Kerr-Tar RPO. |  | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | CONSTRUCTION | 110000 | FY 2026: 110000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  |  |  | 162000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 3000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 1000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 3000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 1000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 15000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 4000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 3000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 1000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 3000
C-5612 | Highway | Other | Various | Locations in Land of Sky and Southwestern RPO. | Improve congestion and air quality. |  | Haywood, Swain | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 1000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  |  |  | 6304000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | ENGINEERING | 414000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | ENGINEERING | 104000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 414000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | RIGHT-OF-WAY | 104000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | CONSTRUCTION | 2486000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | CONSTRUCTION | 622000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | IMPLEMENTATION | 414000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | IMPLEMENTATION | 104000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | OPERATIONS | 414000
C-5613 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) Area. | Improve congestion and air quality. |  | Mecklenburg, Iredell, Union | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | OPERATIONS | 104000
C-5613BD | Highway | Locally Selected | SR 1138 (Arrowood Road) | NC 49 (South Tryon) to South Boulevard. | Install ITS upgrades. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | CMAQ | CONSTRUCTION | 485000
C-5613BD | Highway | Locally Selected | SR 1138 (Arrowood Road) | NC 49 (South Tryon) to South Boulevard. | Install ITS upgrades. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L(M) | CONSTRUCTION | 129000
C-5613BE | Highway | Locally Selected | SR 2467 (Mallard Creek Road) | NC 24 (Harris Boulevard) to Governor Hunt Road. | Install ITS and traffic management upgrades. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | CMAQ | CONSTRUCTION | 158000
C-5613BE | Highway | Locally Selected | SR 2467 (Mallard Creek Road) | NC 24 (Harris Boulevard) to Governor Hunt Road. | Install ITS and traffic management upgrades. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L(M) | CONSTRUCTION | 42000
C-5613J | Highway | Locally Selected | NC 115 | Hickory Street intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | CMAQ | RIGHT-OF-WAY | 350000 | FY 2026: 300000
C-5613J | Highway | Locally Selected | NC 115 | Hickory Street intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | L(M) | RIGHT-OF-WAY | 325000 | FY 2026: 300000
C-5613J | Highway | Locally Selected | NC 115 | Hickory Street intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | CMAQ | CONSTRUCTION | 822000 | FY 2026: 822000
C-5613J | Highway | Locally Selected | NC 115 | Hickory Street intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | BGDA | CONSTRUCTION | 1121000 | FY 2026: 1121000
C-5613J | Highway | Locally Selected | NC 115 | Hickory Street intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | L(M) | CONSTRUCTION | 1526000 | FY 2026: 1526000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | ENGINEERING | 9000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | L(M) | ENGINEERING | 3000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 9000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 3000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 45000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | L(M) | CONSTRUCTION | 12000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 9000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | L(M) | IMPLEMENTATION | 3000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | OPERATIONS | 9000
C-5614 | Highway | Other | Various | Locations in Northwestern Piedmont RPO. | Improve congestion and air quality. |  | Davie | 9 | Northwest Piedmont RPO |  | Exempt |  | L(M) | OPERATIONS | 3000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 92000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 24000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 92000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 24000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 728000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 182000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 92000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 24000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | OPERATIONS | 92000
C-5616 | Highway | Other | Various | Locations in Rocky Mount MPO. | Improve congestion and air quality. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | OPERATIONS | 24000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  |  |  | 127000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | CMAQ | ENGINEERING | 5000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | L(M) | ENGINEERING | 1000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 5000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 1000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 30000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | L(M) | CONSTRUCTION | 8000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 5000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | L(M) | IMPLEMENTATION | 1000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | CMAQ | OPERATIONS | 5000
C-5617 | Highway | Other | Various | Locations in Rocky River RPO. | Improve congestion and air quality. |  | Union | 10 | Rocky River RPO |  | Exempt |  | L(M) | OPERATIONS | 1000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | ENGINEERING | 36000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 9000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 36000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 9000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 204000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 51000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 36000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | L(M) | IMPLEMENTATION | 9000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | OPERATIONS | 36000
C-5618 | Highway | Other | Various | Locations in Triangle Area RPO. | Improve congestion and air quality. |  | Chatham, Orange | 7, 8 | Central Pines RPO |  | Exempt |  | L(M) | OPERATIONS | 9000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  |  |  | 40000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | ENGINEERING | 335000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 85000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 335000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 85000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1995000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 500000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 335000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | IMPLEMENTATION | 85000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | OPERATIONS | 335000
C-5619 | Highway | Other | Various | Locations in Upper Coastal Plain RPO. | Improve congestion and air quality. |  | Johnston, Edgecombe, Nash | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | OPERATIONS | 85000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  |  |  | 2221000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 291000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 75000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 291000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 75000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 4266000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 1065000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 291000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 75000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 291000
C-5620 | Highway | Other | Various | Locations in Winston-Salem TPO. | Improve congestion and air quality. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 75000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | CMAQ | ENGINEERING | 1533000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | BA | ENGINEERING | 333000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | ENGINEERING | 50000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | CMAQ | RIGHT-OF-WAY | 4946000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | BA | RIGHT-OF-WAY | 785000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | RIGHT-OF-WAY | 452000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | CMAQ | CONSTRUCTION | 7474000 | FY 2026: 667000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | BGDA | CONSTRUCTION | 4861000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | CONSTRUCTION | 9618000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (Catawba Avenue) in Cornelius. | Construct roundabouts. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | T(M) | CONSTRUCTION | 1870000 | FY 2026: 167000
C-5622 | Bike & Ped | Locally Selected | Highland Branch Greenway | Sims Legion Park to Bulb Avenue in Gastonia. | Construct greenway. | 0.62 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $1,068,204. | Exempt |  | CMAQ | CONSTRUCTION | 1068000
C-5622 | Bike & Ped | Locally Selected | Highland Branch Greenway | Sims Legion Park to Bulb Avenue in Gastonia. | Construct greenway. | 0.62 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $1,068,204. | Exempt |  | L(M) | CONSTRUCTION | 267000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  |  |  | 270000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGANY | ENGINEERING | 8000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 2000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2026: 100000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 25000 | FY 2026: 25000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | CMAQ | CONSTRUCTION | 1000000 | FY 2027: 1000000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGANY | CONSTRUCTION | 736000 | FY 2027: 736000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (Smith Level Road / South Greensboro Street) | Public Works Drive to East/West Main Street in Carrboro | Construct sidewalk on one side of street. | 0.24 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 940000 | FY 2027: 940000
C-5700 | Bike & Ped | Locally Selected | SR 1352 (Oakdale Road) | Existing sidewalk east of East Main Street to Chimney Court in Jamestown | Extend sidewalk. | 0.53 | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  |  |  | 40000
C-5700 | Bike & Ped | Locally Selected | SR 1352 (Oakdale Road) | Existing sidewalk east of East Main Street to Chimney Court in Jamestown | Extend sidewalk. | 0.53 | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
C-5700 | Bike & Ped | Locally Selected | SR 1352 (Oakdale Road) | Existing sidewalk east of East Main Street to Chimney Court in Jamestown | Extend sidewalk. | 0.53 | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 2000
C-5700 | Bike & Ped | Locally Selected | SR 1352 (Oakdale Road) | Existing sidewalk east of East Main Street to Chimney Court in Jamestown | Extend sidewalk. | 0.53 | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 136000
C-5700 | Bike & Ped | Locally Selected | SR 1352 (Oakdale Road) | Existing sidewalk east of East Main Street to Chimney Court in Jamestown | Extend sidewalk. | 0.53 | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 34000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  |  |  | 2761000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | CMAQ | RIGHT-OF-WAY | 256000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | L(M) | RIGHT-OF-WAY | 68000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | CMAQ | CONSTRUCTION | 1912000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | BGDA | CONSTRUCTION | 157000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | BA | CONSTRUCTION | 650000
C-5701 | Highway | Locally Selected | NC 801 | NC 150 intersection in Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | L(M) | CONSTRUCTION | 517000
C-5702 | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program, including emissions-reducing sub-awards, in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project |  | Exempt |  |  |  | 2994000
C-5702A | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Exempt
C-5702B | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Exempt
C-5702C | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project |  | Exempt
C-5702D | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project |  | Exempt |  | CMAQ | IMPLEMENTATION | 12018000
C-5702D | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project |  | Exempt |  | L(M) | IMPLEMENTATION | 3005000
C-5702E | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. Including education and outreach. |  | Statewide | 99 | Statewide Project |  | Exempt |  | CMAQ | IMPLEMENTATION | 8067000 | FY 2026: 3600000
C-5702E | Highway | Other | North Carolina Clean Energy Technology Center | Systemwide | Conduct emissions-reducing sub-awards in all CMAQ-eligible counties. Including education and outreach. |  | Statewide | 99 | Statewide Project |  | Exempt |  | L(M) | IMPLEMENTATION | 2017000 | FY 2026: 900000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  |  |  | 2120000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | CMAQ | RIGHT-OF-WAY | 600000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | L(M) | RIGHT-OF-WAY | 11000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | T(M) | RIGHT-OF-WAY | 139000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | CMAQ | CONSTRUCTION | 9081000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | L(M) | CONSTRUCTION | 319000
C-5703 | Highway | Other | Gastonia | Citywide. | Upgrade citywide signal system. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | T(M) | CONSTRUCTION | 1963000
C-5704 | Bike & Ped | Locally Selected | Cramerton-McAdenville Greenway Connector | Paved trail at South Fork Village in Cramerton to Riverside Drive in McAdenville, following South Fork of Catawba River. | Construct greenway. | 0.37 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | ENGINEERING | 66000
C-5704 | Bike & Ped | Locally Selected | Cramerton-McAdenville Greenway Connector | Paved trail at South Fork Village in Cramerton to Riverside Drive in McAdenville, following South Fork of Catawba River. | Construct greenway. | 0.37 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CRPDA | ENGINEERING | 187000
C-5704 | Bike & Ped | Locally Selected | Cramerton-McAdenville Greenway Connector | Paved trail at South Fork Village in Cramerton to Riverside Drive in McAdenville, following South Fork of Catawba River. | Construct greenway. | 0.37 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L(M) | ENGINEERING | 64000
C-5704 | Bike & Ped | Locally Selected | Cramerton-McAdenville Greenway Connector | Paved trail at South Fork Village in Cramerton to Riverside Drive in McAdenville, following South Fork of Catawba River. | Construct greenway. | 0.37 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | CONSTRUCTION | 930000 | FY 2026: 930000
C-5704 | Bike & Ped | Locally Selected | Cramerton-McAdenville Greenway Connector | Paved trail at South Fork Village in Cramerton to Riverside Drive in McAdenville, following South Fork of Catawba River. | Construct greenway. | 0.37 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L(M) | CONSTRUCTION | 233000 | FY 2026: 233000
EB-3314 | Bike & Ped | Pre-STI (Historic) | Various | Locations statewide | Statewide pedestrian facilities program. |  | Statewide | 99 | Statewide Project | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 6476000
EB-4020 | Bike & Ped | Locally Selected | Brushy Fork Greenway | Waterworks Road to Reynolds Park Road in Winston-Salem | Construct paved multi-use trail. | 2.2 | Forsyth | 9 | Winston-Salem Area TPO |  | Pre-STI (Transition) |  |  |  | 1473000
EB-4020A | Bike & Ped | Locally Selected | Brushy Fork Greenway | Waterworks Road to Old Greensboro Road | Construct paved multi-use trail. |  | Forsyth | 9 | Winston-Salem Area TPO | COMPLETE
EB-4020B | Bike & Ped | Locally Selected | Brushy Fork Greenway | Old Greensboro Road to Lowery Street | Construct paved multi-use trail. |  | Forsyth | 9 | Winston-Salem Area TPO | COMPLETE
EB-4020C | Bike & Ped | Transition | Brushy Fork Greenway | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | BGANY | ENGINEERING | 500000 | FY 2026: 500000
EB-4020C | Bike & Ped | Transition | Brushy Fork Greenway | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | L(M) | ENGINEERING | 125000 | FY 2026: 125000
EB-4020C | Bike & Ped | Transition | Brushy Fork Greenway | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | BGANY | UTILITIES | 155000 | FY 2026: 155000
EB-4020C | Bike & Ped | Transition | Brushy Fork Greenway | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | L(M) | UTILITIES | 39000 | FY 2026: 39000
EB-4020C | Bike & Ped | Transition | Brushy Fork Greenway | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 1943000 | FY 2027: 1943000
EB-4020C | Bike & Ped | Transition | Brushy Fork Greenway | Lowery Street to Reynolds Park Road | Construct paved multi-use trail. | 0.53 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 486000 | FY 2027: 486000
EB-4539 | Bike & Ped | Pre-STI (Historic) | Cape Fear River Greenway | Clark Park to the Cape Fear Botanical Gardens in Fayetteville | Construct second phase of an off-road multi-use trail. |  | Cumberland | 6 | Fayetteville Area MPO |  | Pre-STI (Transition) |  |  |  | 2600000
EB-4539A | Bike & Ped | Pre-STI (Historic) | Cape Fear River Greenway | Clark Park South to the Cape Fear Botanical Gardens. I-95 Business / US 301 to the south side of CSX rail line. | Construct second phase of an off-road multi-use trail. | 1.23 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
EB-4539BB | Bike & Ped | Pre-STI (Historic) | Cape Fear River Greenway | Clark Park South to the Cape Fear Botanical Gardens. Existing trail at Clark Park to the north side of CSX rail line | Construct second phase of an off-road multi-use trail. | 1.26 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
EB-4539BC | Bike & Ped | Pre-STI (Historic) | Cape Fear River Greenway | North of CSX rail line to south of CSX rail line in Fayetteville. | Construct second phase of an off-road multi-use trail. | 0.27 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | TAANY | CONSTRUCTION | 761000
EB-4539BC | Bike & Ped | Pre-STI (Historic) | Cape Fear River Greenway | North of CSX rail line to south of CSX rail line in Fayetteville. | Construct second phase of an off-road multi-use trail. | 0.27 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 190000
EB-4707 | Bike & Ped | Pre-STI (Historic) | SR 2220 (Old Chapel Hill Road) SR 1838 (Old Durham Road) | US 15 / US 501 in Orange County to SR 1116 (Garrett Road) in Durham County | Construct bicycle, pedestrian, and transit improvements and roundabout. | 2.7 | Durham, Orange | 5, 7 | Triangle West TPO |  | Pre-STI (Transition) |  |  |  | 13348000
EB-4707A | Highway | Transition | SR 1838 (Old Durham) / SR 2220 (Old Chapel Hill Road) | US 15 / US 501 in Orange County to SR 1113 (Pope Road) in Durham County. | Construct bicycle, pedestrian, and transit improvements and construct roundabout. | 1 | Orange, Durham | 5, 7 | Triangle West TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
EB-4707B | Highway | Transition | SR 2220 (Old Chapel Hill Road) | SR 1113 (Pope Road) to SR 1116 (Garrett Road). | Construct bicycle, pedestrian, and transit improvements and construct roundabout. | 2.63 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
EB-5517 | Bike & Ped | Transition | New Pedestrian Bridge And Approaches | Existing sidewalk to Piedmont Environmental Center entrance in High Point and Jamestown | Construct pedestrian bridge over east fork of Deep River. | 0.5 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN | Pre-STI (Transition) |  |  |  | 1200000
EB-5518 | Bike & Ped | Transition | Latham Park Greenway | Battleground Avenue to Mendenhall Street in Greensboro | Remove through lane on Hill Street and construct multi-use path. | 0.11 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | Pre-STI (Transition) |  |  |  | 562000
EB-5519 | Bike & Ped | Transition | SR 4121 (East Main Street) | Existing sidewalk near Jamestown Municipal Building to Yorkleigh Lane near Guilford Technical Community College Jamestown Campus / Ragsdale High School complex in Jamestown | Construct sidewalk. | 0.57 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN | Pre-STI (Transition) |  |  |  | 1062000
EB-5521 | Bike & Ped | Transition | NC 134 (North Main Street); SR 1005 (South Main Street) | SR 1323 (Okeewemee Road) to Barnhill Street in Troy | Construct sidewalks. | 2.37 | Montgomery | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION BY TOWN OF TROY | Pre-STI (Transition) |  |  |  | 1330000
EB-5521 | Bike & Ped | Transition | NC 134 (North Main Street); SR 1005 (South Main Street) | SR 1323 (Okeewemee Road) to Barnhill Street in Troy | Construct sidewalks. | 2.37 | Montgomery | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION BY TOWN OF TROY | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 1760000 | FY 2026: 1760000
EB-5521 | Bike & Ped | Transition | NC 134 (North Main Street); SR 1005 (South Main Street) | SR 1323 (Okeewemee Road) to Barnhill Street in Troy | Construct sidewalks. | 2.37 | Montgomery | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION BY TOWN OF TROY | Pre-STI (Transition) |  | T | CONSTRUCTION | 440000 | FY 2026: 440000
EB-5531 | Bike & Ped | Transition | 12th Street; Yellow Jacket Lane / SR 1446 (Bess Town Road) | Chadwick Court to Kaiser Road; 12th Street to 14th Street (NC 274) in Bessemer City | Construct sidewalks. | 0.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 240000 | FY 2026: 240000
EB-5531 | Bike & Ped | Transition | 12th Street; Yellow Jacket Lane / SR 1446 (Bess Town Road) | Chadwick Court to Kaiser Road; 12th Street to 14th Street (NC 274) in Bessemer City | Construct sidewalks. | 0.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 60000 | FY 2026: 60000
EB-5533 | Bike & Ped | Transition | Gastonia | Poston Park to South Fork River Greenway in Gastonia. | Construct trail. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 875000
EB-5539 | Bike & Ped | Transition | South Tar River Greenway | Pitt Street to Nash Street in Greenville. | Construct greenway using existing sidewalks, roads and on new location along the river. | 0.89 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  |  |  | 2984000
EB-5540 | Bike & Ped | STI (Prioritization) | Little Cross Creek Greenway Extension | Filter Plant Drive to Rowan Street bridge in Fayetteville | Construct multi-use path. | 0.75 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 75000
EB-5540 | Bike & Ped | STI (Prioritization) | Little Cross Creek Greenway Extension | Filter Plant Drive to Rowan Street bridge in Fayetteville | Construct multi-use path. | 0.75 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | CONSTRUCTION | 600000 | FY 2027: 600000
EB-5540 | Bike & Ped | STI (Prioritization) | Little Cross Creek Greenway Extension | Filter Plant Drive to Rowan Street bridge in Fayetteville | Construct multi-use path. | 0.75 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 150000 | FY 2027: 150000
EB-5541 | Bike & Ped | Locally Selected | Big Cross Creek Greenway. | Little Cross Creek to I-295. | Construct multi-use path. |  | Cumberland | 6 | Fayetteville Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS. | Not Funded |  |  |  | 720000
EB-5547 | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Existing Flat Creek Greenway Trailhead north of US 70 to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.991M. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.915M. | Division 13 |  |  |  | 866000
EB-5547A | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to Flat Creek Greenway in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | ENGINEERING | 232000
EB-5547A | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to Flat Creek Greenway in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | ENGINEERING | 58000
EB-5547A | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to Flat Creek Greenway in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 1279000 | FY 2026: 44000; FY 2027: 1235000
EB-5547A | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to Flat Creek Greenway in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 320000 | FY 2026: 320000
EB-5547B | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | ENGINEERING | 147000
EB-5547B | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | ENGINEERING | 37000
EB-5547B | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 16000
EB-5547B | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 4000
EB-5547B | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 1241000 | FY 2026: 12000; FY 2027: 1229000
EB-5547B | Bike & Ped | Locally Selected | Black Mountain Riverwalk Greenway | Black Mountain Avenue to the Oaks Trail in Black Mountain | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 310000 | FY 2026: 310000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGANY | ENGINEERING | 120000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | ENGINEERING | 30000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGANY | RIGHT-OF-WAY | 24000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | RIGHT-OF-WAY | 6000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGANY | CONSTRUCTION | 590000 | FY 2027: 590000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGDA | CONSTRUCTION | 2400000 | FY 2027: 2400000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (South 17th Street) | Harbour Drive to Shipyard Boulevard in Wilmington. | Construct multi-use path. | 1.76 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | CONSTRUCTION | 748000 | FY 2027: 748000
EB-5619 | Bike & Ped | Other | Grants Creek Greenway | Kelsey Scott Park to Catawba College in Salisbury | Construct multi-use path. |  | Rowan | 9 | Cabarrus-Rowan MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SALISBURY | Division 9 |  |  |  | 702000
EB-5619A | Bike & Ped | Locally Selected | Grants Creek Greenway | Vicinity of Forestdale Drive to Catawba College in Salisbury. | Construct low-water bridge greenway connection. |  | Rowan | 9 | Cabarrus-Rowan MPO | COMPLETE | Division 9
EB-5619B | Bike & Ped | Locally Selected | Grants Creek Greenway | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | RIGHT-OF-WAY | 660000
EB-5619B | Bike & Ped | Locally Selected | Grants Creek Greenway | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 165000
EB-5619B | Bike & Ped | Locally Selected | Grants Creek Greenway | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | UTILITIES | 8000
EB-5619B | Bike & Ped | Locally Selected | Grants Creek Greenway | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | UTILITIES | 2000
EB-5619B | Bike & Ped | Locally Selected | Grants Creek Greenway | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 1380000 | FY 2026: 1380000
EB-5619B | Bike & Ped | Locally Selected | Grants Creek Greenway | Catawba College and Meadowbrook Neighborhood to south of Statesville Boulevard in Salisbury | Construct multi-use path. | 0.61 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 345000 | FY 2026: 345000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | ENGINEERING | 540000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | ENGINEERING | 135000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 52000 | FY 2026: 52000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 13000 | FY 2026: 13000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | UTILITIES | 36000 | FY 2026: 36000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | UTILITIES | 9000 | FY 2026: 9000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1635000 | FY 2027: 1635000
EB-5619C | Bike & Ped | Locally Selected | Grants Creek Greenway | South of Statesville Boulevard to Kelsey Scott Park along Wiltshire Place, East Colonial Drive, and South McCoy Road in Salisbury | Construct multi-use path. | 0.31 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 409000 | FY 2027: 409000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 196000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 640000 | FY 2026: 640000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 160000 | FY 2026: 160000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 60000 | FY 2026: 60000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | UTILITIES | 15000 | FY 2026: 15000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 704000 | FY 2027: 704000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29 / US 74 (East Franklin Boulevard) | SR 2200 (Cox Road) to east of Duhart's Creek in Gastonia | Construct sidewalk in gaps on south side of roadway, pedestrian improvements. | 0.52 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 176000 | FY 2027: 176000
EB-5703 | Bike & Ped | STI (Prioritization) | Lasalle Street | Kangaroo Drive to Sprunt Avenue in Durham | Construct sidewalks on both sides from Kangaroo Drive to US 70 Business (Hillsborough Road) and on one side from Hillsborough Road to Sprunt Avenue. | 0.69 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  |  |  | 717000
EB-5703 | Bike & Ped | STI (Prioritization) | Lasalle Street | Kangaroo Drive to Sprunt Avenue in Durham | Construct sidewalks on both sides from Kangaroo Drive to US 70 Business (Hillsborough Road) and on one side from Hillsborough Road to Sprunt Avenue. | 0.69 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | RIGHT-OF-WAY | 412000
EB-5703 | Bike & Ped | STI (Prioritization) | Lasalle Street | Kangaroo Drive to Sprunt Avenue in Durham | Construct sidewalks on both sides from Kangaroo Drive to US 70 Business (Hillsborough Road) and on one side from Hillsborough Road to Sprunt Avenue. | 0.69 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | RIGHT-OF-WAY | 103000
EB-5703 | Bike & Ped | STI (Prioritization) | Lasalle Street | Kangaroo Drive to Sprunt Avenue in Durham | Construct sidewalks on both sides from Kangaroo Drive to US 70 Business (Hillsborough Road) and on one side from Hillsborough Road to Sprunt Avenue. | 0.69 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | CONSTRUCTION | 1440000 | FY 2026: 1440000
EB-5703 | Bike & Ped | STI (Prioritization) | Lasalle Street | Kangaroo Drive to Sprunt Avenue in Durham | Construct sidewalks on both sides from Kangaroo Drive to US 70 Business (Hillsborough Road) and on one side from Hillsborough Road to Sprunt Avenue. | 0.69 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | CONSTRUCTION | 360000 | FY 2026: 360000
EB-5704 | Bike & Ped | STI (Prioritization) | Raynor Street | North Miami Boulevard to North Hardee Street in Durham | Construct sidewalk on one side of street. | 0.35 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  |  |  | 268000
EB-5704 | Bike & Ped | STI (Prioritization) | Raynor Street | North Miami Boulevard to North Hardee Street in Durham | Construct sidewalk on one side of street. | 0.35 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | RIGHT-OF-WAY | 135000
EB-5704 | Bike & Ped | STI (Prioritization) | Raynor Street | North Miami Boulevard to North Hardee Street in Durham | Construct sidewalk on one side of street. | 0.35 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | RIGHT-OF-WAY | 34000
EB-5704 | Bike & Ped | STI (Prioritization) | Raynor Street | North Miami Boulevard to North Hardee Street in Durham | Construct sidewalk on one side of street. | 0.35 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | CONSTRUCTION | 640000
EB-5704 | Bike & Ped | STI (Prioritization) | Raynor Street | North Miami Boulevard to North Hardee Street in Durham | Construct sidewalk on one side of street. | 0.35 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | CONSTRUCTION | 160000
EB-5707 | Bike & Ped | STI (Prioritization) | Stoney Creek Greenway | US 70 Bypass to SR 1560 (Royall Avenue) in Goldsboro. | Construct 10 foot wide asphalt greenway. | 0.39 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 15000
EB-5707 | Bike & Ped | STI (Prioritization) | Stoney Creek Greenway | US 70 Bypass to SR 1560 (Royall Avenue) in Goldsboro. | Construct 10 foot wide asphalt greenway. | 0.39 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | L(M) | CONSTRUCTION | 23000
EB-5707 | Bike & Ped | STI (Prioritization) | Stoney Creek Greenway | US 70 Bypass to SR 1560 (Royall Avenue) in Goldsboro. | Construct 10 foot wide asphalt greenway. | 0.39 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | SRTS | CONSTRUCTION | 368000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  |  |  | 276000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | RIGHT-OF-WAY | 142000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | RIGHT-OF-WAY | 35000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | CONSTRUCTION | 617000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | CONSTRUCTION | 153000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 to Research Triangle Park western limit in Durham | Construct sections of sidewalk on south side. | 0.57 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | SRTS | CONSTRUCTION | 330000
EB-5711 | Bike & Ped | STI (Prioritization) | US 64 Business (Sunset Avenue) | SR 1836 (May Drive) to Northbound US 301 Business (Church Street) in Rocky Mount. | Install pedestrian signals. | 1.7 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  |  |  | 25000
EB-5711 | Bike & Ped | STI (Prioritization) | US 64 Business (Sunset Avenue) | SR 1836 (May Drive) to Northbound US 301 Business (Church Street) in Rocky Mount. | Install pedestrian signals. | 1.7 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 464000
EB-5711 | Bike & Ped | STI (Prioritization) | US 64 Business (Sunset Avenue) | SR 1836 (May Drive) to Northbound US 301 Business (Church Street) in Rocky Mount. | Install pedestrian signals. | 1.7 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 116000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 Bypass (North Duke Street) | Murray Avenue to US 501 Business (North Roxboro Road) in Durham | Construct sidewalk on east side to fill in existing gaps. | 2.42 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  |  |  | 437000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 Bypass (North Duke Street) | Murray Avenue to US 501 Business (North Roxboro Road) in Durham | Construct sidewalk on east side to fill in existing gaps. | 2.42 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | TAANY | RIGHT-OF-WAY | 237000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 Bypass (North Duke Street) | Murray Avenue to US 501 Business (North Roxboro Road) in Durham | Construct sidewalk on east side to fill in existing gaps. | 2.42 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | L(M) | RIGHT-OF-WAY | 59000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 Bypass (North Duke Street) | Murray Avenue to US 501 Business (North Roxboro Road) in Durham | Construct sidewalk on east side to fill in existing gaps. | 2.42 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | TAANY | CONSTRUCTION | 2720000 | FY 2026: 28000; FY 2027: 2692000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 Bypass (North Duke Street) | Murray Avenue to US 501 Business (North Roxboro Road) in Durham | Construct sidewalk on east side to fill in existing gaps. | 2.42 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | L(M) | CONSTRUCTION | 680000 | FY 2026: 680000
EB-5716 | Bike & Ped | STI (Prioritization) | Holden Road; East Lindsay Street | South of Meadowview Road to Spring Garden Road; Murrow Boulevard to Bessemer Avenue in Greensboro | Construct sidewalk. | 0.89 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 530000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (Western Boulevard) | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Wake | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | TAANY | RIGHT-OF-WAY | 4960000 | FY 2028: 4960000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (Western Boulevard) | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Wake | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | L(M) | RIGHT-OF-WAY | 1240000 | FY 2028: 1240000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (Western Boulevard) | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Wake | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | TAANY | UTILITIES | 248000 | FY 2028: 248000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (Western Boulevard) | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Wake | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | L(M) | UTILITIES | 62000 | FY 2028: 62000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (Western Boulevard) | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Wake | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | TAANY | CONSTRUCTION | 4480000 | FY 2030: 2106000; FY 2031: 1971000; FY 2032: 403000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (Western Boulevard) | West of SR 1321 (Avent Ferry Road) in Raleigh | Construct bicycle / pedestrian tunnel. | 0.06 | Wake | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | L(M) | CONSTRUCTION | 1120000 | FY 2030: 526000; FY 2031: 493000; FY 2032: 101000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  |  |  | 870000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  | HP | RIGHT-OF-WAY | 1440000 | FY 2026: 1440000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  | L(M) | RIGHT-OF-WAY | 360000 | FY 2026: 360000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  | HP | UTILITIES | 880000 | FY 2026: 880000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  | L(M) | UTILITIES | 220000 | FY 2026: 220000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  | TAANY | CONSTRUCTION | 3680000 | FY 2027: 1803000; FY 2028: 1877000
EB-5720 | Bike & Ped | STI (Prioritization) | Bryant Bridge North / Goose Creek West Trail | NC 55 to Drew-Granby Park in Durham | Construct multi-use path and connecting sidewalks. | 1.11 | Durham | 5 | Triangle West TPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. DEMO ID NC200. | Division 5 |  | L(M) | CONSTRUCTION | 920000 | FY 2027: 451000; FY 2028: 469000
EB-5721 | Bike & Ped | STI (Prioritization) | Orange County Bicycle Route 1 | Cleland Drive to Willow Drive in Chapel Hill | Upgrade existing off-road path and construct new section of path. | 0.67 | Orange | 7 | Triangle West TPO |  | Division 7 |  |  |  | 138000
EB-5721 | Bike & Ped | STI (Prioritization) | Orange County Bicycle Route 1 | Cleland Drive to Willow Drive in Chapel Hill | Upgrade existing off-road path and construct new section of path. | 0.67 | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 747000 | FY 2026: 747000
EB-5721 | Bike & Ped | STI (Prioritization) | Orange County Bicycle Route 1 | Cleland Drive to Willow Drive in Chapel Hill | Upgrade existing off-road path and construct new section of path. | 0.67 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TADA | CONSTRUCTION | 1413000 | FY 2026: 1413000
EB-5721 | Bike & Ped | STI (Prioritization) | Orange County Bicycle Route 1 | Cleland Drive to Willow Drive in Chapel Hill | Upgrade existing off-road path and construct new section of path. | 0.67 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 540000 | FY 2026: 540000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 415000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TADA | ENGINEERING | 32000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | ENGINEERING | 8000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 728000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TADA | RIGHT-OF-WAY | 344000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 268000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 4676000 | FY 2026: 4676000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TAANY | CONSTRUCTION | 1978000 | FY 2026: 1978000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (Silas Creek Parkway) | Drumcliffe Road to Lockland Avenue in Winston-Salem | Construct sidewalks along Silas Creek Parkway to connect existing sections. | 2.28 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 1664000 | FY 2026: 1664000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | TADA | ENGINEERING | 837000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | TAANY | ENGINEERING | 116000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 238000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | TAANY | RIGHT-OF-WAY | 100000 | FY 2026: 100000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 25000 | FY 2026: 25000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 2042000 | FY 2026: 20000; FY 2027: 1736000; FY 2028: 286000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | TAANY | CONSTRUCTION | 869000 | FY 2026: 9000; FY 2027: 738000; FY 2028: 122000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (Indian Trail Fairview Road) to SR 1367 (Unionville Indian Trail Road); SR 1367 (Unionville Indian Trail Road) to Oakwood Lane in Indian Trail | Construct multi-use path. | 0.6 | Union | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 1020000 | FY 2026: 10000; FY 2027: 867000; FY 2028: 143000
EB-5732 | Bike & Ped | STI (Prioritization) | SR 2894 (Bruton Smith Boulevard / Concord Mills Boulevard); Portion of Weddington Road | US 29 to John Q. Hammonds Drive in Concord | Construct shared use path on north side of road. | 1.71 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  |  |  | 720000
EB-5732 | Bike & Ped | STI (Prioritization) | SR 2894 (Bruton Smith Boulevard / Concord Mills Boulevard); Portion of Weddington Road | US 29 to John Q. Hammonds Drive in Concord | Construct shared use path on north side of road. | 1.71 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TAANY | RIGHT-OF-WAY | 3405000 | FY 2029: 3405000
EB-5732 | Bike & Ped | STI (Prioritization) | SR 2894 (Bruton Smith Boulevard / Concord Mills Boulevard); Portion of Weddington Road | US 29 to John Q. Hammonds Drive in Concord | Construct shared use path on north side of road. | 1.71 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TAANY | UTILITIES | 187000 | FY 2029: 187000
EB-5732 | Bike & Ped | STI (Prioritization) | SR 2894 (Bruton Smith Boulevard / Concord Mills Boulevard); Portion of Weddington Road | US 29 to John Q. Hammonds Drive in Concord | Construct shared use path on north side of road. | 1.71 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TAANY | CONSTRUCTION | 9700000 | FY 2029: 1552000; FY 2030: 3748000; FY 2031: 4012000; FY 2032: 388000
EB-5732 | Bike & Ped | STI (Prioritization) | SR 2894 (Bruton Smith Boulevard / Concord Mills Boulevard); Portion of Weddington Road | US 29 to John Q. Hammonds Drive in Concord | Construct shared use path on north side of road. | 1.71 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 800000 | FY 2029: 800000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  |  |  | 39000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 164000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 41000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 114000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | UTILITIES | 29000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1840000 | FY 2026: 1840000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (East Raleigh Street) | South 7th Avenue to US 64 (East 11th Street) in Siler City | Construct sidewalk on south side. | 1.1 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 460000 | FY 2026: 460000
EB-5741 | Bike & Ped | STI (Prioritization) | US 1 / US 15 / US 501 (Sandhills Boulevard) | Maple Avenue in Aberdeen. | Construct mid-block crosswalk, median refuge island, and install pedestrian signal. | 0.26 | Moore | 8 | Sandhills MPO |  | Division 8 |  |  |  | 8000
EB-5741 | Bike & Ped | STI (Prioritization) | US 1 / US 15 / US 501 (Sandhills Boulevard) | Maple Avenue in Aberdeen. | Construct mid-block crosswalk, median refuge island, and install pedestrian signal. | 0.26 | Moore | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | CONSTRUCTION | 250000
EB-5741 | Bike & Ped | STI (Prioritization) | US 1 / US 15 / US 501 (Sandhills Boulevard) | Maple Avenue in Aberdeen. | Construct mid-block crosswalk, median refuge island, and install pedestrian signal. | 0.26 | Moore | 8 | Sandhills MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 62000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (Wicker Street) | SR 1190 (Legion Drive) to north of High Ridge Drive at Kiwanis Family Park in Sanford | Construct multi-use path. | 0.42 | Lee | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | TA5T50 | ENGINEERING | 62000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (Wicker Street) | SR 1190 (Legion Drive) to north of High Ridge Drive at Kiwanis Family Park in Sanford | Construct multi-use path. | 0.42 | Lee | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | L(M) | ENGINEERING | 15000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (Wicker Street) | SR 1190 (Legion Drive) to north of High Ridge Drive at Kiwanis Family Park in Sanford | Construct multi-use path. | 0.42 | Lee | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | TA5T50 | CONSTRUCTION | 808000 | FY 2027: 404000; FY 2028: 404000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (Wicker Street) | SR 1190 (Legion Drive) to north of High Ridge Drive at Kiwanis Family Park in Sanford | Construct multi-use path. | 0.42 | Lee | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | L(M) | CONSTRUCTION | 202000 | FY 2027: 202000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (South New Hope Road) | SR 2200 (Armstrong Park Road) to SR 1255 (Hudson Boulevard) in Cramerton | Construct missing sidewalk on south side of NC 279. | 1.12 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 321000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (South New Hope Road) | SR 2200 (Armstrong Park Road) to SR 1255 (Hudson Boulevard) in Cramerton | Construct missing sidewalk on south side of NC 279. | 1.12 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 257000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (South New Hope Road) | SR 2200 (Armstrong Park Road) to SR 1255 (Hudson Boulevard) in Cramerton | Construct missing sidewalk on south side of NC 279. | 1.12 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 64000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (South New Hope Road) | SR 2200 (Armstrong Park Road) to SR 1255 (Hudson Boulevard) in Cramerton | Construct missing sidewalk on south side of NC 279. | 1.12 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 640000 | FY 2027: 640000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (South New Hope Road) | SR 2200 (Armstrong Park Road) to SR 1255 (Hudson Boulevard) in Cramerton | Construct missing sidewalk on south side of NC 279. | 1.12 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 160000 | FY 2027: 160000
EB-5744 | Bike & Ped | STI (Prioritization) | SR 1950 (West Academy Street) | SR 1952 (High Point Street) to Hillary Street in Randleman | Construct sidewalk on north side. | 1.04 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  |  |  | 69000
EB-5744 | Bike & Ped | STI (Prioritization) | SR 1950 (West Academy Street) | SR 1952 (High Point Street) to Hillary Street in Randleman | Construct sidewalk on north side. | 1.04 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 640000 | FY 2027: 640000
EB-5744 | Bike & Ped | STI (Prioritization) | SR 1950 (West Academy Street) | SR 1952 (High Point Street) to Hillary Street in Randleman | Construct sidewalk on north side. | 1.04 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 160000 | FY 2027: 160000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 308000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 246000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 62000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 720000 | FY 2026: 720000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 180000 | FY 2026: 180000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 300000 | FY 2026: 300000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | UTILITIES | 300000 | FY 2026: 300000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 2720000 | FY 2027: 2203000; FY 2028: 517000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (Hudson Boulevard); SR 2466 (Redbud Drive) | SR 2200 (Gaston Day School Road) to SR 2466 (Redbud Drive); SR 1255 (Hudson Boulevard) to NC 279 (South New Hope Road) in Cramerton | Construct sidewalk on one side. | 1.11 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 680000 | FY 2027: 632000; FY 2028: 48000
EB-5748 | Bike & Ped | STI (Prioritization) | SR 2439 (Beaty Road) | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 8000
EB-5748 | Bike & Ped | STI (Prioritization) | SR 2439 (Beaty Road) | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 2000
EB-5748 | Bike & Ped | STI (Prioritization) | SR 2439 (Beaty Road) | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 185000 | FY 2026: 185000
EB-5748 | Bike & Ped | STI (Prioritization) | SR 2439 (Beaty Road) | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 46000 | FY 2026: 46000
EB-5748 | Bike & Ped | STI (Prioritization) | SR 2439 (Beaty Road) | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 640000 | FY 2027: 640000
EB-5748 | Bike & Ped | STI (Prioritization) | SR 2439 (Beaty Road) | Ferstl Avenue to Smith Street in Belmont | Construct sidewalk on one side. | 0.36 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 160000 | FY 2027: 160000
EB-5750 | Bike & Ped | STI (Prioritization) | SR 1124 (Main Avenue Northwest) | 7th Avenue NE to 9th Street Northwest in Newton | Construct greenway with park nodes and pedestrian bridge over NC 127. | 1.2 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  |  |  | 4000
EB-5750 | Bike & Ped | STI (Prioritization) | SR 1124 (Main Avenue Northwest) | 7th Avenue NE to 9th Street Northwest in Newton | Construct greenway with park nodes and pedestrian bridge over NC 127. | 1.2 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | TAANY | CONSTRUCTION | 11280000
EB-5750 | Bike & Ped | STI (Prioritization) | SR 1124 (Main Avenue Northwest) | 7th Avenue NE to 9th Street Northwest in Newton | Construct greenway with park nodes and pedestrian bridge over NC 127. | 1.2 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 2820000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TAANY | ENGINEERING | 370000 | FY 2026: 350000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | L(M) | ENGINEERING | 93000 | FY 2026: 88000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | RIGHT-OF-WAY | 140000 | FY 2026: 140000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | UTILITIES | 760000 | FY 2026: 760000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | CONSTRUCTION | 3968000 | FY 2027: 3008000; FY 2028: 960000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (Baldwin Avenue) | Perry Street to US 70 (East Court Street) in Marion | Construct curb and gutter, and sidewalk along east side and install crosswalks. | 0.56 | McDowell | 13 | Foothills RPO |  | Division 13 |  | L(M) | CONSTRUCTION | 32000 | FY 2027: 32000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (Depot Street) | US 441 Business (East Main Street) to SR 1667 (Wayah Street) in Franklin | Construct missing sections of sidewalk along west side and construct new sidewalk on east side. | 0.63 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 69000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (Depot Street) | US 441 Business (East Main Street) to SR 1667 (Wayah Street) in Franklin | Construct missing sections of sidewalk along west side and construct new sidewalk on east side. | 0.63 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | TAANY | ENGINEERING | 14000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (Depot Street) | US 441 Business (East Main Street) to SR 1667 (Wayah Street) in Franklin | Construct missing sections of sidewalk along west side and construct new sidewalk on east side. | 0.63 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | ENGINEERING | 4000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (Depot Street) | US 441 Business (East Main Street) to SR 1667 (Wayah Street) in Franklin | Construct missing sections of sidewalk along west side and construct new sidewalk on east side. | 0.63 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | TAANY | CONSTRUCTION | 260000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (Depot Street) | US 441 Business (East Main Street) to SR 1667 (Wayah Street) in Franklin | Construct missing sections of sidewalk along west side and construct new sidewalk on east side. | 0.63 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | CONSTRUCTION | 66000
EB-5761 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | NC 97 (Raleigh Boulevard) to US 64 in Rocky Mount. | Construct streetscape improvements including sidewalk and bike lanes. | 1.69 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 120000 | FY 2026: 120000
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 30000 | FY 2026: 30000
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | RIGHT-OF-WAY | 215000 | FY 2027: 215000
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 54000 | FY 2027: 54000
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | UTILITIES | 181000 | FY 2027: 181000
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 6800000 | FY 2028: 68000; FY 2029: 5032000; FY 2030: 1700000
EB-5761A | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) and US 301 Business (Franklin Street) | US 301 Business (Church Street) from NC 97 (Raleigh Boulevard) to West Holly Street and US 301 Business (Franklin Street) from NC 97 (Raleigh Boulevard) to Falls Road | Implement road diet reducing the number of travel lanes from three to two and install buffered bike lanes on the left side of the street. | 0.89 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 1700000 | FY 2028: 17000; FY 2029: 1258000; FY 2030: 425000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 120000 | FY 2029: 120000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 30000 | FY 2029: 30000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | RIGHT-OF-WAY | 145000 | FY 2030: 145000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 36000 | FY 2030: 36000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | UTILITIES | 619000 | FY 2030: 619000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 3200000 | FY 2031: 32000; FY 2032: 2368000; FY 2033: 800000
EB-5761B | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | Holly Street to US 64 Interchange | Install pavement markings, Install bike lanes, Install pedestrian signal heads, Provide sidewalk and curb extensions. | 0.72 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 800000 | FY 2031: 8000; FY 2032: 592000; FY 2033: 200000
EB-5763 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 160000
EB-5763 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 40000
EB-5763 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | RIGHT-OF-WAY | 60000 | FY 2027: 60000
EB-5763 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2027: 15000
EB-5763 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 2400000 | FY 2028: 2400000
EB-5763 | Bike & Ped | STI (Prioritization) | US 301 Business (Church Street) | River Drive to Monk Street in Rocky Mount | Upgrade abandoned railroad to multi-use path. | 2.43 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 600000 | FY 2028: 600000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 315000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 280000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 70000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 960000 | FY 2026: 960000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 240000 | FY 2026: 240000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 640000 | FY 2026: 640000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | UTILITIES | 160000 | FY 2026: 160000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 800000 | FY 2026: 8000; FY 2027: 792000
EB-5768 | Bike & Ped | STI (Prioritization) | South Marietta Street / SR 1877 (Hilltop Drive) | SR 1255 (Hudson Boulevard) to Clyde Street in Gastonia | Construct sidewalk. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 200000 | FY 2026: 200000
EB-5774 | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to US 25 in Asheville | Construct multi-use path along Beaverdam Creek. |  | Buncombe | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | Division 13 |  |  |  | 536000
EB-5774 | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to US 25 in Asheville | Construct multi-use path along Beaverdam Creek. |  | Buncombe | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | Division 13 |  | BGDA | ENGINEERING | 1600000
EB-5774 | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to US 25 in Asheville | Construct multi-use path along Beaverdam Creek. |  | Buncombe | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | Division 13 |  | L(M) | ENGINEERING | 400000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to the Mills at Riverside in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | TADA | RIGHT-OF-WAY | 3406000 | FY 2026: 3406000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to the Mills at Riverside in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 853000 | FY 2026: 853000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to the Mills at Riverside in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 4808000 | FY 2027: 4808000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (Riverside Drive) | US 19 / US 23 / US 70 (Exit 25) to the Mills at Riverside in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 1202000 | FY 2027: 1202000
EB-5774B | Bike & Ped | Locally Selected | Beaverdam Creek Greenway | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGDA | RIGHT-OF-WAY | 176000
EB-5774B | Bike & Ped | Locally Selected | Beaverdam Creek Greenway | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | TADA | RIGHT-OF-WAY | 310000
EB-5774B | Bike & Ped | Locally Selected | Beaverdam Creek Greenway | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 122000
EB-5774B | Bike & Ped | Locally Selected | Beaverdam Creek Greenway | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 2000000 | FY 2026: 20000; FY 2027: 1518000; FY 2028: 462000
EB-5774B | Bike & Ped | Locally Selected | Beaverdam Creek Greenway | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 760000 | FY 2026: 760000
EB-5774B | Bike & Ped | Locally Selected | Beaverdam Creek Greenway | The Mills at Riverside to US 25 in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 690000 | FY 2026: 690000
EB-5777 | Bike & Ped | Locally Selected | McDowell Creek Tributary Greenway | Smithville Park at Catawba Avenue to SR 2147 (Westmoreland Road); SR 2147 (Westmoreland Road) from east of Amberwood Glen Drive to SR 2600 (Washam Potts Road) in Cornelius | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 768000
EB-5777 | Bike & Ped | Locally Selected | McDowell Creek Tributary Greenway | Smithville Park at Catawba Avenue to SR 2147 (Westmoreland Road); SR 2147 (Westmoreland Road) from east of Amberwood Glen Drive to SR 2600 (Washam Potts Road) in Cornelius | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 192000
EB-5777 | Bike & Ped | Locally Selected | McDowell Creek Tributary Greenway | Smithville Park at Catawba Avenue to SR 2147 (Westmoreland Road); SR 2147 (Westmoreland Road) from east of Amberwood Glen Drive to SR 2600 (Washam Potts Road) in Cornelius | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1632000 | FY 2026: 1632000
EB-5777 | Bike & Ped | Locally Selected | McDowell Creek Tributary Greenway | Smithville Park at Catawba Avenue to SR 2147 (Westmoreland Road); SR 2147 (Westmoreland Road) from east of Amberwood Glen Drive to SR 2600 (Washam Potts Road) in Cornelius | Construct shared-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 408000 | FY 2026: 408000
EB-5781 | Bike & Ped | STI (Prioritization) | Stewart Creek Greenway | State Street to Rozzelles Ferry Road in Charlotte | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1693000
EB-5781 | Bike & Ped | STI (Prioritization) | Stewart Creek Greenway | State Street to Rozzelles Ferry Road in Charlotte | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CRPDA | CONSTRUCTION | 834000
EB-5781 | Bike & Ped | STI (Prioritization) | Stewart Creek Greenway | State Street to Rozzelles Ferry Road in Charlotte | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 632000
EB-5782 | Bike & Ped | STI (Prioritization) | McAlpine Creek Greenway | NC 51 to Four Mile Creek Greenway in Charlotte | Construct greenway. | 1.65 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 3926000
EB-5782 | Bike & Ped | STI (Prioritization) | McAlpine Creek Greenway | NC 51 to Four Mile Creek Greenway in Charlotte | Construct greenway. | 1.65 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 1848000
EB-5782 | Bike & Ped | STI (Prioritization) | McAlpine Creek Greenway | NC 51 to Four Mile Creek Greenway in Charlotte | Construct greenway. | 1.65 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 1444000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | ENGINEERING | 305000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | ENGINEERING | 76000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 30000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | RIGHT-OF-WAY | 238000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 67000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 1619000 | FY 2026: 1619000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 99000 | FY 2026: 99000
EB-5783 | Bike & Ped | Locally Selected | SR 3168 (Sam Newell Road) | Northeast Parkway to Crown Point Elementary School in Matthews | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 305000 | FY 2026: 305000
EB-5785 | Bike & Ped | Locally Selected | Upper McDowell Creek Greenway | Chilgrove Lane to NC 73 in Huntersville | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | CMAQ | CONSTRUCTION | 4271000
EB-5785 | Bike & Ped | Locally Selected | Upper McDowell Creek Greenway | Chilgrove Lane to NC 73 in Huntersville | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L(M) | CONSTRUCTION | 1068000
EB-5787 | Bike & Ped | Locally Selected | Bellingham Park Greenway | Bellingham Park to SR 1142 (Johnson Dairy Road) in Mooresville | Extend greenway. |  | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | TADA | CONSTRUCTION | 3555000
EB-5787 | Bike & Ped | Locally Selected | Bellingham Park Greenway | Bellingham Park to SR 1142 (Johnson Dairy Road) in Mooresville | Extend greenway. |  | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | L(M) | CONSTRUCTION | 889000
EB-5788 | Bike & Ped | Locally Selected | Shelton Avenue Multi-Use Path | Garner Bagnal Boulevard to SR 2342 (Amity Hill Road) in Statesville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 12 |  |  |  | 240000
EB-5788 | Bike & Ped | Locally Selected | Shelton Avenue Multi-Use Path | Garner Bagnal Boulevard to SR 2342 (Amity Hill Road) in Statesville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 12 |  | BGDA | RIGHT-OF-WAY | 201000
EB-5788 | Bike & Ped | Locally Selected | Shelton Avenue Multi-Use Path | Garner Bagnal Boulevard to SR 2342 (Amity Hill Road) in Statesville | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 12 |  | L(M) | RIGHT-OF-WAY | 50000
EB-5790 | Bike & Ped | Locally Selected | Various | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Buncombe | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TADA | ENGINEERING | 96000
EB-5790 | Bike & Ped | Locally Selected | Various | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Buncombe | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | ENGINEERING | 9000
EB-5790 | Bike & Ped | Locally Selected | Various | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Buncombe | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L(M) | ENGINEERING | 26000
EB-5790 | Bike & Ped | Locally Selected | Various | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Buncombe | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | BGDA | CONSTRUCTION | 182000
EB-5790 | Bike & Ped | Locally Selected | Various | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Buncombe | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | CONSTRUCTION | 1120000
EB-5790 | Bike & Ped | Locally Selected | Various | Locations along East of the Riverway in Asheville | Install on-street crossings and connections for bicyclists and pedestrians. |  | Buncombe | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | CONSTRUCTION | 326000
EB-5798 | Bike & Ped | Locally Selected | US 221 | Main Street to Moses H. Cone Memorial Park and Bass Lake in Blowing Rock | Construct sidewalk. | 0.6 | Watauga | 11 | High Country RPO | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK | Exempt |  |  |  | 1201000
EB-5806 | Bike & Ped | Locally Selected | Hospital Avenue | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Caldwell | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | TADA | RIGHT-OF-WAY | 96000
EB-5806 | Bike & Ped | Locally Selected | Hospital Avenue | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Caldwell | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | L(M) | RIGHT-OF-WAY | 24000
EB-5806 | Bike & Ped | Locally Selected | Hospital Avenue | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Caldwell | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | BGANY | CONSTRUCTION | 414000
EB-5806 | Bike & Ped | Locally Selected | Hospital Avenue | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Caldwell | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | BGDA | CONSTRUCTION | 1901000
EB-5806 | Bike & Ped | Locally Selected | Hospital Avenue | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Caldwell | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | TADA | CONSTRUCTION | 125000
EB-5806 | Bike & Ped | Locally Selected | Hospital Avenue | SR 1300 (Harper Avenue) to US 321 (Blowing Rock Boulevard) in Lenoir | Construct sidewalk. |  | Caldwell | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | L(M) | CONSTRUCTION | 610000
EB-5807 | Bike & Ped | Locally Selected | Morganton Downtown Greenway Connector, US 64 Bypass (Sanford Drive) | Catawba River Greenway near Alphabet Lane to existing section of the Downtown Greenway at the intersection of College Street and NC 181 (North Green Street) in Morganton. | Construct greenway. |  | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  |  |  | 40000
EB-5807 | Bike & Ped | Locally Selected | Morganton Downtown Greenway Connector, US 64 Bypass (Sanford Drive) | Catawba River Greenway near Alphabet Lane to existing section of the Downtown Greenway at the intersection of College Street and NC 181 (North Green Street) in Morganton. | Construct greenway. |  | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | BGANY | CONSTRUCTION | 1000000
EB-5807 | Bike & Ped | Locally Selected | Morganton Downtown Greenway Connector, US 64 Bypass (Sanford Drive) | Catawba River Greenway near Alphabet Lane to existing section of the Downtown Greenway at the intersection of College Street and NC 181 (North Green Street) in Morganton. | Construct greenway. |  | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | BGDA | CONSTRUCTION | 295000
EB-5807 | Bike & Ped | Locally Selected | Morganton Downtown Greenway Connector, US 64 Bypass (Sanford Drive) | Catawba River Greenway near Alphabet Lane to existing section of the Downtown Greenway at the intersection of College Street and NC 181 (North Green Street) in Morganton. | Construct greenway. |  | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | L(M) | CONSTRUCTION | 324000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 60000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | ENGINEERING | 8000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | ENGINEERING | 2000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | RIGHT-OF-WAY | 4000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 1000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 176000 | FY 2026: 176000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TAANY | CONSTRUCTION | 361000 | FY 2026: 361000
EB-5810 | Bike & Ped | STI (Prioritization) | Barbara Jane Avenue | Old Greensboro Road to Woodrow Powell Drive in Winston-Salem | Construct sidewalk. | 0.96 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 134000 | FY 2026: 134000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 150000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | ENGINEERING | 120000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 30000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | RIGHT-OF-WAY | 104000 | FY 2028: 104000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 26000 | FY 2028: 26000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | UTILITIES | 120000 | FY 2028: 120000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 30000 | FY 2028: 30000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | CONSTRUCTION | 8320000 | FY 2030: 83000; FY 2031: 4742000; FY 2032: 3162000; FY 2033: 333000
EB-5812 | Bike & Ped | STI (Prioritization) | Salem Creek Greenway | Forsyth Technical Community College to existing greenway at Marketplace Mall in Winston-Salem | Construct greenway. | 1.04 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 2080000 | FY 2030: 2080000
EB-5817 | Bike & Ped | Locally Selected | McDowell Creek Greenway | Magnolia Plaza to SR 2147 (Westmoreland Road) in Cornelius | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  |  |  | 450000
EB-5817 | Bike & Ped | Locally Selected | McDowell Creek Greenway | Magnolia Plaza to SR 2147 (Westmoreland Road) in Cornelius | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | BGDA | CONSTRUCTION | 1026000
EB-5817 | Bike & Ped | Locally Selected | McDowell Creek Greenway | Magnolia Plaza to SR 2147 (Westmoreland Road) in Cornelius | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | TADA | CONSTRUCTION | 1400000
EB-5817 | Bike & Ped | Locally Selected | McDowell Creek Greenway | Magnolia Plaza to SR 2147 (Westmoreland Road) in Cornelius | Construct greenway. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | L(M) | CONSTRUCTION | 1456000
EB-5818 | Bike & Ped | Locally Selected | US 21 (Turnersburg Highway) | Statesville Greenway - Gregory Creek Segment to Statesville Greenway - Fourth Creek Greenway Segment near Statesville. | Construct greenway connector under US 21. |  | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  |  |  | 450000
EB-5818 | Bike & Ped | Locally Selected | US 21 (Turnersburg Highway) | Statesville Greenway - Gregory Creek Segment to Statesville Greenway - Fourth Creek Greenway Segment near Statesville. | Construct greenway connector under US 21. |  | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | BGDA | CONSTRUCTION | 875000 | FY 2026: 875000
EB-5818 | Bike & Ped | Locally Selected | US 21 (Turnersburg Highway) | Statesville Greenway - Gregory Creek Segment to Statesville Greenway - Fourth Creek Greenway Segment near Statesville. | Construct greenway connector under US 21. |  | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | CONSTRUCTION | 876000 | FY 2026: 876000
EB-5818 | Bike & Ped | Locally Selected | US 21 (Turnersburg Highway) | Statesville Greenway - Gregory Creek Segment to Statesville Greenway - Fourth Creek Greenway Segment near Statesville. | Construct greenway connector under US 21. |  | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L(M) | CONSTRUCTION | 681000 | FY 2026: 681000
EB-5819 | Bike & Ped | Locally Selected | Various | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | ENGINEERING | 26000
EB-5819 | Bike & Ped | Locally Selected | Various | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | ENGINEERING | 180000
EB-5819 | Bike & Ped | Locally Selected | Various | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | ENGINEERING | 52000
EB-5819 | Bike & Ped | Locally Selected | Various | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 451000
EB-5819 | Bike & Ped | Locally Selected | Various | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | CONSTRUCTION | 418000
EB-5819 | Bike & Ped | Locally Selected | Various | Locations in downtown Waxhaw | Install pedestrian and bicycle facility enhancements. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | CONSTRUCTION | 869000
EB-5820 | Bike & Ped | Locally Selected | Various | Locations in Charlotte | Expand bicycle routes. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Division 10 |  |  |  | 675000
EB-5821 | Bike & Ped | Locally Selected | Reems Creek Greenway | Western edge of Weaverville to Karpen Soccer Fields in Weaverville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | IN PROGRESS | Division 13
EB-5821 | Bike & Ped | Locally Selected | Reems Creek Greenway | Western edge of Weaverville to Karpen Soccer Fields in Weaverville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | IN PROGRESS | Division 13 |  | BGDA | ENGINEERING | 480000 | FY 2029: 480000
EB-5821 | Bike & Ped | Locally Selected | Reems Creek Greenway | Western edge of Weaverville to Karpen Soccer Fields in Weaverville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | IN PROGRESS | Division 13 |  | L(M) | ENGINEERING | 120000 | FY 2029: 120000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | ENGINEERING | 480000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L(M) | ENGINEERING | 120000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | RIGHT-OF-WAY | 1680000 | FY 2026: 1680000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L(M) | RIGHT-OF-WAY | 420000 | FY 2026: 420000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | UTILITIES | 80000 | FY 2026: 80000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L(M) | UTILITIES | 20000 | FY 2026: 20000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | CONSTRUCTION | 1960000 | FY 2027: 420000; FY 2028: 914000; FY 2029: 626000
EB-5822 | Bike & Ped | STI (Prioritization) | North Rad Greenway | SR 1477 (Riverside Drive) and SR 1231 (Hill Street) to Pearson Bridge Road in Asheville | Construct multi-use path along the French Broad River. | 1.48 | Buncombe | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L(M) | CONSTRUCTION | 240000 | FY 2027: 240000
EB-5823 | Bike & Ped | Locally Selected | Bent Creek Greenway | Hominy Creek River Park to Western NC Farmers Market in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGDA | ENGINEERING | 320000 | FY 2029: 320000
EB-5823 | Bike & Ped | Locally Selected | Bent Creek Greenway | Hominy Creek River Park to Western NC Farmers Market in Asheville | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | ENGINEERING | 80000 | FY 2029: 80000
EB-5824 | Bike & Ped | Locally Selected | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGANY | ENGINEERING | 528000
EB-5824 | Bike & Ped | Locally Selected | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGDA | ENGINEERING | 520000
EB-5824 | Bike & Ped | Locally Selected | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | L(M) | ENGINEERING | 262000
EB-5824 | Bike & Ped | Locally Selected | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGANY | CONSTRUCTION | 2789000 | FY 2027: 1210000; FY 2028: 1579000
EB-5824 | Bike & Ped | Locally Selected | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGDA | CONSTRUCTION | 37000 | FY 2027: 37000
EB-5824 | Bike & Ped | Locally Selected | Hominy Creek Greenway / SR 3412 (Sand Hill Road) | Warren Haynes Drive to east of US 19 / US 23 in Candler | Construct multi-use path. |  | Buncombe | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | L(M) | CONSTRUCTION | 1018000 | FY 2027: 1018000
EB-5829 | Bike & Ped | Locally Selected | Four Mile Creek Greenway | SR 3448 (South Trade Street) in Matthews | Construct greenway crossing under roadway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | ENGINEERING | 113000
EB-5829 | Bike & Ped | Locally Selected | Four Mile Creek Greenway | SR 3448 (South Trade Street) in Matthews | Construct greenway crossing under roadway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | ENGINEERING | 28000
EB-5829 | Bike & Ped | Locally Selected | Four Mile Creek Greenway | SR 3448 (South Trade Street) in Matthews | Construct greenway crossing under roadway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | CONSTRUCTION | 2174000
EB-5829 | Bike & Ped | Locally Selected | Four Mile Creek Greenway | SR 3448 (South Trade Street) in Matthews | Construct greenway crossing under roadway. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | CONSTRUCTION | 725000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGDA | ENGINEERING | 420000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | TADA | ENGINEERING | 300000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | ENGINEERING | 180000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGDA | RIGHT-OF-WAY | 240000 | FY 2026: 240000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | RIGHT-OF-WAY | 60000 | FY 2026: 60000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGANY | CONSTRUCTION | 7555000 | FY 2027: 76000; FY 2028: 4165000; FY 2029: 2898000; FY 2030: 416000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGDA | CONSTRUCTION | 1247000 | FY 2027: 1247000
EB-5831 | Bike & Ped | Locally Selected | Coxe Avenue | Patton Avenue to Short Coxe Avenue in Asheville | Improve bicycle and pedestrian infrastructure. |  | Buncombe | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | CONSTRUCTION | 2201000 | FY 2027: 2201000
EB-5832 | Bike & Ped | STI (Prioritization) | SR 2833 (Mallard Creek Church Road) | SR 2472 (Mallard Creek Road) to SR 2746 (Claude Freeman Drive) in Charlotte | Construct multi-use trail on south side of road. | 0.62 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  |  |  | 364000
EB-5832 | Bike & Ped | STI (Prioritization) | SR 2833 (Mallard Creek Church Road) | SR 2472 (Mallard Creek Road) to SR 2746 (Claude Freeman Drive) in Charlotte | Construct multi-use trail on south side of road. | 0.62 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 800000
EB-5832 | Bike & Ped | STI (Prioritization) | SR 2833 (Mallard Creek Church Road) | SR 2472 (Mallard Creek Road) to SR 2746 (Claude Freeman Drive) in Charlotte | Construct multi-use trail on south side of road. | 0.62 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TAANY | CONSTRUCTION | 542000
EB-5832 | Bike & Ped | STI (Prioritization) | SR 2833 (Mallard Creek Church Road) | SR 2472 (Mallard Creek Road) to SR 2746 (Claude Freeman Drive) in Charlotte | Construct multi-use trail on south side of road. | 0.62 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | CONSTRUCTION | 336000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 163000 | FY 2026: 163000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 41000 | FY 2026: 41000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | UTILITIES | 336000 | FY 2026: 336000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | UTILITIES | 84000 | FY 2026: 84000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | CONSTRUCTION | 7205000 | FY 2030: 72000; FY 2031: 2739000; FY 2032: 4394000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CONSTRUCTION | 1802000 | FY 2030: 18000; FY 2031: 1099000; FY 2032: 685000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (Guess Road) | Hillcrest Drive to SR 1407 (West Carver Street) in Durham | Construct sidewalks on both sides. | 1.14 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | CONSTRUCTION | 694000 | FY 2030: 694000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | ENGINEERING | 84000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | ENGINEERING | 21000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 280000 | FY 2030: 280000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 70000 | FY 2030: 70000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | UTILITIES | 200000 | FY 2030: 200000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | UTILITIES | 50000 | FY 2030: 50000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | CONSTRUCTION | 8480000 | FY 2031: 89000; FY 2032: 4829000; FY 2033: 3225000; FY 2034: 337000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (Apex Highway) | SR 1171 (Riddle Road) to Cecil Street in Durham | Construct sidewalk on east side to fill in missing gaps. | 1.07 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CONSTRUCTION | 2120000 | FY 2031: 2120000
EB-5837 | Bike & Ped | STI (Prioritization) | Third Fork Creek Trail | Southern Boundaries Park to American Tobacco Trail in Durham | Construct shared use path and sidewalks, and install beacon at SR 1158 (Cornwallis Road) crossing. | 1.6 | Durham | 5 | Triangle West TPO |  | Division 5 |  |  |  | 567000
EB-5837 | Bike & Ped | STI (Prioritization) | Third Fork Creek Trail | Southern Boundaries Park to American Tobacco Trail in Durham | Construct shared use path and sidewalks, and install beacon at SR 1158 (Cornwallis Road) crossing. | 1.6 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 784000 | FY 2026: 784000
EB-5837 | Bike & Ped | STI (Prioritization) | Third Fork Creek Trail | Southern Boundaries Park to American Tobacco Trail in Durham | Construct shared use path and sidewalks, and install beacon at SR 1158 (Cornwallis Road) crossing. | 1.6 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 196000 | FY 2026: 196000
EB-5837 | Bike & Ped | STI (Prioritization) | Third Fork Creek Trail | Southern Boundaries Park to American Tobacco Trail in Durham | Construct shared use path and sidewalks, and install beacon at SR 1158 (Cornwallis Road) crossing. | 1.6 | Durham | 5 | Triangle West TPO |  | Division 5 |  | TAANY | CONSTRUCTION | 4640000 | FY 2027: 3202000; FY 2028: 1438000
EB-5837 | Bike & Ped | STI (Prioritization) | Third Fork Creek Trail | Southern Boundaries Park to American Tobacco Trail in Durham | Construct shared use path and sidewalks, and install beacon at SR 1158 (Cornwallis Road) crossing. | 1.6 | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CONSTRUCTION | 1160000 | FY 2027: 1160000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (Church Street) | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Wake | 5 | Capital Area MPO |  | Division 5 |  | TAANY | ENGINEERING | 240000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (Church Street) | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 60000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (Church Street) | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Wake | 5 | Capital Area MPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 200000 | FY 2026: 200000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (Church Street) | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 50000 | FY 2026: 50000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (Church Street) | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Wake | 5 | Capital Area MPO |  | Division 5 |  | TAANY | CONSTRUCTION | 1160000 | FY 2026: 12000; FY 2027: 1148000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (Church Street) | SR 3014 (Morrisville-Carpenter Road) to Durham County line in Morrisville | Construct sidewalks to fill in gaps. | 2.97 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 290000 | FY 2026: 290000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (Salem Parkway) | NC 150 (Peters Creek Parkway) to the Strollway in Winston-Salem | Construct multi-use path. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | BGDA | CONSTRUCTION | 477000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (Salem Parkway) | NC 150 (Peters Creek Parkway) to the Strollway in Winston-Salem | Construct multi-use path. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | TAANY | CONSTRUCTION | 1600000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (Salem Parkway) | NC 150 (Peters Creek Parkway) to the Strollway in Winston-Salem | Construct multi-use path. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | TADA | CONSTRUCTION | 907000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (Salem Parkway) | NC 150 (Peters Creek Parkway) to the Strollway in Winston-Salem | Construct multi-use path. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | L(M) | CONSTRUCTION | 746000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TAANY | ENGINEERING | 640000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L | ENGINEERING | 306000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | HF(M) | ENGINEERING | 582000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TAANY | RIGHT-OF-WAY | 320000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L | RIGHT-OF-WAY | 80000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | CMAQ | CONSTRUCTION | 131000 | FY 2026: 131000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TAANY | CONSTRUCTION | 3230000 | FY 2026: 3230000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L | CONSTRUCTION | 971000 | FY 2026: 971000
EB-5844 | Bike & Ped | STI (Prioritization) | SR 2154 (Little Texas Road) | SR 2180 (Lane Street) to SR 2126 (Dale Earnhardt Boulevard) in Kannapolis | Construct sidewalk and curb and gutter. | 2.02 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | HF(M) | CONSTRUCTION | 520000 | FY 2026: 520000
EB-5845 | Bike & Ped | STI (Prioritization) | Various | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | TA5T50 | ENGINEERING | 154000
EB-5845 | Bike & Ped | STI (Prioritization) | Various | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | L(M) | ENGINEERING | 38000
EB-5845 | Bike & Ped | STI (Prioritization) | Various | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | TA5T50 | RIGHT-OF-WAY | 224000 | FY 2026: 224000
EB-5845 | Bike & Ped | STI (Prioritization) | Various | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | L(M) | RIGHT-OF-WAY | 56000 | FY 2026: 56000
EB-5845 | Bike & Ped | STI (Prioritization) | Various | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | TA5T50 | CONSTRUCTION | 344000 | FY 2027: 172000; FY 2028: 172000
EB-5845 | Bike & Ped | STI (Prioritization) | Various | S. South Street from SR 1371 (Worth Street) to SR 2426 (Rockford Street); SR 2426 (Rockford Street) from Penn Street to US 52; SR 1371 (Worth Street) from South Street to US 52 in Mount Airy | Construct sidewalks. | 0.69 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | L(M) | CONSTRUCTION | 86000 | FY 2027: 86000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Dare | 1 | Albemarle RPO |  | Division 1 |  | TA5T50 | ENGINEERING | 80000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Dare | 1 | Albemarle RPO |  | Division 1 |  | L(M) | ENGINEERING | 20000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Dare | 1 | Albemarle RPO |  | Division 1 |  | TA5T50 | UTILITIES | 8000 | FY 2026: 8000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Dare | 1 | Albemarle RPO |  | Division 1 |  | L(M) | UTILITIES | 2000 | FY 2026: 2000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Dare | 1 | Albemarle RPO |  | Division 1 |  | TA5T50 | CONSTRUCTION | 5760000 | FY 2027: 2650000; FY 2028: 2304000; FY 2029: 806000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | Cypress Knee Lane to Jejac Street in Kitty Hawk | Construct sidewalk on west side. | 3.87 | Dare | 1 | Albemarle RPO |  | Division 1 |  | L(M) | CONSTRUCTION | 1440000 | FY 2027: 662000; FY 2028: 576000; FY 2029: 202000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TALT5 | ENGINEERING | 96000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L(M) | ENGINEERING | 19000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | HF(M) | ENGINEERING | 5000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TALT5 | RIGHT-OF-WAY | 157000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L(M) | RIGHT-OF-WAY | 16000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | HF(M) | RIGHT-OF-WAY | 23000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TALT5 | CONSTRUCTION | 921000 | FY 2026: 233000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L(M) | CONSTRUCTION | 135000 | FY 2026: 16000
EB-5857 | Bike & Ped | STI (Prioritization) | NC 200 | North Love Chapel Road to Carmel Road in Stanfield | Construct sidewalks and ADA ramps on west side of road. | 0.84 | Stanly | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | HF(M) | CONSTRUCTION | 95000 | FY 2026: 95000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | ENGINEERING | 656000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | ENGINEERING | 164000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | RIGHT-OF-WAY | 16000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | RIGHT-OF-WAY | 4000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | UTILITIES | 112000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | UTILITIES | 28000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | CONSTRUCTION | 960000
EB-5858 | Bike & Ped | STI (Prioritization) | New Route | City of Brevard existing multi-use path to Hawg Wild Smokehouse & Taproom property in Brevard | Construct bicycle and pedestrian bridge across Davidson River. | 0.04 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | CONSTRUCTION | 240000
EB-5859 | Bike & Ped | Locally Selected | Hazelwood Avenue (Plott Creek Road) | Richland Creek Bridge to Will Hyatt Road in Waynesville | Construct pedestrian improvements. | 0.56 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION | Division 14 |  |  |  | 183000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | ENGINEERING | 214000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | ENGINEERING | 53000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | RIGHT-OF-WAY | 184000 | FY 2026: 184000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | RIGHT-OF-WAY | 46000 | FY 2026: 46000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | UTILITIES | 128000 | FY 2026: 128000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | UTILITIES | 32000 | FY 2026: 32000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | CONSTRUCTION | 1920000 | FY 2030: 19000; FY 2031: 1728000; FY 2032: 173000
EB-5860 | Bike & Ped | STI (Prioritization) | SR 2162 (Blythe Street) | US 64 (Brevard Road) to NC 191 (Haywood Road) in Laurel Park | Construct sidewalks. | 0.78 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | CONSTRUCTION | 480000 | FY 2030: 480000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TAANY | ENGINEERING | 148000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | ENGINEERING | 37000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TAANY | RIGHT-OF-WAY | 8000 | FY 2026: 8000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TAANY | UTILITIES | 8000 | FY 2026: 8000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | UTILITIES | 2000 | FY 2026: 2000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TAANY | CONSTRUCTION | 3429000 | FY 2026: 34000; FY 2027: 2778000; FY 2028: 617000
EB-5861 | Bike & Ped | STI (Prioritization) | Third Street Greenway | West of Old Mocksville Road near Grants Creek at existing Salisbury Greenway to Fieldcrest Cannon Lane in Spencer | Construct greenway and sidewalk. | 5.77 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 857000 | FY 2026: 9000; FY 2027: 694000; FY 2028: 154000
EB-5862 | Bike & Ped | STI (Prioritization) | Industrial Park Avenue | Randolph Community College entrance to Continuing Education and Industrial Center in Asheboro | Construct sidewalk on south side. | 0.26 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  |  |  | 20000
EB-5862 | Bike & Ped | STI (Prioritization) | Industrial Park Avenue | Randolph Community College entrance to Continuing Education and Industrial Center in Asheboro | Construct sidewalk on south side. | 0.26 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 118000
EB-5862 | Bike & Ped | STI (Prioritization) | Industrial Park Avenue | Randolph Community College entrance to Continuing Education and Industrial Center in Asheboro | Construct sidewalk on south side. | 0.26 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 29000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 Business (Carthage Street) | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 236000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 Business (Carthage Street) | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | ENGINEERING | 59000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 Business (Carthage Street) | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 120000 | FY 2026: 120000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 Business (Carthage Street) | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 30000 | FY 2026: 30000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 Business (Carthage Street) | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1175000 | FY 2027: 1175000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 Business (Carthage Street) | NC 42 (Wicker Street) to Chatham Street in Sanford | Reduce number of lanes and construct bicycle / pedestrian accommodations. | 0.85 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 294000 | FY 2027: 294000
EB-5864 | Bike & Ped | STI (Prioritization) | Knoll Road | NC 2 (Midland Road) to SR 1843 (Airport Road) near Southern Pines. | Construct multi-use path along Knoll Road to connect with existing Southern Pines Greenway on Midland Road. | 1.44 | Moore | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | ENGINEERING | 152000
EB-5864 | Bike & Ped | STI (Prioritization) | Knoll Road | NC 2 (Midland Road) to SR 1843 (Airport Road) near Southern Pines. | Construct multi-use path along Knoll Road to connect with existing Southern Pines Greenway on Midland Road. | 1.44 | Moore | 8 | Sandhills MPO |  | Division 8 |  | L(M) | ENGINEERING | 38000
EB-5864 | Bike & Ped | STI (Prioritization) | Knoll Road | NC 2 (Midland Road) to SR 1843 (Airport Road) near Southern Pines. | Construct multi-use path along Knoll Road to connect with existing Southern Pines Greenway on Midland Road. | 1.44 | Moore | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | CONSTRUCTION | 2880000 | FY 2026: 2880000
EB-5864 | Bike & Ped | STI (Prioritization) | Knoll Road | NC 2 (Midland Road) to SR 1843 (Airport Road) near Southern Pines. | Construct multi-use path along Knoll Road to connect with existing Southern Pines Greenway on Midland Road. | 1.44 | Moore | 8 | Sandhills MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 720000 | FY 2026: 720000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 61000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 15000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 80000 | FY 2026: 80000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | UTILITIES | 72000 | FY 2026: 72000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | UTILITIES | 18000 | FY 2026: 18000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 744000 | FY 2028: 521000; FY 2029: 223000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (Atkinson Street) | US 401 Business (South Main Street) to West Vance Street in Laurinburg | Construct sidewalks. | 0.96 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 186000 | FY 2028: 186000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 119000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | ENGINEERING | 30000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 496000 | FY 2026: 496000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 124000 | FY 2026: 124000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 480000 | FY 2026: 480000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | UTILITIES | 120000 | FY 2026: 120000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 812000 | FY 2027: 812000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (Fields Drive) | SR 1237 (Carthage Street) to US 421 Business (Future I-685 / Horner Boulevard) in Sanford | Construct sidewalk. | 0.99 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 203000 | FY 2027: 203000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 93000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | ENGINEERING | 23000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 89000 | FY 2026: 89000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 22000 | FY 2026: 22000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 80000 | FY 2026: 80000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | UTILITIES | 20000 | FY 2026: 20000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 884000 | FY 2027: 884000
EB-5868 | Bike & Ped | STI (Prioritization) | Woodland Street | Evergreen Lane to Globe Street in Sanford | Construct sidewalk. | 1.25 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 221000 | FY 2027: 221000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (Johnson Street) | US 15 / US 501 to Mike Place in Aberdeen | Construct sidewalks. | 0.39 | Moore | 8 | Sandhills MPO |  | Division 8 |  |  |  | 34000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (Johnson Street) | US 15 / US 501 to Mike Place in Aberdeen | Construct sidewalks. | 0.39 | Moore | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | RIGHT-OF-WAY | 24000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (Johnson Street) | US 15 / US 501 to Mike Place in Aberdeen | Construct sidewalks. | 0.39 | Moore | 8 | Sandhills MPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 6000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (Johnson Street) | US 15 / US 501 to Mike Place in Aberdeen | Construct sidewalks. | 0.39 | Moore | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | CONSTRUCTION | 240000 | FY 2027: 178000; FY 2028: 62000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (Johnson Street) | US 15 / US 501 to Mike Place in Aberdeen | Construct sidewalks. | 0.39 | Moore | 8 | Sandhills MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 60000 | FY 2027: 60000
EB-5872 | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Sunset Drive in Laurinburg | Construct sidewalk on west side, and provide pedestrian accommodations at US 15 / US 401 / US 501 intersection and across US 74. | 1.2 | Scotland | 8 | Lumber River RPO | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A. | Division 8 |  |  |  | 87000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 70000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 17000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 133000 | FY 2027: 133000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 33000 | FY 2027: 33000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 348000 | FY 2029: 348000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (West Boulevard) | SR 1105 (Turnpike Road) to Glasgow Drive and east of US 15 / US 401 / US 501 to Sunset Drive in Laurinburg. | Construct sidewalk on west side. | 1.27 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 88000 | FY 2029: 88000
EB-5872B | Bike & Ped | Locally Selected | SR 1108 (West Boulevard) | Glasgow Drive to east of US 15 / US 401 / US 501 (McColl Road) in Laurinburg. | Provide pedestrian accommodations at US 15 / US 401 / US 501 intersection and across US 74. |  | Scotland | 8 | Lumber River RPO |  | Exempt
EB-5873 | Bike & Ped | STI (Prioritization) | SR 1278 (University Parkway) | SR 1300 (East Green Drive) to SR 1113 (East Martin Luther King Jr. Drive) in High Point | Construct sidewalk. | 0.6 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 344000
EB-5873 | Bike & Ped | STI (Prioritization) | SR 1278 (University Parkway) | SR 1300 (East Green Drive) to SR 1113 (East Martin Luther King Jr. Drive) in High Point | Construct sidewalk. | 0.6 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 86000
EB-5874 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Johnson Street to SR 1278 (University Parkway) in High Point | Construct sidewalk. | 0.65 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 680000
EB-5874 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Johnson Street to SR 1278 (University Parkway) in High Point | Construct sidewalk. | 0.65 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 170000
EB-5876 | Bike & Ped | STI (Prioritization) | Holden Road | SR 4121 (West Gate City Boulevard) to Isler Street in Greensboro | Construct sidewalks. | 1.56 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | Division 7 |  |  |  | 393000
EB-5877 | Bike & Ped | STI (Prioritization) | Farmington Drive | Holden Road to SR 4121 (West Gate City Boulevard) in Greensboro | Construct sidewalks. | 0.97 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 86000
EB-5877 | Bike & Ped | STI (Prioritization) | Farmington Drive | Holden Road to SR 4121 (West Gate City Boulevard) in Greensboro | Construct sidewalks. | 0.97 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | RIGHT-OF-WAY | 20000
EB-5877 | Bike & Ped | STI (Prioritization) | Farmington Drive | Holden Road to SR 4121 (West Gate City Boulevard) in Greensboro | Construct sidewalks. | 0.97 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | RIGHT-OF-WAY | 5000
EB-5877 | Bike & Ped | STI (Prioritization) | Farmington Drive | Holden Road to SR 4121 (West Gate City Boulevard) in Greensboro | Construct sidewalks. | 0.97 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 960000 | FY 2026: 960000
EB-5877 | Bike & Ped | STI (Prioritization) | Farmington Drive | Holden Road to SR 4121 (West Gate City Boulevard) in Greensboro | Construct sidewalks. | 0.97 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | CONSTRUCTION | 240000 | FY 2026: 240000
EB-5878 | Bike & Ped | STI (Prioritization) | West Meadowview Road | SR 1007 (Randleman Road) to South Elm-Eugene Street in Greensboro | Construct sidewalks. | 0.47 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 18000
EB-5878 | Bike & Ped | STI (Prioritization) | West Meadowview Road | SR 1007 (Randleman Road) to South Elm-Eugene Street in Greensboro | Construct sidewalks. | 0.47 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | RIGHT-OF-WAY | 40000
EB-5878 | Bike & Ped | STI (Prioritization) | West Meadowview Road | SR 1007 (Randleman Road) to South Elm-Eugene Street in Greensboro | Construct sidewalks. | 0.47 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | RIGHT-OF-WAY | 10000
EB-5878 | Bike & Ped | STI (Prioritization) | West Meadowview Road | SR 1007 (Randleman Road) to South Elm-Eugene Street in Greensboro | Construct sidewalks. | 0.47 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 760000 | FY 2026: 760000
EB-5878 | Bike & Ped | STI (Prioritization) | West Meadowview Road | SR 1007 (Randleman Road) to South Elm-Eugene Street in Greensboro | Construct sidewalks. | 0.47 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | CONSTRUCTION | 190000 | FY 2026: 190000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  |  |  | 16000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | ENGINEERING | 13000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | ENGINEERING | 3000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 2640000 | FY 2029: 2640000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 660000 | FY 2029: 660000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | UTILITIES | 760000 | FY 2029: 760000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | UTILITIES | 190000 | FY 2029: 190000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 744000 | FY 2032: 744000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | SR 1716 (Graham-Hopedale Road) to SR 1719 (Sellars Mill Road) in Burlington | Construct sidewalk. | 0.41 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 186000 | FY 2032: 186000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | ENGINEERING | 71000 | FY 2026: 71000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 18000 | FY 2026: 18000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 64000 | FY 2027: 64000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 16000 | FY 2027: 16000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | UTILITIES | 144000 | FY 2027: 144000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | UTILITIES | 36000 | FY 2027: 36000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | CONSTRUCTION | 552000 | FY 2028: 6000; FY 2029: 546000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (Jones Ferry Road) | Davie Road to SR 1010 (West Main Street) in Carrboro | Construct sidewalk on north side. | 0.51 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 138000 | FY 2028: 138000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (Wendover Avenue) | Grecade Street to SR 1001 (North Church Street) and SR 2526 (Summit Avenue) to US 29 (North O'Henry Boulevard) in Greensboro | Construct sidewalks. | 2.21 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 381000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (Wendover Avenue) | Grecade Street to SR 1001 (North Church Street) and SR 2526 (Summit Avenue) to US 29 (North O'Henry Boulevard) in Greensboro | Construct sidewalks. | 2.21 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 237000 | FY 2026: 237000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (Wendover Avenue) | Grecade Street to SR 1001 (North Church Street) and SR 2526 (Summit Avenue) to US 29 (North O'Henry Boulevard) in Greensboro | Construct sidewalks. | 2.21 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 59000 | FY 2026: 59000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (Wendover Avenue) | Grecade Street to SR 1001 (North Church Street) and SR 2526 (Summit Avenue) to US 29 (North O'Henry Boulevard) in Greensboro | Construct sidewalks. | 2.21 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 2249000 | FY 2028: 2249000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (Wendover Avenue) | Grecade Street to SR 1001 (North Church Street) and SR 2526 (Summit Avenue) to US 29 (North O'Henry Boulevard) in Greensboro | Construct sidewalks. | 2.21 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 562000 | FY 2028: 562000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 24000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 6000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | UTILITIES | 600000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | UTILITIES | 150000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 568000 | FY 2026: 568000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (North Church Street) | Beaumont Avenue to SR 1716 (Graham-Hopedale Road) in Burlington | Construct sidewalk. | 0.47 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 142000 | FY 2026: 142000
EB-5886 | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) in Carrboro to NC 86 (Martin Luther King, Jr. Boulevard) in Chapel Hill | Construct bicycle and pedestrian improvements. | 1.7 | Orange | 7 | Triangle West TPO |  | Division 7
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | ENGINEERING | 136000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | ENGINEERING | 34000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | RIGHT-OF-WAY | 720000 | FY 2030: 360000; FY 2031: 360000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | RIGHT-OF-WAY | 180000 | FY 2030: 90000; FY 2031: 90000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | UTILITIES | 880000 | FY 2030: 880000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | UTILITIES | 220000 | FY 2030: 220000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | CONSTRUCTION | 5600000 | FY 2033: 58000; FY 2034: 3643000; FY 2035: 1676000 | 223000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | SR 1772 (North Greensboro Street) to south of Norfolk-Southern Railroad tracks in Carrboro. | Construct bicycle and pedestrian improvements. | 0.43 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | CONSTRUCTION | 1400000 | FY 2033: 14000; FY 2034: 911000; FY 2035: 419000 | 56000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | ENGINEERING | 427000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | ENGINEERING | 107000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | RIGHT-OF-WAY | 691000 | FY 2028: 691000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | RIGHT-OF-WAY | 173000 | FY 2028: 173000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | CONSTRUCTION | 2483000 | FY 2031: 1788000; FY 2032: 695000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (Estes Drive) | South of Norfolk-Southern Railroad tracks to NC 86 (Martin Luther King Jr. Blvd) in Chapel Hill. | Construct bicycle and pedestrian improvements. | 1.29 | Orange | 7 | Triangle West TPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | CONSTRUCTION | 621000 | FY 2031: 447000; FY 2032: 174000
EB-5888 | Bike & Ped | STI (Prioritization) | SR 1747 (East Stadium Drive) | SR 1962 (North Pierce Street) to Freedom Park in Eden | Construct sidewalk. | 0.57 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  |  |  | 124000
EB-5888 | Bike & Ped | STI (Prioritization) | SR 1747 (East Stadium Drive) | SR 1962 (North Pierce Street) to Freedom Park in Eden | Construct sidewalk. | 0.57 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | TA5T50 | CONSTRUCTION | 1518000 | FY 2026: 17000; FY 2027: 1501000
EB-5888 | Bike & Ped | STI (Prioritization) | SR 1747 (East Stadium Drive) | SR 1962 (North Pierce Street) to Freedom Park in Eden | Construct sidewalk. | 0.57 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | L(M) | CONSTRUCTION | 383000 | FY 2026: 219000; FY 2027: 164000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (West Main Street); SR 1539 (Penny Road) | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 2000000 | FY 2027: 2000000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (West Main Street); SR 1539 (Penny Road) | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 500000 | FY 2027: 500000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (West Main Street); SR 1539 (Penny Road) | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | UTILITIES | 1520000 | FY 2027: 1520000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (West Main Street); SR 1539 (Penny Road) | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 380000 | FY 2027: 380000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (West Main Street); SR 1539 (Penny Road) | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 3281000 | FY 2030: 33000; FY 2031: 3018000; FY 2032: 230000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (West Main Street); SR 1539 (Penny Road) | Existing sidewalk on SR 1486 (West Main Street) to park access on SR 1539 (Penny Road) in Jamestown | Construct sidewalk with curb and gutter. | 0.7 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 820000 | FY 2030: 820000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | ENGINEERING | 37000 | FY 2026: 37000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | ENGINEERING | 9000 | FY 2026: 9000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 336000 | FY 2027: 336000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 84000 | FY 2027: 84000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | UTILITIES | 184000 | FY 2027: 184000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | UTILITIES | 46000 | FY 2027: 46000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | TAANY | CONSTRUCTION | 360000 | FY 2028: 4000; FY 2029: 356000
EB-5890 | Bike & Ped | STI (Prioritization) | Barnes Street | King Street to SR 1005 (Jones Ferry Road) in Carrboro | Construct sidewalk. | 0.25 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 90000 | FY 2028: 90000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  |  |  | 130000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | TALT5 | ENGINEERING | 280000 | FY 2026: 280000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | L(M) | ENGINEERING | 70000 | FY 2026: 70000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | TALT5 | RIGHT-OF-WAY | 408000 | FY 2030: 408000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 102000 | FY 2030: 102000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | TALT5 | UTILITIES | 1040000 | FY 2030: 520000; FY 2031: 520000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | L(M) | UTILITIES | 260000 | FY 2030: 130000; FY 2031: 130000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | TALT5 | CONSTRUCTION | 5279000 | FY 2032: 1376000; FY 2033: 3328000; FY 2034: 575000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 Business | East Jackson Street to Mayo River State Park in Mayodan | Construct multi-use path. | 1.37 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | L(M) | CONSTRUCTION | 1320000 | FY 2032: 344000; FY 2033: 832000; FY 2034: 144000
EB-5894 | Bike & Ped | STI (Prioritization) | Black Creek Greenway | West Dynasty Drive to Old Reedy Creek Road in Cary | Construct greenway. | 2.74 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | CMAQ | CONSTRUCTION | 985000
EB-5894 | Bike & Ped | STI (Prioritization) | Black Creek Greenway | West Dynasty Drive to Old Reedy Creek Road in Cary | Construct greenway. | 2.74 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | TAANY | CONSTRUCTION | 11112000
EB-5894 | Bike & Ped | STI (Prioritization) | Black Creek Greenway | West Dynasty Drive to Old Reedy Creek Road in Cary | Construct greenway. | 2.74 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 3024000
EB-5895 | Bike & Ped | STI (Prioritization) | NC 55 (East Williams Street) | SR 1301 (Sunset Lake Road) to NC 55 in Holly Springs | Construct sidewalk. | 0.9 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  |  |  | 100000
EB-5895 | Bike & Ped | STI (Prioritization) | NC 55 (East Williams Street) | SR 1301 (Sunset Lake Road) to NC 55 in Holly Springs | Construct sidewalk. | 0.9 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | TAANY | CONSTRUCTION | 400000
EB-5895 | Bike & Ped | STI (Prioritization) | NC 55 (East Williams Street) | SR 1301 (Sunset Lake Road) to NC 55 in Holly Springs | Construct sidewalk. | 0.9 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 100000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (West Naomi Street) | West Academy Street to US 220 Business (South Main Street) in Randleman | Construct sidewalk, implement road diet, and install raised crosswalk and median. |  | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  |  |  | 50000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (West Naomi Street) | West Academy Street to US 220 Business (South Main Street) in Randleman | Construct sidewalk, implement road diet, and install raised crosswalk and median. |  | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 1520000 | FY 2026: 1520000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (West Naomi Street) | West Academy Street to US 220 Business (South Main Street) in Randleman | Construct sidewalk, implement road diet, and install raised crosswalk and median. |  | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 380000 | FY 2026: 380000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (West Naomi Street) | West Academy Street to US 220 Business (South Main Street) in Randleman | Construct sidewalk, implement road diet, and install raised crosswalk and median. |  | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 2316000 | FY 2027: 2061000; FY 2028: 255000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (West Naomi Street) | West Academy Street to US 220 Business (South Main Street) in Randleman | Construct sidewalk, implement road diet, and install raised crosswalk and median. |  | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 584000 | FY 2027: 584000
EB-5899 | Bike & Ped | STI (Prioritization) | NC 731 (East Allenton Street) | Existing sidewalk on NC 731 to Stanbeck Park in Mt. Gilead | Construct sidewalk. | 0.19 | Montgomery | 8 | Piedmont Triad RPO |  | Division 8 |  |  |  | 14000
EB-5899 | Bike & Ped | STI (Prioritization) | NC 731 (East Allenton Street) | Existing sidewalk on NC 731 to Stanbeck Park in Mt. Gilead | Construct sidewalk. | 0.19 | Montgomery | 8 | Piedmont Triad RPO |  | Division 8 |  | TALT5 | CONSTRUCTION | 222000
EB-5899 | Bike & Ped | STI (Prioritization) | NC 731 (East Allenton Street) | Existing sidewalk on NC 731 to Stanbeck Park in Mt. Gilead | Construct sidewalk. | 0.19 | Montgomery | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 55000
EB-5900 | Bike & Ped | STI (Prioritization) | Summerfield South Greenway | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 432000
EB-5900 | Bike & Ped | STI (Prioritization) | Summerfield South Greenway | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 108000
EB-5900 | Bike & Ped | STI (Prioritization) | Summerfield South Greenway | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 144000 | FY 2026: 144000
EB-5900 | Bike & Ped | STI (Prioritization) | Summerfield South Greenway | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 36000 | FY 2026: 36000
EB-5900 | Bike & Ped | STI (Prioritization) | Summerfield South Greenway | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 5440000 | FY 2026: 5440000
EB-5900 | Bike & Ped | STI (Prioritization) | Summerfield South Greenway | US 220 to Centerfield Road in Summerfield | Construct multi-use path. | 2.58 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 1360000 | FY 2026: 1360000
EB-5903 | Bike & Ped | Locally Selected | Union Street | Tulip Ave Southwest to NC 3 | Construct sidewalk extension. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  |  |  | 10000
EB-5903 | Bike & Ped | Locally Selected | Union Street | Tulip Ave Southwest to NC 3 | Construct sidewalk extension. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | CMAQ | CONSTRUCTION | 373000
EB-5903 | Bike & Ped | Locally Selected | Union Street | Tulip Ave Southwest to NC 3 | Construct sidewalk extension. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | TADA | CONSTRUCTION | 320000
EB-5903 | Bike & Ped | Locally Selected | Union Street | Tulip Ave Southwest to NC 3 | Construct sidewalk extension. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | L(M) | CONSTRUCTION | 173000
EB-5904 | Bike & Ped | STI (Prioritization) | Durham Rail Trail | Pettigrew Street to Avondale Drive in Durham | Construct multi-use trail on former rail corridor. | 1.75 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | DP | CONSTRUCTION | 9000000 | FY 2026: 9000000
EB-5904 | Bike & Ped | STI (Prioritization) | Durham Rail Trail | Pettigrew Street to Avondale Drive in Durham | Construct multi-use trail on former rail corridor. | 1.75 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | BGDA | CONSTRUCTION | 2984000 | FY 2026: 2984000
EB-5904 | Bike & Ped | STI (Prioritization) | Durham Rail Trail | Pettigrew Street to Avondale Drive in Durham | Construct multi-use trail on former rail corridor. | 1.75 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | TAANY | CONSTRUCTION | 1928000 | FY 2026: 1928000
EB-5904 | Bike & Ped | STI (Prioritization) | Durham Rail Trail | Pettigrew Street to Avondale Drive in Durham | Construct multi-use trail on former rail corridor. | 1.75 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | TADA | CONSTRUCTION | 1928000 | FY 2026: 1928000
EB-5904 | Bike & Ped | STI (Prioritization) | Durham Rail Trail | Pettigrew Street to Avondale Drive in Durham | Construct multi-use trail on former rail corridor. | 1.75 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | L(M) | CONSTRUCTION | 4960000 | FY 2026: 4960000
EB-5905 | Bike & Ped | STI (Prioritization) | US 64 Business (Thomas Street) | SR 1005 (East Raleigh Boulevard) to US 64 Business (Sunset Avenue) in Rocky Mount | Add pedestrian signals. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | BG50200 | CONSTRUCTION | 1120000 | FY 2028: 930000; FY 2029: 190000
EB-5905 | Bike & Ped | STI (Prioritization) | US 64 Business (Thomas Street) | SR 1005 (East Raleigh Boulevard) to US 64 Business (Sunset Avenue) in Rocky Mount | Add pedestrian signals. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 280000 | FY 2028: 232000; FY 2029: 48000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | ENGINEERING | 67000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 17000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | RIGHT-OF-WAY | 504000 | FY 2026: 504000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 126000 | FY 2026: 126000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | UTILITIES | 176000 | FY 2026: 176000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | UTILITIES | 44000 | FY 2026: 44000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | CONSTRUCTION | 1120000 | FY 2028: 1120000
EB-5907 | Bike & Ped | STI (Prioritization) | Cross Creek Parks Connector Trail | NC 24 (Bragg Boulevard) to Ray Avenue in Fayetteville | Construct greenway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 280000 | FY 2028: 280000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TADA | ENGINEERING | 1082000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | ENGINEERING | 114000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L(M) | ENGINEERING | 299000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | CRPDA | RIGHT-OF-WAY | 960000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | RIGHT-OF-WAY | 504000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L(M) | RIGHT-OF-WAY | 366000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TADA | CONSTRUCTION | 1132000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | CONSTRUCTION | 11688000
EB-5911 | Bike & Ped | STI (Prioritization) | Old Lenoir Road Multi-Use Path | SR 1312 (9th Street NW) to Hickory Water Plant in Hickory | Construct multi-use path. | 1.76 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L(M) | CONSTRUCTION | 3205000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 288000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TAANY | ENGINEERING | 418000 | FY 2026: 418000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 18000 | FY 2026: 18000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 2487000 | FY 2027: 2487000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 13000 | FY 2027: 13000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 430000 | FY 2027: 430000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 4330000 | FY 2028: 678000; FY 2029: 3652000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (Tuckaseegee Road) | NC 273 to Marina Village Drive; Marina Village Drive North to Broome Street in Mount Holly | Construct sidewalk on south side; Construct sidewalk on west side. | 0.48 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 170000 | FY 2028: 170000
EB-5913 | Bike & Ped | STI (Prioritization) | SR 2014 (Lakewood Road) | SR 2565 (Eagle Road) to Lake Drive in Cramerton | Construct sidewalk and pedestrian bridge over South Fork River Inlet. | 0.14 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 131000
EB-5913 | Bike & Ped | STI (Prioritization) | SR 2014 (Lakewood Road) | SR 2565 (Eagle Road) to Lake Drive in Cramerton | Construct sidewalk and pedestrian bridge over South Fork River Inlet. | 0.14 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 33000
EB-5913 | Bike & Ped | STI (Prioritization) | SR 2014 (Lakewood Road) | SR 2565 (Eagle Road) to Lake Drive in Cramerton | Construct sidewalk and pedestrian bridge over South Fork River Inlet. | 0.14 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 283000 | FY 2026: 283000
EB-5913 | Bike & Ped | STI (Prioritization) | SR 2014 (Lakewood Road) | SR 2565 (Eagle Road) to Lake Drive in Cramerton | Construct sidewalk and pedestrian bridge over South Fork River Inlet. | 0.14 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 71000 | FY 2026: 71000
EB-5916 | Bike & Ped | STI (Prioritization) | Fonta Flora Trail | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TA5200 | ENGINEERING | 448000
EB-5916 | Bike & Ped | STI (Prioritization) | Fonta Flora Trail | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | McDowell | 13 | Foothills RPO |  | Division 13 |  | L | ENGINEERING | 112000
EB-5916 | Bike & Ped | STI (Prioritization) | Fonta Flora Trail | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | RIGHT-OF-WAY | 48000 | FY 2026: 48000
EB-5916 | Bike & Ped | STI (Prioritization) | Fonta Flora Trail | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | McDowell | 13 | Foothills RPO |  | Division 13 |  | L | RIGHT-OF-WAY | 12000 | FY 2026: 12000
EB-5916 | Bike & Ped | STI (Prioritization) | Fonta Flora Trail | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | McDowell | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | CONSTRUCTION | 3759000 | FY 2026: 3759000
EB-5916 | Bike & Ped | STI (Prioritization) | Fonta Flora Trail | US 70 to SR 1221 (Resistoflex Road) in Marion | Construct greenway. | 1.57 | McDowell | 13 | Foothills RPO |  | Division 13 |  | L | CONSTRUCTION | 941000 | FY 2026: 941000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | ENGINEERING | 160000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 40000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | RIGHT-OF-WAY | 160000 | FY 2027: 160000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2027: 40000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | UTILITIES | 640000 | FY 2027: 640000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 160000 | FY 2027: 160000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | CONSTRUCTION | 720000 | FY 2028: 7000; FY 2029: 713000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (Jonestown Road) | East of US 421 to SR 1001 (Country Club Road) in Winston-Salem | Construct sidewalk along Jonestown Road. | 0.64 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 180000 | FY 2028: 180000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | ENGINEERING | 360000 | FY 2026: 360000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L(M) | ENGINEERING | 90000 | FY 2026: 90000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | RIGHT-OF-WAY | 560000 | FY 2030: 560000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L(M) | RIGHT-OF-WAY | 140000 | FY 2030: 140000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | UTILITIES | 880000 | FY 2030: 880000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L(M) | UTILITIES | 220000 | FY 2030: 220000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | CONSTRUCTION | 2080000 | FY 2033: 21000; FY 2034: 2059000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (North Main Street) | 12th Street to 22nd Street in Kannapolis | Construct sidewalk. | 0.92 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L(M) | CONSTRUCTION | 520000 | FY 2033: 520000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 104000 | FY 2027: 104000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 26000 | FY 2027: 26000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | UTILITIES | 368000 | FY 2027: 368000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 92000 | FY 2027: 92000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 432000 | FY 2027: 432000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (Eastchester Drive) | Centennial Street to Lassiter Drive in High Point | Construct sidewalk. | 0.41 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 108000 | FY 2027: 108000
EB-5923 | Bike & Ped | STI (Prioritization) | SR 1432 (Skyland Drive) | SR 1429 (Chipper Curve Road) to US 23 Business in Sylva | Construct sidewalk. | 0.72 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 110000
EB-5923 | Bike & Ped | STI (Prioritization) | SR 1432 (Skyland Drive) | SR 1429 (Chipper Curve Road) to US 23 Business in Sylva | Construct sidewalk. | 0.72 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | TALT5 | CONSTRUCTION | 768000
EB-5923 | Bike & Ped | STI (Prioritization) | SR 1432 (Skyland Drive) | SR 1429 (Chipper Curve Road) to US 23 Business in Sylva | Construct sidewalk. | 0.72 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | L(M) | CONSTRUCTION | 192000
EB-5924 | Bike & Ped | Locally Selected | New Route | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Watauga | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS. | Exempt |  | FLAP | ENGINEERING | 486000 | FY 2026: 4000
EB-5924 | Bike & Ped | Locally Selected | New Route | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Watauga | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS. | Exempt |  | L(M) | ENGINEERING | 117000
EB-5924 | Bike & Ped | Locally Selected | New Route | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Watauga | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS. | Exempt |  | FLAP | CONSTRUCTION | 1306000 | FY 2026: 1306000
EB-5924 | Bike & Ped | Locally Selected | New Route | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Watauga | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS. | Exempt |  | L(M) | CONSTRUCTION | 169000 | FY 2026: 169000
EB-5924 | Bike & Ped | Locally Selected | New Route | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Watauga | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 145000 | FY 2026: 145000
EB-5924 | Bike & Ped | Locally Selected | New Route | Middle Fork Greenway in Blowing Rock | Construct greenway. |  | Watauga | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $150 K OF HF(M)/HF IS CONTINGENCY FUNDS. | Exempt |  | HF | CONSTRUCTION | 6000 | FY 2026: 6000
EB-5926 | Bike & Ped | Locally Selected | US 19 (Soco Road) | US 276 to Fie Top Road in Maggie Valley | Construct bicycle and pedestrian improvements. |  | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  |  |  | 241000
EB-5926 | Bike & Ped | Locally Selected | US 19 (Soco Road) | US 276 to Fie Top Road in Maggie Valley | Construct bicycle and pedestrian improvements. |  | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  | BGANY | CONSTRUCTION | 80000
EB-5926 | Bike & Ped | Locally Selected | US 19 (Soco Road) | US 276 to Fie Top Road in Maggie Valley | Construct bicycle and pedestrian improvements. |  | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  | BGDA | CONSTRUCTION | 1440000
EB-5926 | Bike & Ped | Locally Selected | US 19 (Soco Road) | US 276 to Fie Top Road in Maggie Valley | Construct bicycle and pedestrian improvements. |  | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  | L(M) | CONSTRUCTION | 380000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | TADA | ENGINEERING | 186000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | ENGINEERING | 79000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | TADA | RIGHT-OF-WAY | 362000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | RIGHT-OF-WAY | 155000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | BGANY | CONSTRUCTION | 1159000 | FY 2026: 1159000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | BGDA | CONSTRUCTION | 9000 | FY 2026: 9000
EB-5929 | Bike & Ped | Locally Selected | South McDowell Street | Baxter Street to SR 1798 (East Stonewall Street) in Charlotte | Construct bike lanes and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | CONSTRUCTION | 501000 | FY 2026: 501000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  |  |  | 170000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | ENGINEERING | 203000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 109000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | RIGHT-OF-WAY | 129000 | FY 2026: 129000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 70000 | FY 2026: 70000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | CONSTRUCTION | 1055000 | FY 2026: 1055000
EB-5930 | Bike & Ped | Locally Selected | Rumple Street; Wagner Street | US 21 / NC 115 to Thomas Street; US 21 / NC 115 to West Avenue in Troutman | Improve sidewalks. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 568000 | FY 2026: 568000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | ENGINEERING | 20000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | ENGINEERING | 5000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | TADA | RIGHT-OF-WAY | 1207000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | RIGHT-OF-WAY | 302000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | CMAQ | CONSTRUCTION | 4013000 | FY 2026: 4013000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | CONSTRUCTION | 1322000 | FY 2027: 1322000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L(M) | CONSTRUCTION | 330000 | FY 2027: 330000
EB-5931 | Bike & Ped | Locally Selected | North Indian Trail Road | SR 1371 (Southfork Road) to Liberty Lane in Indian Trail | Construct complete street. Construct intersection improvements at SR 1008 (Indian Trail Road) and SR 1367 (Unionville-Indian Trail Road). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | CONSTRUCTION | 1726000 | FY 2026: 1726000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  |  |  | 80000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | ENGINEERING | 97000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | ENGINEERING | 25000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | RIGHT-OF-WAY | 174000 | FY 2026: 174000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | RIGHT-OF-WAY | 43000 | FY 2026: 43000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | CONSTRUCTION | 1000000 | FY 2027: 1000000
EB-5932 | Bike & Ped | Locally Selected | Richardson Greenway South, US 21 / NC 115 (South Main Street) | Troutman Elementary School to Jacobs Woods subdivision in Troutman | Construct greenway. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | L(M) | CONSTRUCTION | 250000 | FY 2027: 250000
EB-5933 | Bike & Ped | Locally Selected | Kincaid Multi-Use Path | Eugenia Street and Spring Street to South Prong Rocky River Greenway near Davidson Elementary in Davidson | Construct multi-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | ENGINEERING | 175000
EB-5933 | Bike & Ped | Locally Selected | Kincaid Multi-Use Path | Eugenia Street and Spring Street to South Prong Rocky River Greenway near Davidson Elementary in Davidson | Construct multi-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | ENGINEERING | 44000
EB-5933 | Bike & Ped | Locally Selected | Kincaid Multi-Use Path | Eugenia Street and Spring Street to South Prong Rocky River Greenway near Davidson Elementary in Davidson | Construct multi-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | CONSTRUCTION | 702000 | FY 2026: 702000
EB-5933 | Bike & Ped | Locally Selected | Kincaid Multi-Use Path | Eugenia Street and Spring Street to South Prong Rocky River Greenway near Davidson Elementary in Davidson | Construct multi-use path. |  | Mecklenburg | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | CONSTRUCTION | 176000 | FY 2026: 176000
EB-5935 | Bike & Ped | Locally Selected | Centennial Boulevard | North Lookout Street to Main Street in Claremont | Construct sidewalk. | 1.16 | Catawba | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | ENGINEERING | 8000
EB-5935 | Bike & Ped | Locally Selected | Centennial Boulevard | North Lookout Street to Main Street in Claremont | Construct sidewalk. | 1.16 | Catawba | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L(M) | ENGINEERING | 2000
EB-5935 | Bike & Ped | Locally Selected | Centennial Boulevard | North Lookout Street to Main Street in Claremont | Construct sidewalk. | 1.16 | Catawba | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | CONSTRUCTION | 472000
EB-5935 | Bike & Ped | Locally Selected | Centennial Boulevard | North Lookout Street to Main Street in Claremont | Construct sidewalk. | 1.16 | Catawba | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L(M) | CONSTRUCTION | 118000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | TADA | ENGINEERING | 400000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | L(M) | ENGINEERING | 100000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | TADA | RIGHT-OF-WAY | 180000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | L(M) | RIGHT-OF-WAY | 45000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 1420000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | BGDA | CONSTRUCTION | 1232000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | TADA | CONSTRUCTION | 58000
EB-5937 | Bike & Ped | Locally Selected | Book Walk | City Walk to Ridgeview Library in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | $1.420M STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | L(M) | CONSTRUCTION | 678000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | TADA | ENGINEERING | 640000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L(M) | ENGINEERING | 160000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | TADA | RIGHT-OF-WAY | 84000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L(M) | RIGHT-OF-WAY | 21000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 2476000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | TAANY | CONSTRUCTION | 1600000
EB-5938 | Bike & Ped | Locally Selected | Book Walk South | Ridgeview Library to Walmart in Hickory | Construct multi-use path. | 0.61 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L(M) | CONSTRUCTION | 1019000
EB-5939 | Bike & Ped | Locally Selected | Riverwalk | Old Lenoir Road at City owned property to end of proposed Rosales Bridge in Hickory | Construct multi-use path. | 0.59 | Burke | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 13 |  |  |  | 2500000
EB-5939 | Bike & Ped | Locally Selected | Riverwalk | Old Lenoir Road at City owned property to end of proposed Rosales Bridge in Hickory | Construct multi-use path. | 0.59 | Burke | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 13 |  | BGDA | CONSTRUCTION | 5200000
EB-5939 | Bike & Ped | Locally Selected | Riverwalk | Old Lenoir Road at City owned property to end of proposed Rosales Bridge in Hickory | Construct multi-use path. | 0.59 | Burke | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 13 |  | L(M) | CONSTRUCTION | 1300000
EB-5944 | Bike & Ped | Locally Selected | SR 1319 (Johnston Boulevard) | SR 3548 (Patton Avenue) to Iona Circle in Asheville | Construct sidewalks. | 0.95 | Buncombe | 13 | French Broad River MPO | $1.88M OF STBG-DA FUNDS SWAPPED FOR $1.88M IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | TAANY | CONSTRUCTION | 1880000
EB-5944 | Bike & Ped | Locally Selected | SR 1319 (Johnston Boulevard) | SR 3548 (Patton Avenue) to Iona Circle in Asheville | Construct sidewalks. | 0.95 | Buncombe | 13 | French Broad River MPO | $1.88M OF STBG-DA FUNDS SWAPPED FOR $1.88M IN TAP-ANYAREA FUNDS ON 12-12-24. | Division 13 |  | L | CONSTRUCTION | 470000
EB-5946 | Bike & Ped | Locally Selected | NC 280 | French Broad River to NC 191 (Haywood Road) in Mills River | Construct multi-use path. | 3.09 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TADA | ENGINEERING | 300000 | FY 2026: 300000
EB-5946 | Bike & Ped | Locally Selected | NC 280 | French Broad River to NC 191 (Haywood Road) in Mills River | Construct multi-use path. | 3.09 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | ENGINEERING | 75000 | FY 2026: 75000
EB-5947 | Bike & Ped | Locally Selected | SR 2032 (New Haw Creek Road) | Beverly Road to SR 2034 (Bell Road) in Asheville | Construct sidewalks. | 0.79 | Buncombe | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 8000
EB-5947 | Bike & Ped | Locally Selected | SR 2032 (New Haw Creek Road) | Beverly Road to SR 2034 (Bell Road) in Asheville | Construct sidewalks. | 0.79 | Buncombe | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | L(M) | ENGINEERING | 2000
EB-5947 | Bike & Ped | Locally Selected | SR 2032 (New Haw Creek Road) | Beverly Road to SR 2034 (Bell Road) in Asheville | Construct sidewalks. | 0.79 | Buncombe | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | BGANY | CONSTRUCTION | 1892000
EB-5947 | Bike & Ped | Locally Selected | SR 2032 (New Haw Creek Road) | Beverly Road to SR 2034 (Bell Road) in Asheville | Construct sidewalks. | 0.79 | Buncombe | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | L(M) | CONSTRUCTION | 473000
EB-5948 | Bike & Ped | Locally Selected | SR 3075 (Onteora Boulevard) | Lincoln Avenue to Raleigh Road in Asheville | Construct sidewalks. | 0.39 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | BGDA | CONSTRUCTION | 572000
EB-5948 | Bike & Ped | Locally Selected | SR 3075 (Onteora Boulevard) | Lincoln Avenue to Raleigh Road in Asheville | Construct sidewalks. | 0.39 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | TADA | CONSTRUCTION | 340000
EB-5948 | Bike & Ped | Locally Selected | SR 3075 (Onteora Boulevard) | Lincoln Avenue to Raleigh Road in Asheville | Construct sidewalks. | 0.39 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | L(M) | CONSTRUCTION | 228000
EB-5949 | Bike & Ped | Locally Selected | NC 51 | Johnston Drive intersection in Pineville | Relocate Johnston Drive to align with existing Church Street intersection. | 0.06 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 OF NC194 EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | BGDA | CONSTRUCTION | 1175000
EB-5949 | Bike & Ped | Locally Selected | NC 51 | Johnston Drive intersection in Pineville | Relocate Johnston Drive to align with existing Church Street intersection. | 0.06 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 OF NC194 EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | O | CONSTRUCTION | 2576000
EB-5949 | Bike & Ped | Locally Selected | NC 51 | Johnston Drive intersection in Pineville | Relocate Johnston Drive to align with existing Church Street intersection. | 0.06 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 OF NC194 EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | L(M) | CONSTRUCTION | 653000
EB-5950 | Highway | Locally Selected | SR 1305 (Kensington Drive) | NC 16 to Sunset Hill Road in Waxhaw. | Improve corridor. | 0.24 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | RIGHT-OF-WAY | 421000
EB-5950 | Highway | Locally Selected | SR 1305 (Kensington Drive) | NC 16 to Sunset Hill Road in Waxhaw. | Improve corridor. | 0.24 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | RIGHT-OF-WAY | 170000
EB-5950 | Highway | Locally Selected | SR 1305 (Kensington Drive) | NC 16 to Sunset Hill Road in Waxhaw. | Improve corridor. | 0.24 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGANY | CONSTRUCTION | 2749000 | FY 2026: 2749000
EB-5950 | Highway | Locally Selected | SR 1305 (Kensington Drive) | NC 16 to Sunset Hill Road in Waxhaw. | Improve corridor. | 0.24 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | CONSTRUCTION | 375000 | FY 2026: 375000
EB-5950 | Highway | Locally Selected | SR 1305 (Kensington Drive) | NC 16 to Sunset Hill Road in Waxhaw. | Improve corridor. | 0.24 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L(M) | CONSTRUCTION | 1215000 | FY 2026: 1215000
EB-5952 | Bike & Ped | Locally Selected | Fairlawn Drive | NC 67 (Reynolda Road) to SR 1528 (Silas Creek Parkway) in Winston-Salem | Construct sidewalk. | 0.39 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 99000
EB-5952 | Bike & Ped | Locally Selected | Fairlawn Drive | NC 67 (Reynolda Road) to SR 1528 (Silas Creek Parkway) in Winston-Salem | Construct sidewalk. | 0.39 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 198000
EB-5952 | Bike & Ped | Locally Selected | Fairlawn Drive | NC 67 (Reynolda Road) to SR 1528 (Silas Creek Parkway) in Winston-Salem | Construct sidewalk. | 0.39 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 50000
EB-5952 | Bike & Ped | Locally Selected | Fairlawn Drive | NC 67 (Reynolda Road) to SR 1528 (Silas Creek Parkway) in Winston-Salem | Construct sidewalk. | 0.39 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 593000
EB-5952 | Bike & Ped | Locally Selected | Fairlawn Drive | NC 67 (Reynolda Road) to SR 1528 (Silas Creek Parkway) in Winston-Salem | Construct sidewalk. | 0.39 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 148000
EB-5953 | Bike & Ped | Locally Selected | SR 4000 (University Parkway) | SR 1686 (Shattalon Drive) to Robin Wood Lane in Winston-Salem | Construct sidewalk. | 0.3 | Forsyth | 9 | Winston-Salem Area TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | Division 9 |  |  |  | 95000
EB-5953 | Bike & Ped | Locally Selected | SR 4000 (University Parkway) | SR 1686 (Shattalon Drive) to Robin Wood Lane in Winston-Salem | Construct sidewalk. | 0.3 | Forsyth | 9 | Winston-Salem Area TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | Division 9 |  | BGDA | CONSTRUCTION | 508000 | FY 2028: 508000
EB-5953 | Bike & Ped | Locally Selected | SR 4000 (University Parkway) | SR 1686 (Shattalon Drive) to Robin Wood Lane in Winston-Salem | Construct sidewalk. | 0.3 | Forsyth | 9 | Winston-Salem Area TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | Division 9 |  | L(M) | CONSTRUCTION | 127000 | FY 2028: 127000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 226000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | ENGINEERING | 32000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | ENGINEERING | 8000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 234000 | FY 2026: 234000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 59000 | FY 2026: 59000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 2944000 | FY 2028: 2944000
EB-5954 | Bike & Ped | Locally Selected | Griffith Road | Kimwell Drive to Burke Mill Road in Winston-Salem | Construct sidewalk. | 1.07 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 736000 | FY 2028: 736000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 70000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | ENGINEERING | 42000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | ENGINEERING | 11000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 53000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 13000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 376000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 286000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (Robinhood Road) | Speaks Farm Road to Muddy Creek Greenway in Winston-Salem | Construct sidewalk. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 166000
EB-5956 | Bike & Ped | Locally Selected | SR 1992 (Sullivantown Road) | US 311 at Harley Drive to Walkertown High / Middle School in Walkertown | Install bicycle and pedestrian facilities and construct sidewalk. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 70000
EB-5956 | Bike & Ped | Locally Selected | SR 1992 (Sullivantown Road) | US 311 at Harley Drive to Walkertown High / Middle School in Walkertown | Install bicycle and pedestrian facilities and construct sidewalk. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 694000 | FY 2026: 694000
EB-5956 | Bike & Ped | Locally Selected | SR 1992 (Sullivantown Road) | US 311 at Harley Drive to Walkertown High / Middle School in Walkertown | Install bicycle and pedestrian facilities and construct sidewalk. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 174000 | FY 2026: 174000
EB-5958 | Bike & Ped | Locally Selected | Blue Heron Trail | Twins Way near intersection with US 158 to pedestrian tunnel under I-40 in Bermuda Run | Construct section of multi-use path. | 1 | Davie | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | BGANY | CONSTRUCTION | 1452000
EB-5958 | Bike & Ped | Locally Selected | Blue Heron Trail | Twins Way near intersection with US 158 to pedestrian tunnel under I-40 in Bermuda Run | Construct section of multi-use path. | 1 | Davie | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | BGDA | CONSTRUCTION | 1502000
EB-5958 | Bike & Ped | Locally Selected | Blue Heron Trail | Twins Way near intersection with US 158 to pedestrian tunnel under I-40 in Bermuda Run | Construct section of multi-use path. | 1 | Davie | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | L(M) | CONSTRUCTION | 739000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  |  |  | 110000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | ENGINEERING | 154000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | ENGINEERING | 38000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 196000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 49000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | UTILITIES | 336000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | UTILITIES | 84000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 120000 | FY 2027: 120000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (Idols Road) | SR 1103 (Middlebrook Drive) to Tanglewood Park Road in Clemmons | Construct sidewalk. | 0.92 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 30000 | FY 2027: 30000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  |  |  | 125000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | ENGINEERING | 100000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | ENGINEERING | 25000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 206000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 51000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | UTILITIES | 160000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | UTILITIES | 40000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 2137000 | FY 2026: 2137000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | Jerry Long YMCA on Peacehaven Road to roundabout west of Frank Morgan Elementary School in Clemmons | Construct sidewalk and crosswalks where gaps exist. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 534000 | FY 2026: 534000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 Business (North Bridge Street) | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | TALT5 | ENGINEERING | 50000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 Business (North Bridge Street) | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | L(M) | ENGINEERING | 13000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 Business (North Bridge Street) | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | TALT5 | RIGHT-OF-WAY | 42000 | FY 2026: 42000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 Business (North Bridge Street) | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | L(M) | RIGHT-OF-WAY | 11000 | FY 2026: 11000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 Business (North Bridge Street) | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | TALT5 | CONSTRUCTION | 140000 | FY 2027: 70000; FY 2028: 70000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 Business (North Bridge Street) | NC 268 (CC Camp Road) to SR 1486 (Highland Avenue) in Elkin | Construct sidewalk on west side of roadway. | 0.23 | Surry | 11 | Northwest Piedmont RPO |  | Division 11 |  | L(M) | CONSTRUCTION | 35000 | FY 2027: 35000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | ENGINEERING | 126000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | ENGINEERING | 31000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | RIGHT-OF-WAY | 176000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | RIGHT-OF-WAY | 44000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | UTILITIES | 192000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | UTILITIES | 48000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | TAANY | CONSTRUCTION | 2880000 | FY 2031: 2880000
EB-5963 | Bike & Ped | STI (Prioritization) | SR 1764 (South Grove Street) | SR 1764 (E Barnwell Street) to US 176 (Spartanburg Highway) in Hendersonville | Construct sidewalk. | 0.72 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | L(M) | CONSTRUCTION | 720000 | FY 2031: 720000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | ENGINEERING | 221000 | FY 2026: 205000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | L(M) | ENGINEERING | 4000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | RIGHT-OF-WAY | 21000 | FY 2026: 21000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2026: 4000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | UTILITIES | 60000 | FY 2026: 60000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | CONSTRUCTION | 1564000 | FY 2027: 1564000
EB-5964 | Bike & Ped | STI (Prioritization) | Various | US 441 Business (E Main Street) from NC 28 (Highlands Road) to Old Cat Creek Road in Franklin; Old Cat Creek Road from US 441 Business (E Main Street) to 1st Street in Franklin; 1st Street from Old Cat Creek Road to Grace Presbyterian Church driveway | Construct sidewalk loop. | 0.83 | Macon | 14 | Southwestern RPO |  | Division 14 |  | L(M) | CONSTRUCTION | 36000 | FY 2027: 36000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | TAANY | ENGINEERING | 568000 | FY 2026: 568000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | ENGINEERING | 142000 | FY 2026: 142000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | TAANY | RIGHT-OF-WAY | 4880000 | FY 2028: 4880000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 1220000 | FY 2028: 1220000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | TAANY | UTILITIES | 880000 | FY 2028: 880000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | UTILITIES | 220000 | FY 2028: 220000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | TAANY | CONSTRUCTION | 5600000 | FY 2031: 56000; FY 2032: 4144000; FY 2033: 1400000
EB-5965 | Bike & Ped | STI (Prioritization) | Deaverview Road | US 19 / US 23 / US 74A (Patton Avenue) to Pisgah View Road in Asheville | Construct sidewalk. | 0.75 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 1400000 | FY 2031: 1400000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | ENGINEERING | 120000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | L | ENGINEERING | 30000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | RIGHT-OF-WAY | 540000 | FY 2027: 540000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | L | RIGHT-OF-WAY | 126000 | FY 2027: 126000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | UTILITIES | 400000 | FY 2027: 400000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | L | UTILITIES | 100000 | FY 2027: 100000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | CONSTRUCTION | 1680000 | FY 2027: 17000; FY 2028: 1663000
EB-5966 | Bike & Ped | STI (Prioritization) | Thermal Belt Rail Trail | Various locations along Victory Drive, Allen Street / SR 2124 (Railroad Street), SR 1903 (Pine Street), Broadway Street, East Liberty Street / Beaver Street, Main Street, and SR 2183 (Westview Street) in Rutherfordton | Construct sidewalk connections. | 2.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | L | CONSTRUCTION | 420000 | FY 2027: 420000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 371000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 93000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 768000 | FY 2026: 768000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 192000 | FY 2026: 192000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 499000 | FY 2028: 339000; FY 2029: 160000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 542000 | FY 2028: 542000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 | Trade Street to Independence Point Parkway in Matthews | Construct multi-use path on south side. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 259000 | FY 2028: 259000
EB-5970 | Bike & Ped | STI (Prioritization) | Irwin Creek Greenway | Existing Irwin Creek Greenway to Hamilton Street in Charlotte | Construct greenway. | 0.55 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 3245000 | FY 2028: 32000; FY 2029: 2661000; FY 2030: 552000
EB-5970 | Bike & Ped | STI (Prioritization) | Irwin Creek Greenway | Existing Irwin Creek Greenway to Hamilton Street in Charlotte | Construct greenway. | 0.55 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 1391000 | FY 2028: 139000; FY 2029: 1252000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | ENGINEERING | 240000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | L(M) | ENGINEERING | 60000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | RIGHT-OF-WAY | 344000 | FY 2026: 344000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 86000 | FY 2026: 86000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | UTILITIES | 65000 | FY 2026: 65000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | L(M) | UTILITIES | 16000 | FY 2026: 16000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | CONSTRUCTION | 960000 | FY 2027: 442000; FY 2028: 518000
EB-5972 | Bike & Ped | STI (Prioritization) | North Second Avenue | Park Ridge to SR 1573 (Salisbury Avenue) in Albemarle | Construct sidewalks and install ADA ramps and crosswalks. | 0.51 | Stanly | 10 | Rocky River RPO |  | Division 10 |  | L(M) | CONSTRUCTION | 240000 | FY 2027: 240000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (New Hope Road) | US 29 / US 74 (Franklin Boulevard) to Hunt Avenue in Gastonia | Construct sidewalk on east side of NC 279 (New Hope Road) from US 29 / US 74 (Franklin Boulevard) to Court Drive and west side of NC 279 (New Hope Road) from Court Drive to Hunt Avenue. | 1.03 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 516000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (New Hope Road) | US 29 / US 74 (Franklin Boulevard) to Hunt Avenue in Gastonia | Construct sidewalk on east side of NC 279 (New Hope Road) from US 29 / US 74 (Franklin Boulevard) to Court Drive and west side of NC 279 (New Hope Road) from Court Drive to Hunt Avenue. | 1.03 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 413000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (New Hope Road) | US 29 / US 74 (Franklin Boulevard) to Hunt Avenue in Gastonia | Construct sidewalk on east side of NC 279 (New Hope Road) from US 29 / US 74 (Franklin Boulevard) to Court Drive and west side of NC 279 (New Hope Road) from Court Drive to Hunt Avenue. | 1.03 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 103000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (New Hope Road) | US 29 / US 74 (Franklin Boulevard) to Hunt Avenue in Gastonia | Construct sidewalk on east side of NC 279 (New Hope Road) from US 29 / US 74 (Franklin Boulevard) to Court Drive and west side of NC 279 (New Hope Road) from Court Drive to Hunt Avenue. | 1.03 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 1652000 | FY 2027: 17000; FY 2028: 1635000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (New Hope Road) | US 29 / US 74 (Franklin Boulevard) to Hunt Avenue in Gastonia | Construct sidewalk on east side of NC 279 (New Hope Road) from US 29 / US 74 (Franklin Boulevard) to Court Drive and west side of NC 279 (New Hope Road) from Court Drive to Hunt Avenue. | 1.03 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 413000 | FY 2027: 413000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to Court Drive in Gastonia | Construct sidewalk on both sides. | 0.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 350000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to Court Drive in Gastonia | Construct sidewalk on both sides. | 0.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 280000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to Court Drive in Gastonia | Construct sidewalk on both sides. | 0.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 70000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to Court Drive in Gastonia | Construct sidewalk on both sides. | 0.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 1120000 | FY 2027: 11000; FY 2028: 1109000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to Court Drive in Gastonia | Construct sidewalk on both sides. | 0.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 280000 | FY 2027: 280000
EB-5977 | Bike & Ped | Locally Selected | 9th Street NW Connector | City Walk to Old Lenoir Road in Hickory | Construct multi-use path. | 0.27 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  |  |  | 348000
EB-5977 | Bike & Ped | Locally Selected | 9th Street NW Connector | City Walk to Old Lenoir Road in Hickory | Construct multi-use path. | 0.27 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGDA | RIGHT-OF-WAY | 86000
EB-5977 | Bike & Ped | Locally Selected | 9th Street NW Connector | City Walk to Old Lenoir Road in Hickory | Construct multi-use path. | 0.27 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L(M) | RIGHT-OF-WAY | 22000
EB-5977 | Bike & Ped | Locally Selected | 9th Street NW Connector | City Walk to Old Lenoir Road in Hickory | Construct multi-use path. | 0.27 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | CRPDA | CONSTRUCTION | 1168000
EB-5977 | Bike & Ped | Locally Selected | 9th Street NW Connector | City Walk to Old Lenoir Road in Hickory | Construct multi-use path. | 0.27 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L(M) | CONSTRUCTION | 292000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  |  |  | 312000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | TAANY | RIGHT-OF-WAY | 180000 | FY 2026: 180000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | TAANY | UTILITIES | 8000 | FY 2026: 8000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | UTILITIES | 2000 | FY 2026: 2000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | TAANY | CONSTRUCTION | 6720000 | FY 2026: 2320000; FY 2027: 4400000
EB-5978 | Bike & Ped | STI (Prioritization) | College Street | North Green Street to US 70 in Morganton | Construct multi-use path. | 1.33 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 580000 | FY 2026: 580000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | TAP | ENGINEERING | 8000 | FY 2026: 8000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | L | ENGINEERING | 2000 | FY 2026: 2000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | TAANY | RIGHT-OF-WAY | 16000 | FY 2026: 16000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2026: 4000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | TAP | UTILITIES | 16000 | FY 2026: 16000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | L | UTILITIES | 4000 | FY 2026: 4000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | TAP | CONSTRUCTION | 224000 | FY 2027: 224000
EB-5979 | Bike & Ped | STI (Prioritization) | US 17 BUS (East Main Street) | Skewarkee Trail to US 17 | Construction of a 10 foot wide multi-use path. | 0.33 | Martin | 1 | Mid-East RPO |  | Division 1 |  | L | CONSTRUCTION | 56000 | FY 2027: 56000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (North Howe Street) | East Owen Street to Dosher Hospital in Southport | Construct sidewalk. | 0.26 | Brunswick | 3 | Cape Fear RPO |  | Division 3 |  | TA5T50 | ENGINEERING | 24000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (North Howe Street) | East Owen Street to Dosher Hospital in Southport | Construct sidewalk. | 0.26 | Brunswick | 3 | Cape Fear RPO |  | Division 3 |  | L(M) | ENGINEERING | 6000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (North Howe Street) | East Owen Street to Dosher Hospital in Southport | Construct sidewalk. | 0.26 | Brunswick | 3 | Cape Fear RPO |  | Division 3 |  | TA5T50 | CONSTRUCTION | 140000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (North Howe Street) | East Owen Street to Dosher Hospital in Southport | Construct sidewalk. | 0.26 | Brunswick | 3 | Cape Fear RPO |  | Division 3 |  | L(M) | CONSTRUCTION | 35000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (North Howe Street) | East Owen Street to Dosher Hospital in Southport | Construct sidewalk. | 0.26 | Brunswick | 3 | Cape Fear RPO |  | Division 3 |  | L | CONSTRUCTION | 20000 | FY 2027: 20000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | TA5T50 | ENGINEERING | 640000 | FY 2026: 400000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | L | ENGINEERING | 160000 | FY 2026: 100000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | TA5T50 | RIGHT-OF-WAY | 1920000 | FY 2027: 1920000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | L | RIGHT-OF-WAY | 480000 | FY 2027: 480000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | TA5T50 | UTILITIES | 17000 | FY 2027: 17000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | L | UTILITIES | 3000 | FY 2027: 3000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | TA5T50 | CONSTRUCTION | 4240000 | FY 2028: 43000; FY 2029: 4197000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) | Grove Street to SR 1328 (Brookshire Road) in Boone | Construct multi-use path. | 1.14 | Watauga | 11 | High Country RPO |  | Division 11 |  | L | CONSTRUCTION | 1060000 | FY 2028: 1060000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 240000 | FY 2027: 240000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 60000 | FY 2027: 60000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | RIGHT-OF-WAY | 400000 | FY 2029: 400000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 100000 | FY 2029: 100000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | UTILITIES | 60000 | FY 2029: 60000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | UTILITIES | 40000 | FY 2029: 40000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 2960000 | FY 2031: 2220000; FY 2032: 740000
EB-5984 | Bike & Ped | STI (Prioritization) | East Raleigh Boulevard | US 64 to Arlington Street in Rocky Mount | Construct pedestrian improvements. | 2.28 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 740000 | FY 2031: 555000; FY 2032: 185000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 120000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 30000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 400000 | FY 2028: 400000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 100000 | FY 2028: 100000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 8000 | FY 2028: 8000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 2000 | FY 2028: 2000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 5520000 | FY 2031: 5520000
EB-5985 | Bike & Ped | STI (Prioritization) | Cone Boulevard | US 29 (O'Henry Boulevard) to St. Regis Road in Greensboro | Construct sidewalk. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 1380000 | FY 2031: 1380000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 32000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 8000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 1360000 | FY 2028: 1360000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 340000 | FY 2028: 340000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 8000 | FY 2028: 8000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 2000 | FY 2028: 2000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 4160000 | FY 2031: 2579000; FY 2032: 1581000
EB-5986 | Bike & Ped | STI (Prioritization) | Benjamin Parkway | Elam Avenue to US 220 (Battleground Avenue) in Greensboro | Construct Benjamin Parkway side path including roadway improvements, signal modifications, and crossing improvements. | 1.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 1040000 | FY 2031: 645000; FY 2032: 395000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 79000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 20000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 696000 | FY 2028: 696000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 174000 | FY 2028: 174000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 8000 | FY 2028: 8000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 2000 | FY 2028: 2000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 3440000 | FY 2031: 2374000; FY 2032: 1066000
EB-5987 | Bike & Ped | STI (Prioritization) | Old Battleground Road | Lake Brandt Road to Bicentennial Greenway in Greensboro | Construct multi-use path. | 0.6 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 860000 | FY 2031: 593000; FY 2032: 267000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | ENGINEERING | 24000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | ENGINEERING | 6000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 32000 | FY 2030: 32000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 8000 | FY 2030: 8000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | UTILITIES | 224000 | FY 2030: 224000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | UTILITIES | 56000 | FY 2030: 56000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 248000 | FY 2032: 248000
EB-5988 | Bike & Ped | STI (Prioritization) | Lee Avenue | West Lebanon Avenue to SR 1454 (West Haggard Avenue) in Elon | Construct sidewalk. | 0.15 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 62000 | FY 2032: 62000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | ENGINEERING | 96000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 24000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 128000 | FY 2029: 128000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 32000 | FY 2029: 32000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | UTILITIES | 64000 | FY 2029: 64000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 16000 | FY 2029: 16000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 3040000 | FY 2031: 1702000; FY 2032: 1338000
EB-5989 | Bike & Ped | STI (Prioritization) | Cedrow Drive | West of I-74 to east of I-74 in High Point | Construct multi-use facility across I-74. | 0.08 | Guilford | 7 | High Point Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 760000 | FY 2031: 760000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 48000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 12000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 1840000 | FY 2028: 1840000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 460000 | FY 2028: 460000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 48000 | FY 2028: 48000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 12000 | FY 2028: 12000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 1440000 | FY 2031: 893000; FY 2032: 547000
EB-5995 | Bike & Ped | STI (Prioritization) | Lawndale Drive | Pisgah Church Road to Lake Brandt Road in Greensboro | Construct sidewalk. | 2.54 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 360000 | FY 2031: 360000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (North Church Street) | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 80000 | FY 2026: 80000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (North Church Street) | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (North Church Street) | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 8000 | FY 2026: 8000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (North Church Street) | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 2000 | FY 2026: 2000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (North Church Street) | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 3600000 | FY 2027: 3600000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (North Church Street) | Henry Street / Electra Drive to Lees Chapel Road in Greensboro | Construct sidewalk. | 1.2 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 900000 | FY 2027: 900000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 210000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 53000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 2000000 | FY 2028: 2000000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 500000 | FY 2028: 500000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 1120000 | FY 2028: 1120000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 280000 | FY 2028: 280000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 1520000 | FY 2031: 183000; FY 2032: 1337000
EB-5997 | Bike & Ped | STI (Prioritization) | Green Valley Road | Market Street to Battleground Avenue in Greensboro | Construct sidewalks. | 1.29 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 380000 | FY 2031: 380000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | ENGINEERING | 163000 | FY 2026: 163000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | L(M) | ENGINEERING | 41000 | FY 2026: 41000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | RIGHT-OF-WAY | 384000 | FY 2028: 384000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | L(M) | RIGHT-OF-WAY | 96000 | FY 2028: 96000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | UTILITIES | 880000 | FY 2028: 880000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | L(M) | UTILITIES | 220000 | FY 2028: 220000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | CONSTRUCTION | 5760000 | FY 2031: 3110000; FY 2032: 2650000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | Willow Drive to SR 1741 / SR 1838 (Old Durham-Chapel Hill Road) in Chapel Hill | Construct multi-use paths. | 1.24 | Orange | 7 | Triangle West TPO | COORDINATE WITH U-5304 | Division 7 |  | L(M) | CONSTRUCTION | 1440000 | FY 2031: 1440000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (North Poplar Street) | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Moore | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | TA50200 | ENGINEERING | 21000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (North Poplar Street) | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Moore | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | L(M) | ENGINEERING | 5000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (North Poplar Street) | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Moore | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | TA50200 | RIGHT-OF-WAY | 27000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (North Poplar Street) | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Moore | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | L(M) | RIGHT-OF-WAY | 7000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (North Poplar Street) | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Moore | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | TA50200 | CONSTRUCTION | 272000 | FY 2027: 3000; FY 2028: 269000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (North Poplar Street) | Johnson Street to US 1 (Sandhills Boulevard) in Aberdeen | Construct sidewalk. | 0.36 | Moore | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | L(M) | CONSTRUCTION | 68000 | FY 2027: 68000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (Charlotte Avenue) | Chatham Street to SR 1002 (11th Street) in Sanford | Construct sidewalks and implement road diet with bicycle lanes. | 0.95 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 153000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (Charlotte Avenue) | Chatham Street to SR 1002 (11th Street) in Sanford | Construct sidewalks and implement road diet with bicycle lanes. | 0.95 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | ENGINEERING | 38000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (Charlotte Avenue) | Chatham Street to SR 1002 (11th Street) in Sanford | Construct sidewalks and implement road diet with bicycle lanes. | 0.95 | Lee | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1120000 | FY 2026: 739000; FY 2027: 381000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (Charlotte Avenue) | Chatham Street to SR 1002 (11th Street) in Sanford | Construct sidewalks and implement road diet with bicycle lanes. | 0.95 | Lee | 8 | Central Pines RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 280000 | FY 2026: 280000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (East Dixie Drive) | Executive Way to Centerpoint Plaza Shopping Center in Asheboro | Construct sidewalk. | 0.15 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 272000 | FY 2027: 272000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (East Dixie Drive) | Executive Way to Centerpoint Plaza Shopping Center in Asheboro | Construct sidewalk. | 0.15 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 68000 | FY 2027: 68000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (East Dixie Drive) | Executive Way to Centerpoint Plaza Shopping Center in Asheboro | Construct sidewalk. | 0.15 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | UTILITIES | 90000 | FY 2027: 90000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (East Dixie Drive) | Executive Way to Centerpoint Plaza Shopping Center in Asheboro | Construct sidewalk. | 0.15 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1680000 | FY 2027: 17000; FY 2028: 1663000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (East Dixie Drive) | Executive Way to Centerpoint Plaza Shopping Center in Asheboro | Construct sidewalk. | 0.15 | Randolph | 8 | Piedmont Triad RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 420000 | FY 2027: 420000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 266000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | ENGINEERING | 67000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 176000 | FY 2026: 176000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 44000 | FY 2026: 44000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 128000 | FY 2026: 128000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | UTILITIES | 32000 | FY 2026: 32000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1600000 | FY 2026: 16000; FY 2027: 1584000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (West 3rd Street) | North Garden Avenue to SR 1108 (North Chatham Avenue) in Siler City | Construct sidewalk. | 0.45 | Chatham | 8 | Central Pines RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 400000 | FY 2026: 400000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | ENGINEERING | 271000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 68000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | CMAQ | RIGHT-OF-WAY | 238000 | FY 2027: 238000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | RIGHT-OF-WAY | 88000 | FY 2027: 88000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 82000 | FY 2027: 82000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | CMAQ | CONSTRUCTION | 2265000 | FY 2028: 23000; FY 2029: 2242000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | CONSTRUCTION | 2090000 | FY 2028: 21000; FY 2029: 2069000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (Salem Parkway) | Lockland Avenue to NC 150 (Peters Creek Parkway) in Winston-Salem | Construct multi-use path. | 0.35 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 1089000 | FY 2028: 11000; FY 2029: 1078000
EB-6012 | Bike & Ped | STI (Prioritization) | Downtown Greenway | Chaney Avenue to Wardola Drive in Jacksonville | Construct multi-use path. | 0.58 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TA50200 | CONSTRUCTION | 1094000
EB-6012 | Bike & Ped | STI (Prioritization) | Downtown Greenway | Chaney Avenue to Wardola Drive in Jacksonville | Construct multi-use path. | 0.58 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 273000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | TAP | ENGINEERING | 136000 | FY 2027: 136000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | L | ENGINEERING | 34000 | FY 2027: 34000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | TAP | RIGHT-OF-WAY | 320000 | FY 2028: 320000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | L | RIGHT-OF-WAY | 80000 | FY 2028: 80000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | TAP | UTILITIES | 112000 | FY 2028: 112000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | L(M) | UTILITIES | 28000 | FY 2028: 28000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | TAP | CONSTRUCTION | 2000000 | FY 2029: 2000000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (Third Street) | SR 1563 (Union Chapel Road) to Walmart Shopping Center/Jones Road in Pembroke | Construct sidewalk. | 0.7 | Robeson | 6 | Lumber River RPO |  | Division 6 |  | L | CONSTRUCTION | 500000 | FY 2029: 500000
EB-6014 | Bike & Ped | STI (Prioritization) | Campbell University sidewalk | Wade Steward Circle to Pearson Road in Buies Creek | Construct sidewalk. | 0.81 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | TAANY | RIGHT-OF-WAY | 28000
EB-6014 | Bike & Ped | STI (Prioritization) | Campbell University sidewalk | Wade Steward Circle to Pearson Road in Buies Creek | Construct sidewalk. | 0.81 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | L(M) | RIGHT-OF-WAY | 7000
EB-6014 | Bike & Ped | STI (Prioritization) | Campbell University sidewalk | Wade Steward Circle to Pearson Road in Buies Creek | Construct sidewalk. | 0.81 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | TAANY | CONSTRUCTION | 504000
EB-6014 | Bike & Ped | STI (Prioritization) | Campbell University sidewalk | Wade Steward Circle to Pearson Road in Buies Creek | Construct sidewalk. | 0.81 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | L(M) | CONSTRUCTION | 126000
EB-6015 | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 1 | Scotland | 8 | Lumber River RPO
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 53000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 13000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 61000 | FY 2026: 61000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2026: 15000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 528000 | FY 2028: 322000; FY 2029: 206000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | SR 1674 (Lauchwood Drive) to Plaza Road in Laurinburg. | Construct sidewalks. | 0.52 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 132000 | FY 2028: 81000; FY 2029: 51000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 56000 | FY 2026: 56000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 14000 | FY 2026: 14000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 24000 | FY 2027: 24000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 6000 | FY 2027: 6000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | UTILITIES | 232000 | FY 2027: 232000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | UTILITIES | 58000 | FY 2027: 58000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1040000 | FY 2028: 645000; FY 2029: 395000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 Business (South Main Street) | Plaza Road to Crepe Myrtle Avenue in Laurinburg | Construct sidewalks. | 0.45 | Scotland | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 260000 | FY 2028: 161000; FY 2029: 99000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | ENGINEERING | 206000 | FY 2027: 206000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 52000 | FY 2027: 52000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | RIGHT-OF-WAY | 576000 | FY 2029: 576000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 144000 | FY 2029: 144000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | UTILITIES | 960000 | FY 2029: 960000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | UTILITIES | 240000 | FY 2029: 240000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | CONSTRUCTION | 3040000 | FY 2031: 1490000; FY 2032: 1550000
EB-6016 | Bike & Ped | STI (Prioritization) | East Clayton Connector Greenway | SR 2851 (East Front Street) to SR 1902 (Glen Laurel Road) in Clayton. | Construct greenway. | 1.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 760000 | FY 2031: 372000; FY 2032: 388000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | ENGINEERING | 66000 | FY 2028: 66000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 17000 | FY 2028: 17000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | RIGHT-OF-WAY | 1200000 | FY 2030: 1200000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 300000 | FY 2030: 300000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | UTILITIES | 8000 | FY 2030: 8000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | UTILITIES | 2000 | FY 2030: 2000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TAANY | CONSTRUCTION | 1680000 | FY 2032: 1058000; FY 2033: 622000
EB-6017 | Bike & Ped | STI (Prioritization) | Mountains to Sea Trail | Fox Ridge Road to Neuse River Bridge in Clayton. | Construct greenway. | 0.54 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 420000 | FY 2032: 265000; FY 2033: 155000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 22000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 6000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 256000 | FY 2026: 256000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 64000 | FY 2026: 64000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | UTILITIES | 128000 | FY 2026: 128000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | L(M) | UTILITIES | 32000 | FY 2026: 32000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 2320000 | FY 2028: 1902000; FY 2029: 418000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (Spring Street); SR 1615 (South Main Street) | Spring Street from SR 1640 (Wiregrass Road) to NC 177 and Main Street from Bridges Street to NC 38 in Hamlet | Construct sidewalks. | 0.58 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 580000 | FY 2028: 580000
EB-6019 | Bike & Ped | Locally Selected | SR 1308 (Laura Duncan Road) | Community Park Drive to SR 5878 (North Salem Street) in Apex | Improve safety of pedestrian crossing. |  | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | Division 5 |  |  |  | 9000
EB-6019 | Bike & Ped | Locally Selected | SR 1308 (Laura Duncan Road) | Community Park Drive to SR 5878 (North Salem Street) in Apex | Improve safety of pedestrian crossing. |  | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | Division 5 |  | BGDA | CONSTRUCTION | 381000
EB-6019 | Bike & Ped | Locally Selected | SR 1308 (Laura Duncan Road) | Community Park Drive to SR 5878 (North Salem Street) in Apex | Improve safety of pedestrian crossing. |  | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | Division 5 |  | L(M) | CONSTRUCTION | 163000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGDA | ENGINEERING | 140000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L(M) | ENGINEERING | 35000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGDA | RIGHT-OF-WAY | 120000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L(M) | RIGHT-OF-WAY | 30000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGDA | CONSTRUCTION | 2165000 | FY 2026: 999000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L(M) | CONSTRUCTION | 541000 | FY 2026: 250000
EB-6020 | Bike & Ped | Locally Selected | North Willow Street; South Park Street | East Julia Street to SR 1501 (Junny Road); West Lillington Street to NC 210 in Angier | Construct sidewalk extension. | 0.73 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L | CONSTRUCTION | 749000 | FY 2026: 749000
EB-6021 | Bike & Ped | Locally Selected | Beaver Creek Greenway Extension | Kelly Road Park to Apex Nature Park in Apex | Realign adjacent segment of existing Beaver Creek Greenway. | 1.21 | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 4496000
EB-6021 | Bike & Ped | Locally Selected | Beaver Creek Greenway Extension | Kelly Road Park to Apex Nature Park in Apex | Realign adjacent segment of existing Beaver Creek Greenway. | 1.21 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 1123000
EB-6021 | Bike & Ped | Locally Selected | Beaver Creek Greenway Extension | Kelly Road Park to Apex Nature Park in Apex | Realign adjacent segment of existing Beaver Creek Greenway. | 1.21 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 2582000
EB-6025 | Bike & Ped | Locally Selected | Rice Hope Multi-Use Path | Along NC 133 from Morecamble Boulevard to Rice Hope Run in Belville | Construct multi-use path. | 0.17 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TADA | ENGINEERING | 14000
EB-6025 | Bike & Ped | Locally Selected | Rice Hope Multi-Use Path | Along NC 133 from Morecamble Boulevard to Rice Hope Run in Belville | Construct multi-use path. | 0.17 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | ENGINEERING | 4000
EB-6025 | Bike & Ped | Locally Selected | Rice Hope Multi-Use Path | Along NC 133 from Morecamble Boulevard to Rice Hope Run in Belville | Construct multi-use path. | 0.17 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TADA | CONSTRUCTION | 298000
EB-6025 | Bike & Ped | Locally Selected | Rice Hope Multi-Use Path | Along NC 133 from Morecamble Boulevard to Rice Hope Run in Belville | Construct multi-use path. | 0.17 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 74000
EB-6026 | Bike & Ped | Locally Selected | Belville Elementary Multi-Use Path | Along NC 133 connecting north and south entrances of Hawkeswater development to Belville Elementary School in Bellville | Construct multi-use path. | 0.37 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TADA | ENGINEERING | 42000
EB-6026 | Bike & Ped | Locally Selected | Belville Elementary Multi-Use Path | Along NC 133 connecting north and south entrances of Hawkeswater development to Belville Elementary School in Bellville | Construct multi-use path. | 0.37 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | ENGINEERING | 10000
EB-6026 | Bike & Ped | Locally Selected | Belville Elementary Multi-Use Path | Along NC 133 connecting north and south entrances of Hawkeswater development to Belville Elementary School in Bellville | Construct multi-use path. | 0.37 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TADA | CONSTRUCTION | 749000
EB-6026 | Bike & Ped | Locally Selected | Belville Elementary Multi-Use Path | Along NC 133 connecting north and south entrances of Hawkeswater development to Belville Elementary School in Bellville | Construct multi-use path. | 0.37 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 187000
EB-6027 | Bike & Ped | Locally Selected | SR 1403 (Middle Sound Loop) | South of Market Street from Red Cedar Road to existing trail at corner of Market Street and Middle Sound Loop Road near Wilmington. | Construct multi-use path. | 6.73 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT OF WAY IN PROGRESS. | Division 3 |  |  |  | 305000
EB-6027 | Bike & Ped | Locally Selected | SR 1403 (Middle Sound Loop) | South of Market Street from Red Cedar Road to existing trail at corner of Market Street and Middle Sound Loop Road near Wilmington. | Construct multi-use path. | 6.73 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT OF WAY IN PROGRESS. | Division 3 |  | L | RIGHT-OF-WAY | 500000
EB-6027 | Bike & Ped | Locally Selected | SR 1403 (Middle Sound Loop) | South of Market Street from Red Cedar Road to existing trail at corner of Market Street and Middle Sound Loop Road near Wilmington. | Construct multi-use path. | 6.73 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT OF WAY IN PROGRESS. | Division 3 |  | L | CONSTRUCTION | 1000000
EB-6028 | Bike & Ped | Locally Selected | US 17 Business (Market Street) | 21st Street in Wilmington | Construct signalized pedestrian crossing. | 0 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION | Division 3 |  |  |  | 75000
EB-6028 | Bike & Ped | Locally Selected | US 17 Business (Market Street) | 21st Street in Wilmington | Construct signalized pedestrian crossing. | 0 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION | Division 3 |  | TADA | CONSTRUCTION | 131000
EB-6028 | Bike & Ped | Locally Selected | US 17 Business (Market Street) | 21st Street in Wilmington | Construct signalized pedestrian crossing. | 0 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION | Division 3 |  | L(M) | CONSTRUCTION | 33000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | TADA | ENGINEERING | 184000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L(M) | ENGINEERING | 46000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | TADA | RIGHT-OF-WAY | 80000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L(M) | RIGHT-OF-WAY | 20000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGDA | CONSTRUCTION | 1445000 | FY 2026: 1445000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | TADA | CONSTRUCTION | 216000 | FY 2026: 216000
EB-6030 | Bike & Ped | Locally Selected | US 401 Bypass (Skibo Road) | Richwood Court to NC 24 (Bragg Boulevard) near Fayetteville. | Construct sidewalk. | 2.73 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | L(M) | CONSTRUCTION | 415000 | FY 2026: 415000
EB-6031 | Bike & Ped | Locally Selected | US 401 (Ramsey Street) | Summerchase Drive to SR 1611 (Andrews Road) near Fayetteville. | Construct sidewalk. | 0.17 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Division 6 |  | TADA | CONSTRUCTION | 68000
EB-6031 | Bike & Ped | Locally Selected | US 401 (Ramsey Street) | Summerchase Drive to SR 1611 (Andrews Road) near Fayetteville. | Construct sidewalk. | 0.17 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Division 6 |  | L(M) | CONSTRUCTION | 17000
EB-6032 | Bike & Ped | Locally Selected | NC 59 (Hope Mills Road) | Fayetteville City limits to Sumac Circle in Fayetteville. | Construct sidewalk. | 1.32 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Division 6 |  |  |  | 23000
EB-6032 | Bike & Ped | Locally Selected | NC 59 (Hope Mills Road) | Fayetteville City limits to Sumac Circle in Fayetteville. | Construct sidewalk. | 1.32 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Division 6 |  | TADA | CONSTRUCTION | 300000
EB-6032 | Bike & Ped | Locally Selected | NC 59 (Hope Mills Road) | Fayetteville City limits to Sumac Circle in Fayetteville. | Construct sidewalk. | 1.32 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Division 6 |  | L(M) | CONSTRUCTION | 75000
EB-6033 | Bike & Ped | Other | Various | Locations statewide | Safe routes to school education. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 2833000
EB-6034 | Bike & Ped | Locally Selected | SR 1144 (First Street) | East of West First Street Extension to east of Greensboro Street in Ocean Isle Beach | Construct bike lanes. | 2.88 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 622000
EB-6034 | Bike & Ped | Locally Selected | SR 1144 (First Street) | East of West First Street Extension to east of Greensboro Street in Ocean Isle Beach | Construct bike lanes. | 2.88 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 414000
EB-6036 | Bike & Ped | Locally Selected | Hornets Nest Park | SR 2025 (Oakdale Road / Miranda Road) to Kiev Drive in Charlotte. | Construct sidewalks on the north side. | 2.83 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 5000
EB-6036 | Bike & Ped | Locally Selected | Hornets Nest Park | SR 2025 (Oakdale Road / Miranda Road) to Kiev Drive in Charlotte. | Construct sidewalks on the north side. | 2.83 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 2526000 | FY 2026: 1030000
EB-6036 | Bike & Ped | Locally Selected | Hornets Nest Park | SR 2025 (Oakdale Road / Miranda Road) to Kiev Drive in Charlotte. | Construct sidewalks on the north side. | 2.83 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 632000 | FY 2026: 258000
EB-6037 | Bike & Ped | Other | Various | Locations statewide | Rails to trails program |  | Statewide | 99 | Statewide Project | LOCAL FUNDS REPRESENT LOCAL MATCH FOR RIGHT-OF-WAY AND CONSTRUCTION OF TRAILS BY LOCAL GOVERNMENTS. | Division 99
EB-6037A | Bike & Ped | Other | Shelby Rail Trail | South Dekab Street to Gardner Street in Shelby. Graham Street to West Marion Street in Shelby | Construct multi-use path. | 10.41 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TAANY | ENGINEERING | 8000
EB-6037A | Bike & Ped | Other | Shelby Rail Trail | South Dekab Street to Gardner Street in Shelby. Graham Street to West Marion Street in Shelby | Construct multi-use path. | 10.41 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | ENGINEERING | 2000
EB-6037A | Bike & Ped | Other | Shelby Rail Trail | South Dekab Street to Gardner Street in Shelby. Graham Street to West Marion Street in Shelby | Construct multi-use path. | 10.41 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TAANY | CONSTRUCTION | 4160000 | FY 2026: 2038000; FY 2027: 416000
EB-6037A | Bike & Ped | Other | Shelby Rail Trail | South Dekab Street to Gardner Street in Shelby. Graham Street to West Marion Street in Shelby | Construct multi-use path. | 10.41 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L(M) | CONSTRUCTION | 1038000
EB-6037B | Bike & Ped | Other | Ecusta Trail | Brevard Bike Path in Brevard to Kangua Road in Hendersonville | Construct multi-use path. | 19.57 | Henderson, Transylvania | 14 | French Broad River MPO, Land-of-Sky RPO | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE. | Division 14 |  | TAANY | RIGHT-OF-WAY | 6400000
EB-6037B | Bike & Ped | Other | Ecusta Trail | Brevard Bike Path in Brevard to Kangua Road in Hendersonville | Construct multi-use path. | 19.57 | Henderson, Transylvania | 14 | French Broad River MPO, Land-of-Sky RPO | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE. | Division 14 |  | L(M) | RIGHT-OF-WAY | 1600000
EB-6037C | Bike & Ped | Other | A&Y Greenway | Spring Garden Street to South of Rollins Road in Greensboro. | Construct multi-use path. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 2749000
EB-6037C | Bike & Ped | Other | A&Y Greenway | Spring Garden Street to South of Rollins Road in Greensboro. | Construct multi-use path. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 4400000
EB-6037C | Bike & Ped | Other | A&Y Greenway | Spring Garden Street to South of Rollins Road in Greensboro. | Construct multi-use path. | 3.08 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 1787000
EB-6038 | Bike & Ped | Locally Selected | Various | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | DP | ENGINEERING | 1764000
EB-6038 | Bike & Ped | Locally Selected | Various | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | L | ENGINEERING | 288000
EB-6038 | Bike & Ped | Locally Selected | Various | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | DP | RIGHT-OF-WAY | 403000
EB-6038 | Bike & Ped | Locally Selected | Various | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | L | RIGHT-OF-WAY | 259000
EB-6038 | Bike & Ped | Locally Selected | Various | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | DP | CONSTRUCTION | 15092000
EB-6038 | Bike & Ped | Locally Selected | Various | SR 1371 (Clement Boulevard NW) from Hickory Airport to 19th Street Lane NW in Hickory; 19th Street Lane NW from Clement Boulevard to 13th Avenue Drive NW in Hickory; 13th Avenue Drive NW from 19th Street Lane NW to US 321 in Hickory; US 321 from 13th Aven | Construct multi-use trails. Construct bicycle / pedestrian bridge over US 321. | 2.58 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | L | CONSTRUCTION | 4124000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 59000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | ENGINEERING | 539000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 149000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | RIGHT-OF-WAY | 48000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | RIGHT-OF-WAY | 12000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | CONSTRUCTION | 984000
EB-6039 | Bike & Ped | Locally Selected | St. Joseph Avenue / Lewis Drive | Lake Park Boulevard to Access Road in Carolina Beach | Construct bike lanes. | 1.3 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 247000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 53000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 13000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 90000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 22000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 16000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 4000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1164000 | FY 2026: 1164000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (Harper Road) | North of Fair Oaks Drive to Morgan Elementary School western entrance in Clemmons | Construct pedestrian improvements, including sidewalk. | 0.62 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 291000 | FY 2026: 291000
EB-6041 | Bike & Ped | Locally Selected | Spring Lake | Near the Little River in the Town of Spring Lake | Construct greenway trail. | 5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 190000
EB-6041 | Bike & Ped | Locally Selected | Spring Lake | Near the Little River in the Town of Spring Lake | Construct greenway trail. | 5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 48000
EB-6041 | Bike & Ped | Locally Selected | Spring Lake | Near the Little River in the Town of Spring Lake | Construct greenway trail. | 5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 102000
EB-6041 | Bike & Ped | Locally Selected | Spring Lake | Near the Little River in the Town of Spring Lake | Construct greenway trail. | 5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 26000
EB-6042 | Bike & Ped | Locally Selected | Various | Locations including along the Tar River, Moye Boulevard, the Norfolk Southern rail corridor, and Town Creek in Greenville | Construct multi-use path. | 2.27 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  |  |  | 3306000
EB-6042 | Bike & Ped | Locally Selected | Various | Locations including along the Tar River, Moye Boulevard, the Norfolk Southern rail corridor, and Town Creek in Greenville | Construct multi-use path. | 2.27 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 3600000
EB-6042 | Bike & Ped | Locally Selected | Various | Locations including along the Tar River, Moye Boulevard, the Norfolk Southern rail corridor, and Town Creek in Greenville | Construct multi-use path. | 2.27 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | L | CONSTRUCTION | 4691000
EB-6046 | Bike & Ped | Locally Selected | SR 1307 (West Chatham Street) | Hunter Street to Saunder Street in Apex | Construct sidewalk extensions and improve safety of pedestrian crossing. | 0.31 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 8000
EB-6046 | Bike & Ped | Locally Selected | SR 1307 (West Chatham Street) | Hunter Street to Saunder Street in Apex | Construct sidewalk extensions and improve safety of pedestrian crossing. | 0.31 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 2000
EB-6046 | Bike & Ped | Locally Selected | SR 1307 (West Chatham Street) | Hunter Street to Saunder Street in Apex | Construct sidewalk extensions and improve safety of pedestrian crossing. | 0.31 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 381000
EB-6046 | Bike & Ped | Locally Selected | SR 1307 (West Chatham Street) | Hunter Street to Saunder Street in Apex | Construct sidewalk extensions and improve safety of pedestrian crossing. | 0.31 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 572000
EB-6048 | Bike & Ped | Locally Selected | US 64 Business (Wendell Boulevard) | North of SR 2346 (Hanor Lane) to east of SR 2353 (Old Wilson Road) in Wendell | Construct geometric improvements, sidewalk extension and install pedestrian crossing at SR 2329 (Marshburn Road). | 1.47 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 60000
EB-6048 | Bike & Ped | Locally Selected | US 64 Business (Wendell Boulevard) | North of SR 2346 (Hanor Lane) to east of SR 2353 (Old Wilson Road) in Wendell | Construct geometric improvements, sidewalk extension and install pedestrian crossing at SR 2329 (Marshburn Road). | 1.47 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | RIGHT-OF-WAY | 15000
EB-6048 | Bike & Ped | Locally Selected | US 64 Business (Wendell Boulevard) | North of SR 2346 (Hanor Lane) to east of SR 2353 (Old Wilson Road) in Wendell | Construct geometric improvements, sidewalk extension and install pedestrian crossing at SR 2329 (Marshburn Road). | 1.47 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 1260000
EB-6048 | Bike & Ped | Locally Selected | US 64 Business (Wendell Boulevard) | North of SR 2346 (Hanor Lane) to east of SR 2353 (Old Wilson Road) in Wendell | Construct geometric improvements, sidewalk extension and install pedestrian crossing at SR 2329 (Marshburn Road). | 1.47 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 315000
EB-6051 | Bike & Ped | Locally Selected | Various | Lawyers Road from Lebanon Road / Wilson Grove Road to Apple Creek Drive in Mint Hill; Wilgrove-Mint Hill Road from Jim Harper Lane to Wilson Grove Road in Mint Hill; Wilson Grove Road from Wilgrove-Mint Hill Road to Central Drive in Mint Hill | Extend sidewalks. | 3.37 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 188000
EB-6051 | Bike & Ped | Locally Selected | Various | Lawyers Road from Lebanon Road / Wilson Grove Road to Apple Creek Drive in Mint Hill; Wilgrove-Mint Hill Road from Jim Harper Lane to Wilson Grove Road in Mint Hill; Wilson Grove Road from Wilgrove-Mint Hill Road to Central Drive in Mint Hill | Extend sidewalks. | 3.37 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 188000
EB-6051 | Bike & Ped | Locally Selected | Various | Lawyers Road from Lebanon Road / Wilson Grove Road to Apple Creek Drive in Mint Hill; Wilgrove-Mint Hill Road from Jim Harper Lane to Wilson Grove Road in Mint Hill; Wilson Grove Road from Wilgrove-Mint Hill Road to Central Drive in Mint Hill | Extend sidewalks. | 3.37 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 30000 | FY 2026: 30000
EB-6051 | Bike & Ped | Locally Selected | Various | Lawyers Road from Lebanon Road / Wilson Grove Road to Apple Creek Drive in Mint Hill; Wilgrove-Mint Hill Road from Jim Harper Lane to Wilson Grove Road in Mint Hill; Wilson Grove Road from Wilgrove-Mint Hill Road to Central Drive in Mint Hill | Extend sidewalks. | 3.37 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 30000 | FY 2026: 30000
EB-6052 | Bike & Ped | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 6000
EB-6052 | Bike & Ped | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 4000
EB-6052 | Bike & Ped | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 240000
EB-6052 | Bike & Ped | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 160000
EB-6052 | Bike & Ped | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 751000 | FY 2026: 751000
EB-6052 | Bike & Ped | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2940 (North Tryon Street) to JW Clay Boulevard in Charlotte | Construct multi-use path. | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 501000 | FY 2026: 501000
EL-4828 | Bike & Ped | Transition | Morgan Creek Greenway | SR 1919 (Smith Level road) to University Lake in Carrboro | Construct greenway and connections. | 1.7 | Orange | 7 | Triangle West TPO | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO | Pre-STI (Transition) |  |  |  | 253000
EL-4828A | Bike & Ped | Transition | Morgan Creek Greenway | Phase 1 - Abbey Lane to SR 1919 (Smith Level Road) in Carrboro and Piedmont EMC utility easement to SR 1919 (Smith Level Road) in Carrboro | Construct greenway and connections. | 0.29 | Orange | 7 | Triangle West TPO |  | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 863000 | FY 2026: 863000
EL-4828A | Bike & Ped | Transition | Morgan Creek Greenway | Phase 1 - Abbey Lane to SR 1919 (Smith Level Road) in Carrboro and Piedmont EMC utility easement to SR 1919 (Smith Level Road) in Carrboro | Construct greenway and connections. | 0.29 | Orange | 7 | Triangle West TPO |  | Pre-STI (Transition) |  | TADA | CONSTRUCTION | 730000 | FY 2026: 730000
EL-4828A | Bike & Ped | Transition | Morgan Creek Greenway | Phase 1 - Abbey Lane to SR 1919 (Smith Level Road) in Carrboro and Piedmont EMC utility easement to SR 1919 (Smith Level Road) in Carrboro | Construct greenway and connections. | 0.29 | Orange | 7 | Triangle West TPO |  | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 399000 | FY 2026: 399000
EL-5100 | Bike & Ped | Other | Various | Locations in the Capital Area MPO | Pedestrian, bicycle, and transit projects in the Capital Area Metropolitan Planning Organization (CAMPO). |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  |  |  | 22332000
EL-5101 | Bike & Ped | Other | Various | Locations in the Greensboro Urban Area MPO | Pedestrian and bicycle projects in the Greensboro Urban Area Metropolitan Planning Organization (GUAMPO). |  | Guilford | 7 | Greensboro Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS | Division 7 |  |  |  | 32374000
EL-5101DR | Bike & Ped | Locally Selected | Murrow Boulevard | Murrow Boulevard bridge over Church Street | Repair bridge deck and complete greenway across structure. |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | BGDA | CONSTRUCTION | 1440000
EL-5101DR | Bike & Ped | Locally Selected | Murrow Boulevard | Murrow Boulevard bridge over Church Street | Repair bridge deck and complete greenway across structure. |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | L(M) | CONSTRUCTION | 360000
ER-2971 | Bike & Ped | Pre-STI (Historic) | Various | Locations statewide | Sidewalk program in all fourteen highway divisions. |  | Statewide | 99 | Statewide Project | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E | Pre-STI (Transition) |  |  |  | 25408000
ER-5600 | Highway | Other | Various | Locations statewide | Manage vegetation and clear zones. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 3264000
ER-5600 | Highway | Other | Various | Locations statewide | Manage vegetation and clear zones. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  | STPE | ENGINEERING | 700000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
ER-5600 | Highway | Other | Various | Locations statewide | Manage vegetation and clear zones. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  | STPE | CONSTRUCTION | 9000000 | FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
F-5700 | Ferry | STI (Prioritization) | Hatteras Ferry | Hatteras to Ocracoke Ferry | Purchase river class ferry. |  | Dare, Hyde | 1 | Albemarle RPO | COMPLETE | Division 1 |  |  |  | 13313000
F-5702 | Ferry | Other | Hatteras to Ocracoke Ferry | Hatteras to Ocracoke Ferry | Construct two passenger ferries to be used along new route from Hatteras in Dare County to Ocracoke in Hyde County. Implement transit system to aid passengers on Ocracoke Island. |  | Dare, Hyde | 1 | Albemarle RPO | OTHER FUNDS ARE FROM STATE APPROPRIATION 7355. | Division 1 |  |  |  | 6700000
F-5702A | Ferry | Other | Hatteras to Ocracoke Ferry - Loading Facility | Loading facility | Improve parking lot and construct connectivity measures. |  | Dare | 1 | Albemarle RPO | COMPLETE. WORK ACCOMPLISHED UNDER F-5702B. | Division 1
F-5702B | Ferry | Other | Hatteras to Ocracoke Ferry | Ocracoke Terminal - Silver Lake | Construct Ocracoke pedestrian waiting and access accommodations. |  | Hyde | 1 | Albemarle RPO | COMPLETE. | Division 1
F-5702C | Ferry | Other | Hatteras to Ocracoke Ferry | Hatteras to Ocracoke Ferry | Construct two passenger ferries. |  | Dare, Hyde | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1
F-5702E | Ferry | Other | Hatteras to Ocracoke Ferry | Hatteras and Ocracoke terminals | Construct dock improvements. |  | Dare, Halifax | 1, 4 | Albemarle RPO | COMPLETE. WORK ACCOMPLISHED UNDER F-5702B. | Division 1, 4
F-5704 | Ferry | STI (Prioritization) | Cedar Island to Ocracoke Ferry | Cedar Island to Ocracoke Ferry | Replace M/V Silver Lake Sound Class Ferry. |  | Carteret, Hyde | 1, 2 | Albemarle RPO, Down East RPO |  | Division 1, 2 |  | FBP | ENGINEERING | 3031000
F-5704 | Ferry | STI (Prioritization) | Cedar Island to Ocracoke Ferry | Cedar Island to Ocracoke Ferry | Replace M/V Silver Lake Sound Class Ferry. |  | Carteret, Hyde | 1, 2 | Albemarle RPO, Down East RPO |  | Division 1, 2 |  | T | CONSTRUCTION | 23600000 | FY 2028: 11800000; FY 2029: 11800000
F-5704 | Ferry | STI (Prioritization) | Cedar Island to Ocracoke Ferry | Cedar Island to Ocracoke Ferry | Replace M/V Silver Lake Sound Class Ferry. |  | Carteret, Hyde | 1, 2 | Albemarle RPO, Down East RPO |  | Division 1, 2 |  | FBP | CONSTRUCTION | 2000000 | FY 2028: 1000000; FY 2029: 1000000
FF-0001 | Ferry | Federal Lands Access Program | Hatteras to Ocracoke Ferry | Hatteras and Ocracoke Island terminals | Construct ferry ramp and dock improvements. |  | Dare, Hyde | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. PREVIOUSLY BR-0170. | Exempt |  | FLAP | ENGINEERING | 1070000
FF-0001 | Ferry | Federal Lands Access Program | Hatteras to Ocracoke Ferry | Hatteras and Ocracoke Island terminals | Construct ferry ramp and dock improvements. |  | Dare, Hyde | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. PREVIOUSLY BR-0170. | Exempt |  | HFB | UTILITIES | 10000 | FY 2026: 10000
FF-0001 | Ferry | Federal Lands Access Program | Hatteras to Ocracoke Ferry | Hatteras and Ocracoke Island terminals | Construct ferry ramp and dock improvements. |  | Dare, Hyde | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. PREVIOUSLY BR-0170. | Exempt |  | HFB | CONSTRUCTION | 20000000 | FY 2027: 20000000
FF-0001A | Highway | Federal Lands Access Program | NC 12 | Ocracoke and Hatteras Ferry terminals | Replace passenger ferry docks. |  | Dare, Hyde | 1 | Albemarle RPO |  | Exempt |  | FLAP | CONSTRUCTION | 3250000 | FY 2026: 2430000; FY 2027: 820000
FO-0001 | Ferry | Other | Cherry Branch Ferry | Maintenance depot | Planning and design study. |  | Craven | 2 | Down East RPO |  | Public Transit |  | T | PLANNING | 100000
FO-0001 | Ferry | Other | Cherry Branch Ferry | Maintenance depot | Planning and design study. |  | Craven | 2 | Down East RPO |  | Public Transit |  | FSRC | PLANNING | 400000
HA-0001 | Highway | Appalachian Development Highway System | New Route | Burke County Industrial Park. | Construct access road. | 0.36 | Burke | 13 | Greater Hickory MPO | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | ENGINEERING | 200000
HA-0001 | Highway | Appalachian Development Highway System | New Route | Burke County Industrial Park. | Construct access road. | 0.36 | Burke | 13 | Greater Hickory MPO | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | CONSTRUCTION | 1700000
HA-0002 | Highway | Appalachian Development Highway System | Mountain Industrial Drive | Jennings Industrial Park. | Construct road extension. | 0.41 | Transylvania | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | Exempt |  | ADHSL | ENGINEERING | 200000
HA-0002 | Highway | Appalachian Development Highway System | Mountain Industrial Drive | Jennings Industrial Park. | Construct road extension. | 0.41 | Transylvania | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | Exempt |  | ADHSL | RIGHT-OF-WAY | 10000
HA-0002 | Highway | Appalachian Development Highway System | Mountain Industrial Drive | Jennings Industrial Park. | Construct road extension. | 0.41 | Transylvania | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | Exempt |  | ADHSL | CONSTRUCTION | 739000
HA-0003 | Highway | Appalachian Development Highway System | SR 1970 (Commercial Boulevard) | Industrial Park. | Construct road extension. | 0.38 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | RIGHT-OF-WAY | 70000
HA-0003 | Highway | Appalachian Development Highway System | SR 1970 (Commercial Boulevard) | Industrial Park. | Construct road extension. | 0.38 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | CONSTRUCTION | 1830000
HA-0004 | Highway | Appalachian Development Highway System | US 441 | SR 1515 (Hyatt Road) intersection. | Construct intersection improvements and right-in / right-out at Ingles Development site. | 0.5 | Macon | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION. | Exempt |  |  |  | 300000
HA-0004 | Highway | Appalachian Development Highway System | US 441 | SR 1515 (Hyatt Road) intersection. | Construct intersection improvements and right-in / right-out at Ingles Development site. | 0.5 | Macon | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 1900000
HA-0005 | Highway | Appalachian Development Highway System | New Route | Rutherfordton Industrial Park. | Construct access road. | 0.14 | Rutherford | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | Exempt |  | ADHSL | ENGINEERING | 15000
HA-0005 | Highway | Appalachian Development Highway System | New Route | Rutherfordton Industrial Park. | Construct access road. | 0.14 | Rutherford | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | Exempt |  | ADHSL | RIGHT-OF-WAY | 15000 | FY 2027: 15000
HA-0005 | Highway | Appalachian Development Highway System | New Route | Rutherfordton Industrial Park. | Construct access road. | 0.14 | Rutherford | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | Exempt |  | ADHSL | CONSTRUCTION | 900000 | FY 2028: 10000; FY 2029: 890000
HA-0006 | Highway | Appalachian Development Highway System | Northwest Drive; AEV Lane | NC 88 to Benfield Drive; Northwest Drive to American Emergency Vehicles facility. | Widen road to 12-foot lanes. | 0.49 | Ashe | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | Exempt |  | ADHSL | ENGINEERING | 47000
HA-0006 | Highway | Appalachian Development Highway System | Northwest Drive; AEV Lane | NC 88 to Benfield Drive; Northwest Drive to American Emergency Vehicles facility. | Widen road to 12-foot lanes. | 0.49 | Ashe | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | Exempt |  | ADHSL | RIGHT-OF-WAY | 60000
HA-0006 | Highway | Appalachian Development Highway System | Northwest Drive; AEV Lane | NC 88 to Benfield Drive; Northwest Drive to American Emergency Vehicles facility. | Widen road to 12-foot lanes. | 0.49 | Ashe | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | Exempt |  | ADHSL | CONSTRUCTION | 643000
HA-0007 | Highway | Appalachian Development Highway System | New Route | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Catawba | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | ADHS | ENGINEERING | 91000
HA-0007 | Highway | Appalachian Development Highway System | New Route | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Catawba | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | L | ENGINEERING | 150000
HA-0007 | Highway | Appalachian Development Highway System | New Route | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Catawba | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | HF | ENGINEERING | 91000
HA-0007 | Highway | Appalachian Development Highway System | New Route | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Catawba | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | ADHS | CONSTRUCTION | 909000
HA-0007 | Highway | Appalachian Development Highway System | New Route | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Catawba | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | L | CONSTRUCTION | 851000
HA-0007 | Highway | Appalachian Development Highway System | New Route | SR 1476 (Fairgrove Church Road Southeast). | Construct 0.27 mile access road to cul-de-sac. | 0.27 | Catawba | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | HF | CONSTRUCTION | 259000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  |  |  | 5100000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HFB | RIGHT-OF-WAY | 590000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HFB | UTILITIES | 500000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | DP | CONSTRUCTION | 94100000 | FY 2026: 34622000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | BFP | CONSTRUCTION | 242313000 | FY 2026: 4400000; FY 2027: 99131000; FY 2028: 79304000; FY 2029: 59478000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 18783000 | FY 2026: 4696000; FY 2027: 4696000; FY 2028: 3757000; FY 2029: 2817000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 60109000 | FY 2026: 60109000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HFB | CONSTRUCTION | 45856000 | FY 2026: 25509000; FY 2027: 1826000; FY 2028: 1461000; FY 2029: 1095000
HB-0001 | Highway | Bridges | US 64 | Bridge 880007 over Alligator River | Replace bridge. | 4 | Tyrrell | 1 | Albemarle RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HF(M) | CONSTRUCTION | 60579000 | FY 2026: 1100000; FY 2027: 24783000; FY 2028: 19826000; FY 2029: 14870000
HB-0001A | Highway | Other | US 64 (Future I-87) | I-95 interchange to NC 12. | Install broadband fiber and ITS for traveler information systems. | 145.54 | Martin, Edgecombe, Washington, Dare, Tyrrell, Nash | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | DP | CONSTRUCTION | 15900000 | FY 2027: 2650000; FY 2028: 6625000; FY 2029: 6625000
HB-0001A | Highway | Other | US 64 (Future I-87) | I-95 interchange to NC 12. | Install broadband fiber and ITS for traveler information systems. | 145.54 | Martin, Edgecombe, Washington, Dare, Tyrrell, Nash | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 9540000 | FY 2027: 0; FY 2028: 0; FY 2029: 2385000; FY 2030: 5724000; FY 2031: 1431000
HB-0001A | Highway | Other | US 64 (Future I-87) | I-95 interchange to NC 12. | Install broadband fiber and ITS for traveler information systems. | 145.54 | Martin, Edgecombe, Washington, Dare, Tyrrell, Nash | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1060000 | FY 2027: 0; FY 2028: 0; FY 2029: 265000; FY 2030: 636000; FY 2031: 159000
HB-0002 | Highway | Bridges | I-40 | Bridges 430248 and 430249 over SR 1613 (Beaverdam Road). | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 2000000
HB-0002 | Highway | Bridges | I-40 | Bridges 430248 and 430249 over SR 1613 (Beaverdam Road). | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | UTILITIES | 390000
HB-0002 | Highway | Bridges | I-40 | Bridges 430248 and 430249 over SR 1613 (Beaverdam Road). | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HIB | CONSTRUCTION | 23276000
HB-0002 | Highway | Bridges | I-40 | Bridges 430248 and 430249 over SR 1613 (Beaverdam Road). | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | CONSTRUCTION | 15000000
HB-0003 | Highway | Bridges | I-40 | Bridge 430239 over SR 1550 (Incinerator Road). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 1000000 | FY 2026: 100000
HB-0003 | Highway | Bridges | I-40 | Bridge 430239 over SR 1550 (Incinerator Road). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | UTILITIES | 30000
HB-0003 | Highway | Bridges | I-40 | Bridge 430239 over SR 1550 (Incinerator Road). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | CONSTRUCTION | 27600000
HB-0004 | Highway | Bridges | I-40 | Bridge 430243 over NC 215 (Champion Drive). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 1100000 | FY 2026: 100000
HB-0004 | Highway | Bridges | I-40 | Bridge 430243 over NC 215 (Champion Drive). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | UTILITIES | 360000
HB-0004 | Highway | Bridges | I-40 | Bridge 430243 over NC 215 (Champion Drive). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | CONSTRUCTION | 32860000 | FY 2026: 17200000
HB-0005 | Highway | Bridges | I-40 | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 1600000 | FY 2026: 42000; FY 2027: 252000; FY 2028: 252000; FY 2029: 252000; FY 2030: 802000
HB-0005 | Highway | Bridges | I-40 | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 400000 | FY 2026: 10000; FY 2027: 63000; FY 2028: 63000; FY 2029: 63000; FY 2030: 201000
HB-0005 | Highway | Bridges | I-40 | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | BFP | UTILITIES | 136000 | FY 2026: 136000
HB-0005 | Highway | Bridges | I-40 | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T(M) | UTILITIES | 34000 | FY 2026: 34000
HB-0005 | Highway | Bridges | I-40 | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 20401000 | FY 2032: 204000; FY 2033: 6120000; FY 2034: 5712000; FY 2035: 4693000 | 3672000
HB-0005 | Highway | Bridges | I-40 | Bridges 430205 and 430208 over SR 1364 (Coleman Mountain Road). | Replace bridges. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5100000 | FY 2032: 51000; FY 2033: 1530000; FY 2034: 1428000; FY 2035: 1173000 | 918000
HB-0006 | Highway | Bridges | US 74 | Bridge 430126 over I-40. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 801000 | FY 2028: 25000; FY 2029: 205000; FY 2030: 205000; FY 2031: 206000; FY 2032: 160000
HB-0006 | Highway | Bridges | US 74 | Bridge 430126 over I-40. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 199000 | FY 2028: 6000; FY 2029: 51000; FY 2030: 51000; FY 2031: 51000; FY 2032: 40000
HB-0006 | Highway | Bridges | US 74 | Bridge 430126 over I-40. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 7200000 | FY 2034: 72000; FY 2035: 2808000 | 4320000
HB-0006 | Highway | Bridges | US 74 | Bridge 430126 over I-40. | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1800000 | FY 2034: 18000; FY 2035: 702000 | 1080000
HB-0007 | Highway | Bridges | SR 1529 (Mount Olive Church Road) | Bridges 770299 and 770300 over Saddle Tree Swamp. | Replace bridges. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGOFF | RIGHT-OF-WAY | 77000
HB-0007 | Highway | Bridges | SR 1529 (Mount Olive Church Road) | Bridges 770299 and 770300 over Saddle Tree Swamp. | Replace bridges. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGOFF | UTILITIES | 185000
HB-0007 | Highway | Bridges | SR 1529 (Mount Olive Church Road) | Bridges 770299 and 770300 over Saddle Tree Swamp. | Replace bridges. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGOFF | CONSTRUCTION | 1339000
HB-0008 | Highway | Bridges | SR 1214 (Mount Pisgah Church Road) | Bridge 420034 over Upper Little River. | Replace bridge. | 0.25 | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | RIGHT-OF-WAY | 330000 | FY 2026: 330000
HB-0008 | Highway | Bridges | SR 1214 (Mount Pisgah Church Road) | Bridge 420034 over Upper Little River. | Replace bridge. | 0.25 | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | UTILITIES | 100000 | FY 2026: 100000
HB-0008 | Highway | Bridges | SR 1214 (Mount Pisgah Church Road) | Bridge 420034 over Upper Little River. | Replace bridge. | 0.25 | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | CONSTRUCTION | 2700000 | FY 2028: 1323000; FY 2029: 1377000
HB-0009 | Highway | Bridges | SR 1800 (Blacksmith Road) | Bridge 230250 over Ricefield Branch. | Replace bridge. | 0.25 | Columbus | 6 | Cape Fear RPO |  | Division 6 |  | BGOFF | RIGHT-OF-WAY | 140000 | FY 2029: 140000
HB-0009 | Highway | Bridges | SR 1800 (Blacksmith Road) | Bridge 230250 over Ricefield Branch. | Replace bridge. | 0.25 | Columbus | 6 | Cape Fear RPO |  | Division 6 |  | BGOFF | UTILITIES | 130000 | FY 2029: 130000
HB-0009 | Highway | Bridges | SR 1800 (Blacksmith Road) | Bridge 230250 over Ricefield Branch. | Replace bridge. | 0.25 | Columbus | 6 | Cape Fear RPO |  | Division 6 |  | BGOFF | CONSTRUCTION | 1600000 | FY 2030: 1280000; FY 2031: 320000
HB-0010 | Highway | Bridges | SR 1716 (Jackie Lee Road) | Bridge 250091 over Wade Canal. | Replace bridge. | 0.25 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | RIGHT-OF-WAY | 120000 | FY 2028: 120000
HB-0010 | Highway | Bridges | SR 1716 (Jackie Lee Road) | Bridge 250091 over Wade Canal. | Replace bridge. | 0.25 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | CONSTRUCTION | 1300000 | FY 2030: 897000; FY 2031: 403000
HB-0015 | Highway | Bridges | US 19 / US 23 / US 74 | Bridge 430133 over SR 1527 (Jones Cove Road). | Replace bridge. | 0.25 | Haywood | 14 | French Broad River MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY | Highway Fund
HB-0016 | Highway | Bridges | NC 32 | Bridge 930015 over Albemarle Sound. | Preserve bridge. | 3.5 | Washington | 1 | Albemarle RPO |  | Region A |  | BFP | CONSTRUCTION | 40001000 | FY 2027: 4841000; FY 2028: 13606000; FY 2029: 10830000; FY 2030: 9754000; FY 2031: 970000
HB-0016 | Highway | Bridges | NC 32 | Bridge 930015 over Albemarle Sound. | Preserve bridge. | 3.5 | Washington | 1 | Albemarle RPO |  | Region A |  | T(M) | CONSTRUCTION | 10000000 | FY 2027: 1210000; FY 2028: 3402000; FY 2029: 2708000; FY 2030: 2438000; FY 2031: 242000
HB-0017 | Highway | Bridges | US 64 | Bridge 270009 over Croatan Sound in Manns Harbor. | Preserve bridge. | 2.85 | Dare | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | BFP | CONSTRUCTION | 44018000 | FY 2026: 12960000
HB-0017 | Highway | Bridges | US 64 | Bridge 270009 over Croatan Sound in Manns Harbor. | Preserve bridge. | 2.85 | Dare | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 11005000 | FY 2026: 3240000
HB-0018 | Highway | Bridges | I-40 | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 568000 | FY 2026: 568000
HB-0018 | Highway | Bridges | I-40 | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 142000 | FY 2026: 142000
HB-0018 | Highway | Bridges | I-40 | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | UTILITIES | 528000 | FY 2026: 528000
HB-0018 | Highway | Bridges | I-40 | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | T(M) | UTILITIES | 132000 | FY 2026: 132000
HB-0018 | Highway | Bridges | I-40 | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 47919000 | FY 2030: 479000; FY 2031: 12938000; FY 2032: 12938000; FY 2033: 11501000; FY 2034: 10063000
HB-0018 | Highway | Bridges | I-40 | Bridges 480006 and 480007 over Catawba River. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 11981000 | FY 2030: 120000; FY 2031: 3235000; FY 2032: 3235000; FY 2033: 2875000; FY 2034: 2516000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 222000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 890000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 140000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 42000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | T(M) | RIGHT-OF-WAY | 11000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 559000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 54000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | UTILITIES | 16000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | T(M) | UTILITIES | 4000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HF(M) | UTILITIES | 216000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 1294000 | FY 2027: 1294000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 6626000 | FY 2027: 1922000; FY 2028: 2054000; FY 2029: 1590000; FY 2030: 1060000
HB-0020 | Highway | Bridges | SR 1185 (Curtis Bridge Road) | Bridge 960730 over Yadkin River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 5178000 | FY 2027: 1502000; FY 2028: 1605000; FY 2029: 1243000; FY 2030: 828000
HB-0021 | Highway | Municipal Bridge | Oxford Road | Bridge 730419 over Meeting House Branch in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | BFPOFF | RIGHT-OF-WAY | 50000
HB-0021 | Highway | Municipal Bridge | Oxford Road | Bridge 730419 over Meeting House Branch in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | BFPOFF | UTILITIES | 143000
HB-0021 | Highway | Municipal Bridge | Oxford Road | Bridge 730419 over Meeting House Branch in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | BFPOFF | CONSTRUCTION | 1180000
HB-0022 | Highway | Municipal Bridge | Rock Springs Road | Bridge 730096 over Greens Mill Run in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BFPOFF | RIGHT-OF-WAY | 100000 | FY 2029: 100000
HB-0022 | Highway | Municipal Bridge | Rock Springs Road | Bridge 730096 over Greens Mill Run in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BFPOFF | UTILITIES | 126000 | FY 2029: 126000
HB-0022 | Highway | Municipal Bridge | Rock Springs Road | Bridge 730096 over Greens Mill Run in Greenville. | Replace bridge. | 0.25 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | BFPOFF | CONSTRUCTION | 1800000 | FY 2030: 846000; FY 2031: 954000
HB-0023 | Highway | Bridges | SR 1876 (Sonoma Road / Max Thompson Road) | Bridge 430169 over West Fork Pigeon River and bridge 430170 over East Fork Pigeon River. | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | RIGHT-OF-WAY | 320000
HB-0023 | Highway | Bridges | SR 1876 (Sonoma Road / Max Thompson Road) | Bridge 430169 over West Fork Pigeon River and bridge 430170 over East Fork Pigeon River. | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | UTILITIES | 300000
HB-0023 | Highway | Bridges | SR 1876 (Sonoma Road / Max Thompson Road) | Bridge 430169 over West Fork Pigeon River and bridge 430170 over East Fork Pigeon River. | Replace bridges. | 0.25 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 5000000
HB-0024 | Highway | Bridges | US 401 | Bridge 340056 over Sandy Creek. | Replace bridge. | 0.25 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BFP | RIGHT-OF-WAY | 60000 | FY 2027: 60000
HB-0024 | Highway | Bridges | US 401 | Bridge 340056 over Sandy Creek. | Replace bridge. | 0.25 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BFP | UTILITIES | 180000 | FY 2027: 180000
HB-0024 | Highway | Bridges | US 401 | Bridge 340056 over Sandy Creek. | Replace bridge. | 0.25 | Franklin | 5 | Capital Area MPO |  | Division 5 |  | BFP | CONSTRUCTION | 3700000 | FY 2029: 37000; FY 2030: 2257000; FY 2031: 1406000
HB-0025 | Highway | Bridges | SR 1004 (Poors Ford Road) | Bridge 740087 over Broad River. | Replace bridge. | 0.25 | Polk | 14 | Foothills RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 310000 | FY 2026: 310000
HB-0025 | Highway | Bridges | SR 1004 (Poors Ford Road) | Bridge 740087 over Broad River. | Replace bridge. | 0.25 | Polk | 14 | Foothills RPO |  | Division 14 |  | BGOFF | UTILITIES | 600000 | FY 2026: 600000
HB-0025 | Highway | Bridges | SR 1004 (Poors Ford Road) | Bridge 740087 over Broad River. | Replace bridge. | 0.25 | Polk | 14 | Foothills RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 13900000 | FY 2028: 139000; FY 2029: 7506000; FY 2030: 4865000; FY 2031: 1390000
HB-0026 | Highway | Bridges | SR 1533 (Everett Road) | Bridge 870030 over French Broad River. | Replace bridge. | 0.25 | Transylvania | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 380000 | FY 2026: 380000
HB-0026 | Highway | Bridges | SR 1533 (Everett Road) | Bridge 870030 over French Broad River. | Replace bridge. | 0.25 | Transylvania | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | UTILITIES | 130000 | FY 2026: 130000
HB-0026 | Highway | Bridges | SR 1533 (Everett Road) | Bridge 870030 over French Broad River. | Replace bridge. | 0.25 | Transylvania | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 7200000 | FY 2028: 2808000; FY 2029: 2664000; FY 2030: 1728000
HB-0027 | Highway | Bridges | SR 1355 (Panther Creek Road) | Bridge 430206 over Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 70000 | FY 2026: 70000
HB-0027 | Highway | Bridges | SR 1355 (Panther Creek Road) | Bridge 430206 over Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | UTILITIES | 40000 | FY 2026: 40000
HB-0027 | Highway | Bridges | SR 1355 (Panther Creek Road) | Bridge 430206 over Fines Creek. | Replace bridge. | 0.25 | Haywood | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 2400000 | FY 2028: 24000; FY 2029: 2184000; FY 2030: 192000
HB-0029 | Highway | Bridges | SR 1179 (Bridge Street) | Bridge 910497 over Norfolk Southern Railroad in Fuquay-Varina. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2027: 100000
HB-0029 | Highway | Bridges | SR 1179 (Bridge Street) | Bridge 910497 over Norfolk Southern Railroad in Fuquay-Varina. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | UTILITIES | 100000 | FY 2027: 100000
HB-0029 | Highway | Bridges | SR 1179 (Bridge Street) | Bridge 910497 over Norfolk Southern Railroad in Fuquay-Varina. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2029: 1380000; FY 2030: 620000
HB-0030 | Highway | Bridges | SR 1679 (Peeks Creek Road) | Bridge 550055 over Cullasaja River. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | BGOFF | RIGHT-OF-WAY | 480000
HB-0030 | Highway | Bridges | SR 1679 (Peeks Creek Road) | Bridge 550055 over Cullasaja River. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | BGOFF | UTILITIES | 360000
HB-0030 | Highway | Bridges | SR 1679 (Peeks Creek Road) | Bridge 550055 over Cullasaja River. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | BGOFF | CONSTRUCTION | 3200000 | FY 2026: 1952000; FY 2027: 1248000
HB-0031 | Highway | Bridges | Third Street, Fourth Street, Fifth Street | Bridges 330185, 330191, and 330203 over US 52 (Future I-285) / US 311 in downtown Winston-Salem. | Replace bridges. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 950000 | FY 2027: 950000
HB-0031 | Highway | Bridges | Third Street, Fourth Street, Fifth Street | Bridges 330185, 330191, and 330203 over US 52 (Future I-285) / US 311 in downtown Winston-Salem. | Replace bridges. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 50000 | FY 2027: 50000
HB-0031 | Highway | Bridges | Third Street, Fourth Street, Fifth Street | Bridges 330185, 330191, and 330203 over US 52 (Future I-285) / US 311 in downtown Winston-Salem. | Replace bridges. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 9500000 | FY 2029: 95000; FY 2030: 3515000; FY 2031: 3135000; FY 2032: 2090000; FY 2033: 665000
HB-0032 | Highway | Bridges | SR 1004 (Hudson Chapel Road) | Bridge 480081 over Catawba River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | RIGHT-OF-WAY | 1000000
HB-0032 | Highway | Bridges | SR 1004 (Hudson Chapel Road) | Bridge 480081 over Catawba River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | UTILITIES | 10000
HB-0032 | Highway | Bridges | SR 1004 (Hudson Chapel Road) | Bridge 480081 over Catawba River. | Replace bridge. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 20400000 | FY 2028: 204000; FY 2029: 7140000; FY 2030: 5508000; FY 2031: 4284000; FY 2032: 3264000
HB-0033 | Highway | Bridges | Polo Road | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFP | RIGHT-OF-WAY | 240000 | FY 2029: 240000
HB-0033 | Highway | Bridges | Polo Road | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T(M) | RIGHT-OF-WAY | 60000 | FY 2029: 60000
HB-0033 | Highway | Bridges | Polo Road | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFP | UTILITIES | 240000 | FY 2029: 240000
HB-0033 | Highway | Bridges | Polo Road | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T(M) | UTILITIES | 60000 | FY 2029: 60000
HB-0033 | Highway | Bridges | Polo Road | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFP | CONSTRUCTION | 6610000 | FY 2031: 2362000; FY 2032: 2736000; FY 2033: 1512000
HB-0033 | Highway | Bridges | Polo Road | Bridge 330284 over SR 4000 (University Parkway) in Winston-Salem. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T(M) | CONSTRUCTION | 1439000 | FY 2031: 590000; FY 2032: 547000; FY 2033: 302000
HB-0034 | Highway | Bridges | SR 1007 (Plank Road) | Bridge 180169 over Deep River. | Replace bridge. | 0.25 | Chatham, Lee | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | RIGHT-OF-WAY | 325000 | FY 2030: 325000
HB-0034 | Highway | Bridges | SR 1007 (Plank Road) | Bridge 180169 over Deep River. | Replace bridge. | 0.25 | Chatham, Lee | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | UTILITIES | 325000 | FY 2030: 325000
HB-0034 | Highway | Bridges | SR 1007 (Plank Road) | Bridge 180169 over Deep River. | Replace bridge. | 0.25 | Chatham, Lee | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | CONSTRUCTION | 6500000 | FY 2032: 1430000; FY 2033: 2730000; FY 2034: 1820000; FY 2035: 520000
HB-0035 | Highway | Bridges | SR 1535 (Price Road) | Bridge 780177 over Matrimony Creek in Eden. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 410000
HB-0035 | Highway | Bridges | SR 1535 (Price Road) | Bridge 780177 over Matrimony Creek in Eden. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | UTILITIES | 300000
HB-0035 | Highway | Bridges | SR 1535 (Price Road) | Bridge 780177 over Matrimony Creek in Eden. | Replace bridge. | 0.25 | Rockingham | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 4900000 | FY 2026: 49000; FY 2027: 3283000; FY 2028: 1274000; FY 2029: 294000
HB-0036 | Highway | Bridges | Sixteenth Street | Bridge 330390 over rail corridor and Bridge 330244 over US 52( Future I-285) / NC 8 in Winston-Salem. | Replace bridge. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 1300000 | FY 2026: 1300000
HB-0036 | Highway | Bridges | Sixteenth Street | Bridge 330390 over rail corridor and Bridge 330244 over US 52( Future I-285) / NC 8 in Winston-Salem. | Replace bridge. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 850000 | FY 2026: 850000
HB-0036 | Highway | Bridges | Sixteenth Street | Bridge 330390 over rail corridor and Bridge 330244 over US 52( Future I-285) / NC 8 in Winston-Salem. | Replace bridge. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 4200000 | FY 2027: 42000; FY 2028: 2268000; FY 2029: 1554000; FY 2030: 336000
HB-0037 | Highway | Bridges | SR 1679 (Gold Mine Road) | Bridge 550056 over Cullasaja River. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HB-0037 | Highway | Bridges | SR 1679 (Gold Mine Road) | Bridge 550056 over Cullasaja River. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | UTILITIES | 50000 | FY 2026: 50000
HB-0037 | Highway | Bridges | SR 1679 (Gold Mine Road) | Bridge 550056 over Cullasaja River. | Replace bridge. | 0.25 | Macon | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1000000 | FY 2027: 1000000
HB-0038 | Highway | Bridges | SR 1745 (Bend of the River Road) | Bridge 630110 over Tar River Reservoir. | Replace bridge. | 0.25 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | BGOFF | CONSTRUCTION | 6500000 | FY 2027: 2470000; FY 2028: 3120000; FY 2029: 910000
HB-0039 | Highway | STI (Prioritization) | US 17 / US 76 / US 421 | Bridge 640013 (Cape Fear Memorial Bridge) over Cape Fear River. | Replace bridge. This is a toll project. Wilmington MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 0.8 | New Hanover | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2031 - 2045. | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 41000000 |  | 410000 | 3690000 | 8200000 | 8200000 | 8200000 | 8200000 | 4100000
HB-0039 | Highway | STI (Prioritization) | US 17 / US 76 / US 421 | Bridge 640013 (Cape Fear Memorial Bridge) over Cape Fear River. | Replace bridge. This is a toll project. Wilmington MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 0.8 | New Hanover | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2031 - 2045. | Statewide Mobility |  | BOND R | UTILITIES | 3300000 | FY 2027: 33000; FY 2028: 3267000
HB-0039 | Highway | STI (Prioritization) | US 17 / US 76 / US 421 | Bridge 640013 (Cape Fear Memorial Bridge) over Cape Fear River. | Replace bridge. This is a toll project. Wilmington MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 0.8 | New Hanover | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2031 - 2045. | Statewide Mobility |  | NHP | GARVEE CON | 110505000 | FY 2031: 7367000; FY 2032: 7367000; FY 2033: 7367000; FY 2034: 7367000; FY 2035: 7367000 | 51569000
HB-0039 | Highway | STI (Prioritization) | US 17 / US 76 / US 421 | Bridge 640013 (Cape Fear Memorial Bridge) over Cape Fear River. | Replace bridge. This is a toll project. Wilmington MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 0.8 | New Hanover | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2031 - 2045. | Statewide Mobility |  | DP | CONSTRUCTION | 242150000 | FY 2027: 9768000; FY 2028: 87912000; FY 2029: 144470000
HB-0039 | Highway | STI (Prioritization) | US 17 / US 76 / US 421 | Bridge 640013 (Cape Fear Memorial Bridge) over Cape Fear River. | Replace bridge. This is a toll project. Wilmington MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 0.8 | New Hanover | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2031 - 2045. | Statewide Mobility |  | BOND R | CONSTRUCTION | 649650000 | FY 2027: 50890000; FY 2028: 195360000; FY 2029: 195360000; FY 2030: 110360000; FY 2031: 97680000
HB-0040 | Highway | Bridges | US 76 / US 74 | Bridges 640021, 640022, and 64024 in New Hanover County. | Replace bridges. | 0.9 | New Hanover | 3 | Wilmington Urban Area MPO | PROJECT BEING DELIVERED THROUGH STRUCTURES MANAGEMENT HIGH FUND BRIDGE PROGRAM. | Region B |  | HFB | RIGHT-OF-WAY | 32200000 | FY 2026: 32200000
HB-0040 | Highway | Bridges | US 76 / US 74 | Bridges 640021, 640022, and 64024 in New Hanover County. | Replace bridges. | 0.9 | New Hanover | 3 | Wilmington Urban Area MPO | PROJECT BEING DELIVERED THROUGH STRUCTURES MANAGEMENT HIGH FUND BRIDGE PROGRAM. | Region B |  | HFB | UTILITIES | 2000000 | FY 2026: 2000000
HB-0040 | Highway | Bridges | US 76 / US 74 | Bridges 640021, 640022, and 64024 in New Hanover County. | Replace bridges. | 0.9 | New Hanover | 3 | Wilmington Urban Area MPO | PROJECT BEING DELIVERED THROUGH STRUCTURES MANAGEMENT HIGH FUND BRIDGE PROGRAM. | Region B |  | HFB | CONSTRUCTION | 48100000 | FY 2026: 48100000
HB-0041 | Highway | Bridges | I-77 | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 296000 | FY 2026: 296000
HB-0041 | Highway | Bridges | I-77 | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 74000 | FY 2026: 74000
HB-0041 | Highway | Bridges | I-77 | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | UTILITIES | 256000 | FY 2026: 256000
HB-0041 | Highway | Bridges | I-77 | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | T(M) | UTILITIES | 64000 | FY 2026: 64000
HB-0041 | Highway | Bridges | I-77 | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 19120000 | FY 2030: 191000; FY 2031: 11889000; FY 2032: 7040000
HB-0041 | Highway | Bridges | I-77 | Bridges 480133 and 480128 over Third Creek. | Replace bridges. | 0.25 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 4780000 | FY 2030: 48000; FY 2031: 2972000; FY 2032: 1760000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 25000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 73000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 300000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 200000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 70000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 146000 | FY 2026: 146000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 772000 | FY 2026: 687000; FY 2027: 85000
HB-0043 | Highway | Bridges | SR 1523 (Silas Creek Road) | Bridge 040047 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 583000 | FY 2026: 519000; FY 2027: 64000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 42000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 260000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 167000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 21000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 185000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 84000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 2000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 8000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 243000 | FY 2026: 243000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 986000 | FY 2026: 10000; FY 2027: 799000; FY 2028: 177000
HB-0044 | Highway | Bridges | SR 1644 (McNeil Road) | Bridge 040093 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 972000 | FY 2026: 10000; FY 2027: 787000; FY 2028: 175000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 240000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 270000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 40000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 691000 | FY 2026: 7000; FY 2027: 622000; FY 2028: 62000
HB-0045 | Highway | Bridges | SR 1609 (Upper Cranberry Creek Road) | Bridge 040183 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 582000; FY 2028: 59000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 36000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 225000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 145000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 19000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 127000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 74000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 2000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 8000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 210000 | FY 2026: 210000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1248000 | FY 2026: 12000; FY 2027: 1136000; FY 2028: 100000
HB-0046 | Highway | Bridges | SR 1105 (New River Bridge Road) | Bridge 040226 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 840000 | FY 2026: 8000; FY 2027: 765000; FY 2028: 67000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 22000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 75000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 339000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 210000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 20000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 129000 | FY 2026: 129000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 953000 | FY 2026: 10000; FY 2027: 943000
HB-0047 | Highway | Bridges | SR 1528 (Jim Duvall Road) | Bridge 040304 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 518000 | FY 2026: 5000; FY 2027: 513000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 225000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 400000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 20000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 260000 | FY 2026: 260000
HB-0048 | Highway | Bridges | SR 1606 (Double Springs Church Road) | Bridge 040343 over Cranberry Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1041000 | FY 2026: 10000; FY 2027: 936000; FY 2028: 95000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 56000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 130000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 222000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 11000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 87000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 42000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 40000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 324000 | FY 2026: 324000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 682000 | FY 2026: 7000; FY 2027: 552000; FY 2028: 123000
HB-0049 | Highway | Bridges | SR 1602 (North Fulton Reeves Road) | Bridge 040351 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1295000 | FY 2026: 13000; FY 2027: 1049000; FY 2028: 233000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 56000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 125000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 222000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 172000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 840000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 688000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 2000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 8000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 323000 | FY 2026: 323000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1582000 | FY 2026: 16000; FY 2027: 1076000; FY 2028: 490000
HB-0050 | Highway | Bridges | SR 1563 (Clifton Road) | Bridge 040463 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1295000 | FY 2026: 13000; FY 2027: 881000; FY 2028: 401000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 42000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 159000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 167000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 38000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 172000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 10000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 460000 | FY 2026: 460000
HB-0051 | Highway | Bridges | SR 1159 (Boggs Road) | Bridge 040466 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 460000 | FY 2026: 363000; FY 2027: 97000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 36000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 200000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 145000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 17000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 124000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 69000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 3000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 12000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 210000 | FY 2026: 210000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1348000 | FY 2026: 13000; FY 2027: 1227000; FY 2028: 108000
HB-0052 | Highway | Bridges | SR 1104 (Brown Road) | Bridge 040477 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 840000 | FY 2026: 8000; FY 2027: 765000; FY 2028: 67000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 25000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 300000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 100000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 20000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 181000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 79000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 8000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 32000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 146000 | FY 2026: 146000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 972000 | FY 2026: 10000; FY 2027: 875000; FY 2028: 87000
HB-0053 | Highway | Bridges | SR 1126 (Ed Little Road) | Bridge 040480 over North Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 583000 | FY 2026: 6000; FY 2027: 525000; FY 2028: 52000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 56000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 220000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 222000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 150000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 30000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 324000 | FY 2026: 324000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 2082000 | FY 2026: 21000; FY 2027: 1416000; FY 2028: 645000
HB-0054 | Highway | Bridges | SR 1222 (Methodist Camp Road) | Bridge 040509 over South Fork New River. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1295000 | FY 2026: 13000; FY 2027: 881000; FY 2028: 401000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 265000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 270000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 10000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 2191000 | FY 2026: 22000; FY 2027: 2169000
HB-0055 | Highway | Bridges | SR 1326 (Puckett Road) | Bridge 050091 over Elk River. | Replace bridge. | 0.25 | Avery | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 641000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 511000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 12000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 211000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 48000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 16000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 64000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 991000 | FY 2026: 10000; FY 2027: 892000; FY 2028: 89000
HB-0056 | Highway | Bridges | SR 1514 (Indian Grave Road) | Bridge 130130 over Yadkin River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 646000 | FY 2026: 6000; FY 2027: 582000; FY 2028: 58000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 320000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 290000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 10000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 991000 | FY 2026: 10000; FY 2027: 822000; FY 2028: 159000
HB-0057 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130185 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 537000; FY 2028: 104000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 320000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 160000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 60000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 791000 | FY 2026: 8000; FY 2027: 720000; FY 2028: 63000
HB-0058 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130186 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 589000; FY 2028: 52000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | ENGINEERING | 28000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | BGOFF | ENGINEERING | 310000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | ENGINEERING | 111000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | RIGHT-OF-WAY | 120000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | UTILITIES | 40000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | BGOFF | CONSTRUCTION | 891000 | FY 2026: 9000; FY 2027: 811000; FY 2028: 71000
HB-0059 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130275 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | CONSTRUCTION | 648000 | FY 2026: 6000; FY 2027: 590000; FY 2028: 52000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 36000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 280000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 145000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 270000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 60000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 210000 | FY 2026: 210000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 948000 | FY 2026: 9000; FY 2027: 863000; FY 2028: 76000
HB-0060 | Highway | Bridges | SR 1356 (Old Johns River Road) | Bridge 130317 over Johns River. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 841000 | FY 2026: 8000; FY 2027: 765000; FY 2028: 68000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | ENGINEERING | 22000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | ENGINEERING | 389000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | RIGHT-OF-WAY | 26000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | BGOFF | RIGHT-OF-WAY | 8000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | RIGHT-OF-WAY | 106000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | UTILITIES | 8000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | UTILITIES | 32000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | CONSTRUCTION | 130000 | FY 2026: 130000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | BGOFF | CONSTRUCTION | 853000 | FY 2026: 9000; FY 2027: 844000
HB-0061 | Highway | Bridges | SR 1574 (C C Camp Road) | Bridge 130349 over Jones Creek. | Replace bridge. | 0.25 | Caldwell | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | CONSTRUCTION | 518000 | FY 2026: 5000; FY 2027: 513000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 275000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 17000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 414000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 69000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 48000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1191000 | FY 2026: 12000; FY 2027: 1084000; FY 2028: 95000
HB-0062 | Highway | Bridges | SR 1594 (Aldridge Road) | Bridge 940319 over Watauga River. | Replace bridge. | 0.25 | Watauga | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 589000; FY 2028: 52000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 315000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 4000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 53000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 4000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 16000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 791000 | FY 2026: 8000; FY 2027: 783000
HB-0063 | Highway | Bridges | SR 1559 (Colvard Road) | Bridge 960341 over Mid Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 641000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 22000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 310000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 89000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 26000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 104000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 8000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 32000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 129000 | FY 2026: 129000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 753000 | FY 2026: 8000; FY 2027: 745000
HB-0064 | Highway | Bridges | SR 1567 (Sheets Gap Road) | Bridge 960655 over Wingler Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 518000 | FY 2026: 5000; FY 2027: 513000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 25000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 400000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 214000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 53000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 4000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 16000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 146000 | FY 2026: 146000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1172000 | FY 2026: 12000; FY 2027: 996000; FY 2028: 164000
HB-0065 | Highway | Bridges | SR 1170 (Casper Hawkins Road) | Bridge 960691 over Stony Fork Creek. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 584000 | FY 2026: 6000; FY 2027: 496000; FY 2028: 82000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 300000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 11000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 77000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 42000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 48000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1291000 | FY 2026: 13000; FY 2027: 1175000; FY 2028: 103000
HB-0066 | Highway | Bridges | SR 1355 (White Oak Road) | Bridge 960340 over South Fork Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 589000; FY 2028: 52000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | ENGINEERING | 260000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 200000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 10000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 791000 | FY 2026: 8000; FY 2027: 783000
HB-0067 | Highway | Bridges | SR 1433 (Scenic Valley Road) | Bridge 020082 over Brush Creek. | Replace bridge. | 0.25 | Alleghany | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 6000; FY 2027: 641000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 261000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 127000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 2000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 8000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 691000 | FY 2026: 691000
HB-0068 | Highway | Bridges | SR 1527 (Helton Road) | Bridge 040048 over Helton Creek. | Replace bridge. | 0.25 | Ashe | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 648000 | FY 2026: 648000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 333000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 1334000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 745000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGANY | RIGHT-OF-WAY | 221000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | T(M) | RIGHT-OF-WAY | 55000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 2980000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 261000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGANY | UTILITIES | 78000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | T(M) | UTILITIES | 20000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HF(M) | UTILITIES | 1043000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 1627000 | FY 2027: 1627000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BFP | CONSTRUCTION | 6507000 | FY 2027: 65000; FY 2028: 1952000; FY 2029: 1887000; FY 2030: 1497000; FY 2031: 1106000
HB-0069 | Highway | Bridges | US 421 Business | Bridge 960012 over Reddies River. | Replace bridge. | 0.25 | Wilkes | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 6506000 | FY 2027: 77000; FY 2028: 1948000; FY 2029: 1883000; FY 2030: 1494000; FY 2031: 1104000
HB-0070 | Highway | Bridges | US 13 / US 17 (Future I-87) | Bridges 070155, 070156, 070158, and 070159 over Roanoke River overflow | Repair bridges. | 1 | Bertie | 1 | Peanut Belt RPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 3440000 | FY 2026: 1901000; FY 2027: 1539000
HB-0070 | Highway | Bridges | US 13 / US 17 (Future I-87) | Bridges 070155, 070156, 070158, and 070159 over Roanoke River overflow | Repair bridges. | 1 | Bertie | 1 | Peanut Belt RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 860000 | FY 2026: 475000; FY 2027: 385000
HB-0071 | Highway | Bridges | SR 2207 (Faith Rock Road) | Bridge 750176 over creek off Deep River. | Replace bridge. |  | Randolph | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. RIGHT-OF-WAY IN PROGRESS | Division 8 |  | BGOFF | RIGHT-OF-WAY | 20000
HB-0071 | Highway | Bridges | SR 2207 (Faith Rock Road) | Bridge 750176 over creek off Deep River. | Replace bridge. |  | Randolph | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. RIGHT-OF-WAY IN PROGRESS | Division 8 |  | HP | CONSTRUCTION | 409000 | FY 2026: 221000; FY 2027: 188000
HB-0071 | Highway | Bridges | SR 2207 (Faith Rock Road) | Bridge 750176 over creek off Deep River. | Replace bridge. |  | Randolph | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. RIGHT-OF-WAY IN PROGRESS | Division 8 |  | BGOFF | CONSTRUCTION | 289000 | FY 2026: 156000; FY 2027: 133000
HB-0071 | Highway | Bridges | SR 2207 (Faith Rock Road) | Bridge 750176 over creek off Deep River. | Replace bridge. |  | Randolph | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T(M) | CONSTRUCTION | 102000 | FY 2026: 55000; FY 2027: 47000
HB-0072 | Highway | Bridges | SR 1629 (Flat Rock Road) | Bridge 380199 over Fork Creek | Replace bridge. |  | Granville | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077. | Division 5 |  | HP | CONSTRUCTION | 770000 | FY 2026: 439000; FY 2027: 331000
HB-0072 | Highway | Bridges | SR 1629 (Flat Rock Road) | Bridge 380199 over Fork Creek | Replace bridge. |  | Granville | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077. | Division 5 |  | BGOFF | CONSTRUCTION | 1238000 | FY 2026: 706000; FY 2027: 532000
HB-0072 | Highway | Bridges | SR 1629 (Flat Rock Road) | Bridge 380199 over Fork Creek | Replace bridge. |  | Granville | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077. | Division 5 |  | T(M) | CONSTRUCTION | 193000 | FY 2026: 110000; FY 2027: 83000
HB-0088 | Highway | Bridges | Various | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BGOFF | CONSTRUCTION | 272854000 | 0 | 0 | 0 | 0 | 11787000 | 18789000 | 23752000 | 35661000 | 36573000 | 36573000 | 109719000
HB-0088DIV | Highway | Bridges | Various | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BFP | CONSTRUCTION | 144938000 | 0 | 0 | 0 | 0 | 21757000 | 0 | 0 | 0 | 10415000 | 21284000 | 91482000
HB-0088REG | Highway | Bridges | Various | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Region SW |  | BFP | CONSTRUCTION | 144938000 | 0 | 0 | 0 | 0 | 21757000 | 0 | 0 | 0 | 10415000 | 21284000 | 91482000
HB-0088SW | Highway | Bridges | Various | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | BFP | CONSTRUCTION | 193250000 | 0 | 0 | 0 | 0 | 29009000 | 0 | 0 | 0 | 13886000 | 28379000 | 121976000
HB-0099A | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program inspections. |  | Statewide | 99 | Statewide Project
HB-0099ADIV | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program inspections. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 85800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000
HB-0099AREG | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program inspections. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 85800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000
HB-0099ASW | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program inspections. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 114400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000
HB-0099B | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program structure inventory and appraisal. |  | Statewide | 99 | Statewide Project
HB-0099BDIV | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program structure inventory and appraisal. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 6600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
HB-0099C | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program analysis. |  | Statewide | 99 | Statewide Project
HB-0099CDIV | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program analysis. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 8580000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000
HB-0099CREG | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program analysis. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 8580000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000
HB-0099CSW | Highway | Bridges | Various | Locations statewide | Funding for bridge inspection program analysis. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 11440000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000
HB-8888 | Highway | Bridges | Various | Locations statewide | Bridge replacement program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BGOFF | CONSTRUCTION | 6844000
HB-8888DIV | Highway | Bridges | Various | Locations divisionwide | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BFP | CONSTRUCTION | 0
HB-8888DIV | Highway | Bridges | Various | Locations divisionwide | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T(M) | CONSTRUCTION | 0
HB-8888REG | Highway | Bridges | Various | Locations regionwide | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Region SW |  | BFP | CONSTRUCTION | 0
HB-8888REG | Highway | Bridges | Various | Locations regionwide | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T(M) | CONSTRUCTION | 0
HB-8888SW | Highway | Bridges | Various | Locations statewide | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | BFP | CONSTRUCTION | 0
HB-8888SW | Highway | Bridges | Various | Locations statewide | Unprogrammed bridge replacement program balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 0
HE-0001 | Highway | Economic Development | I-26 | SR 3865 (Frederick Law Olmstead Way East) interchange | Construct new interchange near an access road near mile marker 35. | 1 | Buncombe | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | Exempt |  | HF | ENGINEERING | 4595000
HE-0001 | Highway | Economic Development | I-26 | SR 3865 (Frederick Law Olmstead Way East) interchange | Construct new interchange near an access road near mile marker 35. | 1 | Buncombe | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | Exempt |  | HF | RIGHT-OF-WAY | 200000
HE-0001 | Highway | Economic Development | I-26 | SR 3865 (Frederick Law Olmstead Way East) interchange | Construct new interchange near an access road near mile marker 35. | 1 | Buncombe | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | Exempt |  | HF | MITIGATION | 64000
HE-0001A | Highway | Economic Development | I-26 | Mile marker 35. | Construct new interchange. |  | Buncombe | 13 | French Broad River MPO | DP represents MPDG Rural Grant | Exempt |  | DP | CONSTRUCTION | 17500000
HE-0001A | Highway | Economic Development | I-26 | Mile marker 35. | Construct new interchange. |  | Buncombe | 13 | French Broad River MPO | DP represents MPDG Rural Grant | Exempt |  | HF(M) | CONSTRUCTION | 17500000
HE-0001A | Highway | Economic Development | I-26 | Mile marker 35. | Construct new interchange. |  | Buncombe | 13 | French Broad River MPO | DP represents MPDG Rural Grant | Exempt |  | HF | CONSTRUCTION | 10242000
HE-0001B | Highway | Economic Development | New Route | Frederick Law Olmstead Way East to I-26. | Construct two lane road with sidewalk. |  | Buncombe | 13 | French Broad River MPO | DP represents MPDG Rural Grant | Exempt |  | DP | CONSTRUCTION | 12000000 | FY 2026: 12000000
HE-0001B | Highway | Economic Development | New Route | Frederick Law Olmstead Way East to I-26. | Construct two lane road with sidewalk. |  | Buncombe | 13 | French Broad River MPO | DP represents MPDG Rural Grant | Exempt |  | HF(M) | CONSTRUCTION | 3000000 | FY 2026: 3000000
HE-0001BA | Highway | Economic Development | New Route | Frederick Law Olmstead Way East to I-26 | Construct two lane road with sidewalk. Clearing for utilities. |  | Buncombe | 13 | French Broad River MPO |  | Exempt |  | HF | CONSTRUCTION | 1400000
HE-0002 | Highway | Economic Development | New Route; SR 1152 (Holly Springs - New Hill Road); SR 1153 (Old Holly Springs Apex Road) | Green Oaks Parkway near Irving Parkway intersection in Holly Springs; SR 1153 (Old Holly Springs Apex Road) intersection; Bennet Know Parkway intersection in Holly Springs. | Construct access road; Construct intersection improvements. | 1.55 | Wake | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES. OTHER FUNDS REPRESENT STATE CONTINGENCY FUNDS. | Division 5 |  | T | CONSTRUCTION | 6690000 | FY 2026: 4456000
HE-0002 | Highway | Economic Development | New Route; SR 1152 (Holly Springs - New Hill Road); SR 1153 (Old Holly Springs Apex Road) | Green Oaks Parkway near Irving Parkway intersection in Holly Springs; SR 1153 (Old Holly Springs Apex Road) intersection; Bennet Know Parkway intersection in Holly Springs. | Construct access road; Construct intersection improvements. | 1.55 | Wake | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES. OTHER FUNDS REPRESENT STATE CONTINGENCY FUNDS. | Division 5 |  | O | CONSTRUCTION | 3000000
HE-0003 | Highway | Economic Development | SR 1710 (Grace Drive / Watkins Drive); SR 1737 (Power Place) | US 158 to north of SR 1734 (Kennametal Drive); US 158 intersection | Widen to 4-lanes; Realign intersection. | 0.72 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR ROSEBURG FOREST PRODUCTS. | Division 4 |  | T | CONSTRUCTION | 2050000
HE-0004 | Highway | Economic Development | Various | Routes at the Randolph County Megasite near Liberty. | Construct road enhancements and wetland mitigation. | 3.18 | Randolph | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | RIGHT-OF-WAY | 11000000
HE-0004 | Highway | Economic Development | Various | Routes at the Randolph County Megasite near Liberty. | Construct road enhancements and wetland mitigation. | 3.18 | Randolph | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | UTILITIES | 1000000
HE-0004 | Highway | Economic Development | Various | Routes at the Randolph County Megasite near Liberty. | Construct road enhancements and wetland mitigation. | 3.18 | Randolph | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | MITIGATION | 4100000
HE-0004 | Highway | Economic Development | Various | Routes at the Randolph County Megasite near Liberty. | Construct road enhancements and wetland mitigation. | 3.18 | Randolph | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | CONSTRUCTION | 156350000
HE-0005 | Highway | Economic Development | Piedmont Triad International Airport manufacturing site | Piedmont Triad International Airport manufacturing site in Greensboro. | Construct road improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | Exempt |  | HF | RIGHT-OF-WAY | 1000000
HE-0005 | Highway | Economic Development | Piedmont Triad International Airport manufacturing site | Piedmont Triad International Airport manufacturing site in Greensboro. | Construct road improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | Exempt |  | HF | UTILITIES | 500000
HE-0005 | Highway | Economic Development | Piedmont Triad International Airport manufacturing site | Piedmont Triad International Airport manufacturing site in Greensboro. | Construct road improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | Exempt |  | HF | CONSTRUCTION | 30000000 | FY 2026: 1766000
HE-0006 | Highway | Economic Development | Triangle Innovation Point megasite | Locations in Division 8. | Construct roadway improvements near the triangle innovation point megasite. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund
HE-0006A | Highway | Economic Development | Various | Site Design 1A | Resurface and strengthen roadways surrounding Triangle Innovation Point megasite. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | CONSTRUCTION | 7000000
HE-0006B | Highway | Economic Development | Various | Site Design 1B and 1C | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | ENGINEERING | 3000000
HE-0006B | Highway | Economic Development | Various | Site Design 1B and 1C | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | RIGHT-OF-WAY | 10000000
HE-0006B | Highway | Economic Development | Various | Site Design 1B and 1C | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | UTILITIES | 5000000
HE-0006B | Highway | Economic Development | Various | Site Design 1B and 1C | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | CONSTRUCTION | 175000000
HE-0006C | Highway | Economic Development | Various | Site Design 2A and 2B | Construct roadway improvements including multiple industrial access roads and new interchanges along US 1. |  | Chatham | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | CONSTRUCTION | 50000000 | FY 2026: 25000000
HE-0007 | Highway | Economic Development | SR 1004 (Old Oxford Road); SR 1794 (Teknika Parkway); SR 2635 (International Drive) | North of Redmill Road; SR 1632 (Red Mill Road) intersection; End of road to SR 1004 (Old Oxford Road). | Construct access road and intersection improvements. |  | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5
HE-0007A | Highway | Economic Development | SR 1004 (Old Oxford Road) | First Avenue (Merck Driveway) | Construct right turn lane. | 0.1 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | ENGINEERING | 25000
HE-0007A | Highway | Economic Development | SR 1004 (Old Oxford Road) | First Avenue (Merck Driveway) | Construct right turn lane. | 0.1 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | CONSTRUCTION | 165000 | FY 2026: 165000
HE-0007B | Highway | Economic Development | SR 1794 (Teknika Parkway) | SR 1632 (Red Mill Road) | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T | ENGINEERING | 90000
HE-0007B | Highway | Economic Development | SR 1794 (Teknika Parkway) | SR 1632 (Red Mill Road) | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T | RIGHT-OF-WAY | 195000
HE-0007B | Highway | Economic Development | SR 1794 (Teknika Parkway) | SR 1632 (Red Mill Road) | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T | CONSTRUCTION | 815000 | FY 2026: 424000; FY 2027: 391000
HE-0007C | Highway | Economic Development | SR 2635 (International Drive) | SR 1004 (Old Oxford Road) to new location | Construct new lanes. | 0.49 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Division 5 |  | T | ENGINEERING | 600000
HE-0007D | Highway | Economic Development | SR 1631 (Snow Hill Road) | SR 1004 (Old Oxford Road) | Construct a left turn lane and signalize intersection. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | ENGINEERING | 200000
HE-0007D | Highway | Economic Development | SR 1631 (Snow Hill Road) | SR 1004 (Old Oxford Road) | Construct a left turn lane and signalize intersection. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HE-0007D | Highway | Economic Development | SR 1631 (Snow Hill Road) | SR 1004 (Old Oxford Road) | Construct a left turn lane and signalize intersection. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | UTILITIES | 75000 | FY 2026: 75000
HE-0007D | Highway | Economic Development | SR 1631 (Snow Hill Road) | SR 1004 (Old Oxford Road) | Construct a left turn lane and signalize intersection. | 0.5 | Durham | 5 | Triangle West TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | CONSTRUCTION | 700000 | FY 2027: 700000
HE-0008 | Highway | Economic Development | US 64 | Across from SR 2112 (Decker Road). | Extend left turn lane and construct right turn lane at proposed new access road and widen rail crossing 836515Y. | 0.09 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR. | Division 9 |  | T | ENGINEERING | 300000
HE-0008 | Highway | Economic Development | US 64 | Across from SR 2112 (Decker Road). | Extend left turn lane and construct right turn lane at proposed new access road and widen rail crossing 836515Y. | 0.09 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR. | Division 9 |  | T | CONSTRUCTION | 1500000
HE-0009 | Highway | Economic Development | NC 152 | Intersection with Access Road east of I-85 / US 601 in China Grove. | Widen pavement and construct roundabout. |  | Rowan | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | ENGINEERING | 600000
HE-0009 | Highway | Economic Development | NC 152 | Intersection with Access Road east of I-85 / US 601 in China Grove. | Widen pavement and construct roundabout. |  | Rowan | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | MITIGATION | 889000
HE-0009 | Highway | Economic Development | NC 152 | Intersection with Access Road east of I-85 / US 601 in China Grove. | Widen pavement and construct roundabout. |  | Rowan | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | CONSTRUCTION | 5411000 | FY 2026: 2879000
HE-0009A | Highway | Economic Development | NC 152 | NC 152, intersection with proposed access road east of I-85 / US 601 in China Grove | Construct intersection improvements. Widen pavement and construct turn lanes for Phase I of roadway improvements. | 0.4 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. CONSTRUCTION BY STATE FORCES. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | CONSTRUCTION | 1000000
HE-0010 | Highway | Economic Development | US 1; SR 1127 (New Hill - Holleman Road); SR 1149 (Friendship Road) | SR 1127 (New Hill - Holleman Road) interchange; SR 1149 (Friendship Road) intersection; SR 1152 (Old Holly Springs-New Hill Road) in Holly Springs. | Construct intersection improvements. |  | Wake | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | Division 5 |  | T | ENGINEERING | 1125000
HE-0010 | Highway | Economic Development | US 1; SR 1127 (New Hill - Holleman Road); SR 1149 (Friendship Road) | SR 1127 (New Hill - Holleman Road) interchange; SR 1149 (Friendship Road) intersection; SR 1152 (Old Holly Springs-New Hill Road) in Holly Springs. | Construct intersection improvements. |  | Wake | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | Division 5 |  | T | RIGHT-OF-WAY | 200000 | FY 2026: 200000
HE-0010 | Highway | Economic Development | US 1; SR 1127 (New Hill - Holleman Road); SR 1149 (Friendship Road) | SR 1127 (New Hill - Holleman Road) interchange; SR 1149 (Friendship Road) intersection; SR 1152 (Old Holly Springs-New Hill Road) in Holly Springs. | Construct intersection improvements. |  | Wake | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | Division 5 |  | T | CONSTRUCTION | 8675000 | FY 2027: 2144000; FY 2028: 5009000; FY 2029: 1522000
HE-0011 | Highway | Economic Development | US 64 | West of Siler City | Construct roadway improvements and industrial access road. |  | Chatham | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | ENGINEERING | 1000000
HE-0011 | Highway | Economic Development | US 64 | West of Siler City | Construct roadway improvements and industrial access road. |  | Chatham | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | RIGHT-OF-WAY | 250000
HE-0011 | Highway | Economic Development | US 64 | West of Siler City | Construct roadway improvements and industrial access road. |  | Chatham | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | UTILITIES | 250000
HE-0011 | Highway | Economic Development | US 64 | West of Siler City | Construct roadway improvements and industrial access road. |  | Chatham | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | CONSTRUCTION | 8500000
HE-0012 | Highway | Economic Development | New Route | New route in Fayetteville. | Construct new access road and improvements at SR 1838 (Dunn Road) intersection. | 0.2 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | Division 6 |  | T | RIGHT-OF-WAY | 20000
HE-0012 | Highway | Economic Development | New Route | New route in Fayetteville. | Construct new access road and improvements at SR 1838 (Dunn Road) intersection. | 0.2 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | Division 6 |  | T | UTILITIES | 50000
HE-0012 | Highway | Economic Development | New Route | New route in Fayetteville. | Construct new access road and improvements at SR 1838 (Dunn Road) intersection. | 0.2 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | Division 6 |  | T | CONSTRUCTION | 1100000
HE-0014 | Highway | Economic Development | SR 1104 (Old Linwood Road) | North of SR 1254 (Brown Street). | Construct new access road and improvements to SR 1104 (Old Linwood Road). |  | Davidson | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | Division 9 |  | T | ENGINEERING | 400000
HE-0014 | Highway | Economic Development | SR 1104 (Old Linwood Road) | North of SR 1254 (Brown Street). | Construct new access road and improvements to SR 1104 (Old Linwood Road). |  | Davidson | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | Division 9 |  | T | UTILITIES | 10000
HE-0014 | Highway | Economic Development | SR 1104 (Old Linwood Road) | North of SR 1254 (Brown Street). | Construct new access road and improvements to SR 1104 (Old Linwood Road). |  | Davidson | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | Division 9 |  | T | CONSTRUCTION | 8590000 | FY 2026: 3325000
HE-0015 | Highway | Economic Development | NC 49 | Prince Circle to West of General Services Drive Southwest. | Upgrade existing full access crossover to reduced conflict intersection with leftovers and signalized U-turn leftovers. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841. | Division 10 |  | T | CONSTRUCTION | 2000000
HE-0015 | Highway | Economic Development | NC 49 | Prince Circle to West of General Services Drive Southwest. | Upgrade existing full access crossover to reduced conflict intersection with leftovers and signalized U-turn leftovers. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841. | Division 10 |  | O | CONSTRUCTION | 2091000
HE-0016 | Highway | Economic Development | New Route | 0.5 miles east of Brunswick County line to 1.5 miles east of Brunswick County line on US 74. | Construct road on new location and intersecting roads with US 74 on east and west termini. | 1 | Brunswick | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. O FUNDS REPRESENT BRUNSWICK COUNTY PUBLIC UTILITY FUNDING. | Division 3 |  | T | ENGINEERING | 725000
HE-0016 | Highway | Economic Development | New Route | 0.5 miles east of Brunswick County line to 1.5 miles east of Brunswick County line on US 74. | Construct road on new location and intersecting roads with US 74 on east and west termini. | 1 | Brunswick | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. O FUNDS REPRESENT BRUNSWICK COUNTY PUBLIC UTILITY FUNDING. | Division 3 |  | T | UTILITIES | 40000
HE-0016 | Highway | Economic Development | New Route | 0.5 miles east of Brunswick County line to 1.5 miles east of Brunswick County line on US 74. | Construct road on new location and intersecting roads with US 74 on east and west termini. | 1 | Brunswick | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. O FUNDS REPRESENT BRUNSWICK COUNTY PUBLIC UTILITY FUNDING. | Division 3 |  | T | CONSTRUCTION | 9235000 | FY 2026: 2153000; FY 2027: 4399000; FY 2028: 2683000
HE-0016 | Highway | Economic Development | New Route | 0.5 miles east of Brunswick County line to 1.5 miles east of Brunswick County line on US 74. | Construct road on new location and intersecting roads with US 74 on east and west termini. | 1 | Brunswick | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. O FUNDS REPRESENT BRUNSWICK COUNTY PUBLIC UTILITY FUNDING. | Division 3 |  | O | CONSTRUCTION | 53000
HE-0017 | Highway | Economic Development | SR 1711 (Bethune Drive) | East of US 401 intersection in Fayetteville. | Install signal at US 401 (Ramsey Street) intersection and extend SR 1711 (Bethune Drive). |  | Cumberland | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | ENGINEERING | 800000
HE-0017 | Highway | Economic Development | SR 1711 (Bethune Drive) | East of US 401 intersection in Fayetteville. | Install signal at US 401 (Ramsey Street) intersection and extend SR 1711 (Bethune Drive). |  | Cumberland | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | RIGHT-OF-WAY | 300000 | FY 2026: 300000
HE-0017 | Highway | Economic Development | SR 1711 (Bethune Drive) | East of US 401 intersection in Fayetteville. | Install signal at US 401 (Ramsey Street) intersection and extend SR 1711 (Bethune Drive). |  | Cumberland | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | UTILITIES | 700000 | FY 2026: 700000
HE-0017 | Highway | Economic Development | SR 1711 (Bethune Drive) | East of US 401 intersection in Fayetteville. | Install signal at US 401 (Ramsey Street) intersection and extend SR 1711 (Bethune Drive). |  | Cumberland | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | CONSTRUCTION | 8200000 | FY 2027: 4100000; FY 2028: 4100000
HE-0018 | Highway | Economic Development | SR 1302 (North 23rd Street) | US 74 (Martin Luther King Jr. Parkway) to Airport Boulevard. | Widen Northbound Lane. | 0.6 | New Hanover | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FRONTIER SCIENTIFIC SOLUTIONS. O FUNDS REPRESENT WILMINGTON INTERNATIONAL AIRPORT (ILM) FUNDING. | Division 3 |  | O | ENGINEERING | 560000
HE-0018 | Highway | Economic Development | SR 1302 (North 23rd Street) | US 74 (Martin Luther King Jr. Parkway) to Airport Boulevard. | Widen Northbound Lane. | 0.6 | New Hanover | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FRONTIER SCIENTIFIC SOLUTIONS. O FUNDS REPRESENT WILMINGTON INTERNATIONAL AIRPORT (ILM) FUNDING. | Division 3 |  | O | RIGHT-OF-WAY | 400000
HE-0018 | Highway | Economic Development | SR 1302 (North 23rd Street) | US 74 (Martin Luther King Jr. Parkway) to Airport Boulevard. | Widen Northbound Lane. | 0.6 | New Hanover | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FRONTIER SCIENTIFIC SOLUTIONS. O FUNDS REPRESENT WILMINGTON INTERNATIONAL AIRPORT (ILM) FUNDING. | Division 3 |  | T | UTILITIES | 460000
HE-0018 | Highway | Economic Development | SR 1302 (North 23rd Street) | US 74 (Martin Luther King Jr. Parkway) to Airport Boulevard. | Widen Northbound Lane. | 0.6 | New Hanover | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FRONTIER SCIENTIFIC SOLUTIONS. O FUNDS REPRESENT WILMINGTON INTERNATIONAL AIRPORT (ILM) FUNDING. | Division 3 |  | O | UTILITIES | 40000
HE-0018 | Highway | Economic Development | SR 1302 (North 23rd Street) | US 74 (Martin Luther King Jr. Parkway) to Airport Boulevard. | Widen Northbound Lane. | 0.6 | New Hanover | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FRONTIER SCIENTIFIC SOLUTIONS. O FUNDS REPRESENT WILMINGTON INTERNATIONAL AIRPORT (ILM) FUNDING. | Division 3 |  | T | CONSTRUCTION | 1900000 | FY 2027: 1900000
HE-0019 | Highway | Economic Development | NC 61 | Guilford County | NC 61 road widening, turn lanes and installation of two signals. NCDOT will add a right turn lane on the I-40 / I-85 north-bound exit ramp plus signal modifications and install left turn lane on I-40 / I-85 south-bound exit ramp and add signal. |  | Guilford | 7 | Burlington-Graham MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AHOLD DELHAIZE USA. | Division 7 |  | T | CONSTRUCTION | 500000 | FY 2026: 500000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Mile marker 5.3 to mile marker 7.5. | Install guardrail. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | ENGINEERING | 4000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Mile marker 5.3 to mile marker 7.5. | Install guardrail. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | ENGINEERING | 1000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Mile marker 5.3 to mile marker 7.5. | Install guardrail. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | CONSTRUCTION | 188000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Mile marker 5.3 to mile marker 7.5. | Install guardrail. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | CONSTRUCTION | 47000
HF-0002 | Highway | Federal Lands Access Program | SR 1408 (Fish Hatchery Road) | West of US 276 to end of pavement. | Install guardrail. | 1.65 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | ENGINEERING | 8000
HF-0002 | Highway | Federal Lands Access Program | SR 1408 (Fish Hatchery Road) | West of US 276 to end of pavement. | Install guardrail. | 1.65 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 2000
HF-0002 | Highway | Federal Lands Access Program | SR 1408 (Fish Hatchery Road) | West of US 276 to end of pavement. | Install guardrail. | 1.65 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | CONSTRUCTION | 184000
HF-0002 | Highway | Federal Lands Access Program | SR 1408 (Fish Hatchery Road) | West of US 276 to end of pavement. | Install guardrail. | 1.65 | Transylvania | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 46000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Various locations along Wilson Creek. | Widen pavement. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | ENGINEERING | 140000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Various locations along Wilson Creek. | Widen pavement. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 35000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Various locations along Wilson Creek. | Widen pavement. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | CONSTRUCTION | 1260000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (Brown Mountain Beach Road) | Various locations along Wilson Creek. | Widen pavement. | 2.19 | Caldwell | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 315000
HF-0004 | Highway | Federal Lands Access Program | US 276 | US 64 to Avery Creek Trailhead. | Install guardrail and construct sidewalk. | 0.5 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | ENGINEERING | 420000 | FY 2026: 396000
HF-0004 | Highway | Federal Lands Access Program | US 276 | US 64 to Avery Creek Trailhead. | Install guardrail and construct sidewalk. | 0.5 | Transylvania | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 105000 | FY 2026: 99000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | ENGINEERING | 516000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | ENGINEERING | 129000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF | ENGINEERING | 100000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | RIGHT-OF-WAY | 248000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 62000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | UTILITIES | 229000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | UTILITIES | 57000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | CONSTRUCTION | 207000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF | CONSTRUCTION | 3907000
HF-0005 | Highway | Bridges | SR 1140 (Myers Chapel Road) | Bridge 210063 over Blair Creek and bridge 210088 over Hyatt Mill Creek. | Replace bridges. | 0.5 | Clay | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | CONSTRUCTION | 52000
HF-0006 | Highway | Federal Lands Access Program | US 64 | Dry Falls Recreation Area. | Improve parking area, construct pedestrian bridge, and construct observation platform. | 0.2 | Macon | 14 | Southwestern RPO | FLAP PROJECT NC 64. AWARDED $1.0M. | Exempt |  | FLAP | ENGINEERING | 500000
HF-0007 | Highway | Federal Lands Access Program | SR 1286 / SR 1383 (Tsali Road) | NC 28 to End of Maintenance. | Resurface and repair corridor. | 1.85 | Graham, Swain | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | Exempt |  | FLAP | ENGINEERING | 150000
HF-0007 | Highway | Federal Lands Access Program | SR 1286 / SR 1383 (Tsali Road) | NC 28 to End of Maintenance. | Resurface and repair corridor. | 1.85 | Graham, Swain | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | Exempt |  | FLAP | CONSTRUCTION | 1050000
HF-0007 | Highway | Federal Lands Access Program | SR 1286 / SR 1383 (Tsali Road) | NC 28 to End of Maintenance. | Resurface and repair corridor. | 1.85 | Graham, Swain | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | Exempt |  | HF | CONSTRUCTION | 2740000
HF-0008 | Highway | Federal Lands Access Program | NC 615 (Marsh Causeway) | HQ / VC Entrance Road to west of Knotts Island Road. | Improve corridor at various locations. | 3.89 | Currituck | 1 | Albemarle RPO | FLAP PROJECT NC 71. AWARDED $700K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | FLAP | ENGINEERING | 50000
HF-0008 | Highway | Federal Lands Access Program | NC 615 (Marsh Causeway) | HQ / VC Entrance Road to west of Knotts Island Road. | Improve corridor at various locations. | 3.89 | Currituck | 1 | Albemarle RPO | FLAP PROJECT NC 71. AWARDED $700K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | FLAP | CONSTRUCTION | 650000
HI-0001 | Highway | Interstate Maintenance | I-85 / US 15 | North of SR 1637 (Redwood Road) in Durham County to south of US 15 / SR 1100 (Gate One Road) in Granville County. | Rehabilitate pavement. | 2.03 | Granville, Durham | 5 | Triangle West TPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 40000
HI-0001 | Highway | Interstate Maintenance | I-85 / US 15 | North of SR 1637 (Redwood Road) in Durham County to south of US 15 / SR 1100 (Gate One Road) in Granville County. | Rehabilitate pavement. | 2.03 | Granville, Durham | 5 | Triangle West TPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) |  | 10000
HI-0001 | Highway | Interstate Maintenance | I-85 / US 15 | North of SR 1637 (Redwood Road) in Durham County to south of US 15 / SR 1100 (Gate One Road) in Granville County. | Rehabilitate pavement. | 2.03 | Granville, Durham | 5 | Triangle West TPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4532000
HI-0001 | Highway | Interstate Maintenance | I-85 / US 15 | North of SR 1637 (Redwood Road) in Durham County to south of US 15 / SR 1100 (Gate One Road) in Granville County. | Rehabilitate pavement. | 2.03 | Granville, Durham | 5 | Triangle West TPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 1133000
HI-0002 | Highway | Interstate Maintenance | I-85 | NC 109 in Thomasville to SR 1009 (South Main Street) in Archdale. | Pavement rehabilitation. | 7.61 | Randolph, Davidson | 8, 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12538000
HI-0002 | Highway | Interstate Maintenance | I-85 | NC 109 in Thomasville to SR 1009 (South Main Street) in Archdale. | Pavement rehabilitation. | 7.61 | Randolph, Davidson | 8, 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 3134000
HI-0003 | Highway | Interstate Maintenance | I-73 / US 220 | SR 1009 (Old US Highway 311) to Guilford County line. | Rehabilitate pavement. | 7.69 | Randolph | 8 | Piedmont Triad RPO, High Point Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6497000 | FY 2029: 1689000; FY 2030: 3054000; FY 2031: 1754000
HI-0003 | Highway | Interstate Maintenance | I-73 / US 220 | SR 1009 (Old US Highway 311) to Guilford County line. | Rehabilitate pavement. | 7.69 | Randolph | 8 | Piedmont Triad RPO, High Point Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1624000 | FY 2029: 422000; FY 2030: 763000; FY 2031: 439000
HI-0004 | Highway | Interstate Maintenance | I-74 | SR 1928 (Cedar Square Road) to I-73 / US 220. | Rehabilitate pavement. | 7.58 | Randolph | 8 | High Point Urban Area MPO, Piedmont Triad RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6512000 | FY 2031: 2084000; FY 2032: 3061000; FY 2033: 1367000
HI-0004 | Highway | Interstate Maintenance | I-74 | SR 1928 (Cedar Square Road) to I-73 / US 220. | Rehabilitate pavement. | 7.58 | Randolph | 8 | High Point Urban Area MPO, Piedmont Triad RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1628000 | FY 2031: 521000; FY 2032: 765000; FY 2033: 342000
HI-0005 | Highway | Interstate Maintenance | I-285 / US 52 (Future I-74) / NC 8 | SR 4205 (S. Main Street) in Forsyth County to SR 3010 (Old US 52) in Davidson County. | Rehabilitate pavement. | 18.55 | Forsyth, Davidson | 9 | Winston-Salem Area TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 11360000 | FY 2026: 106000; FY 2027: 4287000; FY 2028: 4133000; FY 2029: 2834000
HI-0005 | Highway | Interstate Maintenance | I-285 / US 52 (Future I-74) / NC 8 | SR 4205 (S. Main Street) in Forsyth County to SR 3010 (Old US 52) in Davidson County. | Rehabilitate pavement. | 18.55 | Forsyth, Davidson | 9 | Winston-Salem Area TPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 2840000 | FY 2026: 27000; FY 2027: 1072000; FY 2028: 1033000; FY 2029: 708000
HI-0005A | Highway | Interstate Maintenance | I-85 | I-285 / US 52 / NC 8 | Preserve Bridges 280147, 280152, 280513, 280515, 280516, 280136, 330027, 330028, 330053, and 330054. |  | Forsyth, Davidson | 9 | Winston-Salem Area TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13000000 | FY 2026: 122000; FY 2027: 4906000; FY 2028: 4729000; FY 2029: 3243000
HI-0006 | Highway | Interstate Maintenance | US 264 (Future I-587) | I-795 to Toisnot Swamp. | Rehabilitate pavement. | 7.05 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10965000
HI-0006 | Highway | Interstate Maintenance | US 264 (Future I-587) | I-795 to Toisnot Swamp. | Rehabilitate pavement. | 7.05 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2741000
HI-0007 | Highway | Interstate Maintenance | US 264 (Future I-587) | Toisnot Swamp to the Greene County Line. | Rehabilitate pavement. | 8.23 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8812000
HI-0007 | Highway | Interstate Maintenance | US 264 (Future I-587) | Toisnot Swamp to the Greene County Line. | Rehabilitate pavement. | 8.23 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2203000
HI-0008 | Highway | Interstate Maintenance | I-95 | Mile marker 97 to mile marker 101. | Rehabilitate pavement. | 4.01 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5783000
HI-0008 | Highway | Interstate Maintenance | I-95 | Mile marker 97 to mile marker 101. | Rehabilitate pavement. | 4.01 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1446000
HI-0009 | Highway | Interstate Maintenance | I-40 | Mile marker 81 / SR 1001 (Sugar Hill Road) to mile marker 86 / NC 226. | Rehabilitate pavement. | 4.97 | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 14900000 | FY 2028: 149000; FY 2029: 8195000; FY 2030: 5215000; FY 2031: 1341000
HI-0010 | Highway | Interstate Maintenance | I-40 | Mile marker 67 to mile marker 73 (Old Fort Mountain). | Construct safety and drainage improvements, rehabilitate pavement, and reconstruct median barrier. | 5.95 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHP | CONSTRUCTION | 3120000 | FY 2026: 3120000
HI-0010 | Highway | Interstate Maintenance | I-40 | Mile marker 67 to mile marker 73 (Old Fort Mountain). | Construct safety and drainage improvements, rehabilitate pavement, and reconstruct median barrier. | 5.95 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 14080000
HI-0010 | Highway | Interstate Maintenance | I-40 | Mile marker 67 to mile marker 73 (Old Fort Mountain). | Construct safety and drainage improvements, rehabilitate pavement, and reconstruct median barrier. | 5.95 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 4300000 | FY 2026: 780000
HI-0011 | Highway | Interstate Maintenance | I-40 | Johnston County line to Duplin County line. | Rehabilitate pavement. | 20.18 | Sampson | 3 | Mid-Carolina RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7450000 | FY 2028: 1788000; FY 2029: 2682000; FY 2030: 1937000; FY 2031: 1043000
HI-0011 | Highway | Interstate Maintenance | I-40 | Johnston County line to Duplin County line. | Rehabilitate pavement. | 20.18 | Sampson | 3 | Mid-Carolina RPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 14950000 | FY 2028: 3588000; FY 2029: 5382000; FY 2030: 3887000; FY 2031: 2093000
HI-0012 | Highway | Interstate Maintenance | I-40 | Sampson County line to Pender County line. | Rehabilitate pavement. | 28 | Duplin | 3 | Eastern Carolina RPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 9088000 | FY 2030: 1727000; FY 2031: 2817000; FY 2032: 2363000; FY 2033: 1636000; FY 2034: 545000
HI-0012 | Highway | Interstate Maintenance | I-40 | Sampson County line to Pender County line. | Rehabilitate pavement. | 28 | Duplin | 3 | Eastern Carolina RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 22012000 | FY 2030: 4182000; FY 2031: 6824000; FY 2032: 5723000; FY 2033: 3962000; FY 2034: 1321000
HI-0013 | Highway | Interstate Maintenance | US 264 (Future I-587) | The US 64 / US 264 split to the Wilson County line. | Rehabilitate pavement. | 14.27 | Nash, Wake, Johnston | 4, 5 | Upper Coastal Plain RPO, Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13200000 | FY 2027: 2904000; FY 2028: 5412000; FY 2029: 3564000; FY 2030: 1320000
HI-0013 | Highway | Interstate Maintenance | US 264 (Future I-587) | The US 64 / US 264 split to the Wilson County line. | Rehabilitate pavement. | 14.27 | Nash, Wake, Johnston | 4, 5 | Upper Coastal Plain RPO, Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 3300000 | FY 2027: 726000; FY 2028: 1353000; FY 2029: 891000; FY 2030: 330000
HI-0014 | Highway | Interstate Maintenance | US 264 (Future I-587) | Wilson County line to I-95. | Rehabilitate pavement. | 4.55 | Wilson | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8480000 | FY 2026: 1018000; FY 2027: 3307000; FY 2028: 4155000
HI-0014 | Highway | Interstate Maintenance | US 264 (Future I-587) | Wilson County line to I-95. | Rehabilitate pavement. | 4.55 | Wilson | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 2120000 | FY 2026: 254000; FY 2027: 827000; FY 2028: 1039000
HI-0015 | Highway | Interstate Maintenance | US 74 (Future I-74) | East of NC 214 to west of SR 1824 (Water Tank Road). | Rehabilitate pavement. | 7 | Columbus | 6 | Cape Fear RPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 10300000 | FY 2026: 1248000
HI-0016 | Highway | Interstate Maintenance | US 74 (Future I-74) | East of NC 41 to east of Columbus County line. | Rehabilitate pavement. | 10.93 | Robeson | 6 | Lumber River RPO | TO BE LET WITH HI-0017. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13100000 | FY 2026: 781000
HI-0017 | Highway | Interstate Maintenance | US 74 (Future I-74) | Scotland County line to I-74 / US 74 Business. | Rehabilitate pavement. | 3.44 | Robeson | 6 | Lumber River RPO | TO BE LET WITH HI-0016. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6880000
HI-0017 | Highway | Interstate Maintenance | US 74 (Future I-74) | Scotland County line to I-74 / US 74 Business. | Rehabilitate pavement. | 3.44 | Robeson | 6 | Lumber River RPO | TO BE LET WITH HI-0016. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1720000
HI-0018 | Highway | Interstate Maintenance | US 74 (Future I-74) | West of US 701 Business to west of NC 214. | Rehabilitate pavement. | 17.59 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHFP | CONSTRUCTION | 13501000 | FY 2026: 5115000; FY 2027: 3746000; FY 2028: 1250000
HI-0018 | Highway | Interstate Maintenance | US 74 (Future I-74) | West of US 701 Business to west of NC 214. | Rehabilitate pavement. | 17.59 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13129000 | FY 2026: 5351000; FY 2027: 3384000; FY 2028: 1524000
HI-0019 | Highway | Interstate Maintenance | US 74 (Future I-74) | West of SR 1585 (Union Valley Road) to west of US 701 Business. | Rehabilitate pavement. | 6.54 | Columbus | 6 | Cape Fear RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4320000 | FY 2031: 1512000; FY 2032: 2376000; FY 2033: 432000
HI-0019 | Highway | Interstate Maintenance | US 74 (Future I-74) | West of SR 1585 (Union Valley Road) to west of US 701 Business. | Rehabilitate pavement. | 6.54 | Columbus | 6 | Cape Fear RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1080000 | FY 2031: 378000; FY 2032: 594000; FY 2033: 108000
HI-0020 | Highway | Interstate Maintenance | US 74 (Future I-74) | Robeson County line to west of SR 1585 (Union Valley Road). | Rehabilitate pavement. | 13.86 | Columbus | 6 | Cape Fear RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12000000 | FY 2031: 3000000; FY 2032: 4920000; FY 2033: 3360000; FY 2034: 720000
HI-0020 | Highway | Interstate Maintenance | US 74 (Future I-74) | Robeson County line to west of SR 1585 (Union Valley Road). | Rehabilitate pavement. | 13.86 | Columbus | 6 | Cape Fear RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 3000000 | FY 2031: 750000; FY 2032: 1230000; FY 2033: 840000; FY 2034: 180000
HI-0021 | Highway | Interstate Maintenance | I-95 | Robeson County line to NC 53 / NC 210 | Rehabilitate pavement. | 10.28 | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 6876000 | FY 2029: 2269000; FY 2030: 3438000; FY 2031: 1169000
HI-0021 | Highway | Interstate Maintenance | I-95 | Robeson County line to NC 53 / NC 210 | Rehabilitate pavement. | 10.28 | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1124000 | FY 2029: 371000; FY 2030: 562000; FY 2031: 191000
HI-0022 | Highway | Interstate Maintenance | I-95 | NC 53 to I-95 Business / US 301. | Rehabilitate pavement. | 8.92 | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2049000 | FY 2029: 676000; FY 2030: 1107000; FY 2031: 266000
HI-0022 | Highway | Interstate Maintenance | I-95 | NC 53 to I-95 Business / US 301. | Rehabilitate pavement. | 8.92 | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 3751000 | FY 2029: 1238000; FY 2030: 2025000; FY 2031: 488000
HI-0023 | Highway | Interstate Maintenance | I-885 | I-40 to 0.4 miles north of TW Alexander Drive. | Rehabilitate pavement. | 2.28 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3491000
HI-0023 | Highway | Interstate Maintenance | I-885 | I-40 to 0.4 miles north of TW Alexander Drive. | Rehabilitate pavement. | 2.28 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 872000
HI-0024 | Highway | Interstate Maintenance | US 13 / US 17 (Future I-87) | SR 1154 (Buds Lane) to US 13 Business Overpass | Rehabilitate pavement. | 2.18 | Bertie | 1 | Peanut Belt RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1760000 | FY 2029: 18000; FY 2030: 1355000; FY 2031: 387000
HI-0024 | Highway | Interstate Maintenance | US 13 / US 17 (Future I-87) | SR 1154 (Buds Lane) to US 13 Business Overpass | Rehabilitate pavement. | 2.18 | Bertie | 1 | Peanut Belt RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 440000 | FY 2029: 4000; FY 2030: 339000; FY 2031: 97000
HI-0025 | Highway | Interstate Maintenance | US 17 (Future I-87) | US 13 Business Overpass to pavement joint near US 17 | Rehabilitate open grade friction course pavement. | 6.48 | Bertie | 1 | Peanut Belt RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1600000 | FY 2029: 16000; FY 2030: 1232000; FY 2031: 352000
HI-0025 | Highway | Interstate Maintenance | US 17 (Future I-87) | US 13 Business Overpass to pavement joint near US 17 | Rehabilitate open grade friction course pavement. | 6.48 | Bertie | 1 | Peanut Belt RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 400000 | FY 2029: 4000; FY 2030: 308000; FY 2031: 88000
HI-0026 | Highway | Interstate Maintenance | US 17 (Future I-87) | Bridges 710014 and 710080 over Perquimans River to SR 1304 (Cartwright Swamp Road) | Rehabilitate pavement. | 4.38 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3519000 | FY 2029: 35000; FY 2030: 2182000; FY 2031: 1302000
HI-0026 | Highway | Interstate Maintenance | US 17 (Future I-87) | Bridges 710014 and 710080 over Perquimans River to SR 1304 (Cartwright Swamp Road) | Rehabilitate pavement. | 4.38 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 881000 | FY 2029: 9000; FY 2030: 546000; FY 2031: 326000
HI-0027 | Highway | Interstate Maintenance | US 17 (Future I-87) | SR 1304 (Cartwright Swamp Road) to Pasquotank County line | Rehabilitate pavement. | 4.17 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3360000 | FY 2030: 34000; FY 2031: 2184000; FY 2032: 1142000
HI-0027 | Highway | Interstate Maintenance | US 17 (Future I-87) | SR 1304 (Cartwright Swamp Road) to Pasquotank County line | Rehabilitate pavement. | 4.17 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 840000 | FY 2030: 8000; FY 2031: 546000; FY 2032: 286000
HI-0028 | Highway | Interstate Maintenance | US 17 (Future I-87) | US 17 Business to bridges 710014 and 710080 over Perquimans River | Rehabilitate pavement. | 1.74 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1600000 | FY 2030: 16000; FY 2031: 1232000; FY 2032: 352000
HI-0028 | Highway | Interstate Maintenance | US 17 (Future I-87) | US 17 Business to bridges 710014 and 710080 over Perquimans River | Rehabilitate pavement. | 1.74 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 400000 | FY 2030: 4000; FY 2031: 308000; FY 2032: 88000
HI-9999 | Highway | Interstate Maintenance | Various |  | Interstate maintenance program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 797394000 | 0 | 0 | 0 | 0 | 0 | 47526000 | 61566000 | 89886000 | 118416000 | 120000000 | 360000000
HI-9999 | Highway | Interstate Maintenance | Various |  | Interstate maintenance program - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 199348000 | 0 | 0 | 0 | 0 | 0 | 11881000 | 15391000 | 22472000 | 29604000 | 30000000 | 90000000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGANY | ENGINEERING | 1368000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L(M) | ENGINEERING | 342000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGANY | RIGHT-OF-WAY | 3632000 | FY 2026: 3632000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGDA | RIGHT-OF-WAY | 784000 | FY 2026: 784000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L(M) | RIGHT-OF-WAY | 1104000 | FY 2026: 1104000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGDA | CONSTRUCTION | 6280000 | FY 2029: 6280000
HL-0001 | Highway | Locally Selected | SR 1394 (Poplar Tent Road) | SR 1449 (Harris Road) intersection in Concord; SR 2880 (Moss Drive) to Fullerton Place Drive. | Construct intersection improvements; Widen to four lanes. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L(M) | CONSTRUCTION | 1570000 | FY 2029: 1570000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4th Street Drive Southwest) intersection in Hickory. | Construct intersection improvements. | 0.5 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | BGDA | RIGHT-OF-WAY | 80000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4th Street Drive Southwest) intersection in Hickory. | Construct intersection improvements. | 0.5 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | L(M) | RIGHT-OF-WAY | 20000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4th Street Drive Southwest) intersection in Hickory. | Construct intersection improvements. | 0.5 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | BGANY | CONSTRUCTION | 320000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4th Street Drive Southwest) intersection in Hickory. | Construct intersection improvements. | 0.5 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | BGDA | CONSTRUCTION | 400000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4th Street Drive Southwest) intersection in Hickory. | Construct intersection improvements. | 0.5 | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | L(M) | CONSTRUCTION | 180000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGDA | ENGINEERING | 551000 | FY 2026: 407000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | HF(M) | ENGINEERING | 138000 | FY 2026: 102000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGANY | CONSTRUCTION | 2899000 | FY 2026: 1860000; FY 2027: 1039000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGDA | CONSTRUCTION | 2706000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | L | CONSTRUCTION | 39000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | HF | CONSTRUCTION | 1065000
HL-0003 | Highway | Locally Selected | US 19 / US 23 Business (Haywood Road) | US 19 / US 23 / US 74 (Patton Avenue) to Ridgelawn Road. | Upgrade roadway including resurfacing and pedestrian improvements. | 1.88 | Buncombe | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | HF(M) | CONSTRUCTION | 1401000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGDA | ENGINEERING | 384000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L(M) | ENGINEERING | 96000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | RIGHT-OF-WAY | 80000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGDA | RIGHT-OF-WAY | 496000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L(M) | RIGHT-OF-WAY | 144000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | CONSTRUCTION | 3840000
HL-0004 | Highway | Locally Selected | 17th Street Northwest | 9th Avenue Northwest to SR 1371 (Clement Boulevard Northwest). | Extend roadway. | 0.2 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L(M) | CONSTRUCTION | 960000
HL-0005 | Highway | Locally Selected | Various | Locations in Salisbury. | Upgrade signal System. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 343000
HL-0005 | Highway | Locally Selected | Various | Locations in Salisbury. | Upgrade signal System. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 86000
HL-0006 | Highway | Locally Selected | US 401 | SR 1393 (Hilltop-Needmore Road) / SR 2751 (Hilltop Road) / SR 2752 (Air Park Road) intersection and SR 1375 (Lake Wheeler Road) intersection in Fuquay-Varina. | Construct reduced conflict intersections and realign SR 2751 (Hilltop Road) to intersect opposite SR 1375 (Lake Wheeler Road). | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | NHPBA | RIGHT-OF-WAY | 2601000 | FY 2026: 149000; FY 2027: 149000
HL-0006 | Highway | Locally Selected | US 401 | SR 1393 (Hilltop-Needmore Road) / SR 2751 (Hilltop Road) / SR 2752 (Air Park Road) intersection and SR 1375 (Lake Wheeler Road) intersection in Fuquay-Varina. | Construct reduced conflict intersections and realign SR 2751 (Hilltop Road) to intersect opposite SR 1375 (Lake Wheeler Road). | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | NHPBA | UTILITIES | 509000
HL-0006 | Highway | Locally Selected | US 401 | SR 1393 (Hilltop-Needmore Road) / SR 2751 (Hilltop Road) / SR 2752 (Air Park Road) intersection and SR 1375 (Lake Wheeler Road) intersection in Fuquay-Varina. | Construct reduced conflict intersections and realign SR 2751 (Hilltop Road) to intersect opposite SR 1375 (Lake Wheeler Road). | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | NHPBA | CONSTRUCTION | 30500000 | FY 2026: 3690000; FY 2027: 11416000; FY 2028: 8693000; FY 2029: 6701000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (Technology Drive) / SR 6107 (East Williams Street) intersection in Apex. | Upgrade intersection to interchange or alternative intersection. | 1 | Wake | 5 | Capital Area MPO |  | Exempt |  | BA | ENGINEERING | 2615000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (Technology Drive) / SR 6107 (East Williams Street) intersection in Apex. | Upgrade intersection to interchange or alternative intersection. | 1 | Wake | 5 | Capital Area MPO |  | Exempt |  | NHPBA | RIGHT-OF-WAY | 9100000 | FY 2026: 910000; FY 2027: 910000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (Technology Drive) / SR 6107 (East Williams Street) intersection in Apex. | Upgrade intersection to interchange or alternative intersection. | 1 | Wake | 5 | Capital Area MPO |  | Exempt |  | NHPBA | UTILITIES | 2900000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (Technology Drive) / SR 6107 (East Williams Street) intersection in Apex. | Upgrade intersection to interchange or alternative intersection. | 1 | Wake | 5 | Capital Area MPO |  | Exempt |  | NHPBA | CONSTRUCTION | 27099000 | FY 2026: 6051000; FY 2027: 11208000; FY 2028: 7643000; FY 2029: 2197000
HL-0008 | Highway | Locally Selected | Various | Locations in Capital Area MPO (CAMPO). | Construct intersection improvements. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY | Exempt
HL-0008C | Highway | Locally Selected | NC 50 (Benson Road) | SR 2812 (Timber Drive) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BA | RIGHT-OF-WAY | 100000
HL-0008C | Highway | Locally Selected | NC 50 (Benson Road) | SR 2812 (Timber Drive) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BA | CONSTRUCTION | 525000 | FY 2026: 520000
HL-0008D | Highway | Locally Selected | SR 1152 (Holly Springs Road) | SR 1301 (Sunset Lake Road) intersection in Holly Springs. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 1330000
HL-0008D | Highway | Locally Selected | SR 1152 (Holly Springs Road) | SR 1301 (Sunset Lake Road) intersection in Holly Springs. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 170000
HL-0008D | Highway | Locally Selected | SR 1152 (Holly Springs Road) | SR 1301 (Sunset Lake Road) intersection in Holly Springs. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 3400000 | FY 2026: 34000; FY 2027: 2961000; FY 2028: 405000
HL-0008F | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | BGBA | RIGHT-OF-WAY | 408000
HL-0008F | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 102000
HL-0008F | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | BGBA | UTILITIES | 40000
HL-0008F | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T(M) | UTILITIES | 10000
HL-0008F | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | BGBA | CONSTRUCTION | 1600000
HL-0008F | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1006 (Old Stage Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T(M) | CONSTRUCTION | 400000
HL-0008G | Highway | Locally Selected | SR 1375 (Lake Wheeler Road) | SR 1393 (Hilltop-Needmore Road) intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | RIGHT-OF-WAY | 790000
HL-0008G | Highway | Locally Selected | SR 1375 (Lake Wheeler Road) | SR 1393 (Hilltop-Needmore Road) intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 240000
HL-0008G | Highway | Locally Selected | SR 1375 (Lake Wheeler Road) | SR 1393 (Hilltop-Needmore Road) intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | CONSTRUCTION | 2000000 | FY 2026: 404000
HL-0008H | Highway | Locally Selected | SR 1371 (Lake Wheeler Road) / SR 1375 (Lake Wheeler Road) | SR 1375 (Simpkins Road) / Simpkins Farm Lane intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BA | RIGHT-OF-WAY | 251000
HL-0008H | Highway | Locally Selected | SR 1371 (Lake Wheeler Road) / SR 1375 (Lake Wheeler Road) | SR 1375 (Simpkins Road) / Simpkins Farm Lane intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BA | UTILITIES | 300000
HL-0008H | Highway | Locally Selected | SR 1371 (Lake Wheeler Road) / SR 1375 (Lake Wheeler Road) | SR 1375 (Simpkins Road) / Simpkins Farm Lane intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BA | CONSTRUCTION | 1750000 | FY 2026: 1732000
HL-0008I | Highway | Locally Selected | SR 1006 (Old Stage Road) | SR 2736 (Rock Service Station Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 3100000 | FY 2026: 310000; FY 2027: 310000
HL-0008I | Highway | Locally Selected | SR 1006 (Old Stage Road) | SR 2736 (Rock Service Station Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 350000
HL-0008I | Highway | Locally Selected | SR 1006 (Old Stage Road) | SR 2736 (Rock Service Station Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 9300000 | FY 2026: 93000; FY 2027: 5385000; FY 2028: 3822000
HL-0008J | Highway | Locally Selected | NC 50 | SR 2728 (Rand Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | ENGINEERING | 10000
HL-0008J | Highway | Locally Selected | NC 50 | SR 2728 (Rand Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | RIGHT-OF-WAY | 1500000
HL-0008J | Highway | Locally Selected | NC 50 | SR 2728 (Rand Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | UTILITIES | 100000
HL-0008J | Highway | Locally Selected | NC 50 | SR 2728 (Rand Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | CONSTRUCTION | 17200000 | FY 2027: 4616000; FY 2028: 7843000; FY 2029: 4741000
HL-0008L | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1386 (Bells Lake Road) / SR 1386 (Graham Newton Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 300000
HL-0008L | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1386 (Bells Lake Road) / SR 1386 (Graham Newton Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 225000
HL-0008L | Highway | Locally Selected | SR 1010 (Ten Ten Road) | SR 1386 (Bells Lake Road) / SR 1386 (Graham Newton Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 3000000 | FY 2026: 1686000
HL-0008O | Highway | Locally Selected | NC 42 | SR 2735 (Johnston Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 175000
HL-0008O | Highway | Locally Selected | NC 42 | SR 2735 (Johnston Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 125000
HL-0008O | Highway | Locally Selected | NC 42 | SR 2735 (Johnston Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 1300000 | FY 2026: 274000
HL-0008P | Highway | Locally Selected | SR 1010 (Ten Ten Road) | NC 50 (Benson Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 370000
HL-0008P | Highway | Locally Selected | SR 1010 (Ten Ten Road) | NC 50 (Benson Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 240000
HL-0008P | Highway | Locally Selected | SR 1010 (Ten Ten Road) | NC 50 (Benson Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | HSIP | CONSTRUCTION | 400000 | FY 2028: 122000; FY 2029: 278000
HL-0008P | Highway | Locally Selected | SR 1010 (Ten Ten Road) | NC 50 (Benson Road) intersection in Garner. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 2300000 | FY 2028: 699000; FY 2029: 1601000
HL-0008Q | Highway | Locally Selected | SR 1390 (Optimist Farm Road) | SR 1386 (Bells Lake Road) intersection in Apex. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | ENGINEERING | 10000
HL-0008Q | Highway | Locally Selected | SR 1390 (Optimist Farm Road) | SR 1386 (Bells Lake Road) intersection in Apex. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 360000
HL-0008Q | Highway | Locally Selected | SR 1390 (Optimist Farm Road) | SR 1386 (Bells Lake Road) intersection in Apex. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 60000
HL-0008Q | Highway | Locally Selected | SR 1390 (Optimist Farm Road) | SR 1386 (Bells Lake Road) intersection in Apex. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 3800000 | FY 2026: 1634000; FY 2027: 2166000
HL-0008S | Highway | Locally Selected | SR 1379 (Penny Road) | SR 1382 (Olde South Road) intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | DELETED | Exempt
HL-0009 | Highway | Locally Selected | NC 711 (Third Street) | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | ENGINEERING | 350000
HL-0009 | Highway | Locally Selected | NC 711 (Third Street) | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 100000
HL-0009 | Highway | Locally Selected | NC 711 (Third Street) | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | UTILITIES | 930000
HL-0009 | Highway | Locally Selected | NC 711 (Third Street) | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | CONSTRUCTION | 3882000
HL-0009 | Highway | Locally Selected | NC 711 (Third Street) | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | L | CONSTRUCTION | 1178000
HL-0009 | Highway | Locally Selected | NC 711 (Third Street) | South Vance Street to SR 1555 (South Jones Street) in Pembroke. | Construct improvements to connect The University of North Carolina at Pembroke to the headquarters of the Lumbee Tribe in Pembroke. | 0.17 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | HF | CONSTRUCTION | 3750000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 236000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGDA | ENGINEERING | 16000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L(M) | ENGINEERING | 63000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | RIGHT-OF-WAY | 96000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L(M) | RIGHT-OF-WAY | 24000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | CONSTRUCTION | 448000 | FY 2026: 448000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGDA | CONSTRUCTION | 592000 | FY 2026: 592000
HL-0013 | Highway | Locally Selected | 9th Street | Bridge 100522 over Tomahawk Branch in Black Mountain. | Replace bridge. |  | Buncombe | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L(M) | CONSTRUCTION | 260000 | FY 2026: 260000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 28000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGDA | ENGINEERING | 32000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L(M) | ENGINEERING | 15000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | CONSTRUCTION | 272000 | FY 2027: 272000
HL-0014 | Highway | Locally Selected | SR 3214 (Biltmore Avenue) | White Fawn Drive intersection in Asheville. | Install a traffic signal and construct pedestrian improvements. |  | Buncombe | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L(M) | CONSTRUCTION | 68000 | FY 2027: 68000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGDA | ENGINEERING | 657000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | ENGINEERING | 164000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGDA | RIGHT-OF-WAY | 226000 | FY 2026: 226000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | RIGHT-OF-WAY | 56000 | FY 2026: 56000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGANY | UTILITIES | 230000 | FY 2026: 230000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | UTILITIES | 58000 | FY 2026: 58000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGANY | CONSTRUCTION | 2315000 | FY 2027: 2315000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGDA | CONSTRUCTION | 186000 | FY 2027: 186000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (West Mountain Street) | Beaucrest Street to Asbury Drive in Kernersville. | Construct turn-lane between Kernersville YMCA and Deere-Hitachi East entrance, and extend existing sidewalk from Beaucrest Street to Asbury Drive. | 0.77 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | CONSTRUCTION | 624000 | FY 2027: 624000
HL-0023 | Highway | Locally Selected | Rea Road | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BA | ENGINEERING | 10000
HL-0023 | Highway | Locally Selected | Rea Road | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | ENGINEERING | 14000
HL-0023 | Highway | Locally Selected | Rea Road | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BA | RIGHT-OF-WAY | 816000
HL-0023 | Highway | Locally Selected | Rea Road | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | CONSTRUCTION | 5834000 | FY 2026: 2292000; FY 2027: 3542000
HL-0023 | Highway | Locally Selected | Rea Road | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | O | CONSTRUCTION | 51000 | FY 2026: 51000
HL-0023 | Highway | Locally Selected | Rea Road | I-485 Outer Loop to Williams Pond Lane. | Widen to six lanes. | 0.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | HF | CONSTRUCTION | 300000 | FY 2026: 300000
HL-0024 | Highway | Locally Selected | SR 3468 (Weddington Road) | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BA | ENGINEERING | 1211000
HL-0024 | Highway | Locally Selected | SR 3468 (Weddington Road) | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 800000
HL-0024 | Highway | Locally Selected | SR 3468 (Weddington Road) | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BA | RIGHT-OF-WAY | 1500000 | FY 2026: 489000; FY 2027: 150000; FY 2028: 150000
HL-0024 | Highway | Locally Selected | SR 3468 (Weddington Road) | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BA | UTILITIES | 800000
HL-0024 | Highway | Locally Selected | SR 3468 (Weddington Road) | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | T(DA) | UTILITIES | 400000
HL-0024 | Highway | Locally Selected | SR 3468 (Weddington Road) | SR 3440 (McKee Road) intersection in Matthews. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | T(DA) | CONSTRUCTION | 4723000 | FY 2029: 1937000; FY 2030: 2120000; FY 2031: 666000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | BA | ENGINEERING | 1016000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | T(DA) | ENGINEERING | 133000 | FY 2026: 133000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | BA | RIGHT-OF-WAY | 701000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | T(DA) | UTILITIES | 500000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | T(DA) | MITIGATION | 24000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | T(DA) | CONSTRUCTION | 6805000 | FY 2026: 1588000; FY 2027: 3846000; FY 2028: 1371000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | L(M) | CONSTRUCTION | 384000 | FY 2026: 384000
HL-0025 | Highway | Locally Selected | Greylock Ridge Road | East John Street to Tank Town Road. | Construct roadway on new location. | 0.25 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. $1.563M IN BGDA FUNDS SWITCHED WITH $1.563M IN T(DA) FUNDS AS PART OF FUND SWAP 5-25. | Division 10 |  | L | CONSTRUCTION | 711000 | FY 2026: 711000
HL-0026 | Highway | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization. | Unallocated Surface Transportation Block Grant Program Funds. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO |  | Division 6, 8 |  | BGANY | CONSTRUCTION | 11260000 | FY 2026: 2815000; FY 2027: 2815000; FY 2028: 2815000; FY 2029: 2815000
HL-0026 | Highway | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization. | Unallocated Surface Transportation Block Grant Program Funds. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO |  | Division 6, 8 |  | BGDA | CONSTRUCTION | 75322000 | 0 | 0 | 0 | 0 | 0 | 1487000 | 5746000 | 5746000 | 5746000 | 5746000 | 40222000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | ENGINEERING | 50000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | ENGINEERING | 12000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 1208000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | RIGHT-OF-WAY | 302000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | UTILITIES | 460000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | UTILITIES | 115000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 462000
HL-0027 | Highway | Locally Selected | SR 1301 (Sunset Lake Road) | US 401 to SR 1431 (Products Road) in Fuquay-Varina. | Widen to four lane facility. | 0.55 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | CONSTRUCTION | 116000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (Mill Creek Drive) / Ideal Lane intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | ENGINEERING | 107000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (Mill Creek Drive) / Ideal Lane intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | ENGINEERING | 27000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (Mill Creek Drive) / Ideal Lane intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 2022000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (Mill Creek Drive) / Ideal Lane intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 505000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (Mill Creek Drive) / Ideal Lane intersection in Fuquay-Varina. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 675000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (Avent Ferry Road) to South Main Street in Holly Springs. | Construct 3rd southbound lane. | 0.39 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | RIGHT-OF-WAY | 51000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (Avent Ferry Road) to South Main Street in Holly Springs. | Construct 3rd southbound lane. | 0.39 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | RIGHT-OF-WAY | 51000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (Avent Ferry Road) to South Main Street in Holly Springs. | Construct 3rd southbound lane. | 0.39 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 457000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (Avent Ferry Road) to South Main Street in Holly Springs. | Construct 3rd southbound lane. | 0.39 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 457000
HL-0030 | Highway | Locally Selected | South Main Street | SR 1152 (Holly Springs Road) to Earp Street in Holly Springs. | Construct intersection improvements, add turn lanes and sidewalk on northbound Main Street. | 0.12 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 293000
HL-0030 | Highway | Locally Selected | South Main Street | SR 1152 (Holly Springs Road) to Earp Street in Holly Springs. | Construct intersection improvements, add turn lanes and sidewalk on northbound Main Street. | 0.12 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | RIGHT-OF-WAY | 158000
HL-0030 | Highway | Locally Selected | South Main Street | SR 1152 (Holly Springs Road) to Earp Street in Holly Springs. | Construct intersection improvements, add turn lanes and sidewalk on northbound Main Street. | 0.12 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 487000
HL-0030 | Highway | Locally Selected | South Main Street | SR 1152 (Holly Springs Road) to Earp Street in Holly Springs. | Construct intersection improvements, add turn lanes and sidewalk on northbound Main Street. | 0.12 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L(M) | CONSTRUCTION | 262000
HL-0031 | Highway | Locally Selected | SR 1007 (Poole Road) | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 272000
HL-0031 | Highway | Locally Selected | SR 1007 (Poole Road) | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Division 5 |  | HF(M) | RIGHT-OF-WAY | 68000
HL-0031 | Highway | Locally Selected | SR 1007 (Poole Road) | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Division 5 |  | BGDA | UTILITIES | 120000
HL-0031 | Highway | Locally Selected | SR 1007 (Poole Road) | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Division 5 |  | HF(M) | UTILITIES | 30000
HL-0031 | Highway | Locally Selected | SR 1007 (Poole Road) | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 1361000
HL-0031 | Highway | Locally Selected | SR 1007 (Poole Road) | SR 2233 (Smithfield Road). | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Division 5 |  | HF(M) | CONSTRUCTION | 339000
HL-0032 | Highway | Locally Selected | Lake Boone Trail | I-440 to Ridge Road in Raleigh. | Upgrade roadway to complete street. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1235000
HL-0032 | Highway | Locally Selected | Lake Boone Trail | I-440 to Ridge Road in Raleigh. | Upgrade roadway to complete street. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 477000
HL-0033 | Highway | Locally Selected | SR 3126 (Airport Boulevard) | Garden Square Lane to SR 1637 (Church Street) in Morrisville. | Construct roadway on new location. | 0.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 360000
HL-0033 | Highway | Locally Selected | SR 3126 (Airport Boulevard) | Garden Square Lane to SR 1637 (Church Street) in Morrisville. | Construct roadway on new location. | 0.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | RIGHT-OF-WAY | 240000
HL-0033 | Highway | Locally Selected | SR 3126 (Airport Boulevard) | Garden Square Lane to SR 1637 (Church Street) in Morrisville. | Construct roadway on new location. | 0.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 3884000 | FY 2026: 3884000
HL-0033 | Highway | Locally Selected | SR 3126 (Airport Boulevard) | Garden Square Lane to SR 1637 (Church Street) in Morrisville. | Construct roadway on new location. | 0.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L(M) | CONSTRUCTION | 2590000 | FY 2026: 2590000
HL-0033 | Highway | Locally Selected | SR 3126 (Airport Boulevard) | Garden Square Lane to SR 1637 (Church Street) in Morrisville. | Construct roadway on new location. | 0.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 4626000 | FY 2026: 4626000
HL-0034 | Highway | Locally Selected | SR 1356 (Raleigh Road Parkway) | Atlantic Christian College Drive to NC 42 / NC 58 in Wilson. | Modernize roadway. | 0.47 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Exempt |  | BA | ENGINEERING | 45000
HL-0034 | Highway | Locally Selected | SR 1356 (Raleigh Road Parkway) | Atlantic Christian College Drive to NC 42 / NC 58 in Wilson. | Modernize roadway. | 0.47 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Exempt |  | BA | UTILITIES | 75000
HL-0034 | Highway | Locally Selected | SR 1356 (Raleigh Road Parkway) | Atlantic Christian College Drive to NC 42 / NC 58 in Wilson. | Modernize roadway. | 0.47 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Exempt |  | BA | CONSTRUCTION | 2357000
HL-0036 | Highway | Locally Selected | NC 59 (North Main Street) | Lakeview Road to second entrance of Lake Park Concession Stand at Boatmans Drive. | Design and construct 10 foot multi-use path. | 1.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 40000
HL-0036 | Highway | Locally Selected | NC 59 (North Main Street) | Lakeview Road to second entrance of Lake Park Concession Stand at Boatmans Drive. | Design and construct 10 foot multi-use path. | 1.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 10000
HL-0036 | Highway | Locally Selected | NC 59 (North Main Street) | Lakeview Road to second entrance of Lake Park Concession Stand at Boatmans Drive. | Design and construct 10 foot multi-use path. | 1.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 614000
HL-0036 | Highway | Locally Selected | NC 59 (North Main Street) | Lakeview Road to second entrance of Lake Park Concession Stand at Boatmans Drive. | Design and construct 10 foot multi-use path. | 1.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 154000
HL-0037 | Highway | Locally Selected | Various | Routes in Division 12. | Perform various maintenance activities including resurfacing and pavement restriping. |  | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDACV | CONSTRUCTION | 975000
HL-0038 | Highway | Locally Selected | Various | Routes in Division 10. | Perform various maintenance activities including resurfacing, traffic signal loop replacement, pavement restriping and markers, and sign replacement. |  | Mecklenburg | 10 | Charlotte Regional TPO |  |  |  | BGDACV | ENGINEERING | 5000
HL-0038A | Highway | Locally Selected | US 29 / US 74 (Wilkinson Boulevard); US 29 (North Tryon Street) | Gaston County line to Field Ridge Road; West Sugar Creek Road to Old Concord Road. | Resurface roadways. | 3.46 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | BGDACV | CONSTRUCTION | 2596000
HL-0038B | Highway | Locally Selected | Various | Routes in Division 10. | Replace pavement markings and snow plowable markers. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDACV | CONSTRUCTION | 2318000
HL-0038C | Highway | Locally Selected | Various | Routes in Division 10. | Replace traffic signal loops. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | BGDACV | CONSTRUCTION | 90000
HL-0038D | Highway | Locally Selected | I-485 | Various locations along interstate. | Replace overhead signs. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDACV | CONSTRUCTION | 705000
HL-0039 | Highway | Locally Selected | Various | Routes in Division 10. | Perform various maintenance activities including resurfacing, traffic signal loop replacement, and pavement restriping. |  | Union | 10 | Charlotte Regional TPO
HL-0039A | Highway | Locally Selected | North Charlotte Avenue; New Town Road | Walnut Street to NC 200; Cuthbertson Road to Ennis Road. | Resurface roadways. | 3.23 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDACV | CONSTRUCTION | 938000
HL-0039B | Highway | Locally Selected | Various | Routes in Division 10. | Replace pavement markings. |  | Union | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | BGDACV | CONSTRUCTION | 126000
HL-0039C | Highway | Locally Selected | Various | Routes in Division 10. | Replace traffic signal loops. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDACV | CONSTRUCTION | 189000
HL-0040 | Highway | Locally Selected | North Carolina Port Authority | Wilmington. | Construct new north gate on North Carolina Port Authority property. |  | New Hanover | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY. | Division 3 |  | CRPDA | ENGINEERING | 250000
HL-0040 | Highway | Locally Selected | North Carolina Port Authority | Wilmington. | Construct new north gate on North Carolina Port Authority property. |  | New Hanover | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY. | Division 3 |  | L(M) | ENGINEERING | 63000
HL-0041 | Highway | Locally Selected | SR 2768 (Judd Parkway) | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION | Exempt |  | CMAQ | ENGINEERING | 69000
HL-0041 | Highway | Locally Selected | SR 2768 (Judd Parkway) | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION | Exempt |  | HF(M) | ENGINEERING | 17000
HL-0041 | Highway | Locally Selected | SR 2768 (Judd Parkway) | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000
HL-0041 | Highway | Locally Selected | SR 2768 (Judd Parkway) | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION | Exempt |  | HF(M) | RIGHT-OF-WAY | 13000
HL-0041 | Highway | Locally Selected | SR 2768 (Judd Parkway) | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 1550000
HL-0041 | Highway | Locally Selected | SR 2768 (Judd Parkway) | US 401 (South Main Street) intersection in Fuquay-Varina. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. UNDER CONSTRUCTION | Exempt |  | HF(M) | CONSTRUCTION | 611000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | ENGINEERING | 202000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | ENGINEERING | 51000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | RIGHT-OF-WAY | 112000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | RIGHT-OF-WAY | 28000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | UTILITIES | 208000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | UTILITIES | 52000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 975000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 900000
HL-0042 | Highway | Locally Selected | SR 1110 (Wilbon Road) / SR 5056 (Judd Parkway) | NC 55 Intersection in Fuquay-Varina. | Construct dedicated turn lanes on SR 5056 leg of Judd Parkway. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 469000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | ENGINEERING | 152000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF(M) | ENGINEERING | 38000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | RIGHT-OF-WAY | 220000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 55000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | UTILITIES | 160000 | FY 2026: 160000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF(M) | UTILITIES | 40000 | FY 2026: 40000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 672000 | FY 2026: 8000; FY 2027: 664000
HL-0043 | Highway | Locally Selected | SR 1005 (Six Forks Road) | SR 2006 (Durant Road) intersection in Raleigh. | Add northbound and westbound right turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 168000 | FY 2026: 2000; FY 2027: 166000
HL-0044 | Highway | Locally Selected | SR 1230 (Bunn Road) | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 85000 | FY 2026: 85000
HL-0044 | Highway | Locally Selected | SR 1230 (Bunn Road) | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | ENGINEERING | 21000 | FY 2026: 21000
HL-0044 | Highway | Locally Selected | SR 1230 (Bunn Road) | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 30000 | FY 2027: 30000
HL-0044 | Highway | Locally Selected | SR 1230 (Bunn Road) | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 8000 | FY 2027: 8000
HL-0044 | Highway | Locally Selected | SR 1230 (Bunn Road) | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 370000 | FY 2027: 370000
HL-0044 | Highway | Locally Selected | SR 1230 (Bunn Road) | Kenmore Avenue to US 401 / NC 56 (Bickett Boulevard) in Louisburg. | Reduce 4 lanes to 2 lanes and construct bicycle and pedestrian improvements. | 0.35 | Franklin | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | CONSTRUCTION | 92000 | FY 2027: 92000
HL-0045 | Highway | Locally Selected | Exchange Park Lane | Faribault Lane to US 70 Business (South Churton Street) in Hillsborough. | Repair bridge 670241 over Eno River. | 0.13 | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 321000 | FY 2026: 321000
HL-0045 | Highway | Locally Selected | Exchange Park Lane | Faribault Lane to US 70 Business (South Churton Street) in Hillsborough. | Repair bridge 670241 over Eno River. | 0.13 | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 80000 | FY 2026: 80000
HL-0046 | Highway | Locally Selected | SR 4240 (East Gate City Boulevard) | Willow Road to Florida Street in Greensboro. | Modernize roadway, add curb and gutter, and construct sidewalks. | 0.91 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | RIGHT-OF-WAY | 200000
HL-0046 | Highway | Locally Selected | SR 4240 (East Gate City Boulevard) | Willow Road to Florida Street in Greensboro. | Modernize roadway, add curb and gutter, and construct sidewalks. | 0.91 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | RIGHT-OF-WAY | 50000
HL-0046 | Highway | Locally Selected | SR 4240 (East Gate City Boulevard) | Willow Road to Florida Street in Greensboro. | Modernize roadway, add curb and gutter, and construct sidewalks. | 0.91 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T(DA) | UTILITIES | 100000 | FY 2026: 100000
HL-0046 | Highway | Locally Selected | SR 4240 (East Gate City Boulevard) | Willow Road to Florida Street in Greensboro. | Modernize roadway, add curb and gutter, and construct sidewalks. | 0.91 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T(DA) | CONSTRUCTION | 4500000 | FY 2026: 2250000; FY 2027: 2250000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | ENGINEERING | 8000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 2000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 56000 | FY 2026: 56000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 14000 | FY 2026: 14000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 160000 | FY 2027: 160000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 440000 | FY 2027: 440000
HL-0047 | Highway | Locally Selected | SR 2523 (Yanceyville Street); SR 2876 (Sands Drive); Old Battleground Road | Lees Chapel Road to Future I-840 (Greensboro Urban Loop); East Cone Boulevard to McKnight Mill Road; US 220 (Battleground Avenue) to British Lake Drive in Greensboro. | Widen and modernize roadway, construct curb and gutter and sidewalks; construct sidewalk; construct sidewalk. | 0.86 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 150000 | FY 2027: 150000
HL-0048 | Highway | Locally Selected | Various | Locations in Greensboro. | Pedestrian signal installation, accessible ramp construction, and traffic signal replacement at various intersections in Greensboro. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDACV | ENGINEERING | 255000
HL-0048 | Highway | Locally Selected | Various | Locations in Greensboro. | Pedestrian signal installation, accessible ramp construction, and traffic signal replacement at various intersections in Greensboro. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 8000 | FY 2026: 8000
HL-0048 | Highway | Locally Selected | Various | Locations in Greensboro. | Pedestrian signal installation, accessible ramp construction, and traffic signal replacement at various intersections in Greensboro. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HL-0048 | Highway | Locally Selected | Various | Locations in Greensboro. | Pedestrian signal installation, accessible ramp construction, and traffic signal replacement at various intersections in Greensboro. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 800000 | FY 2027: 800000
HL-0048 | Highway | Locally Selected | Various | Locations in Greensboro. | Pedestrian signal installation, accessible ramp construction, and traffic signal replacement at various intersections in Greensboro. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 200000 | FY 2027: 200000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | ENGINEERING | 176000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | ENGINEERING | 44000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 11000 | FY 2026: 11000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 3000 | FY 2026: 3000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | UTILITIES | 160000 | FY 2026: 160000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | UTILITIES | 40000 | FY 2026: 40000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1157000 | FY 2027: 473000; FY 2028: 684000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | CONSTRUCTION | 1601000 | FY 2027: 1601000
HL-0049 | Highway | Locally Selected | Brenner Avenue | US 70 / US 601 (Jake Alexander Boulevard) to Milford Hills Road in Salisbury. | Construct median and construct roundabout at Milford Hills Road. | 0.21 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 689000 | FY 2027: 518000; FY 2028: 171000
HL-0050 | Highway | Locally Selected | SR 1349 (Dillard Drive) | Village Tavern Road to SR 1319 (Jones Franklin Road) in Raleigh. | Install two way left turn lane. | 0.15 | Wake | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 505000
HL-0050 | Highway | Locally Selected | SR 1349 (Dillard Drive) | Village Tavern Road to SR 1319 (Jones Franklin Road) in Raleigh. | Install two way left turn lane. | 0.15 | Wake | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF | RIGHT-OF-WAY | 296000
HL-0050 | Highway | Locally Selected | SR 1349 (Dillard Drive) | Village Tavern Road to SR 1319 (Jones Franklin Road) in Raleigh. | Install two way left turn lane. | 0.15 | Wake | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 298000 | FY 2026: 298000
HL-0050 | Highway | Locally Selected | SR 1349 (Dillard Drive) | Village Tavern Road to SR 1319 (Jones Franklin Road) in Raleigh. | Install two way left turn lane. | 0.15 | Wake | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF | CONSTRUCTION | 174000 | FY 2026: 174000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | ENGINEERING | 88000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | ENGINEERING | 22000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | RIGHT-OF-WAY | 56000 | FY 2026: 56000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | RIGHT-OF-WAY | 14000 | FY 2026: 14000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | UTILITIES | 8000 | FY 2026: 8000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | UTILITIES | 2000 | FY 2026: 2000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | CONSTRUCTION | 320000 | FY 2027: 320000
HL-0051 | Highway | Locally Selected | SR 1319 (Jones Franklin Road) | Athens Drive intersection in Raleigh. | Install left turn lanes. |  | Wake | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | CONSTRUCTION | 80000 | FY 2027: 80000
HL-0052 | Highway | Locally Selected | Blue Ridge Road | Homewood Banks Drive to Crabtree Valley Avenue in Raleigh. | Add center turn lane, raised median, complete street improvements, and grade separation with House Creek Greenway Connections. | 0.32 | Wake | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | BGDA | ENGINEERING | 8000
HL-0052 | Highway | Locally Selected | Blue Ridge Road | Homewood Banks Drive to Crabtree Valley Avenue in Raleigh. | Add center turn lane, raised median, complete street improvements, and grade separation with House Creek Greenway Connections. | 0.32 | Wake | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | L(M) | ENGINEERING | 2000
HL-0052 | Highway | Locally Selected | Blue Ridge Road | Homewood Banks Drive to Crabtree Valley Avenue in Raleigh. | Add center turn lane, raised median, complete street improvements, and grade separation with House Creek Greenway Connections. | 0.32 | Wake | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | BGANY | CONSTRUCTION | 6398000
HL-0052 | Highway | Locally Selected | Blue Ridge Road | Homewood Banks Drive to Crabtree Valley Avenue in Raleigh. | Add center turn lane, raised median, complete street improvements, and grade separation with House Creek Greenway Connections. | 0.32 | Wake | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | L(M) | CONSTRUCTION | 1599000
HL-0053 | Highway | Locally Selected | SR 2822 (Robinson Church Road) | NC 24 to Plott Road. | Widen to three lanes. | 0.58 | Mecklenburg | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | T(DA) | ENGINEERING | 5000 | FY 2026: 5000
HL-0053 | Highway | Locally Selected | SR 2822 (Robinson Church Road) | NC 24 to Plott Road. | Widen to three lanes. | 0.58 | Mecklenburg | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | L | ENGINEERING | 5000 | FY 2026: 5000
HL-0053 | Highway | Locally Selected | SR 2822 (Robinson Church Road) | NC 24 to Plott Road. | Widen to three lanes. | 0.58 | Mecklenburg | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | T(DA) | CONSTRUCTION | 6222000 | FY 2028: 1773000; FY 2029: 3093000; FY 2030: 1356000
HL-0053 | Highway | Locally Selected | SR 2822 (Robinson Church Road) | NC 24 to Plott Road. | Widen to three lanes. | 0.58 | Mecklenburg | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 6222000 | FY 2028: 6222000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | T(DA) | ENGINEERING | 380000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | L | ENGINEERING | 95000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGANY | RIGHT-OF-WAY | 466000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | O | RIGHT-OF-WAY | 60000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | L(M) | RIGHT-OF-WAY | 117000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGANY | CONSTRUCTION | 1098000 | FY 2027: 672000; FY 2028: 426000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | L(M) | CONSTRUCTION | 275000 | FY 2027: 275000
HL-0055 | Highway | Locally Selected | SR 1357 (Potter Road) | SR 1358 (Forest Lawn Drive) intersection in Weddington. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | HF | CONSTRUCTION | 400000 | FY 2027: 245000; FY 2028: 155000
HL-0056 | Highway | Locally Selected | NC 115 | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | T(DA) | ENGINEERING | 526000
HL-0056 | Highway | Locally Selected | NC 115 | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | L | ENGINEERING | 225000
HL-0056 | Highway | Locally Selected | NC 115 | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | T(DA) | RIGHT-OF-WAY | 1996000 | FY 2027: 499000; FY 2028: 998000; FY 2029: 499000
HL-0056 | Highway | Locally Selected | NC 115 | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 856000 | FY 2027: 214000; FY 2028: 428000; FY 2029: 214000
HL-0056 | Highway | Locally Selected | NC 115 | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | T(DA) | CONSTRUCTION | 3457000 | FY 2029: 3457000
HL-0056 | Highway | Locally Selected | NC 115 | Harvest Point Drive to Sam Furr Road. | Improve corridor. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | L | CONSTRUCTION | 1481000 | FY 2029: 1481000
HL-0057 | Highway | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2004 (Mount Holly-Huntersville Road) to I-85 North ramp. | Install overhead street lights. | 7.92 | Mecklenburg | 10 | Charlotte Regional TPO | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024. | Division 10 |  | BA | ENGINEERING | 10000
HL-0057 | Highway | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2004 (Mount Holly-Huntersville Road) to I-85 North ramp. | Install overhead street lights. | 7.92 | Mecklenburg | 10 | Charlotte Regional TPO | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024. | Division 10 |  | T(DA) | CONSTRUCTION | 988000 | FY 2026: 988000
HL-0057 | Highway | Locally Selected | NC 24 (W.T. Harris Boulevard) | SR 2004 (Mount Holly-Huntersville Road) to I-85 North ramp. | Install overhead street lights. | 7.92 | Mecklenburg | 10 | Charlotte Regional TPO | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024. | Division 10 |  | L | CONSTRUCTION | 534000 | FY 2026: 534000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | BGDA | ENGINEERING | 86000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | HF | ENGINEERING | 65000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | BGDA | RIGHT-OF-WAY | 737000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | HF | RIGHT-OF-WAY | 322000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | BGDA | UTILITIES | 370000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | HF | UTILITIES | 200000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 180000 | FY 2026: 180000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | BGDA | CONSTRUCTION | 2389000 | FY 2026: 2389000
HL-0059 | Highway | Locally Selected | NC 8 (Germanton Road) | SR 1686 (Oak Summit Road) intersection in Winston Salem. | Construct left turn lanes and signal improvements. |  | Forsyth | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Exempt |  | HF | CONSTRUCTION | 467000 | FY 2026: 467000
HL-0060 | Highway | Locally Selected | Various | Routes in High Point | High Point signal system retiming study. |  | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 1218000
HL-0060 | Highway | Locally Selected | Various | Routes in High Point | High Point signal system retiming study. |  | Guilford | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 305000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | ENGINEERING | 320000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 80000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 986000 | FY 2026: 986000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 599000 | FY 2026: 599000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | HF(M) | RIGHT-OF-WAY | 397000 | FY 2026: 397000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | UTILITIES | 414000 | FY 2026: 414000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | UTILITIES | 104000 | FY 2026: 104000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | CONSTRUCTION | 1294000 | FY 2027: 1294000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 311000 | FY 2027: 311000
HL-0061 | Highway | Locally Selected | NC 109 | Ray Lanning Road to Wallburg Road. | Construct turn lane and traffic signal. | 0.21 | Davidson | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 402000 | FY 2027: 402000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGDA | ENGINEERING | 1117000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | ENGINEERING | 279000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGDA | RIGHT-OF-WAY | 764000 | FY 2026: 764000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | RIGHT-OF-WAY | 191000 | FY 2026: 191000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | UTILITIES | 306000 | FY 2026: 306000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | UTILITIES | 76000 | FY 2026: 76000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | CONSTRUCTION | 5156000 | FY 2027: 5156000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (Morehead Road) to Cedar Drive. | Construct access management improvements. | 0.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | CONSTRUCTION | 1289000 | FY 2027: 1289000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | ENGINEERING | 666000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | ENGINEERING | 167000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 886000 | FY 2027: 886000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | RIGHT-OF-WAY | 222000 | FY 2027: 222000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | UTILITIES | 8000 | FY 2027: 8000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | UTILITIES | 2000 | FY 2027: 2000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | CONSTRUCTION | 3325000 | FY 2028: 3325000
HL-0063 | Highway | Locally Selected | SR 1173 (Caldwell Road) | NC 49 to US 29. | Extend roadway approximately 3000 feet and construct intersection improvements at SR 1173 (Caldwell Road) and NC 49. | 0.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | CONSTRUCTION | 831000 | FY 2028: 831000
HL-0064 | Highway | Locally Selected | US 29 (Main Street) | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | ENGINEERING | 8000
HL-0064 | Highway | Locally Selected | US 29 (Main Street) | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | ENGINEERING | 2000
HL-0064 | Highway | Locally Selected | US 29 (Main Street) | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | UTILITIES | 2609000 | FY 2026: 2609000
HL-0064 | Highway | Locally Selected | US 29 (Main Street) | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | UTILITIES | 652000 | FY 2026: 652000
HL-0064 | Highway | Locally Selected | US 29 (Main Street) | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 15377000 | FY 2026: 4809000; FY 2027: 10568000
HL-0064 | Highway | Locally Selected | US 29 (Main Street) | Kerr Street to Horah Street in Salisbury. | Construct safety improvements. | 0.52 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 3844000 | FY 2026: 1202000; FY 2027: 2642000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | ENGINEERING | 912000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | CRPANY | ENGINEERING | 1569000 | FY 2026: 1569000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | T(M) | ENGINEERING | 393000 | FY 2026: 393000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | HF(M) | ENGINEERING | 228000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | RIGHT-OF-WAY | 1050000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | CRPANY | RIGHT-OF-WAY | 2000000 | FY 2026: 2000000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | T(M) | RIGHT-OF-WAY | 500000 | FY 2026: 500000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | UTILITIES | 2110000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | CONSTRUCTION | 15968000 | FY 2026: 15968000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | HSIP | CONSTRUCTION | 900000 | FY 2026: 900000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | CRPANY | CONSTRUCTION | 4890000 | FY 2026: 4890000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | L | CONSTRUCTION | 510000 | FY 2026: 510000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | T(M) | CONSTRUCTION | 1222000 | FY 2026: 1222000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | HF(M) | CONSTRUCTION | 2360000 | FY 2026: 2360000
HL-0065 | Highway | Locally Selected | US 221A (Charlotte Road) | US 221 (South Main Street) to US 221 (South Broadway Street). | Construct complete street to include intersection improvements, multi-use path, sidewalks, and improved transit facilities. | 6.08 | Rutherford | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | 5311 | CONSTRUCTION | 100000 | FY 2026: 100000
HL-0090 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization (FBRMPO) area. | Unallocated Carbon Reduction Program funds. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 599000 | FY 2026: 599000
HL-0090 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization (FBRMPO) area. | Unallocated Carbon Reduction Program funds. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Exempt |  | L(M) | CONSTRUCTION | 150000 | FY 2026: 150000
HL-0091 | Highway | Locally Selected | Various | Burlington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Alamance, Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt
HL-0091 | Highway | Locally Selected | Various | Burlington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Alamance, Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1365000 | FY 2026: 274000
HL-0091 | Highway | Locally Selected | Various | Burlington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Alamance, Guilford, Orange | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | CONSTRUCTION | 343000 | FY 2026: 69000
HL-0092 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) area. | Unallocated Carbon Reduction Program funds. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1146000 | FY 2026: 0; FY 2027: 1146000
HL-0092 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) area. | Unallocated Carbon Reduction Program funds. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 287000 | FY 2026: 0; FY 2027: 287000
HL-0093 | Highway | Locally Selected | Various | Cabarrus-Rowan Planning Organization (CRMPO) area. | Unallocated Carbon Reduction Program funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 0 | FY 2026: 0
HL-0093 | Highway | Locally Selected | Various | Cabarrus-Rowan Planning Organization (CRMPO) area. | Unallocated Carbon Reduction Program funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 0 | FY 2026: 0
HL-0094 | Highway | Locally Selected | Various | Triangle West Transportation Planning Organization | Unallocated Carbon Reduction Program funds. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1918000 | FY 2026: 647000
HL-0094 | Highway | Locally Selected | Various | Triangle West Transportation Planning Organization | Unallocated Carbon Reduction Program funds. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO |  | Exempt |  | L(M) | CONSTRUCTION | 377000 | FY 2026: 215000
HL-0095 | Highway | Locally Selected | Various | Fayetteville Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 4392000 | FY 2026: 242000
HL-0095 | Highway | Locally Selected | Various | Fayetteville Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 1098000 | FY 2026: 61000
HL-0096 | Highway | Locally Selected | Various | Gaston Cleveland Lincoln Planning Organization (GCLMPO) area. | Unallocated Carbon Reduction Program funds. |  | Gaston, Cleveland, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1232000 | FY 2026: 384000
HL-0096 | Highway | Locally Selected | Various | Gaston Cleveland Lincoln Planning Organization (GCLMPO) area. | Unallocated Carbon Reduction Program funds. |  | Gaston, Cleveland, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L(M) | CONSTRUCTION | 308000 | FY 2026: 96000
HL-0097 | Highway | Locally Selected | Various | Goldsboro Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Wayne | 4 | Goldsboro Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1414000 | FY 2026: 118000
HL-0097 | Highway | Locally Selected | Various | Goldsboro Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Wayne | 4 | Goldsboro Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 331000 | FY 2026: 30000
HL-0098 | Highway | Locally Selected | Various | Greensboro Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1472000 | FY 2026: 736000
HL-0098 | Highway | Locally Selected | Various | Greensboro Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 368000 | FY 2026: 184000
HL-0099 | Highway | Locally Selected | Various | Greenville Planning Metropolitan Organization | Unallocated Carbon Reduction Program funds. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 2633000 | FY 2026: 261000
HL-0099 | Highway | Locally Selected | Various | Greenville Planning Metropolitan Organization | Unallocated Carbon Reduction Program funds. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 662000 | FY 2026: 65000
HL-0100 | Highway | Locally Selected | Various | Greater Hickory Planning Organization (GHMPO) area. | Unallocated Carbon Reduction Program funds. |  | Catawba, Alexander, Burke, Caldwell | 11, 12, 13 | Greater Hickory MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 0 | FY 2026: 0
HL-0100 | Highway | Locally Selected | Various | Greater Hickory Planning Organization (GHMPO) area. | Unallocated Carbon Reduction Program funds. |  | Catawba, Alexander, Burke, Caldwell | 11, 12, 13 | Greater Hickory MPO |  | Exempt |  | L(M) | CONSTRUCTION | 0 | FY 2026: 0
HL-0101 | Highway | Locally Selected | Various | High Point Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Davidson, Guilford, Randolph, Forsyth | 7, 8, 9 | High Point Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1893000 | FY 2026: 380000
HL-0101 | Highway | Locally Selected | Various | High Point Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Davidson, Guilford, Randolph, Forsyth | 7, 8, 9 | High Point Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 473000 | FY 2026: 95000
HL-0102 | Highway | Locally Selected | Various | Jacksonville Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 2372000 | FY 2026: 241000
HL-0102 | Highway | Locally Selected | Various | Jacksonville Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 530000 | FY 2026: 60000
HL-0103 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Exempt |  | CRPDA | CONSTRUCTION | 245000 | FY 2026: 51000
HL-0103 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Exempt |  | L(M) | CONSTRUCTION | 97000 | FY 2026: 13000
HL-0104 | Highway | Locally Selected | Various | New Bern Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Craven | 2 | New Bern Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 684000 | FY 2026: 0
HL-0104 | Highway | Locally Selected | Various | New Bern Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Craven | 2 | New Bern Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 215000 | FY 2026: 0
HL-0105 | Highway | Locally Selected | Various | Capital Area Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 4806000 | FY 2026: 2403000
HL-0105 | Highway | Locally Selected | Various | Capital Area Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 1202000 | FY 2026: 601000
HL-0106 | Highway | Locally Selected | Various | Rocky Mount Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Nash, Edgecombe, Wilson | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | BGANY | CONSTRUCTION | 696000
HL-0106 | Highway | Locally Selected | Various | Rocky Mount Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Nash, Edgecombe, Wilson | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 465000 | FY 2026: 0
HL-0106 | Highway | Locally Selected | Various | Rocky Mount Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | Nash, Edgecombe, Wilson | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 145000 | FY 2026: 0
HL-0107 | Highway | Locally Selected | Various | Wilmington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 2981000 | FY 2026: 0
HL-0107 | Highway | Locally Selected | Various | Wilmington Metropolitan Planning Organization | Unallocated Carbon Reduction Program funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 746000 | FY 2026: 0
HL-0108 | Highway | Locally Selected | Winston-Salem Planning Organization | Routes in Winston-Salem Area Transportation Planning Organization | Unallocated Carbon Reduction Program funds. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 0 | FY 2026: 0
HL-0108 | Highway | Locally Selected | Winston-Salem Planning Organization | Routes in Winston-Salem Area Transportation Planning Organization | Unallocated Carbon Reduction Program funds. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 0 | FY 2026: 0
HL-0109 | Highway | Locally Selected | South 3rd Street | Ann Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 380000
HL-0109 | Highway | Locally Selected | South 3rd Street | Ann Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 109000
HL-0109 | Highway | Locally Selected | South 3rd Street | Ann Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 532000
HL-0109 | Highway | Locally Selected | South 3rd Street | Ann Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 132000
HL-0110 | Highway | Locally Selected | South 3rd Street | Orange Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | BGANY | ENGINEERING | 55000
HL-0110 | Highway | Locally Selected | South 3rd Street | Orange Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | HF | ENGINEERING | 14000
HL-0110 | Highway | Locally Selected | South 3rd Street | Orange Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | BGANY | CONSTRUCTION | 219000
HL-0110 | Highway | Locally Selected | South 3rd Street | Orange Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | L | CONSTRUCTION | 12000
HL-0110 | Highway | Locally Selected | South 3rd Street | Orange Street intersection in Wilmington. | Install traffic signal heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | HF | CONSTRUCTION | 55000 | FY 2026: 54000
HL-0111 | Highway | Locally Selected | Beaty Street | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | ENGINEERING | 215000
HL-0111 | Highway | Locally Selected | Beaty Street | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 143000
HL-0111 | Highway | Locally Selected | Beaty Street | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 203000 | FY 2027: 203000
HL-0111 | Highway | Locally Selected | Beaty Street | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 136000 | FY 2027: 136000
HL-0111 | Highway | Locally Selected | Beaty Street | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1645000 | FY 2029: 1645000
HL-0111 | Highway | Locally Selected | Beaty Street | Main Street intersection in Davidson. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 1097000 | FY 2029: 1097000
HL-0112 | Highway | Locally Selected | SR 2479 (Dearmon Road) | SR 2475 (Benfield Road) to SR 2480 (Browne Road). | Construct complete street improvements. | 0.78 | Mecklenburg | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | T(DA) | ENGINEERING | 4000
HL-0112 | Highway | Locally Selected | SR 2479 (Dearmon Road) | SR 2475 (Benfield Road) to SR 2480 (Browne Road). | Construct complete street improvements. | 0.78 | Mecklenburg | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | L | ENGINEERING | 6000
HL-0112 | Highway | Locally Selected | SR 2479 (Dearmon Road) | SR 2475 (Benfield Road) to SR 2480 (Browne Road). | Construct complete street improvements. | 0.78 | Mecklenburg | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | T(DA) | CONSTRUCTION | 5482000 | FY 2028: 2587000; FY 2029: 2194000; FY 2030: 701000
HL-0112 | Highway | Locally Selected | SR 2479 (Dearmon Road) | SR 2475 (Benfield Road) to SR 2480 (Browne Road). | Construct complete street improvements. | 0.78 | Mecklenburg | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | L | CONSTRUCTION | 10183000 | FY 2031: 10183000
HL-0113 | Highway | Locally Selected | Lancaster Highway | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | HF represents SPOT Mobility funds | Exempt |  | L | ENGINEERING | 313000
HL-0113 | Highway | Locally Selected | Lancaster Highway | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | HF represents SPOT Mobility funds | Exempt |  | L | UTILITIES | 400000 | FY 2026: 400000
HL-0113 | Highway | Locally Selected | Lancaster Highway | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | HF represents SPOT Mobility funds | Exempt |  | CMAQ | CONSTRUCTION | 1185000 | FY 2027: 1185000
HL-0113 | Highway | Locally Selected | Lancaster Highway | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | HF represents SPOT Mobility funds | Exempt |  | L | CONSTRUCTION | 1600000 | FY 2027: 1600000
HL-0113 | Highway | Locally Selected | Lancaster Highway | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | HF represents SPOT Mobility funds | Exempt |  | HF | CONSTRUCTION | 454000 | FY 2027: 454000
HL-0113 | Highway | Locally Selected | Lancaster Highway | Providence Road West intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | HF represents SPOT Mobility funds | Exempt |  | HF(M) | CONSTRUCTION | 296000 | FY 2027: 296000
HL-0114 | Highway | Locally Selected | Langtree Road | Pin Oak Lane to Mount Mourne Loop. | Widen roadway. | 1.21 | Iredell | 12 | Charlotte Regional TPO | $873K IN STBG-DA FUNDS SWAPPED FOR $873K IN STATE FUNDS ON 5-17-23 | Division 12 |  | T(DA) | ENGINEERING | 873000
HL-0114 | Highway | Locally Selected | Langtree Road | Pin Oak Lane to Mount Mourne Loop. | Widen roadway. | 1.21 | Iredell | 12 | Charlotte Regional TPO | $873K IN STBG-DA FUNDS SWAPPED FOR $873K IN STATE FUNDS ON 5-17-23 | Division 12 |  | L | ENGINEERING | 218000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | BGANY | ENGINEERING | 369000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | L | ENGINEERING | 92000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | BGANY | RIGHT-OF-WAY | 414000 | FY 2027: 414000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | L | RIGHT-OF-WAY | 103000 | FY 2027: 103000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | BGANY | CONSTRUCTION | 1053000 | FY 2028: 1053000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | BGDA | CONSTRUCTION | 1426000 | FY 2028: 1426000
HL-0115 | Highway | Locally Selected | NC 16 (North Broome Street) | North Church Street to NC 75. | Widen to three lanes, construct intersection improvements, construct sidewalks, and upgrade existing pedestrian facilities. | 0.38 | Union | 10 | Charlotte Regional TPO | $1.836M IN BGDA FUNDS SWITCHED WITH $1.836M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region E |  | L | CONSTRUCTION | 620000 | FY 2028: 620000
HL-0116 | Highway | Locally Selected | SR 1307 (Bonds Grove Church Road) | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | ENGINEERING | 350000
HL-0116 | Highway | Locally Selected | SR 1307 (Bonds Grove Church Road) | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 88000
HL-0116 | Highway | Locally Selected | SR 1307 (Bonds Grove Church Road) | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 476000 | FY 2026: 476000
HL-0116 | Highway | Locally Selected | SR 1307 (Bonds Grove Church Road) | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 119000 | FY 2026: 119000
HL-0116 | Highway | Locally Selected | SR 1307 (Bonds Grove Church Road) | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 3541000 | FY 2028: 35000; FY 2029: 2759000; FY 2030: 747000
HL-0116 | Highway | Locally Selected | SR 1307 (Bonds Grove Church Road) | SR 1301 (Waxhaw Marvin Road) intersection in Waxhaw. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 885000 | FY 2028: 885000
HL-0117 | Highway | Locally Selected | NC 218 | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | CMAQ | ENGINEERING | 140000
HL-0117 | Highway | Locally Selected | NC 218 | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | HF(M) | ENGINEERING | 60000
HL-0117 | Highway | Locally Selected | NC 218 | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | CMAQ | RIGHT-OF-WAY | 216000
HL-0117 | Highway | Locally Selected | NC 218 | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | HF(M) | RIGHT-OF-WAY | 92000
HL-0117 | Highway | Locally Selected | NC 218 | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | CMAQ | CONSTRUCTION | 1644000 | FY 2027: 941000; FY 2028: 703000
HL-0117 | Highway | Locally Selected | NC 218 | SR 1001 (Love Mill Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | HF(M) | CONSTRUCTION | 705000 | FY 2027: 404000; FY 2028: 301000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | T(DA) | ENGINEERING | 148000 | FY 2026: 148000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | L(M) | ENGINEERING | 37000 | FY 2026: 37000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | T(DA) | RIGHT-OF-WAY | 2168000 | FY 2028: 2168000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | L(M) | RIGHT-OF-WAY | 542000 | FY 2028: 542000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | L | RIGHT-OF-WAY | 1332000 | FY 2027: 1332000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | T(DA) | UTILITIES | 482000 | FY 2028: 482000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | L(M) | UTILITIES | 121000 | FY 2028: 121000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | T(DA) | CONSTRUCTION | 8461000 | FY 2029: 8461000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | L(M) | CONSTRUCTION | 2115000 | FY 2029: 2115000
HL-0118 | Highway | Locally Selected | Stumptown Road | Shepherds Road to NC 115; NC 115 to Aberfeld Road | Construct turn lanes, sidewalk, and pedestrian accommodations and upgrade signal. Construct turn lanes at NC 115 and Stumptown Road intersection in Huntersville; Construct road extension and new at-grade railroad crossing. | 0.154 | Mecklenburg | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23; $6.103M IN STBG-DA FUNDS SWAPPED FOR $6.103M IN STATE FUNDS ON 2-17-25. | Region E |  | L | CONSTRUCTION | 6297000 | FY 2029: 6297000
HL-0119 | Highway | Locally Selected | SR 1005 (Six Forks Road) | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Wake | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | BGDA | ENGINEERING | 23000
HL-0119 | Highway | Locally Selected | SR 1005 (Six Forks Road) | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Wake | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L(M) | ENGINEERING | 6000
HL-0119 | Highway | Locally Selected | SR 1005 (Six Forks Road) | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Wake | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L | ENGINEERING | 22000
HL-0119 | Highway | Locally Selected | SR 1005 (Six Forks Road) | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Wake | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | BGANY | CONSTRUCTION | 13999000 | FY 2026: 5737000; FY 2027: 4902000; FY 2028: 3220000
HL-0119 | Highway | Locally Selected | SR 1005 (Six Forks Road) | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Wake | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L(M) | CONSTRUCTION | 3500000
HL-0119 | Highway | Locally Selected | SR 1005 (Six Forks Road) | Rowan Street to SR 1827 (Lynn Road) in Raleigh. | Construct six-lane median divided avenue with sidewalks, separated bikeways, protected intersections, upgraded traffic signals and upgraded transit stops. | 1.69 | Wake | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L | CONSTRUCTION | 13499000 | FY 2026: 5532000; FY 2027: 4727000; FY 2028: 3105000
HL-0121 | Highway | Locally Selected | NC 50 | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | ENGINEERING | 213000
HL-0121 | Highway | Locally Selected | NC 50 | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF(M) | ENGINEERING | 53000
HL-0121 | Highway | Locally Selected | NC 50 | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 82000
HL-0121 | Highway | Locally Selected | NC 50 | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF(M) | RIGHT-OF-WAY | 21000
HL-0121 | Highway | Locally Selected | NC 50 | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 622000 | FY 2026: 622000
HL-0121 | Highway | Locally Selected | NC 50 | SR 1901 (Old Weaver Trail) intersection in Creedmoor. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF(M) | CONSTRUCTION | 156000 | FY 2026: 156000
HL-0122 | Highway | Locally Selected | NC 50 | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | ENGINEERING | 266000
HL-0122 | Highway | Locally Selected | NC 50 | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | ENGINEERING | 66000
HL-0122 | Highway | Locally Selected | NC 50 | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | RIGHT-OF-WAY | 150000
HL-0122 | Highway | Locally Selected | NC 50 | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | RIGHT-OF-WAY | 37000
HL-0122 | Highway | Locally Selected | NC 50 | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | CONSTRUCTION | 750000 | FY 2026: 750000
HL-0122 | Highway | Locally Selected | NC 50 | Mount Vernon Church Road intersection in Raleigh. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | CONSTRUCTION | 190000 | FY 2026: 190000
HL-0123 | Highway | Locally Selected | Various | Locations in Concord. | Upgrade software for Concord citywide signal system. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CRPDA | ENGINEERING | 800000
HL-0123 | Highway | Locally Selected | Various | Locations in Concord. | Upgrade software for Concord citywide signal system. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 200000
HL-0123 | Highway | Locally Selected | Various | Locations in Concord. | Upgrade software for Concord citywide signal system. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 400000 | FY 2026: 400000
HL-0123 | Highway | Locally Selected | Various | Locations in Concord. | Upgrade software for Concord citywide signal system. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 100000 | FY 2026: 100000
HL-0126 | Highway | Locally Selected | Lindley Road | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | ENGINEERING | 8000
HL-0126 | Highway | Locally Selected | Lindley Road | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 2000
HL-0126 | Highway | Locally Selected | Lindley Road | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | UTILITIES | 8000
HL-0126 | Highway | Locally Selected | Lindley Road | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 2000
HL-0126 | Highway | Locally Selected | Lindley Road | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 1843000 | FY 2026: 1843000
HL-0126 | Highway | Locally Selected | Lindley Road | SR 2147 (West Friendly Avenue) to SR 1546 (North College Road) in Greensboro. | Modernize roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 461000 | FY 2026: 461000
HL-0127 | Highway | Locally Selected | US 70 Business | SR 1553 (Shotwell Road) intersection in Clayton. | Construct intersection improvements. | 0.5 | Johnston | 4 | Capital Area MPO | HF(M) REPRESENTS HIGH-IMPACT LOW-COST FUNDS | Exempt |  | CRPDA | CONSTRUCTION | 4600000
HL-0127 | Highway | Locally Selected | US 70 Business | SR 1553 (Shotwell Road) intersection in Clayton. | Construct intersection improvements. | 0.5 | Johnston | 4 | Capital Area MPO | HF(M) REPRESENTS HIGH-IMPACT LOW-COST FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 1151000 | FY 2026: 216000
HL-0128 | Highway | Locally Selected | SR 1003 (Rolesville Road) | SR 2320 (Riley Hill Road) intersection in Wendell. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) FUNDING REPRESENTS SPOT MOBILITY FUNDS. | Division 5 |  | BGDA | ENGINEERING | 158000
HL-0128 | Highway | Locally Selected | SR 1003 (Rolesville Road) | SR 2320 (Riley Hill Road) intersection in Wendell. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) FUNDING REPRESENTS SPOT MOBILITY FUNDS. | Division 5 |  | HF(M) | ENGINEERING | 39000
HL-0128 | Highway | Locally Selected | SR 1003 (Rolesville Road) | SR 2320 (Riley Hill Road) intersection in Wendell. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) FUNDING REPRESENTS SPOT MOBILITY FUNDS. | Division 5 |  | BGDA | RIGHT-OF-WAY | 72000
HL-0128 | Highway | Locally Selected | SR 1003 (Rolesville Road) | SR 2320 (Riley Hill Road) intersection in Wendell. | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) FUNDING REPRESENTS SPOT MOBILITY FUNDS. | Division 5 |  | HF(M) | RIGHT-OF-WAY | 18000
HL-0129 | Highway | Locally Selected | SR 1552 (South Robertson Street / Amelia Church Road); SR 1004 (Main Street) | Kenmore Drive to SR 1004 (Main Street); SR 1552 (South Robertson Street) to South Moore Street in Clayton. | Install curb and gutter, construct sidewalks, and construct intersection improvements. |  | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TADA | ENGINEERING | 490000
HL-0129 | Highway | Locally Selected | SR 1552 (South Robertson Street / Amelia Church Road); SR 1004 (Main Street) | Kenmore Drive to SR 1004 (Main Street); SR 1552 (South Robertson Street) to South Moore Street in Clayton. | Install curb and gutter, construct sidewalks, and construct intersection improvements. |  | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 210000
HL-0129 | Highway | Locally Selected | SR 1552 (South Robertson Street / Amelia Church Road); SR 1004 (Main Street) | Kenmore Drive to SR 1004 (Main Street); SR 1552 (South Robertson Street) to South Moore Street in Clayton. | Install curb and gutter, construct sidewalks, and construct intersection improvements. |  | Johnston | 4 | Capital Area MPO |  | Division 4 |  | TADA | RIGHT-OF-WAY | 385000 | FY 2026: 385000
HL-0129 | Highway | Locally Selected | SR 1552 (South Robertson Street / Amelia Church Road); SR 1004 (Main Street) | Kenmore Drive to SR 1004 (Main Street); SR 1552 (South Robertson Street) to South Moore Street in Clayton. | Install curb and gutter, construct sidewalks, and construct intersection improvements. |  | Johnston | 4 | Capital Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 165000 | FY 2026: 165000
HL-0131 | Highway | Locally Selected | NC 133 | Belville Riverwalk Park entrance | Construct traffic signal and related pedestrian infrastructure |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 65000
HL-0131 | Highway | Locally Selected | NC 133 | Belville Riverwalk Park entrance | Construct traffic signal and related pedestrian infrastructure |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 16000
HL-0131 | Highway | Locally Selected | NC 133 | Belville Riverwalk Park entrance | Construct traffic signal and related pedestrian infrastructure |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1166000 | FY 2026: 1166000
HL-0131 | Highway | Locally Selected | NC 133 | Belville Riverwalk Park entrance | Construct traffic signal and related pedestrian infrastructure |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 292000 | FY 2026: 292000
HL-0132 | Highway | Locally Selected | Various | Locations in Shallotte | Install adaptive signal system in Shallotte. |  | Brunswick | 3 | Grand Strand Area Transportation Study | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS. | Division 3 |  | BGDA | CONSTRUCTION | 167000
HL-0132 | Highway | Locally Selected | Various | Locations in Shallotte | Install adaptive signal system in Shallotte. |  | Brunswick | 3 | Grand Strand Area Transportation Study | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS. | Division 3 |  | CRPDA | CONSTRUCTION | 151000
HL-0132 | Highway | Locally Selected | Various | Locations in Shallotte | Install adaptive signal system in Shallotte. |  | Brunswick | 3 | Grand Strand Area Transportation Study | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS. | Division 3 |  | HF(M) | CONSTRUCTION | 80000
HL-0133 | Highway | Locally Selected | Various | Wake County | Construct congestion and safety improvements at various locations in Wake County. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | BA | ENGINEERING | 2500000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (Main Street) | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region F |  | BGANY | ENGINEERING | 377000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (Main Street) | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region F |  | L | ENGINEERING | 203000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (Main Street) | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region F |  | BGANY | RIGHT-OF-WAY | 1028000 | FY 2027: 1028000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (Main Street) | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region F |  | L | RIGHT-OF-WAY | 554000 | FY 2027: 554000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (Main Street) | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region F |  | BGANY | CONSTRUCTION | 2142000 | FY 2029: 2142000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (Main Street) | Murdock Road / Old Mountain Road intersection in Troutman. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Region F |  | L | CONSTRUCTION | 1153000 | FY 2029: 1153000
HL-0135 | Highway | Locally Selected | SR 1315 (New Town Road) | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | BGANY | ENGINEERING | 285000
HL-0135 | Highway | Locally Selected | SR 1315 (New Town Road) | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | HF(M) | ENGINEERING | 122000
HL-0135 | Highway | Locally Selected | SR 1315 (New Town Road) | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | BGANY | RIGHT-OF-WAY | 313000 | FY 2026: 313000
HL-0135 | Highway | Locally Selected | SR 1315 (New Town Road) | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | HF(M) | RIGHT-OF-WAY | 134000 | FY 2026: 134000
HL-0135 | Highway | Locally Selected | SR 1315 (New Town Road) | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | BGANY | CONSTRUCTION | 2552000 | FY 2027: 2552000
HL-0135 | Highway | Locally Selected | SR 1315 (New Town Road) | Cuthbertson Road intersection in Wesley Chapel | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | L(M) | CONSTRUCTION | 1094000 | FY 2027: 1094000
HL-0137 | Highway | Locally Selected | WT Harris Boulevard | Sugar Creek intersection in Charlotte | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | BGANY | ENGINEERING | 7000
HL-0137 | Highway | Locally Selected | WT Harris Boulevard | Sugar Creek intersection in Charlotte | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | L | ENGINEERING | 3000
HL-0137 | Highway | Locally Selected | WT Harris Boulevard | Sugar Creek intersection in Charlotte | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | BGANY | CONSTRUCTION | 1331000 | FY 2028: 1331000
HL-0137 | Highway | Locally Selected | WT Harris Boulevard | Sugar Creek intersection in Charlotte | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | L | CONSTRUCTION | 570000 | FY 2028: 570000
HL-0138 | Highway | Locally Selected | Brown-Grier Road; Sandy Porter Road | NC 160 to I-485; William Glen to Brown-Grier Road | Improve corridors. |  | Mecklenburg | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | BGANY | ENGINEERING | 4000
HL-0138 | Highway | Locally Selected | Brown-Grier Road; Sandy Porter Road | NC 160 to I-485; William Glen to Brown-Grier Road | Improve corridors. |  | Mecklenburg | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | L | ENGINEERING | 6000
HL-0138 | Highway | Locally Selected | Brown-Grier Road; Sandy Porter Road | NC 160 to I-485; William Glen to Brown-Grier Road | Improve corridors. |  | Mecklenburg | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | BGANY | CONSTRUCTION | 11113000 | FY 2027: 11113000
HL-0138 | Highway | Locally Selected | Brown-Grier Road; Sandy Porter Road | NC 160 to I-485; William Glen to Brown-Grier Road | Improve corridors. |  | Mecklenburg | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 12-12-24. | Division 10 |  | L | CONSTRUCTION | 20638000 | FY 2027: 20638000
HL-0139 | Highway | Locally Selected | Indian Trail | Crooked Creek Park, Chestnut Square Park, and Crossing Paths Park in Indian Trail. | Install Level 2 electric vehicle chargers. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | ENGINEERING | 4000
HL-0139 | Highway | Locally Selected | Indian Trail | Crooked Creek Park, Chestnut Square Park, and Crossing Paths Park in Indian Trail. | Install Level 2 electric vehicle chargers. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L | ENGINEERING | 1000
HL-0139 | Highway | Locally Selected | Indian Trail | Crooked Creek Park, Chestnut Square Park, and Crossing Paths Park in Indian Trail. | Install Level 2 electric vehicle chargers. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | CONSTRUCTION | 627000 | FY 2026: 627000
HL-0139 | Highway | Locally Selected | Indian Trail | Crooked Creek Park, Chestnut Square Park, and Crossing Paths Park in Indian Trail. | Install Level 2 electric vehicle chargers. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 157000 | FY 2026: 157000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 8000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 2000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 1600000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 400000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | UTILITIES | 400000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | UTILITIES | 100000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 5672000 | FY 2026: 5672000
HL-0140 | Highway | Locally Selected | SR 5220 (Jones Sausage Road) | SR 1004 (East Garner Road) to Southern Boundary of Amazon Fulfillment Center | Widen roadway to 4-lane divided facility. | 0.6 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 1418000 | FY 2026: 1418000
HL-0141 | Highway | Locally Selected | SR 2765 (Old Honeycutt Road) | Intersection of Old Honeycutt Road and Kennebec Road (SR 2754) | Provide signalization at the intersection. Add curb, gutter, sidewalk and ADA ramps. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 12000
HL-0141 | Highway | Locally Selected | SR 2765 (Old Honeycutt Road) | Intersection of Old Honeycutt Road and Kennebec Road (SR 2754) | Provide signalization at the intersection. Add curb, gutter, sidewalk and ADA ramps. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 3000
HL-0141 | Highway | Locally Selected | SR 2765 (Old Honeycutt Road) | Intersection of Old Honeycutt Road and Kennebec Road (SR 2754) | Provide signalization at the intersection. Add curb, gutter, sidewalk and ADA ramps. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 970000
HL-0141 | Highway | Locally Selected | SR 2765 (Old Honeycutt Road) | Intersection of Old Honeycutt Road and Kennebec Road (SR 2754) | Provide signalization at the intersection. Add curb, gutter, sidewalk and ADA ramps. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 242000
HL-0142 | Highway | Locally Selected | US 401 / NC 211 | Various locations along routes in Raeford | Install and maintain 5 electric vehicle DC fast chargers. |  | Hoke | 8 | Fayetteville Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 40000
HL-0142 | Highway | Locally Selected | US 401 / NC 211 | Various locations along routes in Raeford | Install and maintain 5 electric vehicle DC fast chargers. |  | Hoke | 8 | Fayetteville Area MPO |  | Exempt |  | L(M) | ENGINEERING | 10000
HL-0142 | Highway | Locally Selected | US 401 / NC 211 | Various locations along routes in Raeford | Install and maintain 5 electric vehicle DC fast chargers. |  | Hoke | 8 | Fayetteville Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 464000 | FY 2026: 464000
HL-0142 | Highway | Locally Selected | US 401 / NC 211 | Various locations along routes in Raeford | Install and maintain 5 electric vehicle DC fast chargers. |  | Hoke | 8 | Fayetteville Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 116000 | FY 2026: 116000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | ENGINEERING | 60000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | ENGINEERING | 15000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2026: 160000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | RIGHT-OF-WAY | 40000 | FY 2026: 40000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | UTILITIES | 80000 | FY 2026: 80000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | UTILITIES | 20000 | FY 2026: 20000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | CONSTRUCTION | 280000 | FY 2028: 280000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 intersection in Fayetteville | Upgrade existing traffic signals with pedestrian improvements. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | CONSTRUCTION | 70000 | FY 2028: 70000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | ENGINEERING | 160000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | ENGINEERING | 40000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2026: 80000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | UTILITIES | 120000 | FY 2026: 120000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | UTILITIES | 30000 | FY 2026: 30000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | CONSTRUCTION | 720000 | FY 2027: 720000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (David Parnell Street) and SR 1725 (North Fayetteville Street) intersections in Parkton | Construct intersection improvements. |  | Robeson | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | CONSTRUCTION | 180000 | FY 2027: 180000
HL-0145 | Highway | Locally Selected | SR 1112 (Rockfish Road) | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 200000
HL-0145 | Highway | Locally Selected | SR 1112 (Rockfish Road) | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | ENGINEERING | 50000
HL-0145 | Highway | Locally Selected | SR 1112 (Rockfish Road) | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2026: 80000
HL-0145 | Highway | Locally Selected | SR 1112 (Rockfish Road) | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HL-0145 | Highway | Locally Selected | SR 1112 (Rockfish Road) | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 2202000 | FY 2028: 2202000
HL-0145 | Highway | Locally Selected | SR 1112 (Rockfish Road) | Near Rockfish Elementary School | Construct additional right turn lane on SR 1112 (Rockfish Road). |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | CONSTRUCTION | 550000 | FY 2028: 550000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 400000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | ENGINEERING | 100000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 128000 | FY 2026: 128000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | RIGHT-OF-WAY | 32000 | FY 2026: 32000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | UTILITIES | 240000 | FY 2026: 240000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | UTILITIES | 60000 | FY 2026: 60000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 2000000 | FY 2028: 2000000
HL-0146 | Highway | Locally Selected | SR 1115 (Buffalo Lake Road) | SR 1141 (Alpine Drive) intersection north of Spout Springs | Construct roundabout. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | CONSTRUCTION | 500000 | FY 2028: 500000
HL-0152 | Highway | Locally Selected | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | CRPDA | ENGINEERING | 686000
HL-0152 | Highway | Locally Selected | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | L | ENGINEERING | 171000
HL-0152 | Highway | Locally Selected | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | CRPANY | CONSTRUCTION | 834000 | FY 2027: 834000
HL-0152 | Highway | Locally Selected | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | BGDA | CONSTRUCTION | 965000 | FY 2027: 965000
HL-0152 | Highway | Locally Selected | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | CRPDA | CONSTRUCTION | 1433000 | FY 2027: 1433000
HL-0152 | Highway | Locally Selected | NC 27 (Mt Holly Road); Mt. Holly-Huntersville Road | I-485 to Mt. Holly-Huntersville Road; NC 27 (Mt. Holly Road) to Hardwood Lane | Install ITS infrastructure, improve traffic flow, upgrade and add signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | $834K IN CRPDA FUNDS SWITCHED WITH $834K IN CRPANY FUNDS AS PART OF FUND SWAP 12-12-24. | Exempt |  | L | CONSTRUCTION | 808000 | FY 2027: 808000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 10000 | FY 2026: 10000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 3000 | FY 2026: 3000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 3000 | FY 2026: 3000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 10000 | FY 2026: 10000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | UTILITIES | 3000 | FY 2026: 3000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1180000 | FY 2027: 1180000
HL-0153 | Highway | Locally Selected | Sullivantown Road | Intersection of US 311; SR 2004 (Main Street) and US 311 (Harley Drive) | Convert Sullivantown Road to one-way traffic |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 295000 | FY 2027: 295000
HL-0154 | Highway | Locally Selected | US 421 (Salem Parkway) | Silas Creek Parkway to Martin Luther King Jr Drive | Replace existing lighting with LED lighting |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | ENGINEERING | 32000
HL-0154 | Highway | Locally Selected | US 421 (Salem Parkway) | Silas Creek Parkway to Martin Luther King Jr Drive | Replace existing lighting with LED lighting |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 8000
HL-0154 | Highway | Locally Selected | US 421 (Salem Parkway) | Silas Creek Parkway to Martin Luther King Jr Drive | Replace existing lighting with LED lighting |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 768000 | FY 2026: 768000
HL-0154 | Highway | Locally Selected | US 421 (Salem Parkway) | Silas Creek Parkway to Martin Luther King Jr Drive | Replace existing lighting with LED lighting |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 192000 | FY 2026: 192000
HL-0155 | Highway | Locally Selected | (New Route) Highland School Road | SR 1115 (Buffalo Lake Road) to SR 1139 (Tingen Road) south of Highland Elementary and Middle School campuses | Construct two-lane minor thoroughfare partially on new ground. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | T(DA) | ENGINEERING | 320000
HL-0155 | Highway | Locally Selected | (New Route) Highland School Road | SR 1115 (Buffalo Lake Road) to SR 1139 (Tingen Road) south of Highland Elementary and Middle School campuses | Construct two-lane minor thoroughfare partially on new ground. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 80000
HL-0155 | Highway | Locally Selected | (New Route) Highland School Road | SR 1115 (Buffalo Lake Road) to SR 1139 (Tingen Road) south of Highland Elementary and Middle School campuses | Construct two-lane minor thoroughfare partially on new ground. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | T(DA) | CONSTRUCTION | 2463000 | FY 2028: 2463000
HL-0155 | Highway | Locally Selected | (New Route) Highland School Road | SR 1115 (Buffalo Lake Road) to SR 1139 (Tingen Road) south of Highland Elementary and Middle School campuses | Construct two-lane minor thoroughfare partially on new ground. |  | Harnett | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 616000 | FY 2028: 616000
HL-0156 | Highway | Locally Selected | Various | Locations in Chatham County. | Purchase and install two electric vehicle charging stations. |  | Chatham | 8 | Triangle West TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 213000 | FY 2026: 213000
HL-0156 | Highway | Locally Selected | Various | Locations in Chatham County. | Purchase and install two electric vehicle charging stations. |  | Chatham | 8 | Triangle West TPO |  | Exempt |  | L(M) | CONSTRUCTION | 53000 | FY 2026: 53000
HL-0157 | Highway | Locally Selected | I-85 | SR 1430 (George Liles Parkway) Interchange in Concord. | Install lighting at interchange. | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | BGDA | CONSTRUCTION | 800000
HL-0157 | Highway | Locally Selected | I-85 | SR 1430 (George Liles Parkway) Interchange in Concord. | Install lighting at interchange. | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 133000
HL-0157 | Highway | Locally Selected | I-85 | SR 1430 (George Liles Parkway) Interchange in Concord. | Install lighting at interchange. | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Exempt |  | HF(M) | CONSTRUCTION | 67000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | T(DA) | ENGINEERING | 5000 | FY 2026: 5000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 5000 | FY 2026: 5000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | L | ENGINEERING | 750000 | FY 2026: 750000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 848000 | FY 2027: 848000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 848000 | FY 2027: 848000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | T(DA) | UTILITIES | 5000 | FY 2027: 5000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | UTILITIES | 5000 | FY 2027: 5000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | T(DA) | CONSTRUCTION | 4065000 | FY 2029: 4065000
HL-0158 | Highway | Locally Selected | Waxhaw Parkway West | SR 1307 (Waxhaw-Marvin Road) to NC 16 in Waxhaw. | Extend roadway. | 1 | Union | 10 | Charlotte Regional TPO | HELMS ROAD EXTENSION PROJECT. $4.923M IN BGDA FUNDS SWITCHED WITH $4.923M IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 4065000 | FY 2029: 4065000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | ENGINEERING | 162000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 41000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 29000 | FY 2026: 29000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 7000 | FY 2026: 7000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | UTILITIES | 80000 | FY 2026: 80000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | UTILITIES | 20000 | FY 2026: 20000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | CONSTRUCTION | 1342000 | FY 2028: 1342000
HL-0159 | Highway | Locally Selected | US 74 | Marshville Lake Park Intersection in Marshville. | Construct right turn lanes. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 335000 | FY 2028: 335000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 1124000 | FY 2027: 1124000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | ENGINEERING | 1124000 | FY 2027: 1124000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 283000 | FY 2029: 283000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 283000 | FY 2029: 283000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | UTILITIES | 76000 | FY 2029: 76000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | UTILITIES | 76000 | FY 2029: 76000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 3749000 | FY 2031: 3749000
HL-0160 | Highway | Locally Selected | Indian Trail-Fairview Road | SR 1519 (Younts Road) and SR 1522 (Stinson Hartis Road) intersections in Indian Trail. | Improve intersections. | 0.2 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 3749000 | FY 2031: 3749000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | BGDA | ENGINEERING | 298000 | FY 2026: 298000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | L(M) | ENGINEERING | 298000 | FY 2026: 298000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | BGDA | RIGHT-OF-WAY | 19000 | FY 2028: 19000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | L(M) | RIGHT-OF-WAY | 19000 | FY 2028: 19000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | BGDA | UTILITIES | 5000 | FY 2028: 5000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | L(M) | UTILITIES | 5000 | FY 2028: 5000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | BGDA | CONSTRUCTION | 1583000 | FY 2029: 1583000
HL-0161 | Highway | Locally Selected | NC 16 | SR 2373 (Rozzelles Ferry Road) Intersection in Charlotte. | Improve intersection. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | L(M) | CONSTRUCTION | 1583000 | FY 2029: 1583000
HL-0162 | Highway | Locally Selected | SR 2137 (Ervin Cook Road) | South Birkdale Commons Parkway to Whitaker Pointe Drive. | Extend roadway. Construct roundabout at Whitaker Pointe Drive and South Birkdale Commons Parkway. | 0.4 | Mecklenburg | 10 | Charlotte Regional TPO | $406K IN BGDA FUNDS SWITCHED WITH $406K IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | T(DA) | ENGINEERING | 406000 | FY 2026: 406000
HL-0162 | Highway | Locally Selected | SR 2137 (Ervin Cook Road) | South Birkdale Commons Parkway to Whitaker Pointe Drive. | Extend roadway. Construct roundabout at Whitaker Pointe Drive and South Birkdale Commons Parkway. | 0.4 | Mecklenburg | 10 | Charlotte Regional TPO | $406K IN BGDA FUNDS SWITCHED WITH $406K IN T(DA) FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 406000 | FY 2026: 406000
HL-0163 | Highway | Locally Selected | NC 27 (Freedom Drive); Eastway Drive | Valerie C. Woodard Center and Ella B. Scarborough Community Resource Center. | Install electric vehicle fast charging stations. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | ENGINEERING | 40000 | FY 2027: 40000
HL-0163 | Highway | Locally Selected | NC 27 (Freedom Drive); Eastway Drive | Valerie C. Woodard Center and Ella B. Scarborough Community Resource Center. | Install electric vehicle fast charging stations. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 10000 | FY 2027: 10000
HL-0163 | Highway | Locally Selected | NC 27 (Freedom Drive); Eastway Drive | Valerie C. Woodard Center and Ella B. Scarborough Community Resource Center. | Install electric vehicle fast charging stations. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 92000 | FY 2027: 92000
HL-0163 | Highway | Locally Selected | NC 27 (Freedom Drive); Eastway Drive | Valerie C. Woodard Center and Ella B. Scarborough Community Resource Center. | Install electric vehicle fast charging stations. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 535000 | FY 2027: 535000
HL-0163 | Highway | Locally Selected | NC 27 (Freedom Drive); Eastway Drive | Valerie C. Woodard Center and Ella B. Scarborough Community Resource Center. | Install electric vehicle fast charging stations. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 157000 | FY 2027: 157000
HL-0164 | Highway | Locally Selected | SR 1001 (Church Street) | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS. | Division 7 |  | HF | ENGINEERING | 500000
HL-0164 | Highway | Locally Selected | SR 1001 (Church Street) | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS. | Division 7 |  | HSIP | RIGHT-OF-WAY | 400000 | FY 2027: 400000
HL-0164 | Highway | Locally Selected | SR 1001 (Church Street) | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS. | Division 7 |  | T(DA) | RIGHT-OF-WAY | 139000 | FY 2027: 139000
HL-0164 | Highway | Locally Selected | SR 1001 (Church Street) | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS. | Division 7 |  | HF | RIGHT-OF-WAY | 211000 | FY 2027: 211000
HL-0164 | Highway | Locally Selected | SR 1001 (Church Street) | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS. | Division 7 |  | T(DA) | UTILITIES | 750000 | FY 2027: 750000
HL-0164 | Highway | Locally Selected | SR 1001 (Church Street) | Old Lake Janette Road intersection. | Construct Roundabout. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | "HF" FUNDS REPRESENT HIGH IMPACT / LOW COST FUNDS. | Division 7 |  | T(DA) | CONSTRUCTION | 2750000 | FY 2028: 2750000
HL-0165 | Highway | Locally Selected | Various Routes | in Greensboro | Upgrade signal system, Phase 1. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | ENGINEERING | 287000 | FY 2026: 287000
HL-0165 | Highway | Locally Selected | Various Routes | in Greensboro | Upgrade signal system, Phase 1. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(DA) | ENGINEERING | 481000 | FY 2026: 481000
HL-0165 | Highway | Locally Selected | Various Routes | in Greensboro | Upgrade signal system, Phase 1. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 107000 | FY 2026: 107000
HL-0165 | Highway | Locally Selected | Various Routes | in Greensboro | Upgrade signal system, Phase 1. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 674000 | FY 2027: 674000
HL-0165 | Highway | Locally Selected | Various Routes | in Greensboro | Upgrade signal system, Phase 1. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(DA) | CONSTRUCTION | 1130000 | FY 2027: 1130000
HL-0165 | Highway | Locally Selected | Various Routes | in Greensboro | Upgrade signal system, Phase 1. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 251000 | FY 2027: 251000
HL-0168 | Highway | Locally Selected | Murrow Boulevard | Bridge #400462 | Rehabilitate bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 4672000 | FY 2026: 4672000
HL-0168 | Highway | Locally Selected | Murrow Boulevard | Bridge #400462 | Rehabilitate bridge. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 1168000 | FY 2026: 1168000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | BGDA | ENGINEERING | 169000 | FY 2026: 169000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | HF | ENGINEERING | 127000 | FY 2026: 127000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | HF(M) | ENGINEERING | 42000 | FY 2026: 42000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | BGDA | RIGHT-OF-WAY | 17000 | FY 2026: 17000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | HF | RIGHT-OF-WAY | 13000 | FY 2026: 13000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | HF(M) | RIGHT-OF-WAY | 4000 | FY 2026: 4000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | BGDA | UTILITIES | 5000 | FY 2026: 5000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | HF(M) | UTILITIES | 1000 | FY 2026: 1000
HL-0170 | Highway | Locally Selected | Ten-Ten Road | US 401 to East of Topans Drive | Widen to 2 eastbound lanes. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT SAFETY FUNDS | Division 5 |  | HF | UTILITIES | 4000 | FY 2026: 4000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | BGDA | ENGINEERING | 229000 | FY 2026: 229000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | HF(M) | ENGINEERING | 57000 | FY 2026: 57000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | HF | ENGINEERING | 95000 | FY 2026: 95000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | BGDA | RIGHT-OF-WAY | 516000 | FY 2026: 516000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | HF(M) | RIGHT-OF-WAY | 129000 | FY 2026: 129000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | HF | RIGHT-OF-WAY | 215000 | FY 2026: 215000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | BGDA | UTILITIES | 6000 | FY 2026: 6000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | HF(M) | UTILITIES | 2000 | FY 2026: 2000
HL-0171 | Highway | Locally Selected | NC 42 | Piney Grove Wilbon | Construct left turn lanes on all four approaches. |  | Wake | 5 | Capital Area MPO | HF FUNDS REPRESENT SPOT MOBILITY FUNDS | Division 5 |  | HF | UTILITIES | 2000 | FY 2026: 2000
HL-0172 | Highway | Locally Selected | Bowling Road | South Main Street | Operational improvements. Install traffic signal, curb and gutter, sidepath, and ADA-compliant ramps. |  | Wake | 5 | Capital Area MPO |  | Division 5
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 502000 | FY 2026: 502000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 125000 | FY 2026: 125000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 145000 | FY 2026: 145000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 324000 | FY 2026: 324000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 81000 | FY 2026: 81000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 93000 | FY 2026: 93000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | UTILITIES | 6000 | FY 2026: 6000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | UTILITIES | 2000 | FY 2026: 2000
HL-0173 | Highway | Locally Selected | Olive Chapel Road | Apex Barbecue Road | Add westbound turn lane, signalize, realign curve, complete sidewalk gap, and add pedestrian accomodations at intersection. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | UTILITIES | 2000 | FY 2026: 2000
HL-0174 | Highway | Locally Selected | Holly Springs Road | NC 55 to North Main Street | Widen to four lane divided facility with bike/ped accommodations. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 2400000 | FY 2026: 2400000
HL-0174 | Highway | Locally Selected | Holly Springs Road | NC 55 to North Main Street | Widen to four lane divided facility with bike/ped accommodations. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 600000 | FY 2026: 600000
HL-0175 | Highway | Locally Selected | Airport Road | Thorne Road to Knoll Road in Southern Pines | Improve roadway. |  | Moore | 8 | Sandhills MPO |  | Exempt |  | CRPDA | ENGINEERING | 234000 | FY 2026: 234000
HL-0175 | Highway | Locally Selected | Airport Road | Thorne Road to Knoll Road in Southern Pines | Improve roadway. |  | Moore | 8 | Sandhills MPO |  | Exempt |  | L(M) | ENGINEERING | 59000 | FY 2026: 59000
HL-0176 | Highway | Locally Selected | McCanless Road | I-85 | Construct interchange ramps. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | BGDA | ENGINEERING | 3286000 | FY 2026: 3286000
HL-0176 | Highway | Locally Selected | McCanless Road | I-85 | Construct interchange ramps. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 822000 | FY 2026: 822000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGDA | ENGINEERING | 224000 | FY 2026: 224000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | HF(M) | ENGINEERING | 56000 | FY 2026: 56000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGDA | RIGHT-OF-WAY | 240000 | FY 2027: 240000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | HF(M) | RIGHT-OF-WAY | 60000 | FY 2027: 60000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGDA | UTILITIES | 113000 | FY 2027: 113000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | HF(M) | UTILITIES | 29000 | FY 2027: 29000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGDA | CONSTRUCTION | 1448000 | FY 2029: 1448000
HL-0177 | Highway | Locally Selected | NC 3 | SR 1442 (Windy Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | HF(M) REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | HF(M) | CONSTRUCTION | 362000 | FY 2029: 362000
HL-0178 | Highway | Locally Selected | SR 1431 (Weddington Road) | SR 1414 (Rock Hill Church Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDA | ENGINEERING | 8000 | FY 2026: 8000
HL-0178 | Highway | Locally Selected | SR 1431 (Weddington Road) | SR 1414 (Rock Hill Church Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | ENGINEERING | 2000 | FY 2026: 2000
HL-0178 | Highway | Locally Selected | SR 1431 (Weddington Road) | SR 1414 (Rock Hill Church Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDA | CONSTRUCTION | 2392000 | FY 2027: 2392000
HL-0178 | Highway | Locally Selected | SR 1431 (Weddington Road) | SR 1414 (Rock Hill Church Road) intersection in Concord | Construct roundabout | 0.1 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 598000 | FY 2027: 598000
HL-0179 | Highway | Locally Selected | SR 1438 (Lanvale Road) | SR 1472 (Fletcher road / village road) intersection in Leland | Install traffic signal. |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 35000 | FY 2026: 35000
HL-0179 | Highway | Locally Selected | SR 1438 (Lanvale Road) | SR 1472 (Fletcher road / village road) intersection in Leland | Install traffic signal. |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HF(M) | ENGINEERING | 9000 | FY 2026: 9000
HL-0179 | Highway | Locally Selected | SR 1438 (Lanvale Road) | SR 1472 (Fletcher road / village road) intersection in Leland | Install traffic signal. |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 1465000 | FY 2028: 1465000
HL-0179 | Highway | Locally Selected | SR 1438 (Lanvale Road) | SR 1472 (Fletcher road / village road) intersection in Leland | Install traffic signal. |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HF | CONSTRUCTION | 3500000 | FY 2028: 3500000
HL-0179 | Highway | Locally Selected | SR 1438 (Lanvale Road) | SR 1472 (Fletcher road / village road) intersection in Leland | Install traffic signal. |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HF(M) | CONSTRUCTION | 365000 | FY 2028: 365000
HL-0180 | Highway | Locally Selected | SR 1563 (Sloop Point Road) | SR 1565 (Country Club Drive) intersection in Hampstead. | Install traffic signal. |  | Pender | 3 | Wilmington Urban Area MPO |  | Division 3
HL-0181 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Federal Point Shopping Center Driveway intersection north of Bennet Lane in Carolina Beach. | Install traffic signal. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B
HM-0002 | Highway | Municipal Bridge | Shelley Road | Bridge 910378 over Mine Creek from Shadowbrook Drive to Forest Lawn Court. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | RIGHT-OF-WAY | 300000 | FY 2026: 300000
HM-0002 | Highway | Municipal Bridge | Shelley Road | Bridge 910378 over Mine Creek from Shadowbrook Drive to Forest Lawn Court. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | UTILITIES | 250000 | FY 2026: 250000
HM-0002 | Highway | Municipal Bridge | Shelley Road | Bridge 910378 over Mine Creek from Shadowbrook Drive to Forest Lawn Court. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | CONSTRUCTION | 2500000 | FY 2026: 2125000; FY 2027: 375000
HM-0003 | Highway | Municipal Bridge | Cheswick Drive | Bridge 910627 over Big Branch connecting Oakland Drive to Cheswick Drive. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | ENGINEERING | 500000
HM-0003 | Highway | Municipal Bridge | Cheswick Drive | Bridge 910627 over Big Branch connecting Oakland Drive to Cheswick Drive. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | RIGHT-OF-WAY | 250000
HM-0003 | Highway | Municipal Bridge | Cheswick Drive | Bridge 910627 over Big Branch connecting Oakland Drive to Cheswick Drive. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | UTILITIES | 250000
HM-0003 | Highway | Municipal Bridge | Cheswick Drive | Bridge 910627 over Big Branch connecting Oakland Drive to Cheswick Drive. | Replace bridge. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | CONSTRUCTION | 1250000 | FY 2026: 328000
HM-0004 | Highway | Municipal Bridge | Old Greensboro Road | Bridge 330330 over Brushy Fork Creek | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | ENGINEERING | 1240000 | FY 2026: 1240000
HM-0004 | Highway | Municipal Bridge | Old Greensboro Road | Bridge 330330 over Brushy Fork Creek | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | RIGHT-OF-WAY | 300000 | FY 2027: 300000
HM-0004 | Highway | Municipal Bridge | Old Greensboro Road | Bridge 330330 over Brushy Fork Creek | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | UTILITIES | 475000 | FY 2027: 475000
HM-0004 | Highway | Municipal Bridge | Old Greensboro Road | Bridge 330330 over Brushy Fork Creek | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | CONSTRUCTION | 2800000 | FY 2028: 2800000
HM-9999 | Highway | Bridges | Various | Locations statewide | Municipal bridge inspection program. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BGOFF | IMPLEMENTATION | 13000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2000000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | SR 2697 (New Hope Road) | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 129000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | SR 2697 (New Hope Road) | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T | ENGINEERING | 32000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | SR 2697 (New Hope Road) | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000 | FY 2028: 50000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | SR 2697 (New Hope Road) | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T | RIGHT-OF-WAY | 13000 | FY 2028: 13000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | SR 2697 (New Hope Road) | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 541000 | FY 2029: 348000; FY 2030: 193000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | SR 2697 (New Hope Road) | Eva Mae Drive intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T | CONSTRUCTION | 135000 | FY 2029: 87000; FY 2030: 48000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | SR 1306 (Erwin Road) | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | ENGINEERING | 206000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | SR 1306 (Erwin Road) | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | T(M) | ENGINEERING | 52000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | SR 1306 (Erwin Road) | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 96000 | FY 2026: 96000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | SR 1306 (Erwin Road) | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 24000 | FY 2026: 24000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | SR 1306 (Erwin Road) | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 960000 | FY 2027: 960000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | SR 1306 (Erwin Road) | SR 1308 (Cornwallis Road) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | T(M) | CONSTRUCTION | 240000 | FY 2027: 240000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | SR 1121 (Cornwallis Road) | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | ENGINEERING | 198000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | SR 1121 (Cornwallis Road) | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | HF(M) | ENGINEERING | 50000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | SR 1121 (Cornwallis Road) | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 16000 | FY 2026: 16000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | SR 1121 (Cornwallis Road) | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | HF(M) | RIGHT-OF-WAY | 4000 | FY 2026: 4000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | SR 1121 (Cornwallis Road) | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 696000 | FY 2027: 696000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | SR 1121 (Cornwallis Road) | SR 1945 (Alston Avenue) intersection in Durham. | Construct turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Exempt |  | HF(M) | CONSTRUCTION | 174000 | FY 2027: 174000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | CRPLT5 | ENGINEERING | 560000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | ENGINEERING | 140000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | CMAQ | RIGHT-OF-WAY | 125000 | FY 2026: 125000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 31000 | FY 2026: 31000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | CMAQ | CONSTRUCTION | 1556000 | FY 2027: 611000; FY 2028: 945000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | SR 1611 (Dorsey Road) intersection. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | CONSTRUCTION | 389000 | FY 2027: 153000; FY 2028: 236000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | US 70 (Glenwood Avenue) | Cole Street / Wade Avenue eastbound ramps intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | CMAQ | ENGINEERING | 99000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | US 70 (Glenwood Avenue) | Cole Street / Wade Avenue eastbound ramps intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 25000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | US 70 (Glenwood Avenue) | Cole Street / Wade Avenue eastbound ramps intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | CMAQ | CONSTRUCTION | 208000 | FY 2026: 208000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | US 70 (Glenwood Avenue) | Cole Street / Wade Avenue eastbound ramps intersection in Raleigh. | Construct turn lanes. | 0.5 | Wake | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 52000 | FY 2026: 52000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Granville | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | CMAQ | ENGINEERING | 354000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Granville | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | HF(M) | ENGINEERING | 88000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Granville | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | CMAQ | RIGHT-OF-WAY | 112000 | FY 2026: 112000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Granville | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 28000 | FY 2026: 28000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Granville | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 1309000 | FY 2027: 1309000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | SR 1129 (Hester Road) intersection in Creedmoor. | Construct roundabout. | 0.5 | Granville | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 327000 | FY 2027: 327000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | SR 1001 (Pearces Road) | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 94000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | SR 1001 (Pearces Road) | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T | ENGINEERING | 24000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | SR 1001 (Pearces Road) | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 32000 | FY 2026: 32000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | SR 1001 (Pearces Road) | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T | RIGHT-OF-WAY | 8000 | FY 2026: 8000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | SR 1001 (Pearces Road) | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1120000 | FY 2027: 560000; FY 2028: 560000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | SR 1001 (Pearces Road) | SR 2320 (Proctor Street) intersection in Zebulon. | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Exempt |  | T | CONSTRUCTION | 280000 | FY 2027: 140000; FY 2028: 140000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | CRP550 | ENGINEERING | 520000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | T(M) | ENGINEERING | 130000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | CRP550 | RIGHT-OF-WAY | 2640000 | FY 2026: 2640000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | T(M) | RIGHT-OF-WAY | 660000 | FY 2026: 660000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | CRP550 | UTILITIES | 200000 | FY 2026: 200000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | T(M) | UTILITIES | 50000 | FY 2026: 50000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | CRP550 | CONSTRUCTION | 4800000 | FY 2026: 4800000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64 / US 74A | North Washington Street Intersection in Rutherfordton. | Construct roundabout. | 0.5 | Rutherford | 13 | Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 1200000 | FY 2026: 1200000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | ENGINEERING | 371000 | FY 2026: 45000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | ENGINEERING | 91000 | FY 2026: 9000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | RIGHT-OF-WAY | 320000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 80000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | UTILITIES | 40000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | UTILITIES | 10000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | CONSTRUCTION | 2720000 | FY 2026: 598000; FY 2027: 2122000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | SR 1312 (Oxendine School Road / Red Hill Road) in Maxton. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | CONSTRUCTION | 680000 | FY 2026: 150000; FY 2027: 530000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPLT5 | ENGINEERING | 486000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | ENGINEERING | 122000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPLT5 | RIGHT-OF-WAY | 120000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | RIGHT-OF-WAY | 30000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPLT5 | UTILITIES | 144000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | UTILITIES | 36000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPLT5 | CONSTRUCTION | 2960000 | FY 2026: 1391000; FY 2027: 1569000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | NC 904 intersection in Fairmont. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | CONSTRUCTION | 740000 | FY 2026: 392000; FY 2027: 348000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 Business (Madison Street) | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPANY | ENGINEERING | 320000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 Business (Madison Street) | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | ENGINEERING | 80000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 Business (Madison Street) | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPANY | RIGHT-OF-WAY | 80000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 Business (Madison Street) | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | RIGHT-OF-WAY | 20000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 Business (Madison Street) | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | CRPANY | CONSTRUCTION | 1760000 | FY 2026: 510000; FY 2027: 1250000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 Business (Madison Street) | SR 1916 (Lee Street) and SR 1953 (Franklin Street) intersection in Whiteville. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | CONSTRUCTION | 440000 | FY 2026: 128000; FY 2027: 312000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | SR 1120 (Veazey Road) | SR 1239 (Central Avenue) and SR 1174 (Westbrook Drive) intersection in Butner. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Exempt |  | CRPLT5 | ENGINEERING | 560000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | SR 1120 (Veazey Road) | SR 1239 (Central Avenue) and SR 1174 (Westbrook Drive) intersection in Butner. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Exempt |  | L(M) | ENGINEERING | 107000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | SR 1120 (Veazey Road) | SR 1239 (Central Avenue) and SR 1174 (Westbrook Drive) intersection in Butner. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Exempt |  | T(M) | ENGINEERING | 33000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | SR 1120 (Veazey Road) | SR 1239 (Central Avenue) and SR 1174 (Westbrook Drive) intersection in Butner. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Exempt |  | CRPLT5 | CONSTRUCTION | 1607000 | FY 2026: 1607000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | SR 1120 (Veazey Road) | SR 1239 (Central Avenue) and SR 1174 (Westbrook Drive) intersection in Butner. | Construct roundabout. | 0.5 | Granville | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 402000 | FY 2026: 402000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | CRPLT5 | ENGINEERING | 220000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | ENGINEERING | 55000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | CRPLT5 | UTILITIES | 16000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | UTILITIES | 4000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | CRPLT5 | CONSTRUCTION | 1900000 | FY 2026: 1881000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | NC 211 Bypass intersection in Bladenboro. | Construct roundabout. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | CONSTRUCTION | 475000 | FY 2026: 470000
HN-0026 | Highway | NCDOT Selected (Other Selection Process) | Central Pines Regional Council | - | Transportation demand management program for organizations. |  | Wake, Durham, Orange | 5, 7 | Capital Area MPO, Triangle West TPO |  | Exempt
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | Central Pines Regional Council | Central Pines | Transportation Demand Management Program For Organizations In Capital Area MPO |  | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 2517000 | FY 2026: 639000; FY 2027: 658000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | Central Pines Regional Council | Central Pines | Transportation Demand Management Program For Organizations In Capital Area MPO |  | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 629000 | FY 2026: 160000; FY 2027: 164000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | Central Pines Regional Council | Central Pines | Transportation Demand Management Program For Organizations In Triangle West TPO |  | Durham, Orange | 5, 7 | Triangle West TPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 2453000 | FY 2026: 622000; FY 2027: 641000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | Central Pines Regional Council | Central Pines | Transportation Demand Management Program For Organizations In Triangle West TPO |  | Durham, Orange | 5, 7 | Triangle West TPO |  | Exempt |  | L(M) | IMPLEMENTATION | 612000 | FY 2026: 155000; FY 2027: 160000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 to US 321 Business. | Extend right turn lane. Add right turn lane on southbound off ramp from US 321. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Exempt |  | CRPANY | ENGINEERING | 164000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 to US 321 Business. | Extend right turn lane. Add right turn lane on southbound off ramp from US 321. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Exempt |  | HF(M) | ENGINEERING | 41000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 to US 321 Business. | Extend right turn lane. Add right turn lane on southbound off ramp from US 321. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Exempt |  | CRPANY | CONSTRUCTION | 832000 | FY 2026: 832000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 to US 321 Business. | Extend right turn lane. Add right turn lane on southbound off ramp from US 321. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 208000 | FY 2026: 208000
HN-0028 | Highway | NCDOT Selected (Other Selection Process) | US 421 | SR 1710 (Speer Bridge Road) interchange in Yadkinville. | Construct roundabouts at ramp terminals. |  | Yadkin | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 3600000
HN-0028 | Highway | NCDOT Selected (Other Selection Process) | US 421 | SR 1710 (Speer Bridge Road) interchange in Yadkinville. | Construct roundabouts at ramp terminals. |  | Yadkin | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 400000
HN-0029 | Highway | NCDOT Selected (Other Selection Process) | NC 141 | SR 1533 (Hendrix Road) intersection in Marble. | Construct left turn lane. |  | Cherokee | 14 | Southwestern RPO |  | Region G |  | CRPLT5 | CONSTRUCTION | 480000
HN-0029 | Highway | NCDOT Selected (Other Selection Process) | NC 141 | SR 1533 (Hendrix Road) intersection in Marble. | Construct left turn lane. |  | Cherokee | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 120000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 595000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | T(M) | ENGINEERING | 149000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 104000 | FY 2026: 104000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 26000 | FY 2026: 26000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 3360000 | FY 2026: 3360000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (Cascade Lake Road) intersection in Cedar Mountain. | Construct roundabout. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Exempt |  | T(M) | CONSTRUCTION | 840000 | FY 2026: 840000
HN-0033 | Highway | NCDOT Selected (Other Selection Process) | NC 55 | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Wayne | 4 | Eastern Carolina RPO |  | Exempt |  | CRPANY | ENGINEERING | 880000
HN-0033 | Highway | NCDOT Selected (Other Selection Process) | NC 55 | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Wayne | 4 | Eastern Carolina RPO |  | Exempt |  | T(M) | ENGINEERING | 220000
HN-0033 | Highway | NCDOT Selected (Other Selection Process) | NC 55 | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Wayne | 4 | Eastern Carolina RPO |  | Exempt |  | CRPANY | RIGHT-OF-WAY | 530000 | FY 2026: 530000
HN-0033 | Highway | NCDOT Selected (Other Selection Process) | NC 55 | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Wayne | 4 | Eastern Carolina RPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 132000 | FY 2026: 132000
HN-0033 | Highway | NCDOT Selected (Other Selection Process) | NC 55 | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Wayne | 4 | Eastern Carolina RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 5054000 | FY 2026: 5054000
HN-0033 | Highway | NCDOT Selected (Other Selection Process) | NC 55 | SR 1744 (Old Seven Springs Road / Indian Springs Road) intersection in Mount Olive | Construct roundabout. |  | Wayne | 4 | Eastern Carolina RPO |  | Exempt |  | T(M) | CONSTRUCTION | 1264000 | FY 2026: 1264000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | Various | Chatham County | Purchase and install four electric vehicle charging stations. |  | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRPANY | ENGINEERING | 59000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | Various | Chatham County | Purchase and install four electric vehicle charging stations. |  | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 15000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | Various | Chatham County | Purchase and install four electric vehicle charging stations. |  | Chatham | 8 | Central Pines RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 37000 | FY 2026: 37000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | Various | Chatham County | Purchase and install four electric vehicle charging stations. |  | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 9000 | FY 2026: 9000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | Roberta Road | Main Street Intersection. | Construct roundabout. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225. | Division 10 |  | CMAQ | ENGINEERING | 572000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | Roberta Road | Main Street Intersection. | Construct roundabout. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225. | Division 10 |  | L | ENGINEERING | 143000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | Roberta Road | Main Street Intersection. | Construct roundabout. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2027: 200000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | Roberta Road | Main Street Intersection. | Construct roundabout. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225. | Division 10 |  | L | RIGHT-OF-WAY | 50000 | FY 2027: 50000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | Roberta Road | Main Street Intersection. | Construct roundabout. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225. | Division 10 |  | CMAQ | CONSTRUCTION | 1393000 | FY 2028: 1393000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | Roberta Road | Main Street Intersection. | Construct roundabout. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | Total fund of 2,706,125 is split in to 80/20 percent. The local match is 541,225. | Division 10 |  | L | CONSTRUCTION | 348000 | FY 2028: 348000
HN-0037 | Highway | NCDOT Selected (Other Selection Process) | Statewide | Statewide | Develop Carbon Reduction Strategy and Emissions tool. |  | Statewide | 99 | Statewide Project |  | Exempt |  | CRPANY | IMPLEMENTATION | 250000
HN-0038 | Highway | NCDOT Selected (Other Selection Process) | North Carolina State University | Clean Energy Technology Center. | Clean Fuels and Advanced Technologies (CFAT). |  | Wake | 5 | Capital Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 4744000
HN-0038 | Highway | NCDOT Selected (Other Selection Process) | North Carolina State University | Clean Energy Technology Center. | Clean Fuels and Advanced Technologies (CFAT). |  | Wake | 5 | Capital Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 1186000
HN-0039 | Highway | NCDOT Selected (Other Selection Process) | North Carolina Clean Energy Technology Center | Systemwide | Funding for Clean Fuels and Advanced Technologies (CFAT). |  | Statewide | 99 | Statewide Project |  | Exempt |  | CMAQ | ENGINEERING | 4744000
HN-0039 | Highway | NCDOT Selected (Other Selection Process) | North Carolina Clean Energy Technology Center | Systemwide | Funding for Clean Fuels and Advanced Technologies (CFAT). |  | Statewide | 99 | Statewide Project |  | Exempt |  | L(M) | ENGINEERING | 1186000
HN-0040 | Highway | NCDOT Selected (Other Selection Process) | SR 1908 (Fire Dept Road) | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 800000
HN-0040 | Highway | NCDOT Selected (Other Selection Process) | SR 1908 (Fire Dept Road) | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Exempt |  | T(M) | ENGINEERING | 200000
HN-0040 | Highway | NCDOT Selected (Other Selection Process) | SR 1908 (Fire Dept Road) | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 800000 | FY 2026: 800000
HN-0040 | Highway | NCDOT Selected (Other Selection Process) | SR 1908 (Fire Dept Road) | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 200000 | FY 2026: 200000
HN-0040 | Highway | NCDOT Selected (Other Selection Process) | SR 1908 (Fire Dept Road) | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 5440000 | FY 2026: 5440000
HN-0040 | Highway | NCDOT Selected (Other Selection Process) | SR 1908 (Fire Dept Road) | Buffalo Road intersection north of Wilson's Mills. | Construct roundabout. |  | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Exempt |  | T(M) | CONSTRUCTION | 1360000 | FY 2026: 1360000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | CRP550 | ENGINEERING | 140000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | ENGINEERING | 35000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | CRP550 | RIGHT-OF-WAY | 80000 | FY 2026: 80000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | CRP550 | UTILITIES | 120000 | FY 2026: 120000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | UTILITIES | 30000 | FY 2026: 30000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | CRP550 | CONSTRUCTION | 1336000 | FY 2026: 1336000
HN-0041 | Highway | NCDOT Selected (Other Selection Process) | NC 58 | SR 1259 (Taylor Notion Road) intersection | Construct roundabout. | 0.1 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 334000 | FY 2026: 334000
HN-0042 | Highway | NCDOT Selected (Other Selection Process) | US 74 | Anson High School Road | Intersection improvements | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | CRPLT5 | ENGINEERING | 384000 | FY 2026: 384000
HN-0042 | Highway | NCDOT Selected (Other Selection Process) | US 74 | Anson High School Road | Intersection improvements | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | ENGINEERING | 96000 | FY 2026: 96000
HN-0042 | Highway | NCDOT Selected (Other Selection Process) | US 74 | Anson High School Road | Intersection improvements | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | CRPLT5 | RIGHT-OF-WAY | 155000 | FY 2026: 155000
HN-0042 | Highway | NCDOT Selected (Other Selection Process) | US 74 | Anson High School Road | Intersection improvements | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 39000 | FY 2026: 39000
HN-0042 | Highway | NCDOT Selected (Other Selection Process) | US 74 | Anson High School Road | Intersection improvements | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | CRPLT5 | CONSTRUCTION | 2102000 | FY 2026: 2102000
HN-0042 | Highway | NCDOT Selected (Other Selection Process) | US 74 | Anson High School Road | Intersection improvements | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 525000 | FY 2026: 525000
HN-0043 | Highway | NCDOT Selected (Other Selection Process) | Rutherfordton | Systemwide | Purchase four electric vehicles |  | Rutherford | 13 | Foothills RPO |  | Exempt |  | CRP550 | CAPITAL | 233000 | FY 2026: 233000
HN-0043 | Highway | NCDOT Selected (Other Selection Process) | Rutherfordton | Systemwide | Purchase four electric vehicles |  | Rutherford | 13 | Foothills RPO |  | Exempt |  | L(M) | CAPITAL | 58000 | FY 2026: 58000
HO-0001 | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle pilot program. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS. | Exempt |  | DP | ENGINEERING | 64000
HO-0001 | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle pilot program. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS. | Exempt |  | HF(M) | ENGINEERING | 247000
HO-0001 | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle pilot program. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 227000
HO-0001AA | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle infrastructure, connected vehicle applications, traffic signal improvements, project management. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | DP | ENGINEERING | 186000
HO-0001AA | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle infrastructure, connected vehicle applications, traffic signal improvements, project management. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | HF(M) | ENGINEERING | 183000
HO-0001AA | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle infrastructure, connected vehicle applications, traffic signal improvements, project management. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | DP | CONSTRUCTION | 1491000 | FY 2026: 35000
HO-0001AA | Highway | Other | North Carolina State University | - | NCDOT multi-modal connected vehicle infrastructure, connected vehicle applications, traffic signal improvements, project management. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | HF(M) | CONSTRUCTION | 1490000 | FY 2026: 35000
HO-0001AB | Highway | Other | North Carolina State University | - | Install fiber optic cable. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | DP | ENGINEERING | 75000
HO-0001AB | Highway | Other | North Carolina State University | - | Install fiber optic cable. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | HF(M) | ENGINEERING | 75000
HO-0001AB | Highway | Other | North Carolina State University | - | Install fiber optic cable. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | DP | CONSTRUCTION | 84000 | FY 2026: 84000
HO-0001AB | Highway | Other | North Carolina State University | - | Install fiber optic cable. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | HF(M) | CONSTRUCTION | 84000 | FY 2026: 55000; FY 2027: 29000
HO-0001B | Highway | Other | North Carolina State University | NCSU Campus | Systems engineering, grant administration. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | DP | ENGINEERING | 50000
HO-0001B | Highway | Other | North Carolina State University | NCSU Campus | Systems engineering, grant administration. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | HF(M) | ENGINEERING | 150000
HO-0001C | Highway | Other | North Carolina State University | - | Before & after study, expansion feasibility study. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | DP | ENGINEERING | 156000
HO-0001C | Highway | Other | North Carolina State University | - | Before & after study, expansion feasibility study. |  | Wake | 5 | Capital Area MPO |  | Exempt |  | HF(M) | ENGINEERING | 154000
HO-0002 | Highway | Other | US 74 | I-40 in Asheville to I-140 in Wilmington. | Implement broadband, ITS, and resiliency improvements. | 279.24 | Columbus, Robeson, Cleveland, Anson, Gaston, Polk, Scotland, Henderson, Richmond, Rutherford, Mecklenburg, Brunswick, Buncombe, Union | 3, 6, 8, 10, 12, 13, 14 | Lumber River RPO, Cape Fear RPO, Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS.
HO-0002A | Highway | Other | U 74 | I-40 in Asheville to I-77 at I-485 (south) in Charlotte. | Install broadband for Traveler Information Systems. | 123.09 | Cleveland, Polk, Gaston, Henderson, Rutherford, Mecklenburg, Buncombe | 10, 12, 13, 14 | Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C. | Statewide Mobility |  | HSIP | CONSTRUCTION | 16592000
HO-0002A | Highway | Other | U 74 | I-40 in Asheville to I-77 at I-485 (south) in Charlotte. | Install broadband for Traveler Information Systems. | 123.09 | Cleveland, Polk, Gaston, Henderson, Rutherford, Mecklenburg, Buncombe | 10, 12, 13, 14 | Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1843000
HO-0002B | Highway | Other | US 74 | Eastern end of Monroe Bypass to I-95 in Lumberton. | Install broadband and ITS for Traveler Information Systems. | 86.48 | Anson, Robeson, Richmond, Scotland, Union | 6, 8, 10 | Lumber River RPO, Rocky River RPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 12794000
HO-0002B | Highway | Other | US 74 | Eastern end of Monroe Bypass to I-95 in Lumberton. | Install broadband and ITS for Traveler Information Systems. | 86.48 | Anson, Robeson, Richmond, Scotland, Union | 6, 8, 10 | Lumber River RPO, Rocky River RPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1422000
HO-0002C | Highway | Other | US 74 | I-95 in Lumberton to I-140 in Wilmington. | Install broadband for Traveler Information Systems. | 69.67 | Columbus, Robeson, Brunswick | 3, 6 | Cape Fear RPO, Lumber River RPO, Wilmington Urban Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 9410000
HO-0002C | Highway | Other | US 74 | I-95 in Lumberton to I-140 in Wilmington. | Install broadband for Traveler Information Systems. | 69.67 | Columbus, Robeson, Brunswick | 3, 6 | Cape Fear RPO, Lumber River RPO, Wilmington Urban Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1045000
HO-0002D | Highway | Other | US 74 | Eastern end of Monroe Bypass to I-140 in Wilmington. | Install flood gates and flood monitoring. | 156.15 | Columbus, Robeson, Anson, Scotland, Richmond, Brunswick, Union | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO |  | Statewide Mobility |  | DP | ENGINEERING | 1760000
HO-0002D | Highway | Other | US 74 | Eastern end of Monroe Bypass to I-140 in Wilmington. | Install flood gates and flood monitoring. | 156.15 | Columbus, Robeson, Anson, Scotland, Richmond, Brunswick, Union | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO |  | Statewide Mobility |  | T | ENGINEERING | 440000
HO-0003 | Highway | Other | Great Smoky Mountains National Park | Regionwide | Funding for regional outreach and educational program. |  | Haywood | 14 | Land-of-Sky RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 200000
HO-0003 | Highway | Other | Great Smoky Mountains National Park | Regionwide | Funding for regional outreach and educational program. |  | Haywood | 14 | Land-of-Sky RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 50000
HO-0004 | Highway | Other | Great Smoky Mountains National Park | Regionwide | Funding for sustainable transportation practices to reduce air pollution. |  | Swain | 14 | Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 300000
HO-0004 | Highway | Other | Great Smoky Mountains National Park | Regionwide | Funding for sustainable transportation practices to reduce air pollution. |  | Swain | 14 | Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 75000
HO-0005 | Highway | Other | Various | Locations in Divisions 4, 5, 7, 9, and 10. | Install statewide ITS devices. |  | Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Nash, Davie, Edgecombe, Granville, Haywood | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Winston-Salem Area TPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MPO, Kerr-Tar RPO, Lan | UNDER CONSTRUCTION. | Exempt |  | CMAQ | CONSTRUCTION | 17284000
HO-0005 | Highway | Other | Various | Locations in Divisions 4, 5, 7, 9, and 10. | Install statewide ITS devices. |  | Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Nash, Davie, Edgecombe, Granville, Haywood | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Winston-Salem Area TPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MPO, Kerr-Tar RPO, Lan | UNDER CONSTRUCTION. | Exempt |  | T(M) | CONSTRUCTION | 4321000
HO-0009 | Highway | Other | North Carolina Department of Environment and Natural Resources | Statewide | North Carolina air awareness outreach program to provide education and produce daily air quality forecasts. |  | Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Lincoln, Nash, Chatham, Davie, Edgecombe, Franklin, Granville, Haywood, Person, Swain | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban Area MPO, Roc | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 1173000
HO-0009 | Highway | Other | North Carolina Department of Environment and Natural Resources | Statewide | North Carolina air awareness outreach program to provide education and produce daily air quality forecasts. |  | Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Lincoln, Nash, Chatham, Davie, Edgecombe, Franklin, Granville, Haywood, Person, Swain | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban Area MPO, Roc | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | O | IMPLEMENTATION | 282000
HO-0009 | Highway | Other | North Carolina Department of Environment and Natural Resources | Statewide | North Carolina air awareness outreach program to provide education and produce daily air quality forecasts. |  | Mecklenburg, Wake, Guilford, Forsyth, Durham, Cabarrus, Gaston, Johnston, Union, Catawba, Davidson, Iredell, Orange, Rowan, Lincoln, Nash, Chatham, Davie, Edgecombe, Franklin, Granville, Haywood, Person, Swain | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Triangle West TPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban Area MPO, Roc | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 149000
HO-0010 | Highway | Other | Statewide Traffic Operations | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management. |  | Statewide | 99 | Statewide Project
HO-0010A | Highway | Other | Statewide Traffic Operations | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management in the Triangle and Metrolina Areas. |  | Wake, Iredell, Mecklenburg, Rowan, Cleveland, Union, Cabarrus, Gaston, Johnston, Durham, Lincoln, Franklin, Orange, Chatham, Granville, Harnett | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Triangle West TPO |  | Statewide Mobility |  | CRPANY | IMPLEMENTATION | 3200000
HO-0010A | Highway | Other | Statewide Traffic Operations | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management in the Triangle and Metrolina Areas. |  | Wake, Iredell, Mecklenburg, Rowan, Cleveland, Union, Cabarrus, Gaston, Johnston, Durham, Lincoln, Franklin, Orange, Chatham, Granville, Harnett | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Triangle West TPO |  | Statewide Mobility |  | HF(M) | IMPLEMENTATION | 800000
HO-0010B | Highway | Other | Statewide Traffic Operations | Statewide | Implement statewide traffic operations activities such as traffic management centers, traveler information, intelligent transportation systems (ITS), and traffic incident and event management. |  | Statewide | 99 | Statewide Project |  | Exempt |  | CMAQ | IMPLEMENTATION | 93220000 | FY 2026: 33456000
HO-0011 | Highway | Other | I-40; I-95 | Tennessee state line to mile marker 20; Exit 13 to south of proposed I-295. | Implement system to provide real time alerts in vehicles when drivers encounter a road anomaly requiring them to take driving action. | 40 | Haywood, Robeson | 6, 14 | Land-of-Sky RPO, Lumber River RPO | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH. | Statewide Mobility |  | DP | IMPLEMENTATION | 1534000
HO-0011 | Highway | Other | I-40; I-95 | Tennessee state line to mile marker 20; Exit 13 to south of proposed I-295. | Implement system to provide real time alerts in vehicles when drivers encounter a road anomaly requiring them to take driving action. | 40 | Haywood, Robeson | 6, 14 | Land-of-Sky RPO, Lumber River RPO | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH. | Statewide Mobility |  | O | IMPLEMENTATION | 438000
HO-0012 | Highway | Other | Blue Ridge Parkway Association | Statewide. | Update Blue Ridge Parkway Association travel planner and map brochure. Redesign Blue Ridge Parkway website and mobile application. Implement marketing plan for Blue Ridge Parkway Association. |  | Buncombe, Alleghany, Jackson, Watauga, Ashe, Swain, Haywood, Avery, McDowell, Transylvania, Yancey, Mitchell, Henderson, Wilkes, Burke, Caldwell | 11, 13, 14 | High Country RPO, French Broad River MPO, Southwestern RPO, Land-of-Sky RPO, Foothills RPO, Greater Hickory MPO | NATIONAL SCENIC BYWAYS GRANT AWARD: $460,000. DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. LOCAL MATCH PROVIDED BY BLUE RIDGE PARKWAYS ASSOCIATION. | Exempt |  | DP | IMPLEMENTATION | 460000
HO-0012 | Highway | Other | Blue Ridge Parkway Association | Statewide. | Update Blue Ridge Parkway Association travel planner and map brochure. Redesign Blue Ridge Parkway website and mobile application. Implement marketing plan for Blue Ridge Parkway Association. |  | Buncombe, Alleghany, Jackson, Watauga, Ashe, Swain, Haywood, Avery, McDowell, Transylvania, Yancey, Mitchell, Henderson, Wilkes, Burke, Caldwell | 11, 13, 14 | High Country RPO, French Broad River MPO, Southwestern RPO, Land-of-Sky RPO, Foothills RPO, Greater Hickory MPO | NATIONAL SCENIC BYWAYS GRANT AWARD: $460,000. DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. LOCAL MATCH PROVIDED BY BLUE RIDGE PARKWAYS ASSOCIATION. | Exempt |  | L | IMPLEMENTATION | 115000
HO-0013 | Highway | Other | SR 1010 (Franklin Street); Rosemary Street | Merritt Mill Road to Henderson Street, and connecting streets in Downtown Chapel Hill. | Install new mast arm and curb and sidewalk improvements. | 2 | Orange | 7 | Triangle West TPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. DEMO ID NC201. | Exempt |  | DP | ENGINEERING | 400000
HO-0013 | Highway | Other | SR 1010 (Franklin Street); Rosemary Street | Merritt Mill Road to Henderson Street, and connecting streets in Downtown Chapel Hill. | Install new mast arm and curb and sidewalk improvements. | 2 | Orange | 7 | Triangle West TPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. DEMO ID NC201. | Exempt |  | DP | RIGHT-OF-WAY | 250000 | FY 2026: 250000
HO-0013 | Highway | Other | SR 1010 (Franklin Street); Rosemary Street | Merritt Mill Road to Henderson Street, and connecting streets in Downtown Chapel Hill. | Install new mast arm and curb and sidewalk improvements. | 2 | Orange | 7 | Triangle West TPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. DEMO ID NC201. | Exempt |  | DP | UTILITIES | 550000 | FY 2026: 550000
HO-0013 | Highway | Other | SR 1010 (Franklin Street); Rosemary Street | Merritt Mill Road to Henderson Street, and connecting streets in Downtown Chapel Hill. | Install new mast arm and curb and sidewalk improvements. | 2 | Orange | 7 | Triangle West TPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. DEMO ID NC201. | Exempt |  | DP | CONSTRUCTION | 800000 | FY 2026: 800000
HO-0013 | Highway | Other | SR 1010 (Franklin Street); Rosemary Street | Merritt Mill Road to Henderson Street, and connecting streets in Downtown Chapel Hill. | Install new mast arm and curb and sidewalk improvements. | 2 | Orange | 7 | Triangle West TPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. DEMO ID NC201. | Exempt |  | L | CONSTRUCTION | 500000 | FY 2026: 500000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | ENGINEERING | 1282000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | ENGINEERING | 148000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | RIGHT-OF-WAY | 684000 | FY 2026: 684000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | RIGHT-OF-WAY | 76000 | FY 2026: 76000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | UTILITIES | 189000 | FY 2026: 189000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | UTILITIES | 21000 | FY 2026: 21000
HO-0014 | Highway | Other | NC 72 | NC 41 to NC 211 in Lumberton. | Construct complete street improvements. | 2.06 | Robeson | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | DP | CONSTRUCTION | 8600000 | FY 2027: 8600000
HO-0015 | Highway | Other | Blue Ridge Parkway | Regionwide. | Marketing and branding for Blue Ridge Parkway Association. |  | Avery, Buncombe, Burke, Haywood, Henderson, Jackson, McDowell, Mitchell, Swain, Transylvania, Alleghany, Ashe, Caldwell, Watauga, Wilkes | 11, 13, 14 | French Broad River MPO, Greater Hickory MPO, High Country RPO, Land-of-Sky RPO, Southwestern RPO, Foothills RPO | DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. | Exempt |  | DP | IMPLEMENTATION | 460000
HO-0017 | Highway | Other | Durham | I-85, US 70, and possibly I-40. | Construct ev charging stations. |  | Durham | 5 | Triangle West TPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | DP | CONSTRUCTION | 4864000 | FY 2026: 4864000
HO-0017 | Highway | Other | Durham | I-85, US 70, and possibly I-40. | Construct ev charging stations. |  | Durham | 5 | Triangle West TPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | L(M) | CONSTRUCTION | 1216000 | FY 2026: 1216000
HO-0019 | Highway | Other | Various | Locations in Divisions 1, 4, 5, 6, 8, 12, and 14. | install EV chargers at multiple community colleges. |  | Chatham, Cumberland, Edgecombe, Gaston, Harnett, Henderson, Lee, Lincoln, Martin, Transylvania, Bertie, Hertford, Nash, Randolph, Wake | 1, 4, 5, 6, 8, 12, 14 | Capital Area MPO, Central Pines RPO, Fayetteville Area MPO, French Broad River MPO, Gaston-Cleveland-Lincoln MPO, Land-of-Sky RPO, Mid-Carolina RPO, Peanut Belt RPO, Piedmont Triad RPO, Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. HF REPRESENT CONTINGENCY FUNDS. | Exempt |  | DP | CONSTRUCTION | 1007000 | FY 2026: 1007000
HO-0019 | Highway | Other | Various | Locations in Divisions 1, 4, 5, 6, 8, 12, and 14. | install EV chargers at multiple community colleges. |  | Chatham, Cumberland, Edgecombe, Gaston, Harnett, Henderson, Lee, Lincoln, Martin, Transylvania, Bertie, Hertford, Nash, Randolph, Wake | 1, 4, 5, 6, 8, 12, 14 | Capital Area MPO, Central Pines RPO, Fayetteville Area MPO, French Broad River MPO, Gaston-Cleveland-Lincoln MPO, Land-of-Sky RPO, Mid-Carolina RPO, Peanut Belt RPO, Piedmont Triad RPO, Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. HF REPRESENT CONTINGENCY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 252000 | FY 2026: 252000
HO-0020 | Highway | Other | NC 12 | Rodanthe to Oregon inlet. | Conduct planning study for the long-term operation of the roadway during major storm events. |  | Dare | 1 | Albemarle RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT AWARD. | Exempt |  | DP | PLANNING | 1865000
HO-0021 | Highway | Other | US 74 (Future I-74) | Bridges 770466 and 770118 over the Lumber River | Reinforce shoulder embankments. |  | Robeson | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. S(M) FUNDS REPRESENT NC OFFICE OF STATE BUDGET AND MANAGEMENT FUNDING $225,000 AND NC DEPARTMENT OF ENVIRONMENTAL QUALITY FUNDING (UP TO $270,000). | Exempt |  | DP | ENGINEERING | 244000
HO-0021 | Highway | Other | US 74 (Future I-74) | Bridges 770466 and 770118 over the Lumber River | Reinforce shoulder embankments. |  | Robeson | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. S(M) FUNDS REPRESENT NC OFFICE OF STATE BUDGET AND MANAGEMENT FUNDING $225,000 AND NC DEPARTMENT OF ENVIRONMENTAL QUALITY FUNDING (UP TO $270,000). | Exempt |  | S(M) | ENGINEERING | 61000
HO-0021 | Highway | Other | US 74 (Future I-74) | Bridges 770466 and 770118 over the Lumber River | Reinforce shoulder embankments. |  | Robeson | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. S(M) FUNDS REPRESENT NC OFFICE OF STATE BUDGET AND MANAGEMENT FUNDING $225,000 AND NC DEPARTMENT OF ENVIRONMENTAL QUALITY FUNDING (UP TO $270,000). | Exempt |  | DP | CONSTRUCTION | 1560000 | FY 2026: 1560000
HO-0021 | Highway | Other | US 74 (Future I-74) | Bridges 770466 and 770118 over the Lumber River | Reinforce shoulder embankments. |  | Robeson | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. S(M) FUNDS REPRESENT NC OFFICE OF STATE BUDGET AND MANAGEMENT FUNDING $225,000 AND NC DEPARTMENT OF ENVIRONMENTAL QUALITY FUNDING (UP TO $270,000). | Exempt |  | S(M) | CONSTRUCTION | 390000 | FY 2026: 390000
HO-0022 | Highway | Other | Durham | Various locations in the City of Durham. | Install ev charging equipment to support equitable electrification. |  | Durham | 5 | Triangle West TPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | DP | CONSTRUCTION | 4000000 | FY 2026: 4000000
HO-0022 | Highway | Other | Durham | Various locations in the City of Durham. | Install ev charging equipment to support equitable electrification. |  | Durham | 5 | Triangle West TPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | L | CONSTRUCTION | 1000000 | FY 2026: 1000000
HO-0023 | Highway | Other | SR 1202 (Hickory Fork Road) | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Chowan | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | DP | ENGINEERING | 79000
HO-0023 | Highway | Other | SR 1202 (Hickory Fork Road) | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Chowan | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | HF(M) | ENGINEERING | 21000
HO-0023 | Highway | Other | SR 1202 (Hickory Fork Road) | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Chowan | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | DP | RIGHT-OF-WAY | 118000 | FY 2026: 118000
HO-0023 | Highway | Other | SR 1202 (Hickory Fork Road) | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Chowan | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | HF(M) | RIGHT-OF-WAY | 32000 | FY 2026: 32000
HO-0023 | Highway | Other | SR 1202 (Hickory Fork Road) | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Chowan | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | DP | CONSTRUCTION | 275000 | FY 2028: 275000
HO-0023 | Highway | Other | SR 1202 (Hickory Fork Road) | Culvert BP 021-2074 Over Pembroke Creek. | Replace culvert. |  | Chowan | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | HF(M) | CONSTRUCTION | 75000 | FY 2028: 75000
HO-0024 | Highway | Other | Statewide | Statewide | Improve 1000 isolated closed-loop system signals. |  | Statewide | 99 | Statewide Project | DP FUNDS REPRESENT FEDERAL ATTAIN GRANT FUNDING. HF(M) FUNDS REPRESENT NCDOT TRAFFIC SYSTEMS AND OPERATION FUNDING. O(M) FUNDS REPRESENT IN-KIND MATCH FROM VARIOUS PARTNERS AND MUNICIPALITIES. | Exempt |  | DP | IMPLEMENTATION | 11946000 | FY 2026: 3021000; FY 2027: 3060000; FY 2028: 2900000
HO-0024 | Highway | Other | Statewide | Statewide | Improve 1000 isolated closed-loop system signals. |  | Statewide | 99 | Statewide Project | DP FUNDS REPRESENT FEDERAL ATTAIN GRANT FUNDING. HF(M) FUNDS REPRESENT NCDOT TRAFFIC SYSTEMS AND OPERATION FUNDING. O(M) FUNDS REPRESENT IN-KIND MATCH FROM VARIOUS PARTNERS AND MUNICIPALITIES. | Exempt |  | O(M) | IMPLEMENTATION | 1000000 | FY 2026: 250000; FY 2027: 250000; FY 2028: 250000
HO-0024 | Highway | Other | Statewide | Statewide | Improve 1000 isolated closed-loop system signals. |  | Statewide | 99 | Statewide Project | DP FUNDS REPRESENT FEDERAL ATTAIN GRANT FUNDING. HF(M) FUNDS REPRESENT NCDOT TRAFFIC SYSTEMS AND OPERATION FUNDING. O(M) FUNDS REPRESENT IN-KIND MATCH FROM VARIOUS PARTNERS AND MUNICIPALITIES. | Exempt |  | HF(M) | IMPLEMENTATION | 2986000 | FY 2026: 755000; FY 2027: 765000; FY 2028: 725000
HO-0025 | Highway | Other | Various | North Carolina Clean Energy Technology Center. | Conduct a clean-fuel advanced technology outreach and awareness program in all CMAQ-eligible counties. |  | Statewide | 99 | Statewide Project | INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Exempt
HO-0026 | Highway | Other | Durham | Bridge 310246 - Pettigrew Street over Campus Drive; bridge 310280 - Ramseur Street over South Roxboro Street. | Conduct Planning and Environmental Linkages (PEL) study for the replacement of two bridges. |  | Durham | 5 | Triangle West TPO | "DP" FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM (BIP) GRANT AWARD AND "O(M)" FUNDS REPRESENT AN IN-KIND MATCH. | Exempt |  | DP | PLANNING | 500000
HO-0026 | Highway | Other | Durham | Bridge 310246 - Pettigrew Street over Campus Drive; bridge 310280 - Ramseur Street over South Roxboro Street. | Conduct Planning and Environmental Linkages (PEL) study for the replacement of two bridges. |  | Durham | 5 | Triangle West TPO | "DP" FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM (BIP) GRANT AWARD AND "O(M)" FUNDS REPRESENT AN IN-KIND MATCH. | Exempt |  | O(M) | PLANNING | 125000
HO-0027 | Highway | Other | US 64 | East of the East Lake Community to west of SR 1169 (Robertson Landing Road). | Install wildlife underpasses and fencing. | 2.5 | Dare | 1 | Albemarle RPO | DP funds represent Wildlife Crossings Pilot Program Grant. O(M) funds represent private donations. O phase represents Education / Outreach and Monitoring activities. | Exempt |  | DP | ENGINEERING | 560000 | FY 2026: 560000
HO-0027 | Highway | Other | US 64 | East of the East Lake Community to west of SR 1169 (Robertson Landing Road). | Install wildlife underpasses and fencing. | 2.5 | Dare | 1 | Albemarle RPO | DP funds represent Wildlife Crossings Pilot Program Grant. O(M) funds represent private donations. O phase represents Education / Outreach and Monitoring activities. | Exempt |  | HF(M) | ENGINEERING | 140000 | FY 2026: 140000
HO-0027 | Highway | Other | US 64 | East of the East Lake Community to west of SR 1169 (Robertson Landing Road). | Install wildlife underpasses and fencing. | 2.5 | Dare | 1 | Albemarle RPO | DP funds represent Wildlife Crossings Pilot Program Grant. O(M) funds represent private donations. O phase represents Education / Outreach and Monitoring activities. | Exempt |  | DP | CONSTRUCTION | 24440000 | FY 2027: 24440000
HO-0027 | Highway | Other | US 64 | East of the East Lake Community to west of SR 1169 (Robertson Landing Road). | Install wildlife underpasses and fencing. | 2.5 | Dare | 1 | Albemarle RPO | DP funds represent Wildlife Crossings Pilot Program Grant. O(M) funds represent private donations. O phase represents Education / Outreach and Monitoring activities. | Exempt |  | O(M) | CONSTRUCTION | 4000000 | FY 2027: 4000000
HO-0027 | Highway | Other | US 64 | East of the East Lake Community to west of SR 1169 (Robertson Landing Road). | Install wildlife underpasses and fencing. | 2.5 | Dare | 1 | Albemarle RPO | DP funds represent Wildlife Crossings Pilot Program Grant. O(M) funds represent private donations. O phase represents Education / Outreach and Monitoring activities. | Exempt |  | HF(M) | CONSTRUCTION | 2110000 | FY 2027: 2110000
HO-0028 | Highway | Other | Various | Routes in Grimeland. | Repave 22 sections of roadway. |  | Pitt | 2 | Mid-East RPO | DP FUNDS REPRESENTS NC203 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $1,116,276. | Exempt |  | DP | CONSTRUCTION | 1116000 | FY 2026: 1116000
HO-0028 | Highway | Other | Various | Routes in Grimeland. | Repave 22 sections of roadway. |  | Pitt | 2 | Mid-East RPO | DP FUNDS REPRESENTS NC203 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $1,116,276. | Exempt |  | L(M) | CONSTRUCTION | 279000 | FY 2026: 279000
HO-0029 | Highway | Other | Various | Charlotte Regional Transportation Planning Organization - Making Our Roads SAFER: A Cross-Jurisdictional Study (aka RAISE) | Fund planning activities by comprehensively examining prevailing transportation issues throughout the MPO's planning area. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | DP | PLANNING | 5000000 | FY 2026: 5000000
HO-0030 | Highway | Other | Charlotte | Freedom Drive/Ashely Road/Tuckaseegee Road | Construct complete street, traffic safety, and transit access/mobility service improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | DP | CONSTRUCTION | 25000000 | FY 2026: 25000000
HO-0030 | Highway | Other | Charlotte | Freedom Drive/Ashely Road/Tuckaseegee Road | Construct complete street, traffic safety, and transit access/mobility service improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 8692000 | FY 2026: 8692000
HO-0031 | Highway | Other | Mooresville | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | DP | PLANNING | 144000 | FY 2026: 144000
HO-0031 | Highway | Other | Mooresville | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | PLANNING | 36000 | FY 2026: 36000
HO-0032 | Highway | Other | Marvin | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | DP | PLANNING | 58000 | FY 2026: 58000
HO-0032 | Highway | Other | Marvin | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | PLANNING | 14000 | FY 2026: 14000
HO-0033 | Highway | Other | Huntersville | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | DP | PLANNING | 240000 | FY 2026: 240000
HO-0033 | Highway | Other | Huntersville | Safe Streets and Roads for All Planning Grant | Funding for a safety study to prioritize actions that reduce transportation-related injuries and deaths. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | PLANNING | 60000 | FY 2026: 60000
HO-0034 | Highway | Other | Various | Locations in downtown Siler City | Complete final design for bus stops, streetscape elements, stormwater infrastructure, underground utility design, lighting, and flood mitigation with water quality improvements in Siler City’s downtown area. |  | Chatham | 8 | Central Pines RPO | DP FUNDS REPRESENT RAISE GRANT FUNDING | Exempt |  | DP | ENGINEERING | 6194000 | FY 2026: 6194000
HO-0035 | Highway | Other | Various | Locations in the Loves Creek Tributary area around Raleigh Street | Complete final design for bus stops, streetscape improvements, stormwater infrastructure upgrades, underground utility design, lighting, and flood mitigation with water quality improvements in the Loves Creek Tributary area. |  | Chatham | 8 | Central Pines RPO | DP FUNDS REPRESENT RAISE GRANT FUNDING | Exempt |  | DP | ENGINEERING | 3995000 | FY 2026: 3995000
HP-0001 | Highway | STI (Prioritization) | US 74 | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Union | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4720000
HP-0001 | Highway | STI (Prioritization) | US 74 | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Union | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 1180000
HP-0001 | Highway | STI (Prioritization) | US 74 | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Union | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2240000
HP-0001 | Highway | STI (Prioritization) | US 74 | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Union | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 560000
HP-0001 | Highway | STI (Prioritization) | US 74 | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Union | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 85840000
HP-0001 | Highway | STI (Prioritization) | US 74 | Indian Trail / Fairview Road to North Rocky River Road in Monroe. | Widen roadway to six lanes. |  | Union | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 21460000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 to I-85 in southwest Charlotte. | Construct one express lane in each direction. This is a toll project (express lanes only). |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | RIGHT-OF-WAY | 1600000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 to I-85 in southwest Charlotte. | Construct one express lane in each direction. This is a toll project (express lanes only). |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | UTILITIES | 23700000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 to I-85 in southwest Charlotte. | Construct one express lane in each direction. This is a toll project (express lanes only). |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 91500000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 to I-85 in southwest Charlotte. | Construct one express lane in each direction. This is a toll project (express lanes only). |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | CONSTRUCTION | 154700000
HP-0003 | Highway | STI (Prioritization) | I 40 | Cary Towne Boulevard to Wade Avenue | Construct operational improvements including auxiliary lanes between Wade Avenue and Cary Towne Boulevard and interchange improvements at Cary Towne Boulevard. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 6000000
HP-0003 | Highway | STI (Prioritization) | I 40 | Cary Towne Boulevard to Wade Avenue | Construct operational improvements including auxiliary lanes between Wade Avenue and Cary Towne Boulevard and interchange improvements at Cary Towne Boulevard. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 500000
HP-0003 | Highway | STI (Prioritization) | I 40 | Cary Towne Boulevard to Wade Avenue | Construct operational improvements including auxiliary lanes between Wade Avenue and Cary Towne Boulevard and interchange improvements at Cary Towne Boulevard. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 27500000
HP-0004 | Highway | STI (Prioritization) | I-85 | SR 1291 (Billy Graham Parkway) interchange in Charlotte. | Construct interchange improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 8400000
HP-0004 | Highway | STI (Prioritization) | I-85 | SR 1291 (Billy Graham Parkway) interchange in Charlotte. | Construct interchange improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 700000
HP-0004 | Highway | STI (Prioritization) | I-85 | SR 1291 (Billy Graham Parkway) interchange in Charlotte. | Construct interchange improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 38700000
HP-0005 | Highway | STI (Prioritization) | Various | Division 5 | Provide communication and cameras to improve signal timing. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
HP-0005 | Highway | STI (Prioritization) | Various | Division 5 | Provide communication and cameras to improve signal timing. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15596000
HP-0006 | Highway | STI (Prioritization) | Various | Chapel Hill Carrboro | Implement an improved signal system for the Town of Chapel Hill and Town of Carrboro. | 14.79 | Orange, Durham | 5, 7 | Triangle West TPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1700000
HP-0006 | Highway | STI (Prioritization) | Various | Chapel Hill Carrboro | Implement an improved signal system for the Town of Chapel Hill and Town of Carrboro. | 14.79 | Orange, Durham | 5, 7 | Triangle West TPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 13910000
HP-0007 | Highway | STI (Prioritization) | US 70 Business | Raynor Road and Guy Road intersection in Raleigh | Convert intersections to reduced conflict intersections. | 1.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2500000
HP-0007 | Highway | STI (Prioritization) | US 70 Business | Raynor Road and Guy Road intersection in Raleigh | Convert intersections to reduced conflict intersections. | 1.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 1340000
HP-0007 | Highway | STI (Prioritization) | US 70 Business | Raynor Road and Guy Road intersection in Raleigh | Convert intersections to reduced conflict intersections. | 1.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 14000000
HP-0008 | Highway | STI (Prioritization) | Holly Springs | Holly Springs | Install fiber to connect existing town fiber to intersections, upgrade existing infrastructure including cabinets, controllers, and software. | 4.58 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 3085000 | FY 2028: 2005000; FY 2029: 1080000
HP-0009 | Highway | STI (Prioritization) | US 401 / US 70 Business | SR 1370 (Tryon Road) intersection in Raleigh | Improve intersection signals and merging between Tryon Road and Mechanical Boulevard. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1500000
HP-0009 | Highway | STI (Prioritization) | US 401 / US 70 Business | SR 1370 (Tryon Road) intersection in Raleigh | Improve intersection signals and merging between Tryon Road and Mechanical Boulevard. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0009 | Highway | STI (Prioritization) | US 401 / US 70 Business | SR 1370 (Tryon Road) intersection in Raleigh | Improve intersection signals and merging between Tryon Road and Mechanical Boulevard. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 5500000
HP-0010 | Highway | STI (Prioritization) | Town of Cary | Town of Cary | Upgrade existing infrastructure, install new fiber, controllers, signals, connected vehicle technology and other equipment as necessary. | 7.94 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6000000
HP-0010 | Highway | STI (Prioritization) | Town of Cary | Town of Cary | Upgrade existing infrastructure, install new fiber, controllers, signals, connected vehicle technology and other equipment as necessary. | 7.94 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 4000000
HP-0011 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (Nursery Road) intersection in Fayetteville | Upgrade at-grade intersection to interchange. | 2 | Harnett | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 400000
HP-0011 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (Nursery Road) intersection in Fayetteville | Upgrade at-grade intersection to interchange. | 2 | Harnett | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 400000
HP-0011 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (Nursery Road) intersection in Fayetteville | Upgrade at-grade intersection to interchange. | 2 | Harnett | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 33400000
HP-0012 | Highway | STI (Prioritization) | US 401 | SR 1370 (Tryon Road) intersection in Raleigh | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2500000
HP-0012 | Highway | STI (Prioritization) | US 401 | SR 1370 (Tryon Road) intersection in Raleigh | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0012 | Highway | STI (Prioritization) | US 401 | SR 1370 (Tryon Road) intersection in Raleigh | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 8000000
HP-0013 | Highway | STI (Prioritization) | US 1 (Raleigh Road) | Belmont Drive (Old County Home Road) and Welcome Avenue intersection in Henderson | Construct intersection improvements. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 600000
HP-0013 | Highway | STI (Prioritization) | US 1 (Raleigh Road) | Belmont Drive (Old County Home Road) and Welcome Avenue intersection in Henderson | Construct intersection improvements. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 200000
HP-0013 | Highway | STI (Prioritization) | US 1 (Raleigh Road) | Belmont Drive (Old County Home Road) and Welcome Avenue intersection in Henderson | Construct intersection improvements. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 2000000
HP-0014 | Highway | STI (Prioritization) | NC 55 | SR 1114 (South Main Street) to SR 1152 (New Hill Road); West Holly Springs Road | Upgrade corridor to six lane expressway. | 1.6 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 3300000
HP-0014 | Highway | STI (Prioritization) | NC 55 | SR 1114 (South Main Street) to SR 1152 (New Hill Road); West Holly Springs Road | Upgrade corridor to six lane expressway. | 1.6 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 550000
HP-0014 | Highway | STI (Prioritization) | NC 55 | SR 1114 (South Main Street) to SR 1152 (New Hill Road); West Holly Springs Road | Upgrade corridor to six lane expressway. | 1.6 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 44800000
HP-0015 | Highway | STI (Prioritization) | US 401 Bypass (Pamalee Drive) | NC 24 / NC 87 (Bragg Boulevard) to NC 210 (Murchison Road). | Construct raised center median with access management improvements. | 2.32 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 24000000
HP-0015 | Highway | STI (Prioritization) | US 401 Bypass (Pamalee Drive) | NC 24 / NC 87 (Bragg Boulevard) to NC 210 (Murchison Road). | Construct raised center median with access management improvements. | 2.32 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 29400000
HP-0015 | Highway | STI (Prioritization) | US 401 Bypass (Pamalee Drive) | NC 24 / NC 87 (Bragg Boulevard) to NC 210 (Murchison Road). | Construct raised center median with access management improvements. | 2.32 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 36000000
HP-0016 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | NC 50 (Creedmoor Road) intersection | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 5300000
HP-0016 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | NC 50 (Creedmoor Road) intersection | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 800000
HP-0016 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | NC 50 (Creedmoor Road) intersection | Construct intersection improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 19800000
HP-0017 | Highway | STI (Prioritization) | NC 55 Bypass | SR 1114 (South Main Street) intersection | Convert existing at-grade intersection to interchange. | 2 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 18200000
HP-0017 | Highway | STI (Prioritization) | NC 55 Bypass | SR 1114 (South Main Street) intersection | Convert existing at-grade intersection to interchange. | 2 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 12300000
HP-0017 | Highway | STI (Prioritization) | NC 55 Bypass | SR 1114 (South Main Street) intersection | Convert existing at-grade intersection to interchange. | 2 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 24700000
HP-0018 | Highway | STI (Prioritization) | NC 55 (Apex Highway) | SR 1121 (Cornwallis Road) intersection | Construct intersection improvements. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1000000
HP-0018 | Highway | STI (Prioritization) | NC 55 (Apex Highway) | SR 1121 (Cornwallis Road) intersection | Construct intersection improvements. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0018 | Highway | STI (Prioritization) | NC 55 (Apex Highway) | SR 1121 (Cornwallis Road) intersection | Construct intersection improvements. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 1500000
HP-0019 | Highway | STI (Prioritization) | NC 211 (North Roberts Avenue) | SR 1531 (Saddletree Road / Clybourn Church Road) intersection in Lumberton | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 600000
HP-0019 | Highway | STI (Prioritization) | NC 211 (North Roberts Avenue) | SR 1531 (Saddletree Road / Clybourn Church Road) intersection in Lumberton | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 700000
HP-0019 | Highway | STI (Prioritization) | NC 211 (North Roberts Avenue) | SR 1531 (Saddletree Road / Clybourn Church Road) intersection in Lumberton | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4000000
HP-0020 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (Nursery Road) to SR 1451 (Manchester Road). | Widen roadway. | 3.23 | Cumberland, Harnett | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 28300000
HP-0020 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (Nursery Road) to SR 1451 (Manchester Road). | Widen roadway. | 3.23 | Cumberland, Harnett | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 2600000
HP-0020 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (Nursery Road) to SR 1451 (Manchester Road). | Widen roadway. | 3.23 | Cumberland, Harnett | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 33300000
HP-0021 | Highway | STI (Prioritization) | Various | Locations in Henderson | Install citywide signal system. | 9.71 | Vance | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 300000
HP-0021 | Highway | STI (Prioritization) | Various | Locations in Henderson | Install citywide signal system. | 9.71 | Vance | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4736000
HP-0022 | Highway | STI (Prioritization) | NC 49 (Maple Avenue) | I-85 / I-40 to NC 54 (Chapel Hill Road) intersection | Relocate NC 49 (Maple Avenue) on new alignment, and construct signalized intersection at Plaza Drive and Plantation Drive. | 1 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | RIGHT-OF-WAY | 1400000
HP-0022 | Highway | STI (Prioritization) | NC 49 (Maple Avenue) | I-85 / I-40 to NC 54 (Chapel Hill Road) intersection | Relocate NC 49 (Maple Avenue) on new alignment, and construct signalized intersection at Plaza Drive and Plantation Drive. | 1 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | UTILITIES | 1000000
HP-0022 | Highway | STI (Prioritization) | NC 49 (Maple Avenue) | I-85 / I-40 to NC 54 (Chapel Hill Road) intersection | Relocate NC 49 (Maple Avenue) on new alignment, and construct signalized intersection at Plaza Drive and Plantation Drive. | 1 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | CONSTRUCTION | 4200000
HP-0023 | Highway | STI (Prioritization) | US 158 | NC 801 Intersection in Bermuda Run | Upgrade intersection with left turn lane on eastbound US 158, right thru lane, and right turn lane on NC 801. | 0.5 | Davie | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 3600000
HP-0023 | Highway | STI (Prioritization) | US 158 | NC 801 Intersection in Bermuda Run | Upgrade intersection with left turn lane on eastbound US 158, right thru lane, and right turn lane on NC 801. | 0.5 | Davie | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 600000
HP-0023 | Highway | STI (Prioritization) | US 158 | NC 801 Intersection in Bermuda Run | Upgrade intersection with left turn lane on eastbound US 158, right thru lane, and right turn lane on NC 801. | 0.5 | Davie | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3100000
HP-0024 | Highway | STI (Prioritization) | US 401 | SR 5056 / SR 2768 (Judd Parkway) to NC 55 / NC 42 (Five Points inersection) | Construct access management improvements. | 1.18 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 3500000
HP-0024 | Highway | STI (Prioritization) | US 401 | SR 5056 / SR 2768 (Judd Parkway) to NC 55 / NC 42 (Five Points inersection) | Construct access management improvements. | 1.18 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 470000
HP-0024 | Highway | STI (Prioritization) | US 401 | SR 5056 / SR 2768 (Judd Parkway) to NC 55 / NC 42 (Five Points inersection) | Construct access management improvements. | 1.18 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 5800000
HP-0025 | Highway | STI (Prioritization) | NC 98 | SR 1907; SR 1005 (Six Forks Road) intersection | Construct intersection upgrades. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2500000
HP-0025 | Highway | STI (Prioritization) | NC 98 | SR 1907; SR 1005 (Six Forks Road) intersection | Construct intersection upgrades. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0025 | Highway | STI (Prioritization) | NC 98 | SR 1907; SR 1005 (Six Forks Road) intersection | Construct intersection upgrades. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 8000000
HP-0026 | Highway | STI (Prioritization) | I 40 | US 158 (Stratford Road) | Improve westbound exit loop. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0026 | Highway | STI (Prioritization) | I 40 | US 158 (Stratford Road) | Improve westbound exit loop. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3300000
HP-0027 | Highway | STI (Prioritization) | US 52 (Future I-285) | US 421 (Salem Parkway) - Exit 109 to Exit 112 | Upgrade US 52 to Interstate standards (I-285) by widening existing facilities. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 56400000
HP-0027 | Highway | STI (Prioritization) | US 52 (Future I-285) | US 421 (Salem Parkway) - Exit 109 to Exit 112 | Upgrade US 52 to Interstate standards (I-285) by widening existing facilities. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 4200000
HP-0027 | Highway | STI (Prioritization) | US 52 (Future I-285) | US 421 (Salem Parkway) - Exit 109 to Exit 112 | Upgrade US 52 to Interstate standards (I-285) by widening existing facilities. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 317100000
HP-0028 | Highway | STI (Prioritization) | NC 152 | SR 1509 (Miller Road) intersection in China Grove | Construct roundabout. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1400000
HP-0028 | Highway | STI (Prioritization) | NC 152 | SR 1509 (Miller Road) intersection in China Grove | Construct roundabout. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0028 | Highway | STI (Prioritization) | NC 152 | SR 1509 (Miller Road) intersection in China Grove | Construct roundabout. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4200000
HP-0029 | Highway | STI (Prioritization) | NC 150 | SR 1526 (Rowan Mill Road) and SR 1526 (Sherrills Ford Road) intersections in Sherrills Ford and Salisbury | Add storage and turn lanes. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 3600000
HP-0029 | Highway | STI (Prioritization) | NC 150 | SR 1526 (Rowan Mill Road) and SR 1526 (Sherrills Ford Road) intersections in Sherrills Ford and Salisbury | Add storage and turn lanes. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 2300000
HP-0029 | Highway | STI (Prioritization) | NC 150 | SR 1526 (Rowan Mill Road) and SR 1526 (Sherrills Ford Road) intersections in Sherrills Ford and Salisbury | Add storage and turn lanes. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 14000000
HP-0030 | Highway | STI (Prioritization) | US 70 (Church Street) | NC 62 intersection | Construct intersection improvements. |  | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 700000
HP-0030 | Highway | STI (Prioritization) | US 70 (Church Street) | NC 62 intersection | Construct intersection improvements. |  | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0030 | Highway | STI (Prioritization) | US 70 (Church Street) | NC 62 intersection | Construct intersection improvements. |  | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 1200000
HP-0031 | Highway | STI (Prioritization) | US 421 | SR 1122 (Jamestown Road) intersection in Winston-Salem | Upgrade intersection, remove two-way traffic from US 421 Northbound on-ramp, and extend acceleration lane distance onto mainline. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 4300000
HP-0031 | Highway | STI (Prioritization) | US 421 | SR 1122 (Jamestown Road) intersection in Winston-Salem | Upgrade intersection, remove two-way traffic from US 421 Northbound on-ramp, and extend acceleration lane distance onto mainline. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 1500000
HP-0031 | Highway | STI (Prioritization) | US 421 | SR 1122 (Jamestown Road) intersection in Winston-Salem | Upgrade intersection, remove two-way traffic from US 421 Northbound on-ramp, and extend acceleration lane distance onto mainline. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 14900000
HP-0032 | Highway | STI (Prioritization) | US 1 | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 21300000 | FY 2027: 2130000; FY 2028: 7455000; FY 2029: 7455000; FY 2030: 2130000; FY 2031: 2130000
HP-0032 | Highway | STI (Prioritization) | US 1 | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 3300000 | FY 2027: 1100000; FY 2028: 1100000; FY 2029: 1100000
HP-0032 | Highway | STI (Prioritization) | US 1 | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 20600000 | FY 2030: 5150000; FY 2031: 7210000; FY 2032: 5150000; FY 2033: 3090000
HP-0033 | Highway | STI (Prioritization) | NC 55 | NC 210 intersection in Angier | Construct turn lanes. | 0.1 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 800000
HP-0033 | Highway | STI (Prioritization) | NC 55 | NC 210 intersection in Angier | Construct turn lanes. | 0.1 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 800000
HP-0033 | Highway | STI (Prioritization) | NC 55 | NC 210 intersection in Angier | Construct turn lanes. | 0.1 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2200000
HP-0034 | Highway | STI (Prioritization) | NC 55 | North Broad Street intersection in Angier | Construct roundabout. | 0.5 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2700000
HP-0034 | Highway | STI (Prioritization) | NC 55 | North Broad Street intersection in Angier | Construct roundabout. | 0.5 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 600000
HP-0034 | Highway | STI (Prioritization) | NC 55 | North Broad Street intersection in Angier | Construct roundabout. | 0.5 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4400000
HP-0035 | Highway | STI (Prioritization) | SR 1117 (Nursery Road) | SR 3242 (Overhills Road) intersection | Construct roundabout. | 0.5 | Harnett | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1400000
HP-0035 | Highway | STI (Prioritization) | SR 1117 (Nursery Road) | SR 3242 (Overhills Road) intersection | Construct roundabout. | 0.5 | Harnett | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 500000
HP-0035 | Highway | STI (Prioritization) | SR 1117 (Nursery Road) | SR 3242 (Overhills Road) intersection | Construct roundabout. | 0.5 | Harnett | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4200000
HP-0036 | Highway | STI (Prioritization) | US 401 | SR 1414 (Piney Grove Rawls Road) to SR 1443 (Lafayette Road) | Install traffic signals, restrict turns at Chalybeate Road, close Lafayette School Road. | 4.46 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 800000
HP-0036 | Highway | STI (Prioritization) | US 401 | SR 1414 (Piney Grove Rawls Road) to SR 1443 (Lafayette Road) | Install traffic signals, restrict turns at Chalybeate Road, close Lafayette School Road. | 4.46 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0036 | Highway | STI (Prioritization) | US 401 | SR 1414 (Piney Grove Rawls Road) to SR 1443 (Lafayette Road) | Install traffic signals, restrict turns at Chalybeate Road, close Lafayette School Road. | 4.46 | Harnett | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3800000
HP-0037 | Highway | STI (Prioritization) | NC 410 (N. Brown Street) | US 74 / 76 Business (E. Strawberry Boulevard) | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 700000
HP-0037 | Highway | STI (Prioritization) | NC 410 (N. Brown Street) | US 74 / 76 Business (E. Strawberry Boulevard) | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0037 | Highway | STI (Prioritization) | NC 410 (N. Brown Street) | US 74 / 76 Business (E. Strawberry Boulevard) | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3500000
HP-0038 | Highway | STI (Prioritization) | US 74 | SR 1800 (Blacksmith Road) intersection | Convert at-grade intersection to grade separation. | 2 | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1400000
HP-0038 | Highway | STI (Prioritization) | US 74 | SR 1800 (Blacksmith Road) intersection | Convert at-grade intersection to grade separation. | 2 | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0038 | Highway | STI (Prioritization) | US 74 | SR 1800 (Blacksmith Road) intersection | Convert at-grade intersection to grade separation. | 2 | Columbus | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 7100000
HP-0039 | Highway | STI (Prioritization) | NC 82 | Norris Road / Antioch Road intersection | Construct intersection improvements. | 0.5 | Harnett | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1400000
HP-0039 | Highway | STI (Prioritization) | NC 82 | Norris Road / Antioch Road intersection | Construct intersection improvements. | 0.5 | Harnett | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0039 | Highway | STI (Prioritization) | NC 82 | Norris Road / Antioch Road intersection | Construct intersection improvements. | 0.5 | Harnett | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4200000
HP-0040 | Highway | STI (Prioritization) | New Route | Camden Road to Hunting Ridge Road | Construct new facility. | 0.27 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 500000
HP-0040 | Highway | STI (Prioritization) | New Route | Camden Road to Hunting Ridge Road | Construct new facility. | 0.27 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 500000
HP-0040 | Highway | STI (Prioritization) | New Route | Camden Road to Hunting Ridge Road | Construct new facility. | 0.27 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9600000
HP-0041 | Highway | STI (Prioritization) | New Route | Rockfish Road to NC 59 (North Main Street) | Construct new facility. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 4800000
HP-0041 | Highway | STI (Prioritization) | New Route | Rockfish Road to NC 59 (North Main Street) | Construct new facility. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 800000
HP-0041 | Highway | STI (Prioritization) | New Route | Rockfish Road to NC 59 (North Main Street) | Construct new facility. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 17700000
HP-0042 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | Two Bale Lane to SR 1102 (Gillis Hill Road) | Widen roadway and extend on new location. | 1.08 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3900000
HP-0042 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | Two Bale Lane to SR 1102 (Gillis Hill Road) | Widen roadway and extend on new location. | 1.08 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 600000
HP-0042 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | Two Bale Lane to SR 1102 (Gillis Hill Road) | Widen roadway and extend on new location. | 1.08 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40100000
HS-2001 | Highway | Safety | Various | Routes in Division 1. | Construct safety improvements. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2001A | Highway | Safety | US 158 | US 158 and SR 1147 (Indiantown Road) Intersection. | Construct roundabout. | 0.5 | Currituck | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 40000
HS-2001A | Highway | Safety | US 158 | US 158 and SR 1147 (Indiantown Road) Intersection. | Construct roundabout. | 0.5 | Currituck | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 4000
HS-2001B | Highway | Safety | US 13; US 17; NC 171 | Various locations. | Upgrade curve warning signs. |  | Martin, Bertie | 1 | Mid-East RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 32000
HS-2001B | Highway | Safety | US 13; US 17; NC 171 | Various locations. | Upgrade curve warning signs. |  | Martin, Bertie | 1 | Mid-East RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 4000
HS-2001C | Highway | Safety | SR 1354 (Millpond Road) | US 158 to SR 1001 (Turnpike Road). | Upgrade pavement markings. | 4.42 | Pasquotank | 1 | Albemarle RPO |  | Division 1 |  | HSIP | CONSTRUCTION | 36000
HS-2001C | Highway | Safety | SR 1354 (Millpond Road) | US 158 to SR 1001 (Turnpike Road). | Upgrade pavement markings. | 4.42 | Pasquotank | 1 | Albemarle RPO |  | Division 1 |  | T(M) | CONSTRUCTION | 4000
HS-2001D | Highway | Safety | Various | Routes in Division 1. | Upgrade warning signs at curves. |  | Pasquotank, Camden, Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | HSIP | CONSTRUCTION | 37000
HS-2001D | Highway | Safety | Various | Routes in Division 1. | Upgrade warning signs at curves. |  | Pasquotank, Camden, Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) | CONSTRUCTION | 4000
HS-2001E | Highway | Safety | Various | Routes in Division 1. | Upgrade warning signs at curves. |  | Bertie, Currituck | 1 | Peanut Belt RPO, Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | HSIP | CONSTRUCTION | 11000
HS-2001E | Highway | Safety | Various | Routes in Division 1. | Upgrade warning signs at curves. |  | Bertie, Currituck | 1 | Peanut Belt RPO, Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) | CONSTRUCTION | 1000
HS-2001F | Highway | Safety | US 158 | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Currituck | 1 | Albemarle RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 317000 | FY 2028: 317000
HS-2001F | Highway | Safety | US 158 | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Currituck | 1 | Albemarle RPO |  | Region A |  | T | RIGHT-OF-WAY | 633000 | FY 2028: 633000
HS-2001F | Highway | Safety | US 158 | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Currituck | 1 | Albemarle RPO |  | Region A |  | HSIP | UTILITIES | 20000 | FY 2028: 20000
HS-2001F | Highway | Safety | US 158 | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Currituck | 1 | Albemarle RPO |  | Region A |  | T | UTILITIES | 40000 | FY 2028: 40000
HS-2001F | Highway | Safety | US 158 | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Currituck | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 1433000 | FY 2028: 1433000
HS-2001F | Highway | Safety | US 158 | US 158 and SR 1104 (Edgewater Road) intersection. | Construct U-turn bulbouts. | 0.36 | Currituck | 1 | Albemarle RPO |  | Region A |  | T | CONSTRUCTION | 2867000 | FY 2028: 2867000
HS-2001G | Highway | Safety | US 13; NC 11 / SR 1212 (Shortcut Road) | SR 1302 (Lea Lumber Company Road) in Bertie County to north of SR 1418 (Arrow Road) in Hertford County, and SR 1212 (Shortcut Road) in Hertford County to US 158 in Gates County; 450 feet south of SR 1130 (Modlin Road) to US 13. | Install rumble stripes and pavement markings. | 22.2 | Bertie, Hertford, Gates | 1 | Peanut Belt RPO, Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 806000
HS-2001G | Highway | Safety | US 13; NC 11 / SR 1212 (Shortcut Road) | SR 1302 (Lea Lumber Company Road) in Bertie County to north of SR 1418 (Arrow Road) in Hertford County, and SR 1212 (Shortcut Road) in Hertford County to US 158 in Gates County; 450 feet south of SR 1130 (Modlin Road) to US 13. | Install rumble stripes and pavement markings. | 22.2 | Bertie, Hertford, Gates | 1 | Peanut Belt RPO, Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 90000
HS-2001H | Highway | Safety | US 64 | East of SR 1326 (Keiser Drive) to SR 1229 (Old Highway 64) intersection. | Install rumble stripes. | 5.19 | Tyrrell | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 225000
HS-2001H | Highway | Safety | US 64 | East of SR 1326 (Keiser Drive) to SR 1229 (Old Highway 64) intersection. | Install rumble stripes. | 5.19 | Tyrrell | 1 | Albemarle RPO |  | Region A |  | T(M) | CONSTRUCTION | 25000
HS-2001I | Highway | Safety | NC 344 | South of airport entrance to SR 1100 (Sawmill Road). | Install rumble stripes and pavement markings. | 3.72 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 144000
HS-2001I | Highway | Safety | NC 344 | South of airport entrance to SR 1100 (Sawmill Road). | Install rumble stripes and pavement markings. | 3.72 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | T(M) | CONSTRUCTION | 16000
HS-2002 | Highway | Safety | Various | Routes in Division 2. | Construct safety improvements. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2002A | Highway | Safety | SR 1703 (14th Street) | Haskett Way to Berkley Road. | Install crosswalk, wheelchair ramps, sidewalk, fence, and remove crosswalks. | 0.09 | Pitt | 2 | Greenville Urban Area MPO | COMPLETE. | Division 2 |  | HSIP | CONSTRUCTION | 45000
HS-2002A | Highway | Safety | SR 1703 (14th Street) | Haskett Way to Berkley Road. | Install crosswalk, wheelchair ramps, sidewalk, fence, and remove crosswalks. | 0.09 | Pitt | 2 | Greenville Urban Area MPO | COMPLETE. | Division 2 |  | T(M) | CONSTRUCTION | 5000
HS-2002AA | Highway | Safety | NC 58 | East of Lee Drive in Atlantic Beach. | Install rectangular rapid flashing beacons. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 29000
HS-2002AA | Highway | Safety | NC 58 | East of Lee Drive in Atlantic Beach. | Install rectangular rapid flashing beacons. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 3000
HS-2002AB | Highway | Safety | US 70 | SR 1174 (Turner Street) intersection in Beaufort. | Install pedestrian signal heads at existing crosswalks. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 50000
HS-2002AB | Highway | Safety | US 70 | SR 1174 (Turner Street) intersection in Beaufort. | Install pedestrian signal heads at existing crosswalks. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 6000
HS-2002AC | Highway | Safety | US 70 | SR 1300 (Merrimon Road) intersection. | Upgrade traffic signal. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 22000
HS-2002AC | Highway | Safety | US 70 | SR 1300 (Merrimon Road) intersection. | Upgrade traffic signal. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 2000
HS-2002AD | Highway | Safety | NC 55 | West of NC 903 to NC 11. | Install rumble stripes. | 11.76 | Lenoir, Wayne | 2, 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region A, B |  | HSIP | CONSTRUCTION | 342000
HS-2002AD | Highway | Safety | NC 55 | West of NC 903 to NC 11. | Install rumble stripes. | 11.76 | Lenoir, Wayne | 2, 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region A, B |  | T(M) | CONSTRUCTION | 38000
HS-2002AE | Highway | Safety | US 70 (Future I-42) / US 258 (West Vernon Avenue) | East of US 258 in Kinston. | Remove eastbound left-over. | 0.5 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 184000
HS-2002AE | Highway | Safety | US 70 (Future I-42) / US 258 (West Vernon Avenue) | East of US 258 in Kinston. | Remove eastbound left-over. | 0.5 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | T(M) | CONSTRUCTION | 20000
HS-2002AF | Highway | Safety | US 70 (Future I-42) | Gladys Teasley Lane to SR 1753 (Arthur Farm Road) in Morehead City. | Construct reduced conflict intersection. | 0.65 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | UTILITIES | 135000
HS-2002AF | Highway | Safety | US 70 (Future I-42) | Gladys Teasley Lane to SR 1753 (Arthur Farm Road) in Morehead City. | Construct reduced conflict intersection. | 0.65 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | UTILITIES | 15000
HS-2002AF | Highway | Safety | US 70 (Future I-42) | Gladys Teasley Lane to SR 1753 (Arthur Farm Road) in Morehead City. | Construct reduced conflict intersection. | 0.65 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 960000
HS-2002AF | Highway | Safety | US 70 (Future I-42) | Gladys Teasley Lane to SR 1753 (Arthur Farm Road) in Morehead City. | Construct reduced conflict intersection. | 0.65 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 240000
HS-2002AG | Highway | Safety | US 70 (Future I-42) | SR 1002 (Wyse Fork Road) / SR 1309 (Caswell Station Road) intersection. | Construct reduced conflict intersection. | 0.5 | Jones | 2 | Down East RPO |  | Region B |  | HSIP | UTILITIES | 27000
HS-2002AG | Highway | Safety | US 70 (Future I-42) | SR 1002 (Wyse Fork Road) / SR 1309 (Caswell Station Road) intersection. | Construct reduced conflict intersection. | 0.5 | Jones | 2 | Down East RPO |  | Region B |  | T(M) | UTILITIES | 3000
HS-2002AG | Highway | Safety | US 70 (Future I-42) | SR 1002 (Wyse Fork Road) / SR 1309 (Caswell Station Road) intersection. | Construct reduced conflict intersection. | 0.5 | Jones | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 868000
HS-2002AG | Highway | Safety | US 70 (Future I-42) | SR 1002 (Wyse Fork Road) / SR 1309 (Caswell Station Road) intersection. | Construct reduced conflict intersection. | 0.5 | Jones | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 96000
HS-2002AH | Highway | Safety | US 264 Alternate (Greenville Boulevard) | South of Luci Drive to NC 33 (10th Street) in Greenville. | Construct pedestrian improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | UTILITIES | 112000
HS-2002AH | Highway | Safety | US 264 Alternate (Greenville Boulevard) | South of Luci Drive to NC 33 (10th Street) in Greenville. | Construct pedestrian improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | T(M) | UTILITIES | 12000
HS-2002AH | Highway | Safety | US 264 Alternate (Greenville Boulevard) | South of Luci Drive to NC 33 (10th Street) in Greenville. | Construct pedestrian improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 288000
HS-2002AH | Highway | Safety | US 264 Alternate (Greenville Boulevard) | South of Luci Drive to NC 33 (10th Street) in Greenville. | Construct pedestrian improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 32000
HS-2002AI | Highway | Safety | US 70 | NC 101 intersection in Beaufort. | Upgrade traffic signal. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 50000
HS-2002AI | Highway | Safety | US 70 | NC 101 intersection in Beaufort. | Upgrade traffic signal. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 6000
HS-2002B | Highway | Safety | NC 24 | SR 1259 (Taylor Notion Road) to US 70. | Install rumble stripes and pavement markings. | 15.07 | Carteret | 2 | Down East RPO | COMPLETE. | Statewide Mobility |  | HSIP | CONSTRUCTION | 576000
HS-2002B | Highway | Safety | NC 24 | SR 1259 (Taylor Notion Road) to US 70. | Install rumble stripes and pavement markings. | 15.07 | Carteret | 2 | Down East RPO | COMPLETE. | Statewide Mobility |  | T(M) | CONSTRUCTION | 64000
HS-2002C | Highway | Safety | US 70 (Future I-42) | SR 1324 (Kennedy Home Road) / SR 1519 (Eason Road) intersection and adjacent crossover to the west. | Construct restricted crossing intersections. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | UTILITIES | 18000
HS-2002C | Highway | Safety | US 70 (Future I-42) | SR 1324 (Kennedy Home Road) / SR 1519 (Eason Road) intersection and adjacent crossover to the west. | Construct restricted crossing intersections. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | UTILITIES | 2000
HS-2002C | Highway | Safety | US 70 (Future I-42) | SR 1324 (Kennedy Home Road) / SR 1519 (Eason Road) intersection and adjacent crossover to the west. | Construct restricted crossing intersections. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 225000
HS-2002C | Highway | Safety | US 70 (Future I-42) | SR 1324 (Kennedy Home Road) / SR 1519 (Eason Road) intersection and adjacent crossover to the west. | Construct restricted crossing intersections. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 25000
HS-2002D | Highway | Safety | US 264 | SR 1410 (Voa Road) intersection. | Construct reduced conflict intersection. | 0.5 | Beaufort | 2 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 14000
HS-2002D | Highway | Safety | US 264 | SR 1410 (Voa Road) intersection. | Construct reduced conflict intersection. | 0.5 | Beaufort | 2 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 2000
HS-2002D | Highway | Safety | US 264 | SR 1410 (Voa Road) intersection. | Construct reduced conflict intersection. | 0.5 | Beaufort | 2 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 845000
HS-2002D | Highway | Safety | US 264 | SR 1410 (Voa Road) intersection. | Construct reduced conflict intersection. | 0.5 | Beaufort | 2 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 94000
HS-2002E | Highway | Safety | US 264 Alternate (Greenville Boulevard) | SR 1534 (Old Pactolus Road) intersection. | Construct restricted-crossing intersection. | 0.48 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 794000
HS-2002E | Highway | Safety | US 264 Alternate (Greenville Boulevard) | SR 1534 (Old Pactolus Road) intersection. | Construct restricted-crossing intersection. | 0.48 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 88000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (Main Street) | SR 1005 (Sunset Boulevard) Intersection. | Install all way stop and channelization, and revise overhead flasher. | 1 | Craven | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HSIP | RIGHT-OF-WAY | 14000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (Main Street) | SR 1005 (Sunset Boulevard) Intersection. | Install all way stop and channelization, and revise overhead flasher. | 1 | Craven | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | T(M) | RIGHT-OF-WAY | 2000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (Main Street) | SR 1005 (Sunset Boulevard) Intersection. | Install all way stop and channelization, and revise overhead flasher. | 1 | Craven | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HSIP | CONSTRUCTION | 52000 | FY 2026: 52000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (Main Street) | SR 1005 (Sunset Boulevard) Intersection. | Install all way stop and channelization, and revise overhead flasher. | 1 | Craven | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 6000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (Main Street) | SR 1005 (Sunset Boulevard) Intersection. | Install all way stop and channelization, and revise overhead flasher. | 1 | Craven | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HF | CONSTRUCTION | 55000 | FY 2026: 55000
HS-2002G | Highway | Safety | NC 58 (Salter Path Road) | West of Tradewinds Drive. | Install crosswalk with rapid flashing beacons. | 0.5 | Carteret | 2 | Down East RPO | COMPLETE. | Region B |  | HSIP | CONSTRUCTION | 22000
HS-2002G | Highway | Safety | NC 58 (Salter Path Road) | West of Tradewinds Drive. | Install crosswalk with rapid flashing beacons. | 0.5 | Carteret | 2 | Down East RPO | COMPLETE. | Region B |  | T(M) | CONSTRUCTION | 2000
HS-2002H | Highway | Safety | NC 58 (West Fort Macon Road) | Atlantic Station Shopping Center / Atlantic Beach Town Park. | Install pedestrian heads and wheel chair ramp revisions. | 0.5 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 11000
HS-2002H | Highway | Safety | NC 58 (West Fort Macon Road) | Atlantic Station Shopping Center / Atlantic Beach Town Park. | Install pedestrian heads and wheel chair ramp revisions. | 0.5 | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 1000
HS-2002I | Highway | Safety | NC 58 | West of Cedar Lane. | Install crosswalks, concrete pedestrian island, sidewalks, and rectangular rapid-flashing beacons. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 86000
HS-2002I | Highway | Safety | NC 58 | West of Cedar Lane. | Install crosswalks, concrete pedestrian island, sidewalks, and rectangular rapid-flashing beacons. | 0.5 | Carteret | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 10000
HS-2002J | Highway | Safety | NC 33 | US 13 / NC 11 (Memorial Drive) to Daughtridge Drive in Greenville. | Install median island and revise pavement markings. | 0.07 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 108000
HS-2002J | Highway | Safety | NC 33 | US 13 / NC 11 (Memorial Drive) to Daughtridge Drive in Greenville. | Install median island and revise pavement markings. | 0.07 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 12000
HS-2002K | Highway | Safety | NC 11 | SR 1716 (Harvey Rouse Road), NC 118 / SR 1091 (Grifton-Hugo Road), and SR 1714 (Creek Road) intersections. | Construct reduced conflict intersection. | 0.68 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | UTILITIES | 72000
HS-2002K | Highway | Safety | NC 11 | SR 1716 (Harvey Rouse Road), NC 118 / SR 1091 (Grifton-Hugo Road), and SR 1714 (Creek Road) intersections. | Construct reduced conflict intersection. | 0.68 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | UTILITIES | 8000
HS-2002K | Highway | Safety | NC 11 | SR 1716 (Harvey Rouse Road), NC 118 / SR 1091 (Grifton-Hugo Road), and SR 1714 (Creek Road) intersections. | Construct reduced conflict intersection. | 0.68 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 1112000
HS-2002K | Highway | Safety | NC 11 | SR 1716 (Harvey Rouse Road), NC 118 / SR 1091 (Grifton-Hugo Road), and SR 1714 (Creek Road) intersections. | Construct reduced conflict intersection. | 0.68 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 124000
HS-2002L | Highway | Safety | US 264 Alternate (Greenville Boulevard) | NC 11 / NC 43 / NC 903 (Memorial Drive) intersection, and NC 11 / NC 903 (Memorial Drive) and Mall Drive intersection in Greenville. | Construct turn lanes. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 806000
HS-2002L | Highway | Safety | US 264 Alternate (Greenville Boulevard) | NC 11 / NC 43 / NC 903 (Memorial Drive) intersection, and NC 11 / NC 903 (Memorial Drive) and Mall Drive intersection in Greenville. | Construct turn lanes. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 90000
HS-2002M | Highway | Safety | SR 1598 (10th Street) | College Hill Drive and Elm Street intersections in Greenville. | Upgrade traffic signal. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HSIP | CONSTRUCTION | 50000
HS-2002M | Highway | Safety | SR 1598 (10th Street) | College Hill Drive and Elm Street intersections in Greenville. | Upgrade traffic signal. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | T(M) | CONSTRUCTION | 6000
HS-2002N | Highway | Safety | US 258 | SR 1342 (Will Baker Road / Central Avenue) intersection. | Upgrade traffic signal and install flasher. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 78000
HS-2002N | Highway | Safety | US 258 | SR 1342 (Will Baker Road / Central Avenue) intersection. | Upgrade traffic signal and install flasher. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 8000
HS-2002O | Highway | Safety | US 17 Business (Martin Luther King Jr. Boulevard) | Trent Creek Road Intersection. | Install Flasher. | 0.5 | Craven | 2 | New Bern Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 38000
HS-2002O | Highway | Safety | US 17 Business (Martin Luther King Jr. Boulevard) | Trent Creek Road Intersection. | Install Flasher. | 0.5 | Craven | 2 | New Bern Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 4000
HS-2002P | Highway | Safety | US 258 | SR 1120 (Nobles Mill Road) and SR 1908 (Bill Stroud Road) intersections. | Construct turn lanes. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | Region B |  | HSIP | UTILITIES | 135000
HS-2002P | Highway | Safety | US 258 | SR 1120 (Nobles Mill Road) and SR 1908 (Bill Stroud Road) intersections. | Construct turn lanes. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | Region B |  | T(M) | UTILITIES | 15000
HS-2002P | Highway | Safety | US 258 | SR 1120 (Nobles Mill Road) and SR 1908 (Bill Stroud Road) intersections. | Construct turn lanes. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | Region B |  | HSIP | CONSTRUCTION | 595000
HS-2002P | Highway | Safety | US 258 | SR 1120 (Nobles Mill Road) and SR 1908 (Bill Stroud Road) intersections. | Construct turn lanes. | 0.5 | Lenoir | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | Region B |  | T(M) | CONSTRUCTION | 66000
HS-2002Q | Highway | Safety | US 258 | NC 24 to US 70 in Kinston. | Install rumble stripes. | 25.07 | Lenoir, Onslow, Jones | 2, 3 | Eastern Carolina RPO, Jacksonville Urban Area MPO, Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 527000 | FY 2026: 228000
HS-2002Q | Highway | Safety | US 258 | NC 24 to US 70 in Kinston. | Install rumble stripes. | 25.07 | Lenoir, Onslow, Jones | 2, 3 | Eastern Carolina RPO, Jacksonville Urban Area MPO, Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 58000 | FY 2026: 25000
HS-2002R | Highway | Safety | SR 1702 (Evans Street) | Howell Street intersection in Greenville. | Install traffic signal with pedestrian accommodations. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | UTILITIES | 58000
HS-2002R | Highway | Safety | SR 1702 (Evans Street) | Howell Street intersection in Greenville. | Install traffic signal with pedestrian accommodations. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | T(M) | UTILITIES | 6000
HS-2002R | Highway | Safety | SR 1702 (Evans Street) | Howell Street intersection in Greenville. | Install traffic signal with pedestrian accommodations. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 360000
HS-2002R | Highway | Safety | SR 1702 (Evans Street) | Howell Street intersection in Greenville. | Install traffic signal with pedestrian accommodations. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | T(M) | CONSTRUCTION | 40000
HS-2002S | Highway | Safety | NC 43 | NC 118 in Craven County to SR 1730 (Herman Garris Road) in Pitt County, and SR 1205 (Rock Spring Road) to southern limits of Falkland, and northern limits of Falkland in Pitt County to NC 42 in Edgecombe County. | Install rumble stripes and pavement markings. | 33.01 | Pitt, Craven, Edgecombe | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Down East RPO, Upper Coastal Plain RPO |  | Region A, B |  | HSIP | CONSTRUCTION | 734000
HS-2002S | Highway | Safety | NC 43 | NC 118 in Craven County to SR 1730 (Herman Garris Road) in Pitt County, and SR 1205 (Rock Spring Road) to southern limits of Falkland, and northern limits of Falkland in Pitt County to NC 42 in Edgecombe County. | Install rumble stripes and pavement markings. | 33.01 | Pitt, Craven, Edgecombe | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Down East RPO, Upper Coastal Plain RPO |  | Region A, B |  | T(M) | CONSTRUCTION | 82000
HS-2002T | Highway | Safety | US 264 | Wilson County line to SR 1128 (Davenport Farm Road) / SR 1206 (Bell Arthur Road) in Pitt County. | Install rumble stripes. | 11.76 | Pitt, Greene | 2 | Mid-East RPO, Eastern Carolina RPO, Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 340000
HS-2002T | Highway | Safety | US 264 | Wilson County line to SR 1128 (Davenport Farm Road) / SR 1206 (Bell Arthur Road) in Pitt County. | Install rumble stripes. | 11.76 | Pitt, Greene | 2 | Mid-East RPO, Eastern Carolina RPO, Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 38000
HS-2002U | Highway | Safety | SR 1310 (Lennoxville Road) | Carteret Avenue intersection in Beaufort. | Install crosswalk signalization. |  | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 22000
HS-2002U | Highway | Safety | SR 1310 (Lennoxville Road) | Carteret Avenue intersection in Beaufort. | Install crosswalk signalization. |  | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. | Division 2 |  | T(M) | CONSTRUCTION | 2000
HS-2002V | Highway | Safety | NC 55 (Neuse Boulevard) | SR 1215 (Simmons Street) intersection in New Bern. | Install pedestrian signals and crosswalks. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 16000
HS-2002V | Highway | Safety | NC 55 (Neuse Boulevard) | SR 1215 (Simmons Street) intersection in New Bern. | Install pedestrian signals and crosswalks. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 2000
HS-2002W | Highway | Safety | NC 55 (Neuse Boulevard) | SR 1309 / SR 1402 (Glenburnie Road) in New Bern. | Install pedestrian signals and crosswalks. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 16000
HS-2002W | Highway | Safety | NC 55 (Neuse Boulevard) | SR 1309 / SR 1402 (Glenburnie Road) in New Bern. | Install pedestrian signals and crosswalks. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 2000
HS-2002X | Highway | Safety | SR 1725 (County Home Road) | Crosswalk south of District Park Drive in Greenville. | Install rectangular rapid flashing beacons. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 32000
HS-2002X | Highway | Safety | SR 1725 (County Home Road) | Crosswalk south of District Park Drive in Greenville. | Install rectangular rapid flashing beacons. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | T(M) | CONSTRUCTION | 4000
HS-2002Y | Highway | Safety | NC 55 (Neuse Boulevard) | Fort Totten Drive and First Street intersections. | Upgrade traffic signals and install pedestrian heads. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 68000
HS-2002Y | Highway | Safety | NC 55 (Neuse Boulevard) | Fort Totten Drive and First Street intersections. | Upgrade traffic signals and install pedestrian heads. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 8000
HS-2002Z | Highway | Safety | SR 1131 (Reedy Branch Road) | Bulldog Run and Eddie Smith Street intersections in Winterville. | Install rectangular rapid flashing beacons. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 50000
HS-2002Z | Highway | Safety | SR 1131 (Reedy Branch Road) | Bulldog Run and Eddie Smith Street intersections in Winterville. | Install rectangular rapid flashing beacons. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | T(M) | CONSTRUCTION | 6000
HS-2003 | Highway | Safety | Various | Routes in Division 3 | Construct safety improvements. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2003A | Highway | Safety | SR 1217 (17th Street) | Dock Street intersection in Wilmington. | Install signal heads. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 75000
HS-2003A | Highway | Safety | SR 1217 (17th Street) | Dock Street intersection in Wilmington. | Install signal heads. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T(M) | CONSTRUCTION | 8000
HS-2003AA | Highway | Safety | SR 1308 (Bell Fork Road) | Brynn Marr Road intersection. | Upgrade traffic signal, signing, and pavement markings. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | HSIP | RIGHT-OF-WAY | 113000
HS-2003AA | Highway | Safety | SR 1308 (Bell Fork Road) | Brynn Marr Road intersection. | Upgrade traffic signal, signing, and pavement markings. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T(M) | RIGHT-OF-WAY | 13000
HS-2003AA | Highway | Safety | SR 1308 (Bell Fork Road) | Brynn Marr Road intersection. | Upgrade traffic signal, signing, and pavement markings. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | HSIP | CONSTRUCTION | 221000 | FY 2026: 221000
HS-2003AA | Highway | Safety | SR 1308 (Bell Fork Road) | Brynn Marr Road intersection. | Upgrade traffic signal, signing, and pavement markings. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T(M) | CONSTRUCTION | 25000 | FY 2026: 25000
HS-2003AB | Highway | Safety | SR 1428 (Riggs Road) | Nautical Wave Road to SR 1744 (Hubert Boulevard). | Install pavement markings. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 66000
HS-2003AB | Highway | Safety | SR 1428 (Riggs Road) | Nautical Wave Road to SR 1744 (Hubert Boulevard). | Install pavement markings. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T(M) | CONSTRUCTION | 5000
HS-2003AC | Highway | Safety | US 117 | SR 1411 (Ashton Road / Old River Road) intersection. | Install traffic signal. | 0.5 | Pender | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 292000
HS-2003AC | Highway | Safety | US 117 | SR 1411 (Ashton Road / Old River Road) intersection. | Install traffic signal. | 0.5 | Pender | 3 | Cape Fear RPO |  | Region B |  | T(M) | CONSTRUCTION | 32000
HS-2003AD | Highway | Safety | US 117 / NC 132 (College Road) | Crews Drive intersection. | Upgrade traffic signal and install signalized pedestrian crossings. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 221000 | FY 2026: 24000
HS-2003AD | Highway | Safety | US 117 / NC 132 (College Road) | Crews Drive intersection. | Upgrade traffic signal and install signalized pedestrian crossings. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 25000 | FY 2026: 3000
HS-2003AE | Highway | Safety | US 117 / NC 132 (College Road) | SR 1411 (Wrightsville Avenue) intersection in Wilmington. | Install Crosswalks and pedestrian countdown heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 99000
HS-2003AE | Highway | Safety | US 117 / NC 132 (College Road) | SR 1411 (Wrightsville Avenue) intersection in Wilmington. | Install Crosswalks and pedestrian countdown heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 11000
HS-2003AF | Highway | Safety | US 17 Business (Marine Boulevard) | SR 1308 (Gum Branch Road / Bell Fork Road) intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 74000
HS-2003AF | Highway | Safety | US 17 Business (Marine Boulevard) | SR 1308 (Gum Branch Road / Bell Fork Road) intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 8000
HS-2003AG | Highway | Safety | US 17 Business (Marine Boulevard) | SR 1336 (Onslow Drive) intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 130000
HS-2003AG | Highway | Safety | US 17 Business (Marine Boulevard) | SR 1336 (Onslow Drive) intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 14000
HS-2003AH | Highway | Safety | US 117 (Future I-785) | I-40 in Sampson County to Wayne County line. | Install guardrail. | 6.95 | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 456000
HS-2003AH | Highway | Safety | US 117 (Future I-785) | I-40 in Sampson County to Wayne County line. | Install guardrail. | 6.95 | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 51000
HS-2003AI | Highway | Safety | US 117/NC 132 (College Road) | SR 2160 (Long Ridge Road) intersection. | Install traffic signal with pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 518000 | FY 2026: 518000
HS-2003AI | Highway | Safety | US 117/NC 132 (College Road) | SR 2160 (Long Ridge Road) intersection. | Install traffic signal with pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 58000 | FY 2026: 58000
HS-2003AJ | Highway | Safety | US 17 (Marine Boulevard) | Henderson Drive intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 46000
HS-2003AJ | Highway | Safety | US 17 (Marine Boulevard) | Henderson Drive intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | T(M) | RIGHT-OF-WAY | 5000
HS-2003AJ | Highway | Safety | US 17 (Marine Boulevard) | Henderson Drive intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 143000 | FY 2026: 2000; FY 2027: 141000
HS-2003AJ | Highway | Safety | US 17 (Marine Boulevard) | Henderson Drive intersection in Jacksonville. | Construct safety improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 16000 | FY 2026: 0; FY 2027: 16000
HS-2003AK | Highway | Safety | SR 1301 (Princess Place Drive) | North 30th Street intersection in Wilmington. | Construct safety improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | HSIP | RIGHT-OF-WAY | 14000
HS-2003AK | Highway | Safety | SR 1301 (Princess Place Drive) | North 30th Street intersection in Wilmington. | Construct safety improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T(M) | RIGHT-OF-WAY | 2000
HS-2003AK | Highway | Safety | SR 1301 (Princess Place Drive) | North 30th Street intersection in Wilmington. | Construct safety improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | HSIP | CONSTRUCTION | 136000 | FY 2026: 136000
HS-2003AK | Highway | Safety | SR 1301 (Princess Place Drive) | North 30th Street intersection in Wilmington. | Construct safety improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T(M) | CONSTRUCTION | 15000 | FY 2026: 15000
HS-2003AL | Highway | Safety | US 117 | NC 53 intersection in Burgaw. | Upgrade traffic signal. | 0.5 | Pender | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 11000
HS-2003AL | Highway | Safety | US 117 | NC 53 intersection in Burgaw. | Upgrade traffic signal. | 0.5 | Pender | 3 | Cape Fear RPO |  | Region B |  | T(M) | CONSTRUCTION | 1000
HS-2003AM | Highway | Safety | NC 53 (Western Boulevard) | Forum Road / Marty Goldman Way intersection in Jacksonville. | Install Crosswalks and pedestrian signals. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 160000
HS-2003AM | Highway | Safety | NC 53 (Western Boulevard) | Forum Road / Marty Goldman Way intersection in Jacksonville. | Install Crosswalks and pedestrian signals. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 18000
HS-2003AN | Highway | Safety | US 17 / US 76 (Dawson Street and Wooster Street) | SR 1216 (16th Street) and SR 1217 (17th Street) intersections in Wilmington. | Upgrade traffic signal, crosswalks, and pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 132000
HS-2003AN | Highway | Safety | US 17 / US 76 (Dawson Street and Wooster Street) | SR 1216 (16th Street) and SR 1217 (17th Street) intersections in Wilmington. | Upgrade traffic signal, crosswalks, and pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 15000
HS-2003AO | Highway | Safety | SR 1175(Kerr Avenue) | SR 2048 (Gordon Road) / SR 1327 (Farley Drive) intersection. | Upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 30000
HS-2003AO | Highway | Safety | SR 1175(Kerr Avenue) | SR 2048 (Gordon Road) / SR 1327 (Farley Drive) intersection. | Upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T(M) | CONSTRUCTION | 3000
HS-2003AP | Highway | Safety | SR 1302 (23rd Street) | SR 1301 (Princess Place Drive) intersection in Wilmington. | Upgrade traffic signals and install pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 176000
HS-2003AP | Highway | Safety | SR 1302 (23rd Street) | SR 1301 (Princess Place Drive) intersection in Wilmington. | Upgrade traffic signals and install pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 20000
HS-2003AQ | Highway | Safety | SR 2817 (17th Street) | Castle Street intersection in Wilmington. | Upgrade traffic signals and install pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 342000
HS-2003AQ | Highway | Safety | SR 2817 (17th Street) | Castle Street intersection in Wilmington. | Upgrade traffic signals and install pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T(M) | CONSTRUCTION | 38000
HS-2003AR | Highway | Safety | US 17 Business | NC 906 (Midway Road) intersection. | Install traffic signal. | 0.5 | Brunswick | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | HSIP | RIGHT-OF-WAY | 43000
HS-2003AR | Highway | Safety | US 17 Business | NC 906 (Midway Road) intersection. | Install traffic signal. | 0.5 | Brunswick | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T(M) | RIGHT-OF-WAY | 5000
HS-2003AR | Highway | Safety | US 17 Business | NC 906 (Midway Road) intersection. | Install traffic signal. | 0.5 | Brunswick | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | HSIP | CONSTRUCTION | 232000 | FY 2026: 3000; FY 2027: 229000
HS-2003AR | Highway | Safety | US 17 Business | NC 906 (Midway Road) intersection. | Install traffic signal. | 0.5 | Brunswick | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T(M) | CONSTRUCTION | 25000 | FY 2026: 0; FY 2027: 25000
HS-2003AS | Highway | Safety | US 74 / US 76 (Andrew Jackson Highway) | SR 1426 (Lanvale Road) eastbound ramp. | Install traffic signal. | 0.5 | Brunswick | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 405000
HS-2003AS | Highway | Safety | US 74 / US 76 (Andrew Jackson Highway) | SR 1426 (Lanvale Road) eastbound ramp. | Install traffic signal. | 0.5 | Brunswick | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 45000
HS-2003AT | Highway | Safety | NC 24 | SR 1445 (Norris Road) intersection in Swansboro. | Install ramps and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | HSIP | RIGHT-OF-WAY | 112000
HS-2003AT | Highway | Safety | NC 24 | SR 1445 (Norris Road) intersection in Swansboro. | Install ramps and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T(M) | RIGHT-OF-WAY | 12000
HS-2003AT | Highway | Safety | NC 24 | SR 1445 (Norris Road) intersection in Swansboro. | Install ramps and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | HSIP | CONSTRUCTION | 292000 | FY 2026: 292000
HS-2003AT | Highway | Safety | NC 24 | SR 1445 (Norris Road) intersection in Swansboro. | Install ramps and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T(M) | CONSTRUCTION | 32000 | FY 2026: 32000
HS-2003B | Highway | Safety | Various | Routes in Division 3. | Install pavement markings. |  | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | HSIP | CONSTRUCTION | 3089000
HS-2003B | Highway | Safety | Various | Routes in Division 3. | Install pavement markings. |  | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | T(M) | CONSTRUCTION | 343000
HS-2003C | Highway | Safety | SR 1535 (Liddell Road) | SR 1534 (Drummersville Road) intersection. | Install all way stop. | 0.5 | Duplin | 3 | Eastern Carolina RPO |  | Division 3 |  | HSIP | CONSTRUCTION | 18000
HS-2003C | Highway | Safety | SR 1535 (Liddell Road) | SR 1534 (Drummersville Road) intersection. | Install all way stop. | 0.5 | Duplin | 3 | Eastern Carolina RPO |  | Division 3 |  | T(M) | CONSTRUCTION | 2000
HS-2003D | Highway | Safety | US 17 (Future I-74) | SR 1130 (Mount Pisgah Road) / SR 1344 (Sellers Road) intersection. | Install signalized leftover. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 242000 | FY 2026: 242000
HS-2003D | Highway | Safety | US 17 (Future I-74) | SR 1130 (Mount Pisgah Road) / SR 1344 (Sellers Road) intersection. | Install signalized leftover. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 27000 | FY 2026: 27000
HS-2003E | Highway | Safety | US 117 (Sycamore Street) | SR 1102 (Charity Road) intersection in Rose Hill. | Revise traffic signal and pavement markings. | 0.5 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 92000
HS-2003E | Highway | Safety | US 117 (Sycamore Street) | SR 1102 (Charity Road) intersection in Rose Hill. | Revise traffic signal and pavement markings. | 0.5 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 10000
HS-2003F | Highway | Safety | US 17 | NC 210 intersection in Surf City. | Revise traffic signal and install traffic signs. | 0.5 | Pender | 3 | Cape Fear RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 244000
HS-2003F | Highway | Safety | US 17 | NC 210 intersection in Surf City. | Revise traffic signal and install traffic signs. | 0.5 | Pender | 3 | Cape Fear RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 27000
HS-2003G | Highway | Safety | NC 130 | SR 1120 (Sabbath Home Road) / SR 1239 (Ocean View Avenue) intersection in Holden Beach. | Revise traffic signal and pavement markings. | 0.5 | Brunswick | 3 | Grand Strand Area Transportation Study |  | Region B |  | HSIP | CONSTRUCTION | 91000
HS-2003G | Highway | Safety | NC 130 | SR 1120 (Sabbath Home Road) / SR 1239 (Ocean View Avenue) intersection in Holden Beach. | Revise traffic signal and pavement markings. | 0.5 | Brunswick | 3 | Grand Strand Area Transportation Study |  | Region B |  | T(M) | CONSTRUCTION | 10000
HS-2003H | Highway | Safety | US 117 / NC 132 (College Road) | Lake Avenue-Hugh McRae Park in Wilmington. | Revise traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 59000 | FY 2026: 59000
HS-2003H | Highway | Safety | US 117 / NC 132 (College Road) | Lake Avenue-Hugh McRae Park in Wilmington. | Revise traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 7000 | FY 2026: 7000
HS-2003I | Highway | Safety | NC 403 | SR 1306 (Beautancus Road) intersection. | Construct safety improvements. | 0.5 | Duplin | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2003I | Highway | Safety | NC 403 | SR 1306 (Beautancus Road) intersection. | Construct safety improvements. | 0.5 | Duplin | 3 | Eastern Carolina RPO |  | Region B |  | T(M) | CONSTRUCTION | 7000 | FY 2026: 7000
HS-2003J | Highway | Safety | US 17 (Oleander Drive) | 42nd Street intersection in Wilmington. | Revise traffic signal and pavement markings. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2003J | Highway | Safety | US 17 (Oleander Drive) | 42nd Street intersection in Wilmington. | Revise traffic signal and pavement markings. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 7000 | FY 2026: 7000
HS-2003K | Highway | Safety | US 74 | SR 1627 (3rd Street / Martin Luther King, Jr. Boulevard) westbound on-ramp in Wilmington. | Revise traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 14000
HS-2003K | Highway | Safety | US 74 | SR 1627 (3rd Street / Martin Luther King, Jr. Boulevard) westbound on-ramp in Wilmington. | Revise traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2000
HS-2003L | Highway | Safety | US 17 / US 76 (Oleander Drive) | SR 1421 (Greenville Loop Road / Greenville Avenue) intersection in Wilmington. | Revise traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 76000 | FY 2026: 76000
HS-2003L | Highway | Safety | US 17 / US 76 (Oleander Drive) | SR 1421 (Greenville Loop Road / Greenville Avenue) intersection in Wilmington. | Revise traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 8000 | FY 2026: 8000
HS-2003M | Highway | Safety | US 117 (Norwood Street) | SR 1173 (Southerland Street) intersection in Wallace. | Revise traffic signal. | 0.5 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 40000
HS-2003M | Highway | Safety | US 117 (Norwood Street) | SR 1173 (Southerland Street) intersection in Wallace. | Revise traffic signal. | 0.5 | Duplin | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 4000
HS-2003N | Highway | Safety | NC 24 Business (Routeledge Road) | NC 24 / NC 903 (South Kenansville Bypass) intersection in Kenansville. | Revise traffic signal. | 0.5 | Duplin | 3 | Eastern Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 227000
HS-2003N | Highway | Safety | NC 24 Business (Routeledge Road) | NC 24 / NC 903 (South Kenansville Bypass) intersection in Kenansville. | Revise traffic signal. | 0.5 | Duplin | 3 | Eastern Carolina RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 25000
HS-2003O | Highway | Safety | US 74 / US 76 | SR 1714 (Enterprise Drive) and SR 1494 (Wood Treatment Road) intersections in Leland. | Install traffic signals. | 0.5 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 480000 | FY 2026: 480000
HS-2003O | Highway | Safety | US 74 / US 76 | SR 1714 (Enterprise Drive) and SR 1494 (Wood Treatment Road) intersections in Leland. | Install traffic signals. | 0.5 | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 53000 | FY 2026: 53000
HS-2003P | Highway | Safety | US 117 (Shipyard Boulevard) | Converse Road / Longstreet Drive intersection in Wilmington. | Upgrade traffic signal and add pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 27000
HS-2003P | Highway | Safety | US 117 (Shipyard Boulevard) | Converse Road / Longstreet Drive intersection in Wilmington. | Upgrade traffic signal and add pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 3000
HS-2003P | Highway | Safety | US 117 (Shipyard Boulevard) | Converse Road / Longstreet Drive intersection in Wilmington. | Upgrade traffic signal and add pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 244000 | FY 2026: 244000
HS-2003P | Highway | Safety | US 117 (Shipyard Boulevard) | Converse Road / Longstreet Drive intersection in Wilmington. | Upgrade traffic signal and add pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 27000 | FY 2026: 27000
HS-2003Q | Highway | Safety | US 17 (Dawson Street) | US 421 (3rd Street) intersection in Wilmington. | Upgrade traffic signal, pavement markings, and add pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 166000 | FY 2026: 166000
HS-2003Q | Highway | Safety | US 17 (Dawson Street) | US 421 (3rd Street) intersection in Wilmington. | Upgrade traffic signal, pavement markings, and add pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 18000 | FY 2026: 18000
HS-2003R | Highway | Safety | US 421 | SR 1573 (Dow Road) intersection in Carolina Beach. | Upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 21000 | FY 2026: 21000
HS-2003R | Highway | Safety | US 421 | SR 1573 (Dow Road) intersection in Carolina Beach. | Upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 2000 | FY 2026: 2000
HS-2003S | Highway | Safety | US 17 Business (Market Street) | SR 1272 (New Centre Drive) intersection in Wilmington. | Install crosswalks. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 52000
HS-2003S | Highway | Safety | US 17 Business (Market Street) | SR 1272 (New Centre Drive) intersection in Wilmington. | Install crosswalks. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | RIGHT-OF-WAY | 6000
HS-2003S | Highway | Safety | US 17 Business (Market Street) | SR 1272 (New Centre Drive) intersection in Wilmington. | Install crosswalks. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 103000 | FY 2026: 103000
HS-2003S | Highway | Safety | US 17 Business (Market Street) | SR 1272 (New Centre Drive) intersection in Wilmington. | Install crosswalks. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 11000 | FY 2026: 11000
HS-2003T | Highway | Safety | US 17 Business (Market Street) | SR 2219 (Green Meadows Drive) intersection in Wilmington. | Upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 57000 | FY 2026: 57000
HS-2003T | Highway | Safety | US 17 Business (Market Street) | SR 2219 (Green Meadows Drive) intersection in Wilmington. | Upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 6000
HS-2003U | Highway | Safety | SR 2048 (Gordon Road) | West of I-40. | Install pavement markings. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | HSIP | CONSTRUCTION | 33000
HS-2003U | Highway | Safety | SR 2048 (Gordon Road) | West of I-40. | Install pavement markings. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | T(M) | CONSTRUCTION | 4000
HS-2003V | Highway | Safety | US 17 / US 76 (Oleander Drive) | SR 1209 (Independence Boulevard) intersection in Wilmington. | Upgrade traffic signal with pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 27000
HS-2003V | Highway | Safety | US 17 / US 76 (Oleander Drive) | SR 1209 (Independence Boulevard) intersection in Wilmington. | Upgrade traffic signal with pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 3000
HS-2003V | Highway | Safety | US 17 / US 76 (Oleander Drive) | SR 1209 (Independence Boulevard) intersection in Wilmington. | Upgrade traffic signal with pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 45000 | FY 2026: 45000
HS-2003V | Highway | Safety | US 17 / US 76 (Oleander Drive) | SR 1209 (Independence Boulevard) intersection in Wilmington. | Upgrade traffic signal with pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | CONSTRUCTION | 5000 | FY 2026: 5000
HS-2003W | Highway | Safety | US 17 (Future I-74) | SR 1136 (Red Bug Road) and SR 1345 (Royal Oak Road) intersections in Shallotte. | Construct reduced conflict intersection. | 0.5 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 1710000
HS-2003W | Highway | Safety | US 17 (Future I-74) | SR 1136 (Red Bug Road) and SR 1345 (Royal Oak Road) intersections in Shallotte. | Construct reduced conflict intersection. | 0.5 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 190000
HS-2003X | Highway | Safety | NC 24 | SR 1514 (Phillips Loop Road) intersection in Swansboro. | Install crosswalks with pedestrian signals and advance flashers. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 166000
HS-2003X | Highway | Safety | NC 24 | SR 1514 (Phillips Loop Road) intersection in Swansboro. | Install crosswalks with pedestrian signals and advance flashers. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 18000
HS-2003X | Highway | Safety | NC 24 | SR 1514 (Phillips Loop Road) intersection in Swansboro. | Install crosswalks with pedestrian signals and advance flashers. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 182000 | FY 2026: 182000
HS-2003X | Highway | Safety | NC 24 | SR 1514 (Phillips Loop Road) intersection in Swansboro. | Install crosswalks with pedestrian signals and advance flashers. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | CONSTRUCTION | 20000 | FY 2026: 20000
HS-2003Y | Highway | Safety | US 117 / NC 132 (College Road) | SR 2313 (Wilshire Boulevard) intersection in Wilmington. | Install pedestrian countdown heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 57000 | FY 2026: 57000
HS-2003Y | Highway | Safety | US 117 / NC 132 (College Road) | SR 2313 (Wilshire Boulevard) intersection in Wilmington. | Install pedestrian countdown heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 6000
HS-2003Z | Highway | Safety | US 17 / US 76 (Wooster Street) | SR 1217 (17th Street) intersection in Wilmington. | Revise traffic signal and install pedestrian countdown heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 103000 | FY 2026: 103000
HS-2003Z | Highway | Safety | US 17 / US 76 (Wooster Street) | SR 1217 (17th Street) intersection in Wilmington. | Revise traffic signal and install pedestrian countdown heads. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 11000 | FY 2026: 11000
HS-2004 | Highway | Safety | Various | Routes in Division 4. | Construct safety improvements. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2004AA | Highway | Safety | US 64 Business (Sunset Avenue) | River Drive / Lake Drive intersection in Rocky Mount. | Construct various pedestrian and safety improvements. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 194000
HS-2004AA | Highway | Safety | US 64 Business (Sunset Avenue) | River Drive / Lake Drive intersection in Rocky Mount. | Construct various pedestrian and safety improvements. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO |  | Region A |  | T(M) | CONSTRUCTION | 22000
HS-2004AB | Highway | Safety | US 64 Business (Raleigh Boulevard) | NC 43 (Fairview Road) intersection in Rocky Mount. | Install pedestrian signal heads. | 0.5 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 115000
HS-2004AB | Highway | Safety | US 64 Business (Raleigh Boulevard) | NC 43 (Fairview Road) intersection in Rocky Mount. | Install pedestrian signal heads. | 0.5 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Region A |  | T(M) | CONSTRUCTION | 13000
HS-2004AC | Highway | Safety | SR 1556 (Wayne Memorial Drive) | US 70 Bypass to Greene County line. | Install rumble stripes with pavement markings. | 7.3 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 189000
HS-2004AC | Highway | Safety | SR 1556 (Wayne Memorial Drive) | US 70 Bypass to Greene County line. | Install rumble stripes with pavement markings. | 7.3 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 21000
HS-2004AD | Highway | Safety | NC 39 | US 301 north of Selma to Wake County line. | Install rumble stripes and pavement markings. | 18.5 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 441000
HS-2004AD | Highway | Safety | NC 39 | US 301 north of Selma to Wake County line. | Install rumble stripes and pavement markings. | 18.5 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 49000
HS-2004B | Highway | Safety | NC 97 | SR 1603 (Old Carriage Road) intersection. | Install left turn lane. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 77000
HS-2004B | Highway | Safety | NC 97 | SR 1603 (Old Carriage Road) intersection. | Install left turn lane. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T(M) | RIGHT-OF-WAY | 9000
HS-2004B | Highway | Safety | NC 97 | SR 1603 (Old Carriage Road) intersection. | Install left turn lane. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 184000
HS-2004B | Highway | Safety | NC 97 | SR 1603 (Old Carriage Road) intersection. | Install left turn lane. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 20000
HS-2004C | Highway | Safety | SR 1537 (Airport Road) | SR 1545 (Mt. Carmel Church Road) intersection | Install all way stop. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 59000
HS-2004C | Highway | Safety | SR 1537 (Airport Road) | SR 1545 (Mt. Carmel Church Road) intersection | Install all way stop. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 7000
HS-2004D | Highway | Safety | SR 1002 (Pikeville-Princeton Road) | SR 1320 (Hinnant Road) intersection. | Install all way stop with island. | 0.5 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 58000
HS-2004D | Highway | Safety | SR 1002 (Pikeville-Princeton Road) | SR 1320 (Hinnant Road) intersection. | Install all way stop with island. | 0.5 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 6000
HS-2004E | Highway | Safety | NC 111 | SR 1754 (Zion Church Road) intersection. | Install all way stop utilizing existing overhead flashers. | 0.5 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 137000
HS-2004E | Highway | Safety | NC 111 | SR 1754 (Zion Church Road) intersection. | Install all way stop utilizing existing overhead flashers. | 0.5 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 15000
HS-2004F | Highway | Safety | SR 1103 (Wiggins Mill Road) | SR 1169 (Radford Road) intersection. | Install all way stop utilizing existing overhead flashers. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H. | Division 4 |  | HSIP | CONSTRUCTION | 27000
HS-2004F | Highway | Safety | SR 1103 (Wiggins Mill Road) | SR 1169 (Radford Road) intersection. | Install all way stop utilizing existing overhead flashers. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H. | Division 4 |  | T(M) | CONSTRUCTION | 3000
HS-2004G | Highway | Safety | NC 48 | NC 903 intersection. | Install all way stop and revise existing overhead and shoulder-mounted flashers. | 0.5 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H. | Region A |  | HSIP | CONSTRUCTION | 45000
HS-2004G | Highway | Safety | NC 48 | NC 903 intersection. | Install all way stop and revise existing overhead and shoulder-mounted flashers. | 0.5 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H. | Region A |  | T(M) | CONSTRUCTION | 5000
HS-2004H | Highway | Safety | SR 1001 (Old Bailey Highway) | SR 1717 (Macedonia Road / Sandy Cross Road) intersection. | Install all way stop. | 0.5 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G. | Division 4 |  | HSIP | CONSTRUCTION | 22000
HS-2004H | Highway | Safety | SR 1001 (Old Bailey Highway) | SR 1717 (Macedonia Road / Sandy Cross Road) intersection. | Install all way stop. | 0.5 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G. | Division 4 |  | T(M) | CONSTRUCTION | 2000
HS-2004I | Highway | Safety | SR 1744 (Indian Springs Road) | SR 1941 (Northeast Church Road) intersection. | Install all way stop. | 0.5 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 58000
HS-2004I | Highway | Safety | SR 1744 (Indian Springs Road) | SR 1941 (Northeast Church Road) intersection. | Install all way stop. | 0.5 | Wayne | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 6000
HS-2004J | Highway | Safety | Various | Routes in Division 4. | Construct safety improvements. |  | Halifax, Johnston | 4 | Peanut Belt RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 4721000
HS-2004J | Highway | Safety | Various | Routes in Division 4. | Construct safety improvements. |  | Halifax, Johnston | 4 | Peanut Belt RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 525000
HS-2004L | Highway | Safety | NC 242 | North of SR 1116 (Godwin Lake Road) to North of SR 1116 (Godwin Lake Road). | Construct curve improvement. | 0.23 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 245000
HS-2004L | Highway | Safety | NC 242 | North of SR 1116 (Godwin Lake Road) to North of SR 1116 (Godwin Lake Road). | Construct curve improvement. | 0.23 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | RIGHT-OF-WAY | 27000
HS-2004L | Highway | Safety | NC 242 | North of SR 1116 (Godwin Lake Road) to North of SR 1116 (Godwin Lake Road). | Construct curve improvement. | 0.23 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 616000
HS-2004L | Highway | Safety | NC 242 | North of SR 1116 (Godwin Lake Road) to North of SR 1116 (Godwin Lake Road). | Construct curve improvement. | 0.23 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 68000
HS-2004M | Highway | Safety | NC 48 | Waterloo Drive / Roundtree Drive and Greyson Road / Cunningham Drive intersections. | Install mini roundabouts. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 397000
HS-2004M | Highway | Safety | NC 48 | Waterloo Drive / Roundtree Drive and Greyson Road / Cunningham Drive intersections. | Install mini roundabouts. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 44000
HS-2004N | Highway | Safety | SR 1700 (Oak Level Road) | SR 1603 (Old Carriage Road) intersection. | Revise traffic signal. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 316000
HS-2004N | Highway | Safety | SR 1700 (Oak Level Road) | SR 1603 (Old Carriage Road) intersection. | Revise traffic signal. | 0.5 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 35000
HS-2004O | Highway | Safety | SR 1320 (Airport Boulevard) | Chelsea Drive and Jetstream Drive intersections in Wilson. | Install traffic signals. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | UTILITIES | 126000
HS-2004O | Highway | Safety | SR 1320 (Airport Boulevard) | Chelsea Drive and Jetstream Drive intersections in Wilson. | Install traffic signals. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | UTILITIES | 14000
HS-2004O | Highway | Safety | SR 1320 (Airport Boulevard) | Chelsea Drive and Jetstream Drive intersections in Wilson. | Install traffic signals. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 638000
HS-2004O | Highway | Safety | SR 1320 (Airport Boulevard) | Chelsea Drive and Jetstream Drive intersections in Wilson. | Install traffic signals. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 71000
HS-2004P | Highway | Safety | US 301 (Brightleaf Boulevard) | North Street intersection in Smithfield. | Install crosswalks, pedestrian improvements, and traffic signals. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 315000
HS-2004P | Highway | Safety | US 301 (Brightleaf Boulevard) | North Street intersection in Smithfield. | Install crosswalks, pedestrian improvements, and traffic signals. | 0.5 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 35000
HS-2004Q | Highway | Safety | US 64 (Future I-87) | Bridges 630019 and 630020 over Tar River. | Improve pavement. | 0.5 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 810000
HS-2004Q | Highway | Safety | US 64 (Future I-87) | Bridges 630019 and 630020 over Tar River. | Improve pavement. | 0.5 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 90000
HS-2004R | Highway | Safety | US 258 | Pitt County line to US 64 in Edgecombe County, and Princeville to SR 1102 (Mullin Road) in Halifax County. | Install pavement markings and rumble stripes. | 31.69 | Edgecombe, Halifax | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 702000
HS-2004R | Highway | Safety | US 258 | Pitt County line to US 64 in Edgecombe County, and Princeville to SR 1102 (Mullin Road) in Halifax County. | Install pavement markings and rumble stripes. | 31.69 | Edgecombe, Halifax | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 78000
HS-2004S | Highway | Safety | SR 1902 (Glen Laurel Road) | SR 1903 (Vinson Road) intersection. | Install traffic signal. | 0.5 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 315000
HS-2004S | Highway | Safety | SR 1902 (Glen Laurel Road) | SR 1903 (Vinson Road) intersection. | Install traffic signal. | 0.5 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T(M) | CONSTRUCTION | 35000
HS-2004T | Highway | Safety | US 158 | Eastern Littleton Town limits to West of SR 1432 (Everetts School Road). | Install rumble stripes and pavement markings. | 9.41 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 207000
HS-2004T | Highway | Safety | US 158 | Eastern Littleton Town limits to West of SR 1432 (Everetts School Road). | Install rumble stripes and pavement markings. | 9.41 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 23000
HS-2004U | Highway | Safety | NC 58 | Northern Statonsburg town limits to 0.3 miles north of SR 1622 (Evansdale Road) in Wilson County, south of SR 1314 (Thompson Chapel Church Road) in Wilson County to southern Nashville town limits in Nash County, and south of SR 1004 (Taylors Store Road) t | Install rumble stripes and pavement markings. |  | Nash, Wilson | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 621000
HS-2004U | Highway | Safety | NC 58 | Northern Statonsburg town limits to 0.3 miles north of SR 1622 (Evansdale Road) in Wilson County, south of SR 1314 (Thompson Chapel Church Road) in Wilson County to southern Nashville town limits in Nash County, and south of SR 1004 (Taylors Store Road) t | Install rumble stripes and pavement markings. |  | Nash, Wilson | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 69000
HS-2004V | Highway | Safety | NC 111 | Multiple segments from Wayne / Duplin county line to Edgecombe / Martin county line. | Install rumble stripes and pavement markings. |  | Wayne, Edgecombe, Wilson | 4 | Upper Coastal Plain RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 1945000
HS-2004V | Highway | Safety | NC 111 | Multiple segments from Wayne / Duplin county line to Edgecombe / Martin county line. | Install rumble stripes and pavement markings. |  | Wayne, Edgecombe, Wilson | 4 | Upper Coastal Plain RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 216000
HS-2004W | Highway | Safety | US 70 (Future I-42) | US 70 Alternate / SR 2532 (West Edwards Street) and SR 2314 (Pondfield Road) intersections in Princeton. | Construct reduced conflict intersection with westbound U-turn. | 0.38 | Johnston | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 720000
HS-2004W | Highway | Safety | US 70 (Future I-42) | US 70 Alternate / SR 2532 (West Edwards Street) and SR 2314 (Pondfield Road) intersections in Princeton. | Construct reduced conflict intersection with westbound U-turn. | 0.38 | Johnston | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 80000
HS-2004X | Highway | Safety | NC 43 | North of SR 1425 (Castalia Road) in Nash County to NC 561 in Halifax County. | Install rumble stripes. | 13.51 | Nash, Halifax | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 325000
HS-2004X | Highway | Safety | NC 43 | North of SR 1425 (Castalia Road) in Nash County to NC 561 in Halifax County. | Install rumble stripes. | 13.51 | Nash, Halifax | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 36000
HS-2004Y | Highway | Safety | Various | Ramps in Division 4 | Install wrong way pavement markings and signs. | 0.5 | Johnston, Nash, Wayne, Wilson, Edgecombe, Halifax | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 1395000
HS-2004Y | Highway | Safety | Various | Ramps in Division 4 | Install wrong way pavement markings and signs. | 0.5 | Johnston, Nash, Wayne, Wilson, Edgecombe, Halifax | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 155000
HS-2005 | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. |  |  |  |  | 22000
HS-2005A | Highway | Safety | SR 1602 (Main Street) | SR 1207 (Spring Street) intersection in Oxford. | Construct mini-roundabout. |  | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 90000
HS-2005A | Highway | Safety | SR 1602 (Main Street) | SR 1207 (Spring Street) intersection in Oxford. | Construct mini-roundabout. |  | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 10000
HS-2005B | Highway | Safety | NC 903 | NC 903 causeway on Eatons Ferry Bridge over Lake Gaston. | Upgrade guardrail. | 0.85 | Warren | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 117000
HS-2005B | Highway | Safety | NC 903 | NC 903 causeway on Eatons Ferry Bridge over Lake Gaston. | Upgrade guardrail. | 0.85 | Warren | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | T(M) | CONSTRUCTION | 13000
HS-2005C | Highway | Safety | NC 54 | NC 55 intersection in Durham. | Install concrete pedestrian refuge islands in all quadrants. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 68000 | FY 2026: 1000; FY 2027: 67000
HS-2005C | Highway | Safety | NC 54 | NC 55 intersection in Durham. | Install concrete pedestrian refuge islands in all quadrants. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | CONSTRUCTION | 7000 | FY 2026: 0; FY 2027: 7000
HS-2005D | Highway | Safety | SR 1303 (Pickett Road) | SR 1116 (Garrett Road) / Luna Lane intersection in Durham. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000
HS-2005D | Highway | Safety | SR 1303 (Pickett Road) | SR 1116 (Garrett Road) / Luna Lane intersection in Durham. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | RIGHT-OF-WAY | 0
HS-2005D | Highway | Safety | SR 1303 (Pickett Road) | SR 1116 (Garrett Road) / Luna Lane intersection in Durham. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 36000
HS-2005D | Highway | Safety | SR 1303 (Pickett Road) | SR 1116 (Garrett Road) / Luna Lane intersection in Durham. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 4000
HS-2005E | Highway | Safety | US 15 / US 501 Business | NC 751 (Academy Road) interchange in Durham. | Install guardrail. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 158000
HS-2005E | Highway | Safety | US 15 / US 501 Business | NC 751 (Academy Road) interchange in Durham. | Install guardrail. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Region C |  | T(M) | CONSTRUCTION | 18000
HS-2005F | Highway | Safety | Various | Downtown Raleigh Business District. | Revise traffic signals at various locations. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 180000
HS-2005F | Highway | Safety | Various | Downtown Raleigh Business District. | Revise traffic signals at various locations. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 20000
HS-2005G | Highway | Safety | SR 2215 (Buffaloe Road) | SR 2214 (Southhall Road) / Brintons Cottage Street and Valley Stream Drive intersections in Raleigh. | Revise traffic signals, curb ramps, and pavement markings. | 0.33 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 132000
HS-2005G | Highway | Safety | SR 2215 (Buffaloe Road) | SR 2214 (Southhall Road) / Brintons Cottage Street and Valley Stream Drive intersections in Raleigh. | Revise traffic signals, curb ramps, and pavement markings. | 0.33 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 15000
HS-2005H | Highway | Safety | SR 1973 (Page Road) | Churchill Hall / Arby's / McDonalds Driveway. | Install directional crossover. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | CONSTRUCTION | 18000
HS-2005H | Highway | Safety | SR 1973 (Page Road) | Churchill Hall / Arby's / McDonalds Driveway. | Install directional crossover. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | T(M) | CONSTRUCTION | 2000
HS-2005I | Highway | Safety | SR 1645 (Lumley Road) | I-540 westbound ramp / Arco Corporate Drive in Raleigh. | Upgrade traffic signal and construct turn lane. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 216000
HS-2005I | Highway | Safety | SR 1645 (Lumley Road) | I-540 westbound ramp / Arco Corporate Drive in Raleigh. | Upgrade traffic signal and construct turn lane. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 24000
HS-2005J | Highway | Safety | SR 2516 (Hodge Road) | Mingo Creek Trail crossing. | Relocate crosswalk. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 171000
HS-2005J | Highway | Safety | SR 2516 (Hodge Road) | Mingo Creek Trail crossing. | Relocate crosswalk. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 19000
HS-2005K | Highway | Safety | US 401 | SR 2108 / SR 2036 (New Hope Road) intersection and US 401 at Calvary Drive intersection. | Install pedestrian signals and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 436000
HS-2005K | Highway | Safety | US 401 | SR 2108 / SR 2036 (New Hope Road) intersection and US 401 at Calvary Drive intersection. | Install pedestrian signals and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | T(M) | CONSTRUCTION | 51000
HS-2005L | Highway | Safety | SR 1327 (Gregson Street) | Knox Street intersection. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | UTILITIES | 14000 | FY 2026: 14000
HS-2005L | Highway | Safety | SR 1327 (Gregson Street) | Knox Street intersection. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | T(M) | UTILITIES | 2000 | FY 2026: 2000
HS-2005L | Highway | Safety | SR 1327 (Gregson Street) | Knox Street intersection. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | CONSTRUCTION | 99000 | FY 2026: 99000
HS-2005L | Highway | Safety | SR 1327 (Gregson Street) | Knox Street intersection. | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | T(M) | CONSTRUCTION | 11000 | FY 2026: 11000
HS-2005M | Highway | Safety | NC 55 (Alston Avenue) | SR 1670 (Geer Street) intersection in Durham. | Revise traffic signal and install pedestrian signal heads. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 56000 | FY 2026: 1000; FY 2027: 55000
HS-2005M | Highway | Safety | NC 55 (Alston Avenue) | SR 1670 (Geer Street) intersection in Durham. | Revise traffic signal and install pedestrian signal heads. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 0; FY 2027: 6000
HS-2005O | Highway | Safety | US 1 / US 158 | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Warren | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | RIGHT-OF-WAY | 28000
HS-2005O | Highway | Safety | US 1 / US 158 | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Warren | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | RIGHT-OF-WAY | 3000
HS-2005O | Highway | Safety | US 1 / US 158 | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Warren | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | UTILITIES | 72000
HS-2005O | Highway | Safety | US 1 / US 158 | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Warren | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | UTILITIES | 8000
HS-2005O | Highway | Safety | US 1 / US 158 | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Warren | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | CONSTRUCTION | 382000 | FY 2026: 382000
HS-2005O | Highway | Safety | US 1 / US 158 | SR 1237 (Mason Drewry Road) intersection. | Realign intersection. | 0.5 | Warren | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | CONSTRUCTION | 42000 | FY 2026: 42000
HS-2005P | Highway | Safety | US 501 | NC 57 (Hillsborough Road) intersection. | Install traffic signal. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | UTILITIES | 14000 | FY 2026: 14000
HS-2005P | Highway | Safety | US 501 | NC 57 (Hillsborough Road) intersection. | Install traffic signal. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | UTILITIES | 2000 | FY 2026: 2000
HS-2005P | Highway | Safety | US 501 | NC 57 (Hillsborough Road) intersection. | Install traffic signal. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 387000 | FY 2026: 387000
HS-2005P | Highway | Safety | US 501 | NC 57 (Hillsborough Road) intersection. | Install traffic signal. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | CONSTRUCTION | 43000 | FY 2026: 43000
HS-2005Q | Highway | Safety | SR 1142 (Humie Olive Road) | Blazing Trail Drive / Driveway access to Apex Friendship High and Elementary Schools intersection. | Install traffic and pedestrian signals. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 117000
HS-2005Q | Highway | Safety | SR 1142 (Humie Olive Road) | Blazing Trail Drive / Driveway access to Apex Friendship High and Elementary Schools intersection. | Install traffic and pedestrian signals. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T(M) | CONSTRUCTION | 13000
HS-2005S | Highway | Safety | NC 98 | SR 1815 (Mineral Springs Road) intersection. | Construct right turn lanes and sidewalk. | 0.5 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | CONSTRUCTION | 1080000 | FY 2026: 11000; FY 2027: 1069000
HS-2005S | Highway | Safety | NC 98 | SR 1815 (Mineral Springs Road) intersection. | Construct right turn lanes and sidewalk. | 0.5 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | CONSTRUCTION | 120000 | FY 2026: 1000; FY 2027: 119000
HS-2006 | Highway | Safety | Various | Routes in Division 6 | Construct safety improvements. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2006A | Highway | Safety | SR 1415 (Yadkin Road) | US 401 (Skibo Road), SR 1437 (Sante Fe Drive), and Southwick Drive intersections. | Add signalized pedestrian crossings and upgrade signal. | 1 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 467000
HS-2006A | Highway | Safety | SR 1415 (Yadkin Road) | US 401 (Skibo Road), SR 1437 (Sante Fe Drive), and Southwick Drive intersections. | Add signalized pedestrian crossings and upgrade signal. | 1 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 100000
HS-2006AA | Highway | Safety | SR 1340 (Odom Street / Prospect Road) | NC 771 (Third Street) and SR 1566 (Corinth Road) in Pembroke. | Install crosswalks, pedestrian signal heads, refuge islands and rectangular rapid flashing beacons. Upgrade traffic signal. | 0.89 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 752000
HS-2006AA | Highway | Safety | SR 1340 (Odom Street / Prospect Road) | NC 771 (Third Street) and SR 1566 (Corinth Road) in Pembroke. | Install crosswalks, pedestrian signal heads, refuge islands and rectangular rapid flashing beacons. Upgrade traffic signal. | 0.89 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 84000
HS-2006AB | Highway | Safety | Various | Routes in Division 6. | Install pavement markings in freeway / expressway ramps. |  | Cumberland, Robeson, Columbus, Harnett | 6 | Lumber River RPO, Fayetteville Area MPO, Mid-Carolina RPO, Cape Fear RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 180000
HS-2006AB | Highway | Safety | Various | Routes in Division 6. | Install pavement markings in freeway / expressway ramps. |  | Cumberland, Robeson, Columbus, Harnett | 6 | Lumber River RPO, Fayetteville Area MPO, Mid-Carolina RPO, Cape Fear RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 20000
HS-2006AC | Highway | Safety | NC 210 | Bladen County line to NC 53 in Cumberland County, and Cumberland County line to Lillington city limits in Harnett County. | Install rumble stripes and pavement markings. |  | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 1053000
HS-2006AC | Highway | Safety | NC 210 | Bladen County line to NC 53 in Cumberland County, and Cumberland County line to Lillington city limits in Harnett County. | Install rumble stripes and pavement markings. |  | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 117000
HS-2006AD | Highway | Safety | NC 71 | Lumber Bridge city limits to Parkton city limits, and Parkton city limits to US 301. | Install rumble stripes and pavement markings. |  | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 288000
HS-2006AD | Highway | Safety | NC 71 | Lumber Bridge city limits to Parkton city limits, and Parkton city limits to US 301. | Install rumble stripes and pavement markings. |  | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 32000
HS-2006AE | Highway | Safety | SR 1561 (University Road) | NC 711 to Hawk Drive in Pembroke. | Install pedestrian signals and crosswalks. | 0.51 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 270000
HS-2006AE | Highway | Safety | SR 1561 (University Road) | NC 711 to Hawk Drive in Pembroke. | Install pedestrian signals and crosswalks. | 0.51 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 30000
HS-2006B | Highway | Safety | SR 1006 (Person Street) | US 301 / I-95 Business (Eastern Boulevard) to east of Water Street. | Upgrade section from four lanes to three lanes and construct intersection improvements. | 0.34 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 586000
HS-2006B | Highway | Safety | SR 1006 (Person Street) | US 301 / I-95 Business (Eastern Boulevard) to east of Water Street. | Upgrade section from four lanes to three lanes and construct intersection improvements. | 0.34 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 65000
HS-2006C | Highway | Safety | NC 53 (Cedar Creek Road) | North of Plymouth Street to south of Troy Drive. | Install median, U-turn bulbout, sidewalk, and rectangular rapid flashing beacon crossing. | 0.21 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | RIGHT-OF-WAY | 188000
HS-2006C | Highway | Safety | NC 53 (Cedar Creek Road) | North of Plymouth Street to south of Troy Drive. | Install median, U-turn bulbout, sidewalk, and rectangular rapid flashing beacon crossing. | 0.21 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) | RIGHT-OF-WAY | 20000
HS-2006C | Highway | Safety | NC 53 (Cedar Creek Road) | North of Plymouth Street to south of Troy Drive. | Install median, U-turn bulbout, sidewalk, and rectangular rapid flashing beacon crossing. | 0.21 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | CONSTRUCTION | 1620000
HS-2006C | Highway | Safety | NC 53 (Cedar Creek Road) | North of Plymouth Street to south of Troy Drive. | Install median, U-turn bulbout, sidewalk, and rectangular rapid flashing beacon crossing. | 0.21 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) | CONSTRUCTION | 180000
HS-2006D | Highway | Safety | SR 1935 (Howell Road) | SR 1924 (Barker Ten Mile Road) intersection, and north leg of SR 1005 (Tolarsville Road) intersection. | Upgrade intersection to all way stop, and realign intersection. | 0.5 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | RIGHT-OF-WAY | 22000
HS-2006D | Highway | Safety | SR 1935 (Howell Road) | SR 1924 (Barker Ten Mile Road) intersection, and north leg of SR 1005 (Tolarsville Road) intersection. | Upgrade intersection to all way stop, and realign intersection. | 0.5 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | RIGHT-OF-WAY | 2000
HS-2006D | Highway | Safety | SR 1935 (Howell Road) | SR 1924 (Barker Ten Mile Road) intersection, and north leg of SR 1005 (Tolarsville Road) intersection. | Upgrade intersection to all way stop, and realign intersection. | 0.5 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 509000
HS-2006D | Highway | Safety | SR 1935 (Howell Road) | SR 1924 (Barker Ten Mile Road) intersection, and north leg of SR 1005 (Tolarsville Road) intersection. | Upgrade intersection to all way stop, and realign intersection. | 0.5 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 57000
HS-2006E | Highway | Safety | Various | Routes in Division 6. | Install long life pavement markings. |  | Harnett, Bladen, Cumberland, Columbus | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 4244000
HS-2006E | Highway | Safety | Various | Routes in Division 6. | Install long life pavement markings. |  | Harnett, Bladen, Cumberland, Columbus | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 471000
HS-2006F | Highway | Safety | NC 211 | Brunswick County line to NC 214. | Install rumble stripes. | 9.48 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 946000
HS-2006F | Highway | Safety | NC 211 | Brunswick County line to NC 214. | Install rumble stripes. | 9.48 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 105000
HS-2006G | Highway | Safety | SR 1835 (Rock Hill Road) | SR 1838 (Dunn Road) intersection in Eastover. | Realign intersection to form T-intersection. | 0.15 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 254000
HS-2006G | Highway | Safety | SR 1835 (Rock Hill Road) | SR 1838 (Dunn Road) intersection in Eastover. | Realign intersection to form T-intersection. | 0.15 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 28000
HS-2006H | Highway | Safety | NC 27 | Moore County line to NC 24 / NC 27 split, NC 24 to Lillington, US 421 to Coats, and Coats to Johnston County line. | Install rumble stripes and pavement markings. |  | Harnett | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 958000
HS-2006H | Highway | Safety | NC 27 | Moore County line to NC 24 / NC 27 split, NC 24 to Lillington, US 421 to Coats, and Coats to Johnston County line. | Install rumble stripes and pavement markings. |  | Harnett | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 106000
HS-2006I | Highway | Safety | NC 710 | SR 1340 (Prospect Road) intersection. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | RIGHT-OF-WAY | 225000
HS-2006I | Highway | Safety | NC 710 | SR 1340 (Prospect Road) intersection. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | RIGHT-OF-WAY | 25000
HS-2006I | Highway | Safety | NC 710 | SR 1340 (Prospect Road) intersection. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | CONSTRUCTION | 1980000 | FY 2026: 1366000
HS-2006I | Highway | Safety | NC 710 | SR 1340 (Prospect Road) intersection. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | CONSTRUCTION | 220000 | FY 2026: 152000
HS-2006J | Highway | Safety | US 501 / NC 130 | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | RIGHT-OF-WAY | 62000
HS-2006J | Highway | Safety | US 501 / NC 130 | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | RIGHT-OF-WAY | 6000
HS-2006J | Highway | Safety | US 501 / NC 130 | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | UTILITIES | 63000
HS-2006J | Highway | Safety | US 501 / NC 130 | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | UTILITIES | 7000
HS-2006J | Highway | Safety | US 501 / NC 130 | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | CONSTRUCTION | 891000
HS-2006J | Highway | Safety | US 501 / NC 130 | Near SR 1134 (Kitchen Road). | Improve curve. | 0.14 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T(M) | CONSTRUCTION | 99000
HS-2006K | Highway | Safety | SR 1441 (Chalybeate Springs Road) | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | HSIP | RIGHT-OF-WAY | 40000
HS-2006K | Highway | Safety | SR 1441 (Chalybeate Springs Road) | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | T(M) | RIGHT-OF-WAY | 4000
HS-2006K | Highway | Safety | SR 1441 (Chalybeate Springs Road) | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | HSIP | UTILITIES | 22000
HS-2006K | Highway | Safety | SR 1441 (Chalybeate Springs Road) | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | T(M) | UTILITIES | 2000
HS-2006K | Highway | Safety | SR 1441 (Chalybeate Springs Road) | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | HSIP | CONSTRUCTION | 1035000
HS-2006K | Highway | Safety | SR 1441 (Chalybeate Springs Road) | NC 55 to US 401. | Improve curve and pavement. | 4.23 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | T(M) | CONSTRUCTION | 115000
HS-2006L | Highway | Safety | NC 87 | SR 1004 (Tar Heel Road) / SR 1316 (Tar Heel Ferry Road) intersections. | Revise traffic signals. | 0.5 | Bladen | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 109000
HS-2006L | Highway | Safety | NC 87 | SR 1004 (Tar Heel Road) / SR 1316 (Tar Heel Ferry Road) intersections. | Revise traffic signals. | 0.5 | Bladen | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 12000
HS-2006M | Highway | Safety | SR 1325 (Gum Springs Road) | Near SR 1327 (Live Oak Methodist Church Road). | Improve curve. | 0.25 | Bladen | 6 | Mid-Carolina RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 157000
HS-2006M | Highway | Safety | SR 1325 (Gum Springs Road) | Near SR 1327 (Live Oak Methodist Church Road). | Improve curve. | 0.25 | Bladen | 6 | Mid-Carolina RPO |  | Division 6 |  | T(M) | CONSTRUCTION | 17000
HS-2006N | Highway | Safety | SR 1596 (Glensford Drive) | US 401 (Raeford Road) to SR 1400 (Cliffdale Road) in Fayetteville. | Install pavement markings and sign improvements. | 1.16 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 73000
HS-2006N | Highway | Safety | SR 1596 (Glensford Drive) | US 401 (Raeford Road) to SR 1400 (Cliffdale Road) in Fayetteville. | Install pavement markings and sign improvements. | 1.16 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 8000
HS-2006O | Highway | Safety | SR 1596 (Glensford Drive) | Berean Baptist Academy Entrance and Chambersburg Road intersection. | Install Rectangular rapid flashing beacons with refuge islands. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 301000
HS-2006O | Highway | Safety | SR 1596 (Glensford Drive) | Berean Baptist Academy Entrance and Chambersburg Road intersection. | Install Rectangular rapid flashing beacons with refuge islands. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 33000
HS-2006P | Highway | Safety | SR 3950 (Ramsey Street) | Bridge 250216 in Fayetteville. | Install Guardrail. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 225000
HS-2006P | Highway | Safety | SR 3950 (Ramsey Street) | Bridge 250216 in Fayetteville. | Install Guardrail. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 25000
HS-2006Q | Highway | Safety | SR 1532 (Langdon Road) | Bridge 420015. | Upgrade guardrail. | 0.5 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | RIGHT-OF-WAY | 36000
HS-2006Q | Highway | Safety | SR 1532 (Langdon Road) | Bridge 420015. | Upgrade guardrail. | 0.5 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | RIGHT-OF-WAY | 4000
HS-2006Q | Highway | Safety | SR 1532 (Langdon Road) | Bridge 420015. | Upgrade guardrail. | 0.5 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 1590000
HS-2006Q | Highway | Safety | SR 1532 (Langdon Road) | Bridge 420015. | Upgrade guardrail. | 0.5 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 177000
HS-2006R | Highway | Safety | I-95 | Mile marker 2.0 to mile marker 12.45. | Install cable median barrier. | 10.45 | Robeson | 6 | Lumber River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 734000
HS-2006R | Highway | Safety | I-95 | Mile marker 2.0 to mile marker 12.45. | Install cable median barrier. | 10.45 | Robeson | 6 | Lumber River RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 82000
HS-2006S | Highway | Safety | US 501 | NC 130 to Scotland County line. | Install rumble stripes. | 5.41 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 946000
HS-2006S | Highway | Safety | US 501 | NC 130 to Scotland County line. | Install rumble stripes. | 5.41 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 105000
HS-2006T | Highway | Safety | NC 72 | US 74 to NC 41 / NC 211. | Install rumble stripes and pavement markings. | 11.84 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 946000
HS-2006T | Highway | Safety | NC 72 | US 74 to NC 41 / NC 211. | Install rumble stripes and pavement markings. | 11.84 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 105000
HS-2006U | Highway | Safety | NC 72 | NC 711 to NC 710. | Install rumble stripes and pavement markings. | 14.42 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 946000
HS-2006U | Highway | Safety | NC 72 | NC 711 to NC 710. | Install rumble stripes and pavement markings. | 14.42 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 105000
HS-2006V | Highway | Safety | SR 1600 (McArthur Road) | SR 1615 (Rosehill Road / Stacy Weaver Road) in Fayetteville. | Construct signalized pedestrian accommodations. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 171000
HS-2006V | Highway | Safety | SR 1600 (McArthur Road) | SR 1615 (Rosehill Road / Stacy Weaver Road) in Fayetteville. | Construct signalized pedestrian accommodations. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | CONSTRUCTION | 19000
HS-2006W | Highway | Safety | US 401 | Fayetteville to Cumberland County line, Harnett County line to Lillington, and Lillington to Wake County line. | Install rumble stripes and pavement markings. |  | Harnett, Cumberland | 6 | Mid-Carolina RPO, Capital Area MPO, Fayetteville Area MPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 878000
HS-2006W | Highway | Safety | US 401 | Fayetteville to Cumberland County line, Harnett County line to Lillington, and Lillington to Wake County line. | Install rumble stripes and pavement markings. |  | Harnett, Cumberland | 6 | Mid-Carolina RPO, Capital Area MPO, Fayetteville Area MPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 98000
HS-2006X | Highway | Safety | US 401 (Skibo Road) | SR 1007 (All American Freeway) northbound and southbound ramps in Fayetteville. | Install signalized pedestrian accommodations. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 792000
HS-2006X | Highway | Safety | US 401 (Skibo Road) | SR 1007 (All American Freeway) northbound and southbound ramps in Fayetteville. | Install signalized pedestrian accommodations. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 88000
HS-2006Y | Highway | Safety | SR 1115 (Buffalo Lake Road) | NC 27 to NC 87. | Install rumble stripes and pavement markings. | 4.57 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 212000
HS-2006Y | Highway | Safety | SR 1115 (Buffalo Lake Road) | NC 27 to NC 87. | Install rumble stripes and pavement markings. | 4.57 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T(M) | CONSTRUCTION | 24000
HS-2006Z | Highway | Safety | SR 1414 (Broadfoot Road) | Arsenal Avenue intersection in Fayetteville. | Install crosswalks with pedestrian signal head. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 351000
HS-2006Z | Highway | Safety | SR 1414 (Broadfoot Road) | Arsenal Avenue intersection in Fayetteville. | Install crosswalks with pedestrian signal head. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | CONSTRUCTION | 39000
HS-2007 | Highway | Safety | Various | Routes in Division | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2007A | Highway | Safety | I-85 Business / US 29 / US 70 | Randolph County line to north of SR 1145 (Riverdale Drive) in High Point. | Install guardrail. | 6.52 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 486000
HS-2007A | Highway | Safety | I-85 Business / US 29 / US 70 | Randolph County line to north of SR 1145 (Riverdale Drive) in High Point. | Install guardrail. | 6.52 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 54000
HS-2007B | Highway | Safety | I-85 Business / US 29 / US 70 Northbound | North of SR 1145 (Riverdale Drive) to I-85 in High Point. | Install guardrail. | 3.13 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 243000
HS-2007B | Highway | Safety | I-85 Business / US 29 / US 70 Northbound | North of SR 1145 (Riverdale Drive) to I-85 in High Point. | Install guardrail. | 3.13 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 27000
HS-2007C | Highway | Safety | Various | Secondary routes in Division 7. | Install long-life pavement markings. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | HSIP | CONSTRUCTION | 1545000
HS-2007C | Highway | Safety | Various | Secondary routes in Division 7. | Install long-life pavement markings. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | T(M) | CONSTRUCTION | 172000
HS-2007D | Highway | Safety | I-74 | US 29 / US 70 (I-85 Business) interchange. | Upgrade signals, pavement markings, and signing. | 1 | Guilford | 7 | High Point Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 360000 | FY 2026: 356000
HS-2007D | Highway | Safety | I-74 | US 29 / US 70 (I-85 Business) interchange. | Upgrade signals, pavement markings, and signing. | 1 | Guilford | 7 | High Point Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 40000 | FY 2026: 40000
HS-2007E | Highway | Safety | NC 62 | West of SR 1138 (Tom Ball Road) to west of the Alamance County line. | Install pavement markings. | 20.69 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | HSIP | CONSTRUCTION | 361000
HS-2007E | Highway | Safety | NC 62 | West of SR 1138 (Tom Ball Road) to west of the Alamance County line. | Install pavement markings. | 20.69 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T(M) | CONSTRUCTION | 40000
HS-2007F | Highway | Safety | NC 87 | I-40 Eastbound on-ramp. | Install pedestrian accommodations. | 0.5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 78000
HS-2007F | Highway | Safety | NC 87 | I-40 Eastbound on-ramp. | Install pedestrian accommodations. | 0.5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 9000
HS-2007G | Highway | Safety | US 29 | Lakeview Memorial Park Cemetery entrance intersection. | Construct directional crossover. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 369000
HS-2007G | Highway | Safety | US 29 | Lakeview Memorial Park Cemetery entrance intersection. | Construct directional crossover. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 41000
HS-2007H | Highway | Safety | SR 1009 (Old NC 86) | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 9000
HS-2007H | Highway | Safety | SR 1009 (Old NC 86) | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | T(M) | RIGHT-OF-WAY | 1000
HS-2007H | Highway | Safety | SR 1009 (Old NC 86) | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | UTILITIES | 4000
HS-2007H | Highway | Safety | SR 1009 (Old NC 86) | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | T(M) | UTILITIES | 0
HS-2007H | Highway | Safety | SR 1009 (Old NC 86) | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | CONSTRUCTION | 123000 | FY 2026: 123000
HS-2007H | Highway | Safety | SR 1009 (Old NC 86) | SR 1727 (Eubanks Road) intersection near Chapel Hill. | Modify right turn lane. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | T(M) | CONSTRUCTION | 14000 | FY 2026: 14000
HS-2007I | Highway | Safety | SR 4240 (East Gate City Boulevard) / Lee Street | I-40 Westbound ramp intersection. | Install traffic signal and turn lane improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 4000
HS-2007I | Highway | Safety | SR 4240 (East Gate City Boulevard) / Lee Street | I-40 Westbound ramp intersection. | Install traffic signal and turn lane improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | UTILITIES | 0
HS-2007I | Highway | Safety | SR 4240 (East Gate City Boulevard) / Lee Street | I-40 Westbound ramp intersection. | Install traffic signal and turn lane improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 677000 | FY 2026: 677000
HS-2007I | Highway | Safety | SR 4240 (East Gate City Boulevard) / Lee Street | I-40 Westbound ramp intersection. | Install traffic signal and turn lane improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 75000 | FY 2026: 75000
HS-2007J | Highway | Safety | NC 86 (Martin Luther King Boulevard) | Critz Drive intersection. | Install pedestrian improvements. | 0.5 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 459000
HS-2007J | Highway | Safety | NC 86 (Martin Luther King Boulevard) | Critz Drive intersection. | Install pedestrian improvements. | 0.5 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 51000
HS-2007K | Highway | Safety | I-40 | Buffalo Creek Bridge east For 1,550 feet and I-40 Exit 219 to US 29 South. | Install guardrail. | 0.4 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 293000
HS-2007K | Highway | Safety | I-40 | Buffalo Creek Bridge east For 1,550 feet and I-40 Exit 219 to US 29 South. | Install guardrail. | 0.4 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 32000
HS-2008 | Highway | Safety | Various | Routes in Division 8. | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2008A | Highway | Safety | US 74 (Future I-74) | Richmond County line to SR 1363. | Upgrade guardrail. | 4.33 | Scotland | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | HSIP | CONSTRUCTION | 324000
HS-2008A | Highway | Safety | US 74 (Future I-74) | Richmond County line to SR 1363. | Upgrade guardrail. | 4.33 | Scotland | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 36000
HS-2008B | Highway | Safety | Various | National Highway System and primary routes in Division 8 District 2. | Upgrade guardrail. |  | Moore, Hoke, Lee | 8 | Central Pines RPO, Lumber River RPO, Sandhills MPO | UNDER CONSTRUCTION | Region E |  | HSIP | CONSTRUCTION | 225000
HS-2008B | Highway | Safety | Various | National Highway System and primary routes in Division 8 District 2. | Upgrade guardrail. |  | Moore, Hoke, Lee | 8 | Central Pines RPO, Lumber River RPO, Sandhills MPO | UNDER CONSTRUCTION | Region E |  | T(M) | CONSTRUCTION | 25000
HS-2008C | Highway | Safety | Various | Secondary routes In Chatham, Lee, Hoke, Randolph and Scotland Counties. | Install long-life pavement markings. |  | Chatham, Hoke, Lee, Randolph, Scotland | 8 | Central Pines RPO, Lumber River RPO, Piedmont Triad RPO, High Point Urban Area MPO, Fayetteville Area MPO, Triangle West TPO |  | Region E |  | HSIP | CONSTRUCTION | 1422000
HS-2008C | Highway | Safety | Various | Secondary routes In Chatham, Lee, Hoke, Randolph and Scotland Counties. | Install long-life pavement markings. |  | Chatham, Hoke, Lee, Randolph, Scotland | 8 | Central Pines RPO, Lumber River RPO, Piedmont Triad RPO, High Point Urban Area MPO, Fayetteville Area MPO, Triangle West TPO |  | Region E |  | T(M) | CONSTRUCTION | 158000
HS-2008D | Highway | Safety | US 421 (Future I-685) | Chatham County line to the Guilford County line. | Install one mile and half mile markers and revise exit number signs. | 9.98 | Randolph | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 45000
HS-2008D | Highway | Safety | US 421 (Future I-685) | Chatham County line to the Guilford County line. | Install one mile and half mile markers and revise exit number signs. | 9.98 | Randolph | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5000
HS-2008E | Highway | Safety | US 74 (Future I-74) | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Scotland | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 33000
HS-2008E | Highway | Safety | US 74 (Future I-74) | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Scotland | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T | RIGHT-OF-WAY | 67000
HS-2008E | Highway | Safety | US 74 (Future I-74) | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Scotland | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | UTILITIES | 17000
HS-2008E | Highway | Safety | US 74 (Future I-74) | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Scotland | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T | UTILITIES | 33000
HS-2008E | Highway | Safety | US 74 (Future I-74) | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Scotland | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 980000 | FY 2026: 382000; FY 2027: 598000
HS-2008E | Highway | Safety | US 74 (Future I-74) | NC 144 (Morgan Street) / SR 1148 (Saint Johns Church Road) intersection. | Construct signalized reduced conflict intersection. | 0.5 | Scotland | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T | CONSTRUCTION | 1960000 | FY 2026: 764000; FY 2027: 1196000
HS-2008F | Highway | Safety | NC 5 | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Moore | 8 | Sandhills MPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 167000 | FY 2026: 167000
HS-2008F | Highway | Safety | NC 5 | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Moore | 8 | Sandhills MPO |  | Region E |  | T | RIGHT-OF-WAY | 333000 | FY 2026: 333000
HS-2008F | Highway | Safety | NC 5 | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Moore | 8 | Sandhills MPO |  | Region E |  | HSIP | UTILITIES | 83000 | FY 2027: 83000
HS-2008F | Highway | Safety | NC 5 | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Moore | 8 | Sandhills MPO |  | Region E |  | T | UTILITIES | 167000 | FY 2027: 167000
HS-2008F | Highway | Safety | NC 5 | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Moore | 8 | Sandhills MPO |  | Region E |  | HSIP | CONSTRUCTION | 1183000 | FY 2028: 826000; FY 2029: 357000
HS-2008F | Highway | Safety | NC 5 | SR 1205 (Morganton Road) intersection. | Improve intersection by redesigning turn lanes and installing a pedestrian hybrid beacon. | 0.5 | Moore | 8 | Sandhills MPO |  | Region E |  | T | CONSTRUCTION | 2367000 | FY 2028: 1653000; FY 2029: 714000
HS-2009 | Highway | Safety | Various | Routes in Division 9. | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2009A | Highway | Safety | Various | Secondary routes in Division 9. | Install long-life pavement markings. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 1710000
HS-2009A | Highway | Safety | Various | Secondary routes in Division 9. | Install long-life pavement markings. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO |  | Division 9 |  | T(M) | CONSTRUCTION | 190000
HS-2009B | Highway | Safety | US 64 | SR 2782 (Bowers Road) to east of SR 2012 (Heath Church Road) / SR 2227 (New Bowers Road). | Construct four reduced conflict intersections and leftover with U-turn bulb. | 0.61 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | UTILITIES | 18000
HS-2009B | Highway | Safety | US 64 | SR 2782 (Bowers Road) to east of SR 2012 (Heath Church Road) / SR 2227 (New Bowers Road). | Construct four reduced conflict intersections and leftover with U-turn bulb. | 0.61 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T(M) | UTILITIES | 2000
HS-2009B | Highway | Safety | US 64 | SR 2782 (Bowers Road) to east of SR 2012 (Heath Church Road) / SR 2227 (New Bowers Road). | Construct four reduced conflict intersections and leftover with U-turn bulb. | 0.61 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 2418000
HS-2009B | Highway | Safety | US 64 | SR 2782 (Bowers Road) to east of SR 2012 (Heath Church Road) / SR 2227 (New Bowers Road). | Construct four reduced conflict intersections and leftover with U-turn bulb. | 0.61 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 269000
HS-2009C | Highway | Safety | US 29 / US 70 | Vicinity of Fleet Darr Road west of SR 2123 (Lexington Avenue) Connector. | Install directional leftovers. | 0.5 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | HSIP | CONSTRUCTION | 450000 | FY 2029: 450000
HS-2009C | Highway | Safety | US 29 / US 70 | Vicinity of Fleet Darr Road west of SR 2123 (Lexington Avenue) Connector. | Install directional leftovers. | 0.5 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | CONSTRUCTION | 50000 | FY 2029: 50000
HS-2009D | Highway | Safety | SR 1007 (Jake Alexander Boulevard) | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | HSIP | RIGHT-OF-WAY | 45000
HS-2009D | Highway | Safety | SR 1007 (Jake Alexander Boulevard) | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | T(M) | RIGHT-OF-WAY | 5000
HS-2009D | Highway | Safety | SR 1007 (Jake Alexander Boulevard) | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | HSIP | UTILITIES | 18000
HS-2009D | Highway | Safety | SR 1007 (Jake Alexander Boulevard) | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | T(M) | UTILITIES | 2000
HS-2009D | Highway | Safety | SR 1007 (Jake Alexander Boulevard) | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | HSIP | CONSTRUCTION | 468000
HS-2009D | Highway | Safety | SR 1007 (Jake Alexander Boulevard) | Morlan Park Road intersection. | Install concrete channelization and leftover with U-turn bulb. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | T(M) | CONSTRUCTION | 52000
HS-2009E | Highway | Safety | SR 1002 (Old Concord Road) | Jake Alexander Boulevard in Salisbury to the Cabarrus County line. | Install pavement markings. | 10.94 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | CONSTRUCTION | 356000
HS-2009E | Highway | Safety | SR 1002 (Old Concord Road) | Jake Alexander Boulevard in Salisbury to the Cabarrus County line. | Install pavement markings. | 10.94 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | T(M) | CONSTRUCTION | 40000
HS-2009F | Highway | Safety | NC 109 | Mile marker 0.256 in Forsyth County to mile marker 38.367 in Davidson County. | Install centerline and edgeline sinusoidal rumble stripes. | 0.48 | Davidson, Forsyth | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 214000
HS-2009F | Highway | Safety | NC 109 | Mile marker 0.256 in Forsyth County to mile marker 38.367 in Davidson County. | Install centerline and edgeline sinusoidal rumble stripes. | 0.48 | Davidson, Forsyth | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 24000
HS-2009H | Highway | Safety | SR 1528 (North Point Boulevard) | University Plaza Shopping Center main driveway and BP filling station driveway intersection. Also, Northcliffe Drive intersection. | Construct two reduced conflict intersections. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | UTILITIES | 22000
HS-2009H | Highway | Safety | SR 1528 (North Point Boulevard) | University Plaza Shopping Center main driveway and BP filling station driveway intersection. Also, Northcliffe Drive intersection. | Construct two reduced conflict intersections. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T(M) | UTILITIES | 2000
HS-2009H | Highway | Safety | SR 1528 (North Point Boulevard) | University Plaza Shopping Center main driveway and BP filling station driveway intersection. Also, Northcliffe Drive intersection. | Construct two reduced conflict intersections. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 909000
HS-2009H | Highway | Safety | SR 1528 (North Point Boulevard) | University Plaza Shopping Center main driveway and BP filling station driveway intersection. Also, Northcliffe Drive intersection. | Construct two reduced conflict intersections. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T(M) | CONSTRUCTION | 101000
HS-2009I | Highway | Safety | NC 152 | NC 153 intersection near China Grove. | Construct intersection improvements. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 18000
HS-2009I | Highway | Safety | NC 152 | NC 153 intersection near China Grove. | Construct intersection improvements. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | T(M) | RIGHT-OF-WAY | 2000
HS-2009I | Highway | Safety | NC 152 | NC 153 intersection near China Grove. | Construct intersection improvements. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | CONSTRUCTION | 342000
HS-2009I | Highway | Safety | NC 152 | NC 153 intersection near China Grove. | Construct intersection improvements. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | T(M) | CONSTRUCTION | 38000
HS-2009J | Highway | Safety | Various | Multiple freeway and expressway ramps in Division 9. | Install long-life wrong way pavement markings. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO, High Point Urban Area MPO, Northwest Piedmont RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 472000
HS-2009J | Highway | Safety | Various | Multiple freeway and expressway ramps in Division 9. | Install long-life wrong way pavement markings. |  | Forsyth, Davidson, Davie | 9 | Winston-Salem Area TPO, High Point Urban Area MPO, Northwest Piedmont RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 52000
HS-2009K | Highway | Safety | NC 109 | SR 2335 (Canaan Church Road) / Snyder Station Road intersection near Denton. | Install turn lanes. | 0.5 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | CRPLT5 | CONSTRUCTION | 536000
HS-2009K | Highway | Safety | NC 109 | SR 2335 (Canaan Church Road) / Snyder Station Road intersection near Denton. | Install turn lanes. | 0.5 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | CONSTRUCTION | 134000
HS-2009L | Highway | Safety | NC 62 (Cloninger Drive) | SR 2055 (Liberty Drive) intersection in Thomasville. | Improve vertical alignment. | 0.5 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | HSIP | CONSTRUCTION | 477000
HS-2009L | Highway | Safety | NC 62 (Cloninger Drive) | SR 2055 (Liberty Drive) intersection in Thomasville. | Improve vertical alignment. | 0.5 | Davidson | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | CONSTRUCTION | 53000
HS-2010 | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2010A | Highway | Safety | NC 24 / NC 27 | SR 3110 (Arlington Church Road) intersection near Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | RIGHT-OF-WAY | 4000
HS-2010A | Highway | Safety | NC 24 / NC 27 | SR 3110 (Arlington Church Road) intersection near Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | CONSTRUCTION | 2025000
HS-2010B | Highway | Safety | I-277 | Multiple exits | Install smart cushions. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 144000
HS-2010C | Highway | Safety | NC 218 | US 74 in Anson County to US 601 in Union County, and from Mill Grove Road in Union County to I-485 in Mecklenburg County. | Install milled rumble stripes. | 27.51 | Union, Anson, Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | CONSTRUCTION | 616000
HS-2010D | Highway | Safety | NC 24 / NC 27 | SR 1120 (Bethel School Road) intersection in Midland. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 301000
HS-2010D | Highway | Safety | NC 24 / NC 27 | SR 1120 (Bethel School Road) intersection in Midland. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 790000
HS-2010E | Highway | Safety | NC 49 (South Tryon Street) | General Drive; SR 1347 (Nevada Boulevard) intersections in Charlotte. | Install traffic signal at NC 49 and General Drive, and convert NC 49 at SR 1347 (Nevada Boulevard) to a directional crossover. | 0.42 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | UTILITIES | 25000
HS-2010E | Highway | Safety | NC 49 (South Tryon Street) | General Drive; SR 1347 (Nevada Boulevard) intersections in Charlotte. | Install traffic signal at NC 49 and General Drive, and convert NC 49 at SR 1347 (Nevada Boulevard) to a directional crossover. | 0.42 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 1470000
HS-2010F | Highway | Safety | NC 24 / NC 27 | SR 1100 (Pine Bluff Road / Reed Mine Road) intersection near Locust. | Construct a reduced conflict intersection. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 5000
HS-2010F | Highway | Safety | NC 24 / NC 27 | SR 1100 (Pine Bluff Road / Reed Mine Road) intersection near Locust. | Construct a reduced conflict intersection. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | CONSTRUCTION | 1160000
HS-2010G | Highway | Safety | NC 51 | SR 4982 (Polk Street) intersection in Charlotte. | Install pedestrian signals and accommodations. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 70000
HS-2010G | Highway | Safety | NC 51 | SR 4982 (Polk Street) intersection in Charlotte. | Install pedestrian signals and accommodations. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 410000
HS-2010H | Highway | Safety | NC 49 | SR 1155 (Zion Church Road) intersection near Concord. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 210000
HS-2010H | Highway | Safety | NC 49 | SR 1155 (Zion Church Road) intersection near Concord. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 70000
HS-2010H | Highway | Safety | NC 49 | SR 1155 (Zion Church Road) intersection near Concord. | Construct reduced conflict intersection with signalized bulb-outs. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1949000 | FY 2026: 1475000; FY 2027: 474000
HS-2010J | Highway | Safety | NC 73 (Sam Furr Road) | SR 5544 (Catawba Avenue) and Glenfurness Drive intersections in Huntersville. | Install pedestrian accommodations. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | CONSTRUCTION | 865000
HS-2010K | Highway | Safety | NC 24 / NC 27 | Leonard Avenue intersection in Albemarle. | Install audible pedestrian signals. | 0.5 | Stanly | 10 | Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 15000
HS-2010L | Highway | Safety | SR 5901 (Billy Graham Parkway) | NC 49 (Tryon Road) to I-85. | Install guardrail. | 5.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
HS-2010M | Highway | Safety | I-85; I-77; I-277; I-485; and US 74 | Various locations. | Install wrong way pavement markings and signs. |  | Mecklenburg, Cabarrus | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 783000
HS-2010N | Highway | Safety | NC 740; US 52 | Mile marker 0 to mile marker 12.8 in Stanly County; Mile marker 4.9 to mile marker 10.5 in Anson County. | Install rumble stripes and long life pavement markings. |  | Stanly, Anson | 10 | Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 636000
HS-2010O | Highway | Safety | NC 73 | Mile marker 0 to mile marker 4.3, mile marker 13.1 to mile marker 18.9, mile marker 20.9 to mile marker 24.0 in Cabarrus County; Mile marker 0 to mile marker 8.1 in Stanly County. | Install rumble stripes and long life pavement markings. |  | Cabarrus, Stanly | 10 | Cabarrus-Rowan MPO, Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 1400000
HS-2010P | Highway | Safety | NC 49; US 601; NC 3 | Mile marker 13.8 to mile marker 15.8; Mile marker 5.4 to mile marker 12.3; Mile marker 13.8 to mile marker 20.3. | Install rumble stripes and long life pavement markings. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | CONSTRUCTION | 885000
HS-2010Q | Highway | Safety | NC 49 | SR 2635 (Old Airport Road) intersection in Concord. | Install directional crossover with U-turn bulb-out. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 10000
HS-2010Q | Highway | Safety | NC 49 | SR 2635 (Old Airport Road) intersection in Concord. | Install directional crossover with U-turn bulb-out. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 10000
HS-2010Q | Highway | Safety | NC 49 | SR 2635 (Old Airport Road) intersection in Concord. | Install directional crossover with U-turn bulb-out. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 750000 | FY 2027: 597000; FY 2028: 153000
HS-2010R | Highway | Safety | SR 1168 (Robinson Church Road) | SR 1169 (Peach Orchard Road) intersection near Harrisburg. | Widen shoulders and improve superelevation. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HS-2010R | Highway | Safety | SR 1168 (Robinson Church Road) | SR 1169 (Peach Orchard Road) intersection near Harrisburg. | Widen shoulders and improve superelevation. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | UTILITIES | 25000 | FY 2027: 25000
HS-2010R | Highway | Safety | SR 1168 (Robinson Church Road) | SR 1169 (Peach Orchard Road) intersection near Harrisburg. | Widen shoulders and improve superelevation. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | CONSTRUCTION | 730000 | FY 2027: 435000; FY 2028: 295000
HS-2011 | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2011A | Highway | Safety | Various | Routes in Division 11. | Install long life pavement markings. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 1816000
HS-2011B | Highway | Safety | US 221 / US 321 | Deerfield Road intersection to Boone Mall in Boone. | Install pedestrian countdown heads and flashing yellow arrows at various intersections. | 0.99 | Watauga | 11 | High Country RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 116000
HS-2011C | Highway | Safety | SR 1511 (Roseboro Road) | Mile marker 0.77 to mile marker 0.82 near Linville. | Install shoulder guardrail. | 0.05 | Avery | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 20000
HS-2011D | Highway | Safety | Various | Routes in Division 11. | Install long life pavement markings. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 855000
HS-2011E | Highway | Safety | NC 16 | US 221 to the Virginia state line. | Install new and upgrade existing guardrail. |  | Ashe | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | HSIP | CONSTRUCTION | 2200000 | FY 2026: 625000
HS-2011F | Highway | Safety | Various | Routes in Division 11. | Install rumble stripes and long life pavement markings. Install shoulder guardrail near SR 2329 (Woodhaven Road). |  | Wilkes | 11 | High Country RPO |  | Division 11 |  | HSIP | CONSTRUCTION | 420000
HS-2011G | Highway | Safety | NC 89 (Pine Street) | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Surry | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | ENGINEERING | 100000
HS-2011G | Highway | Safety | NC 89 (Pine Street) | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Surry | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HSIP | RIGHT-OF-WAY | 300000 | FY 2026: 300000
HS-2011G | Highway | Safety | NC 89 (Pine Street) | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Surry | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | RIGHT-OF-WAY | 125000 | FY 2026: 125000
HS-2011G | Highway | Safety | NC 89 (Pine Street) | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Surry | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | UTILITIES | 25000 | FY 2026: 25000
HS-2011G | Highway | Safety | NC 89 (Pine Street) | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Surry | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HSIP | CONSTRUCTION | 509000 | FY 2027: 389000; FY 2028: 120000
HS-2011G | Highway | Safety | NC 89 (Pine Street) | SR 1345 (Beulah Road / Beulah Church Road) intersection near Lowgap. | Construct roundabout. | 0.5 | Surry | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | CONSTRUCTION | 765000 | FY 2029: 584000; FY 2030: 181000
HS-2012 | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2012A | Highway | Safety | SR 1849 (Mount Pleasant Road) | Bridge 018163 over Mountain Creek portion on Lake Norman. | Install guardrail. | 0.05 | Catawba | 12 | Greater Hickory MPO | COMPLETE | Division 12 |  | HSIP | CONSTRUCTION | 76000
HS-2012A | Highway | Safety | SR 1849 (Mount Pleasant Road) | Bridge 018163 over Mountain Creek portion on Lake Norman. | Install guardrail. | 0.05 | Catawba | 12 | Greater Hickory MPO | COMPLETE | Division 12 |  | T(M) | CONSTRUCTION | 8000
HS-2012B | Highway | Safety | SR 1844 (Slanting Bridge Road) | Bridge 018023 over Lake Norman. | Upgrade guardrail and end units. | 0.09 | Catawba | 12 | Greater Hickory MPO | COMPLETE | Division 12 |  | HSIP | CONSTRUCTION | 335000
HS-2012B | Highway | Safety | SR 1844 (Slanting Bridge Road) | Bridge 018023 over Lake Norman. | Upgrade guardrail and end units. | 0.09 | Catawba | 12 | Greater Hickory MPO | COMPLETE | Division 12 |  | T(M) | CONSTRUCTION | 37000
HS-2012C | Highway | Safety | SR 1125 (Shearers Road) | SR 1147 (Rocky River Road) intersection near Mooresville. | Install traffic signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | ENGINEERING | 18000
HS-2012C | Highway | Safety | SR 1125 (Shearers Road) | SR 1147 (Rocky River Road) intersection near Mooresville. | Install traffic signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | T(M) | ENGINEERING | 2000
HS-2012C | Highway | Safety | SR 1125 (Shearers Road) | SR 1147 (Rocky River Road) intersection near Mooresville. | Install traffic signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 184000
HS-2012C | Highway | Safety | SR 1125 (Shearers Road) | SR 1147 (Rocky River Road) intersection near Mooresville. | Install traffic signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | T(M) | CONSTRUCTION | 20000
HS-2012D | Highway | Safety | Various | Secondary routes in Division 12. | Install long life pavement markings. |  | Alexander, Catawba, Iredell | 12 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 3254000
HS-2012D | Highway | Safety | Various | Secondary routes in Division 12. | Install long life pavement markings. |  | Alexander, Catawba, Iredell | 12 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | T(M) | CONSTRUCTION | 361000
HS-2012E | Highway | Safety | Various | Secondary routes in Division 12. | Install long life pavement markings. |  | Lincoln, Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 2408000
HS-2012E | Highway | Safety | Various | Secondary routes in Division 12. | Install long life pavement markings. |  | Lincoln, Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | T(M) | CONSTRUCTION | 267000
HS-2012F | Highway | Safety | SR 1360 (Beth Haven Church Road) | SR 1373 (Wingate Hill Road / Forney Hill Road) intersection near Denver. | Install all-way stop, upgrade signs and pavement markings, and improve shoulders. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 22000
HS-2012F | Highway | Safety | SR 1360 (Beth Haven Church Road) | SR 1373 (Wingate Hill Road / Forney Hill Road) intersection near Denver. | Install all-way stop, upgrade signs and pavement markings, and improve shoulders. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | T(M) | CONSTRUCTION | 2000
HS-2012G | Highway | Safety | NC 18 | Mile marker 0.0 to mile marker 6.0. | Install centerline and shoulder rumble stripes. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 406000
HS-2012G | Highway | Safety | NC 18 | Mile marker 0.0 to mile marker 6.0. | Install centerline and shoulder rumble stripes. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | T(M) | CONSTRUCTION | 45000
HS-2012H | Highway | Safety | NC 10 | Mile marker 19.8 to mile marker 27.1. | Install centerline and shoulder rumble stripes. |  | Catawba | 12 | Greater Hickory MPO |  | Region F |  | HSIP | CONSTRUCTION | 420000
HS-2012H | Highway | Safety | NC 10 | Mile marker 19.8 to mile marker 27.1. | Install centerline and shoulder rumble stripes. |  | Catawba | 12 | Greater Hickory MPO |  | Region F |  | T(M) | CONSTRUCTION | 47000
HS-2012I | Highway | Safety | NC 10 | Mile marker 11.9 to mile marker 15.0. | Install centerline and shoulder rumble stripes. |  | Catawba | 12 | Greater Hickory MPO |  | Region F |  | HSIP | CONSTRUCTION | 204000
HS-2012I | Highway | Safety | NC 10 | Mile marker 11.9 to mile marker 15.0. | Install centerline and shoulder rumble stripes. |  | Catawba | 12 | Greater Hickory MPO |  | Region F |  | T(M) | CONSTRUCTION | 23000
HS-2012J | Highway | Safety | NC 275 | Mile marker 5.1 to mile marker 9.7. | Install centerline and shoulder rumble stripes. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 137000
HS-2012J | Highway | Safety | NC 275 | Mile marker 5.1 to mile marker 9.7. | Install centerline and shoulder rumble stripes. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | T(M) | CONSTRUCTION | 15000
HS-2012K | Highway | Safety | NC 150 | Mile marker 11.4 to mile marker 11.9. | Install centerline and shoulder rumble stripes. |  | Iredell | 12 | Charlotte Regional TPO |  | Region F |  | HSIP | CONSTRUCTION | 22000
HS-2012K | Highway | Safety | NC 150 | Mile marker 11.4 to mile marker 11.9. | Install centerline and shoulder rumble stripes. |  | Iredell | 12 | Charlotte Regional TPO |  | Region F |  | T(M) | CONSTRUCTION | 2000
HS-2012L | Highway | Safety | NC 18 | Mile marker 13.5 to mile marker 18.6. | Install centerline and shoulder rumble stripes. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 167000
HS-2012L | Highway | Safety | NC 18 | Mile marker 13.5 to mile marker 18.6. | Install centerline and shoulder rumble stripes. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | T(M) | CONSTRUCTION | 19000
HS-2012M | Highway | Safety | NC 10 | Mile marker 0.0 to mile marker 2.2 in Lincoln County and mile marker 0.0 to mile marker 11.0 in Catawba County. | Install centerline and shoulder rumble stripes. |  | Catawba, Lincoln | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 472000
HS-2012M | Highway | Safety | NC 10 | Mile marker 0.0 to mile marker 2.2 in Lincoln County and mile marker 0.0 to mile marker 11.0 in Catawba County. | Install centerline and shoulder rumble stripes. |  | Catawba, Lincoln | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F |  | T(M) | CONSTRUCTION | 52000
HS-2013 | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2013A | Highway | Safety | US 321 | Bridges 012366 and 012367 at the Catawba County line. | Install guardrail. | 0.19 | Burke | 13 | Greater Hickory MPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 92000
HS-2013B | Highway | Safety | NC 226 | US 19E to SR 1250 (Snow Creek Road). | Upgrade guardrail. | 6.04 | Mitchell | 13 | High Country RPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 290000
HS-2013C | Highway | Safety | NC 181 | US 64 to SR 1405 (Brown Mountain Beach Road). | Upgrade guardrail. | 11.35 | Burke | 13 | Greater Hickory MPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 195000
HS-2013D | Highway | Safety | NC 226 | SR 1250 (Snow Creek Road) to NC 261. | Upgrade guardrail. | 3.36 | Mitchell | 13 | High Country RPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 272000
HS-2013E | Highway | Safety | US 64 / NC 18 | NC 181 to Caldwell County line. | Upgrade guardrail. | 7.49 | Burke | 13 | Greater Hickory MPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 385000
HS-2013F | Highway | Safety | US 321; US 70; US 19E; US 221A | Various locations. | Upgrade guardrail. |  | Burke, Mitchell, Rutherford | 13 | Greater Hickory MPO, Foothills RPO, High Country RPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 348000
HS-2013G | Highway | Safety | SR 1510 (Hudlow Road) | US 221A to NC 64. | Upgrade guardrail. | 5.39 | Rutherford | 13 | Foothills RPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 497000
HS-2013H | Highway | Safety | US 221 | NC 226 / US 221 BUS to US 70. | Improve pavement. | 2.49 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 530000
HS-2013I | Highway | Safety | SR 1318 (Big Laurel Road) | SR 1340 (Pine Branch Road) to US 23 near Mars Hill. | Install guardrail. | 8.59 | Madison | 13 | Land-of-Sky RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 520000
HS-2013J | Highway | Safety | US 19W | SR 1454 (Cane River School Road) to SR 1382 (Silver Gap Road) near Burnsville. | Install guardrail. | 5.07 | Yancey | 13 | High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 731000
HS-2013K | Highway | Safety | SR 1003 (Reems Creek Road) | SR 2106 (Parker Cove Road) to SR 2114 (Sugar Cove Road) near Weaverville. | Install guardrail. | 3.61 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 274000
HS-2013L | Highway | Safety | NC 226 | US 19E to NC 261 near Spruce Pine. | Install guardrail. | 9.4 | Mitchell | 13 | High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 590000
HS-2013M | Highway | Safety | SR 1135 (Old Fort / Sugar Hill Road) | SR 1103 (Bat Cave Road) to SR 1001 (Sugar Hill Road / Montford Cove Road) near Old Fort. | Install guardrail. | 8.95 | McDowell | 13 | Foothills RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 890000
HS-2013N | Highway | Safety | SR 1006 (Bostic-Sunshine Highway) | SR 1007 (Andrews Mill Road / Piney Mountain Church Road) to NC 226 near Bostic. | Install guardrail. | 9.78 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 875000
HS-2013O | Highway | Safety | SR 3075 (Onteora Boulevard) | Bridge 100460 over I-40. | Construct sidewalk and upgrade bridge rail. | 0.5 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 395000
HS-2013P | Highway | Safety | NC 63 | SR 1220 (South Turkey Creek Road) intersection near Leicester. | Construct turn lane. | 0.5 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2013P | Highway | Safety | NC 63 | SR 1220 (South Turkey Creek Road) intersection near Leicester. | Construct turn lane. | 0.5 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 715000 | FY 2027: 310000; FY 2028: 405000
HS-2013Q | Highway | Safety | Various | Primary and secondary two-lane and four-lane roadways in Division 13. | Install long life pavement markings. |  | Buncombe, McDowell, Yancey, Madison, Burke, Rutherford, Mitchell | 13 | French Broad River MPO, Foothills RPO, High Country RPO, Land-of-Sky RPO, Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 3337000 | FY 2026: 3337000
HS-2013R | Highway | Safety | Various | Primary and secondary two-lane roadways in Division 13. | Install long life pavement markings. |  | Burke, Madison, Rutherford, McDowell | 13 | Foothills RPO, Greater Hickory MPO, Land-of-Sky RPO, French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 2966000 | FY 2026: 322000
HS-2014 | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2014A | Highway | Safety | US 64 / NC 28 | SR 1560 (Rogers Road) to SR 1533 (Walnut Creek Road) near Franklin. | Install centerline rumble stripes, long life pavement markings, and intermittent paved shoulders. | 5.76 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 1080000
HS-2014A | Highway | Safety | US 64 / NC 28 | SR 1560 (Rogers Road) to SR 1533 (Walnut Creek Road) near Franklin. | Install centerline rumble stripes, long life pavement markings, and intermittent paved shoulders. | 5.76 | Macon | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | T(M) | CONSTRUCTION | 120000
HS-2014AA | Highway | Safety | US 64 | SR 1147 (Oak Forest Road) intersection near Hayesville. | Extend two-way left lane. | 0.5 | Clay | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 46000
HS-2014AA | Highway | Safety | US 64 | SR 1147 (Oak Forest Road) intersection near Hayesville. | Extend two-way left lane. | 0.5 | Clay | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 5000
HS-2014AB | Highway | Safety | NC 108 (Mills Street) | SR 1534 (Peak Street) intersection in Columbus. | Install pedestrian signals and upgrade curb ramp. | 0.5 | Polk | 14 | Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 152000
HS-2014AB | Highway | Safety | NC 108 (Mills Street) | SR 1534 (Peak Street) intersection in Columbus. | Install pedestrian signals and upgrade curb ramp. | 0.5 | Polk | 14 | Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 16000
HS-2014AC | Highway | Safety | US 276 (Greenville Highway) | SR 1118 (Gallimore Road) intersection in Brevard. | Install traffic signal with pedestrian signals. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Region G |  | HSIP | CONSTRUCTION | 193000 | FY 2026: 13000
HS-2014AC | Highway | Safety | US 276 (Greenville Highway) | SR 1118 (Gallimore Road) intersection in Brevard. | Install traffic signal with pedestrian signals. | 0.5 | Transylvania | 14 | Land-of-Sky RPO |  | Region G |  | T(M) | CONSTRUCTION | 22000 | FY 2026: 2000
HS-2014AD | Highway | Safety | SR 1356 (Savannah Drive) | US 23 Business to Nicol Arms Road. | Construct sidewalk. | 0.12 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 131000 | FY 2026: 18000
HS-2014AD | Highway | Safety | SR 1356 (Savannah Drive) | US 23 Business to Nicol Arms Road. | Construct sidewalk. | 0.12 | Jackson | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 15000 | FY 2026: 2000
HS-2014B | Highway | Safety | SR 1157 (Cullowhee Mountain Road) | Mile marker 2.6 to mile marker 6.6 near Cullowhee. | Install guardrail. | 4.02 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 99000
HS-2014B | Highway | Safety | SR 1157 (Cullowhee Mountain Road) | Mile marker 2.6 to mile marker 6.6 near Cullowhee. | Install guardrail. | 4.02 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | T(M) | CONSTRUCTION | 11000
HS-2014C | Highway | Safety | Various | Freeway ramps in Division 14 | Install snowplowable markers and pavement markings for wrong way ramp arrows. | 0.5 | Haywood, Henderson, Macon, Polk, Swain | 14 | Southwestern RPO, Foothills RPO, French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 46000
HS-2014C | Highway | Safety | Various | Freeway ramps in Division 14 | Install snowplowable markers and pavement markings for wrong way ramp arrows. | 0.5 | Haywood, Henderson, Macon, Polk, Swain | 14 | Southwestern RPO, Foothills RPO, French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 6000
HS-2014D | Highway | Safety | SR 1325 (Centennial Drive) | Three midblock crossings near SR 1169 (Central Drive). | Install rectangular flashing beacons. | 0.5 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 53000
HS-2014D | Highway | Safety | SR 1325 (Centennial Drive) | Three midblock crossings near SR 1169 (Central Drive). | Install rectangular flashing beacons. | 0.5 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | T(M) | CONSTRUCTION | 6000
HS-2014E | Highway | Safety | US 74 | SR 1392 (Barkers Creek Road) to east of SR 1388 (Dicks Creek Road) and from Jackson County line to Bridges 050107 and 050110. | Improve pavement. | 9.77 | Haywood, Jackson | 14 | French Broad River MPO, Southwestern RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 878000
HS-2014E | Highway | Safety | US 74 | SR 1392 (Barkers Creek Road) to east of SR 1388 (Dicks Creek Road) and from Jackson County line to Bridges 050107 and 050110. | Improve pavement. | 9.77 | Haywood, Jackson | 14 | French Broad River MPO, Southwestern RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 97000
HS-2014F | Highway | Safety | SR 1100 (Old Highway 64 West) | SR 1135 (Settawig Road) intersection near Brasstown. | Widen and install guardrail. | 0.5 | Clay | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 40000
HS-2014F | Highway | Safety | SR 1100 (Old Highway 64 West) | SR 1135 (Settawig Road) intersection near Brasstown. | Widen and install guardrail. | 0.5 | Clay | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | T(M) | CONSTRUCTION | 5000
HS-2014G | Highway | Safety | NC 143 | Long Hungry Road intersection near Robbinsville. | Improve alignment and superelevation. | 0.5 | Graham | 14 | Southwestern RPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 2000
HS-2014G | Highway | Safety | NC 143 | Long Hungry Road intersection near Robbinsville. | Improve alignment and superelevation. | 0.5 | Graham | 14 | Southwestern RPO |  | Region G |  | T(M) | RIGHT-OF-WAY | 0
HS-2014G | Highway | Safety | NC 143 | Long Hungry Road intersection near Robbinsville. | Improve alignment and superelevation. | 0.5 | Graham | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 464000
HS-2014G | Highway | Safety | NC 143 | Long Hungry Road intersection near Robbinsville. | Improve alignment and superelevation. | 0.5 | Graham | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 52000
HS-2014H | Highway | Safety | US 23 Business (Haywood Road); SR 1557 (Front Street) | Church Street intersection in Dillsboro; SR 1558 (Depot Street) intersection in Dillsboro. | Install rectangular rapid flashing beacon and upgrade curb ramps. | 0.5 | Jackson | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 96000
HS-2014H | Highway | Safety | US 23 Business (Haywood Road); SR 1557 (Front Street) | Church Street intersection in Dillsboro; SR 1558 (Depot Street) intersection in Dillsboro. | Install rectangular rapid flashing beacon and upgrade curb ramps. | 0.5 | Jackson | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 11000
HS-2014I | Highway | Safety | US 25 Business (Asheville Highway) | Hendersonville City limit to SR 1534 (Naples Road). | Install rumble stripes and long life pavement markings. | 4.3 | Henderson | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 314000
HS-2014I | Highway | Safety | US 25 Business (Asheville Highway) | Hendersonville City limit to SR 1534 (Naples Road). | Install rumble stripes and long life pavement markings. | 4.3 | Henderson | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 35000
HS-2014J | Highway | Safety | Various | Secondary routes in Division 14. | Install long life pavement markings. |  | Haywood, Polk | 14 | French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 2312000
HS-2014J | Highway | Safety | Various | Secondary routes in Division 14. | Install long life pavement markings. |  | Haywood, Polk | 14 | French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | T(M) | CONSTRUCTION | 258000
HS-2014K | Highway | Safety | US 19 | Holston Village Road and SR 1197 (Golf Course Road) intersections near Waynesville. | Construct intersection improvements. | 0.5 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 99000
HS-2014K | Highway | Safety | US 19 | Holston Village Road and SR 1197 (Golf Course Road) intersections near Waynesville. | Construct intersection improvements. | 0.5 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | T(M) | CONSTRUCTION | 11000
HS-2014L | Highway | Safety | US 64 | SR 1574 (Fruitland Road), SR 1006 (Howard Gap Road), SR 1519 (Thompson Street) / SR 1751 (Freeman Street), and SR 1749 (Orr's Camp Road) / SR 1634 (Carolina Avenue) intersections in Hendersonville. | Construct intersection improvements. | 0.5 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 513000
HS-2014L | Highway | Safety | US 64 | SR 1574 (Fruitland Road), SR 1006 (Howard Gap Road), SR 1519 (Thompson Street) / SR 1751 (Freeman Street), and SR 1749 (Orr's Camp Road) / SR 1634 (Carolina Avenue) intersections in Hendersonville. | Construct intersection improvements. | 0.5 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | T(M) | CONSTRUCTION | 57000
HS-2014M | Highway | Safety | US 64 (Asheville Highway) | SR 1592 (Hospital Drive) / Straus Parkway intersection in Brevard. | Construct intersection improvements. | 0.5 | Transylvania | 14 | Land-of-Sky RPO, French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 203000
HS-2014M | Highway | Safety | US 64 (Asheville Highway) | SR 1592 (Hospital Drive) / Straus Parkway intersection in Brevard. | Construct intersection improvements. | 0.5 | Transylvania | 14 | Land-of-Sky RPO, French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 22000
HS-2014O | Highway | Safety | US 64 | SR 1586 (South Mills Gap Road) / Tuttle Road intersection near Edneyville. | Install traffic signal. | 0.5 | Henderson | 14 | French Broad River MPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 18000
HS-2014O | Highway | Safety | US 64 | SR 1586 (South Mills Gap Road) / Tuttle Road intersection near Edneyville. | Install traffic signal. | 0.5 | Henderson | 14 | French Broad River MPO |  | Region G |  | T(M) | RIGHT-OF-WAY | 2000
HS-2014O | Highway | Safety | US 64 | SR 1586 (South Mills Gap Road) / Tuttle Road intersection near Edneyville. | Install traffic signal. | 0.5 | Henderson | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 68000
HS-2014O | Highway | Safety | US 64 | SR 1586 (South Mills Gap Road) / Tuttle Road intersection near Edneyville. | Install traffic signal. | 0.5 | Henderson | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 8000
HS-2014P | Highway | Safety | Various | Primary and secondary routes in Division 14. | Install long life pavement markings. |  | Macon, Cherokee, Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 2659000
HS-2014P | Highway | Safety | Various | Primary and secondary routes in Division 14. | Install long life pavement markings. |  | Macon, Cherokee, Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | T(M) | CONSTRUCTION | 296000
HS-2014Q | Highway | Safety | US 64; US 25 Business | Various locations. | Upgrade signal system. |  | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 202000
HS-2014Q | Highway | Safety | US 64; US 25 Business | Various locations. | Upgrade signal system. |  | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | T(M) | CONSTRUCTION | 22000
HS-2014R | Highway | Safety | Various | Primary and secondary routes in Division 14. | Install long life pavement markings. |  | Haywood, Henderson, Jackson, Polk, Transylvania | 14 | Foothills RPO, French Broad River MPO, Land-of-Sky RPO, Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 1102000
HS-2014R | Highway | Safety | Various | Primary and secondary routes in Division 14. | Install long life pavement markings. |  | Haywood, Henderson, Jackson, Polk, Transylvania | 14 | Foothills RPO, French Broad River MPO, Land-of-Sky RPO, Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | T(M) | CONSTRUCTION | 122000
HS-2014S | Highway | Safety | US 19 | Jackson County to Maggie Valley. | Install long life pavement markings. | 3.5 | Haywood | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 237000
HS-2014S | Highway | Safety | US 19 | Jackson County to Maggie Valley. | Install long life pavement markings. | 3.5 | Haywood | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 26000
HS-2014T | Highway | Safety | US 19 | SR 1336 (Old River Road / Deep Creek Street) to Jackson County. | Install rumble stripes and long life pavement markings. | 5.15 | Swain | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 328000
HS-2014T | Highway | Safety | US 19 | SR 1336 (Old River Road / Deep Creek Street) to Jackson County. | Install rumble stripes and long life pavement markings. | 5.15 | Swain | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 36000
HS-2014U | Highway | Safety | US 19 | Cherokee County line to Swain County line. | Install rumble stripes and long life pavement markings. | 2.61 | Macon | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 158000
HS-2014U | Highway | Safety | US 19 | Cherokee County line to Swain County line. | Install rumble stripes and long life pavement markings. | 2.61 | Macon | 14 | Southwestern RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 18000
HS-2014V | Highway | Safety | SR 1564 (Brasstown Road) | John C. Campbell Folk School. | Install four rectangular flashing beacons and construct concrete landing pads. | 0.49 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 135000
HS-2014V | Highway | Safety | SR 1564 (Brasstown Road) | John C. Campbell Folk School. | Install four rectangular flashing beacons and construct concrete landing pads. | 0.49 | Cherokee | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 15000
HS-2014W | Highway | Safety | US 64 (Murphy Road) | SR 1146 (Patton Road) and SR 1442 (Old Murphy Road) intersections near Franklin. | Construct directional leftover with U-turn bulb-outs. |  | Macon | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 1309000 | FY 2026: 1309000
HS-2014W | Highway | Safety | US 64 (Murphy Road) | SR 1146 (Patton Road) and SR 1442 (Old Murphy Road) intersections near Franklin. | Construct directional leftover with U-turn bulb-outs. |  | Macon | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 146000 | FY 2026: 146000
HS-2014X | Highway | Safety | US 64 / US 74 | NC 60 near Murphy. | Construct directional leftover with U-turn bulb-outs. | 0.5 | Cherokee | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 841000
HS-2014X | Highway | Safety | US 64 / US 74 | NC 60 near Murphy. | Construct directional leftover with U-turn bulb-outs. | 0.5 | Cherokee | 14 | Southwestern RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 93000
HS-2014Y | Highway | Safety | US 19 (Dellwood Road) | North Lakeshore Drive. | Install traffic signal with pedestrian accommodations. | 0.5 | Haywood | 14 | French Broad River MPO |  | Region G |  | HSIP | UTILITIES | 126000
HS-2014Y | Highway | Safety | US 19 (Dellwood Road) | North Lakeshore Drive. | Install traffic signal with pedestrian accommodations. | 0.5 | Haywood | 14 | French Broad River MPO |  | Region G |  | T(M) | UTILITIES | 14000
HS-2014Y | Highway | Safety | US 19 (Dellwood Road) | North Lakeshore Drive. | Install traffic signal with pedestrian accommodations. | 0.5 | Haywood | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 369000 | FY 2026: 180000
HS-2014Y | Highway | Safety | US 19 (Dellwood Road) | North Lakeshore Drive. | Install traffic signal with pedestrian accommodations. | 0.5 | Haywood | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 41000 | FY 2026: 20000
HS-2014Z | Highway | Safety | SR 1337 (West Deep Creek Road) | SR 1338 (Deep Creek Cemetery Road) intersection in Bryson City. | Install pedestrian accommodations. | 0.5 | Swain | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 132000 | FY 2026: 18000
HS-2014Z | Highway | Safety | SR 1337 (West Deep Creek Road) | SR 1338 (Deep Creek Cemetery Road) intersection in Bryson City. | Install pedestrian accommodations. | 0.5 | Swain | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 15000 | FY 2026: 2000
HS-2015 | Highway | Safety | Various | Locations statewide. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Statewide | 99 | Statewide Project
HS-2015DIV | Highway | Safety | Various | Locations statewide. Division Needs funding. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | VRU | ENGINEERING | 26805000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000
HS-2015REG | Highway | Safety | Various | Locations statewide. Regional Impact funding. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Statewide | 99 | Statewide Project |  | Region SW |  | VRU | ENGINEERING | 26805000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000
HS-2015SW | Highway | Safety | Various | Locations statewide. Statewide Mobility funding. | Vulnerable road user pedestrian / bicycle improvement program excluding Grand Strand MPO. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | VRU | ENGINEERING | 35740000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000
HS-2016 | Highway | Safety | Various | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO
HS-2016DIV | Highway | Safety | Various | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1 |  | VRU | CONSTRUCTION | 300000
HS-2016REG | Highway | Safety | Various | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | VRU | CONSTRUCTION | 300000
HS-2016SW | Highway | Safety | Various | Routes in Division 1. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2017 | Highway | Safety | Various | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO
HS-2017DIV | Highway | Safety | Various | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2 |  | VRU | CONSTRUCTION | 300000
HS-2017REG | Highway | Safety | Various | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Region B |  | VRU | CONSTRUCTION | 300000
HS-2017SW | Highway | Safety | Various | Routes in Division 2. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2018 | Highway | Safety | Various | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO
HS-2018DIV | Highway | Safety | Various | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO |  | Division 3 |  | VRU | CONSTRUCTION | 300000
HS-2018REG | Highway | Safety | Various | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO |  | Region B |  | VRU | CONSTRUCTION | 300000
HS-2018SW | Highway | Safety | Various | Routes in Division 3. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2019 | Highway | Safety | Various | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO
HS-2019DIV | Highway | Safety | Various | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | VRU | CONSTRUCTION | 300000
HS-2019REG | Highway | Safety | Various | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Region A |  | VRU | CONSTRUCTION | 300000
HS-2019SW | Highway | Safety | Various | Routes in Division 4. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2020 | Highway | Safety | Various | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO
HS-2020DIV | Highway | Safety | Various | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Division 5 |  | VRU | CONSTRUCTION | 300000
HS-2020REG | Highway | Safety | Various | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Region C |  | VRU | CONSTRUCTION | 300000
HS-2020SW | Highway | Safety | Various | Routes in Division 5. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2021 | Highway | Safety | Various | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO
HS-2021DIV | Highway | Safety | Various | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Division 6 |  | VRU | CONSTRUCTION | 300000
HS-2021REG | Highway | Safety | Various | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Region C |  | VRU | CONSTRUCTION | 300000
HS-2021SW | Highway | Safety | Various | Routes in Division 6. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2022 | Highway | Safety | Various | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO
HS-2022DIV | Highway | Safety | Various | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Division 7 |  | VRU | CONSTRUCTION | 300000
HS-2022REG | Highway | Safety | Various | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Region D |  | VRU | CONSTRUCTION | 300000
HS-2022SW | Highway | Safety | Various | Routes in Division 7. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2023 | Highway | Safety | Various | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO
HS-2023DIV | Highway | Safety | Various | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Division 8 |  | VRU | CONSTRUCTION | 300000
HS-2023REG | Highway | Safety | Various | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Region E |  | VRU | CONSTRUCTION | 300000
HS-2023SW | Highway | Safety | Various | Routes in Division 8. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2024 | Highway | Safety | Various | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO
HS-2024DIV | Highway | Safety | Various | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Division 9 |  | VRU | CONSTRUCTION | 300000
HS-2024REG | Highway | Safety | Various | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Region D |  | VRU | CONSTRUCTION | 300000
HS-2024SW | Highway | Safety | Various | Routes in Division 9. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2025 | Highway | Safety | Various | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO
HS-2025DIV | Highway | Safety | Various | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Division 10 |  | VRU | CONSTRUCTION | 300000
HS-2025REG | Highway | Safety | Various | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Region E |  | VRU | CONSTRUCTION | 300000
HS-2025SW | Highway | Safety | Various | Routes in Division 10. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2026 | Highway | Safety | Various | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO
HS-2026DIV | Highway | Safety | Various | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | Division 11 |  | VRU | CONSTRUCTION | 300000
HS-2026REG | Highway | Safety | Various | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | Region F |  | VRU | CONSTRUCTION | 300000
HS-2026SW | Highway | Safety | Various | Routes in Division 11. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2027 | Highway | Safety | Various | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO
HS-2027DIV | Highway | Safety | Various | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | Division 12 |  | VRU | CONSTRUCTION | 300000
HS-2027REG | Highway | Safety | Various | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | Region F |  | VRU | CONSTRUCTION | 300000
HS-2027SW | Highway | Safety | Various | Routes in Division 12. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2028 | Highway | Safety | Various | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO
HS-2028DIV | Highway | Safety | Various | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | Division 13 |  | VRU | CONSTRUCTION | 300000
HS-2028REG | Highway | Safety | Various | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | Region G |  | VRU | CONSTRUCTION | 300000
HS-2028SW | Highway | Safety | Various | Routes in Division 13. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2029 | Highway | Safety | Various | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO
HS-2029DIV | Highway | Safety | Various | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | Division 14 |  | VRU | CONSTRUCTION | 300000
HS-2029REG | Highway | Safety | Various | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | Region G |  | VRU | CONSTRUCTION | 300000
HS-2029SW | Highway | Safety | Various | Routes in Division 14. | Implement Vulnerable Road User Bicycle and Pedestrian Improvement Program. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2401 | Highway | Safety | Various | Routes in Division 1. | Construct safety improvements. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2401A | Highway | Safety | US 17 (Future I-87) | US 17 Business / NC 343 Intersection in South Mills | Modify the median opening and install traffic signal. | 0.5 | Camden | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1350000 | FY 2026: 1350000
HS-2401A | Highway | Safety | US 17 (Future I-87) | US 17 Business / NC 343 Intersection in South Mills | Modify the median opening and install traffic signal. | 0.5 | Camden | 1 | Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 150000 | FY 2026: 150000
HS-2401B | Highway | Safety | Various | Primary routes in Division 1 | Upgrade guardrail end units. |  | Hertford, Currituck, Martin, Dare, Gates, Bertie, Northampton, Camden | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 442000
HS-2401B | Highway | Safety | Various | Primary routes in Division 1 | Upgrade guardrail end units. |  | Hertford, Currituck, Martin, Dare, Gates, Bertie, Northampton, Camden | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 49000
HS-2401C | Highway | Safety | US 64 (Future I-87); US 17 Bypass; US 17; NC 11; US 13 | Various locations in Division 1 | Install wrong way pavement markings, markers, and signs at ramps. |  | Washington, Martin, Pasquotank, Chowan, Tyrrell, Bertie, Hertford | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 153000
HS-2401C | Highway | Safety | US 64 (Future I-87); US 17 Bypass; US 17; NC 11; US 13 | Various locations in Division 1 | Install wrong way pavement markings, markers, and signs at ramps. |  | Washington, Martin, Pasquotank, Chowan, Tyrrell, Bertie, Hertford | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 17000
HS-2401D | Highway | Safety | NC 11 | SR 1212 (Short Cut Road) to US 158 | Install rumble stripes and pavement markers. |  | Hertford | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 245000
HS-2401D | Highway | Safety | NC 11 | SR 1212 (Short Cut Road) to US 158 | Install rumble stripes and pavement markers. |  | Hertford | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 27000
HS-2401E | Highway | Safety | NC 186 | Garysburg to the Virginia State line, excluding the seaboard town limits | Install rumble stripes and pavement markings. |  | Northampton | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 411000
HS-2401E | Highway | Safety | NC 186 | Garysburg to the Virginia State line, excluding the seaboard town limits | Install rumble stripes and pavement markings. |  | Northampton | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 46000
HS-2401F | Highway | Safety | US 17 Business (Ehringhaus Street) | NC 344 (Halstead Boulevard) intersection in Elizabeth City | Install audible pedestrian signals. |  | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 11000
HS-2401F | Highway | Safety | US 17 Business (Ehringhaus Street) | NC 344 (Halstead Boulevard) intersection in Elizabeth City | Install audible pedestrian signals. |  | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 1000
HS-2401G | Highway | Safety | US 17 (Future I-87) | Chowan County line to SR 1101 (Bear Swamp Road) | Install rumble stripes. | 4 | Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 144000
HS-2401G | Highway | Safety | US 17 (Future I-87) | Chowan County line to SR 1101 (Bear Swamp Road) | Install rumble stripes. | 4 | Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 16000
HS-2401H | Highway | Safety | US 17 Business | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Martin | 1 | Mid-East RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 90000 | FY 2027: 90000
HS-2401H | Highway | Safety | US 17 Business | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Martin | 1 | Mid-East RPO |  | Region A |  | T(M) | RIGHT-OF-WAY | 10000 | FY 2027: 10000
HS-2401H | Highway | Safety | US 17 Business | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Martin | 1 | Mid-East RPO |  | Region A |  | HSIP | UTILITIES | 27000 | FY 2027: 27000
HS-2401H | Highway | Safety | US 17 Business | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Martin | 1 | Mid-East RPO |  | Region A |  | T(M) | UTILITIES | 3000 | FY 2027: 3000
HS-2401H | Highway | Safety | US 17 Business | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Martin | 1 | Mid-East RPO |  | Region A |  | HSIP | CONSTRUCTION | 945000 | FY 2027: 945000
HS-2401H | Highway | Safety | US 17 Business | SR 1001 (Bear Grass Road), SR 1190 (Harrisway Drive), and Country Club Drive | Construct reduced conflict intersection. |  | Martin | 1 | Mid-East RPO |  | Region A |  | T(M) | CONSTRUCTION | 105000 | FY 2027: 105000
HS-2401I | Highway | Safety | US 158 | SR 1206 (The Woods Road) / Dogwood Trail intersection in Kitty Hawk | Install curb, gutter, ramps and crosswalks. |  | Dare | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 102000
HS-2401I | Highway | Safety | US 158 | SR 1206 (The Woods Road) / Dogwood Trail intersection in Kitty Hawk | Install curb, gutter, ramps and crosswalks. |  | Dare | 1 | Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 11000
HS-2401J | Highway | Safety | US 158 | SR 1186 (Walnut Island Boulevard) to SR 1131 (Poplar Branch Road) in Grandy | Install pedestrian signal heads, crosswalks, and sidewalks. | 0.25 | Currituck | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 166000
HS-2401J | Highway | Safety | US 158 | SR 1186 (Walnut Island Boulevard) to SR 1131 (Poplar Branch Road) in Grandy | Install pedestrian signal heads, crosswalks, and sidewalks. | 0.25 | Currituck | 1 | Albemarle RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 18000
HS-2401K | Highway | Safety | US 158 | NC 168 to Wright Brothers Memorial Bridge, and US 158 to north of Lark Drive | Install rumble stripes and pavement markings. | 40 | Currituck | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 569000
HS-2401K | Highway | Safety | US 158 | NC 168 to Wright Brothers Memorial Bridge, and US 158 to north of Lark Drive | Install rumble stripes and pavement markings. | 40 | Currituck | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 63000
HS-2401L | Highway | Safety | NC 12 (Virginia Dare Trail) | Neptune Drive intersection in Kill Devil Hills | Remove existing crosswalk, install new crosswalk with pedestrian heads, and revise signal. |  | Dare | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 90000
HS-2401L | Highway | Safety | NC 12 (Virginia Dare Trail) | Neptune Drive intersection in Kill Devil Hills | Remove existing crosswalk, install new crosswalk with pedestrian heads, and revise signal. |  | Dare | 1 | Albemarle RPO |  | Region A |  | T(M) | CONSTRUCTION | 10000
HS-2401M | Highway | Safety | NC 344 | Tanglewood Parkway to Mount Everest Drive in Elizabeth City. | Remove portion of median island and install pedestrian accommodations. | 0.36 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 81000
HS-2401M | Highway | Safety | NC 344 | Tanglewood Parkway to Mount Everest Drive in Elizabeth City. | Remove portion of median island and install pedestrian accommodations. | 0.36 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | T(M) | CONSTRUCTION | 9000
HS-2401N | Highway | Safety | NC 168 | SR 1229 (Baxter Lane) intersection and Currituck Sand Company access north of Moyock | Install traffic signal. |  | Currituck | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 450000
HS-2401N | Highway | Safety | NC 168 | SR 1229 (Baxter Lane) intersection and Currituck Sand Company access north of Moyock | Install traffic signal. |  | Currituck | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 50000
HS-2401O | Highway | Safety | NC 34 | US 158 in Camden County to NC 168 in Currituck County | Install rumble stripes and pavement markings. | 9 | Currituck, Camden | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 257000
HS-2401O | Highway | Safety | NC 34 | US 158 in Camden County to NC 168 in Currituck County | Install rumble stripes and pavement markings. | 9 | Currituck, Camden | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 29000
HS-2401P | Highway | Safety | US 158 / US 258 | SR 1157 (Charlie Powell Road), SR 1230 (Clover Circle), and SR 1160 (Benthall Bridge Road) intersections near Murfreesboro | Upgrade roadway to reduced conflict intersections. | 2 | Hertford | 1 | Peanut Belt RPO | HF FUNDS REPRESENT HIGH IMPACT-LOW COST DIVISION FUNDS ($1,421,000) AND RESURFACING FUNDS ($2,000,000). | Region A |  | HSIP | CONSTRUCTION | 1679000 | FY 2026: 1679000
HS-2401P | Highway | Safety | US 158 / US 258 | SR 1157 (Charlie Powell Road), SR 1230 (Clover Circle), and SR 1160 (Benthall Bridge Road) intersections near Murfreesboro | Upgrade roadway to reduced conflict intersections. | 2 | Hertford | 1 | Peanut Belt RPO | HF FUNDS REPRESENT HIGH IMPACT-LOW COST DIVISION FUNDS ($1,421,000) AND RESURFACING FUNDS ($2,000,000). | Region A |  | HF | CONSTRUCTION | 3421000
HS-2401Q | Highway | Safety | US 64; US 158; NC 32 | Various locations | Install rumble stripes and snow plowable pavement markers. |  | Northampton, Chowan, Gates, Tyrrell | 1 | Albemarle RPO, Peanut Belt RPO |  | Region A |  | HSIP | CONSTRUCTION | 1755000 | FY 2026: 1755000
HS-2401Q | Highway | Safety | US 64; US 158; NC 32 | Various locations | Install rumble stripes and snow plowable pavement markers. |  | Northampton, Chowan, Gates, Tyrrell | 1 | Albemarle RPO, Peanut Belt RPO |  | Region A |  | T(M) | CONSTRUCTION | 195000 | FY 2026: 195000
HS-2401R | Highway | Safety | US 17 | West of SR 1220 (Wiggins Road) to east of SR 1227 (Swing Gate Road) / SR 1301 (Old Neck Road). | Close, modify, or install a crossover at three locations. | 0.8 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 25000 | FY 2026: 25000
HS-2401R | Highway | Safety | US 17 | West of SR 1220 (Wiggins Road) to east of SR 1227 (Swing Gate Road) / SR 1301 (Old Neck Road). | Close, modify, or install a crossover at three locations. | 0.8 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 40000 | FY 2026: 40000
HS-2401R | Highway | Safety | US 17 | West of SR 1220 (Wiggins Road) to east of SR 1227 (Swing Gate Road) / SR 1301 (Old Neck Road). | Close, modify, or install a crossover at three locations. | 0.8 | Perquimans | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 896000 | FY 2027: 896000
HS-2402 | Highway | Safety | Various | Routes in Division 2. | Construct safety improvements. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2402A | Highway | Safety | US 258 Business | Cooperative Way / Sharon Lane intersection in Farmville | Install all way stop. |  | Pitt | 2 | Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 112000
HS-2402A | Highway | Safety | US 258 Business | Cooperative Way / Sharon Lane intersection in Farmville | Install all way stop. |  | Pitt | 2 | Mid-East RPO |  | Region B |  | T(M) | CONSTRUCTION | 12000
HS-2402AA | Highway | Safety | NC 11 | South of SR 1143 (Liddell Road) to north of SR 1144 (Tulls Mill Road / South Lenoir Drive). | Install two reduced conflict intersections. | 0.7 | Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 1400000 | FY 2026: 1400000
HS-2402AC | Highway | Safety | US 264 | SR 1565 (Grimesland Bridge Road) and the eastern intersection of SR 1564 (Old Washington Road) | Construct Reduced Conflict Intersection. | 0.5 | Pitt | 2 | Mid-East RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 175000 | FY 2027: 175000
HS-2402AC | Highway | Safety | US 264 | SR 1565 (Grimesland Bridge Road) and the eastern intersection of SR 1564 (Old Washington Road) | Construct Reduced Conflict Intersection. | 0.5 | Pitt | 2 | Mid-East RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 200000 | FY 2027: 200000
HS-2402AC | Highway | Safety | US 264 | SR 1565 (Grimesland Bridge Road) and the eastern intersection of SR 1564 (Old Washington Road) | Construct Reduced Conflict Intersection. | 0.5 | Pitt | 2 | Mid-East RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 950000 | FY 2028: 950000
HS-2402B | Highway | Safety | US 17 | North of Onslow County line to South of NC 58 in Jones County; North of SR 1433 (Antioch Road) to North of SR 1134 (Old New Bern Road) in Beaufort County | Install rumble stripes and pavement markings. | 26.5 | Craven, Jones, Beaufort | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 590000
HS-2402B | Highway | Safety | US 17 | North of Onslow County line to South of NC 58 in Jones County; North of SR 1433 (Antioch Road) to North of SR 1134 (Old New Bern Road) in Beaufort County | Install rumble stripes and pavement markings. | 26.5 | Craven, Jones, Beaufort | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 66000
HS-2402C | Highway | Safety | NC 33 | SR 1240 (Mayo Road) to West of SR 1002 (Bay City Road) in Beaufort County; West of SR 1965 (Main Street Extension) to East of SR 1136 (Gray Road) in Chocowinity; West of SR 1143 (Taylor Road) to East of SR 1568 (Calvert Street in Pitt County | Install rumble stripes. | 56 | Beaufort, Pitt, Edgecombe, Pamlico | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A, B |  | HSIP | CONSTRUCTION | 1260000
HS-2402C | Highway | Safety | NC 33 | SR 1240 (Mayo Road) to West of SR 1002 (Bay City Road) in Beaufort County; West of SR 1965 (Main Street Extension) to East of SR 1136 (Gray Road) in Chocowinity; West of SR 1143 (Taylor Road) to East of SR 1568 (Calvert Street in Pitt County | Install rumble stripes. | 56 | Beaufort, Pitt, Edgecombe, Pamlico | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A, B |  | T(M) | CONSTRUCTION | 140000
HS-2402D | Highway | Safety | SR 1598 (10th Street) | Anderson Street intersection in Greenville | Install a pedestrian hybrid beacon. |  | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 158000
HS-2402D | Highway | Safety | SR 1598 (10th Street) | Anderson Street intersection in Greenville | Install a pedestrian hybrid beacon. |  | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | T(M) | CONSTRUCTION | 18000
HS-2402E | Highway | Safety | NC 58 | Loon Drive / Emerald Plantation Road; Mangrove Drive; Bogue Inlet Drive intersections in Emerald Isle. | Implement a leading pedestrian interval at the signalized intersections. |  | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 8000
HS-2402E | Highway | Safety | NC 58 | Loon Drive / Emerald Plantation Road; Mangrove Drive; Bogue Inlet Drive intersections in Emerald Isle. | Implement a leading pedestrian interval at the signalized intersections. |  | Carteret | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 1000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (Ivy Road) and SR 1753 (Stokestown St. John Road) intersections south of Greenville | Install traffic signals at both intersections and construct left turn lanes on SR 2241 (Ivy Road). |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | UTILITIES | 450000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (Ivy Road) and SR 1753 (Stokestown St. John Road) intersections south of Greenville | Install traffic signals at both intersections and construct left turn lanes on SR 2241 (Ivy Road). |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | T(M) | UTILITIES | 50000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (Ivy Road) and SR 1753 (Stokestown St. John Road) intersections south of Greenville | Install traffic signals at both intersections and construct left turn lanes on SR 2241 (Ivy Road). |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 333000 | FY 2026: 333000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (Ivy Road) and SR 1753 (Stokestown St. John Road) intersections south of Greenville | Install traffic signals at both intersections and construct left turn lanes on SR 2241 (Ivy Road). |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | T(M) | CONSTRUCTION | 37000 | FY 2026: 37000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 135000 | FY 2026: 135000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | T(M) | RIGHT-OF-WAY | 15000 | FY 2026: 15000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | UTILITIES | 270000 | FY 2026: 270000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | T(M) | UTILITIES | 30000 | FY 2026: 30000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 855000 | FY 2027: 855000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (Speight Seed Farm Road) / SR 1207 (Nash Joyner Road) intersection in Greenville | Construct reduced conflict intersection with right turn lanes. |  | Pitt | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | T(M) | CONSTRUCTION | 95000 | FY 2027: 95000
HS-2402H | Highway | Safety | NC 102 (Third Street); SR 1149 (Lee Street) | SR 1149 (Lee Street) intersection in Ayden; Second Street intersection in Ayden | Upgrade traffic signals and install / upgrade pedestrian signals and other accommodations. |  | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 65000
HS-2402H | Highway | Safety | NC 102 (Third Street); SR 1149 (Lee Street) | SR 1149 (Lee Street) intersection in Ayden; Second Street intersection in Ayden | Upgrade traffic signals and install / upgrade pedestrian signals and other accommodations. |  | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 7000
HS-2402I | Highway | Safety | SR 1124 (Nine Mile Road); SR 1756 (Lake Road) | NC 24 to Parker Court in Newport; SR 1124 (Nine Mile Road / Nine Foot Road) in Carteret County to SR 1745 (Miller Boulevard) in Craven County | Install rumble stripes and pavement markings. | 13.5 | Carteret, Craven | 2 | Down East RPO |  | Division 2 |  | HSIP | CONSTRUCTION | 292000
HS-2402I | Highway | Safety | SR 1124 (Nine Mile Road); SR 1756 (Lake Road) | NC 24 to Parker Court in Newport; SR 1124 (Nine Mile Road / Nine Foot Road) in Carteret County to SR 1745 (Miller Boulevard) in Craven County | Install rumble stripes and pavement markings. | 13.5 | Carteret, Craven | 2 | Down East RPO |  | Division 2 |  | T(M) | CONSTRUCTION | 32000
HS-2402J | Highway | Safety | SR 1395 (West Vernon Avenue) | Greenbriar Road Intersection in Kinston | Install / upgrade pedestrian signals and other pedestrian accommodations. |  | Lenoir | 2 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | HSIP | RIGHT-OF-WAY | 7000
HS-2402J | Highway | Safety | SR 1395 (West Vernon Avenue) | Greenbriar Road Intersection in Kinston | Install / upgrade pedestrian signals and other pedestrian accommodations. |  | Lenoir | 2 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | T(M) | RIGHT-OF-WAY | 1000
HS-2402J | Highway | Safety | SR 1395 (West Vernon Avenue) | Greenbriar Road Intersection in Kinston | Install / upgrade pedestrian signals and other pedestrian accommodations. |  | Lenoir | 2 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | HSIP | CONSTRUCTION | 102000 | FY 2026: 102000
HS-2402J | Highway | Safety | SR 1395 (West Vernon Avenue) | Greenbriar Road Intersection in Kinston | Install / upgrade pedestrian signals and other pedestrian accommodations. |  | Lenoir | 2 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | T(M) | CONSTRUCTION | 11000 | FY 2026: 11000
HS-2402K | Highway | Safety | US 17 Business (Carolina Avenue) | Washington Street intersection in Washington | Install channelization, pedestrian signals, and other accommodations. |  | Beaufort | 2 | Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 87000
HS-2402K | Highway | Safety | US 17 Business (Carolina Avenue) | Washington Street intersection in Washington | Install channelization, pedestrian signals, and other accommodations. |  | Beaufort | 2 | Mid-East RPO |  | Region B |  | T(M) | CONSTRUCTION | 10000
HS-2402L | Highway | Safety | NC 101 | SR 1212 (Airport Road) near Beaufort to Outer Banks Drive near Havelock | Install rumble stripes and pavement markings. | 19.3 | Carteret, Craven | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 315000
HS-2402L | Highway | Safety | NC 101 | SR 1212 (Airport Road) near Beaufort to Outer Banks Drive near Havelock | Install rumble stripes and pavement markings. | 19.3 | Carteret, Craven | 2 | Down East RPO |  | Region B |  | T(M) | CONSTRUCTION | 35000
HS-2402M | Highway | Safety | Various | Primary routes throughout Division 2 | Replace guardrail end units. |  | Carteret, Craven, Beaufort, Lenoir | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO, Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 454000
HS-2402M | Highway | Safety | Various | Primary routes throughout Division 2 | Replace guardrail end units. |  | Carteret, Craven, Beaufort, Lenoir | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO, Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | T(M) | CONSTRUCTION | 50000
HS-2402N | Highway | Safety | SR 1598 (10th Street) | 5th Street intersection in Greenville. | Install / upgrade traffic signals, pavement markings, pedestrian signals, and other accommodations. |  | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | RIGHT-OF-WAY | 3000
HS-2402N | Highway | Safety | SR 1598 (10th Street) | 5th Street intersection in Greenville. | Install / upgrade traffic signals, pavement markings, pedestrian signals, and other accommodations. |  | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | T(M) | RIGHT-OF-WAY | 0
HS-2402N | Highway | Safety | SR 1598 (10th Street) | 5th Street intersection in Greenville. | Install / upgrade traffic signals, pavement markings, pedestrian signals, and other accommodations. |  | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 228000
HS-2402N | Highway | Safety | SR 1598 (10th Street) | 5th Street intersection in Greenville. | Install / upgrade traffic signals, pavement markings, pedestrian signals, and other accommodations. |  | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | T(M) | CONSTRUCTION | 25000
HS-2402O | Highway | Safety | NC 43 | US 264 interchange ramps | Construct roundabouts. |  | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 529000 | FY 2026: 529000
HS-2402O | Highway | Safety | NC 43 | US 264 interchange ramps | Construct roundabouts. |  | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | T(M) | CONSTRUCTION | 59000 | FY 2026: 59000
HS-2402O | Highway | Safety | NC 43 | US 264 interchange ramps | Construct roundabouts. |  | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HF | CONSTRUCTION | 813000 | FY 2026: 813000
HS-2402P | Highway | Safety | NC 101 | SR 1392 (Adams Creek Road) intersection | Improve intersection with channelization and supplemental stop sign installation. |  | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 49000
HS-2402Q | Highway | Safety | NC 11 / NC 43 / NC 903 (Memorial Drive) | Arlington Boulevard Intersection in Greenville | Revise traffic signal and install pedestrian signals, crosswalks, and sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  | HSIP | RIGHT-OF-WAY | 6000
HS-2402Q | Highway | Safety | NC 11 / NC 43 / NC 903 (Memorial Drive) | Arlington Boulevard Intersection in Greenville | Revise traffic signal and install pedestrian signals, crosswalks, and sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  | HSIP | CONSTRUCTION | 128000 | FY 2026: 128000
HS-2402Q | Highway | Safety | NC 11 / NC 43 / NC 903 (Memorial Drive) | Arlington Boulevard Intersection in Greenville | Revise traffic signal and install pedestrian signals, crosswalks, and sidewalk. |  | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  | T(M) | CONSTRUCTION | 14000 | FY 2026: 14000
HS-2402R | Highway | Safety | US 258 (Wesley Church Road) | US 264 to I-587 eastbound ramps. | Install rumble stripes. |  | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 80000
HS-2402S | Highway | Safety | NC 58 | North of Camp Peletier Road in Carteret County Maysville in Jones County; East of SR 1338 (Goshen Lane) to Trenton in Jones County; East of SR 1124 (Greentown Road) in Jones County to SR 1900 (Collier Loftin Road) in Lenoir County | Install rumble stripes. |  | Jones, Lenoir, Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 1115000
HS-2402T | Highway | Safety | US 70 | SR 1429 (Olga Road) to NC 12; NC 12 from US 70 to SR 1388 (Lola Road) | Install rumble stripes. |  | Carteret | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 675000
HS-2402U | Highway | Safety | NC 903 | LaGrange Town limits in Lenoir County to SR 1104 (Hull Road) in Greene County; US 13/258 in Greene County to NC 11 in Pitt County; US 13 / NC 11 to Martin County line in Pitt County | Install rumble stripes. |  | Pitt, Greene, Lenoir | 2 | Eastern Carolina RPO, Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 950000
HS-2402V | Highway | Safety | NC 58 | North of SR 1745 (Cunningham Road) in Lenoir County to northwest of Carolina Drive in Greene County; Northwestern intersection of US 13 to Wilson County line in Greene County | Install rumble stripes. |  | Greene, Lenoir | 2 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 660000
HS-2402W | Highway | Safety | US 264 | NC 32 to the western town limits of Pantego | Install rumble stripes. |  | Beaufort | 2 | Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 575000
HS-2402X | Highway | Safety | NC 102 | NC 11 Bypass southbound ramps in Ayden. | Construct concrete islands to prevent left turns from NC 11 Bypass. |  | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 41000 | FY 2026: 41000
HS-2402Y | Highway | Safety | US 70 (Arendell Street) | SR 1602 (35th Street) intersection in Morehead City. | Install pedestrian signals with other pedestrian accomodations. |  | Carteret | 2 | Down East RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 210000 | FY 2027: 210000
HS-2402Z | Highway | Safety | US 264 | NC 30 intersection east of Greenville. | Close full movement crossover and install reduced conflict intersection. | 1 | Pitt | 2 | Mid-East RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HS-2402Z | Highway | Safety | US 264 | NC 30 intersection east of Greenville. | Close full movement crossover and install reduced conflict intersection. | 1 | Pitt | 2 | Mid-East RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 265000 | FY 2027: 265000
HS-2402Z | Highway | Safety | US 264 | NC 30 intersection east of Greenville. | Close full movement crossover and install reduced conflict intersection. | 1 | Pitt | 2 | Mid-East RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1020000 | FY 2027: 1020000
HS-2403 | Highway | Safety | Various | Routes in Division 3. | Construct safety improvements. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2403A | Highway | Safety | SR 1216 (16th Street); SR 1217 (17th Street) | Queen Street and Castle Street intersections; Queen Street intersection in Wilmington | Install crosswalks and other pedestrian improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 730000
HS-2403A | Highway | Safety | SR 1216 (16th Street); SR 1217 (17th Street) | Queen Street and Castle Street intersections; Queen Street intersection in Wilmington | Install crosswalks and other pedestrian improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T(M) | CONSTRUCTION | 81000
HS-2403AA | Highway | Safety | NC 53 (Western Boulevard) | SR 1308 (Gum Branch Road) intersection in Jacksonville. | Upgrade traffic signal. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 13000 | FY 2026: 13000
HS-2403AB | Highway | Safety | US 421 | SR 1311 (Five Bridge Road) / SR 1356 (North Boulevard) intersection in Clinton. | Upgrade traffic signal. |  | Sampson | 3 | Mid-Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 120000 | FY 2026: 120000
HS-2403AC | Highway | Safety | US 117 | SR 1209 (Independence Boulveard) intersection in Wilmington. | Upgrade traffic singal and install signalized pedestrian crodding and pavement markings. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 136000 | FY 2026: 136000
HS-2403AD | Highway | Safety | NC 111 | West of US 258 to Onslow County line. | Widen road and install center and edgeline sinusoidal rumble strips. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 445000 | FY 2026: 445000
HS-2403AE | Highway | Safety | SR 1532 (Flokstone Road) | US 17 to SR 1531 (Tar Landing Road). | Install center and edgeline sinusoidal rumble strips. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 93000
HS-2403AF | Highway | Safety | US 117 | South of SR 2160 (Long Ridge Road) to south of NC 133 intersection north of Wilmington. | Widen road and install center and edgeline sinusoidal rumble strips. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 406000 | FY 2026: 406000
HS-2403AG | Highway | Safety | US 17 Business (Market Street) | SR 1216 (16th Street) intersection in Wilmington. | Upgrade traffic signal and construct curb bump-outs. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 6000 | FY 2026: 6000
HS-2403AG | Highway | Safety | US 17 Business (Market Street) | SR 1216 (16th Street) intersection in Wilmington. | Upgrade traffic signal and construct curb bump-outs. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403AG | Highway | Safety | US 17 Business (Market Street) | SR 1216 (16th Street) intersection in Wilmington. | Upgrade traffic signal and construct curb bump-outs. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 261000 | FY 2026: 261000
HS-2403AH | Highway | Safety | US 17 | NC 210 intersection east of Holly Ridge. | Install signal heads. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 21000 | FY 2026: 21000
HS-2403AI | Highway | Safety | SR 1336 (Henderson Drive) | SR 1308 (Gum Branch Road) intersection and intersection south of SR 1308 (Gum Branch Road) in Jacksonville. | Upgrade traffic signals and install accessible pedestrian signals. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 60000 | FY 2026: 60000
HS-2403AJ | Highway | Safety | NC 172; NC 24 | US 17 to SR 1678 (Old Ferry Road); NC 53 to SR 1406 (Piney Green Road). | Install rumble strips and pavement markings. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 438000 | FY 2026: 438000
HS-2403AK | Highway | Safety | Various | Routes in Onslow County | Install rumble strips. | 17.25 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 1136000 | FY 2026: 1136000
HS-2403AL | Highway | Safety | SR 1318 (Blue Clay Road) | SR 1302 (N. 23rd Street) to SR 1336 (Sidbury Road). | Install rumble strips. | 4.7 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 271000 | FY 2026: 271000
HS-2403AM | Highway | Safety | SR 1520 (Grissom Road) | SR 1492 (Myrtle Grove Road) to SR 1521 (Piner Road). | Install rumble strips. | 0.4 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 27000 | FY 2026: 27000
HS-2403AN | Highway | Safety | US 421 | Independence Boulevard intersection in Wilmington. | Upgrade traffic signal and add pedestrian accomodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 38000 | FY 2026: 38000
HS-2403AO | Highway | Safety | SR 1302 (23rd Street) | NC 133 (Castle Hayne Road) to US 74 east ramp. | Upgrade traffic signal and add pedestrian accomodations. | 0.6 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 280000 | FY 2026: 280000
HS-2403AP | Highway | Safety | US 117 | SR 1412 (New Road) intersection in Saint Helena. | Install traffic signal. |  | Pender | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 324000 | FY 2027: 324000
HS-2403AP | Highway | Safety | US 117 | SR 1412 (New Road) intersection in Saint Helena. | Install traffic signal. |  | Pender | 3 | Cape Fear RPO |  | Region B |  | T(M) | CONSTRUCTION | 36000 | FY 2027: 36000
HS-2403AQ | Highway | Safety | NC 41 / SR 1163 (Teachey Road) | NC 41 (Southerland Street) / SR 1173 (East Southerland Street) intersection in Wallace. | Upgrade traffic signal. |  | Duplin | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 17000 | FY 2026: 17000
HS-2403AR | Highway | Safety | US 17 (Market Street) | SR 1402 (Porters Neck Road) intersection in Wilmington. | Upgrade traffic signal. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 9000 | FY 2026: 9000
HS-2403AR | Highway | Safety | US 17 (Market Street) | SR 1402 (Porters Neck Road) intersection in Wilmington. | Upgrade traffic signal. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 2000 | FY 2026: 2000
HS-2403AS | Highway | Safety | US 74 | I-140 ramp intersections in Leland. | Upgrade traffic signals and install advanced warning flasher. |  | Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 210000 | FY 2026: 210000
HS-2403AT | Highway | Safety | US 421 (Carolina Beach Road) | SR 1276 (Cathay Road) intersection in Wilmington. | Upgrade traffic signal. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 18000 | FY 2026: 18000
HS-2403AU | Highway | Safety | US 74 / US 76 (Eastwood Road) | Lumina Commons Driveway intersection in Wilmington. | Improve left turn lane offsets and pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2027: 5000
HS-2403AU | Highway | Safety | US 74 / US 76 (Eastwood Road) | Lumina Commons Driveway intersection in Wilmington. | Improve left turn lane offsets and pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 5000 | FY 2027: 5000
HS-2403AU | Highway | Safety | US 74 / US 76 (Eastwood Road) | Lumina Commons Driveway intersection in Wilmington. | Improve left turn lane offsets and pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1150000 | FY 2027: 1150000
HS-2403AV | Highway | Safety | SR 1308 (Gumbranch Road) | Nottingham Road to Plaza drive in Jacksonville | Improve pedestrian accommodations. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 1047000 | FY 2026: 1047000
HS-2403AW | Highway | Safety | NC 133 | SR 1518 (Daws Creek Road) to SR 1551 (Blackwell Road) | Install rumble strips. | 18.7 | Brunswick | 3 | Wilmington Urban Area MPO, Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 276000 | FY 2026: 276000
HS-2403AX | Highway | Safety | NC 41 | North of NC 50 to Beulaville city limits | Widen roadway and install rumble strips. | 23 | Duplin | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 718000 | FY 2026: 718000
HS-2403AY | Highway | Safety | US 421 | SR 1114 (Blueberry Road) north of NC 210 | Install rumble strips. | 8.9 | Pender | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 210000 | FY 2026: 210000
HS-2403AZ | Highway | Safety | US 421 | Pender County line to north of Pearson Road | Install rumble strips. | 22.1 | Sampson | 3 | Mid-Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 702000 | FY 2027: 702000
HS-2403B | Highway | Safety | NC 53; US 117 (Future I-795); US 701 | Various locations along routes | Install center and edgeline sinusoidal rumble stripes. | 63.83 | Onslow, Pender, Sampson, Duplin, New Hanover | 3 | Cape Fear RPO, Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 3384000 | FY 2026: 3384000
HS-2403B | Highway | Safety | NC 53; US 117 (Future I-795); US 701 | Various locations along routes | Install center and edgeline sinusoidal rumble stripes. | 63.83 | Onslow, Pender, Sampson, Duplin, New Hanover | 3 | Cape Fear RPO, Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO |  | Region B |  | T(M) | CONSTRUCTION | 376000 | FY 2026: 376000
HS-2403C | Highway | Safety | NC 111 | Onslow County line to NC 41; NC 41 / NC 241 in Beulaville to NC 11; NC 11 / NC 903 to Wayne County line | Install centerline rumble stripes & shoulder rumble strips. | 27.8 | Duplin | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 1360000 | FY 2026: 1360000
HS-2403D | Highway | Safety | SR 1336 (Sidbury Road) | SR 1318 (Blue Clay Road) to US 17 North of Wilmington | Install centerline and shoulder sinusoidal rumble stripes with bicycle pattern. | 7.2 | New Hanover, Pender | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | HSIP | CONSTRUCTION | 421000
HS-2403E | Highway | Safety | US 17; US 258; US 421; NC 24; NC 87 | Various locations in Division 3 | Upgrade guardrail end units. |  | Onslow, Duplin, Brunswick, New Hanover, Pender, Sampson | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Cape Fear RPO, Mid-Carolina RPO, Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 352000
HS-2403F | Highway | Safety | NC 53 (Western Boulevard) | Carolina Forest Boulevard and North Plain Road intersections in Jacksonville | Install near side signal heads. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 35000 | FY 2026: 35000
HS-2403G | Highway | Safety | US 17/ US 76 (Oleander Drive) | Country Club Road intersection in Wilmington | Install near side signal head and upgrade traffic signal. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 51000 | FY 2026: 51000
HS-2403H | Highway | Safety | US 17 Business (North Marine Boulevard) | McDaniel Drive and Workshop Lane intersections in Jacksonville | Install near side signal heads. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2403I | Highway | Safety | NC 172 | SR 1500 (Starling Road) near Hubert | Install traffic signal. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 450000 | FY 2026: 450000
HS-2403J | Highway | Safety | SR 1403 (Country Club Road) | Academic Drive intersection in Jacksonville | Install traffic signal, pedestrian signals, and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2403J | Highway | Safety | SR 1403 (Country Club Road) | Academic Drive intersection in Jacksonville | Install traffic signal, pedestrian signals, and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403J | Highway | Safety | SR 1403 (Country Club Road) | Academic Drive intersection in Jacksonville | Install traffic signal, pedestrian signals, and pedestrian accommodations. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 505000 | FY 2026: 505000
HS-2403K | Highway | Safety | US 17 | SR 1561 (Sloop Point Road) northeast of Hampstead | Install traffic signal. | 0.5 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2403K | Highway | Safety | US 17 | SR 1561 (Sloop Point Road) northeast of Hampstead | Install traffic signal. | 0.5 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403K | Highway | Safety | US 17 | SR 1561 (Sloop Point Road) northeast of Hampstead | Install traffic signal. | 0.5 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 300000 | FY 2026: 300000
HS-2403L | Highway | Safety | US 117 | SR 1150 (Lodge/High School Road) intersection in Teachey | Install traffic signal. |  | Duplin | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 161000 | FY 2026: 161000
HS-2403M | Highway | Safety | NC 50 (Roland Avenue) | NC 210 / SR 1534 (Belt Road) intersection in Surf City | Upgrade traffic signal and pavement markings. |  | Pender | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 40000 | FY 2027: 40000
HS-2403N | Highway | Safety | US 117 / NC 132 | SR 2206 (West Northchase Parkway) / SR 2257 (Southeast Northchase Parkway) intersection north of Wilmington | Upgrade traffic signal. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 113000 | FY 2026: 113000
HS-2403O | Highway | Safety | US 17 Business (Market Street) | 10th Street intersection in Wilmington | Upgrade traffic signal and install pedestrian signals. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 82000 | FY 2026: 82000
HS-2403P | Highway | Safety | US 17 Business (Market Street) | 5th Avenue intersection in Wilmington | Upgrade traffic signal with pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 47000 | FY 2026: 47000
HS-2403Q | Highway | Safety | US 17 Business (Market Street) | Lullwater Drive intersection in Wilmington | Upgrade signing and traffic signal with pedestrian accommodations. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 51000 | FY 2026: 51000
HS-2403R | Highway | Safety | SR 1308 (Gum Branch Road) | SR 1903 (Ramsey Drive) / SR 1944 (Hunting Green Drive) and SR 1920 (Raintree Road) intersections in Jacksonville | Install traffic signals. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 55000 | FY 2026: 55000
HS-2403R | Highway | Safety | SR 1308 (Gum Branch Road) | SR 1903 (Ramsey Drive) / SR 1944 (Hunting Green Drive) and SR 1920 (Raintree Road) intersections in Jacksonville | Install traffic signals. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403R | Highway | Safety | SR 1308 (Gum Branch Road) | SR 1903 (Ramsey Drive) / SR 1944 (Hunting Green Drive) and SR 1920 (Raintree Road) intersections in Jacksonville | Install traffic signals. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 625000 | FY 2027: 625000
HS-2403S | Highway | Safety | SR 1501 (Garner Chapel Road) | NC 403 to SR 1306 / SR 1522 (Red Hill Road / Washboard Road) east of Mt. Olive | Install rumble stripes. | 9.41 | Duplin | 3 | Eastern Carolina RPO |  | Division 3 |  | HSIP | CONSTRUCTION | 368000 | FY 2027: 368000
HS-2403T | Highway | Safety | US 258 / NC 24 | SR 1320 (Wells Road) to SR 1238 (Koonce Fork Road) south of Richlands | Install rumble stripes. | 7.34 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 292000 | FY 2026: 292000
HS-2403U | Highway | Safety | SR 1216 (Piney Woods Road); SR 1002 (Island Creek Road); US 421 | US 421 to SR 1336 (Horse Branch Road); NC 210 to New Hanover County line; North of SR 1217 (Teddar Road) to New Hanover County line. | Install rumble stripes. | 13.41 | Pender | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 1038000
HS-2403V | Highway | Safety | SR 1114 (Blueberry Road) | SR 1113 (Montague Road) to NC 210 North of Wilmington. | Install rumble stripes. | 2.71 | Pender | 3 | Cape Fear RPO |  | Division 3 |  | HSIP | CONSTRUCTION | 162000 | FY 2027: 162000
HS-2403W | Highway | Safety | NC 133; NC 87 | SR 1100 (Country Club Drive) to north of Port Loop Road; South of NC 133 to north of SR 1729 (Van Galloway Trail). | Install rumble stripes and pavement markings. | 7.7 | Brunswick | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 765000 | FY 2027: 765000
HS-2403X | Highway | Safety | SR 1300 (Ash-Little River Road) | NC 130 to SR 1303 (Hickman Road). | Install rumble stripes and pavement markings. | 11.02 | Brunswick | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | Division 3 |  | HSIP | CONSTRUCTION | 630000 | FY 2027: 630000
HS-2403Y | Highway | Safety | NC 41; NC 55 | Bladen County line to west of SR 1155 (Ward Road); East of NC 242 to east of Harnett County line. | Install rumble stripes and pavement markings. | 15.75 | Sampson | 3 | Mid-Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 904000 | FY 2027: 904000
HS-2403Z | Highway | Safety | NC 24 | Cumberland County line to east of SR 1292 (Dixie Road). | Install rumble stripes. | 17.25 | Sampson | 3 | Mid-Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 439000 | FY 2027: 439000
HS-2404 | Highway | Safety | Various | Routes in Division 4. | Construct safety improvements. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2404A | Highway | Safety | NC 55 | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 68000 | FY 2027: 68000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | T(M) | RIGHT-OF-WAY | 8000 | FY 2027: 8000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | UTILITIES | 86000 | FY 2027: 86000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | T(M) | UTILITIES | 10000 | FY 2027: 10000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | CONSTRUCTION | 472000 | FY 2028: 472000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (Grantham School Road) intersection | Realign intersection. | 0.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | T(M) | CONSTRUCTION | 52000 | FY 2028: 52000
HS-2404B | Highway | Safety | NC 210 | Harnett County line to NC 50 and SR 1382 (North Pleasant-Coates Road) to SR 1010 (Cleveland Road). | Install rumble stripes and snowplowable pavement markers | 17 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 510000 | FY 2026: 510000
HS-2404B | Highway | Safety | NC 210 | Harnett County line to NC 50 and SR 1382 (North Pleasant-Coates Road) to SR 1010 (Cleveland Road). | Install rumble stripes and snowplowable pavement markers | 17 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 57000 | FY 2026: 57000
HS-2404C | Highway | Safety | NC 55 | West of Lenoir County line to Mount Olive city limits and SR 1135 (Country Club Road) to Sampson County line | Install rumble stripes and pavement markings. | 23.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | CONSTRUCTION | 725000 | FY 2026: 725000
HS-2404C | Highway | Safety | NC 55 | West of Lenoir County line to Mount Olive city limits and SR 1135 (Country Club Road) to Sampson County line | Install rumble stripes and pavement markings. | 23.5 | Wayne | 4 | Eastern Carolina RPO |  | Region A |  | T(M) | CONSTRUCTION | 81000 | FY 2026: 81000
HS-2404D | Highway | Safety | US 70 Business / US 117 Business (Ash Street) | SR 1925 (John Street) and US 117 Business (William Street) intersections in Goldsboro. | Install / revise pedestrian accommodations including traffic signals, pedestrian signals, and crosswalk improvements. |  | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 216000
HS-2404D | Highway | Safety | US 70 Business / US 117 Business (Ash Street) | SR 1925 (John Street) and US 117 Business (William Street) intersections in Goldsboro. | Install / revise pedestrian accommodations including traffic signals, pedestrian signals, and crosswalk improvements. |  | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T(M) | CONSTRUCTION | 24000
HS-2404E | Highway | Safety | Various | Secondary roads in Nash County. | Install long life pavement markings. |  | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 2170000
HS-2404F | Highway | Safety | SR 1192 (Hines Street) | Lodge Street intersection in Wilson. | Upgrade traffic signal to include pedestrian accommodations and install crosswalks. | 0 | Wilson | 4 | Upper Coastal Plain RPO |  | Division 4 |  | HSIP | CONSTRUCTION | 72000 | FY 2027: 72000
HS-2404F | Highway | Safety | SR 1192 (Hines Street) | Lodge Street intersection in Wilson. | Upgrade traffic signal to include pedestrian accommodations and install crosswalks. | 0 | Wilson | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T(M) | CONSTRUCTION | 8000 | FY 2027: 8000
HS-2404G | Highway | Safety | SR 1007 (Brogden Road) | US 301 to Wayne County line. | Construct paved shoulders, resurface, and install rumble stripes and pavement markings. | 14.6 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | HSIP | CONSTRUCTION | 1215000 | FY 2026: 1215000
HS-2404G | Highway | Safety | SR 1007 (Brogden Road) | US 301 to Wayne County line. | Construct paved shoulders, resurface, and install rumble stripes and pavement markings. | 14.6 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T(M) | CONSTRUCTION | 135000 | FY 2026: 135000
HS-2404H | Highway | Safety | NC 42 / NC 43 | SR 1162 (Sally Jenkins Street) to ECU Health Driveway in Pinetops. | Install pedestrian improvement. | 0.1 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2026: 45000
HS-2404H | Highway | Safety | NC 42 / NC 43 | SR 1162 (Sally Jenkins Street) to ECU Health Driveway in Pinetops. | Install pedestrian improvement. | 0.1 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2404H | Highway | Safety | NC 42 / NC 43 | SR 1162 (Sally Jenkins Street) to ECU Health Driveway in Pinetops. | Install pedestrian improvement. | 0.1 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 261000 | FY 2027: 261000
HS-2404H | Highway | Safety | NC 42 / NC 43 | SR 1162 (Sally Jenkins Street) to ECU Health Driveway in Pinetops. | Install pedestrian improvement. | 0.1 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 29000 | FY 2027: 29000
HS-2404I | Highway | Safety | SR 1003 (New Hope Road) | US 13 (Berkley Boulevard) to SR 1719 (Beston Road) in Goldsboro. | Install pavement markings. | 5.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 80000 | FY 2026: 80000
HS-2404I | Highway | Safety | SR 1003 (New Hope Road) | US 13 (Berkley Boulevard) to SR 1719 (Beston Road) in Goldsboro. | Install pavement markings. | 5.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 9000 | FY 2026: 9000
HS-2404J | Highway | Safety | US 301 / NC 96 (Brightleaf Boulevard) | SR 1921 (Hospital Road) intersection in Smithfield. | Update traffic signal and install pedestrian improvements. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 41000 | FY 2026: 41000
HS-2404J | Highway | Safety | US 301 / NC 96 (Brightleaf Boulevard) | SR 1921 (Hospital Road) intersection in Smithfield. | Update traffic signal and install pedestrian improvements. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 4000 | FY 2026: 4000
HS-2404K | Highway | Safety | US 701 | SR 1143 (Stricklands Crossroads Road) intersection north of Newton Grove. | Install left turn lanes. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | UTILITIES | 93000 | FY 2026: 93000
HS-2404K | Highway | Safety | US 701 | SR 1143 (Stricklands Crossroads Road) intersection north of Newton Grove. | Install left turn lanes. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | UTILITIES | 10000 | FY 2026: 10000
HS-2404K | Highway | Safety | US 701 | SR 1143 (Stricklands Crossroads Road) intersection north of Newton Grove. | Install left turn lanes. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 401000 | FY 2026: 401000
HS-2404K | Highway | Safety | US 701 | SR 1143 (Stricklands Crossroads Road) intersection north of Newton Grove. | Install left turn lanes. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 45000 | FY 2026: 45000
HS-2404L | Highway | Safety | NC 111 | SR 1109 (Fountain Road) | Construct mini-roundabout with lighting. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | UTILITIES | 81000 | FY 2026: 81000
HS-2404L | Highway | Safety | NC 111 | SR 1109 (Fountain Road) | Construct mini-roundabout with lighting. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | UTILITIES | 9000 | FY 2026: 9000
HS-2404L | Highway | Safety | NC 111 | SR 1109 (Fountain Road) | Construct mini-roundabout with lighting. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 572000 | FY 2026: 572000
HS-2404L | Highway | Safety | NC 111 | SR 1109 (Fountain Road) | Construct mini-roundabout with lighting. | 0.5 | Edgecombe | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2404M | Highway | Safety | US 64 Business E (Tarboro Street) | NC 97 (Atlantic Avenue/Arlington Street) | Upgrade traffic signal, ramps, and crosswalks and install pedestrian signal heads. | 0.5 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 137000 | FY 2026: 137000
HS-2404M | Highway | Safety | US 64 Business E (Tarboro Street) | NC 97 (Atlantic Avenue/Arlington Street) | Upgrade traffic signal, ramps, and crosswalks and install pedestrian signal heads. | 0.5 | Edgecombe | 4 | Rocky Mount Urban Area MPO |  | Region A |  | T(M) | CONSTRUCTION | 15000 | FY 2026: 15000
HS-2404N | Highway | Safety | NC 43 | Northern Pinetops municipal limit to SR 1232 (Meadowbrook Road) | Install 6-inch pavement markings and pavement markers. | 13.7 | Edgecombe | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 155000 | FY 2026: 155000
HS-2404N | Highway | Safety | NC 43 | Northern Pinetops municipal limit to SR 1232 (Meadowbrook Road) | Install 6-inch pavement markings and pavement markers. | 13.7 | Edgecombe | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 17000 | FY 2026: 17000
HS-2404O | Highway | Safety | US 301 | Northern Rocky Mount Municipal limit to SR 1516 (Johnston Road) | Install 6-inch pavement markings and pavement markers. | 3.1 | Nash | 4 | Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 43000 | FY 2026: 43000
HS-2404O | Highway | Safety | US 301 | Northern Rocky Mount Municipal limit to SR 1516 (Johnston Road) | Install 6-inch pavement markings and pavement markers. | 3.1 | Nash | 4 | Rocky Mount Urban Area MPO |  | Region A |  | T(M) | CONSTRUCTION | 5000 | FY 2026: 5000
HS-2404P | Highway | Safety | SR 1555 (Barber Mill Road) | SR 1010 (Cleveland Road) to SR 3908 (Veterans Parkway) | Install 6-inch pavement markings. | 5.7 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2404P | Highway | Safety | SR 1555 (Barber Mill Road) | SR 1010 (Cleveland Road) to SR 3908 (Veterans Parkway) | Install 6-inch pavement markings. | 5.7 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 7000 | FY 2026: 7000
HS-2404Q | Highway | Safety | SR 1010 (Cleveland Road) | NC 210 to the Wake County line. | Install 6-inch pavement markings and markers. | 13.7 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 77000 | FY 2026: 77000
HS-2404Q | Highway | Safety | SR 1010 (Cleveland Road) | NC 210 to the Wake County line. | Install 6-inch pavement markings and markers. | 13.7 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 9000 | FY 2026: 9000
HS-2404R | Highway | Safety | Various | Various secondary roads. | Install long life pavement markings. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 1746000 | FY 2027: 1746000
HS-2404R | Highway | Safety | Various | Various secondary roads. | Install long life pavement markings. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 194000 | FY 2027: 194000
HS-2404S | Highway | Safety | Various | Various secondary roads. | Install long life pavement markings. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 1746000 | FY 2027: 1746000
HS-2404S | Highway | Safety | Various | Various secondary roads. | Install long life pavement markings. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 194000 | FY 2027: 194000
HS-2404T | Highway | Safety | SR 1544 (Halifax Road) | NC 97 to SR 1770 (Sunset Avenue) | Install 6-inch pavement markings and snowplowable pavement markers. | 5.22 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 70000 | FY 2026: 70000
HS-2404T | Highway | Safety | SR 1544 (Halifax Road) | NC 97 to SR 1770 (Sunset Avenue) | Install 6-inch pavement markings and snowplowable pavement markers. | 5.22 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T(M) | CONSTRUCTION | 8000 | FY 2026: 8000
HS-2404U | Highway | Safety | NC 242 | Benson town limits to I-40. | Install rumble stripes with 6-inch pavement markings and snowplowable pavement markers. | 2.22 | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 44000 | FY 2026: 44000
HS-2404U | Highway | Safety | NC 242 | Benson town limits to I-40. | Install rumble stripes with 6-inch pavement markings and snowplowable pavement markers. | 2.22 | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 5000 | FY 2026: 5000
HS-2404V | Highway | Safety | US 70 Business (Market Street) | Front Street to US 301 (Brightleaf Boulevard). | Install raised concrete median, crosswalks, and pedestrian signal heads, revise street parking, and widen lanes. | 0.6 | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 900000 | FY 2026: 900000
HS-2404V | Highway | Safety | US 70 Business (Market Street) | Front Street to US 301 (Brightleaf Boulevard). | Install raised concrete median, crosswalks, and pedestrian signal heads, revise street parking, and widen lanes. | 0.6 | Johnston | 4 | Upper Coastal Plain RPO |  | Region A |  | T(M) | CONSTRUCTION | 100000 | FY 2026: 100000
HS-2405 | Highway | Safety | Various | Routes in Division 5. | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2405A | Highway | Safety | US 158 (Oxford Loop Road) | US 158 Business (Williamsboro Street) / SR 1646 (Southeast Industry Drive) intersection. | Upgrade traffic signal. | 0.5 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 39000
HS-2405A | Highway | Safety | US 158 (Oxford Loop Road) | US 158 Business (Williamsboro Street) / SR 1646 (Southeast Industry Drive) intersection. | Upgrade traffic signal. | 0.5 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | T(M) | CONSTRUCTION | 4000
HS-2405AA | Highway | Safety | US 70 / US 401 / NC 50 (Wilmington Street) | SR 1370/SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | HSIP | UTILITIES | 2000
HS-2405AA | Highway | Safety | US 70 / US 401 / NC 50 (Wilmington Street) | SR 1370/SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | UTILITIES | 0
HS-2405AA | Highway | Safety | US 70 / US 401 / NC 50 (Wilmington Street) | SR 1370/SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 243000 | FY 2026: 243000
HS-2405AA | Highway | Safety | US 70 / US 401 / NC 50 (Wilmington Street) | SR 1370/SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 27000 | FY 2026: 27000
HS-2405AB | Highway | Safety | SR 2000 (Falls Of Neuse Road) | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000
HS-2405AB | Highway | Safety | SR 2000 (Falls Of Neuse Road) | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 0
HS-2405AB | Highway | Safety | SR 2000 (Falls Of Neuse Road) | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000
HS-2405AB | Highway | Safety | SR 2000 (Falls Of Neuse Road) | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 0
HS-2405AB | Highway | Safety | SR 2000 (Falls Of Neuse Road) | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 103000 | FY 2026: 103000
HS-2405AB | Highway | Safety | SR 2000 (Falls Of Neuse Road) | North Bend Drive intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 11000 | FY 2026: 11000
HS-2405AC | Highway | Safety | SR 2000 (Falls Of Neuse Road) | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000
HS-2405AC | Highway | Safety | SR 2000 (Falls Of Neuse Road) | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 0
HS-2405AC | Highway | Safety | SR 2000 (Falls Of Neuse Road) | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000
HS-2405AC | Highway | Safety | SR 2000 (Falls Of Neuse Road) | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 0
HS-2405AC | Highway | Safety | SR 2000 (Falls Of Neuse Road) | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 122000 | FY 2026: 122000
HS-2405AC | Highway | Safety | SR 2000 (Falls Of Neuse Road) | Newton Road intersection | Upgrade traffic signal and install/upgrade pedestian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 14000 | FY 2026: 14000
HS-2405AD | Highway | Safety | US 501 (Roxboro Road / Durham Road) | SR 1002 (Mason Road); SR 1631 (Snow Hill Road) in Durham County to 1,100 feet south of SR 1147 (Bessie Daniel Road) in Person County, excluding five lane sections. | Install rumble stripes. | 16 | Durham, Person | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 104000 | FY 2026: 104000
HS-2405AD | Highway | Safety | US 501 (Roxboro Road / Durham Road) | SR 1002 (Mason Road); SR 1631 (Snow Hill Road) in Durham County to 1,100 feet south of SR 1147 (Bessie Daniel Road) in Person County, excluding five lane sections. | Install rumble stripes. | 16 | Durham, Person | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | CONSTRUCTION | 12000 | FY 2026: 12000
HS-2405AE | Highway | Safety | US 15 | I-85 to Virginia state line | Install rumble stripes. | 37 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 994000 | FY 2026: 994000
HS-2405AE | Highway | Safety | US 15 | I-85 to Virginia state line | Install rumble stripes. | 37 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | CONSTRUCTION | 110000 | FY 2026: 110000
HS-2405AF | Highway | Safety | US 1 | NC 96 to Chappell Lane | Install rumble stripes. | 12.7 | Franklin, Vance | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 69000 | FY 2026: 69000
HS-2405AF | Highway | Safety | US 1 | NC 96 to Chappell Lane | Install rumble stripes. | 12.7 | Franklin, Vance | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 8000 | FY 2026: 8000
HS-2405AG | Highway | Safety | NC 39 | NC 97 in Wake County to Virginia state line | Install rumble stripes. | 22.5 | Vance, Franklin, Wake | 5 | Kerr-Tar RPO, Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 1534000 | FY 2026: 1534000
HS-2405AG | Highway | Safety | NC 39 | NC 97 in Wake County to Virginia state line | Install rumble stripes. | 22.5 | Vance, Franklin, Wake | 5 | Kerr-Tar RPO, Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 170000 | FY 2026: 170000
HS-2405AH | Highway | Safety | NC 54 (Miami Boulevard) | SR 1978 (Hopson Road) intersection | Construct Multi-use path |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | CONSTRUCTION | 150000 | FY 2026: 150000
HS-2405AI | Highway | Safety | SR 3008 (Edenton Street) | Harrington Street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HS-2405AI | Highway | Safety | SR 3008 (Edenton Street) | Harrington Street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 20000 | FY 2026: 20000
HS-2405AI | Highway | Safety | SR 3008 (Edenton Street) | Harrington Street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 300000 | FY 2027: 300000
HS-2405AJ | Highway | Safety | SR 1152 (Holly Springs Road) | SR 4089 (Winding Oak Way); YMCA Driveway | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 12000 | FY 2026: 12000
HS-2405AJ | Highway | Safety | SR 1152 (Holly Springs Road) | SR 4089 (Winding Oak Way); YMCA Driveway | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 6000 | FY 2026: 6000
HS-2405AJ | Highway | Safety | SR 1152 (Holly Springs Road) | SR 4089 (Winding Oak Way); YMCA Driveway | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 248000 | FY 2027: 248000
HS-2405AK | Highway | Safety | SR 1004 (Garner Road) | SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install pedestrian signals, curb ramps, and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 8000
HS-2405AK | Highway | Safety | SR 1004 (Garner Road) | SR 2684 (Tryon Road) intersection | Upgrade traffic signal and install pedestrian signals, curb ramps, and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 145000 | FY 2026: 145000
HS-2405AL | Highway | Safety | NC 96; SR 1100 (East Main Street) | Cross Street intersection | Upgrade traffic signal and install pedestrian signals | 0.5 | Franklin | 5 | Capital Area MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405AL | Highway | Safety | NC 96; SR 1100 (East Main Street) | Cross Street intersection | Upgrade traffic signal and install pedestrian signals | 0.5 | Franklin | 5 | Capital Area MPO |  | Region C |  | HSIP | UTILITIES | 10000 | FY 2026: 10000
HS-2405AL | Highway | Safety | NC 96; SR 1100 (East Main Street) | Cross Street intersection | Upgrade traffic signal and install pedestrian signals | 0.5 | Franklin | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 165000 | FY 2027: 165000
HS-2405AM | Highway | Safety | US 158 | Hardwood Drive in Person County to US Tobacco Cooperative driveway in Granville County. | Install rumble stipes. | 3.7 | Granville, Person | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1331000 | FY 2026: 1331000
HS-2405AN | Highway | Safety | SR 3009 (Edwards Mill Road) | SR 1728 (Wade Avenue) ramp terminals | Upgrade traffic signal, install pedestrian signals, and install rectangular rapid flashing beacons at slip ramps. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 185000 | FY 2026: 185000
HS-2405AO | Highway | Safety | Various | Intersections in Roxboro | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405AO | Highway | Safety | Various | Intersections in Roxboro | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | UTILITIES | 20000 | FY 2026: 20000
HS-2405AO | Highway | Safety | Various | Intersections in Roxboro | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Person | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 943000 | FY 2027: 943000
HS-2405AP | Highway | Safety | Various | Intersections in Henderson | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2027: 10000
HS-2405AP | Highway | Safety | Various | Intersections in Henderson | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | UTILITIES | 20000 | FY 2027: 20000
HS-2405AP | Highway | Safety | Various | Intersections in Henderson | Upgrade pedestrian accommodations including crosswalks, pedestrian signal heads, curb ramps, sidewalks, leading pedestrian interval and/or traffic signal upgrades. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 1255000 | FY 2028: 1255000
HS-2405AQ | Highway | Safety | SR 1835 (Pinecrest Road) | Grove Barton Road; Toscana Drive intersection | Install traffic signal and intersection pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2026: 30000
HS-2405AQ | Highway | Safety | SR 1835 (Pinecrest Road) | Grove Barton Road; Toscana Drive intersection | Install traffic signal and intersection pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2405AQ | Highway | Safety | SR 1835 (Pinecrest Road) | Grove Barton Road; Toscana Drive intersection | Install traffic signal and intersection pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 340000 | FY 2027: 340000
HS-2405AR | Highway | Safety | Various | Downtown Raleigh | Construct pedestrian improvements at multiple existing crosswalks including pedestrian curb extensions, raised crosswalks, and median refuge islands. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2405AR | Highway | Safety | Various | Downtown Raleigh | Construct pedestrian improvements at multiple existing crosswalks including pedestrian curb extensions, raised crosswalks, and median refuge islands. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2405AR | Highway | Safety | Various | Downtown Raleigh | Construct pedestrian improvements at multiple existing crosswalks including pedestrian curb extensions, raised crosswalks, and median refuge islands. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 1020000 | FY 2027: 1020000
HS-2405AS | Highway | Safety | US 1 (Capital Boulevard) | Calvary Drive intersection. | Construct signal and crosswalk upgrades and install median fence. | 0.5 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 395000
HS-2405AT | Highway | Safety | SR 2544 (Sunnybrook Road) | Middle Branch Road intersection. | Install traffic signal. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 15000 | FY 2026: 15000
HS-2405AT | Highway | Safety | SR 2544 (Sunnybrook Road) | Middle Branch Road intersection. | Install traffic signal. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 160000 | FY 2026: 160000
HS-2405AU | Highway | Safety | Various | SR 1119 (Buckhorn Duncan Road) from Harnett County line to SR 1116 (Cass Holt Road); SR 1371/SR 1375 (Lake Wheeler Road) from SR 1009 (Tryon Road) to SR 5411 (Lakewind Court); SE 14003 (Cokesbury Road) from Wake County line to NC 42 in Harnett County. | Install 6-inch edgeline pavement marking. | 4.9 | Wake, Harnett | 5, 6 | Capital Area MPO |  | Division 5, 6 |  | HSIP | CONSTRUCTION | 300000 | FY 2026: 300000
HS-2405AV | Highway | Safety | SR 1615 (High House Road) | Cornerstone Drive intersection. | Upgrade traffic signal and intersection to include pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 15000 | FY 2026: 15000
HS-2405AV | Highway | Safety | SR 1615 (High House Road) | Cornerstone Drive intersection. | Upgrade traffic signal and intersection to include pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 135000 | FY 2026: 135000
HS-2405AW | Highway | Safety | SR 1827 (Lynn Road) | Glendower Road intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HS-2405AW | Highway | Safety | SR 1827 (Lynn Road) | Glendower Road intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2405AW | Highway | Safety | SR 1827 (Lynn Road) | Glendower Road intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 655000 | FY 2027: 655000
HS-2405AX | Highway | Safety | SR 2765 (Old Honeycutt Road) | Fuquay-Varina Parkway intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 8000 | FY 2026: 8000
HS-2405AX | Highway | Safety | SR 2765 (Old Honeycutt Road) | Fuquay-Varina Parkway intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 10000 | FY 2026: 10000
HS-2405AX | Highway | Safety | SR 2765 (Old Honeycutt Road) | Fuquay-Varina Parkway intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 382000 | FY 2027: 382000
HS-2405AY | Highway | Safety | NC 751 (Academy Road) | Pinecrest Road intersection | Install pedestiran and bicycle improvements. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 60000 | FY 2026: 60000
HS-2405AZ | Highway | Safety | SR 2000 (Wake Forest Road) | Hardimont Road/New Hope Church Road and Bland Road intersections | Update traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405AZ | Highway | Safety | SR 2000 (Wake Forest Road) | Hardimont Road/New Hope Church Road and Bland Road intersections | Update traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 15000 | FY 2026: 15000
HS-2405AZ | Highway | Safety | SR 2000 (Wake Forest Road) | Hardimont Road/New Hope Church Road and Bland Road intersections | Update traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 360000 | FY 2027: 360000
HS-2405B | Highway | Safety | NC 157 (Guess Road) | Durham municipal limits to Orange County line. | Install long-life pavement markings. |  | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 201000
HS-2405B | Highway | Safety | NC 157 (Guess Road) | Durham municipal limits to Orange County line. | Install long-life pavement markings. |  | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Region C |  | T(M) | CONSTRUCTION | 22000
HS-2405BA | Highway | Safety | Various | Routes in Wake and Franklin counties | Install experimental pavement markings to evaluate wet retroreflectivity. |  | Wake, Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 2925000 | FY 2026: 2925000
HS-2405BB | Highway | Safety | SR 1822 (Leesville Road) | Country Trail/Tylerton Drive intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405BB | Highway | Safety | SR 1822 (Leesville Road) | Country Trail/Tylerton Drive intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 10000 | FY 2026: 10000
HS-2405BB | Highway | Safety | SR 1822 (Leesville Road) | Country Trail/Tylerton Drive intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 475000 | FY 2027: 475000
HS-2405BC | Highway | Safety | SR 2765 (Old Honeycutt Road) | Fitness Drive / Weststone Boulevard intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 50000 | FY 2026: 50000
HS-2405BC | Highway | Safety | SR 2765 (Old Honeycutt Road) | Fitness Drive / Weststone Boulevard intersection | Install traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 300000 | FY 2026: 300000
HS-2405BF | Highway | Safety | SR 1229 (Main Street) | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Franklin | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 22000 | FY 2027: 22000
HS-2405BF | Highway | Safety | SR 1229 (Main Street) | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Franklin | 5 | Kerr-Tar RPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 3000 | FY 2027: 3000
HS-2405BF | Highway | Safety | SR 1229 (Main Street) | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Franklin | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | UTILITIES | 4000 | FY 2027: 4000
HS-2405BF | Highway | Safety | SR 1229 (Main Street) | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Franklin | 5 | Kerr-Tar RPO |  | Division 5 |  | T(M) | UTILITIES | 1000 | FY 2027: 1000
HS-2405BF | Highway | Safety | SR 1229 (Main Street) | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Franklin | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 306000 | FY 2028: 306000
HS-2405BF | Highway | Safety | SR 1229 (Main Street) | West Nash Street to Allen Lane / Jolly Street | Install pedestrian improvements. | 0.9 | Franklin | 5 | Kerr-Tar RPO |  | Division 5 |  | T(M) | CONSTRUCTION | 34000 | FY 2028: 34000
HS-2405BJ | Highway | Safety | SR 2921 (North Raleigh Boulevard) | Glascock Street intersection | Upgrade traffic signal and install pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 4000 | FY 2026: 4000
HS-2405BJ | Highway | Safety | SR 2921 (North Raleigh Boulevard) | Glascock Street intersection | Upgrade traffic signal and install pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2405BJ | Highway | Safety | SR 2921 (North Raleigh Boulevard) | Glascock Street intersection | Upgrade traffic signal and install pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 292000 | FY 2027: 292000
HS-2405BJ | Highway | Safety | SR 2921 (North Raleigh Boulevard) | Glascock Street intersection | Upgrade traffic signal and install pedestrian improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 33000 | FY 2027: 33000
HS-2405C | Highway | Safety | Various | US 401 in Franklin County. NC 42 in Wake County. NC 56 in Franklin and Granville Counties. NC 96 in Wake and Granville Counties. SR 1006 in Wake County. NC 50 in Wake and Granville Counties. | Install long-life pavement markings. |  | Wake, Franklin, Granville | 5 | Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 1184000 | FY 2026: 1171000
HS-2405C | Highway | Safety | Various | US 401 in Franklin County. NC 42 in Wake County. NC 56 in Franklin and Granville Counties. NC 96 in Wake and Granville Counties. SR 1006 in Wake County. NC 50 in Wake and Granville Counties. | Install long-life pavement markings. |  | Wake, Franklin, Granville | 5 | Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | T(M) | CONSTRUCTION | 131000 | FY 2026: 130000
HS-2405D | Highway | Safety | SR 1656 (Trinity Road) | SR 3009 (Edwards Mill Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 14000
HS-2405D | Highway | Safety | SR 1656 (Trinity Road) | SR 3009 (Edwards Mill Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 2000
HS-2405D | Highway | Safety | SR 1656 (Trinity Road) | SR 3009 (Edwards Mill Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 112000 | FY 2026: 112000
HS-2405D | Highway | Safety | SR 1656 (Trinity Road) | SR 3009 (Edwards Mill Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 12000 | FY 2026: 12000
HS-2405E | Highway | Safety | US 70 (Glenwood Road) | SR 1820 (Lead Mine Road) / SR 1670 (Blue Ridge Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 158000 | FY 2026: 158000
HS-2405E | Highway | Safety | US 70 (Glenwood Road) | SR 1820 (Lead Mine Road) / SR 1670 (Blue Ridge Road) intersection. | Upgrade traffic signal to provide pedestrian accommodations and crosswalks. | 0.5 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 18000 | FY 2026: 18000
HS-2405F | Highway | Safety | Various | Secondary routes in Division 5 | Install long life pavement markings. |  | Granville, Vance, Person | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 1665000
HS-2405F | Highway | Safety | Various | Secondary routes in Division 5 | Install long life pavement markings. |  | Granville, Vance, Person | 5 | Kerr-Tar RPO |  | Division 5 |  | T(M) | CONSTRUCTION | 185000
HS-2405G | Highway | Safety | SR 1349 (Dillard Drive) | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 7000 | FY 2026: 7000
HS-2405G | Highway | Safety | SR 1349 (Dillard Drive) | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2405G | Highway | Safety | SR 1349 (Dillard Drive) | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 27000 | FY 2026: 27000
HS-2405G | Highway | Safety | SR 1349 (Dillard Drive) | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 3000 | FY 2026: 3000
HS-2405G | Highway | Safety | SR 1349 (Dillard Drive) | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 267000 | FY 2027: 267000
HS-2405G | Highway | Safety | SR 1349 (Dillard Drive) | Dillard Drive Middle School driveway; Orabelle Court intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 30000 | FY 2027: 30000
HS-2405H | Highway | Safety | SR 2049 (Forestville Road) | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2405H | Highway | Safety | SR 2049 (Forestville Road) | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 0 | FY 2026: 0
HS-2405H | Highway | Safety | SR 2049 (Forestville Road) | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 18000 | FY 2026: 18000
HS-2405H | Highway | Safety | SR 2049 (Forestville Road) | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 2000 | FY 2026: 2000
HS-2405H | Highway | Safety | SR 2049 (Forestville Road) | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 219000 | FY 2027: 219000
HS-2405H | Highway | Safety | SR 2049 (Forestville Road) | Cashew Drive intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 24000 | FY 2027: 24000
HS-2405I | Highway | Safety | SR 1110 (Barbee Chapel Road) | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2405I | Highway | Safety | SR 1110 (Barbee Chapel Road) | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 0 | FY 2026: 0
HS-2405I | Highway | Safety | SR 1110 (Barbee Chapel Road) | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2405I | Highway | Safety | SR 1110 (Barbee Chapel Road) | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | T(M) | UTILITIES | 0 | FY 2026: 0
HS-2405I | Highway | Safety | SR 1110 (Barbee Chapel Road) | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | HSIP | CONSTRUCTION | 108000 | FY 2026: 108000
HS-2405I | Highway | Safety | SR 1110 (Barbee Chapel Road) | Downing Creek Parkway; Hales Wood Road intersection | Install traffic signal with pedestrian accommodations. | 0.5 | Durham | 5 | Triangle West TPO |  | Division 5 |  | T(M) | CONSTRUCTION | 12000 | FY 2026: 12000
HS-2405J | Highway | Safety | US 70 / US 401 (South Saunders Street) | I-40 / I-440 ramp terminals | Uprade ramp traffic signals. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 324000 | FY 2026: 324000
HS-2405J | Highway | Safety | US 70 / US 401 (South Saunders Street) | I-40 / I-440 ramp terminals | Uprade ramp traffic signals. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 36000 | FY 2026: 36000
HS-2405K | Highway | Safety | SR 2026 (North Person Street) | Polk street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2405K | Highway | Safety | SR 2026 (North Person Street) | Polk street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 0 | FY 2026: 0
HS-2405K | Highway | Safety | SR 2026 (North Person Street) | Polk street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 135000 | FY 2027: 135000
HS-2405K | Highway | Safety | SR 2026 (North Person Street) | Polk street intersection | Install traffic signal with pedestrian signals and high visibility crosswalks and connect to Raleigh signal system. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 15000 | FY 2027: 15000
HS-2405L | Highway | Safety | Various | All freeway ramp locations in Division 5 | Bring wrong way driver deterrence markings up to standard. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Capital Area MPO, Triangle West TPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  | HSIP | CONSTRUCTION | 984000
HS-2405L | Highway | Safety | Various | All freeway ramp locations in Division 5 | Bring wrong way driver deterrence markings up to standard. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Capital Area MPO, Triangle West TPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 109000
HS-2405M | Highway | Safety | US 501 Business (Roxboro Street) | Maynard Avenue intersection | Install traffic signal with pedestrian accommodations and connect to the Durham signal system. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 22000 | FY 2026: 22000
HS-2405M | Highway | Safety | US 501 Business (Roxboro Street) | Maynard Avenue intersection | Install traffic signal with pedestrian accommodations and connect to the Durham signal system. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2405M | Highway | Safety | US 501 Business (Roxboro Street) | Maynard Avenue intersection | Install traffic signal with pedestrian accommodations and connect to the Durham signal system. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 160000 | FY 2026: 2000; FY 2027: 158000
HS-2405M | Highway | Safety | US 501 Business (Roxboro Street) | Maynard Avenue intersection | Install traffic signal with pedestrian accommodations and connect to the Durham signal system. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | CONSTRUCTION | 18000 | FY 2026: 0; FY 2027: 18000
HS-2405N | Highway | Safety | NC 96 (Martin Luther King Jr. Avenue) | SR 1646 (East Industry Drive) intersection | Install/upgrade pedestrian accommodations. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 256000 | FY 2026: 256000
HS-2405N | Highway | Safety | NC 96 (Martin Luther King Jr. Avenue) | SR 1646 (East Industry Drive) intersection | Install/upgrade pedestrian accommodations. | 0.5 | Granville | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | CONSTRUCTION | 28000 | FY 2026: 28000
HS-2405O | Highway | Safety | SR 2754 (Kennebec Road) | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2026: 45000
HS-2405O | Highway | Safety | SR 2754 (Kennebec Road) | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2405O | Highway | Safety | SR 2754 (Kennebec Road) | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 45000 | FY 2026: 45000
HS-2405O | Highway | Safety | SR 2754 (Kennebec Road) | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 5000 | FY 2026: 5000
HS-2405O | Highway | Safety | SR 2754 (Kennebec Road) | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 504000 | FY 2026: 504000
HS-2405O | Highway | Safety | SR 2754 (Kennebec Road) | SR 2763 (Maude Stewart Road) intersection | Construct roundabout. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 56000 | FY 2026: 56000
HS-2405P | Highway | Safety | US 501 (Roxboro Road) | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 4000 | FY 2026: 4000
HS-2405P | Highway | Safety | US 501 (Roxboro Road) | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2405P | Highway | Safety | US 501 (Roxboro Road) | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | UTILITIES | 4000 | FY 2026: 4000
HS-2405P | Highway | Safety | US 501 (Roxboro Road) | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | UTILITIES | 1000 | FY 2026: 1000
HS-2405P | Highway | Safety | US 501 (Roxboro Road) | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 111000 | FY 2027: 111000
HS-2405P | Highway | Safety | US 501 (Roxboro Road) | Rippling Stream Road intersection | Install traffic signal. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | T(M) | CONSTRUCTION | 12000 | FY 2027: 12000
HS-2405Q | Highway | Safety | SR 5144 (Heritage Lake Road) | Heritage Heights Lane intersection | Construct crosswalk and sidewalk improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 135000 | FY 2026: 135000
HS-2405Q | Highway | Safety | SR 5144 (Heritage Lake Road) | Heritage Heights Lane intersection | Construct crosswalk and sidewalk improvements. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 15000 | FY 2026: 15000
HS-2405R | Highway | Safety | SR 3067 (TW Alexander Drive) | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 7000
HS-2405R | Highway | Safety | SR 3067 (TW Alexander Drive) | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 1000
HS-2405R | Highway | Safety | SR 3067 (TW Alexander Drive) | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000
HS-2405R | Highway | Safety | SR 3067 (TW Alexander Drive) | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 0
HS-2405R | Highway | Safety | SR 3067 (TW Alexander Drive) | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 112000 | FY 2026: 112000
HS-2405R | Highway | Safety | SR 3067 (TW Alexander Drive) | Brier Club Lane; Salem Glen Lane intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 12000 | FY 2026: 12000
HS-2405S | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 3000 | FY 2026: 3000
HS-2405S | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 0 | FY 2026: 0
HS-2405S | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 4000 | FY 2026: 4000
HS-2405S | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 1000 | FY 2026: 1000
HS-2405S | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 396000 | FY 2027: 396000
HS-2405S | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Garner Road to Haywood Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 44000 | FY 2027: 44000
HS-2405T | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 4000 | FY 2026: 4000
HS-2405T | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2405T | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000 | FY 2026: 3000
HS-2405T | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 0 | FY 2026: 0
HS-2405T | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 346000 | FY 2026: 346000
HS-2405T | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | SR 3670 (Blount Street) to South East Street | Upgrade traffic signal and pedestrian accommodations. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 39000 | FY 2026: 39000
HS-2405U | Highway | Safety | SR 1652 (Harrison Avenue) | SR 3081 (Chapel Hill Road) intersection | Upgrade traffic signal and install pedestrian signal and other pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 72000 | FY 2026: 72000
HS-2405U | Highway | Safety | SR 1652 (Harrison Avenue) | SR 3081 (Chapel Hill Road) intersection | Upgrade traffic signal and install pedestrian signal and other pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 8000 | FY 2026: 8000
HS-2405V | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 14000 | FY 2026: 14000
HS-2405V | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2405V | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 4000 | FY 2026: 4000
HS-2405V | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 1000 | FY 2026: 1000
HS-2405V | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 365000 | FY 2027: 365000
HS-2405V | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Gregg Street to Rock Quarry Road | Install/upgrade traffic signals and pedestrian acommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 40000 | FY 2027: 40000
HS-2405W | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 4000 | FY 2026: 4000
HS-2405W | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2405W | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 9000 | FY 2026: 9000
HS-2405W | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | UTILITIES | 1000 | FY 2026: 1000
HS-2405W | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 423000 | FY 2026: 423000
HS-2405W | Highway | Safety | SR 4363 (Martin Luther King Jr. Boulevard) | Raleigh Boulevard to Poole Road | Upgrade traffic signals, install/upgrade pedestrian accommodations, and install lighting. | 1 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 47000 | FY 2026: 47000
HS-2405X | Highway | Safety | US 70 (Glenwood Avenue) | Hilburn Drive; Glenwood Forest Drive intersection | Install/upgrade crosswalks, pedestrian signals, and sidewalk. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | HSIP | UTILITIES | 2000
HS-2405X | Highway | Safety | US 70 (Glenwood Avenue) | Hilburn Drive; Glenwood Forest Drive intersection | Install/upgrade crosswalks, pedestrian signals, and sidewalk. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | UTILITIES | 0
HS-2405X | Highway | Safety | US 70 (Glenwood Avenue) | Hilburn Drive; Glenwood Forest Drive intersection | Install/upgrade crosswalks, pedestrian signals, and sidewalk. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 204000 | FY 2026: 204000
HS-2405X | Highway | Safety | US 70 (Glenwood Avenue) | Hilburn Drive; Glenwood Forest Drive intersection | Install/upgrade crosswalks, pedestrian signals, and sidewalk. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2405Y | Highway | Safety | SR 2026 (Hammond Road) | Rush Street intersection | Upgrade traffic signals and install/upgrade pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 165000 | FY 2026: 165000
HS-2405Y | Highway | Safety | SR 2026 (Hammond Road) | Rush Street intersection | Upgrade traffic signals and install/upgrade pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Division 5 |  | T(M) | CONSTRUCTION | 18000 | FY 2026: 18000
HS-2405Z | Highway | Safety | US 70 / US 401 / NC 50 (Wilmington Street) | Chapanoke Road intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 80000 | FY 2026: 80000
HS-2405Z | Highway | Safety | US 70 / US 401 / NC 50 (Wilmington Street) | Chapanoke Road intersection | Upgrade traffic signal and pedestrian accommodations. | 0.5 | Wake | 5 | Capital Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 9000 | FY 2026: 9000
HS-2406 | Highway | Safety | Various | Routes in Division 6. | Construct safety improvements. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2406A | Highway | Safety | NC 87 | Mile marker 1.033 to mile marker 6.933 near Riegelwood | Install rumble stripes and pavement markers. | 5.9 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 261000
HS-2406A | Highway | Safety | NC 87 | Mile marker 1.033 to mile marker 6.933 near Riegelwood | Install rumble stripes and pavement markers. | 5.9 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 29000
HS-2406AA | Highway | Safety | SR 1404 (Morganton Road) | SR 1596 (Glensford Drive)/Cross Creek Mall, Cross Point/Cross Creek Mall, and US 401 (Skibo Road) | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2026: 45000
HS-2406AA | Highway | Safety | SR 1404 (Morganton Road) | SR 1596 (Glensford Drive)/Cross Creek Mall, Cross Point/Cross Creek Mall, and US 401 (Skibo Road) | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2406AA | Highway | Safety | SR 1404 (Morganton Road) | SR 1596 (Glensford Drive)/Cross Creek Mall, Cross Point/Cross Creek Mall, and US 401 (Skibo Road) | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 558000 | FY 2027: 558000
HS-2406AA | Highway | Safety | SR 1404 (Morganton Road) | SR 1596 (Glensford Drive)/Cross Creek Mall, Cross Point/Cross Creek Mall, and US 401 (Skibo Road) | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | CONSTRUCTION | 62000 | FY 2027: 62000
HS-2406AB | Highway | Safety | US 701 Bypass | Lewis Street intersection | Install crosswalk with Rectangular Rapid Flashing Beacons and median fencing. | 0.2 | Columbus | 6 | Cape Fear RPO |  | Region C |  | HSIP | CONSTRUCTION | 293000 | FY 2026: 293000
HS-2406AB | Highway | Safety | US 701 Bypass | Lewis Street intersection | Install crosswalk with Rectangular Rapid Flashing Beacons and median fencing. | 0.2 | Columbus | 6 | Cape Fear RPO |  | Region C |  | T(M) | CONSTRUCTION | 32000 | FY 2026: 32000
HS-2406AC | Highway | Safety | US 701 Bypass | Williamson Street intersection | Install sidewalk, crosswalk with Rectangular Rapid Flashing Beacons, and median fencing. | 0.1 | Columbus | 6 | Cape Fear RPO |  | Region C |  | HSIP | CONSTRUCTION | 183000 | FY 2026: 183000
HS-2406AC | Highway | Safety | US 701 Bypass | Williamson Street intersection | Install sidewalk, crosswalk with Rectangular Rapid Flashing Beacons, and median fencing. | 0.1 | Columbus | 6 | Cape Fear RPO |  | Region C |  | T(M) | CONSTRUCTION | 20000 | FY 2026: 20000
HS-2406B | Highway | Safety | US 501 | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Robeson | 6 | Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 27000
HS-2406B | Highway | Safety | US 501 | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 3000
HS-2406B | Highway | Safety | US 501 | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Robeson | 6 | Lumber River RPO |  | Region C |  | HSIP | UTILITIES | 63000
HS-2406B | Highway | Safety | US 501 | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | UTILITIES | 7000
HS-2406B | Highway | Safety | US 501 | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Robeson | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 1125000 | FY 2026: 1125000
HS-2406B | Highway | Safety | US 501 | NC 130 intersection in Raemon | Realign intersection, remove slip lanes, and add right turn lane. |  | Robeson | 6 | Lumber River RPO |  | Region C |  | T(M) | CONSTRUCTION | 125000 | FY 2026: 125000
HS-2406C | Highway | Safety | US 401 (Ramsey Street) | At Northgate shopping center in Fayetteville | Install crosswalk, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 297000
HS-2406C | Highway | Safety | US 401 (Ramsey Street) | At Northgate shopping center in Fayetteville | Install crosswalk, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 33000
HS-2406D | Highway | Safety | US 401 Business (Ramsey Street) | Langdon street and Colonial Drive intersections in Fayetteville | Install crosswalk, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 252000
HS-2406D | Highway | Safety | US 401 Business (Ramsey Street) | Langdon street and Colonial Drive intersections in Fayetteville | Install crosswalk, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 28000
HS-2406E | Highway | Safety | US 701 | SR 1806 (Mercer Mill Road), Swanzy Street, and King Street intersections in Elizabethtown | Install crosswalks, pedestrian signal heads, and upgrade traffic signals. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 644000
HS-2406E | Highway | Safety | US 701 | SR 1806 (Mercer Mill Road), Swanzy Street, and King Street intersections in Elizabethtown | Install crosswalks, pedestrian signal heads, and upgrade traffic signals. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | CONSTRUCTION | 72000
HS-2406F | Highway | Safety | US 401 (Ramsey Street) | Treetop Drive intersection in Fayetteville | Install / upgrade crosswalks, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 180000
HS-2406F | Highway | Safety | US 401 (Ramsey Street) | Treetop Drive intersection in Fayetteville | Install / upgrade crosswalks, pedestrian signal heads, curb ramps, and upgrade traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 20000
HS-2406G | Highway | Safety | US 701 | Mile marker 1.96 to 9.46 in Bladen County, mile marker 2.57 to 15.48 and mile marker 19.97 to 30.35 in Columbus County | Install rumble stripes and pavement markings. | 30.79 | Columbus, Bladen | 6 | Cape Fear RPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 873000
HS-2406G | Highway | Safety | US 701 | Mile marker 1.96 to 9.46 in Bladen County, mile marker 2.57 to 15.48 and mile marker 19.97 to 30.35 in Columbus County | Install rumble stripes and pavement markings. | 30.79 | Columbus, Bladen | 6 | Cape Fear RPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 97000
HS-2406HA | Highway | Safety | NC 87 | SR 1725 (Braddy Plantation Road) to East of NC 87 Business. | Install centerline and shoulder sinusoidal rumble stripes. |  | Bladen | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 306000
HS-2406HA | Highway | Safety | NC 87 | SR 1725 (Braddy Plantation Road) to East of NC 87 Business. | Install centerline and shoulder sinusoidal rumble stripes. |  | Bladen | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 34000
HS-2406HB | Highway | Safety | NC 87 | Columbus County line to SR 1725 (Braddy Plantation Road) in Bladen County. | Install rumble stripes and pavement markings. |  | Bladen | 6 | Mid-Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 270000
HS-2406HB | Highway | Safety | NC 87 | Columbus County line to SR 1725 (Braddy Plantation Road) in Bladen County. | Install rumble stripes and pavement markings. |  | Bladen | 6 | Mid-Carolina RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 30000
HS-2406I | Highway | Safety | Various | Routes in Bladen, Columbus, and Cumberland Counties | Upgrade 60 guardrail end units. |  | Cumberland, Columbus, Bladen | 6 | Fayetteville Area MPO, Cape Fear RPO, Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 548000
HS-2406I | Highway | Safety | Various | Routes in Bladen, Columbus, and Cumberland Counties | Upgrade 60 guardrail end units. |  | Cumberland, Columbus, Bladen | 6 | Fayetteville Area MPO, Cape Fear RPO, Mid-Carolina RPO |  | Region C |  | T(M) | CONSTRUCTION | 61000
HS-2406J | Highway | Safety | NC 130; NC 410 | Mile marker 0 to mile marker 17.04; Mile marker 2.62 to 13.6 | Install rumble stripes and pavement markings. |  | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 801000
HS-2406J | Highway | Safety | NC 130; NC 410 | Mile marker 0 to mile marker 17.04; Mile marker 2.62 to 13.6 | Install rumble stripes and pavement markings. |  | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 89000
HS-2406K | Highway | Safety | US 301 | Mile marker 0 to 1.674 in Cumberland County and mile marker 6.171 to 9.703 in Harnett County | Install rumble stripes and pavement markings. |  | Harnett, Cumberland | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 252000
HS-2406K | Highway | Safety | US 301 | Mile marker 0 to 1.674 in Cumberland County and mile marker 6.171 to 9.703 in Harnett County | Install rumble stripes and pavement markings. |  | Harnett, Cumberland | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 28000
HS-2406L | Highway | Safety | US 301 | Mile marker 24.42 to 32.52 and mile marker 33.865 to 40.92 | Install rumble stripes and pavement markings. |  | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 603000
HS-2406L | Highway | Safety | US 301 | Mile marker 24.42 to 32.52 and mile marker 33.865 to 40.92 | Install rumble stripes and pavement markings. |  | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 67000
HS-2406M | Highway | Safety | US 301; SR 1003 (Chicken Road) | Mile marker 10.14 to 22.23; Mile marker 5.785 to 19.004 | Install rumble stripes and pavement markings. |  | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 216000
HS-2406M | Highway | Safety | US 301; SR 1003 (Chicken Road) | Mile marker 10.14 to 22.23; Mile marker 5.785 to 19.004 | Install rumble stripes and pavement markings. |  | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T(M) | CONSTRUCTION | 24000
HS-2406N | Highway | Safety | NC 87 | NC 131 intersection in Tarheel. | Install traffic signal. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 4000
HS-2406N | Highway | Safety | NC 87 | NC 131 intersection in Tarheel. | Install traffic signal. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 1000
HS-2406N | Highway | Safety | NC 87 | NC 131 intersection in Tarheel. | Install traffic signal. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | UTILITIES | 117000
HS-2406N | Highway | Safety | NC 87 | NC 131 intersection in Tarheel. | Install traffic signal. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | UTILITIES | 13000
HS-2406N | Highway | Safety | NC 87 | NC 131 intersection in Tarheel. | Install traffic signal. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 459000 | FY 2026: 459000
HS-2406N | Highway | Safety | NC 87 | NC 131 intersection in Tarheel. | Install traffic signal. |  | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | CONSTRUCTION | 51000 | FY 2026: 51000
HS-2406O | Highway | Safety | US 401 (Skibo Road) | SR 1400 (Cliffdale Road) intersection in Fayetteville. | Revise traffic signal, and install crosswalks and pedestrian signal heads. |  | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 234000
HS-2406O | Highway | Safety | US 401 (Skibo Road) | SR 1400 (Cliffdale Road) intersection in Fayetteville. | Revise traffic signal, and install crosswalks and pedestrian signal heads. |  | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 26000
HS-2406P | Highway | Safety | US 401 Business (Robeson Street) | SR 1168 (Whitfield Street) intersection in Fayetteville. | Revise traffic signal, and install crosswalks and pedestrian signal heads. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 162000
HS-2406P | Highway | Safety | US 401 Business (Robeson Street) | SR 1168 (Whitfield Street) intersection in Fayetteville. | Revise traffic signal, and install crosswalks and pedestrian signal heads. |  | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 18000
HS-2406Q | Highway | Safety | NC 410 (Brown Street) | First Avenue intersection in Chadbourn. | Upgrade traffic signal with pedestrian heads. |  | Columbus | 6 | Cape Fear RPO |  | Region C |  | HSIP | CONSTRUCTION | 77000
HS-2406Q | Highway | Safety | NC 410 (Brown Street) | First Avenue intersection in Chadbourn. | Upgrade traffic signal with pedestrian heads. |  | Columbus | 6 | Cape Fear RPO |  | Region C |  | T(M) | CONSTRUCTION | 8000
HS-2406R | Highway | Safety | SR 1404 (Morganton Road) | McPherson Church Road. | Install/upgrade crosswalks, crosswalk ramps signalized pedestrian heads, and traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 270000 | FY 2026: 270000
HS-2406R | Highway | Safety | SR 1404 (Morganton Road) | McPherson Church Road. | Install/upgrade crosswalks, crosswalk ramps signalized pedestrian heads, and traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | CONSTRUCTION | 30000 | FY 2026: 30000
HS-2406S | Highway | Safety | US 401 (Skibo Road) | NC 24 / NC 87 (Bragg Boulevard) eastbound ramps (Swain Street). | Install/upgrade crosswalks and traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 657000 | FY 2026: 657000
HS-2406S | Highway | Safety | US 401 (Skibo Road) | NC 24 / NC 87 (Bragg Boulevard) eastbound ramps (Swain Street). | Install/upgrade crosswalks and traffic signal. |  | Cumberland | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 73000 | FY 2026: 73000
HS-2406T | Highway | Safety | NC 41 (Broad Street) | SR 1150 (Peanut Road)/Newton Street | Revise traffic signal and install pedestrian signals and crosswalks. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | UTILITIES | 135000 | FY 2026: 135000
HS-2406T | Highway | Safety | NC 41 (Broad Street) | SR 1150 (Peanut Road)/Newton Street | Revise traffic signal and install pedestrian signals and crosswalks. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | UTILITIES | 15000 | FY 2026: 15000
HS-2406T | Highway | Safety | NC 41 (Broad Street) | SR 1150 (Peanut Road)/Newton Street | Revise traffic signal and install pedestrian signals and crosswalks. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 297000 | FY 2026: 297000
HS-2406T | Highway | Safety | NC 41 (Broad Street) | SR 1150 (Peanut Road)/Newton Street | Revise traffic signal and install pedestrian signals and crosswalks. | 0.5 | Bladen | 6 | Mid-Carolina RPO |  | Region C |  | T(M) | CONSTRUCTION | 33000 | FY 2026: 33000
HS-2406U | Highway | Safety | NC 53 | Bladen County to Fayetteville City limits | Install rumble strips and long life pavement markings and markers. | 12.9 | Cumberland | 6 | Fayetteville Area MPO, Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 432000 | FY 2026: 432000
HS-2406U | Highway | Safety | NC 53 | Bladen County to Fayetteville City limits | Install rumble strips and long life pavement markings and markers. | 12.9 | Cumberland | 6 | Fayetteville Area MPO, Mid-Carolina RPO |  | Region C |  | T(M) | CONSTRUCTION | 48000 | FY 2026: 48000
HS-2406V | Highway | Safety | SR 1400 (Cliffdale Road) | SR 1593 (Hoke Loop Road) intersection | Install signalized pedestrian crossing. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 157000 | FY 2026: 157000
HS-2406V | Highway | Safety | SR 1400 (Cliffdale Road) | SR 1593 (Hoke Loop Road) intersection | Install signalized pedestrian crossing. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | CONSTRUCTION | 17000 | FY 2026: 17000
HS-2406W | Highway | Safety | US 401 (Pamalee Drive) | Cain Road and Helen Street intersections | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 302000 | FY 2026: 302000
HS-2406W | Highway | Safety | US 401 (Pamalee Drive) | Cain Road and Helen Street intersections | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C |  | T(M) | CONSTRUCTION | 33000 | FY 2026: 33000
HS-2406X | Highway | Safety | SR 1004 (Tar Heel Road) | NC 87 to Robeson County line | Install rumble strips and long life pavement markings and markers. | 2.6 | Bladen | 6 | Mid-Carolina RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 153000 | FY 2026: 153000
HS-2406X | Highway | Safety | SR 1004 (Tar Heel Road) | NC 87 to Robeson County line | Install rumble strips and long life pavement markings and markers. | 2.6 | Bladen | 6 | Mid-Carolina RPO |  | Division 6 |  | T(M) | CONSTRUCTION | 17000 | FY 2026: 17000
HS-2406Y | Highway | Safety | SR 1004 (Rough and Ready Road) | SR 1415 (Dolph Lewis Road) to US 701 | Install rumble strips and long life pavement markings and markers. | 10.9 | Columbus | 6 | Cape Fear RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 414000 | FY 2026: 414000
HS-2406Y | Highway | Safety | SR 1004 (Rough and Ready Road) | SR 1415 (Dolph Lewis Road) to US 701 | Install rumble strips and long life pavement markings and markers. | 10.9 | Columbus | 6 | Cape Fear RPO |  | Division 6 |  | T(M) | CONSTRUCTION | 46000 | FY 2026: 46000
HS-2406Z | Highway | Safety | SR 1404 (Morganton Road) | Sycamore Dairy Road, SR 1007 (All American Expressway) Northbound Ramp, and Southbound Ramp | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 522000 | FY 2026: 522000
HS-2406Z | Highway | Safety | SR 1404 (Morganton Road) | Sycamore Dairy Road, SR 1007 (All American Expressway) Northbound Ramp, and Southbound Ramp | Upgrade traffic signal and install pedestrian signal heads and crosswalks. | 0.3 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T(M) | CONSTRUCTION | 58000 | FY 2026: 58000
HS-2407 | Highway | Safety | Various | Routes in Division 7. | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2407A | Highway | Safety | SR 2526 (Summit Avenue) | Textile Drive intersection | Install pedestrian signal heads, crosswalks, and other intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | UTILITIES | 4000
HS-2407A | Highway | Safety | SR 2526 (Summit Avenue) | Textile Drive intersection | Install pedestrian signal heads, crosswalks, and other intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | UTILITIES | 0
HS-2407A | Highway | Safety | SR 2526 (Summit Avenue) | Textile Drive intersection | Install pedestrian signal heads, crosswalks, and other intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 63000
HS-2407A | Highway | Safety | SR 2526 (Summit Avenue) | Textile Drive intersection | Install pedestrian signal heads, crosswalks, and other intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | CONSTRUCTION | 7000
HS-2407B | Highway | Safety | SR 1007 (Randleman Road) | Webster Road intersection | Install traffic signal. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 5000
HS-2407B | Highway | Safety | SR 1007 (Randleman Road) | Webster Road intersection | Install traffic signal. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | UTILITIES | 40000
HS-2407B | Highway | Safety | SR 1007 (Randleman Road) | Webster Road intersection | Install traffic signal. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 145000 | FY 2026: 145000
HS-2407C | Highway | Safety | US 29 Northbound | SR 2613 (North O'Henry Boulevard) in the vicinity of Joe Brown Drive; SR 2937 (North O'Henry Boulevard) in the vicinity of the flea market; SR 2622 / SR 5235 (Corbin Road) | Close directional leftovers. | 0.9 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 615000 | FY 2027: 615000
HS-2407D | Highway | Safety | US 29 | Brentwood Street to I-85. | Install median guardrail. | 6.24 | Guilford | 7 | High Point Urban Area MPO |  | Region D |  | HSIP | CONSTRUCTION | 2780000 | FY 2026: 2780000
HS-2407E | Highway | Safety | SR 1005 (Greensboro-Chapel Hill Road) | Guilford County line to Orange County line. | Install 6-inch rumble strips and long life pavement markings. | 18.53 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 1285000 | FY 2027: 1285000
HS-2407F | Highway | Safety | NC 119 | NC 54 to SR 2126 (Old Hillsbotough Road); SR 1921 (Mebane Rogers Road) to Caswell County line. | Install 6-inch rumble strips and long life pavement markings. | 13.3 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | HSIP | CONSTRUCTION | 960000 | FY 2027: 960000
HS-2407G | Highway | Safety | Various | Routes in Chapel Hill and Carrboro. | Install pedestrian accommodations at multiple signalized intrsections. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 600000 | FY 2027: 600000
HS-2407G | Highway | Safety | Various | Routes in Chapel Hill and Carrboro. | Install pedestrian accommodations at multiple signalized intrsections. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | UTILITIES | 170000 | FY 2027: 170000
HS-2407G | Highway | Safety | Various | Routes in Chapel Hill and Carrboro. | Install pedestrian accommodations at multiple signalized intrsections. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | CONSTRUCTION | 840000 | FY 2027: 840000
HS-2407H | Highway | Safety | Various | Routes in Chapel Hill. | Upgraded traffic signals and install pedestrian accomodations at multiple signalized intersections. | 0.5 | Orange | 7 | Triangle West TPO |  | Division 7 |  | HSIP | CONSTRUCTION | 350000 | FY 2027: 350000
HS-2407I | Highway | Safety | NC 14 | 1050 feet North of Cox Street to NC 87. | Install rumble strips. | 3.91 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | HSIP | CONSTRUCTION | 410000 | FY 2027: 410000
HS-2407J | Highway | Safety | Various | Routes in Burlington. | Upgraded traffic signals and install pedestrian accomodations at multiple signalized intersections. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 90000 | FY 2027: 90000
HS-2407K | Highway | Safety | Various | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 1800000 | FY 2027: 1800000
HS-2407K | Highway | Safety | Various | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | T(M) | RIGHT-OF-WAY | 200000 | FY 2027: 200000
HS-2407K | Highway | Safety | Various | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | UTILITIES | 518000 | FY 2027: 518000
HS-2407K | Highway | Safety | Various | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | T(M) | UTILITIES | 57000 | FY 2027: 57000
HS-2407K | Highway | Safety | Various | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 2412000 | FY 2027: 2412000
HS-2407K | Highway | Safety | Various | Intersections in Burlington. | Install pedestrian heads, curb ramps, and crosswalks. Revise traffic signals to include Leading Pedestrian Interval (LPI). | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | T(M) | CONSTRUCTION | 268000 | FY 2027: 268000
HS-2407P | Highway | Safety | NC 87 | SR 1005 (Greensboro Chapel Hill Road) to SR 2316 (Thompson Road). | Install rumble stripes with 6-inch long life pavement markings. | 11 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | HSIP | CONSTRUCTION | 729000 | FY 2028: 729000
HS-2407P | Highway | Safety | NC 87 | SR 1005 (Greensboro Chapel Hill Road) to SR 2316 (Thompson Road). | Install rumble stripes with 6-inch long life pavement markings. | 11 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | T(M) | CONSTRUCTION | 81000 | FY 2028: 81000
HS-2407Q | Highway | Safety | I-40 / I-85 | Ramps at SR 1226, SR 1158, NC 62, NC 49, NC 87, NC 54, SR 1928, SR 1981, and NC 119 interchanges. | Upgrade traffic signals. | 12.4 | Alamance | 7 | Burlington-Graham MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 161000 | FY 2027: 161000
HS-2407Q | Highway | Safety | I-40 / I-85 | Ramps at SR 1226, SR 1158, NC 62, NC 49, NC 87, NC 54, SR 1928, SR 1981, and NC 119 interchanges. | Upgrade traffic signals. | 12.4 | Alamance | 7 | Burlington-Graham MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 18000 | FY 2027: 18000
HS-2407R | Highway | Safety | US 311 | SR 2141 (Young Road) to NC 14, south of Eden. | Install rumble strips and 6-inch long life pavement markings. | 8.4 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | HSIP | CONSTRUCTION | 594000 | FY 2027: 594000
HS-2407R | Highway | Safety | US 311 | SR 2141 (Young Road) to NC 14, south of Eden. | Install rumble strips and 6-inch long life pavement markings. | 8.4 | Rockingham | 7 | Piedmont Triad RPO |  | Region D |  | T(M) | CONSTRUCTION | 66000 | FY 2027: 66000
HS-2407S | Highway | Safety | NC 49 | NC 62 in Alamance County to NC 86 in Orange County. | Install rumble strips and 6-inch long life pavement markings. | 9 | Orange, Alamance | 7 | Central Pines RPO, Burlington-Graham MPO |  | Region D |  | HSIP | CONSTRUCTION | 630000 | FY 2027: 630000
HS-2407S | Highway | Safety | NC 49 | NC 62 in Alamance County to NC 86 in Orange County. | Install rumble strips and 6-inch long life pavement markings. | 9 | Orange, Alamance | 7 | Central Pines RPO, Burlington-Graham MPO |  | Region D |  | T(M) | CONSTRUCTION | 70000 | FY 2027: 70000
HS-2408 | Highway | Safety | Various | Routes in Division 8. | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2408A | Highway | Safety | NC 751; SR 1008 (Farrington Point Road) | NC 751 from US 64 to Durham County line; SR 1008 (Farrington Point Road) from SR 1972 (Pea Ridge Road) to Orange County line | Install rumble stripes. | 21.8 | Chatham | 8 | Central Pines RPO, Triangle West TPO |  | Region E |  | HSIP | CONSTRUCTION | 626000
HS-2408A | Highway | Safety | NC 751; SR 1008 (Farrington Point Road) | NC 751 from US 64 to Durham County line; SR 1008 (Farrington Point Road) from SR 1972 (Pea Ridge Road) to Orange County line | Install rumble stripes. | 21.8 | Chatham | 8 | Central Pines RPO, Triangle West TPO |  | Region E |  | T(M) | CONSTRUCTION | 70000
HS-2408B | Highway | Safety | US 1 | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Moore | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 22000 | FY 2026: 22000
HS-2408B | Highway | Safety | US 1 | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Moore | 8 | Central Pines RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2408B | Highway | Safety | US 1 | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Moore | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 22000 | FY 2026: 22000
HS-2408B | Highway | Safety | US 1 | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Moore | 8 | Central Pines RPO |  | Statewide Mobility |  | T(M) | UTILITIES | 2000 | FY 2026: 2000
HS-2408B | Highway | Safety | US 1 | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Moore | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 742000 | FY 2027: 742000
HS-2408B | Highway | Safety | US 1 | SR 2026 (Youngs Road) | Install reduced conflict intersection. | 0.5 | Moore | 8 | Central Pines RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 82000 | FY 2027: 82000
HS-2408C | Highway | Safety | US 421 | SR 1531 (Swanns Station Road) intersection | Install traffic signal and turn lanes. | 0.5 | Lee | 8 | Central Pines RPO |  | Region E |  | HSIP | UTILITIES | 15000 | FY 2026: 15000
HS-2408C | Highway | Safety | US 421 | SR 1531 (Swanns Station Road) intersection | Install traffic signal and turn lanes. | 0.5 | Lee | 8 | Central Pines RPO |  | Region E |  | HSIP | CONSTRUCTION | 550000 | FY 2027: 550000
HS-2408F | Highway | Safety | US 421 | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Chatham | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 4000 | FY 2027: 4000
HS-2408F | Highway | Safety | US 421 | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Chatham | 8 | Central Pines RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2027: 1000
HS-2408F | Highway | Safety | US 421 | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Chatham | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 4000 | FY 2027: 4000
HS-2408F | Highway | Safety | US 421 | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Chatham | 8 | Central Pines RPO |  | Statewide Mobility |  | T(M) | UTILITIES | 1000 | FY 2027: 1000
HS-2408F | Highway | Safety | US 421 | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Chatham | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 954000 | FY 2028: 954000
HS-2408F | Highway | Safety | US 421 | SR 1007 (Plank Road) / SR 2144 (Fayetteville Road) intersection. | Install directional crossover. | 0.5 | Chatham | 8 | Central Pines RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 106000 | FY 2028: 106000
HS-2409 | Highway | Safety | Various | Routes in Division 9. | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2409A | Highway | Safety | NC 150 | SR 2983 (Fishel Road) intersection | Construct reduced conflict intersection. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | HSIP | UTILITIES | 45000
HS-2409A | Highway | Safety | NC 150 | SR 2983 (Fishel Road) intersection | Construct reduced conflict intersection. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | T(M) | UTILITIES | 5000
HS-2409A | Highway | Safety | NC 150 | SR 2983 (Fishel Road) intersection | Construct reduced conflict intersection. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 990000
HS-2409A | Highway | Safety | NC 150 | SR 2983 (Fishel Road) intersection | Construct reduced conflict intersection. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | T(M) | CONSTRUCTION | 110000
HS-2409B | Highway | Safety | SR 1002 (Old Concord Road) | Martin Luther King Jr. Avenue South intersection | Upgrade traffic signal and install/upgrade pedestrian signals and other pedestrian accommodations. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | UTILITIES | 27000
HS-2409B | Highway | Safety | SR 1002 (Old Concord Road) | Martin Luther King Jr. Avenue South intersection | Upgrade traffic signal and install/upgrade pedestrian signals and other pedestrian accommodations. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | T(M) | UTILITIES | 3000
HS-2409B | Highway | Safety | SR 1002 (Old Concord Road) | Martin Luther King Jr. Avenue South intersection | Upgrade traffic signal and install/upgrade pedestrian signals and other pedestrian accommodations. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | CONSTRUCTION | 144000 | FY 2026: 144000
HS-2409B | Highway | Safety | SR 1002 (Old Concord Road) | Martin Luther King Jr. Avenue South intersection | Upgrade traffic signal and install/upgrade pedestrian signals and other pedestrian accommodations. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | T(M) | CONSTRUCTION | 16000 | FY 2026: 16000
HS-2409C | Highway | Safety | SR 1725 (University Parkway) | West 14th Street intersection in Winston-Salem. | Upgrade traffic signal, install pedestrian signals and crosswalks, and modify sidewalk and median. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 645000
HS-2409E | Highway | Safety | US 601 | SR 1414 (Angell Road) intersection | Improve sight distance. | 0.5 | Davie | 9 | Northwest Piedmont RPO |  | Region D |  | HSIP | CONSTRUCTION | 712000 | FY 2026: 712000
HS-2409E | Highway | Safety | US 601 | SR 1414 (Angell Road) intersection | Improve sight distance. | 0.5 | Davie | 9 | Northwest Piedmont RPO |  | Region D |  | T(M) | CONSTRUCTION | 79000 | FY 2026: 79000
HS-2409F | Highway | Safety | NC 152 | Iredell County line to SR 1211 (Patterson Street/Brown Road) | Install rumble stripes and 6-inch long life pavement markings. | 7.9 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | CONSTRUCTION | 620000 | FY 2026: 620000
HS-2409G | Highway | Safety | US 64 | Iredell County line to I-40 | Install rumble strips. | 7.1 | Davie | 9 | Northwest Piedmont RPO |  | Region D |  | HSIP | CONSTRUCTION | 575000 | FY 2026: 575000
HS-2409H | Highway | Safety | US 601 | Rowan County line to north of Crepe Myrtle Lane | Install rumble strips. | 6.9 | Davie | 9 | Northwest Piedmont RPO |  | Region D |  | HSIP | CONSTRUCTION | 560000 | FY 2026: 560000
HS-2409I | Highway | Safety | NC 801 | I-40 to US 601 | Install rumble strips. | 10.7 | Davie | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO |  | Region D |  | HSIP | CONSTRUCTION | 800000 | FY 2026: 800000
HS-2409J | Highway | Safety | US 158 | East of Crowe Street to east of R.R. Gerald Lane | Install rumble strips. | 7.2 | Davie | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO |  | Region D |  | HSIP | CONSTRUCTION | 575000 | FY 2026: 575000
HS-2409K | Highway | Safety | SR 1112 (South Main Street) | West Dalton Road/East Dalton Road intersection | Install pedestrian signals. | 0.5 | Stokes | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 18000 | FY 2026: 18000
HS-2409L | Highway | Safety | US 29-70/NC 150 (Salisbury Avenue); SR 1915 (Andrews Street/Jefferson Street) | SR 1915 (Jefferson Street), 4th Street, 5th Street, and 6th Street intersections; SR 2100 (Long Street) intersection | Upgrade traffic signals with pedestrian accommodations and upgrade curb ramps. | 2.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2409L | Highway | Safety | US 29-70/NC 150 (Salisbury Avenue); SR 1915 (Andrews Street/Jefferson Street) | SR 1915 (Jefferson Street), 4th Street, 5th Street, and 6th Street intersections; SR 2100 (Long Street) intersection | Upgrade traffic signals with pedestrian accommodations and upgrade curb ramps. | 2.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2409L | Highway | Safety | US 29-70/NC 150 (Salisbury Avenue); SR 1915 (Andrews Street/Jefferson Street) | SR 1915 (Jefferson Street), 4th Street, 5th Street, and 6th Street intersections; SR 2100 (Long Street) intersection | Upgrade traffic signals with pedestrian accommodations and upgrade curb ramps. | 2.5 | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | CONSTRUCTION | 270000 | FY 2026: 270000
HS-2410 | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2410A | Highway | Safety | SR 1790 (Winecoff School Road) | Winecoff Elementary School in Concord | Install pedestrian accommodations. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 9000 | FY 2026: 9000
HS-2410A | Highway | Safety | SR 1790 (Winecoff School Road) | Winecoff Elementary School in Concord | Install pedestrian accommodations. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | T(M) | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2410A | Highway | Safety | SR 1790 (Winecoff School Road) | Winecoff Elementary School in Concord | Install pedestrian accommodations. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | CONSTRUCTION | 87000 | FY 2029: 87000
HS-2410A | Highway | Safety | SR 1790 (Winecoff School Road) | Winecoff Elementary School in Concord | Install pedestrian accommodations. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | T(M) | CONSTRUCTION | 10000 | FY 2029: 10000
HS-2410B | Highway | Safety | SR 3300 (7th Street) | Bascom Street / Cameron Avenue in Charlotte | Install traffic signal with pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 22000 | FY 2026: 22000
HS-2410B | Highway | Safety | SR 3300 (7th Street) | Bascom Street / Cameron Avenue in Charlotte | Install traffic signal with pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | RIGHT-OF-WAY | 2000 | FY 2026: 2000
HS-2410B | Highway | Safety | SR 3300 (7th Street) | Bascom Street / Cameron Avenue in Charlotte | Install traffic signal with pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 210000 | FY 2028: 210000
HS-2410B | Highway | Safety | SR 3300 (7th Street) | Bascom Street / Cameron Avenue in Charlotte | Install traffic signal with pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | CONSTRUCTION | 23000 | FY 2028: 23000
HS-2410C | Highway | Safety | SR 3624 (Rea Road) | Piper Glen Drive and Bevington Place intersections in Charlotte | Upgrade the traffic signals and install pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2410C | Highway | Safety | SR 3624 (Rea Road) | Piper Glen Drive and Bevington Place intersections in Charlotte | Upgrade the traffic signals and install pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | RIGHT-OF-WAY | 0 | FY 2026: 0
HS-2410C | Highway | Safety | SR 3624 (Rea Road) | Piper Glen Drive and Bevington Place intersections in Charlotte | Upgrade the traffic signals and install pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 285000 | FY 2028: 285000
HS-2410C | Highway | Safety | SR 3624 (Rea Road) | Piper Glen Drive and Bevington Place intersections in Charlotte | Upgrade the traffic signals and install pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | CONSTRUCTION | 32000 | FY 2028: 32000
HS-2410D | Highway | Safety | US 29 (Concord Parkway) | SR 2894 (Bruton Smith Boulevard) intersection in Concord | Install pedestrian signal upgrades. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | CONSTRUCTION | 26000
HS-2410D | Highway | Safety | US 29 (Concord Parkway) | SR 2894 (Bruton Smith Boulevard) intersection in Concord | Install pedestrian signal upgrades. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Region E |  | T(M) | CONSTRUCTION | 3000
HS-2410E | Highway | Safety | SR 3687 (Park Road) | Jim Hynes Circle intersection in Charlotte. | Install pedestrian signal. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 50000 | FY 2026: 18000
HS-2410E | Highway | Safety | SR 3687 (Park Road) | Jim Hynes Circle intersection in Charlotte. | Install pedestrian signal. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 2000
HS-2410G | Highway | Safety | SR 2935 (The Plaza) | Cove Creek Drive intersection in Charlotte | Construct directional crossover. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 513000
HS-2410H | Highway | Safety | NC 51 | Palomino Drive / Hoods Village Drive intersection in Mint Hill | Construct directional crossover. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 260000 | FY 2026: 260000
HS-2410H | Highway | Safety | NC 51 | Palomino Drive / Hoods Village Drive intersection in Mint Hill | Construct directional crossover. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | UTILITIES | 15000 | FY 2026: 15000
HS-2410H | Highway | Safety | NC 51 | Palomino Drive / Hoods Village Drive intersection in Mint Hill | Construct directional crossover. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 848000 | FY 2028: 848000
HS-2410I | Highway | Safety | NC 73 | SR 1425 (Nelson Mountain Road) / SR 1243 (Cane Drive) intersection near Albemarle | Re-align intersection and construct turn lanes. |  | Stanly | 10 | Rocky River RPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 125000 | FY 2026: 125000
HS-2410I | Highway | Safety | NC 73 | SR 1425 (Nelson Mountain Road) / SR 1243 (Cane Drive) intersection near Albemarle | Re-align intersection and construct turn lanes. |  | Stanly | 10 | Rocky River RPO |  | Region E |  | HSIP | UTILITIES | 65000 | FY 2026: 65000
HS-2410I | Highway | Safety | NC 73 | SR 1425 (Nelson Mountain Road) / SR 1243 (Cane Drive) intersection near Albemarle | Re-align intersection and construct turn lanes. |  | Stanly | 10 | Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 912000 | FY 2028: 912000
HS-2410J | Highway | Safety | NC 51 (Matthews Township Parkway) | Fullwood Lane intersection in Matthews | Construct pedestrian improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 15000 | FY 2026: 15000
HS-2410J | Highway | Safety | NC 51 (Matthews Township Parkway) | Fullwood Lane intersection in Matthews | Construct pedestrian improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2410J | Highway | Safety | NC 51 (Matthews Township Parkway) | Fullwood Lane intersection in Matthews | Construct pedestrian improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 277000 | FY 2027: 277000
HS-2410K | Highway | Safety | SR 3448 (Pleasant Plains Road) | Squirrel Lake Park entrance intersection in Matthews. | Construct sidewalks and install pedestrian improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | UTILITIES | 10000 | FY 2026: 10000
HS-2410K | Highway | Safety | SR 3448 (Pleasant Plains Road) | Squirrel Lake Park entrance intersection in Matthews. | Construct sidewalks and install pedestrian improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 101000 | FY 2026: 101000
HS-2410L | Highway | Safety | Various | Various locations. | Install signal at various location on secondary routes. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 1153000 | FY 2026: 1153000
HS-2410M | Highway | Safety | SR 1313 (Joe Kerr Road) | SR 3486 (Wheatfield Drive) intersection in Marvin. | Install pedestrian signs and crosswalk. |  | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | ENGINEERING | 30000
HS-2410M | Highway | Safety | SR 1313 (Joe Kerr Road) | SR 3486 (Wheatfield Drive) intersection in Marvin. | Install pedestrian signs and crosswalk. |  | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | UTILITIES | 10000
HS-2410M | Highway | Safety | SR 1313 (Joe Kerr Road) | SR 3486 (Wheatfield Drive) intersection in Marvin. | Install pedestrian signs and crosswalk. |  | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 90000 | FY 2026: 90000
HS-2410N | Highway | Safety | SR 3468 (Weddington Road) | Vicinity of Socrates Academy | Construct pedestrian improvements. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 10000
HS-2410N | Highway | Safety | SR 3468 (Weddington Road) | Vicinity of Socrates Academy | Construct pedestrian improvements. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | UTILITIES | 5000
HS-2410N | Highway | Safety | SR 3468 (Weddington Road) | Vicinity of Socrates Academy | Construct pedestrian improvements. | 0.1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 115000 | FY 2026: 115000
HS-2410O | Highway | Safety | NC 16 (Providence Road) | High Ridge Drive/Greyson Ridge Drive. | Install pedestrian signals and upgrade pedestrian accommodations. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 116000 | FY 2026: 116000
HS-2410P | Highway | Safety | NC 49 (University City Boulevard) | Oak Leigh Drive intersection in Charlotte. | Install a directional crossover with a half signal for lefts onto Oak Leigh Drive. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 1000 | FY 2027: 1000
HS-2410P | Highway | Safety | NC 49 (University City Boulevard) | Oak Leigh Drive intersection in Charlotte. | Install a directional crossover with a half signal for lefts onto Oak Leigh Drive. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | UTILITIES | 1000 | FY 2028: 1000
HS-2410P | Highway | Safety | NC 49 (University City Boulevard) | Oak Leigh Drive intersection in Charlotte. | Install a directional crossover with a half signal for lefts onto Oak Leigh Drive. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 983000 | FY 2029: 983000
HS-2411 | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2411A | Highway | Safety | SR 1143 (New Browns Ford Road) | Bridge 960093 over Yadkin River. | Install guardrail. |  | Wilkes | 11 | High Country RPO |  | Division 11 |  | HSIP | CONSTRUCTION | 76000
HS-2411B | Highway | Safety | I-77 | Various locations. | Upgrade guardrail end units. |  | Yadkin, Surry | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 152000
HS-2411C | Highway | Safety | US 421 | SR 1301 (Fall Creek Road) to East of SR 1461 (Old US Hwy 421), including ramps to US 421/US 221. | Install 6-inch rumble strips, thermo long life pavement markings, and three CCTV cameras. |  | Watauga, Wilkes | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 600000
HS-2411D | Highway | Safety | US 321 | SR 1370 (Kirby Mountain Road) to Green Hill Road. | Install rumble strips and pavement markings. |  | Caldwell | 11 | Greater Hickory MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 562000 | FY 2026: 562000
HS-2411D | Highway | Safety | US 321 | SR 1370 (Kirby Mountain Road) to Green Hill Road. | Install rumble strips and pavement markings. |  | Caldwell | 11 | Greater Hickory MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2411E | Highway | Safety | US 221/ 421 | US 221/421 AND SR 1655 (LANDFILL ROAD) INTERSECTION AND ON INNOVATION DRIVE. | INSTALL REDUCED CONFLICT INTERSECTION RIGHT IN/ RIGHT OUT ONLY AND IMPROVEMENTS TO ADJACENT ROADWAY (INNOVATION DRIVE) FOR REDIRECTED TRAFFIC. |  | Watauga | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 100000
HS-2411E | Highway | Safety | US 221/ 421 | US 221/421 AND SR 1655 (LANDFILL ROAD) INTERSECTION AND ON INNOVATION DRIVE. | INSTALL REDUCED CONFLICT INTERSECTION RIGHT IN/ RIGHT OUT ONLY AND IMPROVEMENTS TO ADJACENT ROADWAY (INNOVATION DRIVE) FOR REDIRECTED TRAFFIC. |  | Watauga | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 150000
HS-2411E | Highway | Safety | US 221/ 421 | US 221/421 AND SR 1655 (LANDFILL ROAD) INTERSECTION AND ON INNOVATION DRIVE. | INSTALL REDUCED CONFLICT INTERSECTION RIGHT IN/ RIGHT OUT ONLY AND IMPROVEMENTS TO ADJACENT ROADWAY (INNOVATION DRIVE) FOR REDIRECTED TRAFFIC. |  | Watauga | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 900000 | FY 2026: 900000
HS-2411E | Highway | Safety | US 221/ 421 | US 221/421 AND SR 1655 (LANDFILL ROAD) INTERSECTION AND ON INNOVATION DRIVE. | INSTALL REDUCED CONFLICT INTERSECTION RIGHT IN/ RIGHT OUT ONLY AND IMPROVEMENTS TO ADJACENT ROADWAY (INNOVATION DRIVE) FOR REDIRECTED TRAFFIC. |  | Watauga | 11 | High Country RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 100000 | FY 2026: 100000
HS-2411F | Highway | Safety | US 221; US 421 | Mile Marker 0.4 in Ashe County, Mile Marker 18.3 in Watauga County; Mile Marker 30.1 in Wilkes County. | Install Dynamic Message Signs. |  | Wilkes, Ashe, Watauga | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 27000 | FY 2026: 27000
HS-2411F | Highway | Safety | US 221; US 421 | Mile Marker 0.4 in Ashe County, Mile Marker 18.3 in Watauga County; Mile Marker 30.1 in Wilkes County. | Install Dynamic Message Signs. |  | Wilkes, Ashe, Watauga | 11 | High Country RPO |  | Statewide Mobility |  | T(M) | UTILITIES | 3000 | FY 2026: 3000
HS-2411F | Highway | Safety | US 221; US 421 | Mile Marker 0.4 in Ashe County, Mile Marker 18.3 in Watauga County; Mile Marker 30.1 in Wilkes County. | Install Dynamic Message Signs. |  | Wilkes, Ashe, Watauga | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 580000 | FY 2026: 580000
HS-2411F | Highway | Safety | US 221; US 421 | Mile Marker 0.4 in Ashe County, Mile Marker 18.3 in Watauga County; Mile Marker 30.1 in Wilkes County. | Install Dynamic Message Signs. |  | Wilkes, Ashe, Watauga | 11 | High Country RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 65000 | FY 2026: 65000
HS-2411G | Highway | Safety | US 421 | SR 2325 (Red White & Blue Road/Mathis Farm Road). | Install Open Graded Friction Course. |  | Wilkes | 11 | High Country RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 346000 | FY 2026: 346000
HS-2411G | Highway | Safety | US 421 | SR 2325 (Red White & Blue Road/Mathis Farm Road). | Install Open Graded Friction Course. |  | Wilkes | 11 | High Country RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 39000 | FY 2026: 39000
HS-2412 | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2412A | Highway | Safety | NC 10 | Mile Marker 7.7 to Mile Marker 15.4 | Install rumble strips. | 7.7 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 305000 | FY 2026: 305000
HS-2412B | Highway | Safety | NC 150 | North of SR 2068 (Troy Road) to SR 1651 (Delview Road) | Install rumble strips with six inch long life pavement markings. | 7.3 | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 389000 | FY 2026: 389000
HS-2413 | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2413A | Highway | Safety | US 64 / NC 18; US 64 / US 74 | SR 1008 (Bills Creek Road) to Rutherfordton western municipal limit | Install long life pavement markings. | 17.46 | Rutherford, Burke | 13 | Foothills RPO, Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 608000 | FY 2026: 608000
HS-2413A | Highway | Safety | US 64 / NC 18; US 64 / US 74 | SR 1008 (Bills Creek Road) to Rutherfordton western municipal limit | Install long life pavement markings. | 17.46 | Rutherford, Burke | 13 | Foothills RPO, Greater Hickory MPO |  | Region G |  | T(M) | CONSTRUCTION | 68000 | FY 2026: 68000
HS-2413B | Highway | Safety | US 64 | Rutherfordton Northeast Municipal Limit to Morganton Southwest Municipal Limit | Install long life pavement markings. | 28.03 | Rutherford, Burke, McDowell | 13 | Foothills RPO, Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 686000 | FY 2026: 686000
HS-2413B | Highway | Safety | US 64 | Rutherfordton Northeast Municipal Limit to Morganton Southwest Municipal Limit | Install long life pavement markings. | 28.03 | Rutherford, Burke, McDowell | 13 | Foothills RPO, Greater Hickory MPO |  | Region G |  | T(M) | CONSTRUCTION | 76000 | FY 2026: 76000
HS-2413C | Highway | Safety | US 221 | US 221 Business to north of NC 226 near Marion. | Install rumble stripes and 6" long life pavement markings. |  | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 400000 | FY 2026: 400000
HS-2413C | Highway | Safety | US 221 | US 221 Business to north of NC 226 near Marion. | Install rumble stripes and 6" long life pavement markings. |  | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 44000 | FY 2026: 44000
HS-2413D | Highway | Safety | US 70 | Mile marker 7.0 to mile marker 15.0 and mile marker 20.0 to mile marker 27.0 near Marion. | Install rumble stripes and 6" long life pavement markings. |  | McDowell | 13 | Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 540000 | FY 2026: 540000
HS-2413D | Highway | Safety | US 70 | Mile marker 7.0 to mile marker 15.0 and mile marker 20.0 to mile marker 27.0 near Marion. | Install rumble stripes and 6" long life pavement markings. |  | McDowell | 13 | Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 60000 | FY 2026: 60000
HS-2413E | Highway | Safety | US 70 | Various locations | Install rumble stripes and 6" long life pavement markings. |  | Burke | 13 | Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 207000 | FY 2026: 207000
HS-2413E | Highway | Safety | US 70 | Various locations | Install rumble stripes and 6" long life pavement markings. |  | Burke | 13 | Greater Hickory MPO |  | Region G |  | T(M) | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2413F | Highway | Safety | NC 226 | Various locations in Bakersville and Spruce Pine | Install rumble stripes and 6" long life pavement markings. |  | Mitchell | 13 | High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 315000 | FY 2026: 315000
HS-2413F | Highway | Safety | NC 226 | Various locations in Bakersville and Spruce Pine | Install rumble stripes and 6" long life pavement markings. |  | Mitchell | 13 | High Country RPO |  | Region G |  | T(M) | CONSTRUCTION | 30000 | FY 2026: 30000
HS-2413G | Highway | Safety | SR 3136 (Cane Creek Road) | SR 3116 (Mills Gap Road) to US 74 Alternate near Fairview | Install rumble stripes and long life pavement markings. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 270000 | FY 2026: 270000
HS-2413G | Highway | Safety | SR 3136 (Cane Creek Road) | SR 3116 (Mills Gap Road) to US 74 Alternate near Fairview | Install rumble stripes and long life pavement markings. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | T(M) | CONSTRUCTION | 24000 | FY 2026: 24000
HS-2413H | Highway | Safety | Various | Primary and secondary routes in Division 13 | Install horizontal alignment warning signs. |  | Burke | 13 | Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 394000 | FY 2026: 394000
HS-2413H | Highway | Safety | Various | Primary and secondary routes in Division 13 | Install horizontal alignment warning signs. |  | Burke | 13 | Greater Hickory MPO |  | Region G |  | T(M) | CONSTRUCTION | 44000 | FY 2026: 44000
HS-2413I | Highway | Safety | SR 1002 (Old Leicester Highway) | NC 63 to SR 1607 (Bear Creek Road) near Leicester | Install guardrail. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 267000 | FY 2026: 267000
HS-2413J | Highway | Safety | SR 1727 (Monticello Road) | SR 1882 (New Stock Road) to east of NC 251 (Old Marshall Highway) | Install guardrail. |  | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 300000 | FY 2026: 300000
HS-2413K | Highway | Safety | US 19 / US 23 / US 74 ALT (Smokey Park Highway) | I-40 to Cooper Boulevard | Install pedestrian signals and crosswalks, and construct sidewalks. | 26.2 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | UTILITIES | 25000
HS-2413K | Highway | Safety | US 19 / US 23 / US 74 ALT (Smokey Park Highway) | I-40 to Cooper Boulevard | Install pedestrian signals and crosswalks, and construct sidewalks. | 26.2 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 905000
HS-2413L | Highway | Safety | I-40 | Buncombe County Line to Burke County Line. | Upgrade guardrail end units. |  | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 285000 | FY 2026: 25000
HS-2413M | Highway | Safety | US 221 | Rutherford County Line to Avery County Line. | Upgrade guardrail end units. |  | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 645000 | FY 2026: 645000
HS-2413N | Highway | Safety | US 70 / US 74 ALT (College Street);US 70 / US 74 ALT (Tunnel Road) | SR 3284 (Charlotte Street); Kenilworth Road/Kenilworth Knolls | Construct pedestrian improvements. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | UTILITIES | 95000 | FY 2027: 95000
HS-2413N | Highway | Safety | US 70 / US 74 ALT (College Street);US 70 / US 74 ALT (Tunnel Road) | SR 3284 (Charlotte Street); Kenilworth Road/Kenilworth Knolls | Construct pedestrian improvements. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Region G |  | T(M) | UTILITIES | 10000 | FY 2027: 10000
HS-2413N | Highway | Safety | US 70 / US 74 ALT (College Street);US 70 / US 74 ALT (Tunnel Road) | SR 3284 (Charlotte Street); Kenilworth Road/Kenilworth Knolls | Construct pedestrian improvements. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 158000 | FY 2027: 158000
HS-2413N | Highway | Safety | US 70 / US 74 ALT (College Street);US 70 / US 74 ALT (Tunnel Road) | SR 3284 (Charlotte Street); Kenilworth Road/Kenilworth Knolls | Construct pedestrian improvements. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 17000 | FY 2027: 17000
HS-2413O | Highway | Safety | SR 2435 (Old US 70 Highway) | Woolwine Drive to the bus entrance at Owen Middle School | Construct pedestrian improvements. | 0.2 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 50000 | FY 2027: 50000
HS-2413O | Highway | Safety | SR 2435 (Old US 70 Highway) | Woolwine Drive to the bus entrance at Owen Middle School | Construct pedestrian improvements. | 0.2 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | UTILITIES | 1000 | FY 2027: 1000
HS-2413O | Highway | Safety | SR 2435 (Old US 70 Highway) | Woolwine Drive to the bus entrance at Owen Middle School | Construct pedestrian improvements. | 0.2 | Buncombe | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 378000 | FY 2028: 378000
HS-2413P | Highway | Safety | Primary and secondary routes | Various locations in Division 13 | Construct pedestrian improvements. | 20 | McDowell, Mitchell | 13 | Foothills RPO, High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 373000 | FY 2026: 373000
HS-2413Q | Highway | Safety | SR 1786 (Miller Bridge Road) | NC 18 and SR 1761 (Old NC Highway 10) | Install rumble stripes with 6-inch long life pavement markings. | 5.9 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 135000 | FY 2026: 135000
HS-2413R | Highway | Safety | Various | Various locations in Division 13 | Install horizontal alignment warning signs. | 0.1 | Buncombe, Madison, Rutherford | 13 | French Broad River MPO, Land-of-Sky RPO, Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 939000 | FY 2026: 939000
HS-2413S | Highway | Safety | NC 191 | Blue Ridge Parkway in Buncombe County to NC 280 in Henderson County. | Install rumble stripes with long life pavement markings. | 7.3 | Buncombe, Henderson | 13, 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 135000 | FY 2027: 135000
HS-2413S | Highway | Safety | NC 191 | Blue Ridge Parkway in Buncombe County to NC 280 in Henderson County. | Install rumble stripes with long life pavement markings. | 7.3 | Buncombe, Henderson | 13, 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 15000 | FY 2027: 15000
HS-2413T | Highway | Safety | SR 3116 (Mills Gap Road) | SR 3157 (Weston Road) and SR 3136 (Cane Creek Road). | Install rumble stripes with long life pavement markings. | 2.3 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 46000 | FY 2027: 46000
HS-2413T | Highway | Safety | SR 3116 (Mills Gap Road) | SR 3157 (Weston Road) and SR 3136 (Cane Creek Road). | Install rumble stripes with long life pavement markings. | 2.3 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | T(M) | CONSTRUCTION | 5000 | FY 2027: 5000
HS-2413U | Highway | Safety | SR 1006 (Bostic Sunshine Highway) | North of Bostic municipal limit to NC 226. | Install rumble stripes with long life pavement markings. | 11.7 | Rutherford | 13 | Foothills RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 237000 | FY 2026: 237000
HS-2413V | Highway | Safety | NC 181 | SR 1414 (St Marys Church Road) and NC 183. | Install rumble stripes with long life pavement markings. | 24.6 | Burke | 13 | Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 550000 | FY 2026: 550000
HS-2413W | Highway | Safety | SR 1781 (Broadway Street) | N. Lexington Avenue/I-240 westbound on-ramp in Asheville. | Install pedestrian signals and upgrade curb ramps. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 74000 | FY 2026: 74000
HS-2413X | Highway | Safety | SR 3556 (Amboy Road) | Short Michigan Avenue intersection in Asheville. | Install Rectangular Rapid Flashing Beacon (RRFB) with crosswalk lighting, and upgrade curb ramps and sidewalk. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | UTILITIES | 25000 | FY 2026: 25000
HS-2413X | Highway | Safety | SR 3556 (Amboy Road) | Short Michigan Avenue intersection in Asheville. | Install Rectangular Rapid Flashing Beacon (RRFB) with crosswalk lighting, and upgrade curb ramps and sidewalk. | 0.1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 29000 | FY 2026: 29000
HS-2414 | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2414A | Highway | Safety | US 19 / US 74 | Nantahala Outdoors Center / Appalachian Trail near SR 1103 (Silvermine Road) near Wesser | Install pedestrian rectangular rapid flashing beacons. | 0.5 | Swain | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 43000
HS-2414A | Highway | Safety | US 19 / US 74 | Nantahala Outdoors Center / Appalachian Trail near SR 1103 (Silvermine Road) near Wesser | Install pedestrian rectangular rapid flashing beacons. | 0.5 | Swain | 14 | Southwestern RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5000
HS-2414B | Highway | Safety | US 19 Business | SR 1424 (Connahetta Street) and Maple Street intersections | Install pedestrian rectangular rapid flashing beacons. | 0.5 | Cherokee | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 68000
HS-2414B | Highway | Safety | US 19 Business | SR 1424 (Connahetta Street) and Maple Street intersections | Install pedestrian rectangular rapid flashing beacons. | 0.5 | Cherokee | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 8000
HS-2414C | Highway | Safety | US 64 (6th Avenue West) | North Oak Street intersection in Hendersonville | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Henderson | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 59000 | FY 2026: 14000
HS-2414C | Highway | Safety | US 64 (6th Avenue West) | North Oak Street intersection in Hendersonville | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Henderson | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 1000
HS-2414D | Highway | Safety | SR 1668 (Fulton Road) | US 64 to SR 1667 (Wells Grove Road) near Franklin | Install guardrail. |  | Macon | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 171000
HS-2414D | Highway | Safety | SR 1668 (Fulton Road) | US 64 to SR 1667 (Wells Grove Road) near Franklin | Install guardrail. |  | Macon | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 19000
HS-2414E | Highway | Safety | SR 1372 (Lower Burningtown Road) | SR 1474 (Saldeer Mountain Road) to SR 1392 (Middle Burningtown Road) near Franklin | Install guardrail. |  | Macon | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 337000
HS-2414E | Highway | Safety | SR 1372 (Lower Burningtown Road) | SR 1474 (Saldeer Mountain Road) to SR 1392 (Middle Burningtown Road) near Franklin | Install guardrail. |  | Macon | 14 | Southwestern RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 38000
HS-2414F | Highway | Safety | NC 191 (Haywood Road) | Ridgewood Boulevard / Whitmire Street intersection in Hendersonville | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Henderson | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 59000 | FY 2026: 20000
HS-2414F | Highway | Safety | NC 191 (Haywood Road) | Ridgewood Boulevard / Whitmire Street intersection in Hendersonville | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Henderson | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 6000 | FY 2026: 2000
HS-2414G | Highway | Safety | SR 1512 (Ecusta Road) | Ecusta Bypass intersection in Brevard | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Transylvania | 14 | Land-of-Sky RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 31000
HS-2414G | Highway | Safety | SR 1512 (Ecusta Road) | Ecusta Bypass intersection in Brevard | Install rectangular rapid flashing beacon and actuated crosswalk lighting. |  | Transylvania | 14 | Land-of-Sky RPO |  | Division 14 |  | T(M) | CONSTRUCTION | 4000
HS-2414H | Highway | Safety | US 64 | Mile marker 5.0 to mile marker 13.0 and mile marker 25.0 to mile marker 31.0 near Brevard | Install rumble stripes with 6" long life pavement markings. |  | Transylvania | 14 | Land-of-Sky RPO |  | Region G |  | HSIP | CONSTRUCTION | 522000
HS-2414H | Highway | Safety | US 64 | Mile marker 5.0 to mile marker 13.0 and mile marker 25.0 to mile marker 31.0 near Brevard | Install rumble stripes with 6" long life pavement markings. |  | Transylvania | 14 | Land-of-Sky RPO |  | Region G |  | T(M) | CONSTRUCTION | 58000
HS-2414I | Highway | Safety | I-26; US 74; US 25 | Various locations. | Upgrade guardrail end units. |  | Henderson, Polk | 14 | French Broad River MPO, Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 315000 | FY 2026: 315000
HS-2414I | Highway | Safety | I-26; US 74; US 25 | Various locations. | Upgrade guardrail end units. |  | Henderson, Polk | 14 | French Broad River MPO, Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 35000 | FY 2026: 35000
HS-2414J | Highway | Safety | US 441; US 19 | Various locations. | Upgrade guardrail end units. |  | Jackson, Swain | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 99000
HS-2414J | Highway | Safety | US 441; US 19 | Various locations. | Upgrade guardrail end units. |  | Jackson, Swain | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 11000
HS-2414K | Highway | Safety | US 19; US 23; US 64 | Various locations. | Upgrade guardrail end units. |  | Macon | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 765000
HS-2414K | Highway | Safety | US 19; US 23; US 64 | Various locations. | Upgrade guardrail end units. |  | Macon | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 85000
HS-2414L | Highway | Safety | US 19 | Various locations. | Upgrade guardrail end units. |  | Cherokee | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 117000
HS-2414L | Highway | Safety | US 19 | Various locations. | Upgrade guardrail end units. |  | Cherokee | 14 | Southwestern RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 13000
HS-2414M | Highway | Safety | US 64 | Various locations. | Upgrade guardrail end units. |  | Clay | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 675000
HS-2414M | Highway | Safety | US 64 | Various locations. | Upgrade guardrail end units. |  | Clay | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 75000
HS-2414N | Highway | Safety | US 23 / US 441 | SR 1320 (Greens Creek Road). | Install a Directional Leftover with one bulb-out (RCI). |  | Jackson | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 873000 | FY 2026: 873000
HS-2414N | Highway | Safety | US 23 / US 441 | SR 1320 (Greens Creek Road). | Install a Directional Leftover with one bulb-out (RCI). |  | Jackson | 14 | Southwestern RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 97000 | FY 2026: 97000
HS-2414O | Highway | Safety | US 64 (Rosman Highway) | Estatoe Trail Greenway Crossing near SR 1347 (Carolina Ave) (0.17 mile northeast of SR 1347 (Carolina Ave)). | Install a pedestrian hybrid beacon. |  | Transylvania | 14 | Land-of-Sky RPO |  | Region G |  | HSIP | CONSTRUCTION | 153000
HS-2414O | Highway | Safety | US 64 (Rosman Highway) | Estatoe Trail Greenway Crossing near SR 1347 (Carolina Ave) (0.17 mile northeast of SR 1347 (Carolina Ave)). | Install a pedestrian hybrid beacon. |  | Transylvania | 14 | Land-of-Sky RPO |  | Region G |  | T(M) | CONSTRUCTION | 17000
HS-2414P | Highway | Safety | I-40 | Mile marker 9.5 | Install LED chevrons and flatten shoulder. | 0.1 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 532000 | FY 2026: 532000
HS-2414P | Highway | Safety | I-40 | Mile marker 9.5 | Install LED chevrons and flatten shoulder. | 0.1 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 59000 | FY 2026: 59000
HS-2414Q | Highway | Safety | Various | Two lane primary and secondary routes. | Install long life pavement markings. |  | Haywood, Macon, Jackson, Transylvania, Swain | 14 | Southwestern RPO, Land-of-Sky RPO |  | Region G |  | HSIP | CONSTRUCTION | 2700000 | FY 2026: 2700000
HS-2414Q | Highway | Safety | Various | Two lane primary and secondary routes. | Install long life pavement markings. |  | Haywood, Macon, Jackson, Transylvania, Swain | 14 | Southwestern RPO, Land-of-Sky RPO |  | Region G |  | T(M) | CONSTRUCTION | 300000 | FY 2026: 300000
HS-2414R | Highway | Safety | SR 1793 (Tracy Grove Road) | SR 1525 (Dana Road) to SR 1006 (Howard Gap Road) | Install rumble stripes with 6" long life pavement markings. | 3.07 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | HSIP | CONSTRUCTION | 103000 | FY 2026: 103000
HS-2414R | Highway | Safety | SR 1793 (Tracy Grove Road) | SR 1525 (Dana Road) to SR 1006 (Howard Gap Road) | Install rumble stripes with 6" long life pavement markings. | 3.07 | Henderson | 14 | French Broad River MPO |  | Division 14 |  | T(M) | CONSTRUCTION | 12000 | FY 2026: 12000
HS-2414S | Highway | Safety | Various | US, NC, and SR routes. | Install curve warning signs on multiple routes. |  | Graham, Clay, Cherokee | 14 | Southwestern RPO, Land-of-Sky RPO, Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 1417000 | FY 2026: 1417000
HS-2414S | Highway | Safety | Various | US, NC, and SR routes. | Install curve warning signs on multiple routes. |  | Graham, Clay, Cherokee | 14 | Southwestern RPO, Land-of-Sky RPO, Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 158000 | FY 2026: 158000
HS-2414T | Highway | Safety | US 276 | Near Laurel Brook Drive to the Waynesville city limit. | Install rumble stripes with long life pavement markings. | 15.3 | Haywood | 14 | Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 396000 | FY 2026: 396000
HS-2414T | Highway | Safety | US 276 | Near Laurel Brook Drive to the Waynesville city limit. | Install rumble stripes with long life pavement markings. | 15.3 | Haywood | 14 | Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 44000 | FY 2026: 44000
HS-2414U | Highway | Safety | US 19/US 23 (Carolina Boulevard) | Waitsel Way (Midway Medical Center). | Install directional left over with bulb-out. | 0.1 | Haywood | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 414000 | FY 2027: 414000
HS-2414U | Highway | Safety | US 19/US 23 (Carolina Boulevard) | Waitsel Way (Midway Medical Center). | Install directional left over with bulb-out. | 0.1 | Haywood | 14 | French Broad River MPO |  | Region G |  | T(M) | CONSTRUCTION | 46000 | FY 2027: 46000
HS-2420 | Highway | Safety | Various | Locations statewide. | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project
HS-2420DIV | Highway | Safety | Various | Locations statewide. Division Needs funding. | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 30600000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000
HS-2420REG | Highway | Safety | Various | Locations statewide. Regional Impact funding. | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 30600000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000 | 2550000
HS-2420SW | Highway | Safety | Various | Locations statewide. Statewide Mobility funding. | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 40800000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000
HS-2421 | Highway | Safety | Various | Locations statewide. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Statewide | 99 | Statewide Project
HS-2421DIV | Highway | Safety | Various | Locations statewide. Division Needs funding. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 51000000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000
HS-2421REG | Highway | Safety | Various | Locations statewide. Regional Impact funding. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 51000000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000
HS-2421SW | Highway | Safety | Various | Locations statewide. Statewide Mobility funding. | Funding for safety management program, project identification, analysis and preliminary engineering. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 68000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
HS-2422 | Highway | Safety | Various | Locations statewide. | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project
HS-2422DIV | Highway | Safety | Various | Locations statewide. Division Needs funding. | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 18000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
HS-2422REG | Highway | Safety | Various | Locations statewide. Regional Impact funding. | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 21500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 5000000 | 1500000 | 1500000 | 1500000 | 1500000
HS-2422SW | Highway | Safety | Various | Locations statewide. Statewide Mobility funding. | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 24000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
HS-2601 | Highway | Safety | Various | Various locations in Division 1 | Safety Improvements. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2602 | Highway | Safety | Various | Various locations in Division 2 | Safety Improvements. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2603 | Highway | Safety | Various | Various locations in Division 3 | Safety Improvements. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2604 | Highway | Safety | Various | Various locations in Division 4 | Safety Improvements. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2605 | Highway | Safety | Various | Various locations in Division 5 | Safety Improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2606 | Highway | Safety | Various | Various locations in Division 6 | Safety Improvements. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2607 | Highway | Safety | Various | Various locations in Division 7 | Safety Improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2608 | Highway | Safety | Various | Various locations in Division 8 | Safety Improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Triangle West TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2609 | Highway | Safety | Various | Various locations in Division 9 | Safety Improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2610 | Highway | Safety | Various | Various locations in Division 10 | Safety Improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2610A | Highway | Safety | US 52 | SR 1414 (Morton Street) to north of SR 1486 | Install rumble stripes with long life pavement markings. | 8.3 | Stanly | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 318000 | FY 2027: 318000
HS-2610A | Highway | Safety | US 52 | SR 1414 (Morton Street) to north of SR 1486 | Install rumble stripes with long life pavement markings. | 8.3 | Stanly | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 35000 | FY 2027: 35000
HS-2610B | Highway | Safety | SR 1003 (White Store Road) | Anson County line to US 601 | Install rumble stripes with long life pavement markings. | 12.6 | Union | 10 | Rocky River RPO |  | Division 10 |  | HSIP | CONSTRUCTION | 375000 | FY 2027: 375000
HS-2610B | Highway | Safety | SR 1003 (White Store Road) | Anson County line to US 601 | Install rumble stripes with long life pavement markings. | 12.6 | Union | 10 | Rocky River RPO |  | Division 10 |  | T(M) | CONSTRUCTION | 42000 | FY 2027: 42000
HS-2610I | Highway | Safety | SR 1901 (Hasty Road); SR 1238 (Hasty Road) | East of SR 1740 (Old Hwy 74) to Anson County line; Union County line to SR 1252 (Lower White Store Road). | Install rumble stripes with long life pavement markings. | 7 | Union, Anson | 10 | Rocky River RPO |  | Division 10 |  | HSIP | CONSTRUCTION | 133000 | FY 2027: 133000
HS-2610I | Highway | Safety | SR 1901 (Hasty Road); SR 1238 (Hasty Road) | East of SR 1740 (Old Hwy 74) to Anson County line; Union County line to SR 1252 (Lower White Store Road). | Install rumble stripes with long life pavement markings. | 7 | Union, Anson | 10 | Rocky River RPO |  | Division 10 |  | T(M) | CONSTRUCTION | 15000 | FY 2027: 15000
HS-2610J | Highway | Safety | US 74 | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2027: 45000
HS-2610J | Highway | Safety | US 74 | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 5000 | FY 2027: 5000
HS-2610J | Highway | Safety | US 74 | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 45000 | FY 2027: 45000
HS-2610J | Highway | Safety | US 74 | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | UTILITIES | 5000 | FY 2027: 5000
HS-2610J | Highway | Safety | US 74 | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 765000 | FY 2028: 765000
HS-2610J | Highway | Safety | US 74 | SR 1251 (Horne Town Road) / SR 1469 (Freedom Road) | Install directional leftover and close existing crossover just west of intersection of US 74 and SR 1251 (Horne Town Road) / SR 1469 (Freedom Road). | 0.1 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 85000 | FY 2028: 85000
HS-2610K | Highway | Safety | SR 1365 (Stallings Road) | Vicinity of Stallings Municipal Park | Install a Rectangular Rapid Flashing Beacon (RRFB) at the existing crosswalk and add yield bar pavement markings. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 45000 | FY 2026: 45000
HS-2610K | Highway | Safety | SR 1365 (Stallings Road) | Vicinity of Stallings Municipal Park | Install a Rectangular Rapid Flashing Beacon (RRFB) at the existing crosswalk and add yield bar pavement markings. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | CONSTRUCTION | 5000 | FY 2026: 5000
HS-2610L | Highway | Safety | SR 3286 (Tom Short Road) | SR 2968 (Carisbrooke Drive) intersection in Charlotte | Install a Rectangular Rapid Flashing Beacon (RRFB) at the existing crosswalk and add yield bar pavement markings. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 45000 | FY 2026: 45000
HS-2610L | Highway | Safety | SR 3286 (Tom Short Road) | SR 2968 (Carisbrooke Drive) intersection in Charlotte | Install a Rectangular Rapid Flashing Beacon (RRFB) at the existing crosswalk and add yield bar pavement markings. | 0.1 | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | T(M) | CONSTRUCTION | 5000 | FY 2026: 5000
HS-2610U | Highway | Safety | US 52 | NC 742 to Ansonville town limits | Install rumble stripes with long life pavement markings. | 8.2 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 218000 | FY 2026: 218000
HS-2610U | Highway | Safety | US 52 | NC 742 to Ansonville town limits | Install rumble stripes with long life pavement markings. | 8.2 | Anson | 10 | Rocky River RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 24000 | FY 2026: 24000
HS-2610V | Highway | Safety | SR 1110 (Mayesville Road) | NC 742 to South Carolina state line | Install rumble stripes with long life pavement markings. | 4.6 | Anson | 10 | Rocky River RPO |  | Division 10 |  | HSIP | CONSTRUCTION | 23000 | FY 2027: 23000
HS-2610V | Highway | Safety | SR 1110 (Mayesville Road) | NC 742 to South Carolina state line | Install rumble stripes with long life pavement markings. | 4.6 | Anson | 10 | Rocky River RPO |  | Division 10 |  | T(M) | CONSTRUCTION | 3000 | FY 2027: 3000
HS-2611 | Highway | Safety | Various | Various locations in Division 11. | Safety Improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2612 | Highway | Safety | Various | Various locations in Division 12. | Safety Improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2612D | Highway | Safety | SR 1005 (Old Mountain Road) | Alexander County line to south of SR 1498 (Southwood Drive) | Install rumble strips. | 12.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | HSIP | CONSTRUCTION | 399000 | FY 2026: 399000
HS-2612D | Highway | Safety | SR 1005 (Old Mountain Road) | Alexander County line to south of SR 1498 (Southwood Drive) | Install rumble strips. | 12.1 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 |  | T(M) | CONSTRUCTION | 44000 | FY 2026: 44000
HS-2613 | Highway | Safety | Various | Various locations in Division 13. | Safety Improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2614 | Highway | Safety | Various | Various locations in Division 14. | Safety Improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-9999 | Highway | Safety | Various | Locations statewide. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project
HS-9999DIV | Highway | Safety | Various | Locations statewide. Division Needs funding. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project |  | Division 99 |  | HSIP | CONSTRUCTION | 258560000 | 4989000 | 15206000 | 17280000 | 19216000 | 19674000 | 20316000 | 20335000 | 20335000 | 20335000 | 20335000 | 61005000
HS-9999DIV | Highway | Safety | Various | Locations statewide. Division Needs funding. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T(M) | CONSTRUCTION | 28726000 | 554000 | 1690000 | 1920000 | 2135000 | 2186000 | 2257000 | 2259000 | 2259000 | 2259000 | 2259000 | 6777000
HS-9999REG | Highway | Safety | Various | Locations statewide. Regional Impact funding. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project |  | Region SW |  | HSIP | CONSTRUCTION | 258605000 | 4989000 | 15206000 | 17280000 | 19216000 | 19674000 | 20316000 | 20335000 | 20335000 | 20335000 | 20335000 | 61005000
HS-9999REG | Highway | Safety | Various | Locations statewide. Regional Impact funding. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project |  | Region SW |  | T(M) | CONSTRUCTION | 28731000 | 554000 | 1690000 | 1920000 | 2135000 | 2186000 | 2257000 | 2259000 | 2259000 | 2259000 | 2259000 | 6777000
HS-9999SW | Highway | Safety | Various | Locations statewide. Statewide Mobility funding. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 344793000 | 6652000 | 20273000 | 23040000 | 25621000 | 26231000 | 27087000 | 27112000 | 27112000 | 27112000 | 27112000 | 81336000
HS-9999SW | Highway | Safety | Various | Locations statewide. Statewide Mobility funding. | Highway safety improvement program - unprogrammed balance |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 38309000 | 739000 | 2253000 | 2560000 | 2847000 | 2915000 | 3010000 | 3012000 | 3012000 | 3012000 | 3012000 | 9036000
HV-0001 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | Construction of electric vehicle supply equipment along North Carolina's alternative corridors and NEVI planning. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T(M) | ENGINEERING | 2181000 | FY 2026: 1840000
HV-0001 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | Construction of electric vehicle supply equipment along North Carolina's alternative corridors and NEVI planning. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | NEVI | ENGINEERING | 8729000 | FY 2026: 7362000
HV-0001 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | Construction of electric vehicle supply equipment along North Carolina's alternative corridors and NEVI planning. |  | Statewide | 99 | Statewide Project |  | Division 99 |  |  | CONSTRUCTION
HV-0001 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | Construction of electric vehicle supply equipment along North Carolina's alternative corridors and NEVI planning. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T(M) | CONSTRUCTION | 18344000 | FY 2026: 18340000
HV-0001 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | Construction of electric vehicle supply equipment along North Carolina's alternative corridors and NEVI planning. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | NEVI | CONSTRUCTION | 73378000 | FY 2026: 73362000
HV-0001A | Highway | National Electric Vehicle Infrastructure | Elizabeth City | Firehouse Subs. | Install 4 DC fast charging ports. |  | Pasquotank | 1 | Albemarle RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE | Division 1 |  | O | CONSTRUCTION | 161000
HV-0001A | Highway | National Electric Vehicle Infrastructure | Elizabeth City | Firehouse Subs. | Install 4 DC fast charging ports. |  | Pasquotank | 1 | Albemarle RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE | Division 1 |  | NEVI | CONSTRUCTION | 697000
HV-0001A | Highway | National Electric Vehicle Infrastructure | Elizabeth City | Firehouse Subs. | Install 4 DC fast charging ports. |  | Pasquotank | 1 | Albemarle RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE | Division 1 |  | S(M) | CONSTRUCTION | 13000
HV-0001B | Highway | National Electric Vehicle Infrastructure | Marion | Loves Marion Travel Stop #308. | Install 4 DC fast charging ports. |  | McDowell | 13 | Foothills RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM LOVE'S TRAVEL STOPS & COUNTY STORES INC | Division 13 |  | O(M) | CONSTRUCTION | 150000
HV-0001B | Highway | National Electric Vehicle Infrastructure | Marion | Loves Marion Travel Stop #308. | Install 4 DC fast charging ports. |  | McDowell | 13 | Foothills RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM LOVE'S TRAVEL STOPS & COUNTY STORES INC | Division 13 |  | O | CONSTRUCTION | 526000
HV-0001B | Highway | National Electric Vehicle Infrastructure | Marion | Loves Marion Travel Stop #308. | Install 4 DC fast charging ports. |  | McDowell | 13 | Foothills RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM LOVE'S TRAVEL STOPS & COUNTY STORES INC | Division 13 |  | NEVI | CONSTRUCTION | 648000
HV-0001B | Highway | National Electric Vehicle Infrastructure | Marion | Loves Marion Travel Stop #308. | Install 4 DC fast charging ports. |  | McDowell | 13 | Foothills RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM LOVE'S TRAVEL STOPS & COUNTY STORES INC | Division 13 |  | S(M) | CONSTRUCTION | 12000
HV-0001C | Highway | National Electric Vehicle Infrastructure | Warsaw | Pilot Travel Center. | Install 4 DC fast charging ports. |  | Duplin | 3 | Eastern Carolina RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 3 |  | O(M) | CONSTRUCTION | 83000
HV-0001C | Highway | National Electric Vehicle Infrastructure | Warsaw | Pilot Travel Center. | Install 4 DC fast charging ports. |  | Duplin | 3 | Eastern Carolina RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 3 |  | O | CONSTRUCTION | 324000
HV-0001C | Highway | National Electric Vehicle Infrastructure | Warsaw | Pilot Travel Center. | Install 4 DC fast charging ports. |  | Duplin | 3 | Eastern Carolina RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 3 |  | NEVI | CONSTRUCTION | 360000
HV-0001C | Highway | National Electric Vehicle Infrastructure | Warsaw | Pilot Travel Center. | Install 4 DC fast charging ports. |  | Duplin | 3 | Eastern Carolina RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 3 |  | S(M) | CONSTRUCTION | 7000
HV-0001D | Highway | National Electric Vehicle Infrastructure | Candor | Pilot Travel Center | Install 4 DC fast charging ports. |  | Montgomery | 8 | Piedmont Triad RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 8 |  | O(M) | CONSTRUCTION | 113000
HV-0001D | Highway | National Electric Vehicle Infrastructure | Candor | Pilot Travel Center | Install 4 DC fast charging ports. |  | Montgomery | 8 | Piedmont Triad RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 8 |  | O | CONSTRUCTION | 130000
HV-0001D | Highway | National Electric Vehicle Infrastructure | Candor | Pilot Travel Center | Install 4 DC fast charging ports. |  | Montgomery | 8 | Piedmont Triad RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 8 |  | NEVI | CONSTRUCTION | 489000
HV-0001D | Highway | National Electric Vehicle Infrastructure | Candor | Pilot Travel Center | Install 4 DC fast charging ports. |  | Montgomery | 8 | Piedmont Triad RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM PILOT TRAVEL CENTERS LLC | Division 8 |  | S(M) | CONSTRUCTION | 9000
HV-0001E | Highway | National Electric Vehicle Infrastructure | Jonesville | Breakfastime. | Install 6 DC fast charging ports. |  | Yadkin | 11 | Northwest Piedmont RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 11 |  | O(M) | CONSTRUCTION | 145000
HV-0001E | Highway | National Electric Vehicle Infrastructure | Jonesville | Breakfastime. | Install 6 DC fast charging ports. |  | Yadkin | 11 | Northwest Piedmont RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 11 |  | O | CONSTRUCTION | 103000
HV-0001E | Highway | National Electric Vehicle Infrastructure | Jonesville | Breakfastime. | Install 6 DC fast charging ports. |  | Yadkin | 11 | Northwest Piedmont RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 11 |  | NEVI | CONSTRUCTION | 625000
HV-0001E | Highway | National Electric Vehicle Infrastructure | Jonesville | Breakfastime. | Install 6 DC fast charging ports. |  | Yadkin | 11 | Northwest Piedmont RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 11 |  | S(M) | CONSTRUCTION | 12000
HV-0001F | Highway | National Electric Vehicle Infrastructure | Charlotte | Northlake Mall. | Install 4 DC fast charging ports. |  | Mecklenburg | 10 | Charlotte Regional TPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM SCHNEIDER ELECTRIC BUILDINGS AMERICAS INC | Division 10 |  | O(M) | CONSTRUCTION | 273000
HV-0001F | Highway | National Electric Vehicle Infrastructure | Charlotte | Northlake Mall. | Install 4 DC fast charging ports. |  | Mecklenburg | 10 | Charlotte Regional TPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM SCHNEIDER ELECTRIC BUILDINGS AMERICAS INC | Division 10 |  | NEVI | CONSTRUCTION | 1178000
HV-0001F | Highway | National Electric Vehicle Infrastructure | Charlotte | Northlake Mall. | Install 4 DC fast charging ports. |  | Mecklenburg | 10 | Charlotte Regional TPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM SCHNEIDER ELECTRIC BUILDINGS AMERICAS INC | Division 10 |  | S(M) | CONSTRUCTION | 22000
HV-0001G | Highway | National Electric Vehicle Infrastructure | Leland | Piggly Wiggly. | Install 4 DC fast charging ports. |  | Brunswick | 3 | Cape Fear RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM FRANCIS ENERGY CHARGING LLC | Division 3 |  | O(M) | CONSTRUCTION | 248000
HV-0001G | Highway | National Electric Vehicle Infrastructure | Leland | Piggly Wiggly. | Install 4 DC fast charging ports. |  | Brunswick | 3 | Cape Fear RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM FRANCIS ENERGY CHARGING LLC | Division 3 |  | NEVI | CONSTRUCTION | 1071000
HV-0001G | Highway | National Electric Vehicle Infrastructure | Leland | Piggly Wiggly. | Install 4 DC fast charging ports. |  | Brunswick | 3 | Cape Fear RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM FRANCIS ENERGY CHARGING LLC | Division 3 |  | S(M) | CONSTRUCTION | 20000
HV-0001H | Highway | National Electric Vehicle Infrastructure | New Bern | Piggly Wiggly | Install 4 DC fast charging ports. |  | Craven | 2 | Down East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 2 |  | O(M) | CONSTRUCTION | 147000
HV-0001H | Highway | National Electric Vehicle Infrastructure | New Bern | Piggly Wiggly | Install 4 DC fast charging ports. |  | Craven | 2 | Down East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 2 |  | O | CONSTRUCTION | 93000
HV-0001H | Highway | National Electric Vehicle Infrastructure | New Bern | Piggly Wiggly | Install 4 DC fast charging ports. |  | Craven | 2 | Down East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 2 |  | NEVI | CONSTRUCTION | 633000
HV-0001H | Highway | National Electric Vehicle Infrastructure | New Bern | Piggly Wiggly | Install 4 DC fast charging ports. |  | Craven | 2 | Down East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM EVGATEWAY | Division 2 |  | S(M) | CONSTRUCTION | 12000
HV-0001I | Highway | National Electric Vehicle Infrastructure | Williamston | Publix | Install 6 DC fast charging ports. |  | Martin | 1 | Mid-East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE | Division 1 |  | O(M) | CONSTRUCTION | 161000
HV-0001I | Highway | National Electric Vehicle Infrastructure | Williamston | Publix | Install 6 DC fast charging ports. |  | Martin | 1 | Mid-East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE | Division 1 |  | NEVI | CONSTRUCTION | 697000
HV-0001I | Highway | National Electric Vehicle Infrastructure | Williamston | Publix | Install 6 DC fast charging ports. |  | Martin | 1 | Mid-East RPO | O AND O(M) FUNDS REPRESENT PRIVATE FUNDS FROM ECAMION USA INC DBA JULE | Division 1 |  | S(M) | CONSTRUCTION | 13000
HV-9999 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | National Electric Vehicle Infrastructure Program (NEVI) - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T(M) | CONSTRUCTION | 1385000 | [10 empty] | 1385000
HV-9999 | Highway | National Electric Vehicle Infrastructure | Various | Locations statewide. | National Electric Vehicle Infrastructure Program (NEVI) - unprogrammed balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | NEVI | CONSTRUCTION | 5540000 | [10 empty] | 5540000
I-0305 | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County. | Construct additional lanes. | 7.8 | Orange, Durham | 5, 7 | Triangle West TPO | COMBINED LET WITH U-5845 |  |  |  |  | 6343000
I-0305A | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 14320000 | [10 empty] | 14320000
I-0305A | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 3580000 | [10 empty] | 3580000
I-0305A | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | NHP | UTILITIES | 960000 | [10 empty] | 960000
I-0305A | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | T(M) | UTILITIES | 240000 | [10 empty] | 240000
I-0305A | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | NHP | CONSTRUCTION | 96719000 | [10 empty] | 96719000
I-0305A | Highway | STI (Prioritization) | I-85 | West of SR 1006 (Orange Grove Road) in Orange County to west of SR 1400 (Sparger Road) in Durham County | Add lanes. | 7.81 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | T(M) | CONSTRUCTION | 24179000 | [10 empty] | 24179000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 53680000 | FY 2030: 11273000; FY 2031: 15567000; FY 2032: 15030000; FY 2033: 1074000; FY 2034: 10736000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 13420000 | FY 2030: 2818000; FY 2031: 3892000; FY 2032: 3758000; FY 2033: 268000; FY 2034: 2684000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | NHP | UTILITIES | 960000 | FY 2030: 480000; FY 2031: 480000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | T(M) | UTILITIES | 240000 | FY 2030: 120000; FY 2031: 120000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | NHP | CONSTRUCTION | 76960000 | FY 2034: 18470000; FY 2035: 21549000 | 36941000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (South Churton Street) in Hillsborough | Construct interchange improvements. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | T(M) | CONSTRUCTION | 19240000 | FY 2034: 4618000; FY 2035: 5387000 | 9235000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 in Hillsborough | Upgrade interchange. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | NHP | RIGHT-OF-WAY | 9440000 | [10 empty] | 9440000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 in Hillsborough | Upgrade interchange. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | T(M) | RIGHT-OF-WAY | 2360000 | [10 empty] | 2360000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 in Hillsborough | Upgrade interchange. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | NHP | UTILITIES | 2480000 | [10 empty] | 2480000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 in Hillsborough | Upgrade interchange. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | T(M) | UTILITIES | 620000 | [10 empty] | 620000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 in Hillsborough | Upgrade interchange. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | NHP | CONSTRUCTION | 45200000 | [10 empty] | 45200000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 in Hillsborough | Upgrade interchange. | 1 | Orange | 7 | Triangle West TPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | T(M) | CONSTRUCTION | 11300000 | [10 empty] | 11300000
I-0911 | Highway | STI (Prioritization) | I-40 | West of NC 801 in Bermuda Run to west of SR 1122 (Jonestown Road) in Winston-Salem. | Add lanes. | 7 | Forsyth, Davie | 9 | Winston-Salem Area TPO | PARTS B AND C COMPLETE |  |  |  |  | 77937000
I-0911A | Highway | STI (Prioritization) | I-40 | West of NC 801 in Davie County to SR 1101 (Harper Road) in Forsyth County. | Add lanes. | 2.33 | Davie, Forsyth | 9 | Winston-Salem Area TPO | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 35894000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2392000
I-0914 | Highway | Pre-STI (Historic) | I-85 | US 158 (mile marker 213.5) in Vance County to Virginia state line. | Rehabilitate pavement and upgrade signs. | 19 | Warren, Vance | 5 | Kerr-Tar RPO |  | Pre-STI (Transition) |  |  |  | 164443000
I-0914A | Highway | Pre-STI (Historic) | I-85 | South of US 158 in Vance County to Virginia state line | Refurbish signs and signposts. |  | Warren, Vance | 5 | Kerr-Tar RPO | COMPLETE
I-0914BA | Highway | Transition | I-85 | South of US 158 in Vance County to North of SR 1237 (Manson Drewry Road) in Warren County. | Rehabilitate pavement and upgrade signs. | 5.81 | Vance, Warren | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
I-0914BB | Highway | Transition | I-85 | North of SR 1237 (Manson Drewry Road) to Virginia State line. | Rehabilitate pavement and upgrade signs. | 7.72 | Warren | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
I-0914BC | Highway | Pre-STI (Historic) | I-85 | South of US 158 in Vance County to Virginia state line | ITS deployment for Parts BA and BB. |  | Warren, Vance | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
I-2304 | Highway | Pre-STI (Historic) | I-85 | North of SR 2120 (Long Ferry Road) in Rowan County to US 29 / US 52 / US 70 / I-85 Business in Davidson County. | Construct additional lanes, and reconstruct Bridges 790137 and 790465 (Yadkin River Bridge). | 6.8 | Davidson, Rowan | 9 | High Point Urban Area MPO, Cabarrus-Rowan MPO | INCLUDES B-3833; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION; GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS | Pre-STI (Transition) |  |  |  | 291988000
I-2304AC | Highway | Pre-STI (Historic) | I-85 | North of SR 2120 (Long Ferry Road) in Rowan County to North of NC 150 in Davidson County, including Yadkin River Bridge. | Reconstruct bridge. |  | Davidson, Rowan | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC | Exempt |  | NHP | GARVEE ROW | 1066000
I-2304AC | Highway | Pre-STI (Historic) | I-85 | North of SR 2120 (Long Ferry Road) in Rowan County to North of NC 150 in Davidson County, including Yadkin River Bridge. | Reconstruct bridge. |  | Davidson, Rowan | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC | Exempt |  | NHP | GARVEE CON | 8220000
I-2304AD | Highway | Pre-STI (Historic) | I-85 | North of NC 150 to US 29 / US 70 / US 52 / I-85 Business | Reconstruct bridge. |  | Davidson | 9 | High Point Urban Area MPO | COMPLETE; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021 | Pre-STI (Transition) |  | NHP | GARVEE ROW | 984000
I-2304AE | Highway | Pre-STI (Historic) | I-85 | North Carolina Railroad mile marker 326.4. | Realign curve at Duke South of Linwood Yard. |  | Davidson | 9 | High Point Urban Area MPO | COMPLETE
I-2304AF | Highway | Transition | I-85 | In Division 9. | Implement intelligent transportation system (ITS). |  | Davidson, Rowan | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | COMPLETE | Pre-STI (Transition)
I-2513 | Highway | STI (Prioritization) | I-26 / I-240 | I-40 to US 19 / US 23. | Construct multi-lane freeway, part on new location. | 4.7 | Buncombe | 13 | French Broad River MPO | [5 empty] | 17496000
I-2513AA | Highway | Interstate Maintenance | I-40 | East of SR 1224 (Monte Vista Road) to pavement joint west of SR 3412 (Sand Hill Road). | Reconstruct pavement. | 1.39 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHFP | RIGHT-OF-WAY | 2000000 | FY 2026: 200000
I-2513AA | Highway | Interstate Maintenance | I-40 | East of SR 1224 (Monte Vista Road) to pavement joint west of SR 3412 (Sand Hill Road). | Reconstruct pavement. | 1.39 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHFP | UTILITIES | 100000
I-2513AA | Highway | Interstate Maintenance | I-40 | East of SR 1224 (Monte Vista Road) to pavement joint west of SR 3412 (Sand Hill Road). | Reconstruct pavement. | 1.39 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HP | CONSTRUCTION | 4000000 | FY 2026: 1074000
I-2513AA | Highway | Interstate Maintenance | I-40 | East of SR 1224 (Monte Vista Road) to pavement joint west of SR 3412 (Sand Hill Road). | Reconstruct pavement. | 1.39 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 69196000 | FY 2026: 26734000; FY 2027: 3866000; FY 2028: 1460000
I-2513AA | Highway | Interstate Maintenance | I-40 | East of SR 1224 (Monte Vista Road) to pavement joint west of SR 3412 (Sand Hill Road). | Reconstruct pavement. | 1.39 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHFP | CONSTRUCTION | 9320000 | FY 2026: 2505000
I-2513AB | Highway | STI (Prioritization) | I-26 / I-40 | I-40 / US 19 / US 23 (Smokey Park Highway) interchanges. | Widen I-40 eastbound to I-26 eastbound ramp. Widen I-26 westbound between I-40 ramps. Construct new I-40 westbound to US 19 / US 23 (Smokey Park Highway) northbound ramp. | 1 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | NHP | RIGHT-OF-WAY | 3400000 | FY 2026: 340000
I-2513AB | Highway | STI (Prioritization) | I-26 / I-40 | I-40 / US 19 / US 23 (Smokey Park Highway) interchanges. | Widen I-40 eastbound to I-26 eastbound ramp. Widen I-26 westbound between I-40 ramps. Construct new I-40 westbound to US 19 / US 23 (Smokey Park Highway) northbound ramp. | 1 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | NHP | UTILITIES | 100000
I-2513AB | Highway | STI (Prioritization) | I-26 / I-40 | I-40 / US 19 / US 23 (Smokey Park Highway) interchanges. | Widen I-40 eastbound to I-26 eastbound ramp. Widen I-26 westbound between I-40 ramps. Construct new I-40 westbound to US 19 / US 23 (Smokey Park Highway) northbound ramp. | 1 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | HP | CONSTRUCTION | 6250000 | FY 2026: 932000
I-2513AB | Highway | STI (Prioritization) | I-26 / I-40 | I-40 / US 19 / US 23 (Smokey Park Highway) interchanges. | Widen I-40 eastbound to I-26 eastbound ramp. Widen I-26 westbound between I-40 ramps. Construct new I-40 westbound to US 19 / US 23 (Smokey Park Highway) northbound ramp. | 1 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | NHP | CONSTRUCTION | 44957000 | FY 2026: 14785000; FY 2027: 7173000; FY 2028: 2367000
I-2513AC | Highway | STI (Prioritization) | I-26 / I-240 | North of I-40 to SR 3548 (Haywood Road). | Widen to six lane freeway. | 1.85 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | BUILD NC ROW | 8820000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000
I-2513AC | Highway | STI (Prioritization) | I-26 / I-240 | North of I-40 to SR 3548 (Haywood Road). | Widen to six lane freeway. | 1.85 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | RIGHT-OF-WAY | 33149000
I-2513AC | Highway | STI (Prioritization) | I-26 / I-240 | North of I-40 to SR 3548 (Haywood Road). | Widen to six lane freeway. | 1.85 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | UTILITIES | 3750000
I-2513AC | Highway | STI (Prioritization) | I-26 / I-240 | North of I-40 to SR 3548 (Haywood Road). | Widen to six lane freeway. | 1.85 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | BUILD NC CON | 117000000 |  |  | 3900000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 58500000
I-2513AC | Highway | STI (Prioritization) | I-26 / I-240 | North of I-40 to SR 3548 (Haywood Road). | Widen to six lane freeway. | 1.85 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | CONSTRUCTION | 127400000 | FY 2027: 32610000; FY 2028: 5002000; FY 2029: 2828000; FY 2030: 45654000; FY 2031: 41306000
I-2513B | Highway | STI (Prioritization) | I-26 / I-40 | SR 3548 (Haywood Road) to US 19 / US 23 at SR 1781 (Broadway Street). | Widen to six lane freeway. | 2.75 | Buncombe | 13 | French Broad River MPO | GARVEE BOND FUNDING: $60 M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $250M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $250M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 150700000 | FY 2026: 52745000; FY 2027: 15070000; FY 2028: 15070000
I-2513B | Highway | STI (Prioritization) | I-26 / I-40 | SR 3548 (Haywood Road) to US 19 / US 23 at SR 1781 (Broadway Street). | Widen to six lane freeway. | 2.75 | Buncombe | 13 | French Broad River MPO | GARVEE BOND FUNDING: $60 M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $250M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $250M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | UTILITIES | 24100000 | FY 2026: 10845000; FY 2027: 1205000
I-2513B | Highway | STI (Prioritization) | I-26 / I-40 | SR 3548 (Haywood Road) to US 19 / US 23 at SR 1781 (Broadway Street). | Widen to six lane freeway. | 2.75 | Buncombe | 13 | French Broad River MPO | GARVEE BOND FUNDING: $60 M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $250M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $250M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | GARVEE CON | 650010000 |  | 21667000 | 21667000 | 43334000 | 43334000 | 43334000 | 43334000 | 43334000 | 43334000 | 43334000 | 303338000
I-2513B | Highway | STI (Prioritization) | I-26 / I-40 | SR 3548 (Haywood Road) to US 19 / US 23 at SR 1781 (Broadway Street). | Widen to six lane freeway. | 2.75 | Buncombe | 13 | French Broad River MPO | GARVEE BOND FUNDING: $60 M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $250M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $250M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | CONSTRUCTION | 577178000 | 107718000 | 0 | 223959000 | 0 | 105469000 | 43087000
I-2513C | Highway | STI (Prioritization) | I-26 | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 7120000 | [10 empty] | 7120000
I-2513C | Highway | STI (Prioritization) | I-26 | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 1780000 | [10 empty] | 1780000
I-2513C | Highway | STI (Prioritization) | I-26 | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | NHP | UTILITIES | 10720000 | [10 empty] | 10720000
I-2513C | Highway | STI (Prioritization) | I-26 | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T(M) | UTILITIES | 2680000 | [10 empty] | 2680000
I-2513C | Highway | STI (Prioritization) | I-26 | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | NHP | CONSTRUCTION | 209360000 | [10 empty] | 209360000
I-2513C | Highway | STI (Prioritization) | I-26 | I-40 / I-240 interchange in Asheville | Construct interchange improvements. | 1 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T(M) | CONSTRUCTION | 52341000 | [10 empty] | 52341000
I-2513D | Highway | STI (Prioritization) | SR 1477 (Riverside Drive) | SR 1517 (Hill Street) to SR 1781 (Broadway Street). | Widen roadway to include bicycle lanes and construct multi-use path. | 1.44 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | Division 13 |  | BGANY | RIGHT-OF-WAY | 24900000 | FY 2026: 8715000; FY 2027: 2490000; FY 2028: 2490000
I-2513D | Highway | STI (Prioritization) | SR 1477 (Riverside Drive) | SR 1517 (Hill Street) to SR 1781 (Broadway Street). | Widen roadway to include bicycle lanes and construct multi-use path. | 1.44 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | Division 13 |  | BGANY | UTILITIES | 3300000 | FY 2026: 1485000; FY 2027: 165000
I-2513D | Highway | STI (Prioritization) | SR 1477 (Riverside Drive) | SR 1517 (Hill Street) to SR 1781 (Broadway Street). | Widen roadway to include bicycle lanes and construct multi-use path. | 1.44 | Buncombe | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | Division 13 |  | BGANY | CONSTRUCTION | 22822000 | FY 2026: 6289000; FY 2027: 482000
I-2808 | Highway | Interstate Maintenance | I-77 | South of SR 1125 (Mile Marker 71.0) in Yadkin County to US 21 Bypass (mile marker 83.5) in Surry County (Exit 83). | Rehabilitate pavement. | 12 | Yadkin, Surry | 11 | Northwest Piedmont RPO | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912. |  |  |  |  | 79239000
I-2808A | Highway | Pre-STI (Historic) | I-77 | South of SR 1125 (Ashbury Church Road) (mile marker 71.0) to US 21 in Yadkin County (Exit 79) | Rehabilitate pavement. | 6.592 | Yadkin | 11 | Northwest Piedmont RPO | COMPLETE | Pre-STI (Transition)
I-2808B | Highway | Interstate Maintenance | I-77 | US 21 in Yadkin County (Exit 79) to US 21 Bypass (Exit 83) in Surry County. | Rehabilitate pavement. | 0 | Yadkin, Surry | 11 | Northwest Piedmont RPO | SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
I-3306 | Highway | STI (Prioritization) | I-40 | I-85 in Orange County to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Widen to six lanes and install ITS. | 20.7 | Orange, Durham | 5, 7 | Triangle West TPO | [5 empty] | 88683000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 interchange in Orange County to Durham County line. | Widen to six lanes, improve NC 86 interchange, and install ITS. | 11.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 10724000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 interchange in Orange County to Durham County line. | Widen to six lanes, improve NC 86 interchange, and install ITS. | 11.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | NHP | UTILITIES | 628000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 interchange in Orange County to Durham County line. | Widen to six lanes, improve NC 86 interchange, and install ITS. | 11.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | NHP | GARVEE CON | 65637000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4373000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 interchange in Orange County to Durham County line. | Widen to six lanes, improve NC 86 interchange, and install ITS. | 11.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | NHP | CONSTRUCTION | 220928000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 interchange in Orange County to Durham County line. | Widen to six lanes, improve NC 86 interchange, and install ITS. | 11.73 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | T(M) | CONSTRUCTION | 17000000
I-3306AC | Highway | STI (Prioritization) | NC 86 | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Orange | 7 | Triangle West TPO |  | Region D |  | NHP | RIGHT-OF-WAY | 1120000
I-3306AC | Highway | STI (Prioritization) | NC 86 | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) | RIGHT-OF-WAY | 280000
I-3306AC | Highway | STI (Prioritization) | NC 86 | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Orange | 7 | Triangle West TPO |  | Region D |  | NHP | UTILITIES | 536000
I-3306AC | Highway | STI (Prioritization) | NC 86 | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) | UTILITIES | 134000
I-3306AC | Highway | STI (Prioritization) | NC 86 | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Orange | 7 | Triangle West TPO |  | Region D |  | NHP | CONSTRUCTION | 5840000 | FY 2027: 2336000; FY 2028: 2512000; FY 2029: 992000
I-3306AC | Highway | STI (Prioritization) | NC 86 | I-40 interchange ramps C/D to Northwood Drive in Chapel Hill. | Upgrade to reduced conflict intersection. | 0.47 | Orange | 7 | Triangle West TPO |  | Region D |  | T(M) | CONSTRUCTION | 1460000 | FY 2027: 584000; FY 2028: 627000; FY 2029: 249000
I-3306AD | Highway | STI (Prioritization) | I-40 | I-85 interchange in Orange County to Durham County line. | Towing contract for I-3306A construction. |  | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | CONSTRUCTION | 2280000
I-3306B | Highway | Pre-STI (Historic) | I-40 | Orange County line to NC 147 (Durham Freeway / Triangle Expressway) in Durham | Widen roadway | 10.626 | Durham | 5 | Triangle West TPO | COMPLETE
I-3318 | Highway | Interstate Maintenance | I-95 | US 70 to US 301. | Rehabilitate pavement. | 10.7 | Johnston | 4 | Upper Coastal Plain RPO | [5 empty] | 27566000
I-3318A | Highway | Interstate Maintenance | I-95 | US to north of mile marker 100. | Rehabilitate bridge and pavement. | 2.859 | Johnston | 4 | Upper Coastal Plain RPO | COMPLETE.
I-3318BB | Highway | Transition | I-95 | Bridges 500114 and 500116 over Little River. | Replace bridges and approaches. |  | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
I-3802 | Highway | STI (Prioritization) | I-85 | NC 73 (Exit 55) in Cabarrus County to US 29 / US 601 Connector (Exit 68) in Rowan County. | Widen to eight lanes. | 13.6 | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | PROJECT COMPLETED. SEGMENT B INCLUDES B-5365 AND I-3610 |  |  |  |  | 414875000
I-3802A | Highway | Transition | I-85 | NC 73 intersection in Cabarrus County (Exit 55) to SR 2180 (Lane Street) in Cabarrus County. | Widen to eight lanes. | 7.35 | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition)
I-3802AA | Highway | Pre-STI (Historic) | I-85 | NC 73 (Exit 55) to SR 2180 (Lane Street). | Install ITS. | 7.35 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | CMAQ | CONSTRUCTION | 498000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | NC 73 (Exit 55) to SR 2180 (Lane Street). | Install ITS. | 7.35 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | CRPDA | CONSTRUCTION | 1520000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | NC 73 (Exit 55) to SR 2180 (Lane Street). | Install ITS. | 7.35 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 505000
I-3802B | Highway | STI (Prioritization) | I-85 | SR 2180 (Lane Street) in Cabarrus County to US 29 / US 601 connector in Rowan County. | Widen to eight lanes. | 6.49 | Rowan | 9 | Cabarrus-Rowan MPO | COMPLETE - DESIGN-BUILD PROJECT | Statewide Mobility
I-3804 | Highway | STI (Prioritization) | I-85 | SR 1221 (Old Beatty Ford Road) intersection near Landis. | Upgrade grade separation to interchange. | 1 | Rowan | 9 | Cabarrus-Rowan MPO | INCLUDED IN I-3802B - DESIGN-BUILD PROJECT | Division 9
I-3819 | Highway | STI (Prioritization) | I-40 | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Iredell | 12 | Charlotte Regional TPO | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023 |  |  |  |  | 186182000
I-3819A | Highway | Pre-STI (Historic) | I-40 | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Iredell | 12 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE CON | 4388000
I-3819B | Highway | STI (Prioritization) | I-40 | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | RIGHT-OF-WAY | 840000
I-3819B | Highway | STI (Prioritization) | I-40 | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | BUILD NC CON | 142590000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000
I-3819B | Highway | STI (Prioritization) | I-40 | I-77 interchange in Statesville. | Construct interchange improvements. | 1 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | CONSTRUCTION | 217775000
I-4400 | Highway | STI (Prioritization) | I-26 | US 25 to NC 280. | Widen to add additional lanes. | 13.6 | Henderson, Buncombe | 13, 14 | French Broad River MPO | [5 empty] | 246000000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Henderson | 14 | French Broad River MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 1280000 | [10 empty] | 1280000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Henderson | 14 | French Broad River MPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 320000 | [10 empty] | 320000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Henderson | 14 | French Broad River MPO |  | Not Funded |  | NHP | UTILITIES | 400000 | [10 empty] | 400000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Henderson | 14 | French Broad River MPO |  | Not Funded |  | T(M) | UTILITIES | 100000 | [10 empty] | 100000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Henderson | 14 | French Broad River MPO |  | Not Funded |  | NHP | CONSTRUCTION | 91841000 | [10 empty] | 91841000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 to US 64. | Widen to add additional lanes. | 4.64 | Henderson | 14 | French Broad River MPO |  | Not Funded |  | T(M) | CONSTRUCTION | 22959000 | [10 empty] | 22959000
I-4400BA | Highway | STI (Prioritization) | I-26 | US 64 Interchange. | Construct interchange improvements. | 1 | Henderson | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 350000
I-4400BA | Highway | STI (Prioritization) | I-26 | US 64 Interchange. | Construct interchange improvements. | 1 | Henderson | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 106600000
I-4400BB | Highway | STI (Prioritization) | I-26 | US 64 to US 25 Business. | Widen to add additional lanes. | 5.73 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033 | Statewide Mobility |  | NHP | GARVEE CON | 52752000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000
I-4400C | Highway | STI (Prioritization) | I-26 | US 25 Business to NC 280. | Widen to add additional lanes. | 3.29 | Henderson, Buncombe | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035 | Region G |  | NHP | GARVEE CON | 61776000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 1716000 | 1716000
I-4409 | Highway | STI (Prioritization) | SR 2500 (Blue Ridge Road) | I-40 grade separation; US 70 to south of I-40; south of I-40 to SR 2713 (South Blue Ridge Road) | Upgrade I-40 / SR 250 (Blue Ridge Road) grade separation to interchange; Widen to three lanes; Upgrade roadway. | 1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  |  |  | 2400000
I-4409A | Highway | STI (Prioritization) | I-40 | Bridge 100488 over SR 2500 (Blue Ridge Road) | Replace bridge. | 0.25 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | NHP | RIGHT-OF-WAY | 1000000
I-4409A | Highway | STI (Prioritization) | I-40 | Bridge 100488 over SR 2500 (Blue Ridge Road) | Replace bridge. | 0.25 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | NHP | UTILITIES | 900000
I-4409A | Highway | STI (Prioritization) | I-40 | Bridge 100488 over SR 2500 (Blue Ridge Road) | Replace bridge. | 0.25 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | NHP | CONSTRUCTION | 7000000 | FY 2026: 70000; FY 2027: 2030000; FY 2028: 1960000; FY 2029: 1680000; FY 2030: 1260000
I-4409B | Highway | STI (Prioritization) | SR 2500 (Blue Ridge Road) | I-40 grade separation; US 70 to south of I-40; south of I-40 to SR 2713 (South Blue Ridge Road) | Upgrade I-40 / SR 250 (Blue Ridge Road) grade separation to interchange; Widen to three lanes; Upgrade roadway. | 1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | NHP | RIGHT-OF-WAY | 7700000 | FY 2026: 2053000; FY 2027: 4107000; FY 2028: 770000; FY 2029: 770000
I-4409B | Highway | STI (Prioritization) | SR 2500 (Blue Ridge Road) | I-40 grade separation; US 70 to south of I-40; south of I-40 to SR 2713 (South Blue Ridge Road) | Upgrade I-40 / SR 250 (Blue Ridge Road) grade separation to interchange; Widen to three lanes; Upgrade roadway. | 1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | NHP | UTILITIES | 1000000 | FY 2026: 1000000
I-4409B | Highway | STI (Prioritization) | SR 2500 (Blue Ridge Road) | I-40 grade separation; US 70 to south of I-40; south of I-40 to SR 2713 (South Blue Ridge Road) | Upgrade I-40 / SR 250 (Blue Ridge Road) grade separation to interchange; Widen to three lanes; Upgrade roadway. | 1 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | NHP | CONSTRUCTION | 23700000 | FY 2028: 237000; FY 2029: 6873000; FY 2030: 6636000; FY 2031: 5688000; FY 2032: 4266000
I-4700 | Highway | STI (Prioritization) | I-26 | NC 280 (Exit 40) to I-40 at Asheville. | Construct additional lanes. | 9.32 | Buncombe, Henderson | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033 | Statewide Mobility |  |  |  | 318380000
I-4700 | Highway | STI (Prioritization) | I-26 | NC 280 (Exit 40) to I-40 at Asheville. | Construct additional lanes. | 9.32 | Buncombe, Henderson | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033 | Statewide Mobility |  | NHP | GARVEE CON | 62468000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000
I-4700C | Highway | STI (Prioritization) | NC 146 (Long Shoals Road) | Schenck Parkway/Skyland Inn Drive intersection in Asheville. | Construct intersection improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G |  | NHP | UTILITIES | 100000 | FY 2026: 100000
I-4700C | Highway | STI (Prioritization) | NC 146 (Long Shoals Road) | Schenck Parkway/Skyland Inn Drive intersection in Asheville. | Construct intersection improvements. |  | Buncombe | 13 | French Broad River MPO |  | Region G |  | NHP | CONSTRUCTION | 4100000 | FY 2026: 2050000; FY 2027: 2050000
I-4729 | Highway | STI (Prioritization) | I-26 | US 74 / NC 108 interchange (Exit 67). | Construct interchange improvements and improvements on NC 108. |  | Polk | 14 | Foothills RPO | [5 empty] | 33579000
I-4729A | Highway | STI (Prioritization) | I-26 | US 74 / NC 108 interchange (Exit 67). | Construct ramps from I-26 westbound to US 74 eastbound and from US 74 westbound to I-26 eastbound. | 1 | Polk | 14 | Foothills RPO | COMPLETE | Region G
I-4729B | Highway | STI (Prioritization) | I-26 | NC 108 at Exit 67. | Construct improvements. |  | Polk | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | RIGHT-OF-WAY | 3200000 | FY 2030: 550000; FY 2031: 1100000; FY 2032: 550000
I-4729B | Highway | STI (Prioritization) | I-26 | NC 108 at Exit 67. | Construct improvements. |  | Polk | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | UTILITIES | 2000000 | FY 2030: 1000000
I-4729B | Highway | STI (Prioritization) | I-26 | NC 108 at Exit 67. | Construct improvements. |  | Polk | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | CONSTRUCTION | 33600000 | FY 2033: 4032000; FY 2034: 9744000; FY 2035: 8400000 | 11424000
I-4739 | Highway | STI (Prioritization) | I-40 | I-40 / NC 42 Interchange (Exit 312). | Improve access. | 1 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | Statewide Mobility |  |  |  | 57928000
I-4739 | Highway | STI (Prioritization) | I-40 | I-40 / NC 42 Interchange (Exit 312). | Improve access. | 1 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | Statewide Mobility |  | NHP | GARVEE ROW | 19305000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000
I-4739 | Highway | STI (Prioritization) | I-40 | I-40 / NC 42 Interchange (Exit 312). | Improve access. | 1 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | Statewide Mobility |  | NHP | CONSTRUCTION | 40137000
I-4744 | Highway | Pre-STI (Historic) | I-40 | SR 1728 (Wade Avenue) US I-440 / US 1 / US 64. | Widen to six lanes. | 4 | Wake | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020 | Pre-STI (Transition) |  |  |  | 69363000
I-4744 | Highway | Pre-STI (Historic) | I-40 | SR 1728 (Wade Avenue) US I-440 / US 1 / US 64. | Widen to six lanes. | 4 | Wake | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020 | Pre-STI (Transition) |  | NHP | GARVEE CON | 4635000
I-4750 | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Widen and reconstruct roadway. | 23 | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO | FUNDING FOR I-4750 AA INCLUDED IN I-5405 |  |  |  |  | 8681000
I-4750AA | Highway | Transition | I-77 | SR 5544 (West Catawba Avenue) to NC 150. | Construct high occupancy/toll (hot) lanes. | 7.79 | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO | COMPLETE - UNDER CONSTRUCTION WITH PROJECT I-5405
I-4750AB | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 8400000 | [10 empty] | 8400000
I-4750AB | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 2100000 | [10 empty] | 2100000
I-4750AB | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO |  | Not Funded |  | NHP | UTILITIES | 540000 | [10 empty] | 540000
I-4750AB | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO |  | Not Funded |  | T(M) | UTILITIES | 135000 | [10 empty] | 135000
I-4750AB | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO |  | Not Funded |  | NHP | CONSTRUCTION | 106400000 | [10 empty] | 106400000
I-4750AB | Highway | STI (Prioritization) | I-77 | SR 5544 (West Catawba Avenue) Exit 28 to NC 150. | Construct one additional lane in each direction. |  | Iredell, Mecklenburg | 10, 12 | Charlotte Regional TPO |  | Not Funded |  | T(M) | CONSTRUCTION | 26600000 | [10 empty] | 26600000
I-4750AC | Highway | Transition | I-77 | Griffth Street (Exit 30) interchange. | Construct roundabouts at northbound and southbound ramp termini. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE | Exempt
I-4759 | Highway | STI (Prioritization) | I-40 | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  |  |  | 4148000
I-4759 | Highway | STI (Prioritization) | I-40 | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | GARVEE ROW | 1582000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
I-4759 | Highway | STI (Prioritization) | I-40 | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | RIGHT-OF-WAY | 10000000
I-4759 | Highway | STI (Prioritization) | I-40 | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGDA | RIGHT-OF-WAY | 4000000
I-4759 | Highway | STI (Prioritization) | I-40 | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | UTILITIES | 700000
I-4759 | Highway | STI (Prioritization) | I-40 | SR 1228 (Liberty Road). | Upgrade grade separation to an interchange and construct two lane roadway north of I-40 to SR 1224 (Monte Vista Road) and four lane roadway south of I-40 to US 19 / US 23 / NC 151 with parts on new location. | 1.52 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | CONSTRUCTION | 88900000 | FY 2030: 8001000; FY 2031: 23114000; FY 2032: 21336000; FY 2033: 19558000; FY 2034: 16891000
I-4759A | Highway | STI (Prioritization) | I-40; SR 1228 (Liberty Road) | Various locations. | Clearing work. |  | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  | BGANY | CONSTRUCTION | 500000 | FY 2029: 500000
I-4906 | Highway | Pre-STI (Historic) | I-95 | Cumberland County line to Johnston County line. | Repair pavement. | 8.8 | Harnett | 6 | Mid-Carolina RPO | COMPLETE. GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019. | Pre-STI (Transition) |  |  |  | 6384000
I-5000 | Highway | STI (Prioritization) | I-85 | US 321 interchange. | Construct geometric safety improvements to interchange. | 0.17 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 27078000
I-5106 | Highway | Pre-STI (Historic) | I-77 | Mile marker 57.83 to mile marker 61.74. | Rehabilitate pavement. | 3.9 | Iredell | 12 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020 | Pre-STI (Transition) |  |  |  | 6037000
I-5106 | Highway | Pre-STI (Historic) | I-77 | Mile marker 57.83 to mile marker 61.74. | Rehabilitate pavement. | 3.9 | Iredell | 12 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020 | Pre-STI (Transition) |  | NHP | GARVEE CON | 439000
I-5110 | Highway | Transition | Future I-73 | NC 68 to Greensboro Western Loop. | Construct six-lane freeway on new location. | 3 | Guilford | 7 | Greensboro Urban Area MPO | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 152283000
I-5111 | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (Exit 301) to NC 42 (Exit 312). | Add two general purpose lanes in each direction. | 10.71 | Wake, Johnston | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK 2019-2033. |  |  |  |  | 323026000
I-5111REG | Highway | STI (Prioritization) | I-40 | Wake County line to NC 42. | Add two general purpose lanes in each direction. | 1.55 | Johnston | 4 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region A |  | NHP | GARVEE ROW | 3479000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000
I-5111REG | Highway | STI (Prioritization) | I-40 | Wake County line to NC 42. | Add two general purpose lanes in each direction. | 1.55 | Johnston | 4 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region A |  | NHP | CONSTRUCTION | 23795000
I-5111SW | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (Exit 301) to Johnston County line | Construct 2 lanes in each direction. | 9.18 | Wake | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Statewide Mobility |  | NHP | GARVEE ROW | 15826000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000
I-5111SW | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (Exit 301) to Johnston County line | Construct 2 lanes in each direction. | 9.18 | Wake | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Statewide Mobility |  | NHP | CONSTRUCTION | 128398000
I-5504 | Highway | STI (Prioritization) | I-26 | NC 191 (Brevard Road). | Upgrade interchange. | 1 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT | Statewide Mobility |  |  |  | 53784000
I-5506 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) interchange in Cary. | Improve interchange and construct auxiliary lane on I-40 westbound from SR 1002 (Aviation Parkway) to SR 3015 (Airport Boulevard). | 1 | Wake | 5 | Capital Area MPO | PROJECT COMPLETE. | Statewide Mobility |  |  |  | 25333000
I-5507 | Highway | STI (Prioritization) | I-485 | I-77 south of Charlotte to US 74 (Independence Boulevard). | Construct one express lane in each direction. This is a toll project (express lanes only). | 16.62 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT | Statewide Mobility |  |  |  | 25492000
I-5507 | Highway | STI (Prioritization) | I-485 | I-77 south of Charlotte to US 74 (Independence Boulevard). | Construct one express lane in each direction. This is a toll project (express lanes only). | 16.62 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT | Statewide Mobility |  | T | CONSTRUCTION | 504856000 | FY 2026: 46200000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (Airport Boulevard) intersection in Cary/Morrisville. | Revise interchange; Construct auxiliary lanes on I-40 eastbound from I-540 to SR 3015 (Airport Boulevard) and from SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway), and construct auxiliary lane on I-40 westbound from SR 3015 (Airport Boulevard) t | 2.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  |  |  | 26914000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (Airport Boulevard) intersection in Cary/Morrisville. | Revise interchange; Construct auxiliary lanes on I-40 eastbound from I-540 to SR 3015 (Airport Boulevard) and from SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway), and construct auxiliary lane on I-40 westbound from SR 3015 (Airport Boulevard) t | 2.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  | NHP | GARVEE CON | 12870000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (Airport Boulevard) intersection in Cary/Morrisville. | Revise interchange; Construct auxiliary lanes on I-40 eastbound from I-540 to SR 3015 (Airport Boulevard) and from SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway), and construct auxiliary lane on I-40 westbound from SR 3015 (Airport Boulevard) t | 2.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  | NHP | CONSTRUCTION | 35530000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (Airport Boulevard) intersection in Cary/Morrisville. | Revise interchange; Construct auxiliary lanes on I-40 eastbound from I-540 to SR 3015 (Airport Boulevard) and from SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway), and construct auxiliary lane on I-40 westbound from SR 3015 (Airport Boulevard) t | 2.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 3333000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  |  |  | 600000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | T(M) |  | 150000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | NHP | UTILITIES | 1840000 | FY 2027: 920000; FY 2028: 920000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | T(M) | UTILITIES | 460000 | FY 2027: 230000; FY 2028: 230000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | NHP | CONSTRUCTION | 130480000 | FY 2027: 23486000; FY 2028: 31316000; FY 2029: 28706000; FY 2030: 26096000; FY 2031: 20876000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 to SR 1009 (Lake Wheeler Road) in Raleigh. | Construct additional lanes. | 4.44 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | T(M) | CONSTRUCTION | 32620000 | FY 2027: 5872000; FY 2028: 7828000; FY 2029: 7176000; FY 2030: 6524000; FY 2031: 5220000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 interchange in Raleigh. | Reconstruct interchange. | 1 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $80M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 40800000 | FY 2027: 16320000; FY 2028: 16320000; FY 2029: 4080000; FY 2030: 4080000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 interchange in Raleigh. | Reconstruct interchange. | 1 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $80M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | UTILITIES | 2799000 | FY 2027: 933000; FY 2028: 933000; FY 2029: 933000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 interchange in Raleigh. | Reconstruct interchange. | 1 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $80M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | GARVEE CON | 103995000 |  |  |  | 6933000 | 6933000 | 6933000 | 6933000 | 6933000 | 6933000 | 6933000 | 48531000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 interchange in Raleigh. | Reconstruct interchange. | 1 | Wake | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $80M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | CONSTRUCTION | 250900000 | FY 2027: 43017000; FY 2028: 49635000; FY 2029: 0; FY 2030: 78832000; FY 2031: 79416000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  |  |  | 1424000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) |  | 356000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 640000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 160000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | NHP | UTILITIES | 152000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) | UTILITIES | 38000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | NHP | CONSTRUCTION | 7440000 | FY 2027: 893000; FY 2028: 3720000; FY 2029: 2306000; FY 2030: 521000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (Alston Avenue) to NC 147 (Durham Freeway / Triangle Expressway) in Durham. | Construct westbound auxiliary lane. | 0.53 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) | CONSTRUCTION | 1860000 | FY 2027: 223000; FY 2028: 930000; FY 2029: 577000; FY 2030: 130000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (Wake Forest Road) intersection in Raleigh. | Improve interchange. | 1 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  |  |  | 11165000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (Wake Forest Road) intersection in Raleigh. | Improve interchange. | 1 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  | NHP | GARVEE ROW | 1736000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (Wake Forest Road) intersection in Raleigh. | Improve interchange. | 1 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  | NHP | UTILITIES | 2000000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (Wake Forest Road) intersection in Raleigh. | Improve interchange. | 1 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  | NHP | CONSTRUCTION | 23000000 | FY 2029: 2530000; FY 2030: 7820000; FY 2031: 6440000; FY 2032: 4370000; FY 2033: 1840000
I-5711 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1007 (Mebane-Oaks Road) in Mebane. | Improve interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; | Statewide Mobility |  |  |  | 4381000
I-5711 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1007 (Mebane-Oaks Road) in Mebane. | Improve interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; | Statewide Mobility |  | T(M) |  | 1095000
I-5711 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1007 (Mebane-Oaks Road) in Mebane. | Improve interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; | Statewide Mobility |  | NHP | CONSTRUCTION | 7865000
I-5711 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1007 (Mebane-Oaks Road) in Mebane. | Improve interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; | Statewide Mobility |  | T(M) | CONSTRUCTION | 1965000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  |  |  | 320000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) |  | 80000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 11119000 | FY 2028: 2224000; FY 2029: 2891000; FY 2030: 3002000; FY 2031: 1890000; FY 2032: 1112000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 2781000 | FY 2028: 556000; FY 2029: 723000; FY 2030: 751000; FY 2031: 473000; FY 2032: 278000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 880000 | FY 2028: 440000; FY 2029: 440000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | UTILITIES | 220000 | FY 2028: 110000; FY 2029: 110000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 22081000 | FY 2031: 5962000; FY 2032: 7728000; FY 2033: 4637000; FY 2034: 2650000; FY 2035: 1104000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (Sandy Ridge Road) in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5519000 | FY 2031: 1490000; FY 2032: 1932000; FY 2033: 1159000; FY 2034: 662000; FY 2035: 276000
I-5714 | Highway | STI (Prioritization) | I-77 | SR 2136 (Gilead Road) interchange. | Upgrade interchange. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 13600000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  |  |  | 3600000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) |  | 900000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 16799000 | FY 2026: 3119000; FY 2027: 1519000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 4201000 | FY 2026: 780000; FY 2027: 380000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 2400000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | UTILITIES | 600000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 63919000 | FY 2027: 14702000; FY 2028: 17258000; FY 2029: 14062000; FY 2030: 10227000; FY 2031: 7670000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 interchange. | Upgrade interchange to split diamond configuration. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | CONSTRUCTION | 15981000 | FY 2027: 3675000; FY 2028: 4315000; FY 2029: 3516000; FY 2030: 2557000; FY 2031: 1918000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  |  |  | 320000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) |  | 80000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 224000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 56000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | NHP | CONSTRUCTION | 9840000 | FY 2026: 984000; FY 2027: 4133000; FY 2028: 3149000; FY 2029: 1574000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (Lenoir Rhyne Boulevard) interchange. | Construct interchange improvements. | 1 | Catawba | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | T(M) | CONSTRUCTION | 2460000 | FY 2026: 246000; FY 2027: 1033000; FY 2028: 787000; FY 2029: 394000
I-5718 | Highway | STI (Prioritization) | I-77 | South Carolina state line to I-277 / NC 16 (Brookshire Freeway). | Widen freeway to ten lanes by constructing managed lanes and reconstruct I-277 interchanges. This is a toll project (managed lanes only). | 11.2 | Mecklenburg | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 1508000000 | FY 2029: 1508000000
I-5718 | Highway | STI (Prioritization) | I-77 | South Carolina state line to I-277 / NC 16 (Brookshire Freeway). | Widen freeway to ten lanes by constructing managed lanes and reconstruct I-277 interchanges. This is a toll project (managed lanes only). | 11.2 | Mecklenburg | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | BOND R | UTILITIES | 42000000 | FY 2029: 42000000
I-5718 | Highway | STI (Prioritization) | I-77 | South Carolina state line to I-277 / NC 16 (Brookshire Freeway). | Widen freeway to ten lanes by constructing managed lanes and reconstruct I-277 interchanges. This is a toll project (managed lanes only). | 11.2 | Mecklenburg | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | NHP | GARVEE CON | 404415000 | FY 2031: 8987000; FY 2032: 8987000; FY 2033: 17974000; FY 2034: 17974000; FY 2035: 26961000 | 323532000
I-5718 | Highway | STI (Prioritization) | I-77 | South Carolina state line to I-277 / NC 16 (Brookshire Freeway). | Widen freeway to ten lanes by constructing managed lanes and reconstruct I-277 interchanges. This is a toll project (managed lanes only). | 11.2 | Mecklenburg | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | NHP | CONSTRUCTION | 300000000 | FY 2031: 0; FY 2032: 100000000; FY 2033: 0; FY 2034: 100000000; FY 2035: 0 | 100000000
I-5718 | Highway | STI (Prioritization) | I-77 | South Carolina state line to I-277 / NC 16 (Brookshire Freeway). | Widen freeway to ten lanes by constructing managed lanes and reconstruct I-277 interchanges. This is a toll project (managed lanes only). | 11.2 | Mecklenburg | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | BOND R | CONSTRUCTION | 2058900000 | FY 2029: 2058900000
I-5719 | Highway | STI (Prioritization) | I-85 | US 321 to NC 273. | Widen to eight lanes. | 9.8 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | Statewide Mobility
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street) | Widen to eight lanes. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 47200000 | FY 2029: 4720000; FY 2030: 16520000; FY 2031: 16520000; FY 2032: 4720000; FY 2033: 4720000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street) | Widen to eight lanes. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | UTILITIES | 12300000 | FY 2029: 3075000; FY 2030: 6150000; FY 2031: 3075000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street) | Widen to eight lanes. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | GARVEE CON | 130005000 |  |  |  | 8667000 | 8667000 | 8667000 | 8667000 | 8667000 | 8667000 | 8667000 | 69336000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street) | Widen to eight lanes. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | CONSTRUCTION | 312276000 | FY 2029: 0; FY 2030: 119208000; FY 2031: 66642000; FY 2032: 51696000; FY 2033: 74730000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street) | Widen to eight lanes. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | T | CONSTRUCTION | 85924000 | FY 2029: 0; FY 2030: 0; FY 2031: 42962000; FY 2032: 42962000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | DP | RIGHT-OF-WAY | 15000000 | FY 2026: 10752000; FY 2027: 1176000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 19650000 | FY 2026: 0; FY 2027: 11970000; FY 2028: 3840000; FY 2029: 3840000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 3750000 | FY 2026: 2688000; FY 2027: 294000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | DP | UTILITIES | 15000000 | FY 2026: 5420000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | UTILITIES | 29150000 | FY 2026: 17175000; FY 2027: 11975000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | T(M) | UTILITIES | 3750000 | FY 2026: 1355000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | GARVEE CON | 286005000 |  | 13000000 | 13000000 | 19067000 | 19067000 | 19067000 | 19067000 | 19067000 | 19067000 | 19067000 | 126536000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | DP | CONSTRUCTION | 52344000 | FY 2026: 20704000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | CONSTRUCTION | 110070000 | FY 2026: 72995000; FY 2027: 0; FY 2028: 35885000; FY 2029: 1190000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273 | Widen to eight lanes. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $70M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | T(M) | CONSTRUCTION | 13086000 | FY 2026: 6758000
I-5719C | Highway | STI (Prioritization) | I-85 | South Carolina state line to NC 273 | Piedmont Northern Railroad bridge, two Norfolk Southern Railroad bridges, and Bridge 350142 over SR 2213 (Grove Street) within the limits of I-5719A |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 3531000 | FY 2026: 353000; FY 2027: 1236000; FY 2028: 1236000; FY 2029: 353000; FY 2030: 353000
I-5719C | Highway | STI (Prioritization) | I-85 | South Carolina state line to NC 273 | Piedmont Northern Railroad bridge, two Norfolk Southern Railroad bridges, and Bridge 350142 over SR 2213 (Grove Street) within the limits of I-5719A |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T | UTILITIES | 2600000 | FY 2026: 650000; FY 2027: 1300000; FY 2028: 650000
I-5719C | Highway | STI (Prioritization) | I-85 | South Carolina state line to NC 273 | Piedmont Northern Railroad bridge, two Norfolk Southern Railroad bridges, and Bridge 350142 over SR 2213 (Grove Street) within the limits of I-5719A |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 23240000 | FY 2026: 232000; FY 2027: 6740000; FY 2028: 6042000; FY 2029: 5578000; FY 2030: 4648000
I-5719C | Highway | STI (Prioritization) | I-85 | South Carolina state line to NC 273 | Piedmont Northern Railroad bridge, two Norfolk Southern Railroad bridges, and Bridge 350142 over SR 2213 (Grove Street) within the limits of I-5719A |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 209160000 | FY 2026: 2092000; FY 2027: 60656000; FY 2028: 54382000; FY 2029: 50198000; FY 2030: 41832000
I-5719D | Highway | STI (Prioritization) | I-85 | Various locations. | Implement flood risk, vulnerability assessment, and flood warning system along the I-85 corridor. |  | Gaston, Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | IMPLEMENTATION | 160000
I-5719D | Highway | STI (Prioritization) | I-85 | Various locations. | Implement flood risk, vulnerability assessment, and flood warning system along the I-85 corridor. |  | Gaston, Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | IMPLEMENTATION | 40000
I-5719FA | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street). | Install and implement Intelligent Transportation System (ITS) components including Active Traffic Management and Incident Management. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 3280000 | FY 2028: 3280000
I-5719FA | Highway | STI (Prioritization) | I-85 | US 321 to NC 7 (McAdenville Road / Main Street). | Install and implement Intelligent Transportation System (ITS) components including Active Traffic Management and Incident Management. | 6.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 820000 | FY 2028: 820000
I-5719FB | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273. | Install and implement Intelligent Transportation System (ITS) components including Active Traffic Management and Incident Management. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 5720000
I-5719FB | Highway | STI (Prioritization) | I-85 | NC 7 (McAdenville Road / Main Street) to NC 273. | Install and implement Intelligent Transportation System (ITS) components including Active Traffic Management and Incident Management. | 3.4 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1430000
I-5719FC | Highway | STI (Prioritization) | I-85 | South Carolina state line to US 74. | Install broadband for Traveler Information Systems. | 9.5 | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 5640000
I-5719FC | Highway | STI (Prioritization) | I-85 | South Carolina state line to US 74. | Install broadband for Traveler Information Systems. | 9.5 | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | HSIP | CONSTRUCTION | 510000 | FY 2026: 510000
I-5719FC | Highway | STI (Prioritization) | I-85 | South Carolina state line to US 74. | Install broadband for Traveler Information Systems. | 9.5 | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | L(M) | CONSTRUCTION | 60000 | FY 2026: 60000
I-5719FC | Highway | STI (Prioritization) | I-85 | South Carolina state line to US 74. | Install broadband for Traveler Information Systems. | 9.5 | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1440000 | FY 2026: 30000
I-5719FD | Highway | STI (Prioritization) | I-85 | South Carolina state line to NC 273. | Implement Intelligent Transportation System (ITS) Statewide Resilience, connected vehicle technology, and traveler information. | 26.8 | Gaston, Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 5576000
I-5719FD | Highway | STI (Prioritization) | I-85 | South Carolina state line to NC 273. | Implement Intelligent Transportation System (ITS) Statewide Resilience, connected vehicle technology, and traveler information. | 26.8 | Gaston, Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1394000
I-5740 | Highway | Interstate Maintenance | I-85 | SR 2205 (Old US 64) to 0.4 miles north of US 64. | Rehabilitate pavement. | 2.6 | Davidson | 9 | High Point Urban Area MPO | COMPLETE | Statewide Mobility |  |  |  | 3217000
I-5740A | Highway | Bridges | I-85 | Bridges 280181 and 280182 over US 64 near Lexington. | Rehabilitate bridges. | 0.25 | Davidson | 9 | High Point Urban Area MPO | COMPLETE | Statewide Mobility
I-5746 | Highway | Interstate Maintenance | I-277 | I-77 to East 10th Street. | Resurface roadway and rehabilitate bridges. | 3.5 | Mecklenburg | 10 | Charlotte Regional TPO | [5 empty] | 20898000
I-5746A | Highway | Interstate Maintenance | I-277 (Belk Freeway) | I-77 to East Stonewall Street. | Rehabilitate bridges 590078, 590118, 590505, 590506, 590507, 590508, 590509, and 590510. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE | Statewide Mobility
I-5746B | Highway | Interstate Maintenance | I-277 (Belk Freeway) | East Stonewall Street to East 10th Street. | Rehabilitate bridges 590047, 590309, 590315, 590316, 590448, 590449, 590450, 590451, 590452, 590478, 590479, 590487, 590488, and 590522. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE | Statewide Mobility
I-5746C | Highway | Interstate Maintenance | I-277 (Brookshire Freeway) | I-77 to East 10th Street. | Resurface roadway and rehabilitate bridges 590044, 590048, 590138, 590320, 590322, 590326, 590327, 590328, 590330, and 590332. | 1.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 35214000 | FY 2026: 5200000
I-5746C | Highway | Interstate Maintenance | I-277 (Brookshire Freeway) | I-77 to East 10th Street. | Resurface roadway and rehabilitate bridges 590044, 590048, 590138, 590320, 590322, 590326, 590327, 590328, 590330, and 590332. | 1.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 8803000 | FY 2026: 1300000
I-5769 | Highway | Interstate Maintenance | I-77 | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 1.11 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  |  |  | 292000
I-5769 | Highway | Interstate Maintenance | I-77 | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 1.11 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 3915000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000
I-5769 | Highway | Interstate Maintenance | I-77 | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 1.11 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12544000
I-5769 | Highway | Interstate Maintenance | I-77 | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 1.11 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 1073000
I-5786 | Highway | Interstate Maintenance | I-95 | South of SR 1001 (Lizzie Mill Road) to Johnston/Wilson County line north of NC 222. | Rehabilitate pavement. | 11.75 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 70484000
I-5786A | Highway | Interstate Maintenance | I-95 | Bridge 500117 on SR 2399 (Truck Stop Road) over I-95. | Replace bridge and adjust service roads and approaches. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Statewide Mobility
I-5795 | Highway | Interstate Maintenance | I-40 | 0.3 mile east of SR 3153 (Hanes Mall Boulevard) to 0.9 mile east of NC 150 (Peters Creek Parkway) in Winston-Salem and SR 2747 (Clemmonsville Road) in Winston-Salem to Guilford County line. | Pavement rehabilitation and rehabilitation of bridges 330161, 330162, 330444, 330448, 330449,330508, and 330509. | 13.66 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 100000
I-5795 | Highway | Interstate Maintenance | I-40 | 0.3 mile east of SR 3153 (Hanes Mall Boulevard) to 0.9 mile east of NC 150 (Peters Creek Parkway) in Winston-Salem and SR 2747 (Clemmonsville Road) in Winston-Salem to Guilford County line. | Pavement rehabilitation and rehabilitation of bridges 330161, 330162, 330444, 330448, 330449,330508, and 330509. | 13.66 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHFP | CONSTRUCTION | 11318000
I-5795 | Highway | Interstate Maintenance | I-40 | 0.3 mile east of SR 3153 (Hanes Mall Boulevard) to 0.9 mile east of NC 150 (Peters Creek Parkway) in Winston-Salem and SR 2747 (Clemmonsville Road) in Winston-Salem to Guilford County line. | Pavement rehabilitation and rehabilitation of bridges 330161, 330162, 330444, 330448, 330449,330508, and 330509. | 13.66 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12496000
I-5796 | Highway | Interstate Maintenance | I-85 | North of SR 5901 (Billy Graham Parkway) to south of NC 16 at mile marker 35.93. | Rehabilitate pavement. | 2.92 | Mecklenburg | 10 | Charlotte Regional TPO | TO BE LET WITH I-5770 - UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 525000
I-5805 | Highway | Interstate Maintenance | I-40 | SR 2158 (Old Mocksville Road) to Davie County line. | Rehabilitate pavement. | 8.26 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 10000
I-5805 | Highway | Interstate Maintenance | I-40 | SR 2158 (Old Mocksville Road) to Davie County line. | Rehabilitate pavement. | 8.26 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 12686000 | FY 2030: 2410000; FY 2031: 3172000; FY 2032: 2791000; FY 2033: 2410000; FY 2034: 1903000
I-5805 | Highway | Interstate Maintenance | I-40 | SR 2158 (Old Mocksville Road) to Davie County line. | Rehabilitate pavement. | 8.26 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 40314000 | FY 2030: 7660000; FY 2031: 10078000; FY 2032: 8869000; FY 2033: 7660000; FY 2034: 6047000
I-5821 | Highway | Interstate Maintenance | I-85 | Randolph County line to SR 1113 (Kivett Drive). | Rehabilitate pavement. | 4.5 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789 | Statewide Mobility |  |  |  | 100000
I-5826 | Highway | Interstate Maintenance | I-85 | Concrete pavement joint at US 29 / NC 49 connector to concrete pavement joint north of NC 73. | Preserve pavement and bridge 590296. | 13.93 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  |  |  | 217000
I-5826 | Highway | Interstate Maintenance | I-85 | Concrete pavement joint at US 29 / NC 49 connector to concrete pavement joint north of NC 73. | Preserve pavement and bridge 590296. | 13.93 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000
I-5826 | Highway | Interstate Maintenance | I-85 | Concrete pavement joint at US 29 / NC 49 connector to concrete pavement joint north of NC 73. | Preserve pavement and bridge 590296. | 13.93 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5694000
I-5826 | Highway | Interstate Maintenance | I-85 | Concrete pavement joint at US 29 / NC 49 connector to concrete pavement joint north of NC 73. | Preserve pavement and bridge 590296. | 13.93 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 666000
I-5828 | Highway | Interstate Maintenance | I-485 | I-77 to NC 49; Bridges 590661, 590662, 590663, 590664, and 590643 | Rehabilitate pavement; Rehabilitate bridges. | 56.03 | Mecklenburg | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | Statewide Mobility |  |  |  | 310000
I-5828 | Highway | Interstate Maintenance | I-485 | I-77 to NC 49; Bridges 590661, 590662, 590663, 590664, and 590643 | Rehabilitate pavement; Rehabilitate bridges. | 56.03 | Mecklenburg | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | Statewide Mobility |  | NHPIM | CONSTRUCTION | 9050000 | FY 2029: 3530000; FY 2030: 3982000; FY 2031: 1538000
I-5828 | Highway | Interstate Maintenance | I-485 | I-77 to NC 49; Bridges 590661, 590662, 590663, 590664, and 590643 | Rehabilitate pavement; Rehabilitate bridges. | 56.03 | Mecklenburg | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | Statewide Mobility |  | HFB | CONSTRUCTION | 2900000 | FY 2029: 1131000; FY 2030: 1276000; FY 2031: 493000
I-5829 | Highway | Interstate Maintenance | I-77 | Mile marker 91.0 to mile marker 95.0. | Rehabilitate pavement. | 4.39 | Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION |  |  |  |  | 3050000
I-5829A | Highway | Interstate Maintenance | I-77 | Mile marker 91.0 to mile marker 95.0. | Perform diamond grinding. | 4.39 | Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 3600000
I-5831 | Highway | Interstate Maintenance | I-26 | Tennessee state line to mile marker 9.0. | Rehabilitate pavement and bridges 560540, 560541, 560547, 560548, 560549. 560550, and 560551. | 9 | Madison | 13 | Land-of-Sky RPO | [5 empty] | 10000
I-5831A | Highway | Interstate Maintenance | I-26 | Tennessee state line to mile marker 9.0. | Rehabilitate bridges 560540, 560541, 560547, 560548, 560549. 560550, and 560551 and replace curb and drainage boxes. | 9.04 | Madison | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 8043000
I-5831A | Highway | Interstate Maintenance | I-26 | Tennessee state line to mile marker 9.0. | Rehabilitate bridges 560540, 560541, 560547, 560548, 560549. 560550, and 560551 and replace curb and drainage boxes. | 9.04 | Madison | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2011000
I-5831B | Highway | Interstate Maintenance | I-26 | Tennessee state line to mile marker 9.0. | Rehabilitate pavement. | 9.04 | Madison | 13 | Land-of-Sky RPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 23594000 | FY 2026: 7786000; FY 2027: 13212000; FY 2028: 2596000
I-5831B | Highway | Interstate Maintenance | I-26 | Tennessee state line to mile marker 9.0. | Rehabilitate pavement. | 9.04 | Madison | 13 | Land-of-Sky RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5896000 | FY 2026: 1946000; FY 2027: 3302000; FY 2028: 648000
I-5834 | Highway | Interstate Maintenance | I-40 | Mile marker 27.0 to mile marker 34.0. | Rehabilitate pavement. | 7 | Haywood | 14 | French Broad River MPO, Land-of-Sky RPO | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP. |  |  |  |  | 5000000
I-5834A | Highway | Interstate Maintenance | I-40 | Mile marker 27.0 to mile marker 30.0. | Rehabilitate pavement. | 3 | Haywood | 14 | French Broad River MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4733000
I-5834A | Highway | Interstate Maintenance | I-40 | Mile marker 27.0 to mile marker 30.0. | Rehabilitate pavement. | 3 | Haywood | 14 | French Broad River MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 2566000
I-5834B | Highway | Interstate Maintenance | I-40 | Mile marker 30.0 to mile marker 34.0 | Rehabilitate pavement. | 4 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13475000
I-5834B | Highway | Interstate Maintenance | I-40 | Mile marker 30.0 to mile marker 34.0 | Rehabilitate pavement. | 4 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 483000
I-5850 | Highway | Interstate Maintenance | I-95 | North of US 301 (mile marker 22) to Cumberland County line (mile marker 40). | Rehabilitate pavement. | 15.7 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO |  | Statewide Mobility |  |  |  | 19090000
I-5850A | Highway | Interstate Maintenance | I-95 | North of US 301 (mile marker 22) to Cumberland County line (mile marker 40). | Rehabilitate bridge and improve interstate. | 17.99 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | COMPLETE. | Statewide Mobility
I-5850B | Highway | Interstate Maintenance | I-95 | North of US 301 (mile marker 22) to Cumberland County line (mile marker 40). | Rehabilitate pavement. | 18.97 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility
I-5852 | Highway | Interstate Maintenance | I-73 | I-85 to SR 2085 (Bryan Boulevard) in Greensboro. | Rehabilitate pavement and bridge. | 10.7 | Guilford | 7 | Greensboro Urban Area MPO | [5 empty] | 20272000
I-5852A | Highway | Interstate Maintenance | I-73 / US 421 | I-85 to I-40. | Rehabilitate pavement. | 6.62 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
I-5852B | Highway | Interstate Maintenance | I-73 / I-840 | I-40 to SR 2085 (Bryan Boulevard). | Rehabilitate pavement. | 3.26 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
I-5858 | Highway | Interstate Maintenance | I-85 | US 29 / US 601 in China Grove to US 601 (Jake Alexander Boulevard) in Salisbury and from south of US 52 in Salisbury to north of SR 2120 (Long Ferry Road) in Spencer. | Rehabilitate pavement. | 1.08 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  |  |  | 11072000
I-5858 | Highway | Interstate Maintenance | I-85 | US 29 / US 601 in China Grove to US 601 (Jake Alexander Boulevard) in Salisbury and from south of US 52 in Salisbury to north of SR 2120 (Long Ferry Road) in Spencer. | Rehabilitate pavement. | 1.08 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  | NHPIM | GARVEE CON | 12012000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000
I-5861 | Highway | Interstate Maintenance | I-485 | Oakdale Road Interchange at mile marker 17.2. | Rehabilitate pavement and bridges 590955 and 590956. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 568000
I-5861 | Highway | Interstate Maintenance | I-485 | Oakdale Road Interchange at mile marker 17.2. | Rehabilitate pavement and bridges 590955 and 590956. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 142000
I-5861 | Highway | Interstate Maintenance | I-485 | Oakdale Road Interchange at mile marker 17.2. | Rehabilitate pavement and bridges 590955 and 590956. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1004000
I-5861 | Highway | Interstate Maintenance | I-485 | Oakdale Road Interchange at mile marker 17.2. | Rehabilitate pavement and bridges 590955 and 590956. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 252000
I-5864 | Highway | Interstate Maintenance | I-77 | Mile marker 71.8 to mile marker 75.8. | Rehabilitate pavement. | 2.08 | Yadkin | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | Statewide Mobility |  |  |  | 8000
I-5864 | Highway | Interstate Maintenance | I-77 | Mile marker 71.8 to mile marker 75.8. | Rehabilitate pavement. | 2.08 | Yadkin | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | Statewide Mobility |  | T(M) |  | 2000
I-5864 | Highway | Interstate Maintenance | I-77 | Mile marker 71.8 to mile marker 75.8. | Rehabilitate pavement. | 2.08 | Yadkin | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5028000 | FY 2028: 1206000; FY 2029: 2665000; FY 2030: 1157000
I-5864 | Highway | Interstate Maintenance | I-77 | Mile marker 71.8 to mile marker 75.8. | Rehabilitate pavement. | 2.08 | Yadkin | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1257000 | FY 2028: 302000; FY 2029: 666000; FY 2030: 289000
I-5865 | Highway | Interstate Maintenance | I-77 | Mile marker 75.8 to US 21 (Exit 79). | Rehabilitate pavement. | 1.89 | Yadkin | 11 | Northwest Piedmont RPO | COMBINE WITH I-5864 FOR LETTING. | Statewide Mobility |  |  |  | 50000
I-5865 | Highway | Interstate Maintenance | I-77 | Mile marker 75.8 to US 21 (Exit 79). | Rehabilitate pavement. | 1.89 | Yadkin | 11 | Northwest Piedmont RPO | COMBINE WITH I-5864 FOR LETTING. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2990000 | FY 2030: 957000; FY 2031: 1854000; FY 2032: 179000
I-5873 | Highway | STI (Prioritization) | I-40 | NC 54 interchange in Raleigh. | Improve interchange. | 1 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  |  |  | 4800000
I-5877 | Highway | STI (Prioritization) | I-95 | SR 1811 (Bud Hawkins Road) (Exit 70) and SR 1001 (Long Beach Road) (Exit 71). | Improve interchanges. | 1 | Harnett | 6 | Fayetteville Area MPO, Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 2649000
I-5877 | Highway | STI (Prioritization) | I-95 | SR 1811 (Bud Hawkins Road) (Exit 70) and SR 1001 (Long Beach Road) (Exit 71). | Improve interchanges. | 1 | Harnett | 6 | Fayetteville Area MPO, Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 3304000
I-5877 | Highway | STI (Prioritization) | I-95 | SR 1811 (Bud Hawkins Road) (Exit 70) and SR 1001 (Long Beach Road) (Exit 71). | Improve interchanges. | 1 | Harnett | 6 | Fayetteville Area MPO, Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 69733000
I-5878 | Highway | STI (Prioritization) | I-95 | US 421 (Exit 73) and SR 1793 (Pope Road) (Exit 72). | Improve interchanges. | 1 | Harnett | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 12000000
I-5878 | Highway | STI (Prioritization) | I-95 | US 421 (Exit 73) and SR 1793 (Pope Road) (Exit 72). | Improve interchanges. | 1 | Harnett | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 78860000 | FY 2026: 14500000; FY 2027: 3770000
I-5878A | Highway | STI (Prioritization) | I-95 | US 421 (Exit 73) and SR 1793 (Pope Road) (Exit 72). | Clear for utilities. |  | Harnett | 6 | Mid-Carolina RPO | COMPLETE. | Statewide Mobility |  | T | CONSTRUCTION | 139000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  |  |  | 912000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  | T(M) |  | 228000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  | NHP | RIGHT-OF-WAY | 6520000 | FY 2026: 6520000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  | T(M) | RIGHT-OF-WAY | 1630000 | FY 2026: 1630000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  | NHP | CONSTRUCTION | 12023000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (Carthage Road / West Carthage Road) (Exit 19). | Improve Interchange. | 1 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  | T(M) | CONSTRUCTION | 3005000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  |  |  | 1468000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T(M) |  | 367000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | RIGHT-OF-WAY | 2880000 | FY 2026: 288000; FY 2027: 288000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T(M) | RIGHT-OF-WAY | 720000 | FY 2026: 72000; FY 2027: 72000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | UTILITIES | 1120000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T(M) | UTILITIES | 280000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | CONSTRUCTION | 36000000 | FY 2026: 15140000; FY 2027: 7426000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (Thomasville Road) / Clemmonsville Road interchange in Winston-Salem. | Convert half diamond interchange at NC 109 (Thomasville Road) to full diamond, and remove connector roads and half diamond interchange at Clemmonsville Road. | 1 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T(M) | CONSTRUCTION | 9000000 | FY 2026: 3785000; FY 2027: 1857000
I-5883 | Highway | STI (Prioritization) | I-95 | SR 1808 (Jonesboro Road) (Exit 75) and SR 1709 (Hodges Chapel Road) (Exit 77). | Improve interchanges. | 1 | Harnett | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 8975000
I-5883 | Highway | STI (Prioritization) | I-95 | SR 1808 (Jonesboro Road) (Exit 75) and SR 1709 (Hodges Chapel Road) (Exit 77). | Improve interchanges. | 1 | Harnett | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 100613000 | FY 2026: 0; FY 2027: 4810000
I-5888 | Highway | Interstate Maintenance | I-40 | Mile marker 37.0 to mile marker 44.0. | Rehabilitate pavement and bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 6.5 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  |  |  | 12099000
I-5888A | Highway | Interstate Maintenance | I-40 | Mile marker 37.0 to mile marker 44.0. | Rehabilitate pavement and bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 6.73 | Buncombe | 13 | French Broad River MPO | COMPLETE | Statewide Mobility
I-5888B | Highway | Interstate Maintenance | I-40 | Mile marker 37.0 to mile marker 44.0. | Rehabilitate bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 7.17 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5520000 | FY 2027: 2594000; FY 2028: 2926000
I-5888B | Highway | Interstate Maintenance | I-40 | Mile marker 37.0 to mile marker 44.0. | Rehabilitate bridges 100024, 100071, 100156, 100164, 100210, and 100215. | 7.17 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1380000 | FY 2027: 649000; FY 2028: 731000
I-5889 | Highway | Interstate Maintenance | I-40 | Mile marker 44.0 to mile marker 50.0. | Rehabilitate pavement and preserve bridges 100334, 100339, 100344, 100347, 100352, 100356, 100358, 10036, 100369, 100374, 100377, and 1000378. | 4 | Buncombe | 13 | French Broad River MPO | [5 empty] | 10123000
I-5889A | Highway | Interstate Maintenance | I-40 | Mile marker 46.0 to mile marker 50.0. | Preserve bridges 100334, 100339, 100344, 100347, 100352, 100356, 100358, 10036, 100369, 100374, 100377, and 1000378. | 4.65 | Buncombe | 13 | French Broad River MPO | COMPLETE. | Statewide Mobility
I-5889B | Highway | Interstate Maintenance | I-40 | Mile marker 44.0 to mile marker 50.0. | Rehabilitate pavement and preserve bridges 100334, 100339, 100344, 100347, 100352, and 100356. | 4.62 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 35936000
I-5889B | Highway | Interstate Maintenance | I-40 | Mile marker 44.0 to mile marker 50.0. | Rehabilitate pavement and preserve bridges 100334, 100339, 100344, 100347, 100352, and 100356. | 4.62 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 4000000
I-5890 | Highway | Interstate Maintenance | I-40 | Mile marker 55.0 to mile marker 67.5. | Rehabilitate pavement. | 11.99 | Buncombe | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033. | Statewide Mobility |  |  |  | 15125000
I-5890 | Highway | Interstate Maintenance | I-40 | Mile marker 55.0 to mile marker 67.5. | Rehabilitate pavement. | 11.99 | Buncombe | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 23160000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000
I-5891 | Highway | Interstate Maintenance | I-40 | Mile marker 93.0 to mile marker 119.0. | Rehabilitate pavement and bridges 110139, 110140, 10149, and 110150. | 23.92 | Burke | 13 | Greater Hickory MPO | [5 empty] | 41542000
I-5891A | Highway | Interstate Maintenance | I-40 | Mile marker 93.0 to mile marker 119.0. | Rehabilitate pavement. | 25.73 | Burke | 13 | Greater Hickory MPO | COMPLETE | Statewide Mobility
I-5891B | Highway | Interstate Maintenance | I-40 | Mile marker 93.0 to mile marker 119.0. | Rehabilitate bridges 110139, 110140, 10149, and 110150. | 26.03 | Burke | 13 | Greater Hickory MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 3125000 | FY 2029: 1656000; FY 2030: 1469000
I-5891B | Highway | Interstate Maintenance | I-40 | Mile marker 93.0 to mile marker 119.0. | Rehabilitate bridges 110139, 110140, 10149, and 110150. | 26.03 | Burke | 13 | Greater Hickory MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 875000 | FY 2029: 464000; FY 2030: 411000
I-5898 | Highway | STI (Prioritization) | Future I-73 / US 220 | US 311 / NC 135 interchange near Mayodan. | Replace bridge 780074 and upgrade interchange. | 1 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  |  |  | 937000
I-5898 | Highway | STI (Prioritization) | Future I-73 / US 220 | US 311 / NC 135 interchange near Mayodan. | Replace bridge 780074 and upgrade interchange. | 1 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 1500000
I-5898 | Highway | STI (Prioritization) | Future I-73 / US 220 | US 311 / NC 135 interchange near Mayodan. | Replace bridge 780074 and upgrade interchange. | 1 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | UTILITIES | 1600000
I-5898 | Highway | STI (Prioritization) | Future I-73 / US 220 | US 311 / NC 135 interchange near Mayodan. | Replace bridge 780074 and upgrade interchange. | 1 | Rockingham | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 20900000 | FY 2026: 3553000; FY 2027: 8151000; FY 2028: 5225000; FY 2029: 2717000; FY 2030: 1254000
I-5900 | Highway | Interstate Maintenance | I-40 | Mile marker 73.0 to mile marker 86.0. | Rehabilitate pavement. | 12.99 | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  |  |  | 10000
I-5900 | Highway | Interstate Maintenance | I-40 | Mile marker 73.0 to mile marker 86.0. | Rehabilitate pavement. | 12.99 | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 12140000 | FY 2027: 2792000; FY 2028: 4006000; FY 2029: 3278000; FY 2030: 2064000
I-5900 | Highway | Interstate Maintenance | I-40 | Mile marker 73.0 to mile marker 86.0. | Rehabilitate pavement. | 12.99 | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7940000 | FY 2027: 1826000; FY 2028: 2620000; FY 2029: 2144000; FY 2030: 1350000
I-5900 | Highway | Interstate Maintenance | I-40 | Mile marker 73.0 to mile marker 86.0. | Rehabilitate pavement. | 12.99 | McDowell | 13 | Foothills RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5020000 | FY 2027: 1155000; FY 2028: 1657000; FY 2029: 1355000; FY 2030: 853000
I-5901 | Highway | Interstate Maintenance | I-240 | Mile marker 4.0 to mile marker 9.0. | Rehabilitate pavement. | 4.69 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  |  |  | 8000
I-5901 | Highway | Interstate Maintenance | I-240 | Mile marker 4.0 to mile marker 9.0. | Rehabilitate pavement. | 4.69 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  | T(M) |  | 2000
I-5901 | Highway | Interstate Maintenance | I-240 | Mile marker 4.0 to mile marker 9.0. | Rehabilitate pavement. | 4.69 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 16800000 | FY 2027: 3696000; FY 2028: 5544000; FY 2029: 4368000; FY 2030: 3192000
I-5901 | Highway | Interstate Maintenance | I-240 | Mile marker 4.0 to mile marker 9.0. | Rehabilitate pavement. | 4.69 | Buncombe | 13 | French Broad River MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 4200000 | FY 2027: 924000; FY 2028: 1386000; FY 2029: 1092000; FY 2030: 798000
I-5902 | Highway | Interstate Maintenance | I-485 | SR 1786 (Old Gum Branch Road) to NC 27. | Rehabilitate bridges 590945, 590946, and 590947. | 0.65 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 10000
I-5902 | Highway | Interstate Maintenance | I-485 | SR 1786 (Old Gum Branch Road) to NC 27. | Rehabilitate bridges 590945, 590946, and 590947. | 0.65 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1600000 | FY 2028: 16000; FY 2029: 1376000; FY 2030: 208000
I-5904 | Highway | Interstate Maintenance | I-485 | Blair Road to Idlewild Road. | Rehabilitate pavement. | 6.19 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  |  |  | 660000
I-5904 | Highway | Interstate Maintenance | I-485 | Blair Road to Idlewild Road. | Rehabilitate pavement. | 6.19 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 7785000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000
I-5904 | Highway | Interstate Maintenance | I-485 | Blair Road to Idlewild Road. | Rehabilitate pavement. | 6.19 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 2016000
I-5905 | Highway | Interstate Maintenance | I-85 | West of NC 16 (Brookshire Boulevard) to concrete pavement joint at US 29 / NC 49 Connector. | Rehabilitate pavement. | 2 | Mecklenburg | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 100000
I-5905 | Highway | Interstate Maintenance | I-85 | West of NC 16 (Brookshire Boulevard) to concrete pavement joint at US 29 / NC 49 Connector. | Rehabilitate pavement. | 2 | Mecklenburg | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3067000
I-5905 | Highway | Interstate Maintenance | I-85 | West of NC 16 (Brookshire Boulevard) to concrete pavement joint at US 29 / NC 49 Connector. | Rehabilitate pavement. | 2 | Mecklenburg | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 13217000
I-5905 | Highway | Interstate Maintenance | I-85 | West of NC 16 (Brookshire Boulevard) to concrete pavement joint at US 29 / NC 49 Connector. | Rehabilitate pavement. | 2 | Mecklenburg | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 3304000
I-5907 | Highway | Interstate Maintenance | I-74 | I-77 to US 601. | Rehabilitate pavement. | 6.28 | Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 8000
I-5907 | Highway | Interstate Maintenance | I-74 | I-77 to US 601. | Rehabilitate pavement. | 6.28 | Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 2000
I-5907 | Highway | Interstate Maintenance | I-74 | I-77 to US 601. | Rehabilitate pavement. | 6.28 | Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 4435000
I-5907 | Highway | Interstate Maintenance | I-74 | I-77 to US 601. | Rehabilitate pavement. | 6.28 | Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1108000
I-5912 | Highway | Interstate Maintenance | I-77 | US 21 in Yadkin County (Exit 79) to mile marker 83.4 in Surry County. | Rehabilitate pavement. | 4.36 | Yadkin, Surry | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 57425000
I-5915 | Highway | Interstate Maintenance | I-40 | Mile marker 130.7 to mile marker 150.2. | Rehabilitate pavement and bridge. | 19.5 | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | [5 empty] | 13150000
I-5915A | Highway | Interstate Maintenance | I-40 | East of SR 1007 (1st Street West) to East of NC 115. | Rehabilitate pavement. | 32.62 | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | COMPLETE | Statewide Mobility
I-5915B | Highway | Interstate Maintenance | I-40 | East of SR 1007 (1st Street West) to East of NC 115. | Rehabilitate bridge. |  | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2553000 | FY 2026: 400000
I-5915B | Highway | Interstate Maintenance | I-40 | East of SR 1007 (1st Street West) to East of NC 115. | Rehabilitate bridge. |  | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 7319000
I-5915B | Highway | Interstate Maintenance | I-40 | East of SR 1007 (1st Street West) to East of NC 115. | Rehabilitate bridge. |  | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2368000
I-5918 | Highway | Interstate Maintenance | I-77 | Mile marker 36.5 to mile marker 50.0. | Rehabilitate pavement. | 13.55 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 10000
I-5918 | Highway | Interstate Maintenance | I-77 | Mile marker 36.5 to mile marker 50.0. | Rehabilitate pavement. | 13.55 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 7570000
I-5918 | Highway | Interstate Maintenance | I-77 | Mile marker 36.5 to mile marker 50.0. | Rehabilitate pavement. | 13.55 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 14237000 | FY 2026: 4814000; FY 2027: 1519000
I-5918 | Highway | Interstate Maintenance | I-77 | Mile marker 36.5 to mile marker 50.0. | Rehabilitate pavement. | 13.55 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | PROTCT | CONSTRUCTION | 8394000 | FY 2026: 2838000; FY 2027: 896000
I-5919 | Highway | Interstate Maintenance | I-77 | Mile marker 52.6 to mile marker 56.8. | Rehabilitate pavement. | 3.1 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 10000
I-5919 | Highway | Interstate Maintenance | I-77 | Mile marker 52.6 to mile marker 56.8. | Rehabilitate pavement. | 3.1 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8773000 | FY 2026: 4017000; FY 2027: 992000
I-5920 | Highway | Interstate Maintenance | I-77 | Mile marker 58.4 to Yadkin County line. | Rehabilitate pavement. | 10.41 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 10000
I-5920 | Highway | Interstate Maintenance | I-77 | Mile marker 58.4 to Yadkin County line. | Rehabilitate pavement. | 10.41 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 10000000 | FY 2028: 2100000; FY 2029: 3400000; FY 2030: 2600000; FY 2031: 1900000
I-5920 | Highway | Interstate Maintenance | I-77 | Mile marker 58.4 to Yadkin County line. | Rehabilitate pavement. | 10.41 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 14302000 | FY 2028: 3003000; FY 2029: 4863000; FY 2030: 3719000; FY 2031: 2717000
I-5921 | Highway | Interstate Maintenance | I-85 | Cleveland County line to mile marker 14.0. | Rehabilitate pavement. | 5.91 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  |  |  | 10000
I-5921 | Highway | Interstate Maintenance | I-85 | Cleveland County line to mile marker 14.0. | Rehabilitate pavement. | 5.91 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 21120000 | FY 2027: 4013000; FY 2028: 8026000; FY 2029: 5702000; FY 2030: 3379000
I-5921 | Highway | Interstate Maintenance | I-85 | Cleveland County line to mile marker 14.0. | Rehabilitate pavement. | 5.91 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5280000 | FY 2027: 1003000; FY 2028: 2006000; FY 2029: 1426000; FY 2030: 845000
I-5924 | Highway | Interstate Maintenance | I-40 | Mile marker 15.0 to mile marker 20.5. | Rehabilitate pavement. | 5.5 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  |  |  | 10000
I-5924 | Highway | Interstate Maintenance | I-40 | Mile marker 15.0 to mile marker 20.5. | Rehabilitate pavement. | 5.5 | Haywood | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10900000 | FY 2028: 2289000; FY 2029: 4251000; FY 2030: 2943000; FY 2031: 1417000
I-5925 | Highway | Interstate Maintenance | I-26 | Mile marker 50.0 to Polk County line. | Rehabilitate pavement. | 7.96 | Henderson | 14 | French Broad River MPO |  | Statewide Mobility |  |  |  | 800000
I-5925 | Highway | Interstate Maintenance | I-26 | Mile marker 50.0 to Polk County line. | Rehabilitate pavement. | 7.96 | Henderson | 14 | French Broad River MPO |  | Statewide Mobility |  | T(M) |  | 200000
I-5925 | Highway | Interstate Maintenance | I-26 | Mile marker 50.0 to Polk County line. | Rehabilitate pavement. | 7.96 | Henderson | 14 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12160000 | FY 2027: 2554000; FY 2028: 4742000; FY 2029: 3283000; FY 2030: 1581000
I-5925 | Highway | Interstate Maintenance | I-26 | Mile marker 50.0 to Polk County line. | Rehabilitate pavement. | 7.96 | Henderson | 14 | French Broad River MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 3040000 | FY 2027: 638000; FY 2028: 1186000; FY 2029: 821000; FY 2030: 395000
I-5926 | Highway | Interstate Maintenance | I-26 | Henderson County line to mile marker 65.0. | Rehabilitate pavement. | 7.05 | Polk | 14 | Foothills RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 15760000 | FY 2027: 3310000; FY 2028: 6462000; FY 2029: 4254000; FY 2030: 1734000
I-5926 | Highway | Interstate Maintenance | I-26 | Henderson County line to mile marker 65.0. | Rehabilitate pavement. | 7.05 | Polk | 14 | Foothills RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 3940000 | FY 2027: 828000; FY 2028: 1615000; FY 2029: 1064000; FY 2030: 433000
I-5927 | Highway | Interstate Maintenance | I-26 | Mile marker 65.0 to South Carolina state line. | Rehabilitate pavement. | 6.06 | Polk | 14 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 800000
I-5927 | Highway | Interstate Maintenance | I-26 | Mile marker 65.0 to South Carolina state line. | Rehabilitate pavement. | 6.06 | Polk | 14 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 200000
I-5927 | Highway | Interstate Maintenance | I-26 | Mile marker 65.0 to South Carolina state line. | Rehabilitate pavement. | 6.06 | Polk | 14 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 17279000
I-5927 | Highway | Interstate Maintenance | I-26 | Mile marker 65.0 to South Carolina state line. | Rehabilitate pavement. | 6.06 | Polk | 14 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 4321000
I-5928 | Highway | Interstate Maintenance | I-40 | Mile marker 34.0 to Buncombe County line. | Rehabilitate pavement. | 2.74 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  |  |  | 1000000
I-5928 | Highway | Interstate Maintenance | I-40 | Mile marker 34.0 to Buncombe County line. | Rehabilitate pavement. | 2.74 | Haywood | 14 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8749000 | FY 2030: 2362000; FY 2031: 4112000; FY 2032: 2275000
I-5932 | Highway | Interstate Maintenance | I-95 | NC 481 (mile marker 154) to mile marker 167. | Rehabilitate pavement. | 18 | Halifax | 4 | Peanut Belt RPO | [5 empty] | 110000
I-5932A | Highway | Interstate Maintenance | I-95 | NC 561 (mile marker 160) to mile marker 167. | Rehabilitate pavement. | 7.19 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 7675000
I-5932A | Highway | Interstate Maintenance | I-95 | NC 561 (mile marker 160) to mile marker 167. | Rehabilitate pavement. | 7.19 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1918000
I-5932B | Highway | Interstate Maintenance | I-95 | NC 481 (mile marker 154) to NC 561 (mile marker 160) | Rehabilitate pavement. | 6.83 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 6578000
I-5932B | Highway | Interstate Maintenance | I-95 | NC 481 (mile marker 154) to NC 561 (mile marker 160) | Rehabilitate pavement. | 6.83 | Halifax | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1645000
I-5934 | Highway | Interstate Maintenance | I-95 | Mile marker 137.4 to mile marker 142.1. | Rehabilitate bridge and pavement. | 3.92 | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  |  |  | 100000
I-5934 | Highway | Interstate Maintenance | I-95 | Mile marker 137.4 to mile marker 142.1. | Rehabilitate bridge and pavement. | 3.92 | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1125000 | FY 2026: 11000; FY 2027: 844000; FY 2028: 270000
I-5934 | Highway | Interstate Maintenance | I-95 | Mile marker 137.4 to mile marker 142.1. | Rehabilitate bridge and pavement. | 3.92 | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 4375000 | FY 2026: 44000; FY 2027: 3281000; FY 2028: 1050000
I-5939 | Highway | Interstate Maintenance | I-95 | South Carolina state line (mile marker 0.0) to I-74 (mile marker 13). | Rehabilitate pavement. | 5.49 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 8000
I-5939 | Highway | Interstate Maintenance | I-95 | South Carolina state line (mile marker 0.0) to I-74 (mile marker 13). | Rehabilitate pavement. | 5.49 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 2000
I-5939 | Highway | Interstate Maintenance | I-95 | South Carolina state line (mile marker 0.0) to I-74 (mile marker 13). | Rehabilitate pavement. | 5.49 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGIM | CONSTRUCTION | 19119000
I-5939 | Highway | Interstate Maintenance | I-95 | South Carolina state line (mile marker 0.0) to I-74 (mile marker 13). | Rehabilitate pavement. | 5.49 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 4779000
I-5940 | Highway | Interstate Maintenance | I-40 | Duplin County line (mile marker 360) to west of US 117 (mile marker 390). | Rehabilitate bridge and pavement. | 35.89 | Duplin, Pender | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | Statewide Mobility |  | BGIM | GARVEE CON | 28826000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000
I-5940 | Highway | Interstate Maintenance | I-40 | Duplin County line (mile marker 360) to west of US 117 (mile marker 390). | Rehabilitate bridge and pavement. | 35.89 | Duplin, Pender | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | Statewide Mobility |  | BGIM | CONSTRUCTION | 750000
I-5941 | Highway | Interstate Maintenance | I-85 | Orange County line to US 15 / US 501 in Durham. | Rehabilitate pavement. | 2.49 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1614000
I-5941 | Highway | Interstate Maintenance | I-85 | Orange County line to US 15 / US 501 in Durham. | Rehabilitate pavement. | 2.49 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 11875000
I-5943 | Highway | Interstate Maintenance | I-40 | SR 1728 (Wade Avenue) to I-440 / US 1 in Raleigh. | Rehabilitate pavement and bridge. | 3.84 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 8000
I-5943 | Highway | Interstate Maintenance | I-40 | SR 1728 (Wade Avenue) to I-440 / US 1 in Raleigh. | Rehabilitate pavement and bridge. | 3.84 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) |  | 2000
I-5943 | Highway | Interstate Maintenance | I-40 | SR 1728 (Wade Avenue) to I-440 / US 1 in Raleigh. | Rehabilitate pavement and bridge. | 3.84 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 14735000
I-5943 | Highway | Interstate Maintenance | I-40 | SR 1728 (Wade Avenue) to I-440 / US 1 in Raleigh. | Rehabilitate pavement and bridge. | 3.84 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 3684000
I-5944 | Highway | Interstate Maintenance | I-87 / US 64 / US 264 | I-440 in Raleigh to SR 1003 (Rolesville Road). | Rehabilitate pavement. | 9.91 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 22880000 | FY 2031: 5720000; FY 2032: 6864000; FY 2033: 5262000; FY 2034: 3661000; FY 2035: 1373000
I-5944 | Highway | Interstate Maintenance | I-87 / US 64 / US 264 | I-440 in Raleigh to SR 1003 (Rolesville Road). | Rehabilitate pavement. | 9.91 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5720000 | FY 2031: 1430000; FY 2032: 1716000; FY 2033: 1316000; FY 2034: 915000; FY 2035: 343000
I-5945 | Highway | Interstate Maintenance | I-540 | Triangle Towne Center Boulevard in Raleigh to I-495 / US 64 / US 264 in Knightdale. | Rehabilitate pavement. | 8.97 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 22320000 | FY 2031: 5134000; FY 2032: 6473000; FY 2033: 5357000; FY 2034: 3794000; FY 2035: 1562000
I-5945 | Highway | Interstate Maintenance | I-540 | Triangle Towne Center Boulevard in Raleigh to I-495 / US 64 / US 264 in Knightdale. | Rehabilitate pavement. | 8.97 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5580000 | FY 2031: 1283000; FY 2032: 1618000; FY 2033: 1339000; FY 2034: 949000; FY 2035: 391000
I-5946 | Highway | Interstate Maintenance | I-73 / I-74 | South of US 220 / SR 1446 (Haywood Cemetery Road) to Montgomery County line. | Rehabilitate pavement. | 10.5 | Richmond | 8 | Lumber River RPO | [5 empty] | 3718000
I-5946A | Highway | Interstate Maintenance | I-73/I-74 | South of US 220 / SR 1446 (Haywood Cemetery Road) to SR 1455 (Fire Tower Road). | Rehabilitate pavement. | 3.23 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION - LET WITH I-5947B | Statewide Mobility
I-5946B | Highway | Interstate Maintenance | I-73/I-74 | SR 1455 (Fire Tower Road) to Montgomery County line. | Rehabilitate pavement. | 6.86 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | BGIM | CONSTRUCTION | 5450000
I-5946B | Highway | Interstate Maintenance | I-73/I-74 | SR 1455 (Fire Tower Road) to Montgomery County line. | Rehabilitate pavement. | 6.86 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 1362000
I-5947 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | Montgomery County line To Randolph County line. | Rehabilitate pavement. | 24.5 | Montgomery | 8 | Piedmont Triad RPO | [5 empty] | 4735000
I-5947A | Highway | Interstate Maintenance | I-73 / I-74 | Montgomery County line to NC 211. | Rehabilitate pavement. | 8.92 | Montgomery | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | BGIM | CONSTRUCTION | 15839000 | FY 2027: 3326000; FY 2028: 5702000; FY 2029: 4118000; FY 2030: 2693000
I-5947A | Highway | Interstate Maintenance | I-73 / I-74 | Montgomery County line to NC 211. | Rehabilitate pavement. | 8.92 | Montgomery | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 3961000 | FY 2027: 832000; FY 2028: 1426000; FY 2029: 1030000; FY 2030: 673000
I-5947B | Highway | Interstate Maintenance | I-73 / I-74 | NC 211 to NC 24 / NC 27. | Rehabilitate pavement. | 5.05 | Montgomery | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH I-5946A | Statewide Mobility |  | BGIM | CONSTRUCTION | 5520000
I-5947B | Highway | Interstate Maintenance | I-73 / I-74 | NC 211 to NC 24 / NC 27. | Rehabilitate pavement. | 5.05 | Montgomery | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH I-5946A | Statewide Mobility |  | T(M) | CONSTRUCTION | 1380000
I-5947C | Highway | Interstate Maintenance | I-73 / I-74 | NC 24 / NC 27 to Randolph County line. | Rehabilitate pavement. | 10.51 | Montgomery | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | BGIM | CONSTRUCTION | 14081000 | FY 2028: 2957000; FY 2029: 5069000; FY 2030: 3661000; FY 2031: 2394000
I-5947C | Highway | Interstate Maintenance | I-73 / I-74 | NC 24 / NC 27 to Randolph County line. | Rehabilitate pavement. | 10.51 | Montgomery | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 3519000 | FY 2028: 739000; FY 2029: 1267000; FY 2030: 915000; FY 2031: 598000
I-5948 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | Montgomery County line to north of SR 1462 (Park Drive) in Asheboro. | Rehabilitate pavement. | 15.72 | Randolph | 8 | Piedmont Triad RPO |  | Statewide Mobility |  |  |  | 666000
I-5948 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | Montgomery County line to north of SR 1462 (Park Drive) in Asheboro. | Rehabilitate pavement. | 15.72 | Randolph | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | T(M) |  | 166000
I-5948 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | Montgomery County line to north of SR 1462 (Park Drive) in Asheboro. | Rehabilitate pavement. | 15.72 | Randolph | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 21360000 | FY 2028: 3845000; FY 2029: 6408000; FY 2030: 5340000; FY 2031: 3845000; FY 2032: 1922000
I-5948 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | Montgomery County line to north of SR 1462 (Park Drive) in Asheboro. | Rehabilitate pavement. | 15.72 | Randolph | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5340000 | FY 2028: 961000; FY 2029: 1602000; FY 2030: 1335000; FY 2031: 961000; FY 2032: 481000
I-5950 | Highway | Interstate Maintenance | I-85 | I-285 / US 29 / US 52 / US 70 to north of US 64. | Rehabilitate pavement. | 9.58 | Davidson | 9 | High Point Urban Area MPO |  | Statewide Mobility |  |  |  | 8000
I-5950 | Highway | Interstate Maintenance | I-85 | I-285 / US 29 / US 52 / US 70 to north of US 64. | Rehabilitate pavement. | 9.58 | Davidson | 9 | High Point Urban Area MPO |  | Statewide Mobility |  | T(M) |  | 2000
I-5950 | Highway | Interstate Maintenance | I-85 | I-285 / US 29 / US 52 / US 70 to north of US 64. | Rehabilitate pavement. | 9.58 | Davidson | 9 | High Point Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 22834000
I-5950 | Highway | Interstate Maintenance | I-85 | I-285 / US 29 / US 52 / US 70 to north of US 64. | Rehabilitate pavement. | 9.58 | Davidson | 9 | High Point Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 5708000
I-5953 | Highway | Interstate Maintenance | I-785 / I-840 | I-85 to US 70. | Rehabilitate pavement. | 2.14 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 2675000
I-5955 | Highway | Interstate Maintenance | I-40 | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate pavement. | 5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | Statewide Mobility |  |  |  | 120000
I-5955 | Highway | Interstate Maintenance | I-40 | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate pavement. | 5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | Statewide Mobility |  | T(M) |  | 30000
I-5955 | Highway | Interstate Maintenance | I-40 | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate pavement. | 5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10579000
I-5955 | Highway | Interstate Maintenance | I-40 | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate pavement. | 5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | Statewide Mobility |  | T(M) | CONSTRUCTION | 2645000
I-5955A | Highway | Interstate Maintenance | I-40 | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate bridges 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, and 400285. | 5.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6640000 | FY 2026: 424000
I-5955A | Highway | Interstate Maintenance | I-40 | South Buffalo Creek bridge east of US 220 (Freeman Mill Road) to east of SR 3037 / SR 4240 (East Gate City Boulevard) in Greensboro. | Rehabilitate bridges 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, and 400285. | 5.01 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1660000 | FY 2026: 106000
I-5958 | Highway | Interstate Maintenance | I-40 / I-85 | West of SR 1114 (Buckhorn Road) to west of SR 1006 (Orange Grove Road). | Rehabilitate pavement. | 6.74 | Orange | 7 | Triangle West TPO, Burlington-Graham MPO |  | Statewide Mobility |  |  |  | 150000
I-5958 | Highway | Interstate Maintenance | I-40 / I-85 | West of SR 1114 (Buckhorn Road) to west of SR 1006 (Orange Grove Road). | Rehabilitate pavement. | 6.74 | Orange | 7 | Triangle West TPO, Burlington-Graham MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 9288000 | FY 2027: 4458000; FY 2028: 3437000; FY 2029: 1393000
I-5958 | Highway | Interstate Maintenance | I-40 / I-85 | West of SR 1114 (Buckhorn Road) to west of SR 1006 (Orange Grove Road). | Rehabilitate pavement. | 6.74 | Orange | 7 | Triangle West TPO, Burlington-Graham MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 212000 | FY 2027: 102000; FY 2028: 78000; FY 2029: 32000
I-5962 | Highway | STI (Prioritization) | I-77 | SR 1302 (Cornelius Road). | Upgrade grade separation to an interchange. | 1 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 2500000
I-5962 | Highway | STI (Prioritization) | I-77 | SR 1302 (Cornelius Road). | Upgrade grade separation to an interchange. | 1 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 7000000 | FY 2028: 70000; FY 2029: 2520000; FY 2030: 3010000; FY 2031: 700000; FY 2032: 700000
I-5962 | Highway | STI (Prioritization) | I-77 | SR 1302 (Cornelius Road). | Upgrade grade separation to an interchange. | 1 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | UTILITIES | 630000 | FY 2028: 630000
I-5962 | Highway | STI (Prioritization) | I-77 | SR 1302 (Cornelius Road). | Upgrade grade separation to an interchange. | 1 | Iredell | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 58960000 | FY 2031: 590000; FY 2032: 15919000; FY 2033: 15919000; FY 2034: 14150000; FY 2035: 12382000
I-5964 | Highway | STI (Prioritization) | I-40 / Business 85 / US 29 / US 70 / US 220 | Elm Eugene Street interchange in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  |  |  | 200000
I-5964 | Highway | STI (Prioritization) | I-40 / Business 85 / US 29 / US 70 / US 220 | Elm Eugene Street interchange in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) |  | 50000
I-5964 | Highway | STI (Prioritization) | I-40 / Business 85 / US 29 / US 70 / US 220 | Elm Eugene Street interchange in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 960000 | FY 2026: 465000
I-5964 | Highway | STI (Prioritization) | I-40 / Business 85 / US 29 / US 70 / US 220 | Elm Eugene Street interchange in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(DA) | CONSTRUCTION | 332000 | FY 2026: 332000
I-5964 | Highway | STI (Prioritization) | I-40 / Business 85 / US 29 / US 70 / US 220 | Elm Eugene Street interchange in Greensboro. | Improve interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 240000 | FY 2026: 116000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 800000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) |  | 200000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 26320000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 6580000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 13200000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 3300000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 196640000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (Freeman Mill Road) to US 29 / US 70 / US 220 in Greensboro. | Construct additional lanes, improve SR 1007 (Randleman Road) and Elm Eugene Street interchanges, and replace Norfolk Southern Railroad bridge overpass east of Elm Eugene Street. | 2.87 | Guilford | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 49160000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  |  |  | 400000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) |  | 100000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 344000 | FY 2029: 344000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 86000 | FY 2029: 86000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 160000 | FY 2029: 160000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | UTILITIES | 40000 | FY 2029: 40000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 58960000 | FY 2032: 11792000; FY 2033: 14740000; FY 2034: 12971000; FY 2035: 10613000 | 8844000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (Aviation Parkway) to SR 1652 (Harrison Avenue) in Cary. | Construct auxiliary lanes in both directions. | 2.33 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 14740000 | FY 2032: 2948000; FY 2033: 3685000; FY 2034: 3243000; FY 2035: 2653000 | 2211000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  |  |  | 912000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) |  | 228000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 3760000 | FY 2028: 1241000; FY 2029: 1617000; FY 2030: 150000; FY 2031: 376000; FY 2032: 376000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 940000 | FY 2028: 310000; FY 2029: 404000; FY 2030: 38000; FY 2031: 94000; FY 2032: 94000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 16000 | FY 2028: 16000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | UTILITIES | 4000 | FY 2028: 4000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 28560000 | FY 2031: 7140000; FY 2032: 7997000; FY 2033: 6283000; FY 2034: 4570000; FY 2035: 2570000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 to SR 1829 (Leesville Road) in Raleigh. | Construct eastbound auxiliary lane. | 2.53 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 7140000 | FY 2031: 1785000; FY 2032: 1999000; FY 2033: 1571000; FY 2034: 1142000; FY 2035: 643000
I-5972 | Highway | STI (Prioritization) | I-95 | US 70 Business interchange. | Upgrade interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  |  |  | 4700000
I-5972 | Highway | STI (Prioritization) | I-95 | US 70 Business interchange. | Upgrade interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  | NHP | CONSTRUCTION | 43182000 | FY 2026: 6882000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  |  |  | 2200000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  | T | UTILITIES | 195000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  | T | BUILD NC CON | 2040000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  | T | CONSTRUCTION | 4770000 | FY 2026: 350000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701 / NC 96 intersection in Four Oaks | Construct interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | PROJECT TO BE LET WITH B-6044 AND HB-0042. | Region A |  |  |  | 2000000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701 / NC 96 intersection in Four Oaks | Construct interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | PROJECT TO BE LET WITH B-6044 AND HB-0042. | Region A |  | NHP | RIGHT-OF-WAY | 5300000 | FY 2026: 1231000; FY 2027: 1641000; FY 2028: 1368000; FY 2029: 530000; FY 2030: 530000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701 / NC 96 intersection in Four Oaks | Construct interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | PROJECT TO BE LET WITH B-6044 AND HB-0042. | Region A |  | NHP | UTILITIES | 1700000 | FY 2026: 850000; FY 2027: 850000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701 / NC 96 intersection in Four Oaks | Construct interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | PROJECT TO BE LET WITH B-6044 AND HB-0042. | Region A |  | NHFP | CONSTRUCTION | 11700000 | FY 2029: 117000; FY 2030: 3861000; FY 2031: 3042000; FY 2032: 2574000; FY 2033: 2106000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701 / NC 96 intersection in Four Oaks | Construct interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO | PROJECT TO BE LET WITH B-6044 AND HB-0042. | Region A |  | NHP | CONSTRUCTION | 64300000 | FY 2029: 618000; FY 2030: 20394000; FY 2031: 16068000; FY 2032: 16096000; FY 2033: 11124000
I-5979 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 1 (Exit 311) interchange near Rockingham. | Improve interchange. | 1 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Division 8 |  |  |  | 1092000
I-5979 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 1 (Exit 311) interchange near Rockingham. | Improve interchange. | 1 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Division 8 |  | NHP | RIGHT-OF-WAY | 500000
I-5979 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 1 (Exit 311) interchange near Rockingham. | Improve interchange. | 1 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Division 8 |  | NHP | UTILITIES | 210000
I-5979 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 1 (Exit 311) interchange near Rockingham. | Improve interchange. | 1 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Division 8 |  | NHP | CONSTRUCTION | 9810000 | FY 2026: 5528000
I-5981 | Highway | STI (Prioritization) | I-40 | I -74 / US 311 in Winston-Salem to US 421 (Future I-685) / I-40 Business in Guilford County. | Widen to six lanes. | 10.1 | Forsyth, Guilford | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO | [5 empty] | 2010000
I-5981A | Highway | STI (Prioritization) | I-40 | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 960000 | [10 empty] | 960000
I-5981A | Highway | STI (Prioritization) | I-40 | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 240000 | [10 empty] | 240000
I-5981A | Highway | STI (Prioritization) | I-40 | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | UTILITIES | 17360000 | [10 empty] | 17360000
I-5981A | Highway | STI (Prioritization) | I-40 | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T(M) | UTILITIES | 4340000 | [10 empty] | 4340000
I-5981A | Highway | STI (Prioritization) | I-40 | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | CONSTRUCTION | 69601000 | [10 empty] | 69601000
I-5981A | Highway | STI (Prioritization) | I-40 | I-74 / US 311 to SR 2643 (Union Cross Road) | Widen to six lanes. | 4.5 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T(M) | CONSTRUCTION | 17400000 | [10 empty] | 17400000
I-5981B | Highway | STI (Prioritization) | I-40 | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 160000 | [10 empty] | 160000
I-5981B | Highway | STI (Prioritization) | I-40 | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 40000 | [10 empty] | 40000
I-5981B | Highway | STI (Prioritization) | I-40 | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | UTILITIES | 480000 | [10 empty] | 480000
I-5981B | Highway | STI (Prioritization) | I-40 | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T(M) | UTILITIES | 120000 | [10 empty] | 120000
I-5981B | Highway | STI (Prioritization) | I-40 | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | CONSTRUCTION | 35200000 | [10 empty] | 35200000
I-5981B | Highway | STI (Prioritization) | I-40 | SR 2643 (Union Cross Road) to NC 66. | Widen to six lanes. | 2.8 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T(M) | CONSTRUCTION | 8800000 | [10 empty] | 8800000
I-5981C | Highway | STI (Prioritization) | I-40 | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Guilford, Forsyth | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 2560000 | [10 empty] | 2560000
I-5981C | Highway | STI (Prioritization) | I-40 | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Guilford, Forsyth | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 640000 | [10 empty] | 640000
I-5981C | Highway | STI (Prioritization) | I-40 | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Guilford, Forsyth | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | NHP | UTILITIES | 720000 | [10 empty] | 720000
I-5981C | Highway | STI (Prioritization) | I-40 | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Guilford, Forsyth | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T(M) | UTILITIES | 180000 | [10 empty] | 180000
I-5981C | Highway | STI (Prioritization) | I-40 | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Guilford, Forsyth | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | NHP | CONSTRUCTION | 90000000 | [10 empty] | 90000000
I-5981C | Highway | STI (Prioritization) | I-40 | NC 66 to US 421 / I-40 Business. | Widen to six lanes. | 2.83 | Guilford, Forsyth | 7, 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T(M) | CONSTRUCTION | 22500000 | [10 empty] | 22500000
I-5986 | Highway | STI (Prioritization) | I-95 | I-95 Business / US 301 (Exit 56) to I-40 (Exit 81). | Widen to eight lanes. | 26 | Cumberland, Harnett, Johnston | 4, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Upper Coastal Plain RPO | [5 empty] | 143850000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 Business / US 301 (Exit 56) to SR 1001 (Long Branch Road) (Exit 71). | Widen to eight lanes. | 15.76 | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 21073000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 Business / US 301 (Exit 56) to SR 1001 (Long Branch Road) (Exit 71). | Widen to eight lanes. | 15.76 | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | UTILITIES | 2000000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 Business / US 301 (Exit 56) to SR 1001 (Long Branch Road) (Exit 71). | Widen to eight lanes. | 15.76 | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | NHP | CONSTRUCTION | 18000000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 Business / US 301 (Exit 56) to SR 1001 (Long Branch Road) (Exit 71). | Widen to eight lanes. | 15.76 | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 375400000 | FY 2026: 15000000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 Business / US 301 (Exit 56) to SR 1001 (Long Branch Road) (Exit 71). | Widen to eight lanes. | 15.76 | Cumberland, Harnett | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 32000000
I-5986B | Highway | STI (Prioritization) | I-95 | SR 1002 (Long Branch Road) (Exit 71) to I-40 (Exit 81). | Widen to eight lanes. | 10.72 | Harnett, Johnston | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | Statewide Mobility |  | T | RIGHT-OF-WAY | 42400000 | FY 2026: 300000
I-5986B | Highway | STI (Prioritization) | I-95 | SR 1002 (Long Branch Road) (Exit 71) to I-40 (Exit 81). | Widen to eight lanes. | 10.72 | Harnett, Johnston | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | Statewide Mobility |  | T | UTILITIES | 700000
I-5986B | Highway | STI (Prioritization) | I-95 | SR 1002 (Long Branch Road) (Exit 71) to I-40 (Exit 81). | Widen to eight lanes. | 10.72 | Harnett, Johnston | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | Statewide Mobility |  | T | CONSTRUCTION | 92456000 | FY 2026: 17000000; FY 2027: 19420000
I-5986BA | Highway | STI (Prioritization) | I-95 | SR 1001 (Long Branch Road) (Exit 71) to I-40 (Exit 81). | Clear for utilities. | 10.72 | Harnett, Johnston | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 144000
I-5986C | Highway | Other | I-95 | South Carolina state line to Virginia state line. | Install broadband fiber for traveler information systems. | 181.34 | Robeson, Cumberland, Johnston, Nash, Halifax, Wilson, Harnett, Northampton | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | DP | CONSTRUCTION | 16600000
I-5986C | Highway | Other | I-95 | South Carolina state line to Virginia state line. | Install broadband fiber for traveler information systems. | 181.34 | Robeson, Cumberland, Johnston, Nash, Halifax, Wilson, Harnett, Northampton | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 25567000
I-5987 | Highway | STI (Prioritization) | I-95 | South of US 301 to south of proposed I-295. | Widen to eight lanes. | 15.7 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. AA BREAK: O FUNDS REPRESENT WEIGH STATION FUNDING. | Region C |  |  |  | 1010000
I-5987A | Highway | STI (Prioritization) | I-95 | South of US 301 to south of NC 20. | Widen to eight lanes. | 10.24 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | RIGHT-OF-WAY | 3395000
I-5987A | Highway | STI (Prioritization) | I-95 | South of US 301 to south of NC 20. | Widen to eight lanes. | 10.24 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | UTILITIES | 3075000
I-5987A | Highway | STI (Prioritization) | I-95 | South of US 301 to south of NC 20. | Widen to eight lanes. | 10.24 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 170790000 | 11386000 | 11386000 | 11386000 | 11386000 | 11386000 | 11386000 | 11386000 | 11386000 | 11386000 | 11386000 | 32958000
I-5987A | Highway | STI (Prioritization) | I-95 | South of US 301 to south of NC 20. | Widen to eight lanes. | 10.24 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | CONSTRUCTION | 153079000 | FY 2026: 26816000; FY 2027: 42612000
I-5987AA | Highway | STI (Prioritization) | I-95 | North of Lumberton. | Construct weigh in motion station. | 2 | Robeson | 6 | Lumber River RPO | O FUNDS REPRESENT STATE PRIMARY MAINTENANCE FUNDS FOR WEIGH STATIONS. | Region C |  | O | CONSTRUCTION | 4500000 | FY 2028: 4500000
I-5987B | Highway | STI (Prioritization) | I-95 | South of NC 20 to south of proposed I-295. | Widen to eight lanes. | 6.28 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | RIGHT-OF-WAY | 3581000
I-5987B | Highway | STI (Prioritization) | I-95 | South of NC 20 to south of proposed I-295. | Widen to eight lanes. | 6.28 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | UTILITIES | 2624000
I-5987B | Highway | STI (Prioritization) | I-95 | South of NC 20 to south of proposed I-295. | Widen to eight lanes. | 6.28 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 181110000 | 12074000 | 12074000 | 12074000 | 12074000 | 12074000 | 12074000 | 12074000 | 12074000 | 12074000 | 12074000 | 33646000
I-5987B | Highway | STI (Prioritization) | I-95 | South of NC 20 to south of proposed I-295. | Widen to eight lanes. | 6.28 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | CONSTRUCTION | 186346000 | FY 2026: 31820000; FY 2027: 65551000
I-5987C | Highway | STI (Prioritization) | I-95 | South of US 301 to south of proposed I-295. | Install gauge, modeling / hydraulic studies, and stress testing along corridor. | 16.52 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | DP | ENGINEERING | 250000
I-5987C | Highway | STI (Prioritization) | I-95 | South of US 301 to south of proposed I-295. | Install gauge, modeling / hydraulic studies, and stress testing along corridor. | 16.52 | Robeson | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | T | ENGINEERING | 65000
I-5990 | Highway | STI (Prioritization) | I-40 | SR 1761 (Old NC 10) Exit 118 interchange. | Construct interchange improvements. | 1 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  |  |  | 2010000
I-5990 | Highway | STI (Prioritization) | I-40 | SR 1761 (Old NC 10) Exit 118 interchange. | Construct interchange improvements. | 1 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | NHP | RIGHT-OF-WAY | 2496000 | FY 2027: 1556000; FY 2028: 440000; FY 2029: 250000; FY 2030: 250000
I-5990 | Highway | STI (Prioritization) | I-40 | SR 1761 (Old NC 10) Exit 118 interchange. | Construct interchange improvements. | 1 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | NHP | UTILITIES | 605000 | FY 2027: 550000; FY 2028: 55000
I-5990 | Highway | STI (Prioritization) | I-40 | SR 1761 (Old NC 10) Exit 118 interchange. | Construct interchange improvements. | 1 | Burke | 13 | Greater Hickory MPO |  | Division 13 |  | NHP | CONSTRUCTION | 19800000 | FY 2027: 6732000; FY 2028: 8118000; FY 2029: 4950000
I-5992 | Highway | Interstate Maintenance | I-77 | Mile marker 11.0 to mile marker 20.0 and mile marker 24.5 to mile marker 37. | Rehabilitate pavement. | 21.27 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Statewide Mobility |  |  |  | 25600000
I-5993 | Highway | Interstate Maintenance | I-40 | US 15 / US 501 to east of NC 147. | Rehabilitate pavement. | 9.24 | Durham | 5 | Triangle West TPO | TO BE LET WITH I-5994 | Statewide Mobility |  |  |  | 10000
I-5993 | Highway | Interstate Maintenance | I-40 | US 15 / US 501 to east of NC 147. | Rehabilitate pavement. | 9.24 | Durham | 5 | Triangle West TPO | TO BE LET WITH I-5994 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 50700000 | FY 2026: 5576000; FY 2027: 13689000; FY 2028: 12675000; FY 2029: 10648000; FY 2030: 8112000
I-5995 | Highway | Interstate Maintenance | I-40 | East of NC 147 to SR 1728 (Wade Avenue). | Rehabilitate pavement. | 9.37 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO |  | Statewide Mobility |  |  |  | 10000
I-5995 | Highway | Interstate Maintenance | I-40 | East of NC 147 to SR 1728 (Wade Avenue). | Rehabilitate pavement. | 9.37 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 19600000 | FY 2026: 3528000; FY 2027: 5292000; FY 2028: 4508000; FY 2029: 3528000; FY 2030: 2744000
I-5995 | Highway | Interstate Maintenance | I-40 | East of NC 147 to SR 1728 (Wade Avenue). | Rehabilitate pavement. | 9.37 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 35000000 | FY 2026: 6300000; FY 2027: 9450000; FY 2028: 8050000; FY 2029: 6300000; FY 2030: 4900000
I-5997 | Highway | Interstate Maintenance | I-440 / US 1 | SR 1728 (Wade Avenue) to SR 2000 (Wake Forest Road) in Raleigh. | Rehabilitate pavement. | 4.85 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  |  |  | 8000
I-5997 | Highway | Interstate Maintenance | I-440 / US 1 | SR 1728 (Wade Avenue) to SR 2000 (Wake Forest Road) in Raleigh. | Rehabilitate pavement. | 4.85 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) |  | 2000
I-5997 | Highway | Interstate Maintenance | I-440 / US 1 | SR 1728 (Wade Avenue) to SR 2000 (Wake Forest Road) in Raleigh. | Rehabilitate pavement. | 4.85 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 18480000
I-5997 | Highway | Interstate Maintenance | I-440 / US 1 | SR 1728 (Wade Avenue) to SR 2000 (Wake Forest Road) in Raleigh. | Rehabilitate pavement. | 4.85 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 4620000
I-5998 | Highway | Interstate Maintenance | I-540 | I-40 in Durham to US 70 in Raleigh. | Rehabilitate pavement. | 4.25 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH I-5999 AND I-6000 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 19919000 | FY 2027: 4382000; FY 2028: 6374000; FY 2029: 4781000; FY 2030: 3386000; FY 2031: 996000
I-5998 | Highway | Interstate Maintenance | I-540 | I-40 in Durham to US 70 in Raleigh. | Rehabilitate pavement. | 4.25 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH I-5999 AND I-6000 | Statewide Mobility |  | T(M) | CONSTRUCTION | 4981000 | FY 2027: 1096000; FY 2028: 1594000; FY 2029: 1195000; FY 2030: 847000; FY 2031: 249000
I-5999 | Highway | Interstate Maintenance | I-540 | US 70 (Glenwood Avenue) to east of Triangle Town Boulevard in Raleigh. | Rehabilitate pavement. | 12.53 | Wake | 5 | Capital Area MPO | COORDINATE WITH I-5998 AND I-6000; | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10009000
I-5999 | Highway | Interstate Maintenance | I-540 | US 70 (Glenwood Avenue) to east of Triangle Town Boulevard in Raleigh. | Rehabilitate pavement. | 12.53 | Wake | 5 | Capital Area MPO | COORDINATE WITH I-5998 AND I-6000; | Statewide Mobility |  | T(M) | CONSTRUCTION | 2502000
I-6000 | Highway | Interstate Maintenance | I-540 | I-40 in Durham to US 1 in Raleigh. | Rehabilitate pavement and bridge preservation. | 16.34 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH I-5998 AND I-5999 | Statewide Mobility |  |  |  | 8000
I-6000 | Highway | Interstate Maintenance | I-540 | I-40 in Durham to US 1 in Raleigh. | Rehabilitate pavement and bridge preservation. | 16.34 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH I-5998 AND I-5999 | Statewide Mobility |  | T(M) |  | 2000
I-6000 | Highway | Interstate Maintenance | I-540 | I-40 in Durham to US 1 in Raleigh. | Rehabilitate pavement and bridge preservation. | 16.34 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH I-5998 AND I-5999 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6088000 | FY 2029: 2801000; FY 2030: 2557000; FY 2031: 730000
I-6000 | Highway | Interstate Maintenance | I-540 | I-40 in Durham to US 1 in Raleigh. | Rehabilitate pavement and bridge preservation. | 16.34 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH I-5998 AND I-5999 | Statewide Mobility |  | T(M) | CONSTRUCTION | 1522000 | FY 2029: 700000; FY 2030: 639000; FY 2031: 183000
I-6001 | Highway | Interstate Maintenance | I-87 / US 64 (Future I-87) / US 264 (Future I-587) | SR 1003 (Rolesville Road) to Nash County line. | Rehabilitate pavement. | 13.38 | Wake, Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 31520000 | FY 2026: 315000; FY 2027: 14499000; FY 2028: 10402000; FY 2029: 6304000
I-6001 | Highway | Interstate Maintenance | I-87 / US 64 (Future I-87) / US 264 (Future I-587) | SR 1003 (Rolesville Road) to Nash County line. | Rehabilitate pavement. | 13.38 | Wake, Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 7880000 | FY 2026: 79000; FY 2027: 3625000; FY 2028: 2600000; FY 2029: 1576000
I-6003 | Highway | Interstate Maintenance | I-40 | SR 1436 (Pinebrook School Road) to west of NC 801. | Rehabilitate pavement. | 4.76 | Davie | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6142000
I-6003 | Highway | Interstate Maintenance | I-40 | SR 1436 (Pinebrook School Road) to west of NC 801. | Rehabilitate pavement. | 4.76 | Davie | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 1535000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 8000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) |  | 2000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | NHP | RIGHT-OF-WAY | 4560000 | FY 2026: 1322000; FY 2027: 958000; FY 2028: 1277000; FY 2029: 91000; FY 2030: 912000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | RIGHT-OF-WAY | 1140000 | FY 2026: 331000; FY 2027: 239000; FY 2028: 319000; FY 2029: 23000; FY 2030: 228000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | NHP | UTILITIES | 880000 | FY 2026: 880000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | UTILITIES | 220000 | FY 2026: 220000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | NHP | CONSTRUCTION | 18480000 | FY 2031: 6283000; FY 2032: 6283000; FY 2033: 3511000; FY 2034: 2403000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (Rock Creek Dairy Road) interchange near Sedalia. | Upgrade interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T(M) | CONSTRUCTION | 4620000 | FY 2031: 1571000; FY 2032: 1571000; FY 2033: 878000; FY 2034: 600000
I-6009 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1158 (Huffman Mill Road) interchange in Burlington. | Construct additional left turn lane on I-40 westbound ramp and improve operations at SR 1308 (Garden Road) intersection. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 500000
I-6009 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1158 (Huffman Mill Road) interchange in Burlington. | Construct additional left turn lane on I-40 westbound ramp and improve operations at SR 1308 (Garden Road) intersection. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 40000
I-6009 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1158 (Huffman Mill Road) interchange in Burlington. | Construct additional left turn lane on I-40 westbound ramp and improve operations at SR 1308 (Garden Road) intersection. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2400000
I-6011 | Highway | STI (Prioritization) | US 74 (Future I-74) | Near Lumberton to US 76 near Chadbourn. | Upgrade US 74 to interstate standards. | 22.71 | Columbus, Robeson | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  |  |  | 10000
I-6011 | Highway | STI (Prioritization) | US 74 (Future I-74) | Near Lumberton to US 76 near Chadbourn. | Upgrade US 74 to interstate standards. | 22.71 | Columbus, Robeson | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 179000 | [10 empty] | 179000
I-6011 | Highway | STI (Prioritization) | US 74 (Future I-74) | Near Lumberton to US 76 near Chadbourn. | Upgrade US 74 to interstate standards. | 22.71 | Columbus, Robeson | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  | T | UTILITIES | 1469000 | [10 empty] | 1469000
I-6011 | Highway | STI (Prioritization) | US 74 (Future I-74) | Near Lumberton to US 76 near Chadbourn. | Upgrade US 74 to interstate standards. | 22.71 | Columbus, Robeson | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  | T | CONSTRUCTION | 169100000 | [10 empty] | 169100000
I-6011A | Highway | STI (Prioritization) | US 74 (Future I-74) | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGLT5 | RIGHT-OF-WAY | 240000 | FY 2026: 120000
I-6011A | Highway | STI (Prioritization) | US 74 (Future I-74) | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | T(M) | RIGHT-OF-WAY | 60000 | FY 2026: 30000
I-6011A | Highway | STI (Prioritization) | US 74 (Future I-74) | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGLT5 | UTILITIES | 240000 | FY 2026: 80000
I-6011A | Highway | STI (Prioritization) | US 74 (Future I-74) | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | T(M) | UTILITIES | 60000 | FY 2026: 20000
I-6011A | Highway | STI (Prioritization) | US 74 (Future I-74) | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | BGLT5 | CONSTRUCTION | 7359000 | FY 2027: 1398000; FY 2028: 3606000; FY 2029: 2355000
I-6011A | Highway | STI (Prioritization) | US 74 (Future I-74) | SR 2225 (Creek Road) intersection north of Orrum | Upgrade at-grade intersection to interchange. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 6 |  | T(M) | CONSTRUCTION | 1841000 | FY 2027: 350000; FY 2028: 902000; FY 2029: 589000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 3360000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 840000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 720000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 180000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 37600000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 interchange Northeast of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 9400000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 472000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 118000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 312000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 78000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 18400000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. Harris Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 4600000
I-6015 | Highway | STI (Prioritization) | I-485 | NC 51 (Pineville-Matthews Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 840000
I-6015 | Highway | STI (Prioritization) | I-485 | NC 51 (Pineville-Matthews Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 720000
I-6015 | Highway | STI (Prioritization) | I-485 | NC 51 (Pineville-Matthews Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 14000000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 interchange west of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | HF | RIGHT-OF-WAY | 2000000 | FY 2026: 160000; FY 2027: 200000; FY 2028: 200000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 interchange west of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | HF | UTILITIES | 970000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 interchange west of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 5000000 | FY 2026: 50000; FY 2027: 1600000; FY 2028: 1450000; FY 2029: 1050000; FY 2030: 850000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 interchange west of Charlotte. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | HF | CONSTRUCTION | 36400000 | FY 2026: 364000; FY 2027: 11648000; FY 2028: 10556000; FY 2029: 7644000; FY 2030: 6188000
I-6016A | Highway | Other | I-85 | I-485 interchange west of Charlotte | Improve interchange. Clearing work only. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Highway Fund |  | HF | CONSTRUCTION | 200000 | FY 2026: 36000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 11920000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 2980000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3760000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 940000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 16560000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (South Tryon Street) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 4140000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 45520000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 11380000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1840000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 460000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 58320000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (Brookshire Boulevard) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 14580000
I-6028 | Highway | Interstate Maintenance | US 13/US 64 (Future I-87) | Edgecombe County line to US 13 / 17 and US 64 interchange. | Rehabilitate pavement. | 18.56 | Martin | 1 | Mid-East RPO | "A" BREAK DELETED, WORK WAS COMPLETED WITH CONTRACT RESURFACING. | Statewide Mobility |  |  |  | 10000
I-6028B | Highway | Interstate Maintenance | US 64 (Future I-87) | US 64 Alternate to NC 125 | Rehabilitate pavement. | 4.7 | Martin | 1 | Mid-East RPO | COMPLETE. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4859000
I-6028B | Highway | Interstate Maintenance | US 64 (Future I-87) | US 64 Alternate to NC 125 | Rehabilitate pavement. | 4.7 | Martin | 1 | Mid-East RPO | COMPLETE. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1214000
I-6028C | Highway | Interstate Maintenance | US 64 (Future I-87) | NC 125 to US 13 / 17 and US 64 interchange. | Rehabilitate pavement. | 4.11 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4800000
I-6028C | Highway | Interstate Maintenance | US 64 (Future I-87) | NC 125 to US 13 / 17 and US 64 interchange. | Rehabilitate pavement. | 4.11 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1200000
I-6029 | Highway | Interstate Maintenance | US 17 (Future I-87) | Perquimans County line to north end of US 17 (Elizabeth City) Bypass. | Rehabilitate pavement. | 10.29 | Pasquotank | 1 | Albemarle RPO | COMPLETE. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  |  |  | 10000
I-6029 | Highway | Interstate Maintenance | US 17 (Future I-87) | Perquimans County line to north end of US 17 (Elizabeth City) Bypass. | Rehabilitate pavement. | 10.29 | Pasquotank | 1 | Albemarle RPO | COMPLETE. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  | NHPIM | GARVEE CON | 4125000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000
I-6029 | Highway | Interstate Maintenance | US 17 (Future I-87) | Perquimans County line to north end of US 17 (Elizabeth City) Bypass. | Rehabilitate pavement. | 10.29 | Pasquotank | 1 | Albemarle RPO | COMPLETE. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  | NHP | CONSTRUCTION | 5625000
I-6029 | Highway | Interstate Maintenance | US 17 (Future I-87) | Perquimans County line to north end of US 17 (Elizabeth City) Bypass. | Rehabilitate pavement. | 10.29 | Pasquotank | 1 | Albemarle RPO | COMPLETE. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2136000
I-6032 | Highway | Interstate Maintenance | US 264 (Future I-587) | Pitt County line to Wilson County line. | Rehabilitate pavement. | 4.18 | Greene | 2 | Eastern Carolina RPO | COMPLETE. LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033. | Statewide Mobility |  |  |  | 7165000
I-6032 | Highway | Interstate Maintenance | US 264 (Future I-587) | Pitt County line to Wilson County line. | Rehabilitate pavement. | 4.18 | Greene | 2 | Eastern Carolina RPO | COMPLETE. LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 4830000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000
I-6035 | Highway | Interstate Maintenance | US 264/US 258 (Future I-587) | Greene County line to SR 1467 (Stantonsburg Road) interchange (Greenville Southwest Bypass). | Rehabilitate pavement. | 13.19 | Pitt | 2 | Mid-East RPO, Greenville Urban Area MPO | COMPLETE. LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033. | Statewide Mobility |  |  |  | 21960000
I-6035 | Highway | Interstate Maintenance | US 264/US 258 (Future I-587) | Greene County line to SR 1467 (Stantonsburg Road) interchange (Greenville Southwest Bypass). | Rehabilitate pavement. | 13.19 | Pitt | 2 | Mid-East RPO, Greenville Urban Area MPO | COMPLETE. LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 14420000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000
I-6036 | Highway | Interstate Maintenance | I-140 | US 17 to north of US 74. | Rehabilitate pavement. | 5.08 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 8000
I-6036 | Highway | Interstate Maintenance | I-140 | US 17 to north of US 74. | Rehabilitate pavement. | 5.08 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 2000
I-6036 | Highway | Interstate Maintenance | I-140 | US 17 to north of US 74. | Rehabilitate pavement. | 5.08 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8864000
I-6036 | Highway | Interstate Maintenance | I-140 | US 17 to north of US 74. | Rehabilitate pavement. | 5.08 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2216000
I-6037 | Highway | Interstate Maintenance | I-140 | US 421 to I-40. | Rehabilitate bridge and pavement. | 6.79 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5840000 | FY 2028: 2161000; FY 2029: 2920000; FY 2030: 759000
I-6037 | Highway | Interstate Maintenance | I-140 | US 421 to I-40. | Rehabilitate bridge and pavement. | 6.79 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1460000 | FY 2028: 540000; FY 2029: 730000; FY 2030: 190000
I-6039 | Highway | Interstate Maintenance | I-40 | End I-40 (mile marker 420) to NC 210 (mile marker 408). | Rehabilitate pavement. | 11.88 | New Hanover, Pender | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHFP | CONSTRUCTION | 6775000
I-6039 | Highway | Interstate Maintenance | I-40 | End I-40 (mile marker 420) to NC 210 (mile marker 408). | Rehabilitate pavement. | 11.88 | New Hanover, Pender | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 16229000
I-6040 | Highway | Interstate Maintenance | I-40 | West of US 117 (mile marker 388) to NC 210 (mile marker 408). | Rehabilitate pavement. | 15.05 | Pender | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 15815000
I-6040 | Highway | Interstate Maintenance | I-40 | West of US 117 (mile marker 388) to NC 210 (mile marker 408). | Rehabilitate pavement. | 15.05 | Pender | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 3953000
I-6041 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1225 (Kingsboro Road) to NC 33. | Rehabilitate pavement. | 10.18 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  |  |  | 10000
I-6041 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1225 (Kingsboro Road) to NC 33. | Rehabilitate pavement. | 10.18 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | HP | CONSTRUCTION | 7000000
I-6041 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1225 (Kingsboro Road) to NC 33. | Rehabilitate pavement. | 10.18 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 11909000 | FY 2026: 476000
I-6041 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1225 (Kingsboro Road) to NC 33. | Rehabilitate pavement. | 10.18 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1750000
I-6041A | Highway | Interstate Maintenance | US 64 (Future I-87) | Bridges 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, and 320326. | Rehabilitate Bridges. |  | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3200000
I-6041A | Highway | Interstate Maintenance | US 64 (Future I-87) | Bridges 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, and 320326. | Rehabilitate Bridges. |  | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 800000
I-6042 | Highway | Interstate Maintenance | US 64 (Future I-87) | NC 33 to Martin County line. | Rehabilitate pavement. | 10.45 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | HP | CONSTRUCTION | 5300000
I-6042 | Highway | Interstate Maintenance | US 64 (Future I-87) | NC 33 to Martin County line. | Rehabilitate pavement. | 10.45 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13075000
I-6042 | Highway | Interstate Maintenance | US 64 (Future I-87) | NC 33 to Martin County line. | Rehabilitate pavement. | 10.45 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1325000
I-6042A | Highway | Interstate Maintenance | US 64 (Future I-87) | Bridges 320327 and 320328. | Rehabilitate Bridges. |  | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 240000
I-6042A | Highway | Interstate Maintenance | US 64 (Future I-87) | Bridges 320327 and 320328. | Rehabilitate Bridges. |  | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 60000
I-6044 | Highway | Interstate Maintenance | US 70 (Future I-42) | SR 1003 (Buffalo Road) to Wayne County line. | Rehabilitate pavement. | 13.32 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033. | Statewide Mobility |  |  |  | 2137000
I-6044 | Highway | Interstate Maintenance | US 70 (Future I-42) | SR 1003 (Buffalo Road) to Wayne County line. | Rehabilitate pavement. | 13.32 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 6090000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000
I-6045 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1306 (South Old Franklin Road) to SR 1603 (Old Carriage Road). | Rehabilitate pavement. | 11.12 | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 10000
I-6045 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1306 (South Old Franklin Road) to SR 1603 (Old Carriage Road). | Rehabilitate pavement. | 11.12 | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 835000
I-6045 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1306 (South Old Franklin Road) to SR 1603 (Old Carriage Road). | Rehabilitate pavement. | 11.12 | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHFP | CONSTRUCTION | 15825000
I-6045A | Highway | Interstate Maintenance | US 64 (Future I-87) | Bridges 630072 and 630074. | Rehabilitate bridge. |  | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 416000
I-6045A | Highway | Interstate Maintenance | US 64 (Future I-87) | Bridges 630072 and 630074. | Rehabilitate bridge. |  | Nash | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 104000
I-6046 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1603 (Old Carriage Road) to SR 1225 (Kingsboro Road). | Rehabilitate bridge. | 12.63 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 8000
I-6046 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1603 (Old Carriage Road) to SR 1225 (Kingsboro Road). | Rehabilitate bridge. | 12.63 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 2000
I-6046 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1603 (Old Carriage Road) to SR 1225 (Kingsboro Road). | Rehabilitate bridge. | 12.63 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 19205000
I-6046 | Highway | Interstate Maintenance | US 64 (Future I-87) | SR 1603 (Old Carriage Road) to SR 1225 (Kingsboro Road). | Rehabilitate bridge. | 12.63 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 4801000
I-6047 | Highway | Interstate Maintenance | I-795 | Wilson County line to SR 2075 (Ash Street). | Upgrade guardrail, shoulders, and median repairs. | 13.55 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | Statewide Mobility |  |  |  | 10000
I-6047 | Highway | Interstate Maintenance | I-795 | Wilson County line to SR 2075 (Ash Street). | Upgrade guardrail, shoulders, and median repairs. | 13.55 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | Statewide Mobility |  | NHPIM | GARVEE CON | 4860000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000
I-6047 | Highway | Interstate Maintenance | I-795 | Wilson County line to SR 2075 (Ash Street). | Upgrade guardrail, shoulders, and median repairs. | 13.55 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2033000
I-6048 | Highway | Interstate Maintenance | US 117 (Future I-795) | US 70 to Duplin County line. | Rehabilitate bridge and pavement. | 16.69 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 8000
I-6048 | Highway | Interstate Maintenance | US 117 (Future I-795) | US 70 to Duplin County line. | Rehabilitate bridge and pavement. | 16.69 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) |  | 2000
I-6048 | Highway | Interstate Maintenance | US 117 (Future I-795) | US 70 to Duplin County line. | Rehabilitate bridge and pavement. | 16.69 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6354000
I-6048 | Highway | Interstate Maintenance | US 117 (Future I-795) | US 70 to Duplin County line. | Rehabilitate bridge and pavement. | 16.69 | Wayne | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1588000
I-6052 | Highway | Interstate Maintenance | I-277 (Brookshire Freeway) | West of I-77 to east of I-77. | Rehabilitate bridges 590339, 590337, 590338, 590341, 590342, 590281, 590282, and 590283 . | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 880000
I-6052 | Highway | Interstate Maintenance | I-277 (Brookshire Freeway) | West of I-77 to east of I-77. | Rehabilitate bridges 590339, 590337, 590338, 590341, 590342, 590281, 590282, and 590283 . | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1860000 | FY 2026: 300000
I-6052 | Highway | Interstate Maintenance | I-277 (Brookshire Freeway) | West of I-77 to east of I-77. | Rehabilitate bridges 590339, 590337, 590338, 590341, 590342, 590281, 590282, and 590283 . | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 11840000
I-6052 | Highway | Interstate Maintenance | I-277 (Brookshire Freeway) | West of I-77 to east of I-77. | Rehabilitate bridges 590339, 590337, 590338, 590341, 590342, 590281, 590282, and 590283 . | 0.32 | Mecklenburg | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2960000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 8000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) |  | 2000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 21578000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 5395000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 524000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 131000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 19439000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (Sugar Creed Road) interchange. | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 4861000
I-6055 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 74 Business east of Hamlet to US 74 Business west of Laurinburg. | Upgrade corridor to interstate standards. | 9.84 | Scotland, Richmond | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
I-6055 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 74 Business east of Hamlet to US 74 Business west of Laurinburg. | Upgrade corridor to interstate standards. | 9.84 | Scotland, Richmond | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 43000000
I-6055 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 74 Business east of Hamlet to US 74 Business west of Laurinburg. | Upgrade corridor to interstate standards. | 9.84 | Scotland, Richmond | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 8500000
I-6055 | Highway | STI (Prioritization) | US 74 / Future I-74 | US 74 Business east of Hamlet to US 74 Business west of Laurinburg. | Upgrade corridor to interstate standards. | 9.84 | Scotland, Richmond | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 224100000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (Trollingwood-Hawfields Road) in Mebane. | Upgrade interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | RIGHT-OF-WAY | 5100000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (Trollingwood-Hawfields Road) in Mebane. | Upgrade interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | UTILITIES | 2500000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (Trollingwood-Hawfields Road) in Mebane. | Upgrade interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | BUILD NC CON | 10680000 |  | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 4272000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (Trollingwood-Hawfields Road) in Mebane. | Upgrade interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | CONSTRUCTION | 11700000 | FY 2026: 4862000; FY 2027: 1041000; FY 2028: 5797000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (Trollingwood-Hawfields Road) in Mebane. | Upgrade interchange. | 1 | Alamance | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | HF | CONSTRUCTION | 10000000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (Brogden Road) interchange. | Improve interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (Brogden Road) interchange. | Improve interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2000000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (Brogden Road) interchange. | Improve interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2000000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (Brogden Road) interchange. | Improve interchange. | 1 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 26300000
I-6063 | Highway | Interstate Maintenance | I-40 | Mile marker 50.0 to mile marker 55.0. | Rehabilitate pavement. | 4.96 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  |  |  | 10000
I-6063 | Highway | Interstate Maintenance | I-40 | Mile marker 50.0 to mile marker 55.0. | Rehabilitate pavement. | 4.96 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 6435000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000
I-6063 | Highway | Interstate Maintenance | I-40 | Mile marker 50.0 to mile marker 55.0. | Rehabilitate pavement. | 4.96 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 22120000
I-6063 | Highway | Interstate Maintenance | I-40 | Mile marker 50.0 to mile marker 55.0. | Rehabilitate pavement. | 4.96 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 1667000
I-6064 | Highway | STI (Prioritization) | I-95 | Mile marker 13 to mile marker 22. | Widen to eight lanes and rehabilitate pavement. | 9 | Robeson | 6 | Lumber River RPO | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879. |  |  |  |  | 10000
I-6064A | Highway | STI (Prioritization) | I-95 | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | DP | RIGHT-OF-WAY | 2470000
I-6064A | Highway | STI (Prioritization) | I-95 | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 617000
I-6064A | Highway | STI (Prioritization) | I-95 | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | DP | UTILITIES | 2600000
I-6064A | Highway | STI (Prioritization) | I-95 | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 4100000 | FY 2026: 250000
I-6064A | Highway | STI (Prioritization) | I-95 | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | DP | CONSTRUCTION | 16930000
I-6064A | Highway | STI (Prioritization) | I-95 | I -74 (Exit 13) to Carthage Road (Exit 19). | Widen to eight lanes. | 5.75 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 243755000 | FY 2026: 132314000; FY 2027: 19000000
I-6064B | Highway | STI (Prioritization) | I-95 | Carthage Road (Exit 19) to US 301 (Fayetteville Road) (Exit 22). | Widen to eight lanes. | 2.79 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 9788000 | FY 2026: 1100000
I-6064B | Highway | STI (Prioritization) | I-95 | Carthage Road (Exit 19) to US 301 (Fayetteville Road) (Exit 22). | Widen to eight lanes. | 2.79 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 3425000
I-6064B | Highway | STI (Prioritization) | I-95 | Carthage Road (Exit 19) to US 301 (Fayetteville Road) (Exit 22). | Widen to eight lanes. | 2.79 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 125846000 | FY 2026: 40000000; FY 2027: 47900000
I-6064C | Highway | Interstate Maintenance | I-95 | Mile marker 13 to mile marker 22. | Rehabilitate bridge. | 9 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 105193000
I-6064C | Highway | Interstate Maintenance | I-95 | Mile marker 13 to mile marker 22. | Rehabilitate bridge. | 9 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 26299000
I-6064D | Highway | Other | I-95 | Mile marker 13 to mile marker 22. | Gauge installation, modeling / hydraulic studies, and stress testing along corridor. | 9.01 | Robeson | 6 | Lumber River RPO |  | Statewide Mobility |  | DP | ENGINEERING | 250000
I-6064D | Highway | Other | I-95 | Mile marker 13 to mile marker 22. | Gauge installation, modeling / hydraulic studies, and stress testing along corridor. | 9.01 | Robeson | 6 | Lumber River RPO |  | Statewide Mobility |  | T | ENGINEERING | 65000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BGDA | ENGINEERING | 1456000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BA | ENGINEERING | 190000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | ENGINEERING | 174000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2027: 80000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | RIGHT-OF-WAY | 20000 | FY 2027: 20000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(DA) | CONSTRUCTION | 36063000 | FY 2029: 4644000; FY 2030: 16509000; FY 2031: 9987000; FY 2032: 4923000
I-6065 | Highway | Locally Selected | I-77 | I-485 to NC 150. | Construct peak period shoulder use lanes. | 16.38 | Mecklenburg, Iredell | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | CONSTRUCTION | 9017000 | FY 2029: 1161000; FY 2030: 4128000; FY 2031: 2497000; FY 2032: 1231000
M-0219 | Highway | Other | Various | Locations statewide. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Statewide | 99 | Statewide Project | [5 empty] | 4258000
M-0219DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 1200000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
M-0219REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 1200000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
M-0219SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for photogrammetry, preliminary engineering for miscellaneous projects |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 1600000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
M-0376 | Highway | Other | Various | Locations statewide. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Statewide | 99 | Statewide Project | IN PROGRESS |  |  |  |  | 12931000
M-0376DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 10620000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
M-0376REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 13500000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
M-0376SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for statewide geotechnical studies and investigations project to cover non-project specific work. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 14160000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2000000
M-0379 | Highway | Bridges | Various | Locations statewide. | Funding for scour evaluation program of existing bridges. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 3100000
M-0391 | Highway | Other | Various | Locations statewide. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project | IN PROGRESS |  |  |  |  | 4076000
M-0391DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 1920000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
M-0391REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 1920000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
M-0391SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for structure design, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 2560000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
M-0392 | Highway | Other | Various | Locations statewide. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project | IN PROGRESS |  |  |  |  | 4180000
M-0392DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 1788000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
M-0392REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 1788000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
M-0392SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for hydraulics, preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 2384000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0414 | Highway | Bridges | Various | Locations statewide. | Funding for the municipal bridge inspection program. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BGOFF | IMPLEMENTATION | 4200000
M-0414 | Highway | Bridges | Various | Locations statewide. | Funding for the municipal bridge inspection program. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | L | IMPLEMENTATION | 800000
M-0418 | Highway | Bridges | Various | Locations statewide. | Funding for storm water runoff. Research, design, construct, maintain and monitor storm water drainage from 50 bridges over waterways. |  | Statewide | 99 | Statewide Project | UNDER CONSTRUCTION | Division 99 |  |  |  | 6994000
M-0426 | Highway | Other | Various | Statewide | Funding for training, education, and workforce development. |  | Statewide | 99 | Statewide Project | AUTHORIZED UNDER 23 U.S.C. 504e
M-0426DIV | Highway | Other | Various | Statewide | Funding for training, education, and workforce development. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | NHP | IMPLEMENTATION | 1140000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000
M-0426REG | Highway | Other | Various | Statewide | Funding for training, education, and workforce development. |  | Statewide | 99 | Statewide Project |  | Region SW |  | NHP | IMPLEMENTATION | 1140000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000
M-0426SW | Highway | Other | Various | Statewide | Funding for training, education, and workforce development. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | NHP | IMPLEMENTATION | 1520000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
M-0451 | Highway | Other | Various | Locations statewide. | Funding for statewide landscape plans for STIP construction projects. |  | Statewide | 99 | Statewide Project | [5 empty] | 712000
M-0451DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for statewide landscape plans for STIP construction projects. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 1203000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000
M-0451REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for statewide landscape plans for STIP construction projects. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 1203000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000
M-0451SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for statewide landscape plans for STIP construction projects. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 1606000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000
M-0452 | Highway | Other | Various | Locations statewide. | Funding for tolling/financial feasibility studies. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  |  |  | 1064000
M-0452 | Highway | Other | Various | Locations statewide. | Funding for tolling/financial feasibility studies. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0460 | Highway | Other | Various | Statewide | Funding for National Summer Transportation Institute (NSTI). |  | Statewide | 99 | Statewide Project |  | Exempt |  | FO | IMPLEMENTATION | 2400000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0478 | Highway | Other | Various | Statewide | Funding for on-the-job training program. |  | Statewide | 99 | Statewide Project |  | Exempt |  | FO | IMPLEMENTATION | 6000000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
M-0479 | Highway | Other | Various | Locations statewide. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Statewide | 99 | Statewide Project | [5 empty] | 7000000
M-0479A | Highway | Other | Various | Locations statewide. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Statewide | 99 | Statewide Project
M-0479ADIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 7200000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
M-0479AREG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 7200000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
M-0479ASW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for statewide project - Environmental Analysis Unit - Atlas Integration Project. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
M-0479B | Highway | Other | Various | Locations statewide. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project
M-0479BDIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 2400000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
M-0479BREG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 2400000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
M-0479BSW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for statewide project - Environmental Analysis Unit - preliminary engineering for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0479DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 24000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
M-0479REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 24000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
M-0479SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for statewide project - Environmental Analysis Unit - Project Atlas. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 32000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
M-0480 | Highway | Other | Various | Statewide | Funding for Disadvantaged Business Enterprise (DBE) training and supportive services. |  | Statewide | 99 | Statewide Project |  | Exempt |  | FO | IMPLEMENTATION | 3600000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
M-0482 | Highway | Other | Various | Locations statewide. | Funding for federal state transportation innovation council (STIC) incentive funded projects |  | Statewide | 99 | Statewide Project | DP FUNDS REPRESENT FEDERAL STIC FUNDS. | Exempt |  | DP | IMPLEMENTATION | 400000 | FY 2026: 100000
M-0482 | Highway | Other | Various | Locations statewide. | Funding for federal state transportation innovation council (STIC) incentive funded projects |  | Statewide | 99 | Statewide Project | DP FUNDS REPRESENT FEDERAL STIC FUNDS. | Exempt |  | HF(M) | IMPLEMENTATION | 100000 | FY 2026: 25000
M-0505 | Highway | Other | Various | Locations statewide. | Funding for Transportation Program Management Unit (TPMU) oversight for locally-administered projects including preparation of agreements and funding authorization requests. |  | Statewide | 99 | Statewide Project |  | Division 99 |  |  |  | 535000
M-0505 | Highway | Other | Various | Locations statewide. | Funding for Transportation Program Management Unit (TPMU) oversight for locally-administered projects including preparation of agreements and funding authorization requests. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 5000000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
M-0510 | Bike & Ped | Other | Various | Locations statewide | Funding for national recreational trails. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 1476000
M-0510 | Bike & Ped | Other | Various | Locations statewide | Funding for national recreational trails. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  | T(M) |  | 369000
M-0510 | Bike & Ped | Other | Various | Locations statewide | Funding for national recreational trails. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  | TA | CONSTRUCTION | 15360000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000
M-0510 | Bike & Ped | Other | Various | Locations statewide | Funding for national recreational trails. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  | T(M) | CONSTRUCTION | 3840000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
M-0515 | Highway | Other | Various | Locations statewide. | Right-of-way branch, review of local public agency (LPA) projects by the appraisal section. |  | Statewide | 99 | Statewide Project |  | Division 99 |  |  |  | 250000
M-0515 | Highway | Other | Various | Locations statewide. | Right-of-way branch, review of local public agency (LPA) projects by the appraisal section. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | RIGHT-OF-WAY | 4000000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
M-0531 | Highway | Other | Various | Various | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Statewide | 99 | Statewide Project |  | Division 99
M-0531DIV | Highway | Other | Various | Various Locations. | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Statewide | 99 | Statewide Project |  | Division 99 |  | BGANY | IMPLEMENTATION | 4620000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000
M-0531REG | Highway | Other | Various | Various Locations. | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Statewide | 99 | Statewide Project |  | Region SW |  | BGANY | IMPLEMENTATION | 4620000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000
M-0531SW | Highway | Other | Various | Various Locations. | Funding for Transportation Scholarship, Internship Programs, Fellowship Programs, Training, and Educational Outreach for Historically Black Colleges and Universities (HBCU) and Minority Serving Institutions (MSI). |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | BGANY | IMPLEMENTATION | 6160000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000
M-0534 | Highway | Other | Various | Locations statewide. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Statewide | 99 | Statewide Project | IN PROGRESS |  |  |  |  | 2000000
M-0534DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
M-0534REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
M-0534SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding fo hydraulics, preliminary engineering for the highway floodplain program (HFP) to facilitate federal emergency management agency (FEMA) and national flood insurance program (NFIP) compliance and flood resilience. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 12800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000
M-0539 | Highway | Other | Various | Locations statewide. | Funding for environmental mitigation and minimization. |  | Statewide | 99 | Statewide Project
M-0539DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for environmental mitigation and minimization. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | MITIGATION | 43200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000
M-0539REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for environmental mitigation and minimization. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | MITIGATION | 43200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000
M-0539SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for environmental mitigation and minimization. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | MITIGATION | 57600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000
M-0552A | Highway | Other | Various | Locations statewide. | Funding for roadway design for open roads designer (ORD) training and development. |  | Statewide | 99 | Statewide Project
M-0552ADIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for roadway design for open roads designer (ORD) training and development. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 1650000 | FY 2026: 450000; FY 2027: 450000
M-0552AREG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for roadway design for open roads designer (ORD) training and development. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 1650000 | FY 2026: 450000; FY 2027: 450000
M-0552ASW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for roadway design for open roads designer (ORD) training and development. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 2200000 | FY 2026: 600000; FY 2027: 600000
M-0552B | Highway | Other | Various | Locations statewide. | Funding for roadway design for training and development for miscellaneous projects. |  | Statewide | 99 | Statewide Project
M-0552BDIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for roadway design for training and development for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 1180000 | FY 2026: 128000; FY 2027: 128000
M-0552BREG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for roadway design for training and development for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 1180000 | FY 2026: 128000; FY 2027: 128000
M-0552BSW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for roadway design for training and development for miscellaneous projects. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 1572000 | FY 2026: 170000; FY 2027: 170000
M-0553A | Highway | Other | Various | Locations statewide. | Funding for integrated project delivery. |  | Statewide | 99 | Statewide Project
M-0553ADIV | Highway | Other | Various | Statewide | Funding for integrated project delivery. |  | Statewide | 99 | Statewide Project |  | Exempt |  | T | ENGINEERING | 5250000 | FY 2026: 450000; FY 2027: 450000
M-0553AREG | Highway | Other | Various | Statewide | Funding for integrated project delivery. |  | Statewide | 99 | Statewide Project |  | Exempt |  | T | ENGINEERING | 5250000 | FY 2026: 450000; FY 2027: 450000
M-0553ASW | Highway | Other | Various | Statewide | Funding for integrated project delivery. |  | Statewide | 99 | Statewide Project |  | Exempt |  | T | ENGINEERING | 7000000 | FY 2026: 600000; FY 2027: 600000
M-0553B | Highway | Other | Various | Locations statewide. | Funding for training and special projects |  | Statewide | 99 | Statewide Project
M-0553BDIV | Highway | Other | Various | Statewide | Funding for traIning and special projects. |  | Statewide | 99 | Statewide Project |  | Exempt |  | T | ENGINEERING | 3180000 | FY 2026: 90000; FY 2027: 90000
M-0553BREG | Highway | Other | Various | Statewide | Funding for training and special projects. |  | Statewide | 99 | Statewide Project |  | Exempt |  | T | ENGINEERING | 3180000 | FY 2026: 90000; FY 2027: 90000
M-0553BSW | Highway | Other | Various | Statewide | Funding for training and special projects. |  | Statewide | 99 | Statewide Project |  | Exempt |  | T | ENGINEERING | 4240000 | FY 2026: 120000; FY 2027: 120000
M-0554 | Highway | Other | Various | Locations statewide. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Statewide | 99 | Statewide Project
M-0554DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | MITIGATION | 105000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
M-0554REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | MITIGATION | 105000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
M-0554SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for NCDOT mitigation order to Division of Mitigation Services (DMS). |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | MITIGATION | 140000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000
M-0555 | Highway | Other | Various | Locations statewide. | Funding for utility encroachment and administrative activities. |  | Statewide | 99 | Statewide Project
M-0555DIV | Highway | Other | Various | Locations statewide. Division Needs funding. | Funding for utility encroachment and administrative activities. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | UTILITIES | 2160000 | 900000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
M-0555REG | Highway | Other | Various | Locations statewide. Regional Impact funding. | Funding for utility encroachment and administrative activities. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | UTILITIES | 2160000 | 900000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
M-0555SW | Highway | Other | Various | Locations statewide. Statewide Mobility funding. | Funding for utility encroachment and administrative activities. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | UTILITIES | 2880000 | 1200000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000
M-0556 | Highway | Other | Statewide | Statewide | Advanced Right-of-Way acquisition account. Revolving account to fund Advanced Right-of-Way acquisition. Funds to be repaid from the STIP project at the time the project is funded. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 6000000
M-0563 | Highway | Other | Various | Locations statewide. | Funding for protect formula planning for resilience program. |  | Statewide | 99 | Statewide Project
M-0563A | Highway | Other | Various | Locations statewide. | Funding for hazard characterization and warning tools. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | PROTCT | ENGINEERING | 2688000 | FY 2026: 672000
M-0563A | Highway | Other | Various | Locations statewide. | Funding for hazard characterization and warning tools. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | ENGINEERING | 672000 | FY 2026: 168000
M-0563B | Highway | Other | Various | Locations statewide. | Funding for hazard corridor vulnerability assessments. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | ENGINEERING | 280000 | FY 2026: 70000
M-0563B | Highway | Other | Various | Locations statewide. | Funding for hazard corridor vulnerability assessments. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | PROTCT | ENGINEERING | 1120000 | FY 2026: 280000
M-0563C | Highway | Other | Various | Locations statewide. | Funding for Geotechnical Asset Management (GAM) database and landslide mitigation planning. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | ENGINEERING | 448000 | FY 2026: 112000
M-0563C | Highway | Other | Various | Locations statewide. | Funding for Geotechnical Asset Management (GAM) database and landslide mitigation planning. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | PROTCT | ENGINEERING | 1792000 | FY 2026: 448000
M-0563D | Highway | Other | Various | Locations statewide. | Funding for lidar data collection. |  | Alamance, Cumberland, Durham, Guilford, Wake, Caswell, Chatham, Granville, Harnett, Hoke, Lee, Montgomery, Moore, Orange, Person, Randolph, Richmond, Rockingham, Scotland | 5, 6, 7, 8 | Capital Area MPO, Fayetteville Area MPO, Greensboro Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Kerr-Tar RPO, Lumber River RPO, Mid-Carolina RPO, Northwest Piedmont RPO, Piedmont Triad RPO, Rock |  | Statewide Mobility |  | T(M) | ENGINEERING | 257000
M-0563D | Highway | Other | Various | Locations statewide. | Funding for lidar data collection. |  | Alamance, Cumberland, Durham, Guilford, Wake, Caswell, Chatham, Granville, Harnett, Hoke, Lee, Montgomery, Moore, Orange, Person, Randolph, Richmond, Rockingham, Scotland | 5, 6, 7, 8 | Capital Area MPO, Fayetteville Area MPO, Greensboro Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Kerr-Tar RPO, Lumber River RPO, Mid-Carolina RPO, Northwest Piedmont RPO, Piedmont Triad RPO, Rock |  | Statewide Mobility |  | PROTCT | ENGINEERING | 1028000
M-0563E | Highway | Other | Various | Locations statewide. | Funding for resilience program reporting, management, and support. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T(M) | ENGINEERING | 510000 | FY 2026: 170000
M-0563E | Highway | Other | Various | Locations statewide. | Funding for resilience program reporting, management, and support. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | PROTCT | ENGINEERING | 2040000 | FY 2026: 680000
M-0570 | Bike & Ped | Other | Various | Systemwide | Funding for multi-modal planning. |  | Statewide | 99 | Statewide Project
M-0570M | Bike & Ped | Other | Kinston | Various locations in Kinston | Funding for multi-modal planning. |  | Lenoir | 2 | Eastern Carolina RPO |  | Exempt |  | CRPANY | PLANNING | 44000
M-0570M | Bike & Ped | Other | Kinston | Various locations in Kinston | Funding for multi-modal planning. |  | Lenoir | 2 | Eastern Carolina RPO |  | Exempt |  | L | PLANNING | 13000
M-0570M | Bike & Ped | Other | Kinston | Various locations in Kinston | Funding for multi-modal planning. |  | Lenoir | 2 | Eastern Carolina RPO |  | Exempt |  | HF(M) | PLANNING | 11000
M-0570N | Bike & Ped | Other | Vandemere | Various locations in Vandemere | Funding for bicycle and pedestrian project acceleration plan. |  | Pamlico | 2 | Down East RPO |  | Exempt |  | CRPLT5 | PLANNING | 34000
M-0570N | Bike & Ped | Other | Vandemere | Various locations in Vandemere | Funding for bicycle and pedestrian project acceleration plan. |  | Pamlico | 2 | Down East RPO |  | Exempt |  | L | PLANNING | 5000
M-0570N | Bike & Ped | Other | Vandemere | Various locations in Vandemere | Funding for bicycle and pedestrian project acceleration plan. |  | Pamlico | 2 | Down East RPO |  | Exempt |  | HF(M) | PLANNING | 9000
M-0570P | Bike & Ped | Other | Surf City | Various locations in Surf City | Funding for bicycle and pedestrian planning. |  | Pender, Onslow | 3 | Cape Fear RPO |  | Exempt |  | CRPANY | PLANNING | 46000
M-0570P | Bike & Ped | Other | Surf City | Various locations in Surf City | Funding for bicycle and pedestrian planning. |  | Pender, Onslow | 3 | Cape Fear RPO |  | Exempt |  | L | PLANNING | 6000
M-0570P | Bike & Ped | Other | Surf City | Various locations in Surf City | Funding for bicycle and pedestrian planning. |  | Pender, Onslow | 3 | Cape Fear RPO |  | Exempt |  | HF(M) | PLANNING | 12000
M-0570Q | Bike & Ped | Other | Burgaw | Various locations in Burgaw | Funding for bicycle and pedestrian project acceleration plan. |  | Pender | 3 | Cape Fear RPO |  | Exempt |  | CRPLT5 | PLANNING | 34000
M-0570Q | Bike & Ped | Other | Burgaw | Various locations in Burgaw | Funding for bicycle and pedestrian project acceleration plan. |  | Pender | 3 | Cape Fear RPO |  | Exempt |  | L | PLANNING | 5000
M-0570Q | Bike & Ped | Other | Burgaw | Various locations in Burgaw | Funding for bicycle and pedestrian project acceleration plan. |  | Pender | 3 | Cape Fear RPO |  | Exempt |  | HF(M) | PLANNING | 9000
M-0570S | Bike & Ped | Other | UNC Wilmington | Various locations at UNC Wilmington | Funding for multi-modal planning. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPANY | PLANNING | 44000
M-0570S | Bike & Ped | Other | UNC Wilmington | Various locations at UNC Wilmington | Funding for multi-modal planning. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Exempt |  | L | PLANNING | 13000
M-0570S | Bike & Ped | Other | UNC Wilmington | Various locations at UNC Wilmington | Funding for multi-modal planning. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Exempt |  | HF(M) | PLANNING | 11000
M-0575 | Highway | Other | Various | Various | Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Statewide | 99 | Southwestern RPO |  | Division 99 |  | BGANY | IMPLEMENTATION | 103000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
M-0575DIV | Highway | Other | Various | Various Locations. | Funding for Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Statewide | 99 | Statewide Project |  | Division 99
M-0575REG | Highway | Other | Various | Various Locations. | Funding for Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Statewide | 99 | Statewide Project |  | Region SW
M-0575SW | Highway | Other | Various | Various Locations. | Funding for Garrett A Morgan Programs to provide professional development and transportation career training for high school students through the page program and industry education and career outreach to K-12 students. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility
P-2918 | Rail | Other | Piedmont Corridor | Regionwide | Train 74 / 75 operations between Charlotte and Raleigh, equipment and capital yard maintenance facility. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  |  |  | 186176000
P-2918 | Rail | Other | Piedmont Corridor | Regionwide | Train 74 / 75 operations between Charlotte and Raleigh, equipment and capital yard maintenance facility. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  | CMAQ | OPERATIONS | 49115000 | FY 2026: 10037000; FY 2027: 10552000
P-2918 | Rail | Other | Piedmont Corridor | Regionwide | Train 74 / 75 operations between Charlotte and Raleigh, equipment and capital yard maintenance facility. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  | HF(M) | OPERATIONS | 12278000 | FY 2026: 2509000; FY 2027: 2638000
P-2918A | Rail | Other | Piedmont Corridor | - | Rebuild 2 F59PHI locomotives. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918B | Rail | Other | Piedmont Corridor | - | Purchase 2 used locomotives. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | COMPLETE
P-2918C | Rail | Other | Piedmont Corridor | - | Rehabilitate equipment - 3 locomotives. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918D | Rail | Other | Piedmont Corridor | - | Rehabilitate equipment - 3 passenger cars. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | COMPLETE
P-2918E | Rail | Other | Piedmont Corridor | - | Passenger train security system, CCTV data network and generators. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918F | Rail | Other | Piedmont Corridor | CRISP Charlotte Maintenance Facility. | Track extension and shop building. |  | Mecklenburg | 10 | Charlotte Regional TPO | IN PROGRESS
P-2918G | Rail | Other | Piedmont Corridor | - | Purchase 4 used passenger cars and rehabilitate 7 passenger cars. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918H | Rail | Other | Piedmont Corridor | Capital Yard Phase 1 Improvements | Extend Tracks 1 and 2, perform major work on Track 3. |  | Wake | 5 | Capital Area MPO | IN PROGRESS
P-2918I | Rail | Other | Piedmont Corridor | - | Equip 9 stations and platforms with ADA/FRA Passenger Information Display Systems. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-5200 | Rail | Other | Piedmont and Northern Railroad | Gastonia and Mount Holly, including the Belmont Spur. | Reactivate rail corridor. |  | Gaston, Mecklenburg | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO | [5 empty] | 7897000
P-5200A | Rail | Other | Piedmont and Northern Railroad | Various locations | Construct crossing signal. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
P-5200B | Rail | Other | Piedmont and Northern Railroad | Various locations | Install crossing sign/pavement marking. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
P-5200C | Rail | Other | Piedmont and Northern Railroad | Various locations | Rail track construction engineering oversight. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
P-5200D | Rail | Transition | Piedmont and Northern Railroad | Belmont Spur. | Reactivate rail corridor. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | BGANY | RIGHT-OF-WAY | 40000
P-5200D | Rail | Transition | Piedmont and Northern Railroad | Belmont Spur. | Reactivate rail corridor. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | T(M) | RIGHT-OF-WAY | 10000
P-5200D | Rail | Transition | Piedmont and Northern Railroad | Belmont Spur. | Reactivate rail corridor. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 680000
P-5200D | Rail | Transition | Piedmont and Northern Railroad | Belmont Spur. | Reactivate rail corridor. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 170000
P-5200EA | Rail | Other | Piedmont and Northern Railroad | Various locations | Relocate thrift depot. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5200EB | Rail | Other | Piedmont and Northern Railroad | Various locations | Stabilize thrift depot. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5205 | Rail | Pre-STI (Historic) | Piedmont Corridor | Graham to Haw River. | Realign siding and curve. |  | Alamance | 7 | Burlington-Graham MPO | COMPLETE. | Pre-STI (Transition) |  |  |  | 11605000
P-5208 | Rail | Pre-STI (Historic) | Piedmont Corridor | Haydock to Junker | Restore double track |  | Cabarrus, Mecklenburg | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 151176000
P-5500 | Rail | Pre-STI (Historic) | Raleigh Union Station | North Carolina Railroad | Construct Raleigh train station and associated rail track and siding improvements to increase passenger and freight capacity. |  | Wake | 5 | Capital Area MPO | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION | Pre-STI (Transition) |  |  |  | 39875000
P-5500A | Rail | Transition | CSX S-Line | Raleigh Union Station | Improve track and signals. |  | Wake | 5 | Capital Area MPO | DELETED - WORK TO BE ACCOMPLISHED UNDER P-5005D.
P-5500B | Rail | Pre-STI (Historic) | NC Railroad | Raleigh Union Station | Station site work. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5500C | Rail | Pre-STI (Historic) | NC Railroad | Raleigh Union Station | Improve track. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5602 | Rail | Other | Various | Routes statewide. | Funding for statewide rail preliminary engineering. |  | Statewide | 99 | Statewide Project | IN PROGRESS |  |  |  |  | 4170000
P-5602DIV | Rail | Other | Various | Routes statewide in the Division Needs category. | Funding for statewide rail preliminary engineering. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
P-5602REG | Rail | Other | Various | Routes statewide in the Regional Impact category | Funding for statewide rail preliminary engineering. |  | Statewide | 99 | Statewide Project |  | Region SW |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
P-5602SW | Rail | Other | Various | Routes statewide in the Statewide Mobility category. | Funding for statewide rail preliminary engineering. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | T | ENGINEERING | 6400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000
P-5700 | Rail | STI (Prioritization) | Norfolk Southern Mainline | Norfolk Southern "Roundhouse" property in Division 7. | Construct parking lot with space for international containers, including security fence, pole-mounted lighting, and paved entrance. |  | Guilford | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | Division 7 |  |  |  | 200000
P-5700 | Rail | STI (Prioritization) | Norfolk Southern Mainline | Norfolk Southern "Roundhouse" property in Division 7. | Construct parking lot with space for international containers, including security fence, pole-mounted lighting, and paved entrance. |  | Guilford | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | Division 7 |  | T | CONSTRUCTION | 850000 | FY 2026: 8000; FY 2027: 842000
P-5700 | Rail | STI (Prioritization) | Norfolk Southern Mainline | Norfolk Southern "Roundhouse" property in Division 7. | Construct parking lot with space for international containers, including security fence, pole-mounted lighting, and paved entrance. |  | Guilford | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | Division 7 |  | O | CONSTRUCTION | 850000 | FY 2026: 850000
P-5701 | Rail | STI (Prioritization) | Norfolk Southern H Line | Mile marker 41.7 in Hillsborough. | Construct platform, passenger rail station building, site access, utilities, and parking. |  | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT. | Division 7 |  |  |  | 810000
P-5701A | Rail | STI (Prioritization) | Norfolk Southern H Line | Milepost 41.7 in Hillsborough. | Construct passenger rail station building, site access, utilities, and parking. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | T | CONSTRUCTION | 6290000
P-5701A | Rail | STI (Prioritization) | Norfolk Southern H Line | Milepost 41.7 in Hillsborough. | Construct passenger rail station building, site access, utilities, and parking. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | O | CONSTRUCTION | 570000
P-5701B | Rail | STI (Prioritization) | Norfolk Southern H Line | Milepost 41.7 in Hillsborough. | Construct station platform and realign curve at Milepost 41.4. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | T | CONSTRUCTION | 1000000 | FY 2026: 500000
P-5705 | Rail | STI (Prioritization) | Charlotte Gateway Station | Charlotte | Update and maintain Charlotte Gateway Station. |  | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL PRIIA GRANT AWARD = $2,578,000 |  |  |  |  | 89614000
P-5705A | Rail | STI (Prioritization) | Charlotte Gateway Station | Charlotte Junction. | Construct WYE connection track. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | DP | RIGHT-OF-WAY | 500000
P-5705A | Rail | STI (Prioritization) | Charlotte Gateway Station | Charlotte Junction. | Construct WYE connection track. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | DP | CONSTRUCTION | 2578000
P-5705A | Rail | STI (Prioritization) | Charlotte Gateway Station | Charlotte Junction. | Construct WYE connection track. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 10422000
P-5705B | Rail | STI (Prioritization) | Charlotte Gateway Station | Various locations | Acquire right-of-way. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E
P-5705BA | Rail | STI (Prioritization) | Charlotte Gateway Station | Various locations | Install track, structure, and signals. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E
P-5705BB | Rail | STI (Prioritization) | Charlotte Gateway Station | Various locations | Install platform and canopy. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E
P-5706 | Rail | STI (Prioritization) | Norfolk Southern H Line | East Durham between CP Nelson and CP East Durham. | Construct East Durham railroad safety improvements. Project will straighten existing railroad curvature between CP Nelson and CP East Durham and includes a combination of grade separations and closures at Ellis Road South End (734737A), Glover Road (73473 | 6.9 | Durham | 5 | Triangle West TPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | Statewide Mobility |  |  |  | 4928000
P-5706 | Rail | STI (Prioritization) | Norfolk Southern H Line | East Durham between CP Nelson and CP East Durham. | Construct East Durham railroad safety improvements. Project will straighten existing railroad curvature between CP Nelson and CP East Durham and includes a combination of grade separations and closures at Ellis Road South End (734737A), Glover Road (73473 | 6.9 | Durham | 5 | Triangle West TPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 9328000 | FY 2026: 1518000; FY 2027: 2276000; FY 2028: 933000; FY 2029: 933000
P-5706 | Rail | STI (Prioritization) | Norfolk Southern H Line | East Durham between CP Nelson and CP East Durham. | Construct East Durham railroad safety improvements. Project will straighten existing railroad curvature between CP Nelson and CP East Durham and includes a combination of grade separations and closures at Ellis Road South End (734737A), Glover Road (73473 | 6.9 | Durham | 5 | Triangle West TPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 66000000 | FY 2030: 7920000; FY 2031: 17820000; FY 2032: 15840000; FY 2033: 13860000; FY 2034: 10560000
P-5707 | Rail | STI (Prioritization) | CSX S Line | SR 2052 (Rogers Road Extension) crossing (633905Y) in Wake Forest. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  |  |  | 3420000
P-5707 | Rail | STI (Prioritization) | CSX S Line | SR 2052 (Rogers Road Extension) crossing (633905Y) in Wake Forest. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | RIGHT-OF-WAY | 7000000
P-5707 | Rail | STI (Prioritization) | CSX S Line | SR 2052 (Rogers Road Extension) crossing (633905Y) in Wake Forest. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 39800000 | FY 2026: 8756000; FY 2027: 11144000; FY 2028: 8756000; FY 2029: 6368000; FY 2030: 4776000
P-5709 | Rail | STI (Prioritization) | Norfolk Southern H Line | Franklin Boulevard Crossing (722959A) in Greensboro and O'Ferrell Street Crossing. | Construct grade separation at Franklin Boulevard crossing (722959A) in Greensboro, and close O'Ferrell Street crossing (722961B). |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 3484000
P-5709 | Rail | STI (Prioritization) | Norfolk Southern H Line | Franklin Boulevard Crossing (722959A) in Greensboro and O'Ferrell Street Crossing. | Construct grade separation at Franklin Boulevard crossing (722959A) in Greensboro, and close O'Ferrell Street crossing (722961B). |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | T | UTILITIES | 2016000 | FY 2026: 450000
P-5709 | Rail | STI (Prioritization) | Norfolk Southern H Line | Franklin Boulevard Crossing (722959A) in Greensboro and O'Ferrell Street Crossing. | Construct grade separation at Franklin Boulevard crossing (722959A) in Greensboro, and close O'Ferrell Street crossing (722961B). |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 26005000 | FY 2027: 5675000; FY 2028: 9286000; FY 2029: 6048000; FY 2030: 3418000; FY 2031: 1578000
P-5709 | Rail | STI (Prioritization) | Norfolk Southern H Line | Franklin Boulevard Crossing (722959A) in Greensboro and O'Ferrell Street Crossing. | Construct grade separation at Franklin Boulevard crossing (722959A) in Greensboro, and close O'Ferrell Street crossing (722961B). |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | O | CONSTRUCTION | 1005000 | FY 2027: 1005000
P-5711 | Rail | Other | CSX A Line | National Gateway Corridor | Construct freight rail and intermodal terminal infrastructure (CCX). | 12 | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO |  | Statewide Mobility |  |  |  | 94739000
P-5711A | Rail | Other | CSX A Line | National Gateway Corridor | Improve CSX intermodal terminal and track. |  | Edgecombe | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 43100000
P-5711C | Rail | Other | CSX A Line | National Gateway Corridor | Construct highway improvements |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility
P-5713 | Rail | STI (Prioritization) | North Carolina Railroad (NCRR) / Norfolk Southern | SR 1424 (Hilltop Road) in Greensboro. | Upgrade at-grade crossing to grade separation. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | T | RIGHT-OF-WAY | 9100000 | FY 2026: 2275000; FY 2027: 4550000; FY 2028: 2275000
P-5713 | Rail | STI (Prioritization) | North Carolina Railroad (NCRR) / Norfolk Southern | SR 1424 (Hilltop Road) in Greensboro. | Upgrade at-grade crossing to grade separation. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | T | UTILITIES | 1600000 | FY 2026: 800000; FY 2027: 800000
P-5713 | Rail | STI (Prioritization) | North Carolina Railroad (NCRR) / Norfolk Southern | SR 1424 (Hilltop Road) in Greensboro. | Upgrade at-grade crossing to grade separation. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | T | CONSTRUCTION | 19932000 | FY 2027: 199000; FY 2028: 8172000; FY 2029: 6578000; FY 2030: 3189000; FY 2031: 1794000
P-5713 | Rail | STI (Prioritization) | North Carolina Railroad (NCRR) / Norfolk Southern | SR 1424 (Hilltop Road) in Greensboro. | Upgrade at-grade crossing to grade separation. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | O | CONSTRUCTION | 268000 | FY 2027: 268000
P-5714 | Rail | STI (Prioritization) | North Carolina Railroad Norfolk Southern | Pomona Yard. | Extend auxiliary track and add power turnouts. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | CONSTRUCTION | 5100000 | FY 2027: 51000; FY 2028: 4641000; FY 2029: 408000
P-5714 | Rail | STI (Prioritization) | North Carolina Railroad Norfolk Southern | Pomona Yard. | Extend auxiliary track and add power turnouts. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION | Region D |  | O | CONSTRUCTION | 1500000 | FY 2027: 1500000
P-5715 | Rail | STI (Prioritization) | CSX | Crossing 630607N at New Hope Church Road in Raleigh. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  |  |  | 9832000
P-5715 | Rail | STI (Prioritization) | CSX | Crossing 630607N at New Hope Church Road in Raleigh. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 22780000 | FY 2026: 10191000; FY 2027: 6636000; FY 2028: 1900000
P-5717 | Rail | STI (Prioritization) | Norfolk Southern H Line | Crossing 734742W at SR 1121 (Cornwallis Road) in Durham. | Construct grade separation. |  | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  |  |  | 1200000
P-5717 | Rail | STI (Prioritization) | Norfolk Southern H Line | Crossing 734742W at SR 1121 (Cornwallis Road) in Durham. | Construct grade separation. |  | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T | RIGHT-OF-WAY | 4378000
P-5717 | Rail | STI (Prioritization) | Norfolk Southern H Line | Crossing 734742W at SR 1121 (Cornwallis Road) in Durham. | Construct grade separation. |  | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T | UTILITIES | 1878000
P-5717 | Rail | STI (Prioritization) | Norfolk Southern H Line | Crossing 734742W at SR 1121 (Cornwallis Road) in Durham. | Construct grade separation. |  | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T | CONSTRUCTION | 41600000 | FY 2026: 6240000; FY 2027: 11232000; FY 2028: 9984000; FY 2029: 7904000; FY 2030: 6240000
P-5718 | Rail | STI (Prioritization) | CSX | Crossing 643351A at SR 1415 (NE Maynard Road) in Cary. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  |  |  | 3681000
P-5718 | Rail | STI (Prioritization) | CSX | Crossing 643351A at SR 1415 (NE Maynard Road) in Cary. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | T | RIGHT-OF-WAY | 37300000 | FY 2028: 11563000; FY 2029: 15666000; FY 2030: 2611000; FY 2031: 3730000; FY 2032: 3730000
P-5718 | Rail | STI (Prioritization) | CSX | Crossing 643351A at SR 1415 (NE Maynard Road) in Cary. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | T | UTILITIES | 4500000 | FY 2028: 2250000; FY 2029: 2250000
P-5718 | Rail | STI (Prioritization) | CSX | Crossing 643351A at SR 1415 (NE Maynard Road) in Cary. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | T | CONSTRUCTION | 40549000 | FY 2031: 8921000; FY 2032: 10948000; FY 2033: 8921000; FY 2034: 6488000; FY 2035: 5271000
P-5718 | Rail | STI (Prioritization) | CSX | Crossing 643351A at SR 1415 (NE Maynard Road) in Cary. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | O | CONSTRUCTION | 1452000 | FY 2031: 1452000
P-5719 | Rail | STI (Prioritization) | Piedmont Corridor | Regionwide | Purchase and refurbish rail cars for Piedmont Service expansion. |  | Guilford, Davidson, Rowan, Alamance, Cabarrus, Orange, Wake, Durham, Mecklenburg, Randolph | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Triangle West TPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT |  |  |  |  | 9637000
P-5719A | Rail | STI (Prioritization) | Piedmont Corridor | - | Acquire and rebuild two additional locomotives. |  | Guilford, Wake, Mecklenburg | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | COMPLETE | Exempt
P-5719B | Rail | STI (Prioritization) | Piedmont Corridor | - | Acquire and rebuild two coach and one lounge/baggage rail cars. |  | Guilford, Wake, Mecklenburg | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS | Exempt
P-5719C | Rail | STI (Prioritization) | Piedmont Corridor | Regionwide | Purchase new trains and upgrade maintenance facility. |  | Davidson, Alamance, Cabarrus, Durham, Guilford, Mecklenburg, Orange, Rowan, Wake | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Greensboro Urban Area MPO, Triangle West TPO |  | Region C, D, E |  | DP | CONSTRUCTION | 156888000 | FY 2026: 156888000
P-5719C | Rail | STI (Prioritization) | Piedmont Corridor | Regionwide | Purchase new trains and upgrade maintenance facility. |  | Davidson, Alamance, Cabarrus, Durham, Guilford, Mecklenburg, Orange, Rowan, Wake | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Greensboro Urban Area MPO, Triangle West TPO |  | Region C, D, E |  | T | CONSTRUCTION | 55641000 | FY 2026: 10572000; FY 2027: 13354000; FY 2028: 12241000; FY 2029: 10572000; FY 2030: 8902000
P-5720 | Rail | STI (Prioritization) | CSX | Crossing 630601X at SR 2006 (Durant Road) in Raleigh. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307 | Region C |  |  |  | 8853000
P-5720 | Rail | STI (Prioritization) | CSX | Crossing 630601X at SR 2006 (Durant Road) in Raleigh. | Construct grade separation. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307 | Region C |  | T | CONSTRUCTION | 21910000 | FY 2026: 2407000; FY 2027: 10301000
P-5721 | Rail | STI (Prioritization) | Norfolk Southern | Jamestown siding in Jamestown. | Construct extension. |  | Guilford | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  |  |  | 407000
P-5721 | Rail | STI (Prioritization) | Norfolk Southern | Jamestown siding in Jamestown. | Construct extension. |  | Guilford | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | CONSTRUCTION | 2035000 | FY 2026: 20000; FY 2027: 1750000; FY 2028: 265000
P-5721 | Rail | STI (Prioritization) | Norfolk Southern | Jamestown siding in Jamestown. | Construct extension. |  | Guilford | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | O | CONSTRUCTION | 2035000 | FY 2026: 2035000
P-5722 | Rail | STI (Prioritization) | Norfolk Southern | Kimberly Clark in Lexington. | Construct lead. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. | Region D |  |  |  | 204000
P-5722 | Rail | STI (Prioritization) | Norfolk Southern | Kimberly Clark in Lexington. | Construct lead. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. | Region D |  | T | CONSTRUCTION | 1019000 | FY 2027: 632000; FY 2028: 387000
P-5722 | Rail | STI (Prioritization) | Norfolk Southern | Kimberly Clark in Lexington. | Construct lead. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. | Region D |  | O | CONSTRUCTION | 1019000 | FY 2027: 1019000
P-5724 | Rail | Economic Development | CSX | Rail spur for industrial access near end of SR 1495 (Pell Drive) in Maxton. | Construct spine track and turnouts, and rehabilitate existing track sections. |  | Scotland | 8 | Lumber River RPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CSX; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM | Division 8 |  |  |  | 9795000
P-5725 | Rail | STI (Prioritization) | Various | Locations in Kannapolis. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall, and signaling equipment. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  |  |  | 1850000
P-5725 | Rail | STI (Prioritization) | Various | Locations in Kannapolis. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall, and signaling equipment. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 3400000 | FY 2027: 3400000
P-5726 | Rail | STI (Prioritization) | Norfolk Southern | Norfolk Southern mainline in Rowan County. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall and signal equipment. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  |  |  | 4108000
P-5726 | Rail | STI (Prioritization) | Norfolk Southern | Norfolk Southern mainline in Rowan County. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall and signal equipment. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | RIGHT-OF-WAY | 1638000
P-5726 | Rail | STI (Prioritization) | Norfolk Southern | Norfolk Southern mainline in Rowan County. | Construct track improvements, second platform, pedestrian underpass, sitework, retaining wall and signal equipment. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | CONSTRUCTION | 13600000 | FY 2028: 5032000; FY 2029: 4896000; FY 2030: 3264000; FY 2031: 408000
P-5726A | Rail | STI (Prioritization) | Norfolk Southern Mainline | Salisbury Train Station | Construct second platform and pedestrian underpass. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | CONSTRUCTION | 2500000 | FY 2027: 1750000; FY 2028: 750000
P-5726B | Rail | STI (Prioritization) | Norfolk Southern Mainline | Salisbury Norfolk Southern Crossover. | Relocation. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | CONSTRUCTION | 4000000 | FY 2026: 1432000; FY 2027: 2568000
P-5730 | Rail | STI (Prioritization) | Clanton Road | End point of Clanton Road to US 29 / US 74 (Wilkinson Boulevard). | Extend roadway. Construct grade separation of Norfolk Southern Railroad and close the Donald Ross Road crossing. |  | Mecklenburg | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  |  |  | 2000000
P-5730 | Rail | STI (Prioritization) | Clanton Road | End point of Clanton Road to US 29 / US 74 (Wilkinson Boulevard). | Extend roadway. Construct grade separation of Norfolk Southern Railroad and close the Donald Ross Road crossing. |  | Mecklenburg | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | T | RIGHT-OF-WAY | 13600000 | FY 2030: 3400000; FY 2031: 6800000; FY 2032: 3400000
P-5730 | Rail | STI (Prioritization) | Clanton Road | End point of Clanton Road to US 29 / US 74 (Wilkinson Boulevard). | Extend roadway. Construct grade separation of Norfolk Southern Railroad and close the Donald Ross Road crossing. |  | Mecklenburg | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | T | UTILITIES | 1200000 | FY 2030: 600000; FY 2031: 600000
P-5730 | Rail | STI (Prioritization) | Clanton Road | End point of Clanton Road to US 29 / US 74 (Wilkinson Boulevard). | Extend roadway. Construct grade separation of Norfolk Southern Railroad and close the Donald Ross Road crossing. |  | Mecklenburg | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | T | CONSTRUCTION | 61966000 | FY 2034: 6196000; FY 2035: 18589000 | 37181000
P-5730 | Rail | STI (Prioritization) | Clanton Road | End point of Clanton Road to US 29 / US 74 (Wilkinson Boulevard). | Extend roadway. Construct grade separation of Norfolk Southern Railroad and close the Donald Ross Road crossing. |  | Mecklenburg | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | O | CONSTRUCTION | 835000 | FY 2034: 8000; FY 2035: 408000 | 419000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 50000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | RIGHT-OF-WAY | 2400000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 6500000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | UTILITIES | 10000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | DP | CONSTRUCTION | 14050000 | FY 2026: 5198000; FY 2027: 4356000; FY 2028: 3512000; FY 2029: 984000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 16950000 | FY 2026: 3390000; FY 2027: 4238000; FY 2028: 3898000; FY 2029: 3051000; FY 2030: 2373000
P-5731 | Rail | STI (Prioritization) | Norfolk Southern | Crossing 722306Y (East 7th avenue) in Lexington. | Construct grade separation in vicinity of 5th street and close crossing 722306Y. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 41000000 | FY 2026: 13177000; FY 2027: 14220000; FY 2028: 10627000; FY 2029: 2976000
P-5732 | Rail | Other | North Carolina Railroad | Lexington train station. | Construct track improvements and multi-modal passenger rail and bus station in the Lexington depot district. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Exempt |  | DP | CONSTRUCTION | 10950000 | FY 2026: 10950000
P-5732 | Rail | Other | North Carolina Railroad | Lexington train station. | Construct track improvements and multi-modal passenger rail and bus station in the Lexington depot district. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Exempt |  | O | CONSTRUCTION | 2138000 | FY 2026: 2138000
P-5732 | Rail | Other | North Carolina Railroad | Lexington train station. | Construct track improvements and multi-modal passenger rail and bus station in the Lexington depot district. |  | Davidson | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Exempt |  | L | CONSTRUCTION | 2612000 | FY 2026: 2612000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  |  |  | 30000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | CMAQ | ENGINEERING | 523000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | T | ENGINEERING | 197000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | CMAQ | RIGHT-OF-WAY | 3853000 | FY 2026: 3853000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | T | RIGHT-OF-WAY | 1447000 | FY 2026: 1447000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | CMAQ | CONSTRUCTION | 4143000 | FY 2026: 2320000; FY 2027: 1823000
P-5733 | Rail | STI (Prioritization) | Norfolk Southern | City of Salisbury. | Upgrade station building, expand waiting space and surface parking. |  | Rowan | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | T | CONSTRUCTION | 1556000 | FY 2026: 871000; FY 2027: 685000
P-5734 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | SR 1655 (Trinity Road) crossing in Cary. | Construct grade separation and close crossing 630657S. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  |  |  | 3000000
P-5734 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | SR 1655 (Trinity Road) crossing in Cary. | Construct grade separation and close crossing 630657S. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | T | RIGHT-OF-WAY | 23400000 | FY 2028: 234000; FY 2029: 11466000; FY 2030: 9360000; FY 2031: 2340000
P-5734 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | SR 1655 (Trinity Road) crossing in Cary. | Construct grade separation and close crossing 630657S. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | T | UTILITIES | 960000 | FY 2028: 960000
P-5734 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | SR 1655 (Trinity Road) crossing in Cary. | Construct grade separation and close crossing 630657S. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | T | CONSTRUCTION | 28765000 | FY 2031: 4027000; FY 2032: 8917000; FY 2033: 7191000; FY 2034: 5178000; FY 2035: 3452000
P-5734 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | SR 1655 (Trinity Road) crossing in Cary. | Construct grade separation and close crossing 630657S. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | O | CONSTRUCTION | 835000 | FY 2031: 835000
P-5735 | Rail | STI (Prioritization) | Norfolk Southern Main Line | SR 1584 (Yanceyville Street) crossing in Greensboro. | Construct grade separation and close crossing 722542d. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1270000
P-5735 | Rail | STI (Prioritization) | Norfolk Southern Main Line | SR 1584 (Yanceyville Street) crossing in Greensboro. | Construct grade separation and close crossing 722542d. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7000000
P-5735 | Rail | STI (Prioritization) | Norfolk Southern Main Line | SR 1584 (Yanceyville Street) crossing in Greensboro. | Construct grade separation and close crossing 722542d. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 20411000
P-5735 | Rail | STI (Prioritization) | Norfolk Southern Main Line | SR 1584 (Yanceyville Street) crossing in Greensboro. | Construct grade separation and close crossing 722542d. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 1390000
P-5736 | Rail | STI (Prioritization) | North Carolina Railroad; Norfolk Southern H Line | Beryl Road crossing in Raleigh. | Extend Beryl Road to Royal Avenue, and close crossing 630647L. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  |  |  | 300000
P-5736 | Rail | STI (Prioritization) | North Carolina Railroad; Norfolk Southern H Line | Beryl Road crossing in Raleigh. | Extend Beryl Road to Royal Avenue, and close crossing 630647L. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | RIGHT-OF-WAY | 3700000 | FY 2030: 3700000
P-5736 | Rail | STI (Prioritization) | North Carolina Railroad; Norfolk Southern H Line | Beryl Road crossing in Raleigh. | Extend Beryl Road to Royal Avenue, and close crossing 630647L. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | UTILITIES | 1700000 | FY 2030: 1700000
P-5736 | Rail | STI (Prioritization) | North Carolina Railroad; Norfolk Southern H Line | Beryl Road crossing in Raleigh. | Extend Beryl Road to Royal Avenue, and close crossing 630647L. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | CONSTRUCTION | 5396000 | FY 2033: 3022000; FY 2034: 2374000
P-5736 | Rail | STI (Prioritization) | North Carolina Railroad; Norfolk Southern H Line | Beryl Road crossing in Raleigh. | Extend Beryl Road to Royal Avenue, and close crossing 630647L. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | O | CONSTRUCTION | 4000 | FY 2033: 4000
P-5737 | Rail | STI (Prioritization) | CSX S Line | SR 2108 (Millbrook Road) in Raleigh. | Construct grade separation and close crossing 630605A. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  |  |  | 2010000
P-5737 | Rail | STI (Prioritization) | CSX S Line | SR 2108 (Millbrook Road) in Raleigh. | Construct grade separation and close crossing 630605A. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | T | RIGHT-OF-WAY | 6111000
P-5737 | Rail | STI (Prioritization) | CSX S Line | SR 2108 (Millbrook Road) in Raleigh. | Construct grade separation and close crossing 630605A. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | T | UTILITIES | 1228000
P-5737 | Rail | STI (Prioritization) | CSX S Line | SR 2108 (Millbrook Road) in Raleigh. | Construct grade separation and close crossing 630605A. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 10518000 | FY 2027: 10518000
P-5737 | Rail | STI (Prioritization) | CSX S Line | SR 2108 (Millbrook Road) in Raleigh. | Construct grade separation and close crossing 630605A. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | T | CONSTRUCTION | 15882000 | FY 2027: 3335000; FY 2028: 5082000; FY 2029: 3812000; FY 2030: 2700000; FY 2031: 953000
P-5740 | Rail | STI (Prioritization) | CSX Southeast Line | Wilmington. | Construct Wilmington Beltline Speed Improvements | 13 | New Hanover, Brunswick | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT FEDERAL CRISI GRANT. | Statewide Mobility |  |  |  | 4080000
P-5740A | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Rehabilitate ties and curves, realign curve, upgrade bridges. |  | New Hanover, Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | DP | CONSTRUCTION | 15522000
P-5740A | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Rehabilitate ties and curves, realign curve, upgrade bridges. |  | New Hanover, Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 17478000
P-5740B | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Close and improve various at-grade crossings. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 2600000
P-5740B | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Close and improve various at-grade crossings. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 270000
P-5740B | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Close and improve various at-grade crossings. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | DP | CONSTRUCTION | 2393000 | FY 2026: 300000; FY 2027: 2033000; FY 2028: 60000
P-5740B | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Close and improve various at-grade crossings. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 1807000 | FY 2026: 289000; FY 2027: 1355000; FY 2028: 163000
P-5740C | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Install railroad grade crossing signals and gates at various at-grade crossings. |  | New Hanover, Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | DP | CONSTRUCTION | 6639000 | FY 2026: 66000; FY 2027: 4382000; FY 2028: 2191000
P-5740C | Rail | STI (Prioritization) | CSX SE Line | Wilmington. | Install railroad grade crossing signals and gates at various at-grade crossings. |  | New Hanover, Brunswick | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1661000 | FY 2026: 17000; FY 2027: 1096000; FY 2028: 548000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  |  |  | 1300000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | DP | RIGHT-OF-WAY | 31000 | FY 2026: 8000; FY 2027: 15000; FY 2028: 8000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | T | RIGHT-OF-WAY | 5817000 | FY 2026: 58000; FY 2027: 1978000; FY 2028: 1978000; FY 2029: 639000; FY 2030: 1164000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | T | UTILITIES | 826000 | FY 2026: 826000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | DP | CONSTRUCTION | 3110000 | FY 2028: 1804000; FY 2029: 1193000; FY 2030: 113000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | T | CONSTRUCTION | 19740000 | FY 2028: 6514000; FY 2029: 6712000; FY 2030: 3948000; FY 2031: 2566000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (Wesley Chapel Stouts Road). | Construct grade separation. |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | O | CONSTRUCTION | 250000 | FY 2028: 145000; FY 2029: 96000; FY 2030: 9000
P-5747 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | South English Street crossing in Greensboro. | Construct grade separation and close crossing 722955X. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  |  |  | 1500000
P-5747 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | South English Street crossing in Greensboro. | Construct grade separation and close crossing 722955X. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | RIGHT-OF-WAY | 8800000 | FY 2026: 792000; FY 2027: 3080000; FY 2028: 3168000; FY 2029: 880000; FY 2030: 880000
P-5747 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | South English Street crossing in Greensboro. | Construct grade separation and close crossing 722955X. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | UTILITIES | 720000 | FY 2026: 720000
P-5747 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | South English Street crossing in Greensboro. | Construct grade separation and close crossing 722955X. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | CONSTRUCTION | 23659000 | FY 2028: 237000; FY 2029: 8990000; FY 2030: 7571000; FY 2031: 4022000; FY 2032: 2839000
P-5747 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern H Line | South English Street crossing in Greensboro. | Construct grade separation and close crossing 722955X. |  | Guilford | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | O | CONSTRUCTION | 1242000 | FY 2028: 1242000
P-5748 | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct rail siding and grade separation in vicinity of SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Union | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS; OTHER FUNDING PROVIDED BY CSX.
P-5748A | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw. | Construct rail siding. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | T | CONSTRUCTION | 5894000 | FY 2026: 354000
P-5748B | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct grade separation at SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | RIGHT-OF-WAY | 5000000
P-5748B | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct grade separation at SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | UTILITIES | 378000
P-5748B | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct grade separation at SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | DP | CONSTRUCTION | 4700000 | FY 2026: 47000; FY 2027: 2397000; FY 2028: 1598000; FY 2029: 658000
P-5748B | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct grade separation at SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 19251000 | FY 2026: 1540000; FY 2027: 7123000; FY 2028: 5390000; FY 2029: 3273000; FY 2030: 1925000
P-5748B | Rail | STI (Prioritization) | CSX SG Line | SR 1300 (Helms Road) in Waxhaw; SR 1432 (Tory Path) in Waxhaw. | Construct grade separation at SR 1300 (Helms Road). Close at-grade crossings at SR 1300 (Helms Road) and SR 1432 (Troy Path). |  | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | O | CONSTRUCTION | 251000 | FY 2026: 3000; FY 2027: 128000; FY 2028: 85000; FY 2029: 35000
P-5750 | Rail | STI (Prioritization) | CSX SF LINE | Polkton. | Construct rail siding extension. |  | Anson | 10 | Rocky River RPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS |  |  |  |  | 1600000
P-5750A | Rail | STI (Prioritization) | CSX SF LINE | Polkton. | Construct rail siding extension. |  | Anson | 10 | Rocky River RPO |  | Region E |  | DP | CONSTRUCTION | 3200000 | FY 2026: 471000
P-5750A | Rail | STI (Prioritization) | CSX SF LINE | Polkton. | Construct rail siding extension. |  | Anson | 10 | Rocky River RPO |  | Region E |  | T | CONSTRUCTION | 9837000 | FY 2026: 1449000
P-5750B | Rail | STI (Prioritization) | CSX SF LINE | SR 1469 (Freedom Road) intersection in Polkton. | Construct grade separation. |  | Anson | 10 | Rocky River RPO |  | Region E |  | T | RIGHT-OF-WAY | 2000000 | FY 2029: 2000000
P-5750B | Rail | STI (Prioritization) | CSX SF LINE | SR 1469 (Freedom Road) intersection in Polkton. | Construct grade separation. |  | Anson | 10 | Rocky River RPO |  | Region E |  | T | UTILITIES | 480000 | FY 2029: 480000
P-5750B | Rail | STI (Prioritization) | CSX SF LINE | SR 1469 (Freedom Road) intersection in Polkton. | Construct grade separation. |  | Anson | 10 | Rocky River RPO |  | Region E |  | T | CONSTRUCTION | 26400000 | FY 2033: 5544000; FY 2034: 9504000; FY 2035: 6336000 | 5016000
P-5751 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern Main Line | SR 2165 (Turner Street) in Thomasville. | Construct grade separation and close crossing 722327S. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 28300000
P-5751 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern Main Line | SR 2165 (Turner Street) in Thomasville. | Construct grade separation and close crossing 722327S. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2300000
P-5751 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern Main Line | SR 2165 (Turner Street) in Thomasville. | Construct grade separation and close crossing 722327S. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 30678000
P-5751 | Rail | STI (Prioritization) | North Carolina Railroad / Norfolk Southern Main Line | SR 2165 (Turner Street) in Thomasville. | Construct grade separation and close crossing 722327S. |  | Davidson | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 709000
P-5753 | Rail | Other | CSX S Line | CSX S Line from Raleigh to Virginia State line and CSX SA Line from Raleigh to Weldon. | Acquire right of way, upgrade existing track and construct new track. | 50 | Franklin, Vance, Wake, Warren | 5 | Capital Area MPO, Kerr-Tar RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
P-5753A | Rail | Other | CXS S / SA Line | Raleigh to NC 98. | Acquire right of way, upgrade existing track, and construct new track. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AA | Rail | Other | CXS S Line | Raleigh Union Station to NC 98. | Improve rail-line. | 28.66 | Wake | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AE | Rail | Other | CXS S Line | Various | Construct Hargett Street, SR 5908 (Morgan Street), and US 401 (Capital Boulevard) roadway improvements and pedestrian overpass at Jones Street. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AF | Rail | Other | CXS S Line | Whitaker Mill Road | Improve roadway. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AG | Rail | Other | CXS S Line | Highwoods Boulevard Intersection | Construct grade separation. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AH | Rail | Other | CXS S Line | Various | Construct SR 2013 (Gresham Lake Road) and SR 2044 (Ligon Mill Road) grade separations and roadway improvements at SR 2046 (Seawell Drive) and Friendship Chapel Road. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | CMAQ | ENGINEERING | 1500000 | FY 2026: 1500000
P-5753AH | Rail | Other | CXS S Line | Various | Construct SR 2013 (Gresham Lake Road) and SR 2044 (Ligon Mill Road) grade separations and roadway improvements at SR 2046 (Seawell Drive) and Friendship Chapel Road. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | CMAQ | RIGHT-OF-WAY | 26920000 | FY 2027: 13460000; FY 2028: 13460000
P-5753AH | Rail | Other | CXS S Line | Various | Construct SR 2013 (Gresham Lake Road) and SR 2044 (Ligon Mill Road) grade separations and roadway improvements at SR 2046 (Seawell Drive) and Friendship Chapel Road. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | CMAQ | UTILITIES | 580000 | FY 2027: 580000
P-5753AH | Rail | Other | CXS S Line | Various | Construct SR 2013 (Gresham Lake Road) and SR 2044 (Ligon Mill Road) grade separations and roadway improvements at SR 2046 (Seawell Drive) and Friendship Chapel Road. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | CMAQ | CONSTRUCTION | 21000000 | FY 2030: 10500000; FY 2031: 10500000
P-5753AI | Rail | Other | CXS S Line | Ligon Mill Road; Seawell Drive; Friendship Chapel Road | Construct grade separation at Ligon Mill Road; Construct roadway improvements at Seawell Drive and Friendship Chapel Road. |  | Wake | 5 | Capital Area MPO
P-5753B | Rail | Other | CXS S Line | NC 98 to Franklinton |  |  | Wake, Franklin, Vance | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility
P-5753BA | Rail | Other | CXS S Line | NC 98 to Franklinton | Improve rail-line. | 16.88 | Wake, Franklin | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BD | Rail | Other | CXS S Line | Various | Holding Avenue grade separation, Elm Avenue improvements, and Brick Street pedestrian crossing. |  | Franklin | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BE | Rail | Other | CXS S Line | Various | Construct NC 96 / Main Street bypass grade separation and Youngsville roadway improvements. |  | Franklin | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BF | Rail | Other | CXS S Line | Various | SR 1133 (Bert Winston Road) and SR 1125 (Cedar Creek Road) grade separation and Franklinton roadway improvements. |  | Franklin | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BG | Rail | Other | CXS S Line | South Kitrell | Improve roadway. |  | Franklin, Vance | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility
P-5753BH | Rail | Other | CXS S Line | North Kitrell | Roadway improvements of North Kitrell Roadway including McClanahan Street grade separation and SR 1458 (Peter Gill Road). |  | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753C | Rail | Other | CXS S Line | Franklinton to Ridgeway |  |  | Vance, Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CA | Rail | Other | CXS S Line | Franklinton to Ridgeway | Improve S-line. | 36.46 | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CD | Rail | Other | CXS S Line | SR 1115 (Bear Pond Road) | Construct grade separation. |  | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CE | Rail | Other | CXS S Line | SR 1139 (JP Taylor Road) | Construct grade separation and improve roadway. |  | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CF | Rail | Other | CXS S Line | Alexander Avenue | Construct Alexander Avenue grade separation and roadway improvements on SR 1267 (Dabney Drive) |  | Vance | 5 | Kerr-Tar RPO |  | Region C |  | T | RIGHT-OF-WAY | 9000000 | FY 2030: 2250000; FY 2031: 2250000; FY 2032: 2250000; FY 2033: 2250000
P-5753CF | Rail | Other | CXS S Line | Alexander Avenue | Construct Alexander Avenue grade separation and roadway improvements on SR 1267 (Dabney Drive) |  | Vance | 5 | Kerr-Tar RPO |  | Region C |  | T | UTILITIES | 800000 | FY 2030: 800000
P-5753CF | Rail | Other | CXS S Line | Alexander Avenue | Construct Alexander Avenue grade separation and roadway improvements on SR 1267 (Dabney Drive) |  | Vance | 5 | Kerr-Tar RPO |  | Region C |  | T | CONSTRUCTION | 20000000 | FY 2033: 5000000; FY 2034: 5000000; FY 2035: 5000000 | 5000000
P-5753CG | Rail | Other | CXS S Line | Andrews | Construct grade separation and improve downtown roadways. |  | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CH | Rail | Other | CXS S Line | Various | Construct grade separation at SR 1508 (Greystone Road) and Warrenton roadway improvements. |  | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CI | Rail | Other | CXS S Line | Various | Construct grade separation at SR 1507 (Brookston Road) and SR 1501 (South Carroll Street). |  | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CJ | Rail | Other | CXS S Line | SR 1101 (Kimball Road) | Construct grade separation. |  | Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753D | Rail | Other | CXS S Line | Ridgeway to Paschall |  |  | Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DA | Rail | Other | CXS S Line | Ridgeway to VA State Line | Improve rail-line. | 13.51 | Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DC | Rail | Other | CXS S Line | Various | Construct grade separation in Drewry and roadway improvements on SR 1151 (Soul City Boulevard) |  | Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DD | Rail | Other | CXS S Line | Norlina | Construct roadway improvements. |  | Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DE | Rail | Other | CXS S Line | Various | Construct roadway improvements in Wise and on SR 1302 (Felts Road) |  | Warren | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5754 | Rail | Other | SR 2623 (Trailer Drive) | Norfolk Southern (Crossing Number 910 618A, MP O4.11) | Construct at grade crossing improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN | Exempt |  | O | ENGINEERING | 50000
P-5754 | Rail | Other | SR 2623 (Trailer Drive) | Norfolk Southern (Crossing Number 910 618A, MP O4.11) | Construct at grade crossing improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN | Exempt |  | O | CONSTRUCTION | 1200000
R-0204 | Highway | STI (Prioritization) | US 221 / NC 226 | SR 1434 (Toms Creek Road) to SR 1153 (Goose Creek Road / Old Glenwood Road). | Widen to multi-lanes with a bypass of Marion. | 12.4 | McDowell | 13 | Foothills RPO | [5 empty] | 38468000
R-0204A | Highway | Pre-STI (Historic) | US 221 / NC 226 | SR 1434 (Toms Creek Road) north of Marion to US 221 / NC 226 Business. | Widen to multi-lanes, with a bypass of Marion. |  | McDowell | 13 | Foothills RPO | COMPLETE
R-0204B | Highway | Pre-STI (Historic) | US 221 (Marion Bypass) | US 221 / NC 226 Business to south of Southern Railway. | Widen to multi-lanes, with a bypass of Marion. |  | McDowell | 13 | Foothills RPO | COMPLETE
R-0204C | Highway | Pre-STI (Historic) | US 221 (Marion Bypass) | South of Southern Railway to US 221 / NC 226 intersection south of Marion. | Widen to multi-lanes, with a bypass of Marion. | 0.5 | McDowell | 13 | Foothills RPO | COMPLETE
R-0204D | Highway | STI (Prioritization) | US 221 | NC 266 south of Marion to north of I-40. | Widen to multi-lanes with a bypass of Marion. | 0.5 | McDowell | 13 | Foothills RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3000000 | [10 empty] | 3000000
R-0204D | Highway | STI (Prioritization) | US 221 | NC 266 south of Marion to north of I-40. | Widen to multi-lanes with a bypass of Marion. | 0.5 | McDowell | 13 | Foothills RPO |  | Not Funded |  | T | UTILITIES | 500000 | [10 empty] | 500000
R-0204D | Highway | STI (Prioritization) | US 221 | NC 266 south of Marion to north of I-40. | Widen to multi-lanes with a bypass of Marion. | 0.5 | McDowell | 13 | Foothills RPO |  | Not Funded |  | T | CONSTRUCTION | 32500000 | [10 empty] | 32500000
R-0204EA | Highway | STI (Prioritization) | US 221 | I-40 interchange. | Construct interchange improvements. | 2.13 | McDowell | 13 | Foothills RPO |  | Division 13 |  | NHP | RIGHT-OF-WAY | 20100000 | FY 2026: 202000; FY 2027: 6224000; FY 2028: 6224000; FY 2029: 3430000; FY 2030: 4020000
R-0204EA | Highway | STI (Prioritization) | US 221 | I-40 interchange. | Construct interchange improvements. | 2.13 | McDowell | 13 | Foothills RPO |  | Division 13 |  | NHP | UTILITIES | 1600000 | FY 2026: 800000; FY 2027: 800000
R-0204EA | Highway | STI (Prioritization) | US 221 | I-40 interchange. | Construct interchange improvements. | 2.13 | McDowell | 13 | Foothills RPO |  | Division 13 |  | NHP | CONSTRUCTION | 42700000 | FY 2029: 6335000; FY 2030: 12822000; FY 2031: 11317000; FY 2032: 8449000; FY 2033: 3777000
R-0204EB | Highway | STI (Prioritization) | US 221 | North of I-40 to SR 1153 (Goose Creek Road). | Widen to multi-lanes. | 2.13 | McDowell | 13 | Foothills RPO |  | Division 13 |  | NHP | RIGHT-OF-WAY | 4000000 | FY 2030: 40000; FY 2031: 1239000; FY 2032: 1239000; FY 2033: 682000; FY 2034: 800000
R-0204EB | Highway | STI (Prioritization) | US 221 | North of I-40 to SR 1153 (Goose Creek Road). | Widen to multi-lanes. | 2.13 | McDowell | 13 | Foothills RPO |  | Division 13 |  | NHP | UTILITIES | 2200000 | FY 2030: 1100000; FY 2031: 1100000
R-0204EB | Highway | STI (Prioritization) | US 221 | North of I-40 to SR 1153 (Goose Creek Road). | Widen to multi-lanes. | 2.13 | McDowell | 13 | Foothills RPO |  | Division 13 |  | NHP | CONSTRUCTION | 33400000 | FY 2033: 4955000; FY 2034: 10029000; FY 2035: 8852000 | 9564000
R-0211 | Highway | STI (Prioritization) | I-485 (Charlotte Southern Outer Loop) | West of I-77 to US 74. | Construct multi-lane freeway on new location. | 24.18 | Mecklenburg | 10 | Charlotte Regional TPO | [5 empty] | 271729000
R-0211EC | Highway | STI (Prioritization) | I-485 (Charlotte Southern Outer Loop) | SR 3468 (Weddington Road) in Matthews. | Construct interchange. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PROJECT LET WITH I-5507. | Division 10 |  | T | CONSTRUCTION | 9000000
R-0623 | Highway | Transition | NC 24 / NC 27 | Troy Bypass, west of SR 1138 (Dairy Road) to east of Little River. | Widen to four lanes, part on new location. | 5.42 | Montgomery | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 62570000
R-1015 | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 10.1 | Craven | 2 | Down East RPO, New Bern Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8M FOR RIGHT-OF-WAY, $2.2M FOR UTILITIES, AND $100M FOR CONSTRUCTION, PAYBACK FY 2019 - 2033. |  |  |  |  | 216113000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | GARVEE ROW | 2445000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | GARVEE UTL | 1425000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | T(M) | RIGHT-OF-WAY | 158000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | T(M) | UTILITIES | 92000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | GARVEE CON | 60060000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | CONSTRUCTION | 25732000
R-1015DIV | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | T(M) | CONSTRUCTION | 28380000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | GARVEE ROW | 2445000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | GARVEE UTL | 1425000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | T(M) | RIGHT-OF-WAY | 158000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | T(M) | UTILITIES | 92000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | GARVEE CON | 60060000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | CONSTRUCTION | 25731000
R-1015REG | Highway | STI (Prioritization) | US 70 (Havelock Bypass) | North of Pine Grove to North of Carteret County line. | Construct multi-lane facility on new location. | 12.31 | Craven | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | T(M) | CONSTRUCTION | 19916000
R-2220 | Highway | STI (Prioritization) | US 64 | East of I-85 Business in Lexington to Asheboro Bypass. | Widen to multi-lanes. |  | Davidson, Randolph | 8, 9 | High Point Urban Area MPO, Piedmont Triad RPO | [5 empty] | 18647000
R-2220A | Highway | STI (Prioritization) | US 64 | I-85 Business in Lexington to east of I-85. | Widen to multi-lanes. |  | Davidson | 9 | High Point Urban Area MPO | COMPLETE
R-2220B | Highway | STI (Prioritization) | US 64 | I-85 east of Lexington to NC 109. | Widen to multi-lanes. |  | Davidson | 9 | High Point Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 30992000 | [10 empty] | 30992000
R-2220B | Highway | STI (Prioritization) | US 64 | I-85 east of Lexington to NC 109. | Widen to multi-lanes. |  | Davidson | 9 | High Point Urban Area MPO |  | Not Funded |  | T | UTILITIES | 5635000 | [10 empty] | 5635000
R-2220B | Highway | STI (Prioritization) | US 64 | I-85 east of Lexington to NC 109. | Widen to multi-lanes. |  | Davidson | 9 | High Point Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 40572000 | [10 empty] | 40572000
R-2220C | Highway | STI (Prioritization) | US 64 | NC 109 to SR 1409 (Lake Park Road). | Widen to multi-lanes. |  | Randolph, Davidson | 8, 9 | High Point Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 13746000 | [10 empty] | 13746000
R-2220C | Highway | STI (Prioritization) | US 64 | NC 109 to SR 1409 (Lake Park Road). | Widen to multi-lanes. |  | Randolph, Davidson | 8, 9 | High Point Urban Area MPO |  | Not Funded |  | T | UTILITIES | 1650000 | [10 empty] | 1650000
R-2220C | Highway | STI (Prioritization) | US 64 | NC 109 to SR 1409 (Lake Park Road). | Widen to multi-lanes. |  | Randolph, Davidson | 8, 9 | High Point Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 56452000 | [10 empty] | 56452000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Randolph | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 8880000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Randolph | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 2220000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Randolph | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 4000000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Randolph | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 1000000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Randolph | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 93680000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (Lake Park Road) to Asheboro Bypass. | Widen to multi-lanes. | 6.56 | Randolph | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 23420000
R-2233 | Highway | STI (Prioritization) | US 221 | South Carolina state line to north of SR 1366 (Roper Loop Road). | Widen to multi-lanes with bypass of Rutherfordton on new location. | 18.2 | Rutherford | 13 | Foothills RPO | [5 empty] | 146177000
R-2233AA | Highway | Pre-STI (Historic) | US 221 | South Carolina state line to south of Floyd's Creek. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 3.3 | Rutherford | 13 | Foothills RPO | COMPLETE | Division 13
R-2233AB | Highway | Pre-STI (Historic) | US 221 | South Carolina state line to south of Floyd's Creek. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 6.2 | Rutherford | 13 | Foothills RPO | COMPLETE
R-2233BA | Highway | STI (Prioritization) | US 221 | North of US 74 Bypass in Rutherfordton to south of US 74 Business. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 4.52 | Rutherford | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). $15M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Division 13 |  | T | RIGHT-OF-WAY | 18100000 | FY 2026: 4455000; FY 2027: 4455000; FY 2028: 3342000; FY 2029: 3620000
R-2233BA | Highway | STI (Prioritization) | US 221 | North of US 74 Bypass in Rutherfordton to south of US 74 Business. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 4.52 | Rutherford | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). $15M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Division 13 |  | T | UTILITIES | 3000000 | FY 2026: 1500000
R-2233BA | Highway | STI (Prioritization) | US 221 | North of US 74 Bypass in Rutherfordton to south of US 74 Business. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 4.52 | Rutherford | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). $15M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Division 13 |  | T | BUILD NC CON | 58500000 |  |  | 2600000 | 2600000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 29900000
R-2233BA | Highway | STI (Prioritization) | US 221 | North of US 74 Bypass in Rutherfordton to south of US 74 Business. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 4.52 | Rutherford | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). $15M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Division 13 |  | T | CONSTRUCTION | 100200000 | FY 2028: 0; FY 2029: 13560000; FY 2030: 21300000; FY 2031: 33396000; FY 2032: 31944000
R-2233BB | Highway | STI (Prioritization) | US 221 | South of US 74 Business to north of SR 1366 (Roper Loop Road) in Rutherfordton. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 3.51 | Rutherford | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 13 |  | T | RIGHT-OF-WAY | 20000000
R-2233BB | Highway | STI (Prioritization) | US 221 | South of US 74 Business to north of SR 1366 (Roper Loop Road) in Rutherfordton. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 3.51 | Rutherford | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 13 |  | T | BUILD NC CON | 32175000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000
R-2233BB | Highway | STI (Prioritization) | US 221 | South of US 74 Business to north of SR 1366 (Roper Loop Road) in Rutherfordton. | Widen to multi-lanes with bypass of Rutherfordton on new location. | 3.51 | Rutherford | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 13 |  | T | CONSTRUCTION | 100622000 | FY 2026: 26488000; FY 2027: 15000000
R-2246 | Highway | STI (Prioritization) | George Liles Parkway | NC 49 to south of I-85 in Concord. | Widen to four lanes divided, part on new location. | 6.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | [5 empty] | 73291000
R-2246A | Highway | STI (Prioritization) | George Liles Parkway | NC 49 to SR 1304 (Roberta Road) in Concord. | Widen to four lanes divided, part on new location. | 1.59 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6400000
R-2246A | Highway | STI (Prioritization) | George Liles Parkway | NC 49 to SR 1304 (Roberta Road) in Concord. | Widen to four lanes divided, part on new location. | 1.59 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 8800000
R-2246A | Highway | STI (Prioritization) | George Liles Parkway | NC 49 to SR 1304 (Roberta Road) in Concord. | Widen to four lanes divided, part on new location. | 1.59 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 42100000
R-2246B | Highway | Pre-STI (Historic) | George Liles Parkway | SR 1304 (Roberta Road) to SR 1431 (Weddington Road). | Widen to four lanes divided, some on new location. | 2.98 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE
R-2246C | Highway | Pre-STI (Historic) | George Liles Parkway | SR 1431 (Weddington Road) to south of I-85. | Widen to four lanes divided, some on new location. | 1.236 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE
R-2247 | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, I-40 to US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 17.4 | Forsyth | 9 | Winston-Salem Area TPO | [5 empty] | 214599000
R-2247A | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, US 158 to south of I-40 | Construct four lane expressway on new location, including ITS deployment. | 1.95 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 13200000 | [10 empty] | 13200000
R-2247A | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, US 158 to south of I-40 | Construct four lane expressway on new location, including ITS deployment. | 1.95 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | UTILITIES | 18900000 | [10 empty] | 18900000
R-2247A | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, US 158 to south of I-40 | Construct four lane expressway on new location, including ITS deployment. | 1.95 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | CONSTRUCTION | 39101000 | [10 empty] | 39101000
R-2247B | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, south of I-40 to south of US 421 interchange. | Construct four lane expressway on new location, including ITS deployment. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 31900000
R-2247B | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, south of I-40 to south of US 421 interchange. | Construct four lane expressway on new location, including ITS deployment. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3000000
R-2247B | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, south of I-40 to south of US 421 interchange. | Construct four lane expressway on new location, including ITS deployment. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 149500000
R-2247CA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, interchange with US 421 and interchange with SR 1140 (Peace Have Road). | Construct four lane expressway on new location, including ITS deployment. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 500000
R-2247CA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, interchange with US 421 and interchange with SR 1140 (Peace Have Road). | Construct four lane expressway on new location, including ITS deployment. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 261000
R-2247CA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, interchange with US 421 and interchange with SR 1140 (Peace Have Road). | Construct four lane expressway on new location, including ITS deployment. | 1 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 140900000
R-2247CB | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, north of US 421 interchange to SR 1348 (Robinhood Road). | Construct four lane expressway on new location, including ITS deployment. | 3.24 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 11000000
R-2247CB | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, north of US 421 interchange to SR 1348 (Robinhood Road). | Construct four lane expressway on new location, including ITS deployment. | 3.24 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 14000000
R-2247CB | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, north of US 421 interchange to SR 1348 (Robinhood Road). | Construct four lane expressway on new location, including ITS deployment. | 3.24 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 92001000
R-2247CC | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, bridges 330221 and 330222 over Muddy Creek. | Replace bridges. |  | Forsyth | 9 | Winston-Salem Area TPO | COMPLETE - WORK ACCOMPLISHED UNDER B-4507
R-2247CD | Highway | STI (Prioritization) | SR 1891 (Peace Haven Road / Future I-274) | US 421 Interchange and approaches in Winston-Salem. | Construct interchange. | 1 | Forsyth | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247EC | Statewide Mobility
R-2247D | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, north of SR 1348 (Meadowlark Drive / Robinhood Road) to NC 67. | Construct four lane expressway on new location, including ITS deployment. | 4.61 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | T | RIGHT-OF-WAY | 2100000 | FY 2028: 394000; FY 2029: 949000; FY 2030: 317000; FY 2031: 220000; FY 2032: 220000
R-2247D | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, north of SR 1348 (Meadowlark Drive / Robinhood Road) to NC 67. | Construct four lane expressway on new location, including ITS deployment. | 4.61 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | T | UTILITIES | 6500000 | FY 2028: 3250000; FY 2029: 3250000
R-2247D | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, north of SR 1348 (Meadowlark Drive / Robinhood Road) to NC 67. | Construct four lane expressway on new location, including ITS deployment. | 4.61 | Forsyth | 9 | Winston-Salem Area TPO |  | Region D |  | T | CONSTRUCTION | 159100000 | FY 2032: 20683000; FY 2033: 39775000; FY 2034: 36593000; FY 2035: 33411000 | 28638000
R-2247EA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, NC 67 to south of US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 4.53 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | T | RIGHT-OF-WAY | 3800000 | FY 2027: 1026000; FY 2028: 1520000; FY 2029: 494000; FY 2030: 380000; FY 2031: 380000
R-2247EA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, NC 67 to south of US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 4.53 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | T | UTILITIES | 6700000 | FY 2027: 3350000; FY 2028: 3350000
R-2247EA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, NC 67 to south of US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 4.53 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | T | BUILD NC CON | 35100000 |  |  |  |  | 2340000 | 2340000 | 2340000 | 2340000 | 2340000 | 2340000 | 16380000
R-2247EA | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, NC 67 to south of US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 4.53 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | NHP | CONSTRUCTION | 243400000 | FY 2030: 35192000; FY 2031: 67600000; FY 2032: 56784000; FY 2033: 43264000; FY 2034: 40560000
R-2247EB | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, interchange at US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 2.3 | Forsyth | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | Statewide Mobility |  | T | RIGHT-OF-WAY | 517000
R-2247EB | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, interchange at US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 2.3 | Forsyth | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 83655000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000
R-2247EB | Highway | STI (Prioritization) | New Route (Future NC 452 / Future I-274) | Winston-Salem Northern Beltway, western section, interchange at US 52 (Future I-285). | Construct four lane expressway on new location, including ITS deployment. | 2.3 | Forsyth | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | Statewide Mobility |  | BGDA | CONSTRUCTION | 3082000
R-2247EC | Highway | STI (Prioritization) | US 52 / Future I-74 | NC 65 interchange in Winston-Salem. | Reconstruct interchange. | 1 | Forsyth | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247CD | Statewide Mobility
R-2250 | Highway | Pre-STI (Historic) | NC 11 / NC 903 (Greenville Southwest Bypass) | NC 11 to US 264 (Greenville Bypass) in Winterville. | Construct four lane divided facility on new location with bypass of Winterville. | 11.25 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  |  |  | 241492000
R-2250 | Highway | Pre-STI (Historic) | NC 11 / NC 903 (Greenville Southwest Bypass) | NC 11 to US 264 (Greenville Bypass) in Winterville. | Construct four lane divided facility on new location with bypass of Winterville. | 11.25 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | T | CONSTRUCTION | 750000
R-2303 | Highway | STI (Prioritization) | NC 24 | West of SR 1006 (Maxwell Road / Clinton Road) in Cumberland County to I-40 in Duplin County in Warsaw. | Construct four lane divide freeway, partially on new location. | 39.7 | Sampson, Cumberland, Duplin | 3, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Eastern Carolina RPO | [5 empty] | 295231000
R-2303A | Highway | Pre-STI (Historic) | NC 24 | West of SR 1006 (Maxwell Road / Clinton Road) in Cumberland County to SR 1853 (John Nunnery Road) | Construct four lane divide freeway, partially on new location. | 6.15 | Cumberland | 6 | Mid-Carolina RPO, Fayetteville Area MPO | COMPLETE. | Pre-STI (Transition)
R-2303B | Highway | Pre-STI (Historic) | NC 24 | SR 1853 (John Nunnery Road) in Cumberland County to SR 1404 (Dowdy Road) in Sampson County | Construct four lane divide freeway, partially on new location. | 6.95 | Sampson, Cumberland | 3, 6 | Mid-Carolina RPO | COMPLETE. | Pre-STI (Transition)
R-2303C | Highway | Transition | NC 24 | SR 1404 (Sowdy Road) to SR 1303 (Mitchell Loop Road). | Construct four lane divided highway, part on new location. | 6.12 | Sampson | 3 | Mid-Carolina RPO | COMPLETE. | Pre-STI (Transition)
R-2303D | Highway | Transition | NC 24 | SR 1303 (Mitchell Loop Road) to US 421/ US 701 / SR 1296 (Sunset Avenue). | Construct four lane divided highway, part on new location. | 6.9 | Sampson | 3 | Mid-Carolina RPO | COMPLETE. | Pre-STI (Transition)
R-2303DA | Highway | Pre-STI (Historic) | NC 24 | West of SR 1262 (Airport Road) to east of US 421 | Construct four lane divided highway, part on new location. |  | Sampson | 3 | Mid-Carolina RPO | COMPLETED.
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421 / US 701 / SR 1296 (Sunset Avenue) to SR 1935 (Cecil Odie Road). | Construct four lane divide freeway, partially on new location. | 4.77 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | ENGINEERING | 5055000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 337000 | 44000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421 / US 701 / SR 1296 (Sunset Avenue) to SR 1935 (Cecil Odie Road). | Construct four lane divide freeway, partially on new location. | 4.77 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | BUILD NC ROW | 4395000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421 / US 701 / SR 1296 (Sunset Avenue) to SR 1935 (Cecil Odie Road). | Construct four lane divide freeway, partially on new location. | 4.77 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | BUILD NC CON | 31410000 | 2094000 | 2094000 | 2094000 | 2094000 | 2094000 | 2094000 | 2094000 | 2094000 | 2094000 | 1697000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421 / US 701 / SR 1296 (Sunset Avenue) to SR 1935 (Cecil Odie Road). | Construct four lane divide freeway, partially on new location. | 4.77 | Sampson | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | CONSTRUCTION | 6986000
R-2303F | Highway | STI (Prioritization) | NC 24 | SR 1935 (Cecil Odie Road) in Sampson County to I-40 in Duplin County. | Construct four lane divide freeway, partially on new location. | 9.61 | Sampson, Duplin | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | Not Funded |  | T | RIGHT-OF-WAY | 35700000 | [10 empty] | 35700000
R-2303F | Highway | STI (Prioritization) | NC 24 | SR 1935 (Cecil Odie Road) in Sampson County to I-40 in Duplin County. | Construct four lane divide freeway, partially on new location. | 9.61 | Sampson, Duplin | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | Not Funded |  | T | UTILITIES | 2300000 | [10 empty] | 2300000
R-2303F | Highway | STI (Prioritization) | NC 24 | SR 1935 (Cecil Odie Road) in Sampson County to I-40 in Duplin County. | Construct four lane divide freeway, partially on new location. | 9.61 | Sampson, Duplin | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | Not Funded |  | T | CONSTRUCTION | 338100000 | [10 empty] | 338100000
R-2307 | Highway | STI (Prioritization) | NC 150 | NC 16 interchange to US 21. | Widen to multi-lanes. | 14.8 | Catawba, Iredell, Lincoln | 12 | Greater Hickory MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717. |  |  |  |  | 21114000
R-2307A | Highway | STI (Prioritization) | NC 150 | Relocated NC 16 (STIP Project R-2206) to east of SR 1840 (Greenwood Road). | Widen to four lanes with a bypass of the Terrell Historic District. | 7.94 | Catawba, Lincoln | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 155000000
R-2307A | Highway | STI (Prioritization) | NC 150 | Relocated NC 16 (STIP Project R-2206) to east of SR 1840 (Greenwood Road). | Widen to four lanes with a bypass of the Terrell Historic District. | 7.94 | Catawba, Lincoln | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9500000
R-2307A | Highway | STI (Prioritization) | NC 150 | Relocated NC 16 (STIP Project R-2206) to east of SR 1840 (Greenwood Road). | Widen to four lanes with a bypass of the Terrell Historic District. | 7.94 | Catawba, Lincoln | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 207200000
R-2307B | Highway | STI (Prioritization) | NC 150 | SR 1840 (Greenwood Road) in Catawba County to west of SR 1303 / SR 1180 (Perth Road / Doolie Road) in Iredell County; SR 1383 / SR 1180 to US 21 in Iredell County | Widen to four lanes; Widen to six lanes. | 6.9 | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION FUNDED WITH TOLL CREDITS. BUILD NC BONDS: $50M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); $22.5M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE) | Region F |  | NHP | CONSTRUCTION | 289272000 | FY 2026: 72318000; FY 2027: 63640000; FY 2028: 52069000; FY 2029: 40498000
R-2307BA | Highway | STI (Prioritization) | NC 150 | Good Luck Lane to Morrison Plantation Parkway in Mooresville. | Extend eastbound right and through lane. | 0.28 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 1600000
R-2413 | Highway | Pre-STI (Historic) | Future I-73 | NC 68 at SR 2011 (Edgefield Road) in Guilford County to US 220 / NC 68 intersection in Rockingham County. | Construct four lane freeway, on new location, and four lanes along us 220 to NC 68 in Rockingham County. | 12.1 | Guilford, Rockingham | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO |  | Pre-STI (Transition) |  |  |  | 311602000
R-2413A | Highway | Transition | Future I 73 | SR 2011 (Edgefield Road) to SR 2127 (Brook Bank Road) | Construct roadway. | 4 | Guilford | 7 | Greensboro Urban Area MPO | COMBINED WITH I-5110 AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | CONSTRUCTION | 55000
R-2413B | Highway | Transition | Future I 73 | SR 2127 (Brook Bank Road) to Haw River | Construct roadway. | 4.4 | Guilford | 7 | Greensboro Urban Area MPO | COMBINED WITH I-5110 AND R-2413A FOR DESIGN-BUILD LET - UNDER CONSTRUCTION | Pre-STI (Transition)
R-2413C | Highway | Pre-STI (Historic) | US 220 / Future I 73 | Haw River to NC 68 / US 220 Intersection | Construct roadway. | 5.071 | Rockingham, Guilford | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-2413CA | Highway | Pre-STI (Historic) | US 220 / Future I 73 | NC 68 intersection | Convert at-grade intersection to interchange. | 1 | Rockingham | 7 | Piedmont Triad RPO | IN PROGRESS | Pre-STI (Transition)
R-2501 | Highway | STI (Prioritization) | US 1 | South Carolina state line to SR 1001 (Marston Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 24.1 | Richmond | 8 | Lumber River RPO | [5 empty] | 28064000
R-2501A | Highway | STI (Prioritization) | US 1 | South Carolina state line to SR 1104 (Osborne Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.089 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | RIGHT-OF-WAY | 4500000 | [10 empty] | 4500000
R-2501A | Highway | STI (Prioritization) | US 1 | South Carolina state line to SR 1104 (Osborne Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.089 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | CONSTRUCTION | 25700000 | [10 empty] | 25700000
R-2501BA | Highway | STI (Prioritization) | US 1 | SR 1104 (Osborne Road) to US 74 Bypass. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.282 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | RIGHT-OF-WAY | 5519000 | [10 empty] | 5519000
R-2501BA | Highway | STI (Prioritization) | US 1 | SR 1104 (Osborne Road) to US 74 Bypass. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.282 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | UTILITIES | 908000 | [10 empty] | 908000
R-2501BA | Highway | STI (Prioritization) | US 1 | SR 1104 (Osborne Road) to US 74 Bypass. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 5.282 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | CONSTRUCTION | 40501000 | [10 empty] | 40501000
R-2501BB | Highway | STI (Prioritization) | US 1 | US 74 Bypass to US 74 Business. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 4.07 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | RIGHT-OF-WAY | 13300000 | [10 empty] | 13300000
R-2501BB | Highway | STI (Prioritization) | US 1 | US 74 Bypass to US 74 Business. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 4.07 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | UTILITIES | 2523000 | [10 empty] | 2523000
R-2501BB | Highway | STI (Prioritization) | US 1 | US 74 Bypass to US 74 Business. | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 4.07 | Richmond | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | CONSTRUCTION | 67699000 | [10 empty] | 67699000
R-2501BC | Highway | STI (Prioritization) | US 1 | US 74 Business to north of SR 1606 (Fox Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 7.15 | Richmond | 8 | Lumber River RPO | COORDINATE WITH R-5928 | Not Funded |  | T | RIGHT-OF-WAY | 24248000 | [10 empty] | 24248000
R-2501BC | Highway | STI (Prioritization) | US 1 | US 74 Business to north of SR 1606 (Fox Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 7.15 | Richmond | 8 | Lumber River RPO | COORDINATE WITH R-5928 | Not Funded |  | T | UTILITIES | 6950000 | [10 empty] | 6950000
R-2501BC | Highway | STI (Prioritization) | US 1 | US 74 Business to north of SR 1606 (Fox Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 7.15 | Richmond | 8 | Lumber River RPO | COORDINATE WITH R-5928 | Not Funded |  | T | CONSTRUCTION | 101101000 | [10 empty] | 101101000
R-2501C | Highway | STI (Prioritization) | US 1 | North of SR 1606 (Fox Road) to south of SR 1001 (Marston Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 3.43 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 8 |  | T | ENGINEERING | 217000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 49000
R-2501C | Highway | STI (Prioritization) | US 1 | North of SR 1606 (Fox Road) to south of SR 1001 (Marston Road). | Widen to four lanes with variable width median with bypass of Rockingham on new location. | 3.43 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 8 |  | T | BUILD NC CON | 12975000 | 906000 | 906000 | 906000 | 906000 | 906000 | 906000 | 906000 | 901000
R-2511 | Highway | STI (Prioritization) | US 17 | Washington Bypass north of NC 171 to multi-lanes south of Williamston. | Widen to four lanes. | 10.01 | Martin, Beaufort | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  |  |  | 16222000
R-2511 | Highway | STI (Prioritization) | US 17 | Washington Bypass north of NC 171 to multi-lanes south of Williamston. | Widen to four lanes. | 10.01 | Martin, Beaufort | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  | T | RIGHT-OF-WAY | 10471000
R-2511 | Highway | STI (Prioritization) | US 17 | Washington Bypass north of NC 171 to multi-lanes south of Williamston. | Widen to four lanes. | 10.01 | Martin, Beaufort | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  | T | UTILITIES | 2200000
R-2511 | Highway | STI (Prioritization) | US 17 | Washington Bypass north of NC 171 to multi-lanes south of Williamston. | Widen to four lanes. | 10.01 | Martin, Beaufort | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  | T | CONSTRUCTION | 99343000 | FY 2026: 19901000; FY 2027: 15000000
R-2513 | Highway | STI (Prioritization) | US 17 | NC 43 to SR 1438 (Spruill Town Road). | Widen to multi-lanes. | 15.2 | Craven | 2 | Down East RPO | [5 empty] | 1914000
R-2513A | Highway | STI (Prioritization) | US 17 | North of NC 43 to SR 1438 (Spruill Town Road). | Widen to multi-lanes. | 1.86 | Craven | 2 | Down East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 4100000 | FY 2030: 984000; FY 2031: 1148000; FY 2032: 1148000; FY 2033: 410000; FY 2034: 410000
R-2513A | Highway | STI (Prioritization) | US 17 | North of NC 43 to SR 1438 (Spruill Town Road). | Widen to multi-lanes. | 1.86 | Craven | 2 | Down East RPO |  | Division 2 |  | T | UTILITIES | 2400000 | FY 2030: 1200000; FY 2031: 1200000
R-2513A | Highway | STI (Prioritization) | US 17 | North of NC 43 to SR 1438 (Spruill Town Road). | Widen to multi-lanes. | 1.86 | Craven | 2 | Down East RPO |  | Division 2 |  | T | CONSTRUCTION | 26500000 | FY 2033: 265000; FY 2034: 9010000; FY 2035: 8215000 | 9010000
R-2513B | Highway | STI (Prioritization) | US 17 | SR 1438 (Spruill Town Road) to SR 1637 (Mill Pond Road). | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5800000 | [10 empty] | 5800000
R-2513B | Highway | STI (Prioritization) | US 17 | SR 1438 (Spruill Town Road) to SR 1637 (Mill Pond Road). | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | UTILITIES | 800000 | [10 empty] | 800000
R-2513B | Highway | STI (Prioritization) | US 17 | SR 1438 (Spruill Town Road) to SR 1637 (Mill Pond Road). | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | CONSTRUCTION | 16300000 | [10 empty] | 16300000
R-2513C | Highway | STI (Prioritization) | US 17 | SR 1637 (Mill Pond Road) to SR 1646 (Mile Road). | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2300000 | [10 empty] | 2300000
R-2513C | Highway | STI (Prioritization) | US 17 | SR 1637 (Mill Pond Road) to SR 1646 (Mile Road). | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | UTILITIES | 600000 | [10 empty] | 600000
R-2513C | Highway | STI (Prioritization) | US 17 | SR 1637 (Mill Pond Road) to SR 1646 (Mile Road). | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | CONSTRUCTION | 11300000 | [10 empty] | 11300000
R-2513D | Highway | STI (Prioritization) | US 17 | SR 1646 (Mile Road) in Craven County to SR 1130 (C.C. Road) in Beaufort County. | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4600000 | [10 empty] | 4600000
R-2513D | Highway | STI (Prioritization) | US 17 | SR 1646 (Mile Road) in Craven County to SR 1130 (C.C. Road) in Beaufort County. | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | UTILITIES | 600000 | [10 empty] | 600000
R-2513D | Highway | STI (Prioritization) | US 17 | SR 1646 (Mile Road) in Craven County to SR 1130 (C.C. Road) in Beaufort County. | Widen to multi-lanes. |  | Craven | 2 | Down East RPO |  | Not Funded |  | T | CONSTRUCTION | 21000000 | [10 empty] | 21000000
R-2513E | Highway | STI (Prioritization) | US 17 | SR 1130 (C.C. Road) to south of SR 1127 (Possum Track Road). | Widen to multi-lanes. |  | Beaufort | 2 | Mid-East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4600000 | [10 empty] | 4600000
R-2513E | Highway | STI (Prioritization) | US 17 | SR 1130 (C.C. Road) to south of SR 1127 (Possum Track Road). | Widen to multi-lanes. |  | Beaufort | 2 | Mid-East RPO |  | Not Funded |  | T | UTILITIES | 600000 | [10 empty] | 600000
R-2513E | Highway | STI (Prioritization) | US 17 | SR 1130 (C.C. Road) to south of SR 1127 (Possum Track Road). | Widen to multi-lanes. |  | Beaufort | 2 | Mid-East RPO |  | Not Funded |  | T | CONSTRUCTION | 18300000 | [10 empty] | 18300000
R-2514 | Highway | Pre-STI (Historic) | US 17 | North of Jacksonville to New Bern Bypass. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 22.1 | Jones, Onslow | 2, 3 | Down East RPO, Jacksonville Urban Area MPO | [5 empty] | 233049000
R-2514A | Highway | Pre-STI (Historic) | US 17 | Multi-lane section north of Jacksonville to South of Belgrade. | Widen to multi-lanes with bypass of Belgrade, Maysville and Pollocksville on new location. | 6.17 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. | Pre-STI (Transition)
R-2514B | Highway | Transition | US 17 | South of Belgrade to north of Maysville. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 4.36 | Onslow, Jones | 2, 3 | Jacksonville Urban Area MPO, Down East RPO | COMPLETE. | Pre-STI (Transition) |  | T | CONSTRUCTION | 6000
R-2514C | Highway | Transition | US 17 | North of Maysville to south of NC 58. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 5.66 | Jones | 2 | Down East RPO | COMPLETE. | Pre-STI (Transition)
R-2514D | Highway | Transition | US 17 | South of NC 58 to the New Bern Bypass. | Widen to multi-lanes with bypasses of Belgrade, Maysville and Pollocksville on new location. | 5.8 | Jones | 2 | Down East RPO | COMPLETE. | Pre-STI (Transition)
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 to Troy Bypass. | Widen to a four lane divided facility. | 9.1 | Montgomery | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  |  |  | 200000
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 to Troy Bypass. | Widen to a four lane divided facility. | 9.1 | Montgomery | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  | T | ENGINEERING | 7802000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 522000
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 to Troy Bypass. | Widen to a four lane divided facility. | 9.1 | Montgomery | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  | T | BUILD NC ROW | 854000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 56000
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 to Troy Bypass. | Widen to a four lane divided facility. | 9.1 | Montgomery | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  | BGLT5 | CONSTRUCTION | 131500000 | FY 2027: 1315000; FY 2028: 35505000; FY 2029: 34190000; FY 2030: 31560000; FY 2031: 28930000
R-2530 | Highway | STI (Prioritization) | NC 24 / NC 27 | SR 1963 (St. Martin Road) in Albemarle to NC 73. | Widen to multi-lanes. | 8.9 | Stanly | 10 | Rocky River RPO | [5 empty] | 45876000
R-2530A | Highway | Safety | NC 24 / NC 27 | SR 1963 (St. Martin Road) to Bird Road in Albemarle. | Widen to multi-lanes. |  | Stanly | 10 | Rocky River RPO | COMPLETE
R-2530B | Highway | STI (Prioritization) | NC 24 / NC 27 | Bird Road in Albemarle to west of the Pee Dee River | Widen to multi-lanes. | 6.1 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | ENGINEERING | 8040000 | 536000 | 536000 | 536000 | 536000 | 536000 | 536000 | 536000 | 536000 | 536000 | 28000
R-2530B | Highway | STI (Prioritization) | NC 24 / NC 27 | Bird Road in Albemarle to west of the Pee Dee River | Widen to multi-lanes. | 6.1 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC ROW | 5700000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000
R-2530B | Highway | STI (Prioritization) | NC 24 / NC 27 | Bird Road in Albemarle to west of the Pee Dee River | Widen to multi-lanes. | 6.1 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC UTL | 3600000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
R-2530B | Highway | STI (Prioritization) | NC 24 / NC 27 | Bird Road in Albemarle to west of the Pee Dee River | Widen to multi-lanes. | 6.1 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 62655000 | 4177000 | 4177000 | 4177000 | 4177000 | 4177000 | 4177000 | 4177000 | 4177000 | 4177000 | 3176000
R-2530B | Highway | STI (Prioritization) | NC 24 / NC 27 | Bird Road in Albemarle to west of the Pee Dee River | Widen to multi-lanes. | 6.1 | Stanly | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | CONSTRUCTION | 34306000
R-2536 | Highway | Pre-STI (Historic) | US 64 | Asheboro Southern Bypass, US 64 West to US 64 East. | Construct four lane freeway on new location with interchanges at US 220, NC 49 and zoo access at NC 159. | 12.76 | Randolph | 8 | Piedmont Triad RPO | COMPLETE. | Pre-STI (Transition) |  |  |  | 373758000
R-2553 | Highway | STI (Prioritization) | US 70 (Future I-42) | Existing freeway near Lagrange to existing freeway near Dover. | Upgrade roadway to freeway, partially on new location. | 18.7 | Lenoir | 2 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. |  |  |  |  | 7924000
R-2555 | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | NC 73 (Sam Furr Road) to east of SR 2195 (Torrence Chapel Road) in Cornelius. | Widen to four lanes divided. | 3.4 | Mecklenburg | 10 | Charlotte Regional TPO | [5 empty] | 44964000
R-2555A | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | SR 2151 (Jetton Road) to SR 2195 (Torrence Chapel Road). | Widen to four lanes divided. | 0.9 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE
R-2555B | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | NC 73 (Sam Furr Road) to east of SR 2151 (Jetton Road) in Cornelius. | Widen to four lanes divided. | 2.35 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028 / YR 8 SALE). | Division 10 |  | T | RIGHT-OF-WAY | 5000000 | FY 2026: 5000000
R-2555B | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | NC 73 (Sam Furr Road) to east of SR 2151 (Jetton Road) in Cornelius. | Widen to four lanes divided. | 2.35 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028 / YR 8 SALE). | Division 10 |  | T | UTILITIES | 4000000 | FY 2026: 10000; FY 2027: 590000; FY 2028: 3400000
R-2555B | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | NC 73 (Sam Furr Road) to east of SR 2151 (Jetton Road) in Cornelius. | Widen to four lanes divided. | 2.35 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028 / YR 8 SALE). | Division 10 |  | T | BUILD NC CON | 13005000 |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
R-2555B | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | NC 73 (Sam Furr Road) to east of SR 2151 (Jetton Road) in Cornelius. | Widen to four lanes divided. | 2.35 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028 / YR 8 SALE). | Division 10 |  | T | CONSTRUCTION | 23400000 | FY 2028: 0; FY 2029: 5364000; FY 2030: 8350000; FY 2031: 5344000; FY 2032: 4342000
R-2555B | Highway | STI (Prioritization) | SR 5544 (West Catawba Avenue) | NC 73 (Sam Furr Road) to east of SR 2151 (Jetton Road) in Cornelius. | Widen to four lanes divided. | 2.35 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028 / YR 8 SALE). | Division 10 |  | L | CONSTRUCTION | 1200000 | FY 2028: 168000; FY 2029: 384000; FY 2030: 300000; FY 2031: 348000
R-2561 | Highway | STI (Prioritization) | NC 87 | Elizabethtown Bypass in Bladen County to US 74 / US 76 in Columbus County. | Widen to multi-lanes. | 30.2 | Bladen, Columbus | 6 | Cape Fear RPO, Mid-Carolina RPO | [5 empty] | 10957000
R-2561A | Highway | STI (Prioritization) | NC 87 | Elizabethtown Bypass to SR 1730 (Elwell Ferry Road) in Bladen County. | Widen to multi-lanes. |  | Bladen, Columbus | 6 | Mid-Carolina RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 23000000 | [10 empty] | 23000000
R-2561A | Highway | STI (Prioritization) | NC 87 | Elizabethtown Bypass to SR 1730 (Elwell Ferry Road) in Bladen County. | Widen to multi-lanes. |  | Bladen, Columbus | 6 | Mid-Carolina RPO |  | Not Funded |  | T | UTILITIES | 8300000 | [10 empty] | 8300000
R-2561A | Highway | STI (Prioritization) | NC 87 | Elizabethtown Bypass to SR 1730 (Elwell Ferry Road) in Bladen County. | Widen to multi-lanes. |  | Bladen, Columbus | 6 | Mid-Carolina RPO |  | Not Funded |  | T | CONSTRUCTION | 157400000 | [10 empty] | 157400000
R-2561B | Highway | STI (Prioritization) | NC 87 | SR 1730 (Elwell Ferry Road) in Bladen County to NC 11 in Columbus County. | Widen to multi-lanes. |  | Bladen | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 18800000 | [10 empty] | 18800000
R-2561B | Highway | STI (Prioritization) | NC 87 | SR 1730 (Elwell Ferry Road) in Bladen County to NC 11 in Columbus County. | Widen to multi-lanes. |  | Bladen | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Not Funded |  | T | UTILITIES | 6900000 | [10 empty] | 6900000
R-2561B | Highway | STI (Prioritization) | NC 87 | SR 1730 (Elwell Ferry Road) in Bladen County to NC 11 in Columbus County. | Widen to multi-lanes. |  | Bladen | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Not Funded |  | T | CONSTRUCTION | 100800000 | [10 empty] | 100800000
R-2561C | Highway | STI (Prioritization) | NC 87 | NC 11 to US 74 / US 76 in Columbus County. | Widen to multi-lanes. | 5.99 | Columbus | 6 | Cape Fear RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 26511000 | [10 empty] | 26511000
R-2561C | Highway | STI (Prioritization) | NC 87 | NC 11 to US 74 / US 76 in Columbus County. | Widen to multi-lanes. | 5.99 | Columbus | 6 | Cape Fear RPO |  | Not Funded |  | T | UTILITIES | 4488000 | [10 empty] | 4488000
R-2561C | Highway | STI (Prioritization) | NC 87 | NC 11 to US 74 / US 76 in Columbus County. | Widen to multi-lanes. | 5.99 | Columbus | 6 | Cape Fear RPO |  | Not Funded |  | T | CONSTRUCTION | 85799000 | [10 empty] | 85799000
R-2561CA | Highway | STI (Prioritization) | NC 87 | NC 11 intersection in Sandyfield | Construct interchange. | 1 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 3904000
R-2561CA | Highway | STI (Prioritization) | NC 87 | NC 11 intersection in Sandyfield | Construct interchange. | 1 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 3000000
R-2561CA | Highway | STI (Prioritization) | NC 87 | NC 11 intersection in Sandyfield | Construct interchange. | 1 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | BGLT5 | CONSTRUCTION | 41376000 | FY 2026: 3945000
R-2561CB | Highway | STI (Prioritization) | NC 87 | Columbus County. | Construct detour route ahead of R-2561CA. |  | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 1756000
R-2566 | Highway | STI (Prioritization) | NC 105 | US 221 to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 14.8 | Watauga, Avery | 11 | High Country RPO | [5 empty] | 11735000
R-2566A | Highway | STI (Prioritization) | NC 105 | US 221 in Avery County to SR 1136 (Clarks Creek Road) in Watauga County. | Widen to multi-lanes. |  | Avery, Watauga | 11 | High Country RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 1000000 | [10 empty] | 1000000
R-2566A | Highway | STI (Prioritization) | NC 105 | US 221 in Avery County to SR 1136 (Clarks Creek Road) in Watauga County. | Widen to multi-lanes. |  | Avery, Watauga | 11 | High Country RPO |  | Not Funded |  | T | CONSTRUCTION | 60351000 | [10 empty] | 42457000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (Clarks Creek Road) to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 5.49 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | T | BUILD NC ROW | 240000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (Clarks Creek Road) to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 5.49 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | T | RIGHT-OF-WAY | 13030000 | FY 2026: 3000000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (Clarks Creek Road) to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 5.49 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | T | UTILITIES | 13700000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (Clarks Creek Road) to SR 1107 (NC 105 Bypass) in Boone. | Widen to multi-lanes. | 5.49 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | NHP | CONSTRUCTION | 117200000 | FY 2031: 21096000; FY 2032: 28128000; FY 2033: 25784000; FY 2034: 23440000; FY 2035: 18752000
R-2566BA | Highway | STI (Prioritization) | NC 105 | Watauga River; SR 1112 (Broadstone Road) intersection near Boone. | Construct new bridge over Watauga River; Construct left turn lane at SR 1112 (Broadstone Road). |  | Watauga | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 11 |  | T | UTILITIES | 2850000
R-2566BA | Highway | STI (Prioritization) | NC 105 | Watauga River; SR 1112 (Broadstone Road) intersection near Boone. | Construct new bridge over Watauga River; Construct left turn lane at SR 1112 (Broadstone Road). |  | Watauga | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 11 |  | T | BUILD NC CON | 7980000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000
R-2566BA | Highway | STI (Prioritization) | NC 105 | Watauga River; SR 1112 (Broadstone Road) intersection near Boone. | Construct new bridge over Watauga River; Construct left turn lane at SR 1112 (Broadstone Road). |  | Watauga | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 11 |  | T | CONSTRUCTION | 27350000 | FY 2026: 5000000
R-2566BB | Highway | STI (Prioritization) | NC 105 | SR 1658 (Old Shulls Mill Road) intersection near Boone. | Realign roadway. | 0.5 | Watauga | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 2000000 | FY 2026: 1374000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  |  |  | 44244000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | BOND R | RIGHT-OF-WAY | 42500000 | FY 2027: 4675000; FY 2028: 6375000; FY 2029: 8500000; FY 2030: 11050000; FY 2031: 11900000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | BOND R | UTILITIES | 13000000 | FY 2027: 6500000; FY 2028: 6500000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | BGANY | GARVEE CON | 135210000 |  | 9014000 | 9014000 | 9014000 | 9014000 | 9014000 | 9014000 | 9014000 | 9014000 | 9014000 | 54084000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | T(M) | GARVEE CON | 33795000 |  | 2253000 | 2253000 | 2253000 | 2253000 | 2253000 | 2253000 | 2253000 | 2253000 | 2253000 | 13518000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | O | CONSTRUCTION | 687068000 | FY 2027: 75577000; FY 2028: 103060000; FY 2029: 137414000; FY 2030: 178638000; FY 2031: 192379000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | T(M) | CONSTRUCTION | 43327000 | FY 2027: 4766000; FY 2028: 6499000; FY 2029: 8665000; FY 2030: 11265000; FY 2031: 12132000
R-2576 | Highway | STI (Prioritization) | New Route | Mid-Currituck Bridge from Coinjock to Corolla. | Construct new structure over Currituck Sound and upgrade approaches. This is a toll project. | 6.93 | Currituck | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2027-2041. | Division 1 |  | BOND R | CONSTRUCTION | 201805000 | FY 2027: 22199000; FY 2028: 30271000; FY 2029: 40361000; FY 2030: 52469000; FY 2031: 56505000
R-2577 | Highway | STI (Prioritization) | US 158 | Multi-lanes north of US 421 / I-40 Business in Winston-Salem to US 220 in Stokesdale. | Widen to a four lane divided facility. | 18.8 | Forsyth, Guilford | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | [5 empty] | 5058000
R-2577A | Highway | STI (Prioritization) | US 158 | Multi-lanes north of US 421 / I-40 Business to SR 1965 (Belews Creek Road). | Widen to a four lane divided facility. | 5.21 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | RIGHT-OF-WAY | 36300000
R-2577A | Highway | STI (Prioritization) | US 158 | Multi-lanes north of US 421 / I-40 Business to SR 1965 (Belews Creek Road). | Widen to a four lane divided facility. | 5.21 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | UTILITIES | 469000
R-2577A | Highway | STI (Prioritization) | US 158 | Multi-lanes north of US 421 / I-40 Business to SR 1965 (Belews Creek Road). | Widen to a four lane divided facility. | 5.21 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | BUILD NC CON | 59850000 | 3990000 | 3990000 | 3990000 | 3990000 | 3990000 | 3990000 | 3990000 | 3990000 | 3990000 | 3990000 | 15960000
R-2577A | Highway | STI (Prioritization) | US 158 | Multi-lanes north of US 421 / I-40 Business to SR 1965 (Belews Creek Road). | Widen to a four lane divided facility. | 5.21 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | CONSTRUCTION | 56900000 | FY 2026: 636000; FY 2027: 21853000; FY 2028: 23715000; FY 2029: 10000000
R-2577B | Highway | STI (Prioritization) | US 158 | SR 1965 (Belews Creek Road) in Forsyth County to SR 2034 (Anthony Road) in Guilford County. | Widen to multi-lanes. | 7.53 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 38800000 | [10 empty] | 38800000
R-2577B | Highway | STI (Prioritization) | US 158 | SR 1965 (Belews Creek Road) in Forsyth County to SR 2034 (Anthony Road) in Guilford County. | Widen to multi-lanes. | 7.53 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | UTILITIES | 9700000 | [10 empty] | 9700000
R-2577B | Highway | STI (Prioritization) | US 158 | SR 1965 (Belews Creek Road) in Forsyth County to SR 2034 (Anthony Road) in Guilford County. | Widen to multi-lanes. | 7.53 | Forsyth | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | CONSTRUCTION | 60300000 | [10 empty] | 60300000
R-2577C | Highway | STI (Prioritization) | US 158 | North of SR 2034 (Anthony Road) to US 220. | Widen to multi-lanes. | 5.89 | Guilford, Forsyth | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 74608000 | [10 empty] | 74608000
R-2577C | Highway | STI (Prioritization) | US 158 | North of SR 2034 (Anthony Road) to US 220. | Widen to multi-lanes. | 5.89 | Guilford, Forsyth | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T | UTILITIES | 625000 | [10 empty] | 625000
R-2577C | Highway | STI (Prioritization) | US 158 | North of SR 2034 (Anthony Road) to US 220. | Widen to multi-lanes. | 5.89 | Guilford, Forsyth | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T | CONSTRUCTION | 48400000 | [10 empty] | 48400000
R-2582 | Highway | STI (Prioritization) | US 158 / NC 46 | I-95 / NC 46 in Roanoke Rapids to SR 1333 (Mount Carmel Church Road) east of Jackson. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 15.2 | Northampton | 1 | Peanut Belt RPO | [5 empty] | 17713000
R-2582A | Highway | STI (Prioritization) | US 158 / NC 46 | I-95 / NC 46 in Roanoke Rapids to SR 1312 (St. John Church Road) in Northampton County. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.94 | Northampton | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | ENGINEERING | 8820000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 246000
R-2582A | Highway | STI (Prioritization) | US 158 / NC 46 | I-95 / NC 46 in Roanoke Rapids to SR 1312 (St. John Church Road) in Northampton County. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.94 | Northampton | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | BUILD NC ROW | 3345000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000
R-2582A | Highway | STI (Prioritization) | US 158 / NC 46 | I-95 / NC 46 in Roanoke Rapids to SR 1312 (St. John Church Road) in Northampton County. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.94 | Northampton | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | BUILD NC CON | 56595000 | 3773000 | 3773000 | 3773000 | 3773000 | 3773000 | 3773000 | 3773000 | 3773000 | 3773000 | 2751000
R-2582A | Highway | STI (Prioritization) | US 158 / NC 46 | I-95 / NC 46 in Roanoke Rapids to SR 1312 (St. John Church Road) in Northampton County. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.94 | Northampton | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | CONSTRUCTION | 50214000 | FY 2026: 3000000
R-2582B | Highway | STI (Prioritization) | US 158 / NC 46 | SR 1312 (St. John Church Road) to SR 1333 (Mount Carmel Church Road) east of Jackson. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.4 | Northampton | 1 | Peanut Belt RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5400000 | [10 empty] | 5400000
R-2582B | Highway | STI (Prioritization) | US 158 / NC 46 | SR 1312 (St. John Church Road) to SR 1333 (Mount Carmel Church Road) east of Jackson. | Widen to multi-lanes with bypass of Jackson, partially on new location. | 7.4 | Northampton | 1 | Peanut Belt RPO |  | Not Funded |  | T | CONSTRUCTION | 61400000 | [10 empty] | 61400000
R-2588 | Highway | STI (Prioritization) | NC 191 | US 25 in Hendersonville to NC 280 south of Mills River. | Widen to multi-lanes. | 7.2 | Henderson | 14 | French Broad River MPO | [5 empty] | 1326000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Henderson | 14 | French Broad River MPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 12160000 | [10 empty] | 12160000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Henderson | 14 | French Broad River MPO |  | Not Funded |  | T(M) | RIGHT-OF-WAY | 3040000 | [10 empty] | 3040000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Henderson | 14 | French Broad River MPO |  | Not Funded |  | BGANY | UTILITIES | 1440000 | [10 empty] | 1440000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Henderson | 14 | French Broad River MPO |  | Not Funded |  | T(M) | UTILITIES | 360000 | [10 empty] | 360000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Henderson | 14 | French Broad River MPO |  | Not Funded |  | BGANY | CONSTRUCTION | 15039000 | [10 empty] | 15039000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 to SR 1381 (Mountain Road) in Hendersonville. | Widen to multi-lanes. |  | Henderson | 14 | French Broad River MPO |  | Not Funded |  | T(M) | CONSTRUCTION | 3761000 | [10 empty] | 3761000
R-2588B | Highway | STI (Prioritization) | NC 191 | SR 1381 (Mountain Road) to NC 280 south of Mills River. | Widen to multi-lanes. | 4.41 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). | Division 14 |  | T | RIGHT-OF-WAY | 9500000
R-2588B | Highway | STI (Prioritization) | NC 191 | SR 1381 (Mountain Road) to NC 280 south of Mills River. | Widen to multi-lanes. | 4.41 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). | Division 14 |  | NHP | UTILITIES | 15500000
R-2588B | Highway | STI (Prioritization) | NC 191 | SR 1381 (Mountain Road) to NC 280 south of Mills River. | Widen to multi-lanes. | 4.41 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). | Division 14 |  | T | CONSTRUCTION | 148300000 | FY 2029: 29660000; FY 2030: 34109000; FY 2031: 32626000; FY 2032: 28177000; FY 2033: 23728000
R-2588BA | Highway | STI (Prioritization) | NC 191 | SR 1381 (Mountain Road) to NC 280. | Clear for utilities. |  | Henderson | 14 | French Broad River MPO |  | Division 14 |  | T | CONSTRUCTION | 220000 | FY 2026: 60000
R-2603 | Highway | Transition | NC 268 | NC 18 to SR 1966 (Airport Road). | Construct sidewalk from NC 18 to Shaver Street. Widen to five lanes from Shaver Street to SR 1971 (Fairplains Road). Widen to four lanes divided from Fairplains Road to SR 1966 (Airport Road). | 3.27 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 35831000
R-2612 | Highway | Pre-STI (Historic) | US 421 (Future I-685) | SR 3389 (Woody Mill Road) and SR 3418 (Neelley Road) south of Greensboro. | Upgrade at-grade intersections to interchanges. | 2 | Guilford | 7 | Greensboro Urban Area MPO |  | Exempt |  |  |  | 41680000
R-2612A | Highway | Pre-STI (Historic) | US 421 | SR 3389 (Woody Mill Road) intersection south of Greensboro. | Upgrade at-grade intersections to interchanges. | 0.702 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
R-2612B | Highway | Transition | US 421 (Future I-685) | SR 3418 (Neelley Road) intersection south of Greensboro | Convert at-grade intersections to interchanges. | 0.901 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-2615 | Highway | STI (Prioritization) | US 421 / US 321 | US 421 / US 321 Junction near Vilas to SR 1107 (NC 105 Bypass). | Widen to multi-lanes. | 3.55 | Watauga | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 750000
R-2615 | Highway | STI (Prioritization) | US 421 / US 321 | US 421 / US 321 Junction near Vilas to SR 1107 (NC 105 Bypass). | Widen to multi-lanes. | 3.55 | Watauga | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 55000000
R-2615 | Highway | STI (Prioritization) | US 421 / US 321 | US 421 / US 321 Junction near Vilas to SR 1107 (NC 105 Bypass). | Widen to multi-lanes. | 3.55 | Watauga | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2900000
R-2615 | Highway | STI (Prioritization) | US 421 / US 321 | US 421 / US 321 Junction near Vilas to SR 1107 (NC 105 Bypass). | Widen to multi-lanes. | 3.55 | Watauga | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 78300000
R-2632 | Highway | STI (Prioritization) | NC 73 | US 21 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 4.3 | Mecklenburg | 10 | Charlotte Regional TPO | COORDINATE WITH R-5706A & B. $7.273M IN NHP FUNDS SWITCHED WITH $7.237M IN BGDA AS PART OF FUND SWAP 8-9-22. |  |  |  |  | 30912000
R-2632AA | Highway | STI (Prioritization) | NC 73 | US 21 to NC 115. | Widen to multi-lanes. |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 2.67 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | NHP | RIGHT-OF-WAY | 8300000 | FY 2026: 2030000; FY 2027: 1660000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 2.67 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | NHP | UTILITIES | 5100000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 2.67 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | NHP | CONSTRUCTION | 60862000 | FY 2028: 14607000; FY 2029: 17041000; FY 2030: 13390000; FY 2031: 9129000; FY 2032: 6695000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 2.67 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | BGDA | CONSTRUCTION | 5790000 | FY 2028: 58000; FY 2029: 2432000; FY 2030: 1795000; FY 2031: 1042000; FY 2032: 463000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 to SR 2693 (Davidson-Concord Road) in Huntersville. | Widen to four lanes. | 2.67 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T(M) | CONSTRUCTION | 1448000 | FY 2028: 348000; FY 2029: 405000; FY 2030: 319000; FY 2031: 217000; FY 2032: 159000
R-2632AC | Highway | Pre-STI (Historic) |  |  |  |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE | Pre-STI (Transition)
R-2633 | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | US 17 south of NC 87 in Brunswick County to I-40 in New Hanover County. | Construct four lane divided freeway on new location. | 20.2 | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO | [5 empty] | 684220000
R-2633AA | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | NC 87 south of Bishop to US 74 / US 76 east of Malmo in Brunswick County. | Construct four lane divided freeway on new location. | 5.3 | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE. GARVEE BOND FUNDING: $31.05M FOR CONSTRUCTION, PAYBACK 2010 - 2021. | Pre-STI (Transition) |  | NHP | GARVEE CON | 6810000
R-2633AB | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | NC 87 south of Bishop to US 74 / US 76 east of Malmo in Brunswick County. | Construct four lane divided freeway on new location. |  | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE.
R-2633BA | Highway | Transition | I-40 / US 17 (Wilmington Bypass) | US 74 / US 76 in Brunswick County to SR 1430 (Cedar Hill Road). | Construct new route. | 7.6 | Brunswick | 3 | Wilmington Urban Area MPO | COMPLETE. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK 2014 - 2025. | Pre-STI (Transition) |  | NHP | GARVEE CON | 30750000
R-2633BB | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | SR 1430 (Cedar Hill Road) to West of US 421 north of Wilmington. | Construct four-lane divided freeway on new location. |  | New Hanover, Brunswick | 3 | Wilmington Urban Area MPO | COMPLETE. GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK 2013 - 2024. | Pre-STI (Transition) |  | NHP | GARVEE CON | 51250000
R-2633BC | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | US 74 / US 76 east of Malmo in Brunswick County to west of US 421 north of Wilmington. | Construct four-lane divided freeway on new location. |  | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE.
R-2633CA | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | West of US 421 north of Wilmington to west of NC 133. | Construct four-lane divided freeway on new location. | 3.6 | New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE.
R-2633CB | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | West of NC 133 to US 117. | Construct four-lane divided freeway on new location. | 3.544 | New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE.
R-2633CC | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | US 117 to east of I-40 south of Castle Hayne. | Construct four-lane divided freeway on new location. | 0.85 | New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE.
R-2633D | Highway | Pre-STI (Historic) | I-140/US 17 (Wilmington Bypass). | US 17 south of NC 87 in Brunswick County to I-40 in New Hanover County. | Implementation of Intelligent Transportation Systems (ITS). | 20.13 | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE. | Pre-STI (Transition)
R-2707 | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | West of SR 1162 (Peachtree Road) to west of SR 1001 (Stoney Point Road). | Construct four lane divided freeway on new location. | 18.6 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | [5 empty] | 252509000
R-2707A | Highway | Pre-STI (Historic) | US 74 (Shelby Bypass) | West of SR 1162 (Peachtree Road) to east of SR 1315 (Plato Road). | Acquire right-of-way. | 3.9 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
R-2707AA | Highway | Pre-STI (Historic) | US 74 (Shelby Bypass) | West of SR 1162 (Peachtree Road) to east of SR 1318 (Kimbrell Road). | Construct four lane divided freeway on new location. | 1.88 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
R-2707AB | Highway | Transition | US 74 (Shelby Bypass) | East of SR 1318 (Kimbrell Road) to east of SR 1315 (Plato Lee Road). | Construct four lane divided freeway on new location. | 2.68 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE | Pre-STI (Transition)
R-2707B | Highway | Transition | US 74 (Shelby Bypass) | East of SR 1315 (Plato Lee Road) to east of NC 226. | Construct four lane divided freeway on new location. | 2.58 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE | Pre-STI (Transition)
R-2707C | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | East of NC 226 to east of NC 150. | Construct four lane divided freeway on new location. | 5.42 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Region F |  | T | ENGINEERING | 75000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
R-2707C | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | East of NC 226 to east of NC 150. | Construct four lane divided freeway on new location. | 5.42 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Region F |  | T | BUILD NC CON | 40335000 | 2689000 | 2689000 | 2689000 | 2689000 | 2689000 | 2689000 | 2689000 | 2689000 | 2689000 | 1716000
R-2707D | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | East of NC 150 to existing US 74 west of SR 2238 (Long Branch Road). | Construct four lane divided freeway on new location. | 4.26 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000
R-2707D | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | East of NC 150 to existing US 74 west of SR 2238 (Long Branch Road). | Construct four lane divided freeway on new location. | 4.26 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | RIGHT-OF-WAY | 19394000
R-2707D | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | East of NC 150 to existing US 74 west of SR 2238 (Long Branch Road). | Construct four lane divided freeway on new location. | 4.26 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | BUILD NC CON | 53205000 | 3547000 | 3547000 | 3547000 | 7094000 | 3547000 | 3547000 | 3547000 | 3547000 | 3547000 | 3547000 | 10641000
R-2707D | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | East of NC 150 to existing US 74 west of SR 2238 (Long Branch Road). | Construct four lane divided freeway on new location. | 4.26 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | CONSTRUCTION | 154192000 | FY 2026: 20728000; FY 2027: 37950000; FY 2028: 36781000; FY 2029: 20000000
R-2707E | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | US 74 west of SR 2238 (Long Branch Road) to west of SR 1001 (Stoney Point Road). | Construct four lane divided freeway on new location. | 3.03 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D. | Region F |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000
R-2707E | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | US 74 west of SR 2238 (Long Branch Road) to west of SR 1001 (Stoney Point Road). | Construct four lane divided freeway on new location. | 3.03 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D. | Region F |  | T | RIGHT-OF-WAY | 34242000
R-2707E | Highway | STI (Prioritization) | US 74 (Shelby Bypass) | US 74 west of SR 2238 (Long Branch Road) to west of SR 1001 (Stoney Point Road). | Construct four lane divided freeway on new location. | 3.03 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D. | Region F |  | T | UTILITIES | 5300000
R-2707F | Highway | Pre-STI (Historic) | US 74 (Shelby Bypass) | East of SR 1318 (Kimbrell Road) to east of NC 226 | Construct four lane divided freeway on new location. | 5.27 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE | Pre-STI (Transition)
R-2721 | Highway | STI (Prioritization) | New Route (Future NC 540) | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), NC 55 (South) to east of US 401 south. This is a toll project. | Freeway on new location. | 7.8 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT | Statewide Mobility |  |  |  | 387067000
R-2721A | Highway | STI (Prioritization) | NC 540 | NC 55 Bypass to east of SR 1152 (Holly Springs Road). | Construct freeway on new location. This is a toll project. | 2.84 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHP | CONSTRUCTION | 63600000
R-2721A | Highway | STI (Prioritization) | NC 540 | NC 55 Bypass to east of SR 1152 (Holly Springs Road). | Construct freeway on new location. This is a toll project. | 2.84 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 15900000
R-2721B | Highway | STI (Prioritization) | NC 540 | East of SR 1152 (Holly Springs Road) to east of US 401. | Construct freeway on new location. This is a toll project. | 5.37 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHP | CONSTRUCTION | 50400000
R-2721B | Highway | STI (Prioritization) | NC 540 | East of SR 1152 (Holly Springs Road) to east of US 401. | Construct freeway on new location. This is a toll project. | 5.37 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T(M) | CONSTRUCTION | 12600000
R-2814 | Highway | STI (Prioritization) | US 401 | North of SR 2044 (Ligon Mill Road) to NC 39 in Louisburg. | Widen to four-lane median divided facility, some new location. | 18.5 | Franklin, Wake | 5 | Capital Area MPO, Kerr-Tar RPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 132392000
R-2814A | Highway | Pre-STI (Historic) | US 401 | SR 2044 (Ligon Mill Road) to north of SR 2225 (Louisbury Road) | Widen to four-lane median divided facility. | 2.237 | Wake | 5 | Capital Area MPO | COMPLETE
R-2814B | Highway | Pre-STI (Historic) | US 401 | Rolesville Bypass, north of SR 2225 (Louisbury Road) to NC 96 | Widen to four-lane median divided facility. | 6.401 | Wake | 5 | Capital Area MPO | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022 | Pre-STI (Transition) |  | BGANY | GARVEE ROW | 1727000
R-2814B | Highway | Pre-STI (Historic) | US 401 | Rolesville Bypass, north of SR 2225 (Louisbury Road) to NC 96 | Widen to four-lane median divided facility. | 6.401 | Wake | 5 | Capital Area MPO | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022 | Pre-STI (Transition) |  | BGANY | GARVEE CON | 7083000
R-2814C | Highway | STI (Prioritization) | US 401 | NC 96 to SR 1103 (Flat Rock Church Road / Clifton Pond Road). | Widen to four-lane median divided facility. | 5.98 | Franklin, Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032 | Division 5 |  | BGLT5 | GARVEE CON | 36803000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 6080000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | RIGHT-OF-WAY | 1520000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 4800000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | UTILITIES | 1200000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 65840000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (Flat Rock Church Road / Clifton Pond Road) to SR 1700 (Fox Park Road) south of Louisburg. | Widen to four-lane median divided facility. | 5.31 | Franklin | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T(M) | CONSTRUCTION | 16460000
R-2814E | Highway | Pre-STI (Historic) | US 401 | SR 1700 (Fox Park Road) south of Louisburg to NC 39 in Louisburg | Widen to four-lane median divided facility. | 1.022 | Franklin | 5 | Kerr-Tar RPO | COMPLETE
R-2822 | Highway | STI (Prioritization) | NC 143 | West Buffalo Creek to NC 143 Business. | Upgrade corridor. |  | Graham | 14 | Southwestern RPO | [5 empty] | 2889000
R-2822A | Highway | Pre-STI (Historic) |  |  |  |  | Graham | 14 | Southwestern RPO | COMPLETE
R-2822B | Highway | STI (Prioritization) | NC 143 | West Buffalo Creek to NC 143 Business. | Upgrade corridor. | 4.94 | Graham | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | RIGHT-OF-WAY | 1100000 | FY 2026: 246000; FY 2027: 220000
R-2822B | Highway | STI (Prioritization) | NC 143 | West Buffalo Creek to NC 143 Business. | Upgrade corridor. | 4.94 | Graham | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | UTILITIES | 1900000
R-2822BA | Highway | STI (Prioritization) | NC 143 | West Buffalo Creek to NC 143 Business. | Upgrade corridor. | 4.94 | Graham | 14 | Southwestern RPO |  | Region G |  | T | CONSTRUCTION | 40000000 | FY 2030: 400000; FY 2031: 13200000; FY 2032: 12000000; FY 2033: 8800000; FY 2034: 5600000
R-2822BB | Highway | STI (Prioritization) | NC 143 | Bridge 370013 over Santeetlah Lake. | Replace bridge. |  | Graham | 14 | Southwestern RPO |  | Region G |  | T | CONSTRUCTION | 33500000 | FY 2027: 335000; FY 2028: 11055000; FY 2029: 10050000; FY 2030: 7370000; FY 2031: 4690000
R-2828 | Highway | STI (Prioritization) | New Route (Future NC 540) | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), east of US 401 to I-40. This is a toll project. | Construct freeway on new location. | 8.64 | Wake, Johnston | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | Statewide Mobility |  |  |  | 353157000
R-2828 | Highway | STI (Prioritization) | New Route (Future NC 540) | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), east of US 401 to I-40. This is a toll project. | Construct freeway on new location. | 8.64 | Wake, Johnston | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | Statewide Mobility |  | T(M) |  | 88289000
R-2828 | Highway | STI (Prioritization) | New Route (Future NC 540) | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), east of US 401 to I-40. This is a toll project. | Construct freeway on new location. | 8.64 | Wake, Johnston | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | Statewide Mobility |  | NHP | CONSTRUCTION | 108600000
R-2828 | Highway | STI (Prioritization) | New Route (Future NC 540) | Southern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), east of US 401 to I-40. This is a toll project. | Construct freeway on new location. | 8.64 | Wake, Johnston | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 27150000
R-2829 | Highway | STI (Prioritization) | New Route (Future NC 540) | Eastern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), I-40 to I-87 / US 64 / US 264 Bypass. | Construct freeway on new location. This is a toll project. | 10.8 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  |  |  | 12945000
R-2829 | Highway | STI (Prioritization) | New Route (Future NC 540) | Eastern Wake Freeway / Triangle Expressway Southeast Extension (Raleigh Outer Loop), I-40 to I-87 / US 64 / US 264 Bypass. | Construct freeway on new location. This is a toll project. | 10.8 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 1133000
R-2829A | Highway | STI (Prioritization) | New Route (Future NC 540) | I 40 to south of SR 2542 (Rock Quarry Road) | Construct freeway on new location. This is a toll project. | 6.42 | Wake | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $125 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 41809000 | FY 2026: 20905000; FY 2027: 10452000
R-2829A | Highway | STI (Prioritization) | New Route (Future NC 540) | I 40 to south of SR 2542 (Rock Quarry Road) | Construct freeway on new location. This is a toll project. | 6.42 | Wake | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $125 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | UTILITIES | 3544000 | FY 2026: 1772000
R-2829A | Highway | STI (Prioritization) | New Route (Future NC 540) | I 40 to south of SR 2542 (Rock Quarry Road) | Construct freeway on new location. This is a toll project. | 6.42 | Wake | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $125 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | NHP | GARVEE CON | 168495000 | 11233000 | 11233000 | 11233000 | 11233000 | 11233000 | 11233000 | 11233000 | 11233000 | 11233000 | 11233000 | 44932000
R-2829A | Highway | STI (Prioritization) | New Route (Future NC 540) | I 40 to south of SR 2542 (Rock Quarry Road) | Construct freeway on new location. This is a toll project. | 6.42 | Wake | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $125 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | T(M) | CONSTRUCTION | 41668000 | FY 2026: 10417000; FY 2027: 10417000; FY 2028: 10417000
R-2829A | Highway | STI (Prioritization) | New Route (Future NC 540) | I 40 to south of SR 2542 (Rock Quarry Road) | Construct freeway on new location. This is a toll project. | 6.42 | Wake | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $125 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | CONSTRUCTION | 140400000
R-2829B | Highway | STI (Prioritization) | New Route (Future NC 540) | South of SR 2542 (Rock Quarry Road) to I-87 / US 64 / US 264 Bypass | Construct freeway on new location. This is a toll project. | 3.82 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $175 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 33806000 | FY 2026: 16890000; FY 2027: 8471000
R-2829B | Highway | STI (Prioritization) | New Route (Future NC 540) | South of SR 2542 (Rock Quarry Road) to I-87 / US 64 / US 264 Bypass | Construct freeway on new location. This is a toll project. | 3.82 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $175 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | UTILITIES | 500000 | FY 2026: 250000
R-2829B | Highway | STI (Prioritization) | New Route (Future NC 540) | South of SR 2542 (Rock Quarry Road) to I-87 / US 64 / US 264 Bypass | Construct freeway on new location. This is a toll project. | 3.82 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $175 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | NHP | GARVEE CON | 235905000 | 15727000 | 15727000 | 15727000 | 15727000 | 15727000 | 15727000 | 15727000 | 15727000 | 15727000 | 15727000 | 62908000
R-2829B | Highway | STI (Prioritization) | New Route (Future NC 540) | South of SR 2542 (Rock Quarry Road) to I-87 / US 64 / US 264 Bypass | Construct freeway on new location. This is a toll project. | 3.82 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $175 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | T(M) | CONSTRUCTION | 58332000 | FY 2026: 14583000; FY 2027: 14583000; FY 2028: 14583000
R-2829B | Highway | STI (Prioritization) | New Route (Future NC 540) | South of SR 2542 (Rock Quarry Road) to I-87 / US 64 / US 264 Bypass | Construct freeway on new location. This is a toll project. | 3.82 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $175 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | CONSTRUCTION | 230902000
R-2915 | Highway | STI (Prioritization) | US 221 | US 421 in Watauga County to US 221 Business / NC 88 in Jefferson. | Widen to four lanes divided. | 16.1 | Ashe, Watauga | 11 | High Country RPO | [5 empty] | 175463000
R-2915A | Highway | Transition | US 221 | US 421 in Watauga County to SR 1003 (Idlewild Road) in Ashe County. | Widen to four lanes divided. | 3.6 | Ashe, Watauga | 11 | High Country RPO | COMPLETE | Pre-STI (Transition)
R-2915B | Highway | Transition | US 221 | 1003 (Idlewild Road) to North of South Fork New River. | Widen to four lanes divided. | 1 | Ashe | 11 | High Country RPO | COMPLETE | Pre-STI (Transition)
R-2915C | Highway | STI (Prioritization) | US 221 | North of South Fork New River to south of NC 194. | Widen to four lanes divided. | 4.2 | Ashe | 11 | High Country RPO | COMPLETE | Division 11 |  | BGLT5 | CONSTRUCTION | 15760000
R-2915C | Highway | STI (Prioritization) | US 221 | North of South Fork New River to south of NC 194. | Widen to four lanes divided. | 4.2 | Ashe | 11 | High Country RPO | COMPLETE | Division 11 |  | T(M) | CONSTRUCTION | 3940000
R-2915D | Highway | Transition | US 221 | South of NC 194 to US 221 Bypass. | Widen to four lanes divided. | 3.8 | Ashe | 11 | High Country RPO | COMPLETE | Pre-STI (Transition)
R-2915E | Highway | STI (Prioritization) | US 221 | US 221 Bypass to US 221 Business / NC 88 in Jefferson. | Widen to four lanes divided. | 3.55 | Ashe | 11 | High Country RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 11 |  | T | BUILD NC CON | 27615000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000
R-2915E | Highway | STI (Prioritization) | US 221 | US 221 Bypass to US 221 Business / NC 88 in Jefferson. | Widen to four lanes divided. | 3.55 | Ashe | 11 | High Country RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 11 |  | T | CONSTRUCTION | 17069000
R-3100 | Highway | STI (Prioritization) | NC 16 | SR 1895 (Tower Road) to SR 1800 (Caleb Setzer Road) southeast of Newton. | Widen to four lanes. | 9.1 | Catawba | 12 | Greater Hickory MPO | [5 empty] | 74426000
R-3100A | Highway | STI (Prioritization) | NC 16 | SR 1895 (Tower Road) to SR 1814 (Caldwell Road) southeast of Newton. | Widen to four lanes. | 4.41 | Catawba | 12 | Greater Hickory MPO | COMPLETE; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 12 |  | T | BUILD NC CON | 42510000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000
R-3100B | Highway | STI (Prioritization) | NC 16 | SR 1814 (Caldwell Road) to SR 1801 (Claremont Road) southeast of Newton. | Widen to four lanes. | 3.75 | Catawba | 12 | Greater Hickory MPO | COMPLETE. | Division 12
R-3100C | Highway | Pre-STI (Historic) |  |  |  | 0.653 | Catawba | 12 | Greater Hickory MPO | COMPLETE.
R-3300 | Highway | STI (Prioritization) | US 17 (Hampstead Bypass) | US 17 Bypass south of Hampstead to US 17 North of Hampstead. | Construct freeway on new location. | 12.3 | New Hanover, Pender | 3 | Wilmington Urban Area MPO | [5 empty] | 101547000
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 Bypass south of Hampstead to NC 210. | Construct freeway on new location. | 6.87 | Pender, New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | RIGHT-OF-WAY | 10000000 | FY 2026: 5000000
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 Bypass south of Hampstead to NC 210. | Construct freeway on new location. | 6.87 | Pender, New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | BUILD NC CON | 101400000 |  | 3467000 | 3467000 | 6760000 | 6760000 | 6760000 | 6760000 | 6760000 | 6760000 | 6760000 | 47146000
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 Bypass south of Hampstead to NC 210. | Construct freeway on new location. | 6.87 | Pender, New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | CONSTRUCTION | 133580000 | FY 2026: 44030000; FY 2027: 8220000; FY 2028: 44030000; FY 2029: 1840000; FY 2030: 35460000
R-3300B | Highway | STI (Prioritization) | US 17 | NC 210 to US 17 north of Hampstead. | Construct freeway on new location. | 5.45 | Pender | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | Region B |  | T | RIGHT-OF-WAY | 5000000
R-3300B | Highway | STI (Prioritization) | US 17 | NC 210 to US 17 north of Hampstead. | Construct freeway on new location. | 5.45 | Pender | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | Region B |  | T | BUILD NC CON | 71820000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000
R-3300B | Highway | STI (Prioritization) | US 17 | NC 210 to US 17 north of Hampstead. | Construct freeway on new location. | 5.45 | Pender | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | Region B |  | T | CONSTRUCTION | 157732000 | FY 2026: 46709000; FY 2027: 9000000; FY 2028: 10000000
R-3403 | Highway | STI (Prioritization) | US 17 | Mills Street in Bridgeton to NC 43. | Widen to multi-lanes. | 9.8 | Craven | 2 | Down East RPO, New Bern Area MPO |  | Region B |  |  |  | 28147000
R-3403AA | Highway | Pre-STI (Historic) | US 17 | Mills Street in Bridgeton to north of C Street. | Widen to multi-lanes. |  | Craven | 2 | Down East RPO | COMPLETE.
R-3403AB | Highway | Pre-STI (Historic) | US 17 | North C Street to north of SR 1433 (Antioch Road) | Widen to multi-lanes. |  | Craven | 2 | Down East RPO | COMPLETE.
R-3403B | Highway | STI (Prioritization) | US 17 | SR 1433 (Antioch Road) to north of NC 43. | Widen to multi-lanes. | 7.19 | Craven | 2 | Down East RPO, New Bern Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 8900000 | FY 2030: 2136000; FY 2031: 2492000; FY 2032: 2492000; FY 2033: 890000; FY 2034: 890000
R-3403B | Highway | STI (Prioritization) | US 17 | SR 1433 (Antioch Road) to north of NC 43. | Widen to multi-lanes. | 7.19 | Craven | 2 | Down East RPO, New Bern Area MPO |  | Region B |  | T | UTILITIES | 4100000 | FY 2030: 2050000; FY 2031: 2050000
R-3403B | Highway | STI (Prioritization) | US 17 | SR 1433 (Antioch Road) to north of NC 43. | Widen to multi-lanes. | 7.19 | Craven | 2 | Down East RPO, New Bern Area MPO |  | Region B |  | T | CONSTRUCTION | 129100000 | FY 2033: 1291000; FY 2034: 36148000; FY 2035: 33566000 | 58095000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 to US 70 Business. | Widen to multi-lanes. | 8.64 | Johnston | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  |  |  | 2500000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 to US 70 Business. | Widen to multi-lanes. | 8.64 | Johnston | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | T | BUILD NC ROW | 25995000 |  |  | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 12131000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 to US 70 Business. | Widen to multi-lanes. | 8.64 | Johnston | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | T | RIGHT-OF-WAY | 35900000 | FY 2027: 12777000; FY 2028: 5554000; FY 2029: 6389000; FY 2030: 5590000; FY 2031: 5590000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 to US 70 Business. | Widen to multi-lanes. | 8.64 | Johnston | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | T | UTILITIES | 10500000 | FY 2027: 5250000; FY 2028: 5250000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 to US 70 Business. | Widen to multi-lanes. | 8.64 | Johnston | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | BGANY | CONSTRUCTION | 156900000 | FY 2031: 28242000; FY 2032: 37656000; FY 2033: 34518000; FY 2034: 31380000; FY 2035: 25104000
R-3421 | Highway | STI (Prioritization) | US 220 / Future I-73 / Future I-74 | Rockingham Bypass. | Four lanes divided on new location. | 10.5 | Richmond | 8 | Lumber River RPO | BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 60762000
R-3421A | Highway | STI (Prioritization) | US 220 Bypass / Future I 73 / Future I 74 | US 74 Bypass west of Rockingham at SR 1109 (Zion Church Road) to interchange to south of SR 1140 (Old Charlotte Highway) | Construct roadway. | 2.61 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC ROW | 5495000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 371000
R-3421A | Highway | STI (Prioritization) | US 220 Bypass / Future I 73 / Future I 74 | US 74 Bypass west of Rockingham at SR 1109 (Zion Church Road) to interchange to south of SR 1140 (Old Charlotte Highway) | Construct roadway. | 2.61 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 74948000 | 4959000 | 4959000 | 4959000 | 4959000 | 4959000 | 4959000 | 4959000 | 4774000 | 4774000 | 4772000
R-3421A | Highway | STI (Prioritization) | US 220 Bypass / Future I 73 / Future I 74 | US 74 Bypass west of Rockingham at SR 1109 (Zion Church Road) to interchange to south of SR 1140 (Old Charlotte Highway) | Construct roadway. | 2.61 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | CONSTRUCTION | 31909000
R-3421B | Highway | STI (Prioritization) | US 220 Bypass / Future I 73 / Future I 74 | South of SR 1140 (Old Charlotte Highway) to southwest of SR 1304 (Harrington Road) | Construct roadway. | 9.25 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 39179000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2611000
R-3421B | Highway | STI (Prioritization) | US 220 Bypass / Future I 73 / Future I 74 | South of SR 1140 (Old Charlotte Highway) to southwest of SR 1304 (Harrington Road) | Construct roadway. | 9.25 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | CONSTRUCTION | 44500000
R-3421C | Highway | Transition | US 220 Bypass / Future I 73 / Future I 74 | 0.2 miles southwest of SR 1304 (Harrington Road) to I-73 / I-74 Interchange south of Ellerbe | Construct roadway. | 0.84 | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-3421CA | Highway | STI (Prioritization) | US 220 / Future I 73 / Future I 74 | SR 1336 (Billy Covington Road) | Construct roadway. |  | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | RIGHT-OF-WAY | 75000
R-3421CA | Highway | STI (Prioritization) | US 220 / Future I 73 / Future I 74 | SR 1336 (Billy Covington Road) | Construct roadway. |  | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | UTILITIES | 25000
R-3421CA | Highway | STI (Prioritization) | US 220 / Future I 73 / Future I 74 | SR 1336 (Billy Covington Road) | Construct roadway. |  | Richmond | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | CONSTRUCTION | 532000
R-3430 | Highway | STI (Prioritization) | SR 1001 (Malcolm Boulevard / Connelly Springs Road) | US 70 to SR 1933 (South-West Boulevard) in Lenoir. | Modernize roadway to include bicycle and pedestrian accommodations. | 10 | Caldwell, Burke | 11, 13 | Greater Hickory MPO | [5 empty] | 2807000
R-3430A | Highway | STI (Prioritization) | SR 1001 (Malcolm Boulevard) | US 70 to Catawba River in Rutherford College. | Modernize roadway to include bicycle and pedestrian accommodations. |  | Burke | 13 | Greater Hickory MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000000 | [10 empty] | 10000000
R-3430A | Highway | STI (Prioritization) | SR 1001 (Malcolm Boulevard) | US 70 to Catawba River in Rutherford College. | Modernize roadway to include bicycle and pedestrian accommodations. |  | Burke | 13 | Greater Hickory MPO |  | Not Funded |  | T | UTILITIES | 1600000 | [10 empty] | 1600000
R-3430A | Highway | STI (Prioritization) | SR 1001 (Malcolm Boulevard) | US 70 to Catawba River in Rutherford College. | Modernize roadway to include bicycle and pedestrian accommodations. |  | Burke | 13 | Greater Hickory MPO |  | Not Funded |  | T | CONSTRUCTION | 20000000 | [10 empty] | 20000000
R-3430B | Highway | Bridges | SR 1001 (Connelly Springs Road) | Bridge 110010 over Catawba River. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Highway Fund |  | HFB | RIGHT-OF-WAY | 880000
R-3430B | Highway | Bridges | SR 1001 (Connelly Springs Road) | Bridge 110010 over Catawba River. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Highway Fund |  | HFB | UTILITIES | 370000
R-3430B | Highway | Bridges | SR 1001 (Connelly Springs Road) | Bridge 110010 over Catawba River. | Replace bridge. | 0.25 | Burke | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Highway Fund |  | HFB | CONSTRUCTION | 22902000 | FY 2026: 3368000; FY 2027: 10088000; FY 2028: 7421000; FY 2029: 2025000
R-3430CA | Highway | STI (Prioritization) | SR 1001 (Connelly Springs Road) | Cajah Mountain Road to SR 1933 (South-West Boulevard) in Cajah's Mountain. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.5 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | RIGHT-OF-WAY | 18942000 | FY 2029: 1377000; FY 2030: 4133000; FY 2031: 4133000; FY 2032: 4133000; FY 2033: 5166000
R-3430CA | Highway | STI (Prioritization) | SR 1001 (Connelly Springs Road) | Cajah Mountain Road to SR 1933 (South-West Boulevard) in Cajah's Mountain. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.5 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | UTILITIES | 2265000 | FY 2029: 1133000; FY 2030: 1132000
R-3430CA | Highway | STI (Prioritization) | SR 1001 (Connelly Springs Road) | Cajah Mountain Road to SR 1933 (South-West Boulevard) in Cajah's Mountain. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.5 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | CONSTRUCTION | 52300000 | FY 2033: 4707000; FY 2034: 13598000; FY 2035: 12552000 | 21443000
R-3430CB | Highway | STI (Prioritization) | SR 1001 (Connelly Springs Road) | Catawba River to Cajah Mountain Road in Cajah's Mountain.. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.54 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | RIGHT-OF-WAY | 17857000 | FY 2030: 1299000; FY 2031: 3896000; FY 2032: 3896000; FY 2033: 3896000; FY 2034: 4870000
R-3430CB | Highway | STI (Prioritization) | SR 1001 (Connelly Springs Road) | Catawba River to Cajah Mountain Road in Cajah's Mountain.. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.54 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | UTILITIES | 2135000 | FY 2030: 1068000; FY 2031: 1067000
R-3430CB | Highway | STI (Prioritization) | SR 1001 (Connelly Springs Road) | Catawba River to Cajah Mountain Road in Cajah's Mountain.. | Modernize roadway to include bicycle and pedestrian accommodations. | 3.54 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | CONSTRUCTION | 49300000 | FY 2034: 4437000; FY 2035: 12818000 | 32045000
R-3603 | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.7 | Alexander, Catawba | 12 | Greater Hickory MPO | [5 empty] | 600000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Alexander, Catawba | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | BGANY | RIGHT-OF-WAY | 15680000 | FY 2030: 5702000; FY 2031: 6842000; FY 2032: 1568000; FY 2033: 1568000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Alexander, Catawba | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | T(M) | RIGHT-OF-WAY | 3920000 | FY 2030: 1425000; FY 2031: 1711000; FY 2032: 392000; FY 2033: 392000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Alexander, Catawba | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | BGANY | UTILITIES | 5840000 | FY 2030: 2920000; FY 2031: 2920000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Alexander, Catawba | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | T(M) | UTILITIES | 1460000 | FY 2030: 730000; FY 2031: 730000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Alexander, Catawba | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | BGANY | CONSTRUCTION | 92561000 | FY 2034: 13884000; FY 2035: 21289000 | 57388000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (Cloninger Mill Road) to SR 1156 (Richey Road). | Upgrade two lanes and construct multi-lane curb and gutter. Construct right turn lane on NC 127 at SR 1146 (Bethlehem School Road). | 3.67 | Alexander, Catawba | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | T(M) | CONSTRUCTION | 23139000 | FY 2034: 3471000; FY 2035: 5322000 | 14346000
R-3608 | Highway | STI (Prioritization) | US 401 / NC 39 | NC 56 / NC 581 (Nash Street) to SR 1229 (Main Street). | Widen to multi-lanes. | 1.36 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | Region C |  | T | RIGHT-OF-WAY | 8500000 | FY 2030: 850000; FY 2031: 2975000; FY 2032: 2975000; FY 2033: 850000; FY 2034: 850000
R-3608 | Highway | STI (Prioritization) | US 401 / NC 39 | NC 56 / NC 581 (Nash Street) to SR 1229 (Main Street). | Widen to multi-lanes. | 1.36 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | Region C |  | T | UTILITIES | 3400000 | FY 2030: 1133000; FY 2031: 1133000; FY 2032: 1134000
R-3608 | Highway | STI (Prioritization) | US 401 / NC 39 | NC 56 / NC 581 (Nash Street) to SR 1229 (Main Street). | Widen to multi-lanes. | 1.36 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | Region C |  | T | CONSTRUCTION | 38800000 | FY 2033: 4656000; FY 2034: 11252000; FY 2035: 9700000 | 13192000
R-3822 | Highway | STI (Prioritization) | New Route | NC 125 to south of US 158. | Construct three lane facility on new location. | 1.49 | Halifax | 4 | Peanut Belt RPO | COMPLETE. COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725. | Division 4 |  |  |  | 4972000
R-3825 | Highway | STI (Prioritization) | NC 42 | US 70 to SR 1003 (Buffalo Road). | Widen to multi-lanes. | 6.1 | Johnston | 4 | Capital Area MPO | [5 empty] | 49175000
R-3825A | Highway | Pre-STI (Historic) | NC 42 | US 70 in Clayton to east of SR 1902 (Glen Laurel Road) | Widen to multi-lanes. | 1.5 | Johnston | 4 | Capital Area MPO | COMPLETE.
R-3825B | Highway | STI (Prioritization) | NC 42 | East of SR 1902 (Glen Laurel Road) to SR 1003 (Buffalo Road). | Widen to multi-lanes. | 4.35 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 43650000 | 2910000 | 2910000 | 2910000 | 2910000 | 2910000 | 2910000 | 2910000 | 2910000 | 1517000 | 1517000
R-3825B | Highway | STI (Prioritization) | NC 42 | East of SR 1902 (Glen Laurel Road) to SR 1003 (Buffalo Road). | Widen to multi-lanes. | 4.35 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | CONSTRUCTION | 24798000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (Bradfway Road / North Main Street) | NC 42, US 421 (Future I-685 / Horner Boulevard) in Sanford to SR 1579 (Broadway Road) and SR 1579 (Broadway Road / North Main Street), NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue) in Broadway. | Widen to a four lane divided facility from US 421 (Future I-685) to NC 42 (Avents Ferry Road) and widen to three lanes from NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue). | 5.57 | Lee | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  |  |  | 19418000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (Bradfway Road / North Main Street) | NC 42, US 421 (Future I-685 / Horner Boulevard) in Sanford to SR 1579 (Broadway Road) and SR 1579 (Broadway Road / North Main Street), NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue) in Broadway. | Widen to a four lane divided facility from US 421 (Future I-685) to NC 42 (Avents Ferry Road) and widen to three lanes from NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue). | 5.57 | Lee | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  | T | BUILD NC ROW | 10228000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 680000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (Bradfway Road / North Main Street) | NC 42, US 421 (Future I-685 / Horner Boulevard) in Sanford to SR 1579 (Broadway Road) and SR 1579 (Broadway Road / North Main Street), NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue) in Broadway. | Widen to a four lane divided facility from US 421 (Future I-685) to NC 42 (Avents Ferry Road) and widen to three lanes from NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue). | 5.57 | Lee | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  | T | BUILD NC CON | 14490000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 1932000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (Bradfway Road / North Main Street) | NC 42, US 421 (Future I-685 / Horner Boulevard) in Sanford to SR 1579 (Broadway Road) and SR 1579 (Broadway Road / North Main Street), NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue) in Broadway. | Widen to a four lane divided facility from US 421 (Future I-685) to NC 42 (Avents Ferry Road) and widen to three lanes from NC 42 (Avents Ferry Road) to SR 1538 (East Harrington Avenue). | 5.57 | Lee | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  | T | CONSTRUCTION | 77704000 | FY 2026: 12610000; FY 2027: 15000000; FY 2028: 10000000; FY 2029: 10000000
R-3830A | Highway | STI (Prioritization) | NC 42 | Various | Mitigate railroad. |  | Lee | 8 | Central Pines RPO | UNDER CONSTRUCTION | Division 8 |  | T | CONSTRUCTION | 1900000
R-3833 | Highway | STI (Prioritization) | SR 1100 (Brawley School Road) | SR 1177 (Chuckwood Road) to US 21 in Mooresville. | Widen to multi-lanes with interchange at I-77. | 5.9 | Iredell | 12 | Charlotte Regional TPO | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. |  |  |  |  | 126721000
R-3833A | Highway | Pre-STI (Historic) | SR 1100 (Brawley School Road) | SR 1177 (Chuckwood Road) to SR 1109 (Centre Church Road). | Widen to multi-lanes. | 3.9 | Iredell | 12 | Charlotte Regional TPO | COMPLETE
R-3833B | Highway | Pre-STI (Historic) | SR 1100 (Brawley School Road) | SR 1109 (Centre Church Road) to I-77 | Widen to multi-lanes. | 1.1 | Iredell | 12 | Charlotte Regional TPO | COMPLETE
R-3833C | Highway | STI (Prioritization) | SR 1100 (Brawley School Road) | I-77 to US 21 in Mooresville | Widen to multi-lanes. | 1 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. | Division 12 |  | T | RIGHT-OF-WAY | 5610000
R-3833C | Highway | STI (Prioritization) | SR 1100 (Brawley School Road) | I-77 to US 21 in Mooresville | Widen to multi-lanes. | 1 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. | Division 12 |  | T | UTILITIES | 1950000
R-3833C | Highway | STI (Prioritization) | SR 1100 (Brawley School Road) | I-77 to US 21 in Mooresville | Widen to multi-lanes. | 1 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. | Division 12 |  | T | BUILD NC CON | 19950000 | 1330000 | 1330000 | 1330000 | 2660000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 3990000
R-3833C | Highway | STI (Prioritization) | SR 1100 (Brawley School Road) | I-77 to US 21 in Mooresville | Widen to multi-lanes. | 1 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. | Division 12 |  | T | CONSTRUCTION | 22997000 | FY 2026: 7894000; FY 2027: 242000
R-3833C | Highway | STI (Prioritization) | SR 1100 (Brawley School Road) | I-77 to US 21 in Mooresville | Widen to multi-lanes. | 1 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. | Division 12 |  | L | CONSTRUCTION | 890000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (Lattimore Road) intersection in Mooresboro; West of US 74 Business (Ellenboro Road) to east of Bridges 023048 and 023049 over Sandy Run. | Upgrade at-grade intersection to interchange; Upgrade US 74 to full control of access. | 1.35 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | T | RIGHT-OF-WAY | 16000000 | FY 2026: 5500000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (Lattimore Road) intersection in Mooresboro; West of US 74 Business (Ellenboro Road) to east of Bridges 023048 and 023049 over Sandy Run. | Upgrade at-grade intersection to interchange; Upgrade US 74 to full control of access. | 1.35 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | T | UTILITIES | 5600000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (Lattimore Road) intersection in Mooresboro; West of US 74 Business (Ellenboro Road) to east of Bridges 023048 and 023049 over Sandy Run. | Upgrade at-grade intersection to interchange; Upgrade US 74 to full control of access. | 1.35 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | DP | CONSTRUCTION | 23239000 | FY 2026: 2530000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (Lattimore Road) intersection in Mooresboro; West of US 74 Business (Ellenboro Road) to east of Bridges 023048 and 023049 over Sandy Run. | Upgrade at-grade intersection to interchange; Upgrade US 74 to full control of access. | 1.35 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 38352000 | FY 2026: 3629000
R-4463 | Highway | Pre-STI (Historic) | NC 43 Connector | NC 43 / NC 55 to US 17 in New Bern. | Construct route on new location with interchange at US 70. | 4.2 | Craven | 2 | New Bern Area MPO | [5 empty] | 61329000
R-4463A | Highway | STI (Prioritization) | NC 43 Connector | US 17 Business to south of US 17 / US 70. | Construct route on new location. | 2.29 | Craven | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | ENGINEERING | 1725000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000
R-4463A | Highway | STI (Prioritization) | NC 43 Connector | US 17 Business to south of US 17 / US 70. | Construct route on new location. | 2.29 | Craven | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | BUILD NC ROW | 240000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
R-4463A | Highway | STI (Prioritization) | NC 43 Connector | US 17 Business to south of US 17 / US 70. | Construct route on new location. | 2.29 | Craven | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | RIGHT-OF-WAY | 7783000
R-4463A | Highway | STI (Prioritization) | NC 43 Connector | US 17 Business to south of US 17 / US 70. | Construct route on new location. | 2.29 | Craven | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | UTILITIES | 1350000
R-4463A | Highway | STI (Prioritization) | NC 43 Connector | US 17 Business to south of US 17 / US 70. | Construct route on new location. | 2.29 | Craven | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | CONSTRUCTION | 36870000 | FY 2026: 9586000; FY 2027: 10324000; FY 2028: 8111000; FY 2029: 5899000; FY 2030: 2950000
R-4463AA | Highway | Transition | NC 43 Connector | South of US 17 / US 70 to US 70. | Construct route on new location with interchange at US 70. | 2.5 | Craven | 2 | New Bern Area MPO | COMPLETE.
R-4463B | Highway | Economic Development | New Route | US 70 to NC 43 / NC 55. | Construct NC 43 connector with interchange at US 70. |  | Craven | 2 | New Bern Area MPO | COMPLETE. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOSCH CORPORATION.
R-4467 | Highway | Pre-STI (Historic) | US 17 Business / NC 37 | South of Bridge 710008 (Perquimans River Bridge) to north of NC 37. | Replace bridge. | 0.82 | Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  |  |  | 12519000
R-4467 | Highway | Pre-STI (Historic) | US 17 Business / NC 37 | South of Bridge 710008 (Perquimans River Bridge) to north of NC 37. | Replace bridge. | 0.82 | Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | ENGINEERING | 2415000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000
R-4467 | Highway | Pre-STI (Historic) | US 17 Business / NC 37 | South of Bridge 710008 (Perquimans River Bridge) to north of NC 37. | Replace bridge. | 0.82 | Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC CON | 52605000 | 3507000 | 3507000 | 3507000 | 3507000 | 3507000 | 3507000 | 3507000 | 3507000 | 3269000 | 3269000
R-4467 | Highway | Pre-STI (Historic) | US 17 Business / NC 37 | South of Bridge 710008 (Perquimans River Bridge) to north of NC 37. | Replace bridge. | 0.82 | Perquimans | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | CONSTRUCTION | 12907000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  |  |  | 4800000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) |  | 1200000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | RIGHT-OF-WAY | 160000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) | RIGHT-OF-WAY | 40000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | UTILITIES | 1680000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) | UTILITIES | 420000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | CONSTRUCTION | 38518000
R-4705 | Highway | STI (Prioritization) | SR 1142 (Prison Camp Road) | NC 903 to SR 1182 (East College Road). | Upgrade facility. | 9.58 | Martin | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) | CONSTRUCTION | 9629000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (Reedy Fork Parkway) | US 29 / SR 4771 (Reedy Fork Parkway) interchange improvements in Greensboro. | Improve roadway, modify interchange, and replace bridge 400360. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  |  |  | 10407000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (Reedy Fork Parkway) | US 29 / SR 4771 (Reedy Fork Parkway) interchange improvements in Greensboro. | Improve roadway, modify interchange, and replace bridge 400360. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | ENGINEERING | 4019000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (Reedy Fork Parkway) | US 29 / SR 4771 (Reedy Fork Parkway) interchange improvements in Greensboro. | Improve roadway, modify interchange, and replace bridge 400360. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | BUILD NC ROW | 5824000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (Reedy Fork Parkway) | US 29 / SR 4771 (Reedy Fork Parkway) interchange improvements in Greensboro. | Improve roadway, modify interchange, and replace bridge 400360. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | BUILD NC CON | 32288000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 4036000 | 2018000 | 2018000 | 2018000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (Reedy Fork Parkway) | US 29 / SR 4771 (Reedy Fork Parkway) interchange improvements in Greensboro. | Improve roadway, modify interchange, and replace bridge 400360. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | CONSTRUCTION | 29816000
R-4753 | Highway | STI (Prioritization) | NC 107 | SR 1002 (Old Cullowhee Road) to NC 281. | Upgrade existing roadway. | 4.01 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION | Division 14 |  |  |  | 50599000
R-5014 | Highway | STI (Prioritization) | SR 1217 (Collington Road) | Dead end to US 158 (Croatan Highway) in Kill Devil Hills. | Construct operational safety improvements. | 4.35 | Dare | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  |  |  | 2020000
R-5014 | Highway | STI (Prioritization) | SR 1217 (Collington Road) | Dead end to US 158 (Croatan Highway) in Kill Devil Hills. | Construct operational safety improvements. | 4.35 | Dare | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) |  | 505000
R-5014 | Highway | STI (Prioritization) | SR 1217 (Collington Road) | Dead end to US 158 (Croatan Highway) in Kill Devil Hills. | Construct operational safety improvements. | 4.35 | Dare | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | CONSTRUCTION | 17894000
R-5014 | Highway | STI (Prioritization) | SR 1217 (Collington Road) | Dead end to US 158 (Croatan Highway) in Kill Devil Hills. | Construct operational safety improvements. | 4.35 | Dare | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | T(M) | CONSTRUCTION | 4474000
R-5020 | Highway | STI (Prioritization) | US 701 Bypass (Madison Street - Powell Boulevard) | South of SR 1166 (Pleasant Plains Road) to north of US 74 / US 76 Bypass in Whiteville. | Widen to multi-lane facility. | 3.92 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. |  |  |  |  | 15050000
R-5020A | Highway | STI (Prioritization) | US 701 Bypass | SR 1166 (Pleasant Plains Church Road) to SR 1437 (Virgil Avenue). | Widen to multi-lane facility. | 2.18 | Columbus | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | BG5T50 | CONSTRUCTION | 63600000 | FY 2030: 636000; FY 2031: 17172000; FY 2032: 17808000; FY 2033: 15900000; FY 2034: 12084000
R-5020AA | Highway | STI (Prioritization) | US 701 Business | South of SR 1920 (Mill Pond Road) | Replace culvert. | 0.5 | Columbus | 6 | Cape Fear RPO |  | Region C |  | BG5T50 | CONSTRUCTION | 2000000 | FY 2027: 2000000
R-5020B | Highway | STI (Prioritization) | US 701 Bypass | SR 1437 (Virgil Avenue) to US 74 / US 76. | Widen to multi-lane facility. | 1.74 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 32485000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 28854000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | T(M) |  | 7214000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGANY | UTILITIES | 8680000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | T(M) | UTILITIES | 2170000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGANY | CONSTRUCTION | 191901000 | FY 2026: 6628000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (Midway Road) to NC 87. | Widen to four lanes. | 6.55 | Brunswick | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | T(M) | CONSTRUCTION | 47975000 | FY 2026: 1657000
R-5100 | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to NC 150 in Mooresville. | Widen to four lanes. | 3.2 | Iredell | 12 | Charlotte Regional TPO | COORDINATE WITH U-5817. |  |  |  |  | 1373000
R-5100A | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE). | Division 12 |  | T | ENGINEERING | 600000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
R-5100A | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE). | Division 12 |  | T | BUILD NC ROW | 4050000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 257000 | 257000
R-5100A | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE). | Division 12 |  | T | RIGHT-OF-WAY | 7650000
R-5100A | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE). | Division 12 |  | T | UTILITIES | 5300000
R-5100A | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE). | Division 12 |  | T | BUILD NC CON | 13005000 |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
R-5100A | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | I-77 to SR 1100 (Brawley School Road) in Mooresville. | Widen to four lanes. | 2.35 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $10M CON PAYBACK FY 28-42 (FY 28/YR 8 SALE). | Division 12 |  | T | CONSTRUCTION | 64300000 | FY 2027: 15745000; FY 2028: 0; FY 2029: 18813000; FY 2030: 16620000; FY 2031: 13122000
R-5100B | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | SR 1100 (Brawley School Road) to NC 150 in Mooresville. | Widen to four lanes. | 0.87 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | BUILD NC ROW | 3015000 | 201000 | 201000 | 201000 | 201000 | 201000 | 201000 | 201000 | 201000 | 201000 | 171000 | 171000
R-5100B | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | SR 1100 (Brawley School Road) to NC 150 in Mooresville. | Widen to four lanes. | 0.87 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | RIGHT-OF-WAY | 7325000 | FY 2026: 825000
R-5100B | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | SR 1100 (Brawley School Road) to NC 150 in Mooresville. | Widen to four lanes. | 0.87 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | UTILITIES | 1300000 | FY 2026: 650000; FY 2027: 650000
R-5100B | Highway | STI (Prioritization) | SR 1109 (Williamson Road) | SR 1100 (Brawley School Road) to NC 150 in Mooresville. | Widen to four lanes. | 0.87 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | BGANY | CONSTRUCTION | 10500000 | FY 2026: 105000; FY 2027: 4830000; FY 2028: 3885000; FY 2029: 1680000
R-5113 | Highway | STI (Prioritization) | SR 1005 (Startown Road) | US 70 to NC 10 in Hickory. | Widen to multi-lanes. | 4.62 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2028000
R-5113 | Highway | STI (Prioritization) | SR 1005 (Startown Road) | US 70 to NC 10 in Hickory. | Widen to multi-lanes. | 4.62 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 99500000
R-5113 | Highway | STI (Prioritization) | SR 1005 (Startown Road) | US 70 to NC 10 in Hickory. | Widen to multi-lanes. | 4.62 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 27800000
R-5113 | Highway | STI (Prioritization) | SR 1005 (Startown Road) | US 70 to NC 10 in Hickory. | Widen to multi-lanes. | 4.62 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 74500000
R-5311 | Highway | STI (Prioritization) | US 13 / NC 11 | NC 11 / NC 561 intersection in Ahoskie to US 13 / US 158 / NC 45 intersection near Winton | Widen to multi-lanes. | 7.8 | Hertford | 1 | Peanut Belt RPO | [5 empty] | 20809000
R-5311A | Highway | STI (Prioritization) | US 13 / NC 11 | West of Modlin Road to east of NC 11 / SR 1213 (Old NC 11 Road). | Construct grade separation. | 1 | Hertford | 1 | Peanut Belt RPO | COMPLETE. | Statewide Mobility
R-5311B | Highway | STI (Prioritization) | US 13 / NC 11 | NC 11 / NC 561 intersection near Ahoskie to US 13 / US 158 / NC 45 intersection near Winton. | Widen to multi-lanes. | 7.77 | Hertford | 1 | Peanut Belt RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2900000
R-5311B | Highway | STI (Prioritization) | US 13 / NC 11 | NC 11 / NC 561 intersection near Ahoskie to US 13 / US 158 / NC 45 intersection near Winton. | Widen to multi-lanes. | 7.77 | Hertford | 1 | Peanut Belt RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3000000
R-5311B | Highway | STI (Prioritization) | US 13 / NC 11 | NC 11 / NC 561 intersection near Ahoskie to US 13 / US 158 / NC 45 intersection near Winton. | Widen to multi-lanes. | 7.77 | Hertford | 1 | Peanut Belt RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 193400000
R-5500 | Highway | Other | Indian Reservation Road (IRR) Program. | Various locations. | Improve roads and bridges. Constructed by Eastern Band of Cherokee Indians. |  | Jackson, Swain | 14 | Southwestern RPO | PROGRAM IN PROGRESS | Exempt
R-5600 | Highway | STI (Prioritization) | NC 107; US 23 Business | US 23 Business to NC 116 (Webster Road); SR 1432 (Skyland Drive) to west of Municipal Drive in Sylva. | Construct access management improvements. | 1.85 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  |  |  | 3825000
R-5600 | Highway | STI (Prioritization) | NC 107; US 23 Business | US 23 Business to NC 116 (Webster Road); SR 1432 (Skyland Drive) to west of Municipal Drive in Sylva. | Construct access management improvements. | 1.85 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | T | BUILD NC ROW | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000
R-5600 | Highway | STI (Prioritization) | NC 107; US 23 Business | US 23 Business to NC 116 (Webster Road); SR 1432 (Skyland Drive) to west of Municipal Drive in Sylva. | Construct access management improvements. | 1.85 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | T | RIGHT-OF-WAY | 44700000
R-5600 | Highway | STI (Prioritization) | NC 107; US 23 Business | US 23 Business to NC 116 (Webster Road); SR 1432 (Skyland Drive) to west of Municipal Drive in Sylva. | Construct access management improvements. | 1.85 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | T | UTILITIES | 7200000
R-5600 | Highway | STI (Prioritization) | NC 107; US 23 Business | US 23 Business to NC 116 (Webster Road); SR 1432 (Skyland Drive) to west of Municipal Drive in Sylva. | Construct access management improvements. | 1.85 | Jackson | 14 | Southwestern RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | BG5T50 | CONSTRUCTION | 95913000 | FY 2026: 16305000; FY 2027: 22060000; FY 2028: 22060000; FY 2029: 20142000; FY 2030: 15346000