TC-0041 | Public Transportation (Transit) | Capital (Non-STI) | Tar River Transit | Systemwide | Purchase 4 replacement 25-foot light transit vehicles and 2 replacement 30- foot vehicles. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Public Transit |  | L | CAPITAL | 450000 | FY 2026: 300000
TC-0041 | Public Transportation (Transit) | Capital (Non-STI) | Tar River Transit | Systemwide | Purchase 4 replacement 25-foot light transit vehicles and 2 replacement 30- foot vehicles. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1800000 | FY 2026: 1200000
TC-0042 | Public Transportation (Transit) | Capital (Non-STI) | Chapel Hill Transit | Systemwide | Fund mobilty management under 5310 grant. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | S | CAPITAL | 15000
TC-0042 | Public Transportation (Transit) | Capital (Non-STI) | Chapel Hill Transit | Systemwide | Fund mobilty management under 5310 grant. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5307 | CAPITAL | 60000
TC-0043 | Public Transportation (Transit) | Capital (Non-STI) | Chapel Hill Transit | Systemwide | Fund Ex rider senior shuttle 5310 grant. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | CAPITAL | 274000
TC-0043 | Public Transportation (Transit) | Capital (Non-STI) | Chapel Hill Transit | Systemwide | Fund Ex rider senior shuttle 5310 grant. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5310 | CAPITAL | 274000
TC-5100 | Public Transportation (Transit) | Capital (Non-STI) | Transportation System Craven Area Rural | Systemwide | Funding for mobility management. |  | Craven | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 24000 | FY 2026: 6000
TC-5100 | Public Transportation (Transit) | Capital (Non-STI) | Transportation System Craven Area Rural | Systemwide | Funding for mobility management. |  | Craven | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 96000 | FY 2026: 24000
TD-4701 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | South Tryon Street Garage | Funding to service debt. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 366000
TD-4701 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | South Tryon Street Garage | Funding to service debt. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 2166000 | FY 2026: 600000; FY 2027: 600000; FY 2028: 600000
TD-4701 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | South Tryon Street Garage | Funding to service debt. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 10126000 | FY 2026: 2400000; FY 2027: 2400000; FY 2028: 2400000
TD-4702 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Transit Center | Upgrade facility. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 72000
TD-4702 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Transit Center | Upgrade facility. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 72000
TD-4702 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Transit Center | Upgrade facility. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 576000
TD-4904 | Public Transportation (Transit) | STI (Prioritization) | Jacksonville Transit | Systemwide | Funding for downtown transit center. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 476000 | FY 2026: 188000; FY 2027: 188000
TD-4904 | Public Transportation (Transit) | STI (Prioritization) | Jacksonville Transit | Systemwide | Funding for downtown transit center. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 1900000 | FY 2026: 750000; FY 2027: 750000
TD-4912 | Public Transportation (Transit) | STI (Prioritization) | GoRaleigh | US 64 Business at New Hope Road intersection | Funding to construct transit facility on New Hope Road in Raleigh. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO RALEIGH | Division 5 |  |  |  | 880000
TD-5155 | Public Transportation (Transit) | Locally Selected | Orange Public Transit | Systemwide | Funding for one replacement LTV (25') and radio, vehicle lettering and logos, and on board camera. |  | Orange | 7 | Triangle West TPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | Division 7 |  | BGDA | CAPITAL | 124000
TD-5155 | Public Transportation (Transit) | Locally Selected | Orange Public Transit | Systemwide | Funding for one replacement LTV (25') and radio, vehicle lettering and logos, and on board camera. |  | Orange | 7 | Triangle West TPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | Division 7 |  | L | CAPITAL | 30000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GoCary | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Wake | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | L | ENGINEERING | 2500000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GoCary | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Wake | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | DP | CONSTRUCTION | 1000000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GoCary | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Wake | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | T | CONSTRUCTION | 700000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GoCary | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Wake | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | L | CONSTRUCTION | 60955000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GoCary | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Wake | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | 5307 | CONSTRUCTION | 2000000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GoCary | Systemwide | Construct bus maintenance facility at towerview in Cary. |  | Wake | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | 5339(b) | CONSTRUCTION | 11787000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | L | PLANNING | 26000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | 5339(b) | PLANNING | 104000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | DP | CONSTRUCTION | 20000000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | T | CONSTRUCTION | 8860000 | FY 2026: 2215000; FY 2027: 2215000; FY 2028: 2215000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | O | CONSTRUCTION | 24300000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | L | CONSTRUCTION | 205000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Union Station in Raleigh | Construct bus component. |  | Wake | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | 5339(b) | CONSTRUCTION | 820000
TD-5272 | Public Transportation (Transit) | STI (Prioritization) | GoRaleigh | South Wilmington Street at Pecan Road in Raleigh | Construct off street transfer facility. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO RALEIGH | Division 5
TD-5281 | Public Transportation (Transit) | STI (Prioritization) | Tar River Transit | Systemwide | Construct improvements to driver's break room. |  | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T | CAPITAL | 15000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Expand existing garage facility in Morrisville. |  | Wake | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  |  |  | 15300000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Expand existing garage facility in Morrisville. |  | Wake | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | L | PLANNING | 24000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Expand existing garage facility in Morrisville. |  | Wake | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | 5339(b) | PLANNING | 96000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Expand existing garage facility in Morrisville. |  | Wake | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 163000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Expand existing garage facility in Morrisville. |  | Wake | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | 5339(b) | CONSTRUCTION | 652000
TD-5294 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | NC 98 (Holloway Street) transit corridor | Construct access and bus stop improvements. |  | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION BY GO TRIANGLE | Public Transit |  | DP | PLANNING | 12046000 | FY 2026: 1223000; FY 2027: 10823000
TD-5294 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | NC 98 (Holloway Street) transit corridor | Construct access and bus stop improvements. |  | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION BY GO TRIANGLE | Public Transit |  | L | PLANNING | 5339000 | FY 2026: 306000; FY 2027: 2706000
TD-5295 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Town of Hillsborough | Construct park and ride lot. |  | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY GO TRIANGLE | Public Transit |  | S | CONSTRUCTION | 240000 | FY 2026: 120000
TD-5295 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Town of Hillsborough | Construct park and ride lot. |  | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY GO TRIANGLE | Public Transit |  | L | CONSTRUCTION | 1600000 | FY 2026: 800000
TD-5295 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Town of Hillsborough | Construct park and ride lot. |  | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY GO TRIANGLE | Public Transit |  | 5307 | CONSTRUCTION | 800000 | FY 2026: 800000
TD-5302 | Public Transportation (Transit) | Capital (Non-STI) | City Of Salisbury | Systemwide | Funding for preventive maintenance for bus and bus facility, facility improvements and repairs, automatic bus washer, shop equipment, fueling system, security gate upgrade. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Public Transit |  | L | CAPITAL | 344000 | FY 2026: 61000; FY 2027: 61000; FY 2028: 61000
TD-5302 | Public Transportation (Transit) | Capital (Non-STI) | City Of Salisbury | Systemwide | Funding for preventive maintenance for bus and bus facility, facility improvements and repairs, automatic bus washer, shop equipment, fueling system, security gate upgrade. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Public Transit |  | 5339 | CAPITAL | 1376000 | FY 2026: 244000; FY 2027: 244000; FY 2028: 244000
TD-5303 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | FTA Section 5339 bus and bus facilities grant. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 475000 | FY 2026: 110000; FY 2027: 110000
TD-5303 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | FTA Section 5339 bus and bus facilities grant. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5339 | CAPITAL | 2440000 | FY 2026: 620000; FY 2027: 620000
TD-5304 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Construct bus stop improvements. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 6546000 | FY 2026: 1273000
TD-5305 | Public Transportation (Transit) | Capital (Non-STI) | Cary Transit | Systemwide | Funding for downtown Cary multi modal facility. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 44200000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | Various | Triangle Town Center | Construct transit center and park and ride facility. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 1500000 | FY 2027: 1500000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | Various | Triangle Town Center | Construct transit center and park and ride facility. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 1750000 | FY 2028: 875000; FY 2029: 875000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | Various | Triangle Town Center | Construct transit center and park and ride facility. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | O | CONSTRUCTION | 1750000 | FY 2028: 875000; FY 2029: 875000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | Various | Triangle Town Center | Construct transit center and park and ride facility. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 3158000 | FY 2028: 3158000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct coordinated ADA Facility. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | L | PLANNING | 4000000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct coordinated ADA Facility. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | L | RIGHT-OF-WAY | 2750000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct coordinated ADA Facility. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | DP | CONSTRUCTION | 9966000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct coordinated ADA Facility. |  | Wake | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | L | CONSTRUCTION | 69969000
TD-5309 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 601000
TD-5309 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 151000
TD-5309A | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 200000
TD-5309A | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 50000
TD-5309B | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1200000
TD-5309B | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations in Raleigh | Construct new bus stop sites including ADA accessibility appointments and passenger amenities where appropriate. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 300000
TD-5314 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Various locations | Construct improvements at existing park and ride. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 1105000
TD-5315 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Various locations | Construct new park and ride at Hillsborough Street and I-440 In Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 2220000
TD-5315 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Various locations | Construct new park and ride at Hillsborough Street and I-440 In Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 5200000 | FY 2026: 5200000
TD-5318 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct new transit center at midtown area of Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 547000
TD-5318 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct new transit center at midtown area of Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | RIGHT-OF-WAY | 2249000 | FY 2026: 562000
TD-5318 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Construct new transit center at midtown area of Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 2989000
TD-5319 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Update transit center at the Crabtree valley mall. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 648000 | FY 2026: 324000
TD-5320 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Update transit center at the Triangle Towne Center. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 7527000 | FY 2026: 324000; FY 2028: 2000000; FY 2030: 4879000
TD-6322 | Public Transportation (Transit) | Capital (Non-STI) | City Of Burlington | Various locations | Funding for capital for pedestrian improvements for fixed route services. |  | Alamance | 7 | Burlington-Graham MPO | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | CAPITAL | 240000 | FY 2026: 60000; FY 2027: 60000; FY 2028: 60000
TD-6322 | Public Transportation (Transit) | Capital (Non-STI) | City Of Burlington | Various locations | Funding for capital for pedestrian improvements for fixed route services. |  | Alamance | 7 | Burlington-Graham MPO | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | CAPITAL | 960000 | FY 2026: 240000; FY 2027: 240000; FY 2028: 240000
TE-4901 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Various locations | Construct fixed guideway. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 74308000 | FY 2026: 1995000; FY 2027: 1995000; FY 2028: 1995000
TE-4901 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Various locations | Construct fixed guideway. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 3900000 | FY 2026: 975000; FY 2027: 975000; FY 2028: 975000
TE-4901 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Various locations | Construct fixed guideway. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5309 | CONSTRUCTION | 34160000 | FY 2026: 8540000; FY 2027: 8540000; FY 2028: 8540000
TE-4902 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Various locations | Perform rapid transit corridor studies. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit
TG-0010 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Purchase battery electric buses and charging stations. Funding for onsite training and startup support and testing. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 7448000 | FY 2026: 1266000
TG-0010 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Purchase battery electric buses and charging stations. Funding for onsite training and startup support and testing. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | 5339 | CAPITAL | 7448000 | FY 2026: 1266000
TG-0011 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Various locations | Funding for bus stop improvement program. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 202000
TG-0011 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Various locations | Funding for bus stop improvement program. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | 5339 | CAPITAL | 1012000
TG-0012 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Various locations | Funding for routine capital, preventative maintenance, passenger amenities, and mobility management. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 175000 | FY 2026: 25000; FY 2027: 25000; FY 2028: 25000
TG-0012 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Various locations | Funding for routine capital, preventative maintenance, passenger amenities, and mobility management. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 700000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
TG-0013 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoRaleigh | Various locations | Funding for preventative maintenance. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 5340000 | FY 2026: 1710000
TG-0013 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoRaleigh | Various locations | Funding for preventative maintenance. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 21360000 | FY 2026: 6840000
TG-0014B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Various locations | Funding for capital projects. |  | Guilford, Alamance | 7 | Burlington-Graham MPO, High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 247000 | FY 2026: 41000; FY 2027: 41000; FY 2028: 41000
TG-0014B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Various locations | Funding for capital projects. |  | Guilford, Alamance | 7 | Burlington-Graham MPO, High Point Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 1001000 | FY 2026: 167000; FY 2027: 167000; FY 2028: 167000
TG-0015 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoRaleigh | Various locations | Funding for capital projects. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 8901000 | FY 2026: 4500000
TG-0019 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Various locations | Funding for routine capital including fareboxes, camera systems, APCs and delivery for asset transfer of used buses, depot ticket machine, realtime shelter signage, and bus shelters. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 659000 | FY 2026: 134000; FY 2027: 134000; FY 2028: 134000
TG-0019 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Various locations | Funding for routine capital including fareboxes, camera systems, APCs and delivery for asset transfer of used buses, depot ticket machine, realtime shelter signage, and bus shelters. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 2636000 | FY 2026: 536000; FY 2027: 536000; FY 2028: 536000
TG-0019 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Various locations | Funding for routine capital including fareboxes, camera systems, APCs and delivery for asset transfer of used buses, depot ticket machine, realtime shelter signage, and bus shelters. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5309 | CAPITAL | 0
TG-0020 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transit Authority | Various locations | Acquire or replace bus facilities capital improvements- acquire or replace equipment and systems in Wave transit operation and maintenance facility. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 48000
TG-0020 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transit Authority | Various locations | Acquire or replace bus facilities capital improvements- acquire or replace equipment and systems in Wave transit operation and maintenance facility. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5309 | CAPITAL | 191000
TG-0021 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Davidson County Transportation System | Various locations | Funding for routine maintenance for operations in Thomasville. |  | Davidson | 9 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 72000 | FY 2026: 12000; FY 2027: 12000; FY 2028: 12000
TG-0021 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Davidson County Transportation System | Various locations | Funding for routine maintenance for operations in Thomasville. |  | Davidson | 9 | High Point Urban Area MPO |  | Public Transit |  | 5317 | CAPITAL | 288000 | FY 2026: 48000; FY 2027: 48000; FY 2028: 48000
TG-0022 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Various locations | Renovate maintenance facility. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 300000
TG-0022 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Various locations | Renovate maintenance facility. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | 5339 | CONSTRUCTION | 1200000
TG-0023 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Purchase replacement buses. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 25000
TG-0023 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Purchase replacement buses. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5339 | CAPITAL | 100000
TG-0024 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Systemwide | Replace paratransit buses. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 275000 | FY 2026: 165000
TG-0024 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Systemwide | Replace paratransit buses. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1100000 | FY 2026: 660000
TG-0025 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Systemwide | Purchase new spare paratransit buses. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 55000
TG-0025 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Systemwide | Purchase new spare paratransit buses. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 220000
TG-0026 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transit Authority (WAVE) | Systemwide | Purchase CNG buses. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 572000
TG-0026 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transit Authority (WAVE) | Systemwide | Purchase CNG buses. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5339(b) | CAPITAL | 2860000
TG-0027 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoTriangle | Systemwide. | Construct 11 bus stops. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | CPF | ENGINEERING | 900000
TG-0027 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoTriangle | Systemwide. | Construct 11 bus stops. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 236000
TG-0028 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Chapel Hill Transit | Regionwide. | Expand facility. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | PLANNING | 18884000 | FY 2027: 2000000; FY 2028: 14500000
TG-0028 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Chapel Hill Transit | Regionwide. | Expand facility. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5339(b) | PLANNING | 2500000 | FY 2028: 500000
TG-0029 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoDurham | Systemwide. | Purchase 18 battery electric buses. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | CAPITAL | 6521000 | FY 2026: 6521000
TG-0029 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoDurham | Systemwide. | Purchase 18 battery electric buses. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5339(b) | CAPITAL | 14761000 | FY 2026: 14761000
TG-0030 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoDurham | Systemwide. | Purchase replacement light transit vehicles for godurham access. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | CAPITAL | 570000 | FY 2026: 146000; FY 2027: 140000; FY 2028: 133000
TG-0030 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoDurham | Systemwide. | Purchase replacement light transit vehicles for godurham access. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5339(b) | CAPITAL | 2156000 | FY 2026: 525000; FY 2027: 552000; FY 2028: 579000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engineers, farebox, etc. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1225000 | FY 2026: 735000; FY 2028: 234000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engineers, farebox, etc. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FMOD | CAPITAL | 575000 | FY 2026: 450000; FY 2028: 125000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engineers, farebox, etc. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 2300000 | FY 2026: 1800000; FY 2028: 500000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engineers, farebox, etc. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 2603000 | FY 2026: 1142000; FY 2028: 436000
TG-4729B | Public Transportation (Transit) | Operations and Maintenance | GoRaleigh | Systemwide | Funding for ADA paratransit service. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 16300000 | FY 2026: 6900000
TG-4729B | Public Transportation (Transit) | Operations and Maintenance | GoRaleigh | Systemwide | Funding for ADA paratransit service. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 16300000 | FY 2026: 6900000
TG-4731B | Public Transportation (Transit) | Operations and Maintenance | Chapel Hill Transit | Systemwide | Funding for preventative maintenance. |  | Orange | 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4076000 | FY 2026: 600000; FY 2027: 600000; FY 2028: 600000; FY 2029: 600000
TG-4731B | Public Transportation (Transit) | Operations and Maintenance | Chapel Hill Transit | Systemwide | Funding for preventative maintenance. |  | Orange | 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 16296000 | FY 2026: 2400000; FY 2027: 2400000; FY 2028: 2400000; FY 2029: 2400000
TG-4732A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Chapel Hill Transit | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Orange | 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 576000 | FY 2026: 90000; FY 2027: 90000; FY 2028: 90000
TG-4732A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Chapel Hill Transit | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Orange | 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 2304000 | FY 2026: 360000; FY 2027: 360000; FY 2028: 360000
TG-4738 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoDurham | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1119000 | FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
TG-4738 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoDurham | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4475000 | FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
TG-4738A | Public Transportation (Transit) | Operations and Maintenance | GoDurham | Systemwide | Funding for preventative maintenance. |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4500000 | FY 2026: 750000; FY 2027: 750000; FY 2028: 750000
TG-4738A | Public Transportation (Transit) | Operations and Maintenance | GoDurham | Systemwide | Funding for preventative maintenance. |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 18000000 | FY 2026: 3000000; FY 2027: 3000000; FY 2028: 3000000
TG-4752A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Transportation Authority of Goldsboro-Wayne | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 52000 | FY 2026: 7000; FY 2027: 7000; FY 2028: 7000
TG-4752A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Transportation Authority of Goldsboro-Wayne | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 208000 | FY 2026: 28000; FY 2027: 28000; FY 2028: 28000
TG-4752B | Public Transportation (Transit) | Operations and Maintenance | Transportation Authority of Goldsboro-Wayne | Systemwide | Funding for preventative maintenance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 440000 | FY 2026: 60000; FY 2027: 60000; FY 2028: 60000
TG-4752B | Public Transportation (Transit) | Operations and Maintenance | Transportation Authority of Goldsboro-Wayne | Systemwide | Funding for preventative maintenance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1764000 | FY 2026: 240000; FY 2027: 240000; FY 2028: 240000
TG-4752C | Public Transportation (Transit) | Operations and Maintenance | Transportation Authority of Goldsboro-Wayne | Systemwide | Funding for ADA paratransit service. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 325000 | FY 2026: 55000; FY 2027: 55000; FY 2028: 55000
TG-4752C | Public Transportation (Transit) | Operations and Maintenance | Transportation Authority of Goldsboro-Wayne | Systemwide | Funding for ADA paratransit service. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1300000 | FY 2026: 220000; FY 2027: 220000; FY 2028: 220000
TG-4759 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Systemwide | Funding for preventative maintenance. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 2328000 | FY 2026: 776000; FY 2027: 776000
TG-4759 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Systemwide | Funding for preventative maintenance. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 9309000 | FY 2026: 3103000; FY 2027: 3103000
TG-4767 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greenville Area Transit | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1080000 | FY 2026: 120000; FY 2027: 120000; FY 2028: 120000; FY 2029: 120000
TG-4767 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greenville Area Transit | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4329000 | FY 2026: 481000; FY 2027: 481000; FY 2028: 481000; FY 2029: 481000
TG-4774A | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for preventative maintenance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 120000
TG-4774A | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for preventative maintenance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 620000
TG-4785A | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Systemwide | Funding for ADA paratransit service. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 128000 | FY 2026: 16000; FY 2027: 16000
TG-4785A | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Systemwide | Funding for ADA paratransit service. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 592000 | FY 2026: 64000; FY 2027: 64000
TG-4785B | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Systemwide | Funding for preventative maintenance. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 640000 | FY 2026: 80000; FY 2027: 80000
TG-4785B | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Systemwide | Funding for preventative maintenance. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 2960000 | FY 2026: 320000; FY 2027: 320000
TG-4792B | Public Transportation (Transit) | Operations and Maintenance | GoRaleigh | Systemwide | Funding for ADA paratransit service. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 6289000
TG-4792B | Public Transportation (Transit) | Operations and Maintenance | GoRaleigh | Systemwide | Funding for ADA paratransit service. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 11938000
TG-4814 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Systemwide | Funding for routine capital - bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Guilford, Davidson, Randolph | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 860000 | FY 2026: 47000; FY 2027: 47000; FY 2028: 47000
TG-4814 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | High Point Transit System | Systemwide | Funding for routine capital - bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Guilford, Davidson, Randolph | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4270000 | FY 2026: 190000; FY 2027: 190000; FY 2028: 190000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoTriangle | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Wake, Durham, Orange | 5, 7 | Capital Area MPO, Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 4334000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoTriangle | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Wake, Durham, Orange | 5, 7 | Capital Area MPO, Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 19523000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GoTriangle | Systemwide | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles etc. |  | Wake, Durham, Orange | 5, 7 | Capital Area MPO, Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 6753000
TG-4827 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding to service vehicles. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | Cary Transit | Systemwide | Funding for contracting costs. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 10660000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | Cary Transit | Systemwide | Funding for contracting costs. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5309 | CAPITAL | 595000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | Cary Transit | Systemwide | Funding for contracting costs. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6700000
TG-4951 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for contracts. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 1401000 | FY 2026: 175000; FY 2027: 175000; FY 2028: 175000
TG-4951 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for contracts. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1040000 | FY 2026: 130000; FY 2027: 130000; FY 2028: 130000
TG-4951 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for contracts. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1400000 | FY 2026: 175000; FY 2027: 175000; FY 2028: 175000
TG-4952 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Systemwide | Funding for ADA paratransit service. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 152000 | FY 2026: 20000; FY 2027: 20000
TG-4952 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Systemwide | Funding for ADA paratransit service. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 609000 | FY 2026: 80000; FY 2027: 80000
TG-4957 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 829000 | FY 2026: 166000; FY 2027: 166000; FY 2028: 166000
TG-4957 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3310000 | FY 2026: 662000; FY 2027: 662000; FY 2028: 662000
TG-4971 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Systemwide | Fund operating expenses for Greensboro Transit Authority fixed routes. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 11215000 | FY 2026: 2243000; FY 2027: 2243000; FY 2028: 2243000
TG-4971 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Systemwide | Fund operating expenses for Greensboro Transit Authority fixed routes. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 11215000 | FY 2026: 2243000; FY 2027: 2243000; FY 2028: 2243000
TG-5103A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Concord Kannapolis Area Transit | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1000000
TG-5103A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Concord Kannapolis Area Transit | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6243000
TG-5103B | Public Transportation (Transit) | Operations and Maintenance | Concord Kannapolis Area Transit | Systemwide | Funding for ADA services. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 544000
TG-5103B | Public Transportation (Transit) | Operations and Maintenance | Concord Kannapolis Area Transit | Systemwide | Funding for ADA services. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 2902000
TG-5103C | Public Transportation (Transit) | Operations and Maintenance | Concord Kannapolis Area Transit | Systemwide | Funding for preventative maintenance. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2350000
TG-5103C | Public Transportation (Transit) | Operations and Maintenance | Concord Kannapolis Area Transit | Systemwide | Funding for preventative maintenance. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 12625000
TG-5105 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Systemwide | Funding for routine capital. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 224000 | FY 2026: 56000; FY 2027: 56000; FY 2028: 56000
TG-5105 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Greensboro Transit Authority | Systemwide | Funding for routine capital. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 900000 | FY 2026: 225000; FY 2027: 225000; FY 2028: 225000
TG-5107B | Public Transportation (Transit) | Operations and Maintenance | Greenville Area Transit | Systemwide | Funding for preventative maintenance. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1215000 | FY 2026: 135000; FY 2027: 135000; FY 2028: 135000; FY 2029: 135000
TG-5107B | Public Transportation (Transit) | Operations and Maintenance | Greenville Area Transit | Systemwide | Funding for preventative maintenance. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 4860000 | FY 2026: 540000; FY 2027: 540000; FY 2028: 540000; FY 2029: 540000
TG-5107C | Public Transportation (Transit) | Operations and Maintenance | Greenville Area Transit | Systemwide | Funding for ADA paratransit service. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 270000 | FY 2026: 30000; FY 2027: 30000; FY 2028: 30000; FY 2029: 30000
TG-5107C | Public Transportation (Transit) | Operations and Maintenance | Greenville Area Transit | Systemwide | Funding for ADA paratransit service. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1080000 | FY 2026: 120000; FY 2027: 120000; FY 2028: 120000; FY 2029: 120000
TG-5109 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Systemwide | Funding for preventive maintenance along fixed route. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 416000 | FY 2026: 55000; FY 2027: 55000
TG-5109 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Systemwide | Funding for preventive maintenance along fixed route. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1660000 | FY 2026: 219000; FY 2027: 219000
TG-5118A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for state of good repair - rail. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 3493000 | FY 2026: 702000; FY 2027: 723000 | 1697000
TG-5118A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for state of good repair - rail. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 4484000 | FY 2026: 727000; FY 2027: 200000; FY 2028: 128000 | 1697000
TG-5118A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for state of good repair - rail. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 18338000 | FY 2026: 2908000; FY 2027: 800000; FY 2028: 510000 | 7194000
TG-5118B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for light rail vehicle overhaul. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 11799000 | FY 2026: 4026000; FY 2027: 2714000; FY 2028: 2123000
TG-5118B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for light rail vehicle overhaul. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 45196000 | FY 2026: 14104000; FY 2027: 10857000; FY 2028: 8493000
TG-5118B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for light rail vehicle overhaul. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 2000000 | FY 2026: 2000000
TG-5119 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for preventative maintenance for rail, bus, and facilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 2043000 | FY 2026: 932000; FY 2027: 871000
TG-5119 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for preventative maintenance for rail, bus, and facilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 8168000 | FY 2026: 3726000; FY 2027: 3482000
TG-5126 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem transit | Various locations | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 4642000 | FY 2026: 1214000; FY 2027: 1214000
TG-5126 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem transit | Various locations | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 4642000 | FY 2026: 1214000; FY 2027: 1214000
TG-5220 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for Jacksonville Transit mobility management. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | CAPITAL | 32000 | FY 2026: 4000; FY 2027: 4000
TG-5220 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for Jacksonville Transit mobility management. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 32000 | FY 2026: 4000; FY 2027: 4000
TG-5220 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for Jacksonville Transit mobility management. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 247000 | FY 2026: 32000; FY 2027: 32000
TG-5224A | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for preventive maintenance along fixed route. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 3600000 | FY 2026: 400000; FY 2027: 400000; FY 2028: 400000; FY 2029: 400000; FY 2030: 400000
TG-5224A | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for preventive maintenance along fixed route. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 14400000 | FY 2026: 1600000; FY 2027: 1600000; FY 2028: 1600000; FY 2029: 1600000; FY 2030: 1600000
TG-5224C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for routine capital. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 420000 | FY 2026: 42000; FY 2027: 42000; FY 2028: 42000; FY 2029: 42000; FY 2030: 42000
TG-5224C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for routine capital. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1680000 | FY 2026: 168000; FY 2027: 168000; FY 2028: 168000; FY 2029: 168000; FY 2030: 168000
TG-5224D | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for support vehicle. |  | Cumberland | 6 | Fayetteville Area MPO |  | Public Transit |  | L | CAPITAL | 144000 | FY 2027: 20000; FY 2028: 20000; FY 2029: 20000; FY 2030: 20000
TG-5224D | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for support vehicle. |  | Cumberland | 6 | Fayetteville Area MPO |  | Public Transit |  | 5307 | CAPITAL | 576000 | FY 2027: 80000; FY 2028: 80000; FY 2029: 80000; FY 2030: 80000
TG-5224E | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for ADA services. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 571000 | FY 2026: 83000; FY 2027: 83000; FY 2028: 83000; FY 2029: 83000; FY 2030: 83000
TG-5224E | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for ADA services. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 2270000 | FY 2026: 330000; FY 2027: 330000; FY 2028: 330000; FY 2029: 330000; FY 2030: 330000
TG-5225 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 30000 | FY 2026: 4000; FY 2027: 4000
TG-5225 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for routine capital including bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 119000 | FY 2026: 16000; FY 2027: 16000
TG-5225C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for mobility management. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 130000 | FY 2026: 17000; FY 2027: 17000
TG-5225C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Jacksonville Transit | Various locations | Funding for mobility management. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 523000 | FY 2026: 69000; FY 2027: 69000
TG-5232 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Salisbury | Various locations | Funding for preventive maintenance on buses and facilities. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 996000 | FY 2026: 83000; FY 2027: 83000
TG-5232 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Salisbury | Various locations | Funding for preventive maintenance on buses and facilities. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4008000 | FY 2026: 334000; FY 2027: 334000
TG-5233 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City Of Salisbury | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 224000 | FY 2026: 36000; FY 2027: 36000; FY 2028: 36000
TG-5233 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City Of Salisbury | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, etc. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 896000 | FY 2026: 144000; FY 2027: 144000; FY 2028: 144000
TG-5241 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Winston Salem Transit | Various locations | Funding for preventative maintenance. |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 2605000 | FY 2026: 585000; FY 2027: 585000
TG-5241 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Winston Salem Transit | Various locations | Funding for preventative maintenance. |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 10411000 | FY 2026: 2337000; FY 2027: 2337000
TG-5245 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transportation Authority (WAVE) | Various locations | Funding for preventative maintenance. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 493000
TG-5245 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transportation Authority (WAVE) | Various locations | Funding for preventative maintenance. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1971000
TG-5246 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transportation Authority (WAVE) | Various locations | Funding for the continuation of complimentary para transit service to two counties and four municipalities with in UAZ. |  | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 216000
TG-5246 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cape Fear Public Transportation Authority (WAVE) | Various locations | Funding for the continuation of complimentary para transit service to two counties and four municipalities with in UAZ. |  | Brunswick, New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 877000
TG-5257 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Transportation system Craven Area Rural | Various locations | Funding for ADA paratransit service. |  | Craven | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 65000 | FY 2026: 3000
TG-5257 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Transportation system Craven Area Rural | Various locations | Funding for ADA paratransit service. |  | Craven | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 248000 | FY 2026: 10000
TG-5260 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Salisbury | Various locations | Funding for ADA services. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 144000 | FY 2026: 18000; FY 2027: 18000
TG-5260 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Salisbury | Various locations | Funding for ADA services. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 560000 | FY 2026: 70000; FY 2027: 70000
TG-6137B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Regional Transport Authority | Systemwide | Funding for routine capital, passenger amenities, parts, equipment, preventive maintenance, and capital cost of contracting. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 150000
TG-6137B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Regional Transport Authority | Systemwide | Funding for routine capital, passenger amenities, parts, equipment, preventive maintenance, and capital cost of contracting. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 600000
TG-6143 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, and service new technology for system with Cares 2021 funding. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 172000
TG-6143 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, and service new technology for system with Cares 2021 funding. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 686000
TG-6173B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority | Various locations | Funding for routine capital, preventive maintenance, security and passenger amenities. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 168000 | FY 2026: 28000; FY 2027: 28000; FY 2028: 28000
TG-6173B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority | Various locations | Funding for routine capital, preventive maintenance, security and passenger amenities. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 690000 | FY 2026: 115000; FY 2027: 115000; FY 2028: 115000
TG-6179 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Salisbury | Systemwide | Funding for AVL system. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 280000
TG-6179 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Salisbury | Systemwide | Funding for AVL system. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 1120000
TG-6181 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Apple Country Transit | Systemwide | Funding for contracts. |  | Henderson | 14 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 3220000 | FY 2026: 557000
TG-6181 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Apple Country Transit | Systemwide | Funding for contracts. |  | Henderson | 14 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 2406000 | FY 2026: 262000
TG-6183A | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 250000
TG-6183A | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 1000000
TG-6183B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Systemwide | Funding for preventative maintenance. |  | Buncombe | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 2318000 | FY 2026: 392000
TG-6183B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Systemwide | Funding for preventative maintenance. |  | Buncombe | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 9534000 | FY 2026: 1750000
TG-6184B | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for preventative maintenance. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 85000
TG-6184B | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for preventative maintenance. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 342000
TG-6185 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Systemwide | Funding for routine capital. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 215000 | FY 2026: 43000; FY 2027: 43000; FY 2028: 43000
TG-6185 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Systemwide | Funding for routine capital. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 852000 | FY 2026: 170000; FY 2027: 170000; FY 2028: 170000
TG-6783 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Various locations | Funding for routine capital including passenger shelters, passenger amenities, shop equipment, and spare parts. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 222000 | FY 2026: 35000; FY 2027: 37000
TG-6783 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Piedmont Authority For Regional Transportation | Various locations | Funding for routine capital including passenger shelters, passenger amenities, shop equipment, and spare parts. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 889000 | FY 2026: 140000; FY 2027: 147000
TG-6786 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Buncombe County - Mountain Mobility | Systemwide | Funding for contracts. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 718000
TG-6786 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Buncombe County - Mountain Mobility | Systemwide | Funding for contracts. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 1209000
TG-6788 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Haywood County mountain projects | Funding for deviated fixed route capital and CARES funds. |  | Haywood | 14 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 289000 | FY 2026: 41000; FY 2027: 41000; FY 2028: 41000
TG-6788 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | City of Asheville Transit | Haywood County mountain projects | Funding for deviated fixed route capital and CARES funds. |  | Haywood | 14 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 1193000 | FY 2026: 163000; FY 2027: 163000; FY 2028: 163000
TG-6789 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cabarrus County Transit | Various locations | Funding for capital for Cabarrus County through the City of Concord. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | L | CAPITAL | 376000 | FY 2026: 52000; FY 2027: 54000
TG-6789 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Cabarrus County Transit | Various locations | Funding for capital for Cabarrus County through the City of Concord. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | 5307 | CAPITAL | 1880000 | FY 2026: 260000; FY 2027: 270000
TG-6792 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Gastonia Transit Authority | Various locations | Improve pedestrian walkways. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | CONSTRUCTION | 92000
TG-6792 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Gastonia Transit Authority | Various locations | Improve pedestrian walkways. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | CONSTRUCTION | 366000
TG-6798 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for mobility manager. |  | Catawba | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 195000
TG-6798 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for mobility manager. |  | Catawba | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 775000
TG-6800 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, computer hardware and software, AVL software, etc. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 288000 | FY 2026: 96000
TG-6800 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for bus stop shelters, benches, shop equipment, spare parts, engines, farebox, service vehicles, computer hardware and software, AVL software, etc. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | CAPITAL | 1152000 | FY 2026: 384000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | PLANNING | 150000 | FY 2026: 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | PLANNING | 600000 | FY 2026: 200000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 150000 | FY 2026: 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 600000 | FY 2026: 200000
TG-6802 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | OPERATIONS | 60000
TG-6802 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for ADA paratransit service. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | OPERATIONS | 240000
TG-6804 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for transit app. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 13000
TG-6804 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for transit app. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 50000
TG-6811B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Alamance County Transportation Authority | Systemwide | Funding for preventative maintenance. |  | Alamance, Guilford, Orange | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 50000 | FY 2026: 10000; FY 2027: 10000; FY 2028: 10000
TG-6811B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | Alamance County Transportation Authority | Systemwide | Funding for preventative maintenance. |  | Alamance, Guilford, Orange | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 200000 | FY 2026: 40000; FY 2027: 40000; FY 2028: 40000
TG-6812A | Public Transportation (Transit) | Operations and Maintenance | Burlington | Systemwide | Funding for ADA services. |  | Alamance | 7 | Burlington-Graham MPO | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | OPERATIONS | 272000 | FY 2026: 68000; FY 2027: 68000; FY 2028: 68000
TG-6812A | Public Transportation (Transit) | Operations and Maintenance | Burlington | Systemwide | Funding for ADA services. |  | Alamance | 7 | Burlington-Graham MPO | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | OPERATIONS | 1088000 | FY 2026: 272000; FY 2027: 272000; FY 2028: 272000
TG-6815 | Public Transportation (Transit) | Locally Selected | GoTriangle | Systemwide | Purchase and install new amenities at 13 bus stop locations along routes in Wake County. Upgrades include shelters, bench, or some combinations. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CAPITAL | 259000
TG-6815 | Public Transportation (Transit) | Locally Selected | GoTriangle | Systemwide | Purchase and install new amenities at 13 bus stop locations along routes in Wake County. Upgrades include shelters, bench, or some combinations. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CAPITAL | 830000 | FY 2026: 91000
TG-6815 | Public Transportation (Transit) | Locally Selected | GoTriangle | Systemwide | Purchase and install new amenities at 13 bus stop locations along routes in Wake County. Upgrades include shelters, bench, or some combinations. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5307 | CAPITAL | 726000 | FY 2026: 363000
TG-6816 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations | Develop enhanced transfer points throughout Go Raleigh system in location with high ridership (75 + Boarding per day). |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CAPITAL | 1736000 | FY 2026: 474000
TG-6816 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Various locations | Develop enhanced transfer points throughout Go Raleigh system in location with high ridership (75 + Boarding per day). |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CAPITAL | 635000 | FY 2026: 119000
TI-6109 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Statewide | 5311(F) Intercity bus funds for FTA grants. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | OPERATIONS | 2698000
TK-4900Z | Public Transportation (Transit) | Operations and Maintenance | Statewide | Statewide | Funding for 5311 State administration. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | ADMINISTRATIVE | 3080000
TK-4902 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Statewide | Funding for state administration of Appalachian Development Transportation Assistance Program. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | ADTAP | ADMINISTRATIVE | 235000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for agency administration. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 53000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for agency administration. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 159000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for agency administration. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1658000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | Apple Country Transit | Systemwide | Funding for agency administration. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 270000
TK-5180 | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Various locations | Administration. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 59000 | FY 2026: 4000; FY 2027: 4000; FY 2028: 7000
TK-5180 | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Various locations | Administration. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 175000 | FY 2026: 13000; FY 2027: 13000; FY 2028: 20000
TK-5180 | Public Transportation (Transit) | Operations and Maintenance | Tar River Transit | Various locations | Administration. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 936000 | FY 2026: 68000; FY 2027: 68000; FY 2028: 108000
TK-6105 | Public Transportation (Transit) | Operations and Maintenance | Alleghany County Transit | Systemwide | Funding for agency administration. |  | Alleghany | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 64000
TK-6105 | Public Transportation (Transit) | Operations and Maintenance | Alleghany County Transit | Systemwide | Funding for agency administration. |  | Alleghany | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 184000
TK-6105 | Public Transportation (Transit) | Operations and Maintenance | Alleghany County Transit | Systemwide | Funding for agency administration. |  | Alleghany | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1914000
TK-6106 | Public Transportation (Transit) | Operations and Maintenance | Anson County Transit | Systemwide | Funding for agency administration. |  | Anson | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 80000
TK-6106 | Public Transportation (Transit) | Operations and Maintenance | Anson County Transit | Systemwide | Funding for agency administration. |  | Anson | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 248000
TK-6106 | Public Transportation (Transit) | Operations and Maintenance | Anson County Transit | Systemwide | Funding for agency administration. |  | Anson | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2539000
TK-6107 | Public Transportation (Transit) | Operations and Maintenance | Appalcart | Systemwide | Funding for agency administration. |  | Watauga | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 184000
TK-6107 | Public Transportation (Transit) | Operations and Maintenance | Appalcart | Systemwide | Funding for agency administration. |  | Watauga | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 560000
TK-6107 | Public Transportation (Transit) | Operations and Maintenance | Appalcart | Systemwide | Funding for agency administration. |  | Watauga | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 5814000
TK-6108 | Public Transportation (Transit) | Operations and Maintenance | Ashe County Transportation | Systemwide | Funding for agency administration. |  | Ashe | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 80000
TK-6108 | Public Transportation (Transit) | Operations and Maintenance | Ashe County Transportation | Systemwide | Funding for agency administration. |  | Ashe | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 232000
TK-6108 | Public Transportation (Transit) | Operations and Maintenance | Ashe County Transportation | Systemwide | Funding for agency administration. |  | Ashe | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2426000
TK-6118 | Public Transportation (Transit) | Operations and Maintenance | Cherokee County Transit | Systemwide | Funding for agency administration. |  | Cherokee | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6118 | Public Transportation (Transit) | Operations and Maintenance | Cherokee County Transit | Systemwide | Funding for agency administration. |  | Cherokee | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 216000
TK-6118 | Public Transportation (Transit) | Operations and Maintenance | Cherokee County Transit | Systemwide | Funding for agency administration. |  | Cherokee | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2217000
TK-6120 | Public Transportation (Transit) | Operations and Maintenance | Clay County Transit | Systemwide | Funding for agency administration. |  | Clay | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 73000
TK-6120 | Public Transportation (Transit) | Operations and Maintenance | Clay County Transit | Systemwide | Funding for agency administration. |  | Clay | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 213000
TK-6120 | Public Transportation (Transit) | Operations and Maintenance | Clay County Transit | Systemwide | Funding for agency administration. |  | Clay | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2211000
TK-6127 | Public Transportation (Transit) | Operations and Maintenance | Eastern Band Of Cherokee Indians | Systemwide | Funding for agency administration. |  | Cherokee, Graham, Jackson, Swain | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 136000 | FY 2026: 17000; FY 2027: 17000; FY 2028: 17000
TK-6127 | Public Transportation (Transit) | Operations and Maintenance | Eastern Band Of Cherokee Indians | Systemwide | Funding for agency administration. |  | Cherokee, Graham, Jackson, Swain | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 48000 | FY 2026: 6000; FY 2027: 6000; FY 2028: 6000
TK-6127 | Public Transportation (Transit) | Operations and Maintenance | Eastern Band Of Cherokee Indians | Systemwide | Funding for agency administration. |  | Cherokee, Graham, Jackson, Swain | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 744000 | FY 2026: 93000; FY 2027: 93000; FY 2028: 93000
TK-6137 | Public Transportation (Transit) | Operations and Maintenance | Jackson County Transit | Systemwide | Funding for agency administration. |  | Jackson | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6137 | Public Transportation (Transit) | Operations and Maintenance | Jackson County Transit | Systemwide | Funding for agency administration. |  | Jackson | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 224000
TK-6137 | Public Transportation (Transit) | Operations and Maintenance | Jackson County Transit | Systemwide | Funding for agency administration. |  | Jackson | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2336000
TK-6141 | Public Transportation (Transit) | Operations and Maintenance | Lincoln County Transit | Systemwide | Funding for agency administration. |  | Lincoln | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 263000
TK-6141 | Public Transportation (Transit) | Operations and Maintenance | Lincoln County Transit | Systemwide | Funding for agency administration. |  | Lincoln | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 275000
TK-6141 | Public Transportation (Transit) | Operations and Maintenance | Lincoln County Transit | Systemwide | Funding for agency administration. |  | Lincoln | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2523000
TK-6142 | Public Transportation (Transit) | Operations and Maintenance | Macon County Transit | Systemwide | Funding for agency administration. |  | Macon | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 79000
TK-6142 | Public Transportation (Transit) | Operations and Maintenance | Macon County Transit | Systemwide | Funding for agency administration. |  | Macon | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 231000
TK-6142 | Public Transportation (Transit) | Operations and Maintenance | Macon County Transit | Systemwide | Funding for agency administration. |  | Macon | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2503000
TK-6143 | Public Transportation (Transit) | Operations and Maintenance | Madison County Transportation | Systemwide | Funding for agency administration. |  | Madison | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 56000
TK-6143 | Public Transportation (Transit) | Operations and Maintenance | Madison County Transportation | Systemwide | Funding for agency administration. |  | Madison | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 160000
TK-6143 | Public Transportation (Transit) | Operations and Maintenance | Madison County Transportation | Systemwide | Funding for agency administration. |  | Madison | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1691000
TK-6146 | Public Transportation (Transit) | Operations and Maintenance | Mecklenburg Transportation | Systemwide | Funding for agency administration. |  | Mitchell | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6146 | Public Transportation (Transit) | Operations and Maintenance | Mecklenburg Transportation | Systemwide | Funding for agency administration. |  | Mitchell | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 216000
TK-6146 | Public Transportation (Transit) | Operations and Maintenance | Mecklenburg Transportation | Systemwide | Funding for agency administration. |  | Mitchell | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2257000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | Person County Transit | Systemwide | Funding for agency administration. |  | Person | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 66000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | Person County Transit | Systemwide | Funding for agency administration. |  | Person | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 204000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | Person County Transit | Systemwide | Funding for agency administration. |  | Person | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1822000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | Person County Transit | Systemwide | Funding for agency administration. |  | Person | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 151000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | Polk County Transportation | Systemwide | Funding for agency administration. |  | Polk | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 73000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | Polk County Transportation | Systemwide | Funding for agency administration. |  | Polk | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 227000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | Polk County Transportation | Systemwide | Funding for agency administration. |  | Polk | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2035000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | Polk County Transportation | Systemwide | Funding for agency administration. |  | Polk | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 368000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | Rutherford County Transit | Systemwide | Funding for agency administration. |  | Rutherford | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 80000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | Rutherford County Transit | Systemwide | Funding for agency administration. |  | Rutherford | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 232000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | Rutherford County Transit | Systemwide | Funding for agency administration. |  | Rutherford | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2049000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | Rutherford County Transit | Systemwide | Funding for agency administration. |  | Rutherford | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 392000
TK-6165 | Public Transportation (Transit) | Operations and Maintenance | Swain County Focal Point On Aging, Inc. | Systemwide | Funding for agency administration. |  | Swain | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 132000
TK-6165 | Public Transportation (Transit) | Operations and Maintenance | Swain County Focal Point On Aging, Inc. | Systemwide | Funding for agency administration. |  | Swain | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 101000
TK-6165 | Public Transportation (Transit) | Operations and Maintenance | Swain County Focal Point On Aging, Inc. | Systemwide | Funding for agency administration. |  | Swain | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1659000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | Transportation Administration of Cleveland County | Systemwide | Funding for agency administration. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 120000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | Transportation Administration of Cleveland County | Systemwide | Funding for agency administration. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 360000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | Transportation Administration of Cleveland County | Systemwide | Funding for agency administration. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3108000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | Transportation Administration of Cleveland County | Systemwide | Funding for agency administration. |  | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 577000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | Transylvania County Transit | Systemwide | Funding for agency administration. |  | Transylvania | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 54000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | Transylvania County Transit | Systemwide | Funding for agency administration. |  | Transylvania | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 126000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | Transylvania County Transit | Systemwide | Funding for agency administration. |  | Transylvania | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1820000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | Transylvania County Transit | Systemwide | Funding for agency administration. |  | Transylvania | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 341000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | Wilkes Transportation Authority | Systemwide | Funding for agency administration. |  | Wilkes | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 88000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | Wilkes Transportation Authority | Systemwide | Funding for agency administration. |  | Wilkes | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 272000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | Wilkes Transportation Authority | Systemwide | Funding for agency administration. |  | Wilkes | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2376000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | Wilkes Transportation Authority | Systemwide | Funding for agency administration. |  | Wilkes | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 456000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | Yadkin Valley Economic Development District | Systemwide | Funding for agency administration. |  | Davie, Stokes, Surry, Yadkin | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 168000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | Yadkin Valley Economic Development District | Systemwide | Funding for agency administration. |  | Davie, Stokes, Surry, Yadkin | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 512000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | Yadkin Valley Economic Development District | Systemwide | Funding for agency administration. |  | Davie, Stokes, Surry, Yadkin | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 4432000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | Yadkin Valley Economic Development District | Systemwide | Funding for agency administration. |  | Davie, Stokes, Surry, Yadkin | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 890000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | Yancey County Transportation Authority | Systemwide | Funding for agency administration. |  | Yancey | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 56000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | Yancey County Transportation Authority | Systemwide | Funding for agency administration. |  | Yancey | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 176000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | Yancey County Transportation Authority | Systemwide | Funding for agency administration. |  | Yancey | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1508000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | Yancey County Transportation Authority | Systemwide | Funding for agency administration. |  | Yancey | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 290000
TK-6179 | Public Transportation (Transit) | Operations and Maintenance | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for agency administration. |  | Iredell | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1040000
TL-0001 | Public Transportation (Transit) | Capital (Non-STI) | Jacksonville Transit | Various locations | Construct An Urban Fixed-Route Satellite Transfer Facility For Jacksonville Transit To Include Public Parking, Shelters, Restroom And Passenger Terminal. |  | Onslow | 3 | Jacksonville Urban Area MPO | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CONSTRUCTION | 8000000 | FY 2027: 3500000; FY 2028: 3500000
TL-0002 | Public Transportation (Transit) | Capital (Non-STI) | Jacksonville Transit | Various locations | Retrofitting of Existing Side Walk and Constructing New Side Walk. |  | Onslow | 3 | Jacksonville Urban Area MPO | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CONSTRUCTION | 1230000
TL-0006 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Project development and final design of bus rapid transit in Wake Transit Western corridor (Downtown Raleigh to Downtown Cary). |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 1500000
TL-0006 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Project development and final design of bus rapid transit in Wake Transit Western corridor (Downtown Raleigh to Downtown Cary). |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 45168000
TL-0007 | Public Transportation (Transit) | Planning | GoRaleigh | Systemwide | Project development and final design on bus rapid transit in Wake transit plan Northern corridor. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 15540000 | FY 2026: 5000000
TL-0009 | Public Transportation (Transit) | Capital (Non-STI) | Greenville Area Transit | Various locations | Fleet Service Building Expansion. |  | Pitt | 2 | Greenville Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 183000
TL-0009 | Public Transportation (Transit) | Capital (Non-STI) | Greenville Area Transit | Various locations | Fleet Service Building Expansion. |  | Pitt | 2 | Greenville Urban Area MPO |  | Public Transit |  | CARES | CONSTRUCTION | 1643000
TL-0011 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Construct downtown Apex transfer points. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 32000
TL-0011 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Construct downtown Apex transfer points. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | ENGINEERING | 32000
TL-0011 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Construct downtown Apex transfer points. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | RIGHT-OF-WAY | 9000 | FY 2026: 9000
TL-0011 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Construct downtown Apex transfer points. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | RIGHT-OF-WAY | 9000 | FY 2026: 9000
TL-0011 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Construct downtown Apex transfer points. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 121000 | FY 2026: 121000
TL-0011 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Construct downtown Apex transfer points. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 121000 | FY 2026: 121000
TL-0013 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Project development and final design of bus rapid transit in Wake transit Southern corridor ( Downtown Raleigh to Downtown Garner). |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 1500000
TL-0013 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Project development and final design of bus rapid transit in Wake transit Southern corridor ( Downtown Raleigh to Downtown Garner). |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 40947000 | FY 2026: 8670000
TL-0014 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Systemwide | Installing covered bus shelters with ADA access to major stops such as Walmart and Big lots. Install Simme seats at the remainder of bus stops. Simme seats provide two seats attached to the bus stip sign pole. |  | Davidson | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 112000
TL-0014 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Systemwide | Installing covered bus shelters with ADA access to major stops such as Walmart and Big lots. Install Simme seats at the remainder of bus stops. Simme seats provide two seats attached to the bus stip sign pole. |  | Davidson | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CAPITAL | 28000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Access improvements at the intersection of US 15 -501 and Eastowne drive. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | CMAQ | PLANNING | 80000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Access improvements at the intersection of US 15 -501 and Eastowne drive. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | PLANNING | 20000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Access improvements at the intersection of US 15 -501 and Eastowne drive. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | CMAQ | CONSTRUCTION | 400000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Access improvements at the intersection of US 15 -501 and Eastowne drive. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | CONSTRUCTION | 100000
TL-0020 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Systemwide | Raleigh Union station bus facility inter city/commuter rail park and ride. |  | Wake | 5 | Capital Area MPO | S(M) REPRESENTS STATE RAIL FUNDS. | Public Transit |  | CMAQ | OPERATIONS | 5000000
TL-0020 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Systemwide | Raleigh Union station bus facility inter city/commuter rail park and ride. |  | Wake | 5 | Capital Area MPO | S(M) REPRESENTS STATE RAIL FUNDS. | Public Transit |  | L(M) | OPERATIONS | 624000
TL-0020 | Public Transportation (Transit) | Locally Selected | GoRaleigh | Systemwide | Raleigh Union station bus facility inter city/commuter rail park and ride. |  | Wake | 5 | Capital Area MPO | S(M) REPRESENTS STATE RAIL FUNDS. | Public Transit |  | S(M) | OPERATIONS | 626000
TL-0023 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Build park and ride facility at Gorman street at I-40 in Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 1432000
TL-0023 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | Build park and ride facility at Gorman street at I-40 in Raleigh. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 1614000 | FY 2027: 1614000
TL-0025 | Public Transportation (Transit) | Locally Selected | Winston Salem Transit Authority | Various locations | Improve paratransit tracking and accessibility through GPS and notification services, as well as provide mobile ticketing options for Winston-Salem area transportation planning organization (WSATPO) fixed route bus services by using ICAM (Innovative coor |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 140000
TL-0025 | Public Transportation (Transit) | Locally Selected | Winston Salem Transit Authority | Various locations | Improve paratransit tracking and accessibility through GPS and notification services, as well as provide mobile ticketing options for Winston-Salem area transportation planning organization (WSATPO) fixed route bus services by using ICAM (Innovative coor |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 560000
TL-0027 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | The NC 54 Falconbridge construction project aims to address critical transit access and transit operations safety concerns along NC 54 in the Falconbridge area in Southwestern Durham County, thereby increasing transit ridership and reducing emissions. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | CMAQ | CONSTRUCTION | 903000
TL-0027 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | The NC 54 Falconbridge construction project aims to address critical transit access and transit operations safety concerns along NC 54 in the Falconbridge area in Southwestern Durham County, thereby increasing transit ridership and reducing emissions. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L(M) | CONSTRUCTION | 226000
TL-0029 | Public Transportation (Transit) | Locally Selected | Link Transit | Various locations | Capital improvements for transit vehicles. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 295000 | FY 2026: 45000; FY 2027: 45000; FY 2028: 45000
TL-0029 | Public Transportation (Transit) | Locally Selected | Link Transit | Various locations | Capital improvements for transit vehicles. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 1255000 | FY 2026: 185000; FY 2027: 185000; FY 2028: 185000
TL-0031 | Public Transportation (Transit) | Locally Selected | Union County Transportation | Union County Transportation motor pool facility | Implement low emission alternative fuel conversion. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 160000
TL-0031 | Public Transportation (Transit) | Locally Selected | Union County Transportation | Union County Transportation motor pool facility | Implement low emission alternative fuel conversion. |  | Union | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 40000
TL-0032 | Public Transportation (Transit) | Locally Selected | Charlotte Area Transit System (CATS) | North Davidson and South Tryon bus garages | Install electric bus chargers. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 160000
TL-0032 | Public Transportation (Transit) | Locally Selected | Charlotte Area Transit System (CATS) | North Davidson and South Tryon bus garages | Install electric bus chargers. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 40000
TL-0033 | Public Transportation (Transit) | Locally Selected | Integrated Mobility Division | Various locations | Funding for City of Wilson Ride Microtransit Expansion. |  | Wilson | 4 | Upper Coastal Plain RPO |  | Public Transit |  | CPF | CAPITAL | 4000000 | FY 2026: 2000000
TL-0033 | Public Transportation (Transit) | Locally Selected | Integrated Mobility Division | Various locations | Funding for City of Wilson Ride Microtransit Expansion. |  | Wilson | 4 | Upper Coastal Plain RPO |  | Public Transit |  | L | CAPITAL | 1000000 | FY 2026: 500000
TL-0034 | Public Transportation (Transit) | Locally Selected | Chapel hill Transit | Systemwide | Funding to acquire five new transit electric vehicles |  | Orange | 7 | Triangle West TPO |  | Exempt |  | CMAQ | CAPITAL | 2040000
TL-0034 | Public Transportation (Transit) | Locally Selected | Chapel hill Transit | Systemwide | Funding to acquire five new transit electric vehicles |  | Orange | 7 | Triangle West TPO |  | Exempt |  | L(M) | CAPITAL | 668000
TL-0035 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Southern Village park and ride lot to Eubanks Road park and ride lot. | Construct North-South Bus Rapid Transit (NSBRT) system. | 8.2 | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | ENGINEERING | 2737000
TL-0035 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Southern Village park and ride lot to Eubanks Road park and ride lot. | Construct North-South Bus Rapid Transit (NSBRT) system. | 8.2 | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5307 | ENGINEERING | 8000000
TL-0035 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Southern Village park and ride lot to Eubanks Road park and ride lot. | Construct North-South Bus Rapid Transit (NSBRT) system. | 8.2 | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | CONSTRUCTION | 38744000 | FY 2027: 38744000
TL-0035 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Southern Village park and ride lot to Eubanks Road park and ride lot. | Construct North-South Bus Rapid Transit (NSBRT) system. | 8.2 | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5307 | CONSTRUCTION | 162804000 | FY 2027: 162804000
TL-0046 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 12000
TL-0046 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5307 | ENGINEERING | 48000
TL-0046 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 3000 | FY 2026: 3000
TL-0046 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5307 | RIGHT-OF-WAY | 12000 | FY 2026: 12000
TL-0046 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 50000 | FY 2026: 50000
TL-0046 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Add a waiting pad and landing pad at 5 stops on the 305. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5307 | CONSTRUCTION | 200000 | FY 2026: 200000
TL-0048 | Public Transportation (Transit) | Locally Selected | Greensboro Transit Authority | Systemwide | Route 15 new service. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 2900000
TL-0048 | Public Transportation (Transit) | Locally Selected | Greensboro Transit Authority | Systemwide | Route 15 new service. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 724000
TL-0049 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Various locations | Purchase 2 ADA accessible mini vans. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 150000
TL-0049 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Various locations | Purchase 2 ADA accessible mini vans. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | L | IMPLEMENTATION | 37000
TL-0050 | Public Transportation (Transit) | Locally Selected | Greensboro Transit Authority | Various locations | New crosstown new route. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 5905000
TL-0050 | Public Transportation (Transit) | Locally Selected | Greensboro Transit Authority | Various locations | New crosstown new route. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 1775000
TL-0051 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve three bus stops in Orange county at sites 701, 705, and 706. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L(M) | CONSTRUCTION | 50000
TL-0051 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve three bus stops in Orange county at sites 701, 705, and 706. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5307 | CONSTRUCTION | 200000
TL-0052 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | This transit project will improve 13 stops on the Go triangle 805 coridor on Woodcroft parkway plus two stops on NC 54. 12 stops will add ADA compliant landing pad and continuous pedestrian connectivity to the existing sidewalk/sidepath netwok. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | BGDA | CONSTRUCTION | 626000
TL-0052 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | This transit project will improve 13 stops on the Go triangle 805 coridor on Woodcroft parkway plus two stops on NC 54. 12 stops will add ADA compliant landing pad and continuous pedestrian connectivity to the existing sidewalk/sidepath netwok. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L(M) | CONSTRUCTION | 156000
TL-0053 | Public Transportation (Transit) | Locally Selected | GoTriangle | Route 305 | Add a landing pad at 24 stops between existing sidewalk and back of curb. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 80000
TL-0053 | Public Transportation (Transit) | Locally Selected | GoTriangle | Route 305 | Add a landing pad at 24 stops between existing sidewalk and back of curb. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 20000
TL-0053 | Public Transportation (Transit) | Locally Selected | GoTriangle | Route 305 | Add a landing pad at 24 stops between existing sidewalk and back of curb. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 192000
TL-0053 | Public Transportation (Transit) | Locally Selected | GoTriangle | Route 305 | Add a landing pad at 24 stops between existing sidewalk and back of curb. Trash can pads may be included as warranted. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 48000
TL-0054 | Public Transportation (Transit) | Locally Selected | Winston Salem Transit Authority | Systemwide | Replace bus |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 6159000
TL-0054 | Public Transportation (Transit) | Locally Selected | Winston Salem Transit Authority | Systemwide | Replace bus |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CAPITAL | 1540000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. Douglas Gaylon Depot | Renovation phase 3. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 1600000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. Douglas Gaylon Depot | Renovation phase 3. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 613000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. Douglas Gaylon Depot | Renovation phase 3. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5339 | CONSTRUCTION | 850000
TL-0056 | Public Transportation (Transit) | Locally Selected | Charlotte Area Transit System (CATS) | Systemwide | Purchase two electric buses for Ballantyne - I-485 service. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1750000 | FY 2026: 1750000
TL-0056 | Public Transportation (Transit) | Locally Selected | Charlotte Area Transit System (CATS) | Systemwide | Purchase two electric buses for Ballantyne - I-485 service. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 438000 | FY 2026: 438000
TL-0057 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 58000
TL-0057 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 14000
TL-0057 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 14000
TL-0057 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 4000
TL-0057 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 350000
TL-0057 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Two bus stops improvement at Brier creek in Wake county. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 88000
TL-0058 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 86000
TL-0058 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 22000
TL-0058 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 22000
TL-0058 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 5000
TL-0058 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 324000
TL-0058 | Public Transportation (Transit) | Locally Selected | GoTriangle | Various locations | Improve all bus stops to ADA standards on South of US 64. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 81000
TL-0059 | Public Transportation (Transit) | Locally Selected | GoCary | Various locations | Purchase and install new radios for the GOCARY bus system, Including equipment for a base console operation for a dispatch. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | OPERATIONS | 271000
TL-0059 | Public Transportation (Transit) | Locally Selected | GoCary | Various locations | Purchase and install new radios for the GOCARY bus system, Including equipment for a base console operation for a dispatch. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | L(M) | OPERATIONS | 68000
TL-0060 | Public Transportation (Transit) | Locally Selected | Fayetteville Area System of Transit (FAST) | Various locations | Funding to implement cashless fare system across the fixed route and paratransit fleet. |  | Cumberland | 6 | Fayetteville Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 125000
TL-0060 | Public Transportation (Transit) | Locally Selected | Fayetteville Area System of Transit (FAST) | Various locations | Funding to implement cashless fare system across the fixed route and paratransit fleet. |  | Cumberland | 6 | Fayetteville Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 31000
TL-0062 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Various locations | Improve all bus stops. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 361000
TL-0062 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Various locations | Improve all bus stops. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CONSTRUCTION | 90000
TL-0063 | Public Transportation (Transit) | Locally Selected | Piedmont Authority for Regional Transportation | Various locations | Purchase cutaway vehicles and heavy duty buses. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 1650000
TL-0063 | Public Transportation (Transit) | Locally Selected | Piedmont Authority for Regional Transportation | Various locations | Purchase cutaway vehicles and heavy duty buses. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CAPITAL | 413000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | BGDA | ENGINEERING | 4400000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L(M) | ENGINEERING | 1100000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | DP | CONSTRUCTION | 19000000 | FY 2026: 19000000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | BGDA | CONSTRUCTION | 1100000 | FY 2026: 1100000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L | CONSTRUCTION | 14125000 | FY 2026: 14125000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L(M) | CONSTRUCTION | 275000 | FY 2026: 275000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | DP | CAPITAL | 6000000 | FY 2026: 6000000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L(M) | CAPITAL | 1500000 | FY 2026: 1500000
TL-0064 | Public Transportation (Transit) | Locally Selected | Triangle Mobility hub | Various locations | Purchase battery electric bus. |  | Durham | 5 | Triangle West TPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L | CAPITAL | 4500000 | FY 2026: 4500000
TL-0065 | Public Transportation (Transit) | Locally Selected | GoDurham | Systemwide. | Purchase battery electric buses. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | BGDA | CAPITAL | 863000 | FY 2027: 863000
TL-0065 | Public Transportation (Transit) | Locally Selected | GoDurham | Systemwide. | Purchase battery electric buses. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CAPITAL | 216000 | FY 2027: 216000
TL-0065 | Public Transportation (Transit) | Locally Selected | GoDurham | Systemwide. | Purchase battery electric buses. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | CAPITAL | 103000 | FY 2027: 103000
TL-0066 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Systemwide. | Purchase electric bus |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CAPITAL | 920000 | FY 2027: 920000
TL-0066 | Public Transportation (Transit) | Locally Selected | Chapel Hill Transit | Systemwide. | Purchase electric bus |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L(M) | CAPITAL | 230000 | FY 2027: 230000
TL-0067 | Public Transportation (Transit) | Locally Selected | Greenville Area Transit | Systemwide | Install bus shelters and benches as part of Greenville Area Transit's new routes for headway reduction. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 242000
TL-0067 | Public Transportation (Transit) | Locally Selected | Greenville Area Transit | Systemwide | Install bus shelters and benches as part of Greenville Area Transit's new routes for headway reduction. |  | Pitt | 2 | Greenville Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 61000
TL-0068 | Public Transportation (Transit) | Locally Selected | Greensboro Transit Authority | Systemwide | Fund study and design of Crossmax purple corridor. |  | Guilford | 7 | Greensboro Urban Area MPO | "DP" FUNDS REPRESENT FEDERAL RAISE GRANT AWARD. | Exempt |  | DP | ENGINEERING | 2000000
TL-0068 | Public Transportation (Transit) | Locally Selected | Greensboro Transit Authority | Systemwide | Fund study and design of Crossmax purple corridor. |  | Guilford | 7 | Greensboro Urban Area MPO | "DP" FUNDS REPRESENT FEDERAL RAISE GRANT AWARD. | Exempt |  | L(M) | ENGINEERING | 500000
TL-0069 | Public Transportation (Transit) | Locally Selected | Piedmont Authority for Regional Transportation | Systemwide | Fund the operation of express bus service. |  | Forsyth, Guilford | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO |  | Exempt |  | CMAQ | OPERATIONS | 1800000 | FY 2026: 1800000
TL-0069 | Public Transportation (Transit) | Locally Selected | Piedmont Authority for Regional Transportation | Systemwide | Fund the operation of express bus service. |  | Forsyth, Guilford | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO |  | Exempt |  | L(M) | OPERATIONS | 450000 | FY 2026: 450000
TL-6110 | Public Transportation (Transit) | Locally Selected | Western Piedmont Regional Transit Authority | Systemwide. | Program administration. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 262000
TL-6111 | Public Transportation (Transit) | Locally Selected | GoTriangle | Systemwide. | Purchase two 40 foot busses. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | BGDA | CAPITAL | 909000
TL-6111 | Public Transportation (Transit) | Locally Selected | GoTriangle | Systemwide. | Purchase two 40 foot busses. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | CAPITAL | 224000
TL-6111 | Public Transportation (Transit) | Locally Selected | GoTriangle | Systemwide. | Purchase two 40 foot busses. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L(M) | CAPITAL | 227000
TM-0025 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | Funding for operating assistance. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | OPERATIONS | 2106000
TM-0025 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | Funding for operating assistance. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5310 | OPERATIONS | 2106000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | Funding for operating assistance for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | S | OPERATIONS | 1000000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | Funding for operating assistance for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | OPERATIONS | 13064000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | Funding for operating assistance for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5311 | OPERATIONS | 18064000
TM-0029 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311 State administrative funds for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5311 | ADMINISTRATIVE | 10361000
TM-0030 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311 ADTAP state administrative funds. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | ADTAP | ADMINISTRATIVE | 177000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311(F) Intercity bus funds for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | S | OPERATIONS | 22607000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311(F) Intercity bus funds for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | OPERATIONS | 30000000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311(F) Intercity bus funds for FTA grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5311 | OPERATIONS | 46834000
TM-0033 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311(F) Intercity bus - state admin. |  | Statewide | 99 | Statewide Project |  | Public Transit
TM-0033 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Various locations | 5311(F) Intercity bus - state admin. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5311 | ADMINISTRATIVE | 494000
TM-0035 | Public Transportation (Transit) | Operations and Maintenance | GoTriangle | Various locations | Funding for operational assistance of Morrisville node based smart shuttle. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 3621000 | FY 2026: 740000
TM-0036 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Funding for 5310 state administrative funds. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5310 | ADMINISTRATIVE | 567000
TM-0037 | Public Transportation (Transit) | Operations and Maintenance | Winston-Salem Transit Authority | Systemwide. | Continuation of night, Saturday, and Sunday services. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | OPERATIONS | 810000
TM-0037 | Public Transportation (Transit) | Operations and Maintenance | Winston-Salem Transit Authority | Systemwide. | Continuation of night, Saturday, and Sunday services. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | OPERATIONS | 203000
TM-0039 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Funding for expansion and maintenance facilities. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 6200000 | FY 2026: 2600000; FY 2027: 2600000
TM-0039 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Various locations | Funding for expansion and maintenance facilities. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 21800000 | FY 2026: 10400000; FY 2027: 10400000
TM-0040 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Plan new and replacement circulator routes with new on-demand strategy of micro-transit zones to reduce travel times and improve connectivity to high-frequency routes at mobility hubs. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | ARP | PLANNING | 1500000 | FY 2026: 150000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Charlotte Transportation Center in Uptown Charlotte | Rebuild CATS main transit hub. |  | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | DP | CONSTRUCTION | 15000000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Charlotte Transportation Center in Uptown Charlotte | Rebuild CATS main transit hub. |  | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | L | CONSTRUCTION | 70718000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Charlotte Transportation Center in Uptown Charlotte | Rebuild CATS main transit hub. |  | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | CMAQ | CAPITAL | 2040000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Charlotte Transportation Center in Uptown Charlotte | Rebuild CATS main transit hub. |  | Mecklenburg | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | L | CAPITAL | 668000
TM-0042 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding to purchase electric buses. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | CMAQ | ACQUISITION | 1742000 | FY 2026: 296000
TM-0042 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding to purchase electric buses. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | S | ACQUISITION | 2787000 | FY 2026: 474000
TM-0042 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding to purchase electric buses. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | ACQUISITION | 951000 | FY 2026: 162000
TM-0043 | Public Transportation (Transit) | Capital (Non-STI) | GoDurham | Various locations | Acquisition Of Six (6) Electric Transit Buses. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | ACQUISITION | 6807000 | FY 2026: 6807000
TM-0043 | Public Transportation (Transit) | Capital (Non-STI) | GoDurham | Various locations | Acquisition Of Six (6) Electric Transit Buses. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5339(b) | ACQUISITION | 14476000 | FY 2026: 14476000
TM-0045 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for Gastonia Transit payment kiosk. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CAPITAL | 44000
TM-0045 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Funding for Gastonia Transit payment kiosk. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CAPITAL | 175000
TM-0046 | Public Transportation (Transit) | Operations and Maintenance | Link Transit | Systemwide | Preventative Maintenance. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 612000 | FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0046 | Public Transportation (Transit) | Operations and Maintenance | Link Transit | Systemwide | Preventative Maintenance. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 2460000 | FY 2026: 410000; FY 2027: 410000; FY 2028: 410000
TM-0047 | Public Transportation (Transit) | Capital (Non-STI) | Gastonia Transit Authority | Various locations | Funding for capital rolling stock. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CAPITAL | 200000
TM-0047 | Public Transportation (Transit) | Capital (Non-STI) | Gastonia Transit Authority | Various locations | Funding for capital rolling stock. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CAPITAL | 800000
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | Davidson County Transportation system | Various locations | Operate our deviated fixed routes based in Thomasville, NC along with demand response trips. |  | Davidson | 9 | High Point Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 1650000 | FY 2026: 275000; FY 2027: 275000; FY 2028: 275000
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | Davidson County Transportation system | Various locations | Operate our deviated fixed routes based in Thomasville, NC along with demand response trips. |  | Davidson | 9 | High Point Urban Area MPO |  | Public Transit |  | 5317 | OPERATIONS | 1650000 | FY 2026: 275000; FY 2027: 275000; FY 2028: 275000
TM-0049 | Public Transportation (Transit) | Operations and Maintenance | Integrated Mobility Division | Various | Funding for Macon County Areas of Persistent Poverty (AoPP) Grant. |  | Macon | 14 | Southwestern RPO |  | Public Transit |  | DP | CAPITAL | 470000
TM-0049 | Public Transportation (Transit) | Operations and Maintenance | Integrated Mobility Division | Various | Funding for Macon County Areas of Persistent Poverty (AoPP) Grant. |  | Macon | 14 | Southwestern RPO |  | Public Transit |  | L | CAPITAL | 55000
TM-0051 | Public Transportation (Transit) | Operations and Maintenance | Transportation Authority | Systemwide | Funding for rolling stock-shop vehicle. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 817000
TM-0051 | Public Transportation (Transit) | Operations and Maintenance | Transportation Authority | Systemwide | Funding for rolling stock-shop vehicle. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 48000
TM-0052 | Public Transportation (Transit) | Operations and Maintenance | Union County Transportation | Various locations | Funding for operational expenses and routine capital. |  | Union | 10 | Charlotte Regional TPO |  | Public Transit |  | L(M) | CAPITAL | 971000
TM-0052 | Public Transportation (Transit) | Operations and Maintenance | Union County Transportation | Various locations | Funding for operational expenses and routine capital. |  | Union | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 971000
TM-0053 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Operate micro transit. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 2735000 | FY 2026: 547000; FY 2027: 547000; FY 2028: 547000
TM-0053 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Systemwide | Operate micro transit. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 2735000 | FY 2026: 547000; FY 2027: 547000; FY 2028: 547000
TM-0054 | Public Transportation (Transit) | Operations and Maintenance | Haywood County | Various locations | Funding for operating assistance. |  | Haywood | 14 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 492000 | FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0054 | Public Transportation (Transit) | Operations and Maintenance | Haywood County | Various locations | Funding for operating assistance. |  | Haywood | 14 | French Broad River MPO |  | Public Transit |  | 5307 | OPERATIONS | 492000 | FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0055 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Systemwide | Purchase of five (5) hybrid-electric buses |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 788000
TM-0055 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Systemwide | Purchase of five (5) hybrid-electric buses |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5339(b) | CAPITAL | 4445000
TM-0056 | Public Transportation (Transit) | Operations and Maintenance | Mecklenburg Transit System | Systemwide | Funding for demand response vendor trips, preventative maintenance expenses and security related software. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 249000
TM-0056 | Public Transportation (Transit) | Operations and Maintenance | Mecklenburg Transit System | Systemwide | Funding for demand response vendor trips, preventative maintenance expenses and security related software. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 994000
TM-0057 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Regionwide. | Install battery-electric and hybrid diesel buses and charging infrastructure. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L(M) | CAPITAL | 5603000
TM-0057 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Regionwide. | Install battery-electric and hybrid diesel buses and charging infrastructure. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5339(b) | CAPITAL | 22411000
TM-0058 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Gastonia. | Purchase an electric ADA van. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CONSTRUCTION | 53000
TM-0058 | Public Transportation (Transit) | Operations and Maintenance | Gastonia Transit Authority | Gastonia. | Purchase an electric ADA van. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 213000
TM-0059 | Public Transportation (Transit) | Operations and Maintenance | Union County Transportation | Systemwide | Operational expenses, routine capital, and planning. |  | Union | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 716000 | FY 2026: 97000; FY 2027: 15000
TM-0059 | Public Transportation (Transit) | Operations and Maintenance | Union County Transportation | Systemwide | Operational expenses, routine capital, and planning. |  | Union | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 1222000 | FY 2026: 483000; FY 2027: 74000
TM-0060 | Public Transportation (Transit) | Operations and Maintenance | GoDurham | Systemwide. | Operating expenses for GoDurham fixed route. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | CAPITAL | 18091000 | FY 2026: 4407000; FY 2027: 4628000; FY 2028: 4859000
TM-0060 | Public Transportation (Transit) | Operations and Maintenance | GoDurham | Systemwide. | Operating expenses for GoDurham fixed route. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5307 | CAPITAL | 18091000 | FY 2026: 4407000; FY 2027: 4628000; FY 2028: 4859000
TM-0061 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide. | Operational and capital cost of contracting, pass through, 3rd party contracts. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | OPERATIONS | 90000 | FY 2026: 40000; FY 2027: 50000
TM-0061 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide. | Operational and capital cost of contracting, pass through, 3rd party contracts. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | OPERATIONS | 90000 | FY 2026: 40000; FY 2027: 50000
TM-0062 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide. | Operational and capital cost of contracting, pass through, 3rd party contracts. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | OPERATIONS | 85000 | FY 2026: 45000; FY 2027: 40000
TM-0062 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide. | Operational and capital cost of contracting, pass through, 3rd party contracts. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | OPERATIONS | 111000 | FY 2026: 64000; FY 2027: 47000
TM-0063 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide. | Mobility management and operating assistance for elderly and disabled persons, and other ADA communities. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | OPERATIONS | 48000 | FY 2026: 24000; FY 2027: 24000
TM-0063 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide. | Mobility management and operating assistance for elderly and disabled persons, and other ADA communities. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | OPERATIONS | 188000 | FY 2026: 94000; FY 2027: 94000
TM-0064 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide. | Improve bus stops for enhanced mobility of seniors and individuals living with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 136000 | FY 2026: 40000; FY 2027: 38000
TM-0064 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide. | Improve bus stops for enhanced mobility of seniors and individuals living with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | 5310 | CAPITAL | 696000 | FY 2026: 160000; FY 2027: 304000
TM-0065 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide. | Acquire new light rail vehicles. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | DP | CAPITAL | 2000000 | FY 2027: 2000000
TM-0065 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide. | Acquire new light rail vehicles. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 10190000 | FY 2027: 290000; FY 2028: 9900000
TM-0065 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide. | Acquire new light rail vehicles. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 39160000 | FY 2027: 1160000; FY 2028: 38000000
TM-0066 | Public Transportation (Transit) | Operations and Maintenance | Orange county public transit | Systemwide | Operating assistance |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | OPERATIONS | 858000 | FY 2026: 429000
TM-0066 | Public Transportation (Transit) | Operations and Maintenance | Orange county public transit | Systemwide | Operating assistance |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5307 | OPERATIONS | 858000 | FY 2026: 429000
TM-0067 | Public Transportation (Transit) | Operations and Maintenance | GoDurham | Systemwide | Purchase service for passengers who are eligible for ADA services outside of the 3/4 mile ADA service area of GoDurham. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | ACQUISITION | 100000 | FY 2026: 50000
TM-0067 | Public Transportation (Transit) | Operations and Maintenance | GoDurham | Systemwide | Purchase service for passengers who are eligible for ADA services outside of the 3/4 mile ADA service area of GoDurham. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5310 | ACQUISITION | 400000 | FY 2026: 200000
TM-0068 | Public Transportation (Transit) | Operations and Maintenance | Orange County STEAM | Systemwide | Funding for education program, expand and manage a volunteer driver program, and purchase service for transportation operators. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | L | OPERATIONS | 56000 | FY 2026: 8000
TM-0068 | Public Transportation (Transit) | Operations and Maintenance | Orange County STEAM | Systemwide | Funding for education program, expand and manage a volunteer driver program, and purchase service for transportation operators. |  | Orange | 7 | Triangle West TPO |  | Public Transit |  | 5310 | OPERATIONS | 384000 | FY 2026: 192000
TM-5138 | Public Transportation (Transit) | Operations and Maintenance | City of Asheville Transit | Various locations | Funding for JARC operations. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 408000
TM-5138 | Public Transportation (Transit) | Operations and Maintenance | City of Asheville Transit | Various locations | Funding for JARC operations. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | 3037 | OPERATIONS | 408000
TM-5309 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Various locations | Funding for Job access reverse commute (JARC) - Non urban. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 330000
TM-5309 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Various locations | Funding for Job access reverse commute (JARC) - Non urban. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5316 | OPERATIONS | 330000
TM-6110 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for agency administration. |  | Catawba | 12 | Greater Hickory MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 232000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Coordinated Area Transportation System (RCATS) | Systemwide | Funding for Asheboro flexible route transit launch. |  | Randolph | 8 | Piedmont Triad RPO |  | Exempt |  | CRPANY | CAPITAL | 587000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Coordinated Area Transportation System (RCATS) | Systemwide | Funding for Asheboro flexible route transit launch. |  | Randolph | 8 | Piedmont Triad RPO |  | Exempt |  | L(M) | CAPITAL | 146000
TN-0002 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Mitchell County Transit | Mitchell County Transit | Construct new facility. |  | Mitchell | 13 | High Country RPO |  | Exempt |  | CRPLT5 | CAPITAL | 4000000
TN-0002 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Mitchell County Transit | Mitchell County Transit | Construct new facility. |  | Mitchell | 13 | High Country RPO |  | Exempt |  | L(M) | CAPITAL | 1000000
TN-6116 | Public Transportation (Transit) | Operations and Maintenance | Wake Coordinated Transportation Service | Various locations | Funding for Transit service operating assistance. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 4070000 | FY 2026: 868000
TN-6126 | Public Transportation (Transit) | Locally Selected | Orange County Transit | Systemwide | Funding for 2 ADA accessible mini vans. Expand micro transit. |  | Orange | 7 | Central Pines RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 150000
TN-6126 | Public Transportation (Transit) | Locally Selected | Orange County Transit | Systemwide | Funding for 2 ADA accessible mini vans. Expand micro transit. |  | Orange | 7 | Central Pines RPO |  | Exempt |  | L | IMPLEMENTATION | 38000
TN-6127 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Rutherfordton | Systemwide | Purchase four vehicles |  | Rutherford | 13 | Foothills RPO |  | Exempt |  | CRP550 | CAPITAL | 233000
TN-6127 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Rutherfordton | Systemwide | Purchase four vehicles |  | Rutherford | 13 | Foothills RPO |  | Exempt |  | L(M) | CAPITAL | 58000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | US 25 / US 70 | Construct park and ride at US 25 Business / US 70 Business intersection. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 22000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | US 25 / US 70 | Construct park and ride at US 25 Business / US 70 Business intersection. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | T(M) | ENGINEERING | 6000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | US 25 / US 70 | Construct park and ride at US 25 Business / US 70 Business intersection. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 301000 | FY 2026: 301000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | US 25 / US 70 | Construct park and ride at US 25 Business / US 70 Business intersection. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | T(M) | CONSTRUCTION | 75000 | FY 2026: 75000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Appalcart | Systemwide | Purchase three battery electric buses and associated charger, electric vehicle management and diagnostic tool |  | Watauga | 11 | High Country RPO |  | Exempt |  | T(M) | ENGINEERING | 36000 | FY 2027: 36000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Appalcart | Systemwide | Purchase three battery electric buses and associated charger, electric vehicle management and diagnostic tool |  | Watauga | 11 | High Country RPO |  | Exempt |  | 5311 | ENGINEERING | 144000 | FY 2027: 144000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Appalcart | Systemwide | Purchase three battery electric buses and associated charger, electric vehicle management and diagnostic tool |  | Watauga | 11 | High Country RPO |  | Exempt |  | T(M) | CAPITAL | 965000 | FY 2027: 965000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Appalcart | Systemwide | Purchase three battery electric buses and associated charger, electric vehicle management and diagnostic tool |  | Watauga | 11 | High Country RPO |  | Exempt |  | 5311 | CAPITAL | 3858000 | FY 2027: 3858000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Madison County Transportation | Systemwide | Purchase two transit vehicles. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 8000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Madison County Transportation | Systemwide | Purchase two transit vehicles. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | ENGINEERING | 2000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Madison County Transportation | Systemwide | Purchase two transit vehicles. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CAPITAL | 189000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Madison County Transportation | Systemwide | Purchase two transit vehicles. |  | Madison | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | CAPITAL | 47000
TN-6131 | Public Transportation (Transit) | Locally Selected | Surf City | Systemwide | Purchase two electric vehicles. |  | Pender, Onslow | 3 | Cape Fear RPO, Jacksonville Urban Area MPO |  | Exempt |  | CRPANY | CAPITAL | 80000
TN-6131 | Public Transportation (Transit) | Locally Selected | Surf City | Systemwide | Purchase two electric vehicles. |  | Pender, Onslow | 3 | Cape Fear RPO, Jacksonville Urban Area MPO |  | Exempt |  | L(M) | CAPITAL | 20000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Johnston County | Systemwide | Purchase electric transit vehicles. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | ENGINEERING | 8000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Johnston County | Systemwide | Purchase electric transit vehicles. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 2000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Johnston County | Systemwide | Purchase electric transit vehicles. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | CAPITAL | 400000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Johnston County | Systemwide | Purchase electric transit vehicles. |  | Johnston | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CAPITAL | 100000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Chapel Hill Transit | Systemwide | Purchase five electric transit buses. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | CMAQ | CAPITAL | 2040000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Chapel Hill Transit | Systemwide | Purchase five electric transit buses. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | L | CAPITAL | 158000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Chapel Hill Transit | Systemwide | Purchase five electric transit buses. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | L(M) | CAPITAL | 510000
TN-6134 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Link Transit | Various location | Purchase two electric paratransit vehicles and install chargers. |  | Alamance | 7 | Burlington-Graham MPO |  | Exempt |  | CRPDA | CAPITAL | 448000
TN-6134 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Link Transit | Various location | Purchase two electric paratransit vehicles and install chargers. |  | Alamance | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | CAPITAL | 112000
TN-6135 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Pittsboro | Pittsboro | Provide operating assistance for new transit service in the Town of Pittsboro. |  | Chatham | 8 | Central Pines RPO |  | Exempt |  | CMAQ | OPERATIONS | 140000
TN-6135 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | Pittsboro | Pittsboro | Provide operating assistance for new transit service in the Town of Pittsboro. |  | Chatham | 8 | Central Pines RPO |  | Exempt |  | L(M) | OPERATIONS | 35000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Systemwide | System safety oversight grant for Rail division NCDOT. |  | Statewide | 99 | Statewide Project | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | CAPITAL | 1300000 | FY 2026: 500000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Systemwide | System safety oversight grant for Rail division NCDOT. |  | Statewide | 99 | Statewide Project | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | SSO | CAPITAL | 3200000 | FY 2026: 1000000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Systemwide | System safety oversight grant for Rail division NCDOT. |  | Statewide | 99 | Statewide Project | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | ADMINISTRATIVE | 776000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Systemwide | System safety oversight grant for Rail division NCDOT. |  | Statewide | 99 | Statewide Project | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | SSO | ADMINISTRATIVE | 2504000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | City of Asheville Transit | Systemwide | Funding for transit operations. |  | Buncombe | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 765000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | City of Asheville Transit | Systemwide | Funding for transit operations. |  | Buncombe | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 600000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | City of Asheville Transit | Systemwide | Funding for transit operations. |  | Buncombe | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 600000
TO-4719 | Public Transportation (Transit) | Miscellaneous/Other | Goldsboro-Wayne Transportation Authority | Various locations | Funding for operating assistance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 2140000 | FY 2026: 325000; FY 2027: 325000; FY 2028: 325000
TO-4719 | Public Transportation (Transit) | Miscellaneous/Other | Goldsboro-Wayne Transportation Authority | Various locations | Funding for operating assistance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2140000 | FY 2026: 325000; FY 2027: 325000; FY 2028: 325000
TO-4719 | Public Transportation (Transit) | Miscellaneous/Other | Goldsboro-Wayne Transportation Authority | Various locations | Funding for operating assistance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 4280000 | FY 2026: 650000; FY 2027: 650000; FY 2028: 650000
TO-4726 | Public Transportation (Transit) | Miscellaneous/Other | Greenville Area Transit | Various locations | Funding for operating assistance. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 2200000 | FY 2026: 220000; FY 2027: 220000; FY 2028: 220000; FY 2029: 220000
TO-4726 | Public Transportation (Transit) | Miscellaneous/Other | Greenville Area Transit | Various locations | Funding for operating assistance. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4860000 | FY 2026: 540000; FY 2027: 540000; FY 2028: 540000; FY 2029: 540000
TO-4726 | Public Transportation (Transit) | Miscellaneous/Other | Greenville Area Transit | Various locations | Funding for operating assistance. |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 4860000 | FY 2026: 540000; FY 2027: 540000; FY 2028: 540000; FY 2029: 540000
TO-4751 | Public Transportation (Transit) | Miscellaneous/Other | Cape Fear Public Transit Authority (WAVE) | Various locations | Funding for operating assistance. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 1445000
TO-4751 | Public Transportation (Transit) | Miscellaneous/Other | Cape Fear Public Transit Authority (WAVE) | Various locations | Funding for operating assistance. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 8011000
TO-4751 | Public Transportation (Transit) | Miscellaneous/Other | Cape Fear Public Transit Authority (WAVE) | Various locations | Funding for operating assistance. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 7981000
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | High Point Transit System | Various locations | Funding for operating assistance. |  | Randolph, Davidson, Guilford | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 5588000
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | High Point Transit System | Various locations | Funding for operating assistance. |  | Randolph, Davidson, Guilford | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 27588000 | FY 2026: 2200000; FY 2027: 2200000; FY 2028: 2200000
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | High Point Transit System | Various locations | Funding for operating assistance. |  | Randolph, Davidson, Guilford | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 38618000 | FY 2026: 2200000; FY 2027: 2200000; FY 2028: 2200000
TO-4923 | Public Transportation (Transit) | Miscellaneous/Other | Jacksonville Transit | Various locations | Funding for operating assistance. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | SMAP | OPERATIONS | 858000 | FY 2026: 97000; FY 2027: 93000
TO-4923 | Public Transportation (Transit) | Miscellaneous/Other | Jacksonville Transit | Various locations | Funding for operating assistance. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 3137000 | FY 2026: 427000; FY 2027: 441000
TO-4923 | Public Transportation (Transit) | Miscellaneous/Other | Jacksonville Transit | Various locations | Funding for operating assistance. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 3995000 | FY 2026: 524000; FY 2027: 534000
TO-4971 | Public Transportation (Transit) | Miscellaneous/Other | Greensboro Transit Authority | Systemwide | Funding for operating assistance. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 11529000 | FY 2026: 1647000; FY 2027: 1647000; FY 2028: 1647000
TO-4971 | Public Transportation (Transit) | Miscellaneous/Other | Greensboro Transit Authority | Systemwide | Funding for operating assistance. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 23258000 | FY 2026: 3890000; FY 2027: 3890000; FY 2028: 3890000
TO-4971 | Public Transportation (Transit) | Miscellaneous/Other | Greensboro Transit Authority | Systemwide | Funding for operating assistance. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 13376000 | FY 2026: 2243000; FY 2027: 2243000; FY 2028: 2243000
TO-5024 | Public Transportation (Transit) | Miscellaneous/Other | Craven Area Rural Transportation System | Various locations | Funding for operating assistance. |  | Craven | 2 | New Bern Area MPO |  | Public Transit |  | L | OPERATIONS | 1175000 | FY 2026: 275000
TO-5024 | Public Transportation (Transit) | Miscellaneous/Other | Craven Area Rural Transportation System | Various locations | Funding for operating assistance. |  | Craven | 2 | New Bern Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 1175000 | FY 2026: 275000
TO-5126 | Public Transportation (Transit) | Miscellaneous/Other | Winston Salem Transit | Systemwide | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 7004000
TO-5126 | Public Transportation (Transit) | Miscellaneous/Other | Winston Salem Transit | Systemwide | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 8478000
TO-5126 | Public Transportation (Transit) | Miscellaneous/Other | Winston Salem Transit | Systemwide | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 12574000
TO-5127 | Public Transportation (Transit) | Miscellaneous/Other | Tar River Transit | Systemwide | Funding for operating assistance. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 1200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
TO-5127 | Public Transportation (Transit) | Miscellaneous/Other | Tar River Transit | Systemwide | Funding for operating assistance. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1200000 | FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
TO-5127 | Public Transportation (Transit) | Miscellaneous/Other | Tar River Transit | Systemwide | Funding for operating assistance. |  | Edgecombe, Nash | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3600000 | FY 2026: 400000; FY 2027: 400000; FY 2028: 400000
TO-5128 | Public Transportation (Transit) | Miscellaneous/Other | Capital Area Transit | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 9000000
TO-5128 | Public Transportation (Transit) | Miscellaneous/Other | Capital Area Transit | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 85480000 | FY 2026: 18036000
TO-5128 | Public Transportation (Transit) | Miscellaneous/Other | Capital Area Transit | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 58500000
TO-5129 | Public Transportation (Transit) | Miscellaneous/Other | Cary Transit | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 1140000
TO-5129 | Public Transportation (Transit) | Miscellaneous/Other | Cary Transit | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 18211000 | FY 2026: 4156000
TO-5129 | Public Transportation (Transit) | Miscellaneous/Other | Cary Transit | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 50000
TO-5130 | Public Transportation (Transit) | Miscellaneous/Other | GoDurham | Systemwide | Funding for operating assistance. |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 14030000 | FY 2026: 2806000; FY 2027: 2806000; FY 2028: 2806000
TO-5130 | Public Transportation (Transit) | Miscellaneous/Other | GoDurham | Systemwide | Funding for operating assistance. |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 14030000 | FY 2026: 2806000; FY 2027: 2806000; FY 2028: 2806000
TO-5131 | Public Transportation (Transit) | Miscellaneous/Other | GoTriangle | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 5856000
TO-5131 | Public Transportation (Transit) | Miscellaneous/Other | GoTriangle | Systemwide | Funding for operating assistance. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 31999000 | FY 2026: 6838000
TO-5132 | Public Transportation (Transit) | Miscellaneous/Other | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for operating assistance. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 7656000 | FY 2026: 920000; FY 2027: 920000; FY 2028: 920000; FY 2029: 920000; FY 2030: 920000
TO-5133 | Public Transportation (Transit) | Miscellaneous/Other | Chapel Hill Transit | Systemwide | Funding for operating assistance. |  | Orange | 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 28560000 | FY 2026: 3570000; FY 2027: 3570000; FY 2028: 3570000
TO-5134 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Regional Transport Authority | Various locations | Funding for operating assistance. |  | Alamance | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2750000 | FY 2026: 420000; FY 2027: 420000; FY 2028: 420000
TO-5134 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Regional Transport Authority | Various locations | Funding for operating assistance. |  | Alamance | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 2750000 | FY 2026: 420000; FY 2027: 420000; FY 2028: 420000
TO-5134C | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority For Regional Transportation | Systemwide | Funding for operating assistance. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 4800000 | FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
TO-5134C | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority For Regional Transportation | Systemwide | Funding for operating assistance. |  | Guilford | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 4800000 | FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
TO-5135 | Public Transportation (Transit) | Miscellaneous/Other | City Of Salisbury | Systemwide | Funding for operating assistance. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 430000
TO-5135 | Public Transportation (Transit) | Miscellaneous/Other | City Of Salisbury | Systemwide | Funding for operating assistance. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1920000 | FY 2026: 160000; FY 2027: 160000
TO-5135 | Public Transportation (Transit) | Miscellaneous/Other | City Of Salisbury | Systemwide | Funding for operating assistance. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3420000 | FY 2026: 285000; FY 2027: 285000
TO-5137 | Public Transportation (Transit) | Miscellaneous/Other | Charlotte Area Transit System (CATS) | Systemwide | Funding for operating assistance. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 75312000
TO-5138 | Public Transportation (Transit) | Miscellaneous/Other | Concord Kannapolis Area Transit | Systemwide | Funding for operating assistance. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 4827000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000
TO-5138 | Public Transportation (Transit) | Miscellaneous/Other | Concord Kannapolis Area Transit | Systemwide | Funding for operating assistance. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 20900000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
TO-5138 | Public Transportation (Transit) | Miscellaneous/Other | Concord Kannapolis Area Transit | Systemwide | Funding for operating assistance. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 21500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
TO-5139 | Public Transportation (Transit) | Miscellaneous/Other | City Of Salisbury | Systemwide | Funding for operating free fare. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | CMAQ | OPERATIONS | 408000 | FY 2026: 34000; FY 2027: 34000
TO-5139 | Public Transportation (Transit) | Miscellaneous/Other | City Of Salisbury | Systemwide | Funding for operating free fare. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 96000 | FY 2026: 8000; FY 2027: 8000
TO-5142 | Public Transportation (Transit) | Miscellaneous/Other | Gastonia Transit Authority | Systemwide | Funding for operating assistance. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 1068000
TO-5144 | Public Transportation (Transit) | Miscellaneous/Other | Fayetteville Area System of Transit (FAST) | Various locations | Funding for operating assistance. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 5400000 | FY 2026: 920000; FY 2027: 920000; FY 2028: 920000; FY 2029: 920000
TO-5144 | Public Transportation (Transit) | Miscellaneous/Other | Fayetteville Area System of Transit (FAST) | Various locations | Funding for operating assistance. |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 5400000 | FY 2026: 920000; FY 2027: 920000; FY 2028: 920000; FY 2029: 920000
TO-5149 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operating assistance. |  | Iredell | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 277000
TO-5149 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operating assistance. |  | Iredell | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 410000
TO-5201 | Public Transportation (Transit) | Miscellaneous/Other | City Of Salisbury | Systemwide | Funding for operating assistance. |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 1808000 | FY 2026: 226000; FY 2027: 226000; FY 2028: 226000
TO-5209 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority For Regional Transport | Systemwide | Funding for operating Fixed route. |  | Guilford | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | Public Transit |  | SMAP | OPERATIONS | 3548000 | FY 2026: 720000; FY 2027: 720000; FY 2028: 720000
TO-5209 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority For Regional Transport | Systemwide | Funding for operating Fixed route. |  | Guilford | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | Public Transit |  | L | OPERATIONS | 2486000 | FY 2026: 492000; FY 2027: 492000; FY 2028: 492000
TO-5209 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority For Regional Transport | Systemwide | Funding for operating Fixed route. |  | Guilford | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | Public Transit |  | 5307 | OPERATIONS | 2486000 | FY 2026: 492000; FY 2027: 492000; FY 2028: 492000
TO-5214 | Public Transportation (Transit) | Miscellaneous/Other | Alamance County Transportation Authority | Systemwide | Operating for Alamance county transportation in the Burlington urban area. |  | Alamance | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4365000 | FY 2026: 805000; FY 2027: 805000; FY 2028: 805000
TO-5214 | Public Transportation (Transit) | Miscellaneous/Other | Alamance County Transportation Authority | Systemwide | Operating for Alamance county transportation in the Burlington urban area. |  | Alamance | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 4705000 | FY 2026: 805000; FY 2027: 805000; FY 2028: 805000
TO-5216 | Public Transportation (Transit) | Miscellaneous/Other | Guilford County Transportation | Systemwide | Operating funding for Guilford county through High point MPO. |  | Guilford | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 455000 | FY 2026: 70000; FY 2027: 75000
TO-5216 | Public Transportation (Transit) | Miscellaneous/Other | Guilford County Transportation | Systemwide | Operating funding for Guilford county through High point MPO. |  | Guilford | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 875000 | FY 2026: 140000; FY 2027: 150000
TO-5221 | Public Transportation (Transit) | Miscellaneous/Other | Guilford County Transportation | Systemwide | Funding for operating rural transit. |  | Guilford | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | Public Transit |  | L | OPERATIONS | 175000 | FY 2026: 35000; FY 2027: 35000; FY 2028: 35000
TO-5221 | Public Transportation (Transit) | Miscellaneous/Other | Guilford County Transportation | Systemwide | Funding for operating rural transit. |  | Guilford | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | Public Transit |  | 5307 | OPERATIONS | 175000 | FY 2026: 35000; FY 2027: 35000; FY 2028: 35000
TO-6061 | Public Transportation (Transit) | Miscellaneous/Other | Gastonia Transit Authority | Systemwide | Funding for operating expenses. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 2297000
TO-6061 | Public Transportation (Transit) | Miscellaneous/Other | Gastonia Transit Authority | Systemwide | Funding for operating expenses. |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 2297000
TO-6106 | Public Transportation (Transit) | Miscellaneous/Other | Apple Country Transit | Systemwide | Funding for operating assistance. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 929000 | FY 2026: 278000
TO-6106 | Public Transportation (Transit) | Miscellaneous/Other | Apple Country Transit | Systemwide | Funding for operating assistance. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 705000 | FY 2026: 278000
TO-6106 | Public Transportation (Transit) | Miscellaneous/Other | Apple Country Transit | Systemwide | Funding for operating assistance. |  | Henderson | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 448000
TO-6107 | Public Transportation (Transit) | Miscellaneous/Other | Goldsboro - Wayne Transportation Authority | Systemwide | Funding for operating assistance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 168000 | FY 2026: 21000; FY 2027: 21000; FY 2028: 21000
TO-6107 | Public Transportation (Transit) | Miscellaneous/Other | Goldsboro - Wayne Transportation Authority | Systemwide | Funding for operating assistance. |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 168000 | FY 2026: 21000; FY 2027: 21000; FY 2028: 21000
TO-6135 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Statewide | 5311 Operating funds for FTA grants. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | OPERATIONS | 947000
TO-6139 | Public Transportation (Transit) | Miscellaneous/Other | Greensboro Transit Authority | Systemwide | Funding for operating assistance. |  | Guilford | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | L | OPERATIONS | 121000 | FY 2026: 35000; FY 2027: 51000
TO-6139 | Public Transportation (Transit) | Miscellaneous/Other | Greensboro Transit Authority | Systemwide | Funding for operating assistance. |  | Guilford | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | 5310 | OPERATIONS | 121000 | FY 2026: 35000; FY 2027: 51000
TO-6142 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Statewide | Funding for Urbanized formula program. |  | Statewide | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 9389000
TO-6142 | Public Transportation (Transit) | Miscellaneous/Other | Statewide | Statewide | Funding for Urbanized formula program. |  | Statewide | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 9389000
TO-6150 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority for Regional Transportation | Various locations | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 2805000 | FY 2026: 439000; FY 2027: 485000
TO-6150 | Public Transportation (Transit) | Miscellaneous/Other | Piedmont Authority for Regional Transportation | Various locations | Funding for operating assistance. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 2805000 | FY 2026: 439000; FY 2027: 485000
TO-6151 | Public Transportation (Transit) | Miscellaneous/Other | Burlington Fixed Route Service | Burlington fixed route | Funding for operating assistance. |  | Guilford | 7 | Burlington-Graham MPO |  | Public Transit |  | L | OPERATIONS | 1551000 | FY 2026: 388000; FY 2027: 388000; FY 2028: 400000
TO-6151 | Public Transportation (Transit) | Miscellaneous/Other | Burlington Fixed Route Service | Burlington fixed route | Funding for operating assistance. |  | Guilford | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | OPERATIONS | 1551000 | FY 2026: 388000; FY 2027: 388000; FY 2028: 400000
TO-6154 | Public Transportation (Transit) | Miscellaneous/Other | Buncombe County - Mountain Mobility | Systemwide | Funding for operating assistance. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 2126000 | FY 2026: 250000; FY 2027: 375000; FY 2028: 261000
TO-6154 | Public Transportation (Transit) | Miscellaneous/Other | Buncombe County - Mountain Mobility | Systemwide | Funding for operating assistance. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | 5307 | OPERATIONS | 2376000 | FY 2026: 250000; FY 2027: 375000; FY 2028: 262000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operations. |  | Iredell | 12 | Charlotte Regional TPO |  | Public Transit |  | L(M) | CONSTRUCTION | 100000 | FY 2026: 100000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operations. |  | Iredell | 12 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CONSTRUCTION | 400000 | FY 2026: 400000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operations. |  | Iredell | 12 | Charlotte Regional TPO |  | Public Transit |  | L | OPERATIONS | 1186000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operations. |  | Iredell | 12 | Charlotte Regional TPO |  | Public Transit |  | L(M) | OPERATIONS | 1600000 | FY 2026: 400000; FY 2027: 400000; FY 2028: 400000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operations. |  | Iredell | 12 | Charlotte Regional TPO |  | Public Transit |  | 5307 | OPERATIONS | 1986000 | FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | Iredell County Area Transportation System (ICATS) | Systemwide | Funding for operations. |  | Iredell | 12 | Charlotte Regional TPO |  | Public Transit |  | 5316 | OPERATIONS | 800000 | FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
TO-6162 | Public Transportation (Transit) | Miscellaneous/Other | Western Piedmont Regional Transit Authority | Systemwide | Funding for operating assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 9865000
TO-6162 | Public Transportation (Transit) | Miscellaneous/Other | Western Piedmont Regional Transit Authority | Systemwide | Funding for operating assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 9865000
TO-6166 | Public Transportation (Transit) | STI (Prioritization) | GoRaleigh | Various locations | Construct Infrastructure for rapid bus transit from Research Triangle Park to Clayton | 33.93 | Wake, Johnston | 4, 5 | Capital Area MPO
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Research Triangle Park to Cary. Construct infrastructures, purchase vehicles | 3.86 | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 2000000 | FY 2028: 2000000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Research Triangle Park to Cary. Construct infrastructures, purchase vehicles | 3.86 | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 1000000 | FY 2028: 1000000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Research Triangle Park to Cary. Construct infrastructures, purchase vehicles | 3.86 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 27000000 | FY 2030: 9000000; FY 2031: 9000000; FY 2032: 9000000
TO-6166B | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Cary to Raleigh. Construct infrastructures, purchase vehicles | 9.19 | Wake | 5 | Capital Area MPO |  | Region C |  | L(M) | ENGINEERING | 35000000 | FY 2026: 35000000
TO-6166B | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Cary to Raleigh. Construct infrastructures, purchase vehicles | 9.19 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 20000000 | FY 2030: 6667000; FY 2031: 6667000; FY 2032: 6666000
TO-6166B | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Cary to Raleigh. Construct infrastructures, purchase vehicles | 9.19 | Wake | 5 | Capital Area MPO |  | Region C |  | L(M) | CONSTRUCTION | 190000000 | FY 2027: 190000000
TO-6166B | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to establish bus rapid transit service from Cary to Raleigh. Construct infrastructures, purchase vehicles | 9.19 | Wake | 5 | Capital Area MPO |  | Region C |  | 5309 | CONSTRUCTION | 149990000 | FY 2027: 149990000
TO-6166C | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to construct infrastructure, purchase vehicles and establish service for Bus rapid Transit from Raleigh to Garner | 5.93 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 30000000 | FY 2030: 10000000; FY 2031: 10000000; FY 2032: 10000000
TO-6166C | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to construct infrastructure, purchase vehicles and establish service for Bus rapid Transit from Raleigh to Garner | 5.93 | Wake | 5 | Capital Area MPO |  | Region C |  | L(M) | CONSTRUCTION | 118862000 | FY 2027: 118862000
TO-6166C | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Funding to construct infrastructure, purchase vehicles and establish service for Bus rapid Transit from Raleigh to Garner | 5.93 | Wake | 5 | Capital Area MPO |  | Region C |  | 5309 | CONSTRUCTION | 77780000 | FY 2027: 77780000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Construct infrastructure, purchase vehicles and establish service for bus rapid transit from Garner to Clayton | 15.03 | Johnston, Wake | 4, 5 | Capital Area MPO |  | Region A, C |  | T | RIGHT-OF-WAY | 2000000 | FY 2028: 2000000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Construct infrastructure, purchase vehicles and establish service for bus rapid transit from Garner to Clayton | 15.03 | Johnston, Wake | 4, 5 | Capital Area MPO |  | Region A, C |  | T | UTILITIES | 1000000 | FY 2028: 1000000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | Various | Various locations | Construct infrastructure, purchase vehicles and establish service for bus rapid transit from Garner to Clayton | 15.03 | Johnston, Wake | 4, 5 | Capital Area MPO |  | Region A, C |  | T | CONSTRUCTION | 17000000 | FY 2030: 5667000; FY 2031: 5667000; FY 2032: 5666000
TO-6168 | Public Transportation (Transit) | Miscellaneous/Other | GoRaleigh | Town of Wake Forest reverse circulator | Funding for operating assistance |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 2283000 | FY 2026: 404000
TO-6170 | Public Transportation (Transit) | Miscellaneous/Other | Link Transit | Various locations | Operating assistance to maintain current level of service in addition to service expansion for weekend service |  | Alamance | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | Public Transit |  | L | OPERATIONS | 4920000 | FY 2026: 820000; FY 2027: 820000; FY 2028: 820000
TO-6170 | Public Transportation (Transit) | Miscellaneous/Other | Link Transit | Various locations | Operating assistance to maintain current level of service in addition to service expansion for weekend service |  | Alamance | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | Public Transit |  | 5307 | OPERATIONS | 4920000 | FY 2026: 820000; FY 2027: 820000; FY 2028: 820000
TO-6812A | Public Transportation (Transit) | Miscellaneous/Other | Link Transit | Various locations | ADA Service. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | OPERATIONS | 276000 | FY 2026: 46000; FY 2027: 46000; FY 2028: 46000
TO-6812A | Public Transportation (Transit) | Miscellaneous/Other | Link Transit | Various locations | ADA Service. |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | OPERATIONS | 1080000 | FY 2026: 180000; FY 2027: 180000; FY 2028: 180000
TO-6813 | Public Transportation (Transit) | Locally Selected | Kings Mountain | Five locations | Funding to install 20 new EV chargers |  | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | DP | CONSTRUCTION | 823000
TO-6813 | Public Transportation (Transit) | Locally Selected | Kings Mountain | Five locations | Funding to install 20 new EV chargers |  | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | L | CONSTRUCTION | 206000
TP-0001 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Route 800. | Purchase 3 vehicles, construct stop and access improvements, and improve existing facility at Southpoint Transit Center. |  | Durham, Orange | 5, 7 | Triangle West TPO |  | Region C, D |  | BGANY | CONSTRUCTION | 5000000 | FY 2030: 2500000; FY 2031: 2500000
TP-0001 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Route 800. | Purchase 3 vehicles, construct stop and access improvements, and improve existing facility at Southpoint Transit Center. |  | Durham, Orange | 5, 7 | Triangle West TPO |  | Region C, D |  | L | CONSTRUCTION | 9500000 | FY 2030: 4750000; FY 2031: 4750000
TP-0002 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | Research Triangle Park to the Town of Cary and Downtown Raleigh to North Hills. | Construct bus rapid transit lanes and purchase 24 vehicles. |  | Durham, Wake | 5 | Capital Area MPO, Triangle West TPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 100000000
TP-0003 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | DRX Route. | Purchase two vehicles and install electric charging infrastructure. |  | Durham, Wake | 5 | Capital Area MPO, Triangle West TPO |  | Region C |  | BGANY | CONSTRUCTION | 1500000 | FY 2027: 1500000
TP-0003 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | DRX Route. | Purchase two vehicles and install electric charging infrastructure. |  | Durham, Wake | 5 | Capital Area MPO, Triangle West TPO |  | Region C |  | L | CONSTRUCTION | 1500000 | FY 2027: 1500000
TP-0004 | Public Transportation (Transit) | STI (Prioritization) | GoTriangle | US 15 / US 501 from Durham to Carrboro. | Construct bus rapid transit lanes. |  | Durham, Orange | 5, 7 | Triangle West TPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 40000000
TP-0005 | Public Transportation (Transit) | STI (Prioritization) | Fayetteville Area System of Transit (FAST) | Route 3. | Add shelter packages to existing stops. |  | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | CONSTRUCTION | 43000 | FY 2028: 43000
TP-0006 | Public Transportation (Transit) | STI (Prioritization) | Harnett Area Rural Transit System | Systemwide. | Purchase two expansion vehicles to support on demand services. |  | Harnett | 6 | Fayetteville Area MPO, Capital Area MPO, Mid-Carolina RPO |  | Division 6 |  | T | CAPITAL | 260000 | FY 2028: 260000
TP-4732A | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding for planning assistance |  | Durham, Orange | 5, 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 666000 | FY 2026: 74000; FY 2027: 74000; FY 2028: 74000; FY 2029: 74000
TP-4732A | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding for planning assistance |  | Durham, Orange | 5, 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 666000 | FY 2026: 74000; FY 2027: 74000; FY 2028: 74000; FY 2029: 74000
TP-4732A | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding for planning assistance |  | Durham, Orange | 5, 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 5310000 | FY 2026: 590000; FY 2027: 590000; FY 2028: 590000; FY 2029: 590000
TP-4732B | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding for planning assistance |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 666000 | FY 2026: 74000; FY 2027: 74000; FY 2028: 74000; FY 2029: 74000
TP-4732B | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding for planning assistance |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 666000 | FY 2026: 74000; FY 2027: 74000; FY 2028: 74000; FY 2029: 74000
TP-4732B | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding for planning assistance |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 5310000 | FY 2026: 590000; FY 2027: 590000; FY 2028: 590000; FY 2029: 590000
TP-4908 | Public Transportation (Transit) | Planning | Jacksonville Transit | Systemwide | Funding for planning assistance -5307 |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | PLANNING | 75000 | FY 2026: 10000; FY 2027: 10000
TP-4908 | Public Transportation (Transit) | Planning | Jacksonville Transit | Systemwide | Funding for planning assistance -5307 |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | PLANNING | 75000 | FY 2026: 10000; FY 2027: 10000
TP-4908 | Public Transportation (Transit) | Planning | Jacksonville Transit | Systemwide | Funding for planning assistance -5307 |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | PLANNING | 595000 | FY 2026: 78000; FY 2027: 80000
TP-5100A | Public Transportation (Transit) | Planning | Capital Area Transit | Various locations | Funding for planning assistance -5303 |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 438000 | FY 2026: 75000; FY 2027: 75000; FY 2028: 75000
TP-5100A | Public Transportation (Transit) | Planning | Capital Area Transit | Various locations | Funding for planning assistance -5303 |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 441000 | FY 2026: 75000; FY 2027: 75000; FY 2028: 75000
TP-5100A | Public Transportation (Transit) | Planning | Capital Area Transit | Various locations | Funding for planning assistance -5303 |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 3525000 | FY 2026: 600000; FY 2027: 600000; FY 2028: 600000
TP-5100B | Public Transportation (Transit) | Planning | GoRaleigh | Various locations | Funding for planning assistance -5307 |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 900000 | FY 2026: 375000
TP-5100B | Public Transportation (Transit) | Planning | GoRaleigh | Various locations | Funding for planning assistance -5307 |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 1446000 | FY 2026: 375000
TP-5100B | Public Transportation (Transit) | Planning | GoRaleigh | Various locations | Funding for planning assistance -5307 |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 8980000 | FY 2026: 3000000
TP-5101 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | Systemwide | Funding for planning assistance - 5303 |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | PLANNING | 38000 | FY 2026: 19000
TP-5101 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | Systemwide | Funding for planning assistance - 5303 |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 38000 | FY 2026: 19000
TP-5101 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | Systemwide | Funding for planning assistance - 5303 |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 410000 | FY 2026: 205000
TP-5102 | Public Transportation (Transit) | Planning | Jacksonville Transit | Systemwide | Funding for planning assistance - 5303 |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | PLANNING | 44000 | FY 2026: 6000; FY 2027: 6000
TP-5102 | Public Transportation (Transit) | Planning | Jacksonville Transit | Systemwide | Funding for planning assistance - 5303 |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | PLANNING | 44000 | FY 2026: 6000; FY 2027: 6000
TP-5102 | Public Transportation (Transit) | Planning | Jacksonville Transit | Systemwide | Funding for planning assistance - 5303 |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5303 | PLANNING | 247000 | FY 2026: 32000; FY 2027: 32000
TP-5103 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for planning assistance - 5303 |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 72000 | FY 2026: 8000; FY 2027: 8000; FY 2028: 8000; FY 2029: 8000; FY 2030: 8000
TP-5103 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for planning assistance - 5303 |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 82000 | FY 2026: 9000; FY 2027: 9000; FY 2028: 9000; FY 2029: 9000; FY 2030: 9000
TP-5103 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for planning assistance - 5303 |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 614000 | FY 2026: 67000; FY 2027: 67000; FY 2028: 67000; FY 2029: 67000; FY 2030: 67000
TP-5103B | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for planning assistance - 5303 |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 420000 | FY 2026: 40000; FY 2027: 40000; FY 2028: 40000; FY 2029: 40000; FY 2030: 40000
TP-5103B | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for planning assistance - 5303 |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 420000 | FY 2026: 40000; FY 2027: 40000; FY 2028: 40000; FY 2029: 40000; FY 2030: 40000
TP-5103B | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for planning assistance - 5303 |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3360000 | FY 2026: 320000; FY 2027: 320000; FY 2028: 320000; FY 2029: 320000; FY 2030: 320000
TP-5104 | Public Transportation (Transit) | Capital (Non-STI) | High point Transit System | Systemwide | Funding for planning assistance - 5303 |  | Guilford | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 36000 | FY 2026: 4000; FY 2027: 4000; FY 2028: 4000; FY 2029: 4000
TP-5104 | Public Transportation (Transit) | Capital (Non-STI) | High point Transit System | Systemwide | Funding for planning assistance - 5303 |  | Guilford | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 36000 | FY 2026: 4000; FY 2027: 4000; FY 2028: 4000; FY 2029: 4000
TP-5104 | Public Transportation (Transit) | Capital (Non-STI) | High point Transit System | Systemwide | Funding for planning assistance - 5303 |  | Guilford | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 324000 | FY 2026: 36000; FY 2027: 36000; FY 2028: 36000; FY 2029: 36000
TP-5105 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | Funding for planning assistance - 5303 |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 60000
TP-5105 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | Funding for planning assistance - 5303 |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 60000
TP-5105 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | Funding for planning assistance - 5303 |  | Forsyth | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 498000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Council of Governments | Systemwide | Funding for planning assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | S | PLANNING | 32000 | FY 2026: 8000; FY 2027: 8000; FY 2028: 8000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Council of Governments | Systemwide | Funding for planning assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L(M) | PLANNING | 32000 | FY 2026: 8000; FY 2027: 8000; FY 2028: 8000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Council of Governments | Systemwide | Funding for planning assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5303 | PLANNING | 228000 | FY 2026: 57000; FY 2027: 57000; FY 2028: 57000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Council of Governments | Systemwide | Funding for planning assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L(M) | ADMINISTRATIVE | 17000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Council of Governments | Systemwide | Funding for planning assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | HF | ADMINISTRATIVE | 17000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Council of Governments | Systemwide | Funding for planning assistance. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5303 | ADMINISTRATIVE | 127000
TP-5107 | Public Transportation (Transit) | Planning | Greenville Area Transit | Systemwide | Funding for planning assistance - 5303 |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 47000 | FY 2026: 7000; FY 2027: 7000; FY 2028: 7000; FY 2029: 7000
TP-5107 | Public Transportation (Transit) | Planning | Greenville Area Transit | Systemwide | Funding for planning assistance - 5303 |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 47000 | FY 2026: 7000; FY 2027: 7000; FY 2028: 7000; FY 2029: 7000
TP-5107 | Public Transportation (Transit) | Planning | Greenville Area Transit | Systemwide | Funding for planning assistance - 5303 |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 378000 | FY 2026: 54000; FY 2027: 54000; FY 2028: 54000; FY 2029: 54000
TP-5108 | Public Transportation (Transit) | Capital (Non-STI) | GoDurham | Various locations | Funding for planning assistance -5303 |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 56000
TP-5108 | Public Transportation (Transit) | Capital (Non-STI) | GoDurham | Various locations | Funding for planning assistance -5303 |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 56000
TP-5108 | Public Transportation (Transit) | Capital (Non-STI) | GoDurham | Various locations | Funding for planning assistance -5303 |  | Durham | 5 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 448000
TP-5113 | Public Transportation (Transit) | Capital (Non-STI) | City of Asheville Transit | Systemwide | Funding for planning assistance. |  | Buncombe | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 450000 | FY 2026: 135000
TP-5114 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Systemwide | Funding for planning assistance. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 320000 | FY 2026: 62000
TP-5114 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Systemwide | Funding for planning assistance. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 320000 | FY 2026: 62000
TP-5114 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Systemwide | Funding for planning assistance. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 2578000 | FY 2026: 496000
TP-5114 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Systemwide | Funding for planning assistance. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 17000
TP-5116 | Public Transportation (Transit) | Capital (Non-STI) | Goldsboro - Wayne Transportation Authority | Various locations | Funding for planning assistance |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 36000 | FY 2026: 6000; FY 2027: 6000; FY 2028: 6000
TP-5116 | Public Transportation (Transit) | Capital (Non-STI) | Goldsboro - Wayne Transportation Authority | Various locations | Funding for planning assistance |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 40000 | FY 2026: 7000; FY 2027: 7000; FY 2028: 7000
TP-5116 | Public Transportation (Transit) | Capital (Non-STI) | Goldsboro - Wayne Transportation Authority | Various locations | Funding for planning assistance |  | Wayne | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 316000 | FY 2026: 54000; FY 2027: 54000; FY 2028: 54000
TP-5118 | Public Transportation (Transit) | Capital (Non-STI) | Concord Kannapolis Area Transit | Systemwide | Funding for planning assistance. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 208000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
TP-5118 | Public Transportation (Transit) | Capital (Non-STI) | Concord Kannapolis Area Transit | Systemwide | Funding for planning assistance. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 208000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
TP-5118 | Public Transportation (Transit) | Capital (Non-STI) | Concord Kannapolis Area Transit | Systemwide | Funding for planning assistance. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 1615000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
TP-5150 | Public Transportation (Transit) | Planning | City of Salisbury | Systemwide | Funding for planning assistance -5303 |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 20000
TP-5150 | Public Transportation (Transit) | Planning | City of Salisbury | Systemwide | Funding for planning assistance -5303 |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 150000
TP-5154 | Public Transportation (Transit) | Planning | Statewide | Systemwide | 5304 Planning. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | PLANNING | 954000 | FY 2026: 112000; FY 2027: 114000
TP-5154 | Public Transportation (Transit) | Planning | Statewide | Systemwide | 5304 Planning. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5303 | PLANNING | 4770000 | FY 2026: 560000; FY 2027: 570000
TP-5156 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Lynx Blue Line near Iverson Way in South Charlotte | Add a light rail station. |  | Mecklenburg | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION. | Public Transit |  | L | CAPITAL | 7582000
TP-5159 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Systemwide | Funding for Lynx Silver Line TOD planning in cooperation with CATS, CRTPO, and GCLMPO. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | PLANNING | 382000 | FY 2026: 280000
TP-5159 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Systemwide | Funding for Lynx Silver Line TOD planning in cooperation with CATS, CRTPO, and GCLMPO. |  | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | 5303 | PLANNING | 1527000 | FY 2026: 1122000
TP-5160 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. |  | Wake | 5 | Capital Area MPO |  | Public Transit
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | PLANNING | 4605000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | FUZ | PLANNING | 1195000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5309 | PLANNING | 5950000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 1757000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5309 | RIGHT-OF-WAY | 1027000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | FUZ | RIGHT-OF-WAY | 302000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 39008000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5309 | CONSTRUCTION | 24336000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | FUZ | CONSTRUCTION | 5163000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | ARP | CAPITAL | 5404000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | 5309 | CAPITAL | 3687000
TP-5160B | Public Transportation (Transit) | Capital (Non-STI) | New Bern Avenue | New Bern Avenue. Downtown to New Hope Road | Betterment funding to construct bus rapid transit. | 3.54 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 1628000
TQ-6186 | Public Transportation (Transit) | Capital (Non-STI) | Asheville Redefines Transit | Various locations | Funding for traditional projects - 5310 |  | Buncombe | 13 | French Broad River MPO |  | Public Transit
TQ-6187 | Public Transportation (Transit) | Operations and Maintenance | City of Asheville Transit | Systemwide | Funding for 5310 other projects. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 177000
TQ-6187 | Public Transportation (Transit) | Operations and Maintenance | City of Asheville Transit | Systemwide | Funding for 5310 other projects. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | 5310 | OPERATIONS | 177000
TQ-6507 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for operating assistance - elderly and disabled person. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23 | Public Transit |  | L | OPERATIONS | 474000
TQ-6507 | Public Transportation (Transit) | Operations and Maintenance | Western Piedmont Regional Transit Authority | Systemwide | Funding for operating assistance - elderly and disabled person. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23 | Public Transit |  | 5310 | OPERATIONS | 474000
TQ-6513 | Public Transportation (Transit) | Operations and Maintenance | Cape Fear Public Transportation Authority (WAVE) | Route 205 | Provide Operating Support For Fixed Bus Route 205 Long Leaf Park Which Services Novant Hospital And The Medical Center. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 433000 | FY 2026: 132000
TQ-6513 | Public Transportation (Transit) | Operations and Maintenance | Cape Fear Public Transportation Authority (WAVE) | Route 205 | Provide Operating Support For Fixed Bus Route 205 Long Leaf Park Which Services Novant Hospital And The Medical Center. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | OPERATIONS | 433000 | FY 2026: 132000
TQ-6514 | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for elderly and disabled projects (traditional). |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 316000 | FY 2026: 32000; FY 2027: 32000; FY 2028: 32000; FY 2029: 32000; FY 2030: 32000
TQ-6514 | Public Transportation (Transit) | Operations and Maintenance | Fayetteville Area System of Transit (FAST) | Various locations | Funding for elderly and disabled projects (traditional). |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | OPERATIONS | 1268000 | FY 2026: 128000; FY 2027: 128000; FY 2028: 128000; FY 2029: 128000; FY 2030: 128000
TQ-6597 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | L | OPERATIONS | 1860000 | FY 2026: 465000
TQ-6597 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Various locations | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | OPERATIONS | 1860000 | FY 2026: 465000
TQ-6702 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Systemwide | FTA Section 5310 Winston-Salem allocation set aside for competitive grant to eligible agencies to assist in meeting the transportation needs of low income, disabled, and elderly populations. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 235000
TQ-6702 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Systemwide | FTA Section 5310 Winston-Salem allocation set aside for competitive grant to eligible agencies to assist in meeting the transportation needs of low income, disabled, and elderly populations. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5310 | OPERATIONS | 937000
TQ-6782 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Systemwide | Funding set aside for COMPETE Grant to eligible agencies to assist in meeting the needs of low income, disabled and elderly populations |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 724000 | FY 2026: 90000; FY 2027: 90000
TQ-6782 | Public Transportation (Transit) | Operations and Maintenance | Winston Salem Transit | Systemwide | Funding set aside for COMPETE Grant to eligible agencies to assist in meeting the needs of low income, disabled and elderly populations |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5310 | OPERATIONS | 2883000 | FY 2026: 358000; FY 2027: 358000
TQ-6783 | Public Transportation (Transit) | Capital (Non-STI) | Greensboro Transit Authority | Various locations | Funding for section 5310 for Capital project. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 108000 | FY 2026: 54000
TQ-6783 | Public Transportation (Transit) | Capital (Non-STI) | Greensboro Transit Authority | Various locations | Funding for section 5310 for Capital project. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5310 | CAPITAL | 430000 | FY 2026: 215000
TQ-6954 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Funding for section 5310 for Rural project. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | L | OPERATIONS | 9832000
TQ-6954 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Funding for section 5310 for Rural project. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5310 | OPERATIONS | 16103000
TQ-6957 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | L | OPERATIONS | 489000 | FY 2026: 257000; FY 2027: 232000
TQ-6957 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | OPERATIONS | 489000 | FY 2026: 257000; FY 2027: 232000
TQ-7000 | Public Transportation (Transit) | Operations and Maintenance | Greensboro Transit Authority | Systemwide | Funding for section 5310 for project administration. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 56000 | FY 2026: 28000
TQ-7005 | Public Transportation (Transit) | Operations and Maintenance | Cape Fear PublicTransportation Authority (WAVE) | Systemwide | Funding for Section 5310 Program. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 180000 | FY 2026: 38000
TQ-7009 | Public Transportation (Transit) | Operations and Maintenance | Charlotte Area Transit System (CATS) | Systemwide | Funding for agency administration for 5310 Program. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL TO FY 20-25 FOR THE ADMINISTRATIVE OVERSIGHT OF THE 5310 PROGRAM AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | ADMINISTRATIVE | 279000 | FY 2026: 147000; FY 2027: 132000
TQ-7010 | Public Transportation (Transit) | Capital (Non-STI) | City of Asheville Transit | Systemwide | Funding for agency administration for 5310 Program. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 50000
TQ-7010 | Public Transportation (Transit) | Capital (Non-STI) | City of Asheville Transit | Systemwide | Funding for agency administration for 5310 Program. |  | Buncombe | 13 | French Broad River MPO |  | Public Transit |  | 5310 | CAPITAL | 50000
TQ-8019 | Public Transportation (Transit) | Capital (Non-STI) | Cape Fear Public Transportation Authority (WAVE) | Systemwide | Funding for Section 5310 funds to administer program. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 74000 | FY 2026: 22000
TQ-8019 | Public Transportation (Transit) | Capital (Non-STI) | Cape Fear Public Transportation Authority (WAVE) | Systemwide | Funding for Section 5310 funds to administer program. |  | New Hanover | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | CAPITAL | 297000 | FY 2026: 90000
TQ-9001 | Public Transportation (Transit) | Capital (Non-STI) | Cape Fear Public Transportation Authority (WAVE) | Systemwide | Funding for organizations to remove transportation barriers and connect elders and individuals with disabilities to needed resources. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 97000 | FY 2026: 30000
TQ-9001 | Public Transportation (Transit) | Capital (Non-STI) | Cape Fear Public Transportation Authority (WAVE) | Systemwide | Funding for organizations to remove transportation barriers and connect elders and individuals with disabilities to needed resources. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5310 | CAPITAL | 471000 | FY 2026: 117000
TQ-9033 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | S | CAPITAL | 146000 | FY 2027: 146000
TQ-9033 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | L | CAPITAL | 266000 | FY 2026: 162000
TQ-9033 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding for operating projects for enhanced mobility to seniors and individuals with disabilities. |  | Mecklenburg | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | CAPITAL | 2064000 | FY 2026: 647000; FY 2027: 583000
TQ-9037 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | 5310 Administration and Capital. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 3468000 | FY 2026: 1640000
TQ-9037 | Public Transportation (Transit) | Capital (Non-STI) | GoRaleigh | Systemwide | 5310 Administration and Capital. |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | CAPITAL | 13870000 | FY 2026: 6560000
TQ-9038 | Public Transportation (Transit) | Capital (Non-STI) | Statewide | Systemwide | Funding for 5310 capital projects for rural areas and small urban areas. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5310 | CAPITAL | 2850000
TQ-9039 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Regional Transit Authority | Systemwide | Purchase service vehicles. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 260000 | FY 2026: 30000; FY 2027: 30000
TQ-9039 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Regional Transit Authority | Systemwide | Purchase service vehicles. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5310 | CAPITAL | 1040000 | FY 2026: 120000; FY 2027: 120000
TS-4758 | Public Transportation (Transit) | Capital (Non-STI) | Greensboro Transit Authority | Systemwide | Safety and security. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | L | CAPITAL | 68000 | FY 2026: 17000; FY 2027: 17000; FY 2028: 17000
TS-4758 | Public Transportation (Transit) | Capital (Non-STI) | Greensboro Transit Authority | Systemwide | Safety and security. |  | Guilford | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | 5307 | CAPITAL | 264000 | FY 2026: 66000; FY 2027: 66000; FY 2028: 66000
TS-4900Z | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Statewide RTAP. |  | Statewide | 99 | Statewide Project | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | RTAP | ADMINISTRATIVE | 480000
TS-5104 | Public Transportation (Transit) | Capital (Non-STI) | Capital Area Transit | Systemwide | Safety and security minimum 1 % set aside |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 259000 | FY 2026: 50000; FY 2027: 50000
TS-5104 | Public Transportation (Transit) | Capital (Non-STI) | Capital Area Transit | Systemwide | Safety and security minimum 1 % set aside |  | Wake | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1033000 | FY 2026: 200000; FY 2027: 200000
TS-5107 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Safety and security minimum 1 % set aside |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1233000 | FY 2026: 229000; FY 2027: 184000; FY 2028: 374000
TS-5107 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Safety and security minimum 1 % set aside |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4932000 | FY 2026: 917000; FY 2027: 737000; FY 2028: 1495000
TS-5109 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Safety and security minimum 1 % set aside |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 60000 | FY 2026: 6000; FY 2027: 6000; FY 2028: 6000; FY 2029: 6000; FY 2030: 6000
TS-5109 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Safety and security minimum 1 % set aside |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 240000 | FY 2026: 24000; FY 2027: 24000; FY 2028: 24000; FY 2029: 24000; FY 2030: 24000
TS-5112 | Public Transportation (Transit) | Capital (Non-STI) | Greenville Area Transit | Systemwide | Safety and security minimum 1 % set aside |  | Pitt | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 34000
TS-5113 | Public Transportation (Transit) | Capital (Non-STI) | High Point Transit System | Systemwide | Funding for safety and security, minimum set 1 % aside. |  | Davidson, Guilford, Randolph | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 18000 | FY 2026: 2000; FY 2027: 2000; FY 2028: 2000; FY 2029: 2000
TS-5113 | Public Transportation (Transit) | Capital (Non-STI) | High Point Transit System | Systemwide | Funding for safety and security, minimum set 1 % aside. |  | Davidson, Guilford, Randolph | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 126000 | FY 2026: 14000; FY 2027: 14000; FY 2028: 14000; FY 2029: 14000
TS-5114 | Public Transportation (Transit) | Capital (Non-STI) | Jacksonville Transit | Systemwide | Funding for safety and security, minimum set 1 % aside. |  | Onslow | 3 | Jacksonville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 116000
TS-5116 | Public Transportation (Transit) | Capital (Non-STI) | Concord Kannapolis Area Transit | Systemwide | Safety and security minimum 1 % set aside |  | Cabarrus | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
TS-5119 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Durham, Orange | 5, 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 16000 | FY 2026: 2000; FY 2027: 2000; FY 2028: 2000; FY 2029: 2000
TS-5119 | Public Transportation (Transit) | Capital (Non-STI) | GoTriangle | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Durham, Orange | 5, 7 | Triangle West TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 140000 | FY 2026: 17000; FY 2027: 2000; FY 2028: 17000; FY 2029: 17000
TS-5120 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 25000
TS-5120 | Public Transportation (Transit) | Capital (Non-STI) | Winston Salem Transit | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Forsyth | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 102000
TS-5133 | Public Transportation (Transit) | Capital (Non-STI) | City Of Salisbury | Systemwide | Funding for safety and security, minimum set 1 % aside |  | Rowan | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 28000 | FY 2026: 7000; FY 2027: 7000; FY 2028: 7000
TS-7001 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Funding 5329 State safety and oversight. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | S | ADMINISTRATIVE | 812000 | FY 2026: 70000; FY 2027: 70000
TS-7001 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Funding 5329 State safety and oversight. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | FED | ADMINISTRATIVE | 4224000 | FY 2026: 346000; FY 2027: 346000
TS-7001 | Public Transportation (Transit) | Operations and Maintenance | Statewide | Systemwide | Funding 5329 State safety and oversight. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | ADMINISTRATIVE | 70000 | FY 2027: 70000
TS-7002 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Regional Transit Authority | Systemwide | Funds for safety and security. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 96000 | FY 2026: 7000; FY 2027: 7000; FY 2028: 7000
TS-7002 | Public Transportation (Transit) | Capital (Non-STI) | Western Piedmont Regional Transit Authority | Systemwide | Funds for safety and security. |  | Alexander, Burke, Caldwell, Catawba | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5307 | CAPITAL | 390000 | FY 2026: 29000; FY 2027: 29000; FY 2028: 29000
TT-4907 | Public Transportation (Transit) | Capital (Non-STI) | Jacksonville Transit | Systemwide | Funding for Technology upgrade such as vehicle tracking, passenger information, data communication, traffic signal priority |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 228000 | FY 2026: 20000; FY 2027: 20000
TT-4907 | Public Transportation (Transit) | Capital (Non-STI) | Jacksonville Transit | Systemwide | Funding for Technology upgrade such as vehicle tracking, passenger information, data communication, traffic signal priority |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 912000 | FY 2026: 80000; FY 2027: 80000
TT-5204 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for technology replacement upgrades |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 35000 | FY 2027: 15000; FY 2030: 15000
TT-5204 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for technology replacement upgrades |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 35000 | FY 2027: 15000; FY 2030: 15000
TT-5204 | Public Transportation (Transit) | Capital (Non-STI) | Fayetteville Area System of Transit (FAST) | Systemwide | Funding for technology replacement upgrades |  | Cumberland | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 280000 | FY 2027: 120000; FY 2030: 120000
TU-0001 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Lynx Silver Line light rail | Funding for planning. | 28.84 | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | L | PLANNING | 49647000
TU-0001 | Public Transportation (Transit) | Planning | Charlotte Area Transit System (CATS) | Lynx Silver Line light rail | Funding for planning. | 28.84 | Mecklenburg | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | PLANNING | 5353000
TU-0003 | Public Transportation (Transit) | Planning | NCDOT | Various locations | H.O.P.E Grant opportunity from the FTA. Discretionary Grant awarded by FTA. Planning and design in preparation for electric vehicle deployment. |  | Statewide | 99 | Statewide Project | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | PLANNING | 32000
TU-0003 | Public Transportation (Transit) | Planning | NCDOT | Various locations | H.O.P.E Grant opportunity from the FTA. Discretionary Grant awarded by FTA. Planning and design in preparation for electric vehicle deployment. |  | Statewide | 99 | Statewide Project | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | 5312 | PLANNING | 110000
TU-0003 | Public Transportation (Transit) | Planning | NCDOT | Various locations | H.O.P.E Grant opportunity from the FTA. Discretionary Grant awarded by FTA. Planning and design in preparation for electric vehicle deployment. |  | Statewide | 99 | Statewide Project | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | 5303 | PLANNING | 80000
TU-0004 | Public Transportation (Transit) | Planning | CSX S-LINE | Sanford to Henderson | Transit oriented planning |  | Wake, Lee, Vance | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | UNDERWAY. "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | Public Transit |  | S | PLANNING | 100000
TU-0004 | Public Transportation (Transit) | Planning | CSX S-LINE | Sanford to Henderson | Transit oriented planning |  | Wake, Lee, Vance | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | UNDERWAY. "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | Public Transit |  | FED | PLANNING | 900000
TU-0004 | Public Transportation (Transit) | Planning | CSX S-LINE | Sanford to Henderson | Transit oriented planning |  | Wake, Lee, Vance | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | UNDERWAY. "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | Public Transit |  | L | PLANNING | 505000
TU-0005 | Public Transportation (Transit) | Planning | NCDOT | Systemwide | 5303 Metropolitan Transportation Planning Funds For FTA Grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | S | PLANNING | 1081000
TU-0005 | Public Transportation (Transit) | Planning | NCDOT | Systemwide | 5303 Metropolitan Transportation Planning Funds For FTA Grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | PLANNING | 1081000
TU-0005 | Public Transportation (Transit) | Planning | NCDOT | Systemwide | 5303 Metropolitan Transportation Planning Funds For FTA Grants. |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5303 | PLANNING | 8647000
TU-0006 | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding 5329 State safety and oversight. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | CMAQ | PLANNING | 650000
TU-0006 | Public Transportation (Transit) | Planning | GoTriangle | Systemwide | Funding 5329 State safety and oversight. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 90000
TU-0007 | Public Transportation (Transit) | Planning | GoRaleigh | Systemwide | Gotriangle Wake county bus plan update. |  | Wake | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 860000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Systemwide | NCDOT-IMD Section 5304 program funds to support the IMD urban transit technical assistance activities |  | Statewide | 99 | Statewide Project |  | Public Transit |  | S | PLANNING | 3000000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Systemwide | NCDOT-IMD Section 5304 program funds to support the IMD urban transit technical assistance activities |  | Statewide | 99 | Statewide Project |  | Public Transit |  | L | PLANNING | 3227000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Systemwide | NCDOT-IMD Section 5304 program funds to support the IMD urban transit technical assistance activities |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5303 | PLANNING | 10834000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | Systemwide | NCDOT-IMD Section 5304 program funds to support the IMD urban transit technical assistance activities |  | Statewide | 99 | Statewide Project |  | Public Transit |  | 5303 | ADMINISTRATIVE | 370000
TU-0013 | Public Transportation (Transit) | Planning | GoDurham | Durham Station | Improvements to Durham station to expand equitable access to transit, improve station amenities, increase connection to employment, health care and educational opportunities and construct 8 bus bays, redesigned bus lanes and placed new pavement. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | PLANNING | 12663000
TU-0013 | Public Transportation (Transit) | Planning | GoDurham | Durham Station | Improvements to Durham station to expand equitable access to transit, improve station amenities, increase connection to employment, health care and educational opportunities and construct 8 bus bays, redesigned bus lanes and placed new pavement. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5339(b) | PLANNING | 21532000
TU-0016 | Public Transportation (Transit) | Planning | Integrated Mobility Division | Various locations | This planning project will fund the planning of mobility hubs in seven communities along the S-line passenger rail corridor. Participating communities include Sanford, Apex, Wake Forest, Youngsville, Henderson, Franklinton, and Norlina. |  | Franklin, Lee, Vance, Warren, Wake | 5, 8 | Statewide Project | DP FUNDING REPRESENTS RAISE GRANT FUNDS | Public Transit |  | DP | PLANNING | 3400000
TU-0016 | Public Transportation (Transit) | Planning | Integrated Mobility Division | Various locations | This planning project will fund the planning of mobility hubs in seven communities along the S-line passenger rail corridor. Participating communities include Sanford, Apex, Wake Forest, Youngsville, Henderson, Franklinton, and Norlina. |  | Franklin, Lee, Vance, Warren, Wake | 5, 8 | Statewide Project | DP FUNDING REPRESENTS RAISE GRANT FUNDS | Public Transit |  | L | PLANNING | 1030000 | FY 2026: 45000; FY 2027: 45000; FY 2028: 45000
TU-0016 | Public Transportation (Transit) | Planning | Integrated Mobility Division | Various locations | This planning project will fund the planning of mobility hubs in seven communities along the S-line passenger rail corridor. Participating communities include Sanford, Apex, Wake Forest, Youngsville, Henderson, Franklinton, and Norlina. |  | Franklin, Lee, Vance, Warren, Wake | 5, 8 | Statewide Project | DP FUNDING REPRESENTS RAISE GRANT FUNDS | Public Transit |  | 5307 | PLANNING | 740000 | FY 2026: 185000; FY 2027: 185000; FY 2028: 185000
TU-0017 | Public Transportation (Transit) | Planning | Alamance County Transportation Authority | Various locations | Funding for ACTA planning and feasibility study |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | L | PLANNING | 30000
TU-0017 | Public Transportation (Transit) | Planning | Alamance County Transportation Authority | Various locations | Funding for ACTA planning and feasibility study |  | Alamance | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | PLANNING | 120000
TU-0018 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | J. Douglas Galyon Depot area. | Conduct transit oriented development study. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 20005(b) | PLANNING | 500000
TU-0019 | Public Transportation (Transit) | Planning | GoDurham | Systemwide | Fund planning assistance for GoDurham. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | S | PLANNING | 111000 | FY 2026: 27000; FY 2027: 28000; FY 2028: 30000
TU-0019 | Public Transportation (Transit) | Planning | GoDurham | Systemwide | Fund planning assistance for GoDurham. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | L | PLANNING | 111000 | FY 2026: 27000; FY 2027: 28000; FY 2028: 30000
TU-0019 | Public Transportation (Transit) | Planning | GoDurham | Systemwide | Fund planning assistance for GoDurham. |  | Durham | 5 | Triangle West TPO |  | Public Transit |  | 5303 | PLANNING | 886000 | FY 2026: 215000; FY 2027: 227000; FY 2028: 238000
TU-0020 | Public Transportation (Transit) | Planning | City of Asheville Transit | Various | FY 2021 AOPP - Areas of consistent poverty planning survey and engagement |  | Buncombe | 13 | French Broad River MPO | DP FUNDS REPRESENT FTA DISCRETIONARY GRANT. | Public Transit |  | DP | PLANNING | 268000
TU-0020 | Public Transportation (Transit) | Planning | City of Asheville Transit | Various | FY 2021 AOPP - Areas of consistent poverty planning survey and engagement |  | Buncombe | 13 | French Broad River MPO | DP FUNDS REPRESENT FTA DISCRETIONARY GRANT. | Public Transit |  | L | PLANNING | 67000
TU-0021 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | Systemwide | Transit planning |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | S | PLANNING | 30000
TU-0021 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | Systemwide | Transit planning |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | PLANNING | 30000
TU-0021 | Public Transportation (Transit) | Planning | Greensboro Transit Authority | Systemwide | Transit planning |  | Guilford | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5303 | PLANNING | 242000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Major investment study/alternative analysis for bus rapid transit extension to Research Triangle Park (RTP) and Clayton. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 955000 | FY 2026: 77000; FY 2027: 80000 | 167000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Major investment study/alternative analysis for bus rapid transit extension to Research Triangle Park (RTP) and Clayton. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 955000 | FY 2026: 77000; FY 2027: 80000 | 167000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Major investment study/alternative analysis for bus rapid transit extension to Research Triangle Park (RTP) and Clayton. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 5944000 | FY 2026: 619000; FY 2027: 638000 | 1333000
TW-5102A | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding for bridge inspections and repairs. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 120000 | FY 2026: 30000; FY 2027: 30000; FY 2028: 30000
TW-5102A | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding for bridge inspections and repairs. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 400000 | FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
TW-5102A | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | Funding for bridge inspections and repairs. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 1600000 | FY 2026: 400000; FY 2027: 400000; FY 2028: 400000
TW-5102B | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Fixed guideway | Funding for bridge inspections and emergency repairs. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 573000 | FY 2026: 328000; FY 2027: 4000
TW-5102B | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Fixed guideway | Funding for bridge inspections and emergency repairs. |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FMOD | CONSTRUCTION | 3550000 | FY 2026: 2276000; FY 2027: 29000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | STATE OF GOOD REPAIR - BUS |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 1390000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | STATE OF GOOD REPAIR - BUS |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1390000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | STATE OF GOOD REPAIR - BUS |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1992000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | Charlotte Area Transit System (CATS) | Systemwide | STATE OF GOOD REPAIR - BUS |  | Mecklenburg | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 11110000
U-0071 | Highway | Transition | New Route | East End Connector, NC 147 (Durham Freeway) to north of NC 98 in Durham. | Construct four-lane divided freeway with auxiliary lanes, part on new location. | 2.52 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 219683000
U-0209 | Highway | Pre-STI (Historic) | US 74 (Independence Boulevard) | Brookshire Freeway to Idlewild Road in Charlotte. | Construct additional lanes and interchanges with Sharon Amity Road and Idlewild Road and safety improvements. | 1.4 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024 |  |  |  |  | 334267000
U-0209B | Highway | Pre-STI (Historic) |  |  |  |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE ROW | 10968000
U-0209B | Highway | Pre-STI (Historic) |  |  |  |  | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE CON | 1025000
U-0209BA | Highway | Pre-STI (Historic) |  |  |  |  | Mecklenburg | 10 | Charlotte Regional TPO | WORK TO BE CONSTRUCTED BY PROJECT U-6103 | Pre-STI (Transition)
U-2307 | Highway | STI (Prioritization) | McDonald Parkway | US 70 / US 321 to NC 127 in Hickory. | Construct multi-lanes, part on new location. | 6.6 | Catawba | 12 | Greater Hickory MPO | [5 empty] | 58010000
U-2307AA | Highway | Pre-STI (Historic) |  |  |  |  | Catawba | 12 | Greater Hickory MPO | COMPLETE
U-2307AB | Highway | Pre-STI (Historic) |  |  |  |  | Catawba | 12 | Greater Hickory MPO | COMPLETE
U-2307AD | Highway | Pre-STI (Historic) |  |  |  |  | Catawba | 12 | Greater Hickory MPO | COMPLETE
U-2307AE | Highway | Pre-STI (Historic) |  |  |  |  | Catawba | 12 | Greater Hickory MPO | COMPLETE
U-2307B | Highway | STI (Prioritization) | McDonald Parkway | SR 1453 (Springs Road) to NC 127. | Widen to multi-lanes. | 3.19 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 53800000 | FY 2026: 5918000; FY 2027: 12374000; FY 2028: 12374000; FY 2029: 12374000; FY 2030: 10760000
U-2307B | Highway | STI (Prioritization) | McDonald Parkway | SR 1453 (Springs Road) to NC 127. | Widen to multi-lanes. | 3.19 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | UTILITIES | 15700000 | FY 2026: 7850000; FY 2027: 7850000
U-2307B | Highway | STI (Prioritization) | McDonald Parkway | SR 1453 (Springs Road) to NC 127. | Widen to multi-lanes. | 3.19 | Catawba | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | CONSTRUCTION | 64700000 | FY 2029: 5823000; FY 2030: 16822000; FY 2031: 16175000; FY 2032: 14234000; FY 2033: 11646000
U-2307C | Highway | Pre-STI (Historic) |  |  |  |  | Catawba | 12 | Greater Hickory MPO | COMPLETE
U-2412 | Highway | STI (Prioritization) | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | Proposed US 311 Bypass in High Point to SR 1424 (Hilltop Road) in Greensboro. | Widen to multi-lanes, part on new location. | 7.8 | Guilford | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | [5 empty] | 127674000
U-2412A | Highway | STI (Prioritization) | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | US 311 Bypass to SR 4228 (Vickrey Chapel Road) | Widen roadway. | 3.61 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 64461000 | 4297000 | 4297000 | 4297000 | 4297000 | 4297000 | 4297000 | 4297000 | 4303000 | 2452000 | 2452000
U-2412A | Highway | STI (Prioritization) | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | US 311 Bypass to SR 4228 (Vickrey Chapel Road) | Widen roadway. | 3.61 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | CONSTRUCTION | 16138000
U-2412B | Highway | Pre-STI (Historic) | SR 1486 (Greensboro Road) / SR 4121 (High Point Road) | SR 4228 (Vickrey Chapel Road) to SR 1424 (Hilltop Road) | Widen roadway. | 4.35 | Guilford | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
U-2509 | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | West of Idlewild Road to I-485. | Upgrade roadway to expressway with express lanes and construct improvements on parallel routes. | 6.62 | Mecklenburg | 10 | Charlotte Regional TPO
U-2509AA | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Sharon Forest Drive and Harris Boulevard / Village Lake Drive intersections in Charlotte. | Construct grade separation at Sharon Forest Drive and construct interchange at Village Lake Drive. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 85100000 | FY 2026: 12765000; FY 2027: 15318000; FY 2028: 17020000; FY 2029: 17020000; FY 2030: 22977000
U-2509AA | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Sharon Forest Drive and Harris Boulevard / Village Lake Drive intersections in Charlotte. | Construct grade separation at Sharon Forest Drive and construct interchange at Village Lake Drive. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | Statewide Mobility |  | NHP | UTILITIES | 6500000 | FY 2026: 3250000; FY 2027: 3250000
U-2509AA | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Sharon Forest Drive and Harris Boulevard / Village Lake Drive intersections in Charlotte. | Construct grade separation at Sharon Forest Drive and construct interchange at Village Lake Drive. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | Statewide Mobility |  | NHP | CONSTRUCTION | 78500000 | FY 2031: 11775000; FY 2032: 21195000; FY 2033: 19625000; FY 2034: 14915000; FY 2035: 10990000
U-2509AB | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Sardis Road and SR 3473 (Sam Newell Road) intersections in Charlotte. | Construct interchanges at Sardis Road North and Sam Newell Road. Construct extension of Sardis Road North from US 74 to Arequipa Drive Extension and construct extension of Arequipa Drive from Sardis Road North Extension to Sam Newell Road. | 0.59 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 40700000 | FY 2026: 6105000; FY 2027: 7326000; FY 2028: 8140000; FY 2029: 8140000; FY 2030: 10989000
U-2509AB | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Sardis Road and SR 3473 (Sam Newell Road) intersections in Charlotte. | Construct interchanges at Sardis Road North and Sam Newell Road. Construct extension of Sardis Road North from US 74 to Arequipa Drive Extension and construct extension of Arequipa Drive from Sardis Road North Extension to Sam Newell Road. | 0.59 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | Statewide Mobility |  | NHP | UTILITIES | 5700000 | FY 2026: 2850000; FY 2027: 2850000
U-2509AB | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Sardis Road and SR 3473 (Sam Newell Road) intersections in Charlotte. | Construct interchanges at Sardis Road North and Sam Newell Road. Construct extension of Sardis Road North from US 74 to Arequipa Drive Extension and construct extension of Arequipa Drive from Sardis Road North Extension to Sam Newell Road. | 0.59 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | Statewide Mobility |  | NHP | CONSTRUCTION | 76000000 | FY 2030: 6840000; FY 2031: 21280000; FY 2032: 20520000; FY 2033: 15960000; FY 2034: 11400000
U-2509AC | Highway | STI (Prioritization) | Independence Pointe Parkway | Windsor Square Drive to NC 51. | Construct roadway on new location. | 0.7 | Mecklenburg | 10 | Charlotte Regional TPO | 0 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 5799000 | FY 2030: 825000; FY 2031: 1237000; FY 2032: 1237000; FY 2033: 1237000; FY 2034: 1263000
U-2509AC | Highway | STI (Prioritization) | Independence Pointe Parkway | Windsor Square Drive to NC 51. | Construct roadway on new location. | 0.7 | Mecklenburg | 10 | Charlotte Regional TPO | 0 | Statewide Mobility |  | NHP | UTILITIES | 3500000 | FY 2030: 1750000; FY 2031: 1750000
U-2509AC | Highway | STI (Prioritization) | Independence Pointe Parkway | Windsor Square Drive to NC 51. | Construct roadway on new location. | 0.7 | Mecklenburg | 10 | Charlotte Regional TPO | 0 | Statewide Mobility |  | NHP | CONSTRUCTION | 20400000 | FY 2033: 6936000; FY 2034: 7140000; FY 2035: 4080000 | 2244000
U-2509AD | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Matthews-Mint Hill Road intersection in Charlotte. | Construct interchange at Matthews-Mint Hill Road. Extend Northeast Parkway from Overcash Drive to Waiting Street. | 0.23 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 46800000 | FY 2026: 7956000; FY 2027: 10296000; FY 2028: 10296000; FY 2029: 8892000; FY 2030: 9360000
U-2509AD | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Matthews-Mint Hill Road intersection in Charlotte. | Construct interchange at Matthews-Mint Hill Road. Extend Northeast Parkway from Overcash Drive to Waiting Street. | 0.23 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | Statewide Mobility |  | NHP | UTILITIES | 2600000 | FY 2026: 1300000; FY 2027: 1300000
U-2509AD | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Matthews-Mint Hill Road intersection in Charlotte. | Construct interchange at Matthews-Mint Hill Road. Extend Northeast Parkway from Overcash Drive to Waiting Street. | 0.23 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | Statewide Mobility |  | NHP | CONSTRUCTION | 35700000 | FY 2029: 357000; FY 2030: 13566000; FY 2031: 10353000; FY 2032: 6783000; FY 2033: 4641000
U-2509B | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | West of SR 3143 (Idlewild Road) to Wallace Lane. | Construct additional general purpose and express lanes. Construct express lane interchange on west side of Conference Drive. This is a toll project (express lanes only). | 0.95 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT M1 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 8499000 | FY 2030: 1395000; FY 2031: 2092000; FY 2032: 2092000; FY 2033: 1220000; FY 2034: 1700000
U-2509B | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | West of SR 3143 (Idlewild Road) to Wallace Lane. | Construct additional general purpose and express lanes. Construct express lane interchange on west side of Conference Drive. This is a toll project (express lanes only). | 0.95 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT M1 | Statewide Mobility |  | NHP | UTILITIES | 2100000 | FY 2030: 1050000; FY 2031: 1050000
U-2509B | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | West of SR 3143 (Idlewild Road) to Wallace Lane. | Construct additional general purpose and express lanes. Construct express lane interchange on west side of Conference Drive. This is a toll project (express lanes only). | 0.95 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT M1 | Statewide Mobility |  | NHP | CONSTRUCTION | 75100000 | FY 2033: 9763000; FY 2034: 21779000; FY 2035: 18775000 | 24783000
U-2509C | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Wallace Lane to SR 3356 (Sardis Road). | Construct additional general purpose and express lanes. Construct express lane interchange at Sardis Road. This is a toll project (express lanes only). | 2.45 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT M2 | Not Funded |  | NHP | RIGHT-OF-WAY | 39199000 | [10 empty] | 39199000
U-2509C | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Wallace Lane to SR 3356 (Sardis Road). | Construct additional general purpose and express lanes. Construct express lane interchange at Sardis Road. This is a toll project (express lanes only). | 2.45 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT M2 | Not Funded |  | NHP | UTILITIES | 5600000 | [10 empty] | 5600000
U-2509C | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | Wallace Lane to SR 3356 (Sardis Road). | Construct additional general purpose and express lanes. Construct express lane interchange at Sardis Road. This is a toll project (express lanes only). | 2.45 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT M2 | Not Funded |  | NHP | CONSTRUCTION | 70349000 | [10 empty] | 70349000
U-2509D | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | SR 3356 (Sardis Road) to I-485. | Construct additional general purpose and express lanes. Construct express lane interchanges at I-485 and east side of Conference Drive, and reconstruct interchange at NC 51 (Matthews Township Parkway). This is a toll project (express lanes only). | 3.23 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | Not Funded |  | NHP | RIGHT-OF-WAY | 92299000 | [10 empty] | 92299000
U-2509D | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | SR 3356 (Sardis Road) to I-485. | Construct additional general purpose and express lanes. Construct express lane interchanges at I-485 and east side of Conference Drive, and reconstruct interchange at NC 51 (Matthews Township Parkway). This is a toll project (express lanes only). | 3.23 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | Not Funded |  | NHP | UTILITIES | 10300000 | [10 empty] | 10300000
U-2509D | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | SR 3356 (Sardis Road) to I-485. | Construct additional general purpose and express lanes. Construct express lane interchanges at I-485 and east side of Conference Drive, and reconstruct interchange at NC 51 (Matthews Township Parkway). This is a toll project (express lanes only). | 3.23 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | Not Funded |  | NHP | CONSTRUCTION | 202205000 | [10 empty] | 202205000
U-2509E | Highway | STI (Prioritization) | Various | Krefeld Drive, Arequipa Drive, and Independence Pointe Parkway. | Construct roadway improvements, part on new location. | 3.39 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | Not Funded |  | T | RIGHT-OF-WAY | 43200000 | [10 empty] | 43200000
U-2509E | Highway | STI (Prioritization) | Various | Krefeld Drive, Arequipa Drive, and Independence Pointe Parkway. | Construct roadway improvements, part on new location. | 3.39 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | Not Funded |  | T | UTILITIES | 3500000 | [10 empty] | 3500000
U-2509E | Highway | STI (Prioritization) | Various | Krefeld Drive, Arequipa Drive, and Independence Pointe Parkway. | Construct roadway improvements, part on new location. | 3.39 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | Not Funded |  | T | CONSTRUCTION | 69400000 | [10 empty] | 69400000
U-2509EA | Highway | Locally Selected | SR 3156 (Margaret Wallace Road) | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 5568000 | FY 2026: 1392000; FY 2027: 2784000; FY 2028: 1392000
U-2509EA | Highway | Locally Selected | SR 3156 (Margaret Wallace Road) | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 3000000 | FY 2026: 750000; FY 2027: 1500000; FY 2028: 750000
U-2509EA | Highway | Locally Selected | SR 3156 (Margaret Wallace Road) | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | T(DA) | UTILITIES | 592000
U-2509EA | Highway | Locally Selected | SR 3156 (Margaret Wallace Road) | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | L | UTILITIES | 318000
U-2509EA | Highway | Locally Selected | SR 3156 (Margaret Wallace Road) | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | T(DA) | CONSTRUCTION | 3176000 | FY 2028: 1750000; FY 2029: 1160000; FY 2030: 266000
U-2509EA | Highway | Locally Selected | SR 3156 (Margaret Wallace Road) | Arequipa Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 1711000 | FY 2028: 943000; FY 2029: 625000; FY 2030: 143000
U-2509EB | Highway | STI (Prioritization) | Independence Pointe Parkway | Sardis Road to SR 3474 (Sam Newell Road). | Construct roadway on new location. | 0.63 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT C9 | Division 10 |  | T | RIGHT-OF-WAY | 1200000 | FY 2028: 252000; FY 2029: 348000; FY 2030: 336000; FY 2031: 24000; FY 2032: 240000
U-2509EB | Highway | STI (Prioritization) | Independence Pointe Parkway | Sardis Road to SR 3474 (Sam Newell Road). | Construct roadway on new location. | 0.63 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT C9 | Division 10 |  | T | UTILITIES | 190000 | FY 2028: 95000; FY 2029: 95000
U-2509EB | Highway | STI (Prioritization) | Independence Pointe Parkway | Sardis Road to SR 3474 (Sam Newell Road). | Construct roadway on new location. | 0.63 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENT C9 | Division 10 |  | T | CONSTRUCTION | 12000000 | FY 2031: 5280000; FY 2032: 4320000; FY 2033: 2400000
U-2519 | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | I-95 south of Fayetteville to west of NC 24 / NC 87 (Bragg Boulevard). | Construct freeway on new location. | 22.5 | Cumberland, Robeson | 6 | Fayetteville Area MPO, Lumber River RPO | [5 empty] | 544102000
U-2519AA | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | I-95 in Robeson County to south of SR 1118 (Parkton Road) in Cumberland County. | Construct freeway on new location. | 1.88 | Robeson, Cumberland | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | Region C |  | NHP | GARVEE CON | 123812000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000
U-2519AA | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | I-95 in Robeson County to south of SR 1118 (Parkton Road) in Cumberland County. | Construct freeway on new location. | 1.88 | Robeson, Cumberland | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | Region C |  | NHP | CONSTRUCTION | 125600000
U-2519AA | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | I-95 in Robeson County to south of SR 1118 (Parkton Road) in Cumberland County. | Construct freeway on new location. | 1.88 | Robeson, Cumberland | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | Region C |  | T(M) | CONSTRUCTION | 11030000
U-2519AB | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | South of SR 1118 (Parkton Road) to south of SR 1003 (Camden Road). | Construct freeway on new location. | 4.88 | Cumberland | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. WORK BEING ACCOMPLISHED UNDER U-2519AA. | Region C
U-2519BA | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | South of SR 1003 (Camden Road) to south of SR 1104 (Strickland Bridge Road). | Construct freeway on new location. | 3.96 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Region C |  | NHP | CONSTRUCTION | 161113000 | FY 2026: 15908000
U-2519BB | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | South of SR 1104 (Strickland Bridge Road) to south of US 401. | Construct freeway on new location. | 0.79 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. FUNDING AUTHORIZED UNDER U-2519BA. | Region C
U-2519CA | Highway | STI (Prioritization) | I-295 (Fayetteville Outer Loop) | South of US 401 to south of SR 1400 (Cliffdale Road). | Construct freeway on new location. | 2.63 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 10000
U-2519CB | Highway | Transition | I-295 (Fayetteville Outer Loop) | South of SR 1400 (Cliffdale Road) to east of SR 1415 (Yadkin Road). | Construct freeway on new location. | 4.69 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Pre-STI (Transition)
U-2519DA | Highway | Pre-STI (Historic) | I-295 (Fayetteville Outer Loop) | East of SR 1415 (Yadkin Road) to west of NC 24 / NC 87 (Bragg Boulvard) | Construct freeway on new location. |  | Cumberland | 6 | Fayetteville Area MPO | COMPLETE.
U-2519F | Highway | Pre-STI (Historic) | I-295 (Fayetteville Outer Loop) | Fayetteville outer loop. | Install ITS for Fayetteville outer loop. | 34 | Cumberland, Robeson | 6 | Fayetteville Area MPO, Lumber River RPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 5999000 | FY 2026: 2330000; FY 2027: 2944000; FY 2028: 725000
U-2523 | Highway | STI (Prioritization) | NC 279 | NC 7 to west of NC 275 in Dallas. | Widen to multi-lanes. | 3.6 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  |  |  | 17423000
U-2523A | Highway | Pre-STI (Historic) |  |  |  |  | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
U-2523B | Highway | STI (Prioritization) | NC 279 | North of SR 2275 (Robinson-Clemmer Road) to west of NC 275 in Dallas. | Widen to multi-lanes. | 1.94 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 17500000
U-2523B | Highway | STI (Prioritization) | NC 279 | North of SR 2275 (Robinson-Clemmer Road) to west of NC 275 in Dallas. | Widen to multi-lanes. | 1.94 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 4300000
U-2523B | Highway | STI (Prioritization) | NC 279 | North of SR 2275 (Robinson-Clemmer Road) to west of NC 275 in Dallas. | Widen to multi-lanes. | 1.94 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 39100000
U-2524 | Highway | STI (Prioritization) | I-73 / I-840 / Future I-840 / US 421 | Greensboro Western loop, north of I-85 to Lawndale Drive in Greensboro. | Construct freeway on new location. | 15 | Guilford | 7 | Greensboro Urban Area MPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 635532000
U-2524AA | Highway | Pre-STI (Historic) | SR 1546 (Guilford College Road) | South of SR 1541 (Wendover Avenue) to north of SR 1560 (Sapp Road) | Construct roadway. | 1.244 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524AB | Highway | Pre-STI (Historic) | I-73 / US 421 | Greensboro Western Loop, north of I-85 near SR 1129 (Groometown Road) to north of SR 4121 (High Point Road) | Construct roadway. | 4.207 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524AC | Highway | Pre-STI (Historic) | I-73 / US 421 | Greensboro Western Loop, north of SR 4121 (High Point Road) to south of I-40 | Construct roadway. | 3.471 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524AE | Highway | Pre-STI (Historic) | I-73 / US 421 | Greensboro Western Loop, interchange at proposed SR 4121 (High Point Road) relocation | Construct interchange. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION
U-2524BA | Highway | Pre-STI (Historic) | I-73 / I-840 | Greensboro Western Loop, south of I-40 to north of SR 2147 (West Friendly Avenue) | Construct roadway. | 2.429 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524BB | Highway | Pre-STI (Historic) | I-73 / I-840 | Greensboro Western Loop, north of SR 2147 (West Friendly Avenue) to north of SR 2176 (Bryan Boulevard) | Construct roadway. | 1.872 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524BC | Highway | Transition | I-73 / I-840 | SR 2085 (Bryan Boulevard) Interchange | Modify interchange, including auxiliary lanes, ITS, and Inman Road bridge replacement | 2 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE | Pre-STI (Transition)
U-2524C | Highway | Pre-STI (Historic) | Future I-840 | Greensboro Western Loop, north of SR 2176 (Bryan Boulevard) to US 220 (Battleground Avenue) | Construct roadway. | 3.54 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING $105.9 MILLION; PAYBACK FY 2013-2024 | Pre-STI (Transition) |  | NHP | GARVEE CON | 54285000
U-2524D | Highway | STI (Prioritization) | Future I-840 | Greensboro Western Loop, US 220 (Battleground Avenue) to SR 2303 (Lawndale Drive) | Construct roadway. | 1.64 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
U-2524E | Highway | Pre-STI (Historic) | I-73 / I-840 | Greensboro Western Loop | Install ITS. |  | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2525 | Highway | STI (Prioritization) | I-785 / I-840; Future I-785; Future I-840 | Greensboro Eastern Loop, Lawndale Drive to north of I-40 / I-85 in Greensboro. | Construct freeway on new location. | 12.6 | Guilford | 7 | Greensboro Urban Area MPO | [5 empty] | 367708000
U-2525A | Highway | Pre-STI (Historic) | I-785 / I-840 | Greensboro Eastern Loop, south of SR 3041 (Clapp Farms Road) to US 70 relocation | Relocate roadway. | 1.809 | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-2525B | Highway | Transition | I-785 / I-840 | Greensboro Eastern Loop, US 70 relocation to US 29 north of Greensboro | Relocate roadway. | 4.59 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
U-2525C | Highway | STI (Prioritization) | I-840 | Greensboro Eastern Loop, US 29 north of Greensboro to SR 2303 (Lawndale Drive) | Construct roadway. | 1.89 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | ENGINEERING | 8340000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000
U-2525C | Highway | STI (Prioritization) | I-840 | Greensboro Eastern Loop, US 29 north of Greensboro to SR 2303 (Lawndale Drive) | Construct roadway. | 1.89 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | BUILD NC CON | 37710000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000
U-2525C | Highway | STI (Prioritization) | I-840 | Greensboro Eastern Loop, US 29 north of Greensboro to SR 2303 (Lawndale Drive) | Construct roadway. | 1.89 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | CONSTRUCTION | 57121000
U-2525CA | Highway | STI (Prioritization) | US 70 (Wendover Avenue) | US 70 (Wendover Avenue) at US 29 Interchange | Replace and upgrade overhead signs. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | ENGINEERING | 100000
U-2525CA | Highway | STI (Prioritization) | US 70 (Wendover Avenue) | US 70 (Wendover Avenue) at US 29 Interchange | Replace and upgrade overhead signs. | 1 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | CONSTRUCTION | 1550000 | FY 2026: 1450000
U-2525D | Highway | STI (Prioritization) | I-840 | Interchange at proposed Cone Boulevard extension | Construct interchange. | 15.4 | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 15000000 | [10 empty] | 15000000
U-2530 | Highway | STI (Prioritization) | NC 127 | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. Upgrade and extend SR 1213 and proposed US 321 / NC 127 interchange north of SR 1182. | 4.5 | Catawba | 12 | Greater Hickory MPO | [5 empty] | 12399000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. | 3.14 | Catawba | 12 | Greater Hickory MPO | NC BUILD BONDS: $24M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | BGANY | RIGHT-OF-WAY | 25000000 | FY 2026: 7273000; FY 2027: 7273000; FY 2028: 3636000; FY 2029: 5000000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. | 3.14 | Catawba | 12 | Greater Hickory MPO | NC BUILD BONDS: $24M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | BGANY | UTILITIES | 3900000 | FY 2026: 1950000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. | 3.14 | Catawba | 12 | Greater Hickory MPO | NC BUILD BONDS: $24M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | T | BUILD NC CON | 31200000 |  |  |  |  | 2080000 | 2080000 | 2080000 | 2080000 | 2080000 | 2080000 | 18720000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (Huffman Farm Road) to SR 1108 (Zion Church Road). | Widen to multi-lanes. | 3.14 | Catawba | 12 | Greater Hickory MPO | NC BUILD BONDS: $24M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | T | CONSTRUCTION | 40410000 | FY 2029: 9660000; FY 2030: 0; FY 2031: 7566000; FY 2032: 12880000; FY 2033: 10304000
U-2530B | Highway | Pre-STI (Historic) | NC 127 | US 321 / NC 127 interchange north of SR 1182. | Upgrade and extend. |  | Catawba | 12 | Greater Hickory MPO | COMPLETE
U-2561 | Highway | STI (Prioritization) | NC 43 | SR 1613 (Woodruff Avenue) to I-95. | Widen to multi-lanes. | 0.61 | Nash | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 6745000
U-2561C | Highway | STI (Prioritization) | NC 43 | SR 1613 (Woodruff Avenue) to I-95. | Widen to multi-lanes. | 1.65 | Nash | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BGLT5 | RIGHT-OF-WAY | 4400000 | FY 2026: 748000; FY 2027: 1848000; FY 2028: 924000; FY 2029: 440000; FY 2030: 440000
U-2561C | Highway | STI (Prioritization) | NC 43 | SR 1613 (Woodruff Avenue) to I-95. | Widen to multi-lanes. | 1.65 | Nash | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BGLT5 | UTILITIES | 3100000 | FY 2026: 1550000; FY 2027: 1550000
U-2561C | Highway | STI (Prioritization) | NC 43 | SR 1613 (Woodruff Avenue) to I-95. | Widen to multi-lanes. | 1.65 | Nash | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BGLT5 | CONSTRUCTION | 13600000 | FY 2028: 3128000; FY 2029: 5984000; FY 2030: 3672000; FY 2031: 816000
U-2567 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 150 (Dekalb Street) intersection in Shelby. | Construct interchange. | 1 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1500000
U-2567 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 150 (Dekalb Street) intersection in Shelby. | Construct interchange. | 1 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 21199000
U-2567 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 150 (Dekalb Street) intersection in Shelby. | Construct interchange. | 1 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
U-2567 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 150 (Dekalb Street) intersection in Shelby. | Construct interchange. | 1 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 48400000
U-2579 | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, eastern section, I-74 / US 311 to US 52 (Future I-285). | Multi-lane freeway on new location. | 17.1 | Forsyth | 9 | Winston-Salem Area TPO | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 588926000
U-2579 | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, eastern section, I-74 / US 311 to US 52 (Future I-285). | Multi-lane freeway on new location. | 17.1 | Forsyth | 9 | Winston-Salem Area TPO | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  | T | RIGHT-OF-WAY | 175000
U-2579AA | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, I-74 / US 311 to I-40 | Construct multi-lane freeway. | 0.87 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $20M CONSTRUCTION PAYBACK FY 2026-2040 (SALE 6 / 2026). | Region D |  | T | BUILD NC CON | 25995000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 1733000 | 8665000
U-2579AA | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, I-74 / US 311 to I-40 | Construct multi-lane freeway. | 0.87 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $20M CONSTRUCTION PAYBACK FY 2026-2040 (SALE 6 / 2026). | Region D |  | NHP | CONSTRUCTION | 118133000 | FY 2026: 5552000; FY 2027: 18283000
U-2579AA | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, I-74 / US 311 to I-40 | Construct multi-lane freeway. | 0.87 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $20M CONSTRUCTION PAYBACK FY 2026-2040 (SALE 6 / 2026). | Region D |  | BGDA | CONSTRUCTION | 5037000
U-2579AB | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, I-40 to US 421 / NC 150 / I-40 Business | Construct multi-lane freeway. | 3.27 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | Region D |  | NHP | GARVEE CON | 77220000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000
U-2579AB | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, I-40 to US 421 / NC 150 / I-40 Business | Construct multi-lane freeway. | 3.27 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | Region D |  | NHP | CONSTRUCTION | 213147000 | FY 2026: 31503000
U-2579AB | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, I-40 to US 421 / NC 150 / I-40 Business | Construct multi-lane freeway. | 3.27 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | Region D |  | T(M) | CONSTRUCTION | 20000000
U-2579B | Highway | Transition | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Construct multi-lane freeway. | 2.92 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026 | Pre-STI (Transition) |  | NHP | GARVEE CON | 68971000 | FY 2026: 9853000
U-2579BA | Highway | Transition | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Relocate stream. | 2.92 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | NHP | CONSTRUCTION | 9300000
U-2579BB | Highway | Transition | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Construct noise wall. | 2.92 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | UTILITIES | 234000
U-2579BB | Highway | Transition | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 421 / NC 150 / I-40 Business to US 158 | Construct noise wall. | 2.92 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | CONSTRUCTION | 2855000
U-2579C | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 158 to US 311 | Construct multi-lane freeway. | 1.41 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | NHP | GARVEE ROW | 6138000 | FY 2026: 558000; FY 2027: 558000; FY 2028: 558000; FY 2029: 558000; FY 2030: 558000
U-2579C | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 158 to US 311 | Construct multi-lane freeway. | 1.41 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 11662000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 784000
U-2579C | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 158 to US 311 | Construct multi-lane freeway. | 1.41 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | NHP | CONSTRUCTION | 15560000
U-2579D | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 311 to SR 2211 (Baux Mountain Road) | Construct multi-lane freeway. | 3.2 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 42380000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000
U-2579DA | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 311 to SR 2211 (Baux Mountain Road) | Construct noise wall. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 4800000 | FY 2026: 4080000; FY 2027: 240000
U-2579DA | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, US 311 to SR 2211 (Baux Mountain Road) | Construct noise wall. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1200000 | FY 2026: 1020000; FY 2027: 60000
U-2579E | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, SR 2211 (Baux Mountain Road) to NC 8 | Construct multi-lane freeway. | 2.21 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 33462000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000
U-2579F | Highway | STI (Prioritization) | Future I-74 | Winston-Salem Northern Beltway, Eastern Section, NC 8 to west of NC 66 (University Parkway) | Construct multi-lane freeway. | 2.44 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 26767000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000
U-2579G | Highway | Pre-STI (Historic) | SR 2667 (Hastings Hill Road) | Winston-Salem Northern Beltway, Eastern Section, Bridge No. 366 over US 421 / NC 150 / I-40 Business | Replace bridge. |  | Forsyth | 9 | Winston-Salem Area TPO | PROJECT COMPLETE
U-2581 | Highway | STI (Prioritization) | US 70 | SR 3045 (Mount Hope Church Road) to SR 3056 (Rock Creek Dairy Road). | Widen to multi-lanes, part on new location. | 4.5 | Guilford | 7 | Greensboro Urban Area MPO | [5 empty] | 6281000
U-2581A | Highway | STI (Prioritization) | US 70 | SR 2851 (Penry Road) to SR 2828 (Willowlake Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (Mount Hope Church Road) to SR 2826 (Birch Creek Road) | Widen roadway. | 1.15 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | ENGINEERING | 1609000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 13000 | 13000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (Mount Hope Church Road) to SR 2826 (Birch Creek Road) | Widen roadway. | 1.15 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC ROW | 2618000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (Mount Hope Church Road) to SR 2826 (Birch Creek Road) | Widen roadway. | 1.15 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 11923000 | 795000 | 795000 | 795000 | 795000 | 795000 | 795000 | 795000 | 794000 | 794000 | 794000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (Mount Hope Church Road) to SR 2826 (Birch Creek Road) | Widen roadway. | 1.15 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | CONSTRUCTION | 3612000
U-2581BB | Highway | STI (Prioritization) | US 70 | SR 2826 (Birch Creek Road) to SR 3051 (Knox Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2113000 | [10 empty] | 2113000
U-2581BB | Highway | STI (Prioritization) | US 70 | SR 2826 (Birch Creek Road) to SR 3051 (Knox Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | UTILITIES | 626000 | [10 empty] | 626000
U-2581BB | Highway | STI (Prioritization) | US 70 | SR 2826 (Birch Creek Road) to SR 3051 (Knox Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 8200000 | [10 empty] | 8200000
U-2581BC | Highway | STI (Prioritization) | US 70 | SR 3051 (Knox Road) to SR 3056 (Rock Creek Dairy Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3040000 | [10 empty] | 3040000
U-2581BC | Highway | STI (Prioritization) | US 70 | SR 3051 (Knox Road) to SR 3056 (Rock Creek Dairy Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | UTILITIES | 901000 | [10 empty] | 901000
U-2581BC | Highway | STI (Prioritization) | US 70 | SR 3051 (Knox Road) to SR 3056 (Rock Creek Dairy Road) | Widen roadway. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 11799000 | [10 empty] | 11799000
U-2714 | Highway | STI (Prioritization) | US 117 Business / US 117 (North Williams Street) | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  |  |  | 9483000
U-2714 | Highway | STI (Prioritization) | US 117 Business / US 117 (North Williams Street) | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | ENGINEERING | 4290000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 4000
U-2714 | Highway | STI (Prioritization) | US 117 Business / US 117 (North Williams Street) | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC ROW | 3510000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000
U-2714 | Highway | STI (Prioritization) | US 117 Business / US 117 (North Williams Street) | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC CON | 16875000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000
U-2714 | Highway | STI (Prioritization) | US 117 Business / US 117 (North Williams Street) | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | CONSTRUCTION | 6885000
U-2714 | Highway | STI (Prioritization) | US 117 Business / US 117 (North Williams Street) | North of US 70 to SR 1571 (Tommy's Road) in Goldsboro. | Widen to four lanes and make safety improvements. | 0.96 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | L | CONSTRUCTION | 1327000
U-2719 | Highway | STI (Prioritization) | I-440 / US-1 | South of SR 1313 (Walnut Street) to north of SR 1728 (Wade Avenue) in Raleigh. | Widen from four to six lanes, improve storage at Lake Boone Trail interchange and install ramp meters. | 5.58 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT-OF-WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  |  |  | 262047000
U-2719 | Highway | STI (Prioritization) | I-440 / US-1 | South of SR 1313 (Walnut Street) to north of SR 1728 (Wade Avenue) in Raleigh. | Widen from four to six lanes, improve storage at Lake Boone Trail interchange and install ramp meters. | 5.58 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT-OF-WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  | NHP | GARVEE ROW | 34749000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2311000
U-2719 | Highway | STI (Prioritization) | I-440 / US-1 | South of SR 1313 (Walnut Street) to north of SR 1728 (Wade Avenue) in Raleigh. | Widen from four to six lanes, improve storage at Lake Boone Trail interchange and install ramp meters. | 5.58 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT-OF-WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  | NHP | GARVEE CON | 158558000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000
U-2729 | Highway | STI (Prioritization) | SR 1672 (Hanes Mill Road) | Museum Drive to SR 4000 (University Parkway) in Winston-Salem. | Widen to multi-lane divided facility. | 0.42 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  |  |  | 3710000
U-2729 | Highway | STI (Prioritization) | SR 1672 (Hanes Mill Road) | Museum Drive to SR 4000 (University Parkway) in Winston-Salem. | Widen to multi-lane divided facility. | 0.42 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | ENGINEERING | 1092000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000
U-2729 | Highway | STI (Prioritization) | SR 1672 (Hanes Mill Road) | Museum Drive to SR 4000 (University Parkway) in Winston-Salem. | Widen to multi-lane divided facility. | 0.42 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | BUILD NC ROW | 686000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000
U-2729 | Highway | STI (Prioritization) | SR 1672 (Hanes Mill Road) | Museum Drive to SR 4000 (University Parkway) in Winston-Salem. | Widen to multi-lane divided facility. | 0.42 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | BUILD NC CON | 9975000 | 665000 | 665000 | 665000 | 665000 | 665000 | 665000 | 665000 | 665000 | 665000 | 665000 | 2660000
U-2729 | Highway | STI (Prioritization) | SR 1672 (Hanes Mill Road) | Museum Drive to SR 4000 (University Parkway) in Winston-Salem. | Widen to multi-lane divided facility. | 0.42 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | CONSTRUCTION | 10251000 | FY 2026: 3151000
U-2801 | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | US 25 (Hendersonville Road) to Roberts Road in Asheville. | Widen to multi-lanes. | 7.3 | Buncombe | 13 | French Broad River MPO | [5 empty] | 22226000
U-2801AA | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | US 25 (Hendersonville Road) to SR 3116 (Mills Gap Road). | Widen to multi-lanes. | 2.77 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 92500000 | [10 empty] | 92500000
U-2801AA | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | US 25 (Hendersonville Road) to SR 3116 (Mills Gap Road). | Widen to multi-lanes. | 2.77 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | BGANY | UTILITIES | 8393000 | [10 empty] | 8393000
U-2801AA | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | US 25 (Hendersonville Road) to SR 3116 (Mills Gap Road). | Widen to multi-lanes. | 2.77 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | BGANY | CONSTRUCTION | 84598000 | [10 empty] | 84598000
U-2801AB | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | SR 3116 (Mills Gap Road) to SR 3081 (Rock Hill Road). | Widen to multi-lanes. | 2.68 | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 56600000
U-2801AB | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | SR 3116 (Mills Gap Road) to SR 3081 (Rock Hill Road). | Widen to multi-lanes. | 2.68 | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 8393000
U-2801AB | Highway | STI (Prioritization) | US 25A (Sweeten Creek Road) | SR 3116 (Mills Gap Road) to SR 3081 (Rock Hill Road). | Widen to multi-lanes. | 2.68 | Buncombe | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 110998000
U-2801B | Highway | Pre-STI (Historic) | US 25A (Sweeten Creek Road) | SR 3081 (Rock Hill Road) to SR 3079 (Roberts Road) | Widen to multi-lanes. | 1.473 | Buncombe | 13 | French Broad River MPO | COMPLETE
U-2817 | Highway | STI (Prioritization) | SR 1700 (Evans Street / Old Tar Road) | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 2 |  |  |  | 60010000
U-2817 | Highway | STI (Prioritization) | SR 1700 (Evans Street / Old Tar Road) | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 2 |  | BG50200 | RIGHT-OF-WAY | 22800000
U-2817 | Highway | STI (Prioritization) | SR 1700 (Evans Street / Old Tar Road) | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 2 |  | BG50200 | UTILITIES | 11172000
U-2817 | Highway | STI (Prioritization) | SR 1700 (Evans Street / Old Tar Road) | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 2 |  | T(M) | UTILITIES | 1800000
U-2817 | Highway | STI (Prioritization) | SR 1700 (Evans Street / Old Tar Road) | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 2 |  | T | BUILD NC CON | 65010000 |  | 2167000 | 2167000 | 4334000 | 4334000 | 4334000 | 4334000 | 4334000 | 4334000 | 4334000 | 30338000
U-2817 | Highway | STI (Prioritization) | SR 1700 (Evans Street / Old Tar Road) | SR 1711 (Worthington Road) in Winterville to US 264 Alternate (Greenville Boulevard) in Greenville. | Widen to four lanes. | 3.68 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 2 |  | T | CONSTRUCTION | 73300000 | FY 2027: 0; FY 2028: 21854000; FY 2029: 4592000; FY 2030: 25893000; FY 2031: 20961000
U-2901 | Highway | STI (Prioritization) | NC 55 (Williams Street) | US 1 to north of SR 1160 (Olive Chapel Road) in Apex. | Widen to a multi-lane curb and gutter facility. | 2.8 | Wake | 5 | Capital Area MPO | PROJECTS U-2901AA AND AB COMPLETE |  |  |  |  | 4860000
U-2901B | Highway | STI (Prioritization) | NC 55 (Williams Street) | US 1 to north of SR 1160 (Olive Chapel Road) | Convert existing multilane to median divided section and widen remaining 2-lane sections to multilane. | 1.73 | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 12900000 | FY 2027: 2967000; FY 2028: 3612000; FY 2029: 3483000; FY 2030: 258000; FY 2031: 2580000
U-2901B | Highway | STI (Prioritization) | NC 55 (Williams Street) | US 1 to north of SR 1160 (Olive Chapel Road) | Convert existing multilane to median divided section and widen remaining 2-lane sections to multilane. | 1.73 | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 1700000 | FY 2027: 850000; FY 2028: 850000
U-2901B | Highway | STI (Prioritization) | NC 55 (Williams Street) | US 1 to north of SR 1160 (Olive Chapel Road) | Convert existing multilane to median divided section and widen remaining 2-lane sections to multilane. | 1.73 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 40300000 | FY 2030: 9672000; FY 2031: 10881000; FY 2032: 8463000; FY 2033: 6448000; FY 2034: 4836000
U-2901BA | Highway | STI (Prioritization) | NC 55 (Williams Street) | CSX Railroad bridge over NC 55 | Replace railroad bridge. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 830000 | FY 2026: 272000; FY 2027: 362000; FY 2028: 30000; FY 2029: 83000; FY 2030: 83000
U-2901BA | Highway | STI (Prioritization) | NC 55 (Williams Street) | CSX Railroad bridge over NC 55 | Replace railroad bridge. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 140000 | FY 2026: 140000
U-2901BA | Highway | STI (Prioritization) | NC 55 (Williams Street) | CSX Railroad bridge over NC 55 | Replace railroad bridge. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 30600000 | FY 2028: 8262000; FY 2029: 8874000; FY 2030: 6732000; FY 2031: 4896000; FY 2032: 1836000
U-2925 | Highway | Pre-STI (Historic) | New Route | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) in Winston-Salem. | Construct multi-lane facility on new location. | 1.81 | Forsyth | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT COMPLETE | Pre-STI (Transition) |  |  |  | 93832000
U-2925C | Highway | Locally Selected | New Route | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) | Improve landscaping and lighting. | 1.09 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 362000
U-2925C | Highway | Locally Selected | New Route | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) | Improve landscaping and lighting. | 1.09 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | ENGINEERING | 91000
U-2925C | Highway | Locally Selected | New Route | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) | Improve landscaping and lighting. | 1.09 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1086000
U-2925C | Highway | Locally Selected | New Route | Salem Creek Connector, SR 4326 (Rams Drive) to SR 4325 (Martin Luther King, Jr. Drive) | Improve landscaping and lighting. | 1.09 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | CONSTRUCTION | 272000
U-3109 | Highway | STI (Prioritization) | NC 119 | NC 119 relocation, I-85 to south of SR 1918 (Mrs. White Road) in Mebane. | Four-to-six-lane facility on new location. | 4.2 | Alamance | 7 | Burlington-Graham MPO | [5 empty] | 84313000
U-3109A | Highway | STI (Prioritization) | NC 119 | I-40 / I-85 to north of SR 1921 (Mebane Rogers Road) | Relocate roadway. | 3.01 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | ENGINEERING | 360000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000
U-3109A | Highway | STI (Prioritization) | NC 119 | I-40 / I-85 to north of SR 1921 (Mebane Rogers Road) | Relocate roadway. | 3.01 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 42967000 | 2864000 | 2864000 | 2864000 | 2864000 | 2864000 | 2864000 | 2864000 | 2864000 | 1651000 | 1658000
U-3109B | Highway | STI (Prioritization) | NC 119 | North of SR 1921 (Mebane Rogers Road) to south of SR 1918 (Mrs. White Road). | Relocate roadway. | 1.49 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.533 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 5835000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000
U-3125 | Highway | STI (Prioritization) | US 117 (Future I-795) | I-40 to I-795. | Upgrade roadway to interstate standards, partially on new location. | 24.3 | Wayne, Duplin, Sampson | 3, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO, Mid-Carolina RPO | [5 empty] | 1000000
U-3125A | Highway | STI (Prioritization) | US 117 (Future I-795) | I-40 to SR 1006 (West Trade Road). | Upgrade roadway to interstate standards, partially on new location. | 5.31 | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | RIGHT-OF-WAY | 7300000 | [10 empty] | 7300000
U-3125A | Highway | STI (Prioritization) | US 117 (Future I-795) | I-40 to SR 1006 (West Trade Road). | Upgrade roadway to interstate standards, partially on new location. | 5.31 | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | UTILITIES | 1200000 | [10 empty] | 1200000
U-3125A | Highway | STI (Prioritization) | US 117 (Future I-795) | I-40 to SR 1006 (West Trade Road). | Upgrade roadway to interstate standards, partially on new location. | 5.31 | Duplin, Sampson | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | CONSTRUCTION | 219400000 | [10 empty] | 219400000
U-3125B | Highway | STI (Prioritization) | US 117 (Future I-795) | SR 1006 (West Trade Street) to north of SR 1135 (Country Club Road). | Upgrade roadway to interstate standards, partially on new location. | 6.73 | Wayne, Duplin | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | RIGHT-OF-WAY | 39400000 | [10 empty] | 39400000
U-3125B | Highway | STI (Prioritization) | US 117 (Future I-795) | SR 1006 (West Trade Street) to north of SR 1135 (Country Club Road). | Upgrade roadway to interstate standards, partially on new location. | 6.73 | Wayne, Duplin | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | UTILITIES | 5000000 | [10 empty] | 5000000
U-3125B | Highway | STI (Prioritization) | US 117 (Future I-795) | SR 1006 (West Trade Street) to north of SR 1135 (Country Club Road). | Upgrade roadway to interstate standards, partially on new location. | 6.73 | Wayne, Duplin | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | CONSTRUCTION | 173000000 | [10 empty] | 173000000
U-3125C | Highway | STI (Prioritization) | US 117 (Future I-795) | North of SR 1135 (Country Club Road) to south of SR 1129 (South Landfill Road). | Upgrade roadway to interstate standards, partially on new location. | 3.61 | Wayne | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 90000
U-3125C | Highway | STI (Prioritization) | US 117 (Future I-795) | North of SR 1135 (Country Club Road) to south of SR 1129 (South Landfill Road). | Upgrade roadway to interstate standards, partially on new location. | 3.61 | Wayne | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3100000
U-3125C | Highway | STI (Prioritization) | US 117 (Future I-795) | North of SR 1135 (Country Club Road) to south of SR 1129 (South Landfill Road). | Upgrade roadway to interstate standards, partially on new location. | 3.61 | Wayne | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 35500000
U-3125D | Highway | STI (Prioritization) | US 117 (Future I-795) | South of SR 1129 (South Landfill Road) to south of SR 1927 (Genoa Road). | Upgrade roadway to interstate standards, partially on new location. | 2.42 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 12600000
U-3125D | Highway | STI (Prioritization) | US 117 (Future I-795) | South of SR 1129 (South Landfill Road) to south of SR 1927 (Genoa Road). | Upgrade roadway to interstate standards, partially on new location. | 2.42 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2200000
U-3125D | Highway | STI (Prioritization) | US 117 (Future I-795) | South of SR 1129 (South Landfill Road) to south of SR 1927 (Genoa Road). | Upgrade roadway to interstate standards, partially on new location. | 2.42 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 103100000
U-3125E | Highway | STI (Prioritization) | US 117 (Future I-795) | South of SR 1927 (Genoa Road) to north of NC 581 (Arrington Bridge Road). | Upgrade roadway to interstate standards, partially on new location. | 1.82 | Wayne | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 30500000 | [10 empty] | 30500000
U-3125E | Highway | STI (Prioritization) | US 117 (Future I-795) | South of SR 1927 (Genoa Road) to north of NC 581 (Arrington Bridge Road). | Upgrade roadway to interstate standards, partially on new location. | 1.82 | Wayne | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 2600000 | [10 empty] | 2600000
U-3125E | Highway | STI (Prioritization) | US 117 (Future I-795) | South of SR 1927 (Genoa Road) to north of NC 581 (Arrington Bridge Road). | Upgrade roadway to interstate standards, partially on new location. | 1.82 | Wayne | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 234400000 | [10 empty] | 234400000
U-3125F | Highway | STI (Prioritization) | US 117 (Future I-795) | North of NC 581 (Arrington Bridge Road) to I-795. | Upgrade roadway to interstate standards, partially on new location. | 3.48 | Wayne | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 20200000 | [10 empty] | 20200000
U-3125F | Highway | STI (Prioritization) | US 117 (Future I-795) | North of NC 581 (Arrington Bridge Road) to I-795. | Upgrade roadway to interstate standards, partially on new location. | 3.48 | Wayne | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 1600000 | [10 empty] | 1600000
U-3125F | Highway | STI (Prioritization) | US 117 (Future I-795) | North of NC 581 (Arrington Bridge Road) to I-795. | Upgrade roadway to interstate standards, partially on new location. | 3.48 | Wayne | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 116400000 | [10 empty] | 116400000
U-3301 | Highway | Pre-STI (Historic) | NC 63 (Leicester Highway) | SR 1615 (Gilbert Road) to west of SR 1004 (Newfound Road) in Asheville. | Widen to multi-lanes, some relocation. | 4.32 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION - DESIGN BUILD PROJECT | Pre-STI (Transition) |  |  |  | 55129000
U-3308 | Highway | Transition | NC 55 (Alston Avenue) | NC 147 (Durham Freeway) to US 70 Business / NC 98 (Holloway Street) in Durham. | Widen to four-lane divided facility from NC 147 to Main Street and replace Norfolk Southern Railroad bridges. Modernize from Main Street to US 70 Business / NC 98 (Holloway Street) | 0.9 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 41348000
U-3338 | Highway | STI (Prioritization) | SR 1175 (Kerr Avenue) | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Widen to multi-lanes. | 3.2 | New Hanover | 3 | Wilmington Urban Area MPO | [5 empty] | 76486000
U-3338B | Highway | Transition | SR 1175 (Kerr Avenue) | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway). | Widen to multi-lanes. | 1.49 | New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE. | Pre-STI (Transition)
U-3338C | Highway | STI (Prioritization) | SR 1175 (Kerr Avenue) | SR 1175 (Kerr Avenue) interchange at US 74 (Martin Luther King, Jr. Parkway). | Improve interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BGANY | CONSTRUCTION | 39600000 | FY 2030: 2772000; FY 2031: 11880000; FY 2032: 10296000; FY 2033: 7920000; FY 2034: 6732000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (Archdale Road) | US 311 (Main Street) to east of Springwood Lane in Archdale. | Widen to multi-lanes. | 3.09 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  |  |  | 1520000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (Archdale Road) | US 311 (Main Street) to east of Springwood Lane in Archdale. | Widen to multi-lanes. | 3.09 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | T | RIGHT-OF-WAY | 7901000 | FY 2026: 2231000; FY 2027: 1859000; FY 2028: 1501000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (Archdale Road) | US 311 (Main Street) to east of Springwood Lane in Archdale. | Widen to multi-lanes. | 3.09 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | T | UTILITIES | 6300000 | FY 2026: 3150000; FY 2027: 3150000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (Archdale Road) | US 311 (Main Street) to east of Springwood Lane in Archdale. | Widen to multi-lanes. | 3.09 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | T | CONSTRUCTION | 43600000 | FY 2030: 436000; FY 2031: 12644000; FY 2032: 12208000; FY 2033: 10464000; FY 2034: 7848000
U-3415 | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | SR 1445 (Derita Road) to US 29 / US 601 Bypass. | Widen to multi-lanes. | 6.1 | Cabarrus | 10 | Cabarrus-Rowan MPO | [5 empty] | 2732000
U-3415A | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | East of I-85 to George Liles Parkway. | Widen to multi-lanes. | 2.96 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGANY | RIGHT-OF-WAY | 12900000 | FY 2029: 1548000; FY 2030: 3225000; FY 2031: 3225000; FY 2032: 2322000; FY 2033: 2580000
U-3415A | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | East of I-85 to George Liles Parkway. | Widen to multi-lanes. | 2.96 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGANY | UTILITIES | 900000 | FY 2029: 450000; FY 2030: 450000
U-3415A | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | East of I-85 to George Liles Parkway. | Widen to multi-lanes. | 2.96 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGANY | CONSTRUCTION | 49400000 | FY 2033: 3952000; FY 2034: 15314000; FY 2035: 13338000 | 16796000
U-3415B | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | George Liles Parkway to US 29 / US 601 Bypass. | Widen to multi-lanes. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 9900000 | [10 empty] | 9900000
U-3415B | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | George Liles Parkway to US 29 / US 601 Bypass. | Widen to multi-lanes. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | T | UTILITIES | 13200000 | [10 empty] | 13200000
U-3415B | Highway | STI (Prioritization) | SR 1394 (Poplar Tent Road) | George Liles Parkway to US 29 / US 601 Bypass. | Widen to multi-lanes. |  | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | T | CONSTRUCTION | 32900000 | [10 empty] | 25657000
U-3422 | Highway | STI (Prioritization) | SR 1003 (Camden Road) | Proposed Fayetteville Outer Loop (U-2519) to SR 1596 (Hope Mills Road) in Fayetteville. | Widen to four lanes. | 3.52 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  |  |  | 2500000
U-3422 | Highway | STI (Prioritization) | SR 1003 (Camden Road) | Proposed Fayetteville Outer Loop (U-2519) to SR 1596 (Hope Mills Road) in Fayetteville. | Widen to four lanes. | 3.52 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGANY | RIGHT-OF-WAY | 16175000
U-3422 | Highway | STI (Prioritization) | SR 1003 (Camden Road) | Proposed Fayetteville Outer Loop (U-2519) to SR 1596 (Hope Mills Road) in Fayetteville. | Widen to four lanes. | 3.52 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGANY | UTILITIES | 5225000
U-3422A | Highway | STI (Prioritization) | SR 1003 (Camden Road) | Proposed Fayetteville Outer Loop (U-2519) to just west of SR 1112 (Rockfish Road). | Widen to four-lanes. | 1.53 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | BUILD NC CON | 10395000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 3465000
U-3422A | Highway | STI (Prioritization) | SR 1003 (Camden Road) | Proposed Fayetteville Outer Loop (U-2519) to just west of SR 1112 (Rockfish Road). | Widen to four-lanes. | 1.53 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | CONSTRUCTION | 9231000 | FY 2026: 0; FY 2027: 615000; FY 2028: 3619000; FY 2029: 2757000
U-3422A | Highway | STI (Prioritization) | SR 1003 (Camden Road) | Proposed Fayetteville Outer Loop (U-2519) to just west of SR 1112 (Rockfish Road). | Widen to four-lanes. | 1.53 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | O | CONSTRUCTION | 6249000
U-3422B | Highway | STI (Prioritization) | SR 1003 (Camden Road) | West of SR 1112 (Rockfish Road) to SR 1596 (Hope Mills Road). | Widen to four-lanes. | 1.99 | Cumberland | 6 | Fayetteville Area MPO | O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BULD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 6 |  | T | BUILD NC CON | 24705000 |  | 780000 | 780000 | 1647000 | 1647000 | 1647000 | 1647000 | 1647000 | 1647000 | 1647000 | 10749000
U-3422B | Highway | STI (Prioritization) | SR 1003 (Camden Road) | West of SR 1112 (Rockfish Road) to SR 1596 (Hope Mills Road). | Widen to four-lanes. | 1.99 | Cumberland | 6 | Fayetteville Area MPO | O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BULD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 6 |  | T | CONSTRUCTION | 19987000 | FY 2027: 0; FY 2028: 6205000; FY 2029: 0; FY 2030: 7544000; FY 2031: 6238000
U-3422B | Highway | STI (Prioritization) | SR 1003 (Camden Road) | West of SR 1112 (Rockfish Road) to SR 1596 (Hope Mills Road). | Widen to four-lanes. | 1.99 | Cumberland | 6 | Fayetteville Area MPO | O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BULD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 6 |  | O | CONSTRUCTION | 16814000 | FY 2027: 16814000
U-3431 | Highway | STI (Prioritization) | NC 101 / SR 1763 (Fontana Boulevard / Miller Boulevard); SR 1756 (Lake Road) | SR 1756 (Lake Road) to Outer Banks Drive; SR 1763 (Miller Boulevard) to Havelock Bypass. | Widen to multi-lanes and construct road improvements. | 3.05 | Craven | 2 | Down East RPO |  | Division 2 |  |  |  | 1450000
U-3431 | Highway | STI (Prioritization) | NC 101 / SR 1763 (Fontana Boulevard / Miller Boulevard); SR 1756 (Lake Road) | SR 1756 (Lake Road) to Outer Banks Drive; SR 1763 (Miller Boulevard) to Havelock Bypass. | Widen to multi-lanes and construct road improvements. | 3.05 | Craven | 2 | Down East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 17301000 | FY 2026: 2768000; FY 2027: 3691000; FY 2028: 3691000; FY 2029: 3691000; FY 2030: 3460000
U-3431 | Highway | STI (Prioritization) | NC 101 / SR 1763 (Fontana Boulevard / Miller Boulevard); SR 1756 (Lake Road) | SR 1756 (Lake Road) to Outer Banks Drive; SR 1763 (Miller Boulevard) to Havelock Bypass. | Widen to multi-lanes and construct road improvements. | 3.05 | Craven | 2 | Down East RPO |  | Division 2 |  | T | UTILITIES | 3500000 | FY 2026: 1750000; FY 2027: 1750000
U-3431 | Highway | STI (Prioritization) | NC 101 / SR 1763 (Fontana Boulevard / Miller Boulevard); SR 1756 (Lake Road) | SR 1756 (Lake Road) to Outer Banks Drive; SR 1763 (Miller Boulevard) to Havelock Bypass. | Widen to multi-lanes and construct road improvements. | 3.05 | Craven | 2 | Down East RPO |  | Division 2 |  | T | CONSTRUCTION | 91500000 | FY 2030: 21045000; FY 2031: 21045000; FY 2032: 20130000; FY 2033: 16470000; FY 2034: 12810000
U-3440 | Highway | Transition | NC 3 | West Side Bypass (U-2009) to SR 1691 (Loop Road) in Kannapolis. | Widen to four lanes divided. | 2.58 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 48456000
U-3440 | Highway | Transition | NC 3 | West Side Bypass (U-2009) to SR 1691 (Loop Road) in Kannapolis. | Widen to four lanes divided. | 2.58 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | RIGHT-OF-WAY | 561000
U-3440 | Highway | Transition | NC 3 | West Side Bypass (U-2009) to SR 1691 (Loop Road) in Kannapolis. | Widen to four lanes divided. | 2.58 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | CONSTRUCTION | 3100000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 to SR 1008 (Waxhaw-Indian Trail Road) in Wesley Chapel. | Construct four lane roadway, part on new location. | 4.02 | Union | 10 | Charlotte Regional TPO | NC BUILD BOND $41M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE); | Region E |  |  |  | 18015000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 to SR 1008 (Waxhaw-Indian Trail Road) in Wesley Chapel. | Construct four lane roadway, part on new location. | 4.02 | Union | 10 | Charlotte Regional TPO | NC BUILD BOND $41M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE); | Region E |  | BGANY | RIGHT-OF-WAY | 41000000 | FY 2026: 11576000; FY 2027: 9648000; FY 2028: 8200000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 to SR 1008 (Waxhaw-Indian Trail Road) in Wesley Chapel. | Construct four lane roadway, part on new location. | 4.02 | Union | 10 | Charlotte Regional TPO | NC BUILD BOND $41M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE); | Region E |  | BGANY | UTILITIES | 5700000 | FY 2026: 2850000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 to SR 1008 (Waxhaw-Indian Trail Road) in Wesley Chapel. | Construct four lane roadway, part on new location. | 4.02 | Union | 10 | Charlotte Regional TPO | NC BUILD BOND $41M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE); | Region E |  | T | BUILD NC CON | 53295000 |  |  |  | 3553000 | 3553000 |  | 3553000 | 3553000 | 3553000 | 3553000 | 31977000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 to SR 1008 (Waxhaw-Indian Trail Road) in Wesley Chapel. | Construct four lane roadway, part on new location. | 4.02 | Union | 10 | Charlotte Regional TPO | NC BUILD BOND $41M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE); | Region E |  | T | CONSTRUCTION | 62300000 | FY 2028: 23759000; FY 2029: 0; FY 2030: 9617000; FY 2031: 16528000; FY 2032: 12396000
U-3609 | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1560 (Royal Avenue) to north of SR 1572 (Saulston Road) in Goldsboro. | Widen to multi-lanes. | 3 | Wayne | 4 | Goldsboro Urban Area MPO | [5 empty] | 5806000
U-3609A | Highway | Transition | US 13 (Berkeley Boulevard) | SR 1560 (Royal Avenue) to SR 1003 (New Hope Road). | Widen to multi-lanes. | 1 | Wayne | 4 | Goldsboro Urban Area MPO | COMPLETE. | Pre-STI (Transition)
U-3609B | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Region A |  | T | ENGINEERING | 2400000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
U-3609B | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Region A |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
U-3609B | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Region A |  | T | RIGHT-OF-WAY | 23324000
U-3609B | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Region A |  | T | UTILITIES | 3750000
U-3609B | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Region A |  | T | BUILD NC CON | 13005000 |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 5202000
U-3609B | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1003 (New Hope Road) to US 70 Bypass with intersection improvements at SR 1572 (Saulston Road) | Widen to multi-lanes. | 3.46 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION, PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Region A |  | T | CONSTRUCTION | 22300000 | FY 2026: 3230000; FY 2027: 659000; FY 2028: 8721000; FY 2029: 6137000; FY 2030: 3553000
U-3609BA | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | Hood Swamp Road. | Realignment of Hood Swamp Road. | 0.19 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | CONSTRUCTION | 2030000
U-3618 | Highway | STI (Prioritization) | SR 1569 (Carey Road Extension) | SR 1572 (Rouse Road) to US 258. | Construct multi-lanes on new location. | 1.81 | Lenoir | 2 | Eastern Carolina RPO |  | Division 2 |  |  |  | 1258000
U-3618 | Highway | STI (Prioritization) | SR 1569 (Carey Road Extension) | SR 1572 (Rouse Road) to US 258. | Construct multi-lanes on new location. | 1.81 | Lenoir | 2 | Eastern Carolina RPO |  | Division 2 |  | BG5T50 | RIGHT-OF-WAY | 3200000 | FY 2028: 356000; FY 2029: 853000; FY 2030: 853000; FY 2031: 498000; FY 2032: 640000
U-3618 | Highway | STI (Prioritization) | SR 1569 (Carey Road Extension) | SR 1572 (Rouse Road) to US 258. | Construct multi-lanes on new location. | 1.81 | Lenoir | 2 | Eastern Carolina RPO |  | Division 2 |  | BG5T50 | UTILITIES | 2900000 | FY 2028: 1450000; FY 2029: 1450000
U-3618 | Highway | STI (Prioritization) | SR 1569 (Carey Road Extension) | SR 1572 (Rouse Road) to US 258. | Construct multi-lanes on new location. | 1.81 | Lenoir | 2 | Eastern Carolina RPO |  | Division 2 |  | BG5T50 | CONSTRUCTION | 50300000 | FY 2031: 5030000; FY 2032: 15090000; FY 2033: 12575000; FY 2034: 10060000; FY 2035: 7545000
U-3628 | Highway | STI (Prioritization) | NC 24 / NC 27 | Courthouse west of NC 22 (McNeill Street) to US 15 / US 501 in Carthage. | Widen to three lanes with curb and gutter and bicycle / pedestrian accommodations. | 1.35 | Moore | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | Region E |  |  |  | 1924000
U-3628 | Highway | STI (Prioritization) | NC 24 / NC 27 | Courthouse west of NC 22 (McNeill Street) to US 15 / US 501 in Carthage. | Widen to three lanes with curb and gutter and bicycle / pedestrian accommodations. | 1.35 | Moore | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | Region E |  | T | RIGHT-OF-WAY | 2275000
U-3628 | Highway | STI (Prioritization) | NC 24 / NC 27 | Courthouse west of NC 22 (McNeill Street) to US 15 / US 501 in Carthage. | Widen to three lanes with curb and gutter and bicycle / pedestrian accommodations. | 1.35 | Moore | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | Region E |  | NHP | CONSTRUCTION | 6900000 | FY 2026: 3519000; FY 2027: 828000
U-3633 | Highway | STI (Prioritization) | NC 273 (South Main Street) | Tuckaseegee Road to A & E Drive in Mount Holly. | Widen to four lanes divided. | 1.1 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746 | Region F |  |  |  | 22983000
U-3633 | Highway | STI (Prioritization) | NC 273 (South Main Street) | Tuckaseegee Road to A & E Drive in Mount Holly. | Widen to four lanes divided. | 1.1 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746 | Region F |  | T | BUILD NC CON | 6315000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000
U-4007 | Highway | STI (Prioritization) | US 17 | US 17 Business to SR 1326 (Drummer Kellum Road) in Jacksonville. | Add additional lanes and construct routes on new location. | 1.4 | Onslow | 3 | Jacksonville Urban Area MPO | [5 empty] | 93309000
U-4007A | Highway | Pre-STI (Historic) | SR 1702 (West Huff Drive) | SR 1308 (Bell Fork Road) to east of SR 1470 (Western Boulevard) | Add lanes and construct routes on new location. | 1.4 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE.
U-4007B | Highway | Pre-STI (Historic) | Jacksonville Parkway | Country Club Road to SR 1470 (Western Boulevard) | Add lanes and construct routes on new location. | 0 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE.
U-4007C | Highway | STI (Prioritization) | US 17 | Western Boulevard to Fairway Drive. | Add additional lanes and construct routes on new location. | 0 | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 34775000 | [10 empty] | 34775000
U-4007C | Highway | STI (Prioritization) | US 17 | Western Boulevard to Fairway Drive. | Add additional lanes and construct routes on new location. | 0 | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 26300000 | [10 empty] | 26300000
U-4007D | Highway | STI (Prioritization) | US 17 | Fairway Drive to Drummer Kellum Road. | Add additional lanes and construct routes on new location. | 0 | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 32345000 | [10 empty] | 32345000
U-4007D | Highway | STI (Prioritization) | US 17 | Fairway Drive to Drummer Kellum Road. | Add additional lanes and construct routes on new location. | 0 | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 16600000 | [10 empty] | 16600000
U-4007E | Highway | STI (Prioritization) | NC 53 | US 17 (Marine Boulevard) to SR 2716 (Exchange Drive). | Add additional lanes and construct routes on new location. | 0.7 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736. | Statewide Mobility |  | BG50200 | RIGHT-OF-WAY | 8900000 | FY 2028: 89000; FY 2029: 3026000; FY 2030: 3026000; FY 2031: 979000; FY 2032: 1780000
U-4007E | Highway | STI (Prioritization) | NC 53 | US 17 (Marine Boulevard) to SR 2716 (Exchange Drive). | Add additional lanes and construct routes on new location. | 0.7 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736. | Statewide Mobility |  | BG50200 | UTILITIES | 420000 | FY 2028: 420000
U-4007E | Highway | STI (Prioritization) | NC 53 | US 17 (Marine Boulevard) to SR 2716 (Exchange Drive). | Add additional lanes and construct routes on new location. | 0.7 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736. | Statewide Mobility |  | BG50200 | CONSTRUCTION | 12600000 | FY 2031: 3906000; FY 2032: 5292000; FY 2033: 3402000
U-4015 | Highway | STI (Prioritization) | SR 1556 (Gallimore Dairy Road) | NC 68 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 1.6 | Guilford | 7 | Greensboro Urban Area MPO | [5 empty] | 7113000
U-4015A | Highway | STI (Prioritization) | SR 1556 (Gallimore Dairy Road) | NC 68 to Airpark Road in Greensboro | Widen to multilane. | 1.17 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T | CONSTRUCTION | 20590000 | FY 2026: 7543000; FY 2027: 3302000; FY 2028: 6416000
U-4015B | Highway | Pre-STI (Historic) | SR 1556 (Gallimore Dairy Road) | Airpark Road to SR 1008 (West Market Street) in Greensboro | Widen to multi-lanes. |  | Guilford | 7 | Greensboro Urban Area MPO | COMPLETE
U-4024 | Highway | STI (Prioritization) | US 601 | Existing US 74 to the Monroe Bypass. | Widen to multi-lanes. | 0.89 | Union | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2045000
U-4024 | Highway | STI (Prioritization) | US 601 | Existing US 74 to the Monroe Bypass. | Widen to multi-lanes. | 0.89 | Union | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1200000
U-4024 | Highway | STI (Prioritization) | US 601 | Existing US 74 to the Monroe Bypass. | Widen to multi-lanes. | 0.89 | Union | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 770000
U-4024 | Highway | STI (Prioritization) | US 601 | Existing US 74 to the Monroe Bypass. | Widen to multi-lanes. | 0.89 | Union | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 27700000
U-4403 | Highway | STI (Prioritization) | US 401 (Ramsey Street) | US 401 Business (Martin Luther King, Jr. Freeway) to north of Slocumb Road. | Widen to multi-lanes. | 8.5 | Cumberland | 6 | Fayetteville Area MPO | [5 empty] | 5900000
U-4403A | Highway | STI (Prioritization) | US 401 Business | NC 24 / NC 210 (Grove Street) to US 401 Business (Martin Luther King, Jr. Freeway). | Widen to multi-lanes. |  | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3121000 | [10 empty] | 3121000
U-4403A | Highway | STI (Prioritization) | US 401 Business | NC 24 / NC 210 (Grove Street) to US 401 Business (Martin Luther King, Jr. Freeway). | Widen to multi-lanes. |  | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 7400000 | [10 empty] | 7400000
U-4403B | Highway | STI (Prioritization) | US 401 Business | US 401 Business (Martin Luther King, Jr. Freeway) to US 401 Bypass. | Widen to multi-lanes. | 2.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 20200000
U-4403B | Highway | STI (Prioritization) | US 401 Business | US 401 Business (Martin Luther King, Jr. Freeway) to US 401 Bypass. | Widen to multi-lanes. | 2.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 12600000
U-4403B | Highway | STI (Prioritization) | US 401 Business | US 401 Business (Martin Luther King, Jr. Freeway) to US 401 Bypass. | Widen to multi-lanes. | 2.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 56500000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 Bypass to north of Slocumb Road. | Widen to multi-lanes. | 5.08 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | RIGHT-OF-WAY | 23400000 | FY 2030: 1638000; FY 2031: 6786000; FY 2032: 6552000; FY 2033: 3744000; FY 2034: 4680000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 Bypass to north of Slocumb Road. | Widen to multi-lanes. | 5.08 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | UTILITIES | 20900000 | FY 2030: 6966000; FY 2031: 6967000; FY 2032: 6967000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 Bypass to north of Slocumb Road. | Widen to multi-lanes. | 5.08 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | CONSTRUCTION | 55300000 | FY 2033: 6083000; FY 2034: 14931000; FY 2035: 13825000 | 20461000
U-4404 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | McPherson Church Road to SR 1404 (Morganton Road). | Widen roadway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 1500000
U-4404 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | McPherson Church Road to SR 1404 (Morganton Road). | Widen roadway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | RIGHT-OF-WAY | 5800000 | FY 2029: 58000; FY 2030: 2262000; FY 2031: 2320000; FY 2032: 580000; FY 2033: 580000
U-4404 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | McPherson Church Road to SR 1404 (Morganton Road). | Widen roadway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | UTILITIES | 5400000 | FY 2029: 2700000; FY 2030: 2700000
U-4404 | Highway | STI (Prioritization) | SR 1400 (Cliffdale Road) | McPherson Church Road to SR 1404 (Morganton Road). | Widen roadway. | 0.94 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | T | CONSTRUCTION | 10800000 | FY 2032: 108000; FY 2033: 5724000; FY 2034: 3996000; FY 2035: 972000
U-4405 | Highway | STI (Prioritization) | US 401 (Raeford Road) | SR 3569 (Old Raeford Road) to east of SR 3828 (Robeson Street) in Fayetteville. | Construct access management improvements. | 6 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  |  |  | 70096000
U-4405A | Highway | STI (Prioritization) | US 401 (Raeford Road) | Old Raeford Road to east of Brighton Road in Fayetteville. | Construct access management improvements. | 2.22 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | BGANY | CONSTRUCTION | 35403000
U-4405B | Highway | STI (Prioritization) | US 401 (Raeford Road) | East of Brighton Road to east of Glensford Drive in Fayetteville. | Construct access management improvements. | 1.61 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | BGANY | CONSTRUCTION | 56180000 | FY 2026: 19988000; FY 2027: 13676000; FY 2028: 7788000
U-4405B | Highway | STI (Prioritization) | US 401 (Raeford Road) | East of Brighton Road to east of Glensford Drive in Fayetteville. | Construct access management improvements. | 1.61 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | L | CONSTRUCTION | 10777000 | FY 2026: 3880000; FY 2027: 2586000; FY 2028: 1509000
U-4405C | Highway | STI (Prioritization) | US 401 (Raeford Road) | East of SR 1596 (Glensford Drive) to east of Robeson Street in Fayetteville. | Construct access management improvements. | 2.38 | Cumberland | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 6 |  | T | BUILD NC CON | 15600000 |  |  |  | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 8320000
U-4405C | Highway | STI (Prioritization) | US 401 (Raeford Road) | East of SR 1596 (Glensford Drive) to east of Robeson Street in Fayetteville. | Construct access management improvements. | 2.38 | Cumberland | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Division 6 |  | T | CONSTRUCTION | 51400000 | FY 2029: 0; FY 2030: 12726000; FY 2031: 15216000; FY 2032: 13314000; FY 2033: 10144000
U-4407 | Highway | STI (Prioritization) | US 70 Business (East Ash Street) | SR 1711 (South Oak Forest Road) to US 70 Bypass. | Widen to three lanes. | 1.88 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Region A |  |  |  | 750000
U-4407 | Highway | STI (Prioritization) | US 70 Business (East Ash Street) | SR 1711 (South Oak Forest Road) to US 70 Bypass. | Widen to three lanes. | 1.88 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Region A |  | T | RIGHT-OF-WAY | 4900000 | FY 2026: 1078000; FY 2027: 2107000; FY 2028: 735000; FY 2029: 490000; FY 2030: 490000
U-4407 | Highway | STI (Prioritization) | US 70 Business (East Ash Street) | SR 1711 (South Oak Forest Road) to US 70 Bypass. | Widen to three lanes. | 1.88 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Region A |  | T | UTILITIES | 5300000 | FY 2026: 2650000; FY 2027: 2650000
U-4407 | Highway | STI (Prioritization) | US 70 Business (East Ash Street) | SR 1711 (South Oak Forest Road) to US 70 Bypass. | Widen to three lanes. | 1.88 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Region A |  | T | BUILD NC CON | 13005000 |  |  |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
U-4407 | Highway | STI (Prioritization) | US 70 Business (East Ash Street) | SR 1711 (South Oak Forest Road) to US 70 Bypass. | Widen to three lanes. | 1.88 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE). | Region A |  | T | CONSTRUCTION | 21300000 | FY 2029: 5947000; FY 2030: 329000; FY 2031: 7825000; FY 2032: 5634000; FY 2033: 1565000
U-4424 | Highway | STI (Prioritization) | NC 111 (Wilson Street) | US 64 Alternate (Western Boulevard) to NC 122 (McNair Road). | Widen to three lanes. | 2.28 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 4 |  |  |  | 5072000
U-4424 | Highway | STI (Prioritization) | NC 111 (Wilson Street) | US 64 Alternate (Western Boulevard) to NC 122 (McNair Road). | Widen to three lanes. | 2.28 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 4 |  | T | BUILD NC CON | 6645000 | 443000 | 443000 | 443000 | 443000 | 443000 | 443000 | 443000 | 443000 | 443000 | 443000 | 1772000
U-4424 | Highway | STI (Prioritization) | NC 111 (Wilson Street) | US 64 Alternate (Western Boulevard) to NC 122 (McNair Road). | Widen to three lanes. | 2.28 | Edgecombe | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 4 |  | T | CONSTRUCTION | 15000000 | FY 2026: 3200000
U-4434 | Highway | STI (Prioritization) | SR 1209 (Independence Boulevard Extension) | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Extend roadway on new location. | 1.81 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 4163000
U-4434 | Highway | STI (Prioritization) | SR 1209 (Independence Boulevard Extension) | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Extend roadway on new location. | 1.81 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 133500000
U-4434 | Highway | STI (Prioritization) | SR 1209 (Independence Boulevard Extension) | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Extend roadway on new location. | 1.81 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 2300000
U-4434 | Highway | STI (Prioritization) | SR 1209 (Independence Boulevard Extension) | Randall Parkway to US 74 (Martin Luther King, Jr. Parkway) in Wilmington. | Extend roadway on new location. | 1.81 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 288800000
U-4437 | Highway | STI (Prioritization) | NC 54 (Hillsborough Street) | SR 1664 / SR 3074 (Blue Ridge Road) in vicinity of NC Railroad (CSX Corporation and Norfolk Southern) in Raleigh. | Construct grade separations and access road between NC 54 and SR 1664 / SR 3074. | 3 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT | Division 5 |  |  |  | 69748000
U-4700 | Highway | STI (Prioritization) | US 321 | North of US 70 in Hickory to SR 1933 (Southwest Boulevard). | Widen to six lanes. | 13.3 | Caldwell, Catawba, Burke | 11, 12, 13 | Greater Hickory MPO | INCLUDES B-4450. |  |  |  |  | 11864000
U-4700A | Highway | STI (Prioritization) | US 321 | North of US 70 in Hickory to US 321A. | Widen to six lanes. | 3.35 | Catawba, Caldwell, Burke | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | NHP | GARVEE ROW | 45045000 | 3003000 | 3003000 | 3003000 | 3003000 | 3003000 | 3003000 | 3003000 | 3003000 | 3003000 | 3003000
U-4700A | Highway | STI (Prioritization) | US 321 | North of US 70 in Hickory to US 321A. | Widen to six lanes. | 3.35 | Catawba, Caldwell, Burke | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 15100000
U-4700A | Highway | STI (Prioritization) | US 321 | North of US 70 in Hickory to US 321A. | Widen to six lanes. | 3.35 | Catawba, Caldwell, Burke | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 15000000
U-4700A | Highway | STI (Prioritization) | US 321 | North of US 70 in Hickory to US 321A. | Widen to six lanes. | 3.35 | Catawba, Caldwell, Burke | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | NHP | CONSTRUCTION | 275529000 | FY 2027: 2755000; FY 2028: 74393000; FY 2029: 71638000; FY 2030: 66127000; FY 2031: 60616000
U-4700A | Highway | STI (Prioritization) | US 321 | North of US 70 in Hickory to US 321A. | Widen to six lanes. | 3.35 | Catawba, Caldwell, Burke | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | L | CONSTRUCTION | 699000 | FY 2027: 7000; FY 2028: 188000; FY 2029: 194000; FY 2030: 171000; FY 2031: 139000
U-4700AA | Highway | Bridges | US 321 | Bridge 130367 over Lake Hickory. | Construct interim structure improvements. | 0.5 | Burke, Caldwell | 11, 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHP | CONSTRUCTION | 2705000
U-4700B | Highway | STI (Prioritization) | US 321 | US 321A to SR 1108 (Mission Road). | Widen to six lanes. | 0 | Caldwell | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 35000000 | [10 empty] | 35000000
U-4700B | Highway | STI (Prioritization) | US 321 | US 321A to SR 1108 (Mission Road). | Widen to six lanes. | 0 | Caldwell | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | UTILITIES | 4000000 | [10 empty] | 4000000
U-4700B | Highway | STI (Prioritization) | US 321 | US 321A to SR 1108 (Mission Road). | Widen to six lanes. | 0 | Caldwell | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | CONSTRUCTION | 57500000 | [10 empty] | 57500000
U-4700C | Highway | STI (Prioritization) | US 321 | SR 1108 (Mission Road) to SR 1933 (Southwest Boulevard). | Widen to six lanes. | 0 | Caldwell | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 5000000 | [10 empty] | 5000000
U-4700C | Highway | STI (Prioritization) | US 321 | SR 1108 (Mission Road) to SR 1933 (Southwest Boulevard). | Widen to six lanes. | 0 | Caldwell | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | UTILITIES | 2000000 | [10 empty] | 2000000
U-4700C | Highway | STI (Prioritization) | US 321 | SR 1108 (Mission Road) to SR 1933 (Southwest Boulevard). | Widen to six lanes. | 0 | Caldwell | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | CONSTRUCTION | 12000000 | [10 empty] | 12000000
U-4700CA | Highway | STI (Prioritization) | US 321 | SR 1160 (Mount Herman Road) intersection in Hudson. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | Region F |  | NHP | RIGHT-OF-WAY | 420000
U-4700CA | Highway | STI (Prioritization) | US 321 | SR 1160 (Mount Herman Road) intersection in Hudson. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | Region F |  | NHP | CONSTRUCTION | 7200000 | FY 2026: 72000; FY 2027: 3657000; FY 2028: 2781000; FY 2029: 690000
U-4700CB | Highway | STI (Prioritization) | US 321 | SR 1809 / SR 1952 (Pine Mountain Road) intersection in Hudson. | Upgrade intersection to reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 1070000
U-4700CB | Highway | STI (Prioritization) | US 321 | SR 1809 / SR 1952 (Pine Mountain Road) intersection in Hudson. | Upgrade intersection to reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 100000
U-4700CB | Highway | STI (Prioritization) | US 321 | SR 1809 / SR 1952 (Pine Mountain Road) intersection in Hudson. | Upgrade intersection to reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 11998000 | FY 2026: 120000; FY 2027: 5467000; FY 2028: 4602000; FY 2029: 1809000
U-4700CC | Highway | STI (Prioritization) | US 321 | SR 1108 (Mission Road) intersection in Sawmills. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 450000
U-4700CC | Highway | STI (Prioritization) | US 321 | SR 1108 (Mission Road) intersection in Sawmills. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 100000
U-4700CC | Highway | STI (Prioritization) | US 321 | SR 1108 (Mission Road) intersection in Sawmills. | Construct reduced conflict intersection within the limits of U-4700C. | 0.5 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 8300000 | FY 2026: 4050000; FY 2027: 3217000; FY 2028: 950000
U-4709 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC. | Division 6 |  |  |  | 1400000
U-4709 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC. | Division 6 |  | T | RIGHT-OF-WAY | 9556000
U-4709 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC. | Division 6 |  | T | UTILITIES | 1575000
U-4709 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC. | Division 6 |  | T | BUILD NC CON | 10395000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 3465000
U-4709 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC. | Division 6 |  | T | CONSTRUCTION | 11540000 | FY 2026: 289000; FY 2027: 3904000
U-4709 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road); SR 1115 (Golfview Road) | SR 1115 (Golfview Road) to SR 1596 (Main Street); SR 1112 (Rockfish Road) to SR 1596 (Main Street). | Widen to four lanes. | 1.05 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). O FUNDS REPRESENT UTILITY PAYBACK FROM FAYETTEVILLE PWC. | Division 6 |  | O | CONSTRUCTION | 5540000
U-4712 | Highway | STI (Prioritization) | US 23 Business (South Main Street) | SR 1164 (Hyatt Creek Road) to US 276 (Pigeon Street). | Widen to multi-lanes. | 2.09 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 680000
U-4712 | Highway | STI (Prioritization) | US 23 Business (South Main Street) | SR 1164 (Hyatt Creek Road) to US 276 (Pigeon Street). | Widen to multi-lanes. | 2.09 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 27100000
U-4712 | Highway | STI (Prioritization) | US 23 Business (South Main Street) | SR 1164 (Hyatt Creek Road) to US 276 (Pigeon Street). | Widen to multi-lanes. | 2.09 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4800000
U-4712 | Highway | STI (Prioritization) | US 23 Business (South Main Street) | SR 1164 (Hyatt Creek Road) to US 276 (Pigeon Street). | Widen to multi-lanes. | 2.09 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 25501000
U-4713 | Highway | STI (Prioritization) | New route | SR 3457 (Campus Ridge Road) to SR 3448 (Pleasant Plains Road) in Matthews. | Construct two lane roadway on new location. | 1.1 | Mecklenburg | 10 | Charlotte Regional TPO | [5 empty] | 0
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | T | ENGINEERING | 1155000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | T | BUILD NC ROW | 360000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | T | RIGHT-OF-WAY | 2320000
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | T | UTILITIES | 1100000
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | T | BUILD NC CON | 5205000 | 347000 | 347000 | 347000 | 347000 | 347000 | 347000 | 347000 | 347000 | 347000 | 347000 | 1735000
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | T | CONSTRUCTION | 8471000 | FY 2026: 1861000; FY 2027: 3118000
U-4713A | Highway | STI (Prioritization) | SR 3440 (McKee Road) Extension | SR 3448 (Pleasant Plains Road) to SR 1010 (East John Street). | Construct two lane roadway on new location. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $888,488 FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $4M FOR CON, PAYBACK FY 26-40 (FY 26 / YR 6 SALE). LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS | Division 10 |  | L | CONSTRUCTION | 1940000 | FY 2026: 912000; FY 2027: 485000
U-4713B | Highway | Transition |  |  |  | 1.1 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE | Pre-STI (Transition)
U-4714 | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | SR 3348 / SR 3474 (Trade Street) to SR 1377 (Wesley Chapel-Stouts Road). | Widen to multi-lanes. | 6.5 | Union, Mecklenburg | 10 | Charlotte Regional TPO | [5 empty] | 23619000
U-4714AA | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | SR 3348 / SR 3474 (Trade Street) to west of I-485. | Widen to multi-lanes. | 1.01 | Mecklenburg | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 19700000 | [10 empty] | 19700000
U-4714AA | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | SR 3348 / SR 3474 (Trade Street) to west of I-485. | Widen to multi-lanes. | 1.01 | Mecklenburg | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 1600000 | [10 empty] | 1600000
U-4714AA | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | SR 3348 / SR 3474 (Trade Street) to west of I-485. | Widen to multi-lanes. | 1.01 | Mecklenburg | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | CONSTRUCTION | 30600000 | [10 empty] | 30600000
U-4714AB | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | I-485 interchange in Matthews | Construct interchange improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. LET WITH I-5507. | Division 10
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | BGANY | RIGHT-OF-WAY | 498000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | BGDA | RIGHT-OF-WAY | 9026000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T(M) | RIGHT-OF-WAY | 2256000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T | UTILITIES | 2200000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T | BUILD NC CON | 19500000 |  |  | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 9100000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T(M) | CONSTRUCTION | 1925000 | FY 2027: 212000; FY 2028: 943000; FY 2029: 558000; FY 2030: 212000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T(DA) | CONSTRUCTION | 7700000 | FY 2027: 847000; FY 2028: 3773000; FY 2029: 2233000; FY 2030: 847000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | East of I-485 to west of Morningside Meadow Lane | Widen to multi-lanes. | 2.02 | Union, Mecklenburg | 10 | Charlotte Regional TPO | $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T | CONSTRUCTION | 16075000 | FY 2027: 3418000; FY 2028: 227000; FY 2029: 9012000; FY 2030: 3418000
U-4714BA | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | West of Morningside Meadow Lane to Indian Trail Road | Widen to multi-lanes. | 3.16 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. NC BUILD BONDS: $8.5M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T | BUILD NC CON | 11055000 |  |  | 737000 | 737000 | 737000 | 737000 | 737000 | 737000 | 737000 | 737000 | 5159000
U-4714BA | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | West of Morningside Meadow Lane to Indian Trail Road | Widen to multi-lanes. | 3.16 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. NC BUILD BONDS: $8.5M ON CONSTRUCTION PAYBACK 2028-2042 (SALE 8 / FY 2028). | Division 10 |  | T | CONSTRUCTION | 11500000 | FY 2027: 2200000; FY 2028: 1300000; FY 2029: 5800000; FY 2030: 2200000
U-4714BB | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | Indian Trail Road to east of SR 1377 (Wesley Chapel-Stouts Road). | Widen to multi-lanes. | 3.16 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $35.2M ON CONSTRUCTION PAYBACK 2029-2043 (SALE 9 / FY 2029). OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL. | Division 10 |  | T | BUILD NC CON | 45765000 |  |  |  | 3051000 | 3051000 | 3051000 | 3051000 | 3051000 | 3051000 | 3051000 | 24408000
U-4714BB | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | Indian Trail Road to east of SR 1377 (Wesley Chapel-Stouts Road). | Widen to multi-lanes. | 3.16 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $35.2M ON CONSTRUCTION PAYBACK 2029-2043 (SALE 9 / FY 2029). OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL. | Division 10 |  | T | CONSTRUCTION | 29000000 | FY 2028: 5778000; FY 2029: 0; FY 2030: 8456000; FY 2031: 10914000; FY 2032: 3852000
U-4714BB | Highway | STI (Prioritization) | SR 1009 (John Street / Old Monroe Road) | Indian Trail Road to east of SR 1377 (Wesley Chapel-Stouts Road). | Widen to multi-lanes. | 3.16 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $35.2M ON CONSTRUCTION PAYBACK 2029-2043 (SALE 9 / FY 2029). OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL. | Division 10 |  | O | CONSTRUCTION | 3000000 | FY 2028: 270000; FY 2029: 1170000; FY 2030: 870000; FY 2031: 510000; FY 2032: 180000
U-4716 | Rail | Other | Various | Routes and Norfolk Southern Railroad / North Carolina Railroad in Durham and Morrisville. South of I-40 to north of McCrimmon Parkway. | Construct a grade separation at SR 1978 (Hopson Road), extend Church Street to Hopson Road, close Church Street crossing |  | Durham, Wake | 5 | Triangle West TPO, Capital Area MPO | [5 empty] | 31776000
U-4716A | Rail | Other | SR 1978 (Hopson Road) | 0.2 miles west of NC 54 | Construct railroad grade separation and shift rail line. |  | Durham | 5 | Triangle West TPO | PROJECT COMPLETE
U-4716B | Rail | Pre-STI (Historic) | SR 1980 (Church Street) | 0.1 miles west of NC 54 | Realign and close crossing 734748M of the Norfolk Southern NC Railroad. |  | Durham | 5 | Triangle West TPO | PROJECT COMPLETE | Pre-STI (Transition)
U-4716C | Rail | Other | Norfolk-Southern Railroad / NC Railroad | Clegg to Nelson | Construct passing siding. |  | Durham, Wake | 5 | Capital Area MPO, Triangle West TPO | PROJECT COMPLETE
U-4716D | Highway | STI (Prioritization) | SR 1978 (Hopson Road) | East of SR 1999 (Davis Drive) to NC 54 | Widen to multi-lanes. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | O | RIGHT-OF-WAY | 1126000 | [10 empty] | 1126000
U-4716D | Highway | STI (Prioritization) | SR 1978 (Hopson Road) | East of SR 1999 (Davis Drive) to NC 54 | Widen to multi-lanes. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | O | CONSTRUCTION | 3160000 | [10 empty] | 3160000
U-4724 | Bike & Ped | Transition | SR 1158 (Cornwallis Road) | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  |  |  | 856000
U-4724 | Bike & Ped | Transition | SR 1158 (Cornwallis Road) | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | BGANY | RIGHT-OF-WAY | 1785000
U-4724 | Bike & Ped | Transition | SR 1158 (Cornwallis Road) | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | L | RIGHT-OF-WAY | 448000
U-4724 | Bike & Ped | Transition | SR 1158 (Cornwallis Road) | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 9600000 | FY 2026: 9600000
U-4724 | Bike & Ped | Transition | SR 1158 (Cornwallis Road) | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 300000 | FY 2026: 300000
U-4724 | Bike & Ped | Transition | SR 1158 (Cornwallis Road) | SR 2295 (South Roxboro Street) to SR 1127 (Chapel Hill Road) in Durham | Construct bicycle and pedestrian features. | 1.17 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | L | CONSTRUCTION | 2500000 | FY 2026: 2500000
U-4726 | Bike & Ped | Locally Selected | Various | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Division 5, 7, 8 |  |  |  | 12842000
U-4726 | Bike & Ped | Locally Selected | Various | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Division 5, 7, 8 |  | BGDA | RIGHT-OF-WAY | 1527000
U-4726 | Bike & Ped | Locally Selected | Various | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Division 5, 7, 8 |  | L | RIGHT-OF-WAY | 382000
U-4726 | Bike & Ped | Locally Selected | Various | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Division 5, 7, 8 |  | BGANY | CONSTRUCTION | 429000
U-4726 | Bike & Ped | Locally Selected | Various | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Division 5, 7, 8 |  | BGDA | CONSTRUCTION | 8984000
U-4726 | Bike & Ped | Locally Selected | Various | Triangle West Transportation Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | IN PROGRESS | Division 5, 7, 8 |  | L | CONSTRUCTION | 2353000
U-4726DF | Bike & Ped | Locally Selected | Various | Various | Install bicycle detection at signalized intersections. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 29000
U-4726DF | Bike & Ped | Locally Selected | Various | Various | Install bicycle detection at signalized intersections. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | BGDA | CONSTRUCTION | 96000
U-4726DF | Bike & Ped | Locally Selected | Various | Various | Install bicycle detection at signalized intersections. |  | Orange | 7 | Triangle West TPO |  | Exempt |  | L | CONSTRUCTION | 31000
U-4726HN | Bike & Ped | Locally Selected | SR 1321 (Hillandale Road) | I-85 to NC 147 (Durham Freeway) in Durham | Install pedestrian improvements. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | BGDA | CONSTRUCTION | 4195000
U-4726HN | Bike & Ped | Locally Selected | SR 1321 (Hillandale Road) | I-85 to NC 147 (Durham Freeway) in Durham | Install pedestrian improvements. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | CONSTRUCTION | 1049000
U-4726HO | Bike & Ped | Locally Selected | Carpenter Fletcher Road | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | TADA | ENGINEERING | 8000
U-4726HO | Bike & Ped | Locally Selected | Carpenter Fletcher Road | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | ENGINEERING | 2000
U-4726HO | Bike & Ped | Locally Selected | Carpenter Fletcher Road | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 22000
U-4726HO | Bike & Ped | Locally Selected | Carpenter Fletcher Road | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | RIGHT-OF-WAY | 5000
U-4726HO | Bike & Ped | Locally Selected | Carpenter Fletcher Road | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | BGANY | CONSTRUCTION | 6305000
U-4726HO | Bike & Ped | Locally Selected | Carpenter Fletcher Road | Woodcroft Parkway to SR 1945 (Alston Avenue) | Construct bicycle lanes and sidewalks. |  | Durham | 5 | Triangle West TPO |  | Division 5 |  | L | CONSTRUCTION | 1576000
U-4726IK | Bike & Ped | Locally Selected | SR 1777 (Homestead Road) | SR 1843 (Seawell School Road) to SR 1733 (Weaver Dairy Road Extension) | Construct sidewalks. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | BGDA | CONSTRUCTION | 1600000
U-4726IK | Bike & Ped | Locally Selected | SR 1777 (Homestead Road) | SR 1843 (Seawell School Road) to SR 1733 (Weaver Dairy Road Extension) | Construct sidewalks. |  | Orange | 7 | Triangle West TPO |  | Division 7 |  | L | CONSTRUCTION | 400000
U-4727 | Highway | Locally Selected | Various. | Triangle West Transportation Planning Organization. | Planning (PL) Supplement. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | Division 5, 7, 8 |  |  |  | 15908000
U-4727 | Highway | Locally Selected | Various. | Triangle West Transportation Planning Organization. | Planning (PL) Supplement. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | Division 5, 7, 8 |  | BGDA | PLANNING | 21422000 | FY 2026: 3641000; FY 2027: 3403000; FY 2028: 3574000; FY 2029: 3752000
U-4727 | Highway | Locally Selected | Various. | Triangle West Transportation Planning Organization. | Planning (PL) Supplement. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | Division 5, 7, 8 |  | L | PLANNING | 5354000 | FY 2026: 910000; FY 2027: 850000; FY 2028: 894000; FY 2029: 938000
U-4734 | Highway | STI (Prioritization) | New Route (Macy Grove Road Extension) | SR 1005 (East Mountain Street) to NC 150 (North Main Street) in Kernersville. | Four-lane divided facility on new location. | 1.52 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 9 |  |  |  | 13700000
U-4734 | Highway | STI (Prioritization) | New Route (Macy Grove Road Extension) | SR 1005 (East Mountain Street) to NC 150 (North Main Street) in Kernersville. | Four-lane divided facility on new location. | 1.52 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | BUILD NC CON | 11172000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000
U-4735 | Highway | Locally Selected | Various | Capital Area Metropolitan Metropolitan Planning Organization (CAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | BGANY | CONSTRUCTION | 0
U-4735 | Highway | Locally Selected | Various | Capital Area Metropolitan Metropolitan Planning Organization (CAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 162642000 | 0 | 7194000 | 18006000 | 18006000 | 19906000 | 19906000 | 19906000 | 19906000 | 19906000 | 19906000
U-4739 | Highway | STI (Prioritization) | SR 3556 (Amboy Road / Meadow Road) | I-240 to NC 81 / SR 3214 (Biltmore Avenue). | Upgrade roadway with new bridge over the French Broad River. | 2.87 | Buncombe | 13 | French Broad River MPO | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 13 |  |  |  | 622000
U-4739 | Highway | STI (Prioritization) | SR 3556 (Amboy Road / Meadow Road) | I-240 to NC 81 / SR 3214 (Biltmore Avenue). | Upgrade roadway with new bridge over the French Broad River. | 2.87 | Buncombe | 13 | French Broad River MPO | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 13 |  | BGANY | RIGHT-OF-WAY | 24100000 | FY 2027: 1687000; FY 2028: 6748000; FY 2029: 6507000; FY 2030: 4338000; FY 2031: 4820000
U-4739 | Highway | STI (Prioritization) | SR 3556 (Amboy Road / Meadow Road) | I-240 to NC 81 / SR 3214 (Biltmore Avenue). | Upgrade roadway with new bridge over the French Broad River. | 2.87 | Buncombe | 13 | French Broad River MPO | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 13 |  | BGANY | UTILITIES | 5400000 | FY 2027: 2700000; FY 2028: 2700000
U-4739 | Highway | STI (Prioritization) | SR 3556 (Amboy Road / Meadow Road) | I-240 to NC 81 / SR 3214 (Biltmore Avenue). | Upgrade roadway with new bridge over the French Broad River. | 2.87 | Buncombe | 13 | French Broad River MPO | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 13 |  | T | BUILD NC CON | 16905000 |  |  |  |  | 1127000 | 1127000 | 1127000 | 1127000 | 1127000 | 1127000 | 10143000
U-4739 | Highway | STI (Prioritization) | SR 3556 (Amboy Road / Meadow Road) | I-240 to NC 81 / SR 3214 (Biltmore Avenue). | Upgrade roadway with new bridge over the French Broad River. | 2.87 | Buncombe | 13 | French Broad River MPO | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 13 |  | T | CONSTRUCTION | 45300000 | FY 2030: 0; FY 2031: 4490000; FY 2032: 15158000; FY 2033: 13992000; FY 2034: 11660000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 13675000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | RIGHT-OF-WAY | 630000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 158000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | CONSTRUCTION | 487000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1599000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 276000
U-4741 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 591000
U-4741OK | Bike & Ped | Locally Selected | Piedmont Regional Greenway | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 98000
U-4741OK | Bike & Ped | Locally Selected | Piedmont Regional Greenway | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 25000
U-4741OK | Bike & Ped | Locally Selected | Piedmont Regional Greenway | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 720000
U-4741OK | Bike & Ped | Locally Selected | Piedmont Regional Greenway | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 180000
U-4741OK | Bike & Ped | Locally Selected | Piedmont Regional Greenway | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 1598000 | FY 2027: 1598000
U-4741OK | Bike & Ped | Locally Selected | Piedmont Regional Greenway | SR 2022 (Linville Road) near Salem Lake to SR 2667 Hastings Hill Road | Construct greenway. |  | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 400000 | FY 2027: 400000
U-4742 | Highway | Locally Selected | Winston-Salem Urban Area Metropolitan Planning Organization (WSUAMPO) | Various | Construct intersection improvements. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 7170000
U-4742 | Highway | Locally Selected | Winston-Salem Urban Area Metropolitan Planning Organization (WSUAMPO) | Various | Construct intersection improvements. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 700000
U-4742 | Highway | Locally Selected | Winston-Salem Urban Area Metropolitan Planning Organization (WSUAMPO) | Various | Construct intersection improvements. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 175000
U-4744 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | BGDA | CONSTRUCTION | 155895000 | 0 | 0 | 7871000 | 17263000 | 15523000 | 23345000 | 23345000 | 23345000 | 22312000 | 22891000
U-4744 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization (CRTPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | L | CONSTRUCTION | 38982000 | 0 | 0 | 1968000 | 4316000 | 3880000 | 5839000 | 5839000 | 5839000 | 5578000 | 5723000
U-4751 | Highway | STI (Prioritization) | SR 1409 (Military Cutoff Road Extension) | SR 1409 (Military Cutoff Road) to US 17 (Market Street) in Wilmington. | Construct roadway on new location. | 3.61 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  |  |  | 255562000
U-4751 | Highway | STI (Prioritization) | SR 1409 (Military Cutoff Road Extension) | SR 1409 (Military Cutoff Road) to US 17 (Market Street) in Wilmington. | Construct roadway on new location. | 3.61 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | ENGINEERING | 14850000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000
U-4751 | Highway | STI (Prioritization) | SR 1409 (Military Cutoff Road Extension) | SR 1409 (Military Cutoff Road) to US 17 (Market Street) in Wilmington. | Construct roadway on new location. | 3.61 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | RIGHT-OF-WAY | 355000
U-4751 | Highway | STI (Prioritization) | SR 1409 (Military Cutoff Road Extension) | SR 1409 (Military Cutoff Road) to US 17 (Market Street) in Wilmington. | Construct roadway on new location. | 3.61 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | BUILD NC CON | 36135000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000
U-4751 | Highway | STI (Prioritization) | SR 1409 (Military Cutoff Road Extension) | SR 1409 (Military Cutoff Road) to US 17 (Market Street) in Wilmington. | Construct roadway on new location. | 3.61 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | CONSTRUCTION | 49615000
U-4751A | Highway | STI (Prioritization) | Lendire Road | West of US 17 Business (Market Street) to US 17 Business (Market Street) / SR 1403 (Middle Sound Loop Road). | Realign roadway. | 0.31 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility
U-4753 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | SR 1003 (New Hope Road) to US 70 in Goldsboro. | Widen to four lanes. | 0.87 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  |  |  | 920000
U-4753 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | SR 1003 (New Hope Road) to US 70 in Goldsboro. | Widen to four lanes. | 0.87 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | T | RIGHT-OF-WAY | 6180000
U-4753 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | SR 1003 (New Hope Road) to US 70 in Goldsboro. | Widen to four lanes. | 0.87 | Wayne | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | T | CONSTRUCTION | 21900000 | FY 2026: 3285000; FY 2027: 8103000; FY 2028: 6132000; FY 2029: 4380000
U-4758 | Highway | STI (Prioritization) | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 7518000
U-4758 | Highway | STI (Prioritization) | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | HP | RIGHT-OF-WAY | 6776000
U-4758 | Highway | STI (Prioritization) | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | RIGHT-OF-WAY | 4751000
U-4758 | Highway | STI (Prioritization) | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T(M) | RIGHT-OF-WAY | 1694000
U-4758 | Highway | STI (Prioritization) | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | UTILITIES | 7200000
U-4758 | Highway | STI (Prioritization) | SR 1818 (Johnston Street) / SR 1850 (Sandy Ridge Road) | SR 1820 (Skeet Club Road) to south of I-40 in High Point. | Widen to four lanes. | 4.45 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | CONSTRUCTION | 74901000 | FY 2026: 25893000; FY 2027: 16085000; FY 2028: 9115000; FY 2029: 4104000
U-4762 | Highway | STI (Prioritization) | SR 1250 (Springfield Road) | US 64 Alternate to SR 1243 (Leggett Road). | Widen to three lanes. | 1.26 | Edgecombe | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  |  |  | 2892000
U-4762 | Highway | STI (Prioritization) | SR 1250 (Springfield Road) | US 64 Alternate to SR 1243 (Leggett Road). | Widen to three lanes. | 1.26 | Edgecombe | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | ENGINEERING | 1995000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000
U-4762 | Highway | STI (Prioritization) | SR 1250 (Springfield Road) | US 64 Alternate to SR 1243 (Leggett Road). | Widen to three lanes. | 1.26 | Edgecombe | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 6255000 | 417000 | 417000 | 417000 | 417000 | 417000 | 417000 | 417000 | 417000 | 224000 | 224000
U-4850 | Highway | Locally Selected | Various | Capital Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | Division 4, 5, 6 |  |  |  | 7089000
U-4850 | Highway | Locally Selected | Various | Capital Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | Division 4, 5, 6 |  | BGDA | PLANNING | 16269000 | FY 2026: 1900000; FY 2027: 1900000; FY 2028: 1900000; FY 2029: 1900000
U-4850 | Highway | Locally Selected | Various | Capital Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | Division 4, 5, 6 |  | L | PLANNING | 4067000 | FY 2026: 475000; FY 2027: 475000; FY 2028: 475000; FY 2029: 475000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  |  |  | 3372000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | BGDA | RIGHT-OF-WAY | 8480000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | T(M) | RIGHT-OF-WAY | 2120000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | BGDA | UTILITIES | 12000000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | T(M) | UTILITIES | 3000000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | BGDA | CONSTRUCTION | 27600000 | FY 2027: 2760000; FY 2028: 8004000; FY 2029: 7452000; FY 2030: 5796000; FY 2031: 3588000
U-4900 | Highway | STI (Prioritization) | NC 210 (Murchison Road) | I-295 to south of US 401 Bypass. | Add additional lanes. | 2.33 | Cumberland | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | T(M) | CONSTRUCTION | 6900000 | FY 2026: 1380000; FY 2027: 2070000; FY 2028: 1725000; FY 2029: 1242000; FY 2030: 483000
U-4902 | Highway | STI (Prioritization) | US 17 Business (Market Street) | Colonial Drive to SR 1402 (Porters Neck Road). | Improve access management. | 8.6 | New Hanover | 3 | Wilmington Urban Area MPO | [5 empty] | 54718000
U-4902A | Highway | Pre-STI (Historic) | US 17 Business (Market Street) | SR 1272 (New Centre Drive) to Martin Luther King Jr., Boulevard | Construct access management improvements. | 0.089 | New Hanover | 3 | Wilmington Urban Area MPO | COMPLETE.
U-4902B | Highway | STI (Prioritization) | US 17 Business (Market Street) | CSX Railroad to Cinema Drive; Jacksonville Street to north of US 117 / NC 132 (College Road). | Construct access management improvements. | 1.4 | New Hanover | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000000 | [10 empty] | 10000000
U-4902B | Highway | STI (Prioritization) | US 17 Business (Market Street) | CSX Railroad to Cinema Drive; Jacksonville Street to north of US 117 / NC 132 (College Road). | Construct access management improvements. | 1.4 | New Hanover | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | UTILITIES | 2900000 | [10 empty] | 2900000
U-4902B | Highway | STI (Prioritization) | US 17 Business (Market Street) | CSX Railroad to Cinema Drive; Jacksonville Street to north of US 117 / NC 132 (College Road). | Construct access management improvements. | 1.4 | New Hanover | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 9700000 | [10 empty] | 9700000
U-4902C | Highway | STI (Prioritization) | US 17 Business (Market Street) | North of US 117 / NC 132 (College Road) to Station Road. | Construct access management improvements. | 2.19 | New Hanover | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | Statewide Mobility |  | T | RIGHT-OF-WAY | 50358000 | FY 2030: 16618000; FY 2031: 20143000; FY 2032: 3525000; FY 2033: 5036000; FY 2034: 5036000
U-4902C | Highway | STI (Prioritization) | US 17 Business (Market Street) | North of US 117 / NC 132 (College Road) to Station Road. | Construct access management improvements. | 2.19 | New Hanover | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | Statewide Mobility |  | T | UTILITIES | 5862000 | FY 2030: 2931000; FY 2031: 2931000
U-4902C | Highway | STI (Prioritization) | US 17 Business (Market Street) | North of US 117 / NC 132 (College Road) to Station Road. | Construct access management improvements. | 2.19 | New Hanover | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | Statewide Mobility |  | T | CONSTRUCTION | 112900000 | FY 2033: 22580000; FY 2034: 27096000; FY 2035: 24838000 | 38386000
U-4902D | Highway | STI (Prioritization) | US 17 Business (Market Street) | SR 1403 (Middle Sound Loop Road) to SR 2290 (Mendehnall Drive) / SR 2734 (Marsh Oaks Drive). | Construct access management improvements. | 1.66 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | ENGINEERING | 4290000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000
U-4902D | Highway | STI (Prioritization) | US 17 Business (Market Street) | SR 1403 (Middle Sound Loop Road) to SR 2290 (Mendehnall Drive) / SR 2734 (Marsh Oaks Drive). | Construct access management improvements. | 1.66 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | BUILD NC CON | 12795000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000
U-4902D | Highway | STI (Prioritization) | US 17 Business (Market Street) | SR 1403 (Middle Sound Loop Road) to SR 2290 (Mendehnall Drive) / SR 2734 (Marsh Oaks Drive). | Construct access management improvements. | 1.66 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | CONSTRUCTION | 14814000
U-4906 | Highway | Transition | SR 1308 (Gum Branch Road) | West of SR 1313 (Mills Fields Road) to east of SR 1324 (Ramsey Road) in Jacksonville. | Modernize roadway, provide paved shoulders, and construct intersection improvements. | 7.42 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 16095000
U-4910 | Highway | Transition | SR 1445 (Derita Road) | SR 2894 (Concord Mills Boulevard) to SR 1394 (Poplar Tent Road) in Concord. | Widen to three lanes divided. | 2.6 | Cabarrus | 10 | Cabarrus-Rowan MPO | SEGMENTS A AND B LET TOGETHER |  |  |  |  | 23417000
U-4910A | Highway | Locally Selected | SR 1445 (Derita Road) | SR 2894 (Concord Mills Boulevard) to Aviation Boulevard | Widen to 4-lanes divided. | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 10
U-4910B | Highway | Pre-STI (Historic) | SR 1445 (Derita Road) | Aviation Boulevard to SR 1394 (Poplar Tent Road) | Widen to three lanes divided. | 1.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 908000
U-4910B | Highway | Pre-STI (Historic) | SR 1445 (Derita Road) | Aviation Boulevard to SR 1394 (Poplar Tent Road) | Widen to three lanes divided. | 1.54 | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 227000
U-4913 | Highway | STI (Prioritization) | SR 3174 / SR 1501 (Idlewild Road) | SR 3175 (Stallings Road) to SR 1524 (Stevens Mill Road). | Widen roadway. | 0.77 | Union, Mecklenburg | 10 | Charlotte Regional TPO | PROJECT BEING ACCELERATED BY A LOAN PROVIDED BY THE TOWN OF MATTHEWS. LOAN TO BE PAID BACK TO THE TOWN WITH ROW/UTIL IN 2025 AND CON IN 2026. NCDOT TO BEGIN ROW IN 2024 AND CON IN 2026. |  |  |  |  | 1545000
U-4913A | Highway | STI (Prioritization) | SR 3174 (Idlewild Road) | SR 1375 (Stallings Road) to I-485. | Widen to four lanes. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | T | RIGHT-OF-WAY | 750000
U-4913A | Highway | STI (Prioritization) | SR 3174 (Idlewild Road) | SR 1375 (Stallings Road) to I-485. | Widen to four lanes. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | T | UTILITIES | 250000
U-4913A | Highway | STI (Prioritization) | SR 3174 (Idlewild Road) | SR 1375 (Stallings Road) to I-485. | Widen to four lanes. | 0.53 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | T | CONSTRUCTION | 10600000 | FY 2028: 4452000; FY 2029: 4134000; FY 2030: 2014000
U-4913B | Highway | STI (Prioritization) | SR 3174 / SR 1501 (Idlewild Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to six lanes. | 0.77 | Union, Mecklenburg | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 14947000 | [10 empty] | 14947000
U-4913B | Highway | STI (Prioritization) | SR 3174 / SR 1501 (Idlewild Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to six lanes. | 0.77 | Union, Mecklenburg | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 646000 | [10 empty] | 646000
U-4913B | Highway | STI (Prioritization) | SR 3174 / SR 1501 (Idlewild Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to six lanes. | 0.77 | Union, Mecklenburg | 10 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 21500000 | [10 empty] | 21500000
U-4950 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization. | Planning (PL) Supplement. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | Division 10, 12 |  | BGDA | PLANNING | 14638000 | 1440000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000
U-4950 | Highway | Locally Selected | Various | Charlotte Regional Transportation Planning Organization. | Planning (PL) Supplement. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | Division 10, 12 |  | L | PLANNING | 3660000 | 360000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000
U-4951 | Highway | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO | FORMERLY U-9999D - IN PROGRESS | Division 9 |  |  |  | 1560000
U-4951 | Highway | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO | FORMERLY U-9999D - IN PROGRESS | Division 9 |  | BGDA | PLANNING | 4477000 | FY 2026: 825000; FY 2027: 825000; FY 2028: 825000
U-4951 | Highway | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO | FORMERLY U-9999D - IN PROGRESS | Division 9 |  | L | PLANNING | 1112000 | FY 2026: 206000; FY 2027: 206000; FY 2028: 206000
U-5008 | Highway | Transition | SR 2975 (Sugar Creek Road) | North Carolina Railroad / Norfolk Southern Railway Crossing 715 352H in Charlotte. | Construct grade separation. Close Craighead Road Crossing 715 352H. |  | Mecklenburg | 10 | Charlotte Regional TPO | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS |  |  |  |  | 38497000
U-5008A | Bike & Ped | Other | North Davidson Street | East 37th Street to Bearwood Avenue in Charlotte | Construct sidewalk. | 0.59 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | DP | RIGHT-OF-WAY | 1000000
U-5008A | Bike & Ped | Other | North Davidson Street | East 37th Street to Bearwood Avenue in Charlotte | Construct sidewalk. | 0.59 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | DP | UTILITIES | 25000
U-5008A | Bike & Ped | Other | North Davidson Street | East 37th Street to Bearwood Avenue in Charlotte | Construct sidewalk. | 0.59 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | DP | CONSTRUCTION | 1200000
U-5019 | Highway | STI (Prioritization) | Riverway Multi-Modal Network | City of Asheville. | Construct interconnected network of pedestrian, bicycle, roadway, and streetscape improvements. |  | Buncombe | 13 | French Broad River MPO | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING |  |  |  |  | 10130000
U-5019A | Highway | STI (Prioritization) | Nasty Branch Greenway | Depot Street at Livingston Street Park to south of the intersection of Asheland Avenue and Phifer Street | Construct greenway. | 0.71 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 3412000 | FY 2026: 1706000
U-5019A | Highway | STI (Prioritization) | Nasty Branch Greenway | Depot Street at Livingston Street Park to south of the intersection of Asheland Avenue and Phifer Street | Construct greenway. | 0.71 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 855000
U-5019B | Highway | STI (Prioritization) | French Broad River West Greenway | French Broad River Park to Haywood Road. | Construct greenway. | 0.9 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION | Division 13
U-5019C | Highway | STI (Prioritization) | Wilma Dykeman Riverway | Riverside Drive and Lyman Street intersection in Asheville; Five Points intersection in Asheville. | Construct roundabouts. |  | Buncombe | 13 | French Broad River MPO | COMPLETE | Division 13
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | ENGINEERING | 424000 | FY 2026: 424000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | ENGINEERING | 106000 | FY 2026: 106000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 960000 | FY 2027: 960000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 240000 | FY 2027: 240000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | UTILITIES | 3040000 | FY 2027: 3040000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | UTILITIES | 760000 | FY 2027: 760000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 4250000 | FY 2028: 1615000; FY 2029: 2635000
U-5019E | Highway | STI (Prioritization) | SR 3408 (Craven Street) | Bridge 110743 over French Broad River | Construct bridge improvements. | 0.11 | Buncombe | 13 | French Broad River MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 1050000 | FY 2028: 399000; FY 2029: 651000
U-5021 | Highway | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization (GUAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Guilford | 7 | Greensboro Urban Area MPO | STBG-ANYAREA FUNDS PROVIDED AS PART OF FUNDING SWAP. STATE TRUST FUNDS COULD BE USED IN LIEU OF STBG-ANYAREA ON AN ELIGIBLE STI HIGHWAY PROJECT IF DESIRED. | Division 7 |  | BGANY | CONSTRUCTION | 15766000 | FY 2028: 3941000; FY 2029: 3941000; FY 2030: 3942000; FY 2031: 3942000
U-5021 | Highway | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization (GUAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Guilford | 7 | Greensboro Urban Area MPO | STBG-ANYAREA FUNDS PROVIDED AS PART OF FUNDING SWAP. STATE TRUST FUNDS COULD BE USED IN LIEU OF STBG-ANYAREA ON AN ELIGIBLE STI HIGHWAY PROJECT IF DESIRED. | Division 7 |  | BGDA | CONSTRUCTION | 57239000 | 4817000 | 4817000 | 4817000 | 6097000 | 6097000 | 6097000 | 6097000 | 6097000 | 6097000 | 6097000
U-5022 | Highway | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization (WSUAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | CONSTRUCTION | 42845000 | FY 2028: 8569000; FY 2029: 8569000; FY 2030: 8569000; FY 2031: 8569000; FY 2032: 8569000
U-5022 | Highway | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization (WSUAMPO) | Unallocated Surface Transportation Block Grant Program Funds. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 48799000 |  |  |  | 3367000 | 7572000 | 7572000 | 7572000 | 7572000 | 7572000 | 7572000
U-5023 | Highway | Locally Selected | Various | Triangle West Transportation Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726. | Division 5, 7, 8 |  | BGANY | CONSTRUCTION | 18123000 | FY 2028: 4530000; FY 2029: 4531000; FY 2030: 4531000; FY 2031: 4531000
U-5023 | Highway | Locally Selected | Various | Triangle West Transportation Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726. | Division 5, 7, 8 |  | BGDA | CONSTRUCTION | 16527000 | FY 2033: 2275000; FY 2034: 7126000; FY 2035: 7126000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  |  |  | 2826000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | RIGHT-OF-WAY | 34686000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | UTILITIES | 336000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 26505000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | CONSTRUCTION | 60923000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (Sunset Avenue) in Rocky Mount. | Upgrade grade separation to an interchange. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | L | CONSTRUCTION | 208000
U-5100 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Buncombe, Henderson, Haywood | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | BGANY | CONSTRUCTION | 8857000 | FY 2028: 2214000; FY 2029: 2214000; FY 2030: 2214000; FY 2031: 2215000
U-5100 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Buncombe, Henderson, Haywood | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | BGDA | CONSTRUCTION | 46665000 | 3746000 | 4591000 | 4891000 | 4091000 | 4891000 | 4891000 | 4891000 | 4891000 | 4891000 | 4891000
U-5100 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Buncombe, Henderson, Haywood | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | L | CONSTRUCTION | 13883000 | 937000 | 1148000 | 1776000 | 1576000 | 1777000 | 1777000 | 1223000 | 1223000 | 1223000 | 1223000
U-5101 | Highway | STI (Prioritization) | SR 1437 (Shaw Road); SR 1614 (Shaw Mill Road); SR 1615 (Rosehill Road / Stacey Weaver Drive) | NC 24 (Bragg Boulevard) to US 401 (Ramsey Street). | Widen roadway and construct partially on new location. | 3.6 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 1250000
U-5101A | Highway | STI (Prioritization) | SR 1437 (Shaw Road) | NC 24 (Bragg Boulevard) to NC 210 (Murchison Road). | Widen roadway and construct partially on new location. | 1.89 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 10400000
U-5101A | Highway | STI (Prioritization) | SR 1437 (Shaw Road) | NC 24 (Bragg Boulevard) to NC 210 (Murchison Road). | Widen roadway and construct partially on new location. | 1.89 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 8800000
U-5101A | Highway | STI (Prioritization) | SR 1437 (Shaw Road) | NC 24 (Bragg Boulevard) to NC 210 (Murchison Road). | Widen roadway and construct partially on new location. | 1.89 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 39000000
U-5101B | Highway | STI (Prioritization) | SR 1614 (Shaw Mill Road)-SR 1615 (Rosehill Road / Stacey Weaver Drive) | NC 210 (Murchison Road) to US 401 (Ramsey Street). | Widen roadway and construct partially on new location. |  | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 38500000 | [10 empty] | 38500000
U-5101B | Highway | STI (Prioritization) | SR 1614 (Shaw Mill Road)-SR 1615 (Rosehill Road / Stacey Weaver Drive) | NC 210 (Murchison Road) to US 401 (Ramsey Street). | Widen roadway and construct partially on new location. |  | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 21445000 | [10 empty] | 21445000
U-5101B | Highway | STI (Prioritization) | SR 1614 (Shaw Mill Road)-SR 1615 (Rosehill Road / Stacey Weaver Drive) | NC 210 (Murchison Road) to US 401 (Ramsey Street). | Widen roadway and construct partially on new location. |  | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 36300000 | [10 empty] | 36300000
U-5105 | Highway | Transition | NC 225 / SR 1164 (Erkwood Drive) | SR 1779 (Shepherd Street) intersection in Hendersonville. | Construct intersection improvements. | 0.5 | Henderson | 14 | French Broad River MPO | DIVISION PROJECT - UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 7210000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  |  |  | 2925000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BA | ENGINEERING | 960000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BGANY | RIGHT-OF-WAY | 1750000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | L | RIGHT-OF-WAY | 1750000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 9417000 | FY 2026: 2625000; FY 2027: 798000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 2935000 | FY 2026: 2935000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 332000 | FY 2026: 93000; FY 2027: 28000
U-5108 | Highway | Transition | Northcross Drive Extension | NC 73 in Huntersville to Westmoreland Road in Cornelius. | Construct road on new location. | 0.97 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | L | CONSTRUCTION | 4958000 | FY 2026: 3423000; FY 2027: 107000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGDA | RIGHT-OF-WAY | 541000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L(M) | RIGHT-OF-WAY | 135000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | CMAQ | CONSTRUCTION | 1600000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | HSIP | CONSTRUCTION | 883000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 3016000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 1657000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 284000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L | CONSTRUCTION | 1479000
U-5112 | Highway | Transition | SR 1364 (Pleasant Plains Road) | SR 1357 (Potters Road) intersection in Stallings. | Construct intersection improvements including left turn lanes and modification of traffic signal. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 1284000
U-5114 | Highway | Transition | US 21 | SR 2136 (Gilead Road) intersection in Huntersville. | Construct intersection improvements, including bicycle and pedestrian accommodations. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 19322000
U-5118 | Highway | Locally Selected | Various | Locations in Divisions 4, 5, and 6. | Operational improvements for safety and congestion mitigation. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. $24,867 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 4, 5, 6 |  |  |  | 21170000
U-5118 | Highway | Locally Selected | Various | Locations in Divisions 4, 5, and 6. | Operational improvements for safety and congestion mitigation. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. $24,867 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 3582000
U-5118 | Highway | Locally Selected | Various | Locations in Divisions 4, 5, and 6. | Operational improvements for safety and congestion mitigation. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. $24,867 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 4, 5, 6 |  | L | CONSTRUCTION | 895000
U-5118FB | Highway | Locally Selected | NC 96 (Arendell Avenue) | North of Pearces Road to Dogwood Drive | Construc access management improvements. | 0.4 | Wake | 5 | Capital Area MPO |  | Region C |  | BGANY | CONSTRUCTION | 25000
U-5118FB | Highway | Locally Selected | NC 96 (Arendell Avenue) | North of Pearces Road to Dogwood Drive | Construc access management improvements. | 0.4 | Wake | 5 | Capital Area MPO |  | Region C |  | BGDA | CONSTRUCTION | 825000
U-5118FB | Highway | Locally Selected | NC 96 (Arendell Avenue) | North of Pearces Road to Dogwood Drive | Construc access management improvements. | 0.4 | Wake | 5 | Capital Area MPO |  | Region C |  | L(M) | CONSTRUCTION | 212000
U-5169 | Highway | STI (Prioritization) | I-74 / US 311 | NC 68 (Eastchester Drive) in High Point. | Reconstruct interchange and approaches. | 1 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  |  |  | 32225000
U-5190 | Bike & Ped | Transition | New Leicester Highway | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  |  |  | 202000
U-5190 | Bike & Ped | Transition | New Leicester Highway | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | BGDA | RIGHT-OF-WAY | 193000
U-5190 | Bike & Ped | Transition | New Leicester Highway | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | L | RIGHT-OF-WAY | 48000
U-5190 | Bike & Ped | Transition | New Leicester Highway | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 2199000
U-5190 | Bike & Ped | Transition | New Leicester Highway | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 459000
U-5190 | Bike & Ped | Transition | New Leicester Highway | City limits to SR 3548 (Patton Avenue) in Asheville | Construct sidewalk. |  | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | L | CONSTRUCTION | 664000
U-5207 | Highway | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  |  |  | 2650000
U-5207 | Highway | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  | BGDA | PLANNING | 9267000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 3360000
U-5207 | Highway | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  | L | PLANNING | 2240000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 840000
U-5301 | Highway | STI (Prioritization) | US 64 | West of SR 1308 (Laura Duncan Road) to US 1 in Apex and Cary. | Upgrade and improve corridor. | 3.2 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 82200000 | FY 2026: 11100000; FY 2027: 6900000; FY 2028: 14500000; FY 2029: 16900000; FY 2030: 32800000
U-5301 | Highway | STI (Prioritization) | US 64 | West of SR 1308 (Laura Duncan Road) to US 1 in Apex and Cary. | Upgrade and improve corridor. | 3.2 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 4400000 | FY 2026: 1466000; FY 2027: 1467000; FY 2028: 1467000
U-5301 | Highway | STI (Prioritization) | US 64 | West of SR 1308 (Laura Duncan Road) to US 1 in Apex and Cary. | Upgrade and improve corridor. | 3.2 | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 207100000 | FY 2031: 26923000; FY 2032: 51775000; FY 2033: 47633000; FY 2034: 43491000; FY 2035: 37278000
U-5301A | Highway | STI (Prioritization) | US 64 | CSX Railroad bridge over US 64. | Replace railroad bridge. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 5600000 | FY 2027: 1848000; FY 2028: 2408000; FY 2029: 224000; FY 2030: 560000; FY 2031: 560000
U-5301A | Highway | STI (Prioritization) | US 64 | CSX Railroad bridge over US 64. | Replace railroad bridge. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 104000 | FY 2027: 52000; FY 2028: 52000
U-5301A | Highway | STI (Prioritization) | US 64 | CSX Railroad bridge over US 64. | Replace railroad bridge. |  | Wake | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 32300000 | FY 2029: 8398000; FY 2030: 9367000; FY 2031: 7106000; FY 2032: 5168000; FY 2033: 2261000
U-5302 | Highway | STI (Prioritization) | US 401 | South of SR 1006 (Old Stage Road) to south of SR 2538 (Mechanical Boulevard) / Garner Station Boulevard in Garner. | Construct reduced conflict intersections. | 1.05 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  |  |  | 3345000
U-5302 | Highway | STI (Prioritization) | US 401 | South of SR 1006 (Old Stage Road) to south of SR 2538 (Mechanical Boulevard) / Garner Station Boulevard in Garner. | Construct reduced conflict intersections. | 1.05 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | ENGINEERING | 1801000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 121000
U-5302 | Highway | STI (Prioritization) | US 401 | South of SR 1006 (Old Stage Road) to south of SR 2538 (Mechanical Boulevard) / Garner Station Boulevard in Garner. | Construct reduced conflict intersections. | 1.05 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC ROW | 4128000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 278000
U-5302 | Highway | STI (Prioritization) | US 401 | South of SR 1006 (Old Stage Road) to south of SR 2538 (Mechanical Boulevard) / Garner Station Boulevard in Garner. | Construct reduced conflict intersections. | 1.05 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | RIGHT-OF-WAY | 5803000
U-5302 | Highway | STI (Prioritization) | US 401 | South of SR 1006 (Old Stage Road) to south of SR 2538 (Mechanical Boulevard) / Garner Station Boulevard in Garner. | Construct reduced conflict intersections. | 1.05 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | CONSTRUCTION | 24700000 | FY 2026: 4199000; FY 2027: 7657000; FY 2028: 6422000; FY 2029: 4446000; FY 2030: 1976000
U-5304 | Highway | STI (Prioritization) | US 15 / US 501 (Fordham Boulevard) | NC 86 (South Columbia Street) to I-40 in Chapel Hill. | Upgrade corridor. | 6 | Orange, Durham | 5, 7 | Triangle West TPO | COORDINATE WITH EB-5998 AND U-5774 |  |  |  |  | 10000
U-5304A | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (South Columbia Street) | Improve interchange. | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000000 | [10 empty] | 10000000
U-5304A | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (South Columbia Street) | Improve interchange. | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 1040000 | [10 empty] | 1040000
U-5304A | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (South Columbia Street) | Improve interchange. | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 22001000 | [10 empty] | 22001000
U-5304B | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (North Columbia Street) to NC 54 (Raleigh Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 2.13 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 6000000 | [10 empty] | 6000000
U-5304B | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (North Columbia Street) to NC 54 (Raleigh Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 2.13 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 285000 | [10 empty] | 285000
U-5304B | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (North Columbia Street) to NC 54 (Raleigh Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 2.13 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 22001000 | [10 empty] | 22001000
U-5304C | Highway | Pre-STI (Historic) | US 15 / US 501 | SR 1742 (Ephesus Church Road) intersection | Improve intersection. | 0.5 | Orange | 7 | Triangle West TPO | WORK COMPLETED UNDER U-5550.
U-5304D | Highway | STI (Prioritization) | US 15 / US 501 | NC 54 (Raleigh Road) to SR 1742 (Ephesus Church Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 1.92 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5000000 | [10 empty] | 5000000
U-5304D | Highway | STI (Prioritization) | US 15 / US 501 | NC 54 (Raleigh Road) to SR 1742 (Ephesus Church Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 1.92 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 344000 | [10 empty] | 344000
U-5304D | Highway | STI (Prioritization) | US 15 / US 501 | NC 54 (Raleigh Road) to SR 1742 (Ephesus Church Road) | Construct corridor capacity improvements with sidewalks, wide outside lanes, and transit accommodations. | 1.92 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 30001000 | [10 empty] | 30001000
U-5304E | Highway | STI (Prioritization) | US 15 / US 501 | SR 1902 (Manning Drive) intersection | Convert at-grade intersection to interchange. | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 12000000 | [10 empty] | 12000000
U-5304E | Highway | STI (Prioritization) | US 15 / US 501 | SR 1902 (Manning Drive) intersection | Convert at-grade intersection to interchange. | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 446000 | [10 empty] | 446000
U-5304E | Highway | STI (Prioritization) | US 15 / US 501 | SR 1902 (Manning Drive) intersection | Convert at-grade intersection to interchange. | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 25000000 | [10 empty] | 25000000
U-5304F | Highway | STI (Prioritization) | US 15 / US 501 | SR 1742 (Ephesus Church Road) to I-40 | Construct corridor capacity improvements. | 1.75 | Orange, Durham | 5, 7 | Triangle West TPO |  | Region C, D |  | T | RIGHT-OF-WAY | 4400000 | FY 2028: 1144000; FY 2029: 1496000; FY 2030: 880000; FY 2031: 440000; FY 2032: 440000
U-5304F | Highway | STI (Prioritization) | US 15 / US 501 | SR 1742 (Ephesus Church Road) to I-40 | Construct corridor capacity improvements. | 1.75 | Orange, Durham | 5, 7 | Triangle West TPO |  | Region C, D |  | T | UTILITIES | 1700000 | FY 2028: 850000; FY 2029: 850000
U-5304F | Highway | STI (Prioritization) | US 15 / US 501 | SR 1742 (Ephesus Church Road) to I-40 | Construct corridor capacity improvements. | 1.75 | Orange, Durham | 5, 7 | Triangle West TPO |  | Region C, D |  | T | CONSTRUCTION | 77500000 | FY 2030: 9300000; FY 2031: 23250000; FY 2032: 20150000; FY 2033: 14725000; FY 2034: 10075000
U-5306 | Highway | STI (Prioritization) | US 220 (Battleground Avenue) | Cone Boulevard / Benjamin Parkway, Westridge Road, New Garden Road, and Brassfield Road intersections in Greensboro. | Construct intersection improvements and sidewalk improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | [5 empty] | 9926000
U-5306A | Highway | Transition | US 220 (Battleground Avenue) | Benjamin Parkway; Cone Boulevard intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE | Pre-STI (Transition)
U-5306B | Highway | STI (Prioritization) | US 220 (Battleground Avenue) | Westridge Road intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D
U-5306C | Highway | Transition | US 220 (Battleground Avenue) | New Garden Road intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE | Pre-STI (Transition)
U-5306D | Highway | Pre-STI (Historic) | US 220 (Battleground Avenue) | Brassfield Road intersection and approaches | Construct intersection and sidewalk improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 248000000 | 51630000 | 51630000 | 23785000 | 23785000 | 23785000 | 23785000 | 49600000
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 109700000 | FY 2027: 109700000
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | NHP | UTILITIES | 21600000 | 2138000 | 5014000 | 3612000 | 3612000 | 3612000 | 3612000
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | BOND R | UTILITIES | 16500000 | FY 2027: 16500000
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | NHP | GARVEE CON | 259995000 | FY 2031: 4333000; FY 2032: 4333000; FY 2033: 17333000; FY 2034: 17333000; FY 2035: 17333000 | 121331000
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | NHP | CONSTRUCTION | 93121000 | FY 2031: 5524000; FY 2032: 87597000
U-5307 | Highway | STI (Prioritization) | US 1 (Capital Boulevard) | I-540 in Raleigh to SR 1909 (Purnell Road) / SR 1931 (Harris Road) in Wake Forest | Upgrade roadway to 6 and 8 lane expressway. All lanes tolled. This is a toll project. Capital Area MPO approved toll project in May 2025. Toll status dependent on statutory amendment. | 10 | Wake | 5 | Capital Area MPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | BOND R | CONSTRUCTION | 494279000 | FY 2027: 494279000
U-5308 | Highway | STI (Prioritization) | SR 1547 (Finch Farm Road) | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Randolph | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | ENGINEERING | 2703000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 183000
U-5308 | Highway | STI (Prioritization) | SR 1547 (Finch Farm Road) | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Randolph | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | BUILD NC ROW | 244000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 20000
U-5308 | Highway | STI (Prioritization) | SR 1547 (Finch Farm Road) | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Randolph | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | RIGHT-OF-WAY | 2215000
U-5308 | Highway | STI (Prioritization) | SR 1547 (Finch Farm Road) | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Randolph | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | UTILITIES | 3500000 | FY 2026: 3500000
U-5308 | Highway | STI (Prioritization) | SR 1547 (Finch Farm Road) | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Randolph | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | BUILD NC CON | 20800000 |  |  |  | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 9100000
U-5308 | Highway | STI (Prioritization) | SR 1547 (Finch Farm Road) | SR 3106 (Kennedy Road) to I-85 in Trinity. | Widen to multi-lanes. | 2.13 | Randolph | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | CONSTRUCTION | 35100000 | FY 2028: 5511000; FY 2029: 7044000; FY 2030: 15531000; FY 2031: 7014000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 to US 421 Business. | Construct reduced conflict intersections. | 2.64 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  |  |  | 6977000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 to US 421 Business. | Construct reduced conflict intersections. | 2.64 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | NHP | RIGHT-OF-WAY | 5100000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 to US 421 Business. | Construct reduced conflict intersections. | 2.64 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | NHP | UTILITIES | 1217000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 to US 421 Business. | Construct reduced conflict intersections. | 2.64 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | NHP | CONSTRUCTION | 91349000 | FY 2026: 7465000; FY 2027: 3476000
U-5501 | Highway | Locally Selected | SR 1650 (Reedy Creek Road) | NC 54 (NE Maynard Road) to SR 1652 (Harrison Avenue) in Cary. | Widen from 2 to 3 lanes, to include roundabouts, as well as pedestrian and bicycle enhancements. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | Division 5 |  |  |  | 1869000
U-5501 | Highway | Locally Selected | SR 1650 (Reedy Creek Road) | NC 54 (NE Maynard Road) to SR 1652 (Harrison Avenue) in Cary. | Widen from 2 to 3 lanes, to include roundabouts, as well as pedestrian and bicycle enhancements. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | Division 5 |  | BGDA | CONSTRUCTION | 4526000
U-5501 | Highway | Locally Selected | SR 1650 (Reedy Creek Road) | NC 54 (NE Maynard Road) to SR 1652 (Harrison Avenue) in Cary. | Widen from 2 to 3 lanes, to include roundabouts, as well as pedestrian and bicycle enhancements. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | Division 5 |  | L | CONSTRUCTION | 3166000
U-5501A | Highway | Locally Selected | SR 1650 (Reedy Creek Road) | SR 1652 (Harrison Avenue) to south of Watts Pond Lane in Cary | Widen roadway. Install roundabouts and pedestrian enhancements. | 0.38 | Wake | 5 | Capital Area MPO |  | Division 5
U-5508 | Highway | STI (Prioritization) | NC 24 (Lejeune Boulevard) | NC 53 (Western Boulevard) in Jacksonville. | Upgrade intersection and drainage. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  |  |  | 1262000
U-5508 | Highway | STI (Prioritization) | NC 24 (Lejeune Boulevard) | NC 53 (Western Boulevard) in Jacksonville. | Upgrade intersection and drainage. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BG50200 | RIGHT-OF-WAY | 1100000 | FY 2027: 11000; FY 2028: 374000; FY 2029: 374000; FY 2030: 121000; FY 2031: 220000
U-5508 | Highway | STI (Prioritization) | NC 24 (Lejeune Boulevard) | NC 53 (Western Boulevard) in Jacksonville. | Upgrade intersection and drainage. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BG50200 | UTILITIES | 280000 | FY 2027: 280000
U-5508 | Highway | STI (Prioritization) | NC 24 (Lejeune Boulevard) | NC 53 (Western Boulevard) in Jacksonville. | Upgrade intersection and drainage. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BG50200 | CONSTRUCTION | 3100000 | FY 2030: 1798000; FY 2031: 1302000
U-5518 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | West of SR 3067 (T.W. Alexander Drive) to I-540 in Raleigh. | Upgrade roadway to improve capacity, safety and traffic operations including interchanges at various locations. | 1.26 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  |  |  | 12447000
U-5518 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | West of SR 3067 (T.W. Alexander Drive) to I-540 in Raleigh. | Upgrade roadway to improve capacity, safety and traffic operations including interchanges at various locations. | 1.26 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 135400000 | FY 2030: 54160000; FY 2031: 54160000; FY 2032: 13540000; FY 2033: 13540000
U-5518 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | West of SR 3067 (T.W. Alexander Drive) to I-540 in Raleigh. | Upgrade roadway to improve capacity, safety and traffic operations including interchanges at various locations. | 1.26 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  | NHP | UTILITIES | 19400000 | FY 2030: 9700000; FY 2031: 9700000
U-5518 | Highway | STI (Prioritization) | US 70 (Glenwood Avenue) | West of SR 3067 (T.W. Alexander Drive) to I-540 in Raleigh. | Upgrade roadway to improve capacity, safety and traffic operations including interchanges at various locations. | 1.26 | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  | NHP | CONSTRUCTION | 230000000 | FY 2030: 29900000; FY 2031: 57500000; FY 2032: 52900000; FY 2033: 48300000; FY 2034: 41400000
U-5525 | Highway | Locally Selected | Various | Wilmington Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 313000
U-5525 | Highway | Locally Selected | Various | Wilmington Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | PLANNING | 15873000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 4753000
U-5525 | Highway | Locally Selected | Various | Wilmington Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | PLANNING | 3967000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 1190000
U-5527 | Bike & Ped | Locally Selected | Various | Wilmington Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS. | Division 3 |  |  |  | 273000
U-5527 | Bike & Ped | Locally Selected | Various | Wilmington Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS. | Division 3 |  | TADA | CONSTRUCTION | 16694000 | 0 | 574000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 4060000
U-5528 | Bike & Ped | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  |  |  | 910000
U-5528 | Bike & Ped | Locally Selected | Various | Fayetteville Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Cumberland, Harnett, Hoke, Robeson | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  | TADA | CONSTRUCTION | 21515000 | 0 | 0 | 15000 | 738000 | 738000 | 738000 | 738000 | 738000 | 738000 | 738000 | 5166000
U-5529 | Highway | Locally Selected | SR 1115 (Avent Ferry Road) | West of SR 1101 (Piney Grove - Wilbon Road) to Village Walk Drive in Holly Springs. | Construct operational improvements. | 0.25 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | Division 5 |  |  |  | 280000
U-5529 | Highway | Locally Selected | SR 1115 (Avent Ferry Road) | West of SR 1101 (Piney Grove - Wilbon Road) to Village Walk Drive in Holly Springs. | Construct operational improvements. | 0.25 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | Division 5 |  | BGDA | CONSTRUCTION | 1864000
U-5529 | Highway | Locally Selected | SR 1115 (Avent Ferry Road) | West of SR 1101 (Piney Grove - Wilbon Road) to Village Walk Drive in Holly Springs. | Construct operational improvements. | 0.25 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | Division 5 |  | L | CONSTRUCTION | 466000
U-5530 | Bike & Ped | Locally Selected | Various | Capital Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  |  |  | 12955000
U-5530 | Bike & Ped | Locally Selected | Various | Capital Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 2000000
U-5530 | Bike & Ped | Locally Selected | Various | Capital Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | TADA | CONSTRUCTION | 800000
U-5530 | Bike & Ped | Locally Selected | Various | Capital Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | L | CONSTRUCTION | 700000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 2843000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | ENGINEERING | 80000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | ENGINEERING | 20000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | RIGHT-OF-WAY | 50000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | RIGHT-OF-WAY | 500000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | RIGHT-OF-WAY | 50000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 148000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | CONSTRUCTION | 450000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | CONSTRUCTION | 11300000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 974000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | CONSTRUCTION | 200000
U-5532 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Bicycle, pedestrian, and Transportation Alternatives Program (TAP)–eligible projects. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 3230000
U-5532C | Bike & Ped | Locally Selected | Rudd Station Road | Scott Road to Townsend Road near Greensboro. | Construct sidewalk. | 0.63 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 296000 | FY 2026: 296000
U-5532C | Bike & Ped | Locally Selected | Rudd Station Road | Scott Road to Townsend Road near Greensboro. | Construct sidewalk. | 0.63 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 74000 | FY 2026: 74000
U-5532E | Bike & Ped | Locally Selected | Big Tree Way; Shelby Drive; Hewitt Street; Bridford Parkway and Hornaday Road | Wendover Avenue to Elkhound Trail; Big Tree Way to Edith Lane; Norwolk Street to Merritt Drive; Wendover Avenue to existing west of Nicholas Road | Construct sidewalks. |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | TADA | CONSTRUCTION | 1949000
U-5532E | Bike & Ped | Locally Selected | Big Tree Way; Shelby Drive; Hewitt Street; Bridford Parkway and Hornaday Road | Wendover Avenue to Elkhound Trail; Big Tree Way to Edith Lane; Norwolk Street to Merritt Drive; Wendover Avenue to existing west of Nicholas Road | Construct sidewalks. |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | L | CONSTRUCTION | 487000
U-5532F | Bike & Ped | Locally Selected | Various | Holden Road from Walker Avenue to Spring Garden Street - both sides, Holden Road from Darden Road to Vandalia Road - west side, Holden Road from Madison Avenue to Walker Avenue - both sides, Rankin Road / Martin Avenue | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 1518000 | FY 2026: 1518000
U-5532F | Bike & Ped | Locally Selected | Various | Holden Road from Walker Avenue to Spring Garden Street - both sides, Holden Road from Darden Road to Vandalia Road - west side, Holden Road from Madison Avenue to Walker Avenue - both sides, Rankin Road / Martin Avenue | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 380000 | FY 2026: 380000
U-5532G | Bike & Ped | Locally Selected | Various | Locations in Greensboro | Construct sidewalk improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | RIGHT-OF-WAY | 56000
U-5532G | Bike & Ped | Locally Selected | Various | Locations in Greensboro | Construct sidewalk improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 14000
U-5532G | Bike & Ped | Locally Selected | Various | Locations in Greensboro | Construct sidewalk improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | UTILITIES | 4000
U-5532G | Bike & Ped | Locally Selected | Various | Locations in Greensboro | Construct sidewalk improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | UTILITIES | 1000
U-5532G | Bike & Ped | Locally Selected | Various | Locations in Greensboro | Construct sidewalk improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | CONSTRUCTION | 920000 | FY 2026: 920000
U-5532G | Bike & Ped | Locally Selected | Various | Locations in Greensboro | Construct sidewalk improvements. |  | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 230000 | FY 2026: 230000
U-5532H | Bike & Ped | Locally Selected | Various | North side of Seminole Drive from Josephine Boyd Street; north side of Whippoorwill Drive from Pennydale Drive to Jane Street; and north side of West Bessemer Avenue from Grecade Street to Hill Street. | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 536000 | FY 2026: 536000
U-5532H | Bike & Ped | Locally Selected | Various | North side of Seminole Drive from Josephine Boyd Street; north side of Whippoorwill Drive from Pennydale Drive to Jane Street; and north side of West Bessemer Avenue from Grecade Street to Hill Street. | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 134000 | FY 2026: 134000
U-5532I | Bike & Ped | Locally Selected | Various | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | ENGINEERING | 72000
U-5532I | Bike & Ped | Locally Selected | Various | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 18000
U-5532I | Bike & Ped | Locally Selected | Various | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | RIGHT-OF-WAY | 320000 | FY 2026: 320000
U-5532I | Bike & Ped | Locally Selected | Various | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 80000 | FY 2026: 80000
U-5532I | Bike & Ped | Locally Selected | Various | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 934000 | FY 2027: 934000
U-5532I | Bike & Ped | Locally Selected | Various | Holden Road from Madison Avenue to Friendly Avenue; Cotswold Avenue from Battleground Avenue to Cotswold Terrace (north side); Greenbriar Road from Church Street to Elm Street (north side); and Swing Road from Market Street to Burnt | Install sidewalk. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 234000 | FY 2027: 234000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  |  |  | 3126000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDA | RIGHT-OF-WAY | 220000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDA | UTILITIES | 336000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | L | UTILITIES | 84000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGANY | CONSTRUCTION | 492000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDA | CONSTRUCTION | 12187000
U-5534 | Highway | Locally Selected | Wilmington Urban Area Metropolitan Planning Organization | Various | Wilmington Urban Area MPO STP-DA Program. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | L(M) | CONSTRUCTION | 2413000
U-5534C | Highway | Locally Selected | Greenville Avenue | SR 1411 (Wrightsville Avenue) to Hinton Avenue in Wilmington | Realign intersection and construct bike lanes and sidewalk along Greenville avenue. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 861000
U-5534C | Highway | Locally Selected | Greenville Avenue | SR 1411 (Wrightsville Avenue) to Hinton Avenue in Wilmington | Realign intersection and construct bike lanes and sidewalk along Greenville avenue. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 215000
U-5534G | Highway | Locally Selected | Hooker Road | SR 1411 (Wrightsville Avenue) to Mallard Drive / Rose Avenue intersection in Wilmington. | Construct a 10 foot multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 1916000
U-5534G | Highway | Locally Selected | Hooker Road | SR 1411 (Wrightsville Avenue) to Mallard Drive / Rose Avenue intersection in Wilmington. | Construct a 10 foot multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 479000
U-5534H | Highway | Locally Selected | Hinton Avenue | Park Avenue to Greenville Avenue in Wilmington. | Construct a 10 foot multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 786000
U-5534H | Highway | Locally Selected | Hinton Avenue | Park Avenue to Greenville Avenue in Wilmington. | Construct a 10 foot multi-use path. |  | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L(M) | CONSTRUCTION | 197000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | BGDA | ENGINEERING | 32000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | L(M) | ENGINEERING | 8000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | BGDA | RIGHT-OF-WAY | 32000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | L(M) | RIGHT-OF-WAY | 8000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | BGANY | CONSTRUCTION | 168000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | BGDA | CONSTRUCTION | 430000
U-5534U | Bike & Ped | Locally Selected | Brooklyn Street; Navassa Park | Various locations. | Add bike lanes on Brooklyn Street. Construct multi-use path connecting Brooklyn Street to Navassa Park. |  | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 3 |  | L(M) | CONSTRUCTION | 108000
U-5535 | Bike & Ped | Locally Selected | Various | French Broad River Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | TADA | CONSTRUCTION | 739000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 649000
U-5535 | Bike & Ped | Locally Selected | Various | French Broad River Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | L | CONSTRUCTION | 186000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 163000
U-5536 | Highway | STI (Prioritization) | New Route | Proposed Great Wagon Road from SR 1001 (Shallowford Road) to SR 1308 (Lewisville-Vienna Road) in Lewisville. | Construct two lane facility on new location with bicycle and pedestrian accommodations. | 0.88 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  |  |  | 644000
U-5536 | Highway | STI (Prioritization) | New Route | Proposed Great Wagon Road from SR 1001 (Shallowford Road) to SR 1308 (Lewisville-Vienna Road) in Lewisville. | Construct two lane facility on new location with bicycle and pedestrian accommodations. | 0.88 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | RIGHT-OF-WAY | 14792000
U-5536 | Highway | STI (Prioritization) | New Route | Proposed Great Wagon Road from SR 1001 (Shallowford Road) to SR 1308 (Lewisville-Vienna Road) in Lewisville. | Construct two lane facility on new location with bicycle and pedestrian accommodations. | 0.88 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | UTILITIES | 1300000
U-5536 | Highway | STI (Prioritization) | New Route | Proposed Great Wagon Road from SR 1001 (Shallowford Road) to SR 1308 (Lewisville-Vienna Road) in Lewisville. | Construct two lane facility on new location with bicycle and pedestrian accommodations. | 0.88 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | BUILD NC CON | 7800000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 2600000
U-5536 | Highway | STI (Prioritization) | New Route | Proposed Great Wagon Road from SR 1001 (Shallowford Road) to SR 1308 (Lewisville-Vienna Road) in Lewisville. | Construct two lane facility on new location with bicycle and pedestrian accommodations. | 0.88 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | CONSTRUCTION | 16000000 | FY 2026: 2961000; FY 2027: 6535000; FY 2028: 3376000
U-5537 | Highway | Locally Selected | SR 1521 (Lake Pine Drive) | North of MacGregor Pines Road to north of Versailles Drive. | Widen to 3 lanes including 10 ft multi-use path on east side and 5 ft sidewalk west side. | 0.31 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | Division 5 |  |  |  | 1286000
U-5537 | Highway | Locally Selected | SR 1521 (Lake Pine Drive) | North of MacGregor Pines Road to north of Versailles Drive. | Widen to 3 lanes including 10 ft multi-use path on east side and 5 ft sidewalk west side. | 0.31 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | Division 5 |  | BGDA | CONSTRUCTION | 468000
U-5537 | Highway | Locally Selected | SR 1521 (Lake Pine Drive) | North of MacGregor Pines Road to north of Versailles Drive. | Widen to 3 lanes including 10 ft multi-use path on east side and 5 ft sidewalk west side. | 0.31 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | Division 5 |  | L | CONSTRUCTION | 117000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (Martin Luther King Jr. Boulevard) | US 158 / US 421 / NC 150 / I-40 Business to US 52 (Future I-285) / NC 8 | Construct streetscape improvements. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  |  |  | 120000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (Martin Luther King Jr. Boulevard) | US 158 / US 421 / NC 150 / I-40 Business to US 52 (Future I-285) / NC 8 | Construct streetscape improvements. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | RIGHT-OF-WAY | 500000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (Martin Luther King Jr. Boulevard) | US 158 / US 421 / NC 150 / I-40 Business to US 52 (Future I-285) / NC 8 | Construct streetscape improvements. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | RIGHT-OF-WAY | 100000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (Martin Luther King Jr. Boulevard) | US 158 / US 421 / NC 150 / I-40 Business to US 52 (Future I-285) / NC 8 | Construct streetscape improvements. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1750000 | FY 2026: 1750000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (Martin Luther King Jr. Boulevard) | US 158 / US 421 / NC 150 / I-40 Business to US 52 (Future I-285) / NC 8 | Construct streetscape improvements. | 1.01 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L(M) | CONSTRUCTION | 438000 | FY 2026: 438000
U-5544 | Bike & Ped | Locally Selected | Various | Locations in the Charlotte Regional Transportation Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | TADA | CONSTRUCTION | 19753000 | 0 | 0 | 0 | 1237000 | 3086000 | 3086000 | 3086000 | 3086000 | 3086000 | 3086000
U-5544 | Bike & Ped | Locally Selected | Various | Locations in the Charlotte Regional Transportation Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Mecklenburg, Union, Iredell | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | L | CONSTRUCTION | 4941000 | 0 | 0 | 0 | 309000 | 772000 | 772000 | 772000 | 772000 | 772000 | 772000
U-5545 | Bike & Ped | Locally Selected | Various | Cabarrus Rowan Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 |  | TADA | CONSTRUCTION | 6013000 | 325000 | 632000 | 632000 | 632000 | 632000 | 632000 | 632000 | 632000 | 632000 | 632000
U-5545 | Bike & Ped | Locally Selected | Various | Cabarrus Rowan Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 |  | L | CONSTRUCTION | 1503000 | 81000 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000
U-5546 | Bike & Ped | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Catawba, Burke, Caldwell, Alexander | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | TADA | CONSTRUCTION | 3215000 | 0 | 0 | 16000 | 457000 | 457000 | 457000 | 457000 | 457000 | 457000 | 457000
U-5546 | Bike & Ped | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Catawba, Burke, Caldwell, Alexander | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | L | CONSTRUCTION | 802000 | 0 | 0 | 4000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000
U-5550 | Highway | STI (Prioritization) | US 15 / US 501 (Fordham Boulevard) | SR 1742 (Ephesus Church Road) in Chapel Hill. | Construct intersection improvements. | 0.5 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Statewide Mobility |  |  |  | 2170000
U-5604 | Highway | STI (Prioritization) | Various | US 23 / US 64 / US 441 and Womack Street intersection in Franklin; US 23 / US 64 / US 441 and Maple Street intersection in Franklin; US 23 / US 64 / US 441 and Porter Street intersection in Franklin; US 441 / Main Street and Depot Street intersection in F | Construct intersection improvements. | 1.4 | Macon | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  |  |  | 9756000
U-5604 | Highway | STI (Prioritization) | Various | US 23 / US 64 / US 441 and Womack Street intersection in Franklin; US 23 / US 64 / US 441 and Maple Street intersection in Franklin; US 23 / US 64 / US 441 and Porter Street intersection in Franklin; US 441 / Main Street and Depot Street intersection in F | Construct intersection improvements. | 1.4 | Macon | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  | T | ENGINEERING | 1830000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000
U-5604 | Highway | STI (Prioritization) | Various | US 23 / US 64 / US 441 and Womack Street intersection in Franklin; US 23 / US 64 / US 441 and Maple Street intersection in Franklin; US 23 / US 64 / US 441 and Porter Street intersection in Franklin; US 441 / Main Street and Depot Street intersection in F | Construct intersection improvements. | 1.4 | Macon | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  | T | BUILD NC CON | 7080000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 259000
U-5606 | Highway | STI (Prioritization) | SR 1620 (Dickinson Avenue) | NC 11 to Reade Circle. | Improve roadway. | 1.34 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  |  |  | 3554000
U-5606 | Highway | STI (Prioritization) | SR 1620 (Dickinson Avenue) | NC 11 to Reade Circle. | Improve roadway. | 1.34 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | BG50200 | CONSTRUCTION | 18365000
U-5608 | Highway | Locally Selected | New Route | SR 1211 (Kimball Road) extension, SR 1242 (North Chapel Street) to SR 1221 (Bostian Road) in Landis. | Construct two-lane connector on new location. | 0.27 | Rowan | 9 | Cabarrus-Rowan MPO | PROJECT COMPLETED | Division 9 |  |  |  | 8025000
U-5614 | Highway | Locally Selected | Various | Cabarrus-Rowan Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | Division 9, 10 |  | BGANY | CONSTRUCTION | 10900000 | FY 2026: 2725000; FY 2027: 2725000; FY 2028: 2725000; FY 2029: 2725000
U-5614 | Highway | Locally Selected | Various | Cabarrus-Rowan Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | Division 9, 10 |  | BGDA | CONSTRUCTION | 50299000 | 5191000 | 5012000 | 5012000 | 5012000 | 5012000 | 5012000 | 5012000 | 5012000 | 5012000 | 5012000
U-5614 | Highway | Locally Selected | Various | Cabarrus-Rowan Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Cabarrus, Rowan | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | Division 9, 10 |  | L | CONSTRUCTION | 15300000 | 1979000 | 1934000 | 1935000 | 1934000 | 1253000 | 1253000 | 1253000 | 1253000 | 1253000 | 1253000
U-5615 | Highway | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Catawba, Burke, Caldwell, Alexander | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | BGANY | CONSTRUCTION | 6051000 | FY 2026: 2017000; FY 2027: 2017000; FY 2028: 2017000
U-5615 | Highway | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Catawba, Burke, Caldwell, Alexander | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | BGDA | CONSTRUCTION | 29810000 | 2549000 | 581000 | 2465000 | 3065000 | 3525000 | 3525000 | 3525000 | 3525000 | 3525000 | 3525000
U-5615 | Highway | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Catawba, Burke, Caldwell, Alexander | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | L | CONSTRUCTION | 9212000 | 1141000 | 649000 | 1370000 | 766000 | 881000 | 881000 | 881000 | 881000 | 881000 | 881000
U-5616 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Division 13, 14 |  |  |  | 313000
U-5616 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | BGDA | PLANNING | 3442000 | 115000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
U-5616 | Highway | Locally Selected | Various | French Broad River Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Buncombe, Henderson, Haywood, Madison | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | L | PLANNING | 1030000 | 62000 | 63000 | 63000 | 63000 | 63000 | 63000 | 63000 | 63000 | 63000 | 63000
U-5617 | Highway | Locally Selected | SR 1173 (Williams Road) | Roundabout west of bridge to roundabout east of bridge. | Improve roundabouts west & east of bridge over US 421, and widen to multi-lanes from roundabout east of bridge to west of SR 1001 (Shallowford Road). | 0.28 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. | Division 9 |  |  |  | 1196000
U-5617 | Highway | Locally Selected | SR 1173 (Williams Road) | Roundabout west of bridge to roundabout east of bridge. | Improve roundabouts west & east of bridge over US 421, and widen to multi-lanes from roundabout east of bridge to west of SR 1001 (Shallowford Road). | 0.28 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. | Division 9 |  | BGANY | CONSTRUCTION | 1687000
U-5617 | Highway | Locally Selected | SR 1173 (Williams Road) | Roundabout west of bridge to roundabout east of bridge. | Improve roundabouts west & east of bridge over US 421, and widen to multi-lanes from roundabout east of bridge to west of SR 1001 (Shallowford Road). | 0.28 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. | Division 9 |  | L(M) | CONSTRUCTION | 422000
U-5618 | Highway | Locally Selected | SR 3014 (Morrisville-Carpenter Road) | SR 1613 (Davis Drive) to west of NC 54 in Morrisville. | Widen to 4-lane divided facility. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  |  |  | 900000
U-5618 | Highway | Locally Selected | SR 3014 (Morrisville-Carpenter Road) | SR 1613 (Davis Drive) to west of NC 54 in Morrisville. | Widen to 4-lane divided facility. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | BGDA | CONSTRUCTION | 6186000
U-5618 | Highway | Locally Selected | SR 3014 (Morrisville-Carpenter Road) | SR 1613 (Davis Drive) to west of NC 54 in Morrisville. | Widen to 4-lane divided facility. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | L | CONSTRUCTION | 295000
U-5618 | Highway | Locally Selected | SR 3014 (Morrisville-Carpenter Road) | SR 1613 (Davis Drive) to west of NC 54 in Morrisville. | Widen to 4-lane divided facility. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | L(M) | CONSTRUCTION | 1639000
U-5618 | Highway | Locally Selected | SR 3014 (Morrisville-Carpenter Road) | SR 1613 (Davis Drive) to west of NC 54 in Morrisville. | Widen to 4-lane divided facility. | 1.2 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | HF | CONSTRUCTION | 375000
U-5702 | Highway | STI (Prioritization) | NC 132 (College Road) | SR 1272 (New Centre Drive) to US 421 (Carolina Beach Road). | Access management and travel time improvements. | 9.7 | New Hanover | 3 | Wilmington Urban Area MPO | [5 empty] | 2770000
U-5702A | Highway | STI (Prioritization) | NC 132 (College Road) | SR 1272 (New Centre Drive) to US 117 (Shipyard Boulevard). | Access management and travel time improvements. | 2.64 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 29800000 | FY 2030: 7629000; FY 2031: 11443000; FY 2032: 4768000; FY 2033: 2980000; FY 2034: 2980000
U-5702A | Highway | STI (Prioritization) | NC 132 (College Road) | SR 1272 (New Centre Drive) to US 117 (Shipyard Boulevard). | Access management and travel time improvements. | 2.64 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 12500000 | FY 2030: 6250000; FY 2031: 6250000
U-5702A | Highway | STI (Prioritization) | NC 132 (College Road) | SR 1272 (New Centre Drive) to US 117 (Shipyard Boulevard). | Access management and travel time improvements. | 2.64 | New Hanover | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 38900000 | FY 2033: 8169000; FY 2034: 13226000; FY 2035: 10114000 | 7391000
U-5702B | Highway | STI (Prioritization) | NC 132 (College Road) | US 117 (Shipyard Boulevard) to US 421 (Carolina Beach Road). | Access management and travel time improvements. | 4.23 | New Hanover | 3 | Wilmington Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 30600000 | [10 empty] | 30600000
U-5702B | Highway | STI (Prioritization) | NC 132 (College Road) | US 117 (Shipyard Boulevard) to US 421 (Carolina Beach Road). | Access management and travel time improvements. | 4.23 | New Hanover | 3 | Wilmington Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 15000000 | [10 empty] | 15000000
U-5702B | Highway | STI (Prioritization) | NC 132 (College Road) | US 117 (Shipyard Boulevard) to US 421 (Carolina Beach Road). | Access management and travel time improvements. | 4.23 | New Hanover | 3 | Wilmington Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 50400000 | [10 empty] | 50400000
U-5703 | Highway | STI (Prioritization) | US 74 (Roosevelt Boulevard) | SR 1514 (Rocky River Road) intersection in Monroe. | Construct reduced conflict intersection. | 0.5 | Union | 10 | Charlotte Regional TPO | [5 empty] | 3961000
U-5703A | Highway | STI (Prioritization) | US 74 (Roosevelt Boulevard) | SR 1514 (Rocky River Road) intersection in Monroe. | Construct reduced conflict intersection. | 0.5 | Union | 10 | Charlotte Regional TPO | COMPLETE | Statewide Mobility
U-5703B | Highway | STI (Prioritization) | SR 1514 (Rocky River Road) | James Hamilton Road intersection in Monroe. | Realign James Hamilton Road to intersect with SR 1514 (Rocky River Road) and Myers Road. | 0.14 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY THE CITY OF MONROE. | Statewide Mobility |  | T | RIGHT-OF-WAY | 3457000 | FY 2026: 346000; FY 2027: 346000
U-5703B | Highway | STI (Prioritization) | SR 1514 (Rocky River Road) | James Hamilton Road intersection in Monroe. | Realign James Hamilton Road to intersect with SR 1514 (Rocky River Road) and Myers Road. | 0.14 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY THE CITY OF MONROE. | Statewide Mobility |  | T | UTILITIES | 325000
U-5703B | Highway | STI (Prioritization) | SR 1514 (Rocky River Road) | James Hamilton Road intersection in Monroe. | Realign James Hamilton Road to intersect with SR 1514 (Rocky River Road) and Myers Road. | 0.14 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY THE CITY OF MONROE. | Statewide Mobility |  | T | CONSTRUCTION | 2045000 | FY 2026: 1513000; FY 2027: 532000
U-5703B | Highway | STI (Prioritization) | SR 1514 (Rocky River Road) | James Hamilton Road intersection in Monroe. | Realign James Hamilton Road to intersect with SR 1514 (Rocky River Road) and Myers Road. | 0.14 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS PROVIDED BY THE CITY OF MONROE. | Statewide Mobility |  | O | CONSTRUCTION | 250000 | FY 2026: 22000; FY 2027: 228000
U-5706 | Highway | STI (Prioritization) | New Route | US 74 Business to SR 1426 (Aberdeen Road). | Construct two lane facility utilizing sections of SR 1641 (Clemmer Road) and SR 1645 (Mt. Olive Church Road), remainder on new location. | 4.01 | Richmond | 8 | Lumber River RPO |  | Division 8 |  |  |  | 1685000
U-5706 | Highway | STI (Prioritization) | New Route | US 74 Business to SR 1426 (Aberdeen Road). | Construct two lane facility utilizing sections of SR 1641 (Clemmer Road) and SR 1645 (Mt. Olive Church Road), remainder on new location. | 4.01 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | T | RIGHT-OF-WAY | 18200000 | FY 2027: 3458000; FY 2028: 5278000; FY 2029: 5278000; FY 2030: 364000; FY 2031: 3822000
U-5706 | Highway | STI (Prioritization) | New Route | US 74 Business to SR 1426 (Aberdeen Road). | Construct two lane facility utilizing sections of SR 1641 (Clemmer Road) and SR 1645 (Mt. Olive Church Road), remainder on new location. | 4.01 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | T | UTILITIES | 2500000 | FY 2027: 1250000; FY 2028: 1250000
U-5706 | Highway | STI (Prioritization) | New Route | US 74 Business to SR 1426 (Aberdeen Road). | Construct two lane facility utilizing sections of SR 1641 (Clemmer Road) and SR 1645 (Mt. Olive Church Road), remainder on new location. | 4.01 | Richmond | 8 | Lumber River RPO |  | Division 8 |  | T | CONSTRUCTION | 64300000 | FY 2031: 10288000; FY 2032: 16075000; FY 2033: 14789000; FY 2034: 12860000; FY 2035: 10288000
U-5709 | Highway | STI (Prioritization) | SR 1237 (Carthage Street) | SR 1152 (Fire Tower Road) to NC 42 (Wicker Street) in Sanford. | Widen roadway to a two lane divided facility with bike-ped accommodations. | 0.85 | Lee | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE). | Division 8 |  |  |  | 1214000
U-5709 | Highway | STI (Prioritization) | SR 1237 (Carthage Street) | SR 1152 (Fire Tower Road) to NC 42 (Wicker Street) in Sanford. | Widen roadway to a two lane divided facility with bike-ped accommodations. | 0.85 | Lee | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE). | Division 8 |  | T | RIGHT-OF-WAY | 3427000
U-5709 | Highway | STI (Prioritization) | SR 1237 (Carthage Street) | SR 1152 (Fire Tower Road) to NC 42 (Wicker Street) in Sanford. | Widen roadway to a two lane divided facility with bike-ped accommodations. | 0.85 | Lee | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE). | Division 8 |  | T | UTILITIES | 1700000
U-5709 | Highway | STI (Prioritization) | SR 1237 (Carthage Street) | SR 1152 (Fire Tower Road) to NC 42 (Wicker Street) in Sanford. | Widen roadway to a two lane divided facility with bike-ped accommodations. | 0.85 | Lee | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE). | Division 8 |  | T | BUILD NC CON | 10395000 |  | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 4158000
U-5709 | Highway | STI (Prioritization) | SR 1237 (Carthage Street) | SR 1152 (Fire Tower Road) to NC 42 (Wicker Street) in Sanford. | Widen roadway to a two lane divided facility with bike-ped accommodations. | 0.85 | Lee | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE). | Division 8 |  | T | CONSTRUCTION | 13000000 | FY 2027: 210000; FY 2028: 1240000; FY 2029: 6930000; FY 2030: 4620000
U-5710 | Highway | STI (Prioritization) | US 74 (Eastwood Road) | SR 1409 (Military Cutoff Road) intersection in Wilmington | Upgrade at-grade intersection to an interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  |  |  | 8833000
U-5710 | Highway | STI (Prioritization) | US 74 (Eastwood Road) | SR 1409 (Military Cutoff Road) intersection in Wilmington | Upgrade at-grade intersection to an interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 16900000 | FY 2026: 1690000; FY 2027: 1690000
U-5710 | Highway | STI (Prioritization) | US 74 (Eastwood Road) | SR 1409 (Military Cutoff Road) intersection in Wilmington | Upgrade at-grade intersection to an interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 4000000 | FY 2026: 2000000
U-5710 | Highway | STI (Prioritization) | US 74 (Eastwood Road) | SR 1409 (Military Cutoff Road) intersection in Wilmington | Upgrade at-grade intersection to an interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 60500000 | FY 2027: 605000; FY 2028: 16940000; FY 2029: 16940000; FY 2030: 14520000; FY 2031: 11495000
U-5710A | Highway | STI (Prioritization) | New Location | SR 1409 (Military Cutoff Road) at Drysdale Drive to US 74 (Eastwood Road). | Construct roadway on new location. | 0.3 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 2575000
U-5710A | Highway | STI (Prioritization) | New Location | SR 1409 (Military Cutoff Road) at Drysdale Drive to US 74 (Eastwood Road). | Construct roadway on new location. | 0.3 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGANY | CONSTRUCTION | 8200000
U-5711 | Highway | STI (Prioritization) | SR 1712 (Pineview Street) | West of Sylvan Drive to US 220 Business in Asheboro. | Widen to a three lane facility. | 0.61 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 2376000
U-5711 | Highway | STI (Prioritization) | SR 1712 (Pineview Street) | West of Sylvan Drive to US 220 Business in Asheboro. | Widen to a three lane facility. | 0.61 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | BG5T50 | CONSTRUCTION | 9600000 | FY 2026: 3263000; FY 2027: 4380000; FY 2028: 1957000
U-5713 | Highway | STI (Prioritization) | US 70 (Future I-42) | SR 1124 (Grantham Road) to Neuse River Bridge. | Upgrade roadway to freeway. | 1.8 | Craven | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  |  |  | 1700000
U-5713 | Highway | STI (Prioritization) | US 70 (Future I-42) | SR 1124 (Grantham Road) to Neuse River Bridge. | Upgrade roadway to freeway. | 1.8 | Craven | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  | T | RIGHT-OF-WAY | 88668000
U-5713 | Highway | STI (Prioritization) | US 70 (Future I-42) | SR 1124 (Grantham Road) to Neuse River Bridge. | Upgrade roadway to freeway. | 1.8 | Craven | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  | T | UTILITIES | 1000000
U-5713 | Highway | STI (Prioritization) | US 70 (Future I-42) | SR 1124 (Grantham Road) to Neuse River Bridge. | Upgrade roadway to freeway. | 1.8 | Craven | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  | T | CONSTRUCTION | 152337000 | FY 2026: 14000000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (Richlands Highway) intersection in Jacksonville | Upgrade at-grade intersection to an interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  |  |  | 2150000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (Richlands Highway) intersection in Jacksonville | Upgrade at-grade intersection to an interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  | T | RIGHT-OF-WAY | 35672000 | FY 2028: 2476000; FY 2029: 3300000; FY 2030: 2476000; FY 2031: 1032000; FY 2032: 1032000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (Richlands Highway) intersection in Jacksonville | Upgrade at-grade intersection to an interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  | T | UTILITIES | 3900000 | FY 2028: 1950000; FY 2029: 1950000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (Richlands Highway) intersection in Jacksonville | Upgrade at-grade intersection to an interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  | T | CONSTRUCTION | 66400000 | FY 2031: 5312000; FY 2032: 17928000; FY 2033: 17264000; FY 2034: 14608000; FY 2035: 11288000
U-5717 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1116 (Garrett Road) in Durham. | Upgrade at-grade intersection to an interchange. | 1 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067 | Statewide Mobility |  |  |  | 11400000
U-5717 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1116 (Garrett Road) in Durham. | Upgrade at-grade intersection to an interchange. | 1 | Durham | 5 | Triangle West TPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067 | Statewide Mobility |  | NHP | CONSTRUCTION | 53300000 | FY 2030: 12259000; FY 2031: 12792000; FY 2032: 11726000; FY 2033: 9061000; FY 2034: 7462000
U-5722 | Highway | STI (Prioritization) | US 421 Business / NC 87 | US 1 / US 15 / US 501 to former Atlantic Coast Line Railroad crossing east of Washington Avenue in Sanford. | Reconstruct as a "complete street" with improvements such as medians, sidewalks, bicycle facilities, and streetscaping. | 3.4 | Lee | 8 | Central Pines RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3500000
U-5722 | Highway | STI (Prioritization) | US 421 Business / NC 87 | US 1 / US 15 / US 501 to former Atlantic Coast Line Railroad crossing east of Washington Avenue in Sanford. | Reconstruct as a "complete street" with improvements such as medians, sidewalks, bicycle facilities, and streetscaping. | 3.4 | Lee | 8 | Central Pines RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 29600000
U-5722 | Highway | STI (Prioritization) | US 421 Business / NC 87 | US 1 / US 15 / US 501 to former Atlantic Coast Line Railroad crossing east of Washington Avenue in Sanford. | Reconstruct as a "complete street" with improvements such as medians, sidewalks, bicycle facilities, and streetscaping. | 3.4 | Lee | 8 | Central Pines RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7800000
U-5722 | Highway | STI (Prioritization) | US 421 Business / NC 87 | US 1 / US 15 / US 501 to former Atlantic Coast Line Railroad crossing east of Washington Avenue in Sanford. | Reconstruct as a "complete street" with improvements such as medians, sidewalks, bicycle facilities, and streetscaping. | 3.4 | Lee | 8 | Central Pines RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 19500000
U-5723 | Highway | STI (Prioritization) | US 74 | US 601 interchange in Monroe. | Construct interchange improvements. | 1 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | Statewide Mobility |  |  |  | 3846000
U-5723 | Highway | STI (Prioritization) | US 74 | US 601 interchange in Monroe. | Construct interchange improvements. | 1 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | Statewide Mobility |  | T | UTILITIES | 500000 | FY 2026: 490000
U-5723 | Highway | STI (Prioritization) | US 74 | US 601 interchange in Monroe. | Construct interchange improvements. | 1 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | Statewide Mobility |  | T | CONSTRUCTION | 23100000 | FY 2030: 3234000; FY 2031: 8547000; FY 2032: 6006000; FY 2033: 3696000; FY 2034: 1617000
U-5724 | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1709 (Central Heights Road) at Berkeley Boulevard in Goldsboro. | Realign roadway. | 0.62 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  |  |  | 2670000
U-5724 | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1709 (Central Heights Road) at Berkeley Boulevard in Goldsboro. | Realign roadway. | 0.62 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | RIGHT-OF-WAY | 1322000
U-5724 | Highway | STI (Prioritization) | US 13 (Berkeley Boulevard) | SR 1709 (Central Heights Road) at Berkeley Boulevard in Goldsboro. | Realign roadway. | 0.62 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | CONSTRUCTION | 19839000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 to SR 1745 (Old Farm Road). | Widen to four lanes. | 1.63 | Halifax | 4 | Peanut Belt RPO | COMPLETE. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  |  |  | 17376000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 to SR 1745 (Old Farm Road). | Widen to four lanes. | 1.63 | Halifax | 4 | Peanut Belt RPO | COMPLETE. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  | T | ENGINEERING | 2130000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 to SR 1745 (Old Farm Road). | Widen to four lanes. | 1.63 | Halifax | 4 | Peanut Belt RPO | COMPLETE. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  | T | BUILD NC CON | 14880000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 to SR 1745 (Old Farm Road). | Widen to four lanes. | 1.63 | Halifax | 4 | Peanut Belt RPO | COMPLETE. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  | T | CONSTRUCTION | 12360000
U-5726 | Highway | STI (Prioritization) | US 301 / NC 39 / NC 96 | SR 1623 (Booker Dairy Road) to SR 2302 (Ricks Road). | Construct access management improvements. | 1.58 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 750000
U-5726 | Highway | STI (Prioritization) | US 301 / NC 39 / NC 96 | SR 1623 (Booker Dairy Road) to SR 2302 (Ricks Road). | Construct access management improvements. | 1.58 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | RIGHT-OF-WAY | 13900000 | FY 2026: 1529000; FY 2027: 6394000; FY 2028: 3197000; FY 2029: 1390000; FY 2030: 1390000
U-5726 | Highway | STI (Prioritization) | US 301 / NC 39 / NC 96 | SR 1623 (Booker Dairy Road) to SR 2302 (Ricks Road). | Construct access management improvements. | 1.58 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | UTILITIES | 4300000 | FY 2026: 2150000; FY 2027: 2150000
U-5726 | Highway | STI (Prioritization) | US 301 / NC 39 / NC 96 | SR 1623 (Booker Dairy Road) to SR 2302 (Ricks Road). | Construct access management improvements. | 1.58 | Johnston | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | CONSTRUCTION | 29100000 | FY 2029: 4947000; FY 2030: 9603000; FY 2031: 7566000; FY 2032: 5238000; FY 2033: 1746000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Construct reduced conflict intersection and relocate NC 78 (Tramway Road). | 0.8 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  |  |  | 3000000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Construct reduced conflict intersection and relocate NC 78 (Tramway Road). | 0.8 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | NHP | RIGHT-OF-WAY | 12300000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Construct reduced conflict intersection and relocate NC 78 (Tramway Road). | 0.8 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | NHP | UTILITIES | 1500000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Construct reduced conflict intersection and relocate NC 78 (Tramway Road). | 0.8 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | BUILD NC CON | 15600000 |  | 2080000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 5200000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | South of SR 1198 (Bryan Drive) to SR 1237 (Carthage Street) in Sanford. | Construct reduced conflict intersection and relocate NC 78 (Tramway Road). | 0.8 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | CONSTRUCTION | 17700000 | FY 2027: 0; FY 2028: 474000; FY 2029: 7722000; FY 2030: 5643000; FY 2031: 3861000
U-5728 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1308 (Bell Fork Road) in Jacksonville. | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 3201000
U-5728 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1308 (Bell Fork Road) in Jacksonville. | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | RIGHT-OF-WAY | 590000
U-5728 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1308 (Bell Fork Road) in Jacksonville. | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BG50200 | CONSTRUCTION | 6900000 | FY 2026: 69000; FY 2027: 4761000; FY 2028: 2070000
U-5729 | Highway | STI (Prioritization) | US 421 (Carolina Beach Road) | US 421 (Burnett Boulevard) to US 117 (Shipyard Boulevard) in Wilmington. | Upgrade roadway. | 1.6 | New Hanover | 3 | Wilmington Urban Area MPO | [5 empty] | 14510000
U-5729REG | Highway | STI (Prioritization) | US 421 | US 421 (Burnett Boulevard) to US 117 (Shipyard Boulevard) in Wilmington. | Upgrade roadway. | 1.54 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 18480000
U-5729REG | Highway | STI (Prioritization) | US 421 | US 421 (Burnett Boulevard) to US 117 (Shipyard Boulevard) in Wilmington. | Upgrade roadway. | 1.54 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 6560000
U-5729REG | Highway | STI (Prioritization) | US 421 | US 421 (Burnett Boulevard) to US 117 (Shipyard Boulevard) in Wilmington. | Upgrade roadway. | 1.54 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 28640000
U-5729SW | Highway | STI (Prioritization) | US 421 | US 117 (Shipyard Boulevard) intersection in Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 4620000
U-5729SW | Highway | STI (Prioritization) | US 421 | US 117 (Shipyard Boulevard) intersection in Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1640000
U-5729SW | Highway | STI (Prioritization) | US 421 | US 117 (Shipyard Boulevard) intersection in Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 7160000
U-5730 | Highway | STI (Prioritization) | US 13 (Memorial Drive) | NC 43 (5th Street) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 200000
U-5730 | Highway | STI (Prioritization) | US 13 (Memorial Drive) | NC 43 (5th Street) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | UTILITIES | 125000
U-5730 | Highway | STI (Prioritization) | US 13 (Memorial Drive) | NC 43 (5th Street) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | CONSTRUCTION | 1400000 | FY 2026: 504000; FY 2027: 896000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17 / US 421 in Wilmington. | Construct a fly-over and free flow ramp at interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  |  |  | 1500000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17 / US 421 in Wilmington. | Construct a fly-over and free flow ramp at interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | BGLT5 | RIGHT-OF-WAY | 6100000 | FY 2028: 1464000; FY 2029: 1952000; FY 2030: 1464000; FY 2031: 610000; FY 2032: 610000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17 / US 421 in Wilmington. | Construct a fly-over and free flow ramp at interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | BGLT5 | UTILITIES | 590000 | FY 2028: 590000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17 / US 421 in Wilmington. | Construct a fly-over and free flow ramp at interchange. | 1 | New Hanover | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 48700000 | FY 2030: 3896000; FY 2031: 14123000; FY 2032: 12662000; FY 2033: 10227000; FY 2034: 7792000
U-5732 | Highway | STI (Prioritization) | US 17 | SR 1582 (Washington Acres Road) to Vista Lane. | Construct reduced conflict intersections. | 5.51 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  |  |  | 18604000
U-5732 | Highway | STI (Prioritization) | US 17 | SR 1582 (Washington Acres Road) to Vista Lane. | Construct reduced conflict intersections. | 5.51 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 25200000 | FY 2029: 8400000; FY 2030: 8400000; FY 2031: 8400000
U-5732 | Highway | STI (Prioritization) | US 17 | SR 1582 (Washington Acres Road) to Vista Lane. | Construct reduced conflict intersections. | 5.51 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | UTILITIES | 5100000 | FY 2029: 2550000; FY 2030: 2550000
U-5732 | Highway | STI (Prioritization) | US 17 | SR 1582 (Washington Acres Road) to Vista Lane. | Construct reduced conflict intersections. | 5.51 | Pender | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 60000000 | FY 2032: 7200000; FY 2033: 18600000; FY 2034: 15600000; FY 2035: 11400000 | 7200000
U-5732A | Highway | STI (Prioritization) | Dan Owen Drive Extension | SR 1570 (Factory Road) to Dan Owen Drive. | Construct reduced conflict intersections. |  | Pender | 3 | Wilmington Urban Area MPO | COMPLETE. | Region B
U-5734 | Highway | STI (Prioritization) | US 421 (South Front Street) | US 17 Business / US 76 / US 421 (Cape Fear Memorial Bridge) to US 421 (Burnett Boulevard) in Wilmington. | Widen to multi-lanes. | 0.99 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  |  |  | 1000000
U-5734 | Highway | STI (Prioritization) | US 421 (South Front Street) | US 17 Business / US 76 / US 421 (Cape Fear Memorial Bridge) to US 421 (Burnett Boulevard) in Wilmington. | Widen to multi-lanes. | 0.99 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | RIGHT-OF-WAY | 35799000 | FY 2026: 7637000; FY 2027: 7637000; FY 2028: 7637000; FY 2029: 12252000
U-5734 | Highway | STI (Prioritization) | US 421 (South Front Street) | US 17 Business / US 76 / US 421 (Cape Fear Memorial Bridge) to US 421 (Burnett Boulevard) in Wilmington. | Widen to multi-lanes. | 0.99 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | UTILITIES | 3200000 | FY 2026: 1600000
U-5734 | Highway | STI (Prioritization) | US 421 (South Front Street) | US 17 Business / US 76 / US 421 (Cape Fear Memorial Bridge) to US 421 (Burnett Boulevard) in Wilmington. | Widen to multi-lanes. | 0.99 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | CONSTRUCTION | 37500000 | FY 2029: 3000000; FY 2030: 11625000; FY 2031: 10125000; FY 2032: 7500000; FY 2033: 5250000
U-5735 | Highway | STI (Prioritization) | US 17 (Wilmington Highway) | SR 1130 (Old Maplehurst Road) in Jacksonville. | Construct interchange and associated improvements to MCAS New River main gate. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 1900000
U-5735 | Highway | STI (Prioritization) | US 17 (Wilmington Highway) | SR 1130 (Old Maplehurst Road) in Jacksonville. | Construct interchange and associated improvements to MCAS New River main gate. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | RIGHT-OF-WAY | 38102000 | FY 2028: 3586000; FY 2029: 7172000; FY 2030: 7172000; FY 2031: 7172000; FY 2032: 13000000
U-5735 | Highway | STI (Prioritization) | US 17 (Wilmington Highway) | SR 1130 (Old Maplehurst Road) in Jacksonville. | Construct interchange and associated improvements to MCAS New River main gate. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 6300000 | FY 2028: 3150000; FY 2029: 3150000
U-5735 | Highway | STI (Prioritization) | US 17 (Wilmington Highway) | SR 1130 (Old Maplehurst Road) in Jacksonville. | Construct interchange and associated improvements to MCAS New River main gate. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 96000000 | FY 2032: 8640000; FY 2033: 24960000; FY 2034: 24000000; FY 2035: 21120000 | 17280000
U-5735A | Highway | STI (Prioritization) | US 17 (Wilmington Highway) | MCAS New River Main Gate | Improve roadway to Douglas Gate Entrance. |  | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS. | Exempt |  | O | CONSTRUCTION | 1075000
U-5736 | Highway | STI (Prioritization) | NC 53 (Western Boulevard) | US 17 (Marine Boulevard) to NC 24 (Lejeune Boulevard) in Jacksonville. | Construct access management improvements. | 2.55 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E. | Region B |  |  |  | 7800000
U-5736 | Highway | STI (Prioritization) | NC 53 (Western Boulevard) | US 17 (Marine Boulevard) to NC 24 (Lejeune Boulevard) in Jacksonville. | Construct access management improvements. | 2.55 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E. | Region B |  | BG50200 | RIGHT-OF-WAY | 16100000 | FY 2028: 161000; FY 2029: 5474000; FY 2030: 5474000; FY 2031: 1771000; FY 2032: 3220000
U-5736 | Highway | STI (Prioritization) | NC 53 (Western Boulevard) | US 17 (Marine Boulevard) to NC 24 (Lejeune Boulevard) in Jacksonville. | Construct access management improvements. | 2.55 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E. | Region B |  | BG50200 | UTILITIES | 1600000 | FY 2028: 1600000
U-5736 | Highway | STI (Prioritization) | NC 53 (Western Boulevard) | US 17 (Marine Boulevard) to NC 24 (Lejeune Boulevard) in Jacksonville. | Construct access management improvements. | 2.55 | Onslow | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E. | Region B |  | BG50200 | CONSTRUCTION | 54700000 | FY 2031: 9846000; FY 2032: 14222000; FY 2033: 12581000; FY 2034: 9846000; FY 2035: 8205000
U-5737 | Highway | STI (Prioritization) | US 64 (East 11th Street) | North Glenn Avenue to east of US 421 (Future I-685) in Siler City. | Upgrade roadway to include median for access control, sidewalks, crosswalks, bicycle lanes and / or multi-use side path. | 2.64 | Chatham | 8 | Central Pines RPO |  | Region E |  |  |  | 1656000
U-5737 | Highway | STI (Prioritization) | US 64 (East 11th Street) | North Glenn Avenue to east of US 421 (Future I-685) in Siler City. | Upgrade roadway to include median for access control, sidewalks, crosswalks, bicycle lanes and / or multi-use side path. | 2.64 | Chatham | 8 | Central Pines RPO |  | Region E |  | T | RIGHT-OF-WAY | 10800000 | FY 2026: 1620000; FY 2027: 2484000; FY 2028: 2484000; FY 2029: 2052000; FY 2030: 2160000
U-5737 | Highway | STI (Prioritization) | US 64 (East 11th Street) | North Glenn Avenue to east of US 421 (Future I-685) in Siler City. | Upgrade roadway to include median for access control, sidewalks, crosswalks, bicycle lanes and / or multi-use side path. | 2.64 | Chatham | 8 | Central Pines RPO |  | Region E |  | T | UTILITIES | 3400000 | FY 2026: 680000; FY 2027: 1360000; FY 2028: 1360000
U-5737 | Highway | STI (Prioritization) | US 64 (East 11th Street) | North Glenn Avenue to east of US 421 (Future I-685) in Siler City. | Upgrade roadway to include median for access control, sidewalks, crosswalks, bicycle lanes and / or multi-use side path. | 2.64 | Chatham | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 40300000 | FY 2030: 403000; FY 2031: 12090000; FY 2032: 11284000; FY 2033: 9269000; FY 2034: 7254000
U-5738 | Highway | STI (Prioritization) | SR 2528 (Julian Road) | US 601 (Jake Alexander Boulevard) to SR 2667 (Summit Park Drive) in Salisbury. | Widen to four lane divided facility with bike-ped accommodations. | 1.28 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  |  |  | 3900000
U-5738 | Highway | STI (Prioritization) | SR 2528 (Julian Road) | US 601 (Jake Alexander Boulevard) to SR 2667 (Summit Park Drive) in Salisbury. | Widen to four lane divided facility with bike-ped accommodations. | 1.28 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | T | CONSTRUCTION | 14995000
U-5739 | Highway | STI (Prioritization) | US 258 / NC 24 (Richlands Highway) | SR 1212 (Pony Farm Road) to SR 1213 (Blue Creek Road). | Construct reduced conflict intersections. | 2.16 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  |  |  | 5200000
U-5739 | Highway | STI (Prioritization) | US 258 / NC 24 (Richlands Highway) | SR 1212 (Pony Farm Road) to SR 1213 (Blue Creek Road). | Construct reduced conflict intersections. | 2.16 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  | T | RIGHT-OF-WAY | 2600000 | FY 2028: 676000; FY 2029: 884000; FY 2030: 520000; FY 2031: 260000; FY 2032: 260000
U-5739 | Highway | STI (Prioritization) | US 258 / NC 24 (Richlands Highway) | SR 1212 (Pony Farm Road) to SR 1213 (Blue Creek Road). | Construct reduced conflict intersections. | 2.16 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  | T | UTILITIES | 3200000 | FY 2028: 1600000; FY 2029: 1600000
U-5739 | Highway | STI (Prioritization) | US 258 / NC 24 (Richlands Highway) | SR 1212 (Pony Farm Road) to SR 1213 (Blue Creek Road). | Construct reduced conflict intersections. | 2.16 | Onslow | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  | T | CONSTRUCTION | 31600000 | FY 2031: 3792000; FY 2032: 10428000; FY 2033: 8532000; FY 2034: 6004000; FY 2035: 2844000
U-5742 | Highway | STI (Prioritization) | Various | Routes in Fayetteville. | Install computerized traffic signal system. | 0 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Region C |  |  |  | 9034000
U-5742 | Highway | STI (Prioritization) | Various | Routes in Fayetteville. | Install computerized traffic signal system. | 0 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Region C |  | T | BUILD NC CON | 735000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (East Salisbury Street) to north of US 64 / NC 49 (Dixie Drive) in Asheboro. | Widen to three lanes. | 0.5 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  |  |  | 2151000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (East Salisbury Street) to north of US 64 / NC 49 (Dixie Drive) in Asheboro. | Widen to three lanes. | 0.5 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | RIGHT-OF-WAY | 2006000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (East Salisbury Street) to north of US 64 / NC 49 (Dixie Drive) in Asheboro. | Widen to three lanes. | 0.5 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | UTILITIES | 897000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (East Salisbury Street) to north of US 64 / NC 49 (Dixie Drive) in Asheboro. | Widen to three lanes. | 0.5 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 13700000 | FY 2026: 1370000; FY 2027: 5754000; FY 2028: 4384000; FY 2029: 2192000
U-5745 | Highway | STI (Prioritization) | NC 751 (Hope Valley Road) | SR 1183 (University Drive) intersection in Durham. | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT-OF-WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  |  |  | 2749000
U-5745 | Highway | STI (Prioritization) | NC 751 (Hope Valley Road) | SR 1183 (University Drive) intersection in Durham. | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT-OF-WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | ENGINEERING | 624000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 78000
U-5745 | Highway | STI (Prioritization) | NC 751 (Hope Valley Road) | SR 1183 (University Drive) intersection in Durham. | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT-OF-WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC ROW | 435000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
U-5745 | Highway | STI (Prioritization) | NC 751 (Hope Valley Road) | SR 1183 (University Drive) intersection in Durham. | Construct roundabout. | 0.5 | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT-OF-WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC CON | 1313000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 81000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (Allen Street) to SR 1010 (Ten-Ten road). | Construct additional lanes. | 0.81 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  |  |  | 4276000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (Allen Street) to SR 1010 (Ten-Ten road). | Construct additional lanes. | 0.81 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | T | RIGHT-OF-WAY | 2938000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (Allen Street) to SR 1010 (Ten-Ten road). | Construct additional lanes. | 0.81 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | T | UTILITIES | 1310000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (Allen Street) to SR 1010 (Ten-Ten road). | Construct additional lanes. | 0.81 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | T | CONSTRUCTION | 7410000 | FY 2026: 3061000; FY 2027: 2803000
U-5747 | Highway | STI (Prioritization) | NC 54; SR 1635 (McCrimmon Parkway) | SR 1635 (McCrimmon Parkway) from west of SR 1613 (Davis Drive) to north of SR 1637 (Church Street); NC 54 at SR 1635 (McCrimmon Parkway) in Morrisville. | Widen SR 1635 and upgrade NC 54 at-grade intersection to grade separation, including grade separation. | 2 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  |  |  | 9000
U-5747 | Highway | STI (Prioritization) | NC 54; SR 1635 (McCrimmon Parkway) | SR 1635 (McCrimmon Parkway) from west of SR 1613 (Davis Drive) to north of SR 1637 (Church Street); NC 54 at SR 1635 (McCrimmon Parkway) in Morrisville. | Widen SR 1635 and upgrade NC 54 at-grade intersection to grade separation, including grade separation. | 2 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | ENGINEERING | 3001000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 201000
U-5747A | Highway | STI (Prioritization) | SR 1635 (McCrimmon Parkway) | SR 1613 (Davis Drive) to north of SR 1637 (Church Street) | Widen to four lane divided facility. | 1.07 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $10,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 5 |  | T | RIGHT-OF-WAY | 5000000
U-5747A | Highway | STI (Prioritization) | SR 1635 (McCrimmon Parkway) | SR 1613 (Davis Drive) to north of SR 1637 (Church Street) | Widen to four lane divided facility. | 1.07 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $10,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 5 |  | T | UTILITIES | 500000
U-5747A | Highway | STI (Prioritization) | SR 1635 (McCrimmon Parkway) | SR 1613 (Davis Drive) to north of SR 1637 (Church Street) | Widen to four lane divided facility. | 1.07 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $10,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 5 |  | T | BUILD NC CON | 26010000 |  | 867000 | 867000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 11271000
U-5747A | Highway | STI (Prioritization) | SR 1635 (McCrimmon Parkway) | SR 1613 (Davis Drive) to north of SR 1637 (Church Street) | Widen to four lane divided facility. | 1.07 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $10,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE) | Division 5 |  | T | CONSTRUCTION | 6000000 | FY 2027: 0; FY 2028: 920000; FY 2029: 0; FY 2030: 1700000; FY 2031: 3380000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (Mccrimmon Parkway) intersection | Convert at-grade intersection to grade separation, including grade separation of North Carolina Railroad. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Region C |  | T | BUILD NC ROW | 72000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 7000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (Mccrimmon Parkway) intersection | Convert at-grade intersection to grade separation, including grade separation of North Carolina Railroad. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Region C |  | T | RIGHT-OF-WAY | 2000000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (Mccrimmon Parkway) intersection | Convert at-grade intersection to grade separation, including grade separation of North Carolina Railroad. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Region C |  | T | UTILITIES | 620000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (Mccrimmon Parkway) intersection | Convert at-grade intersection to grade separation, including grade separation of North Carolina Railroad. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Region C |  | T | BUILD NC CON | 13005000 |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (Mccrimmon Parkway) intersection | Convert at-grade intersection to grade separation, including grade separation of North Carolina Railroad. | 0.5 | Wake | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Region C |  | T | CONSTRUCTION | 28200000 | FY 2027: 10945000; FY 2028: 4544000; FY 2029: 8121000; FY 2030: 4590000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). | Region C |  |  |  | 2133000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). | Region C |  | T | ENGINEERING | 1921000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). | Region C |  | T | BUILD NC ROW | 1996000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). | Region C |  | T | RIGHT-OF-WAY | 4844000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). | Region C |  | T | UTILITIES | 212000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (Ligon Mill Road) / SR 2224 (Mitchell Mill Road) and SR 2006 (Perry Creek Road) in Raleigh. | Construct intersection improvements. | 1.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). | Region C |  | T | CONSTRUCTION | 22500000 | FY 2026: 7309000; FY 2027: 4126000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  |  |  | 12093000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | ENGINEERING | 1620000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | BUILD NC ROW | 3468000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | UTILITIES | 1700000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | BUILD NC CON | 13005000 |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 to Perimeter Park Drive in Morrisville. | Construct additional lanes. | 1.29 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR8 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 20100000 | FY 2027: 9331000; FY 2028: 238000; FY 2029: 6618000; FY 2030: 3913000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 intersection in Fuquay-Varina. | Construct intersection improvements. Project will include improvements to NC 55 intersection with NC 42, and construction of connector from NC 55 to SR 5056 (Judd Parkway). | 3 | Wake | 5 | Capital Area MPO |  | Region C |  |  |  | 700000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 intersection in Fuquay-Varina. | Construct intersection improvements. Project will include improvements to NC 55 intersection with NC 42, and construction of connector from NC 55 to SR 5056 (Judd Parkway). | 3 | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 59900000 | FY 2028: 9584000; FY 2029: 14975000; FY 2030: 14975000; FY 2031: 8386000; FY 2032: 11980000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 intersection in Fuquay-Varina. | Construct intersection improvements. Project will include improvements to NC 55 intersection with NC 42, and construction of connector from NC 55 to SR 5056 (Judd Parkway). | 3 | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 3300000 | FY 2028: 1650000; FY 2029: 1650000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 intersection in Fuquay-Varina. | Construct intersection improvements. Project will include improvements to NC 55 intersection with NC 42, and construction of connector from NC 55 to SR 5056 (Judd Parkway). | 3 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 113300000 | FY 2031: 13596000; FY 2032: 28325000; FY 2033: 27192000; FY 2034: 23793000; FY 2035: 20394000
U-5753 | Highway | STI (Prioritization) | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Hoke | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 8 |  |  |  | 800000
U-5753 | Highway | STI (Prioritization) | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Hoke | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 8 |  | BGANY | RIGHT-OF-WAY | 33688000 | FY 2026: 4200000
U-5753 | Highway | STI (Prioritization) | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Hoke | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 8 |  | BGDA | RIGHT-OF-WAY | 8412000
U-5753 | Highway | STI (Prioritization) | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Hoke | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 8 |  | BGANY | UTILITIES | 5000000
U-5753 | Highway | STI (Prioritization) | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Hoke | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | BUILD NC CON | 26010000 |  | 867000 | 867000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 11271000
U-5753 | Highway | STI (Prioritization) | SR 1305 (Wayside Road); SR 1418 (Lindsay Road) | SR 1305 (Wayside Road) / US 401 to Plank Road, and SR 1418 (Lindsay Road) / US 401 to SR 1406 (Rockfish Road). | Widen to multi-lanes. | 4.5 | Hoke | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 8 |  | T | CONSTRUCTION | 37700000 | FY 2027: 963000; FY 2028: 14425000; FY 2029: 3271000; FY 2030: 10963000; FY 2031: 8078000
U-5754 | Highway | STI (Prioritization) | US 29 / US 70 / US 220 (O'Henry Boulevard) | I-40 /I-85 Business to south of Florida Street in Greensboro. | Construct additional lane on I-40 / I-85 Business eastbound ramp onto northbound US 29 / US 70 / US 220 and extend US 29 / US 70 / US 220 southbound ramp onto SR 3762 (Martin Luther King, Jr. Drive) | 0.69 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T | CONSTRUCTION | 6750000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 in Aberdeen to the intersection of Trotter Drive / Blake Boulevard in Pinehurst. | Widen to four lane divided facility from US 1 to Linden Road and a three lane facility from Linden Road to Trotter Drive. | 3.94 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  |  |  | 2800000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 in Aberdeen to the intersection of Trotter Drive / Blake Boulevard in Pinehurst. | Widen to four lane divided facility from US 1 to Linden Road and a three lane facility from Linden Road to Trotter Drive. | 3.94 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | RIGHT-OF-WAY | 8600000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 in Aberdeen to the intersection of Trotter Drive / Blake Boulevard in Pinehurst. | Widen to four lane divided facility from US 1 to Linden Road and a three lane facility from Linden Road to Trotter Drive. | 3.94 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | UTILITIES | 13200000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 in Aberdeen to the intersection of Trotter Drive / Blake Boulevard in Pinehurst. | Widen to four lane divided facility from US 1 to Linden Road and a three lane facility from Linden Road to Trotter Drive. | 3.94 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 119700000 | FY 2026: 33860000; FY 2027: 33530000; FY 2028: 28656000; FY 2029: 22457000
U-5757 | Highway | STI (Prioritization) | NC 8 (Winston Road) | 9th Street to SR 1408 (Biesecker Road) in Lexington. | Widen to four lane divided facility with bike-ped accommodations. | 0.51 | Davidson | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  |  |  | 1861000
U-5757 | Highway | STI (Prioritization) | NC 8 (Winston Road) | 9th Street to SR 1408 (Biesecker Road) in Lexington. | Widen to four lane divided facility with bike-ped accommodations. | 0.51 | Davidson | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 17575000
U-5757 | Highway | STI (Prioritization) | NC 8 (Winston Road) | 9th Street to SR 1408 (Biesecker Road) in Lexington. | Widen to four lane divided facility with bike-ped accommodations. | 0.51 | Davidson | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 15620000 | FY 2026: 9521000
U-5760 | Highway | STI (Prioritization) | Kernersville Southern Loop | US 421 / I-40 Business to NC 66 (West Mountain Street) in Kernersville. interchange at US 421 / NC 150. | Widen Big Mill Farm Road and SR 2649 (Hopkins Road) to a two lane divided facility and construct interchange at US 421 / NC 150. | 2.05 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) | Division 9 |  |  |  | 2905000
U-5760 | Highway | STI (Prioritization) | Kernersville Southern Loop | US 421 / I-40 Business to NC 66 (West Mountain Street) in Kernersville. interchange at US 421 / NC 150. | Widen Big Mill Farm Road and SR 2649 (Hopkins Road) to a two lane divided facility and construct interchange at US 421 / NC 150. | 2.05 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) | Division 9 |  | T | RIGHT-OF-WAY | 11500000
U-5760 | Highway | STI (Prioritization) | Kernersville Southern Loop | US 421 / I-40 Business to NC 66 (West Mountain Street) in Kernersville. interchange at US 421 / NC 150. | Widen Big Mill Farm Road and SR 2649 (Hopkins Road) to a two lane divided facility and construct interchange at US 421 / NC 150. | 2.05 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) | Division 9 |  | T | UTILITIES | 4000000
U-5760 | Highway | STI (Prioritization) | Kernersville Southern Loop | US 421 / I-40 Business to NC 66 (West Mountain Street) in Kernersville. interchange at US 421 / NC 150. | Widen Big Mill Farm Road and SR 2649 (Hopkins Road) to a two lane divided facility and construct interchange at US 421 / NC 150. | 2.05 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) | Division 9 |  | T | BUILD NC CON | 43350000 | 2660000 | 2890000 | 2890000 | 2890000 | 2890000 | 2890000 | 2890000 | 2890000 | 2890000 | 2890000 | 14680000
U-5760 | Highway | STI (Prioritization) | Kernersville Southern Loop | US 421 / I-40 Business to NC 66 (West Mountain Street) in Kernersville. interchange at US 421 / NC 150. | Widen Big Mill Farm Road and SR 2649 (Hopkins Road) to a two lane divided facility and construct interchange at US 421 / NC 150. | 2.05 | Forsyth | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) | Division 9 |  | T | CONSTRUCTION | 49500000 | FY 2026: 0; FY 2027: 825000; FY 2028: 18975000; FY 2029: 16500000; FY 2030: 13200000
U-5761 | Highway | STI (Prioritization) | NC 3 (Dale Earnhardt Boulevard) | US 29 / US 601 (Cannon Boulevard) intersection. | Construct intersection improvements. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  |  |  | 3660000
U-5761 | Highway | STI (Prioritization) | NC 3 (Dale Earnhardt Boulevard) | US 29 / US 601 (Cannon Boulevard) intersection. | Construct intersection improvements. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | UTILITIES | 1800000 | FY 2026: 10000; FY 2027: 1790000
U-5761 | Highway | STI (Prioritization) | NC 3 (Dale Earnhardt Boulevard) | US 29 / US 601 (Cannon Boulevard) intersection. | Construct intersection improvements. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 8100000 | FY 2027: 1053000; FY 2028: 4617000; FY 2029: 2430000
U-5763 | Highway | STI (Prioritization) | NC 51 (Matthews Township Parkway) | SR 3356 (Sardis Road) to SR 1010 (East John Street / Monroe Road). | Widen to six lanes. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 1000000
U-5763 | Highway | STI (Prioritization) | NC 51 (Matthews Township Parkway) | SR 3356 (Sardis Road) to SR 1010 (East John Street / Monroe Road). | Widen to six lanes. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 40100000 | FY 2030: 1860000; FY 2031: 3180000; FY 2032: 3180000; FY 2033: 3180000; FY 2034: 28700000
U-5763 | Highway | STI (Prioritization) | NC 51 (Matthews Township Parkway) | SR 3356 (Sardis Road) to SR 1010 (East John Street / Monroe Road). | Widen to six lanes. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 5800000 | FY 2030: 2900000; FY 2031: 2900000
U-5763 | Highway | STI (Prioritization) | NC 51 (Matthews Township Parkway) | SR 3356 (Sardis Road) to SR 1010 (East John Street / Monroe Road). | Widen to six lanes. | 0.75 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 43000000 | FY 2034: 430000; FY 2035: 14190000 | 28380000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (Dickerson Boulevard) to SR 1007 (Rocky River Road). | Widen to six lanes. | 2.8 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  |  |  | 10572000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (Dickerson Boulevard) to SR 1007 (Rocky River Road). | Widen to six lanes. | 2.8 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  | BGANY | RIGHT-OF-WAY | 59248000 | FY 2026: 1185000; FY 2027: 17182000; FY 2028: 16589000; FY 2029: 12442000; FY 2030: 11850000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (Dickerson Boulevard) to SR 1007 (Rocky River Road). | Widen to six lanes. | 2.8 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  | BGANY | UTILITIES | 7400000 | FY 2026: 3700000; FY 2027: 3700000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (Dickerson Boulevard) to SR 1007 (Rocky River Road). | Widen to six lanes. | 2.8 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  | BGANY | CONSTRUCTION | 74700000 | FY 2030: 6723000; FY 2031: 20916000; FY 2032: 20169000; FY 2033: 15687000; FY 2034: 11205000
U-5765 | Highway | STI (Prioritization) | NC 73 (Sam Furr Road) | SR 5544 (West Catawba Avenue) to SR 2316 (Northcross Drive). | Widen to six lanes. | 1.12 | Mecklenburg | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  |  |  | 510000
U-5765 | Highway | STI (Prioritization) | NC 73 (Sam Furr Road) | SR 5544 (West Catawba Avenue) to SR 2316 (Northcross Drive). | Widen to six lanes. | 1.12 | Mecklenburg | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | RIGHT-OF-WAY | 58430000 | FY 2026: 11686000; FY 2027: 11686000
U-5765 | Highway | STI (Prioritization) | NC 73 (Sam Furr Road) | SR 5544 (West Catawba Avenue) to SR 2316 (Northcross Drive). | Widen to six lanes. | 1.12 | Mecklenburg | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | UTILITIES | 7500000
U-5765 | Highway | STI (Prioritization) | NC 73 (Sam Furr Road) | SR 5544 (West Catawba Avenue) to SR 2316 (Northcross Drive). | Widen to six lanes. | 1.12 | Mecklenburg | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | BUILD NC CON | 23400000 |  | 1560000 | 1560000 | 1560000 | 1560000 | 1560000 | 1560000 | 1560000 | 1560000 | 1560000 | 9360000
U-5765 | Highway | STI (Prioritization) | NC 73 (Sam Furr Road) | SR 5544 (West Catawba Avenue) to SR 2316 (Northcross Drive). | Widen to six lanes. | 1.12 | Mecklenburg | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | CONSTRUCTION | 26300000 | FY 2027: 0; FY 2028: 3707000; FY 2029: 10632000; FY 2030: 7088000; FY 2031: 4873000
U-5766 | Highway | STI (Prioritization) | NC 160 | South Carolina line to I-485. | Widen to multi-lanes. | 6.8 | Mecklenburg | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT CITY OF CHARLOTTE |  |  |  |  | 3000000
U-5766A | Highway | STI (Prioritization) | NC 160 | South Carolina line to NC 49 (South Tryon Road). | Widen to multi-lanes. | 2.04 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 26600000 | FY 2026: 4962000; FY 2027: 7510000; FY 2028: 7510000; FY 2029: 5320000
U-5766A | Highway | STI (Prioritization) | NC 160 | South Carolina line to NC 49 (South Tryon Road). | Widen to multi-lanes. | 2.04 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 10700000 | FY 2026: 5350000; FY 2027: 5350000
U-5766A | Highway | STI (Prioritization) | NC 160 | South Carolina line to NC 49 (South Tryon Road). | Widen to multi-lanes. | 2.04 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 35600000 | FY 2030: 356000; FY 2031: 11748000; FY 2032: 11036000; FY 2033: 7476000; FY 2034: 4984000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (South Tryon Road) to I-485. | Widen to multi-lanes. | 4.31 | Mecklenburg | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $12.3M FOR ROW, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE). | Region E |  | T | BUILD NC ROW | 15990000 | 1066000 | 1066000 | 1066000 | 1066000 | 1066000 | 1066000 | 1066000 | 1066000 | 1066000 | 1066000 | 5330000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (South Tryon Road) to I-485. | Widen to multi-lanes. | 4.31 | Mecklenburg | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $12.3M FOR ROW, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE). | Region E |  | T | RIGHT-OF-WAY | 45900000 | FY 2026: 0; FY 2027: 15636000; FY 2028: 15714000; FY 2029: 2910000; FY 2030: 11640000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (South Tryon Road) to I-485. | Widen to multi-lanes. | 4.31 | Mecklenburg | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $12.3M FOR ROW, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE). | Region E |  | T | UTILITIES | 8200000 | FY 2026: 4100000; FY 2027: 4100000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (South Tryon Road) to I-485. | Widen to multi-lanes. | 4.31 | Mecklenburg | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $12.3M FOR ROW, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE). | Region E |  | O | UTILITIES | 34000000 | FY 2026: 17000000; FY 2027: 17000000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (South Tryon Road) to I-485. | Widen to multi-lanes. | 4.31 | Mecklenburg | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $12.3M FOR ROW, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE). | Region E |  | T | CONSTRUCTION | 137400000 | FY 2029: 28854000; FY 2030: 34350000; FY 2031: 30228000; FY 2032: 24732000; FY 2033: 19236000
U-5767 | Highway | STI (Prioritization) | US 21 (Statesville Road) | Northcross Center Court to SR 2147 (Westmoreland Road). | Widen to multi-lanes. | 1.22 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 4593000
U-5767 | Highway | STI (Prioritization) | US 21 (Statesville Road) | Northcross Center Court to SR 2147 (Westmoreland Road). | Widen to multi-lanes. | 1.22 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 88500000 | FY 2030: 2576000; FY 2031: 32824000; FY 2032: 23600000; FY 2033: 11800000; FY 2034: 17700000
U-5767 | Highway | STI (Prioritization) | US 21 (Statesville Road) | Northcross Center Court to SR 2147 (Westmoreland Road). | Widen to multi-lanes. | 1.22 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 2700000 | FY 2030: 1350000; FY 2031: 1350000
U-5767 | Highway | STI (Prioritization) | US 21 (Statesville Road) | Northcross Center Court to SR 2147 (Westmoreland Road). | Widen to multi-lanes. | 1.22 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 44300000 | FY 2034: 11075000; FY 2035: 12404000 | 20821000
U-5768 | Highway | STI (Prioritization) | NC 49; SR 2827 (Back Creek Church Road) | John Kirk Drive to I-485; Existing SR 2827 (Back Creek Church Road) and NC 49 and SR 5394 (Mallard Creek Church Road)intersection in Harrisburg. | Widen to six lanes; Realign roadway on new location. Close existing grade rail crossing at NC 49 and SR 2827 (Back Creek Church Road). | 2.13 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  |  |  | 2000000
U-5768 | Highway | STI (Prioritization) | NC 49; SR 2827 (Back Creek Church Road) | John Kirk Drive to I-485; Existing SR 2827 (Back Creek Church Road) and NC 49 and SR 5394 (Mallard Creek Church Road)intersection in Harrisburg. | Widen to six lanes; Realign roadway on new location. Close existing grade rail crossing at NC 49 and SR 2827 (Back Creek Church Road). | 2.13 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | T | RIGHT-OF-WAY | 37900000 | FY 2030: 6064000; FY 2031: 7580000; FY 2032: 7959000; FY 2033: 7959000; FY 2034: 8338000
U-5768 | Highway | STI (Prioritization) | NC 49; SR 2827 (Back Creek Church Road) | John Kirk Drive to I-485; Existing SR 2827 (Back Creek Church Road) and NC 49 and SR 5394 (Mallard Creek Church Road)intersection in Harrisburg. | Widen to six lanes; Realign roadway on new location. Close existing grade rail crossing at NC 49 and SR 2827 (Back Creek Church Road). | 2.13 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | T | UTILITIES | 7500000 | FY 2030: 3750000; FY 2031: 3750000
U-5768 | Highway | STI (Prioritization) | NC 49; SR 2827 (Back Creek Church Road) | John Kirk Drive to I-485; Existing SR 2827 (Back Creek Church Road) and NC 49 and SR 5394 (Mallard Creek Church Road)intersection in Harrisburg. | Widen to six lanes; Realign roadway on new location. Close existing grade rail crossing at NC 49 and SR 2827 (Back Creek Church Road). | 2.13 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | T | CONSTRUCTION | 55400000 | FY 2034: 13296000; FY 2035: 14404000 | 27700000
U-5768 | Highway | STI (Prioritization) | NC 49; SR 2827 (Back Creek Church Road) | John Kirk Drive to I-485; Existing SR 2827 (Back Creek Church Road) and NC 49 and SR 5394 (Mallard Creek Church Road)intersection in Harrisburg. | Widen to six lanes; Realign roadway on new location. Close existing grade rail crossing at NC 49 and SR 2827 (Back Creek Church Road). | 2.13 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | L | CONSTRUCTION | 25000000 | FY 2034: 6750000; FY 2035: 7750000 | 10500000
U-5769 | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1316 (Rea Road extension) to SR 3530 (Waxhaw Parkway) in Waxhaw. | Widen to multi-lanes. | 5.7 | Union | 10 | Charlotte Regional TPO | [5 empty] | 3840000
U-5769A | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1316 (Rea Road extension) to SR 1307 (Bonds Grove Church Road) in Waxhaw. | Widen to multi-lanes. | 4.05 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 29800000 | FY 2026: 5722000; FY 2027: 5722000; FY 2028: 5722000; FY 2029: 11680000
U-5769A | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1316 (Rea Road extension) to SR 1307 (Bonds Grove Church Road) in Waxhaw. | Widen to multi-lanes. | 4.05 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 10000
U-5769A | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1316 (Rea Road extension) to SR 1307 (Bonds Grove Church Road) in Waxhaw. | Widen to multi-lanes. | 4.05 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 71000000 | FY 2029: 710000; FY 2030: 21300000; FY 2031: 20590000; FY 2032: 16330000; FY 2033: 12070000
U-5769AA | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1307 (Bonds Grove Church Road) intersection in Waxhaw. | Construct interim safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 4000000 | FY 2026: 1422000; FY 2027: 400000; FY 2028: 400000
U-5769AA | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1307 (Bonds Grove Church Road) intersection in Waxhaw. | Construct interim safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 1000000
U-5769AA | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1307 (Bonds Grove Church Road) intersection in Waxhaw. | Construct interim safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 1225000 | FY 2026: 833000; FY 2027: 392000
U-5769B | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1307 (Bonds Grove Church Road) to SR 3530 (Waxhaw Parkway) in Waxhaw. | Widen to multi-lanes. | 1.73 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 18200000 | FY 2026: 3495000; FY 2027: 3495000; FY 2028: 3495000; FY 2029: 7133000
U-5769B | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1307 (Bonds Grove Church Road) to SR 3530 (Waxhaw Parkway) in Waxhaw. | Widen to multi-lanes. | 1.73 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 10000
U-5769B | Highway | STI (Prioritization) | NC 16 (Providence Road South) | SR 1307 (Bonds Grove Church Road) to SR 3530 (Waxhaw Parkway) in Waxhaw. | Widen to multi-lanes. | 1.73 | Union | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 80900000 | FY 2029: 809000; FY 2030: 22652000; FY 2031: 23461000; FY 2032: 19416000; FY 2033: 14562000
U-5770 | Highway | STI (Prioritization) | I-85 | SR 1009 (South Main Street) intersection in Archdale. | Construct intersection improvements. | 1 | Randolph | 8 | High Point Urban Area MPO | “HF” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | Region E |  |  |  | 1702000
U-5770 | Highway | STI (Prioritization) | I-85 | SR 1009 (South Main Street) intersection in Archdale. | Construct intersection improvements. | 1 | Randolph | 8 | High Point Urban Area MPO | “HF” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | Region E |  | T | RIGHT-OF-WAY | 6358000
U-5770 | Highway | STI (Prioritization) | I-85 | SR 1009 (South Main Street) intersection in Archdale. | Construct intersection improvements. | 1 | Randolph | 8 | High Point Urban Area MPO | “HF” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | Region E |  | T | UTILITIES | 2200000
U-5770A | Highway | STI (Prioritization) | SR 1009 (South Main Street) | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Mill and resurface roadway. | 1.07 | Randolph | 8 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region E |  | T | CONSTRUCTION | 1024000
U-5770A | Highway | STI (Prioritization) | SR 1009 (South Main Street) | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Mill and resurface roadway. | 1.07 | Randolph | 8 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region E |  | HF | CONSTRUCTION | 669000
U-5770B | Highway | STI (Prioritization) | SR 1009 (South Main Street) | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Construct diverging diamond interchange and reduced conflict intersection improvements | 0.99 | Randolph | 8 | High Point Urban Area MPO | NC BUILD BOND $8M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Region E |  | T | UTILITIES | 2400000 | FY 2026: 2400000
U-5770B | Highway | STI (Prioritization) | SR 1009 (South Main Street) | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Construct diverging diamond interchange and reduced conflict intersection improvements | 0.99 | Randolph | 8 | High Point Urban Area MPO | NC BUILD BOND $8M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Region E |  | T | BUILD NC CON | 12195000 |  |  | 1626000 | 813000 | 813000 | 813000 | 813000 | 813000 | 813000 | 813000 | 4878000
U-5770B | Highway | STI (Prioritization) | SR 1009 (South Main Street) | West of Columbus Avenue to SR 3182 (Comanche Road / Tarheel Road) | Construct diverging diamond interchange and reduced conflict intersection improvements | 0.99 | Randolph | 8 | High Point Urban Area MPO | NC BUILD BOND $8M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Region E |  | T | CONSTRUCTION | 17600000 | FY 2028: 0; FY 2029: 7104000; FY 2030: 7424000; FY 2031: 3072000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  |  |  | 2098000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | RIGHT-OF-WAY | 52600000 | FY 2026: 10000000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | BA | RIGHT-OF-WAY | 450000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | UTILITIES | 1600000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | BUILD NC CON | 19500000 |  | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 7800000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T | CONSTRUCTION | 17100000 | FY 2027: 0; FY 2028: 2013000; FY 2029: 7704000; FY 2030: 4815000; FY 2031: 2568000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | T(DA) | CONSTRUCTION | 2559000 | FY 2027: 486000; FY 2028: 870000; FY 2029: 614000; FY 2030: 384000; FY 2031: 205000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (Gilead Road) to Holly Point Drive in Huntersville. | Widen to four lanes. | 2.21 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); | Region E |  | L | CONSTRUCTION | 650000 | FY 2027: 650000
U-5772 | Highway | STI (Prioritization) | NC 115 (Old Statesville Road) | NC 24 (Harris Boulevard) to I-485 in Charlotte. | Widen to multi-lanes. | 2.16 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3500000
U-5772 | Highway | STI (Prioritization) | NC 115 (Old Statesville Road) | NC 24 (Harris Boulevard) to I-485 in Charlotte. | Widen to multi-lanes. | 2.16 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 30600000
U-5772 | Highway | STI (Prioritization) | NC 115 (Old Statesville Road) | NC 24 (Harris Boulevard) to I-485 in Charlotte. | Widen to multi-lanes. | 2.16 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3200000
U-5772 | Highway | STI (Prioritization) | NC 115 (Old Statesville Road) | NC 24 (Harris Boulevard) to I-485 in Charlotte. | Widen to multi-lanes. | 2.16 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 85900000
U-5774 | Highway | STI (Prioritization) | NC 54 | US 15 / US 501 in Chapel Hill to NC 55 in Durham. | Upgrade roadway corridor. | 8.4 | Durham, Orange | 5, 7 | Triangle West TPO | PARTS A THROUGH F ON EXPANDED NHS |  |  |  |  | 1905000
U-5774A | Highway | STI (Prioritization) | NC 54 | US 15/ US 501 interchange | Upgrade interchange | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4800000 | [10 empty] | 4800000
U-5774A | Highway | STI (Prioritization) | NC 54 | US 15/ US 501 interchange | Upgrade interchange | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 720000 | [10 empty] | 720000
U-5774A | Highway | STI (Prioritization) | NC 54 | US 15/ US 501 interchange | Upgrade interchange | 1 | Orange | 7 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 28600000 | [10 empty] | 28600000
U-5774B | Highway | STI (Prioritization) | NC 54 | West of US 15 / US 501 in Orange County to east of SR 1110 (Barbee Chapel Road) in Durham County | Upgrade roadway corridor. | 1.22 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 31300000 | [10 empty] | 31300000
U-5774B | Highway | STI (Prioritization) | NC 54 | West of US 15 / US 501 in Orange County to east of SR 1110 (Barbee Chapel Road) in Durham County | Upgrade roadway corridor. | 1.22 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 7600000 | [10 empty] | 7600000
U-5774B | Highway | STI (Prioritization) | NC 54 | West of US 15 / US 501 in Orange County to east of SR 1110 (Barbee Chapel Road) in Durham County | Upgrade roadway corridor. | 1.22 | Orange, Durham | 5, 7 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 54100000 | [10 empty] | 54100000
U-5774C | Highway | STI (Prioritization) | NC 54 | East of SR 1110 (Barbee Chapel Road) to east of Little Creek | Upgrade roadway corridor. | 1.64 | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 610000 | [10 empty] | 610000
U-5774C | Highway | STI (Prioritization) | NC 54 | East of SR 1110 (Barbee Chapel Road) to east of Little Creek | Upgrade roadway corridor. | 1.64 | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 4400000 | [10 empty] | 4400000
U-5774C | Highway | STI (Prioritization) | NC 54 | East of SR 1110 (Barbee Chapel Road) to east of Little Creek | Upgrade roadway corridor. | 1.64 | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 23001000 | [10 empty] | 23001000
U-5774D | Highway | STI (Prioritization) | NC 54 | Falconbridge Road intersection | Convert at-grade intersection to interchange. | 0.5 | Durham | 5 | Triangle West TPO | SCOPE INCLUDED IN U-5774F
U-5774E | Highway | STI (Prioritization) | NC 54 | SR 1110 (Farrington Road) intersection | Convert at-grade intersection to grade separation. | 0.5 | Durham | 5 | Triangle West TPO | SCOPE INCLUDED IN U-5774F
U-5774F | Highway | STI (Prioritization) | I 40 | NC 54 interchange | Construct interchange improvements, including upgrade of NC 54 from east of Little Creek to east of I-40. | 1 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 117800000 | FY 2030: 11780000; FY 2031: 41230000; FY 2032: 41230000; FY 2033: 11780000; FY 2034: 11780000
U-5774F | Highway | STI (Prioritization) | I 40 | NC 54 interchange | Construct interchange improvements, including upgrade of NC 54 from east of Little Creek to east of I-40. | 1 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHP | UTILITIES | 5500000 | FY 2030: 2750000; FY 2031: 2750000
U-5774F | Highway | STI (Prioritization) | I 40 | NC 54 interchange | Construct interchange improvements, including upgrade of NC 54 from east of Little Creek to east of I-40. | 1 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 156100000 | FY 2033: 28098000; FY 2034: 35903000; FY 2035: 34342000 | 57757000
U-5774G | Highway | STI (Prioritization) | NC 54 | East of I-40 to east of NC 751 | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 1800000 | [10 empty] | 1800000
U-5774G | Highway | STI (Prioritization) | NC 54 | East of I-40 to east of NC 751 | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 800000 | [10 empty] | 800000
U-5774G | Highway | STI (Prioritization) | NC 54 | East of I-40 to east of NC 751 | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 16901000 | [10 empty] | 16901000
U-5774H | Highway | STI (Prioritization) | NC 54 | East of NC 751 to east of SR 1118 (Fayetteville Road) | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5900000 | [10 empty] | 5900000
U-5774H | Highway | STI (Prioritization) | NC 54 | East of NC 751 to east of SR 1118 (Fayetteville Road) | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 726000 | [10 empty] | 726000
U-5774H | Highway | STI (Prioritization) | NC 54 | East of NC 751 to east of SR 1118 (Fayetteville Road) | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 17999000 | [10 empty] | 17999000
U-5774I | Highway | STI (Prioritization) | NC 54 | East of SR 1118 (Fayetteville Road) to east of SR 1106 (Barbee Road) | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2500000 | [10 empty] | 2500000
U-5774I | Highway | STI (Prioritization) | NC 54 | East of SR 1118 (Fayetteville Road) to east of SR 1106 (Barbee Road) | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 617000 | [10 empty] | 617000
U-5774I | Highway | STI (Prioritization) | NC 54 | East of SR 1118 (Fayetteville Road) to east of SR 1106 (Barbee Road) | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 12300000 | [10 empty] | 12300000
U-5774J | Highway | STI (Prioritization) | NC 54 | East of SR 1106 (Barbee Road) to NC 55 | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3200000 | [10 empty] | 3200000
U-5774J | Highway | STI (Prioritization) | NC 54 | East of SR 1106 (Barbee Road) to NC 55 | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | UTILITIES | 420000 | [10 empty] | 420000
U-5774J | Highway | STI (Prioritization) | NC 54 | East of SR 1106 (Barbee Road) to NC 55 | Upgrade roadway corridor. |  | Durham | 5 | Triangle West TPO |  | Not Funded |  | T | CONSTRUCTION | 17100000 | [10 empty] | 17100000
U-5775 | Highway | STI (Prioritization) | US 74 Business (Marion Street) | NC 150 (Cherryville Road) intersection in Shelby. | Realign intersection. | 0.5 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $702,705 FROM CITY OF SHELBY | Region F |  |  |  | 1153000
U-5775 | Highway | STI (Prioritization) | US 74 Business (Marion Street) | NC 150 (Cherryville Road) intersection in Shelby. | Realign intersection. | 0.5 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $702,705 FROM CITY OF SHELBY | Region F |  | T | CONSTRUCTION | 9663000
U-5775 | Highway | STI (Prioritization) | US 74 Business (Marion Street) | NC 150 (Cherryville Road) intersection in Shelby. | Realign intersection. | 0.5 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $702,705 FROM CITY OF SHELBY | Region F |  | L | CONSTRUCTION | 703000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1st Avenue Southeast to 2nd Avenue Southeast in Hickory. | Construct turn lanes. |  | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Region F |  |  |  | 275000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1st Avenue Southeast to 2nd Avenue Southeast in Hickory. | Construct turn lanes. |  | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Region F |  | T | RIGHT-OF-WAY | 2150000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1st Avenue Southeast to 2nd Avenue Southeast in Hickory. | Construct turn lanes. |  | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Region F |  | T | UTILITIES | 436000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1st Avenue Southeast to 2nd Avenue Southeast in Hickory. | Construct turn lanes. |  | Catawba | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Region F |  | BGANY | CONSTRUCTION | 9900000 | FY 2026: 3922000; FY 2027: 1850000
U-5780 | Highway | STI (Prioritization) | NC 150 | SR 2399 (Wiggins Road) intersection in Mooresville. | Realign intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | ENGINEERING | 994000
U-5780 | Highway | STI (Prioritization) | NC 150 | SR 2399 (Wiggins Road) intersection in Mooresville. | Realign intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | RIGHT-OF-WAY | 605000
U-5780 | Highway | STI (Prioritization) | NC 150 | SR 2399 (Wiggins Road) intersection in Mooresville. | Realign intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | UTILITIES | 865000
U-5780 | Highway | STI (Prioritization) | NC 150 | SR 2399 (Wiggins Road) intersection in Mooresville. | Realign intersection. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | CONSTRUCTION | 4520000 | FY 2026: 2310000; FY 2027: 630000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (Blythe Street) to SR 1173 (White Pine Drive) / SR 1186 (Daniel Drive) in Laurel Park. | Modernize roadway with bike lanes and paved shoulders. | 0.99 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  |  |  | 1500000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (Blythe Street) to SR 1173 (White Pine Drive) / SR 1186 (Daniel Drive) in Laurel Park. | Modernize roadway with bike lanes and paved shoulders. | 0.99 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | RIGHT-OF-WAY | 19900000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (Blythe Street) to SR 1173 (White Pine Drive) / SR 1186 (Daniel Drive) in Laurel Park. | Modernize roadway with bike lanes and paved shoulders. | 0.99 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | UTILITIES | 3900000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (Blythe Street) to SR 1173 (White Pine Drive) / SR 1186 (Daniel Drive) in Laurel Park. | Modernize roadway with bike lanes and paved shoulders. | 0.99 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | CONSTRUCTION | 32740000 | FY 2026: 8678000; FY 2027: 5929000; FY 2028: 3061000
U-5785 | Highway | STI (Prioritization) | SR 1708 (Firetower Road) | West of East Arlington Boulevard to NC 33 (East 10th Street) in Greenville. | Widen to four lanes. | 3.4 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES SCOPE OF U-5870. | Division 2 |  |  |  | 18000000
U-5785 | Highway | STI (Prioritization) | SR 1708 (Firetower Road) | West of East Arlington Boulevard to NC 33 (East 10th Street) in Greenville. | Widen to four lanes. | 3.4 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES SCOPE OF U-5870. | Division 2 |  | T | RIGHT-OF-WAY | 58200000 | FY 2026: 26772000; FY 2027: 5820000; FY 2028: 5820000
U-5785 | Highway | STI (Prioritization) | SR 1708 (Firetower Road) | West of East Arlington Boulevard to NC 33 (East 10th Street) in Greenville. | Widen to four lanes. | 3.4 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES SCOPE OF U-5870. | Division 2 |  | T | UTILITIES | 7500000
U-5785 | Highway | STI (Prioritization) | SR 1708 (Firetower Road) | West of East Arlington Boulevard to NC 33 (East 10th Street) in Greenville. | Widen to four lanes. | 3.4 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES SCOPE OF U-5870. | Division 2 |  | T | CONSTRUCTION | 109400000 | FY 2030: 24068000; FY 2031: 27350000; FY 2032: 22974000; FY 2033: 19692000; FY 2034: 15316000
U-5786 | Highway | STI (Prioritization) | SR 1508 (Hickory Tree Road) | US 52 / NC 8 / Future I-285 to NC 150. | Widen to multi-lanes. | 2.91 | Davidson | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 890000
U-5786 | Highway | STI (Prioritization) | SR 1508 (Hickory Tree Road) | US 52 / NC 8 / Future I-285 to NC 150. | Widen to multi-lanes. | 2.91 | Davidson | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 12700000 | FY 2030: 1270000; FY 2031: 4445000; FY 2032: 4445000; FY 2033: 1270000; FY 2034: 1270000
U-5786 | Highway | STI (Prioritization) | SR 1508 (Hickory Tree Road) | US 52 / NC 8 / Future I-285 to NC 150. | Widen to multi-lanes. | 2.91 | Davidson | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | UTILITIES | 5200000 | FY 2030: 2600000; FY 2031: 2600000
U-5786 | Highway | STI (Prioritization) | SR 1508 (Hickory Tree Road) | US 52 / NC 8 / Future I-285 to NC 150. | Widen to multi-lanes. | 2.91 | Davidson | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | CONSTRUCTION | 45700000 | FY 2034: 10511000; FY 2035: 11882000 | 23307000
U-5787 | Highway | STI (Prioritization) | SR 2715 (Trade Street) | NC 53 (Western Boulevard) to McDaniel Drive in Jacksonville. | Construct roadway on new location. | 0.28 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 800000
U-5787 | Highway | STI (Prioritization) | SR 2715 (Trade Street) | NC 53 (Western Boulevard) to McDaniel Drive in Jacksonville. | Construct roadway on new location. | 0.28 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 2600000 | FY 2026: 26000; FY 2027: 702000; FY 2028: 858000; FY 2029: 494000; FY 2030: 520000
U-5787 | Highway | STI (Prioritization) | SR 2715 (Trade Street) | NC 53 (Western Boulevard) to McDaniel Drive in Jacksonville. | Construct roadway on new location. | 0.28 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | UTILITIES | 890000 | FY 2026: 890000
U-5787 | Highway | STI (Prioritization) | SR 2715 (Trade Street) | NC 53 (Western Boulevard) to McDaniel Drive in Jacksonville. | Construct roadway on new location. | 0.28 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 7600000 | FY 2029: 1748000; FY 2030: 4104000; FY 2031: 1748000
U-5788 | Highway | STI (Prioritization) | US 17 Business (Main Street) | Wall Street / Shallotte Avenue intersection in Shallotte | Realign intersection. | 0.5 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  |  |  | 1245000
U-5788 | Highway | STI (Prioritization) | US 17 Business (Main Street) | Wall Street / Shallotte Avenue intersection in Shallotte | Realign intersection. | 0.5 | Brunswick | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 1964000
U-5789 | Highway | STI (Prioritization) | NC 53 (Western Boulevard) | SR 2714 (Jacksonville Parkway) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 1983000
U-5789 | Highway | STI (Prioritization) | NC 53 (Western Boulevard) | SR 2714 (Jacksonville Parkway) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BG50200 | CONSTRUCTION | 8000000 | FY 2026: 4560000; FY 2027: 2240000
U-5790 | Highway | STI (Prioritization) | US 421 (Carolina Beach Road) | NC 132 (South College Road) to Sanders Road in Wilmington. | Widen existing roadway and construct flyovers at US 421 and NC 132. | 1.03 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 1500000
U-5790 | Highway | STI (Prioritization) | US 421 (Carolina Beach Road) | NC 132 (South College Road) to Sanders Road in Wilmington. | Widen existing roadway and construct flyovers at US 421 and NC 132. | 1.03 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 12000000 | FY 2027: 1600000; FY 2028: 4800000; FY 2029: 3200000; FY 2030: 1200000; FY 2031: 1200000
U-5790 | Highway | STI (Prioritization) | US 421 (Carolina Beach Road) | NC 132 (South College Road) to Sanders Road in Wilmington. | Widen existing roadway and construct flyovers at US 421 and NC 132. | 1.03 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | UTILITIES | 3200000 | FY 2027: 1600000; FY 2028: 1600000
U-5790 | Highway | STI (Prioritization) | US 421 (Carolina Beach Road) | NC 132 (South College Road) to Sanders Road in Wilmington. | Widen existing roadway and construct flyovers at US 421 and NC 132. | 1.03 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 39300000 | FY 2029: 2751000; FY 2030: 11790000; FY 2031: 10611000; FY 2032: 7860000; FY 2033: 6288000
U-5791 | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway Extension) | NC 53 (Western Boulevard) to US 17 (New Bern Highway). | Widen to multi-lanes, partially on new location. | 3.83 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 1750000
U-5791A | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | NC 53 (Western Boulevard) to SR 1324 (Ramsey Road). | Widen to multi-lanes, partially on new location. | 1.55 | Onslow | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 3 |  | T | RIGHT-OF-WAY | 20900000 | FY 2027: 209000; FY 2028: 7524000; FY 2029: 8987000; FY 2030: 2090000; FY 2031: 2090000
U-5791A | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | NC 53 (Western Boulevard) to SR 1324 (Ramsey Road). | Widen to multi-lanes, partially on new location. | 1.55 | Onslow | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 3 |  | T | UTILITIES | 1200000 | FY 2027: 600000; FY 2028: 600000
U-5791A | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | NC 53 (Western Boulevard) to SR 1324 (Ramsey Road). | Widen to multi-lanes, partially on new location. | 1.55 | Onslow | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 3 |  | T | BUILD NC CON | 19500000 |  |  |  |  | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 9100000
U-5791A | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | NC 53 (Western Boulevard) to SR 1324 (Ramsey Road). | Widen to multi-lanes, partially on new location. | 1.55 | Onslow | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 3 |  | T | CONSTRUCTION | 66500000 | FY 2029: 815000; FY 2030: 7820000; FY 2031: 22005000; FY 2032: 19560000; FY 2033: 16300000
U-5791B | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | SR 1324 (Ramsey Road) to US 17 (New Bern Highway). | Widen to multi-lanes, partially on new location. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 17600000 | [10 empty] | 17600000
U-5791B | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | SR 1324 (Ramsey Road) to US 17 (New Bern Highway). | Widen to multi-lanes, partially on new location. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 4200000 | [10 empty] | 4200000
U-5791B | Highway | STI (Prioritization) | SR 2714 (Jacksonville Parkway) | SR 1324 (Ramsey Road) to US 17 (New Bern Highway). | Widen to multi-lanes, partially on new location. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 51400000 | [10 empty] | 51400000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (College Road) | US 17 Business (Market Street) to SR 2048 (Gordon Road). | Upgrade roadway. | 1.9 | New Hanover | 3 | Wilmington Urban Area MPO | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE). | Division 3 |  |  |  | 1500000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (College Road) | US 17 Business (Market Street) to SR 2048 (Gordon Road). | Upgrade roadway. | 1.9 | New Hanover | 3 | Wilmington Urban Area MPO | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE). | Division 3 |  | T | RIGHT-OF-WAY | 29100000 | FY 2026: 291000; FY 2027: 6693000; FY 2028: 8148000; FY 2029: 8148000; FY 2030: 5820000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (College Road) | US 17 Business (Market Street) to SR 2048 (Gordon Road). | Upgrade roadway. | 1.9 | New Hanover | 3 | Wilmington Urban Area MPO | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE). | Division 3 |  | T | UTILITIES | 2800000 | FY 2026: 1400000; FY 2027: 1400000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (College Road) | US 17 Business (Market Street) to SR 2048 (Gordon Road). | Upgrade roadway. | 1.9 | New Hanover | 3 | Wilmington Urban Area MPO | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE). | Division 3 |  | T | BUILD NC CON | 39000000 |  |  |  |  | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 23400000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (College Road) | US 17 Business (Market Street) to SR 2048 (Gordon Road). | Upgrade roadway. | 1.9 | New Hanover | 3 | Wilmington Urban Area MPO | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE). | Division 3 |  | T | CONSTRUCTION | 156300000 | FY 2029: 1863000; FY 2030: 20301000; FY 2031: 48438000; FY 2032: 44712000; FY 2033: 40986000
U-5797 | Highway | STI (Prioritization) | SR 1997 (Fayetteville Road) | Farrington Street to East 22nd Street. | Widen to six lanes and modernize roadway. | 1.26 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  |  |  | 1334000
U-5797 | Highway | STI (Prioritization) | SR 1997 (Fayetteville Road) | Farrington Street to East 22nd Street. | Widen to six lanes and modernize roadway. | 1.26 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | RIGHT-OF-WAY | 8200000
U-5797 | Highway | STI (Prioritization) | SR 1997 (Fayetteville Road) | Farrington Street to East 22nd Street. | Widen to six lanes and modernize roadway. | 1.26 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | UTILITIES | 2600000
U-5797 | Highway | STI (Prioritization) | SR 1997 (Fayetteville Road) | Farrington Street to East 22nd Street. | Widen to six lanes and modernize roadway. | 1.26 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | BUILD NC CON | 13005000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 4335000
U-5797 | Highway | STI (Prioritization) | SR 1997 (Fayetteville Road) | Farrington Street to East 22nd Street. | Widen to six lanes and modernize roadway. | 1.26 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | CONSTRUCTION | 28700000 | FY 2026: 0; FY 2027: 7802000; FY 2028: 9675000; FY 2029: 7353000; FY 2030: 3870000
U-5798 | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | US 401 (Raeford Road) to SR 1418 (Lindsay Road). | Widen to four lanes. | 2.4 | Cumberland, Hoke | 6, 8 | Fayetteville Area MPO | COORDINATE WITH U-5753, U-5857, AND U-5858. | Division 6, 8 |  |  |  | 1010000
U-5798A | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | North of SR 1112 (Stoney Point Road) to US 401 (Raeford Road). | Widen to four lanes and replace bridge 250075 over Little Rockfish Creek. | 1.07 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | RIGHT-OF-WAY | 9322000
U-5798A | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | North of SR 1112 (Stoney Point Road) to US 401 (Raeford Road). | Widen to four lanes and replace bridge 250075 over Little Rockfish Creek. | 1.07 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | UTILITIES | 475000
U-5798A | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | North of SR 1112 (Stoney Point Road) to US 401 (Raeford Road). | Widen to four lanes and replace bridge 250075 over Little Rockfish Creek. | 1.07 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 26036000
U-5798B | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | SR 1418 (Lindsay Road) to north of SR 1112 (Stoney Point Road). | Widen to four lanes. | 1.21 | Cumberland, Hoke | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6, 8 |  | T | RIGHT-OF-WAY | 3700000 | FY 2026: 370000; FY 2027: 370000
U-5798B | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | SR 1418 (Lindsay Road) to north of SR 1112 (Stoney Point Road). | Widen to four lanes. | 1.21 | Cumberland, Hoke | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6, 8 |  | T | UTILITIES | 710000
U-5798B | Highway | STI (Prioritization) | SR 1102 (Gillis Hill Road) | SR 1418 (Lindsay Road) to north of SR 1112 (Stoney Point Road). | Widen to four lanes. | 1.21 | Cumberland, Hoke | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6, 8 |  | T | CONSTRUCTION | 17400000 | FY 2026: 5568000; FY 2027: 6438000; FY 2028: 4350000; FY 2029: 1044000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  |  |  | 543000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | ENGINEERING | 2265000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | BUILD NC ROW | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | RIGHT-OF-WAY | 22300000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | UTILITIES | 4000000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 (Pump Station Road) to SR 1930 (Fort Dobbs Road) in Statesville. | Widen to four lanes. Realign offset intersections of SR 1922 (Shumaker Drive) and SR 2171 (Jane Sowers Road). | 0.81 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | CONSTRUCTION | 29400000 | FY 2031: 3528000; FY 2032: 9114000; FY 2033: 7644000; FY 2034: 5586000; FY 2035: 3528000
U-5800 | Highway | STI (Prioritization) | NC 7 | US 74 and US 29 intersections in Belmont. | Construct northbound through lane and intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. TO BE LET WITH I-5719B. | Region F |  |  |  | 180000
U-5800 | Highway | STI (Prioritization) | NC 7 | US 74 and US 29 intersections in Belmont. | Construct northbound through lane and intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. TO BE LET WITH I-5719B. | Region F |  | BG50200 | RIGHT-OF-WAY | 18600000 | FY 2026: 6510000; FY 2027: 6510000; FY 2028: 1860000; FY 2029: 1860000
U-5800 | Highway | STI (Prioritization) | NC 7 | US 74 and US 29 intersections in Belmont. | Construct northbound through lane and intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. TO BE LET WITH I-5719B. | Region F |  | BG50200 | UTILITIES | 3700000 | FY 2026: 1850000; FY 2027: 925000
U-5800 | Highway | STI (Prioritization) | NC 7 | US 74 and US 29 intersections in Belmont. | Construct northbound through lane and intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. TO BE LET WITH I-5719B. | Region F |  | BG50200 | CONSTRUCTION | 19600000 | FY 2026: 4900000; FY 2027: 4900000; FY 2028: 4312000; FY 2029: 3528000
U-5803 | Highway | STI (Prioritization) | SR 2940 (Eastway Drive) | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  |  |  | 705000
U-5803 | Highway | STI (Prioritization) | SR 2940 (Eastway Drive) | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 5400000 | FY 2026: 2700000; FY 2027: 2700000
U-5803 | Highway | STI (Prioritization) | SR 2940 (Eastway Drive) | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 600000 | FY 2026: 600000
U-5803 | Highway | STI (Prioritization) | SR 2940 (Eastway Drive) | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 14219000 | FY 2027: 142000; FY 2028: 4266000; FY 2029: 4124000; FY 2030: 3270000; FY 2031: 2417000
U-5803 | Highway | STI (Prioritization) | SR 2940 (Eastway Drive) | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | O | CONSTRUCTION | 35881000 | FY 2027: 359000; FY 2028: 10764000; FY 2029: 10406000; FY 2030: 8252000; FY 2031: 6100000
U-5803 | Highway | STI (Prioritization) | SR 2940 (Eastway Drive) | Shamrock Drive intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 9419000 | FY 2027: 94000; FY 2028: 2826000; FY 2029: 2732000; FY 2030: 2166000; FY 2031: 1601000
U-5804 | Highway | STI (Prioritization) | SR 3448 (South Trade Street) | Fullwood Lane to Weddington Road in Matthews. | Widen to four lanes. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | [5 empty] | 2223000
U-5804A | Highway | STI (Prioritization) | SR 3448 (South Trade Street) | Fullwood Lane to Four Mile Creek in Matthews. | Widen to four lanes. | 0.43 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE - BY TOWN OF MATTHEWS USING TOWN FUNDS.
U-5804B | Highway | STI (Prioritization) | SR 3448 (South Trade Street) | Four Mile Creek to Weddington Road in Matthews. | Widen to four lanes. | 0.13 | Mecklenburg | 10 | Charlotte Regional TPO | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE). | Division 10 |  | T | BUILD NC CON | 1470000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000
U-5805 | Highway | STI (Prioritization) | SR 1009 (Monroe Road) | Rama Road / Idlewild Road intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  |  |  | 42000
U-5805 | Highway | STI (Prioritization) | SR 1009 (Monroe Road) | Rama Road / Idlewild Road intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | T | RIGHT-OF-WAY | 1386000
U-5805 | Highway | STI (Prioritization) | SR 1009 (Monroe Road) | Rama Road / Idlewild Road intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 5952000 | FY 2026: 2976000; FY 2027: 2976000
U-5805 | Highway | STI (Prioritization) | SR 1009 (Monroe Road) | Rama Road / Idlewild Road intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | T(M) | CONSTRUCTION | 428000 | FY 2026: 214000; FY 2027: 214000
U-5805 | Highway | STI (Prioritization) | SR 1009 (Monroe Road) | Rama Road / Idlewild Road intersection in Charlotte. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 1060000 | FY 2026: 530000; FY 2027: 530000
U-5806 | Highway | STI (Prioritization) | SR 2894 (Concord Mills Boulevard) | Kings Grant Pavilion (Entrance #1) intersection in Concord. | Construct two lane grade separated directional left flyover. | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 10 |  |  |  | 13096000
U-5806 | Highway | STI (Prioritization) | SR 2894 (Concord Mills Boulevard) | Kings Grant Pavilion (Entrance #1) intersection in Concord. | Construct two lane grade separated directional left flyover. | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 10 |  | T | ENGINEERING | 1755000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000
U-5806 | Highway | STI (Prioritization) | SR 2894 (Concord Mills Boulevard) | Kings Grant Pavilion (Entrance #1) intersection in Concord. | Construct two lane grade separated directional left flyover. | 1 | Cabarrus | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 10 |  | T | BUILD NC CON | 10380000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000
U-5808 | Highway | STI (Prioritization) | SR 1362 (Chestnut Lane Connector) | SR 1367 (Matthews Indian Trail Road) to SR 1368 (Gribble Road) in Indian Trail. | Construct road on new location. | 0.39 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025); | Division 10 |  |  |  | 1185000
U-5808 | Highway | STI (Prioritization) | SR 1362 (Chestnut Lane Connector) | SR 1367 (Matthews Indian Trail Road) to SR 1368 (Gribble Road) in Indian Trail. | Construct road on new location. | 0.39 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025); | Division 10 |  | T | RIGHT-OF-WAY | 1615000
U-5808 | Highway | STI (Prioritization) | SR 1362 (Chestnut Lane Connector) | SR 1367 (Matthews Indian Trail Road) to SR 1368 (Gribble Road) in Indian Trail. | Construct road on new location. | 0.39 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025); | Division 10 |  | T | UTILITIES | 1200000
U-5808 | Highway | STI (Prioritization) | SR 1362 (Chestnut Lane Connector) | SR 1367 (Matthews Indian Trail Road) to SR 1368 (Gribble Road) in Indian Trail. | Construct road on new location. | 0.39 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025); | Division 10 |  | T | BUILD NC CON | 7980000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 2128000
U-5808 | Highway | STI (Prioritization) | SR 1362 (Chestnut Lane Connector) | SR 1367 (Matthews Indian Trail Road) to SR 1368 (Gribble Road) in Indian Trail. | Construct road on new location. | 0.39 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025); | Division 10 |  | T | CONSTRUCTION | 12061000 | FY 2026: 3049000; FY 2027: 1413000
U-5809 | Highway | STI (Prioritization) | US 601 (State Street) | SR 1742 (Sharon Drive) to SR 1146 (Lee Avenue) | Construct median and roundabouts. | 0.68 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  |  |  | 0
U-5809 | Highway | STI (Prioritization) | US 601 (State Street) | SR 1742 (Sharon Drive) to SR 1146 (Lee Avenue) | Construct median and roundabouts. | 0.68 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  | T | RIGHT-OF-WAY | 1700000
U-5809 | Highway | STI (Prioritization) | US 601 (State Street) | SR 1742 (Sharon Drive) to SR 1146 (Lee Avenue) | Construct median and roundabouts. | 0.68 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  | T | UTILITIES | 800000
U-5809 | Highway | STI (Prioritization) | US 601 (State Street) | SR 1742 (Sharon Drive) to SR 1146 (Lee Avenue) | Construct median and roundabouts. | 0.68 | Yadkin | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  | BGLT5 | CONSTRUCTION | 23035000 | FY 2026: 6931000; FY 2027: 4734000
U-5810 | Highway | STI (Prioritization) | SR 1514 (Bamboo Road) / SR 1523 (Wilson Ridge) | US 421 / US 221 to SR 1522 (Deerfield Road). | Modernize roadway. | 1.88 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Division 11 |  |  |  | 883000
U-5810 | Highway | STI (Prioritization) | SR 1514 (Bamboo Road) / SR 1523 (Wilson Ridge) | US 421 / US 221 to SR 1522 (Deerfield Road). | Modernize roadway. | 1.88 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Division 11 |  | T | BUILD NC ROW | 4500000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
U-5810 | Highway | STI (Prioritization) | SR 1514 (Bamboo Road) / SR 1523 (Wilson Ridge) | US 421 / US 221 to SR 1522 (Deerfield Road). | Modernize roadway. | 1.88 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Division 11 |  | T | RIGHT-OF-WAY | 14900000
U-5810 | Highway | STI (Prioritization) | SR 1514 (Bamboo Road) / SR 1523 (Wilson Ridge) | US 421 / US 221 to SR 1522 (Deerfield Road). | Modernize roadway. | 1.88 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Division 11 |  | T | UTILITIES | 1300000
U-5810 | Highway | STI (Prioritization) | SR 1514 (Bamboo Road) / SR 1523 (Wilson Ridge) | US 421 / US 221 to SR 1522 (Deerfield Road). | Modernize roadway. | 1.88 | Watauga | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Division 11 |  | BG5T50 | CONSTRUCTION | 42400000 | FY 2026: 424000; FY 2027: 13144000; FY 2028: 11448000; FY 2029: 9752000; FY 2030: 7632000
U-5811 | Highway | STI (Prioritization) | SR 1002 (Aviation Parkway) | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  |  |  | 2000000
U-5811 | Highway | STI (Prioritization) | SR 1002 (Aviation Parkway) | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | BUILD NC ROW | 7800000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 2600000
U-5811 | Highway | STI (Prioritization) | SR 1002 (Aviation Parkway) | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | RIGHT-OF-WAY | 7000000 | FY 2026: 0; FY 2027: 0; FY 2028: 760000; FY 2029: 3380000; FY 2030: 2860000
U-5811 | Highway | STI (Prioritization) | SR 1002 (Aviation Parkway) | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | UTILITIES | 2100000 | FY 2026: 1050000; FY 2027: 1050000
U-5811 | Highway | STI (Prioritization) | SR 1002 (Aviation Parkway) | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | BUILD NC CON | 16905000 |  |  |  |  | 1127000 | 1127000 | 1127000 | 1127000 | 1127000 | 1127000 | 7889000
U-5811 | Highway | STI (Prioritization) | SR 1002 (Aviation Parkway) | NC 54 to I-40 in Morrisville. | Widen to multi-lanes. | 2.45 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | CONSTRUCTION | 29200000 | FY 2030: 0; FY 2031: 13164000; FY 2032: 10128000; FY 2033: 5908000
U-5813 | Highway | STI (Prioritization) | US 64 | Asheboro Bypass to east of I-73 / I-74 / US 220 in Asheboro. | Widen to a four lane divided facility, reconstruct interchange at NC 49, modify interchange at I-73 / I-74 / US 220 and replace bridge 750171 over US 64 and NC 49. | 2.31 | Randolph | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  |  |  | 3000000
U-5813 | Highway | STI (Prioritization) | US 64 | Asheboro Bypass to east of I-73 / I-74 / US 220 in Asheboro. | Widen to a four lane divided facility, reconstruct interchange at NC 49, modify interchange at I-73 / I-74 / US 220 and replace bridge 750171 over US 64 and NC 49. | 2.31 | Randolph | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  | NHP | RIGHT-OF-WAY | 7967000
U-5813 | Highway | STI (Prioritization) | US 64 | Asheboro Bypass to east of I-73 / I-74 / US 220 in Asheboro. | Widen to a four lane divided facility, reconstruct interchange at NC 49, modify interchange at I-73 / I-74 / US 220 and replace bridge 750171 over US 64 and NC 49. | 2.31 | Randolph | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  | NHP | UTILITIES | 3000000
U-5813 | Highway | STI (Prioritization) | US 64 | Asheboro Bypass to east of I-73 / I-74 / US 220 in Asheboro. | Widen to a four lane divided facility, reconstruct interchange at NC 49, modify interchange at I-73 / I-74 / US 220 and replace bridge 750171 over US 64 and NC 49. | 2.31 | Randolph | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  | NHP | CONSTRUCTION | 68441000 | FY 2026: 18498000; FY 2027: 13907000; FY 2028: 10781000
U-5814 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | US 1 (Sandhills Boulevard) in Aberdeen to Brucewood Road in Southern Pines. | Improve access management. | 1.24 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING. | Region E |  |  |  | 3750000
U-5814 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | US 1 (Sandhills Boulevard) in Aberdeen to Brucewood Road in Southern Pines. | Improve access management. | 1.24 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING. | Region E |  | T | RIGHT-OF-WAY | 11500000
U-5814 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | US 1 (Sandhills Boulevard) in Aberdeen to Brucewood Road in Southern Pines. | Improve access management. | 1.24 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING. | Region E |  | T | UTILITIES | 1250000
U-5815 | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | SR 1112 (Roseland Road) in Aberdeen to old US 1 in Southern Pines. | Improve access management. | 2.9 | Moore | 8 | Sandhills MPO |  | Region E |  |  |  | 4650000
U-5815A | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | SR 1112 (Roseland Road) to Knight Street | Construct access management improvements. | 0.58 | Moore | 8 | Sandhills MPO |  | Region E |  | BGANY | RIGHT-OF-WAY | 4700000 | FY 2029: 470000; FY 2030: 2350000; FY 2031: 940000; FY 2032: 470000; FY 2033: 470000
U-5815A | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | SR 1112 (Roseland Road) to Knight Street | Construct access management improvements. | 0.58 | Moore | 8 | Sandhills MPO |  | Region E |  | BGANY | UTILITIES | 3200000 | FY 2029: 1600000; FY 2030: 1600000
U-5815A | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | SR 1112 (Roseland Road) to Knight Street | Construct access management improvements. | 0.58 | Moore | 8 | Sandhills MPO |  | Region E |  | BGANY | CONSTRUCTION | 12700000 | FY 2032: 3683000; FY 2033: 5207000; FY 2034: 3429000; FY 2035: 381000
U-5815B | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | Knight Street in Aberdeen to SR 2080 (Old US 1) in Southern Pines, to include SR 1112 (Roseland Road) realignment at US 1 and radii improvement at US 15 / US 501 / NC 211 | Construct access management improvements, realignment, and radii improvements. | 2.36 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION INCLUDES U-5814. | Region E |  | T | RIGHT-OF-WAY | 6650000
U-5815B | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | Knight Street in Aberdeen to SR 2080 (Old US 1) in Southern Pines, to include SR 1112 (Roseland Road) realignment at US 1 and radii improvement at US 15 / US 501 / NC 211 | Construct access management improvements, realignment, and radii improvements. | 2.36 | Moore | 8 | Sandhills MPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION INCLUDES U-5814. | Region E |  | T | CONSTRUCTION | 154300000 | FY 2026: 43204000; FY 2027: 38575000; FY 2028: 29317000; FY 2029: 24688000
U-5815BA | Highway | STI (Prioritization) | US 1 (Sandhills Boulevard) | Knight Street in Aberdeen to SR 2080 (Old US 1) in Southern Pines | Relocate water transmission line. | 2.36 | Moore | 8 | Sandhills MPO | UNDER CONSTRUCTION | Region E |  | T | CONSTRUCTION | 17900000
U-5816 | Highway | STI (Prioritization) | SR 1305 (Oates Road / Midnight Lane) | US 21 (Charlotte Highway) to SR 1474 (Bluefield Road) in Mooresville. | Widen to three lanes with overpass over I-77. | 1.56 | Iredell | 12 | Charlotte Regional TPO | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  |  |  | 500000
U-5816 | Highway | STI (Prioritization) | SR 1305 (Oates Road / Midnight Lane) | US 21 (Charlotte Highway) to SR 1474 (Bluefield Road) in Mooresville. | Widen to three lanes with overpass over I-77. | 1.56 | Iredell | 12 | Charlotte Regional TPO | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | T | RIGHT-OF-WAY | 22800000 | FY 2026: 1824000; FY 2027: 5472000; FY 2028: 5700000; FY 2029: 5244000; FY 2030: 4560000
U-5816 | Highway | STI (Prioritization) | SR 1305 (Oates Road / Midnight Lane) | US 21 (Charlotte Highway) to SR 1474 (Bluefield Road) in Mooresville. | Widen to three lanes with overpass over I-77. | 1.56 | Iredell | 12 | Charlotte Regional TPO | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | T | UTILITIES | 3200000 | FY 2026: 1600000; FY 2027: 1600000
U-5816 | Highway | STI (Prioritization) | SR 1305 (Oates Road / Midnight Lane) | US 21 (Charlotte Highway) to SR 1474 (Bluefield Road) in Mooresville. | Widen to three lanes with overpass over I-77. | 1.56 | Iredell | 12 | Charlotte Regional TPO | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | T | BUILD NC CON | 20805000 |  |  |  |  | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 12483000
U-5816 | Highway | STI (Prioritization) | SR 1305 (Oates Road / Midnight Lane) | US 21 (Charlotte Highway) to SR 1474 (Bluefield Road) in Mooresville. | Widen to three lanes with overpass over I-77. | 1.56 | Iredell | 12 | Charlotte Regional TPO | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 12 |  | T | CONSTRUCTION | 32000000 | FY 2029: 480000; FY 2030: 0; FY 2031: 11840000; FY 2032: 11040000; FY 2033: 8640000
U-5817 | Highway | STI (Prioritization) | SR 1246 (Fairview Road) | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  |  |  | 4853000
U-5817 | Highway | STI (Prioritization) | SR 1246 (Fairview Road) | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGANY | RIGHT-OF-WAY | 672000
U-5817 | Highway | STI (Prioritization) | SR 1246 (Fairview Road) | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGDA | RIGHT-OF-WAY | 2403000
U-5817 | Highway | STI (Prioritization) | SR 1246 (Fairview Road) | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BA | RIGHT-OF-WAY | 2725000
U-5817 | Highway | STI (Prioritization) | SR 1246 (Fairview Road) | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGANY | UTILITIES | 1900000
U-5817 | Highway | STI (Prioritization) | SR 1246 (Fairview Road) | Existing SR 1246 (Fairview Road) to SR 1206 (Alcove Road). | Extend roadway over I-77 and construct parallel north-south connector roads to SR 1109 (Williamson Road). | 0.11 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGANY | CONSTRUCTION | 25200000 | FY 2027: 252000; FY 2028: 7812000; FY 2029: 7308000; FY 2030: 5544000; FY 2031: 4284000
U-5818 | Highway | STI (Prioritization) | SR 1001 (Sugar Hill Road) | I-40 westbound ramps to 0.3 mile west of I-40 eastbound ramps in Marion. | Widen roadway. | 0.36 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $55,995 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  |  |  | 2536000
U-5818 | Highway | STI (Prioritization) | SR 1001 (Sugar Hill Road) | I-40 westbound ramps to 0.3 mile west of I-40 eastbound ramps in Marion. | Widen roadway. | 0.36 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $55,995 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | ENGINEERING | 1710000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 114000 | 10000
U-5818 | Highway | STI (Prioritization) | SR 1001 (Sugar Hill Road) | I-40 westbound ramps to 0.3 mile west of I-40 eastbound ramps in Marion. | Widen roadway. | 0.36 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $55,995 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC ROW | 75000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
U-5818 | Highway | STI (Prioritization) | SR 1001 (Sugar Hill Road) | I-40 westbound ramps to 0.3 mile west of I-40 eastbound ramps in Marion. | Widen roadway. | 0.36 | McDowell | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $55,995 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 13230000 | 882000 | 882000 | 882000 | 882000 | 882000 | 882000 | 882000 | 882000 | 882000 | 515000
U-5819 | Highway | STI (Prioritization) | NC 27 (West Charlotte Avenue) | SR 2534 (Hawthorne Street) intersection in Mount Holly. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 200000
U-5819 | Highway | STI (Prioritization) | NC 27 (West Charlotte Avenue) | SR 2534 (Hawthorne Street) intersection in Mount Holly. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1800000
U-5819 | Highway | STI (Prioritization) | NC 27 (West Charlotte Avenue) | SR 2534 (Hawthorne Street) intersection in Mount Holly. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 600000
U-5819 | Highway | STI (Prioritization) | NC 27 (West Charlotte Avenue) | SR 2534 (Hawthorne Street) intersection in Mount Holly. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5200000
U-5820 | Highway | STI (Prioritization) | New Route | SR 2576 (Bendix Drive) to US 52 (East Innes Street) at Newsome Road in Salisbury. | Construct a new multi-lane roadway. | 0.6 | Rowan | 9 | Cabarrus-Rowan MPO | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY |  |  |  |  | 5151000
U-5820A | Highway | STI (Prioritization) | New Route | SR 2576 (Bendix Drive) to SR 1006 (Faith Road) | Construct multi-lane roadway on new location. | 0.42 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | BUILD NC CON | 2609000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000
U-5820B | Highway | STI (Prioritization) | New Route | SR 1006 (Faith Road) to US 52 (East Innes Street) | Construct multi-lane roadway on new location. | 0.1 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | T | CONSTRUCTION | 1100000
U-5821 | Highway | STI (Prioritization) | NC 279 (New Hope Road) | SR 2478 (Titman Road) to SR 2435 (Union-New Hope Road) in Gastonia. | Widen to four lanes. | 0 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  |  |  | 1300000
U-5821 | Highway | STI (Prioritization) | NC 279 (New Hope Road) | SR 2478 (Titman Road) to SR 2435 (Union-New Hope Road) in Gastonia. | Widen to four lanes. | 0 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | RIGHT-OF-WAY | 51200000 | FY 2026: 10341000; FY 2027: 10341000
U-5821 | Highway | STI (Prioritization) | NC 279 (New Hope Road) | SR 2478 (Titman Road) to SR 2435 (Union-New Hope Road) in Gastonia. | Widen to four lanes. | 0 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | UTILITIES | 17000000 | FY 2026: 5667000; FY 2027: 5667000; FY 2028: 5666000
U-5821 | Highway | STI (Prioritization) | NC 279 (New Hope Road) | SR 2478 (Titman Road) to SR 2435 (Union-New Hope Road) in Gastonia. | Widen to four lanes. | 0 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | CONSTRUCTION | 109800000 | FY 2028: 21960000; FY 2029: 25254000; FY 2030: 24156000; FY 2031: 20862000; FY 2032: 17568000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  |  |  | 595000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | BGANY | RIGHT-OF-WAY | 1120000 | FY 2026: 1120000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | L(M) | RIGHT-OF-WAY | 280000 | FY 2026: 280000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | BGANY | UTILITIES | 1440000 | FY 2026: 1440000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | L(M) | UTILITIES | 360000 | FY 2026: 360000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | BGANY | CONSTRUCTION | 4800000 | FY 2027: 3312000; FY 2028: 1488000
U-5823 | Highway | STI (Prioritization) | Woodcroft Parkway Extension | SR 1116 (Garrett Road) to NC 751 (Hope Valley Road) in Durham. | Construct roadway on new alignment. | 0.24 | Durham | 5 | Triangle West TPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | L(M) | CONSTRUCTION | 1200000 | FY 2027: 828000; FY 2028: 372000
U-5824 | Highway | STI (Prioritization) | NC 66 (Old Hollow Road) | Harley Drive to US 158 in Walkertown. | Widen to a multi-lane divided facility. | 1.61 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  |  |  | 5399000
U-5824 | Highway | STI (Prioritization) | NC 66 (Old Hollow Road) | Harley Drive to US 158 in Walkertown. | Widen to a multi-lane divided facility. | 1.61 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | RIGHT-OF-WAY | 18798000
U-5824 | Highway | STI (Prioritization) | NC 66 (Old Hollow Road) | Harley Drive to US 158 in Walkertown. | Widen to a multi-lane divided facility. | 1.61 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | BUILD NC CON | 13305000 | 887000 | 887000 | 887000 | 887000 | 887000 | 887000 | 887000 | 887000 | 887000 | 887000 | 3548000
U-5824 | Highway | STI (Prioritization) | NC 66 (Old Hollow Road) | Harley Drive to US 158 in Walkertown. | Widen to a multi-lane divided facility. | 1.61 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) | Division 9 |  | T | CONSTRUCTION | 9900000 | FY 2026: 4328000; FY 2027: 1990000
U-5825 | Highway | STI (Prioritization) | SR 1010 (Ten-Ten Road) | Apex Peakway in Apex to SR 1300 (Kildaire Farm Road) in Cary. | Widen to multi-lanes. | 3.3 | Wake | 5 | Capital Area MPO | COORDINATE WITH U-6066 |  |  |  |  | 3000000
U-5825A | Highway | STI (Prioritization) | SR 1010 (Ten Ten Road) | Apex Peakwy to to SR 1306 (Schieffelin Road). | Widen to four lanes with reduced conflict intersections. |  | Wake | 5 | Capital Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000000 | [10 empty] | 10000000
U-5825A | Highway | STI (Prioritization) | SR 1010 (Ten Ten Road) | Apex Peakwy to to SR 1306 (Schieffelin Road). | Widen to four lanes with reduced conflict intersections. |  | Wake | 5 | Capital Area MPO |  | Not Funded |  | T | UTILITIES | 3300000 | [10 empty] | 3300000
U-5825A | Highway | STI (Prioritization) | SR 1010 (Ten Ten Road) | Apex Peakwy to to SR 1306 (Schieffelin Road). | Widen to four lanes with reduced conflict intersections. |  | Wake | 5 | Capital Area MPO |  | Not Funded |  | T | CONSTRUCTION | 22000000 | [10 empty] | 22000000
U-5825B | Highway | STI (Prioritization) | US 1 | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 30300000 | FY 2027: 3030000; FY 2028: 10605000; FY 2029: 10605000; FY 2030: 3030000; FY 2031: 3030000
U-5825B | Highway | STI (Prioritization) | US 1 | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 2300000 | FY 2027: 767000; FY 2028: 767000; FY 2029: 766000
U-5825B | Highway | STI (Prioritization) | US 1 | SR 1010 (Ten Ten Road) interchange. | Reconstruct interchange. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 66900000 | FY 2030: 16725000; FY 2031: 23415000; FY 2032: 16725000; FY 2033: 10035000
U-5825C | Highway | STI (Prioritization) | SR 1010 (Ten Ten Road) | SR 4070 (Reliance Avenue) to SR 1300 (Kildaire Farm Road). | Widen to four lanes with reduced conflict intersections. |  | Wake | 5 | Capital Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 11500000 | [10 empty] | 11500000
U-5825C | Highway | STI (Prioritization) | SR 1010 (Ten Ten Road) | SR 4070 (Reliance Avenue) to SR 1300 (Kildaire Farm Road). | Widen to four lanes with reduced conflict intersections. |  | Wake | 5 | Capital Area MPO |  | Not Funded |  | T | UTILITIES | 3300000 | [10 empty] | 3300000
U-5825C | Highway | STI (Prioritization) | SR 1010 (Ten Ten Road) | SR 4070 (Reliance Avenue) to SR 1300 (Kildaire Farm Road). | Widen to four lanes with reduced conflict intersections. |  | Wake | 5 | Capital Area MPO |  | Not Funded |  | T | CONSTRUCTION | 59500000 | [10 empty] | 59500000
U-5826 | Highway | STI (Prioritization) | SR 2000 (Falls Of Neuse Road) | I-540 to SR 2006 (Durant Road). | Construct additional lanes. | 0.89 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 5 |  |  |  | 1000000
U-5826 | Highway | STI (Prioritization) | SR 2000 (Falls Of Neuse Road) | I-540 to SR 2006 (Durant Road). | Construct additional lanes. | 0.89 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 5 |  | T | RIGHT-OF-WAY | 280000
U-5826 | Highway | STI (Prioritization) | SR 2000 (Falls Of Neuse Road) | I-540 to SR 2006 (Durant Road). | Construct additional lanes. | 0.89 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 5 |  | T | BUILD NC CON | 5325000 | 355000 | 355000 | 355000 | 355000 | 355000 | 355000 | 355000 | 355000 | 355000 | 355000 | 1420000
U-5826 | Highway | STI (Prioritization) | SR 2000 (Falls Of Neuse Road) | I-540 to SR 2006 (Durant Road). | Construct additional lanes. | 0.89 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 5 |  | T | CONSTRUCTION | 25000000
U-5827 | Highway | STI (Prioritization) | SR 1632 (Louis Stephens Drive) | Poplar Pike Lane in Morrisville to SR 2153 (Little Drive) in Research Triangle Park. | Construct roadway on new location. | 0.55 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  |  |  | 54000
U-5827 | Highway | STI (Prioritization) | SR 1632 (Louis Stephens Drive) | Poplar Pike Lane in Morrisville to SR 2153 (Little Drive) in Research Triangle Park. | Construct roadway on new location. | 0.55 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | ENGINEERING | 1231000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 1000 | 2000
U-5827 | Highway | STI (Prioritization) | SR 1632 (Louis Stephens Drive) | Poplar Pike Lane in Morrisville to SR 2153 (Little Drive) in Research Triangle Park. | Construct roadway on new location. | 0.55 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | BUILD NC ROW | 1340000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 94000
U-5827 | Highway | STI (Prioritization) | SR 1632 (Louis Stephens Drive) | Poplar Pike Lane in Morrisville to SR 2153 (Little Drive) in Research Triangle Park. | Construct roadway on new location. | 0.55 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | BUILD NC CON | 6987000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 83000
U-5827 | Highway | STI (Prioritization) | SR 1632 (Louis Stephens Drive) | Poplar Pike Lane in Morrisville to SR 2153 (Little Drive) in Research Triangle Park. | Construct roadway on new location. | 0.55 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | CONSTRUCTION | 712000
U-5828 | Highway | STI (Prioritization) | McCrimmon Parkway | SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway) in Morrisville. | Widen to a four lane divided facility, part on new location. | 1.42 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 5 |  |  |  | 10935000
U-5828 | Highway | STI (Prioritization) | McCrimmon Parkway | SR 3015 (Airport Boulevard) to SR 1002 (Aviation Parkway) in Morrisville. | Widen to a four lane divided facility, part on new location. | 1.42 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 5 |  | T | BUILD NC CON | 3097000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 213000
U-5832 | Highway | STI (Prioritization) | NC 81 (Swannanoa River Road) | SR 3214 (Biltmore Avenue) to US 74A (South Tunnel Road) in Asheville. | Widen existing roadway. | 1.62 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5832 | Highway | STI (Prioritization) | NC 81 (Swannanoa River Road) | SR 3214 (Biltmore Avenue) to US 74A (South Tunnel Road) in Asheville. | Widen existing roadway. | 1.62 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 50000000
U-5832 | Highway | STI (Prioritization) | NC 81 (Swannanoa River Road) | SR 3214 (Biltmore Avenue) to US 74A (South Tunnel Road) in Asheville. | Widen existing roadway. | 1.62 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 930000
U-5832 | Highway | STI (Prioritization) | NC 81 (Swannanoa River Road) | SR 3214 (Biltmore Avenue) to US 74A (South Tunnel Road) in Asheville. | Widen existing roadway. | 1.62 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 73200000
U-5833 | Highway | STI (Prioritization) | SR 2241 (Oak Street) | SR 2159 (Pine Ridge Road) to US 74 in Forest City. | Widen existing roadway. | 0.64 | Rutherford | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $347,260 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  |  |  | 3114000
U-5833 | Highway | STI (Prioritization) | SR 2241 (Oak Street) | SR 2159 (Pine Ridge Road) to US 74 in Forest City. | Widen existing roadway. | 0.64 | Rutherford | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $347,260 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | ENGINEERING | 1050000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 5000
U-5833 | Highway | STI (Prioritization) | SR 2241 (Oak Street) | SR 2159 (Pine Ridge Road) to US 74 in Forest City. | Widen existing roadway. | 0.64 | Rutherford | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $347,260 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC ROW | 450000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
U-5833 | Highway | STI (Prioritization) | SR 2241 (Oak Street) | SR 2159 (Pine Ridge Road) to US 74 in Forest City. | Widen existing roadway. | 0.64 | Rutherford | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $347,260 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 7530000 | 502000 | 502000 | 502000 | 502000 | 502000 | 502000 | 502000 | 502000 | 502000 | 315000
U-5834 | Highway | STI (Prioritization) | SR 3116 (Mills Gap Road) | US 25 (Hendersonville Road) to SR 3157 (Weston Road) in Asheville. | Upgrade roadway. | 1.91 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  |  |  | 6844000
U-5834 | Highway | STI (Prioritization) | SR 3116 (Mills Gap Road) | US 25 (Hendersonville Road) to SR 3157 (Weston Road) in Asheville. | Upgrade roadway. | 1.91 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | T | RIGHT-OF-WAY | 12333000
U-5834 | Highway | STI (Prioritization) | SR 3116 (Mills Gap Road) | US 25 (Hendersonville Road) to SR 3157 (Weston Road) in Asheville. | Upgrade roadway. | 1.91 | Buncombe | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGANY | CONSTRUCTION | 37600000 | FY 2026: 376000; FY 2027: 15040000; FY 2028: 13160000; FY 2029: 9024000
U-5835 | Highway | STI (Prioritization) | US 221 Business | US 221 / NC 226 to Georgia Avenue in Marion. | Widen existing roadway. | 1.48 | McDowell | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  |  |  | 415000
U-5835 | Highway | STI (Prioritization) | US 221 Business | US 221 / NC 226 to Georgia Avenue in Marion. | Widen existing roadway. | 1.48 | McDowell | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BG5T50 | RIGHT-OF-WAY | 6600000
U-5835 | Highway | STI (Prioritization) | US 221 Business | US 221 / NC 226 to Georgia Avenue in Marion. | Widen existing roadway. | 1.48 | McDowell | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BG5T50 | UTILITIES | 2000000
U-5835 | Highway | STI (Prioritization) | US 221 Business | US 221 / NC 226 to Georgia Avenue in Marion. | Widen existing roadway. | 1.48 | McDowell | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BG5T50 | CONSTRUCTION | 26300000 | FY 2031: 6575000; FY 2032: 7890000; FY 2033: 6575000; FY 2034: 4734000; FY 2035: 526000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (St Mary's Church Road) to Morganton ETJ in Morganton. | Widen existing roadway. | 0.92 | Burke | 13 | Greater Hickory MPO | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Region G |  |  |  | 3571000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (St Mary's Church Road) to Morganton ETJ in Morganton. | Widen existing roadway. | 0.92 | Burke | 13 | Greater Hickory MPO | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Region G |  | T | RIGHT-OF-WAY | 3000000 | FY 2027: 480000; FY 2028: 960000; FY 2029: 960000; FY 2030: 300000; FY 2031: 300000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (St Mary's Church Road) to Morganton ETJ in Morganton. | Widen existing roadway. | 0.92 | Burke | 13 | Greater Hickory MPO | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Region G |  | T | UTILITIES | 2000000 | FY 2027: 1000000; FY 2028: 1000000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (St Mary's Church Road) to Morganton ETJ in Morganton. | Widen existing roadway. | 0.92 | Burke | 13 | Greater Hickory MPO | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Region G |  | T | BUILD NC CON | 4290000 |  |  |  |  | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 2574000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (St Mary's Church Road) to Morganton ETJ in Morganton. | Widen existing roadway. | 0.92 | Burke | 13 | Greater Hickory MPO | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Region G |  | T | CONSTRUCTION | 9900000 | FY 2030: 0; FY 2031: 2112000; FY 2032: 4620000; FY 2033: 3168000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  |  |  | 2743000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  | T | ENGINEERING | 3330000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  | T | BUILD NC ROW | 2790000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  | T | RIGHT-OF-WAY | 4040000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  | T | UTILITIES | 750000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  | T | BUILD NC CON | 23535000 | 1569000 | 1569000 | 1569000 | 3138000 | 1569000 | 1569000 | 1569000 | 1569000 | 1569000 | 1569000 | 4707000
U-5839 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 to US 23 Business (Main Street) in Waynesville. | Upgrade roadway. | 1.06 | Haywood | 14 | French Broad River MPO | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888. | Division 14 |  | T | CONSTRUCTION | 31592000 | FY 2026: 11408000; FY 2027: 10533000; FY 2028: 4932000
U-5840 | Highway | STI (Prioritization) | SR 1547 (Old Airport Road) | US 25 to Mills Gap Road in Fletcher. | Widen existing roadway. | 0.89 | Henderson | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  |  |  | 5430000
U-5840 | Highway | STI (Prioritization) | SR 1547 (Old Airport Road) | US 25 to Mills Gap Road in Fletcher. | Widen existing roadway. | 0.89 | Henderson | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | ENGINEERING | 1575000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
U-5840 | Highway | STI (Prioritization) | SR 1547 (Old Airport Road) | US 25 to Mills Gap Road in Fletcher. | Widen existing roadway. | 0.89 | Henderson | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | BUILD NC ROW | 855000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000
U-5840 | Highway | STI (Prioritization) | SR 1547 (Old Airport Road) | US 25 to Mills Gap Road in Fletcher. | Widen existing roadway. | 0.89 | Henderson | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | BUILD NC CON | 12150000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 307000
U-5841 | Highway | STI (Prioritization) | Friendly Avenue | West of Green Valley Road to Lindell Road in Greensboro. | Widen roadway and construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 1050000
U-5841 | Highway | STI (Prioritization) | Friendly Avenue | West of Green Valley Road to Lindell Road in Greensboro. | Widen roadway and construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T | CONSTRUCTION | 1400000 | FY 2026: 784000; FY 2027: 616000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  |  |  | 100000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | ENGINEERING | 600000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L(M) | ENGINEERING | 150000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | RIGHT-OF-WAY | 1440000 | FY 2028: 1440000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L(M) | RIGHT-OF-WAY | 360000 | FY 2028: 360000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | UTILITIES | 8000 | FY 2028: 8000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L(M) | UTILITIES | 2000 | FY 2028: 2000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | CONSTRUCTION | 5119000 | FY 2031: 51000; FY 2032: 3686000; FY 2033: 1382000
U-5842 | Highway | STI (Prioritization) | Pisgah Church Road | North Elm Street intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L(M) | CONSTRUCTION | 1281000 | FY 2031: 13000; FY 2032: 922000; FY 2033: 346000
U-5843 | Highway | STI (Prioritization) | US 70 (North Church Street) | SR 1817 (Graham-Hopedale Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  |  |  | 1032000
U-5843 | Highway | STI (Prioritization) | US 70 (North Church Street) | SR 1817 (Graham-Hopedale Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | ENGINEERING | 810000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000
U-5843 | Highway | STI (Prioritization) | US 70 (North Church Street) | SR 1817 (Graham-Hopedale Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 2167000 | 155000 | 155000 | 155000 | 56000 | 155000 | 155000 | 155000 | 155000 | 99000 | 96000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (Ramada Road) to US 70 (Church Street) in Burlington. | Widen to a three lane facility. | 1.13 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Division 7 |  |  |  | 1750000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (Ramada Road) to US 70 (Church Street) in Burlington. | Widen to a three lane facility. | 1.13 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Division 7 |  | T | RIGHT-OF-WAY | 13300000 | FY 2026: 1330000; FY 2027: 1330000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (Ramada Road) to US 70 (Church Street) in Burlington. | Widen to a three lane facility. | 1.13 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Division 7 |  | T | UTILITIES | 2600000 | FY 2026: 1300000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (Ramada Road) to US 70 (Church Street) in Burlington. | Widen to a three lane facility. | 1.13 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Division 7 |  | T | BUILD NC CON | 10395000 |  |  | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 693000 | 4851000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (Ramada Road) to US 70 (Church Street) in Burlington. | Widen to a three lane facility. | 1.13 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE) | Division 7 |  | T | CONSTRUCTION | 13000000 | FY 2027: 2478000; FY 2028: 2264000; FY 2029: 5719000; FY 2030: 2539000
U-5845 | Highway | STI (Prioritization) | SR 1009 (South Churton Street) | I-40 to Eno River in Hillsborough. | Widen to multi-lanes. | 2.22 | Orange | 7 | Triangle West TPO | COMBINED LET WITH I-0305B | Division 7 |  |  |  | 2500000
U-5845 | Highway | STI (Prioritization) | SR 1009 (South Churton Street) | I-40 to Eno River in Hillsborough. | Widen to multi-lanes. | 2.22 | Orange | 7 | Triangle West TPO | COMBINED LET WITH I-0305B | Division 7 |  | T | RIGHT-OF-WAY | 19700000 | FY 2030: 4137000; FY 2031: 5713000; FY 2032: 5516000; FY 2033: 394000; FY 2034: 3940000
U-5845 | Highway | STI (Prioritization) | SR 1009 (South Churton Street) | I-40 to Eno River in Hillsborough. | Widen to multi-lanes. | 2.22 | Orange | 7 | Triangle West TPO | COMBINED LET WITH I-0305B | Division 7 |  | T | UTILITIES | 7200000 | FY 2030: 3600000; FY 2031: 3600000
U-5845 | Highway | STI (Prioritization) | SR 1009 (South Churton Street) | I-40 to Eno River in Hillsborough. | Widen to multi-lanes. | 2.22 | Orange | 7 | Triangle West TPO | COMBINED LET WITH I-0305B | Division 7 |  | T | CONSTRUCTION | 50500000 | FY 2034: 13635000; FY 2035: 15150000 | 21715000
U-5846 | Highway | STI (Prioritization) | SR 1772 (Greensboro Street) | SR 1780 (Estes Drive) intersection in Carrboro. | Construct roundabout. |  | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 3185000
U-5850 | Highway | STI (Prioritization) | SR 1007 (Randleman Road) | Elmsley Drive to Glendale Drive in Greensboro. | Widen to multi-lanes. | 0.36 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 830000
U-5850 | Highway | STI (Prioritization) | SR 1007 (Randleman Road) | Elmsley Drive to Glendale Drive in Greensboro. | Widen to multi-lanes. | 0.36 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 600000
U-5850 | Highway | STI (Prioritization) | SR 1007 (Randleman Road) | Elmsley Drive to Glendale Drive in Greensboro. | Widen to multi-lanes. | 0.36 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 400000
U-5850 | Highway | STI (Prioritization) | SR 1007 (Randleman Road) | Elmsley Drive to Glendale Drive in Greensboro. | Widen to multi-lanes. | 0.36 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 4300000 | FY 2026: 2881000; FY 2027: 1419000
U-5851 | Highway | STI (Prioritization) | SR 1001 (Church Street) | US 220 (Wendover Avenue) to east Cone Boulevard in Greensboro. | Construct additional lanes. | 1.65 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 650000
U-5851 | Highway | STI (Prioritization) | SR 1001 (Church Street) | US 220 (Wendover Avenue) to east Cone Boulevard in Greensboro. | Construct additional lanes. | 1.65 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 83700000
U-5851 | Highway | STI (Prioritization) | SR 1001 (Church Street) | US 220 (Wendover Avenue) to east Cone Boulevard in Greensboro. | Construct additional lanes. | 1.65 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 6400000
U-5851 | Highway | STI (Prioritization) | SR 1001 (Church Street) | US 220 (Wendover Avenue) to east Cone Boulevard in Greensboro. | Construct additional lanes. | 1.65 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 18900000
U-5857 | Highway | STI (Prioritization) | SR 1406 (Rockfish Road); New Route (Gillis Hill Road) | SR 1003 (Camden Road) to north of Westfield Drive; North of Westfield Drive to SR 1418 (Lindsay Road). | Widen to multi-lanes, part on new location. | 3.19 | Hoke | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  |  |  | 800000
U-5857 | Highway | STI (Prioritization) | SR 1406 (Rockfish Road); New Route (Gillis Hill Road) | SR 1003 (Camden Road) to north of Westfield Drive; North of Westfield Drive to SR 1418 (Lindsay Road). | Widen to multi-lanes, part on new location. | 3.19 | Hoke | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  | T | RIGHT-OF-WAY | 38200000 | FY 2030: 1910000; FY 2031: 22920000; FY 2032: 5730000; FY 2033: 3820000; FY 2034: 3820000
U-5857 | Highway | STI (Prioritization) | SR 1406 (Rockfish Road); New Route (Gillis Hill Road) | SR 1003 (Camden Road) to north of Westfield Drive; North of Westfield Drive to SR 1418 (Lindsay Road). | Widen to multi-lanes, part on new location. | 3.19 | Hoke | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  | T | UTILITIES | 4600000 | FY 2030: 2300000; FY 2031: 2300000
U-5857 | Highway | STI (Prioritization) | SR 1406 (Rockfish Road); New Route (Gillis Hill Road) | SR 1003 (Camden Road) to north of Westfield Drive; North of Westfield Drive to SR 1418 (Lindsay Road). | Widen to multi-lanes, part on new location. | 3.19 | Hoke | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  | T | CONSTRUCTION | 86400000 | FY 2034: 15552000; FY 2035: 20736000 | 50112000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15th Street) | US 17 Business (Carolina Avenue) to Brown Street. | Widen to multi-lanes. | 1.56 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  |  |  | 914000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15th Street) | US 17 Business (Carolina Avenue) to Brown Street. | Widen to multi-lanes. | 1.56 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 18100000 | FY 2026: 3620000; FY 2027: 5430000; FY 2028: 5430000; FY 2029: 1810000; FY 2030: 1810000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15th Street) | US 17 Business (Carolina Avenue) to Brown Street. | Widen to multi-lanes. | 1.56 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  | T | UTILITIES | 4200000 | FY 2026: 2100000; FY 2027: 2100000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15th Street) | US 17 Business (Carolina Avenue) to Brown Street. | Widen to multi-lanes. | 1.56 | Beaufort | 2 | Mid-East RPO |  | Division 2 |  | T | CONSTRUCTION | 33600000 | FY 2028: 336000; FY 2029: 11088000; FY 2030: 9744000; FY 2031: 7056000; FY 2032: 5376000
U-5862 | Highway | STI (Prioritization) | US 17 (Future I-74; Shallotte Bypass) | SR 1357 (Smith Avenue) intersection in Shallotte | Upgrade intersection to interchange. | 1 | Brunswick | 3 | Grand Strand Area Transportation Study |  | Region B |  |  |  | 1000000
U-5862 | Highway | STI (Prioritization) | US 17 (Future I-74; Shallotte Bypass) | SR 1357 (Smith Avenue) intersection in Shallotte | Upgrade intersection to interchange. | 1 | Brunswick | 3 | Grand Strand Area Transportation Study |  | Region B |  | T | RIGHT-OF-WAY | 8500000 | FY 2028: 1615000; FY 2029: 2720000; FY 2030: 2465000; FY 2031: 850000; FY 2032: 850000
U-5862 | Highway | STI (Prioritization) | US 17 (Future I-74; Shallotte Bypass) | SR 1357 (Smith Avenue) intersection in Shallotte | Upgrade intersection to interchange. | 1 | Brunswick | 3 | Grand Strand Area Transportation Study |  | Region B |  | T | UTILITIES | 1900000 | FY 2028: 950000; FY 2029: 950000
U-5862 | Highway | STI (Prioritization) | US 17 (Future I-74; Shallotte Bypass) | SR 1357 (Smith Avenue) intersection in Shallotte | Upgrade intersection to interchange. | 1 | Brunswick | 3 | Grand Strand Area Transportation Study |  | Region B |  | T | CONSTRUCTION | 43600000 | FY 2031: 436000; FY 2032: 13516000; FY 2033: 12208000; FY 2034: 10028000; FY 2035: 7412000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (Surrett Drive) | I-85 in Trinity to SR 1300 (West Fairfield Road) in High Point. | Widen to multi-lanes. | 3.22 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  |  |  | 3512000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (Surrett Drive) | I-85 in Trinity to SR 1300 (West Fairfield Road) in High Point. | Widen to multi-lanes. | 3.22 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | BGANY | RIGHT-OF-WAY | 28300000 | FY 2029: 3774000; FY 2030: 6468000; FY 2031: 6468000; FY 2032: 5932000; FY 2033: 5658000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (Surrett Drive) | I-85 in Trinity to SR 1300 (West Fairfield Road) in High Point. | Widen to multi-lanes. | 3.22 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | BGANY | UTILITIES | 6700000 | FY 2029: 3350000; FY 2030: 3350000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (Surrett Drive) | I-85 in Trinity to SR 1300 (West Fairfield Road) in High Point. | Widen to multi-lanes. | 3.22 | Randolph, Guilford | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | BGANY | CONSTRUCTION | 44500000 | FY 2033: 4450000; FY 2034: 12460000; FY 2035: 11125000 | 16465000
U-5866 | Highway | STI (Prioritization) | New Route | US 129 (Rodney Orr Bypass) to Robbinsville High School and Middle School in Robbinsville. | Construct new route including bridge over Cheoah River. | 0.31 | Graham | 14 | Southwestern RPO | UNDER CONSTRUCTION | Division 14 |  |  |  | 6284000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(DA) | ENGINEERING | 115000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BA | ENGINEERING | 1174000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | ENGINEERING | 115000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BA | RIGHT-OF-WAY | 2700000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(DA) | RIGHT-OF-WAY | 889000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 665000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | CONSTRUCTION | 4764000 | FY 2026: 2350000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | CRPDA | CONSTRUCTION | 1596000 | FY 2026: 1596000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(M) | CONSTRUCTION | 604000
U-5873 | Highway | Locally Selected | NC 115 | SR 6037 (Potts Street) intersection in Cornelius. | Construct intersection improvements. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L(M) | CONSTRUCTION | 10028000 | FY 2026: 3946000
U-5874 | Highway | Locally Selected | North University Research Park I-85 Overpass | SR 2722 (Louis Rose Place) to Doug Mayes Place. | Construct roadway. | 0.3 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | BGDA | RIGHT-OF-WAY | 1750000
U-5874 | Highway | Locally Selected | North University Research Park I-85 Overpass | SR 2722 (Louis Rose Place) to Doug Mayes Place. | Construct roadway. | 0.3 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | L | RIGHT-OF-WAY | 1750000
U-5874 | Highway | Locally Selected | North University Research Park I-85 Overpass | SR 2722 (Louis Rose Place) to Doug Mayes Place. | Construct roadway. | 0.3 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | BGANY | CONSTRUCTION | 6307000
U-5874 | Highway | Locally Selected | North University Research Park I-85 Overpass | SR 2722 (Louis Rose Place) to Doug Mayes Place. | Construct roadway. | 0.3 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | BGDA | CONSTRUCTION | 9599000
U-5874 | Highway | Locally Selected | North University Research Park I-85 Overpass | SR 2722 (Louis Rose Place) to Doug Mayes Place. | Construct roadway. | 0.3 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | L | CONSTRUCTION | 3977000
U-5875 | Highway | STI (Prioritization) | SR 1203 (Allen Road) | SR 1467 (Stantonsburg Road) to US 13 (Dickinson Avenue Extension). | Widen to four lanes. | 2.33 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 2 |  |  |  | 5063000
U-5875 | Highway | STI (Prioritization) | SR 1203 (Allen Road) | SR 1467 (Stantonsburg Road) to US 13 (Dickinson Avenue Extension). | Widen to four lanes. | 2.33 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 2 |  | T | RIGHT-OF-WAY | 485000
U-5875 | Highway | STI (Prioritization) | SR 1203 (Allen Road) | SR 1467 (Stantonsburg Road) to US 13 (Dickinson Avenue Extension). | Widen to four lanes. | 2.33 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 2 |  | T | UTILITIES | 650000
U-5875 | Highway | STI (Prioritization) | SR 1203 (Allen Road) | SR 1467 (Stantonsburg Road) to US 13 (Dickinson Avenue Extension). | Widen to four lanes. | 2.33 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 2 |  | T | BUILD NC CON | 20805000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 6935000
U-5875 | Highway | STI (Prioritization) | SR 1203 (Allen Road) | SR 1467 (Stantonsburg Road) to US 13 (Dickinson Avenue Extension). | Widen to four lanes. | 2.33 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 2 |  | T | CONSTRUCTION | 47100000 | FY 2026: 0; FY 2027: 11764000; FY 2028: 15144000; FY 2029: 11358000; FY 2030: 8834000
U-5878 | Highway | STI (Prioritization) | Commerce Drive Extension | Commerce Drive to SR 1406 (Piney Green Road). | Construct roadway on new location. | 0.24 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 2225000
U-5878 | Highway | STI (Prioritization) | Commerce Drive Extension | Commerce Drive to SR 1406 (Piney Green Road). | Construct roadway on new location. | 0.24 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 3698000
U-5886 | Highway | STI (Prioritization) | SR 1170 (White Street) | SR 1171 (Willow Road) to US 176 (Spartanburg Highway) in Hendersonville. | Realign and extend roadway. | 0.42 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  |  |  | 1470000
U-5886 | Highway | STI (Prioritization) | SR 1170 (White Street) | SR 1171 (Willow Road) to US 176 (Spartanburg Highway) in Hendersonville. | Realign and extend roadway. | 0.42 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  | T | RIGHT-OF-WAY | 18700000 | FY 2026: 1930000; FY 2027: 3740000
U-5886 | Highway | STI (Prioritization) | SR 1170 (White Street) | SR 1171 (Willow Road) to US 176 (Spartanburg Highway) in Hendersonville. | Realign and extend roadway. | 0.42 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  | T | UTILITIES | 2600000
U-5886 | Highway | STI (Prioritization) | SR 1170 (White Street) | SR 1171 (Willow Road) to US 176 (Spartanburg Highway) in Hendersonville. | Realign and extend roadway. | 0.42 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  | T | CONSTRUCTION | 18200000 | FY 2029: 4004000; FY 2030: 6552000; FY 2031: 4732000; FY 2032: 2912000
U-5887 | Highway | STI (Prioritization) | SR 1783 (Highland Lake Road) | NC 225 to US 176 in Flat Rock. | Upgrade roadway. | 1.07 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 810000
U-5887 | Highway | STI (Prioritization) | SR 1783 (Highland Lake Road) | NC 225 to US 176 in Flat Rock. | Upgrade roadway. | 1.07 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | T | RIGHT-OF-WAY | 2295000
U-5887 | Highway | STI (Prioritization) | SR 1783 (Highland Lake Road) | NC 225 to US 176 in Flat Rock. | Upgrade roadway. | 1.07 | Henderson | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | T | CONSTRUCTION | 7676000
U-5888 | Highway | STI (Prioritization) | US 23 Business (North Main Street) | Walnut Street intersection in Waynesville. | Construct intersection improvements. | 0.5 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH U-5839. | Division 14 |  |  |  | 1411000
U-5888 | Highway | STI (Prioritization) | US 23 Business (North Main Street) | Walnut Street intersection in Waynesville. | Construct intersection improvements. | 0.5 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH U-5839. | Division 14 |  | T | CONSTRUCTION | 8751000
U-5889 | Highway | STI (Prioritization) | SR 1115 (Avent Ferry Road) | SR 1116 (Cass Holt Road) to NC 55 Bypass in Holly Springs. | Widen to multi-lanes, with intersection improvements at SR 1116 (Cass Holt Road), SR 1101 (Piney Grove-Wilbon Road) and NC 55 Bypass. | 1.02 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  |  |  | 10000
U-5889 | Highway | STI (Prioritization) | SR 1115 (Avent Ferry Road) | SR 1116 (Cass Holt Road) to NC 55 Bypass in Holly Springs. | Widen to multi-lanes, with intersection improvements at SR 1116 (Cass Holt Road), SR 1101 (Piney Grove-Wilbon Road) and NC 55 Bypass. | 1.02 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | RIGHT-OF-WAY | 1400000 | FY 2027: 1022000; FY 2028: 98000; FY 2029: 140000; FY 2030: 140000
U-5889 | Highway | STI (Prioritization) | SR 1115 (Avent Ferry Road) | SR 1116 (Cass Holt Road) to NC 55 Bypass in Holly Springs. | Widen to multi-lanes, with intersection improvements at SR 1116 (Cass Holt Road), SR 1101 (Piney Grove-Wilbon Road) and NC 55 Bypass. | 1.02 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | UTILITIES | 500000 | FY 2028: 500000
U-5889 | Highway | STI (Prioritization) | SR 1115 (Avent Ferry Road) | SR 1116 (Cass Holt Road) to NC 55 Bypass in Holly Springs. | Widen to multi-lanes, with intersection improvements at SR 1116 (Cass Holt Road), SR 1101 (Piney Grove-Wilbon Road) and NC 55 Bypass. | 1.02 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | BUILD NC CON | 7155000 |  |  |  |  | 477000 | 477000 | 477000 | 477000 | 477000 | 477000 | 3339000
U-5889 | Highway | STI (Prioritization) | SR 1115 (Avent Ferry Road) | SR 1116 (Cass Holt Road) to NC 55 Bypass in Holly Springs. | Widen to multi-lanes, with intersection improvements at SR 1116 (Cass Holt Road), SR 1101 (Piney Grove-Wilbon Road) and NC 55 Bypass. | 1.02 | Wake | 5 | Capital Area MPO | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Division 5 |  | T | CONSTRUCTION | 10000000 | FY 2029: 2480000; FY 2030: 1120000; FY 2031: 4540000; FY 2032: 1860000
U-5890 | Highway | STI (Prioritization) | SR 1162 (Dabney Drive) | Coble Boulevard to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Vance | 5 | Kerr-Tar RPO | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  |  |  | 1000000
U-5890 | Highway | STI (Prioritization) | SR 1162 (Dabney Drive) | Coble Boulevard to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Vance | 5 | Kerr-Tar RPO | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | BUILD NC ROW | 24045000 |  | 1300000 | 1300000 | 1300000 | 1603000 | 1603000 | 1603000 | 1603000 | 1603000 | 1603000 | 9921000
U-5890 | Highway | STI (Prioritization) | SR 1162 (Dabney Drive) | Coble Boulevard to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Vance | 5 | Kerr-Tar RPO | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | RIGHT-OF-WAY | 17500000 | FY 2027: 0; FY 2028: 12360000; FY 2029: 1440000; FY 2030: 100000; FY 2031: 3600000
U-5890 | Highway | STI (Prioritization) | SR 1162 (Dabney Drive) | Coble Boulevard to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Vance | 5 | Kerr-Tar RPO | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | UTILITIES | 5000000 | FY 2027: 2500000; FY 2028: 2500000
U-5890 | Highway | STI (Prioritization) | SR 1162 (Dabney Drive) | Coble Boulevard to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Vance | 5 | Kerr-Tar RPO | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | BUILD NC CON | 24705000 |  |  |  |  | 1647000 | 1647000 | 1647000 | 1647000 | 1647000 | 1647000 | 11529000
U-5890 | Highway | STI (Prioritization) | SR 1162 (Dabney Drive) | Coble Boulevard to US 158 Business in Henderson. | Upgrade corridor. | 0.65 | Vance | 5 | Kerr-Tar RPO | BUILD NC BOND FUNDING: $15,000,000 FOR ROW PAYBACK 2027 - 2041 (FY 2027/ YR 7 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CON PAYBACK 2030-2044 (FY2030/ YR 10 SALE) AND BUILD NC BOND FUNDING: $3,500,000 FOR ROW PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | CONSTRUCTION | 19900000 | FY 2030: 0; FY 2031: 8093000; FY 2032: 9154000; FY 2033: 2653000
U-5891 | Highway | STI (Prioritization) | NC 50 (Creedmoor Road) | I-540 to north of NC 98. | Widen to multi-lane divided roadway. | 5.12 | Wake | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 143200000 | FY 2030: 14320000; FY 2031: 50120000; FY 2032: 50120000; FY 2033: 14320000; FY 2034: 14320000
U-5891 | Highway | STI (Prioritization) | NC 50 (Creedmoor Road) | I-540 to north of NC 98. | Widen to multi-lane divided roadway. | 5.12 | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 2200000 | FY 2030: 733000; FY 2031: 733000; FY 2032: 734000
U-5891 | Highway | STI (Prioritization) | NC 50 (Creedmoor Road) | I-540 to north of NC 98. | Widen to multi-lane divided roadway. | 5.12 | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 104200000 | FY 2034: 12504000; FY 2035: 26050000 | 65646000
U-5892 | Highway | STI (Prioritization) | US 220 (Battleground Avenue) | Westridge Road to Cotswold Avenue in Greensboro. | Construct additional lanes. | 1.42 | Guilford | 7 | Greensboro Urban Area MPO |  | Region D |  |  |  | 2350000
U-5892 | Highway | STI (Prioritization) | US 220 (Battleground Avenue) | Westridge Road to Cotswold Avenue in Greensboro. | Construct additional lanes. | 1.42 | Guilford | 7 | Greensboro Urban Area MPO |  | Region D |  | NHP | RIGHT-OF-WAY | 7531000 | FY 2026: 2524000; FY 2027: 2781000; FY 2028: 695000; FY 2029: 1506000
U-5892 | Highway | STI (Prioritization) | US 220 (Battleground Avenue) | Westridge Road to Cotswold Avenue in Greensboro. | Construct additional lanes. | 1.42 | Guilford | 7 | Greensboro Urban Area MPO |  | Region D |  | NHP | UTILITIES | 1472000 | FY 2026: 736000
U-5892 | Highway | STI (Prioritization) | US 220 (Battleground Avenue) | Westridge Road to Cotswold Avenue in Greensboro. | Construct additional lanes. | 1.42 | Guilford | 7 | Greensboro Urban Area MPO |  | Region D |  | NHP | CONSTRUCTION | 12400000 | FY 2028: 4588000; FY 2029: 4960000; FY 2030: 2232000; FY 2031: 620000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / I-85 Business | SR 1009 (South Main Street) in High Point. | Reconstruct interchange. | 1 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  |  |  | 3138000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / I-85 Business | SR 1009 (South Main Street) in High Point. | Reconstruct interchange. | 1 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  | T | ENGINEERING | 1820000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / I-85 Business | SR 1009 (South Main Street) in High Point. | Reconstruct interchange. | 1 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  | T | BUILD NC ROW | 8834000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / I-85 Business | SR 1009 (South Main Street) in High Point. | Reconstruct interchange. | 1 | Guilford | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  | T | CONSTRUCTION | 15400000
U-5899 | Highway | STI (Prioritization) | New Route | Forum Parkway connector, SR 3955 (Forum Parkway) to NC 66 (University Parkway) in Rural Hall. | Construct 2-lane roadway on new location. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 2730000
U-5899 | Highway | STI (Prioritization) | New Route | Forum Parkway connector, SR 3955 (Forum Parkway) to NC 66 (University Parkway) in Rural Hall. | Construct 2-lane roadway on new location. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | RIGHT-OF-WAY | 4300000
U-5899 | Highway | STI (Prioritization) | New Route | Forum Parkway connector, SR 3955 (Forum Parkway) to NC 66 (University Parkway) in Rural Hall. | Construct 2-lane roadway on new location. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | UTILITIES | 1300000
U-5899 | Highway | STI (Prioritization) | New Route | Forum Parkway connector, SR 3955 (Forum Parkway) to NC 66 (University Parkway) in Rural Hall. | Construct 2-lane roadway on new location. | 0.44 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 16000000 | FY 2026: 7200000; FY 2027: 5760000; FY 2028: 2880000
U-5901 | Highway | STI (Prioritization) | New Route | Airport Parkway, SR 1710 (Harrison Road) near US 70 / US 601 (Jake Alexander Boulevard) to SR 2539 (Peach Orchard Road) at US 29 in Salisbury. | Construct 2-lane roadway. | 3.63 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  |  |  | 1000000
U-5901 | Highway | STI (Prioritization) | New Route | Airport Parkway, SR 1710 (Harrison Road) near US 70 / US 601 (Jake Alexander Boulevard) to SR 2539 (Peach Orchard Road) at US 29 in Salisbury. | Construct 2-lane roadway. | 3.63 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGANY | RIGHT-OF-WAY | 19600000 | FY 2030: 196000; FY 2031: 4508000; FY 2032: 4704000; FY 2033: 4704000; FY 2034: 5488000
U-5901 | Highway | STI (Prioritization) | New Route | Airport Parkway, SR 1710 (Harrison Road) near US 70 / US 601 (Jake Alexander Boulevard) to SR 2539 (Peach Orchard Road) at US 29 in Salisbury. | Construct 2-lane roadway. | 3.63 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGANY | UTILITIES | 7900000 | FY 2030: 3950000; FY 2031: 3950000
U-5901 | Highway | STI (Prioritization) | New Route | Airport Parkway, SR 1710 (Harrison Road) near US 70 / US 601 (Jake Alexander Boulevard) to SR 2539 (Peach Orchard Road) at US 29 in Salisbury. | Construct 2-lane roadway. | 3.63 | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGANY | CONSTRUCTION | 52090000 | FY 2034: 9376000; FY 2035: 14064000 | 28650000
U-5903 | Highway | STI (Prioritization) | SR 1336 (Henderson Road) | SR 1308 (Gum Branch Road) to NC 53 (Western Boulevard). | Upgrade to reduced conflict intersections. | 1.13 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 1000000
U-5903 | Highway | STI (Prioritization) | SR 1336 (Henderson Road) | SR 1308 (Gum Branch Road) to NC 53 (Western Boulevard). | Upgrade to reduced conflict intersections. | 1.13 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 5900000 | FY 2030: 1534000; FY 2031: 2006000; FY 2032: 1180000; FY 2033: 590000; FY 2034: 590000
U-5903 | Highway | STI (Prioritization) | SR 1336 (Henderson Road) | SR 1308 (Gum Branch Road) to NC 53 (Western Boulevard). | Upgrade to reduced conflict intersections. | 1.13 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | UTILITIES | 4200000 | FY 2030: 2100000; FY 2031: 2100000
U-5903 | Highway | STI (Prioritization) | SR 1336 (Henderson Road) | SR 1308 (Gum Branch Road) to NC 53 (Western Boulevard). | Upgrade to reduced conflict intersections. | 1.13 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 38500000 | FY 2033: 4620000; FY 2034: 11550000; FY 2035: 10010000 | 12320000
U-5905 | Highway | Locally Selected | SR 2112 (Lakeview Road) | Reames Road to NC 115. | Upgrade roadway. | 2.1 | Mecklenburg | 10 | Charlotte Regional TPO | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. |  |  |  |  | 3000000
U-5905A | Highway | Locally Selected | SR 2112 (Lakeview Road) | Reames Road to NC 115. | Upgrade roadway. | 1.72 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  | BGDA | CONSTRUCTION | 155000
U-5905A | Highway | Locally Selected | SR 2112 (Lakeview Road) | Reames Road to NC 115. | Upgrade roadway. | 1.72 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  | BA | CONSTRUCTION | 8506000
U-5905B | Highway | Locally Selected | SR 2112 (Lakeview Road) | NC 24 (Harris Boulevard) and US 21 (Statesville Road) intersections in Charlotte. | Construct intersection improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | CONSTRUCTION | 162000
U-5905B | Highway | Locally Selected | SR 2112 (Lakeview Road) | NC 24 (Harris Boulevard) and US 21 (Statesville Road) intersections in Charlotte. | Construct intersection improvements. | 1 | Mecklenburg | 10 | Charlotte Regional TPO |  | Exempt |  | BA | CONSTRUCTION | 3000000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | BA | ENGINEERING | 1941000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | T | ENGINEERING | 100000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | BA | RIGHT-OF-WAY | 3153000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | T | RIGHT-OF-WAY | 8000000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 7773000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | T | CONSTRUCTION | 1372000 | FY 2026: 651000; FY 2027: 467000; FY 2028: 240000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | T(DA) | CONSTRUCTION | 2275000 | FY 2026: 1080000; FY 2027: 775000; FY 2028: 397000
U-5906 | Highway | Locally Selected | SR 2195 (Torrence Chapel Road) | SR 5544 (West Catawba Avenue) intersection in Cornelius. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 7773000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | ENGINEERING | 1330000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 500000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | RIGHT-OF-WAY | 1298000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | T(DA) | MITIGATION | 336000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | CONSTRUCTION | 2937000 | FY 2026: 362000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | T(DA) | CONSTRUCTION | 5367000 | FY 2026: 1133000
U-5907 | Highway | Locally Selected | New Route | SR 6037 (Potts Street), Sloan Street, and Beaty Street connector. | Construct roadway. | 1.73 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | L | CONSTRUCTION | 2200000
U-5908 | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP. |  |  |  |  | 3050000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGANY | ENGINEERING | 10000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | ENGINEERING | 2000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGANY | RIGHT-OF-WAY | 660000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | RIGHT-OF-WAY | 165000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGANY | CONSTRUCTION | 2401000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 44000
U-5908A | Highway | Locally Selected | Main Street | NC 115 (Old Statesville Road) / SR 2004 (Mount Holly-Huntersville Road) to south of SR 2439 (Ramah Church Road). | Widen and realign roadway. | 1.02 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 1630000
U-5908B | Highway | Locally Selected | NC 115 | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGANY | RIGHT-OF-WAY | 998000
U-5908B | Highway | Locally Selected | NC 115 | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDA | RIGHT-OF-WAY | 1318000
U-5908B | Highway | Locally Selected | NC 115 | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | RIGHT-OF-WAY | 579000
U-5908B | Highway | Locally Selected | NC 115 | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGANY | CONSTRUCTION | 2032000
U-5908B | Highway | Locally Selected | NC 115 | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDA | CONSTRUCTION | 5317000
U-5908B | Highway | Locally Selected | NC 115 | Realigned Main Street south of SR 2439 (Ramah Church Road) and SR 2004 (Mount Holly-Huntersville Road) intersections. | Construct roundabouts. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 4900000
U-5910 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Brunswick | 3 | Grand Strand Area Transportation Study | IN PROGRESS | Division 3 |  |  |  | 26000
U-5910 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Brunswick | 3 | Grand Strand Area Transportation Study | IN PROGRESS | Division 3 |  | BGDA | PLANNING | 392000
U-5910 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Brunswick | 3 | Grand Strand Area Transportation Study | IN PROGRESS | Division 3 |  | L | PLANNING | 148000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 Intersection in Rocky Mount | Construct roundabout. | 0.42 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  |  |  | 50000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 Intersection in Rocky Mount | Construct roundabout. | 0.42 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | CRPLT5 | RIGHT-OF-WAY | 30000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 Intersection in Rocky Mount | Construct roundabout. | 0.42 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | CRPLT5 | UTILITIES | 360000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 Intersection in Rocky Mount | Construct roundabout. | 0.42 | Nash | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | CRPLT5 | CONSTRUCTION | 3900000 | FY 2027: 2691000; FY 2028: 1209000
U-5914 | Highway | STI (Prioritization) | NC 133 | US 17 / US 74 / US 76 to SR 1554 (Old River Road). | Modernize roadway. | 0.48 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 140000
U-5914 | Highway | STI (Prioritization) | NC 133 | US 17 / US 74 / US 76 to SR 1554 (Old River Road). | Modernize roadway. | 0.48 | Brunswick | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 6933000
U-5917 | Highway | STI (Prioritization) | SR 1704 (Fourteenth Street) | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 2 |  |  |  | 5897000
U-5917 | Highway | STI (Prioritization) | SR 1704 (Fourteenth Street) | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 2 |  | T | ENGINEERING | 1740000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000
U-5917 | Highway | STI (Prioritization) | SR 1704 (Fourteenth Street) | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 2 |  | T | BUILD NC ROW | 952000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000
U-5917 | Highway | STI (Prioritization) | SR 1704 (Fourteenth Street) | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 2 |  | T | UTILITIES | 2772000
U-5917 | Highway | STI (Prioritization) | SR 1704 (Fourteenth Street) | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 2 |  | T | BUILD NC CON | 9750000 |  |  | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 4550000
U-5917 | Highway | STI (Prioritization) | SR 1704 (Fourteenth Street) | Red Banks Road to SR 1708 (Firetower Road). | Widen to add median and protected left-turn lanes. | 1.38 | Pitt | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 2 |  | T | CONSTRUCTION | 17200000 | FY 2027: 6175000; FY 2028: 898000; FY 2029: 6175000; FY 2030: 3952000
U-5924 | Highway | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Catawba, Alexander, Burke, Caldwell | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  |  |  | 125000
U-5924 | Highway | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Catawba, Alexander, Burke, Caldwell | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | BGDA | PLANNING | 1400000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 200000
U-5924 | Highway | Locally Selected | Various | Greater Hickory Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Catawba, Alexander, Burke, Caldwell | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | L | PLANNING | 350000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 50000
U-5928 | Highway | Locally Selected | Apex Peakway | James Street to Towhee Drive. | Construct grade separated interchange for Apex Peakway at South Salem Street and CSX Railroad. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | RR | CONSTRUCTION | 10000000
U-5928 | Highway | Locally Selected | Apex Peakway | James Street to Towhee Drive. | Construct grade separated interchange for Apex Peakway at South Salem Street and CSX Railroad. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 2500000
U-5928 | Highway | Locally Selected | Apex Peakway | James Street to Towhee Drive. | Construct grade separated interchange for Apex Peakway at South Salem Street and CSX Railroad. | 0.25 | Wake | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 12500000
U-5929 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 226 (Earl Road) intersection in Shelby. | Construct intersection improvements. | 0.5 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 8500000
U-5929 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 226 (Earl Road) intersection in Shelby. | Construct intersection improvements. | 0.5 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-5929 | Highway | STI (Prioritization) | US 74 (Dixon Boulevard) | NC 226 (Earl Road) intersection in Shelby. | Construct intersection improvements. | 0.5 | Cleveland | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 13600000
U-5930 | Highway | STI (Prioritization) | NC 24 (North Bragg Boulevard) | SR 1451 (Manchester Road) intersection in Spring Lake | Construct interchange. | 1 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-5930 | Highway | STI (Prioritization) | NC 24 (North Bragg Boulevard) | SR 1451 (Manchester Road) intersection in Spring Lake | Construct interchange. | 1 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 13100000
U-5930 | Highway | STI (Prioritization) | NC 24 (North Bragg Boulevard) | SR 1451 (Manchester Road) intersection in Spring Lake | Construct interchange. | 1 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3600000
U-5930 | Highway | STI (Prioritization) | NC 24 (North Bragg Boulevard) | SR 1451 (Manchester Road) intersection in Spring Lake | Construct interchange. | 1 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 65800000
U-5931 | Highway | STI (Prioritization) | US 74 | Secrest Shortcut Road intersection in Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  |  |  | 3500000
U-5931 | Highway | STI (Prioritization) | US 74 | Secrest Shortcut Road intersection in Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  | T | RIGHT-OF-WAY | 4531000 | FY 2027: 44000; FY 2028: 1042000; FY 2029: 1270000; FY 2030: 1270000; FY 2031: 905000
U-5931 | Highway | STI (Prioritization) | US 74 | Secrest Shortcut Road intersection in Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  | T | UTILITIES | 520000 | FY 2027: 520000
U-5931 | Highway | STI (Prioritization) | US 74 | Secrest Shortcut Road intersection in Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  | T | CONSTRUCTION | 8800000 | FY 2030: 88000; FY 2031: 4928000; FY 2032: 2904000; FY 2033: 880000
U-5933 | Highway | STI (Prioritization) | NC 87 / NC 24 | SR 1117 (Nursery Road) intersection north of Fayetteville | Construct intersection improvements. | 0.5 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 700000
U-5933 | Highway | STI (Prioritization) | NC 87 / NC 24 | SR 1117 (Nursery Road) intersection north of Fayetteville | Construct intersection improvements. | 0.5 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 17000
U-5933 | Highway | STI (Prioritization) | NC 87 / NC 24 | SR 1117 (Nursery Road) intersection north of Fayetteville | Construct intersection improvements. | 0.5 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 23000
U-5933 | Highway | STI (Prioritization) | NC 87 / NC 24 | SR 1117 (Nursery Road) intersection north of Fayetteville | Construct intersection improvements. | 0.5 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 2675000
U-5933 | Highway | STI (Prioritization) | NC 87 / NC 24 | SR 1117 (Nursery Road) intersection north of Fayetteville | Construct intersection improvements. | 0.5 | Harnett | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 670000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 to NC 147 in Durham. | Add lanes, rehabilitate pavement, and prioritize the addition of transit accommodations. | 4.82 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  |  |  | 300000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 to NC 147 in Durham. | Add lanes, rehabilitate pavement, and prioritize the addition of transit accommodations. | 4.82 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 10000 | FY 2028: 10000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 to NC 147 in Durham. | Add lanes, rehabilitate pavement, and prioritize the addition of transit accommodations. | 4.82 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHP | UTILITIES | 300000 | FY 2028: 300000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 to NC 147 in Durham. | Add lanes, rehabilitate pavement, and prioritize the addition of transit accommodations. | 4.82 | Durham | 5 | Triangle West TPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 142300000 | FY 2030: 18499000; FY 2031: 35575000; FY 2032: 32729000; FY 2033: 29883000; FY 2034: 25614000
U-5939 | Highway | STI (Prioritization) | US 17 Business (Future I-87) | SR 1145 (Oak Stump Road). | Construct intersection improvements. | 0.5 | Pasquotank | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  |  |  | 500000
U-5939 | Highway | STI (Prioritization) | US 17 Business (Future I-87) | SR 1145 (Oak Stump Road). | Construct intersection improvements. | 0.5 | Pasquotank | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  | BG5T50 | RIGHT-OF-WAY | 5400000 | FY 2026: 1525000; FY 2027: 1525000; FY 2028: 762000; FY 2029: 1080000
U-5939 | Highway | STI (Prioritization) | US 17 Business (Future I-87) | SR 1145 (Oak Stump Road). | Construct intersection improvements. | 0.5 | Pasquotank | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  | BG5T50 | UTILITIES | 530000
U-5939 | Highway | STI (Prioritization) | US 17 Business (Future I-87) | SR 1145 (Oak Stump Road). | Construct intersection improvements. | 0.5 | Pasquotank | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  | BG5T50 | CONSTRUCTION | 17300000 | FY 2028: 1730000; FY 2029: 6574000; FY 2030: 5017000; FY 2031: 3979000
U-5940 | Highway | STI (Prioritization) | US 17 (Hughes Boulevard) | SR 1308 (Church Street) to US 17 Business (North Road Street). | Construct access management improvements. | 1.49 | Pasquotank | 1 | Albemarle RPO |  | Region A |  |  |  | 2000000
U-5940 | Highway | STI (Prioritization) | US 17 (Hughes Boulevard) | SR 1308 (Church Street) to US 17 Business (North Road Street). | Construct access management improvements. | 1.49 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | NHP | RIGHT-OF-WAY | 18700000 | FY 2027: 935000; FY 2028: 5236000; FY 2029: 5236000; FY 2030: 3553000; FY 2031: 3740000
U-5940 | Highway | STI (Prioritization) | US 17 (Hughes Boulevard) | SR 1308 (Church Street) to US 17 Business (North Road Street). | Construct access management improvements. | 1.49 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | NHP | UTILITIES | 4700000 | FY 2027: 4700000
U-5940 | Highway | STI (Prioritization) | US 17 (Hughes Boulevard) | SR 1308 (Church Street) to US 17 Business (North Road Street). | Construct access management improvements. | 1.49 | Pasquotank | 1 | Albemarle RPO |  | Region A |  | NHP | CONSTRUCTION | 21100000 | FY 2030: 5064000; FY 2031: 6963000; FY 2032: 5275000; FY 2033: 3798000
U-5941 | Highway | STI (Prioritization) | US 264 Alternate (Raleigh Road Parkway) | SR 1320 (Airport Boulevard) to east of SR 1165 (Forest Hills Road). | Construct safety improvements. | 1.12 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  |  |  | 50000
U-5941 | Highway | STI (Prioritization) | US 264 Alternate (Raleigh Road Parkway) | SR 1320 (Airport Boulevard) to east of SR 1165 (Forest Hills Road). | Construct safety improvements. | 1.12 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  | BG5T50 | RIGHT-OF-WAY | 12600000 | FY 2028: 2613000; FY 2029: 4480000; FY 2030: 2987000; FY 2031: 1260000; FY 2032: 1260000
U-5941 | Highway | STI (Prioritization) | US 264 Alternate (Raleigh Road Parkway) | SR 1320 (Airport Boulevard) to east of SR 1165 (Forest Hills Road). | Construct safety improvements. | 1.12 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  | BG5T50 | UTILITIES | 4200000 | FY 2028: 2100000; FY 2029: 2100000
U-5941 | Highway | STI (Prioritization) | US 264 Alternate (Raleigh Road Parkway) | SR 1320 (Airport Boulevard) to east of SR 1165 (Forest Hills Road). | Construct safety improvements. | 1.12 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  | BG5T50 | CONSTRUCTION | 21300000 | FY 2031: 2769000; FY 2032: 8094000; FY 2033: 6177000; FY 2034: 4260000
U-5942 | Highway | STI (Prioritization) | Various | Routes in Elizabeth City. | Upgrade signal system. | 20 | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | Region A |  |  |  | 540000
U-5942 | Highway | STI (Prioritization) | Various | Routes in Elizabeth City. | Upgrade signal system. | 20 | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | Region A |  | HP | CONSTRUCTION | 62000
U-5942 | Highway | STI (Prioritization) | Various | Routes in Elizabeth City. | Upgrade signal system. | 20 | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | Region A |  | BG5T50 | CONSTRUCTION | 5297000
U-5943 | Highway | STI (Prioritization) | Various | Routes in Clayton. | Upgrade signal system. | 6.2 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  |  |  | 328000
U-5943 | Highway | STI (Prioritization) | Various | Routes in Clayton. | Upgrade signal system. | 6.2 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | BG50200 | UTILITIES | 260000
U-5943A | Highway | STI (Prioritization) | Various | Routes in Clayton, south of North Carolina Railroad. | Upgrade signal system. |  | Johnston | 4 | Capital Area MPO |  | Region A |  | BG50200 | CONSTRUCTION | 3375000 | FY 2026: 2801000; FY 2027: 540000
U-5943B | Highway | STI (Prioritization) | Various | Routes in Clayton, north of North Carolina Railroad. | Upgrade signal system. Includes rail encroachments. |  | Johnston | 4 | Capital Area MPO |  | Region A |  | BG50200 | CONSTRUCTION | 1125000 | FY 2026: 1125000
U-5945 | Highway | STI (Prioritization) | Various | Routes in Wilson. | Upgrade signal system. | 26.1 | Wilson | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 10000
U-5945 | Highway | STI (Prioritization) | Various | Routes in Wilson. | Upgrade signal system. | 26.1 | Wilson | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | UTILITIES | 2300000
U-5945 | Highway | STI (Prioritization) | Various | Routes in Wilson. | Upgrade signal system. | 26.1 | Wilson | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | CONSTRUCTION | 1700000 | FY 2026: 969000; FY 2027: 391000
U-5947 | Highway | STI (Prioritization) | NC 43 (Benvenue Road) | US 64 Bypass offramp intersection in Rocky Mount | Construct roundabout. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  |  |  | 51000
U-5947 | Highway | STI (Prioritization) | NC 43 (Benvenue Road) | US 64 Bypass offramp intersection in Rocky Mount | Construct roundabout. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | RIGHT-OF-WAY | 80000
U-5947 | Highway | STI (Prioritization) | NC 43 (Benvenue Road) | US 64 Bypass offramp intersection in Rocky Mount | Construct roundabout. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | UTILITIES | 800000
U-5947 | Highway | STI (Prioritization) | NC 43 (Benvenue Road) | US 64 Bypass offramp intersection in Rocky Mount | Construct roundabout. | 1 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | CONSTRUCTION | 5725000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 to south of SR 1518 (Old Folkstone Road). | Widen to multi-lanes. | 5.76 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 1150000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 to south of SR 1518 (Old Folkstone Road). | Widen to multi-lanes. | 5.76 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 33198000 | FY 2030: 3794000; FY 2031: 5691000; FY 2032: 5691000; FY 2033: 5691000; FY 2034: 12331000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 to south of SR 1518 (Old Folkstone Road). | Widen to multi-lanes. | 5.76 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | T | UTILITIES | 15400000 | FY 2030: 5133000; FY 2031: 5133000; FY 2032: 5134000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 to south of SR 1518 (Old Folkstone Road). | Widen to multi-lanes. | 5.76 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | T | CONSTRUCTION | 115400000 | FY 2034: 1154000; FY 2035: 31158000 | 83088000
U-5950 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  |  |  | 500000
U-5950 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  | BG50200 | RIGHT-OF-WAY | 100000
U-5950 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  | BG50200 | UTILITIES | 200000
U-5950 | Highway | STI (Prioritization) | US 17 Business (Marine Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region B |  | BG50200 | CONSTRUCTION | 1500000 | FY 2026: 15000; FY 2027: 1485000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 Business (Marine Boulevard) intersection in Jacksonville | Upgrade at-grade intersection to partial interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 1350000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 Business (Marine Boulevard) intersection in Jacksonville | Upgrade at-grade intersection to partial interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | RIGHT-OF-WAY | 350000 | FY 2027: 350000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 Business (Marine Boulevard) intersection in Jacksonville | Upgrade at-grade intersection to partial interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 330000 | FY 2027: 330000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 Business (Marine Boulevard) intersection in Jacksonville | Upgrade at-grade intersection to partial interchange. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 22600000 | FY 2029: 4294000; FY 2030: 8136000; FY 2031: 6102000; FY 2032: 4068000
U-5952 | Highway | STI (Prioritization) | Various | Routes in Greenville | Upgrade signal system. | 25 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  |  |  | 1610000
U-5952 | Highway | STI (Prioritization) | Various | Routes in Greenville | Upgrade signal system. | 25 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 750000 | FY 2026: 750000
U-5952 | Highway | STI (Prioritization) | Various | Routes in Greenville | Upgrade signal system. | 25 | Pitt | 2 | Greenville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 13100000 | FY 2028: 4978000; FY 2029: 5109000; FY 2030: 3013000
U-5955 | Highway | STI (Prioritization) | NC 16 (Brookshire Boulevard) | I-85 to Idaho Drive in Charlotte. | Construct additional westbound through lane west of Idaho Drive and I-85. Improve I-85 northbound ramp to eastbound NC 16. | 0.38 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 1095000
U-5955A | Highway | STI (Prioritization) | NC 16 (Brookshire Boulevard) | I-85 northbound ramp to eastbound NC 16 in Charlotte. | Improve I-85 northbound ramp to eastbound NC 16. |  | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | T | CONSTRUCTION | 3000000
U-5955B | Highway | STI (Prioritization) | NC 16 (Brookshire Boulevard) | Idaho Drive intersection in Charlotte. | Upgrade intersection to an interchange. | 0.38 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | NHP | RIGHT-OF-WAY | 4300000 | FY 2030: 387000; FY 2031: 1247000; FY 2032: 1204000; FY 2033: 602000; FY 2034: 860000
U-5955B | Highway | STI (Prioritization) | NC 16 (Brookshire Boulevard) | Idaho Drive intersection in Charlotte. | Upgrade intersection to an interchange. | 0.38 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | NHP | UTILITIES | 345000 | FY 2030: 345000
U-5955B | Highway | STI (Prioritization) | NC 16 (Brookshire Boulevard) | Idaho Drive intersection in Charlotte. | Upgrade intersection to an interchange. | 0.38 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | NHP | CONSTRUCTION | 12700000 | FY 2033: 3048000; FY 2034: 5588000; FY 2035: 3048000 | 1016000
U-5956 | Highway | STI (Prioritization) | US 29 | Union Cemetery Road intersection in Concord; West of SR 1414 (Rock Hill Church Road) to east of SR 1414 (Rock Hill Church Road) in Concord. | Realign Union Cemetery Road to intersect with US 29 and SR 1414 (Rock Hill Church Road) intersection; Upgrade roadway. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $10M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  |  |  | 450000
U-5956 | Highway | STI (Prioritization) | US 29 | Union Cemetery Road intersection in Concord; West of SR 1414 (Rock Hill Church Road) to east of SR 1414 (Rock Hill Church Road) in Concord. | Realign Union Cemetery Road to intersect with US 29 and SR 1414 (Rock Hill Church Road) intersection; Upgrade roadway. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $10M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | RIGHT-OF-WAY | 3400000
U-5956 | Highway | STI (Prioritization) | US 29 | Union Cemetery Road intersection in Concord; West of SR 1414 (Rock Hill Church Road) to east of SR 1414 (Rock Hill Church Road) in Concord. | Realign Union Cemetery Road to intersect with US 29 and SR 1414 (Rock Hill Church Road) intersection; Upgrade roadway. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $10M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | UTILITIES | 2050000 | FY 2026: 1550000
U-5956 | Highway | STI (Prioritization) | US 29 | Union Cemetery Road intersection in Concord; West of SR 1414 (Rock Hill Church Road) to east of SR 1414 (Rock Hill Church Road) in Concord. | Realign Union Cemetery Road to intersect with US 29 and SR 1414 (Rock Hill Church Road) intersection; Upgrade roadway. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $10M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | BUILD NC CON | 13005000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 4335000
U-5956 | Highway | STI (Prioritization) | US 29 | Union Cemetery Road intersection in Concord; West of SR 1414 (Rock Hill Church Road) to east of SR 1414 (Rock Hill Church Road) in Concord. | Realign Union Cemetery Road to intersect with US 29 and SR 1414 (Rock Hill Church Road) intersection; Upgrade roadway. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $10M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | CONSTRUCTION | 11900000 | FY 2026: 0; FY 2027: 2264000; FY 2028: 5475000; FY 2029: 3285000; FY 2030: 876000
U-5957 | Highway | STI (Prioritization) | NC 27 (Freedom Drive) | SR 1644 (Toddville Road) to SR 1600 (Moores Chapel Road) in Charlotte. | Widen to four lanes. | 1.25 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 1920000
U-5957 | Highway | STI (Prioritization) | NC 27 (Freedom Drive) | SR 1644 (Toddville Road) to SR 1600 (Moores Chapel Road) in Charlotte. | Widen to four lanes. | 1.25 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 15900000 | FY 2030: 159000; FY 2031: 3339000; FY 2032: 3975000; FY 2033: 3975000; FY 2034: 4452000
U-5957 | Highway | STI (Prioritization) | NC 27 (Freedom Drive) | SR 1644 (Toddville Road) to SR 1600 (Moores Chapel Road) in Charlotte. | Widen to four lanes. | 1.25 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 2200000 | FY 2030: 550000; FY 2031: 1650000
U-5957 | Highway | STI (Prioritization) | NC 27 (Freedom Drive) | SR 1644 (Toddville Road) to SR 1600 (Moores Chapel Road) in Charlotte. | Widen to four lanes. | 1.25 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 28800000 | FY 2034: 5760000; FY 2035: 9792000 | 13248000
U-5961 | Highway | STI (Prioritization) | NC 274 (Union Road) | Osceola Street to Niblick Drive in Gastonia. | Upgrade roadway. | 1.02 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | BG50200 | RIGHT-OF-WAY | 25500000 | FY 2028: 510000; FY 2029: 6120000; FY 2030: 6375000; FY 2031: 6375000; FY 2032: 6120000
U-5961 | Highway | STI (Prioritization) | NC 274 (Union Road) | Osceola Street to Niblick Drive in Gastonia. | Upgrade roadway. | 1.02 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | BG50200 | UTILITIES | 4100000 | FY 2028: 820000; FY 2029: 1640000; FY 2030: 1640000
U-5961 | Highway | STI (Prioritization) | NC 274 (Union Road) | Osceola Street to Niblick Drive in Gastonia. | Upgrade roadway. | 1.02 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | BG50200 | CONSTRUCTION | 19000000 | FY 2031: 4750000; FY 2032: 5890000; FY 2033: 4560000; FY 2034: 3420000; FY 2035: 380000
U-5961 | Highway | STI (Prioritization) | NC 274 (Union Road) | Osceola Street to Niblick Drive in Gastonia. | Upgrade roadway. | 1.02 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | O | CONSTRUCTION | 5000000 | FY 2031: 1502000; FY 2032: 2486000; FY 2033: 1012000
U-5962 | Highway | STI (Prioritization) | NC 16 Business | SR 1373 (Campground Road) and SR 1386 (Will Proctor Road) intersections. | Realign intersections. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 700000
U-5962 | Highway | STI (Prioritization) | NC 16 Business | SR 1373 (Campground Road) and SR 1386 (Will Proctor Road) intersections. | Realign intersections. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 16000000
U-5962 | Highway | STI (Prioritization) | NC 16 Business | SR 1373 (Campground Road) and SR 1386 (Will Proctor Road) intersections. | Realign intersections. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2700000
U-5962 | Highway | STI (Prioritization) | NC 16 Business | SR 1373 (Campground Road) and SR 1386 (Will Proctor Road) intersections. | Realign intersections. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 16511000
U-5962 | Highway | STI (Prioritization) | NC 16 Business | SR 1373 (Campground Road) and SR 1386 (Will Proctor Road) intersections. | Realign intersections. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 288000
U-5964 | Highway | STI (Prioritization) | US 64 (Davie Avenue) | US 21 (Sullivan Road) intersection in Statesville. | Upgrade 5-approach intersection to a single lane roundabout. | 0.5 | Iredell | 12 | Charlotte Regional TPO |  | Region F |  |  |  | 150000
U-5964 | Highway | STI (Prioritization) | US 64 (Davie Avenue) | US 21 (Sullivan Road) intersection in Statesville. | Upgrade 5-approach intersection to a single lane roundabout. | 0.5 | Iredell | 12 | Charlotte Regional TPO |  | Region F |  | T | RIGHT-OF-WAY | 3800000 | FY 2026: 380000; FY 2027: 380000
U-5964 | Highway | STI (Prioritization) | US 64 (Davie Avenue) | US 21 (Sullivan Road) intersection in Statesville. | Upgrade 5-approach intersection to a single lane roundabout. | 0.5 | Iredell | 12 | Charlotte Regional TPO |  | Region F |  | T | UTILITIES | 700000
U-5964 | Highway | STI (Prioritization) | US 64 (Davie Avenue) | US 21 (Sullivan Road) intersection in Statesville. | Upgrade 5-approach intersection to a single lane roundabout. | 0.5 | Iredell | 12 | Charlotte Regional TPO |  | Region F |  | T | CONSTRUCTION | 3299000 | FY 2026: 528000; FY 2027: 2177000; FY 2028: 594000
U-5965 | Highway | STI (Prioritization) | US 29 (Franklin Boulevard) | US 29 (Franklin Boulevard) and NC 274. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  |  |  | 950000
U-5965 | Highway | STI (Prioritization) | US 29 (Franklin Boulevard) | US 29 (Franklin Boulevard) and NC 274. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T | RIGHT-OF-WAY | 6900000 | FY 2026: 690000; FY 2027: 690000
U-5965 | Highway | STI (Prioritization) | US 29 (Franklin Boulevard) | US 29 (Franklin Boulevard) and NC 274. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T | UTILITIES | 300000
U-5965 | Highway | STI (Prioritization) | US 29 (Franklin Boulevard) | US 29 (Franklin Boulevard) and NC 274. | Construct intersection improvements. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | BG50200 | CONSTRUCTION | 7200000 | FY 2026: 72000; FY 2027: 4752000; FY 2028: 2376000
U-5967 | Highway | STI (Prioritization) | Various | Locations in the Town of Morrisville. | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO |  | Region C |  |  |  | 163000
U-5967 | Highway | STI (Prioritization) | Various | Locations in the Town of Morrisville. | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO |  | Region C |  | BGANY | UTILITIES | 25000 | FY 2027: 25000
U-5967 | Highway | STI (Prioritization) | Various | Locations in the Town of Morrisville. | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 8000 | FY 2027: 8000
U-5967 | Highway | STI (Prioritization) | Various | Locations in the Town of Morrisville. | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO |  | Region C |  | BGANY | CONSTRUCTION | 603000 | FY 2028: 458000; FY 2029: 145000
U-5967 | Highway | STI (Prioritization) | Various | Locations in the Town of Morrisville. | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 350000 | FY 2028: 266000; FY 2029: 84000
U-5968 | Highway | STI (Prioritization) | Various | Locations in the City of Durham. | Upgrade ITS / signal system. |  | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  |  |  | 14315000
U-5968 | Highway | STI (Prioritization) | Various | Locations in the City of Durham. | Upgrade ITS / signal system. |  | Durham | 5 | Triangle West TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  | T | BUILD NC CON | 13000000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 862000
U-5969 | Highway | STI (Prioritization) | US 501 | South of US 158 to SR 1601 (North Main Street) in Roxboro. | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 3 | Person | 5 | Kerr-Tar RPO | [5 empty] | 1700000
U-5969A | Highway | STI (Prioritization) | US 501 | South of US 158 to NC 157 | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 0.88 | Person | 5 | Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5700000
U-5969A | Highway | STI (Prioritization) | US 501 | South of US 158 to NC 157 | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 0.88 | Person | 5 | Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 200000
U-5969A | Highway | STI (Prioritization) | US 501 | South of US 158 to NC 157 | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 0.88 | Person | 5 | Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6400000
U-5969B | Highway | STI (Prioritization) | US 501 | NC 157 to SR 1596 (West Morehead Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.03 | Person | 5 | Kerr-Tar RPO |  | Region C |  | T | RIGHT-OF-WAY | 7900000 | FY 2029: 3160000; FY 2030: 3160000; FY 2031: 790000; FY 2032: 790000
U-5969B | Highway | STI (Prioritization) | US 501 | NC 157 to SR 1596 (West Morehead Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.03 | Person | 5 | Kerr-Tar RPO |  | Region C |  | T | UTILITIES | 200000 | FY 2029: 100000; FY 2030: 100000
U-5969B | Highway | STI (Prioritization) | US 501 | NC 157 to SR 1596 (West Morehead Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.03 | Person | 5 | Kerr-Tar RPO |  | Region C |  | T | CONSTRUCTION | 13800000 | FY 2031: 2208000; FY 2032: 5658000; FY 2033: 4002000; FY 2034: 1932000
U-5969C | Highway | STI (Prioritization) | US 501 / NC 49 | SR 1596 (West Morehead Street) to SR 1601 (North Main Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.11 | Person | 5 | Kerr-Tar RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4400000 | [10 empty] | 4400000
U-5969C | Highway | STI (Prioritization) | US 501 / NC 49 | SR 1596 (West Morehead Street) to SR 1601 (North Main Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.11 | Person | 5 | Kerr-Tar RPO |  | Not Funded |  | T | UTILITIES | 250000 | [10 empty] | 250000
U-5969C | Highway | STI (Prioritization) | US 501 / NC 49 | SR 1596 (West Morehead Street) to SR 1601 (North Main Street) | Upgrade to 4-lane median divided facility, improve various intersections with some consolidation of intersections, and fill in sidewalk gaps. | 1.11 | Person | 5 | Kerr-Tar RPO |  | Not Funded |  | T | CONSTRUCTION | 6599000 | [10 empty] | 6599000
U-5971 | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO | [5 empty] | 1369000
U-5971A | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct initial intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO | SUPPLEMENT WITH SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Region G
U-5971AA | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct drainage improvements. |  | Buncombe | 13 | French Broad River MPO | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION. | Region G |  | T | RIGHT-OF-WAY | 100000
U-5971AA | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct drainage improvements. |  | Buncombe | 13 | French Broad River MPO | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION. | Region G |  | T | CONSTRUCTION | 550000
U-5971B | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct final intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 28900000 | [10 empty] | 28900000
U-5971B | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct final intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | UTILITIES | 200000 | [10 empty] | 200000
U-5971B | Highway | STI (Prioritization) | US 19 (Patton Avenue) | NC 63 (New Leicester Highway) intersection in Asheville. | Construct final intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 12900000 | [10 empty] | 12900000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (Hickswood Road) to SR 1823 (Williard Dairy Road) in High Point. | Construct reduced conflict intersections. | 2.92 | Guilford | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Region D |  |  |  | 1675000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (Hickswood Road) to SR 1823 (Williard Dairy Road) in High Point. | Construct reduced conflict intersections. | 2.92 | Guilford | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Region D |  | T | RIGHT-OF-WAY | 16300000 | FY 2027: 4075000; FY 2028: 8313000; FY 2029: 652000; FY 2030: 1630000; FY 2031: 1630000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (Hickswood Road) to SR 1823 (Williard Dairy Road) in High Point. | Construct reduced conflict intersections. | 2.92 | Guilford | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Region D |  | T | UTILITIES | 4700000 | FY 2027: 2350000; FY 2028: 2350000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (Hickswood Road) to SR 1823 (Williard Dairy Road) in High Point. | Construct reduced conflict intersections. | 2.92 | Guilford | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Region D |  | T | BUILD NC CON | 20805000 |  |  |  |  | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 1387000 | 9709000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (Hickswood Road) to SR 1823 (Williard Dairy Road) in High Point. | Construct reduced conflict intersections. | 2.92 | Guilford | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Region D |  | T | CONSTRUCTION | 35800000 | FY 2029: 10066000; FY 2030: 12751000; FY 2031: 8581000; FY 2032: 4402000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Construct reduced conflict intersections. | 2.17 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  |  |  | 3846000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Construct reduced conflict intersections. | 2.17 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | RIGHT-OF-WAY | 4100000 | FY 2026: 226000; FY 2027: 821000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Construct reduced conflict intersections. | 2.17 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | UTILITIES | 3300000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Construct reduced conflict intersections. | 2.17 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | BUILD NC CON | 15600000 |  | 2080000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 5200000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | Intersections from US 15 / US 501 (White Hill Road) / SR 1179 (Rocky Fork Church Road) to south of SR 1198 (Bryan Drive) south of Sanford. | Construct reduced conflict intersections. | 2.17 | Lee | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE); | Region E |  | T | CONSTRUCTION | 27100000 | FY 2027: 0; FY 2028: 3640000; FY 2029: 9775000; FY 2030: 7820000; FY 2031: 5865000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (Voit Gilmore Lane) in Southern Pines to SR 1208 (Page Road) in Pinehurst. | Upgrade SR 1208 (Page Road) intersection and construct improvements to Pinehurst traffic circle and approaches. | 2.3 | Moore | 8 | Sandhills MPO |  | Division 8 |  |  |  | 600000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (Voit Gilmore Lane) in Southern Pines to SR 1208 (Page Road) in Pinehurst. | Upgrade SR 1208 (Page Road) intersection and construct improvements to Pinehurst traffic circle and approaches. | 2.3 | Moore | 8 | Sandhills MPO |  | Division 8 |  | T | RIGHT-OF-WAY | 28900000 | FY 2028: 1156000; FY 2029: 6936000; FY 2030: 6936000; FY 2031: 6936000; FY 2032: 6936000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (Voit Gilmore Lane) in Southern Pines to SR 1208 (Page Road) in Pinehurst. | Upgrade SR 1208 (Page Road) intersection and construct improvements to Pinehurst traffic circle and approaches. | 2.3 | Moore | 8 | Sandhills MPO |  | Division 8 |  | T | UTILITIES | 970000 | FY 2028: 970000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (Voit Gilmore Lane) in Southern Pines to SR 1208 (Page Road) in Pinehurst. | Upgrade SR 1208 (Page Road) intersection and construct improvements to Pinehurst traffic circle and approaches. | 2.3 | Moore | 8 | Sandhills MPO |  | Division 8 |  | T | CONSTRUCTION | 51100000 | FY 2031: 10731000; FY 2032: 13286000; FY 2033: 11242000; FY 2034: 8687000; FY 2035: 7154000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | South Carolina state line to south of SR 1105 (Turnpike Road) in Laurinburg. | Widen to multi-lanes. | 3.44 | Scotland | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3888000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | South Carolina state line to south of SR 1105 (Turnpike Road) in Laurinburg. | Widen to multi-lanes. | 3.44 | Scotland | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 4800000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | South Carolina state line to south of SR 1105 (Turnpike Road) in Laurinburg. | Widen to multi-lanes. | 3.44 | Scotland | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3000000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | South Carolina state line to south of SR 1105 (Turnpike Road) in Laurinburg. | Widen to multi-lanes. | 3.44 | Scotland | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 22000000
U-5989 | Highway | Locally Selected | Various | Wilmington Urban Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Division 3
U-5989 | Highway | Locally Selected | Various | Wilmington Urban Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | CONSTRUCTION | 26925000 | FY 2026: 5385000; FY 2027: 5385000; FY 2028: 5385000; FY 2029: 5385000; FY 2030: 5385000
U-5989 | Highway | Locally Selected | Various | Wilmington Urban Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | New Hanover, Brunswick, Pender | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 100469000 | 84000 | 3324000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 27398000
U-5990 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Division 3 |  |  |  | 825000
U-5990 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Division 3 |  | BGANY | CONSTRUCTION | 2425000 | FY 2026: 2425000
U-5990 | Highway | Locally Selected | Various | Grand Strand Area Transportation Study Metropolitan Planning Organization | Unallocated Surface Transportation Block Grant Program Funds. |  | Brunswick | 3 | Grand Strand Area Transportation Study |  | Division 3 |  | BGDA | CONSTRUCTION | 12206000 | 425000 | 425000 | 425000 | 425000 | 425000 | 425000 | 425000 | 425000 | 425000 | 425000 | 2975000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (Fire Tower Road) to SR 1711 (Worthington Road). | Widen to multi-lanes. | 3.19 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 900000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (Fire Tower Road) to SR 1711 (Worthington Road). | Widen to multi-lanes. | 3.19 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 22800000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (Fire Tower Road) to SR 1711 (Worthington Road). | Widen to multi-lanes. | 3.19 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 19900000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (Fire Tower Road) to SR 1711 (Worthington Road). | Widen to multi-lanes. | 3.19 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 57700000
U-5993 | Highway | STI (Prioritization) | NC 55 (Neuse Boulevard) | US 17 Business (MLK Boulevard) intersection in New Bern | Construct roundabout. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  |  |  | 750000
U-5993 | Highway | STI (Prioritization) | NC 55 (Neuse Boulevard) | US 17 Business (MLK Boulevard) intersection in New Bern | Construct roundabout. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 790000 | FY 2027: 790000
U-5993 | Highway | STI (Prioritization) | NC 55 (Neuse Boulevard) | US 17 Business (MLK Boulevard) intersection in New Bern | Construct roundabout. | 0.5 | Craven | 2 | New Bern Area MPO |  | Region B |  | T | CONSTRUCTION | 5700000 | FY 2029: 57000; FY 2030: 3477000; FY 2031: 2166000
U-5994 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Lockhaven Drive to Country Day Road. | Construct access management improvements. | 0.26 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 800000
U-5994 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Lockhaven Drive to Country Day Road. | Construct access management improvements. | 0.26 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T | CONSTRUCTION | 450000
U-5996 | Highway | STI (Prioritization) | SR 1603 (Old Carriage Road) | Green Hills Road to SR 1770 (Eastern Avenue). | Widen to four lanes from Green Hills Road through US 64 bridge; widen to three lanes from south of US 64 bridge to SR 1770 (Eastern Avenue). | 1.33 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 1000000
U-5996 | Highway | STI (Prioritization) | SR 1603 (Old Carriage Road) | Green Hills Road to SR 1770 (Eastern Avenue). | Widen to four lanes from Green Hills Road through US 64 bridge; widen to three lanes from south of US 64 bridge to SR 1770 (Eastern Avenue). | 1.33 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T | RIGHT-OF-WAY | 529000
U-5996 | Highway | STI (Prioritization) | SR 1603 (Old Carriage Road) | Green Hills Road to SR 1770 (Eastern Avenue). | Widen to four lanes from Green Hills Road through US 64 bridge; widen to three lanes from south of US 64 bridge to SR 1770 (Eastern Avenue). | 1.33 | Nash | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T | CONSTRUCTION | 23940000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (Buffalo Road) to Wilson County line. | Modernize roadway. | 11.43 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 4 |  |  |  | 10000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (Buffalo Road) to Wilson County line. | Modernize roadway. | 11.43 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 4 |  | BGANY | RIGHT-OF-WAY | 3300000 | FY 2026: 1980000; FY 2027: 660000; FY 2028: 330000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (Buffalo Road) to Wilson County line. | Modernize roadway. | 11.43 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 4 |  | BGANY | UTILITIES | 2100000 | FY 2026: 1050000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (Buffalo Road) to Wilson County line. | Modernize roadway. | 11.43 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 4 |  | T | BUILD NC CON | 13005000 |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (Buffalo Road) to Wilson County line. | Modernize roadway. | 11.43 | Johnston | 4 | Capital Area MPO, Upper Coastal Plain RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 4 |  | T | CONSTRUCTION | 16900000 | FY 2027: 4304000; FY 2028: 0; FY 2029: 6140000; FY 2030: 5111000; FY 2031: 1345000
U-6001 | Highway | STI (Prioritization) | SR 1596 (South Main Street) | SR 1243 (Shipman Road) to SR 1118 (Parkton Road). | Widen to multi-lanes. | 1.19 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-6001 | Highway | STI (Prioritization) | SR 1596 (South Main Street) | SR 1243 (Shipman Road) to SR 1118 (Parkton Road). | Widen to multi-lanes. | 1.19 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3900000
U-6001 | Highway | STI (Prioritization) | SR 1596 (South Main Street) | SR 1243 (Shipman Road) to SR 1118 (Parkton Road). | Widen to multi-lanes. | 1.19 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2200000
U-6001 | Highway | STI (Prioritization) | SR 1596 (South Main Street) | SR 1243 (Shipman Road) to SR 1118 (Parkton Road). | Widen to multi-lanes. | 1.19 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 17900000
U-6002 | Highway | STI (Prioritization) | Wilkesboro Street | Yadkinville Road intersection in Mocksville. | Construct roundabout. | 0.5 | Davie | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 750000
U-6002 | Highway | STI (Prioritization) | Wilkesboro Street | Yadkinville Road intersection in Mocksville. | Construct roundabout. | 0.5 | Davie | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 1800000
U-6003 | Highway | STI (Prioritization) | New Route | SR 1969 (Piney Grove Road) to NC 150 (North Main Street) in Kernersville. | Construct two-lane divided facility with bicycle / pedestrian accommodations. | 0.94 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  |  |  | 2670000
U-6003 | Highway | STI (Prioritization) | New Route | SR 1969 (Piney Grove Road) to NC 150 (North Main Street) in Kernersville. | Construct two-lane divided facility with bicycle / pedestrian accommodations. | 0.94 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | T | CONSTRUCTION | 12400000 | FY 2026: 3640000
U-6004 | Highway | STI (Prioritization) | SR 1103 (Lewisville-Clemmons Road) | US 158 to SR 1891 (Peace Haven Road) in Clemmons. | Construct access management and operational improvements. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Division 9 |  |  |  | 750000
U-6004 | Highway | STI (Prioritization) | SR 1103 (Lewisville-Clemmons Road) | US 158 to SR 1891 (Peace Haven Road) in Clemmons. | Construct access management and operational improvements. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Division 9 |  | BGANY | RIGHT-OF-WAY | 33600000 | FY 2026: 10240000; FY 2027: 3360000; FY 2028: 3360000
U-6004 | Highway | STI (Prioritization) | SR 1103 (Lewisville-Clemmons Road) | US 158 to SR 1891 (Peace Haven Road) in Clemmons. | Construct access management and operational improvements. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Division 9 |  | BGANY | UTILITIES | 2975000 | FY 2026: 750000; FY 2027: 2225000
U-6004 | Highway | STI (Prioritization) | SR 1103 (Lewisville-Clemmons Road) | US 158 to SR 1891 (Peace Haven Road) in Clemmons. | Construct access management and operational improvements. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Division 9 |  | T | BUILD NC CON | 11700000 |  |  |  |  | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 5460000
U-6004 | Highway | STI (Prioritization) | SR 1103 (Lewisville-Clemmons Road) | US 158 to SR 1891 (Peace Haven Road) in Clemmons. | Construct access management and operational improvements. | 1.43 | Forsyth | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) | Division 9 |  | T | CONSTRUCTION | 23700000 | FY 2030: 0; FY 2031: 8985000; FY 2032: 10137000; FY 2033: 4578000
U-6005 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | US 52 to SR 3983 (Northridge Drive) in Rural Hall. | Widen to two lane divided facility with bike-ped accommodations. | 1.17 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  |  |  | 500000
U-6005 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | US 52 to SR 3983 (Northridge Drive) in Rural Hall. | Widen to two lane divided facility with bike-ped accommodations. | 1.17 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | RIGHT-OF-WAY | 3800000 | FY 2026: 380000; FY 2027: 380000
U-6005 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | US 52 to SR 3983 (Northridge Drive) in Rural Hall. | Widen to two lane divided facility with bike-ped accommodations. | 1.17 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | UTILITIES | 900000
U-6005 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | US 52 to SR 3983 (Northridge Drive) in Rural Hall. | Widen to two lane divided facility with bike-ped accommodations. | 1.17 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | BUILD NC CON | 7800000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 2600000
U-6005 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | US 52 to SR 3983 (Northridge Drive) in Rural Hall. | Widen to two lane divided facility with bike-ped accommodations. | 1.17 | Forsyth | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) | Division 9 |  | T | CONSTRUCTION | 8000000 | FY 2026: 0; FY 2027: 3940000; FY 2028: 3220000; FY 2029: 840000
U-6006 | Highway | STI (Prioritization) | US 220 Business | SR 2123 (Caudle Road) to SR 2270 (US 311 extension) in Randleman. | Widen to 4-lane divided facility. | 0.72 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5956 | Division 8 |  |  |  | 944000
U-6006 | Highway | STI (Prioritization) | US 220 Business | SR 2123 (Caudle Road) to SR 2270 (US 311 extension) in Randleman. | Widen to 4-lane divided facility. | 0.72 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5956 | Division 8 |  | T | RIGHT-OF-WAY | 2050000 | FY 2026: 72000; FY 2027: 205000; FY 2028: 205000
U-6006 | Highway | STI (Prioritization) | US 220 Business | SR 2123 (Caudle Road) to SR 2270 (US 311 extension) in Randleman. | Widen to 4-lane divided facility. | 0.72 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5956 | Division 8 |  | T | UTILITIES | 2800000
U-6006 | Highway | STI (Prioritization) | US 220 Business | SR 2123 (Caudle Road) to SR 2270 (US 311 extension) in Randleman. | Widen to 4-lane divided facility. | 0.72 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5956 | Division 8 |  | BGANY | CONSTRUCTION | 16000000 | FY 2027: 3680000; FY 2028: 5920000; FY 2029: 4320000; FY 2030: 2080000
U-6007 | Highway | STI (Prioritization) | US 220 Business (South Fayetteville Street) | South of SR 2915 (Ridge Street) to south of SR 1453 (Walker Avenue) in Asheboro. | Construct right turn lane on SR 2915, construct left-overs at SR 1154 (Country Club Drive) / SR 2800 (Atlantic Avenue), and reduce number of lanes from SR 2800 (Atlantic Avenue) to south of SR 1453 (Walker Avenue). | 0.47 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 876000
U-6007 | Highway | STI (Prioritization) | US 220 Business (South Fayetteville Street) | South of SR 2915 (Ridge Street) to south of SR 1453 (Walker Avenue) in Asheboro. | Construct right turn lane on SR 2915, construct left-overs at SR 1154 (Country Club Drive) / SR 2800 (Atlantic Avenue), and reduce number of lanes from SR 2800 (Atlantic Avenue) to south of SR 1453 (Walker Avenue). | 0.47 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 300000
U-6007 | Highway | STI (Prioritization) | US 220 Business (South Fayetteville Street) | South of SR 2915 (Ridge Street) to south of SR 1453 (Walker Avenue) in Asheboro. | Construct right turn lane on SR 2915, construct left-overs at SR 1154 (Country Club Drive) / SR 2800 (Atlantic Avenue), and reduce number of lanes from SR 2800 (Atlantic Avenue) to south of SR 1453 (Walker Avenue). | 0.47 | Randolph | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 1400000 | FY 2026: 133000
U-6008 | Highway | STI (Prioritization) | SR 2085 (Bryan Boulevard) | New Garden Road at Horsepen Creek Road in Greensboro. | Interchange improvements, including new ramp from westbound new garden road to westbound SR 2085 (Bryan Boulevard). | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 680000
U-6008 | Highway | STI (Prioritization) | SR 2085 (Bryan Boulevard) | New Garden Road at Horsepen Creek Road in Greensboro. | Interchange improvements, including new ramp from westbound new garden road to westbound SR 2085 (Bryan Boulevard). | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2100000
U-6008 | Highway | STI (Prioritization) | SR 2085 (Bryan Boulevard) | New Garden Road at Horsepen Creek Road in Greensboro. | Interchange improvements, including new ramp from westbound new garden road to westbound SR 2085 (Bryan Boulevard). | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 290000
U-6008 | Highway | STI (Prioritization) | SR 2085 (Bryan Boulevard) | New Garden Road at Horsepen Creek Road in Greensboro. | Interchange improvements, including new ramp from westbound new garden road to westbound SR 2085 (Bryan Boulevard). | 1 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 7600000
U-6009 | Highway | STI (Prioritization) | US 70 (South Church Street) | Tarleton Avenue to Fifth Street in Burlington. | Widen and construct center turn lane. | 0.93 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Region D |  |  |  | 650000
U-6009 | Highway | STI (Prioritization) | US 70 (South Church Street) | Tarleton Avenue to Fifth Street in Burlington. | Widen and construct center turn lane. | 0.93 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Region D |  | T | RIGHT-OF-WAY | 26600000 | FY 2028: 1064000; FY 2029: 12768000; FY 2030: 7448000; FY 2031: 2660000; FY 2032: 2660000
U-6009 | Highway | STI (Prioritization) | US 70 (South Church Street) | Tarleton Avenue to Fifth Street in Burlington. | Widen and construct center turn lane. | 0.93 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Region D |  | T | UTILITIES | 2100000 | FY 2028: 1050000; FY 2029: 1050000
U-6009 | Highway | STI (Prioritization) | US 70 (South Church Street) | Tarleton Avenue to Fifth Street in Burlington. | Widen and construct center turn lane. | 0.93 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Region D |  | T | BUILD NC CON | 13005000 |  |  |  |  | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 6069000
U-6009 | Highway | STI (Prioritization) | US 70 (South Church Street) | Tarleton Avenue to Fifth Street in Burlington. | Widen and construct center turn lane. | 0.93 | Alamance | 7 | Burlington-Graham MPO | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE). | Region D |  | T | CONSTRUCTION | 10300000 | FY 2030: 0; FY 2031: 4819000; FY 2032: 4669000; FY 2033: 812000
U-6010 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1226 / SR 1311 (University Drive) intersection in Burlington. | Construct intersection improvements, to include widening of US 70 to maintain consistent cross-section with project U-5752 improvements. | 5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  |  |  | 3450000
U-6010 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1226 / SR 1311 (University Drive) intersection in Burlington. | Construct intersection improvements, to include widening of US 70 to maintain consistent cross-section with project U-5752 improvements. | 5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  | T | RIGHT-OF-WAY | 6000000
U-6010 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1226 / SR 1311 (University Drive) intersection in Burlington. | Construct intersection improvements, to include widening of US 70 to maintain consistent cross-section with project U-5752 improvements. | 5 | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  | T | CONSTRUCTION | 16100000
U-6011 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1158 (Huffman Mill Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | Under construction. | Region D |  |  |  | 450000
U-6011 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1158 (Huffman Mill Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | Under construction. | Region D |  | T | RIGHT-OF-WAY | 3000000
U-6011 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1158 (Huffman Mill Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | Under construction. | Region D |  | T | UTILITIES | 630000
U-6011 | Highway | STI (Prioritization) | US 70 (South Church Street) | SR 1158 (Huffman Mill Road) intersection in Burlington. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | Under construction. | Region D |  | T | CONSTRUCTION | 7080000 | FY 2026: 4080000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (Trollingwood-Hawfields Road) / SR 2126 (Old Hillsborough Road) to Lowes Boulevard in Mebane. | Widen to a four lane divided facility. | 0.52 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 1391000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (Trollingwood-Hawfields Road) / SR 2126 (Old Hillsborough Road) to Lowes Boulevard in Mebane. | Widen to a four lane divided facility. | 0.52 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 5500000 | FY 2026: 550000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (Trollingwood-Hawfields Road) / SR 2126 (Old Hillsborough Road) to Lowes Boulevard in Mebane. | Widen to a four lane divided facility. | 0.52 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 900000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (Trollingwood-Hawfields Road) / SR 2126 (Old Hillsborough Road) to Lowes Boulevard in Mebane. | Widen to a four lane divided facility. | 0.52 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 9999000 | FY 2028: 100000; FY 2029: 5999000; FY 2030: 2900000; FY 2031: 1000000
U-6014 | Highway | STI (Prioritization) | SR 1716 (Graham- Hopedale Road) | SR 1720 (West Hanover Road) to Morningside Drive in Burlington. | Widen to a three lane facility with bike-ped accommodations. | 1.38 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 1205000
U-6014 | Highway | STI (Prioritization) | SR 1716 (Graham- Hopedale Road) | SR 1720 (West Hanover Road) to Morningside Drive in Burlington. | Widen to a three lane facility with bike-ped accommodations. | 1.38 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 1500000 | FY 2026: 457000; FY 2027: 150000; FY 2028: 150000
U-6014 | Highway | STI (Prioritization) | SR 1716 (Graham- Hopedale Road) | SR 1720 (West Hanover Road) to Morningside Drive in Burlington. | Widen to a three lane facility with bike-ped accommodations. | 1.38 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 1200000 | FY 2026: 600000
U-6014 | Highway | STI (Prioritization) | SR 1716 (Graham- Hopedale Road) | SR 1720 (West Hanover Road) to Morningside Drive in Burlington. | Widen to a three lane facility with bike-ped accommodations. | 1.38 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 19100000 | FY 2027: 6685000; FY 2028: 7067000; FY 2029: 3438000; FY 2030: 1910000
U-6015 | Highway | STI (Prioritization) | Various | Routes in Burlington and Graham | Upgrade Burlington-Graham signal system. |  | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  |  |  | 3094000
U-6015 | Highway | STI (Prioritization) | Various | Routes in Burlington and Graham | Upgrade Burlington-Graham signal system. |  | Alamance | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 6125000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 413000
U-6016 | Highway | STI (Prioritization) | SR 2124 (Lewiston Road) | SR 2136 (Fleming Road) intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 350000
U-6016 | Highway | STI (Prioritization) | SR 2124 (Lewiston Road) | SR 2136 (Fleming Road) intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 836000
U-6016 | Highway | STI (Prioritization) | SR 2124 (Lewiston Road) | SR 2136 (Fleming Road) intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 302000
U-6016 | Highway | STI (Prioritization) | SR 2124 (Lewiston Road) | SR 2136 (Fleming Road) intersection in Greensboro. | Construct intersection improvements. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 2049000 | FY 2026: 1866000; FY 2027: 163000
U-6017 | Highway | STI (Prioritization) | NC 54 (East Harden Street) | NC 49 (East Elm Street) intersection in Graham. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 949000
U-6017 | Highway | STI (Prioritization) | NC 54 (East Harden Street) | NC 49 (East Elm Street) intersection in Graham. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 2000000
U-6017 | Highway | STI (Prioritization) | NC 54 (East Harden Street) | NC 49 (East Elm Street) intersection in Graham. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 550000
U-6017 | Highway | STI (Prioritization) | NC 54 (East Harden Street) | NC 49 (East Elm Street) intersection in Graham. | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 2100000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (Kersey Valley Road) to SR 1162 (Weant Road) in Archdale. | Improve interchange and realign intersections. | 1 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10M FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 7 |  |  |  | 17000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (Kersey Valley Road) to SR 1162 (Weant Road) in Archdale. | Improve interchange and realign intersections. | 1 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10M FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 7 |  | T | RIGHT-OF-WAY | 2600000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (Kersey Valley Road) to SR 1162 (Weant Road) in Archdale. | Improve interchange and realign intersections. | 1 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10M FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 7 |  | T | UTILITIES | 2811000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (Kersey Valley Road) to SR 1162 (Weant Road) in Archdale. | Improve interchange and realign intersections. | 1 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10M FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 7 |  | T | BUILD NC CON | 13005000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 4335000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (Kersey Valley Road) to SR 1162 (Weant Road) in Archdale. | Improve interchange and realign intersections. | 1 | Guilford | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10M FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 7 |  | T | CONSTRUCTION | 14100000 | FY 2026: 0; FY 2027: 7111000; FY 2028: 4097000; FY 2029: 2892000
U-6019 | Highway | STI (Prioritization) | SR 2334 (Air Harbor Road) | SR 2347 (Lake Brandt Road) | Construct turn lanes and sidewalks. |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 425000
U-6019 | Highway | STI (Prioritization) | SR 2334 (Air Harbor Road) | SR 2347 (Lake Brandt Road) | Construct turn lanes and sidewalks. |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T | CONSTRUCTION | 1586000
U-6020 | Highway | STI (Prioritization) | NC 56 (East C Street) | SR 1215 (West Lyon Station Road) intersection in Butner. | Realign intersection. | 0.5 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  |  |  | 1500000
U-6020 | Highway | STI (Prioritization) | NC 56 (East C Street) | SR 1215 (West Lyon Station Road) intersection in Butner. | Realign intersection. | 0.5 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  | T | RIGHT-OF-WAY | 100000
U-6020 | Highway | STI (Prioritization) | NC 56 (East C Street) | SR 1215 (West Lyon Station Road) intersection in Butner. | Realign intersection. | 0.5 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  | T | CONSTRUCTION | 6150000 | FY 2026: 2657000; FY 2027: 376000
U-6020 | Highway | STI (Prioritization) | NC 56 (East C Street) | SR 1215 (West Lyon Station Road) intersection in Butner. | Realign intersection. | 0.5 | Granville | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  | L | CONSTRUCTION | 2050000 | FY 2026: 918000; FY 2027: 67000
U-6022 | Highway | STI (Prioritization) | Various | Routes in the Town of Fuquay-Varina | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  |  |  | 325000
U-6022 | Highway | STI (Prioritization) | Various | Routes in the Town of Fuquay-Varina | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | BGANY | UTILITIES | 451000
U-6022 | Highway | STI (Prioritization) | Various | Routes in the Town of Fuquay-Varina | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | BGANY | CONSTRUCTION | 4092000
U-6023 | Highway | STI (Prioritization) | Various | Routes in the Town of Wake Forest | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  |  |  | 451000
U-6023 | Highway | STI (Prioritization) | Various | Routes in the Town of Wake Forest | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGANY | UTILITIES | 250000
U-6023 | Highway | STI (Prioritization) | Various | Routes in the Town of Wake Forest | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGANY | CONSTRUCTION | 4176000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (Bickett Boulevard) | Burke Boulevard to NC 56 / NC 581 (Nash Street) in Louisburg. | Upgrade 5-lane section to 4-lane divided facility with bicycle/pedestrian accommodations. | 1.38 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 750000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (Bickett Boulevard) | Burke Boulevard to NC 56 / NC 581 (Nash Street) in Louisburg. | Upgrade 5-lane section to 4-lane divided facility with bicycle/pedestrian accommodations. | 1.38 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6800000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (Bickett Boulevard) | Burke Boulevard to NC 56 / NC 581 (Nash Street) in Louisburg. | Upgrade 5-lane section to 4-lane divided facility with bicycle/pedestrian accommodations. | 1.38 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2800000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (Bickett Boulevard) | Burke Boulevard to NC 56 / NC 581 (Nash Street) in Louisburg. | Upgrade 5-lane section to 4-lane divided facility with bicycle/pedestrian accommodations. | 1.38 | Franklin | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 38800000
U-6026 | Highway | STI (Prioritization) | Various | Routes in the Town of Knightdale | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION. UNDER CONSTRUCTION | Division 5 |  |  |  | 324000
U-6026 | Highway | STI (Prioritization) | Various | Routes in the Town of Knightdale | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION. UNDER CONSTRUCTION | Division 5 |  | BGANY | UTILITIES | 450000
U-6026 | Highway | STI (Prioritization) | Various | Routes in the Town of Knightdale | Construct townwide ITS / signal system. |  | Wake | 5 | Capital Area MPO | FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION. UNDER CONSTRUCTION | Division 5 |  | BGANY | CONSTRUCTION | 2320000
U-6027 | Highway | STI (Prioritization) | US 1 (Proposed) / SR 1516 (Greene Street) | US 220 to US 1 in Rockingham. | Widen to 3-lane facility and re-route US 1 along project. | 0.54 | Richmond | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 650000
U-6027 | Highway | STI (Prioritization) | US 1 (Proposed) / SR 1516 (Greene Street) | US 220 to US 1 in Rockingham. | Widen to 3-lane facility and re-route US 1 along project. | 0.54 | Richmond | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | RIGHT-OF-WAY | 2199000 | FY 2026: 556000; FY 2027: 556000; FY 2028: 556000; FY 2029: 440000
U-6027 | Highway | STI (Prioritization) | US 1 (Proposed) / SR 1516 (Greene Street) | US 220 to US 1 in Rockingham. | Widen to 3-lane facility and re-route US 1 along project. | 0.54 | Richmond | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 1300000
U-6027 | Highway | STI (Prioritization) | US 1 (Proposed) / SR 1516 (Greene Street) | US 220 to US 1 in Rockingham. | Widen to 3-lane facility and re-route US 1 along project. | 0.54 | Richmond | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 8100000 | FY 2028: 81000; FY 2029: 4050000; FY 2030: 2997000; FY 2031: 972000
U-6028 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) | SR 2472 (Mallard Creek Church Road) to Breezewood Drive. | Widen to four lanes. | 1.48 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2340000
U-6028 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) | SR 2472 (Mallard Creek Church Road) to Breezewood Drive. | Widen to four lanes. | 1.48 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 12300000
U-6028 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) | SR 2472 (Mallard Creek Church Road) to Breezewood Drive. | Widen to four lanes. | 1.48 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 14700000
U-6028 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) | SR 2472 (Mallard Creek Church Road) to Breezewood Drive. | Widen to four lanes. | 1.48 | Mecklenburg | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 30000000
U-6031 | Highway | STI (Prioritization) | SR 1009 (Charlotte Avenue) | Seymour Street to NC 200 (Dickerson Boulevard). | Widen to four lanes divided. | 0.37 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 330000
U-6031 | Highway | STI (Prioritization) | SR 1009 (Charlotte Avenue) | Seymour Street to NC 200 (Dickerson Boulevard). | Widen to four lanes divided. | 0.37 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3900000
U-6031 | Highway | STI (Prioritization) | SR 1009 (Charlotte Avenue) | Seymour Street to NC 200 (Dickerson Boulevard). | Widen to four lanes divided. | 0.37 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3100000
U-6031 | Highway | STI (Prioritization) | SR 1009 (Charlotte Avenue) | Seymour Street to NC 200 (Dickerson Boulevard). | Widen to four lanes divided. | 0.37 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 18100000
U-6032 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) / SR 1445 (Derita Road) | I-485 to SR 2894 (Concord Mills Boulevard) | Widen to six lanes. | 0.87 | Mecklenburg, Cabarrus | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $14M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 10 |  |  |  | 2900000
U-6032 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) / SR 1445 (Derita Road) | I-485 to SR 2894 (Concord Mills Boulevard) | Widen to six lanes. | 0.87 | Mecklenburg, Cabarrus | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $14M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 10 |  | T | RIGHT-OF-WAY | 11500000 | FY 2026: 4800000
U-6032 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) / SR 1445 (Derita Road) | I-485 to SR 2894 (Concord Mills Boulevard) | Widen to six lanes. | 0.87 | Mecklenburg, Cabarrus | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $14M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 10 |  | T | UTILITIES | 2514000 | FY 2026: 1225000; FY 2027: 1225000
U-6032 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) / SR 1445 (Derita Road) | I-485 to SR 2894 (Concord Mills Boulevard) | Widen to six lanes. | 0.87 | Mecklenburg, Cabarrus | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $14M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 10 |  | T | BUILD NC CON | 18195000 |  |  |  |  | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 10917000
U-6032 | Highway | STI (Prioritization) | SR 2467 (Mallard Creek Road) / SR 1445 (Derita Road) | I-485 to SR 2894 (Concord Mills Boulevard) | Widen to six lanes. | 0.87 | Mecklenburg, Cabarrus | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $14M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 10 |  | T | CONSTRUCTION | 27400000 | FY 2029: 5796000; FY 2030: 0; FY 2031: 9598000; FY 2032: 7038000; FY 2033: 4968000
U-6033 | Highway | STI (Prioritization) | US 64 / NC 18 | SR 1142 (Callico Road) intersection. | Upgrade roadway. | 0.5 | Caldwell | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  |  |  | 137000
U-6033 | Highway | STI (Prioritization) | US 64 / NC 18 | SR 1142 (Callico Road) intersection. | Upgrade roadway. | 0.5 | Caldwell | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | T | RIGHT-OF-WAY | 400000
U-6033 | Highway | STI (Prioritization) | US 64 / NC 18 | SR 1142 (Callico Road) intersection. | Upgrade roadway. | 0.5 | Caldwell | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | T | UTILITIES | 668000
U-6033 | Highway | STI (Prioritization) | US 64 / NC 18 | SR 1142 (Callico Road) intersection. | Upgrade roadway. | 0.5 | Caldwell | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | T | CONSTRUCTION | 4261000
U-6034 | Highway | STI (Prioritization) | US 321 Alternate | SR 1109 (Pinewood Road) to SR 1106 (Duke Street) | Upgrade roadway. | 1.33 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  |  |  | 349000
U-6034 | Highway | STI (Prioritization) | US 321 Alternate | SR 1109 (Pinewood Road) to SR 1106 (Duke Street) | Upgrade roadway. | 1.33 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | RIGHT-OF-WAY | 16000000 | FY 2026: 4654000; FY 2027: 4267000; FY 2028: 1600000; FY 2029: 1600000
U-6034 | Highway | STI (Prioritization) | US 321 Alternate | SR 1109 (Pinewood Road) to SR 1106 (Duke Street) | Upgrade roadway. | 1.33 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | UTILITIES | 3000000 | FY 2026: 2250000
U-6034 | Highway | STI (Prioritization) | US 321 Alternate | SR 1109 (Pinewood Road) to SR 1106 (Duke Street) | Upgrade roadway. | 1.33 | Caldwell | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | CONSTRUCTION | 27300000 | FY 2029: 273000; FY 2030: 8463000; FY 2031: 7917000; FY 2032: 6006000; FY 2033: 4641000
U-6035 | Highway | STI (Prioritization) | SR 1002 (Dudley Shoals Road) | Grace Chapel Road / Campground Road / SR 1752 (Peach Orchard Road) intersection in Granite Falls. | Construct roundabout. |  | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  |  |  | 1207000
U-6035 | Highway | STI (Prioritization) | SR 1002 (Dudley Shoals Road) | Grace Chapel Road / Campground Road / SR 1752 (Peach Orchard Road) intersection in Granite Falls. | Construct roundabout. |  | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | UTILITIES | 75000
U-6035 | Highway | STI (Prioritization) | SR 1002 (Dudley Shoals Road) | Grace Chapel Road / Campground Road / SR 1752 (Peach Orchard Road) intersection in Granite Falls. | Construct roundabout. |  | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | CONSTRUCTION | 2900000
U-6036 | Highway | STI (Prioritization) | SR 1109 (Pinewood Road) | US 321 to SR 1931 (Bert Huffman Road). | Upgrade roadway. | 0.6 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  |  |  | 800000
U-6036 | Highway | STI (Prioritization) | SR 1109 (Pinewood Road) | US 321 to SR 1931 (Bert Huffman Road). | Upgrade roadway. | 0.6 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | RIGHT-OF-WAY | 1500000
U-6036 | Highway | STI (Prioritization) | SR 1109 (Pinewood Road) | US 321 to SR 1931 (Bert Huffman Road). | Upgrade roadway. | 0.6 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | UTILITIES | 560000
U-6036 | Highway | STI (Prioritization) | SR 1109 (Pinewood Road) | US 321 to SR 1931 (Bert Huffman Road). | Upgrade roadway. | 0.6 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | CONSTRUCTION | 13317000 | FY 2026: 4528000; FY 2027: 2131000
U-6037 | Highway | STI (Prioritization) | US 21 (Charlotte Highway) | NC 150 (Plaza Drive) to SR 1245 (Medical Park Road). | Widen to four lanes divided. | 2.64 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 5000000
U-6037 | Highway | STI (Prioritization) | US 21 (Charlotte Highway) | NC 150 (Plaza Drive) to SR 1245 (Medical Park Road). | Widen to four lanes divided. | 2.64 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 39900000
U-6037 | Highway | STI (Prioritization) | US 21 (Charlotte Highway) | NC 150 (Plaza Drive) to SR 1245 (Medical Park Road). | Widen to four lanes divided. | 2.64 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2500000
U-6037 | Highway | STI (Prioritization) | US 21 (Charlotte Highway) | NC 150 (Plaza Drive) to SR 1245 (Medical Park Road). | Widen to four lanes divided. | 2.64 | Iredell | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 77000000
U-6038 | Highway | STI (Prioritization) | US 74 (Wilkinson Boulevard) | NC 7 (Catawba Street) to SR 2209 (Wesleyan Drive). | Implement adaptive signal system. | 3.87 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Division 12 |  |  |  | 735000
U-6038 | Highway | STI (Prioritization) | US 74 (Wilkinson Boulevard) | NC 7 (Catawba Street) to SR 2209 (Wesleyan Drive). | Implement adaptive signal system. | 3.87 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Division 12 |  | T | BUILD NC CON | 600000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
U-6039 | Highway | STI (Prioritization) | SR 2321 (East Broad Street) | Vine Street to SR 2422 (Signal Hill Drive). | Upgrade roadway and implement access management solutions. | 0.68 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B | Division 12 |  |  |  | 10050000
U-6039 | Highway | STI (Prioritization) | SR 2321 (East Broad Street) | Vine Street to SR 2422 (Signal Hill Drive). | Upgrade roadway and implement access management solutions. | 0.68 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B | Division 12 |  | T | CONSTRUCTION | 5350000
U-6041 | Highway | STI (Prioritization) | US 64 | SR 1124 (Church Road). | Construct left turn lane on westbound US 64 / NC 90. |  | Alexander | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  |  |  | 100000
U-6041 | Highway | STI (Prioritization) | US 64 | SR 1124 (Church Road). | Construct left turn lane on westbound US 64 / NC 90. |  | Alexander | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGLT5 | RIGHT-OF-WAY | 200000
U-6041 | Highway | STI (Prioritization) | US 64 | SR 1124 (Church Road). | Construct left turn lane on westbound US 64 / NC 90. |  | Alexander | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGLT5 | UTILITIES | 400000
U-6041 | Highway | STI (Prioritization) | US 64 | SR 1124 (Church Road). | Construct left turn lane on westbound US 64 / NC 90. |  | Alexander | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGLT5 | CONSTRUCTION | 2700000 | FY 2026: 944000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33rd Street Southwest) | SR 1642 (34th Street Northwest) intersection in Long View. | Realign intersection. | 0.5 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 375000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33rd Street Southwest) | SR 1642 (34th Street Northwest) intersection in Long View. | Realign intersection. | 0.5 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2500000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33rd Street Southwest) | SR 1642 (34th Street Northwest) intersection in Long View. | Realign intersection. | 0.5 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 500000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33rd Street Southwest) | SR 1642 (34th Street Northwest) intersection in Long View. | Realign intersection. | 0.5 | Catawba | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5800000
U-6043 | Highway | STI (Prioritization) | US 29 / US 74 (Franklin Boulevard) | SR 2200 (Cox Road) to 400 feet east of Lineberger Road. | Construct additional lane in the eastbound direction. | 1.06 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  |  |  | 1300000
U-6043 | Highway | STI (Prioritization) | US 29 / US 74 (Franklin Boulevard) | SR 2200 (Cox Road) to 400 feet east of Lineberger Road. | Construct additional lane in the eastbound direction. | 1.06 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | RIGHT-OF-WAY | 1300000 | FY 2026: 130000; FY 2027: 130000
U-6043 | Highway | STI (Prioritization) | US 29 / US 74 (Franklin Boulevard) | SR 2200 (Cox Road) to 400 feet east of Lineberger Road. | Construct additional lane in the eastbound direction. | 1.06 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | UTILITIES | 900000
U-6043 | Highway | STI (Prioritization) | US 29 / US 74 (Franklin Boulevard) | SR 2200 (Cox Road) to 400 feet east of Lineberger Road. | Construct additional lane in the eastbound direction. | 1.06 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BG50200 | CONSTRUCTION | 7900000 | FY 2026: 1884000; FY 2027: 4913000; FY 2028: 1103000
U-6044 | Highway | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to US 29 / US 74. | Widen road and construct operational improvements. | 0.27 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH I-5719. | Division 12 |  |  |  | 1000000
U-6044 | Highway | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to US 29 / US 74. | Widen road and construct operational improvements. | 0.27 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH I-5719. | Division 12 |  | BG50200 | RIGHT-OF-WAY | 49500000 | FY 2029: 19800000; FY 2030: 19800000; FY 2031: 4950000; FY 2032: 4950000
U-6044 | Highway | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to US 29 / US 74. | Widen road and construct operational improvements. | 0.27 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH I-5719. | Division 12 |  | BG50200 | UTILITIES | 1500000 | FY 2029: 750000; FY 2030: 750000
U-6044 | Highway | STI (Prioritization) | SR 2200 (Cox Road) | I-85 to US 29 / US 74. | Widen road and construct operational improvements. | 0.27 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH I-5719. | Division 12 |  | BG50200 | CONSTRUCTION | 14300000 | FY 2029: 6435000; FY 2030: 5577000; FY 2031: 2288000
U-6045 | Highway | STI (Prioritization) | SR 1850 (Sandy Ridge Road) | I-40 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 0.69 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 250000
U-6045 | Highway | STI (Prioritization) | SR 1850 (Sandy Ridge Road) | I-40 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 0.69 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9100000
U-6045 | Highway | STI (Prioritization) | SR 1850 (Sandy Ridge Road) | I-40 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 0.69 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 590000
U-6045 | Highway | STI (Prioritization) | SR 1850 (Sandy Ridge Road) | I-40 to SR 1008 (West Market Street) in Greensboro. | Widen to multi-lanes. | 0.69 | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40100000
U-6047 | Highway | STI (Prioritization) | NC 112 (Sardis Road/ Sandhill Road) | NC 191 (Brevard Road) to US 19 / US 23 (Smokey Park Highway). | Widen roadway to multi-lanes. | 3.59 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 6100000
U-6047 | Highway | STI (Prioritization) | NC 112 (Sardis Road/ Sandhill Road) | NC 191 (Brevard Road) to US 19 / US 23 (Smokey Park Highway). | Widen roadway to multi-lanes. | 3.59 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 61100000
U-6047 | Highway | STI (Prioritization) | NC 112 (Sardis Road/ Sandhill Road) | NC 191 (Brevard Road) to US 19 / US 23 (Smokey Park Highway). | Widen roadway to multi-lanes. | 3.59 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 7900000
U-6047 | Highway | STI (Prioritization) | NC 112 (Sardis Road/ Sandhill Road) | NC 191 (Brevard Road) to US 19 / US 23 (Smokey Park Highway). | Widen roadway to multi-lanes. | 3.59 | Buncombe | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 106800000
U-6048 | Highway | STI (Prioritization) | US 19 / US 23 | SR 1836 (Chestnut Mountain Road) to SR 1200 (Wiggins Road). | Upgrade roadway. | 3.85 | Haywood, Buncombe | 13, 14 | French Broad River MPO |  | Division 13, 14 |  |  |  | 2226000
U-6048 | Highway | STI (Prioritization) | US 19 / US 23 | SR 1836 (Chestnut Mountain Road) to SR 1200 (Wiggins Road). | Upgrade roadway. | 3.85 | Haywood, Buncombe | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | T | RIGHT-OF-WAY | 1000000 | FY 2030: 1000000
U-6048 | Highway | STI (Prioritization) | US 19 / US 23 | SR 1836 (Chestnut Mountain Road) to SR 1200 (Wiggins Road). | Upgrade roadway. | 3.85 | Haywood, Buncombe | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | T | UTILITIES | 700000 | FY 2030: 700000
U-6048 | Highway | STI (Prioritization) | US 19 / US 23 | SR 1836 (Chestnut Mountain Road) to SR 1200 (Wiggins Road). | Upgrade roadway. | 3.85 | Haywood, Buncombe | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | T | CONSTRUCTION | 41600000 | FY 2033: 4992000; FY 2034: 11648000; FY 2035: 10400000 | 14560000
U-6049 | Highway | STI (Prioritization) | NC 225 (South Main Street) | South Main Street at South King Street to US 176. | Widen bridge 440143 to five lanes. | 0.24 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  |  |  | 680000
U-6049 | Highway | STI (Prioritization) | NC 225 (South Main Street) | South Main Street at South King Street to US 176. | Widen bridge 440143 to five lanes. | 0.24 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  | T | RIGHT-OF-WAY | 3400000 | FY 2026: 351000; FY 2027: 680000
U-6049 | Highway | STI (Prioritization) | NC 225 (South Main Street) | South Main Street at South King Street to US 176. | Widen bridge 440143 to five lanes. | 0.24 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  | T | UTILITIES | 400000
U-6049 | Highway | STI (Prioritization) | NC 225 (South Main Street) | South Main Street at South King Street to US 176. | Widen bridge 440143 to five lanes. | 0.24 | Henderson | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  | BGANY | CONSTRUCTION | 8800000 | FY 2029: 3960000; FY 2030: 3520000; FY 2031: 1320000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  |  |  | 166000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGDA | ENGINEERING | 225000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | ENGINEERING | 101000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGANY | RIGHT-OF-WAY | 331000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGDA | RIGHT-OF-WAY | 732000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | RIGHT-OF-WAY | 477000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGANY | CONSTRUCTION | 1644000 | FY 2026: 1644000
U-6054 | Highway | Locally Selected | New Route | Brookdale Drive to US 21. | Construct roadway. | 0.09 | Iredell | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | CONSTRUCTION | 574000 | FY 2026: 574000
U-6055 | Highway | Locally Selected | NC 110 (Pisgah Drive) | Locust Street intersection in Canton. | Construct intersection improvements. | 0.5 | Haywood | 14 | French Broad River MPO | UNDER CONSTRUCTION. STBGDA FUNDS ARE EXEMPT BECAUSE THEY ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE IS PAYING MATCH BECAUSE PROJECT CAME IN RANK ORDER OFF P3.0 PRIORITIZATION LIST | Exempt |  |  |  | 1816000
U-6058 | Highway | STI (Prioritization) | SR 1493 (Live Oak Street) | NC 101 intersection in Beaufort | Construct roundabout. |  | Carteret | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  |  |  | 300000
U-6058 | Highway | STI (Prioritization) | SR 1493 (Live Oak Street) | NC 101 intersection in Beaufort | Construct roundabout. |  | Carteret | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | T | RIGHT-OF-WAY | 1359000
U-6058 | Highway | STI (Prioritization) | SR 1493 (Live Oak Street) | NC 101 intersection in Beaufort | Construct roundabout. |  | Carteret | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | T | UTILITIES | 1200000
U-6058 | Highway | STI (Prioritization) | SR 1493 (Live Oak Street) | NC 101 intersection in Beaufort | Construct roundabout. |  | Carteret | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | BG5T50 | CONSTRUCTION | 5040000 | FY 2026: 3780000; FY 2027: 1210000
U-6058 | Highway | STI (Prioritization) | SR 1493 (Live Oak Street) | NC 101 intersection in Beaufort | Construct roundabout. |  | Carteret | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | T(M) | CONSTRUCTION | 1260000 | FY 2026: 945000; FY 2027: 302000
U-6059 | Highway | STI (Prioritization) | US 421 (Salem Parkway) | Interchange at SR 2662 (Linville Road) and Bridge 330211 on SR 2237 (Old Greensboro Road Northeast) over Norfolk Southern Railroad In Winston-Salem. | Upgrade interchange and replace bridge. | 1.5 | Forsyth | 9 | Winston-Salem Area TPO | [5 empty] | 150000
U-6059A | Highway | Bridges | SR 2377 (Old Greensboro Road NE) | Bridge 330211 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 450000 | FY 2026: 63000; FY 2027: 157000; FY 2028: 140000; FY 2029: 45000; FY 2030: 45000
U-6059A | Highway | Bridges | SR 2377 (Old Greensboro Road NE) | Bridge 330211 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 1100000 | FY 2026: 550000; FY 2027: 550000
U-6059A | Highway | Bridges | SR 2377 (Old Greensboro Road NE) | Bridge 330211 over Norfolk Southern Railroad. | Replace bridge. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 12900000 | FY 2028: 129000; FY 2029: 5934000; FY 2030: 4257000; FY 2031: 2580000
U-6059B | Highway | STI (Prioritization) | US 421 (Salem Parkway) | SR 2662 (Linville Road) interchange | Upgrade interchange. | 1 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-6068 | Not Funded |  | T | RIGHT-OF-WAY | 12600000 | [10 empty] | 12600000
U-6059B | Highway | STI (Prioritization) | US 421 (Salem Parkway) | SR 2662 (Linville Road) interchange | Upgrade interchange. | 1 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-6068 | Not Funded |  | T | UTILITIES | 800000 | [10 empty] | 800000
U-6059B | Highway | STI (Prioritization) | US 421 (Salem Parkway) | SR 2662 (Linville Road) interchange | Upgrade interchange. | 1 | Forsyth | 9 | Winston-Salem Area TPO | COORDINATE WITH U-6068 | Not Funded |  | T | CONSTRUCTION | 42900000 | [10 empty] | 42900000
U-6062 | Highway | STI (Prioritization) | SR 2739 (North Main Street / South Main Street) | SR 2000 (Jackson Park Road) / North Loop Road in Kannapolis to SR 1211 (Kimball Road) in China Grove | Upgrade roadway incorporating bicycle lanes and sidewalks. | 4.26 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 750000
U-6062 | Highway | STI (Prioritization) | SR 2739 (North Main Street / South Main Street) | SR 2000 (Jackson Park Road) / North Loop Road in Kannapolis to SR 1211 (Kimball Road) in China Grove | Upgrade roadway incorporating bicycle lanes and sidewalks. | 4.26 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 33800000
U-6062 | Highway | STI (Prioritization) | SR 2739 (North Main Street / South Main Street) | SR 2000 (Jackson Park Road) / North Loop Road in Kannapolis to SR 1211 (Kimball Road) in China Grove | Upgrade roadway incorporating bicycle lanes and sidewalks. | 4.26 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 10800000
U-6062 | Highway | STI (Prioritization) | SR 2739 (North Main Street / South Main Street) | SR 2000 (Jackson Park Road) / North Loop Road in Kannapolis to SR 1211 (Kimball Road) in China Grove | Upgrade roadway incorporating bicycle lanes and sidewalks. | 4.26 | Rowan | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 35800000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (Sneads Ferry Road / SR 1518 (Old Folkstone Road)). | Construct reduced conflict intersection with intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  |  |  | 750000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (Sneads Ferry Road / SR 1518 (Old Folkstone Road)). | Construct reduced conflict intersection with intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 239000 | FY 2026: 218000; FY 2027: 19000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (Sneads Ferry Road / SR 1518 (Old Folkstone Road)). | Construct reduced conflict intersection with intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 1761000 | FY 2026: 1602000; FY 2027: 141000
U-6072 | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1140 (Strickland Bridge Road) to SR 1115 (Golfview Road). | Widen to multi-lanes. | 5.8 | Cumberland | 6 | Fayetteville Area MPO | [5 empty] | 4500000
U-6072A | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1102 (Gillis Hill Road) to Camden Road | Widen to multi-lanes. | 4.8 | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 13600000 | [10 empty] | 13600000
U-6072A | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1102 (Gillis Hill Road) to Camden Road | Widen to multi-lanes. | 4.8 | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 4960000 | [10 empty] | 4960000
U-6072A | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1102 (Gillis Hill Road) to Camden Road | Widen to multi-lanes. | 4.8 | Cumberland | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 24500000 | [10 empty] | 24500000
U-6072B | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1003 (Camden Road) to SR 1115 (Golfview Road) | Widen to multi-lanes. | 1.55 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 16500000
U-6072B | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1003 (Camden Road) to SR 1115 (Golfview Road) | Widen to multi-lanes. | 1.55 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 1800000
U-6072B | Highway | STI (Prioritization) | SR 1112 (Rockfish Road) | SR 1003 (Camden Road) to SR 1115 (Golfview Road) | Widen to multi-lanes. | 1.55 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 6800000
U-6073 | Highway | STI (Prioritization) | SR 1107 (Fisher Road) | SR 1104 (Strickland Bridge Road) to NC 162 (Bingham Drive). | Widen to multi-lanes. | 2.1 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 2010000
U-6073 | Highway | STI (Prioritization) | SR 1107 (Fisher Road) | SR 1104 (Strickland Bridge Road) to NC 162 (Bingham Drive). | Widen to multi-lanes. | 2.1 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | RIGHT-OF-WAY | 22500000 | FY 2030: 7364000; FY 2031: 9818000; FY 2032: 818000; FY 2033: 2250000; FY 2034: 2250000
U-6073 | Highway | STI (Prioritization) | SR 1107 (Fisher Road) | SR 1104 (Strickland Bridge Road) to NC 162 (Bingham Drive). | Widen to multi-lanes. | 2.1 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | UTILITIES | 2400000 | FY 2030: 1200000; FY 2031: 1200000
U-6073 | Highway | STI (Prioritization) | SR 1107 (Fisher Road) | SR 1104 (Strickland Bridge Road) to NC 162 (Bingham Drive). | Widen to multi-lanes. | 2.1 | Cumberland | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | CONSTRUCTION | 25100000 | FY 2033: 7279000; FY 2034: 8032000; FY 2035: 6275000 | 3514000
U-6078 | Highway | STI (Prioritization) | NC 275; SR 1327 (Fairview Road) | NC 274 and SR 1327 (Fairview Road) intersections in Gastonia; SR 1456 (White Jenkins Road) intersection in Gastonia. | Construct intersection improvements and close intersection of NC 275 and SR 1456 (White Jenkins Road). | 1.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 200000
U-6078 | Highway | STI (Prioritization) | NC 275; SR 1327 (Fairview Road) | NC 274 and SR 1327 (Fairview Road) intersections in Gastonia; SR 1456 (White Jenkins Road) intersection in Gastonia. | Construct intersection improvements and close intersection of NC 275 and SR 1456 (White Jenkins Road). | 1.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 1400000 | FY 2026: 640000; FY 2027: 107000; FY 2028: 140000; FY 2029: 140000
U-6078 | Highway | STI (Prioritization) | NC 275; SR 1327 (Fairview Road) | NC 274 and SR 1327 (Fairview Road) intersections in Gastonia; SR 1456 (White Jenkins Road) intersection in Gastonia. | Construct intersection improvements and close intersection of NC 275 and SR 1456 (White Jenkins Road). | 1.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGANY | UTILITIES | 780000
U-6078 | Highway | STI (Prioritization) | NC 275; SR 1327 (Fairview Road) | NC 274 and SR 1327 (Fairview Road) intersections in Gastonia; SR 1456 (White Jenkins Road) intersection in Gastonia. | Construct intersection improvements and close intersection of NC 275 and SR 1456 (White Jenkins Road). | 1.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGANY | CONSTRUCTION | 7900000 | FY 2027: 3318000; FY 2028: 3318000; FY 2029: 1264000
U-6082 | Highway | STI (Prioritization) | SR 1308 (Bell Fork Road) | SR 1403 (Country Club Road / Hargett Street). | Construct intersection improvements. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 500000
U-6082 | Highway | STI (Prioritization) | SR 1308 (Bell Fork Road) | SR 1403 (Country Club Road / Hargett Street). | Construct intersection improvements. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BG50200 | RIGHT-OF-WAY | 2800000 | FY 2026: 670000; FY 2027: 840000; FY 2028: 630000; FY 2029: 560000
U-6082 | Highway | STI (Prioritization) | SR 1308 (Bell Fork Road) | SR 1403 (Country Club Road / Hargett Street). | Construct intersection improvements. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BG50200 | UTILITIES | 1100000 | FY 2026: 550000
U-6082 | Highway | STI (Prioritization) | SR 1308 (Bell Fork Road) | SR 1403 (Country Club Road / Hargett Street). | Construct intersection improvements. | 1 | Onslow | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BG50200 | CONSTRUCTION | 12900000 | FY 2028: 1419000; FY 2029: 6063000; FY 2030: 4128000; FY 2031: 1290000
U-6084 | Highway | Economic Development | NC 16 (Brookshire Boulevard) | SR 2004 (Mount Holly Huntersville Road) intersection. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE. | Region E |  |  |  | 6135000
U-6084 | Highway | Economic Development | NC 16 (Brookshire Boulevard) | SR 2004 (Mount Holly Huntersville Road) intersection. | Construct intersection improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE. | Region E |  | T | CONSTRUCTION | 1963000
U-6085 | Highway | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS | Division 7 |  |  |  | 153000
U-6085 | Highway | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS | Division 7 |  | BGDA | PLANNING | 7285000 | FY 2026: 1280000; FY 2027: 1280000; FY 2028: 1280000
U-6085 | Highway | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization. | Planning (PL) Supplement. |  | Guilford | 7 | Greensboro Urban Area MPO | IN PROGRESS | Division 7 |  | L | PLANNING | 1821000 | FY 2026: 320000; FY 2027: 320000; FY 2028: 320000
U-6086 | Highway | Locally Selected | NC 51 | Park Road to Carmel Road. | Construct access management improvements. | 1.46 | Mecklenburg | 10 | Charlotte Regional TPO | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP | Exempt |  | BGANY | CONSTRUCTION | 5643000 | FY 2026: 2107000; FY 2027: 2423000; FY 2028: 1113000
U-6086 | Highway | Locally Selected | NC 51 | Park Road to Carmel Road. | Construct access management improvements. | 1.46 | Mecklenburg | 10 | Charlotte Regional TPO | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP | Exempt |  | L(M) | CONSTRUCTION | 1910000 | FY 2026: 1910000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | CMAQ | ENGINEERING | 25000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | BGDA | ENGINEERING | 263000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 66000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | HF(M) | ENGINEERING | 70000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 74000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | BGDA | RIGHT-OF-WAY | 791000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 198000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | HF | RIGHT-OF-WAY | 195000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | CRPDA | CONSTRUCTION | 1006000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 518000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 251000
U-6087 | Highway | Locally Selected | SR 1346 (Potter Road) | SR 1377 (Wesley Chapel Road) intersection in Wesley Chapel. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF IS SPOT MOBILITY AND RESURFACING FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | HF | CONSTRUCTION | 725000
U-6088 | Highway | Locally Selected | SR 1315 (New Town Road) | SR 1312 (Marvin Road) intersection in Marvin. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  |  |  | 800000
U-6088 | Highway | Locally Selected | SR 1315 (New Town Road) | SR 1312 (Marvin Road) intersection in Marvin. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1135000
U-6088 | Highway | Locally Selected | SR 1315 (New Town Road) | SR 1312 (Marvin Road) intersection in Marvin. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 362000
U-6088 | Highway | Locally Selected | SR 1315 (New Town Road) | SR 1312 (Marvin Road) intersection in Marvin. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 96000
U-6088 | Highway | Locally Selected | SR 1315 (New Town Road) | SR 1312 (Marvin Road) intersection in Marvin. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | HF(M) | CONSTRUCTION | 279000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  |  |  | 200000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | ENGINEERING | 258000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | HF(M) | ENGINEERING | 133000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 193000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 27000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | HF(M) | RIGHT-OF-WAY | 41000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1955000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 182000
U-6090 | Highway | Locally Selected | SR 1344 (Weddington-Matthews Road) | SR 1345 (Tilley Morris Road) intersection in Weddington. | Construct roundabout. |  | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | HF(M) | CONSTRUCTION | 306000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  |  |  | 150000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | ENGINEERING | 120000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | ENGINEERING | 30000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | RIGHT-OF-WAY | 515000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | RIGHT-OF-WAY | 120000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 160000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | CONSTRUCTION | 1207000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | CONSTRUCTION | 771000
U-6092 | Highway | Locally Selected | Davidson-Concord Road | Robert Walker Drive intersection in Davidson. | Construct roundabout. |  | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | CONSTRUCTION | 494000
U-6093 | Highway | Locally Selected | SR 2542 (Rock Quarry Road) | Olde Birch Road to SR 2544 (Sunnybrook Road) in Raleigh. | Widen to 4-lane divided facility. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  |  |  | 1230000
U-6093 | Highway | Locally Selected | SR 2542 (Rock Quarry Road) | Olde Birch Road to SR 2544 (Sunnybrook Road) in Raleigh. | Widen to 4-lane divided facility. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 1324000
U-6093 | Highway | Locally Selected | SR 2542 (Rock Quarry Road) | Olde Birch Road to SR 2544 (Sunnybrook Road) in Raleigh. | Widen to 4-lane divided facility. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 567000
U-6093 | Highway | Locally Selected | SR 2542 (Rock Quarry Road) | Olde Birch Road to SR 2544 (Sunnybrook Road) in Raleigh. | Widen to 4-lane divided facility. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 7743000
U-6093 | Highway | Locally Selected | SR 2542 (Rock Quarry Road) | Olde Birch Road to SR 2544 (Sunnybrook Road) in Raleigh. | Widen to 4-lane divided facility. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 3319000
U-6094 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | East of NC 55 to Flint Point Lane in Holly Springs. | Widen from 2 to 4 lanes. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  |  |  | 1022000
U-6094 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | East of NC 55 to Flint Point Lane in Holly Springs. | Widen from 2 to 4 lanes. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | BGDA | RIGHT-OF-WAY | 1184000
U-6094 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | East of NC 55 to Flint Point Lane in Holly Springs. | Widen from 2 to 4 lanes. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | L | RIGHT-OF-WAY | 296000
U-6094 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | East of NC 55 to Flint Point Lane in Holly Springs. | Widen from 2 to 4 lanes. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | BGDA | CONSTRUCTION | 1217000
U-6094 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | East of NC 55 to Flint Point Lane in Holly Springs. | Widen from 2 to 4 lanes. | 0.83 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | L | CONSTRUCTION | 304000
U-6098 | Highway | Economic Development | Various | NC 73 at SR 1430 and Access Road intersections; SR 1620 at SR 1621 (Barr Road) intersection; I-85 ramps at NC 73 interchange | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73; CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD); CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP |  | Cabarrus | 10 | Cabarrus-Rowan MPO | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION. | Division 10 |  |  |  | 850000
U-6098 | Highway | Economic Development | Various | NC 73 at SR 1430 and Access Road intersections; SR 1620 at SR 1621 (Barr Road) intersection; I-85 ramps at NC 73 interchange | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73; CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD); CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP |  | Cabarrus | 10 | Cabarrus-Rowan MPO | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION. | Division 10 |  | T | CONSTRUCTION | 1450000
U-6099 | Highway | Economic Development | SR 5220 (Jones Sausage Road) | SR 1004 (West Garner Road) to I-40 in Garner. | Widen roadway from south of SR 2585 (Wilmington Road) to I-40, including access point improvements, and construct improvements at SR 1004 intersection and I-40 interchange. | 1.44 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMAZON | Division 5 |  |  |  | 5100000
U-6100 | Highway | STI (Prioritization) | US 29 / US 70 / US 220 | SR 4240 (Gate City Boulevard) to south of I-785 in Greensboro. | Construct access management improvements and safety enhancements, including ramp closures and consolidations, reconfigure SR 2526 (Summit Avenue) / Phillips Avenue interchange, and replace bridges 400283 and 400342. | 5.09 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 5200000
U-6100 | Highway | STI (Prioritization) | US 29 / US 70 / US 220 | SR 4240 (Gate City Boulevard) to south of I-785 in Greensboro. | Construct access management improvements and safety enhancements, including ramp closures and consolidations, reconfigure SR 2526 (Summit Avenue) / Phillips Avenue interchange, and replace bridges 400283 and 400342. | 5.09 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2700000
U-6100 | Highway | STI (Prioritization) | US 29 / US 70 / US 220 | SR 4240 (Gate City Boulevard) to south of I-785 in Greensboro. | Construct access management improvements and safety enhancements, including ramp closures and consolidations, reconfigure SR 2526 (Summit Avenue) / Phillips Avenue interchange, and replace bridges 400283 and 400342. | 5.09 | Guilford | 7 | Greensboro Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 28400000
U-6103 | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | I-277 to west of Idlewild Road. | Widen roadway to allow for two-way express lane. This is a toll project (express lanes only). | 4.85 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 1010000
U-6103 | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | I-277 to west of Idlewild Road. | Widen roadway to allow for two-way express lane. This is a toll project (express lanes only). | 4.85 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 12000000 | FY 2030: 2160000; FY 2031: 2880000; FY 2032: 2880000; FY 2033: 1680000; FY 2034: 2400000
U-6103 | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | I-277 to west of Idlewild Road. | Widen roadway to allow for two-way express lane. This is a toll project (express lanes only). | 4.85 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | UTILITIES | 8100000 | FY 2030: 4050000; FY 2031: 4050000
U-6103 | Highway | STI (Prioritization) | US 74 (Independence Boulevard) | I-277 to west of Idlewild Road. | Widen roadway to allow for two-way express lane. This is a toll project (express lanes only). | 4.85 | Mecklenburg | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 248500000 | FY 2033: 32305000; FY 2034: 64610000; FY 2035: 59640000 | 91945000
U-6105 | Highway | Locally Selected | SR 2415 (Bailey Road) | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  |  |  | 490000
U-6105 | Highway | Locally Selected | SR 2415 (Bailey Road) | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | BGANY | RIGHT-OF-WAY | 756000
U-6105 | Highway | Locally Selected | SR 2415 (Bailey Road) | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | BGDA | RIGHT-OF-WAY | 276000
U-6105 | Highway | Locally Selected | SR 2415 (Bailey Road) | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | L | RIGHT-OF-WAY | 1032000
U-6105 | Highway | Locally Selected | SR 2415 (Bailey Road) | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | BGANY | CONSTRUCTION | 2243000 | FY 2026: 1188000; FY 2027: 850000; FY 2028: 205000
U-6105 | Highway | Locally Selected | SR 2415 (Bailey Road) | Poole Place Drive to US 21 (Statesville Road). | Construct roadway. | 0.35 | Mecklenburg | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | L | CONSTRUCTION | 2389000 | FY 2026: 2389000
U-6106 | Highway | Locally Selected | SR 2136 (Gilead Road) | SR 2120 (McCoy Road) to Wynfield Creek Parkway. | Widen to 4-lanes divided. | 0.47 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 1840000
U-6106 | Highway | Locally Selected | SR 2136 (Gilead Road) | SR 2120 (McCoy Road) to Wynfield Creek Parkway. | Widen to 4-lanes divided. | 0.47 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGDA | RIGHT-OF-WAY | 667000
U-6106 | Highway | Locally Selected | SR 2136 (Gilead Road) | SR 2120 (McCoy Road) to Wynfield Creek Parkway. | Widen to 4-lanes divided. | 0.47 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 627000
U-6106 | Highway | Locally Selected | SR 2136 (Gilead Road) | SR 2120 (McCoy Road) to Wynfield Creek Parkway. | Widen to 4-lanes divided. | 0.47 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 8253000
U-6106 | Highway | Locally Selected | SR 2136 (Gilead Road) | SR 2120 (McCoy Road) to Wynfield Creek Parkway. | Widen to 4-lanes divided. | 0.47 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 2431000
U-6109 | Highway | STI (Prioritization) | US 521 (Lancaster Highway / Johnston Road) | South Carolina State Line to SR 4979 (Ballantyne Commons Parkway). | Widen to multi-lanes. | 2.95 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 10000
U-6109 | Highway | STI (Prioritization) | US 521 (Lancaster Highway / Johnston Road) | South Carolina State Line to SR 4979 (Ballantyne Commons Parkway). | Widen to multi-lanes. | 2.95 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | NHP | RIGHT-OF-WAY | 11900000 | FY 2030: 952000; FY 2031: 2856000; FY 2032: 2975000; FY 2033: 2737000; FY 2034: 2380000
U-6109 | Highway | STI (Prioritization) | US 521 (Lancaster Highway / Johnston Road) | South Carolina State Line to SR 4979 (Ballantyne Commons Parkway). | Widen to multi-lanes. | 2.95 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | NHP | UTILITIES | 2100000 | FY 2030: 1050000; FY 2031: 1050000
U-6109 | Highway | STI (Prioritization) | US 521 (Lancaster Highway / Johnston Road) | South Carolina State Line to SR 4979 (Ballantyne Commons Parkway). | Widen to multi-lanes. | 2.95 | Mecklenburg | 10 | Charlotte Regional TPO |  | Region E |  | NHP | CONSTRUCTION | 52900000 | FY 2034: 529000; FY 2035: 17457000 | 34914000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (North Oak Forest Road) intersection in Goldsboro | Construct intersection improvements. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A |  |  |  | 10000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (North Oak Forest Road) intersection in Goldsboro | Construct intersection improvements. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | RIGHT-OF-WAY | 1300000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (North Oak Forest Road) intersection in Goldsboro | Construct intersection improvements. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | UTILITIES | 280000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (North Oak Forest Road) intersection in Goldsboro | Construct intersection improvements. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | CONSTRUCTION | 14000000 | FY 2027: 3220000; FY 2028: 6160000; FY 2029: 3780000; FY 2030: 840000
U-6111 | Highway | STI (Prioritization) | NC 58 (Nash Street Northwest) | SR 1330 (Airport Road) / SR 1332 (Lake Wilson Road) intersection in Wilson | Construct intersection improvements. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  |  |  | 10000
U-6111 | Highway | STI (Prioritization) | NC 58 (Nash Street Northwest) | SR 1330 (Airport Road) / SR 1332 (Lake Wilson Road) intersection in Wilson | Construct intersection improvements. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  | T | RIGHT-OF-WAY | 4800000 | FY 2028: 1104000; FY 2029: 2208000; FY 2030: 528000; FY 2031: 480000; FY 2032: 480000
U-6111 | Highway | STI (Prioritization) | NC 58 (Nash Street Northwest) | SR 1330 (Airport Road) / SR 1332 (Lake Wilson Road) intersection in Wilson | Construct intersection improvements. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  | T | UTILITIES | 720000 | FY 2028: 720000
U-6111 | Highway | STI (Prioritization) | NC 58 (Nash Street Northwest) | SR 1330 (Airport Road) / SR 1332 (Lake Wilson Road) intersection in Wilson | Construct intersection improvements. | 0.5 | Wilson | 4 | Upper Coastal Plain RPO |  | Region A |  | T | CONSTRUCTION | 8100000 | FY 2031: 3240000; FY 2032: 3564000; FY 2033: 1296000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (Ten-Ten Road) intersection in Fuquay-Varina. | Upgrade existing signalized intersection to square-loop interchange. | 1 | Wake | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (Ten-Ten Road) intersection in Fuquay-Varina. | Upgrade existing signalized intersection to square-loop interchange. | 1 | Wake | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 30480000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (Ten-Ten Road) intersection in Fuquay-Varina. | Upgrade existing signalized intersection to square-loop interchange. | 1 | Wake | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 6720000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (Ten-Ten Road) intersection in Fuquay-Varina. | Upgrade existing signalized intersection to square-loop interchange. | 1 | Wake | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 33600000
U-6114 | Highway | STI (Prioritization) | NC 62 (Alamance Road) | SR 1155 (Hatchery Road) / Bonnie Lane intersection in Burlington. | Install traffic signal and add turn lanes. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  |  |  | 10000
U-6114 | Highway | STI (Prioritization) | NC 62 (Alamance Road) | SR 1155 (Hatchery Road) / Bonnie Lane intersection in Burlington. | Install traffic signal and add turn lanes. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | T | RIGHT-OF-WAY | 770000 | FY 2028: 770000
U-6114 | Highway | STI (Prioritization) | NC 62 (Alamance Road) | SR 1155 (Hatchery Road) / Bonnie Lane intersection in Burlington. | Install traffic signal and add turn lanes. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | T | UTILITIES | 270000 | FY 2028: 270000
U-6114 | Highway | STI (Prioritization) | NC 62 (Alamance Road) | SR 1155 (Hatchery Road) / Bonnie Lane intersection in Burlington. | Install traffic signal and add turn lanes. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | T | CONSTRUCTION | 1800000 | FY 2031: 846000; FY 2032: 954000
U-6115 | Highway | STI (Prioritization) | NC 54 | SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) to south of SR 2107 (Whittemore Road) in Graham. | Construct SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) intersection improvements, upgrade ramp intersections at I-40 / I-85, construct SR 2106 (Woody Road) intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  |  |  | 10000
U-6115A | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) intersection in Graham | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2000000
U-6115A | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) intersection in Graham | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 520000
U-6115A | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 1945 (Riverbend Road) / SR 2431 (Johnson Street) intersection in Graham | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5200000
U-6115B | Highway | STI (Prioritization) | NC 54 (East Harden Street) | I-40 / I-85 interchange | Upgrade ramp intersections. | 1 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 880000
U-6115B | Highway | STI (Prioritization) | NC 54 (East Harden Street) | I-40 / I-85 interchange | Upgrade ramp intersections. | 1 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6115B | Highway | STI (Prioritization) | NC 54 (East Harden Street) | I-40 / I-85 interchange | Upgrade ramp intersections. | 1 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 10900000
U-6115C | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 2106 (Woody Drive) intersection | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2700000
U-6115C | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 2106 (Woody Drive) intersection | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 340000
U-6115C | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 2106 (Woody Drive) intersection | Construct intersection improvements. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4500000
U-6115D | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 2106 (Woody Drive) intersection and SR 2107 (Whittemore Road) intersection | Upgrade pipe culverts 000271 and 000297. |  | Alamance | 7 | Burlington-Graham MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 490000 | [10 empty] | 490000
U-6115D | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 2106 (Woody Drive) intersection and SR 2107 (Whittemore Road) intersection | Upgrade pipe culverts 000271 and 000297. |  | Alamance | 7 | Burlington-Graham MPO |  | Not Funded |  | T | UTILITIES | 120000 | [10 empty] | 120000
U-6115D | Highway | STI (Prioritization) | NC 54 (East Harden Street) | SR 2106 (Woody Drive) intersection and SR 2107 (Whittemore Road) intersection | Upgrade pipe culverts 000271 and 000297. |  | Alamance | 7 | Burlington-Graham MPO |  | Not Funded |  | T | CONSTRUCTION | 2100000 | [10 empty] | 2100000
U-6117 | Highway | STI (Prioritization) | Various | Apex townwide signal system. | Upgrade existing infrastructure and install new fiber, controllers, signals, and other equipment as necessary. |  | Wake | 5 | Capital Area MPO | BUILD NC BOND FUNDING: $3,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY2028/ YR 8 SALE). | Division 5 |  | BGANY | UTILITIES | 360000 | FY 2027: 360000
U-6117 | Highway | STI (Prioritization) | Various | Apex townwide signal system. | Upgrade existing infrastructure and install new fiber, controllers, signals, and other equipment as necessary. |  | Wake | 5 | Capital Area MPO | BUILD NC BOND FUNDING: $3,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY2028/ YR 8 SALE). | Division 5 |  | T | BUILD NC CON | 3900000 |  |  | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 1820000
U-6117 | Highway | STI (Prioritization) | Various | Apex townwide signal system. | Upgrade existing infrastructure and install new fiber, controllers, signals, and other equipment as necessary. |  | Wake | 5 | Capital Area MPO | BUILD NC BOND FUNDING: $3,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY2028/ YR 8 SALE). | Division 5 |  | BGANY | CONSTRUCTION | 3200000 | FY 2028: 286000; FY 2029: 2604000; FY 2030: 310000
U-6118 | Highway | STI (Prioritization) | NC 55 | Meridian Parkway to I-40 interchange in Durham. | Construct third southbound lane, upgrade ramp terminals, and include bike-ped facilities. | 2 | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6118 | Highway | STI (Prioritization) | NC 55 | Meridian Parkway to I-40 interchange in Durham. | Construct third southbound lane, upgrade ramp terminals, and include bike-ped facilities. | 2 | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 400000
U-6118 | Highway | STI (Prioritization) | NC 55 | Meridian Parkway to I-40 interchange in Durham. | Construct third southbound lane, upgrade ramp terminals, and include bike-ped facilities. | 2 | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 350000
U-6118 | Highway | STI (Prioritization) | NC 55 | Meridian Parkway to I-40 interchange in Durham. | Construct third southbound lane, upgrade ramp terminals, and include bike-ped facilities. | 2 | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6800000
U-6119 | Highway | STI (Prioritization) | Various | Raleigh citywide signal system. | Upgrade software for existing ITS system. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGANY | CONSTRUCTION | 4700000 | FY 2030: 1962000; FY 2031: 2503000; FY 2032: 235000
U-6120 | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1938 (Junction Road) to SR 1919 (Lynn Road) in Durham. | Construct safety improvements and widen to add median, bicycle lanes, sidewalks, transit stop improvements, and traffic signals where needed. | 0.83 | Durham | 5 | Triangle West TPO
U-6120A | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1838 (Junction Road) to west of SR 1919 (Lynn Road) | Construct safety improvements and widen to add median. Include shared use paths on both sides of the roadway, transit stop improvements, and traffic signals where needed. |  | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9451000
U-6120A | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1838 (Junction Road) to west of SR 1919 (Lynn Road) | Construct safety improvements and widen to add median. Include shared use paths on both sides of the roadway, transit stop improvements, and traffic signals where needed. |  | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-6120A | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1838 (Junction Road) to west of SR 1919 (Lynn Road) | Construct safety improvements and widen to add median. Include shared use paths on both sides of the roadway, transit stop improvements, and traffic signals where needed. |  | Durham | 5 | Triangle West TPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 17800000
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | HSIP | RIGHT-OF-WAY | 500000 | FY 2028: 500000
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | RIGHT-OF-WAY | 110000 | FY 2028: 110000
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | UTILITIES | 0 | FY 2028: 0
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | BUILD NC CON | 4545000 |  |  |  |  | 303000 | 303000 | 303000 | 303000 | 303000 | 303000 | 2121000
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | HSIP | CONSTRUCTION | 285000 | FY 2030: 214000; FY 2031: 71000
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | T | CONSTRUCTION | 3515000 | FY 2030: 1261000; FY 2031: 2254000
U-6120B | Highway | STI (Prioritization) | NC 98 (Holloway Street) | SR 1919 (Lynn Road) intersection | Construct intersection improvements including left turn lanes, safety improvements, and pedstrian accommodations. |  | Durham | 5 | Triangle West TPO | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM. BUILD NC BOND FUNDING: $3,500,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE). | Division 5 |  | L | CONSTRUCTION | 500000 | FY 2030: 500000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (Gallimore Dairy Road) to Triad Center Drive in Greensboro. | Construct reduced conflict intersections. | 2.12 | Guilford | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (Gallimore Dairy Road) to Triad Center Drive in Greensboro. | Construct reduced conflict intersections. | 2.12 | Guilford | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2600000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (Gallimore Dairy Road) to Triad Center Drive in Greensboro. | Construct reduced conflict intersections. | 2.12 | Guilford | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1500000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (Gallimore Dairy Road) to Triad Center Drive in Greensboro. | Construct reduced conflict intersections. | 2.12 | Guilford | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 34200000
U-6128 | Highway | STI (Prioritization) | US 76 (Oleander Drive) | Greenville Loop Road and Greenville Avenue intersections Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  |  |  | 260000
U-6128 | Highway | STI (Prioritization) | US 76 (Oleander Drive) | Greenville Loop Road and Greenville Avenue intersections Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | RIGHT-OF-WAY | 3700000 | FY 2027: 148000; FY 2028: 1591000; FY 2029: 1221000; FY 2030: 370000; FY 2031: 370000
U-6128 | Highway | STI (Prioritization) | US 76 (Oleander Drive) | Greenville Loop Road and Greenville Avenue intersections Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | UTILITIES | 600000 | FY 2027: 600000
U-6128 | Highway | STI (Prioritization) | US 76 (Oleander Drive) | Greenville Loop Road and Greenville Avenue intersections Wilmington | Construct intersection improvements. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | CONSTRUCTION | 6800000 | FY 2030: 884000; FY 2031: 3808000; FY 2032: 2108000
U-6131 | Highway | STI (Prioritization) | NC 54 (West Harden Street) | NC 49 (Maple Avenue) intersection in Burlington. | Install dual left turn lanes in westbound direction. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  |  |  | 10000
U-6131 | Highway | STI (Prioritization) | NC 54 (West Harden Street) | NC 49 (Maple Avenue) intersection in Burlington. | Install dual left turn lanes in westbound direction. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | BG50200 | RIGHT-OF-WAY | 11700000 | FY 2027: 4212000; FY 2028: 5148000; FY 2029: 1170000; FY 2030: 1170000
U-6131 | Highway | STI (Prioritization) | NC 54 (West Harden Street) | NC 49 (Maple Avenue) intersection in Burlington. | Install dual left turn lanes in westbound direction. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | BG50200 | UTILITIES | 1100000 | FY 2027: 550000; FY 2028: 550000
U-6131 | Highway | STI (Prioritization) | NC 54 (West Harden Street) | NC 49 (Maple Avenue) intersection in Burlington. | Install dual left turn lanes in westbound direction. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Region D |  | BG50200 | CONSTRUCTION | 7400000 | FY 2028: 74000; FY 2029: 4662000; FY 2030: 2072000; FY 2031: 592000
U-6133 | Highway | STI (Prioritization) | US 401 Business (Skibo Road) | SR 1400 (Cliffdale Road) intersection in Fayetteville | Construct intersection improvements. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7900000
U-6133 | Highway | STI (Prioritization) | US 401 Business (Skibo Road) | SR 1400 (Cliffdale Road) intersection in Fayetteville | Construct intersection improvements. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
U-6133 | Highway | STI (Prioritization) | US 401 Business (Skibo Road) | SR 1400 (Cliffdale Road) intersection in Fayetteville | Construct intersection improvements. | 0.5 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 8200000
U-6134 | Highway | STI (Prioritization) | NC 16 Bypass | SR 1380 (Optimist Club Road) intersection near Denver. | Upgrade at-grade intersection to interchange. | 1 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  |  |  | 10000
U-6134 | Highway | STI (Prioritization) | NC 16 Bypass | SR 1380 (Optimist Club Road) intersection near Denver. | Upgrade at-grade intersection to interchange. | 1 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BGLT5 | RIGHT-OF-WAY | 500000
U-6134 | Highway | STI (Prioritization) | NC 16 Bypass | SR 1380 (Optimist Club Road) intersection near Denver. | Upgrade at-grade intersection to interchange. | 1 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BGLT5 | UTILITIES | 100000
U-6134 | Highway | STI (Prioritization) | NC 16 Bypass | SR 1380 (Optimist Club Road) intersection near Denver. | Upgrade at-grade intersection to interchange. | 1 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BGLT5 | CONSTRUCTION | 46800000 | FY 2031: 8424000; FY 2032: 12636000; FY 2033: 10764000; FY 2034: 8424000; FY 2035: 6552000
U-6138 | Highway | STI (Prioritization) | NC 279 (North New Hope Road) | US 29 / US 74 (Franklin Boulevard) intersection in Gastonia. | Construct right turn lane from NC 279 (North New Hope Road) to US 29 / US 74 (Franklin Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6138 | Highway | STI (Prioritization) | NC 279 (North New Hope Road) | US 29 / US 74 (Franklin Boulevard) intersection in Gastonia. | Construct right turn lane from NC 279 (North New Hope Road) to US 29 / US 74 (Franklin Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | RIGHT-OF-WAY | 880000
U-6138 | Highway | STI (Prioritization) | NC 279 (North New Hope Road) | US 29 / US 74 (Franklin Boulevard) intersection in Gastonia. | Construct right turn lane from NC 279 (North New Hope Road) to US 29 / US 74 (Franklin Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | UTILITIES | 70000
U-6138 | Highway | STI (Prioritization) | NC 279 (North New Hope Road) | US 29 / US 74 (Franklin Boulevard) intersection in Gastonia. | Construct right turn lane from NC 279 (North New Hope Road) to US 29 / US 74 (Franklin Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | CONSTRUCTION | 2000000
U-6143 | Highway | STI (Prioritization) | NC 7 (East Catawba Street) | US 74 (Wilkinson Boulevard) intersection in Belmont. | Construct northbound right-turn lane on NC 7 (East Catawba Street) and extend existing westbound left-turn lane on US 74 (Wilkinson Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  |  |  | 10000
U-6143 | Highway | STI (Prioritization) | NC 7 (East Catawba Street) | US 74 (Wilkinson Boulevard) intersection in Belmont. | Construct northbound right-turn lane on NC 7 (East Catawba Street) and extend existing westbound left-turn lane on US 74 (Wilkinson Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | NHP | RIGHT-OF-WAY | 630000
U-6143 | Highway | STI (Prioritization) | NC 7 (East Catawba Street) | US 74 (Wilkinson Boulevard) intersection in Belmont. | Construct northbound right-turn lane on NC 7 (East Catawba Street) and extend existing westbound left-turn lane on US 74 (Wilkinson Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | NHP | UTILITIES | 280000
U-6143 | Highway | STI (Prioritization) | NC 7 (East Catawba Street) | US 74 (Wilkinson Boulevard) intersection in Belmont. | Construct northbound right-turn lane on NC 7 (East Catawba Street) and extend existing westbound left-turn lane on US 74 (Wilkinson Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | NHP | CONSTRUCTION | 5000000 | FY 2026: 50000; FY 2027: 3500000; FY 2028: 1450000
U-6143 | Highway | STI (Prioritization) | NC 7 (East Catawba Street) | US 74 (Wilkinson Boulevard) intersection in Belmont. | Construct northbound right-turn lane on NC 7 (East Catawba Street) and extend existing westbound left-turn lane on US 74 (Wilkinson Boulevard). | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | L | CONSTRUCTION | 2200000 | FY 2026: 418000; FY 2027: 1364000; FY 2028: 418000
U-6146 | Highway | STI (Prioritization) | US 29 / US 74 (Wilkinson Boulevard) | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  |  |  | 10000
U-6146 | Highway | STI (Prioritization) | US 29 / US 74 (Wilkinson Boulevard) | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | BUILD NC ROW | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000
U-6146 | Highway | STI (Prioritization) | US 29 / US 74 (Wilkinson Boulevard) | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | RIGHT-OF-WAY | 5800000
U-6146 | Highway | STI (Prioritization) | US 29 / US 74 (Wilkinson Boulevard) | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | UTILITIES | 5500000
U-6146 | Highway | STI (Prioritization) | US 29 / US 74 (Wilkinson Boulevard) | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | CONSTRUCTION | 27600000 | FY 2026: 3588000; FY 2027: 7452000; FY 2028: 6900000; FY 2029: 5520000; FY 2030: 4140000
U-6146 | Highway | STI (Prioritization) | US 29 / US 74 (Wilkinson Boulevard) | Market Street to SR 2015 (Alberta Avenue). | Widen to six lanes. Replace bridge 350082 over South Fork of Catawba River. | 1.19 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | HFB | CONSTRUCTION | 15900000 | FY 2026: 2067000; FY 2027: 4293000; FY 2028: 3975000; FY 2029: 3180000; FY 2030: 2385000
U-6152 | Highway | STI (Prioritization) | US 401 (Robeson Street) | US 401 (Raeford Road) to Walter Street. | Construct access management. | 2.09 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6152 | Highway | STI (Prioritization) | US 401 (Robeson Street) | US 401 (Raeford Road) to Walter Street. | Construct access management. | 2.09 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 21200000
U-6152 | Highway | STI (Prioritization) | US 401 (Robeson Street) | US 401 (Raeford Road) to Walter Street. | Construct access management. | 2.09 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3600000
U-6152 | Highway | STI (Prioritization) | US 401 (Robeson Street) | US 401 (Raeford Road) to Walter Street. | Construct access management. | 2.09 | Cumberland | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 37200000
U-6153 | Highway | Locally Selected | SR 1363 (Bethlehem Road) | Aviation Drive to Bethlehem Road. | Relocate roadway adjacent to Statesville Regional Airport. | 0.76 | Iredell | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  |  |  | 10000
U-6153 | Highway | Locally Selected | SR 1363 (Bethlehem Road) | Aviation Drive to Bethlehem Road. | Relocate roadway adjacent to Statesville Regional Airport. | 0.76 | Iredell | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  | BA | ENGINEERING | 452000
U-6153 | Highway | Locally Selected | SR 1363 (Bethlehem Road) | Aviation Drive to Bethlehem Road. | Relocate roadway adjacent to Statesville Regional Airport. | 0.76 | Iredell | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  | T | CONSTRUCTION | 2098000 | FY 2029: 1049000; FY 2030: 1049000
U-6153 | Highway | Locally Selected | SR 1363 (Bethlehem Road) | Aviation Drive to Bethlehem Road. | Relocate roadway adjacent to Statesville Regional Airport. | 0.76 | Iredell | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  | O | CONSTRUCTION | 2550000 | FY 2029: 2550000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 120000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | ENGINEERING | 273000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | ENGINEERING | 68000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 200000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | RIGHT-OF-WAY | 179000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 95000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | CMAQ | CONSTRUCTION | 2299000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 1494000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | CRPDA | CONSTRUCTION | 167000
U-6154 | Highway | Locally Selected | SR 1308 (Lewisville-Vienna Road) | SR 1348 (Robinhood Road) in Lewisville. | Upgrade existing signalized intersection to a single lane roundabout. | 0.5 | Forsyth | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 990000
U-6157 | Highway | STI (Prioritization) | SR 1130 (Cajah Mountain Road) | SR 1001 (Connelly Springs Road) to US 321 Alternate. | Modernize roadway. | 3.39 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  |  |  | 10000
U-6157 | Highway | STI (Prioritization) | SR 1130 (Cajah Mountain Road) | SR 1001 (Connelly Springs Road) to US 321 Alternate. | Modernize roadway. | 3.39 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGANY | RIGHT-OF-WAY | 13000000 | FY 2026: 3782000; FY 2027: 3151000; FY 2028: 1300000; FY 2029: 1300000
U-6157 | Highway | STI (Prioritization) | SR 1130 (Cajah Mountain Road) | SR 1001 (Connelly Springs Road) to US 321 Alternate. | Modernize roadway. | 3.39 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGANY | UTILITIES | 7000000 | FY 2026: 3500000
U-6157 | Highway | STI (Prioritization) | SR 1130 (Cajah Mountain Road) | SR 1001 (Connelly Springs Road) to US 321 Alternate. | Modernize roadway. | 3.39 | Caldwell | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGANY | CONSTRUCTION | 45100000 | FY 2029: 451000; FY 2030: 13981000; FY 2031: 12177000; FY 2032: 10373000; FY 2033: 8118000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (Crymes Cove Road) and SR 1812 (Raccoon Road) intersection east of Waynesville. | Realign intersection. | 0.5 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (Crymes Cove Road) and SR 1812 (Raccoon Road) intersection east of Waynesville. | Realign intersection. | 0.5 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 100000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (Crymes Cove Road) and SR 1812 (Raccoon Road) intersection east of Waynesville. | Realign intersection. | 0.5 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 200000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (Crymes Cove Road) and SR 1812 (Raccoon Road) intersection east of Waynesville. | Realign intersection. | 0.5 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6200000
U-6159 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 (Great Smokey Mountain Expressway) to US 19 (Dellwood Road). | Construct access management. | 1.32 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6159 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 (Great Smokey Mountain Expressway) to US 19 (Dellwood Road). | Construct access management. | 1.32 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG5T50 | RIGHT-OF-WAY | 11500000
U-6159 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 (Great Smokey Mountain Expressway) to US 19 (Dellwood Road). | Construct access management. | 1.32 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG5T50 | UTILITIES | 2200000
U-6159 | Highway | STI (Prioritization) | US 276 (Russ Avenue) | US 23 / US 74 (Great Smokey Mountain Expressway) to US 19 (Dellwood Road). | Construct access management. | 1.32 | Haywood | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG5T50 | CONSTRUCTION | 25200000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (Dudley Shoals Road) grade separation. | Construct ramp onto US 321 southbound. | 1 | Caldwell | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  |  |  | 10000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (Dudley Shoals Road) grade separation. | Construct ramp onto US 321 southbound. | 1 | Caldwell | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  | NHP | RIGHT-OF-WAY | 2000000 | FY 2026: 200000; FY 2027: 700000; FY 2028: 700000; FY 2029: 200000; FY 2030: 200000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (Dudley Shoals Road) grade separation. | Construct ramp onto US 321 southbound. | 1 | Caldwell | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  | NHP | UTILITIES | 270000 | FY 2026: 270000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (Dudley Shoals Road) grade separation. | Construct ramp onto US 321 southbound. | 1 | Caldwell | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  | NHP | CONSTRUCTION | 6300000 | FY 2028: 1890000; FY 2029: 3276000; FY 2030: 1134000
U-6163 | Highway | STI (Prioritization) | SR 3116 (Mills Gap Road) | SR 3136 (Cane Creek Road). | Construct roundabout. | 0.5 | Buncombe | 13 | French Broad River MPO | HIGHWAY FUNDS ARE HIGH IMPACT/LOW COST FUNDS | Division 13 |  | HF | RIGHT-OF-WAY | 100000 | FY 2026: 100000
U-6163 | Highway | STI (Prioritization) | SR 3116 (Mills Gap Road) | SR 3136 (Cane Creek Road). | Construct roundabout. | 0.5 | Buncombe | 13 | French Broad River MPO | HIGHWAY FUNDS ARE HIGH IMPACT/LOW COST FUNDS | Division 13 |  | HF | UTILITIES | 300000 | FY 2026: 300000
U-6163 | Highway | STI (Prioritization) | SR 3116 (Mills Gap Road) | SR 3136 (Cane Creek Road). | Construct roundabout. | 0.5 | Buncombe | 13 | French Broad River MPO | HIGHWAY FUNDS ARE HIGH IMPACT/LOW COST FUNDS | Division 13 |  | BGANY | CONSTRUCTION | 2400000 | FY 2027: 1560000; FY 2028: 840000
U-6170 | Highway | STI (Prioritization) | SR 1004 (Lawyers Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to four lanes. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6170 | Highway | STI (Prioritization) | SR 1004 (Lawyers Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to four lanes. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5000000
U-6170 | Highway | STI (Prioritization) | SR 1004 (Lawyers Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to four lanes. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 900000
U-6170 | Highway | STI (Prioritization) | SR 1004 (Lawyers Road) | I-485 to SR 1524 (Stevens Mill Road). | Widen to four lanes. | 0.25 | Union | 10 | Charlotte Regional TPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 18700000
U-6187 | Highway | STI (Prioritization) | New Route | SR 1630 (Baltimore Road) to I-40. | Construct 2-lane extension of Baltimore road and interchange at I-40. | 0.71 | Davie | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 9
U-6187 | Highway | STI (Prioritization) | New Route | SR 1630 (Baltimore Road) to I-40. | Construct 2-lane extension of Baltimore road and interchange at I-40. | 0.71 | Davie | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 9 |  | BGANY | RIGHT-OF-WAY | 4000000 | FY 2026: 390000; FY 2027: 390000
U-6187 | Highway | STI (Prioritization) | New Route | SR 1630 (Baltimore Road) to I-40. | Construct 2-lane extension of Baltimore road and interchange at I-40. | 0.71 | Davie | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 9 |  | BGANY | UTILITIES | 1000000
U-6187 | Highway | STI (Prioritization) | New Route | SR 1630 (Baltimore Road) to I-40. | Construct 2-lane extension of Baltimore road and interchange at I-40. | 0.71 | Davie | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 9 |  | T | BUILD NC CON | 26010000 |  | 867000 | 867000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 1734000 | 11271000
U-6187 | Highway | STI (Prioritization) | New Route | SR 1630 (Baltimore Road) to I-40. | Construct 2-lane extension of Baltimore road and interchange at I-40. | 0.71 | Davie | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE) | Division 9 |  | T | CONSTRUCTION | 33900000 | FY 2026: 8430000; FY 2027: 2052000; FY 2028: 17248000; FY 2029: 1319000; FY 2030: 4851000
U-6188 | Highway | STI (Prioritization) | SR 1969 (Piney Grove Road) | North of Nelson Street to SR 2031 (Brown Road) in Kernersville. | Widen to 3 lanes with bicycle / pedestrian accommodations. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 2200000 | FY 2028: 352000; FY 2029: 836000; FY 2030: 572000; FY 2031: 220000; FY 2032: 220000
U-6188 | Highway | STI (Prioritization) | SR 1969 (Piney Grove Road) | North of Nelson Street to SR 2031 (Brown Road) in Kernersville. | Widen to 3 lanes with bicycle / pedestrian accommodations. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | UTILITIES | 500000 | FY 2028: 500000
U-6188 | Highway | STI (Prioritization) | SR 1969 (Piney Grove Road) | North of Nelson Street to SR 2031 (Brown Road) in Kernersville. | Widen to 3 lanes with bicycle / pedestrian accommodations. | 0.52 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 6800000 | FY 2030: 1224000; FY 2031: 3604000; FY 2032: 1972000
U-6189 | Highway | STI (Prioritization) | SR 1156 (Lewisville- Clemmons Road) | SR 1103 (Styers Ferry Road) to SR 1101 (Shallowford Road) in Lewisville. | Widen to 3 lanes with bicycle and pedestrian accommodations. | 2.31 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 14600000 | FY 2030: 2628000; FY 2031: 3504000; FY 2032: 3504000; FY 2033: 2044000; FY 2034: 2920000
U-6189 | Highway | STI (Prioritization) | SR 1156 (Lewisville- Clemmons Road) | SR 1103 (Styers Ferry Road) to SR 1101 (Shallowford Road) in Lewisville. | Widen to 3 lanes with bicycle and pedestrian accommodations. | 2.31 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | UTILITIES | 3300000 | FY 2030: 3300000
U-6189 | Highway | STI (Prioritization) | SR 1156 (Lewisville- Clemmons Road) | SR 1103 (Styers Ferry Road) to SR 1101 (Shallowford Road) in Lewisville. | Widen to 3 lanes with bicycle and pedestrian accommodations. | 2.31 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 27000000 | FY 2033: 3240000; FY 2034: 8640000; FY 2035: 7020000 | 8100000
U-6190 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | SR 1647 (Glade Street) to NC 66 in Rural Hall. | Widen to 3 lanes. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 2900000 | FY 2028: 638000; FY 2029: 957000; FY 2030: 725000; FY 2031: 290000; FY 2032: 290000
U-6190 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | SR 1647 (Glade Street) to NC 66 in Rural Hall. | Widen to 3 lanes. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | UTILITIES | 900000 | FY 2028: 900000
U-6190 | Highway | STI (Prioritization) | NC 65 (Bethania-Rural Hall Road) | SR 1647 (Glade Street) to NC 66 in Rural Hall. | Widen to 3 lanes. | 0.25 | Forsyth | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 3800000 | FY 2030: 646000; FY 2031: 2622000; FY 2032: 532000
U-6191 | Highway | STI (Prioritization) | NC 62 | SR 3252 (Surrett Drive) in Trinity to SR 1009 (North Main Street) in Archdale. | Modernize roadway. | 3.18 | Randolph | 8 | High Point Urban Area MPO |  | Division 8 |  | T | RIGHT-OF-WAY | 21400000 | FY 2029: 3210000; FY 2030: 7490000; FY 2031: 6420000; FY 2032: 2140000; FY 2033: 2140000
U-6191 | Highway | STI (Prioritization) | NC 62 | SR 3252 (Surrett Drive) in Trinity to SR 1009 (North Main Street) in Archdale. | Modernize roadway. | 3.18 | Randolph | 8 | High Point Urban Area MPO |  | Division 8 |  | T | UTILITIES | 12400000 | FY 2029: 6200000; FY 2030: 6200000
U-6191 | Highway | STI (Prioritization) | NC 62 | SR 3252 (Surrett Drive) in Trinity to SR 1009 (North Main Street) in Archdale. | Modernize roadway. | 3.18 | Randolph | 8 | High Point Urban Area MPO |  | Division 8 |  | T | CONSTRUCTION | 30000000 | FY 2033: 300000; FY 2034: 10200000; FY 2035: 8100000 | 11400000
U-6192 | Highway | STI (Prioritization) | US 15 / US 501 | US 64 Bypass to SR 1919 (Smith Level Road). | Upgrade remaining non-synchronized sections of facility to synchronized street. | 10.46 | Chatham | 8 | Central Pines RPO, Triangle West TPO |  | Division 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 13500000
U-6192 | Highway | STI (Prioritization) | US 15 / US 501 | US 64 Bypass to SR 1919 (Smith Level Road). | Upgrade remaining non-synchronized sections of facility to synchronized street. | 10.46 | Chatham | 8 | Central Pines RPO, Triangle West TPO |  | Division 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 10200000
U-6192 | Highway | STI (Prioritization) | US 15 / US 501 | US 64 Bypass to SR 1919 (Smith Level Road). | Upgrade remaining non-synchronized sections of facility to synchronized street. | 10.46 | Chatham | 8 | Central Pines RPO, Triangle West TPO |  | Division 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 83300000
U-6194 | Highway | STI (Prioritization) | Various | Locations in Garner | Improve citywide signal system in Garner. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGANY | UTILITIES | 480000 | FY 2030: 480000
U-6194 | Highway | STI (Prioritization) | Various | Locations in Garner | Improve citywide signal system in Garner. |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | BGANY | CONSTRUCTION | 6800000 | FY 2031: 2584000; FY 2032: 3128000; FY 2033: 1088000
U-6197 | Highway | STI (Prioritization) | SR 1711 (Worthington Road) | SR 1725 (County Home Road) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  |  |  | 10000
U-6197 | Highway | STI (Prioritization) | SR 1711 (Worthington Road) | SR 1725 (County Home Road) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | T | RIGHT-OF-WAY | 1300000 | FY 2027: 312000; FY 2028: 364000; FY 2029: 364000; FY 2030: 130000; FY 2031: 130000
U-6197 | Highway | STI (Prioritization) | SR 1711 (Worthington Road) | SR 1725 (County Home Road) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | T | UTILITIES | 730000 | FY 2027: 730000
U-6197 | Highway | STI (Prioritization) | SR 1711 (Worthington Road) | SR 1725 (County Home Road) intersection in Greenville | Construct intersection improvements. | 0.5 | Pitt | 2 | Greenville Urban Area MPO |  | Division 2 |  | T | CONSTRUCTION | 3100000 | FY 2029: 31000; FY 2030: 2232000; FY 2031: 837000
U-6199 | Highway | STI (Prioritization) | Various | Routes in Wilmington | Improve signal system. | 39.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 10000
U-6199 | Highway | STI (Prioritization) | Various | Routes in Wilmington | Improve signal system. | 39.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 10000 | FY 2028: 10000
U-6199 | Highway | STI (Prioritization) | Various | Routes in Wilmington | Improve signal system. | 39.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | UTILITIES | 1100000 | FY 2028: 1100000
U-6199 | Highway | STI (Prioritization) | Various | Routes in Wilmington | Improve signal system. | 39.2 | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 15500000 | FY 2030: 2480000; FY 2031: 6665000; FY 2032: 4495000; FY 2033: 1860000
U-6202 | Highway | STI (Prioritization) | SR 2048 (Gordon Road) | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S. | Division 3 |  |  |  | 10000
U-6202 | Highway | STI (Prioritization) | SR 2048 (Gordon Road) | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S. | Division 3 |  | T | BUILD NC ROW | 6435000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000
U-6202 | Highway | STI (Prioritization) | SR 2048 (Gordon Road) | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S. | Division 3 |  | T | RIGHT-OF-WAY | 11400000
U-6202 | Highway | STI (Prioritization) | SR 2048 (Gordon Road) | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S. | Division 3 |  | T | UTILITIES | 6651000
U-6202 | Highway | STI (Prioritization) | SR 2048 (Gordon Road) | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S. | Division 3 |  | T | BUILD NC CON | 29475000 | 1965000 | 1965000 | 1965000 | 1965000 | 1965000 | 1965000 | 1965000 | 1965000 | 1965000 | 1965000 | 9160000
U-6202 | Highway | STI (Prioritization) | SR 2048 (Gordon Road) | US 17 Business (Market Street) to I-40. | Widen to four lanes. | 2.49 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $7,496,006 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S. | Division 3 |  | T | CONSTRUCTION | 36484000 | FY 2026: 0; FY 2027: 6709000; FY 2028: 4735000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 to SR 1330 (Raleigh Road). | Construct reduced conflict intersections. | 2.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  |  |  | 10000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 to SR 1330 (Raleigh Road). | Construct reduced conflict intersections. | 2.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 12800000 | FY 2027: 1792000; FY 2028: 3712000; FY 2029: 3584000; FY 2030: 1152000; FY 2031: 2560000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 to SR 1330 (Raleigh Road). | Construct reduced conflict intersections. | 2.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T | UTILITIES | 4000000 | FY 2027: 2000000; FY 2028: 2000000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 to SR 1330 (Raleigh Road). | Construct reduced conflict intersections. | 2.06 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 71600000 | FY 2030: 11456000; FY 2031: 18616000; FY 2032: 17184000; FY 2033: 13604000; FY 2034: 10740000
U-6204 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Country Day Road to New Hope Road. | Construct access management. | 1.08 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 4 |  |  |  | 10000
U-6204 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Country Day Road to New Hope Road. | Construct access management. | 1.08 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 4 |  | BG50200 | RIGHT-OF-WAY | 4101000 | FY 2026: 1406000; FY 2027: 1406000; FY 2028: 469000; FY 2029: 410000; FY 2030: 410000
U-6204 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Country Day Road to New Hope Road. | Construct access management. | 1.08 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 4 |  | BG50200 | UTILITIES | 1400000
U-6204 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Country Day Road to New Hope Road. | Construct access management. | 1.08 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 4 |  | T | BUILD NC CON | 9105000 |  |  | 607000 | 607000 | 607000 | 607000 | 607000 | 607000 | 607000 | 607000 | 4249000
U-6204 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | Country Day Road to New Hope Road. | Construct access management. | 1.08 | Wayne | 4 | Goldsboro Urban Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 4 |  | T | CONSTRUCTION | 18100000 | FY 2028: 0; FY 2029: 5048000; FY 2030: 7028000; FY 2031: 4769000; FY 2032: 1255000
U-6205 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | US 70 Bypass to SR 1547 (Stoney Creek Church Road). | Widen roadway. | 2.79 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  |  |  | 10000
U-6205 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | US 70 Bypass to SR 1547 (Stoney Creek Church Road). | Widen roadway. | 2.79 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 1200000 | FY 2027: 120000; FY 2028: 480000; FY 2029: 360000; FY 2030: 120000; FY 2031: 120000
U-6205 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | US 70 Bypass to SR 1547 (Stoney Creek Church Road). | Widen roadway. | 2.79 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | UTILITIES | 1600000 | FY 2027: 800000; FY 2028: 800000
U-6205 | Highway | STI (Prioritization) | SR 1556 (Wayne Memorial Drive) | US 70 Bypass to SR 1547 (Stoney Creek Church Road). | Widen roadway. | 2.79 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | CONSTRUCTION | 4400000 | FY 2029: 748000; FY 2030: 3036000; FY 2031: 616000
U-6206 | Highway | STI (Prioritization) | SR 1713 (Miller's Chapel Road) | US 70 to SR 1712 (Thoroughfare Road). | Modernize roadway. | 1 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  |  |  | 10000
U-6206 | Highway | STI (Prioritization) | SR 1713 (Miller's Chapel Road) | US 70 to SR 1712 (Thoroughfare Road). | Modernize roadway. | 1 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 9200000 | FY 2029: 2116000; FY 2030: 4232000; FY 2031: 1012000; FY 2032: 920000; FY 2033: 920000
U-6206 | Highway | STI (Prioritization) | SR 1713 (Miller's Chapel Road) | US 70 to SR 1712 (Thoroughfare Road). | Modernize roadway. | 1 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | UTILITIES | 2500000 | FY 2029: 1250000; FY 2030: 1250000
U-6206 | Highway | STI (Prioritization) | SR 1713 (Miller's Chapel Road) | US 70 to SR 1712 (Thoroughfare Road). | Modernize roadway. | 1 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | CONSTRUCTION | 10900000 | FY 2031: 3924000; FY 2032: 4578000; FY 2033: 2398000
U-6207 | Highway | STI (Prioritization) | NC 581 (Bill Lane Boulevard) | Neuse River south of SR 1919 (Westbrook Road) to NC 111. | Modernize roadway. | 4.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6207 | Highway | STI (Prioritization) | NC 581 (Bill Lane Boulevard) | Neuse River south of SR 1919 (Westbrook Road) to NC 111. | Modernize roadway. | 4.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 740000
U-6207 | Highway | STI (Prioritization) | NC 581 (Bill Lane Boulevard) | Neuse River south of SR 1919 (Westbrook Road) to NC 111. | Modernize roadway. | 4.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 460000
U-6207 | Highway | STI (Prioritization) | NC 581 (Bill Lane Boulevard) | Neuse River south of SR 1919 (Westbrook Road) to NC 111. | Modernize roadway. | 4.5 | Wayne | 4 | Goldsboro Urban Area MPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 22000000
U-6208 | Highway | STI (Prioritization) | New Route | SR 1010 (Cleveland Road) to NC 42. | Construct roadway on new location. | 1.46 | Johnston | 4 | Capital Area MPO |  | Division 4 |  |  |  | 10000
U-6208 | Highway | STI (Prioritization) | New Route | SR 1010 (Cleveland Road) to NC 42. | Construct roadway on new location. | 1.46 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 19500000 | FY 2030: 4485000; FY 2031: 8970000; FY 2032: 2145000; FY 2033: 1950000; FY 2034: 1950000
U-6208 | Highway | STI (Prioritization) | New Route | SR 1010 (Cleveland Road) to NC 42. | Construct roadway on new location. | 1.46 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T | UTILITIES | 3900000 | FY 2030: 1950000; FY 2031: 1950000
U-6208 | Highway | STI (Prioritization) | New Route | SR 1010 (Cleveland Road) to NC 42. | Construct roadway on new location. | 1.46 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 33100000 | FY 2034: 7613000; FY 2035: 10592000 | 14895000
U-6216 | Highway | STI (Prioritization) | SR 1010 (Cleveland Road) | North of SR 2231 (Southfort Drive) to SR 1555 (Barber Mill Road). | Widen to multi-lanes. | 4.2 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | BGANY | RIGHT-OF-WAY | 36600000 | FY 2030: 8052000; FY 2031: 10614000; FY 2032: 10614000; FY 2033: 3660000; FY 2034: 3660000
U-6216 | Highway | STI (Prioritization) | SR 1010 (Cleveland Road) | North of SR 2231 (Southfort Drive) to SR 1555 (Barber Mill Road). | Widen to multi-lanes. | 4.2 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | BGANY | UTILITIES | 6300000 | FY 2030: 3150000; FY 2031: 3150000
U-6216 | Highway | STI (Prioritization) | SR 1010 (Cleveland Road) | North of SR 2231 (Southfort Drive) to SR 1555 (Barber Mill Road). | Widen to multi-lanes. | 4.2 | Johnston | 4 | Capital Area MPO |  | Division 4 |  | BGANY | CONSTRUCTION | 100900000 | FY 2035: 1009000 | 99891000
U-6217 | Highway | STI (Prioritization) | SR 1152 (Holly Springs Road) | SR 1010 (Ten-Ten Road) to SR 3977 (Cary Parkway). | Construct intersection improvements at SR 1010, SR 1379 (Penny Road), and SR 3977 (Cary Parkway). | 3.44 | Wake | 5 | Capital Area MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6217 | Highway | STI (Prioritization) | SR 1152 (Holly Springs Road) | SR 1010 (Ten-Ten Road) to SR 3977 (Cary Parkway). | Construct intersection improvements at SR 1010, SR 1379 (Penny Road), and SR 3977 (Cary Parkway). | 3.44 | Wake | 5 | Capital Area MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 18500000
U-6217 | Highway | STI (Prioritization) | SR 1152 (Holly Springs Road) | SR 1010 (Ten-Ten Road) to SR 3977 (Cary Parkway). | Construct intersection improvements at SR 1010, SR 1379 (Penny Road), and SR 3977 (Cary Parkway). | 3.44 | Wake | 5 | Capital Area MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
U-6217 | Highway | STI (Prioritization) | SR 1152 (Holly Springs Road) | SR 1010 (Ten-Ten Road) to SR 3977 (Cary Parkway). | Construct intersection improvements at SR 1010, SR 1379 (Penny Road), and SR 3977 (Cary Parkway). | 3.44 | Wake | 5 | Capital Area MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 49200000
U-6218 | Bike & Ped | Locally Selected | Various | Locations in the Capital Area MPO | Unallocated Transportation Alternatives Program Funds. |  | Wake, Johnston, Franklin, Granville, Harnett | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | TADA | CONSTRUCTION | 26579000 | 2512000 | 2512000 | 2512000 | 2512000 | 2512000 | 2512000 | 2512000 | 2512000 | 2512000 | 2512000
U-6219 | Bike & Ped | Locally Selected | Various | Locations in Triangle West Transportation Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Durham, Orange, Chatham | 5, 7, 8 | Triangle West TPO |  | Division 5, 7, 8 |  | TADA | CONSTRUCTION | 3803000 | FY 2031: 207000; FY 2032: 899000; FY 2033: 899000; FY 2034: 899000; FY 2035: 899000
U-6220 | Bike & Ped | Locally Selected | Various | Greensboro Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Guilford | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 3332000 | 0 | 0 | 0 | 0 | 0 | 256000 | 769000 | 769000 | 769000 | 769000
U-6221 | Bike & Ped | Locally Selected | Various | Winston-Salem Urban Area Metropolitan Planning Organization | Unallocated Transportation Alternatives Program Funds. |  | Forsyth, Davidson, Stokes, Davie | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 6149000 |  |  |  | 413000 | 956000 | 956000 | 956000 | 956000 | 956000 | 956000
U-6222 | Highway | Locally Selected | NC 98 | Camp Kanata Road intersection in Wake Forest. | Construct intersection improvements and add turn lanes on NC 98. | 0.75 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | BGDA | ENGINEERING | 120000
U-6222 | Highway | Locally Selected | NC 98 | Camp Kanata Road intersection in Wake Forest. | Construct intersection improvements and add turn lanes on NC 98. | 0.75 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | HF | ENGINEERING | 30000
U-6222 | Highway | Locally Selected | NC 98 | Camp Kanata Road intersection in Wake Forest. | Construct intersection improvements and add turn lanes on NC 98. | 0.75 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 840000
U-6222 | Highway | Locally Selected | NC 98 | Camp Kanata Road intersection in Wake Forest. | Construct intersection improvements and add turn lanes on NC 98. | 0.75 | Wake | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | HF | CONSTRUCTION | 210000
U-6223 | Highway | Locally Selected | SR 1560 (Ranch Road Extension) | US 70 Business / NC 42 to SR 1560 (Ranch Road) in Clayton. | Construct roadway extension on new location. | 0.4 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | BGDA | RIGHT-OF-WAY | 1735000
U-6223 | Highway | Locally Selected | SR 1560 (Ranch Road Extension) | US 70 Business / NC 42 to SR 1560 (Ranch Road) in Clayton. | Construct roadway extension on new location. | 0.4 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | HF(M) | RIGHT-OF-WAY | 434000
U-6223 | Highway | Locally Selected | SR 1560 (Ranch Road Extension) | US 70 Business / NC 42 to SR 1560 (Ranch Road) in Clayton. | Construct roadway extension on new location. | 0.4 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | BGDA | CONSTRUCTION | 7500000
U-6223 | Highway | Locally Selected | SR 1560 (Ranch Road Extension) | US 70 Business / NC 42 to SR 1560 (Ranch Road) in Clayton. | Construct roadway extension on new location. | 0.4 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | L(M) | CONSTRUCTION | 1500000
U-6223 | Highway | Locally Selected | SR 1560 (Ranch Road Extension) | US 70 Business / NC 42 to SR 1560 (Ranch Road) in Clayton. | Construct roadway extension on new location. | 0.4 | Johnston | 4 | Capital Area MPO | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | HF | CONSTRUCTION | 2250000
U-6225 | Highway | Locally Selected | SR 2700 (White Oak Road) | SR 2709 (Ackerman Road) and SR 2547 (Hebron Church Road) intersection in Garner. | Construct intersection improvements and add multi-lane roundabout. | 1.06 | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. UNDER CONSTRUCTION | Division 5 |  |  |  | 28000
U-6225 | Highway | Locally Selected | SR 2700 (White Oak Road) | SR 2709 (Ackerman Road) and SR 2547 (Hebron Church Road) intersection in Garner. | Construct intersection improvements and add multi-lane roundabout. | 1.06 | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 56000
U-6225 | Highway | Locally Selected | SR 2700 (White Oak Road) | SR 2709 (Ackerman Road) and SR 2547 (Hebron Church Road) intersection in Garner. | Construct intersection improvements and add multi-lane roundabout. | 1.06 | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. UNDER CONSTRUCTION | Division 5 |  | L | RIGHT-OF-WAY | 19000
U-6225 | Highway | Locally Selected | SR 2700 (White Oak Road) | SR 2709 (Ackerman Road) and SR 2547 (Hebron Church Road) intersection in Garner. | Construct intersection improvements and add multi-lane roundabout. | 1.06 | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 2581000
U-6225 | Highway | Locally Selected | SR 2700 (White Oak Road) | SR 2709 (Ackerman Road) and SR 2547 (Hebron Church Road) intersection in Garner. | Construct intersection improvements and add multi-lane roundabout. | 1.06 | Wake | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 860000
U-6227 | Highway | Locally Selected | SR 1624 (Carpenter Fire Station Road) | NC 55 to Cameron Pond Drive in Cary. | Widen to multi lanes. | 0.95 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,645,000 IN STBG-ANYAREA FUNDS RESULTING FROM FUND SWAPS | Division 5 |  | BGDA | RIGHT-OF-WAY | 2533000
U-6227 | Highway | Locally Selected | SR 1624 (Carpenter Fire Station Road) | NC 55 to Cameron Pond Drive in Cary. | Widen to multi lanes. | 0.95 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,645,000 IN STBG-ANYAREA FUNDS RESULTING FROM FUND SWAPS | Division 5 |  | L | RIGHT-OF-WAY | 3096000
U-6227 | Highway | Locally Selected | SR 1624 (Carpenter Fire Station Road) | NC 55 to Cameron Pond Drive in Cary. | Widen to multi lanes. | 0.95 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,645,000 IN STBG-ANYAREA FUNDS RESULTING FROM FUND SWAPS | Division 5 |  | BGANY | CONSTRUCTION | 3645000 | FY 2026: 3645000
U-6227 | Highway | Locally Selected | SR 1624 (Carpenter Fire Station Road) | NC 55 to Cameron Pond Drive in Cary. | Widen to multi lanes. | 0.95 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,645,000 IN STBG-ANYAREA FUNDS RESULTING FROM FUND SWAPS | Division 5 |  | L | CONSTRUCTION | 4455000 | FY 2026: 4455000
U-6229 | Highway | Safety | NC 24 (Bragg Boulevard) | US 401 (Skibo Road) to Glenville Avenue. | Replace median and guardrail, add pedestrian signal, and resurface pavement. | 2.53 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | UTILITIES | 200000
U-6229 | Highway | Safety | NC 24 (Bragg Boulevard) | US 401 (Skibo Road) to Glenville Avenue. | Replace median and guardrail, add pedestrian signal, and resurface pavement. | 2.53 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 2557000
U-6229 | Highway | Safety | NC 24 (Bragg Boulevard) | US 401 (Skibo Road) to Glenville Avenue. | Replace median and guardrail, add pedestrian signal, and resurface pavement. | 2.53 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 5115000
U-6230 | Highway | Economic Development | SR 3684 (Walk Off Way) | Haakon Industries in Enka Commerce Park. | Extend roadway. | 0.27 | Buncombe | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR HAAKON INDUSTRIES. AWARD AMOUNT = $1,300,000 - COMPLETE. | Division 13 |  | T | CONSTRUCTION | 1300000
U-6231 | Highway | Economic Development | New Route | SR 4001 (Reynolds Boulevard) to SR 2264 (Akron Drive) at intersection of SR 1763 (Indiana Avenue). | Construct access road. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL. | Division 9 |  | T | CONSTRUCTION | 1300000
U-6231 | Highway | Economic Development | New Route | SR 4001 (Reynolds Boulevard) to SR 2264 (Akron Drive) at intersection of SR 1763 (Indiana Avenue). | Construct access road. | 0.34 | Forsyth | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL. | Division 9 |  | L | CONSTRUCTION | 2700000
U-6233 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | BGDA | ENGINEERING | 14000
U-6233 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | HF | ENGINEERING | 4000
U-6233 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | BGDA | RIGHT-OF-WAY | 32000
U-6233 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | HF | RIGHT-OF-WAY | 8000
U-6233 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | BGDA | CONSTRUCTION | 205000
U-6233 | Highway | Locally Selected | US 421 (Lake Park Boulevard) | Hamlet Avenue intersection in Carolina Beach. | Construct new traffic signal and improve pedestrian accommodations. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | HF | CONSTRUCTION | 51000
U-6235 | Highway | Locally Selected | Various | Routes in Wilmington | Traffic signal pre-emption for emergency vehicles project. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 179000
U-6235 | Highway | Locally Selected | Various | Routes in Wilmington | Traffic signal pre-emption for emergency vehicles project. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 45000
U-6235 | Highway | Locally Selected | Various | Routes in Wilmington | Traffic signal pre-emption for emergency vehicles project. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 965000
U-6235 | Highway | Locally Selected | Various | Routes in Wilmington | Traffic signal pre-emption for emergency vehicles project. |  | New Hanover | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 241000
U-6237 | Highway | Economic Development | SR 2120 (Long Ferry Road) | SR 2182 (I-85 Service Road) near Spencer. | Construct Right-turn lane on SR 2120, and remove residual pavement and strengthen remaining pavement on SR 2182 (I-85 Service Road). | 0.6 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM | Division 9 |  | T | UTILITIES | 50000
U-6237 | Highway | Economic Development | SR 2120 (Long Ferry Road) | SR 2182 (I-85 Service Road) near Spencer. | Construct Right-turn lane on SR 2120, and remove residual pavement and strengthen remaining pavement on SR 2182 (I-85 Service Road). | 0.6 | Rowan | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM | Division 9 |  | T | CONSTRUCTION | 365000
U-6238 | Highway | Economic Development | Trivium Parkway / New Route | Trivium Corporate Center. | Extend roadway and construct new route. | 0.2 | Catawba | 12 | Greater Hickory MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CATALER NORTH AMERICA. | Division 12 |  | T | CONSTRUCTION | 1316000 | FY 2026: 1316000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | DP | ENGINEERING | 420000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | L | ENGINEERING | 105000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | DP | RIGHT-OF-WAY | 1014000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | L | RIGHT-OF-WAY | 5135000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | DP | CONSTRUCTION | 12175000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | BGDA | CONSTRUCTION | 6718000
U-6239 | Highway | Locally Selected | New Route | Langtree Road to NC 115 (Mecklenburg Highway) | Construct roadway. | 0.84 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORRSVILLE. | Division 12 |  | L | CONSTRUCTION | 9599000
U-6240 | Highway | Locally Selected | SR 1571 (West 5th Street) | Cadillac Street to Reade Circle in Greenville. | Rehabilitate and realign roadway. | 1.07 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  |  |  | 2900000
U-6240 | Highway | Locally Selected | SR 1571 (West 5th Street) | Cadillac Street to Reade Circle in Greenville. | Rehabilitate and realign roadway. | 1.07 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 14800000
U-6240 | Highway | Locally Selected | SR 1571 (West 5th Street) | Cadillac Street to Reade Circle in Greenville. | Rehabilitate and realign roadway. | 1.07 | Pitt | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | L | CONSTRUCTION | 19277000
U-6241 | Highway | Locally Selected | SR 2051 (Burlington Mills Road); US 401 Business (South Main Street) | East of Rolesville Middle School to US 401 Business (South Main Street) in Rolesville; SR 2051 (Burlington Mills Road) to north of SR 1003 (East Young Street) / SR 1945 (West Young Street) in Rolesville. | Realign roadway and construct new intersection with south main street; Construct sidewalk extensions and complete street improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 12041000
U-6241 | Highway | Locally Selected | SR 2051 (Burlington Mills Road); US 401 Business (South Main Street) | East of Rolesville Middle School to US 401 Business (South Main Street) in Rolesville; SR 2051 (Burlington Mills Road) to north of SR 1003 (East Young Street) / SR 1945 (West Young Street) in Rolesville. | Realign roadway and construct new intersection with south main street; Construct sidewalk extensions and complete street improvements. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 8411000
U-6242 | Highway | Locally Selected | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP. | Division 5 |  | BGDA | RIGHT-OF-WAY | 1360000
U-6242 | Highway | Locally Selected | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP. | Division 5 |  | L(M) | RIGHT-OF-WAY | 340000
U-6242 | Highway | Locally Selected | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP. | Division 5 |  | BGDA | UTILITIES | 880000
U-6242 | Highway | Locally Selected | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP. | Division 5 |  | L(M) | UTILITIES | 220000
U-6242 | Highway | Locally Selected | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP. | Division 5 |  | BGANY | CONSTRUCTION | 8918000
U-6242 | Highway | Locally Selected | SR 2015 (Dixie Forest Road) / SR 3555 (Old Wake Forest Road) | SR 2015 / SR 2041 (Spring Forest Road) to US 1 (Capital Boulevard) in Raleigh. | Upgrade to a complete street. | 1.44 | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP. | Division 5 |  | L(M) | CONSTRUCTION | 2230000
U-6243 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | Flint Point Lane to SR 1301 (Sunset Lake Road) in Holly Springs. | Widen to a four-lane median-divided facility and construct sidewalk. | 1.52 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 3600000
U-6243 | Highway | Locally Selected | SR 1152 (Holly Springs Road) | Flint Point Lane to SR 1301 (Sunset Lake Road) in Holly Springs. | Widen to a four-lane median-divided facility and construct sidewalk. | 1.52 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 14400000
U-6244 | Highway | Locally Selected | US 64 Business (Wendell Boulevard) | SR 1007 (Wendell Falls Parkway) in Wendell. | Construct intersection improvements and include closure of Wall Street. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | RIGHT-OF-WAY | 83000
U-6244 | Highway | Locally Selected | US 64 Business (Wendell Boulevard) | SR 1007 (Wendell Falls Parkway) in Wendell. | Construct intersection improvements and include closure of Wall Street. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | RIGHT-OF-WAY | 27000
U-6244 | Highway | Locally Selected | US 64 Business (Wendell Boulevard) | SR 1007 (Wendell Falls Parkway) in Wendell. | Construct intersection improvements and include closure of Wall Street. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 1557000
U-6244 | Highway | Locally Selected | US 64 Business (Wendell Boulevard) | SR 1007 (Wendell Falls Parkway) in Wendell. | Construct intersection improvements and include closure of Wall Street. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 519000
U-6245 | Highway | Economic Development | SR 1146 (West Ten Road) | SR 1114 (Buckhorn Road) to West of SR 1137 (Bushy Cook Road) in Mebane. | Construct overlay, paved shoulders and turn lanes. | 1.68 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE | Division 7 |  | T | ENGINEERING | 109000
U-6245 | Highway | Economic Development | SR 1146 (West Ten Road) | SR 1114 (Buckhorn Road) to West of SR 1137 (Bushy Cook Road) in Mebane. | Construct overlay, paved shoulders and turn lanes. | 1.68 | Orange | 7 | Triangle West TPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE | Division 7 |  | T | CONSTRUCTION | 829000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | BGDA | ENGINEERING | 160000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 40000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | T(DA) | RIGHT-OF-WAY | 280000 | FY 2026: 280000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 70000 | FY 2026: 70000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | T(DA) | CONSTRUCTION | 1365000 | FY 2027: 639000; FY 2028: 726000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | L | CONSTRUCTION | 100000 | FY 2027: 100000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (Rocky River Road) intersection near Monroe. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 615000 | FY 2027: 288000; FY 2028: 327000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | BGDA | ENGINEERING | 254000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | ENGINEERING | 109000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | RIGHT-OF-WAY | 189000 | FY 2027: 189000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | RIGHT-OF-WAY | 81000 | FY 2028: 81000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | BGDA | CONSTRUCTION | 3101000 | FY 2030: 3101000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | CONSTRUCTION | 1787000 | FY 2028: 18000; FY 2029: 1516000; FY 2030: 253000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | CONSTRUCTION | 387000 | FY 2028: 387000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L(M) | CONSTRUCTION | 1329000 | FY 2030: 1329000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (Potter Road) intersection in Wesley Chapel. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | CONSTRUCTION | 381000 | FY 2028: 4000; FY 2029: 323000; FY 2030: 54000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | ENGINEERING | 160000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | ENGINEERING | 40000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | RIGHT-OF-WAY | 1278000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | RIGHT-OF-WAY | 320000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | CONSTRUCTION | 2835000 | FY 2027: 29000; FY 2028: 2074000; FY 2029: 732000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (Old Providence Road) intersection in Waxhaw. | Construct intersection improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | CONSTRUCTION | 709000 | FY 2027: 428000; FY 2028: 281000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | BGDA | ENGINEERING | 448000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | L(M) | ENGINEERING | 112000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | T(DA) | RIGHT-OF-WAY | 400000 | FY 2026: 400000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | L | RIGHT-OF-WAY | 100000 | FY 2026: 100000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | T(DA) | CONSTRUCTION | 3205000 | FY 2028: 3205000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (Langtree Road) intersection near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | L | CONSTRUCTION | 801000 | FY 2028: 801000
U-6251 | Highway | Appalachian Development Highway System | New Route | Hakkon Industries in Enka Commerce Park. | Construct access road. | 0.3 | Buncombe | 13 | French Broad River MPO | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. HF REPRESENTS SPOT MOBILITY FUNDS. | Exempt |  |  |  | 250000
U-6251 | Highway | Appalachian Development Highway System | New Route | Hakkon Industries in Enka Commerce Park. | Construct access road. | 0.3 | Buncombe | 13 | French Broad River MPO | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. HF REPRESENTS SPOT MOBILITY FUNDS. | Exempt |  | ADHSL | MITIGATION | 140000
U-6251A | Highway | Appalachian Development Highway System | New Route | US 19 / US 23 (Smokey Park Highway) to Walkoff Way. | Construct access road. | 0.3 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 1850000
U-6251A | Highway | Appalachian Development Highway System | New Route | US 19 / US 23 (Smokey Park Highway) to Walkoff Way. | Construct access road. | 0.3 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 1000000
U-6251B | Highway | Appalachian Development Highway System | US 19 / US 23 (Smokey Park Highway) | SR 3688 (Enka Heritage Parkway) intersection. | Construct intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | ADHSL | RIGHT-OF-WAY | 900000
U-6251B | Highway | Appalachian Development Highway System | US 19 / US 23 (Smokey Park Highway) | SR 3688 (Enka Heritage Parkway) intersection. | Construct intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 160000
U-6251B | Highway | Appalachian Development Highway System | US 19 / US 23 (Smokey Park Highway) | SR 3688 (Enka Heritage Parkway) intersection. | Construct intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 35000
U-6251B | Highway | Appalachian Development Highway System | US 19 / US 23 (Smokey Park Highway) | SR 3688 (Enka Heritage Parkway) intersection. | Construct intersection improvements. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | HF | CONSTRUCTION | 200000
W-5201 | Highway | Safety | Various | Routes in Division 1. | Improve rumble stripes, guardrail, safety, and lighting. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 695000
W-5202 | Highway | Safety | Various | Routes in Division 2. | Improve rumble stripes, guardrail, safety, and lighting. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS | Region B |  |  |  | 8819000
W-5203 | Highway | Safety | Various | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 21485000
W-5203DIV | Highway | Safety | Various | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Onslow, Brunswick, New Hanover | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO |  | Division 3
W-5203REG | Highway | Safety | Various | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Onslow | 3 | Jacksonville Urban Area MPO |  | Region B
W-5203SW | Highway | Safety | Various | Routes in Division 3. | Improve rumble stripes, guardrail, safety, and lighting. |  | Brunswick, Onslow, New Hanover | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO |  | Statewide Mobility
W-5203U | Highway | Transition | NC 53 (Western Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville. | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | UTILITIES | 61000
W-5203U | Highway | Transition | NC 53 (Western Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville. | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 1863000
W-5203U | Highway | Transition | NC 53 (Western Boulevard) | SR 1336 (Henderson Drive) intersection in Jacksonville. | Construct intersection improvements. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HF(M) | CONSTRUCTION | 500000
W-5204 | Highway | Safety | Various | Routes in Division 4. | Improve rumble stripes, guardrail, safety, and lighting. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 7548000
W-5204DIV | Highway | Safety | Various | Routes in Division 4. | Improve rumble stripes, guardrail, safety, and lighting. |  | Johnston, Wilson | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Division 4
W-5204E | Highway | Safety | SR 1524 (Old Drug Store Road) | SR 1525 (Cornwallis Road) intersection. | Install signal and improve curve. | 0.5 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | HSIP | RIGHT-OF-WAY | 200000
W-5204E | Highway | Safety | SR 1524 (Old Drug Store Road) | SR 1525 (Cornwallis Road) intersection. | Install signal and improve curve. | 0.5 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | HSIP | CONSTRUCTION | 997000
W-5204REG | Highway | Safety | Various | Routes in Division 4. | Improve rumble stripes, guardrail, safety, and lighting. |  | Johnston, Wilson | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A
W-5205 | Highway | Safety | Various | Routes in Division 5. | Improve rumble stripes, guardrail, safety, and lighting. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | UNDER CONSTRUCTION |  |  |  |  | 10184000
W-5205DIV | Highway | Safety | Various | Routes in Division 5 | Improve rumble stripes, guardrail, safety, and lighting. |  | Wake, Durham | 5 | Capital Area MPO, Triangle West TPO |  | Division 5
W-5205REG | Highway | Safety | Various | Routes in Division 5 | Improve rumble stripes, guardrail, safety, and lighting. |  | Wake | 5 | Capital Area MPO |  | Region C
W-5208 | Highway | Safety | Various | Routes in Division 8. | Improve rumble stripes, guardrail, safety, and lighting. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | UNDER CONSTRUCTION |  |  |  |  | 5463000
W-5208MA | Highway | Safety | US 15 / US 501 | NC 144 intersection. | Construct roundabout. | 0.5 | Scotland | 8 | Lumber River RPO | UNDER CONSTRUCTION | Region E
W-5212 | Highway | Safety | Various | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. HF(M) IS SPOT SAFETY FUNDS. |  |  |  |  | 19025000
W-5212DIV | Highway | Safety | Various | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 50000
W-5212DIV | Highway | Safety | Various | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Iredell, Catawba | 12 | Charlotte Regional TPO, Greater Hickory MPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 2500000
W-5212J | Highway | Transition | SR 1302 (Perth Road) | SR 1378 (Judas Road) and SR 1302 (Cornelius Road) intersections near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $178K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | ENGINEERING | 178000
W-5212J | Highway | Transition | SR 1302 (Perth Road) | SR 1378 (Judas Road) and SR 1302 (Cornelius Road) intersections near Mooresville. | Construct intersection improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $178K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | HF(M) | ENGINEERING | 178000
W-5212JA | Highway | Safety | SR 1303 (Perth Road) | SR 1378 (Judas Road) intersection near Mooresville. | Install signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | BGDA | RIGHT-OF-WAY | 13000
W-5212JA | Highway | Safety | SR 1303 (Perth Road) | SR 1378 (Judas Road) intersection near Mooresville. | Install signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | HF(M) | RIGHT-OF-WAY | 12000
W-5212JA | Highway | Safety | SR 1303 (Perth Road) | SR 1378 (Judas Road) intersection near Mooresville. | Install signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 62000
W-5212JA | Highway | Safety | SR 1303 (Perth Road) | SR 1378 (Judas Road) intersection near Mooresville. | Install signal. | 0.5 | Iredell | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | HF(M) | CONSTRUCTION | 63000
W-5212JB | Highway | Safety | SR 1303 (Perth Road) | SR 1302 (Cornelius Road) intersection near Mooresville. | Install signal and turn lanes. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | RIGHT-OF-WAY | 100000
W-5212JB | Highway | Safety | SR 1303 (Perth Road) | SR 1302 (Cornelius Road) intersection near Mooresville. | Install signal and turn lanes. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | HF(M) | RIGHT-OF-WAY | 25000
W-5212JB | Highway | Safety | SR 1303 (Perth Road) | SR 1302 (Cornelius Road) intersection near Mooresville. | Install signal and turn lanes. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | CONSTRUCTION | 873000
W-5212JB | Highway | Safety | SR 1303 (Perth Road) | SR 1302 (Cornelius Road) intersection near Mooresville. | Install signal and turn lanes. | 0.5 | Iredell | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | HF(M) | CONSTRUCTION | 218000
W-5212N | Highway | Safety | NC 279 (Dallas Cherryville Highway) | South of SR 1438 (St. Mark's Church Road) to north of NC 275. | Construct safety improvements including passing zones. | 8.02 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $9.912 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Region F |  | T | BUILD NC CON | 12750000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
W-5212REG | Highway | Safety | Various | Routes in Division 12. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Gaston, Iredell, Catawba | 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO, Greater Hickory MPO |  | Region F
W-5213 | Highway | Safety | Various | Routes in Division 13. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 4768000
W-5213DIV | Highway | Safety | Various | Routes in Division 13. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Buncombe | 13 | French Broad River MPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 50000
W-5213DIV | Highway | Safety | Various | Routes in Division 13. | Install rumble stripes, guardrail, safety and lighting improvements. |  | Buncombe | 13 | French Broad River MPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 700000
W-5213G | Highway | Safety | SR 2002 (Riceville Road) | North of US 70 to SR 2419 (Bull Creek Road) near Haw Creek. | Install 6" long life pavement markings. | 3.64 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 909000
W-5503 | Highway | Transition | NC 268 | Various locations east of Wilkesboro. | Widen roadway, improve shoulders, and install guardrail, rumble stripes, and pavement markings. |  | Wilkes | 11 | High Country RPO | PART COMPLETE | Region F |  |  |  | 3850000
W-5503A | Highway | Safety | NC 268 | SR 1966 (Airport Road) to SR 2026 (Austin Traphill Road). | Install guardrail and pavement markings. | 13.75 | Wilkes | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | HSIP | CONSTRUCTION | 1000000
W-5519 | Highway | Safety | I-95 Business / US 301 | NC 87 South to NC 59. | Construct safety improvements. | 7.29 | Cumberland | 6 | Fayetteville Area MPO | COMPLETE. | Region C |  |  |  | 10123000
W-5600 | Highway | STI (Prioritization) | US 70 (Future I-42) | US 70 Business to Neuse River Bridge. | Construct freeway with interchanges at SR 1501 (Swift Creek Road) and SR 1919 (Wilson's Mills Road). | 5.63 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  |  |  | 9292000
W-5600 | Highway | STI (Prioritization) | US 70 (Future I-42) | US 70 Business to Neuse River Bridge. | Construct freeway with interchanges at SR 1501 (Swift Creek Road) and SR 1919 (Wilson's Mills Road). | 5.63 | Johnston | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHP | CONSTRUCTION | 87693000
W-5601 | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations. |  | Statewide | 99 | Statewide Project | IN PROGRESS |  |  |  |  | 130411000
W-5601DIV | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on division category. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | HSIP | RIGHT-OF-WAY | 68000
W-5601DIV | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on division category. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | HSIP | CONSTRUCTION | 3670000
W-5601R | Highway | Safety | NC 274 | SR 1443 (Dameron Road) to SR 1405 (Ramseur Road). | Install rumble stripes. | 0.5 | Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 90000
W-5601REG | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on regional category. |  | Statewide | 99 | Statewide Project |  | Region SW |  | HSIP | RIGHT-OF-WAY | 68000
W-5601REG | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on regional category. |  | Statewide | 99 | Statewide Project |  | Region SW |  | HSIP | CONSTRUCTION | 6170000
W-5601SW | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on statewide category. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 90000
W-5601SW | Highway | Safety | Various | Locations statewide | Install rumble strips, guardrail, safety and lighting improvements at selected locations on statewide category. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 3360000
W-5601U | Highway | Safety | NC 150 | NC 152 (western intersection) in Mooresville. | Install rumble stripes, guardrail, safety and lighting improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 472000
W-5601U | Highway | Safety | NC 150 | NC 152 (western intersection) in Mooresville. | Install rumble stripes, guardrail, safety and lighting improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 1150000
W-5601U | Highway | Safety | NC 150 | NC 152 (western intersection) in Mooresville. | Install rumble stripes, guardrail, safety and lighting improvements. | 0.5 | Iredell | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | HF | CONSTRUCTION | 815000
W-5602 | Highway | Safety | NC 172 | Camp Lejeune Gate to NC 210. | Upgrade two lane roadway to three lane roadway with two way left turn lane. | 3.74 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Region B |  |  |  | 13657000
W-5602 | Highway | Safety | NC 172 | Camp Lejeune Gate to NC 210. | Upgrade two lane roadway to three lane roadway with two way left turn lane. | 3.74 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Region B |  | T | BUILD NC CON | 7080000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000
W-5602 | Highway | Safety | NC 172 | Camp Lejeune Gate to NC 210. | Upgrade two lane roadway to three lane roadway with two way left turn lane. | 3.74 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Region B |  | T | CONSTRUCTION | 5103000
W-5701 | Highway | Safety | Various | Routes in Division 1. | Construct safety improvements. |  | Bertie, Martin, Camden, Chowan, Currituck, Dare, Gates, Hertford, Hyde, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | IN PROGRESS. |  |  |  |  | 970000
W-5701C | Highway | Safety | SR 1333 (West Main Street Extension) | 0.6 miles north of SR 1338 (Berea Church Road) to 0.2 miles south of SR 1338 (Berea Church Road). | Improve horizontal alignment with curve improvements. | 0.8 | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | HSIP | RIGHT-OF-WAY | 170000
W-5701C | Highway | Safety | SR 1333 (West Main Street Extension) | 0.6 miles north of SR 1338 (Berea Church Road) to 0.2 miles south of SR 1338 (Berea Church Road). | Improve horizontal alignment with curve improvements. | 0.8 | Pasquotank | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | HSIP | CONSTRUCTION | 2165000 | FY 2026: 1061000; FY 2027: 281000
W-5701DIV | Highway | Safety | Various | Routes in Division 1. | Construct safety improvement. |  | Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1 |  | HSIP | RIGHT-OF-WAY | 30000
W-5701DIV | Highway | Safety | Various | Routes in Division 1. | Construct safety improvement. |  | Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1 |  | HSIP | CONSTRUCTION | 375000
W-5701REG | Highway | Safety | Various | Routes in Division 1. | Construct safety improvement. |  | Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 30000
W-5701REG | Highway | Safety | Various | Routes in Division 1. | Construct safety improvement. |  | Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | HSIP | CONSTRUCTION | 375000
W-5701SW | Highway | Safety | Various | Routes in Division 1. | Construct safety improvement. |  | Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5701SW | Highway | Safety | Various | Routes in Division 1. | Construct safety improvement. |  | Bertie, Currituck, Camden, Chowan, Dare, Gates, Hertford, Hyde, Martin, Northampton, Pasquotank, Perquimans, Tyrrell, Washington | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5702 | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | IN PROGRESS |  |  |  |  | 17780000
W-5702DIV | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2 |  | HSIP | RIGHT-OF-WAY | 30000
W-5702DIV | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 375000
W-5702REG | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 131000
W-5702REG | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 3125000
W-5702SW | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5702SW | Highway | Safety | Various | Routes in Division 2. | Construct safety improvement. |  | Beaufort, Carteret, Craven, Pitt, Greene, Jones, Lenoir, Pamlico | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5703 | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | IN PROGRESS |  |  |  |  | 2536000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | RIGHT-OF-WAY | 363000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | BGDA | RIGHT-OF-WAY | 190000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | L | RIGHT-OF-WAY | 47000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | UTILITIES | 127000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | CONSTRUCTION | 3360000 | FY 2026: 3360000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | BGDA | CONSTRUCTION | 272000 | FY 2026: 272000
W-5703C | Highway | Safety | US 421 (Carolina Beach Road) | US 117 / NC 132 (College Road) to 200 feet north of Wiloughby Park. | Install curb and gutter, multi-use path, sidewalk, pedestrian signals, crosswalks, and lighting. | 0.71 | New Hanover | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | L(M) | CONSTRUCTION | 68000 | FY 2026: 68000
W-5703DIV | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 30000
W-5703DIV | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Division 3 |  | HSIP | CONSTRUCTION | 375000
W-5703REG | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Region B |  | HSIP | RIGHT-OF-WAY | 30000
W-5703REG | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Region B |  | HSIP | CONSTRUCTION | 375000
W-5703SW | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5703SW | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5704 | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | IN PROGRESS |  |  |  |  | 20827000
W-5704DIV | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | RIGHT-OF-WAY | 144000
W-5704DIV | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 360000
W-5704E | Highway | Safety | SR 1700 (Covered Bridge Road) | East of SR 1003 (Buffalo Road) to west of SR 2685 (Helena Lane). | Construct safety improvement. | 1.41 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 4 |  | HSIP | RIGHT-OF-WAY | 1200000
W-5704E | Highway | Safety | SR 1700 (Covered Bridge Road) | East of SR 1003 (Buffalo Road) to west of SR 2685 (Helena Lane). | Construct safety improvement. | 1.41 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 4 |  | T | RIGHT-OF-WAY | 600000
W-5704E | Highway | Safety | SR 1700 (Covered Bridge Road) | East of SR 1003 (Buffalo Road) to west of SR 2685 (Helena Lane). | Construct safety improvement. | 1.41 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 4 |  | HSIP | CONSTRUCTION | 4833000 | FY 2026: 1643000; FY 2027: 1933000; FY 2028: 1257000
W-5704E | Highway | Safety | SR 1700 (Covered Bridge Road) | East of SR 1003 (Buffalo Road) to west of SR 2685 (Helena Lane). | Construct safety improvement. | 1.41 | Johnston | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 4 |  | T | CONSTRUCTION | 9667000 | FY 2026: 3287000; FY 2027: 3867000; FY 2028: 2513000
W-5704K | Highway | Safety | SR 1927 (Genoa Road) | Crescent drive intersection. | Construct intersection improvements. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | RIGHT-OF-WAY | 40000
W-5704K | Highway | Safety | SR 1927 (Genoa Road) | Crescent drive intersection. | Construct intersection improvements. | 0.5 | Wayne | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 857000
W-5704REG | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 30000
W-5704REG | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO |  | Region A |  | HSIP | CONSTRUCTION | 455000
W-5704SW | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5704SW | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 480000
W-5705 | Highway | Safety | Various | Routes in Division 5. | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | IN PROGRESS; $150K NHP FUNDING APPLIED TO W-5705S. |  |  |  |  | 6001000
W-5705AI | Highway | Safety | US 501 Business (Roxboro Street) | SR 1443 (Horton Road) / SR 1641 (Denfield Street) intersection. | Construct left turn lanes. | 0.5 | Durham | 5 | Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 1700000
W-5705DIV | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 104000
W-5705DIV | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Division 5 |  | HSIP | CONSTRUCTION | 540000
W-5705G | Highway | Safety | SR 1001 (Warrenton Road) | SR 1507 (Brookston Road) intersection. | Construct intersection improvements. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 790000
W-5705REG | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 104000
W-5705REG | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Region C |  | HSIP | CONSTRUCTION | 540000
W-5705SW | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 137000
W-5705SW | Highway | Safety | Various | Routes in Division 5 | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 720000
W-5706 | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | IN PROGRESS. "HF" FUNDING REPRESENTS HIGH IMPACT / LOW COST (HILC) FUNDS. |  |  |  |  | 14907000
W-5706DIV | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Division 6 |  | HSIP | RIGHT-OF-WAY | 30000
W-5706DIV | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 375000
W-5706L | Highway | Safety | NC 27 / SR 1006 (Old Stage Road) | SR 2084 (Leslies Campbell Avenue) intersection in Buise Creek. | Construct roundabout. | 0.5 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | UTILITIES | 248000
W-5706L | Highway | Safety | NC 27 / SR 1006 (Old Stage Road) | SR 2084 (Leslies Campbell Avenue) intersection in Buise Creek. | Construct roundabout. | 0.5 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HF | UTILITIES | 30000
W-5706L | Highway | Safety | NC 27 / SR 1006 (Old Stage Road) | SR 2084 (Leslies Campbell Avenue) intersection in Buise Creek. | Construct roundabout. | 0.5 | Harnett | 6 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | CONSTRUCTION | 3150000
W-5706N | Highway | Safety | NC 710 | SR 1339 (Deep Branch Road) intersection in Pembroke. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | CRPLT5 | CONSTRUCTION | 3286000
W-5706N | Highway | Safety | NC 710 | SR 1339 (Deep Branch Road) intersection in Pembroke. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) | CONSTRUCTION | 821000
W-5706N | Highway | Safety | NC 710 | SR 1339 (Deep Branch Road) intersection in Pembroke. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | L | CONSTRUCTION | 121000
W-5706N | Highway | Safety | NC 710 | SR 1339 (Deep Branch Road) intersection in Pembroke. | Construct roundabout. | 0.5 | Robeson | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HF | CONSTRUCTION | 500000
W-5706REG | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 135000
W-5706REG | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 519000
W-5706SW | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 90000
W-5706SW | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5706U | Highway | Safety | SR 1404 (Hay Street / Morganton Road) | SR 3578 (Fort Bragg Road), Oakridge Avenue, and Highland Avenue intersections in Fayetteville. | Upgrade traffic signals and improve pedestrian crossings. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 100000
W-5707 | Highway | Safety | Various | Routes in Division 7. | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | IN PROGRESS |  |  |  |  | 4057000
W-5707DIV | Highway | Safety | Various | Routes in Division 7 | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 90000
W-5707DIV | Highway | Safety | Various | Routes in Division 7 | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Division 7 |  | HSIP | CONSTRUCTION | 555000
W-5707REG | Highway | Safety | Various | Routes in Division 7 | Construct safety improvements. |  | Alamance, Caswell, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 90000
W-5707REG | Highway | Safety | Various | Routes in Division 7 | Construct safety improvements. |  | Alamance, Caswell, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Region D |  | HSIP | CONSTRUCTION | 555000
W-5707SW | Highway | Safety | Various | Routes in Division 7 | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 120000
W-5707SW | Highway | Safety | Various | Routes in Division 7 | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 740000
W-5708 | Highway | Safety | Various | Routes in Division 8. | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO | IN PROGRESS |  |  |  |  | 8324000
W-5708DIV | Highway | Safety | Various | Routes in Division 8 | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Division 8 |  | HSIP | RIGHT-OF-WAY | 90000
W-5708DIV | Highway | Safety | Various | Routes in Division 8 | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Division 8 |  | HSIP | CONSTRUCTION | 540000
W-5708L | Highway | Safety | US 220 Business (North Fayetteville Street) | Beasley Street to Balfour Avenue in Asheboro. | Construct two-way left turn lane. | 0.37 | Randolph | 8 | Piedmont Triad RPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 150000 | FY 2026: 150000
W-5708L | Highway | Safety | US 220 Business (North Fayetteville Street) | Beasley Street to Balfour Avenue in Asheboro. | Construct two-way left turn lane. | 0.37 | Randolph | 8 | Piedmont Triad RPO |  | Region E |  | HSIP | CONSTRUCTION | 320000 | FY 2028: 3000; FY 2029: 317000
W-5708REG | Highway | Safety | Various | Routes in Division 8 | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 90000
W-5708REG | Highway | Safety | Various | Routes in Division 8 | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Region E |  | HSIP | CONSTRUCTION | 540000
W-5708SW | Highway | Safety | Various | Routes in Division 8 | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 120000
W-5708SW | Highway | Safety | Various | Routes in Division 8 | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 720000
W-5709 | Highway | Safety | Various | Routes in Division 9. | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; $2.5M NHP FUNDING APPLIED TO W-5709E. |  |  |  |  | 6306000
W-5709DIV | Highway | Safety | Various | Routes in Division 9 | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | RIGHT-OF-WAY | 90000
W-5709DIV | Highway | Safety | Various | Routes in Division 9 | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | CONSTRUCTION | 555000
W-5709E | Highway | Safety | NC 153 (Rice Street) | SR 1197 (Cannon Farm Road / Mt Moriah Church Road) in China Grove. | Construct roundabout. | 0.5 | Rowan | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | BGANY | CONSTRUCTION | 2500000 | FY 2026: 203000
W-5709REG | Highway | Safety | Various | Routes in Division 9 | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 90000
W-5709REG | Highway | Safety | Various | Routes in Division 9 | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Region D |  | HSIP | CONSTRUCTION | 555000
W-5709SW | Highway | Safety | Various | Routes in Division 9 | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 120000
W-5709SW | Highway | Safety | Various | Routes in Division 9 | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 740000
W-5710 | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HF(M) FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. |  |  |  |  | 15485000
W-5710AD | Highway | Safety | SR 1005 (Landsford Road) | SR 1937 (Old Pageland Marshville Road). | Install an all way stop. |  | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 30000
W-5710AH | Highway | Safety | NC 200 (Lancaster Highway) | SR 1137 (Potter Road) intersection near Waxhaw. | Construct safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 650000
W-5710AH | Highway | Safety | NC 200 (Lancaster Highway) | SR 1137 (Potter Road) intersection near Waxhaw. | Construct safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 2623000
W-5710AH | Highway | Safety | NC 200 (Lancaster Highway) | SR 1137 (Potter Road) intersection near Waxhaw. | Construct safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | HF(M) | CONSTRUCTION | 291000
W-5710AI | Highway | Safety | NC 218 | SR 1606 (Sikes Mills Road) intersection near Fairview. | Construct roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 1217000
W-5710AN | Highway | Safety | SR 1009 (Old Charlotte Highway) | Williams Road in Monroe. | Construct safety improvements. |  | Union | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 952000
W-5710AO | Highway | Safety | SR 1002 (Old Salisbury Concord Road) | SR 2400 (Irish Potato Road) near Kannapolis. | Construct safety improvements. | 0.5 | Cabarrus | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | CONSTRUCTION | 1296000
W-5710DIV | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | RIGHT-OF-WAY | 410000
W-5710DIV | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | CONSTRUCTION | 2025000
W-5710REG | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 540000
W-5710REG | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 720000
W-5710SW | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 160000
W-5710SW | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | CMAQ | ENGINEERING | 336000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | HSIP | ENGINEERING | 255000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | ENGINEERING | 67000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | T(M) | ENGINEERING | 28000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 102000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 841000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 960000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 37000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 450000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 400000 | FY 2026: 253000; FY 2027: 147000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | HSIP | CONSTRUCTION | 1355000 | FY 2026: 855000; FY 2027: 500000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 2455000 | FY 2026: 1550000; FY 2027: 905000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 2596000 | FY 2026: 2596000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | T(M) | CONSTRUCTION | 151000 | FY 2026: 95000; FY 2027: 56000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 1363000 | FY 2026: 1100000; FY 2027: 263000
W-5710X | Highway | Safety | SR 2025 (Oakdale Road) | SR 2108 (Sunset Boulevard) / SR 2025 (Miranda Road) / SR 2040 (Lawing Road) intersection near Charlotte. | Construct safety improvements. | 0.5 | Mecklenburg | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 1426000 | FY 2026: 1426000
W-5710Y | Highway | Safety | SR 1315 (New Town Road) | SR 1008 (Waxhaw-Indian Trail Road) intersection in Wesley Chapel. | Construct safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | HSIP | CONSTRUCTION | 850000
W-5710Y | Highway | Safety | SR 1315 (New Town Road) | SR 1008 (Waxhaw-Indian Trail Road) intersection in Wesley Chapel. | Construct safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 1385000
W-5710Y | Highway | Safety | SR 1315 (New Town Road) | SR 1008 (Waxhaw-Indian Trail Road) intersection in Wesley Chapel. | Construct safety improvements. | 0.5 | Union | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | HF(M) | CONSTRUCTION | 346000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | BGDA | ENGINEERING | 156000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | HF(M) | ENGINEERING | 39000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | BGDA | RIGHT-OF-WAY | 28000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | HF(M) | RIGHT-OF-WAY | 7000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | HSIP | CONSTRUCTION | 671000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | BGANY | CONSTRUCTION | 1486000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | L(M) | CONSTRUCTION | 200000
W-5710Z | Highway | Safety | NC 200 (Lancaster Highway) | NC 522 / SR 1007 (South Rocky River Road) / SR 1146 (Parkwood School Road) intersection near Mineral Springs. | Construct 5-approach roundabout. | 0.5 | Union | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | HF(M) | CONSTRUCTION | 214000
W-5711 | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | [5 empty] | 1178000
W-5711DIV | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | RIGHT-OF-WAY | 120000
W-5711DIV | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | CONSTRUCTION | 720000
W-5711REG | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | RIGHT-OF-WAY | 120000
W-5711REG | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | CONSTRUCTION | 720000
W-5711SW | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 160000
W-5711SW | Highway | Safety | Various | Routes in Division 11. | Construct safety improvements. |  | Caldwell, Surry, Watauga, Wilkes, Alleghany, Ashe, Avery, Yadkin | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
W-5712 | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS |  |  |  |  | 5273000
W-5712DIV | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 120000
W-5712DIV | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 720000
W-5712R | Highway | Safety | SR 1003 (Buffalo Shoals Road) | SR 1343 (Ivey Church Road). | Construct safety improvements. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | HSIP | RIGHT-OF-WAY | 42000
W-5712R | Highway | Safety | SR 1003 (Buffalo Shoals Road) | SR 1343 (Ivey Church Road). | Construct safety improvements. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | HSIP | UTILITIES | 5000
W-5712R | Highway | Safety | SR 1003 (Buffalo Shoals Road) | SR 1343 (Ivey Church Road). | Construct safety improvements. | 0.5 | Lincoln | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | HSIP | CONSTRUCTION | 610000
W-5712REG | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 120000
W-5712REG | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 720000
W-5712SW | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 160000
W-5712SW | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
W-5712U | Highway | Safety | NC 150 | Mile marker 19.3 to Gaston County line and from the Cleveland County line to mile marker 1.2. | Construct safety improvements. | 5.88 | Cleveland, Gaston | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 625000
W-5713 | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | COMPLETE |  |  |  |  | 6567000
W-5713DIV | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 120000
W-5713DIV | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 720000
W-5713REG | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 120000
W-5713REG | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 720000
W-5713SW | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 160000
W-5713SW | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
W-5714 | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS |  |  |  |  | 1499000
W-5714DIV | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | RIGHT-OF-WAY | 120000
W-5714DIV | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | CONSTRUCTION | 720000
W-5714E | Highway | Safety | US 64 | SR 1119 (Sapphire Post Office Road) at Chrysler Curve near Sapphire. | Construct safety improvements. | 0.68 | Jackson | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 975000
W-5714REG | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 120000
W-5714REG | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 720000
W-5714SW | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 160000
W-5714SW | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
W-5715 | Highway | Safety | Various | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project
W-5715DIV | Highway | Safety | Various | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | HSIP | ENGINEERING | 4230000
W-5715REG | Highway | Safety | Various | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project |  | Region SW |  | HSIP | ENGINEERING | 4230000
W-5715SW | Highway | Safety | Various | Locations statewide | Funding for signal retiming and signal operations software to improve safety. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | HSIP | ENGINEERING | 5640000
W-5717 | Highway | Safety | Various | Locations statewide | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project
W-5717DIV | Highway | Safety | Various | Locations statewide | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | HSIP | ENGINEERING | 1350000
W-5717REG | Highway | Safety | Various | Locations statewide | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project |  | Region SW |  | HSIP | ENGINEERING | 1350000
W-5717SW | Highway | Safety | Various | Locations statewide | Funding for highway system data collection. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | HSIP | ENGINEERING | 1800000
W-5803 | Highway | Safety | Various | Routes in Division 3. | Construct safety improvement. |  | Duplin, Onslow, Pender, Sampson, Brunswick, New Hanover | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study
W-5803A | Highway | Safety | US 74 (Eastwood Road) | US 17 (Military Cutoff Road) and Cavalier Drive intersections in Wilmington. | Upgrade pedestrian signals. | 0.5 | New Hanover | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 170000
W-5803B | Highway | Safety | US 17 | Pender County line to mile marker 19.3 in Onslow County. | Install shoulder rumble stripes. | 34.89 | Onslow, Pender | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Cape Fear RPO | COMPLETE. | Statewide Mobility |  | HSIP | CONSTRUCTION | 476000
W-5803C | Highway | Safety | US 17 Business (Marine Boulevard) | SR 1402 (Old Bridge Street) intersection. | Upgrade traffic signal, install pavement markings, and improve sight distance. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 85000
W-5803D | Highway | Safety | NC 24 (West Corbett Avenue) | SR 1512 (Old Hammock Road) intersection. | Upgrade pedestrian signals. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. | Statewide Mobility |  | HSIP | CONSTRUCTION | 17000
W-5803E | Highway | Safety | NC 53 (Western Boulevard) | Center Street / Liberty Drive intersection. | Upgrade traffic signal and add additional speed limit signs. | 0.5 | Onslow | 3 | Jacksonville Urban Area MPO | COMPLETE. | Region B |  | HSIP | CONSTRUCTION | 57000
W-5804 | Highway | Safety | Various | Routes in Division 4. | Construct safety improvement. |  | Edgecombe, Johnston, Nash, Wayne, Halifax, Wilson | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO
W-5804A | Highway | Safety | US 301 | NC 581 intersection. | Construct reduced conflict intersection and adjacent bulbouts. | 1 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 100000
W-5804A | Highway | Safety | US 301 | NC 581 intersection. | Construct reduced conflict intersection and adjacent bulbouts. | 1 | Wilson | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 2584000
W-5804B | Highway | Safety | NC 43 | SR 1500 (Swift Creek School Road) intersection. | Realign intersection. | 0.75 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 45000
W-5804B | Highway | Safety | NC 43 | SR 1500 (Swift Creek School Road) intersection. | Realign intersection. | 0.75 | Nash | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 892000
W-5805 | Highway | Safety | Various | Routes in Division 5. | Construct safety improvements. |  | Durham, Wake, Franklin, Granville, Person, Vance, Warren | 5 | Kerr-Tar RPO, Capital Area MPO, Triangle West TPO | W-5805B PROJECT DELETED AT REQUEST OF DIVISION; WORK TO BE ACCOMPLISHED UNDER U-6023.
W-5805C | Highway | Safety | SR 1820 (Lead Mine Road) | SR 1827 (Lynn Road) intersection in Raleigh. | Construct pedestrian refuge islands, revise curb ramps, crosswalks, and other pavement markings. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 292000
W-5805D | Highway | Safety | NC 42 | Bridge 910023 over Middle Creek. | Install guardrail. | 0.5 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 184000
W-5805E | Highway | Safety | NC 98 | SR 2057 / SR 4465 (Moores Pond Road) | Construct roundabout. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | RIGHT-OF-WAY | 140000
W-5805E | Highway | Safety | NC 98 | SR 2057 / SR 4465 (Moores Pond Road) | Construct roundabout. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | UTILITIES | 125000
W-5805E | Highway | Safety | NC 98 | SR 2057 / SR 4465 (Moores Pond Road) | Construct roundabout. |  | Wake | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | CONSTRUCTION | 1540000 | FY 2026: 15000; FY 2027: 1525000
W-5805F | Highway | Safety | Various | Secondary routes in Wake, Warren, and Franklin Counties. | Install long-life pavement markings. |  | Wake, Franklin, Warren | 5 | Capital Area MPO, Kerr-Tar RPO | COMPLETE | Division 5 |  | HSIP | CONSTRUCTION | 2553000
W-5805G | Highway | Safety | US 1 | SR 1113 (Lake Lodge Road) intersection. | Construct unsignalized reduced conflict intersection. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | CRPLT5 | RIGHT-OF-WAY | 80000
W-5805G | Highway | Safety | US 1 | SR 1113 (Lake Lodge Road) intersection. | Construct unsignalized reduced conflict intersection. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 20000
W-5805G | Highway | Safety | US 1 | SR 1113 (Lake Lodge Road) intersection. | Construct unsignalized reduced conflict intersection. | 0.5 | Vance | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1815000 | FY 2026: 435000
W-5805H | Highway | Safety | SR 1004 (Garner Road); Timber Drive East | SR 2539 (Yeargan Road) intersection, SR 2564 (Creech Road) intersection, and Shenstone Boulevard intersection in Garner. | Upgrade traffic signals. | 1 | Wake | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 75000
W-5806 | Highway | Safety | Various | Routes in Division 6. | Construct safety improvement. |  | Bladen, Columbus, Cumberland, Harnett, Robeson | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO
W-5806A | Highway | Safety | NC 11 | SR 1740 (Old Lake Road) intersection. | Construct roundabout. | 0.5 | Columbus | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 50000
W-5806B | Highway | Safety | SR 1117 (Nursery Road); SR 3242 (Overhills Road); SR 1121 (Ray Road) | NC 27 to SR 3242 (Overhills Road); NC 24 / NC 87 to SR 1117 (Nursery Road); SR 1117 (Nursery Road) to SR 3242 (Overhills Road) | Widen curves and install rumble stripes. | 11.01 | Harnett | 6 | Fayetteville Area MPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 400000
W-5806C | Highway | Safety | SR 1615 (Rosehill Road) | Tamarack Drive and Landau Road intersections. | Construct mini-roundabouts. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | RIGHT-OF-WAY | 75000
W-5806C | Highway | Safety | SR 1615 (Rosehill Road) | Tamarack Drive and Landau Road intersections. | Construct mini-roundabouts. | 0.5 | Cumberland | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 3113000
W-5806D | Highway | Safety | NC 27 | SR 1581 (Bailey's Crossroads) / SR 1705 (Fairground Road) intersection. | Realign and construct intersection improvements. | 0.5 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Region C |  | HSIP | RIGHT-OF-WAY | 100000
W-5806D | Highway | Safety | NC 27 | SR 1581 (Bailey's Crossroads) / SR 1705 (Fairground Road) intersection. | Realign and construct intersection improvements. | 0.5 | Harnett | 6 | Capital Area MPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 606000
W-5806E | Highway | Safety | NC 41 (Martin Luther King Jr Drive) | NC 72 (West Second Street) and SR 1599 (Martin Luther King Jr Drive) intersections. | Construct signalized pedestrian crossings. | 0.5 | Robeson | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 315000
W-5807 | Highway | Safety | Various | Routes in Division 7. | Construct safety improvements. |  | Alamance, Caswell, Guilford, Orange, Rockingham | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Triangle West TPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO
W-5807A | Highway | Safety | US 220 Eastbound | SR 2526 (Summit Avenue) ramp terminals in Greensboro. | Modify channelization island, install traffic signal, pedestrian heads, and crosswalks. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | VRU | CONSTRUCTION | 135000 | FY 2026: 58000
W-5807A | Highway | Safety | US 220 Eastbound | SR 2526 (Summit Avenue) ramp terminals in Greensboro. | Modify channelization island, install traffic signal, pedestrian heads, and crosswalks. | 0.5 | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 315000 | FY 2026: 134000
W-5807B | Highway | Safety | SR 1301 (Boone Station Drive) | SR 1301 (Saint Marks Church Road) / Java Lane and Glidwell Drive / Tiki Lane in Burlington. | Install pedestrian signals, curb ramps, and revise pavement markings. | 0.5 | Alamance | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 75000
W-5808 | Highway | Safety | Various | Routes in Division 8. | Construct safety improvements. |  | Chatham, Montgomery, Moore, Randolph, Hoke, Lee, Richmond, Scotland | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Triangle West TPO
W-5808B | Highway | Safety | US 421 (Future I-685) | NC 902 intersection. | Construct reduced conflict intersection. | 0.5 | Chatham | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 100000
W-5808B | Highway | Safety | US 421 (Future I-685) | NC 902 intersection. | Construct reduced conflict intersection. | 0.5 | Chatham | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 1550000
W-5808C | Highway | Safety | SR 2055 (North Poplar Street) | West Maple Avenue intersection in Aberdeen. | Install all-way stop. | 0.5 | Moore | 8 | Sandhills MPO | UNDER CONSTRUCTION. | Division 8 |  | HSIP | RIGHT-OF-WAY | 2000
W-5808C | Highway | Safety | SR 2055 (North Poplar Street) | West Maple Avenue intersection in Aberdeen. | Install all-way stop. | 0.5 | Moore | 8 | Sandhills MPO | UNDER CONSTRUCTION. | Division 8 |  | HSIP | CONSTRUCTION | 15000
W-5809 | Highway | Safety | Various | Routes in Division 9. | Construct safety improvements. |  | Davidson, Davie, Forsyth, Rowan, Stokes | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO
W-5809A | Highway | Safety | NC 109 | Denton northern municipal boundary to SR 2067 (Lambeth Road). Also, SR 1798 (Old Greensboro Road) / SR 1756 (West Lexington Avenue Extension) to SR 1711 (Gumtree Road). | Install rumble stripes and long-life pavement markings. | 15.99 | Davidson | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 1100000
W-5810 | Highway | Safety | Various | Routes in Division 10. | Construct safety improvements. |  | Anson, Cabarrus, Mecklenburg, Stanly, Union | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
W-5812 | Highway | Safety | Various | Routes in Division 12. | Construct safety improvements. |  | Alexander, Catawba, Cleveland, Gaston, Iredell, Lincoln | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
W-5813 | Highway | Safety | Various | Routes in Division 13. | Construct safety improvements. |  | Buncombe, Burke, Madison, McDowell, Mitchell, Rutherford, Yancey | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO
W-5813A | Highway | Safety | US 25 | US 25 (McDowell Street) at Doctor's Drive / Asheville High School entrance. | Install pedestrian signals, high visibility crosswalks, and curb ramps. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 64000
W-5813B | Highway | Safety | Various | Secondary routes in Division 13. | Install long life pavement markings. |  | Rutherford, Burke, Mitchell, Yancey | 13 | Foothills RPO, Greater Hickory MPO, High Country RPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 1600000
W-5813C | Highway | Safety | SR 1332 (North Louisiana Avenue) | SR 1338 (Emma Road) intersection near Asheville. | Install pedestrian signal phasing, high visibility crosswalks, sidewalk and curb ramps. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | RIGHT-OF-WAY | 2000
W-5813C | Highway | Safety | SR 1332 (North Louisiana Avenue) | SR 1338 (Emma Road) intersection near Asheville. | Install pedestrian signal phasing, high visibility crosswalks, sidewalk and curb ramps. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 155000
W-5813E | Highway | Safety | US 19 / US 23 / US 74 ALT (Patton Avenue) | US 19 / US 23 Business (Haywood Road) / SR 1319 (Johnston Road) intersection in Asheville. | Install pedestrian signal phasing, high visibility crosswalks, and curb ramps. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 145000
W-5813F | Highway | Safety | US 19 / US 23 / US 74 ALT (Smokey Park Highway) | Old Haywood Road intersection in Asheville. | Install pedestrian signal phasing, high visibility crosswalks, and curb ramps. | 0.5 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 105000
W-5813G | Highway | Safety | US 70 (Tunnel Road); US 74 ALT (South Tunnel Road) | Old Chunns Cove Road intersection in Asheville; Main Mall Entrance (east leg) and Lower Mall entrance intersections in Asheville. | Install curb ramps, sidewalk, and signal upgrades. | 1 | Buncombe | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 336000
W-5813H | Highway | Safety | NC 197 | SR 1338 (Wilds Branch Road) to the Mitchell County line near Green Mountain. | Install shoulder guardrail. | 3.74 | Yancey | 13 | High Country RPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 474000
W-5813I | Highway | Safety | SR 2806 (Garren Creek Road) | SR 2815 (Village Road) to SR 2786 (Flat Creek Road / Morgan Hill Road) near Fairview. | Install shoulder guardrail. | 6.53 | Buncombe | 13 | Land-of-Sky RPO | COMPLETE | Division 13 |  | HSIP | CONSTRUCTION | 460000
W-5813J | Highway | Safety | US 221 | US 64 in Rutherford County to the McDowell County line; Rutherford County line to I-40. | Install sinusoidal centerline rumble stripes and long life pavement markings. | 18.99 | McDowell, Rutherford | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 501000
W-5814 | Highway | Safety | Various | Routes in Division 14. | Construct safety improvements. |  | Cherokee, Clay, Graham, Haywood, Henderson, Jackson, Macon, Polk, Swain, Transylvania | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO
W-5814A | Highway | Safety | US 276 | South of SR 1326 (Bob Boyd Road). | Construct left turn lane. | 0.5 | Haywood | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 380000
W-5814B | Highway | Safety | US 74 WB | I-26 to the Rutherford County line. | Upgrade guardrail end terminals to current standards. | 12.65 | Polk | 14 | Foothills RPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 199000
W-5814C | Highway | Safety | US 74 EB | I-26 to the Rutherford County line. | Upgrade guardrail end terminals to current standards. | 12.65 | Polk | 14 | Foothills RPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 179000
W-9999 | Highway | Safety | Various | Locations statewide | Funding for highway safety improvement program balance. |  | Statewide | 99 | Statewide Project
W-9999DIV | Highway | Safety | Various | Locations statewide | Funding for highway safety improvement program balance. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | HSIP | CONSTRUCTION | 45163000
W-9999REG | Highway | Safety | Various | Locations statewide | Funding for highway safety improvement program balance. |  | Statewide | 99 | Statewide Project |  | Region SW |  | HSIP | CONSTRUCTION | 55935000
W-9999SW | Highway | Safety | Various | Locations statewide | Funding for highway safety improvement program balance. |  | Statewide | 99 | Statewide Project |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 74580000
Y-4805F | Rail | Rail-Highway Grade Crossing Closure | Carolina Coastal Railway | SR 2513 (Fayetteville Street) intersection in Knightdale | Close existing at-grade crossing (#465681P). |  | Wake | 5 | Capital Area MPO |  | Division 5 |  | RR | CONSTRUCTION | 3000000
Y-4807B | Rail | Rail-Highway Grade Crossing Closure | Lowdermilk Street / Sykes Avenue / Pine Street | SR 3163 (East Market Street) intersections in Greensboro | Realign Lowdermilk Street and Sykes Avenue including relocation of crossing (#722958T) and close Pine Street crossing (#722957L). |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 2430000
Y-4807B | Rail | Rail-Highway Grade Crossing Closure | Lowdermilk Street / Sykes Avenue / Pine Street | SR 3163 (East Market Street) intersections in Greensboro | Realign Lowdermilk Street and Sykes Avenue including relocation of crossing (#722958T) and close Pine Street crossing (#722957L). |  | Guilford | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | RR | CONSTRUCTION | 5000000 | FY 2026: 493000
Y-4810K | Rail | STI (Prioritization) | Norfolk Southern Mainline | Rogers Lake Road Crossing (724408Y) in Kannapolis. | Construct grade separation. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | Statewide Mobility |  |  |  | 2800000
Y-4810K | Rail | STI (Prioritization) | Norfolk Southern Mainline | Rogers Lake Road Crossing (724408Y) in Kannapolis. | Construct grade separation. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | Statewide Mobility |  | T | CONSTRUCTION | 18720000
Y-4810K | Rail | STI (Prioritization) | Norfolk Southern Mainline | Rogers Lake Road Crossing (724408Y) in Kannapolis. | Construct grade separation. |  | Cabarrus | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | Statewide Mobility |  | O | CONSTRUCTION | 450000
Y-5500 | Rail | Rail-Highway Grade Crossing Closure | Various | Various locations | Funding for traffic separation study implementation and closures - unprogrammed balance. |  | Statewide | 99 | Statewide Project | RIGHT-OF-WAY IN PROGRESS | Division 99 |  |  |  | 1944000
Y-5500 | Rail | Rail-Highway Grade Crossing Closure | Various | Various locations | Funding for traffic separation study implementation and closures - unprogrammed balance. |  | Statewide | 99 | Statewide Project | RIGHT-OF-WAY IN PROGRESS | Division 99 |  | RR | RIGHT-OF-WAY | 1500000
Y-5500 | Rail | Rail-Highway Grade Crossing Closure | Various | Various locations | Funding for traffic separation study implementation and closures - unprogrammed balance. |  | Statewide | 99 | Statewide Project | RIGHT-OF-WAY IN PROGRESS | Division 99 |  | RR | CONSTRUCTION | 7560000
Y-5500EC | Rail | Rail-Highway Grade Crossing Closure | SR 1136 (Tally Ho Road) | Norfolk Southern crossing 734 895A in Stem | Close railway-highway crossing. |  | Granville | 5 | Kerr-Tar RPO |  | Division 5 |  | RR | CONSTRUCTION | 150000
Y-5500ED | Rail | Rail-Highway Grade Crossing Closure | Church Street | Norfolk Southern crossing 734 896G in Stem | Close railway-highway crossing. |  | Granville | 5 | Kerr-Tar RPO |  | Division 5 |  | RR | CONSTRUCTION | 300000
Y-5500IA | Rail | Rail-Highway Grade Crossing Closure | SR 1526 (Henderson Grove Church Road) | Railroad crossing 724 362M | Close railway-highway crossing and construct roadway on new location to Julian Road. |  | Rowan | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | RR | CONSTRUCTION | 4900000
Z-5400 | Rail | Rail-Highway Grade Crossing Improvement | Various | Various locations | Construct highway-rail grade crossing safety improvements. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 28841000
Z-5700 | Rail | Rail-Highway Grade Crossing Improvement | Various | Various locations | Construct highway-rail grade crossing safety improvements. |  | Statewide | 99 | Statewide Project | IN PROGRESS | Division 99 |  |  |  | 16738000
Z-5800 | Rail | Rail-Highway Grade Crossing Improvement | Various | Various locations | Construct highway-rail grade crossing safety improvements. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | RR | RIGHT-OF-WAY | 500000
Z-5800 | Rail | Rail-Highway Grade Crossing Improvement | Various | Various locations | Construct highway-rail grade crossing safety improvements. |  | Statewide | 99 | Statewide Project |  | Division 99 |  | RR | CONSTRUCTION | 3280000

## Fund Sources
Fund Source | Fund Type | Description | Subject to STI
20005(b) | Federal | Pilot Program for Transit-Oriented Development Planning | No
3037 | Federal | Job Assistance and Reverse Commute | No
5303 | Federal | Metropolitan Planning (FMPL) | No
5305 | Federal | FTA Discretionary Grant Funds | No
5307 | Federal | Urbanized Area Formula Program (FUZ) | No
5309 | Federal | Capital Program - Bus Earmark (FBUS) | No
5310 | Federal | Elderly and Persons with Disability (FEPD) | No
5311 | Federal | Non Urbanised Area Formula Program (FNU) | No
5312 | Federal | FUZ 5312 | No
5316 | Federal | Job Assistance And Reverse Commute (JARC) | No
5317 | Federal | New Freedom Program | No
5337 | Federal | Urbanized Area Formula Program (FUZ) | No
5339 | Federal | Capital Program - Bus Earmark (FBUS) | No
5339(b) | Federal | Capital Program - Bus Earmark (FBUS) - Discretionary Grant | No
ADHS | Federal | Appalachian Development Highway System | No
ADHSL | Federal | Appalachian Development Highway System (Local Access Roads) | No
ADTAP | Federal | Appalachian Development portion of 5311 - Non Urbanised Area Formula Program (FNU) | No
ARP | Federal | American Rescue Plan | No
BA | State | Bonus Allocation | No
BFP | Federal | Federal Bridge Improvement Program - Formula | Yes
BFPOFF | Federal | Federal Bridge Improvement Program - Formula (Off System) | Yes
BG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
BG50200 | Federal | Surface Transportation Block Grant Program (50K - 200K) | Yes
BG5200 | Federal | Surface Transportation Block Grant Program (5K - 200K) | Yes
BG5T50 | Federal | Surface Transportation Block Grant Program (5K - 50K) | Yes
BGANY | Federal | Surface Transportation Block Grant Program (Any Area) | Yes
BGBA | Federal | Surface Transportation Block Grant Program (Bonus Allocation) | No
BGDA | Federal | Surface Transportation Block Grant Program (Direct Attributable) | Yes
BGDACV | Federal | COVID Relief Funds | Yes
BGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
BGLT5 | Federal | Surface Transportation Block Grant Program (Less than 5K) | Yes
BGOFF | Federal | Surface Transportation Block Grant Program (Off System) | Yes
BOND R | Other | Revenue Bond | No
BONDRT | Other | Revenue Bond (Loan Advance from Highway Trust Fund) | No
BRGI | Federal | Bridge Inspection | Yes
CARES | Federal | CARES Act Funding | No
CMAQ | Federal | Congestion Mitigation | No
CPF | Federal | Community Project Funding/Congressionally Directed Spending (Grants) | No
CRP550 | Federal | Carbon Reduction Program - (5K - 50K) | No
CRPANY | Federal | Carbon Reduction Program - Any Area | No
CRPDA | Federal | Carbon Reduction Program - Direct Attributable (All MPOs) | No
CRPLT5 | Federal | Carbon Reduction Program - (Less than 5K) | No
DOD | Federal | Department of Defense | No
DP | Federal | Discretionary or Demonstration | No
ER | Federal | Emergency Relief | No
ERFO | Federal | Emergency Relief for Federally Owned Roads | No
FBP | Federal | Ferry Boat Program | Yes
FED | Federal | Unidentified Federal Funding | No
FEDT | Federal | Undesignated Federal Transit Funding | No
FF | Federal | Federal Ferry | Yes
FLAP | Federal | Federal Lands Access Program (Park Roads) | No
FLPF | Federal | Federal Lands Program (Forest Roads) | No
FLTP | Federal | Federal Lands Transportation Program | No
FMOD | Federal | Fixed Guideway Modifications | Yes
FO | Federal | Federal Other | No
FSPR | Federal | State Planning and Research | No
FSRC | Federal | Ferry Service for Rural Communities | No
FTTP | Federal | Federal Tribal Transportation Program | No
FUZ | Federal | Capital Program - Bus Earmark (5309) | No
HF | State | Highway Fund | No
HF(M) | State | State Match using Highway Fund | No
HFB | State | Highway Fund Bridge Replacement Program | Yes
HIB | Federal | Highway Infrastructure Bridge Replacement | Yes
HP | Federal | High Priority | Yes
HRRR | Federal | High Risk Rural Roads | Yes
HSIP | Federal | Highway Safety Improvement Program | Yes
L | Other | Local (Other than for required match) | No
L(M) | Other | Local Match | No
NEVI | Federal | National Electric Vehicle Infrasructure Program Funds | Yes
NHFP | Federal | National Highway Freight Program | Yes
NHP | Federal | National Highway Performance Program | Yes
NHPB | Federal | National Highway Performance Program(Bridge) | Yes
NHPBA | Federal | National Highway Performance Program(Bonus Allocation) | No
NHPIM | Federal | National Highway Performance Program (Interstate Maintenance) | Yes
NRT | Federal | National Recreation Trails | Yes
O | Other | Local, Non Federal or State Funds | No
O(M) | Other | Local, Non Federal or State Funds (Match) | No
PROTCT | Federal | PROTECT Formula Program (Promoting Resilient Operations…) | Yes
RR | Federal | Rail-Highway Safety | Yes
RTAP | Federal | Rural Transit Assistance Program | No
S | State | State | No
S(M) | State | State Match for STP-DA or Garvee Projects | Yes
S(M)BA | State | State Match for Bonus Allocation Projects using Federal funds | No
SBG | Federal | Scenic Byway Grant | Yes
SF | State | Ferries | Yes
SMAP | State | Operating Assistance and State Maintenance | No
SRTS | Federal | Safe Roads to School | Yes
SSO | Federal | Safety System Oversight | No
STBG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
STBGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
STHSR | Federal | Stimulus High Speed Rail | No
STPE | Federal | Surface Transportation Program (Enhancement) | Yes
STPOFF | Federal | Surface Transportation Program (Off System) | Yes
T | State | Highway Trust Funds | Yes
T(DA) | State | Highway Trust Funds - Fund Swaps for DA Projects | Yes
T(M) | State | State Match using Highway Trust Fund | Yes
T(M)BA | State | State Match with Highway Trust Funds used as Bonus Allocation Funds | No
TA | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TA50200 | Federal | Transportation Alternatives Program (50K - 200K) | Yes
TA5200 | Federal | Transportation Alternatives Program (5K - 200K) | Yes
TA5T50 | Federal | Transportation Alternatives Program (5K - 50K) | Yes
TAANY | Federal | Transportation Alternatives Program (Any Area) | Yes
TADA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes
TALT5 | Federal | Transportation Alternatives Program (Less than 5K) | Yes
TAP | Federal | Transportation Alternatives Program (Uncategorized) | Yes
VRU | Federal | Vulnerable Road User | Yes