**ANSON COUNTY CTP SCHEDULE** **TRAVEL DEMAND MODEL SCHEDULE**

***CTP Setup***

Initial Data Collection 5/31/2022 Data Collection and Socio-Economic Forecast

CTP Informational Maps 5/31/2022

CUR and Title VI maps/products 5/31/2022

***Vision***

Draft Goals and Objectives Survey 7/31/2022

***System Analysis***

Base Year Traffic Estimates 7/31/2022 Base Year Model Estimation

Base Year Deficiency Analysis 8/31/2022 Base Year Model Calibration

Transmit SE data for endorsement 7/31/2022

Future Year Traffic Estimates 9/30/2022

Future Year Deficiency Analysis 10/31/2022 Future Year Model

***Alternatives Analysis***

Develop, evaluate, &

analyze alternatives 12/31/2022 Alternative Analysis

***Develop Draft Plan***

Internal review of draft CTP

*(Document/Maps/Project Sheets)* 4/30/2023 Model Documentation

Transmit draft CTP To Locals 5/31/2023

Final approval of draft CTP

*(Complete Document w/ Appendices)* 6/30/2023

***Adopt Plan***

Transmit final draft CTP to Locals 7/31/2023

*(Local Adoption July-early October)*

Transmit BOT materials

*(NCBOT Adoption November)* 11/15/2023

***Closeout***

Distribute adopted maps 12/31/2023

Final CTP document 1/31/2024

CTP Closeout 1/31/2024