## Slide 1: Overview of the STIP Program
Chad Reimakoski– NCDOT Division 7 Division Planning Engineer
Nishant Shah – NCDOT Corridor Development Engineer
4/8/2022

## Slide 2
Maintenance and Capital Improvement Funding for North Carolina
2

## Slide 3: What is a State Transportation Improvement Program (STIP)?
A multi-year capital improvement document that denotes scheduling and funding of transportation improvement projects
Must be updated every 4 years (NC typically updates every 2 years)
NC STIP covers a 10-year period
  1st 5 years referred to as the Delivery STIP
  2nd 5 years referred to as the Developmental STIP
Per 23 CFR 450.216 & 23 U.S. Code § 135 STIP’s must also:
  Be submitted to Federal Highway Administration (FHWA) & Federal Transit Administration (FTA) for approval at least every 4 years
  Be fiscally constrained by year
  Include metropolitan TIPs from Metropolitan Planning Organizations
  Provide public comment opportunity on STIP document
  And include the following information:
    Project description and termini
    Estimated total cost (NCDOT includes Utility, R/W, and Construction costs)
    Federal funds to be obligated
    Responsible agency (such as municipality)
3

## Slide 4
2008
2009
2010
2011
2012
2013
2014
2015
2013
Strategic Transportation Investment (STI) legislation is signed into law, directs transportation funding to results of Prioritization Process
2009
Governor signs Exec. Order #2
2008
Strategic Prioritization Office of Transportation (SPOT) is created
2009
Prioritization 1.0 (P1.0) is implemented
2010-2011
Urban Loop Prioritization Process is implemented
2011
P2.0 is implemented
2012
Mobility Fund Prioritization Process is implemented
2012
Legislature codifies Prioritization Process into Law
2007-2008 McKinsey Consulting conducts evaluation of NCDOT and works with NCDOT staff on transformation
2014
P3.0 is implemented in accordance with STI law
2015
P4.0 is implemented
History of Prioritization
4

## Slide 5: Strategic Transportation Investments (STI) Law – The Why
Growing state
Modernize funding formula and remove politics
Better connect people, products, and places
Successful prioritization efforts
Chart: 
| 2000 | 2035
Population | 8081986 | 12122640
Session 2: So you’ve heard about prioritization
5

## Slide 6: Strategic Transportation Investments (STI) Law – The Why
Prioritizes capital expenditures across all modes (Mobility/Expansion + Modernization)
Needs-based, data-driven
Directly ties funding to Prioritization results
Funding comes from Highway Trust Fund and Federal Aid Program
Workgroup used every cycle for improvement
6

## Slide 7
Anticipated Inflation Impact
Inflation is not explicitly factored into the revenue estimates. However, before programming projects in the STIP, available funds were reduced to account for future inflation. NCDOT uses a 3% per year inflation factor.
The 3% was compounded annually for the first five years, then held constant for the last five years. In the first year (2024), half of the inflation rate was used (1.5%) to ramp up to 3% in year 2 (2025). This allows project costs used in the Program to be shown in current (2024) dollars.

## Slide 8
The STIP must be Fiscally Constrained
During the balancing of the STIP, the program is fiscally constrained to the amount of funds projected to be available each year to prevent over committing of future revenues.
This means that schedule changes may need to be made to existing committed projects in the STIP to account for the new projects and their costs that will be added to the new STIP.
The previous committed projects will stay committed but may be delayed to keep the STIP fiscally constrained and balanced.

## Slide 9
Where do potential projects come from?
MPOs / RPOs
NCDOT personnel
Municipalities
CTPs / MTPs
Corridor plans
Citizens
These projects can look to accomplish Short-term and long-term solutions – it’s imperative to work with our partners

## Slide 10: Key Partners
NCDOT funds six modes of transportation
Annual Budget of approx. $4.8B ($2.8B for STI)
19 MPOs / 18 RPOs
14 NCDOT Divisions

## Slide 11
Strategic Prioritization – What is it exactly?
Well it’s exactly like it sounds…a strategic process to prioritize projects.
  It utilizes transportation data, input of local government partners, and the public to generate scores
      These score are used to rank projects across the state.
  Multiple public input opportunities are provided both before project submittal selections are made and finally after the Draft STIP is released.
  The prioritization process is used for all modes and each transportation mode uses different quantitative criteria, measures, and weights to provide technical data driven scores for projects as recommended by the Prioritization Workgroup and approved by the NC Board of Transportation.
  Also, per the intent of STI for transportation modes to compete for funding, a normalization process was recommended and is used to create minimum percentages of funding for highway and non-highway projects in the combined Regional Impact and Division Needs categories.
      The minimum percentage for highways was 90% and minimum percentage for non-highways was 4%. These percentages are the base numbers for the programming process The final 6% is flexed either to Highway or Non-Highway based on scores, funding availability, and other normalization factors.

## Slide 12
How STI Works

## Slide 13
STI Law Eligibility Definitions
Mode | Statewide Mobility
Highway | Interstates (existing & future) NHS routes (July 1, 2012) STRAHNET ADHS Routes Uncompleted Intrastate projects Designated Toll Facilities
Aviation | Large Commercial Service Airports ($500K cap)
Bicycle-Pedestrian | N/A
Public Transportation | N/A
Ferry | N/A
Rail | Freight Service on Class I Railroad Corridors
Regional Impact
Other US and NC Routes
Other Commercial Service Airports not in Statewide ($300K cap)
N/A
Service spanning two or more counties (10% cap)
Vessel or infrastructure expansion
Rail service spanning two or more counties not in Statewide
Division Needs
All County (SR) Routes Federal-Aid Eligible Local Roads
All Airports without Commercial Service (General Aviation) ($18.5M cap)
All projects ($0 state funds)
All other service, including terminals and stations
Replacement vessels
All other service, including terminals and stations (no short lines)

## Slide 14: STIP Expenditures
40%
$
Statewide Mobility
Divided based on % of State Population
Divided based on
Equal Share
Taken off the top of each Region
Bridge Replacement
Highway Safety
Taken off the top of each Division
Bridge Replacement
Highway Safety
DA Funds (STBG & TAP)
Rail-Highway Crossing
Economic Development
Municipal Roads
Taken off the top of Statewide
Interstate Maintenance
Bridge Replacement
Highway Safety
Remaining Funds Available for 22 Buckets is for Projects from Prioritization Process (minus Committed Projects)
30%
$
Regional Impact
30%
$
Division Needs
DA Funds spent on SW & REG
A
1
2
3
4
5
6
7
8
9
10
11
12
13
14
B
C
E
F
G
D
Statewide Mobility
30%
$
Division Needs
30%
$
Regional Impact

## Slide 15
regions &
divisions

## Slide 16
Quantitative Score vs. Local Input
Statewide Mobility | Criteria 1 = 30% Criteria 2 = 25% Criteria 3 = 15% Criteria 4 = 10% Criteria 5 = 15% Criteria 6 = 5% |  | -- | --
Funding Category | QUANTITATIVE |  | LOCAL INPUT | 
 | Data |  | Division | MPO/RPO
Regional Impact | Criteria 1 = 20% Criteria 2 = 20% Criteria 3 = 10% Criteria 4 = 10% Criteria 5 = 10% |  |  | 
Division Needs | Criteria 1 = 15% Criteria 2 = 15% Criteria 3 = 10% Criteria 4 = 5% Criteria 5 = 5% |  |  | 
100%
70%
50%
15% | 15%
25% | 25%

## Slide 17: P6.0 Highway Criteria & Weights:
** There have been minor scoring changes in P7, compared to P6.

## Slide 18
Session 3: P6.0 Scoring
Building Block Level: Measure
(Statewide Highway Mobility Segment Example)
Congestion 30%
Economic Comp 10%
Safety 10%
Benefit/Cost 25%
Funding Leverage
Future Interstate Completion Factor
Freight 25%
18

## Slide 19: Bicycle & Pedestrian Scoring
Session 7: Non-Highway Scoring - Details
Criteria | Measure | Division Needs (50%)
Safety | (Number of crashes x 40%) + (Crash severity x 20%) + (Safety risk x 20%) + (Safety benefit x 20%) | 20%
Accessibility/ Connectivity | Points of Interest pts + Connections pts + Route pts | 15%
Demand/ Density | # of households and employees per square mile near project | 10%
Cost Effectiveness | (Safety + Accessibility/Connectivity + Demand/Density) / Cost to NCDOT | 5%
19

## Slide 20: Scoring Projects

## Slide 21: Public Involvement
Public Input opportunities occur throughout the STIP/ Prioritization process by way of public information meetings, online applications, or directly emailing of comments. Public input opportunities include:
    During the project submittal selection period for submittal to the current prioritization cycle
    During the Regional Projects Local Input Points Period
    During the Division Needs Projects Local Input Period
    After the release of the Draft STIP for each Prioritization Cycle

## Slide 22
22

## Slide 24
How is the STIP organized?
The transportation program in the STIP is organized in an Excel file that can be sorted and filtered as needed by the reader. The information included for each project includes details on the location of the project: County,
NCDOT Highway Division, Route, Description, and Planning Organization. Projects also list the STI category they are funded from, i.e., by Statewide Mobility, Regional Impact, or Division Needs. The phases of projects
(such as Right of Way (R), Utility relocation (U), and Construction (C) are listed by Fiscal Year along with their costs and anticipated funding sources. For those projects with their first phase of work beginning in the second
half of the STIP (years 2029-2033), they are listed as “Funded for Preliminary Engineering Only.” The Department will begin Preliminary Engineering activities (environmental documentation and design work) at the appropriate
time, but the project will need to compete for funding in a future round of Prioritization and therefore the funding years for phases are unknown at this time. (See next section titled “Strategic Prioritization” for details on project
prioritization.)
All projects require extensive planning, environmental impact and design studies. The location and exact type of improvements are subject to refinement and modification during the planning and design phases.

## Slide 25
How is the STIP organized? – Example

## Slide 26
Does rank determine when a project will be scheduled in the STIP?
Projects are not necessarily scheduled in the STIP in the order of their Prioritization rankings. Factors include:
      Major factor is Project Delivery Time
        Lengthy process to get to the construction phase of a project
        Construction funding cannot be allocated until all preconstruction activities have taken place
          Preliminary Engineer
          Environmental requirement
          Right of Way (purchase) and Utility needs (relocations)
          Final Plans for Construction development
      Also STI law provision which direct programming decision
        Corridor Caps
        Individual model caps
        Must be fiscally constraint per state
        Other federal requirements
        Provision in law to exempt select project from Prioritization (during transition period)

## Slide 27: Factors involved in scheduling projects for the STIP
Session 7: Non-Highway Scoring - Details
28

## Slide 28: Committed Projects / Years Subject to Reprioritization
Session 4: How the Prioritization and Programming Process Works
Green = Projects
considered “Committed”
2022
2023
2024
2025
2026
2027
2028
2029
2030
2031
P6.0 Process (cancelled)
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
2020-2029 STIP (resulting from P5.0)
Blue = Projects to evaluate through Prioritization process
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
P5.0 Process
2018-2027 STIP (resulting from P4.0)
2024
2025
2026
2027
2028
2029
2030
2031
2032
2033
2024-2033 STIP (resulting from P6.0 – committed P5.0 projects)
Gray = Projects
Reprioritized in next round
28
Notes: Delivery STIP – GREEN
Developmental STIP - BLUE

## Slide 29: Possible causes for projects to score low and/or not be selected
Low volume, low safety scores, minimal safety benefit
High cost – e.g. corridor cap
Lack of support
Insufficient Communication
More projects than available funding
Projects may drop out of Developmental STIP

## Slide 30: Prioritization 6.0 Funding
Due to rising costs for projects funded in the previously adopted 2020-2029 STIP, little to no funding was projected to be available for new projects in the 2024-2033 STIP timeframe.
Therefore, on August 4, 2021, the Prioritization Workgroup recommended, and the N.C. Board of Transportation approved, the P6.0 prioritization cycle be halted.
  The decision was made to develop the 2024-2033 STIP using existing projects from the previously adopted 2020-2029 STIP.
  The conclusion of the P6.0 cycle was the release of the quantitative scores and the local input point procedure was halted.
  Projects with current construction schedules in the first three years (2024-2027), projects with right-of-way actively underway, and those with federal grants were programmed first; followed by a seniority approach of combined factors as oldest Prioritization cycle and highest scoring projects.
  There were no newly submitted projects from the P6.0 prioritization cycle included in the 2024-2033 STIP.

## Slide 31: P6.0 Funding Availability – Committed Projects Only
As of August 13, 2021
Statewide Mobility
Regional Impact
Division Needs
Division | Available Funding | Programming Status
1 | $506M | $87.3M Over
2 | $506M | $180.5M Over
3 | $506M | $72.7M Under
4 | $506M | $173.5M Under
5 | $506M | $191.7M Over
6 | $506M | $41.5M Under
7 | $506M | $63.2M Under
8 | $506M | $56.0M Over
9 | $506M | $52.7M Under
10 | $506M | $57.2M Over
11 | $506M | $4.4M Under
12 | $506M | $260.7M Over
13 | $506M | $273.9M Over
14 | $506M | $93.4M Over
Region | Available Funding | Programming Status
A (D1 & D4) | $588.8M | $220.2M Over
B (D2 & D3) | $855.1M | $414.8M Over
C (D5 & D6) | $1.56B | $291.1M Over
D (D7 & D9) | $1.17B | $438.8M Over
E (D8 & D10) | $1.46B | $615.6M Over
F (D11 & D12) | $784.0M | $360.0M Over
G (D13 & D14) | $609.2M | $1.00B Over
Available Funding | Programming Status
$9.4B | $2.88B Over
Available funding based on 2024-2033 timeframe

## Slide 32: P7.0 Funding Availability – For funding of uncommitted or new projects
As of May 17, 2024.
Statewide Mobility
Regional Impact
Division Needs
Division | Available Funding
1 | -$19M
2 | -$85M
3 | -$54M
4 | $24M
5 | -$107M
6 | $126M
7 | $184M
8 | $113M
9 | -$15M
10 | -$108M
11 | $40M
12 | -$72M
13 | -$52M
14 | $51M
Region | Available Funding
A (D1 & D4) | -$228M
B (D2 & D3) | -$32M
C (D5 & D6) | $992M
D (D7 & D9) | $458M
E (D8 & D10) | -$471M
F (D11 & D12) | $8M
G (D13 & D14) | -$191M
Available Funding | 
$1.033B | 
Available funding based on snapshot taken May 17, 2024. This is the amount available to add to the STI program.

## Slide 33: Let’s say your priority project was not selected. There could be opportunities for Alternate Funding Options for Mobility / Modernization Projects
Spot Safety / Hwy Safety Improvement
Spot Mobility
Econ. Develop / Small Con / Ind. Access
High-Impact & Low-Cost

## Slide 34: Spot Safety Funding
Funded with state funds ($9 Million per year)
Approximately 150 approved projects per year
Max funding per project = $400,000
Typically can be designed and constructed within 18 months of funding approval
Session 1: I have a transportation need.
34

## Slide 35
Session 1: I have a transportation need.
State Highway Fund Programs
Contingency
$12M annually split equally among House, Senate, and Secretary
Typically limited to $250k per project per sponsor per FY
Spot Mobility / Modernization
Small Construction - $2.1M annually
  $700k reserved & remainder split equally among Divs
  $750k limit per project per FY
36

## Slide 36
Session 1: I have a transportation need.
State Highway Fund Programs
Mobility / Modernization continued
  Economic Development - $5M annually
    $2,500 per job (new or retained)
    $400k maximum
  Public Access (Industrial) - $900k annually
    $1,000 per job (new or retained)
    $250k maximum
  High Impact / Low Cost - $20M annually*
    Split equally among Divisions
    $1M per project maximum
37