Scotland County CTP

(Includes: East Laurinburg, Gibson, Laurinburg, Maxton & Wagram)

Status Report

#### October 1, 2016

# Study Contacts

# TPB Project Engineer: Michael Abuya; (919) 707-0990; mrabuya@ncdot.gov

- RPO Contact: Janet Robertson; (910) 272-5049; jfr@lrcog.org

- Division 8 Contact: Darius Sturdivant; (910) 944-2344; ddsturdivant@ncdot.gov

- Local Contact: Kevin Patterson, Manager; (910) 277-2406;  kpatterson@scotlandcounty.org

# Study Schedule

# Start of Study Letter	 Complete (December 2013)

# First CTP Meeting	 Complete (February 2014)

# Develop CTP Vision	 Complete (April 2014)

Collect/Forecast SE Data	 Complete (June 2014)

Develop Analysis Tool	 Complete (November 2014)

# Deficiency Analysis	 Complete (December 2014)

## Develop Draft CTP	 Complete (February 2016)

###### Draft CTP to Locals	 Complete (June 2016)

## Local Adoption(s)	 November 2016

###### NCDOT Adoption	 December 2016

## CTP Maps Distributed	 December 2016

###### Documentation	 January 2017

## Study Close Out	 January 2017

## Recent Activities

# Presented Draft CTP to locals

## Upcoming Activities

# Finalize Draft CTP and hold a public workshop on the plan

# Local Adoptions