## 1. General Project Risks
1. General Project Risks
1. Utilities: risks related to utility services, such as gas, water, electricity, and telecommunications.
2. Hydraulics: risks related to water management, including drainage systems, flood control, and stormwater management.
3. Geotechnical: risks related to soil and rock mechanics, including slope stability, foundation design, and earthworks.
4. Roadway Design: risks associated with the design of roadway elements, including but not limited to, guardrail installation.
5. Traffic Control Systems (Except Pavement Markings): risks related to the design, installation, and maintenance of traffic control devices, such as signals, signs, and lighting.
6. Pavement: risks related to pavement design, construction, and maintenance, including materials, drainage, and skid resistance.
7. TCP (Construction Phase): risks related to temporary traffic control measures during construction, including traffic diversions, detours, and work zone safety.
8. Environmental: risks related to environmental compliance and impact, including air quality, water quality, and noise.
9. Structural: risks related to bridge and other structural elements, including design, materials, and construction.
10. Traffic Control Systems (pavement markings): risks related specifically to pavement markings as a traffic control device.
11. Corridor/Traffic Design: risks related to the design of the transportation corridor, including land use, access, and connectivity.
12. Procurement: risks related to the procurement process, including contract management, bid evaluation, and contractor selection.
13. Safety: risks related to safety hazards, including worker safety, traffic safety, and public safety.
14. Access/ROW/Easement: risks related to access and right-of-way acquisition, including property acquisition, relocation, and compensation.
15. Contract: risks related to contract terms and conditions, including payment, dispute resolution, and termination.
16. Roadway Alignment: risks related specifically to the horizontal and vertical alignment of the roadway.
17. Finishing and Interior Work: risks associated with the completion of the interior work and finishing touches of buildings and structures within the project.
18. Ferry: risks related to ferry projects, including design, construction, and operation.
19. Other: risks that do not fit into any of the other categories.
20. Schedule: risks related to project schedule, including delays and schedule conflicts.
21. Survey: risks related to survey data accuracy, including data acquisition and processing.
22. Security/Protection: risks related to security and protection, including cybersecurity, physical security, and protection of critical infrastructure.
23. Railroad: risks related to railroad transportation, including track design, construction, and maintenance.
24. Natural Disaster: risks related to natural disasters, including floods, landslides, and earthquakes.
25. Permits: risks related to the permitting process, including environmental permits and building permits.

## 2. Causes for Claims and SAs
1.1 Claims: Generic Causes (GC) and Specific Causes (aka GC Level 2)
1. Design/Plan Issues: Problems arising from flaws in the project design or plans.
Compliance with Standard Specifications
Design/Plan Error-Unspecified
Design/Plan Revision-Unspecified
Increased Traffic Volume
2. Issues with Underground Utilities: Difficulties encountered during construction due to conflicts with existing underground utilities.
Utilities not Relocated on Time
Utility Conflict
3. Natural Disaster: Unforeseen natural disasters such as hurricanes, tornadoes, and floods that impact project progress and completion.
Natural Disaster-Drought
Natural Disaster-Flood
Natural Disaster-Hurricane
Natural Disaster-Sink Hole
Natural Disaster-Slide
Natural Disaster-Thunderstorm
Natural Disaster-Tropical Depression
4. Scheduling and Coordination Issues (Except Start of Work and/or Project Closeout): Challenges with coordinating different aspects of the project, such as subcontractor schedules or scheduling of inspections.
Conflict/Overlap with Other Projects
Coordination Issues-DOT Personnel Unavailability
Coordination Issues-Unspecified
Early Project Completion
Miscommunication (Construction Progress)
Purposeful Limited Work Schedule
Scheduling Conflicts-Inspection
Timely Completion of Project
Waiting for Other Entities to Perform Work
Work Out of Sequence
Work Restriction-Social Event
Work Restriction-Unspecified
5. Contract Amendment: Modifications made to the project contract, resulting in changes in contract line items, schedule, or budget.
Contract Error
Contract Time Adjustment
Contractor Replacement
Elimination of Contract Line Item
Error in Entering Time Extensions in HiCAMS
Line Item Omission
Revise Measurement and Payment Method
Settlement and Release Agreement
Unavailability of Funds/Cash Flow Considerations
6. Project Closeout Issues: Difficulties encountered during project closeout, such as delays in scheduling final inspections or resolving outstanding disputes.
Delay in Project Acceptance
Delay in Receipt of Final Punchlist
Final Punchlist Extra Work
Scheduling Conflicts-Final Inspection/Punchlist
7. Constructability Issues (Except Geotechnical/Underground Conflicts): Issues related to the feasibility and practicality of constructing the project, except for conflicts with geotechnical or underground conditions.
Conflict with Existing (Surface) Objects
Constructability Issues-Seasonal Limitations (Weather)
Constructability Issues-Unspecified
8. Quantities Overrun/Underrun: Variances between the planned and actual amounts of materials, labor, or other resources required for the project.
Quantities Overrun/Underrun-Unspecified
9. M&R/Replacement: Costs incurred due to maintenance and repair or replacement of existing infrastructure or equipment.
M&R/Replacement-Damaged Objects
M&R/Replacement-Unspecified
Vehicular Accident
10. Environmental/Community Concerns: Issues arising from environmental regulations, community opposition, or other social factors.
Animal Protection/Endangered Species
Environmental Concerns/Unspecified
Erosion Control Problems
Historical Site
Vegetation Establishment
Wetland Discovery
11. Design Approval Waiting Period/Indecision/Negotiation: Delays in obtaining approvals for project designs, due to indecision or negotiation issues.
Document Misplacement
Indecision-Unspecified
Negotiation Delays
Untimely Receipt of Design
Untimely Review and Return of Submittals
Untimely Review of Approvals
12. Differing Site Conditions (Except Utilities): Unforeseen subsurface or soil conditions that differ from those indicated in the project plans, except for conflicts with underground utilities.
Differing Site Conditions-Buried Objects
Differing Site Conditions-Contaminated Groundwater
Differing Site Conditions-Contaminated Soil
Differing Site Conditions-Groundwater Discovery/High Groundwater Level
Differing Site Conditions-Hazardous Materials
Differing Site Conditions-Incomplete Work by Others
Differing Site Conditions-Unspecified
Differing Site Conditions-Unsuitable Materials
13. Procurement Issues: Difficulties with the procurement of materials or equipment needed for the project.
DOT Furnished Materials/Equipment Delays
Material Acquisition Delays/Long Lead Items
Material Cost Fluctuation
Material Fabrication Delay
Power Supply Delays
Unavailability of Materials/Material Shortage
Wrong Order Placement
14. Access/ROW/Easement: Challenges related to obtaining the necessary rights-of-way or easements to access the project site.
Extra Work Associated with ROW Agreement
Insufficient Right of Entry
Insufficient ROW
Railroad Right of Entry
Right of Entry Acquisition Delays
ROW Acquisition Delays-Property Owners Agreement
ROW Acquisition Delays-Unspecified
15. Start Date Delays: Delays in starting the project due to issues such as delays to preconstruction meeting, approvals, or unforeseen circumstances.
Delay in Availability of Project
Delay in Contract Execution
Delay in Preconstruction Meeting
Delay in Project Award
Delay in Receipt of Contract Information and Bonds
Start Date Delays-Unspecified
16. Survey/Test Issues: Problems arising from inaccuracies or inconsistencies in project surveys or tests.
Additional Survey-Test Required
Survey Error
Survey Results Delays
17. Permit: Difficulties obtaining necessary permits for the project from regulatory agencies.
Insufficient Permit
Permit Acquisition Waiting Period
Permit Expiration
Permit Limitation
Permit Violation
18. Other: Any other issues not covered by the previous categories.
Covid 19 Impact
Lawsuit Costs
Misinterpretation of Plans
Unavailability of Labor
Unforeseen Issues-Unspecified
1.2 Supplemental Agreements: Generic Causes (GC) and Specific Causes (aka GC Level 2)
1. Design/Plan Issues: Problems arising from flaws in the project design or plans.
Compliance with Standard Specifications
Construction Plans Error/Discrepancy
Design Error-Elevation Difference with Existing Objects
Design Error-Unspecified
Design Revision-Achieve Higher/Acceptable Quality
Design Revision-Change in Design Criteria
Design Revision-Fix Impacts of Previous Revisions
Design Revision-Functionality Issues
Design Revision-Future Maintenance Concerns
Design Revision-per Contractor Request
Design Revision-Toll Collection
Design Revision-Uniformity with Adjacent Projects/Objects
Design Revision-Unspecified
Design Revision-Value Engineering Proposal
Incomplete Design
Increased Traffic Volume
Scope Change
2. Contract Amendment: Modifications made to the project contract, resulting in changes in contract line items, schedule, or budget.
Change in Contract Provisions
Contingency Item
Elimination of Contract Line Item
Insufficient Insurance
Issues with Previous SA
Line Item Omission
Material Substitution Allowance
Mitigation of Potential Risk
Permission to Hold Additional Retainage
Revise Measurement and Payment Method
Risk Management
Settlement and Release Agreement
Unavailability of Funds/Cash Flow Considerations
3. Stakeholder Request: Requests made by external stakeholders, such as local government entities or nearby residents, that require changes to the project.
DOT Request-Unspecified
Stakeholder Request-Future Development Concerns
Stakeholder Request-Unspecified
4. Differing Site Conditions (Except Utilities): Unforeseen site conditions that differ from what was expected, but do not involve underground utilities.
Differing Site Conditions-Buried Objects
Differing Site Conditions-Changes in Site After Bid/During Construction
Differing Site Conditions-Contaminated Soil
Differing Site Conditions-Encountered Rock
Differing Site Conditions-Extra Work from Previous Projects
Differing Site Conditions-Groundwater Discovery/High Groundwater Level
Differing Site Conditions-Incomplete Work by Others
Differing Site Conditions-Not Shown in Construction Plans
Differing Site Conditions-Unspecified
Differing Site Conditions-Unsuitable Materials
Slope Protection/Soil Stabilization
5. M&R/Replacement: Maintenance and repair or replacement of existing infrastructure or equipment.
Damaged Objects
M&R/Replacement-Unspecified
Vehicular Accident
6. Issues with Underground Utilities: Issues related to underground utilities, such as conflicts or damages.
Inability to Locate Utilities
Utilities not Relocated on Time
Utility Conflict
7. Safety Concerns (Except Contaminated Soil): Safety issues that arise during the project, such as accidents or hazards, excluding those related to contaminated soil.
Falling Hazard
Hazardous Materials Removal
Safety Concerns-Unspecified
Sight Distance Concerns
Travelers/Public Safety
Tripping Hazard
8. Constructability Issues (Except Geotechnical/Underground Conflicts): Issues related to the constructability of the project, such as difficulties in executing the design or plans, excluding those related to geotechnical or underground conflicts.
Conflict with Existing (Surface) Objects
Constructability Issues-Unspecified
Height Clearance Issues
9. Construction Method Revision: Changes made to the construction methods or techniques used in the project.
Construction Method Revision-Unspecified
10. Access/ROW/Easement: Issues related to access to the project site or right-of-way or easement concerns.
Easement Acquisition Delays
Extra Work Associated with ROW Agreement
Insufficient ROW
Insufficient Utility Easement
Property Owners Access
Providing Access to Site
Railroad Right of Entry Delays
ROW Acquisition Delays
ROW Revision
Traffic Access Point
11. Erosion Control Problems: Issues related to erosion control measures or practices.
Erosion Control Problems-Unspecified
Waste Site Erosion Control
12. Quantities Overrun/Underrun: Variances in the quantities of materials or labor required for the project, resulting in overruns or underruns.
Quantities Overrun/Underrun-Unspecified
Waste Excessive Material
13. Drainage Issues: Issues related to drainage systems or measures.
Drainage Issues-Unspecified
Stormwater Concerns
14. Scheduling and Coordination Issues: Issues related to project scheduling or coordination with other stakeholders or activities.
Additional ICT Required
Availability Date Delays
Conflict with Other Projects
Conflict/Overlap with Adjacent Projects
Early Project Completion
Miscommunication (Construction Progress)
Overtime Hour Request
Project Phasing Problems
Statewide Initiative to Accelerate Projects
Timely Completion of Project
15. Environmental/Community Concerns: Issues related to environmental or community impacts of the project.
Animal Protection/Endangered Species
Avoid Historical Structure
Construction Impacts
Environmental Concerns-Unspecified
Natural Disaster (Drought)
Noise Control
Vegetation Establishment
Wetland Delineation
16. Procurement Issues: Issues related to the procurement of materials or services for the project.
Error in Bill of Materials
Material Acquisition Delays/Long Lead Items
Material Fabrication Delay
Shop Drawing Error
Unavailability of Materials/Material Shortage
Wrong Order Placement
17. Survey/Test Issues: Issues related to surveys or testing conducted during the project.
Additional Survey/Test Required
Survey Error-Staking
Survey Error-Unspecified
18. Other: Any other issues not covered by the above categories.
Contractor Error
Covid 19 Impact
Equipment/Items Protection
Permit Acquisition Issues
Permit Requirements
Permit Restrictions
Site Security

## 3a. Summary-All Claims
Table 1 Claims - All Project Types | [9 empty] | Table 2 Claims - All Project Types |  |  | Table 4 Claims - Per Project Type
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total | Generic Cause\Project Type | Appalachian Regional Commission | Bicycle and Pedestrian | Bridge Replacement | Ferry | Highway Safety | Interstate | Other | Rail | Railroad - Highway Crossings | Rest Area | Rural | Safe Routes to School | Urban | All Project Types
Design/Plan Issues | Compliance with Standard Specifications | 12 | 4.651% | 258 | 16.17% | 64426.239 | 10414.768 | 53.6337 | 8.6701 | Design/Plan Issues | 258 | 16.17% | Access/ROW/Easement | 0% | 2.857% | 1.176% | 0% | 2.703% | 2.186% | 0% | 10% | 0% | 0% | 2.035% | 0% | 2.459% | 2.13%
| Design/Plan Error-Unspecified | 71 | 27.52% | [6 empty] | Issues with Underground Utilities | 235 | 14.72% | Constructability Issues (Except Geotechnical/Underground Conflicts) | 9.524% | 2.857% | 7.529% | 0% | 5.405% | 7.104% | 3.774% | 7.143% | 0% | 2.703% | 6.395% | 6.667% | 2.869% | 5.89%
| Design/Plan Revision-Unspecified | 172 | 66.67% | [6 empty] | Natural Disaster | 141 | 8.835% | Contract Amendment | 14.29% | 5.714% | 5.882% | 14.29% | 3.378% | 7.104% | 7.547% | 8.571% | 0% | 13.51% | 11.34% | 26.67% | 7.787% | 7.957%
| Increased Traffic Volume | 3 | 1.163% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or Project Closeout) | 141 | 8.835% | Design Approval Waiting Period/Indecision/Negotiation | 4.762% | 11.43% | 4.471% | 7.143% | 2.027% | 3.825% | 7.547% | 1.429% | 0% | 0% | 2.035% | 0% | 3.279% | 3.446%
Issues with Underground Utilities | Utilities not Relocated on Time | 72 | 30.64% | 235 | 14.72% | 165812.2602 | 24414.7125 | 95.555 | 14.0698 | Contract Amendment | 127 | 7.957% | Design/Plan Issues | 38.1% | 20% | 13.88% | 7.143% | 14.19% | 12.57% | 11.32% | 8.571% | 0% | 21.62% | 18.31% | 0% | 22.95% | 16.17%
| Utility Conflict | 163 | 69.36% | [6 empty] | Project Closeout Issues | 109 | 6.83% | Differing Site Conditions (Except Utilities) | 0% | 2.857% | 5.412% | 7.143% | 2.027% | 2.186% | 3.774% | 0% | 0% | 0% | 2.326% | 0% | 2.869% | 3.07%
Natural Disaster | Natural Disaster-Drought | 2 | 1.418% | 141 | 8.835% | 37302.78 | 3295.5464 | 27.2336 | 2.406 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 94 | 5.89% | Environmental/Community Concerns | 4.762% | 0% | 7.294% | 0% | 4.73% | 1.639% | 5.66% | 0% | 0% | 5.405% | 3.779% | 6.667% | 2.869% | 4.261%
| Natural Disaster-Flood | 1 | 0.7092% | [6 empty] | Quantities Overrun/Underrun | 76 | 4.762% | Issues with Underground Utilities | 4.762% | 22.86% | 13.88% | 7.143% | 17.57% | 3.279% | 13.21% | 37.14% | 42.86% | 2.703% | 13.37% | 33.33% | 18.85% | 14.72%
| Natural Disaster-Hurricane | 133 | 94.33% | [6 empty] | M&R/Replacement | 75 | 4.699% | M&R/Replacement | 0% | 5.714% | 2.824% | 7.143% | 4.054% | 10.38% | 3.774% | 2.857% | 0% | 2.703% | 6.395% | 0% | 3.279% | 4.699%
| Natural Disaster-Sinkhole | 1 | 0.7092% | [6 empty] | Environmental/Community Concerns | 68 | 4.261% | Natural Disaster | 9.524% | 2.857% | 9.412% | 28.57% | 12.16% | 11.48% | 5.66% | 0% | 0% | 10.81% | 8.721% | 6.667% | 6.967% | 8.835%
| Natural Disaster-Slide | 2 | 1.418% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 55 | 3.446% | Other | 0% | 0% | 0.4706% | 0% | 0% | 0% | 1.887% | 4.286% | 0% | 0% | 1.453% | 0% | 0.4098% | 0.7519%
| Natural Disaster-Thunderstorm | 1 | 0.7092% | [6 empty] | Differing Site Conditions (Except Utilities) | 49 | 3.07% | Permit | 0% | 0% | 2.353% | 0% | 0% | 0.5464% | 0% | 0% | 0% | 2.703% | 1.163% | 0% | 0.4098% | 1.065%
| Natural Disaster-Tropical Depression | 1 | 0.7092% | [6 empty] | Procurement Issues | 48 | 3.008% | Procurement Issues | 0% | 2.857% | 2.588% | 7.143% | 2.027% | 3.825% | 5.66% | 1.429% | 0% | 10.81% | 3.488% | 0% | 2.049% | 3.008%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 11 | 7.801% | 141 | 8.835% | 137963.9153 | 12188.5414 | 37.3876 | 3.5568 | Access/ROW/Easement | 34 | 2.13% | Project Closeout Issues | 4.762% | 5.714% | 7.765% | 0% | 14.19% | 8.197% | 13.21% | 1.429% | 14.29% | 8.108% | 2.616% | 13.33% | 5.738% | 6.83%
| Coordination Issues-DOT Personnel Unavailability | 12 | 8.511% | [6 empty] | Start Date Delays | 33 | 2.068% | Quantities Overrun/Underrun | 4.762% | 0% | 2.118% | 0% | 7.432% | 9.836% | 0% | 11.43% | 0% | 0% | 3.488% | 6.667% | 6.557% | 4.762%
| Coordination Issues-Unspecified | 3 | 2.128% | [6 empty] | Survey/Test Issues | 24 | 1.504% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 4.762% | 8.571% | 8.471% | 14.29% | 6.081% | 13.66% | 5.66% | 5.714% | 42.86% | 8.108% | 8.43% | 0% | 9.426% | 8.835%
| Early Project Completion | 1 | 0.7092% | [6 empty] | Permit | 17 | 1.065% | Start Date Delays | 0% | 5.714% | 1.647% | 0% | 1.351% | 1.093% | 11.32% | 0% | 0% | 10.81% | 2.907% | 0% | 0% | 2.068%
| Miscommunication (Construction Progress) | 3 | 2.128% | [6 empty] | Other | 12 | 0.7519% | Survey/Test Issues | 0% | 0% | 2.824% | 0% | 0.6757% | 1.093% | 0% | 0% | 0% | 0% | 1.744% | 0% | 1.23% | 1.504%
| Purposeful Limited Work Schedule | 42 | 29.79% | [9 empty] | Grand Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Scheduling Conflicts-Inspection | 10 | 7.092%
| Timely Completion of Project | 1 | 0.7092% | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Waiting for Other Entities to Perform Work | 13 | 9.22% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 20.93%
| Work Out of Sequence | 9 | 6.383% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 18.22%
| Work Restriction-Social Event | 20 | 14.18% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 14.73%
| Work Restriction-Unspecified | 16 | 11.35% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 10.47%
Contract Amendment | Contract Error | 6 | 4.724% | 127 | 7.957% | 695798.9243 | 55367.4583 | 69.2041 | 5.0015 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 7.364%
| Contract Time Adjustment | 4 | 3.15% | [6 empty] | Utility – design, as-builts, etc. | 5.039%
| Contractor Replacement | 2 | 1.575% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 3.876%
| Elimination of Contract Line Item | 9 | 7.087% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 3.101%
| Error in Entering Time Extensions in HiCAMS | 49 | 38.58% | [6 empty] | Unspecified | 16.28%
| Line Item Omission | 23 | 18.11%
| Revise Measurement and Payment Method | 2 | 1.575%
| Settlement and Release Agreement | 27 | 21.26%
| Unavailability of Funds/Cash Flow Considerations | 5 | 3.937%
Project Closeout Issues | Delay in Project Acceptance | 1 | 0.9174% | 109 | 6.83% | 2000 | 136.5915 | 19.1651 | 1.5406
| Delay in Receipt of Final Punchlist | 1 | 0.9174%
| Final Punchlist Extra Work | 12 | 11.01%
| Scheduling Conflicts-Final Inspection/Punchlist | 95 | 87.16%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 4 | 4.255% | 94 | 5.89% | 34563.1064 | 2035.6717 | 79.875 | 5.1836
| Constructability Issues-Seasonal Limitations (Weather) | 87 | 92.55%
| Constructability Issues-Unspecified | 3 | 3.191%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 76 | 100% | 76 | 4.762% | 98518.4124 | 4691.353 | 32.0811 | 0.87537
M&R/Replacement | M&R/Replacement-Damaged Objects | 4 | 5.333% | 75 | 4.699% | 41356.24 | 1943.4323 | 68.9 | 2.5406
| M&R/Replacement-Unspecified | 68 | 90.67%
| Vehicular Accident | 3 | 4%
Environmental/Community Concerns | Animal Protection/Endangered Species | 2 | 2.941% | 68 | 4.261% | 8527.2144 | 363.3149 | 117.25 | 5.1881
| Environmental Concerns/Unspecified | 6 | 8.824%
| Erosion Control Problems | 4 | 5.882%
| Historical Site | 1 | 1.471%
| Vegetation Establishment | 53 | 77.94%
| Wetland Discovery | 2 | 2.941%
Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement | 1 | 1.818% | 55 | 3.446% | 16409.955 | 565.506 | 51.8704 | 2.0656
| Indecision-Unspecified | 31 | 56.36%
| Negotiation Delays | 2 | 3.636%
| Untimely Receipt of Design | 3 | 5.455%
| Untimely Review and Return of Submittals | 14 | 25.45%
| Untimely Review of Approvals | 4 | 7.273%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 10 | 20.41% | 49 | 3.07% | 18494.2114 | 567.8047 | 32 | 0.84956
| Differing Site Conditions-Contaminated Groundwater | 1 | 2.041%
| Differing Site Conditions-Contaminated Soil | 2 | 4.082%
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 8 | 16.33%
| Differing Site Conditions-Hazardous Materials | 4 | 8.163%
| Differing Site Conditions-Incomplete Work by Others | 7 | 14.29%
| Differing Site Conditions-Unspecified | 3 | 6.122%
| Differing Site Conditions-Unsuitable Materials | 14 | 28.57%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 6 | 12.5% | 48 | 3.008% | 20273.3533 | 609.7249 | 77.4884 | 2.4572
| Material Acquisition Delays/Long Lead Items | 11 | 22.92%
| Material Cost Fluctuation | 2 | 4.167%
| Material Fabrication Delay | 1 | 2.083%
| Power Supply Delays | 17 | 35.42%
| Unavailability of Materials/Material Shortage | 8 | 16.67%
| Wrong Order Placement | 3 | 6.25%
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 2 | 5.882% | 34 | 2.13% | 754429.9125 | 16071.8152 | 78.6129 | 1.7972
| Insufficient Right of Entry | 1 | 2.941%
| Insufficient ROW | 3 | 8.824%
| Railroad Right of Entry | 9 | 26.47%
| Right of Entry Acquisition Delays | 1 | 2.941%
| ROW Acquisition Delays-Property Owners Agreement | 2 | 5.882%
| ROW Acquisition Delays-Unspecified | 16 | 47.06%
Start Date Delays | Delay in Availability of Project | 1 | 3.03% | 33 | 2.068% | - | 0 | 29.4545 | 0.71681
| Delay in Contract Execution | 16 | 48.48%
| Delay in Preconstruction Meeting | 9 | 27.27%
| Delay in Project Award | 4 | 12.12%
| Delay in Receipt of Contract Information and Bonds | 1 | 3.03%
| Start Date Delays-Unspecified | 2 | 6.061%
Survey/Test Issues | Additional Survey-Test Required | 4 | 16.67% | 24 | 1.504% | 51268.072 | 770.9485 | 16.2941 | 0.20428
| Survey Error | 18 | 75%
| Survey Results Delays | 2 | 8.333%
Permit | Insufficient Permit | 2 | 11.76% | 17 | 1.065% | 44341.6633 | 472.311 | 47.625 | 0.56195
| Permit Acquisition Waiting Period | 11 | 64.71%
| Permit Expiration | 1 | 5.882%
| Permit Limitation | 2 | 11.76%
| Permit Violation | 1 | 5.882%
Other | Covid 19 Impact | 3 | 25% | 12 | 0.7519% | 45898.3683 | 345.1005 | 120.1429 | 0.62021
| Lawsuit Costs | 1 | 8.333%
| Misinterpretation of Plans | 2 | 16.67%
| Unavailability of Labor | 2 | 16.67%
| Unforeseen Issues-Unspecified | 4 | 33.33%

## 3b. Summary-All SAs
Table 1 Supplementary Agreements (All Project Types) | [7 empty] | Table 2 Supplementary Agreements (All Project Types) |  |  |  |  | Table 5 Supplementary Agreements (per Project Type)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Project Type | Appalachian Regional Commission | Bicycle and Pedestrian | Bridge Replacement | Ferry | Highway Safety | Interstate | Other | Rail | Railroad - Highway Crossings | Rest Area | Rural | Safe Routes to School | Urban | All Project Types
Access/ROW/Easement | Easement Acquisition Delays | 1 | 1.852% | 54 | 2.48% | 26726.0715 | 662.9342 | Design/Plan Issues | 583 | 26.78% |  |  | Access/ROW/Easement | 3.636% | 2.778% | 1.955% | 0% | 3.39% | 1.181% | 2.703% | 4.839% | 4.545% | 1.389% | 2.564% | 0% | 3.132% | 2.48%
| Extra Work Associated with ROW Agreement | 11 | 20.37% |  |  |  |  | Contract Amendment | 324 | 14.88% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 5.455% | 0% | 5.307% | 0% | 2.542% | 7.874% | 0% | 9.677% | 18.18% | 4.167% | 4.968% | 0% | 4.802% | 5.145%
| Insufficient ROW | 10 | 18.52% |  |  |  |  | Stakeholder Request | 178 | 8.176% |  |  | Construction Method Revision | 3.636% | 5.556% | 2.514% | 0% | 0.8475% | 3.543% | 0% | 0% | 0% | 2.778% | 4.487% | 0% | 4.593% | 3.445%
| Insufficient Utility Easement | 2 | 3.704% |  |  |  |  | Differing Site Conditions (Except Utilities) | 173 | 7.947% |  |  | Contract Amendment | 18.18% | 13.89% | 15.64% | 8% | 14.41% | 11.81% | 18.92% | 11.29% | 18.18% | 9.722% | 16.19% | 20% | 15.45% | 14.88%
| Property Owners Access | 10 | 18.52% |  |  |  |  | M&R/Replacement | 156 | 7.166% |  |  | Design/Plan Issues | 23.64% | 5.556% | 26.82% | 72% | 27.97% | 27.17% | 21.62% | 20.97% | 36.36% | 36.11% | 27.88% | 10% | 21.71% | 26.78%
| Providing Access to Site | 6 | 11.11% |  |  |  |  | Issues with Underground Utilities | 127 | 5.834% |  |  | Differing Site Conditions (Except Utilities) | 9.091% | 8.333% | 8.659% | 0% | 10.17% | 5.512% | 18.92% | 11.29% | 9.091% | 6.944% | 6.891% | 20% | 8.768% | 7.947%
| Railroad Right of Entry Delays | 2 | 3.704% |  |  |  |  | Safety Concerns (Except Contaminated Soil) | 118 | 5.42% |  |  | Drainage Issues | 5.455% | 8.333% | 1.676% | 0% | 0.8475% | 2.756% | 2.703% | 0% | 0% | 2.778% | 1.282% | 0% | 2.088% | 1.883%
| ROW Acquisition Delays | 1 | 1.852% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 112 | 5.145% |  |  | Environmental/Community Concerns | 3.636% | 0% | 1.397% | 0% | 0.8475% | 0.7874% | 2.703% | 0% | 0% | 0% | 2.885% | 0% | 0.6263% | 1.47%
| ROW Revision | 1 | 1.852% |  |  |  |  | Construction Method Revision | 75 | 3.445% |  |  | Erosion Control Problems | 0% | 8.333% | 5.587% | 0% | 3.39% | 1.969% | 5.405% | 4.839% | 4.545% | 0% | 1.282% | 0% | 1.67% | 2.48%
| Traffic Access Point | 10 | 18.52% |  |  |  |  | Access/ROW/Easement | 54 | 2.48% |  |  | Issues with Underground Utilities | 3.636% | 11.11% | 4.749% | 2% | 9.322% | 0.7874% | 5.405% | 4.839% | 0% | 1.389% | 4.968% | 10% | 10.86% | 5.834%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 24 | 21.43% | 112 | 5.145% | 34581.1136 | 1779.0927 | Erosion Control Problems | 54 | 2.48% |  |  | M&R/Replacement | 3.636% | 11.11% | 5.028% | 2% | 11.86% | 12.6% | 2.703% | 3.226% | 0% | 13.89% | 6.731% | 10% | 6.054% | 7.166%
| Constructability Issues-Unspecified | 87 | 77.68% |  |  |  |  | Quantities Overrun/Underrun | 50 | 2.297% |  |  | Other | 1.818% | 0% | 1.397% | 6% | 0% | 0% | 0% | 4.839% | 0% | 0% | 0.3205% | 0% | 0.4175% | 0.735%
| Height Clearance Issues | 1 | 0.8929% |  |  |  |  | Drainage Issues | 41 | 1.883% |  |  | Procurement Issues | 3.636% | 0% | 1.676% | 4% | 0.8475% | 0.3937% | 8.108% | 4.839% | 0% | 1.389% | 0.9615% | 0% | 1.044% | 1.378%
Construction Method Revision | Construction Method Revision-Unspecified | 75 | 100% | 75 | 3.445% | 183383.7161 | 6317.767 | Scheduling and Coordination Issues | 34 | 1.562% |  |  | Quantities Overrun/Underrun | 7.273% | 0% | 3.073% | 0% | 2.542% | 2.756% | 8.108% | 1.613% | 0% | 1.389% | 2.404% | 0% | 1.044% | 2.297%
Contract Amendment | Change in Contract Provisions | 6 | 1.852% | 324 | 14.88% | 52388.5095 | 7796.9118 | Environmental/Community Concerns | 32 | 1.47% |  |  | Safety Concerns (Except Contaminated Soil) | 3.636% | 5.556% | 4.469% | 0% | 5.085% | 9.843% | 0% | 3.226% | 9.091% | 4.167% | 5.609% | 10% | 5.01% | 5.42%
| Contingency Item | 1 | 0.3086% |  |  |  |  | Procurement Issues | 30 | 1.378% |  |  | Scheduling and Coordination Issues | 0% | 2.778% | 0.838% | 0% | 0.8475% | 0.3937% | 0% | 3.226% | 0% | 0% | 2.404% | 0% | 2.296% | 1.562%
| Elimination of Contract Line Item | 7 | 2.16% |  |  |  |  | Survey/Test Issues | 20 | 0.9187% |  |  | Stakeholder Request | 1.818% | 16.67% | 6.704% | 6% | 5.085% | 10.24% | 2.703% | 8.065% | 0% | 12.5% | 7.692% | 20% | 9.812% | 8.176%
| Insufficient Insurance | 1 | 0.3086% |  |  |  |  | Other | 16 | 0.735% |  |  | Survey/Test Issues | 1.818% | 0% | 2.514% | 0% | 0% | 0.3937% | 0% | 3.226% | 0% | 1.389% | 0.4808% | 0% | 0.6263% | 0.9187%
| Issues with Previous SA | 6 | 1.852% | [9 empty] | All Generic Cause | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Line Item Omission | 269 | 83.02% |  |  |  |  | Table 3 Supplementary Agreements (All Project Types)
| Material Substitution Allowance | 2 | 0.6173% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA | Table 6 Supplementary Agreements (per Project Type)
| Mitigation of Potential Risk | 2 | 0.6173% |  |  |  |  | Utilities | 370 | 17% | 54376.6917 | 9241.7896 | Risk Area\Project Type | Appalachian Regional Commission | Bicycle and Pedestrian | Bridge Replacement | Ferry | Highway Safety | Interstate | Other | Rail | Railroad - Highway Crossings | Rest Area | Rural | Safe Routes to School | Urban | All Project Types
| Permission to Hold Additional Retainage | 1 | 0.3086% |  |  |  |  | Hydraulics | 241 | 11.07% | 18963.4887 | 2099.3113 | Access/ROW/Easement | 0% | 2.778% | 1.397% | 0% | 0% | 1.181% | 0% | 8.065% | 4.545% | 0% | 2.083% | 0% | 2.923% | 1.929%
| Revise Measurement and Payment Method | 18 | 5.556% |  |  |  |  | Geotechnical | 191 | 8.774% | 33647.6758 | 2952.0928 | Contract | 5.455% | 0% | 0.838% | 6% | 0.8475% | 1.575% | 0% | 0% | 0% | 1.389% | 1.923% | 0% | 2.088% | 1.7%
| Risk Management | 1 | 0.3086% |  |  |  |  | Roadway Design | 178 | 8.176% | 90723.7447 | 7417.9268 | Corridor/Traffic Design | 0% | 0% | 2.514% | 0% | 2.542% | 6.693% | 0% | 1.613% | 0% | 0% | 3.365% | 0% | 3.967% | 3.215%
| Settlement and Release Agreement | 5 | 1.543% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 160 | 7.35% | 42209.0448 | 3102.1806 | Environmental | 10.91% | 16.67% | 8.659% | 4% | 5.932% | 3.937% | 27.03% | 8.065% | 4.545% | 4.167% | 5.929% | 0% | 4.175% | 6.339%
| Unavailability of Funds/Cash Flow Considerations | 5 | 1.543% |  |  |  |  | Pavement | 153 | 7.028% | 165892.6706 | 11658.9704 | Ferry | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.378%
Design/Plan Issues | Compliance with Standard Specifications | 65 | 11.15% | 583 | 26.78% | 75025.9807 | 20091.9369 | TCP (Construction Phase) | 144 | 6.615% | 68616.1442 | 4538.6885 | Finishing and Interior Work | 9.091% | 0% | 0.2793% | 2% | 0% | 0% | 0% | 3.226% | 0% | 26.39% | 0.1603% | 0% | 0.6263% | 1.47%
| Construction Plans Error/Discrepancy | 40 | 6.861% |  |  |  |  | Environmental | 138 | 6.339% | 97808.8418 | 6200.1011 | Geotechnical | 9.091% | 2.778% | 12.85% | 2% | 8.475% | 7.874% | 10.81% | 6.452% | 9.091% | 5.556% | 8.974% | 20% | 7.516% | 8.774%
| Design Error-Elevation Difference with Existing Objects | 19 | 3.259% |  |  |  |  | Structural | 100 | 4.593% | 34431.2402 | 1581.5912 | Hydraulics | 7.273% | 11.11% | 9.218% | 2% | 7.627% | 10.24% | 5.405% | 14.52% | 9.091% | 9.722% | 12.66% | 20% | 13.15% | 11.07%
| Design Error-Unspecified | 49 | 8.405% |  |  |  |  | Traffic Control Systems (pavement Markings) | 78 | 3.583% | 11805.7687 | 422.9903 | Natural Disaster | 0% | 0% | 0.5587% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4808% | 0% | 0% | 0.2756%
| Design Revision-Achieve Higher/Acceptable Quality | 16 | 2.744% |  |  |  |  | Corridor/Traffic Design | 70 | 3.215% | 398137.6847 | 12801.8548 | Other | 0% | 0% | 1.117% | 0% | 0.8475% | 0.7874% | 2.703% | 0% | 0% | 2.778% | 1.442% | 0% | 1.253% | 1.148%
| Design Revision-Change in Design Criteria | 1 | 0.1715% |  |  |  |  | Procurement | 47 | 2.159% | 1994.2218 | 43.0539 | Pavement | 12.73% | 2.778% | 3.911% | 2% | 11.86% | 14.17% | 8.108% | 1.613% | 27.27% | 0% | 7.212% | 0% | 5.219% | 7.028%
| Design Revision-Fix Impacts of Previous Revisions | 10 | 1.715% |  |  |  |  | Safety | 46 | 2.113% | 54848.1009 | 1158.9401 | Permit | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4808% | 0% | 0% | 0.1378%
| Design Revision-Functionality Issues | 8 | 1.372% |  |  |  |  | Access/ROW/Easement | 42 | 1.929% | 49838.6857 | 961.5181 | Procurement | 5.455% | 0% | 1.955% | 14% | 1.695% | 1.181% | 8.108% | 8.065% | 4.545% | 4.167% | 1.282% | 0% | 1.044% | 2.159%
| Design Revision-Future Maintenance Concerns | 16 | 2.744% |  |  |  |  | Contract | 37 | 1.7% | 274118.7948 | 4658.8863 | Railroad | 0% | 2.778% | 0% | 0% | 0% | 0.3937% | 0% | 4.839% | 0% | 0% | 0% | 0% | 0.4175% | 0.3215%
| Design Revision-per Contractor Request | 36 | 6.175% |  |  |  |  | Roadway Alignment | 35 | 1.608% | 30837.0637 | 495.7727 | Roadway Alignment | 1.818% | 0% | 3.073% | 0% | 1.695% | 1.181% | 0% | 0% | 0% | 0% | 1.763% | 0% | 1.461% | 1.608%
| Design Revision-Toll Collection | 1 | 0.1715% |  |  |  |  | Finishing and Interior Work | 32 | 1.47% | 11004.2768 | 161.7533 | Roadway Design | 7.273% | 2.778% | 11.45% | 0% | 12.71% | 8.661% | 10.81% | 1.613% | 9.091% | 0% | 8.013% | 30% | 7.307% | 8.176%
| Design Revision-Uniformity with Adjacent Projects/Objects | 8 | 1.372% |  |  |  |  | Ferry | 30 | 1.378% | 15212.5073 | 209.6349 | Safety | 5.455% | 5.556% | 1.117% | 0% | 1.695% | 2.756% | 0% | 3.226% | 0% | 2.778% | 2.083% | 0% | 2.296% | 2.113%
| Design Revision-Unspecified | 275 | 47.17% |  |  |  |  | Other | 25 | 1.148% | 52732.7848 | 605.5671 | Schedule | 0% | 2.778% | 1.397% | 0% | 0.8475% | 1.181% | 0% | 0% | 0% | 0% | 1.603% | 0% | 1.044% | 1.148%
| Design Revision-Value Engineering Proposal | 10 | 1.715% |  |  |  |  | Schedule | 25 | 1.148% | 551688.6231 | 6335.4229 | Security/Protection | 0% | 0% | 0.838% | 0% | 0% | 0% | 0% | 1.613% | 0% | 1.389% | 0.4808% | 0% | 0.2088% | 0.4134%
| Incomplete Design | 3 | 0.5146% |  |  |  |  | Survey | 10 | 0.4593% | 9684.203 | 44.4842 | Structural | 5.455% | 0% | 9.497% | 2% | 0% | 7.48% | 2.703% | 4.839% | 0% | 8.333% | 3.526% | 0% | 2.296% | 4.593%
| Increased Traffic Volume | 9 | 1.544% |  |  |  |  | Security/Protection | 9 | 0.4134% | 12633.94 | 52.2303 | Survey | 0% | 2.778% | 0.838% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4808% | 0% | 0.6263% | 0.4593%
| Scope Change | 17 | 2.916% |  |  |  |  | Railroad | 7 | 0.3215% | 10945.89 | 35.1958 | TCP (Construction Phase) | 7.273% | 5.556% | 5.866% | 0% | 12.71% | 7.087% | 13.51% | 6.452% | 4.545% | 1.389% | 5.769% | 10% | 7.516% | 6.615%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 2 | 1.156% | 173 | 7.947% | 32991.1179 | 2621.7103 | Natural Disaster | 6 | 0.2756% | 13302.66 | 36.6633 | Traffic Control Systems (Except Pavement Markings) | 3.636% | 11.11% | 2.793% | 2% | 4.237% | 11.42% | 0% | 8.065% | 4.545% | 15.28% | 8.013% | 10% | 8.559% | 7.35%
| Differing Site Conditions-Changes in Site After Bid/During Construction | 4 | 2.312% |  |  |  |  | Permit | 3 | 0.1378% | 24911.76 | 34.3295 | Traffic Control Systems (pavement Markings) | 0% | 5.556% | 4.749% | 0% | 3.39% | 5.118% | 5.405% | 1.613% | 18.18% | 0% | 3.365% | 0% | 2.923% | 3.583%
| Differing Site Conditions-Contaminated Soil | 3 | 1.734% | [9 empty] | Utilities | 9.091% | 25% | 15.08% | 2% | 22.88% | 7.087% | 5.405% | 16.13% | 4.545% | 16.67% | 18.91% | 10% | 23.38% | 17%
| Differing Site Conditions-Encountered Rock | 3 | 1.734% | [9 empty] | All Risk Area | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Differing Site Conditions-Extra Work from Previous Projects | 4 | 2.312%
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 12 | 6.936%
| Differing Site Conditions-Incomplete Work by Others | 2 | 1.156% | [9 empty] | Table 4 Supplementary Agreements (per Project Type)
| Differing Site Conditions-Not Shown in Construction Plans | 25 | 14.45% | [9 empty] | Generic Cause\Risk Area | Access/ROW/Easement | Contract | Corridor/Traffic Design | Environmental | Ferry | Finishing and Interior Work | Geotechnical | Hydraulics | Natural Disaster | Other | Pavement | Permit | Procurement | Railroad | Roadway Alignment | Roadway Design | Safety | Schedule | Security/Protection | Structural | Survey | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | All Risk Area
| Differing Site Conditions-Unspecified | 71 | 41.04% | [9 empty] | Access/ROW/Easement | 42.59% | 0% | 5.556% | 3.704% | 0% | 1.852% | 1.852% | 3.704% | 0% | 0% | 0% | 0% | 0% | 1.852% | 0% | 7.407% | 0% | 0% | 1.852% | 1.852% | 0% | 16.67% | 1.852% | 1.852% | 7.407% | 100%
| Differing Site Conditions-Unsuitable Materials | 20 | 11.56% | [9 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 2.679% | 1.786% | 0% | 0.8929% | 11.61% | 9.821% | 0% | 0.8929% | 7.143% | 0% | 1.786% | 0% | 0.8929% | 7.143% | 0% | 0% | 0% | 2.679% | 0% | 6.25% | 16.07% | 1.786% | 28.57% | 100%
| Slope Protection/Soil Stabilization | 27 | 15.61% | [9 empty] | Construction Method Revision | 0% | 0% | 1.333% | 4% | 0% | 1.333% | 8% | 8% | 0% | 2.667% | 9.333% | 0% | 4% | 0% | 0% | 6.667% | 2.667% | 2.667% | 0% | 5.333% | 0% | 25.33% | 5.333% | 1.333% | 12% | 100%
Drainage Issues | Drainage Issues-Unspecified | 36 | 87.8% | 41 | 1.883% | 13523.6941 | 254.6952 | [5 empty] | Contract Amendment | 2.16% | 7.099% | 1.543% | 2.778% | 0% | 0.6173% | 8.642% | 11.42% | 0% | 2.16% | 4.63% | 0% | 0.6173% | 0% | 0.6173% | 8.025% | 0.3086% | 0.6173% | 0.3086% | 3.395% | 1.235% | 9.568% | 8.025% | 9.568% | 16.67% | 100%
| Stormwater Concerns | 5 | 12.2% | [9 empty] | Design/Plan Issues | 0.6861% | 1.372% | 5.317% | 2.058% | 4.803% | 2.573% | 6.346% | 10.63% | 0.1715% | 0.3431% | 9.605% | 0.3431% | 1.887% | 0.6861% | 3.774% | 13.72% | 1.029% | 0.5146% | 0.1715% | 6.861% | 0% | 3.602% | 10.81% | 5.146% | 7.547% | 100%
Environmental/Community Concerns | Animal Protection/Endangered Species | 3 | 9.375% | 32 | 1.47% | 514825.6191 | 7567.4873 | [5 empty] | Differing Site Conditions (Except Utilities) | 0% | 0% | 0% | 4.624% | 0% | 0.578% | 35.84% | 16.18% | 0% | 1.734% | 6.936% | 0% | 0% | 0% | 4.046% | 5.202% | 0.578% | 0% | 0.578% | 1.734% | 0% | 0% | 4.046% | 0.578% | 17.34% | 100%
| Avoid Historical Structure | 1 | 3.125% | [9 empty] | Drainage Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Construction Impacts | 2 | 6.25% | [9 empty] | Environmental/Community Concerns | 6.25% | 0% | 6.25% | 71.88% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.375% | 0% | 0% | 3.125% | 0% | 0% | 0% | 0% | 0% | 3.125% | 100%
| Environmental Concerns-Unspecified | 8 | 25% | [9 empty] | Erosion Control Problems | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Natural Disaster (Drought) | 1 | 3.125% | [9 empty] | Issues with Underground Utilities | 0% | 0% | 0.7874% | 0% | 0% | 0% | 1.575% | 2.362% | 0% | 0.7874% | 0% | 0% | 0% | 0% | 0% | 0.7874% | 0% | 1.575% | 0% | 0% | 0% | 0.7874% | 0% | 0% | 91.34% | 100%
| Noise Control | 2 | 6.25% | [9 empty] | M&R/Replacement | 0% | 0.641% | 0% | 2.564% | 0% | 1.282% | 10.26% | 19.23% | 1.923% | 0% | 20.51% | 0% | 0% | 0.641% | 0% | 5.769% | 2.564% | 0% | 0% | 12.18% | 0% | 0.641% | 7.051% | 1.282% | 13.46% | 100%
| Vegetation Establishment | 13 | 40.62% | [9 empty] | Other | 0% | 0% | 6.25% | 6.25% | 6.25% | 6.25% | 18.75% | 6.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.5% | 12.5% | 6.25% | 0% | 12.5% | 6.25% | 0% | 0% | 100%
| Wetland Delineation | 2 | 6.25% | [9 empty] | Procurement Issues | 0% | 0% | 0% | 3.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 86.67% | 0% | 0% | 0% | 0% | 0% | 0% | 6.667% | 0% | 3.333% | 0% | 0% | 0% | 100%
Erosion Control Problems | Erosion Control Problems-Unspecified | 52 | 96.3% | 54 | 2.48% | 14589.7044 | 361.8944 | [5 empty] | Quantities Overrun/Underrun | 0% | 2% | 0% | 8% | 0% | 0% | 30% | 2% | 0% | 0% | 20% | 2% | 0% | 0% | 0% | 8% | 4% | 0% | 0% | 10% | 0% | 8% | 4% | 2% | 0% | 100%
| Waste Site Erosion Control | 2 | 3.704% | [9 empty] | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 5.085% | 1.695% | 0% | 0% | 0.8475% | 5.085% | 0.8475% | 0% | 2.542% | 0% | 0% | 0% | 2.542% | 12.71% | 22.03% | 0% | 0% | 0% | 0% | 34.75% | 5.932% | 3.39% | 2.542% | 100%
Issues with Underground Utilities | Inability to Locate Utilities | 7 | 5.512% | 127 | 5.834% | 29096.6257 | 1697.4145 | [5 empty] | Scheduling and Coordination Issues | 2.941% | 2.941% | 2.941% | 0% | 0% | 0% | 2.941% | 11.76% | 0% | 2.941% | 2.941% | 0% | 5.882% | 0% | 0% | 0% | 0% | 41.18% | 0% | 5.882% | 0% | 11.76% | 0% | 2.941% | 2.941% | 100%
| Utilities not Relocated on Time | 7 | 5.512% | [9 empty] | Stakeholder Request | 2.247% | 1.685% | 8.989% | 6.742% | 0.5618% | 4.494% | 1.685% | 3.371% | 0.5618% | 4.494% | 5.056% | 0% | 0.5618% | 0.5618% | 0% | 7.303% | 2.247% | 0% | 1.124% | 2.809% | 0.5618% | 1.685% | 11.24% | 2.247% | 29.78% | 100%
| Utility Conflict | 113 | 88.98% | [9 empty] | Survey/Test Issues | 5% | 0% | 0% | 5% | 0% | 0% | 15% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 20% | 25% | 0% | 0% | 0% | 10% | 100%
M&R/Replacement | Damaged Objects | 6 | 3.846% | 156 | 7.166% | 42963.2381 | 3078.6703 | [5 empty] | All Generic Cause | 1.929% | 1.7% | 3.215% | 6.339% | 1.378% | 1.47% | 8.774% | 11.07% | 0.2756% | 1.148% | 7.028% | 0.1378% | 2.159% | 0.3215% | 1.608% | 8.176% | 2.113% | 1.148% | 0.4134% | 4.593% | 0.4593% | 6.615% | 7.35% | 3.583% | 17% | 100%
| M&R/Replacement-Unspecified | 147 | 94.23%
| Vehicular Accident | 3 | 1.923%
Other | Contractor Error | 2 | 12.5% | 16 | 0.735% | 11380.925 | 83.6448
| Covid 19 Impact | 2 | 12.5%
| Equipment/Items Protection | 3 | 18.75%
| Permit Acquisition Issues | 1 | 6.25%
| Permit Requirements | 4 | 25%
| Permit Restrictions | 2 | 12.5%
| Site Security | 2 | 12.5%
Procurement Issues | Error in Bill of Materials | 2 | 6.667% | 30 | 1.378% | 14827.2033 | 204.3253
| Material Acquisition Delays/Long Lead Items | 5 | 16.67%
| Material Fabrication Delay | 1 | 3.333%
| Shop Drawing Error | 3 | 10%
| Unavailability of Materials/Material Shortage | 18 | 60%
| Wrong Order Placement | 1 | 3.333%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 48 | 96% | 50 | 2.297% | 84632.4362 | 1943.7859
| Waste Excessive Material | 2 | 4%
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 5 | 4.237% | 118 | 5.42% | 30830.5636 | 1671.11
| Hazardous Materials Removal | 8 | 6.78%
| Safety Concerns-Unspecified | 91 | 77.12%
| Sight Distance Concerns | 1 | 0.8475%
| Travelers/Public Safety | 12 | 10.17%
| Tripping Hazard | 1 | 0.8475%
Scheduling and Coordination Issues | Additional ICT Required | 1 | 2.941% | 34 | 1.562% | 230636.1443 | 3602.0344
| Availability Date Delays | 5 | 14.71%
| Conflict with Other Projects | 2 | 5.882%
| Conflict/Overlap with Adjacent Projects | 3 | 8.824%
| Early Project Completion | 14 | 41.18%
| Miscommunication (Construction Progress) | 1 | 2.941%
| Overtime Hour Request | 1 | 2.941%
| Project Phasing Problems | 3 | 8.824%
| Statewide Initiative to Accelerate Projects | 2 | 5.882%
| Timely Completion of Project | 2 | 5.882%
Stakeholder Request | DOT Request-Unspecified | 71 | 39.89% | 178 | 8.176% | 178200.6782 | 14570.3816
| Stakeholder Request-Future Development Concerns | 11 | 6.18%
| Stakeholder Request-Unspecified | 96 | 53.93%
Survey/Test Issues | Additional Survey/Test Required | 6 | 30% | 20 | 0.9187% | 23243.903 | 213.5407
| Survey Error-Staking | 5 | 25%
| Survey Error-Unspecified | 9 | 45%

## 4a. Claim-Appalach Region Comm
Table 1 Claims - Appalachian Regional Commission | [9 empty] | Table 2 Claims - Appalachian Regional Commission
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 50% | 2 | 9.524% | 6509 | 619.9048 | 132 | 12.5714 | Design/Plan Issues | 8 | 38.1%
| Constructability Issues-Unspecified | 1 | 50% | [6 empty] | Contract Amendment | 3 | 14.29%
Contract Amendment | Settlement and Release Agreement | 2 | 66.67% | 3 | 14.29% | 51192.17 | 7313.1671 | 256.5 | 36.6429 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 2 | 9.524%
| Unavailability of Funds/Cash Flow Considerations | 1 | 33.33% | [6 empty] | Natural Disaster | 2 | 9.524%
Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals | 1 | 100% | 1 | 4.762% |  | 0 | 8 | 0.38095 | Design Approval Waiting Period/Indecision/Negotiation | 1 | 4.762%
Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 25% | 8 | 38.1% | 1842.32 | 701.8362 | 8.5714 | 3.2653 | Environmental/Community Concerns | 1 | 4.762%
| Design/Plan Revision-Unspecified | 6 | 75% | [6 empty] | Issues with Underground Utilities | 1 | 4.762%
Environmental/Community Concerns | Animal Protection/Endangered Species | 1 | 100% | 1 | 4.762% |  | 0 | 167 | 7.9524 | Project Closeout Issues | 1 | 4.762%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 100% | 1 | 4.762% | 2750 | 130.9524 | - | - | Quantities Overrun/Underrun | 1 | 4.762%
Natural Disaster | Natural Disaster-Slide | 2 | 100% | 2 | 9.524% | 8411 | 801.0476 | 156 | 14.8571 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 1 | 4.762%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 100% | 1 | 4.762% | 0 | 0 | 5 | 0.2381
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 100% | 1 | 4.762% | 1050 | 50 | - | - | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 1 | 100% | 1 | 4.762% | 0 | 0 | 1 | 0.047619 | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 50%
[10 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 37.5%
[10 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 12.5%
[10 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
[10 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 0%
[10 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 0%
[10 empty] | Utility – design, as-builts, etc. | 0%
[10 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Unspecified | 0%

## 4b. SA-Appalach Region Comm
Table 1 Supplementary Agreements (Appalachian Regional Commission) | [7 empty] | Table 2 Supplementary Agreements (Appalachian Regional Commission) |  |  |  |  | Table 4 Supplementary Agreements (Appalachian Regional Commission)
Generic Cause | Specific Cause | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Contract | Environmental | Finishing and Interior Work | Geotechnical | Hydraulics | Pavement | Procurement | Roadway Alignment | Roadway Design | Safety | Structural | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Providing Access to Site | 1 | 50% | 2 | 3.636% | 7640 | 277.8182 | Design/Plan Issues | 13 | 23.64% |  |  | Access/ROW/Easement | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 100%
| Traffic Access Point | 1 | 50% |  |  |  |  | Contract Amendment | 10 | 18.18% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 33.33% | 0% | 0% | 0% | 0% | 0% | 33.33% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 100% | 3 | 5.455% | 52120 | 2842.9091 | Differing Site Conditions (Except Utilities) | 5 | 9.091% |  |  | Construction Method Revision | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 2 | 100% | 2 | 3.636% | -2952.375 | -107.3591 | Quantities Overrun/Underrun | 4 | 7.273% |  |  | Contract Amendment | 20% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 10% | 10% | 10% | 20% | 100%
Contract Amendment | Issues with Previous SA | 1 | 10% | 10 | 18.18% | 17527.582 | 3186.8331 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 3 | 5.455% |  |  | Design/Plan Issues | 0% | 0% | 30.77% | 7.692% | 0% | 38.46% | 0% | 0% | 15.38% | 0% | 0% | 7.692% | 0% | 0% | 100%
| Line Item Omission | 8 | 80% |  |  |  |  | Drainage Issues | 3 | 5.455% |  |  | Differing Site Conditions (Except Utilities) | 0% | 20% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 100%
| Revise Measurement and Payment Method | 1 | 10% |  |  |  |  | Access/ROW/Easement | 2 | 3.636% |  |  | Drainage Issues | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 23.08% | 13 | 23.64% | 42045.0085 | 9937.9111 | Construction Method Revision | 2 | 3.636% |  |  | Environmental/Community Concerns | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Construction Plans Error/Discrepancy | 1 | 7.692% |  |  |  |  | Environmental/Community Concerns | 2 | 3.636% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
| Design Revision-Fix Impacts of Previous Revisions | 1 | 7.692% |  |  |  |  | Issues with Underground Utilities | 2 | 3.636% |  |  | M&R/Replacement | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 100%
| Design Revision-Unspecified | 8 | 61.54% |  |  |  |  | M&R/Replacement | 2 | 3.636% |  |  | Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 20% | 5 | 9.091% | 87577.282 | 7961.5711 | Procurement Issues | 2 | 3.636% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Not Shown in Construction Plans | 1 | 20% |  |  |  |  | Safety Concerns (Except Contaminated Soil) | 2 | 3.636% |  |  | Quantities Overrun/Underrun | 25% | 0% | 0% | 25% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Unsuitable Materials | 2 | 40% |  |  |  |  | Other | 1 | 1.818% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
| Slope Protection/Soil Stabilization | 1 | 20% |  |  |  |  | Stakeholder Request | 1 | 1.818% |  |  | Stakeholder Request | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100%
Drainage Issues | Stormwater Concerns | 3 | 100% | 3 | 5.455% | 5727.8333 | 312.4273 | Survey/Test Issues | 1 | 1.818% |  |  | Survey/Test Issues | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Environmental/Community Concerns | Vegetation Establishment | 2 | 100% | 2 | 3.636% | 4362 | 158.6182 | [5 empty] | Grand Total | 5.455% | 10.91% | 9.091% | 9.091% | 7.273% | 12.73% | 5.455% | 1.818% | 7.273% | 5.455% | 5.455% | 7.273% | 3.636% | 9.091% | 100%
Issues with Underground Utilities | Utility Conflict | 2 | 100% | 2 | 3.636% | 17198.75 | 625.4091 | Table 3 Supplementary Agreements (Appalachian Regional Commission)
M&R/Replacement | Damaged Objects | 1 | 50% | 2 | 3.636% | 39508 | 1436.6545 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| M&R/Replacement-Unspecified | 1 | 50% |  |  |  |  | Pavement | 7 | 12.73% | 113999.8443 | 14509.0711
Other | Equipment/Items Protection | 1 | 100% | 1 | 1.818% | 302.6 | 5.5018 | Environmental | 6 | 10.91% | 9704.0683 | 1058.6256
Procurement Issues | Unavailability of Materials/Material Shortage | 2 | 100% | 2 | 3.636% | -675 | -24.5455 | Finishing and Interior Work | 5 | 9.091% | 2971.14 | 270.1036
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 4 | 100% | 4 | 7.273% | -97424.2333 | -7085.3988 | Geotechnical | 5 | 9.091% | 105896.8825 | 9626.9893
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 2 | 100% | 2 | 3.636% | 57283.8 | 2083.0473 | Utilities | 5 | 9.091% | 30066.7 | 2733.3364
Stakeholder Request | DOT Request-Unspecified | 1 | 100% | 1 | 1.818% | 540 | 9.8182 | Hydraulics | 4 | 7.273% | 6150.005 | 447.2731
Survey/Test Issues | Survey Error-Unspecified | 1 | 100% | 1 | 1.818% | 7416.52 | 134.8458 | Roadway Design | 4 | 7.273% | 2107 | 153.2364
[8 empty] | TCP (Construction Phase) | 4 | 7.273% | 2357.65 | 171.4655
[8 empty] | Contract | 3 | 5.455% | -182355.06 | -9946.6396
[8 empty] | Procurement | 3 | 5.455% | -675 | -36.8182
[8 empty] | Safety | 3 | 5.455% | 44248.44 | 2413.5513
[8 empty] | Structural | 3 | 5.455% | 26731.9333 | 1458.1055
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 2 | 3.636% | 3031.5 | 110.2364
[8 empty] | Roadway Alignment | 1 | 1.818% | 83840 | 1524.3636

## 5a. Claim-Bicycle & Pedestrian
Table 1 Claims - Bicycle and Pedestrian | [9 empty] | Table 2 Claims - Bicycle and Pedestrian
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Insufficient ROW | 1 | 100% | 1 | 2.857% |  | 0 | 1 | 0.028571 | Issues with Underground Utilities | 8 | 22.86%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 100% | 1 | 2.857% |  | 0 | 180 | 5.1429 | Design/Plan Issues | 7 | 20%
Contract Amendment | Line Item Omission | 2 | 100% | 2 | 5.714% |  | 0 | 1 | 0.057143 | Design Approval Waiting Period/Indecision/Negotiation | 4 | 11.43%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 3 | 75% | 4 | 11.43% |  | 0 | 68.5 | 7.8286 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 8.571%
| Untimely Review and Return of Submittals | 1 | 25% | [6 empty] | Contract Amendment | 2 | 5.714%
Design/Plan Issues | Design/Plan Revision-Unspecified | 6 | 85.71% | 7 | 20% | 10013.3333 | 2002.6667 | 78.1429 | 15.6286 | M&R/Replacement | 2 | 5.714%
| Increased Traffic Volume | 1 | 14.29% | [6 empty] | Project Closeout Issues | 2 | 5.714%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 1 | 100% | 1 | 2.857% | 25536 | 729.6 | - | - | Start Date Delays | 2 | 5.714%
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 25% | 8 | 22.86% | 185009.5033 | 42287.8865 | 107.8333 | 24.6476 | Access/ROW/Easement | 1 | 2.857%
| Utility Conflict | 6 | 75% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 1 | 2.857%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 5.714% | 32423.12 | 1852.7497 | - | - | Differing Site Conditions (Except Utilities) | 1 | 2.857%
Natural Disaster | Natural Disaster-Hurricane | 1 | 100% | 1 | 2.857% |  | 0 | 7 | 0.2 | Natural Disaster | 1 | 2.857%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 100% | 1 | 2.857% |  | 0 | 71 | 2.0286 | Procurement Issues | 1 | 2.857%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 50% | 2 | 5.714% |  | 0 | 7.5 | 0.42857
| Scheduling Conflicts-Final Inspection/Punchlist | 1 | 50% | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 3 | 100% | 3 | 8.571% |  | 0 | 43.3333 | 3.7143 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 14.29%
Start Date Delays | Delay in Contract Execution | 2 | 100% | 2 | 5.714% |  | 0 | 16 | 0.91429 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 14.29%
[10 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 14.29%
[5 empty] | 100% |  |  |  |  | Environmental – vegetation plans, habitat mitigation, etc. | 14.29%
[10 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 14.29%
[10 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
[10 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 0%
[10 empty] | Utility – design, as-builts, etc. | 0%
[10 empty] | Unspecified | 28.57%

## 5b. SA-Bicycle and Pedestrian
Table 1 Supplementary Agreements (SA-Bicycle and Pedestrian) | [7 empty] | Table 2 Supplementary Agreements (SA-Bicycle and Pedestrian) |  |  |  |  | Table 4 Supplementary Agreements (SA-Bicycle and Pedestrian)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Access/ROW/Easement | Environmental | Geotechnical | Hydraulics | Pavement | Railroad | Roadway Design | Safety | Schedule | Survey | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Property Owners Access | 1 | 100% | 1 | 2.778% | 4472 | 124.2222 | Stakeholder Request | 6 | 16.67% |  |  | Access/ROW/Easement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 2 | 100% | 2 | 5.556% | 41899.59 | 2327.755 | Contract Amendment | 5 | 13.89% |  |  | Construction Method Revision | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 50% | 0% | 0% | 0% | 100%
Contract Amendment | Elimination of Contract Line Item | 1 | 20% | 5 | 13.89% | 3166.3625 | 439.7726 | Issues with Underground Utilities | 4 | 11.11% |  |  | Contract Amendment | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 20% | 20% | 0% | 0% | 20% | 100%
| Line Item Omission | 3 | 60% |  |  |  |  | M&R/Replacement | 4 | 11.11% |  |  | Design/Plan Issues | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100%
| Revise Measurement and Payment Method | 1 | 20% |  |  |  |  | Differing Site Conditions (Except Utilities) | 3 | 8.333% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 50% | 2 | 5.556% | 3682.645 | 204.5914 | Drainage Issues | 3 | 8.333% |  |  | Drainage Issues | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Future Maintenance Concerns | 1 | 50% |  |  |  |  | Erosion Control Problems | 3 | 8.333% |  |  | Erosion Control Problems | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Encountered Rock | 1 | 33.33% | 3 | 8.333% | 5707.7733 | 475.6478 | Construction Method Revision | 2 | 5.556% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
| Differing Site Conditions-Not Shown in Construction Plans | 2 | 66.67% |  |  |  |  | Design/Plan Issues | 2 | 5.556% |  |  | M&R/Replacement | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 100%
Drainage Issues | Drainage Issues-Unspecified | 3 | 100% | 3 | 8.333% | 3719.58 | 309.965 | Safety Concerns (Except Contaminated Soil) | 2 | 5.556% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 100% | 3 | 8.333% | 2409.6 | 200.8 | Access/ROW/Easement | 1 | 2.778% |  |  | Scheduling and Coordination Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 25% | 4 | 11.11% | 16109.5 | 1789.9444 | Scheduling and Coordination Issues | 1 | 2.778% |  |  | Stakeholder Request | 0% | 16.67% | 0% | 0% | 0% | 0% | 16.67% | 0% | 0% | 0% | 0% | 50% | 16.67% | 0% | 100%
| Utility Conflict | 3 | 75% | [9 empty] | Grand Total | 2.778% | 16.67% | 2.778% | 11.11% | 2.778% | 2.778% | 2.778% | 5.556% | 2.778% | 2.778% | 5.556% | 11.11% | 5.556% | 25% | 100%
M&R/Replacement | M&R/Replacement-Unspecified | 4 | 100% | 4 | 11.11% | 4997 | 555.2222 | Table 3 Supplementary Agreements (SA-Bicycle and Pedestrian)
Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 2 | 100% | 2 | 5.556% | 2785 | 154.7222 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
Scheduling and Coordination Issues | Early Project Completion | 1 | 100% | 1 | 2.778% | 162710.89 | 4519.7469 | Utilities | 9 | 25% | 11718.1312 | 2929.5328
Stakeholder Request | DOT Request-Unspecified | 2 | 33.33% | 6 | 16.67% | 6144.5833 | 1024.0972 | Environmental | 6 | 16.67% | 3072.3 | 512.05
| Stakeholder Request-Future Development Concerns | 1 | 16.67% |  |  |  |  | Hydraulics | 4 | 11.11% | 3307.185 | 367.465
| Stakeholder Request-Unspecified | 3 | 50% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 4 | 11.11% | 7187.3225 | 798.5914
[8 empty] | Safety | 2 | 5.556% | 36102.24 | 2005.68
[8 empty] | TCP (Construction Phase) | 2 | 5.556% | 10647.35 | 591.5194
[8 empty] | Traffic Control Systems (pavement Markings) | 2 | 5.556% | 4297.25 | 238.7361
[8 empty] | Access/ROW/Easement | 1 | 2.778% | 4472 | 124.2222
[8 empty] | Geotechnical | 1 | 2.778% | 0 | 0
[8 empty] | Pavement | 1 | 2.778% | 6161.72 | 171.1589
[8 empty] | Railroad | 1 | 2.778% | 9075 | 252.0833
[8 empty] | Roadway Design | 1 | 2.778% | 1600 | 44.4444
[8 empty] | Schedule | 1 | 2.778% | 162710.89 | 4519.7469
[8 empty] | Survey | 1 | 2.778% | -11880 | -330

## 6a. Claim-Bridge Replacement
Table 1 Claims - Bridge Replacement | [9 empty] | Table 2 Claims - Bridge Replacement
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Issues with Underground Utilities | Utilities not Relocated on Time | 24 | 40.68% | 59 | 13.88% | 21739.2367 | 3017.9176 | 43.7925 | 6.0794 | Issues with Underground Utilities | 59 | 13.88%
| Utility Conflict | 35 | 59.32% | [6 empty] | Design/Plan Issues | 59 | 13.88%
Design/Plan Issues | Compliance with Standard Specifications | 5 | 8.475% | 59 | 13.88% | 14093.0672 | 1956.4493 | 52.9608 | 7.3522 | Natural Disaster | 40 | 9.412%
| Design/Plan Error-Unspecified | 14 | 23.73% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 36 | 8.471%
| Design/Plan Revision-Unspecified | 39 | 66.1% | [6 empty] | Project Closeout Issues | 33 | 7.765%
| Increased Traffic Volume | 1 | 1.695% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 32 | 7.529%
Natural Disaster | Natural Disaster-Hurricane | 39 | 97.5% | 40 | 9.412% | - | 0 | 22.5 | 2.1176 | Environmental/Community Concerns | 31 | 7.294%
| Natural Disaster-Tropical Depression | 1 | 2.5% | [6 empty] | Contract Amendment | 25 | 5.882%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 6 | 16.67% | 36 | 8.471% | 94214.79 | 7980.5469 | 28.7879 | 2.4385 | Differing Site Conditions (Except Utilities) | 23 | 5.412%
| Purposeful Limited Work Schedule | 11 | 30.56% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 19 | 4.471%
| Scheduling Conflicts-Inspection | 5 | 13.89% | [6 empty] | Survey/Test Issues | 12 | 2.824%
| Timely Completion of Project | 1 | 2.778% | [6 empty] | M&R/Replacement | 12 | 2.824%
| Waiting for Other Entities to Perform Work | 2 | 5.556% | [6 empty] | Procurement Issues | 11 | 2.588%
| Work Out of Sequence | 2 | 5.556% | [6 empty] | Permit | 10 | 2.353%
| Work Restriction-Social Event | 1 | 2.778% | [6 empty] | Quantities Overrun/Underrun | 9 | 2.118%
| Work Restriction-Unspecified | 8 | 22.22% | [6 empty] | Start Date Delays | 7 | 1.647%
Project Closeout Issues | Final Punchlist Extra Work | 2 | 6.061% | 33 | 7.765% | 2000 | 155.2941 | 10.6667 | 0.82824 | Access/ROW/Easement | 5 | 1.176%
| Scheduling Conflicts-Final Inspection/Punchlist | 31 | 93.94% | [6 empty] | Other | 2 | 0.4706%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 2 | 6.25% | 32 | 7.529% | 36691.385 | 2762.6455 | 77.6562 | 5.8471
| Constructability Issues-Seasonal Limitations (Weather) | 29 | 90.62%
| Constructability Issues-Unspecified | 1 | 3.125% | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
Environmental/Community Concerns | Animal Protection/Endangered Species | 1 | 3.226% | 31 | 7.294% | 913 | 66.5953 | 93.6667 | 6.8322 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 32.2%
| Environmental Concerns/Unspecified | 1 | 3.226% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 18.64%
| Erosion Control Problems | 1 | 3.226% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 13.56%
| Vegetation Establishment | 28 | 90.32% | [6 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 13.56%
Contract Amendment | Contract Time Adjustment | 4 | 16% | 25 | 5.882% | 555758.3686 | 32691.6687 | 36.5238 | 2.1485 | Utility – design, as-builts, etc. | 8.475%
| Contractor Replacement | 1 | 4% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 1.695%
| Elimination of Contract Line Item | 2 | 8% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
| Error in Entering Time Extensions in HiCAMS | 9 | 36% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
| Line Item Omission | 5 | 20% | [6 empty] | Unspecified | 11.86%
| Revise Measurement and Payment Method | 1 | 4%
| Settlement and Release Agreement | 3 | 12%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 8 | 34.78% | 23 | 5.412% | 10137.471 | 548.6161 | 26.7 | 1.4449
| Differing Site Conditions-Contaminated Groundwater | 1 | 4.348%
| Differing Site Conditions-Contaminated Soil | 1 | 4.348%
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 7 | 30.43%
| Differing Site Conditions-Incomplete Work by Others | 3 | 13.04%
| Differing Site Conditions-Unspecified | 1 | 4.348%
| Differing Site Conditions-Unsuitable Materials | 2 | 8.696%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 11 | 57.89% | 19 | 4.471% | 12714.68 | 568.421 | 41.2778 | 1.8454
| Untimely Receipt of Design | 1 | 5.263%
| Untimely Review and Return of Submittals | 5 | 26.32%
| Untimely Review of Approvals | 2 | 10.53%
Survey/Test Issues | Additional Survey-Test Required | 4 | 33.33% | 12 | 2.824% | 14511.0583 | 409.724 | 14.125 | 0.39882
| Survey Error | 7 | 58.33%
| Survey Results Delays | 1 | 8.333%
M&R/Replacement | M&R/Replacement-Unspecified | 12 | 100% | 12 | 2.824% | 2963.5275 | 83.6761 | 49.1111 | 1.3867
Procurement Issues | DOT Furnished Materials/Equipment Delays | 2 | 18.18% | 11 | 2.588% | 77894.29 | 2016.0875 | 33 | 0.85412
| Material Acquisition Delays/Long Lead Items | 4 | 36.36%
| Power Supply Delays | 1 | 9.091%
| Unavailability of Materials/Material Shortage | 2 | 18.18%
| Wrong Order Placement | 2 | 18.18%
Permit | Permit Acquisition Waiting Period | 8 | 80% | 10 | 2.353% | 60042.665 | 1412.7686 | 61.3333 | 1.4431
| Permit Limitation | 2 | 20%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 9 | 100% | 9 | 2.118% | 11051.7243 | 234.0365 | 2.6667 | 0.056471
Start Date Delays | Delay in Contract Execution | 2 | 28.57% | 7 | 1.647% | - | 0 | 55.1429 | 0.90824
| Delay in Preconstruction Meeting | 2 | 28.57%
| Delay in Project Award | 1 | 14.29%
| Delay in Receipt of Contract Information and Bonds | 1 | 14.29%
| Start Date Delays-Unspecified | 1 | 14.29%
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 20% | 5 | 1.176% | - | 0 | 36.6 | 0.43059
| Insufficient ROW | 2 | 40%
| ROW Acquisition Delays-Unspecified | 2 | 40%
Other | Covid 19 Impact | 1 | 50% | 2 | 0.4706% | 107204.47 | 504.4916 | 3 | 0.014118
| Unforeseen Issues-Unspecified | 1 | 50%

## 6b. SA-Bridge Replacement
Table 1 Supplementary Agreements (Bridge Replacement) | [7 empty] | Table 2 Supplementary Agreements (Bridge Replacement) |  |  |  |  | Table 4 Supplementary Agreements (Bridge Replacement)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Access/ROW/Easement | Contract | Corridor/Traffic Design | Environmental | Finishing and Interior Work | Geotechnical | Hydraulics | Natural Disaster | Other | Pavement | Procurement | Roadway Alignment | Roadway Design | Safety | Schedule | Security/Protection | Structural | Survey | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 3 | 42.86% | 7 | 1.955% | 5455.8457 | 106.6785 | Design/Plan Issues | 96 | 26.82% |  |  | Access/ROW/Easement | 14.29% | 0% | 0% | 0% | 0% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0% | 28.57% | 0% | 0% | 14.29% | 0% | 0% | 14.29% | 0% | 0% | 14.29% | 100%
| Insufficient ROW | 1 | 14.29% |  |  |  |  | Contract Amendment | 56 | 15.64% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 5.263% | 0% | 0% | 10.53% | 0% | 0% | 0% | 0% | 0% | 0% | 21.05% | 0% | 0% | 0% | 5.263% | 0% | 26.32% | 5.263% | 5.263% | 21.05% | 100%
| Property Owners Access | 2 | 28.57% |  |  |  |  | Differing Site Conditions (Except Utilities) | 31 | 8.659% |  |  | Construction Method Revision | 0% | 0% | 11.11% | 0% | 0% | 0% | 0% | 0% | 11.11% | 11.11% | 0% | 0% | 11.11% | 0% | 0% | 0% | 0% | 0% | 33.33% | 11.11% | 0% | 11.11% | 100%
| Providing Access to Site | 1 | 14.29% |  |  |  |  | Stakeholder Request | 24 | 6.704% |  |  | Contract Amendment | 1.786% | 1.786% | 3.571% | 3.571% | 0% | 14.29% | 7.143% | 0% | 0% | 5.357% | 0% | 0% | 8.929% | 0% | 0% | 0% | 7.143% | 5.357% | 10.71% | 5.357% | 10.71% | 14.29% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 3 | 15.79% | 19 | 5.307% | 8386.76 | 445.1074 | Erosion Control Problems | 20 | 5.587% |  |  | Design/Plan Issues | 0% | 2.083% | 2.083% | 0% | 1.042% | 6.25% | 11.46% | 0% | 1.042% | 6.25% | 2.083% | 8.333% | 21.88% | 0% | 1.042% | 0% | 13.54% | 0% | 4.167% | 3.125% | 9.375% | 6.25% | 100%
| Constructability Issues-Unspecified | 15 | 78.95% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 19 | 5.307% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 0% | 3.226% | 0% | 54.84% | 16.13% | 0% | 3.226% | 3.226% | 0% | 6.452% | 3.226% | 0% | 0% | 0% | 3.226% | 0% | 0% | 0% | 0% | 6.452% | 100%
| Height Clearance Issues | 1 | 5.263% |  |  |  |  | M&R/Replacement | 18 | 5.028% |  |  | Drainage Issues | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 9 | 100% | 9 | 2.514% | 7465.8138 | 187.6881 | Issues with Underground Utilities | 17 | 4.749% |  |  | Environmental/Community Concerns | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Contract Amendment | Insufficient Insurance | 1 | 1.786% | 56 | 15.64% | 6473.1693 | 1012.5628 | Safety Concerns (Except Contaminated Soil) | 16 | 4.469% |  |  | Erosion Control Problems | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Line Item Omission | 53 | 94.64% |  |  |  |  | Quantities Overrun/Underrun | 11 | 3.073% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 5.882% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 94.12% | 100%
| Material Substitution Allowance | 2 | 3.571% |  |  |  |  | Construction Method Revision | 9 | 2.514% |  |  | M&R/Replacement | 0% | 0% | 0% | 0% | 0% | 5.556% | 0% | 11.11% | 0% | 16.67% | 0% | 0% | 5.556% | 0% | 0% | 0% | 27.78% | 0% | 0% | 0% | 0% | 33.33% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 16 | 16.67% | 96 | 26.82% | 15665.0293 | 4200.6782 | Survey/Test Issues | 9 | 2.514% |  |  | Other | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 100%
| Construction Plans Error/Discrepancy | 7 | 7.292% |  |  |  |  | Access/ROW/Easement | 7 | 1.955% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Elevation Difference with Existing Objects | 4 | 4.167% |  |  |  |  | Drainage Issues | 6 | 1.676% |  |  | Quantities Overrun/Underrun | 0% | 0% | 0% | 9.091% | 0% | 63.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.27% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Unspecified | 14 | 14.58% |  |  |  |  | Procurement Issues | 6 | 1.676% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 0% | 0% | 6.25% | 0% | 0% | 0% | 0% | 0% | 6.25% | 31.25% | 25% | 0% | 0% | 0% | 0% | 12.5% | 0% | 6.25% | 12.5% | 100%
| Design Revision-Fix Impacts of Previous Revisions | 1 | 1.042% |  |  |  |  | Environmental/Community Concerns | 5 | 1.397% |  |  | Scheduling and Coordination Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Functionality Issues | 2 | 2.083% |  |  |  |  | Other | 5 | 1.397% |  |  | Stakeholder Request | 8.333% | 0% | 8.333% | 4.167% | 0% | 8.333% | 12.5% | 0% | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 8.333% | 8.333% | 0% | 0% | 4.167% | 0% | 33.33% | 100%
| Design Revision-Future Maintenance Concerns | 2 | 2.083% |  |  |  |  | Scheduling and Coordination Issues | 3 | 0.838% |  |  | Survey/Test Issues | 11.11% | 0% | 0% | 11.11% | 0% | 11.11% | 22.22% | 0% | 0% | 0% | 0% | 0% | 11.11% | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-per Contractor Request | 17 | 17.71% | [9 empty] | Grand Total | 1.397% | 0.838% | 2.514% | 8.659% | 0.2793% | 12.85% | 9.218% | 0.5587% | 1.117% | 3.911% | 1.955% | 3.073% | 11.45% | 1.117% | 1.397% | 0.838% | 9.497% | 0.838% | 5.866% | 2.793% | 4.749% | 15.08% | 100%
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 1.042% |  |  |  |  | Table 3 Supplementary Agreements (Bridge Replacement)
| Design Revision-Unspecified | 29 | 30.21% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Increased Traffic Volume | 2 | 2.083% |  |  |  |  | Utilities | 54 | 15.08% | 23812.8023 | 3591.8752
| Scope Change | 1 | 1.042% |  |  |  |  | Geotechnical | 46 | 12.85% | 55227.552 | 7096.2776
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 3.226% | 31 | 8.659% | 29960.8306 | 2594.3736 | Roadway Design | 41 | 11.45% | 8571.5076 | 981.6531
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 3 | 9.677% |  |  |  |  | Structural | 34 | 9.497% | 23328.9038 | 2215.5942
| Differing Site Conditions-Not Shown in Construction Plans | 5 | 16.13% |  |  |  |  | Hydraulics | 33 | 9.218% | 11869.0268 | 1094.0723
| Differing Site Conditions-Unspecified | 7 | 22.58% |  |  |  |  | Environmental | 31 | 8.659% | 348060.1471 | 30139.2865
| Differing Site Conditions-Unsuitable Materials | 4 | 12.9% |  |  |  |  | TCP (Construction Phase) | 21 | 5.866% | 3794.6111 | 222.5889
| Slope Protection/Soil Stabilization | 11 | 35.48% |  |  |  |  | Traffic Control Systems (pavement Markings) | 17 | 4.749% | 6133.0788 | 291.2356
Drainage Issues | Drainage Issues-Unspecified | 6 | 100% | 6 | 1.676% | 17626.76 | 295.4206 | Pavement | 14 | 3.911% | 24997.5589 | 977.5582
Environmental/Community Concerns | Environmental Concerns-Unspecified | 3 | 60% | 5 | 1.397% | 2133963.016 | 29803.9527 | Roadway Alignment | 11 | 3.073% | 19761.2991 | 607.1908
| Vegetation Establishment | 2 | 40% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 10 | 2.793% | 86025.364 | 2402.9431
Erosion Control Problems | Erosion Control Problems-Unspecified | 20 | 100% | 20 | 5.587% | 3244.832 | 181.2755 | Corridor/Traffic Design | 9 | 2.514% | 268158.7089 | 6741.4201
Issues with Underground Utilities | Inability to Locate Utilities | 1 | 5.882% | 17 | 4.749% | 12091.7682 | 574.1901 | Procurement | 7 | 1.955% | -3473.88 | -67.925
| Utilities not Relocated on Time | 1 | 5.882% |  |  |  |  | Access/ROW/Easement | 5 | 1.397% | 3771.06 | 52.6684
| Utility Conflict | 15 | 88.24% |  |  |  |  | Schedule | 5 | 1.397% | 251731.49 | 3515.8029
M&R/Replacement | Damaged Objects | 1 | 5.556% | 18 | 5.028% | 48245.0639 | 2425.7295 | Other | 4 | 1.117% | 46098.26 | 515.0644
| M&R/Replacement-Unspecified | 17 | 94.44% |  |  |  |  | Safety | 4 | 1.117% | 24655.765 | 275.4834
Other | Contractor Error | 1 | 20% | 5 | 1.397% | 8777.55 | 122.5915 | Contract | 3 | 0.838% | 1000 | 8.3799
| Covid 19 Impact | 2 | 40% |  |  |  |  | Security/Protection | 3 | 0.838% | 5527.8667 | 46.3229
| Equipment/Items Protection | 1 | 20% |  |  |  |  | Survey | 3 | 0.838% | 30903.3333 | 258.9665
| Permit Restrictions | 1 | 20% |  |  |  |  | Natural Disaster | 2 | 0.5587% | 3109.75 | 17.3729
Procurement Issues | Error in Bill of Materials | 2 | 33.33% | 6 | 1.676% | -4586.395 | -76.867 | Finishing and Interior Work | 1 | 0.2793% | 22225 | 62.081
| Unavailability of Materials/Material Shortage | 4 | 66.67%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 11 | 100% | 11 | 3.073% | 32226.8555 | 990.2106
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 2 | 12.5% | 16 | 4.469% | 13001.9025 | 581.0906
| Hazardous Materials Removal | 1 | 6.25%
| Safety Concerns-Unspecified | 11 | 68.75%
| Travelers/Public Safety | 2 | 12.5%
Scheduling and Coordination Issues | Availability Date Delays | 3 | 100% | 3 | 0.838% | 126590.245 | 1060.8121
Stakeholder Request | DOT Request-Unspecified | 8 | 33.33% | 24 | 6.704% | 194491.015 | 13038.5038
| Stakeholder Request-Future Development Concerns | 1 | 4.167%
| Stakeholder Request-Unspecified | 15 | 62.5%
Survey/Test Issues | Additional Survey/Test Required | 2 | 22.22% | 9 | 2.514% | 36203.4456 | 910.1425
| Survey Error-Staking | 2 | 22.22%
| Survey Error-Unspecified | 5 | 55.56%

## 7a. Claim-Ferry
Table 1 Claims - Ferry | [9 empty] | Table 2 Claims - Ferry
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Contract Amendment | Line Item Omission | 2 | 100% | 2 | 14.29% | 8004.73 | 1143.5329 | 236 | 33.7143 | Natural Disaster | 4 | 28.57%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 100% | 1 | 7.143% | 0 | 0 | 87 | 6.2143 | Contract Amendment | 2 | 14.29%
Design/Plan Issues | Design/Plan Error-Unspecified | 1 | 100% | 1 | 7.143% | 10517.15 | 751.225 | 95 | 6.7857 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 2 | 14.29%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 100% | 1 | 7.143% | 5571.87 | 397.9907 | 1 | 0.071429 | Design Approval Waiting Period/Indecision/Negotiation | 1 | 7.143%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 100% | 1 | 7.143% | 26127.93 | 1866.2807 | - | - | Design/Plan Issues | 1 | 7.143%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 7.143% | 0 | 0 | 6 | 0.42857 | Differing Site Conditions (Except Utilities) | 1 | 7.143%
Natural Disaster | Natural Disaster-Hurricane | 4 | 100% | 4 | 28.57% | 0 | 0 | 70 | 20 | Issues with Underground Utilities | 1 | 7.143%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 1 | 100% | 1 | 7.143% | 0 | 0 | 32 | 2.2857 | M&R/Replacement | 1 | 7.143%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 50% | 2 | 14.29% | 0 | 0 | 18 | 2.5714 | Procurement Issues | 1 | 7.143%
| Work Out of Sequence | 1 | 50%
[10 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
[10 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 100%
[10 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 0%
[10 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
[10 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 0%
[10 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
[10 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
[10 empty] | Utility – design, as-builts, etc. | 0%
[10 empty] | Unspecified | 0%

## 7b. SA-Ferry
Table 1 Supplementary Agreements (Ferry) | [7 empty] | Table 2 Supplementary Agreements (Ferry) |  |  |  |  | Table 4 Supplementary Agreements (Ferry)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Contract | Environmental | Ferry | Finishing and Interior Work | Geotechnical | Hydraulics | Natural Disaster | Pavement | Procurement | Structural | Traffic Control Systems (Except Pavement Markings) | Utilities | Grand Total
Contract Amendment | Change in Contract Provisions | 1 | 25% | 4 | 8% | 158581.475 | 12686.518 | Design/Plan Issues | 36 | 72% |  |  | Contract Amendment | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 100%
| Settlement and Release Agreement | 1 | 25% |  |  |  |  | Contract Amendment | 4 | 8% |  |  | Design/Plan Issues | 0% | 5.556% | 77.78% | 0% | 0% | 2.778% | 2.778% | 0% | 8.333% | 0% | 2.778% | 0% | 100%
| Unavailability of Funds/Cash Flow Considerations | 2 | 50% |  |  |  |  | Other | 3 | 6% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Design/Plan Issues | Design Error-Unspecified | 1 | 2.778% | 36 | 72% | 13983.5356 | 10068.1456 | Stakeholder Request | 3 | 6% |  |  | M&R/Replacement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100%
| Design Revision-Unspecified | 35 | 97.22% |  |  |  |  | Procurement Issues | 2 | 4% |  |  | Other | 0% | 0% | 33.33% | 33.33% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 100% | 1 | 2% | 44434.27 | 888.6854 | Issues with Underground Utilities | 1 | 2% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 2% | 17230.79 | 344.6158 | M&R/Replacement | 1 | 2% |  |  | Stakeholder Request | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 33.33% | 33.33% | 0% | 0% | 0% | 100%
Other | Permit Requirements | 3 | 100% | 3 | 6% | 20513 | 1230.78 | [5 empty] | Grand Total | 6% | 4% | 60% | 2% | 2% | 2% | 2% | 2% | 14% | 2% | 2% | 2% | 100%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 2 | 100% | 2 | 4% | 80708.795 | 3228.3518 | Table 3 Supplementary Agreements (Ferry)
Stakeholder Request | DOT Request-Unspecified | 3 | 100% | 3 | 6% | 13005.2733 | 780.3164 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
[8 empty] | Ferry | 30 | 60% | 15212.5073 | 9127.5044
[8 empty] | Procurement | 7 | 14% | 31029.94 | 4344.1916
[8 empty] | Contract | 3 | 6% | 210933.5267 | 12656.0116
[8 empty] | Environmental | 2 | 4% | 1413.29 | 56.5316
[8 empty] | Finishing and Interior Work | 1 | 2% | 33391 | 667.82
[8 empty] | Geotechnical | 1 | 2% | 9280 | 185.6
[8 empty] | Hydraulics | 1 | 2% | 3805.3 | 76.106
[8 empty] | Natural Disaster | 1 | 2% | 23027.5 | 460.55
[8 empty] | Pavement | 1 | 2% | 23546.72 | 470.9344
[8 empty] | Structural | 1 | 2% | 17230.79 | 344.6158
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 1 | 2% | 2359 | 47.18
[8 empty] | Utilities | 1 | 2% | 44434.27 | 888.6854

## 8a, Claim-Highway Safety
Table 1 Claims - Highway Safety | [9 empty] | Table 2 Claims - Highway Safety
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Railroad Right of Entry | 1 | 25% | 4 | 2.703% | 0 | 0 | 95.75 | 2.5878 | Issues with Underground Utilities | 26 | 17.57%
| ROW Acquisition Delays-Unspecified | 3 | 75% | [6 empty] | Design/Plan Issues | 21 | 14.19%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 8 | 100% | 8 | 5.405% | 0 | 0 | 68.375 | 3.6959 | Project Closeout Issues | 21 | 14.19%
Contract Amendment | Elimination of Contract Line Item | 1 | 20% | 5 | 3.378% | 0 | 0 | 27.8 | 0.93919 | Natural Disaster | 18 | 12.16%
| Error in Entering Time Extensions in HiCAMS | 3 | 60% | [6 empty] | Quantities Overrun/Underrun | 11 | 7.432%
| Settlement and Release Agreement | 1 | 20% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 9 | 6.081%
Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement | 1 | 33.33% | 3 | 2.027% | 0 | 0 | 57.6667 | 1.1689 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 8 | 5.405%
| Indecision-Unspecified | 1 | 33.33% | [6 empty] | Environmental/Community Concerns | 7 | 4.73%
| Untimely Review and Return of Submittals | 1 | 33.33% | [6 empty] | M&R/Replacement | 6 | 4.054%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 4.762% | 21 | 14.19% | 6787.2 | 963.0486 | 109.5238 | 15.5405 | Contract Amendment | 5 | 3.378%
| Design/Plan Error-Unspecified | 4 | 19.05% | [6 empty] | Access/ROW/Easement | 4 | 2.703%
| Design/Plan Revision-Unspecified | 16 | 76.19% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 3 | 2.027%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 1 | 33.33% | 3 | 2.027% | 3668.49 | 74.3613 | 9 | 0.18243 | Differing Site Conditions (Except Utilities) | 3 | 2.027%
| Differing Site Conditions-Unspecified | 1 | 33.33% | [6 empty] | Procurement Issues | 3 | 2.027%
| Differing Site Conditions-Unsuitable Materials | 1 | 33.33% | [6 empty] | Start Date Delays | 2 | 1.351%
Environmental/Community Concerns | Vegetation Establishment | 6 | 85.71% | 7 | 4.73% | 0 | 0 | 104.2857 | 4.9324 | Survey/Test Issues | 1 | 0.6757%
| Wetland Discovery | 1 | 14.29%
Issues with Underground Utilities | Utilities not Relocated on Time | 8 | 30.77% | 26 | 17.57% | 5160.21 | 906.5234 | 133.44 | 23.4422 | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Utility Conflict | 18 | 69.23% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 28.57%
M&R/Replacement | M&R/Replacement-Damaged Objects | 1 | 16.67% | 6 | 4.054% | 96211.03 | 3900.4472 | 191.4 | 7.7595 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 28.57%
| M&R/Replacement-Unspecified | 5 | 83.33% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 9.524%
Natural Disaster | Natural Disaster-Hurricane | 18 | 100% | 18 | 12.16% | 0 | 0 | 25.3333 | 3.0811 | Utility – design, as-builts, etc. | 4.762%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 1 | 33.33% | 3 | 2.027% | 0 | 0 | 24 | 0.48649 | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 4.762%
| Power Supply Delays | 2 | 66.67% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 0%
Project Closeout Issues | Final Punchlist Extra Work | 2 | 9.524% | 21 | 14.19% | 0 | 0 | 22.7143 | 3.223 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 0%
| Scheduling Conflicts-Final Inspection/Punchlist | 19 | 90.48% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 11 | 100% | 11 | 7.432% | 26369.47 | 1959.893 | 34.125 | 2.5363 | Unspecified | 23.81%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 1 | 11.11% | 9 | 6.081% | 0 | 0 | 63.7778 | 3.8784
| Coordination Issues-DOT Personnel Unavailability | 1 | 11.11%
| Miscommunication (Construction Progress) | 1 | 11.11%
| Purposeful Limited Work Schedule | 2 | 22.22%
| Scheduling Conflicts-Inspection | 1 | 11.11%
| Work Restriction-Social Event | 2 | 22.22%
| Work Restriction-Unspecified | 1 | 11.11%
Start Date Delays | Delay in Contract Execution | 2 | 100% | 2 | 1.351% | 0 | 0 | 18.5 | 0.25
Survey/Test Issues | Survey Error | 1 | 100% | 1 | 0.6757% | 0 | 0 | 7 | 0.047297

## 8b. SA-Highway Safety
Table 1 Supplementary Agreements (Highway Safety) | [7 empty] | Table 2 Supplementary Agreements (Highway Safety) |  |  |  |  | Table 4 Supplementary Agreements (Highway Safety)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Contract | Corridor/Traffic Design | Environmental | Geotechnical | Hydraulics | Other | Pavement | Procurement | Roadway Alignment | Roadway Design | Safety | Schedule | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Property Owners Access | 2 | 50% | 4 | 3.39% | 12502.6875 | 423.8199 | Design/Plan Issues | 33 | 27.97% |  |  | Access/ROW/Easement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100%
| Traffic Access Point | 2 | 50% |  |  |  |  | Contract Amendment | 17 | 14.41% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 33.33% | 0% | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 100% | 3 | 2.542% | 9796.8 | 249.0712 | M&R/Replacement | 14 | 11.86% |  |  | Construction Method Revision | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 1 | 100% | 1 | 0.8475% | 8373 | 70.9576 | Differing Site Conditions (Except Utilities) | 12 | 10.17% |  |  | Contract Amendment | 0% | 0% | 0% | 0% | 11.76% | 0% | 11.76% | 0% | 0% | 17.65% | 0% | 0% | 17.65% | 11.76% | 5.882% | 23.53% | 100%
Contract Amendment | Line Item Omission | 17 | 100% | 17 | 14.41% | 14070.6259 | 2027.1241 | Issues with Underground Utilities | 11 | 9.322% |  |  | Design/Plan Issues | 0% | 3.03% | 0% | 6.061% | 12.12% | 0% | 24.24% | 0% | 3.03% | 18.18% | 0% | 3.03% | 9.091% | 3.03% | 6.061% | 12.12% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 9.091% | 33 | 27.97% | 8168.329 | 2284.3632 | Safety Concerns (Except Contaminated Soil) | 6 | 5.085% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 8.333% | 8.333% | 0% | 0% | 0% | 8.333% | 8.333% | 33.33% | 100%
| Construction Plans Error/Discrepancy | 1 | 3.03% |  |  |  |  | Stakeholder Request | 6 | 5.085% |  |  | Drainage Issues | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Elevation Difference with Existing Objects | 2 | 6.061% |  |  |  |  | Access/ROW/Easement | 4 | 3.39% |  |  | Environmental/Community Concerns | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Unspecified | 3 | 9.091% |  |  |  |  | Erosion Control Problems | 4 | 3.39% |  |  | Erosion Control Problems | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Achieve Higher/Acceptable Quality | 1 | 3.03% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 3 | 2.542% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 9.091% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 81.82% | 100%
| Design Revision-Future Maintenance Concerns | 1 | 3.03% |  |  |  |  | Quantities Overrun/Underrun | 3 | 2.542% |  |  | M&R/Replacement | 7.143% | 0% | 0% | 14.29% | 7.143% | 0% | 28.57% | 0% | 0% | 21.43% | 7.143% | 0% | 0% | 7.143% | 0% | 7.143% | 100%
| Design Revision-per Contractor Request | 4 | 12.12% |  |  |  |  | Construction Method Revision | 1 | 0.8475% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Unspecified | 15 | 45.45% |  |  |  |  | Drainage Issues | 1 | 0.8475% |  |  | Quantities Overrun/Underrun | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 66.67% | 0% | 0% | 0% | 100%
| Increased Traffic Volume | 1 | 3.03% |  |  |  |  | Environmental/Community Concerns | 1 | 0.8475% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 16.67% | 0% | 50% | 0% | 0% | 0% | 100%
| Scope Change | 2 | 6.061% |  |  |  |  | Procurement Issues | 1 | 0.8475% |  |  | Scheduling and Coordination Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 8.333% | 12 | 10.17% | 45820.2667 | 4659.6881 | Scheduling and Coordination Issues | 1 | 0.8475% |  |  | Stakeholder Request | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 100%
| Differing Site Conditions-Unspecified | 8 | 66.67% | [9 empty] | Grand Total | 0.8475% | 2.542% | 5.932% | 8.475% | 7.627% | 0.8475% | 11.86% | 1.695% | 1.695% | 12.71% | 1.695% | 0.8475% | 12.71% | 4.237% | 3.39% | 22.88% | 100%
| Differing Site Conditions-Unsuitable Materials | 2 | 16.67% |  |  |  |  | Table 3 Supplementary Agreements (Highway Safety)
| Slope Protection/Soil Stabilization | 1 | 8.333% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
Drainage Issues | Drainage Issues-Unspecified | 1 | 100% | 1 | 0.8475% | 18990.19 | 160.9338 | Utilities | 27 | 22.88% | 13451.15 | 3077.8055
Environmental/Community Concerns | Vegetation Establishment | 1 | 100% | 1 | 0.8475% | 3601.4 | 30.5203 | Roadway Design | 15 | 12.71% | 12235.376 | 1555.3444
Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 75% | 4 | 3.39% | 2821.865 | 95.6564 | TCP (Construction Phase) | 15 | 12.71% | 7073.65 | 899.1928
| Waste Site Erosion Control | 1 | 25% |  |  |  |  | Pavement | 14 | 11.86% | 6938.0067 | 823.1533
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 9.091% | 11 | 9.322% | 17511.2978 | 1632.4091 | Geotechnical | 10 | 8.475% | 58368.45 | 4946.4788
| Utility Conflict | 10 | 90.91% |  |  |  |  | Hydraulics | 9 | 7.627% | 9323.5489 | 711.1181
M&R/Replacement | M&R/Replacement-Unspecified | 14 | 100% | 14 | 11.86% | 16164.43 | 1917.8137 | Environmental | 7 | 5.932% | 43382.8657 | 2573.5598
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 100% | 1 | 0.8475% | 0 | 0 | Traffic Control Systems (Except Pavement Markings) | 5 | 4.237% | 16780.75 | 711.0487
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 3 | 100% | 3 | 2.542% | 2823.6667 | 71.7881 | Traffic Control Systems (pavement Markings) | 4 | 3.39% | -17674.8325 | -599.1469
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 1 | 16.67% | 6 | 5.085% | 20101.6833 | 1022.1195 | Corridor/Traffic Design | 3 | 2.542% | 87967 | 2236.4492
| Safety Concerns-Unspecified | 5 | 83.33% |  |  |  |  | Procurement | 2 | 1.695% | 8373 | 141.9153
Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 100% | 1 | 0.8475% | 37455 | 317.4153 | Roadway Alignment | 2 | 1.695% | 8734.5 | 148.0424
Stakeholder Request | DOT Request-Unspecified | 2 | 33.33% | 6 | 5.085% | 60929.9333 | 3098.1322 | Safety | 2 | 1.695% | 6815.275 | 115.5131
| Stakeholder Request-Future Development Concerns | 1 | 16.67% |  |  |  |  | Contract | 1 | 0.8475% | 61290.47 | 519.4108
| Stakeholder Request-Unspecified | 3 | 50% |  |  |  |  | Other | 1 | 0.8475% | 0 | 0
[8 empty] | Schedule | 1 | 0.8475% | 0 | 0

## 9a. Claim-Interstate
Table 1 Claims - Interstate | [9 empty] | Table 2 Claims - Interstate
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Railroad Right of Entry | 1 | 25% | 4 | 2.186% | 4430869 | 96849.5956 | 67.25 | 1.4699 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 25 | 13.66%
| ROW Acquisition Delays-Property Owners Agreement | 1 | 25% | [6 empty] | Design/Plan Issues | 23 | 12.57%
| ROW Acquisition Delays-Unspecified | 2 | 50% | [6 empty] | Natural Disaster | 21 | 11.48%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 13 | 100% | 13 | 7.104% | 16000 | 1136.612 | 45.0769 | 3.2022 | M&R/Replacement | 19 | 10.38%
Contract Amendment | Elimination of Contract Line Item | 2 | 15.38% | 13 | 7.104% | 145875.0229 | 10362.7065 | 75 | 5.3279 | Quantities Overrun/Underrun | 18 | 9.836%
| Error in Entering Time Extensions in HiCAMS | 2 | 15.38% | [6 empty] | Project Closeout Issues | 15 | 8.197%
| Line Item Omission | 4 | 30.77% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 13 | 7.104%
| Settlement and Release Agreement | 3 | 23.08% | [6 empty] | Contract Amendment | 13 | 7.104%
| Unavailability of Funds/Cash Flow Considerations | 2 | 15.38% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 7 | 3.825%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 5 | 71.43% | 7 | 3.825% | 0 | 0 | 47.7143 | 1.8251 | Procurement Issues | 7 | 3.825%
| Negotiation Delays | 2 | 28.57% | [6 empty] | Issues with Underground Utilities | 6 | 3.279%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 13.04% | 23 | 12.57% | 43160.0382 | 5424.4857 | 46.75 | 5.8757 | Access/ROW/Easement | 4 | 2.186%
| Design/Plan Error-Unspecified | 7 | 30.43% | [6 empty] | Differing Site Conditions (Except Utilities) | 4 | 2.186%
| Design/Plan Revision-Unspecified | 12 | 52.17% | [6 empty] | Environmental/Community Concerns | 3 | 1.639%
| Increased Traffic Volume | 1 | 4.348% | [6 empty] | Permit | 1 | 0.5464%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 4 | 100% | 4 | 2.186% | 0 | 0 | 22.25 | 0.48634
Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 33.33% | 3 | 1.639% | 15778.545 | 258.6647 | 30 | 0.4918 | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Historical Site | 1 | 33.33% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 26.09%
| Vegetation Establishment | 1 | 33.33% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 17.39%
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 33.33% | 6 | 3.279% | 173897.54 | 5701.5587 | 214.6667 | 7.0383 | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 13.04%
| Utility Conflict | 4 | 66.67% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 13.04%
M&R/Replacement | M&R/Replacement-Unspecified | 16 | 84.21% | 19 | 10.38% | 101177.8043 | 10504.7994 | 56.2857 | 5.8439 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 8.696%
| Vehicular Accident | 3 | 15.79% | [6 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 4.348%
Natural Disaster | Natural Disaster-Hurricane | 21 | 100% | 21 | 11.48% | 44523.09 | 5109.207 | 31.9048 | 3.6612 | Environmental – vegetation plans, habitat mitigation, etc. | 4.348%
Permit | Permit Acquisition Waiting Period | 1 | 100% | 1 | 0.5464% | 0 | 0 | 40 | 0.21858 | Utility – design, as-builts, etc. | 0%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 14.29% | 7 | 3.825% | 5142.2 | 196.6962 | 203.3333 | 7.7778 | Unspecified | 13.04%
| Material Fabrication Delay | 1 | 14.29%
| Power Supply Delays | 4 | 57.14%
| Unavailability of Materials/Material Shortage | 1 | 14.29%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 6.667% | 15 | 8.197% | 0 | 0 | 28.4 | 2.3279
| Scheduling Conflicts-Final Inspection/Punchlist | 14 | 93.33%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 18 | 100% | 18 | 9.836% | 124312.6562 | 12227.4744 | 44.4545 | 4.3726
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 5 | 20% | 25 | 13.66% | 547.44 | 74.7869 | 61.7083 | 8.4301
| Purposeful Limited Work Schedule | 5 | 20%
| Scheduling Conflicts-Inspection | 1 | 4%
| Work Out of Sequence | 2 | 8%
| Work Restriction-Social Event | 8 | 32%
| Work Restriction-Unspecified | 4 | 16%
Start Date Delays | Delay in Contract Execution | 2 | 100% | 2 | 1.093% | 0 | 0 | 46.5 | 0.5082
Survey/Test Issues | Survey Error | 2 | 100% | 2 | 1.093% | 13851.33 | 151.3807 | 9 | 0.098361
Start Date Delays | 2 | 0.010929
Survey/Test Issues | 2 | 0.010929

## 9b. SA-Interstate
Table 1 Supplementary Agreements (Interstate) | [7 empty] | Table 2 Supplementary Agreements (Interstate) |  |  |  |  | Table 4 Supplementary Agreements (Interstate)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Access/ROW/Easement | Contract | Corridor/Traffic Design | Environmental | Geotechnical | Hydraulics | Other | Pavement | Procurement | Railroad | Roadway Alignment | Roadway Design | Safety | Schedule | Structural | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 33.33% | 3 | 1.181% | 7518.3167 | 88.799 | Design/Plan Issues | 69 | 27.17% |  |  | Access/ROW/Easement | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 100%
| Railroad Right of Entry Delays | 1 | 33.33% |  |  |  |  | M&R/Replacement | 32 | 12.6% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 5% | 0% | 15% | 5% | 0% | 15% | 0% | 0% | 0% | 10% | 0% | 0% | 5% | 10% | 15% | 0% | 20% | 100%
| Traffic Access Point | 1 | 33.33% |  |  |  |  | Contract Amendment | 30 | 11.81% |  |  | Construction Method Revision | 0% | 0% | 0% | 0% | 11.11% | 0% | 0% | 0% | 11.11% | 0% | 0% | 0% | 0% | 11.11% | 33.33% | 22.22% | 0% | 0% | 11.11% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 20 | 100% | 20 | 7.874% | 43401.4511 | 3417.4371 | Stakeholder Request | 26 | 10.24% |  |  | Contract Amendment | 0% | 10% | 3.333% | 3.333% | 3.333% | 6.667% | 3.333% | 6.667% | 3.333% | 0% | 0% | 10% | 0% | 3.333% | 3.333% | 10% | 10% | 20% | 3.333% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 9 | 100% | 9 | 3.543% | 720476.2 | 25528.6843 | Safety Concerns (Except Contaminated Soil) | 25 | 9.843% |  |  | Design/Plan Issues | 1.449% | 1.449% | 10.14% | 0% | 8.696% | 8.696% | 1.449% | 15.94% | 0% | 1.449% | 1.449% | 11.59% | 1.449% | 0% | 7.246% | 4.348% | 14.49% | 5.797% | 4.348% | 100%
Contract Amendment | Change in Contract Provisions | 1 | 3.333% | 30 | 11.81% | 34387.6804 | 4061.5371 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 20 | 7.874% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 0% | 7.143% | 28.57% | 14.29% | 0% | 7.143% | 0% | 0% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 35.71% | 100%
| Elimination of Contract Line Item | 2 | 6.667% |  |  |  |  | Differing Site Conditions (Except Utilities) | 14 | 5.512% |  |  | Drainage Issues | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Issues with Previous SA | 2 | 6.667% |  |  |  |  | Construction Method Revision | 9 | 3.543% |  |  | Environmental/Community Concerns | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Line Item Omission | 19 | 63.33% |  |  |  |  | Drainage Issues | 7 | 2.756% |  |  | Erosion Control Problems | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Mitigation of Potential Risk | 1 | 3.333% |  |  |  |  | Quantities Overrun/Underrun | 7 | 2.756% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
| Revise Measurement and Payment Method | 1 | 3.333% |  |  |  |  | Erosion Control Problems | 5 | 1.969% |  |  | M&R/Replacement | 0% | 0% | 0% | 0% | 12.5% | 15.62% | 0% | 28.12% | 0% | 0% | 0% | 6.25% | 3.125% | 0% | 21.88% | 0% | 12.5% | 0% | 0% | 100%
| Risk Management | 1 | 3.333% |  |  |  |  | Access/ROW/Easement | 3 | 1.181% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Settlement and Release Agreement | 1 | 3.333% |  |  |  |  | Environmental/Community Concerns | 2 | 0.7874% |  |  | Quantities Overrun/Underrun | 0% | 0% | 0% | 0% | 14.29% | 14.29% | 0% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 14.29% | 14.29% | 0% | 0% | 100%
| Unavailability of Funds/Cash Flow Considerations | 2 | 6.667% |  |  |  |  | Issues with Underground Utilities | 2 | 0.7874% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 8% | 0% | 0% | 4% | 0% | 8% | 0% | 0% | 4% | 12% | 20% | 0% | 0% | 28% | 12% | 4% | 0% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 8 | 11.59% | 69 | 27.17% | 67008.6668 | 18203.1418 | Procurement Issues | 1 | 0.3937% |  |  | Scheduling and Coordination Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Elevation Difference with Existing Objects | 3 | 4.348% |  |  |  |  | Scheduling and Coordination Issues | 1 | 0.3937% |  |  | Stakeholder Request | 0% | 0% | 19.23% | 7.692% | 0% | 3.846% | 0% | 23.08% | 0% | 0% | 0% | 15.38% | 0% | 0% | 0% | 0% | 19.23% | 3.846% | 7.692% | 100%
| Design Error-Unspecified | 3 | 4.348% |  |  |  |  | Survey/Test Issues | 1 | 0.3937% |  |  | Survey/Test Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Achieve Higher/Acceptable Quality | 3 | 4.348% | [9 empty] | Grand Total | 1.181% | 1.575% | 6.693% | 3.937% | 7.874% | 10.24% | 0.7874% | 14.17% | 1.181% | 0.3937% | 1.181% | 8.661% | 2.756% | 1.181% | 7.48% | 7.087% | 11.42% | 5.118% | 7.087% | 100%
| Design Revision-Fix Impacts of Previous Revisions | 5 | 7.246% |  |  |  |  | Table 3 Supplementary Agreements (Interstate)
| Design Revision-Future Maintenance Concerns | 2 | 2.899% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Design Revision-per Contractor Request | 2 | 2.899% |  |  |  |  | Pavement | 36 | 14.17% | 119816.4685 | 16981.8617
| Design Revision-Uniformity with Adjacent Projects/Objects | 4 | 5.797% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 29 | 11.42% | 43860.8386 | 5007.7335
| Design Revision-Unspecified | 28 | 40.58% |  |  |  |  | Hydraulics | 26 | 10.24% | 35973.6577 | 3682.3429
| Design Revision-Value Engineering Proposal | 5 | 7.246% |  |  |  |  | Roadway Design | 22 | 8.661% | 41610.6557 | 3604.0725
| Incomplete Design | 1 | 1.449% |  |  |  |  | Geotechnical | 20 | 7.874% | -115143.5526 | -9066.4215
| Increased Traffic Volume | 2 | 2.899% |  |  |  |  | Structural | 19 | 7.48% | 64977.0437 | 4860.4875
| Scope Change | 3 | 4.348% |  |  |  |  | TCP (Construction Phase) | 18 | 7.087% | 32601.76 | 2310.3609
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 1 | 7.143% | 14 | 5.512% | 41633.19 | 2294.7428 | Utilities | 18 | 7.087% | 397953.2867 | 28201.414
| Differing Site Conditions-Extra Work from Previous Projects | 1 | 7.143% |  |  |  |  | Corridor/Traffic Design | 17 | 6.693% | 1032407.9265 | 69098.1683
| Differing Site Conditions-Not Shown in Construction Plans | 1 | 7.143% |  |  |  |  | Traffic Control Systems (pavement Markings) | 13 | 5.118% | 28628.0246 | 1465.2139
| Differing Site Conditions-Unspecified | 7 | 50% |  |  |  |  | Environmental | 10 | 3.937% | 33126.463 | 1304.1915
| Differing Site Conditions-Unsuitable Materials | 3 | 21.43% |  |  |  |  | Safety | 7 | 2.756% | 4455.06 | 122.7772
| Slope Protection/Soil Stabilization | 1 | 7.143% |  |  |  |  | Contract | 4 | 1.575% | 5482.4933 | 86.3385
Drainage Issues | Drainage Issues-Unspecified | 7 | 100% | 7 | 2.756% | 24310.6586 | 669.9788 | Access/ROW/Easement | 3 | 1.181% | 496998.3167 | 5870.0589
Environmental/Community Concerns | Construction Impacts | 1 | 50% | 2 | 0.7874% | 363976.375 | 2865.9557 | Procurement | 3 | 1.181% | -156475 | -1848.1299
| Natural Disaster (Drought) | 1 | 50% |  |  |  |  | Roadway Alignment | 3 | 1.181% | 9675 | 114.2717
Erosion Control Problems | Erosion Control Problems-Unspecified | 5 | 100% | 5 | 1.969% | 52984.46 | 1043.0012 | Schedule | 3 | 1.181% | 10 | 0.11811
Issues with Underground Utilities | Utility Conflict | 2 | 100% | 2 | 0.7874% | 340905 | 2684.2913 | Other | 2 | 0.7874% | 796851.48 | 6274.4211
M&R/Replacement | Damaged Objects | 1 | 3.125% | 32 | 12.6% | 85994.8916 | 10834.0021 | Railroad | 1 | 0.3937% | 40124.43 | 157.9702
| M&R/Replacement-Unspecified | 28 | 87.5%
| Vehicular Accident | 3 | 9.375%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 100% | 1 | 0.3937% | 0 | 0
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 7 | 100% | 7 | 2.756% | 42956.3771 | 1183.8372
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 4% | 25 | 9.843% | 69669.3304 | 6857.2176
| Safety Concerns-Unspecified | 20 | 80%
| Travelers/Public Safety | 4 | 16%
Scheduling and Coordination Issues | Early Project Completion | 1 | 100% | 1 | 0.3937% | 10 | 0.03937
Stakeholder Request | DOT Request-Unspecified | 17 | 65.38% | 26 | 10.24% | 611870.6408 | 62632.4278
| Stakeholder Request-Future Development Concerns | 3 | 11.54%
| Stakeholder Request-Unspecified | 6 | 23.08%
Survey/Test Issues | Survey Error-Unspecified | 1 | 100% | 1 | 0.3937% | 1585.23 | 6.2411

## 10a. Claim-Other
Table 1 Claims - Other | [9 empty] | Table 2 Claims - Other
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 2 | 100% | 2 | 3.774% | 0 | 0 | 153.5 | 5.7925 | Issues with Underground Utilities | 7 | 13.21%
Contract Amendment | Contract Error | 1 | 25% | 4 | 7.547% | 0 | 0 | 198.75 | 15 | Project Closeout Issues | 7 | 13.21%
| Error in Entering Time Extensions in HiCAMS | 3 | 75% | [6 empty] | Design/Plan Issues | 6 | 11.32%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 3 | 75% | 4 | 7.547% | 0 | 0 | 22.75 | 1.717 | Start Date Delays | 6 | 11.32%
| Untimely Review of Approvals | 1 | 25% | [6 empty] | Contract Amendment | 4 | 7.547%
Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 33.33% | 6 | 11.32% | 1916.875 | 217.0047 | 8 | 0.90566 | Design Approval Waiting Period/Indecision/Negotiation | 4 | 7.547%
| Design/Plan Revision-Unspecified | 4 | 66.67% | [6 empty] | Environmental/Community Concerns | 3 | 5.66%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 50% | 2 | 3.774% | 0 | 0 | 12 | 0.45283 | Natural Disaster | 3 | 5.66%
| Differing Site Conditions-Unsuitable Materials | 1 | 50% | [6 empty] | Procurement Issues | 3 | 5.66%
Environmental/Community Concerns | Vegetation Establishment | 3 | 100% | 3 | 5.66% | 0 | 0 | 36.3333 | 2.0566 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 5.66%
Issues with Underground Utilities | Utility Conflict | 7 | 100% | 7 | 13.21% | 0 | 0 | 45 | 5.9434 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 2 | 3.774%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 3.774% | 4576.005 | 172.6794 | - | - | Differing Site Conditions (Except Utilities) | 2 | 3.774%
Natural Disaster | Natural Disaster-Drought | 1 | 33.33% | 3 | 5.66% | 0 | 0 | 21 | 1.1887 | M&R/Replacement | 2 | 3.774%
| natural Disaster-Flood | 1 | 33.33% | [6 empty] | Other | 1 | 1.887%
| Natural Disaster-Hurricane | 1 | 33.33%
Other | Covid 19 Impact | 1 | 100% | 1 | 1.887% | 0 | 0 | 269 | 5.0755 | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 33.33% | 3 | 5.66% | 0 | 0 | 48.3333 | 2.7358 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 16.67%
| Unavailability of Materials/Material Shortage | 2 | 66.67% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 16.67%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 7 | 100% | 7 | 13.21% | 0 | 0 | 13.2857 | 1.7547 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 16.67%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 1 | 33.33% | 3 | 5.66% | 0 | 0 | 76.3333 | 4.3208 | Utility – design, as-builts, etc. | 16.67%
| Coordination Issues-DOT Personnel Unavailability | 1 | 33.33% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 16.67%
| Work Restriction-Social Event | 1 | 33.33% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
Start Date Delays | Delay in Contract Execution | 4 | 66.67% | 6 | 11.32% | 0 | 0 | 17.6667 | 2 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
| Delay in Preconstruction Meeting | 2 | 33.33% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
[10 empty] | Unspecified | 16.67%

## 10b. SA-Other
Table 1 Supplementary Agreements (Other) | [7 empty] | Table 2 Supplementary Agreements (Other) |  |  |  |  | Table 4 Supplementary Agreements (Other)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Environmental | Geotechnical | Hydraulics | Other | Pavement | Procurement | Roadway Design | Structural | TCP (Construction Phase) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Providing Access to Site | 1 | 100% | 1 | 2.703% | 20000 | 540.5405 | Design/Plan Issues | 8 | 21.62% |  |  | Access/ROW/Easement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100%
Contract Amendment | Line Item Omission | 7 | 100% | 7 | 18.92% | 3018.2857 | 571.027 | Contract Amendment | 7 | 18.92% |  |  | Contract Amendment | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 57.14% | 14.29% | 0% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 12.5% | 8 | 21.62% | 9068.6063 | 1960.7797 | Differing Site Conditions (Except Utilities) | 7 | 18.92% |  |  | Design/Plan Issues | 37.5% | 0% | 12.5% | 0% | 0% | 0% | 25% | 12.5% | 0% | 12.5% | 0% | 100%
| Construction Plans Error/Discrepancy | 1 | 12.5% |  |  |  |  | Procurement Issues | 3 | 8.108% |  |  | Differing Site Conditions (Except Utilities) | 0% | 42.86% | 0% | 14.29% | 28.57% | 0% | 14.29% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Achieve Higher/Acceptable Quality | 2 | 25% |  |  |  |  | Quantities Overrun/Underrun | 3 | 8.108% |  |  | Drainage Issues | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 12.5% |  |  |  |  | Erosion Control Problems | 2 | 5.405% |  |  | Environmental/Community Concerns | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Unspecified | 3 | 37.5% |  |  |  |  | Issues with Underground Utilities | 2 | 5.405% |  |  | Erosion Control Problems | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 1 | 14.29% | 7 | 18.92% | -1863.7743 | -352.6059 | Access/ROW/Easement | 1 | 2.703% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
| Differing Site Conditions-Unspecified | 3 | 42.86% |  |  |  |  | Drainage Issues | 1 | 2.703% |  |  | M&R/Replacement | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Unsuitable Materials | 2 | 28.57% |  |  |  |  | Environmental/Community Concerns | 1 | 2.703% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100%
| Slope Protection/Soil Stabilization | 1 | 14.29% |  |  |  |  | M&R/Replacement | 1 | 2.703% |  |  | Quantities Overrun/Underrun | 33.33% | 0% | 0% | 0% | 33.33% | 0% | 33.33% | 0% | 0% | 0% | 0% | 100%
Drainage Issues | Drainage Issues-Unspecified | 1 | 100% | 1 | 2.703% | 6100 | 164.8649 | Stakeholder Request | 1 | 2.703% |  |  | Stakeholder Request | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Environmental/Community Concerns | Environmental Concerns-Unspecified | 1 | 100% | 1 | 2.703% | 15584.25 | 421.1959 | [5 empty] | Grand Total | 27.03% | 10.81% | 5.405% | 2.703% | 8.108% | 8.108% | 10.81% | 2.703% | 13.51% | 5.405% | 5.405% | 100%
Erosion Control Problems | Erosion Control Problems-Unspecified | 2 | 100% | 2 | 5.405% | 3682 | 199.027 | Table 3 Supplementary Agreements (Other)
Issues with Underground Utilities | Utility Conflict | 2 | 100% | 2 | 5.405% | 2844.5 | 153.7568 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 2.703% | 16968.2 | 458.6 | Environmental | 10 | 27.03% | 6827.025 | 1845.1419
Procurement Issues | Unavailability of Materials/Material Shortage | 3 | 100% | 3 | 8.108% | 6148.375 | 498.5169 | TCP (Construction Phase) | 5 | 13.51% | 6165.6 | 833.1892
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 3 | 100% | 3 | 8.108% | 4254.3333 | 344.9459 | Geotechnical | 4 | 10.81% | 6777.405 | 732.6924
Stakeholder Request | DOT Request-Unspecified | 1 | 100% | 1 | 2.703% | 794 | 21.4595 | Roadway Design | 4 | 10.81% | -4460.285 | -482.193
[8 empty] | Pavement | 3 | 8.108% | 2933.3333 | 237.8378
[8 empty] | Procurement | 3 | 8.108% | 6148.375 | 498.5169
[8 empty] | Hydraulics | 2 | 5.405% | 5030 | 271.8919
[8 empty] | Traffic Control Systems (pavement Markings) | 2 | 5.405% | 4240.675 | 229.2257
[8 empty] | Utilities | 2 | 5.405% | 2844.5 | 153.7568
[8 empty] | Other | 1 | 2.703% | 1528.3 | 41.3054
[8 empty] | Structural | 1 | 2.703% | 22967.5 | 620.7432

## 11a. Claim-Rail
Table 1 Claims - Rail | [9 empty] | Table 2 Claims - Rail
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Insufficient Right of Entry | 1 | 14.29% | 7 | 10% | 369355.015 | 36935.5015 | 117 | 11.7 | Issues with Underground Utilities | 26 | 37.14%
| Railroad Right of Entry | 6 | 85.71% | [6 empty] | Quantities Overrun/Underrun | 8 | 11.43%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 20% | 5 | 7.143% | 124500 | 8892.8571 | 132 | 9.4286 | Access/ROW/Easement | 7 | 10%
| Constructability Issues-Seasonal Limitations (Weather) | 4 | 80% | [6 empty] | Contract Amendment | 6 | 8.571%
Contract Amendment | Contract Error | 3 | 50% | 6 | 8.571% | 4542.235 | 389.3344 | 72.75 | 6.2357 | Design/Plan Issues | 6 | 8.571%
| Error in Entering Time Extensions in HiCAMS | 1 | 16.67% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 5 | 7.143%
| Line Item Omission | 1 | 16.67% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 4 | 5.714%
| Unavailability of Funds/Cash Flow Considerations | 1 | 16.67% | [6 empty] | Other | 3 | 4.286%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 100% | 1 | 1.429% | 20105.23 | 287.2176 | 21 | 0.3 | M&R/Replacement | 2 | 2.857%
Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 33.33% | 6 | 8.571% | 116321.4 | 9970.4057 | 49.6 | 4.2514 | Design Approval Waiting Period/Indecision/Negotiation | 1 | 1.429%
| Design/Plan Revision-Unspecified | 4 | 66.67% | [6 empty] | Procurement Issues | 1 | 1.429%
Issues with Underground Utilities | Utilities not Relocated on Time | 4 | 15.38% | 26 | 37.14% | 350556.8563 | 130206.8323 | 100.0909 | 37.1766 | Project Closeout Issues | 1 | 1.429%
| Utility Conflict | 22 | 84.62%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 2.857% | 143896.62 | 4111.332 | 7 | 0.2 | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
Other | Misinterpretation of Plans | 1 | 33.33% | 3 | 4.286% | 144300 | 6184.2857 | 226.5 | 9.7071 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 50%
| Unavailability of Labor | 2 | 66.67% | [6 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 16.67%
Procurement Issues | Power Supply Delays | 1 | 100% | 1 | 1.429% | 0 | 0 | 43 | 0.61429 | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 100% | 1 | 1.429% | 0 | 0 | 45 | 0.64286 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 8 | 100% | 8 | 11.43% | 276266.645 | 31573.3309 | 15.5 | 1.7714 | Structure Design – bridge superstructure, bridge substructure, etc. | 0%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 1 | 25% | 4 | 5.714% | 33838 | 1933.6 | 82 | 4.6857 | Utility – design, as-builts, etc. | 0%
| Coordination Issues-Unspecified | 1 | 25% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
| Waiting for Other Entities to Perform Work | 2 | 50% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Unspecified | 33.33%

## 11b. SA-Rail
Table 1 Supplementary Agreements (Rail) | [7 empty] | Table 2 Supplementary Agreements (Rail) |  |  |  |  | Table 4 Supplementary Agreements (Rail)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Access/ROW/Easement | Corridor/Traffic Design | Environmental | Finishing and Interior Work | Geotechnical | Hydraulics | Pavement | Procurement | Railroad | Roadway Design | Safety | Security/Protection | Structural | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Insufficient ROW | 2 | 66.67% | 3 | 4.839% | 9118.39 | 441.2124 | Survey/Test Issues | 2 | 100% |  |  | Access/ROW/Easement | 66.67% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Providing Access to Site | 1 | 33.33% |  |  |  |  | Stakeholder Request | 5 | 71.43% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 50% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 4 | 66.67% | 6 | 10.17% | 14540.3783 | 1478.6825 | Design/Plan Issues | 13 | 28.26% |  |  | Contract Amendment | 28.57% | 0% | 0% | 0% | 0% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 14.29% | 0% | 14.29% | 100%
| Constructability Issues-Unspecified | 2 | 33.33% |  |  |  |  | Scheduling and Coordination Issues | 2 | 22.22% |  |  | Design/Plan Issues | 0% | 0% | 7.692% | 15.38% | 7.692% | 0% | 7.692% | 7.692% | 15.38% | 7.692% | 0% | 0% | 15.38% | 7.692% | 0% | 7.692% | 0% | 100%
Contract Amendment | Contingency Item | 1 | 14.29% | 7 | 13.21% | 2321.24 | 306.5789 | Differing Site Conditions (Except Utilities) | 7 | 21.21% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 14.29% | 0% | 14.29% | 57.14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 100%
| Line Item Omission | 6 | 85.71% |  |  |  |  | Procurement Issues | 3 | 20% |  |  | Erosion Control Problems | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 23.08% | 13 | 28.26% | 17695.2185 | 5000.8226 | Safety Concerns (Except Contaminated Soil) | 2 | 18.18% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 100%
| Construction Plans Error/Discrepancy | 1 | 7.692% |  |  |  |  | Other | 3 | 16.67% |  |  | M&R/Replacement | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100%
| Design Error-Unspecified | 3 | 23.08% |  |  |  |  | Contract Amendment | 7 | 13.21% |  |  | Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 33.33% | 33.33% | 0% | 0% | 0% | 100%
| Design Revision-per Contractor Request | 1 | 7.692% |  |  |  |  | Issues with Underground Utilities | 3 | 13.04% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Unspecified | 5 | 38.46% |  |  |  |  | Erosion Control Problems | 3 | 11.54% |  |  | Quantities Overrun/Underrun | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 3 | 42.86% | 7 | 21.21% | 14313.6571 | 3036.2303 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 6 | 10.17% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Unspecified | 4 | 57.14% |  |  |  |  | M&R/Replacement | 2 | 10% |  |  | Scheduling and Coordination Issues | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 100% | 3 | 11.54% | 9193.3667 | 1060.7731 | Quantities Overrun/Underrun | 1 | 8.333% |  |  | Stakeholder Request | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 20% | 20% | 0% | 20% | 100%
Issues with Underground Utilities | Utility Conflict | 3 | 100% | 3 | 13.04% | 15075.5 | 1966.3696 | [5 empty] | Survey/Test Issues | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 10% | 20269 | 2026.9 | Table 3 Supplementary Agreements (Rail) |  |  |  |  | Grand Total | 8.065% | 1.613% | 8.065% | 3.226% | 6.452% | 14.52% | 1.613% | 8.065% | 4.839% | 1.613% | 3.226% | 1.613% | 4.839% | 6.452% | 8.065% | 1.613% | 16.13% | 100%
Other | Contractor Error | 1 | 33.33% | 3 | 16.67% | 17936.31 | 2989.385 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Site Security | 2 | 66.67% |  |  |  |  | Utilities | 10 | 16.13% | 18846.808 | 3039.8077
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 33.33% | 3 | 20% | 10636 | 2127.2 | Hydraulics | 9 | 14.52% | 14102.4267 | 2047.1265
| Unavailability of Materials/Material Shortage | 2 | 66.67% |  |  |  |  | Access/ROW/Easement | 5 | 8.065% | 17734.12 | 1430.171
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 100% | 1 | 8.333% | 21600 | 1800 | Environmental | 5 | 8.065% | 8468.658 | 682.9563
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 2 | 100% | 2 | 18.18% | 43208 | 7856 | Procurement | 5 | 8.065% | 20859.2 | 1682.1935
Scheduling and Coordination Issues | Availability Date Delays | 2 | 100% | 2 | 22.22% | 69903.3 | 15534.0667 | Traffic Control Systems (Except Pavement Markings) | 5 | 8.065% | 2494.574 | 201.1753
Stakeholder Request | DOT Request-Unspecified | 2 | 40% | 5 | 71.43% | 14913.888 | 10652.7771 | Geotechnical | 4 | 6.452% | 13709 | 884.4516
| Stakeholder Request-Unspecified | 3 | 60% |  |  |  |  | TCP (Construction Phase) | 4 | 6.452% | 5728 | 369.5484
Survey/Test Issues | Additional Survey/Test Required | 2 | 100% | 2 | 100% | 7851.4 | 7851.4 | Railroad | 3 | 4.839% | 4497.3333 | 217.6129
[8 empty] | Structural | 3 | 4.839% | 28825.03 | 1394.7595
[8 empty] | Finishing and Interior Work | 2 | 3.226% | 65581.425 | 2115.5298
[8 empty] | Safety | 2 | 3.226% | 43208 | 1393.8065
[8 empty] | Corridor/Traffic Design | 1 | 1.613% | 12032.67 | 194.0753
[8 empty] | Pavement | 1 | 1.613% | -32397.5 | -522.5403
[8 empty] | Roadway Design | 1 | 1.613% | 1000 | 16.129
[8 empty] | Security/Protection | 1 | 1.613% | 58041.64 | 936.1555
[8 empty] | Traffic Control Systems (pavement Markings) | 1 | 1.613% | 1092.5 | 17.621

## 12a. Claim-Railroad - HW Crossi
Table 1 Claims - Railroad - Highway Crossings | [9 empty] | Table 2 Claims - Railroad - Highway Crossings
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 33.33% | 3 | 42.86% | 0 | 0 | 25.3333 | 10.8571 | Issues with Underground Utilities | 3 | 42.86%
| Utility Conflict | 2 | 66.67% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 42.86%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 100% | 1 | 14.29% | 0 | 0 | 12 | 1.7143 | Project Closeout Issues | 1 | 14.29%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 1 | 33.33% | 3 | 42.86% | 0 | 0 | 32 | 13.7143
| Work Restriction-Social Event | 1 | 33.33% | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Work Restriction-Unspecified | 1 | 33.33% | [6 empty] | No Design/Plan Issues

## 12b. SA-Railroad - HW Crossings
Table 1 Supplementary Agreements (Railroad - Highway Crossings) | [7 empty] | Table 2 Supplementary Agreements (Railroad - Highway Crossings) |  |  |  |  | Table 4 Supplementary Agreements (Railroad - Highway Crossings)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Access/ROW/Easement | Environmental | Geotechnical | Hydraulics | Pavement | Procurement | Roadway Design | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Insufficient ROW | 1 | 100% | 1 | 4.545% | 850 | 38.6364 | Design/Plan Issues | 8 | 36.36% |  |  | Access/ROW/Easement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 25% | 4 | 18.18% | 23587.25 | 4288.5909 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 4 | 18.18% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 0% | 0% | 75% | 0% | 0% | 0% | 0% | 25% | 0% | 100%
| Constructability Issues-Unspecified | 3 | 75% |  |  |  |  | Contract Amendment | 4 | 18.18% |  |  | Contract Amendment | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 25% | 25% | 25% | 100%
Contract Amendment | Line Item Omission | 4 | 100% | 4 | 18.18% | 1538.3425 | 279.6986 | Differing Site Conditions (Except Utilities) | 2 | 9.091% |  |  | Design/Plan Issues | 0% | 0% | 0% | 12.5% | 37.5% | 12.5% | 12.5% | 0% | 0% | 25% | 0% | 100%
Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 12.5% | 8 | 36.36% | 4257.472 | 1548.1716 | Safety Concerns (Except Contaminated Soil) | 2 | 9.091% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Unspecified | 2 | 25% |  |  |  |  | Access/ROW/Easement | 1 | 4.545% |  |  | Erosion Control Problems | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Unspecified | 5 | 62.5% |  |  |  |  | Erosion Control Problems | 1 | 4.545% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 100% | 2 | 9.091% | 43404 | 3945.8182 | [5 empty] | Grand Total | 4.545% | 4.545% | 9.091% | 9.091% | 27.27% | 4.545% | 9.091% | 4.545% | 4.545% | 18.18% | 4.545% | 100%
Erosion Control Problems | Erosion Control Problems-Unspecified | 1 | 100% | 1 | 4.545% | 222.2 | 10.1 | Table 3 Supplementary Agreements (Railroad - Highway Crossings)
Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 2 | 100% | 2 | 9.091% | 8653.445 | 786.6768 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
[8 empty] | Pavement | 6 | 27.27% | 23881.125 | 6513.0341
[8 empty] | Traffic Control Systems (pavement Markings) | 4 | 18.18% | 911.7075 | 165.765
[8 empty] | Geotechnical | 2 | 9.091% | 43404 | 3945.8182
[8 empty] | Hydraulics | 2 | 9.091% | 9760.07 | 887.2791
[8 empty] | Roadway Design | 2 | 9.091% | 2375 | 215.9091
[8 empty] | Access/ROW/Easement | 1 | 4.545% | 850 | 38.6364
[8 empty] | Environmental | 1 | 4.545% | 222.2 | 10.1
[8 empty] | Procurement | 1 | 4.545% | 0 | 0
[8 empty] | TCP (Construction Phase) | 1 | 4.545% | 16116.75 | 732.5795
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 1 | 4.545% | -1161.6 | -52.8
[8 empty] | Utilities | 1 | 4.545% | 700 | 31.8182

## 13a. Claim-Rest Area
Table 1 Claims - Rest Area | [9 empty] | Table 2 Claims - Rest Area
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 100% | 1 | 2.703% | 0 | 0 | 3 | 0.081081 | Design/Plan Issues | 8 | 21.62%
Contract Amendment | Error in Entering Time Extensions in HiCAMS | 3 | 60% | 5 | 13.51% | 220000 | 29729.7297 | 22 | 2.973 | Contract Amendment | 5 | 13.51%
| Line Item Omission | 1 | 20% | [6 empty] | Natural Disaster | 4 | 10.81%
| Settlement and Release Agreement | 1 | 20% | [6 empty] | Procurement Issues | 4 | 10.81%
Design/Plan Issues | Design/Plan Error-Unspecified | 1 | 12.5% | 8 | 21.62% | 0 | 0 | 45.625 | 9.8649 | Start Date Delays | 4 | 10.81%
| Design/Plan Revision-Unspecified | 7 | 87.5% | [6 empty] | Project Closeout Issues | 3 | 8.108%
Environmental/Community Concerns | Erosion Control Problems | 1 | 50% | 2 | 5.405% | 0 | 0 | 114 | 6.1622 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 8.108%
| Vegetation Establishment | 1 | 50% | [6 empty] | Environmental/Community Concerns | 2 | 5.405%
Issues with Underground Utilities | Utility Conflict | 1 | 100% | 1 | 2.703% | 1881.07 | 50.8397 | 1 | 0.027027 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 1 | 2.703%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 2.703% | 0 | 0 | 65 | 1.7568 | Issues with Underground Utilities | 1 | 2.703%
Natural Disaster | Natural Disaster-Hurricane | 4 | 100% | 4 | 10.81% | 0 | 0 | 10.5 | 1.1351 | M&R/Replacement | 1 | 2.703%
Permit | Insufficient Permit | 1 | 100% | 1 | 2.703% | 0 | 0 | 10 | 0.27027 | Permit | 1 | 2.703%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 25% | 4 | 10.81% | 9928.165 | 1073.3151 | 65.3333 | 7.0631
| Material Cost Fluctuation | 1 | 25% | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Unavailability of Materials/Material Shortage | 1 | 25% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 25%
| Wrong Order Placement | 1 | 25% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 25%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 3 | 100% | 3 | 8.108% | 0 | 0 | 16.6667 | 1.3514 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 12.5%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-Unspecified | 2 | 66.67% | 3 | 8.108% | 0 | 0 | 11 | 0.89189 | Utility – design, as-builts, etc. | 12.5%
| Miscommunication (Construction Progress) | 1 | 33.33% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
Start Date Delays | Delay in Contract Execution | 2 | 50% | 4 | 10.81% | 0 | 0 | 18.5 | 2 | Structure Design – bridge superstructure, bridge substructure, etc. | 0%
| Delay in Project Award | 1 | 25% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
| Start Date Delays-Unspecified | 1 | 25% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Unspecified | 25%

## 13b. SA-Rest Area
Table 1 Supplementary Agreements (Rest Area) | [7 empty] | Table 2 Supplementary Agreements (Rest Area) |  |  |  |  | Table 4 Supplementary Agreements (Rest Area)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Contract | Environmental | Finishing and Interior Work | Geotechnical | Hydraulics | Other | Procurement | Safety | Security/Protection | Structural | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Providing Access to Site | 1 | 100% | 1 | 1.389% | 423.5 | 588.2% | Design/Plan Issues | 26 | 36.11% |  |  | Access/ROW/Easement | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 100% | 3 | 4.167% | 25421.55 | 105923% | M&R/Replacement | 10 | 13.89% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 2 | 100% | 2 | 2.778% | 28601.82 | 79450% | Stakeholder Request | 9 | 12.5% |  |  | Construction Method Revision | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100%
Contract Amendment | Elimination of Contract Line Item | 1 | 14.29% | 7 | 9.722% | 7415.4143 | 72094% | Contract Amendment | 7 | 9.722% |  |  | Contract Amendment | 14.29% | 14.29% | 14.29% | 0% | 0% | 14.29% | 0% | 0% | 0% | 14.29% | 0% | 14.29% | 14.29% | 100%
| Line Item Omission | 5 | 71.43% |  |  |  |  | Differing Site Conditions (Except Utilities) | 5 | 6.944% |  |  | Design/Plan Issues | 0% | 3.846% | 26.92% | 3.846% | 11.54% | 0% | 7.692% | 0% | 3.846% | 7.692% | 0% | 19.23% | 15.38% | 100%
| Unavailability of Funds/Cash Flow Considerations | 1 | 14.29% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 3 | 4.167% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 20% | 20% | 0% | 20% | 0% | 0% | 0% | 20% | 0% | 20% | 0% | 100%
Design/Plan Issues | Construction Plans Error/Discrepancy | 3 | 11.54% | 26 | 36.11% | 5589.7723 | 201853% | Safety Concerns (Except Contaminated Soil) | 3 | 4.167% |  |  | Drainage Issues | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Unspecified | 4 | 15.38% |  |  |  |  | Construction Method Revision | 2 | 2.778% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
| Design Revision-Unspecified | 19 | 73.08% |  |  |  |  | Drainage Issues | 2 | 2.778% |  |  | M&R/Replacement | 0% | 0% | 20% | 0% | 10% | 0% | 0% | 10% | 0% | 20% | 0% | 30% | 10% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 1 | 20% | 5 | 6.944% | 9833.11 | 68285% | Access/ROW/Easement | 1 | 1.389% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Unspecified | 3 | 60% |  |  |  |  | Issues with Underground Utilities | 1 | 1.389% |  |  | Quantities Overrun/Underrun | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Unsuitable Materials | 1 | 20% |  |  |  |  | Procurement Issues | 1 | 1.389% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 33.33% | 100%
Drainage Issues | Drainage Issues-Unspecified | 1 | 50% | 2 | 2.778% | 5550 | 15417% | Quantities Overrun/Underrun | 1 | 1.389% |  |  | Stakeholder Request | 0% | 0% | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 22.22% | 100%
| Stormwater Concerns | 1 | 50% |  |  |  |  | Survey/Test Issues | 1 | 1.389% |  |  | Survey/Test Issues | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Issues with Underground Utilities | Utility Conflict | 1 | 100% | 1 | 1.389% | 4935 | 6854% | [5 empty] | Grand Total | 1.389% | 4.167% | 26.39% | 5.556% | 9.722% | 2.778% | 4.167% | 2.778% | 1.389% | 8.333% | 1.389% | 15.28% | 16.67% | 100%
M&R/Replacement | M&R/Replacement-Unspecified | 10 | 100% | 10 | 13.89% | 10956.802 | 152178% | Table 3 Supplementary Agreements (Rest Area)
Procurement Issues | Shop Drawing Error | 1 | 100% | 1 | 1.389% | 3597.96 | 4997% | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 100% | 1 | 1.389% | 115500 | 160417% | Finishing and Interior Work | 19 | 26.39% | 5683.5542 | 1499.8268
Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 2 | 66.67% | 3 | 4.167% | 1734.4 | 7227% | Utilities | 12 | 16.67% | 5139.3042 | 856.5507
| Tripping Hazard | 1 | 33.33% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 11 | 15.28% | 6414.5055 | 979.9939
Stakeholder Request | DOT Request-Unspecified | 2 | 22.22% | 9 | 12.5% | 7023.9022 | 87799% | Hydraulics | 7 | 9.722% | 4075.15 | 396.1951
| Stakeholder Request-Future Development Concerns | 1 | 11.11% |  |  |  |  | Structural | 6 | 8.333% | 17851.7333 | 1487.6444
| Stakeholder Request-Unspecified | 6 | 66.67% |  |  |  |  | Geotechnical | 4 | 5.556% | 42953.25 | 2386.2917
Survey/Test Issues | Additional Survey/Test Required | 1 | 100% | 1 | 1.389% | 38331 | 53238% | Environmental | 3 | 4.167% | 9047.7 | 376.9875
[8 empty] | Procurement | 3 | 4.167% | 7175.8967 | 298.9957
[8 empty] | Other | 2 | 2.778% | 960.25 | 26.6736
[8 empty] | Safety | 2 | 2.778% | 22702 | 630.6111
[8 empty] | Contract | 1 | 1.389% | 31267.5 | 434.2708
[8 empty] | Security/Protection | 1 | 1.389% | 880 | 12.2222
[8 empty] | TCP (Construction Phase) | 1 | 1.389% | 55938.64 | 776.9256

## 14a. Claim-Rural
Table 1 Claims - Rural | [9 empty] | Table 2 Claims - Rural
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Right of Entry Acquisition Delays | 1 | 14.29% | 7 | 2.035% | 15743.095 | 320.3537 | 97.8571 | 1.9913 | Access/ROW/Easement | 7 | 2.035%
| ROW Acquisition Delays-Unspecified | 6 | 85.71% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 22 | 6.395%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 4.545% | 22 | 6.395% | 21604.9075 | 1381.7092 | 83.2778 | 5.3259 | Contract Amendment | 39 | 11.34%
| Constructability Issues-Seasonal Limitations (Weather) | 20 | 90.91% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 7 | 2.035%
| Constructability Issues-Unspecified | 1 | 4.545% | [6 empty] | Design/Plan Issues | 63 | 18.31%
Contract Amendment | Contractor Replacement | 1 | 2.564% | 39 | 11.34% | 1330002.0672 | 150785.1181 | 94.9286 | 10.7623 | Differing Site Conditions (Except Utilities) | 8 | 2.326%
| Elimination of Contract Line Item | 3 | 7.692% | [6 empty] | Environmental/Community Concerns | 13 | 3.779%
| Error in Entering Time Extensions in HiCAMS | 16 | 41.03% | [6 empty] | Issues with Underground Utilities | 46 | 13.37%
| Line Item Omission | 3 | 7.692% | [6 empty] | M&R/Replacement | 22 | 6.395%
| Settlement and Release Agreement | 16 | 41.03% | [6 empty] | Natural Disaster | 30 | 8.721%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 4 | 57.14% | 7 | 2.035% | 0 | 0 | 54 | 1.0988 | Other | 5 | 1.453%
| Untimely Receipt of Design | 2 | 28.57% | [6 empty] | Permit | 4 | 1.163%
| Untimely Review and Return of Submittals | 1 | 14.29% | [6 empty] | Procurement Issues | 12 | 3.488%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 1.587% | 63 | 18.31% | 132272.86 | 24224.3901 | 47.0435 | 8.6155 | Project Closeout Issues | 9 | 2.616%
| Design/Plan Error-Unspecified | 21 | 33.33% | [6 empty] | Quantities Overrun/Underrun | 12 | 3.488%
| Design/Plan Revision-Unspecified | 41 | 65.08% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 29 | 8.43%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 2 | 25% | 8 | 2.326% | 43123.0625 | 1002.8619 | 90 | 2.093 | Start Date Delays | 10 | 2.907%
| Differing Site Conditions-Unspecified | 1 | 12.5% | [6 empty] | Survey/Test Issues | 6 | 1.744%
| Differing Site Conditions-Unsuitable Materials | 5 | 62.5%
Environmental/Community Concerns | Environmental Concerns/Unspecified | 3 | 23.08% | 13 | 3.779% | 2207.0133 | 83.4046 | 238.5 | 9.0131 | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Vegetation Establishment | 10 | 76.92% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 28.57%
Issues with Underground Utilities | Utilities not Relocated on Time | 17 | 36.96% | 46 | 13.37% | 368771.8191 | 49312.5107 | 108.1026 | 14.4556 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 23.81%
| Utility Conflict | 29 | 63.04% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 11.11%
M&R/Replacement | M&R/Replacement-Damaged Objects | 2 | 9.091% | 22 | 6.395% | 10843.1111 | 693.4548 | 70.4 | 4.5023 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 9.524%
| M&R/Replacement-Unspecified | 20 | 90.91% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 7.937%
Natural Disaster | Natural Disaster-Hurricane | 30 | 100% | 30 | 8.721% | 48307.886 | 4212.897 | 17.1786 | 1.4981 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 4.762%
Other | Covid 19 Impact | 1 | 20% | 5 | 1.453% | 7047.8967 | 102.4404 | 56.5 | 0.82122 | Utility – design, as-builts, etc. | 4.762%
| Lawsuit Costs | 1 | 20% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
| Misinterpretation of Plans | 1 | 20% | [6 empty] | Unspecified | 9.524%
| Unforeseen Issues-Unspecified | 2 | 40%
Permit | Insufficient Permit | 1 | 25% | 4 | 1.163% | 12939.66 | 150.4612 | 31 | 0.36047
| Permit Acquisition Waiting Period | 1 | 25%
| Permit Expiration | 1 | 25%
| Permit Violation | 1 | 25%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 2 | 16.67% | 12 | 3.488% | 9373.65 | 326.9878 | 67.6 | 2.3581
| Material Acquisition Delays/Long Lead Items | 2 | 16.67%
| Material Cost Fluctuation | 1 | 8.333%
| Power Supply Delays | 6 | 50%
| Unavailability of Materials/Material Shortage | 1 | 8.333%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 9 | 100% | 9 | 2.616% | 0 | 0 | 15.3333 | 0.40116
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 12 | 100% | 12 | 3.488% | 91413.6678 | 3188.8489 | 20.25 | 0.7064
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 4 | 13.79% | 29 | 8.43% | 12844.182 | 1082.7944 | 26.96 | 2.2728
| Miscommunication (Construction Progress) | 1 | 3.448%
| Purposeful Limited Work Schedule | 10 | 34.48%
| Scheduling Conflicts-Inspection | 1 | 3.448%
| Waiting for Other Entities to Perform Work | 4 | 13.79%
| Work Out of Sequence | 3 | 10.34%
| Work Restriction-Social Event | 4 | 13.79%
| Work Restriction-Unspecified | 2 | 6.897%
Start Date Delays | Delay in Availability of Project | 1 | 10% | 10 | 2.907% | 0 | 0 | 24.4 | 0.7093
| Delay in Contract Execution | 2 | 20%
| Delay in Preconstruction Meeting | 5 | 50%
| Delay in Project Award | 2 | 20%
Survey/Test Issues | Survey Error | 5 | 83.33% | 6 | 1.744% | 137254.3467 | 2393.9712 | 34.5 | 0.60174
| Survey Results Delays | 1 | 16.67%

## 14b. SA-Rural
Table 1 Supplementary Agreements (Rural) | [7 empty] | Table 2 Supplementary Agreements (Rural) |  |  |  |  | Table 4 Supplementary Agreements (Rural)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Utilities | Hydraulics | Geotechnical | Roadway Design | Traffic Control Systems (Except Pavement Markings) | Pavement | Environmental | TCP (Construction Phase) | Structural | Traffic Control Systems (pavement Markings) | Corridor/Traffic Design | Safety | Access/ROW/Easement | Contract | Roadway Alignment | Schedule | Other | Procurement | Permit | Security/Protection | Survey | Natural Disaster | Finishing and Interior Work | Grand Total
Design/Plan Issues | Compliance with Standard Specifications | 17 | 9.77% | 174 | 27.88% | 108614.5845 | 30286.7591 | Design/Plan Issues | 174 | 27.88% |  |  | Access/ROW/Easement | 12.5% | 6.25% | 0% | 6.25% | 6.25% | 0% | 0% | 18.75% | 0% | 0% | 12.5% | 0% | 37.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Construction Plans Error/Discrepancy | 11 | 6.322% |  |  |  |  | Contract Amendment | 101 | 16.19% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 35.48% | 16.13% | 16.13% | 3.226% | 16.13% | 6.452% | 3.226% | 0% | 3.226% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Elevation Difference with Existing Objects | 4 | 2.299% |  |  |  |  | Stakeholder Request | 48 | 7.692% |  |  | Construction Method Revision | 10.71% | 10.71% | 3.571% | 14.29% | 3.571% | 17.86% | 7.143% | 17.86% | 3.571% | 3.571% | 0% | 3.571% | 0% | 0% | 0% | 0% | 0% | 3.571% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Error-Unspecified | 13 | 7.471% |  |  |  |  | Differing Site Conditions (Except Utilities) | 43 | 6.891% |  |  | Contract Amendment | 21.78% | 14.85% | 9.901% | 4.95% | 7.921% | 3.96% | 1.98% | 6.931% | 1.98% | 9.901% | 0% | 0.9901% | 0.9901% | 6.931% | 1.98% | 0.9901% | 2.97% | 0% | 0% | 0.9901% | 0% | 0% | 0% | 100%
| Design Revision-Achieve Higher/Acceptable Quality | 5 | 2.874% |  |  |  |  | M&R/Replacement | 42 | 6.731% |  |  | Design/Plan Issues | 12.07% | 11.49% | 7.471% | 16.09% | 14.37% | 8.046% | 0.5747% | 1.724% | 6.897% | 4.023% | 6.897% | 1.149% | 1.149% | 1.724% | 3.448% | 0.5747% | 0% | 0.5747% | 1.149% | 0% | 0% | 0% | 0.5747% | 100%
| Design Revision-Change in Design Criteria | 1 | 0.5747% |  |  |  |  | Safety Concerns (Except Contaminated Soil) | 35 | 5.609% |  |  | Differing Site Conditions (Except Utilities) | 11.63% | 23.26% | 39.53% | 2.326% | 2.326% | 4.651% | 6.977% | 0% | 2.326% | 0% | 0% | 0% | 0% | 0% | 4.651% | 0% | 0% | 0% | 0% | 2.326% | 0% | 0% | 0% | 100%
| Design Revision-Functionality Issues | 1 | 0.5747% |  |  |  |  | Issues with Underground Utilities | 31 | 4.968% |  |  | Drainage Issues | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Future Maintenance Concerns | 6 | 3.448% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 31 | 4.968% |  |  | Environmental/Community Concerns | 5.556% | 0% | 0% | 5.556% | 0% | 0% | 66.67% | 0% | 0% | 0% | 5.556% | 0% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 5.556% | 0% | 0% | 0% | 100%
| Design Revision-per Contractor Request | 8 | 4.598% |  |  |  |  | Construction Method Revision | 28 | 4.487% |  |  | Erosion Control Problems | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Toll Collection | 1 | 0.5747% |  |  |  |  | Environmental/Community Concerns | 18 | 2.885% |  |  | Issues with Underground Utilities | 93.55% | 0% | 3.226% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.226% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 0.5747% |  |  |  |  | Access/ROW/Easement | 16 | 2.564% |  |  | M&R/Replacement | 16.67% | 28.57% | 11.9% | 4.762% | 4.762% | 23.81% | 2.381% | 2.381% | 0% | 0% | 0% | 2.381% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.381% | 0% | 100%
| Design Revision-Unspecified | 90 | 51.72% |  |  |  |  | Scheduling and Coordination Issues | 15 | 2.404% |  |  | Other | 0% | 50% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Design Revision-Value Engineering Proposal | 5 | 2.874% |  |  |  |  | Quantities Overrun/Underrun | 15 | 2.404% |  |  | Procurement Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100%
| Increased Traffic Volume | 2 | 1.149% |  |  |  |  | Drainage Issues | 8 | 1.282% |  |  | Quantities Overrun/Underrun | 0% | 0% | 20% | 6.667% | 6.667% | 33.33% | 13.33% | 6.667% | 6.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.667% | 0% | 0% | 0% | 0% | 100%
| Scope Change | 9 | 5.172% |  |  |  |  | Erosion Control Problems | 8 | 1.282% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 2.857% | 0% | 11.43% | 8.571% | 2.857% | 2.857% | 37.14% | 0% | 2.857% | 5.714% | 20% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 2.857% | 0% | 100%
Contract Amendment | Change in Contract Provisions | 4 | 3.96% | 101 | 16.19% | 137159.8069 | 22200.5457 | Procurement Issues | 6 | 0.9615% |  |  | Scheduling and Coordination Issues | 0% | 13.33% | 0% | 0% | 0% | 6.667% | 0% | 13.33% | 6.667% | 0% | 0% | 0% | 0% | 6.667% | 0% | 46.67% | 6.667% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Elimination of Contract Line Item | 1 | 0.9901% |  |  |  |  | Survey/Test Issues | 3 | 0.4808% |  |  | Stakeholder Request | 35.42% | 2.083% | 2.083% | 4.167% | 6.25% | 2.083% | 6.25% | 2.083% | 6.25% | 4.167% | 8.333% | 2.083% | 4.167% | 2.083% | 0% | 0% | 10.42% | 0% | 0% | 0% | 0% | 2.083% | 0% | 100%
| Issues with Previous SA | 2 | 1.98% |  |  |  |  | Other | 2 | 0.3205% |  |  | Survey/Test Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100%
| Line Item Omission | 84 | 83.17% | [9 empty] | Grand Total | 18.91% | 12.66% | 8.974% | 8.013% | 8.013% | 7.212% | 5.929% | 5.769% | 3.526% | 3.365% | 3.365% | 2.083% | 2.083% | 1.923% | 1.763% | 1.603% | 1.442% | 1.282% | 0.4808% | 0.4808% | 0.4808% | 0.4808% | 0.1603% | 100%
| Mitigation of Potential Risk | 1 | 0.9901% |  |  |  |  | Table 3 Supplementary Agreements (Rural)
| Permission to Hold Additional Retainage | 1 | 0.9901% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Revise Measurement and Payment Method | 8 | 7.921% |  |  |  |  | Utilities | 118 | 18.91% | 74738.669 | 14133.2739
Stakeholder Request | DOT Request-Unspecified | 18 | 37.5% | 48 | 7.692% | 175183.9472 | 13475.6882 | Hydraulics | 79 | 12.66% | 28685.1585 | 3631.6146
| Stakeholder Request-Future Development Concerns | 3 | 6.25% |  |  |  |  | Geotechnical | 56 | 8.974% | 40480.5862 | 3632.8731
| Stakeholder Request-Unspecified | 27 | 56.25% |  |  |  |  | Roadway Design | 50 | 8.013% | 69576.6432 | 5575.0515
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 2.326% | 43 | 6.891% | 20484.9567 | 1411.6236 | Traffic Control Systems (Except Pavement Markings) | 50 | 8.013% | 71441.8775 | 5724.5094
| Differing Site Conditions-Contaminated Soil | 2 | 4.651% |  |  |  |  | Pavement | 45 | 7.212% | 258137.305 | 18615.671
| Differing Site Conditions-Encountered Rock | 1 | 2.326% |  |  |  |  | Environmental | 37 | 5.929% | 38030.6684 | 2255.0236
| Differing Site Conditions-Extra Work from Previous Projects | 1 | 2.326% |  |  |  |  | TCP (Construction Phase) | 36 | 5.769% | 30323.0056 | 1749.4042
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 7 | 16.28% |  |  |  |  | Structural | 22 | 3.526% | 21832.0186 | 769.7186
| Differing Site Conditions-Not Shown in Construction Plans | 2 | 4.651% |  |  |  |  | Corridor/Traffic Design | 21 | 3.365% | 261163.0705 | 8789.1418
| Differing Site Conditions-Unspecified | 21 | 48.84% |  |  |  |  | Traffic Control Systems (pavement Markings) | 21 | 3.365% | 15760.3371 | 530.396
| Differing Site Conditions-Unsuitable Materials | 2 | 4.651% |  |  |  |  | Access/ROW/Easement | 13 | 2.083% | 19205.8962 | 400.1228
| Slope Protection/Soil Stabilization | 6 | 13.95% |  |  |  |  | Safety | 13 | 2.083% | 130893.7008 | 2726.9521
M&R/Replacement | Damaged Objects | 2 | 4.762% | 42 | 6.731% | 32528.4936 | 2189.4178 | Contract | 12 | 1.923% | 830505.2778 | 15971.2553
| M&R/Replacement-Unspecified | 40 | 95.24% |  |  |  |  | Roadway Alignment | 11 | 1.763% | 46769.3409 | 824.4595
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 2 | 5.714% | 35 | 5.609% | 25495.8243 | 1430.0542 | Schedule | 10 | 1.603% | 1018010.5162 | 16314.2711
| Hazardous Materials Removal | 1 | 2.857% |  |  |  |  | Other | 9 | 1.442% | 6296.8244 | 90.8196
| Safety Concerns-Unspecified | 28 | 80% |  |  |  |  | Procurement | 8 | 1.282% | -3053.7575 | -39.1507
| Sight Distance Concerns | 1 | 2.857% |  |  |  |  | Natural Disaster | 3 | 0.4808% | 16856.32 | 81.04
| Travelers/Public Safety | 3 | 8.571% |  |  |  |  | Permit | 3 | 0.4808% | 24911.76 | 119.7681
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 6.452% | 31 | 4.968% | 51497.8733 | 2558.3879 | Security/Protection | 3 | 0.4808% | 9306.8333 | 44.7444
| Utility Conflict | 29 | 93.55% |  |  |  |  | Survey | 3 | 0.4808% | 3790.42 | 18.2232
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 7 | 22.58% | 31 | 4.968% | 68684.0374 | 3412.1878 | Finishing and Interior Work | 1 | 0.1603% | 2500 | 4.0064
| Constructability Issues-Unspecified | 24 | 77.42%
Construction Method Revision | Construction Method Revision-Unspecified | 28 | 100% | 28 | 4.487% | 16657.0792 | 747.433
Environmental/Community Concerns | Animal Protection/Endangered Species | 3 | 16.67% | 18 | 2.885% | 55171.8744 | 1591.4964
| Avoid Historical Structure | 1 | 5.556%
| Construction Impacts | 1 | 5.556%
| Environmental Concerns-Unspecified | 4 | 22.22%
| Vegetation Establishment | 7 | 38.89%
| Wetland Delineation | 2 | 11.11%
Access/ROW/Easement | Easement Acquisition Delays | 1 | 6.25% | 16 | 2.564% | 59033.6056 | 1513.6822
| Extra Work Associated with ROW Agreement | 3 | 18.75%
| Insufficient ROW | 2 | 12.5%
| Insufficient Utility Easement | 2 | 12.5%
| Property Owners Access | 5 | 31.25%
| Providing Access to Site | 1 | 6.25%
| Traffic Access Point | 2 | 12.5%
Scheduling and Coordination Issues | Additional ICT Required | 1 | 6.667% | 15 | 2.404% | 428955.2969 | 10311.4254
| Conflict with Other Projects | 2 | 13.33%
| Conflict/Overlap with Adjacent Projects | 1 | 6.667%
| Early Project Completion | 7 | 46.67%
| Overtime Hour Request | 1 | 6.667%
| Project Phasing Problems | 1 | 6.667%
| Statewide Initiative to Accelerate Projects | 1 | 6.667%
| Timely Completion of Project | 1 | 6.667%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 13 | 86.67% | 15 | 2.404% | 256152.7046 | 6157.5169
| Waste Excessive Material | 2 | 13.33%
Drainage Issues | Drainage Issues-Unspecified | 7 | 87.5% | 8 | 1.282% | 17283.875 | 221.5881
| Stormwater Concerns | 1 | 12.5%
Erosion Control Problems | Erosion Control Problems-Unspecified | 7 | 87.5% | 8 | 1.282% | 10811.6963 | 138.6115
| Waste Site Erosion Control | 1 | 12.5%
Procurement Issues | Shop Drawing Error | 1 | 16.67% | 6 | 0.9615% | 9710.5517 | 93.3707
| Unavailability of Materials/Material Shortage | 4 | 66.67%
| Wrong Order Placement | 1 | 16.67%
Survey/Test Issues | Survey Error-Staking | 1 | 33.33% | 3 | 0.4808% | 3790.42 | 18.2232
| Survey Error-Unspecified | 2 | 66.67%
Other | Permit Acquisition Issues | 1 | 50% | 2 | 0.3205% | 3420.025 | 10.9616
| Permit Requirements | 1 | 50%

## 15a. Claim-Safe Route to School
Table 1 Claims - Safe Routes to School | [9 empty] | Table 2 Claims - Safe Routes to School
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 1 | 1 | 6.667% | 0 | 0 | 118 | 7.8667 | Issues with Underground Utilities | 5 | 33.33%
Contract Amendment | Contract Error | 2 | 0.5 | 4 | 26.67% | 0 | 0 | 6.25 | 1.6667 | Contract Amendment | 4 | 26.67%
| Error in Entering Time Extensions in HiCAMS | 2 | 0.5 | [6 empty] | Project Closeout Issues | 2 | 13.33%
Environmental/Community Concerns | Vegetation Establishment | 1 | 1 | 1 | 6.667% | 0 | 0 | 84 | 5.6 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 1 | 6.667%
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 0.4 | 5 | 33.33% | 20533.28 | 6844.4267 | 118.6 | 39.5333 | Environmental/Community Concerns | 1 | 6.667%
| Utility Conflict | 3 | 0.6 | [6 empty] | Natural Disaster | 1 | 6.667%
Natural Disaster | Natural Disaster-Hurricane | 1 | 1 | 1 | 6.667% | 0 | 0 | 14 | 0.93333 | Quantities Overrun/Underrun | 1 | 6.667%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 0.5 | 2 | 13.33% | 0 | 0 | 14 | 1.8667
| Scheduling Conflicts-Final Inspection/Punchlist | 1 | 0.5 | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 1 | 1 | 6.667% | 5655 | 377 | - | - | No Design/Plan Issues

## 15b. SA-Safe Route to School
Table 1 Supplementary Agreements (Safe Routes to School) | [7 empty] | Table 2 Supplementary Agreements (Safe Routes to School) |  |  |  |  | Table 4 Supplementary Agreements (Safe Routes to School)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Geotechnical | Hydraulics | Roadway Design | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Utilities | Grand Total
Contract Amendment | Line Item Omission | 2 | 100% | 2 | 20% | 11831.915 | 2366.383 | Contract Amendment | 2 | 20% |  |  | Contract Amendment | 50% | 0% | 50% | 0% | 0% | 0% | 100%
Design/Plan Issues | Design Error-Unspecified | 1 | 100% | 1 | 10% | 3212.05 | 321.205 | Differing Site Conditions (Except Utilities) | 2 | 20% |  |  | Design/Plan Issues | 0% | 100% | 0% | 0% | 0% | 0% | 100%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 50% | 2 | 20% | 12415 | 2483 | Stakeholder Request | 2 | 20% |  |  | Differing Site Conditions (Except Utilities) | 50% | 0% | 50% | 0% | 0% | 0% | 100%
| Differing Site Conditions-Unspecified | 1 | 50% |  |  |  |  | Design/Plan Issues | 1 | 10% |  |  | Issues with Underground Utilities | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Issues with Underground Utilities | Utility Conflict | 1 | 100% | 1 | 10% | 3672 | 367.2 | Issues with Underground Utilities | 1 | 10% |  |  | M&R/Replacement | 0% | 100% | 0% | 0% | 0% | 0% | 100%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 10% | 18025 | 1802.5 | M&R/Replacement | 1 | 10% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 0% | 100% | 0% | 0% | 100%
Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 1 | 100% | 1 | 10% | 7700 | 770 | Safety Concerns (Except Contaminated Soil) | 1 | 10% |  |  | Stakeholder Request | 0% | 0% | 50% | 0% | 50% | 0% | 100%
Stakeholder Request | DOT Request-Unspecified | 2 | 100% | 2 | 20% | 6951.85 | 1390.37 | [5 empty] | Grand Total | 20% | 20% | 30% | 10% | 10% | 10% | 100%
Table 3 Supplementary Agreements (Safe Routes to School)
[8 empty] | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
[8 empty] | Roadway Design | 3 | 30% | 8747.9333 | 2624.38
[8 empty] | Geotechnical | 2 | 20% | 13525.015 | 2705.003
[8 empty] | Hydraulics | 2 | 20% | 10618.525 | 2123.705
[8 empty] | TCP (Construction Phase) | 1 | 10% | 7700 | 770
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 1 | 10% | 9103.7 | 910.37
[8 empty] | Utilities | 1 | 10% | 3672 | 367.2

## 3. Risk Profile (Specific)
[7 empty] | Compensation Granted |  |  |  | Time Granted
Claim or SA | Count Generic Cause | % Generic Cause | Generic Cause | Generic Cause Level 2 | % Specific Cause | Count GC Level 2 | Min | Most Likely | Max | Expected Value | Min Time Granted (days) | Average Time Granted (days) | Max Time Granted (days) | Expected Value (Time)
claim | 258 | 16.17% | Design/Plan Issues | Compliance with Standard Specifications | 4.651% | 12 | 2600 | 28387.9083 | 101544.4 | 213.4429 | 3 | 134.4286 | 365 | 1.0107
claim | 258 | 16.17% | Design/Plan Issues | Design/Plan Error-Unspecified | 27.52% | 71 | 564.26 | 45016.6687 | 718607 | 2002.6212 | 1 | 56.1429 | 269 | 2.4976
claim | 258 | 16.17% | Design/Plan Issues | Design/Plan Revision-Unspecified | 66.67% | 172 | 308 | 78938.1468 | 851737.48 | 8507.1186 | 1 | 49.5294 | 556 | 5.3378
claim | 258 | 16.17% | Design/Plan Issues | Increased Traffic Volume | 1.163% | 3 | 0 | 0 | 0 | 0 | 1 | 4.3333 | 10 | 0.0081454
claim | 235 | 14.72% | Issues with Underground Utilities | Utilities not Relocated on Time | 30.64% | 72 | 726.43 | 229540.2664 | 2983542.8 | 10355.2 | 1 | 91.7612 | 636 | 4.1396
claim | 235 | 14.72% | Issues with Underground Utilities | Utility Conflict | 69.36% | 163 | 1514.08 | 141029.1467 | 2250000 | 14403.3527 | 1 | 97.3451 | 860 | 9.9419
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Drought | 1.418% | 2 | 0 | 0 | 0 | 0 | 5 | 44 | 83 | 0.055138
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Flood | 0.7092% | 1 | 0 | 0 | 0 | 0 | 17 | 17 | 17 | 0.010652
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Hurricane | 94.33% | 133 | 3300 | 47677.0867 | 132293.2 | 3973.0906 | 1 | 25.7328 | 393 | 2.1444
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Sinkhole | 0.7092% | 1 | 0 | 0 | 0 | 0 | 92 | 92 | 92 | 0.057644
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Slide | 1.418% | 2 | 8411 | 8411 | 8411 | 10.5401 | 156 | 156 | 156 | 0.19549
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Thunderstorm | 0.7092% | 1 | 3948.72 | 3948.72 | 3948.72 | 2.4741 | 0 | 0 | 0 | 0
claim | 141 | 8.835% | Natural Disaster | Natural Disaster-Tropical Depression | 0.7092% | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 0.004386
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 7.801% | 11 | 0 | 0 | 0 | 0 | 1 | 178.8182 | 862 | 1.2325
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 8.511% | 12 | 3739 | 3739 | 3739 | 28.1128 | 2 | 32.7273 | 122 | 0.24607
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-Unspecified | 2.128% | 3 | 63937 | 63937 | 63937 | 120.1823 | 3 | 15 | 27 | 0.028195
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Early Project Completion | 0.7092% | 1 | 1430000 | 1430000 | 1430000 | 895.99 | 0 | 0 | 0 | 0
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Miscommunication (Construction Progress) | 2.128% | 3 | 6937.67 | 6937.67 | 6937.67 | 13.0407 | 3 | 5.5 | 8 | 0.010338
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule | 29.79% | 42 | 0 | 0 | 0 | 0 | 2 | 10.381 | 50 | 0.27318
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 7.092% | 10 | 0 | 0 | 0 | 0 | 1 | 19.4 | 120 | 0.12155
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Timely Completion of Project | 0.7092% | 1 | 20000 | 20000 | 20000 | 12.5313 | 0 | 0 | 0 | 0
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 9.22% | 13 | 750 | 81687.6325 | 216768.79 | 665.3755 | 2 | 65.4167 | 205 | 0.53284
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence | 6.383% | 9 | 35940.43 | 41288.635 | 46636.84 | 232.8306 | 8 | 64.5714 | 180 | 0.36412
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 14.18% | 20 | 86033.59 | 86033.59 | 86033.59 | 1078.1152 | 1 | 15.6316 | 90 | 0.19588
claim | 141 | 8.835% | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified | 11.35% | 16 | 547.44 | 16494.5567 | 41757.02 | 165.359 | 1 | 22.3846 | 97 | 0.22441
claim | 127 | 7.957% | Contract Amendment | Contract Error | 4.724% | 6 | 5203.47 | 5203.47 | 5203.47 | 19.5619 | 2 | 33 | 117 | 0.12406
claim | 127 | 7.957% | Contract Amendment | Contract Time Adjustment | 3.15% | 4 | 0 | 0 | 0 | 0 | 14 | 42 | 64 | 0.10526
claim | 127 | 7.957% | Contract Amendment | Contractor Replacement | 1.575% | 2 | 51683.11 | 51683.11 | 51683.11 | 64.7658 | 1 | 3.5 | 6 | 0.004386
claim | 127 | 7.957% | Contract Amendment | Elimination of Contract Line Item | 7.087% | 9 | 4280.56 | 33717.2775 | 59681.6 | 190.135 | 2 | 23.4 | 47 | 0.13195
claim | 127 | 7.957% | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 38.58% | 49 | 9081.32 | 9081.32 | 9081.32 | 278.8125 | 1 | 51.2917 | 383 | 1.5747
claim | 127 | 7.957% | Contract Amendment | Line Item Omission | 18.11% | 23 | 600.88 | 10304.1891 | 37164.51 | 148.494 | 1 | 49.6471 | 466 | 0.71547
claim | 127 | 7.957% | Contract Amendment | Revise Measurement and Payment Method | 1.575% | 2 | 5592.35 | 10843.835 | 16095.32 | 13.5888 | 0 | 0 | 0 | 0
claim | 127 | 7.957% | Contract Amendment | Settlement and Release Agreement | 21.26% | 27 | 37605.99 | 1375419.1933 | 20600000 | 23268.3698 | 5 | 207.4615 | 428 | 3.5097
claim | 127 | 7.957% | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 3.937% | 5 | 3881 | 3881 | 3881 | 12.1585 | 56 | 80.5 | 112 | 0.25219
claim | 109 | 6.83% | Project Closeout Issues | Delay in Project Acceptance | 0.9174% | 1 | 0 | 0 | 0 | 0 | 201 | 201 | 201 | 0.12594
claim | 109 | 6.83% | Project Closeout Issues | Delay in Receipt of Final Punchlist | 0.9174% | 1 | 0 | 0 | 0 | 0 | 33 | 33 | 33 | 0.020677
claim | 109 | 6.83% | Project Closeout Issues | Final Punchlist Extra Work | 11.01% | 12 | 0 | 0 | 0 | 0 | 1 | 24.1667 | 97 | 0.1817
claim | 109 | 6.83% | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 87.16% | 95 | 2000 | 2000 | 2000 | 119.0476 | 1 | 16.4737 | 106 | 0.98058
claim | 94 | 5.89% | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 4.255% | 4 | 9220 | 86017.6133 | 124500 | 215.583 | 26 | 41.5 | 57 | 0.10401
claim | 94 | 5.89% | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 92.55% | 87 | 2063 | 15384.325 | 35000 | 838.6192 | 2 | 81.6706 | 334 | 4.452
claim | 94 | 5.89% | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3.191% | 3 | 6509 | 14917.69 | 23326.38 | 28.0408 | 4 | 4 | 4 | 0.0075188
claim | 76 | 4.762% | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 100% | 76 | 212.5 | 98518.4124 | 1023042.77 | 4691.353 | 1 | 32.0811 | 250 | 1.5277
claim | 75 | 4.699% | M&R/Replacement | M&R/Replacement-Damaged Objects | 5.333% | 4 | 23332.55 | 23332.55 | 23332.55 | 58.4776 | 6 | 13.6667 | 20 | 0.034252
claim | 75 | 4.699% | M&R/Replacement | M&R/Replacement-Unspecified | 90.67% | 68 | 654.07 | 41957.0297 | 470647.87 | 1787.6429 | 1 | 76.5 | 788 | 3.2594
claim | 75 | 4.699% | M&R/Replacement | Vehicular Accident | 4% | 3 | 0 | 0 | 0 | 0 | 1 | 12.6667 | 19 | 0.02381
claim | 68 | 4.261% | Environmental/Community Concerns | Animal Protection/Endangered Species | 2.941% | 2 | 0 | 0 | 0 | 0 | 26 | 96.5 | 167 | 0.12093
claim | 68 | 4.261% | Environmental/Community Concerns | Environmental Concerns/Unspecified | 8.824% | 6 | 746.04 | 1703.2917 | 4840 | 6.4034 | 0 | 0 | 0 | 0
claim | 68 | 4.261% | Environmental/Community Concerns | Erosion Control Problems | 5.882% | 4 | 17900.66 | 17951.765 | 18002.87 | 44.9919 | 8 | 39.3333 | 85 | 0.09858
claim | 68 | 4.261% | Environmental/Community Concerns | Historical Site | 1.471% | 1 | 30621.65 | 30621.65 | 30621.65 | 19.1865 | 0 | 0 | 0 | 0
claim | 68 | 4.261% | Environmental/Community Concerns | Vegetation Establishment | 77.94% | 53 | 0 | 0 | 0 | 0 | 1 | 125.7358 | 740 | 4.1754
claim | 68 | 4.261% | Environmental/Community Concerns | Wetland Discovery | 2.941% | 2 | 0 | 0 | 0 | 0 | 6 | 30 | 54 | 0.037594
claim | 55 | 3.446% | Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement | 1.818% | 1 | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 0.017544
claim | 55 | 3.446% | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 56.36% | 31 | 20105.23 | 20105.23 | 20105.23 | 390.5151 | 3 | 41.3871 | 141 | 0.80388
claim | 55 | 3.446% | Design Approval Waiting Period/Indecision/Negotiation | Negotiation Delays | 3.636% | 2 | 0 | 0 | 0 | 0 | 41 | 51.5 | 62 | 0.064536
claim | 55 | 3.446% | Design Approval Waiting Period/Indecision/Negotiation | Untimely Receipt of Design | 5.455% | 3 | 0 | 0 | 0 | 0 | 6 | 90.6667 | 251 | 0.17043
claim | 55 | 3.446% | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals | 25.45% | 14 | 0 | 0 | 0 | 0 | 3 | 75.4286 | 364 | 0.66165
claim | 55 | 3.446% | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals | 7.273% | 4 | 12714.68 | 12714.68 | 12714.68 | 31.8664 | 8 | 19.6667 | 36 | 0.04929
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 20.41% | 10 | 3003 | 11420.095 | 27267.74 | 71.5545 | 1 | 7.625 | 14 | 0.047776
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Groundwater | 2.041% | 1 | 3137.37 | 3137.37 | 3137.37 | 1.9658 | 4 | 4 | 4 | 0.0025063
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 4.082% | 2 | 0 | 0 | 0 | 0 | 6 | 9.5 | 13 | 0.011905
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 16.33% | 8 | 1330 | 2309.63 | 3289.26 | 11.5771 | 3 | 12.1667 | 21 | 0.060986
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Hazardous Materials | 8.163% | 4 | 13173.12 | 25577.3733 | 47069 | 64.1037 | 108 | 108 | 108 | 0.27068
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 14.29% | 7 | 0 | 0 | 0 | 0 | 7 | 66.2857 | 296 | 0.29073
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 6.122% | 3 | 10832.19 | 10832.19 | 10832.19 | 20.3613 | 5 | 15 | 29 | 0.028195
claim | 49 | 3.07% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 28.57% | 14 | 3668.49 | 33616.1233 | 84439.77 | 294.8783 | 3 | 47.25 | 242 | 0.41447
claim | 48 | 3.008% | Procurement Issues | DOT Furnished Materials/Equipment Delays | 12.5% | 6 | 0 | 0 | 0 | 0 | 10 | 41.1667 | 130 | 0.15476
claim | 48 | 3.008% | Procurement Issues | Material Acquisition Delays/Long Lead Items | 22.92% | 11 | 5142.2 | 5142.2 | 5142.2 | 35.4412 | 13 | 54.4 | 125 | 0.37494
claim | 48 | 3.008% | Procurement Issues | Material Cost Fluctuation | 4.167% | 2 | 3611.33 | 7075.565 | 10539.8 | 8.8666 | 0 | 0 | 0 | 0
claim | 48 | 3.008% | Procurement Issues | Material Fabrication Delay | 2.083% | 1 | 0 | 0 | 0 | 0 | 69 | 69 | 69 | 0.043233
claim | 48 | 3.008% | Procurement Issues | Power Supply Delays | 35.42% | 17 | 8207.5 | 8207.5 | 8207.5 | 87.4232 | 17 | 125.0625 | 513 | 1.3321
claim | 48 | 3.008% | Procurement Issues | Unavailability of Materials/Material Shortage | 16.67% | 8 | 0 | 0 | 0 | 0 | 1 | 41 | 154 | 0.20551
claim | 48 | 3.008% | Procurement Issues | Wrong Order Placement | 6.25% | 3 | 16245 | 47069.645 | 77894.29 | 88.4768 | 2 | 71.5 | 141 | 0.1344
claim | 34 | 2.13% | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 5.882% | 2 | 0 | 0 | 0 | 0 | 4 | 14.5 | 25 | 0.01817
claim | 34 | 2.13% | Access/ROW/Easement | Insufficient Right of Entry | 2.941% | 1 | 1326240.53 | 1326240.53 | 1326240.53 | 830.9778 | 0 | 0 | 0 | 0
claim | 34 | 2.13% | Access/ROW/Easement | Insufficient ROW | 8.824% | 3 | 0 | 0 | 0 | 0 | 1 | 8 | 12 | 0.015038
claim | 34 | 2.13% | Access/ROW/Easement | Railroad Right of Entry | 26.47% | 9 | 14259.98 | 50393.1767 | 114680.21 | 284.172 | 6 | 99.2857 | 298 | 0.55988
claim | 34 | 2.13% | Access/ROW/Easement | Right of Entry Acquisition Delays | 2.941% | 1 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 0.0068922
claim | 34 | 2.13% | Access/ROW/Easement | ROW Acquisition Delays-Property Owners Agreement | 5.882% | 2 | 0 | 0 | 0 | 0 | 28 | 63.5 | 99 | 0.079574
claim | 34 | 2.13% | Access/ROW/Easement | ROW Acquisition Delays-Unspecified | 47.06% | 16 | 5531.09 | 1139504.81 | 4430869 | 11423.6071 | 14 | 96.9375 | 243 | 0.9718
claim | 33 | 2.068% | Start Date Delays | Delay in Availability of Project | 3.03% | 1 | 0 | 0 | 0 | 0 | 79 | 79 | 79 | 0.049499
claim | 33 | 2.068% | Start Date Delays | Delay in Contract Execution | 48.48% | 16 | 0 | 0 | 0 | 0 | 3 | 20.5625 | 82 | 0.20614
claim | 33 | 2.068% | Start Date Delays | Delay in Preconstruction Meeting | 27.27% | 9 | 0 | 0 | 0 | 0 | 7 | 23.3333 | 111 | 0.13158
claim | 33 | 2.068% | Start Date Delays | Delay in Project Award | 12.12% | 4 | 0 | 0 | 0 | 0 | 21 | 74.25 | 213 | 0.18609
claim | 33 | 2.068% | Start Date Delays | Delay in Receipt of Contract Information and Bonds | 3.03% | 1 | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 0.017544
claim | 33 | 2.068% | Start Date Delays | Start Date Delays-Unspecified | 6.061% | 2 | 0 | 0 | 0 | 0 | 14 | 14.5 | 15 | 0.01817
claim | 24 | 1.504% | Survey/Test Issues | Additional Survey-Test Required | 16.67% | 4 | 650 | 5769.9333 | 12000 | 14.461 | 1 | 1 | 1 | 0.0025063
claim | 24 | 1.504% | Survey/Test Issues | Survey Error | 75% | 18 | 1700 | 70767.2743 | 406401.29 | 798.1272 | 1 | 16.2143 | 75 | 0.18287
claim | 24 | 1.504% | Survey/Test Issues | Survey Results Delays | 8.333% | 2 | 0 | 0 | 0 | 0 | 19 | 24.5 | 30 | 0.030702
claim | 17 | 1.065% | Permit | Insufficient Permit | 11.76% | 2 | 0 | 0 | 0 | 0 | 10 | 23.5 | 37 | 0.029449
claim | 17 | 1.065% | Permit | Permit Acquisition Waiting Period | 64.71% | 11 | 117142.68 | 117142.68 | 117142.68 | 807.3744 | 8 | 55.6364 | 173 | 0.38346
claim | 17 | 1.065% | Permit | Permit Expiration | 5.882% | 1 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 0.02005
claim | 17 | 1.065% | Permit | Permit Limitation | 11.76% | 2 | 2942.65 | 2942.65 | 2942.65 | 3.6875 | 60 | 60 | 60 | 0.075188
claim | 17 | 1.065% | Permit | Permit Violation | 5.882% | 1 | 12939.66 | 12939.66 | 12939.66 | 8.1076 | 11 | 11 | 11 | 0.0068922
claim | 12 | 0.7519% | Other | Covid 19 Impact | 25% | 3 | 0 | 0 | 0 | 0 | 3 | 127.6667 | 269 | 0.23997
claim | 12 | 0.7519% | Other | Lawsuit Costs | 8.333% | 1 | 15389.12 | 15389.12 | 15389.12 | 9.6423 | 0 | 0 | 0 | 0
claim | 12 | 0.7519% | Other | Misinterpretation of Plans | 16.67% | 2 | 3755.92 | 74027.96 | 144300 | 92.7669 | 0 | 0 | 0 | 0
claim | 12 | 0.7519% | Other | Unavailability of Labor | 16.67% | 2 | 0 | 0 | 0 | 0 | 78 | 226.5 | 375 | 0.28383
claim | 12 | 0.7519% | Other | Unforeseen Issues-Unspecified | 33.33% | 4 | 1998.65 | 37315.0567 | 107204.47 | 93.5214 | 2 | 2.5 | 3 | 0.0062657
supplemental | 583 | 26.78% | Design/Plan Issues | Compliance with Standard Specifications | 11.15% | 65 | 0 | 68285.5012 | 1471250 | 2038.8413 |  | 15.38%
supplemental | 583 | 26.78% | Design/Plan Issues | Construction Plans Error/Discrepancy | 6.861% | 40 | 0 | 12480.0667 | 97264.9 | 229.3076 |  | 0%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Error-Elevation Difference with Existing Objects | 3.259% | 19 | 540 | 18060.0205 | 108393.3 | 157.6208 |  | 0%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Error-Unspecified | 8.405% | 49 | -8100.32 | 31702.3139 | 359770 | 713.5569 |  | 4.082%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Achieve Higher/Acceptable Quality | 2.744% | 16 | -193770.15 | 1658.4488 | 99557.93 | 12.1889 |  | 18.75%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Change in Design Criteria | 0.1715% | 1 | 19602 | 19602 | 19602 | 9.0041 |  | 100%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Fix Impacts of Previous Revisions | 1.715% | 10 | 0 | 3459.452 | 15614 | 15.8909 |  | 10%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Functionality Issues | 1.372% | 8 | -230375 | -25265.7425 | 18496.5 | -92.8461 |  | 0%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 2.744% | 16 | -1089.75 | 37328.235 | 302069.28 | 274.3462 |  | 43.75%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-per Contractor Request | 6.175% | 36 | -540321.12 | -3505.2506 | 765888 | -57.9646 |  | 11.11%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Toll Collection | 0.1715% | 1 | 22427.43 | 22427.43 | 22427.43 | 10.302 |  | 0%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Uniformity with Adjacent Projects/Objects | 1.372% | 8 | 5411.35 | 81981.725 | 383270.39 | 301.265 |  | 12.5%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Unspecified | 47.17% | 275 | -1154813.66 | 101840.1811 | 5913904.72 | 12864.5153 |  | 12.36%
supplemental | 583 | 26.78% | Design/Plan Issues | Design Revision-Value Engineering Proposal | 1.715% | 10 | -800369.5 | -221441.063 | 13744.61 | -1017.1845 |  | 30%
supplemental | 583 | 26.78% | Design/Plan Issues | Incomplete Design | 0.5146% | 3 | 22696.25 | 1741322.8233 | 5105264.16 | 2399.618 |  | 0%
supplemental | 583 | 26.78% | Design/Plan Issues | Increased Traffic Volume | 1.544% | 9 | 0 | 61077.9178 | 385103.25 | 252.504 |  | 11.11%
supplemental | 583 | 26.78% | Design/Plan Issues | Scope Change | 2.916% | 17 | 1155 | 99215.5741 | 780503.16 | 774.7656 |  | 11.76%
supplemental | 324 | 14.88% | Contract Amendment | Change in Contract Provisions | 1.852% | 6 | -320155 | 1524204.7433 | 6597392.7 | 4200.8399 |  | 83.33%
supplemental | 324 | 14.88% | Contract Amendment | Contingency Item | 0.3086% | 1 | 6800 | 6800 | 6800 | 3.1236 |  | 0%
supplemental | 324 | 14.88% | Contract Amendment | Elimination of Contract Line Item | 2.16% | 7 | -121916.5 | -25254.5957 | -614.67 | -81.2045 |  | 14.29%
supplemental | 324 | 14.88% | Contract Amendment | Insufficient Insurance | 0.3086% | 1 | 16000 | 16000 | 16000 | 7.3496 |  | 0%
supplemental | 324 | 14.88% | Contract Amendment | Issues with Previous SA | 1.852% | 6 | -609.16 | 10727.9817 | 27505.92 | 29.5672 |  | 33.33%
supplemental | 324 | 14.88% | Contract Amendment | Line Item Omission | 83.02% | 269 | -6415.16 | 17730.0582 | 935795.51 | 2190.8065 |  | 3.346%
supplemental | 324 | 14.88% | Contract Amendment | Material Substitution Allowance | 0.6173% | 2 | 0 | 0 | 0 | 0 |  | 50%
supplemental | 324 | 14.88% | Contract Amendment | Mitigation of Potential Risk | 0.6173% | 2 | 7610.7 | 128805.35 | 250000 | 118.3329 |  | 50%
supplemental | 324 | 14.88% | Contract Amendment | Permission to Hold Additional Retainage | 0.3086% | 1 | 0 | 0 | 0 | 0 |  | 0%
supplemental | 324 | 14.88% | Contract Amendment | Revise Measurement and Payment Method | 5.556% | 18 | -0.02 | 2399.9989 | 43200 | 19.8438 |  | 16.67%
supplemental | 324 | 14.88% | Contract Amendment | Risk Management | 0.3086% | 1 | 2436.78 | 2436.78 | 2436.78 | 1.1193 |  | 0%
supplemental | 324 | 14.88% | Contract Amendment | Settlement and Release Agreement | 1.543% | 5 | 0 | 259519.614 | 796851.48 | 596.0487 |  | 40%
supplemental | 324 | 14.88% | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 1.543% | 5 | 0 | 48164.298 | 118554 | 110.6208 |  | 20%
supplemental | 178 | 8.176% | Stakeholder Request | DOT Request-Unspecified | 39.89% | 71 | -776503 | 272716.8324 | 10558379.25 | 8894.3018 |  | 7.042%
supplemental | 178 | 8.176% | Stakeholder Request | Stakeholder Request-Future Development Concerns | 6.18% | 11 | 1000 | 198859.7873 | 1783266.75 | 1004.8037 |  | 18.18%
supplemental | 178 | 8.176% | Stakeholder Request | Stakeholder Request-Unspecified | 53.93% | 96 | -213332.29 | 102218.4022 | 1952784.52 | 4507.5639 |  | 9.375%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1.156% | 2 | 2019.6 | 12827.8 | 23636 | 11.7848 |  | 0%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 2.312% | 4 | 373.75 | 20584.3175 | 67959.35 | 37.8214 |  | 25%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 1.734% | 3 | 12259.53 | 28199.8133 | 56892.63 | 38.8606 |  | 0%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Encountered Rock | 1.734% | 3 | 2859 | 16153.8067 | 41086.5 | 22.2606 |  | 0%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 2.312% | 4 | 364 | 43939.395 | 169430.68 | 80.7338 |  | 25%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 6.936% | 12 | -75183.28 | 10548.0142 | 84080.15 | 58.1425 |  | 0%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 1.156% | 2 | 4500 | 21094.76 | 37689.52 | 19.3797 |  | 0%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 14.45% | 25 | 365 | 14058.4024 | 170736.28 | 161.4424 |  | 4%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 41.04% | 71 | -31191.14 | 29784.318 | 448810.7 | 971.3765 |  | 7.042%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 11.56% | 20 | -9291 | 66144.8125 | 679248 | 607.6694 |  | 0%
supplemental | 173 | 7.947% | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 15.61% | 27 | 30 | 49364.5741 | 574495.19 | 612.2386 |  | 3.704%
supplemental | 156 | 7.166% | M&R/Replacement | Damaged Objects | 3.846% | 6 | 770 | 7061.08 | 24000 | 19.4609 |  | 16.67%
supplemental | 156 | 7.166% | M&R/Replacement | M&R/Replacement-Unspecified | 94.23% | 147 | -29240 | 42910.9041 | 665100 | 2897.5209 |  | 4.762%
supplemental | 156 | 7.166% | M&R/Replacement | Vehicular Accident | 1.923% | 3 | 75000 | 88689.76 | 112482 | 122.2183 |  | 0%
supplemental | 127 | 5.834% | Issues with Underground Utilities | Inability to Locate Utilities | 5.512% | 7 | 2178 | 5829.4657 | 11440 | 18.7443 |  | 0%
supplemental | 127 | 5.834% | Issues with Underground Utilities | Utilities not Relocated on Time | 5.512% | 7 | 0 | 112431.5114 | 720513.13 | 361.5161 |  | 0%
supplemental | 127 | 5.834% | Issues with Underground Utilities | Utility Conflict | 88.98% | 113 | -29660 | 24345.6471 | 679500 | 1263.6923 |  | 4.425%
supplemental | 118 | 5.42% | Safety Concerns (Except Contaminated Soil) | Falling Hazard | 4.237% | 5 | 3731.75 | 14520.108 | 30181.18 | 33.3489 |  | 0%
supplemental | 118 | 5.42% | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 6.78% | 8 | 4350 | 37163.1062 | 86772.1 | 136.5663 |  | 12.5%
supplemental | 118 | 5.42% | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 77.12% | 91 | -144361.63 | 34272.4363 | 1193795 | 1432.6099 |  | 5.495%
supplemental | 118 | 5.42% | Safety Concerns (Except Contaminated Soil) | Sight Distance Concerns | 0.8475% | 1 | 1265 | 1265 | 1265 | 0.58107 |  | 0%
supplemental | 118 | 5.42% | Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 10.17% | 12 | 0 | 6972.7742 | 33250 | 38.4351 |  | 8.333%
supplemental | 118 | 5.42% | Safety Concerns (Except Contaminated Soil) | Tripping Hazard | 0.8475% | 1 | 2710 | 2710 | 2710 | 1.2448 |  | 0%
supplemental | 112 | 5.145% | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 21.43% | 24 | -18500 | 11870.8208 | 82007.25 | 130.868 |  | 12.5%
supplemental | 112 | 5.145% | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 77.68% | 87 | -92820 | 39952.1889 | 1385864.68 | 1596.6194 |  | 0%
supplemental | 112 | 5.145% | Constructability Issues (Except Geotechnical/Underground Conflicts) | Height Clearance Issues | 0.8929% | 1 | 15004.74 | 15004.74 | 15004.74 | 6.8924 |  | 0%
supplemental | 75 | 3.445% | Construction Method Revision | Construction Method Revision-Unspecified | 100% | 75 | -100000 | 168713.0188 | 6689292.91 | 5812.3456 |  | 12%
supplemental | 54 | 2.48% | Access/ROW/Easement | Easement Acquisition Delays | 1.852% | 1 | 17541.7 | 17541.7 | 17541.7 | 8.0577 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 20.37% | 11 | 804.85 | 8014.5791 | 28682.23 | 40.4963 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | Insufficient ROW | 18.52% | 10 | 850 | 21644.26 | 68345.7 | 99.4224 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | Insufficient Utility Easement | 3.704% | 2 | 10725 | 367827.115 | 724929.23 | 337.9211 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | Property Owners Access | 18.52% | 10 | 950 | 12664.972 | 45200 | 58.1763 |  | 10%
supplemental | 54 | 2.48% | Access/ROW/Easement | Providing Access to Site | 11.11% | 6 | 423.5 | 9281.8617 | 20000 | 25.5816 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | Railroad Right of Entry Delays | 3.704% | 2 | 1650 | 2230 | 2810 | 2.0487 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | ROW Acquisition Delays | 1.852% | 1 | 30000 | 30000 | 30000 | 13.7804 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | ROW Revision | 1.852% | 1 | 490.6 | 490.6 | 490.6 | 0.22536 |  | 0%
supplemental | 54 | 2.48% | Access/ROW/Easement | Traffic Access Point | 18.52% | 10 | 900 | 16811.747 | 98911.83 | 77.2244 |  | 20%
supplemental | 54 | 2.48% | Erosion Control Problems | Erosion Control Problems-Unspecified | 96.3% | 52 | -418.8 | 15039.5937 | 289666.57 | 359.237 |  | 3.846%
supplemental | 54 | 2.48% | Erosion Control Problems | Waste Site Erosion Control | 3.704% | 2 | 1692.71 | 2892.585 | 4092.46 | 2.6574 |  | 0%
supplemental | 50 | 2.297% | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 96% | 48 | -546456 | 82869.2604 | 1903957.36 | 1827.1587 |  | 4.167%
supplemental | 50 | 2.297% | Quantities Overrun/Underrun | Waste Excessive Material | 4% | 2 | 0 | 0 | 0 | 0 |  | 0%
supplemental | 41 | 1.883% | Drainage Issues | Drainage Issues-Unspecified | 87.8% | 36 | 345 | 14569.6656 | 79942.34 | 240.9315 |  | 5.556%
supplemental | 41 | 1.883% | Drainage Issues | Stormwater Concerns | 12.2% | 5 | -587.5 | 5992.7 | 9391 | 13.7637 |  | 0%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Additional ICT Required | 2.941% | 1 | 0 | 0 | 0 | 0 |  | 0%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Availability Date Delays | 14.71% | 5 | 0 | 78597.418 | 251731.49 | 180.5177 |  | 0%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Conflict with Other Projects | 5.882% | 2 | -261882.5 | 39017 | 339916.5 | 35.8447 |  | 50%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 8.824% | 3 | 0 | 32330 | 59535 | 44.5521 |  | 66.67%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Early Project Completion | 41.18% | 14 | 0 | 377086.2236 | 3000000 | 2424.9918 |  | 42.86%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Miscommunication (Construction Progress) | 2.941% | 1 | 15000 | 15000 | 15000 | 6.8902 |  | 0%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Overtime Hour Request | 2.941% | 1 | 26294 | 26294 | 26294 | 12.0781 |  | 0%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Project Phasing Problems | 8.824% | 3 | 2006.61 | 20410.1367 | 45723.8 | 28.126 |  | 0%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Statewide Initiative to Accelerate Projects | 5.882% | 2 | 257971.7 | 477795.85 | 697620 | 438.9489 |  | 50%
supplemental | 34 | 1.562% | Scheduling and Coordination Issues | Timely Completion of Project | 5.882% | 2 | 4650 | 6875 | 9100 | 6.316 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Animal Protection/Endangered Species | 9.375% | 3 | 610.2 | 3267.5667 | 8000 | 4.5028 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Avoid Historical Structure | 3.125% | 1 | 5978.99 | 5978.99 | 5978.99 | 2.7464 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Construction Impacts | 6.25% | 2 | 18878 | 361060.375 | 703242.75 | 331.7045 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Environmental Concerns-Unspecified | 25% | 8 | -10599 | 1372277.8538 | 10663291.58 | 5042.8217 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Natural Disaster (Drought) | 3.125% | 1 | 24710 | 24710 | 24710 | 11.3505 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Noise Control | 6.25% | 2 | 19498.59 | 2022649.295 | 4025800 | 1858.1987 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Vegetation Establishment | 40.62% | 13 | -11611.4 | 52828.1769 | 666214.65 | 315.4645 |  | 0%
supplemental | 32 | 1.47% | Environmental/Community Concerns | Wetland Delineation | 6.25% | 2 | 718.75 | 759.825 | 800.9 | 0.69805 |  | 0%
supplemental | 30 | 1.378% | Procurement Issues | Error in Bill of Materials | 6.667% | 2 | 876.42 | 1875.71 | 2875 | 1.7232 |  | 0%
supplemental | 30 | 1.378% | Procurement Issues | Material Acquisition Delays/Long Lead Items | 16.67% | 5 | 0 | 35785.118 | 125390.84 | 82.1891 |  | 20%
supplemental | 30 | 1.378% | Procurement Issues | Material Fabrication Delay | 3.333% | 1 | 15895 | 15895 | 15895 | 7.3013 |  | 100%
supplemental | 30 | 1.378% | Procurement Issues | Shop Drawing Error | 10% | 3 | 580.06 | 3903.6767 | 7533.01 | 5.3794 |  | 0%
supplemental | 30 | 1.378% | Procurement Issues | Unavailability of Materials/Material Shortage | 60% | 18 | -22500 | 6740.2978 | 53088 | 55.7305 |  | 0%
supplemental | 30 | 1.378% | Procurement Issues | Wrong Order Placement | 3.333% | 1 | 18992.48 | 18992.48 | 18992.48 | 8.7242 |  | 0%
supplemental | 20 | 0.9187% | Survey/Test Issues | Additional Survey/Test Required | 30% | 6 | 1500 | 20052.08 | 63140.24 | 55.2653 |  | 0%
supplemental | 20 | 0.9187% | Survey/Test Issues | Survey Error-Staking | 25% | 5 | 400 | 1069.024 | 1875.12 | 2.4553 |  | 0%
supplemental | 20 | 0.9187% | Survey/Test Issues | Survey Error-Unspecified | 45% | 9 | 900 | 37691.1622 | 212548.82 | 155.8201 |  | 0%
supplemental | 16 | 0.735% | Other | Contractor Error | 12.5% | 2 | -6797.71 | 863.095 | 8523.9 | 0.79292 |  | 0%
supplemental | 16 | 0.735% | Other | Covid 19 Impact | 12.5% | 2 | 0 | 0 | 0 | 0 |  | 0%
supplemental | 16 | 0.735% | Other | Equipment/Items Protection | 18.75% | 3 | 302.6 | 4370.7733 | 10279.72 | 6.0231 |  | 0%
supplemental | 16 | 0.735% | Other | Permit Acquisition Issues | 6.25% | 1 | 4950 | 4950 | 4950 | 2.2738 |  | 0%
supplemental | 16 | 0.735% | Other | Permit Requirements | 25% | 4 | 1890.05 | 15857.2625 | 33391 | 29.136 |  | 0%
supplemental | 16 | 0.735% | Other | Permit Restrictions | 12.5% | 2 | 230 | 7754.375 | 15278.75 | 7.1239 |  | 0%
supplemental | 16 | 0.735% | Other | Site Security | 12.5% | 2 | 2565 | 30303.32 | 58041.64 | 27.8395 |  | 0%
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## 16a. Claim-Urban
Table 1 Claims - Urban | [9 empty] | Table 2 Claims - Urban
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 16.67% | 6 | 2.459% | 95664.05 | 2352.3947 | 74.6667 | 1.8361 | Design/Plan Issues | 56 | 22.95%
| Railroad Right of Entry | 1 | 16.67% | [6 empty] | Issues with Underground Utilities | 46 | 18.85%
| ROW Acquisition Delays-Property Owners Agreement | 1 | 16.67% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 23 | 9.426%
| ROW Acquisition Delays-Unspecified | 3 | 50% | [6 empty] | Contract Amendment | 19 | 7.787%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 7 | 100% | 7 | 2.869% | 0 | 0 | 92 | 2.6393 | Natural Disaster | 17 | 6.967%
Contract Amendment | Elimination of Contract Line Item | 1 | 5.263% | 19 | 7.787% | 16760.5 | 1305.1209 | 36.375 | 2.8325 | Quantities Overrun/Underrun | 16 | 6.557%
| Error in Entering Time Extensions in HiCAMS | 10 | 52.63% | [6 empty] | Project Closeout Issues | 14 | 5.738%
| Line Item Omission | 5 | 26.32% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 8 | 3.279%
| Revise Measurement and Payment Method | 1 | 5.263% | [6 empty] | M&R/Replacement | 8 | 3.279%
| Settlement and Release Agreement | 1 | 5.263% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 7 | 2.869%
| Unavailability of Funds/Cash Flow Considerations | 1 | 5.263% | [6 empty] | Differing Site Conditions (Except Utilities) | 7 | 2.869%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 2 | 25% | 8 | 3.279% | 0 | 0 | 86.5 | 2.8361 | Environmental/Community Concerns | 7 | 2.869%
| Untimely Review and Return of Submittals | 6 | 75% | [6 empty] | Access/ROW/Easement | 6 | 2.459%
Design/Plan Issues | Compliance with Standard Specifications | 2 | 3.571% | 56 | 22.95% | 72292.4639 | 16591.713 | 44.025 | 10.1041 | Procurement Issues | 5 | 2.049%
| Design/Plan Error-Unspecified | 17 | 30.36% | [6 empty] | Survey/Test Issues | 3 | 1.23%
| Design/Plan Revision-Unspecified | 37 | 66.07% | [6 empty] | Other | 1 | 0.4098%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 14.29% | 7 | 2.869% | 19933.78 | 571.8707 | 42 | 1.2049 | Permit | 1 | 0.4098%
| Differing Site Conditions-Contaminated Soil | 1 | 14.29%
| Differing Site Conditions-Hazardous Materials | 4 | 57.14% | [6 empty] | Table 3 "Design/Plan Issues" Category (RBS) | % (Design/Plan Issues)
| Differing Site Conditions-Incomplete Work by Others | 1 | 14.29% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 26.79%
Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 14.29% | 7 | 2.869% | 12551.2667 | 360.0773 | 98.4 | 2.823 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 19.64%
| Erosion Control Problems | 2 | 28.57% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 17.86%
| Vegetation Establishment | 3 | 42.86% | [6 empty] | Structure Design – bridge superstructure, bridge substructure, etc. | 7.143%
| Wetland Discovery | 1 | 14.29% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 7.143%
Issues with Underground Utilities | Utilities not Relocated on Time | 10 | 21.74% | 46 | 18.85% | 42028.7289 | 7923.4489 | 118.4762 | 22.3357 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 5.357%
| Utility Conflict | 36 | 78.26% | [6 empty] | Utility – design, as-builts, etc. | 5.357%
M&R/Replacement | M&R/Replacement-Damaged Objects | 1 | 12.5% | 8 | 3.279% | 13509.9425 | 442.9489 | 31 | 1.0164 | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 1.786%
| M&R/Replacement-Unspecified | 7 | 87.5% | [6 empty] | Unspecified | 8.929%
Natural Disaster | Natural Disaster-Drought | 1 | 5.882% | 17 | 6.967% | 3948.72 | 275.1157 | 41.375 | 2.8827
| Natural Disaster-Hurricane | 14 | 82.35%
| Natural Disaster-Sinkhole | 1 | 5.882%
| Natural Disaster-Thunderstorm | 1 | 5.882%
Other | Unforeseen Issues-Unspecified | 1 | 100% | 1 | 0.4098% | 2742.05 | 11.2379 | 3 | 0.012295
Permit | Permit Acquisition Waiting Period | 1 | 100% | 1 | 0.4098% | 0 | 0 | 36 | 0.14754
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 20% | 5 | 2.049% | 0 | 0 | 109.4 | 2.2418
| Power Supply Delays | 3 | 60%
| Unavailability of Materials/Material Shortage | 1 | 20%
Project Closeout Issues | Delay in Project Acceptance | 1 | 7.143% | 14 | 5.738% | 0 | 0 | 32 | 1.8361
| Delay in Receipt of Final Punchlist | 1 | 7.143%
| Final Punchlist Extra Work | 4 | 28.57%
| Scheduling Conflicts-Final Inspection/Punchlist | 8 | 57.14%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 16 | 100% | 16 | 6.557% | 102317.22 | 6709.3259 | 33.8889 | 2.2222
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 3 | 13.04% | 23 | 9.426% | 732970.215 | 69091.4547 | 21.6667 | 2.0423
| Early Project Completion | 1 | 4.348%
| Purposeful Limited Work Schedule | 14 | 60.87%
| Scheduling Conflicts-Inspection | 1 | 4.348%
| Waiting for Other Entities to Perform Work | 1 | 4.348%
| Work Out of Sequence | 1 | 4.348%
| Work Restriction-Social Event | 2 | 8.696%
Survey/Test Issues | Survey Error | 3 | 100% | 3 | 1.23% | 0 | 0 | 3.3333 | 0.040984

## 16b. SA-Urban
Table 1 Supplementary Agreements (Urban) | [7 empty] | Table 2 Supplementary Agreements (Urban) |  |  |  |  | Table 4 Supplementary Agreements (Urban)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | % |  |  | Generic Cause\Risk Area | Access/ROW/Easement | Contract | Corridor/Traffic Design | Environmental | Finishing and Interior Work | Geotechnical | Hydraulics | Other | Pavement | Procurement | Railroad | Roadway Alignment | Roadway Design | Safety | Schedule | Security/Protection | Structural | Survey | TCP (Construction Phase) | Traffic Control Systems (Except Pavement Markings) | Traffic Control Systems (pavement Markings) | Utilities | Grand Total
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 4 | 26.67% | 15 | 3.132% | 21302.192 | 667.0833 | Design/Plan Issues | 104 | 21.71% |  |  | Access/ROW/Easement | 66.67% | 0% | 0% | 0% | 6.667% | 6.667% | 0% | 0% | 0% | 0% | 6.667% | 0% | 6.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.667% | 100%
| Insufficient ROW | 4 | 26.67% |  |  |  |  | Contract Amendment | 74 | 15.45% |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 0% | 0% | 0% | 4.348% | 0% | 4.348% | 21.74% | 4.348% | 0% | 4.348% | 0% | 0% | 4.348% | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 0% | 30.43% | 100%
| Railroad Right of Entry Delays | 1 | 6.667% |  |  |  |  | Issues with Underground Utilities | 52 | 10.86% |  |  | Construction Method Revision | 0% | 0% | 0% | 0% | 0% | 18.18% | 13.64% | 4.545% | 4.545% | 0% | 0% | 0% | 0% | 0% | 4.545% | 0% | 0% | 0% | 27.27% | 9.091% | 0% | 18.18% | 100%
| ROW Acquisition Delays | 1 | 6.667% |  |  |  |  | Stakeholder Request | 47 | 9.812% |  |  | Contract Amendment | 4.054% | 8.108% | 2.703% | 1.351% | 0% | 9.459% | 16.22% | 2.703% | 4.054% | 0% | 0% | 0% | 8.108% | 0% | 0% | 0% | 2.703% | 0% | 6.757% | 8.108% | 8.108% | 17.57% | 100%
| ROW Revision | 1 | 6.667% |  |  |  |  | Differing Site Conditions (Except Utilities) | 42 | 8.768% |  |  | Design/Plan Issues | 0.9615% | 1.923% | 8.654% | 2.885% | 0% | 6.731% | 13.46% | 0% | 7.692% | 0.9615% | 0.9615% | 5.769% | 10.58% | 2.885% | 0% | 0% | 4.808% | 0% | 5.769% | 16.35% | 3.846% | 5.769% | 100%
| Traffic Access Point | 4 | 26.67% |  |  |  |  | M&R/Replacement | 29 | 6.054% |  |  | Differing Site Conditions (Except Utilities) | 0% | 0% | 0% | 2.381% | 0% | 21.43% | 16.67% | 0% | 14.29% | 0% | 0% | 2.381% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 0% | 23.81% | 100%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 9 | 39.13% | 23 | 4.802% | 12255.6952 | 588.4781 | Safety Concerns (Except Contaminated Soil) | 24 | 5.01% |  |  | Drainage Issues | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Constructability Issues-Unspecified | 14 | 60.87% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 23 | 4.802% |  |  | Environmental/Community Concerns | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Construction Method Revision | Construction Method Revision-Unspecified | 22 | 100% | 22 | 4.593% | 332088.6367 | 15252.5052 | Construction Method Revision | 22 | 4.593% |  |  | Erosion Control Problems | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Contract Amendment | Elimination of Contract Line Item | 2 | 2.703% | 74 | 15.45% | 12720.0915 | 1965.1081 | Access/ROW/Easement | 15 | 3.132% |  |  | Issues with Underground Utilities | 0% | 0% | 1.923% | 0% | 0% | 1.923% | 0% | 0% | 0% | 0% | 0% | 0% | 1.923% | 0% | 1.923% | 0% | 0% | 0% | 1.923% | 0% | 0% | 90.38% | 100%
| Issues with Previous SA | 1 | 1.351% |  |  |  |  | Scheduling and Coordination Issues | 11 | 2.296% |  |  | M&R/Replacement | 0% | 0% | 0% | 3.448% | 0% | 10.34% | 31.03% | 0% | 20.69% | 0% | 0% | 0% | 3.448% | 0% | 0% | 0% | 10.34% | 0% | 0% | 3.448% | 3.448% | 13.79% | 100%
| Line Item Omission | 61 | 82.43% |  |  |  |  | Drainage Issues | 10 | 2.088% |  |  | Other | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Revise Measurement and Payment Method | 7 | 9.459% |  |  |  |  | Erosion Control Problems | 8 | 1.67% |  |  | Procurement Issues | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 100%
| Settlement and Release Agreement | 3 | 4.054% |  |  |  |  | Procurement Issues | 5 | 1.044% |  |  | Quantities Overrun/Underrun | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 100%
Design/Plan Issues | Compliance with Standard Specifications | 13 | 12.5% | 104 | 21.71% | 153708.1566 | 33372.9609 | Quantities Overrun/Underrun | 5 | 1.044% |  |  | Safety Concerns (Except Contaminated Soil) | 0% | 0% | 4.167% | 4.167% | 0% | 0% | 4.167% | 0% | 0% | 0% | 0% | 0% | 8.333% | 12.5% | 0% | 0% | 0% | 0% | 58.33% | 4.167% | 4.167% | 0% | 100%
| Construction Plans Error/Discrepancy | 14 | 13.46% |  |  |  |  | Environmental/Community Concerns | 3 | 0.6263% |  |  | Scheduling and Coordination Issues | 0% | 0% | 9.091% | 0% | 0% | 9.091% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.27% | 0% | 9.091% | 0% | 18.18% | 0% | 9.091% | 0% | 100%
| Design Error-Elevation Difference with Existing Objects | 6 | 5.769% |  |  |  |  | Survey/Test Issues | 3 | 0.6263% |  |  | Stakeholder Request | 0% | 4.255% | 10.64% | 4.255% | 4.255% | 0% | 0% | 4.255% | 2.128% | 0% | 0% | 0% | 10.64% | 6.383% | 0% | 0% | 0% | 2.128% | 2.128% | 8.511% | 0% | 40.43% | 100%
| Design Error-Unspecified | 5 | 4.808% |  |  |  |  | Other | 2 | 0.4175% |  |  | Survey/Test Issues | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 0% | 0% | 0% | 33.33% | 100%
| Design Revision-Achieve Higher/Acceptable Quality | 5 | 4.808% | [9 empty] | Grand Total | 2.923% | 2.088% | 3.967% | 4.175% | 0.6263% | 7.516% | 13.15% | 1.253% | 5.219% | 1.044% | 0.4175% | 1.461% | 7.307% | 2.296% | 1.044% | 0.2088% | 2.296% | 0.6263% | 7.516% | 8.559% | 2.923% | 23.38% | 100%
| Design Revision-Fix Impacts of Previous Revisions | 3 | 2.885% |  |  |  |  | Table 3 Supplementary Agreements (Urban)
| Design Revision-Functionality Issues | 5 | 4.808% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Design Revision-Future Maintenance Concerns | 4 | 3.846% |  |  |  |  | Utilities | 112 | 23.38% | 16122.0464 | 3769.6643
| Design Revision-per Contractor Request | 4 | 3.846% |  |  |  |  | Hydraulics | 63 | 13.15% | 10029.6526 | 1319.1401
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 0.9615% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 41 | 8.559% | 21842.7178 | 1869.6272
| Design Revision-Unspecified | 38 | 36.54% |  |  |  |  | Geotechnical | 36 | 7.516% | 76279.8686 | 5732.9338
| Incomplete Design | 2 | 1.923% |  |  |  |  | TCP (Construction Phase) | 36 | 7.516% | 219074.3224 | 16464.876
| Increased Traffic Volume | 2 | 1.923% |  |  |  |  | Roadway Design | 35 | 7.307% | 318465.8223 | 23269.9453
| Scope Change | 2 | 1.923% |  |  |  |  | Pavement | 25 | 5.219% | 289761.7754 | 15123.2659
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 3 | 7.143% | 42 | 8.768% | 49098.909 | 4305.1235 | Environmental | 20 | 4.175% | 22410.628 | 935.7256
| Differing Site Conditions-Encountered Rock | 1 | 2.381% |  |  |  |  | Corridor/Traffic Design | 19 | 3.967% | 112890.35 | 4477.9053
| Differing Site Conditions-Extra Work from Previous Projects | 1 | 2.381% |  |  |  |  | Access/ROW/Easement | 14 | 2.923% | 17121.8071 | 500.4286
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 2.381% |  |  |  |  | Traffic Control Systems (pavement Markings) | 14 | 2.923% | 11595.7407 | 338.9152
| Differing Site Conditions-Incomplete Work by Others | 2 | 4.762% |  |  |  |  | Safety | 11 | 2.296% | 26435.6964 | 607.0828
| Differing Site Conditions-Not Shown in Construction Plans | 9 | 21.43% |  |  |  |  | Structural | 11 | 2.296% | 55317.6591 | 1270.3429
| Differing Site Conditions-Unspecified | 17 | 40.48% |  |  |  |  | Contract | 10 | 2.088% | 39736.6714 | 829.5756
| Differing Site Conditions-Unsuitable Materials | 2 | 4.762% |  |  |  |  | Roadway Alignment | 7 | 1.461% | 31018.0271 | 453.2906
| Slope Protection/Soil Stabilization | 6 | 14.29% |  |  |  |  | Other | 6 | 1.253% | 28581.5517 | 358.0153
Drainage Issues | Drainage Issues-Unspecified | 10 | 100% | 10 | 2.088% | 7573.286 | 158.1062 | Procurement | 5 | 1.044% | 13899.218 | 145.0858
Environmental/Community Concerns | Noise Control | 2 | 66.67% | 3 | 0.6263% | 1351882.8633 | 8466.9073 | Schedule | 5 | 1.044% | 53696.292 | 560.5041
| Vegetation Establishment | 1 | 33.33% |  |  |  |  | Finishing and Interior Work | 3 | 0.6263% | 14505.25 | 90.8471
Erosion Control Problems | Erosion Control Problems-Unspecified | 8 | 100% | 8 | 1.67% | 39731.1213 | 663.5678 | Survey | 3 | 0.6263% | 1546.9233 | 9.6885
Issues with Underground Utilities | Inability to Locate Utilities | 6 | 11.54% | 52 | 10.86% | 15415.3873 | 1673.4867 | Railroad | 2 | 0.4175% | 6964.9 | 29.081
| Utilities not Relocated on Time | 1 | 1.923% |  |  |  |  | Security/Protection | 1 | 0.2088% | 10279.72 | 21.4608
| Utility Conflict | 45 | 86.54%
M&R/Replacement | Damaged Objects | 1 | 3.448% | 29 | 6.054% | 39544.8293 | 2394.1546
| M&R/Replacement-Unspecified | 28 | 96.55%
Other | Equipment/Items Protection | 1 | 50% | 2 | 0.4175% | 5254.86 | 21.941
| Permit Restrictions | 1 | 50%
Procurement Issues | Material Fabrication Delay | 1 | 20% | 5 | 1.044% | 21477.97 | 224.1959
| Shop Drawing Error | 1 | 20%
| Unavailability of Materials/Material Shortage | 3 | 60%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 5 | 100% | 5 | 1.044% | 25297.598 | 264.0668
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 4.167% | 24 | 5.01% | 19414.0596 | 972.7295
| Safety Concerns-Unspecified | 22 | 91.67%
| Travelers/Public Safety | 1 | 4.167%
Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 9.091% | 11 | 2.296% | 74950.249 | 1721.1957
| Early Project Completion | 5 | 45.45%
| Miscommunication (Construction Progress) | 1 | 9.091%
| Project Phasing Problems | 2 | 18.18%
| Statewide Initiative to Accelerate Projects | 1 | 9.091%
| Timely Completion of Project | 1 | 9.091%
Stakeholder Request | DOT Request-Unspecified | 13 | 27.66% | 47 | 9.812% | 42581.9054 | 4178.1828
| Stakeholder Request-Future Development Concerns | 1 | 2.128%
| Stakeholder Request-Unspecified | 33 | 70.21%
Survey/Test Issues | Additional Survey/Test Required | 1 | 33.33% | 3 | 0.6263% | 21546.7467 | 134.9483
| Survey Error-Staking | 2 | 66.67%

## 2. Risk Profiles (Generic)
|  |  |  | Compensation Granted |  |  |  | Time Granted
Claim or SA | Generic Cause | Count Generic Cause | % Generic Cause | Min | Most Likely | Max | Expected Value | Min Time Granted (days) | Average Time Granted (days) | Max Time Granted (days) | Expected Value (Time)
claim | Design/Plan Issues | 258 | 16.17% | 308 | 64426.239 | 851737.48 | 10414.768 | 1 | 53.6337 | 556 | 8.6701
claim | Issues with Underground Utilities | 235 | 14.72% | 726.43 | 165812.2602 | 2983542.8 | 24414.7125 | 1 | 95.555 | 860 | 14.0698
claim | Natural Disaster | 141 | 8.835% | 3300 | 37302.78 | 132293.2 | 3295.5464 | 1 | 27.2336 | 393 | 2.406
claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 141 | 8.835% | 547.44 | 137963.9153 | 1430000 | 12188.5414 | 1 | 37.3876 | 862 | 3.303
claim | Contract Amendment | 127 | 7.957% | 600.88 | 695798.9243 | 20600000 | 55367.4583 | 1 | 69.2041 | 466 | 5.5068
claim | Project Closeout Issues | 109 | 6.83% | 2000 | 2000 | 2000 | 136.5915 | 1 | 19.1651 | 201 | 1.3089
claim | Constructability Issues (Except Geotechnical/Underground Conflicts) | 94 | 5.89% | 2063 | 34563.1064 | 124500 | 2035.6717 | 2 | 79.875 | 334 | 4.7044
claim | Quantities Overrun/Underrun | 76 | 4.762% | 212.5 | 98518.4124 | 1023042.77 | 4691.353 | 1 | 32.0811 | 250 | 1.5277
claim | M&R/Replacement | 75 | 4.699% | 654.07 | 41356.24 | 470647.87 | 1943.4323 | 1 | 68.9 | 788 | 3.2378
claim | Environmental/Community Concerns | 68 | 4.261% | 746.04 | 8527.2144 | 30621.65 | 363.3149 | 1 | 117.25 | 740 | 4.9956
claim | Design Approval Waiting Period/Indecision/Negotiation | 55 | 3.446% | 12714.68 | 16409.955 | 20105.23 | 565.506 | 3 | 51.8704 | 364 | 1.7875
claim | Differing Site Conditions (Except Utilities) | 49 | 3.07% | 1330 | 18494.2114 | 84439.77 | 567.8047 | 1 | 32 | 296 | 0.98246
claim | Procurement Issues | 48 | 3.008% | 3611.33 | 20273.3533 | 77894.29 | 609.7249 | 1 | 77.4884 | 513 | 2.3305
claim | Access/ROW/Easement | 34 | 2.13% | 5531.09 | 754429.9125 | 4430869 | 16071.8152 | 1 | 78.6129 | 298 | 1.6747
claim | Start Date Delays | 33 | 2.068% |  |  |  | 0 | 3 | 29.4545 | 213 | 0.60902
claim | Survey/Test Issues | 24 | 1.504% | 650 | 51268.072 | 406401.29 | 770.9485 | 1 | 16.2941 | 75 | 0.24502
claim | Permit | 17 | 1.065% | 2942.65 | 44341.6633 | 117142.68 | 472.311 | 8 | 47.625 | 173 | 0.50728
claim | Other | 12 | 0.7519% | 1998.65 | 45898.3683 | 144300 | 345.1005 | 2 | 120.1429 | 375 | 0.90333
supplemental | Design/Plan Issues | 583 | 26.78% | -1154813.66 | 70521.848 | 5913904.72 | 18885.7315 |  | 11.84%
supplemental | Contract Amendment | 324 | 14.88% | -320155 | 48353.91 | 6597392.7 | 7196.4478 |  | 7.716%
supplemental | Stakeholder Request | 178 | 8.176% | -776503 | 176198.4234 | 10558379.25 | 14406.6694
supplemental | Differing Site Conditions (Except Utilities) | 173 | 7.947% | -75183.28 | 32991.1179 | 679248 | 2621.7103 |  | 5.202%
supplemental | M&R/Replacement | 156 | 7.166% | -29240 | 42412.4273 | 665100 | 3039.2001 |  | 1.282%
supplemental | Issues with Underground Utilities | 127 | 5.834% | -29660 | 28180.1965 | 720513.13 | 1643.9527 |  | 6.299%
supplemental | Safety Concerns (Except Contaminated Soil) | 118 | 5.42% | -144361.63 | 30308.0117 | 1193795 | 1642.7861 |  | 13.56%
supplemental | Constructability Issues (Except Geotechnical/Underground Conflicts) | 112 | 5.145% | -92820 | 33712.0078 | 1385864.68 | 1734.3798 |  | 2.679%
supplemental | Construction Method Revision | 75 | 3.445% | -100000 | 168713.0188 | 6689292.91 | 5812.3456 |  | 12%
supplemental | Access/ROW/Easement | 54 | 2.48% | 423.5 | 26726.0715 | 724929.23 | 662.9342 |  | 5.556%
supplemental | Erosion Control Problems | 54 | 2.48% | -418.8 | 14589.7044 | 289666.57 | 361.8944 |  | 9.259%
supplemental | Quantities Overrun/Underrun | 50 | 2.297% | -546456 | 79554.49 | 1903957.36 | 1827.1587 |  | 20%
supplemental | Drainage Issues | 41 | 1.883% | -587.5 | 13523.6941 | 79942.34 | 254.6952 |  | 4.878%
supplemental | Scheduling and Coordination Issues | 34 | 1.562% | -261882.5 | 203502.4803 | 3000000 | 3178.2657
supplemental | Environmental/Community Concerns | 32 | 1.47% | -11611.4 | 514825.6191 | 10663291.58 | 7567.4873 |  | 6.25%
supplemental | Procurement Issues | 30 | 1.378% | -22500 | 11686.696 | 125390.84 | 161.0477 |  | 23.33%
supplemental | Survey/Test Issues | 20 | 0.9187% | 400 | 23243.903 | 212548.82 | 213.5407
supplemental | Other | 16 | 0.735% | -6797.71 | 9958.3094 | 58041.64 | 73.1892 |  | 12.5%
| Total Claims | 1596 | 100% |  |  |  | 0 |  |  |  | 0
| Total SA | 2177 | 100% |  |  |  | 0 |  |  |  | 0
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.