## 0. Cover
PROCESS:
STEP 1: Become familiar with risks on NCDOT projects
Risks specific to Claims and Supplemental Agreements
Summary of Claims
Summary of Supplemental Agreements
Summary of Design/Plan Issues
Summary of Other Issues
STEP 2: Identify Risks by Project Type
| Appalachian Regional Commission | Claims | Supplemental Agreements
| Bicycle and Pedestrian | Claims | Supplemental Agreements
| Bridge Replacement | Claims | Supplemental Agreements
| Ferry | Claims | Supplemental Agreements
| Highway Safety | Claims | Supplemental Agreements
| Interstate | Claims | Supplemental Agreements
| Rail | Claims | Supplemental Agreements
| Railroad - HW Crossings | Claims | Supplemental Agreements
| Rest Area | Claims | Supplemental Agreements
| Rural | Claims | Supplemental Agreements
| Safe Route to School | Claims | Supplemental Agreements
| Urban | Claims | Supplemental Agreements
| Other | Claims | Supplemental Agreements
STEP 3: Identify Risk Mitigation Strategies
Roadway
ROW
Structures
Utilities
Rail
Other
NCDOT Risk Management Tool
The Risk Management Tool (RMT) (1) is a comprehensive software product which offers project managers and their teams a structured approach to identifying and mitigating potential risks, thus leading to better risk management outcomes. RMT provides risk insights for several project categories (e.g., Interstate, Ferry, Rest Area, and Urban) and is based on data from past NCDOT claims and supplemental agreements. Mitigation strategies are also provided for six critical areas of transportation projects: (1) Roadway, (2) Right-of-Way (ROW), (3) Structures, (4) Utilities, (5) Rail, and (6) Other. It can be used to assist NCDOT project management teams in identifying potential risks as well as their cost and schedule impacts during project planning, design, and construction and can assist in completing the Risk Assessment Worksheet (RAW).
RMT contains several tabs beginning with a description of overall project Risk Areas and Design/Plan issues commonly found in transportation projects (tab 1.). An overall summary is provided for all NCDOT claims and supplemental agreements showing percentage of occurrence of specific risks as well as their cost and schedule impact (tabs 2a. and 2b, respectively). A description of the NCDOT design-plan and other issues can be found in tabs 3a. and 3b., respectively. A breakdown of the claims and supplemental agreements by project type (e.g., Urban, Interstate, Rural, and Ferry) is provided in tabs 4a/4b through 16a/16b (e.g., a is for claims and b is for supplemental agreements). Mitigation strategies are shown in tabs 17a. through 17f.
(1) Developed through research grant NCDOT Project 2020-2274.
INTRODUCTION

## 1. Causes for Claims and SAs
Return to Cover Page
2.1 Claims: Generic Causes (GC) and more Specific Causes (GC Level 2)
1. Design/Plan Issues: Problems arising from flaws in the project design or plans.
Compliance with Standard Specifications
Design/Plan Error-Unspecified
Design/Plan Revision-Unspecified
Increased Traffic Volume
2. Issues with Underground Utilities: Difficulties encountered during construction due to conflicts with existing underground utilities.
Utilities not Relocated on Time
Utility Conflict
3. Natural Disaster: Unforeseen natural disasters such as hurricanes, tornadoes, and floods that impact project progress and completion.
Natural Disaster-Drought
Natural Disaster-Flood
Natural Disaster-Hurricane
Natural Disaster-Sink Hole
Natural Disaster-Slide
Natural Disaster-Thunderstorm
Natural Disaster-Tropical Depression
4. Scheduling and Coordination Issues (Except Start of Work and/or Project Closeout): Challenges with coordinating different aspects of the project, such as subcontractor schedules or scheduling of inspections.
Conflict/Overlap with Other Projects
Coordination Issues-DOT Personnel Unavailability
Coordination Issues-Unspecified
Early Project Completion
Miscommunication (Construction Progress)
Purposeful Limited Work Schedule
Scheduling Conflicts-Inspection
Timely Completion of Project
Waiting for Other Entities to Perform Work
Work Out of Sequence
Work Restriction-Social Event
Work Restriction-Unspecified
5. Contract Amendment: Modifications made to the project contract, resulting in changes in contract line items, schedule, or budget.
Contract Error
Contract Time Adjustment
Contractor Replacement
Elimination of Contract Line Item
Error in Entering Time Extensions in HiCAMS
Line Item Omission
Revise Measurement and Payment Method
Settlement and Release Agreement
Unavailability of Funds/Cash Flow Considerations
6. Project Closeout Issues: Difficulties encountered during project closeout, such as delays in scheduling final inspections or resolving outstanding disputes.
Delay in Project Acceptance
Delay in Receipt of Final Punchlist
Final Punchlist Extra Work
Scheduling Conflicts-Final Inspection/Punchlist
7. Constructability Issues (Except Geotechnical/Underground Conflicts): Issues related to the feasibility and practicality of constructing the project, except for conflicts with geotechnical or underground conditions.
Conflict with Existing (Surface) Objects
Constructability Issues-Seasonal Limitations (Weather)
Constructability Issues-Unspecified
8. Quantities Overrun/Underrun: Variances between the planned and actual amounts of materials, labor, or other resources required for the project.
Quantities Overrun/Underrun-Unspecified
9. M&R/Replacement: Costs incurred due to maintenance and repair or replacement of existing infrastructure or equipment.
M&R/Replacement-Damaged Objects
M&R/Replacement-Unspecified
Vehicular Accident
10. Environmental/Community Concerns: Issues arising from environmental regulations, community opposition, or other social factors.
Animal Protection/Endangered Species
Environmental Concerns/Unspecified
Erosion Control Problems
Historical Site
Vegetation Establishment
Wetland Discovery
11. Design Approval Waiting Period/Indecision/Negotiation: Delays in obtaining approvals for project designs, due to indecision or negotiation issues.
Document Misplacement
Indecision-Unspecified
Negotiation Delays
Untimely Receipt of Design
Untimely Review and Return of Submittals
Untimely Review of Approvals
12. Differing Site Conditions (Except Utilities): Unforeseen subsurface or soil conditions that differ from those indicated in the project plans, except for conflicts with underground utilities.
Differing Site Conditions-Buried Objects
Differing Site Conditions-Contaminated Groundwater
Differing Site Conditions-Contaminated Soil
Differing Site Conditions-Groundwater Discovery/High Groundwater Level
Differing Site Conditions-Hazardous Materials
Differing Site Conditions-Incomplete Work by Others
Differing Site Conditions-Unspecified
Differing Site Conditions-Unsuitable Materials
13. Procurement Issues: Difficulties with the procurement of materials or equipment needed for the project.
DOT Furnished Materials/Equipment Delays
Material Acquisition Delays/Long Lead Items
Material Cost Fluctuation
Material Fabrication Delay
Power Supply Delays
Unavailability of Materials/Material Shortage
Wrong Order Placement
14. Access/ROW/Easement: Challenges related to obtaining the necessary rights-of-way or easements to access the project site.
Extra Work Associated with ROW Agreement
Insufficient Right of Entry
Insufficient ROW
Railroad Right of Entry
Right of Entry Acquisition Delays
ROW Acquisition Delays-Property Owners Agreement
ROW Acquisition Delays-Unspecified
15. Start Date Delays: Delays in starting the project due to issues such as delays to preconstruction meeting, approvals, or unforeseen circumstances.
Delay in Availability of Project
Delay in Contract Execution
Delay in Preconstruction Meeting
Delay in Project Award
Delay in Receipt of Contract Information and Bonds
Start Date Delays-Unspecified
16. Survey/Test Issues: Problems arising from inaccuracies or inconsistencies in project surveys or tests.
Additional Survey-Test Required
Survey Error
Survey Results Delays
17. Permit: Difficulties obtaining necessary permits for the project from regulatory agencies.
Insufficient Permit
Permit Acquisition Waiting Period
Permit Expiration
Permit Limitation
Permit Violation
18. Other: Any other issues not covered by the previous categories.
Covid 19 Impact
Lawsuit Costs
Misinterpretation of Plans
Unavailability of Labor
Unforeseen Issues-Unspecified
2.2 Supplemental Agreements: Generic Causes (GC) and more Specific Causes (GC Level 2)
1. Design/Plan Issues: Problems arising from flaws in the project design or plans.
Compliance with Standard Specifications
Construction Plans Error/Discrepancy
Design Error-Elevation Difference with Existing Objects
Design Error-Unspecified
Design Revision-Achieve Higher/Acceptable Quality
Design Revision-Change in Design Criteria
Design Revision-Fix Impacts of Previous Revisions
Design Revision-Functionality Issues
Design Revision-Future Maintenance Concerns
Design Revision-per Contractor Request
Design Revision-Toll Collection
Design Revision-Uniformity with Adjacent Projects/Objects
Design Revision-Unspecified
Design Revision-Value Engineering Proposal
Incomplete Design
Increased Traffic Volume
Scope Change
2. Contract Amendment: Modifications made to the project contract, resulting in changes in contract line items, schedule, or budget.
Change in Contract Provisions
Contingency Item
Elimination of Contract Line Item
Insufficient Insurance
Issues with Previous SA
Line Item Omission
Material Substitution Allowance
Mitigation of Potential Risk
Permission to Hold Additional Retainage
Revise Measurement and Payment Method
Risk Management
Settlement and Release Agreement
Unavailability of Funds/Cash Flow Considerations
3. Stakeholder Request: Requests made by external stakeholders, such as local government entities or nearby residents, that require changes to the project.
DOT Request-Unspecified
Stakeholder Request-Future Development Concerns
Stakeholder Request-Unspecified
4. Differing Site Conditions (Except Utilities): Unforeseen site conditions that differ from what was expected, but do not involve underground utilities.
Differing Site Conditions-Buried Objects
Differing Site Conditions-Changes in Site After Bid/During Construction
Differing Site Conditions-Contaminated Soil
Differing Site Conditions-Encountered Rock
Differing Site Conditions-Extra Work from Previous Projects
Differing Site Conditions-Groundwater Discovery/High Groundwater Level
Differing Site Conditions-Incomplete Work by Others
Differing Site Conditions-Not Shown in Construction Plans
Differing Site Conditions-Unspecified
Differing Site Conditions-Unsuitable Materials
Slope Protection/Soil Stabilization
5. M&R/Replacement: Maintenance and repair or replacement of existing infrastructure or equipment.
Damaged Objects
M&R/Replacement-Unspecified
Vehicular Accident
6. Issues with Underground Utilities: Issues related to underground utilities, such as conflicts or damages.
Inability to Locate Utilities
Utilities not Relocated on Time
Utility Conflict
7. Safety Concerns (Except Contaminated Soil): Safety issues that arise during the project, such as accidents or hazards, excluding those related to contaminated soil.
Falling Hazard
Hazardous Materials Removal
Safety Concerns-Unspecified
Sight Distance Concerns
Travelers/Public Safety
Tripping Hazard
8. Constructability Issues (Except Geotechnical/Underground Conflicts): Issues related to the constructability of the project, such as difficulties in executing the design or plans, excluding those related to geotechnical or underground conflicts.
Conflict with Existing (Surface) Objects
Constructability Issues-Unspecified
Height Clearance Issues
9. Construction Method Revision: Changes made to the construction methods or techniques used in the project.
Construction Method Revision-Unspecified
10. Access/ROW/Easement: Issues related to access to the project site or right-of-way or easement concerns.
Easement Acquisition Delays
Extra Work Associated with ROW Agreement
Insufficient ROW
Insufficient Utility Easement
Property Owners Access
Providing Access to Site
Railroad Right of Entry Delays
ROW Acquisition Delays
ROW Revision
Traffic Access Point
11. Erosion Control Problems: Issues related to erosion control measures or practices.
Erosion Control Problems-Unspecified
Waste Site Erosion Control
12. Quantities Overrun/Underrun: Variances in the quantities of materials or labor required for the project, resulting in overruns or underruns.
Quantities Overrun/Underrun-Unspecified
Waste Excessive Material
13. Drainage Issues: Issues related to drainage systems or measures.
Drainage Issues-Unspecified
Stormwater Concerns
14. Scheduling and Coordination Issues: Issues related to project scheduling or coordination with other stakeholders or activities.
Additional ICT Required
Availability Date Delays
Conflict with Other Projects
Conflict/Overlap with Adjacent Projects
Early Project Completion
Miscommunication (Construction Progress)
Overtime Hour Request
Project Phasing Problems
Statewide Initiative to Accelerate Projects
Timely Completion of Project
15. Environmental/Community Concerns: Issues related to environmental or community impacts of the project.
Animal Protection/Endangered Species
Avoid Historical Structure
Construction Impacts
Environmental Concerns-Unspecified
Natural Disaster (Drought)
Noise Control
Vegetation Establishment
Wetland Delineation
16. Procurement Issues: Issues related to the procurement of materials or services for the project.
Error in Bill of Materials
Material Acquisition Delays/Long Lead Items
Material Fabrication Delay
Shop Drawing Error
Unavailability of Materials/Material Shortage
Wrong Order Placement
17. Survey/Test Issues: Issues related to surveys or testing conducted during the project.
Additional Survey/Test Required
Survey Error-Staking
Survey Error-Unspecified
18. Other: Any other issues not covered by the above categories.
Contractor Error
Covid 19 Impact
Equipment/Items Protection
Permit Acquisition Issues
Permit Requirements
Permit Restrictions
Site Security

## 2a. Summary-All Claims
Return to Cover Page
2a. -- Table 2 Claims - All Project Types | [9 empty] | 2a. -- Table 1 Claims - All Project Types--Based on Generic Cause
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Design/Plan Issues | Compliance with Standard Specifications | 12 | 4.651% | 258 | 16.17% | 64426.239 | 10414.768 | 53.6337 | 8.6701 | Design/Plan Issues | 258 | 16.17%
| Design/Plan Error-Unspecified | 71 | 27.52% | [6 empty] | Issues with Underground Utilities | 235 | 14.72%
| Design/Plan Revision-Unspecified | 172 | 66.67% | [6 empty] | Natural Disaster | 141 | 8.835%
| Increased Traffic Volume | 3 | 1.163% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or Project Closeout) | 141 | 8.835%
Issues with Underground Utilities | Utilities not Relocated on Time | 72 | 30.64% | 235 | 14.72% | 165812.2602 | 24414.7125 | 95.555 | 14.0698 | Contract Amendment | 127 | 7.957%
| Utility Conflict | 163 | 69.36% | [6 empty] | Project Closeout Issues | 109 | 6.83%
Natural Disaster | Natural Disaster-Drought | 2 | 1.418% | 141 | 8.835% | 37302.78 | 3295.5464 | 27.2336 | 2.406 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 94 | 5.89%
| Natural Disaster-Flood | 1 | 0.7092% | [6 empty] | Quantities Overrun/Underrun | 76 | 4.762%
| Natural Disaster-Hurricane | 133 | 94.33% | [6 empty] | M&R/Replacement | 75 | 4.699%
| Natural Disaster-Sinkhole | 1 | 0.7092% | [6 empty] | Environmental/Community Concerns | 68 | 4.261%
| Natural Disaster-Slide | 2 | 1.418% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 55 | 3.446%
| Natural Disaster-Thunderstorm | 1 | 0.7092% | [6 empty] | Differing Site Conditions (Except Utilities) | 49 | 3.07%
| Natural Disaster-Tropical Depression | 1 | 0.7092% | [6 empty] | Procurement Issues | 48 | 3.008%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 11 | 7.801% | 141 | 8.835% | 137963.9153 | 12188.5414 | 37.3876 | 3.5568 | Access/ROW/Easement | 34 | 2.13%
| Coordination Issues-DOT Personnel Unavailability | 12 | 8.511% | [6 empty] | Start Date Delays | 33 | 2.068%
| Coordination Issues-Unspecified | 3 | 2.128% | [6 empty] | Survey/Test Issues | 24 | 1.504%
| Early Project Completion | 1 | 0.7092% | [6 empty] | Permit | 17 | 1.065%
| Miscommunication (Construction Progress) | 3 | 2.128% | [6 empty] | Other | 12 | 0.7519%
| Purposeful Limited Work Schedule | 42 | 29.79%
| Scheduling Conflicts-Inspection | 10 | 7.092%
| Timely Completion of Project | 1 | 0.7092%
| Waiting for Other Entities to Perform Work | 13 | 9.22%
| Work Out of Sequence | 9 | 6.383%
| Work Restriction-Social Event | 20 | 14.18%
| Work Restriction-Unspecified | 16 | 11.35%
Contract Amendment | Contract Error | 6 | 4.724% | 127 | 7.957% | 695798.9243 | 55367.4583 | 69.2041 | 5.0015
| Contract Time Adjustment | 4 | 3.15%
| Contractor Replacement | 2 | 1.575%
| Elimination of Contract Line Item | 9 | 7.087%
| Error in Entering Time Extensions in HiCAMS | 49 | 38.58%
| Line Item Omission | 23 | 18.11%
| Revise Measurement and Payment Method | 2 | 1.575%
| Settlement and Release Agreement | 27 | 21.26%
| Unavailability of Funds/Cash Flow Considerations | 5 | 3.937%
Project Closeout Issues | Delay in Project Acceptance | 1 | 0.9174% | 109 | 6.83% | 2000 | 136.5915 | 19.1651 | 1.5406
| Delay in Receipt of Final Punchlist | 1 | 0.9174%
| Final Punchlist Extra Work | 12 | 11.01%
| Scheduling Conflicts-Final Inspection/Punchlist | 95 | 87.16%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 4 | 4.255% | 94 | 5.89% | 34563.1064 | 2035.6717 | 79.875 | 5.1836
| Constructability Issues-Seasonal Limitations (Weather) | 87 | 92.55%
| Constructability Issues-Unspecified | 3 | 3.191%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 76 | 100% | 76 | 4.762% | 98518.4124 | 4691.353 | 32.0811 | 0.87537
M&R/Replacement | M&R/Replacement-Damaged Objects | 4 | 5.333% | 75 | 4.699% | 41356.24 | 1943.4323 | 68.9 | 2.5406
| M&R/Replacement-Unspecified | 68 | 90.67%
| Vehicular Accident | 3 | 4%
Environmental/Community Concerns | Animal Protection/Endangered Species | 2 | 2.941% | 68 | 4.261% | 8527.2144 | 363.3149 | 117.25 | 5.1881
| Environmental Concerns/Unspecified | 6 | 8.824%
| Erosion Control Problems | 4 | 5.882%
| Historical Site | 1 | 1.471%
| Vegetation Establishment | 53 | 77.94%
| Wetland Discovery | 2 | 2.941%
Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement | 1 | 1.818% | 55 | 3.446% | 16409.955 | 565.506 | 51.8704 | 2.0656
| Indecision-Unspecified | 31 | 56.36%
| Negotiation Delays | 2 | 3.636%
| Untimely Receipt of Design | 3 | 5.455%
| Untimely Review and Return of Submittals | 14 | 25.45%
| Untimely Review of Approvals | 4 | 7.273%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 10 | 20.41% | 49 | 3.07% | 18494.2114 | 567.8047 | 32 | 0.84956
| Differing Site Conditions-Contaminated Groundwater | 1 | 2.041%
| Differing Site Conditions-Contaminated Soil | 2 | 4.082%
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 8 | 16.33%
| Differing Site Conditions-Hazardous Materials | 4 | 8.163%
| Differing Site Conditions-Incomplete Work by Others | 7 | 14.29%
| Differing Site Conditions-Unspecified | 3 | 6.122%
| Differing Site Conditions-Unsuitable Materials | 14 | 28.57%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 6 | 12.5% | 48 | 3.008% | 20273.3533 | 609.7249 | 77.4884 | 2.4572
| Material Acquisition Delays/Long Lead Items | 11 | 22.92%
| Material Cost Fluctuation | 2 | 4.167%
| Material Fabrication Delay | 1 | 2.083%
| Power Supply Delays | 17 | 35.42%
| Unavailability of Materials/Material Shortage | 8 | 16.67%
| Wrong Order Placement | 3 | 6.25%
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 2 | 5.882% | 34 | 2.13% | 754429.9125 | 16071.8152 | 78.6129 | 1.7972
| Insufficient Right of Entry | 1 | 2.941%
| Insufficient ROW | 3 | 8.824%
| Railroad Right of Entry | 9 | 26.47%
| Right of Entry Acquisition Delays | 1 | 2.941%
| ROW Acquisition Delays-Property Owners Agreement | 2 | 5.882%
| ROW Acquisition Delays-Unspecified | 16 | 47.06%
Start Date Delays | Delay in Availability of Project | 1 | 3.03% | 33 | 2.068% | - | 0 | 29.4545 | 0.71681
| Delay in Contract Execution | 16 | 48.48%
| Delay in Preconstruction Meeting | 9 | 27.27%
| Delay in Project Award | 4 | 12.12%
| Delay in Receipt of Contract Information and Bonds | 1 | 3.03%
| Start Date Delays-Unspecified | 2 | 6.061%
Survey/Test Issues | Additional Survey-Test Required | 4 | 16.67% | 24 | 1.504% | 51268.072 | 770.9485 | 16.2941 | 0.20428
| Survey Error | 18 | 75%
| Survey Results Delays | 2 | 8.333%
Permit Issues | Insufficient Permit | 2 | 11.76% | 17 | 1.065% | 44341.6633 | 472.311 | 47.625 | 0.56195
| Permit Acquisition Waiting Period | 11 | 64.71%
| Permit Expiration | 1 | 5.882%
| Permit Limitation | 2 | 11.76%
| Permit Violation | 1 | 5.882%
Other Issues | Covid 19 Impact | 3 | 25% | 12 | 0.7519% | 45898.3683 | 345.1005 | 120.1429 | 0.62021
| Lawsuit Costs | 1 | 8.333%
| Misinterpretation of Plans | 2 | 16.67%
| Unavailability of Labor | 2 | 16.67%
| Unforeseen Issues-Unspecified | 4 | 33.33%

## 2b. Summary-All SAs
Return to Cover Page
2b. -- Table 2 Supplemental Agreements (All Project Types) | [7 empty] | 2b. -- Table 1 Supplemental Agreements (All Project Types)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Easement Acquisition Delays | 1 | 1.852% | 54 | 2.48% | 26726.0715 | 662.9342 | Design/Plan Issues | 583 | 26.78%
| Extra Work Associated with ROW Agreement | 11 | 20.37% |  |  |  |  | Contract Amendment | 324 | 14.88%
| Insufficient ROW | 10 | 18.52% |  |  |  |  | Stakeholder Request | 178 | 8.176%
| Insufficient Utility Easement | 2 | 3.704% |  |  |  |  | Differing Site Conditions (Except Utilities) | 173 | 7.947%
| Property Owners Access | 10 | 18.52% |  |  |  |  | M&R/Replacement | 156 | 7.166%
| Providing Access to Site | 6 | 11.11% |  |  |  |  | Issues with Underground Utilities | 127 | 5.834%
| Railroad Right of Entry Delays | 2 | 3.704% |  |  |  |  | Safety Concerns (Except Contaminated Soil) | 118 | 5.42%
| ROW Acquisition Delays | 1 | 1.852% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 112 | 5.145%
| ROW Revision | 1 | 1.852% |  |  |  |  | Construction Method Revision | 75 | 3.445%
| Traffic Access Point | 10 | 18.52% |  |  |  |  | Access/ROW/Easement | 54 | 2.48%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 24 | 21.43% | 112 | 5.145% | 34581.1136 | 1779.0927 | Erosion Control Problems | 54 | 2.48%
| Constructability Issues-Unspecified | 87 | 77.68% |  |  |  |  | Quantities Overrun/Underrun | 50 | 2.297%
| Height Clearance Issues | 1 | 0.8929% |  |  |  |  | Drainage Issues | 41 | 1.883%
Construction Method Revision | Construction Method Revision-Unspecified | 75 | 100% | 75 | 3.445% | 183383.7161 | 6317.767 | Scheduling and Coordination Issues | 34 | 1.562%
Contract Amendment | Change in Contract Provisions | 6 | 1.852% | 324 | 14.88% | 52388.5095 | 7796.9118 | Environmental/Community Concerns | 32 | 1.47%
| Contingency Item | 1 | 0.3086% |  |  |  |  | Procurement Issues | 30 | 1.378%
| Elimination of Contract Line Item | 7 | 2.16% |  |  |  |  | Survey/Test Issues | 20 | 0.9187%
| Insufficient Insurance | 1 | 0.3086% |  |  |  |  | Other | 16 | 0.735%
| Issues with Previous SA | 6 | 1.852%
| Line Item Omission | 269 | 83.02%
| Material Substitution Allowance | 2 | 0.6173%
| Mitigation of Potential Risk | 2 | 0.6173%
| Permission to Hold Additional Retainage | 1 | 0.3086%
| Revise Measurement and Payment Method | 18 | 5.556%
| Risk Management | 1 | 0.3086%
| Settlement and Release Agreement | 5 | 1.543%
| Unavailability of Funds/Cash Flow Considerations | 5 | 1.543%
Design/Plan Issues | Compliance with Standard Specifications | 65 | 11.15% | 583 | 26.78% | 75025.9807 | 20091.9369
| Construction Plans Error/Discrepancy | 40 | 6.861%
| Design Error-Elevation Difference with Existing Objects | 19 | 3.259%
| Design Error-Unspecified | 49 | 8.405%
| Design Revision-Achieve Higher/Acceptable Quality | 16 | 2.744%
| Design Revision-Change in Design Criteria | 1 | 0.1715%
| Design Revision-Fix Impacts of Previous Revisions | 10 | 1.715%
| Design Revision-Functionality Issues | 8 | 1.372%
| Design Revision-Future Maintenance Concerns | 16 | 2.744%
| Design Revision-per Contractor Request | 36 | 6.175%
| Design Revision-Toll Collection | 1 | 0.1715%
| Design Revision-Uniformity with Adjacent Projects/Objects | 8 | 1.372%
| Design Revision-Unspecified | 275 | 47.17%
| Design Revision-Value Engineering Proposal | 10 | 1.715%
| Incomplete Design | 3 | 0.5146%
| Increased Traffic Volume | 9 | 1.544%
| Scope Change | 17 | 2.916%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 2 | 1.156% | 173 | 7.947% | 32991.1179 | 2621.7103
| Differing Site Conditions-Changes in Site After Bid/During Construction | 4 | 2.312%
| Differing Site Conditions-Contaminated Soil | 3 | 1.734%
| Differing Site Conditions-Encountered Rock | 3 | 1.734%
| Differing Site Conditions-Extra Work from Previous Projects | 4 | 2.312%
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 12 | 6.936%
| Differing Site Conditions-Incomplete Work by Others | 2 | 1.156%
| Differing Site Conditions-Not Shown in Construction Plans | 25 | 14.45%
| Differing Site Conditions-Unspecified | 71 | 41.04%
| Differing Site Conditions-Unsuitable Materials | 20 | 11.56%
| Slope Protection/Soil Stabilization | 27 | 15.61%
Drainage Issues | Drainage Issues-Unspecified | 36 | 87.8% | 41 | 1.883% | 13523.6941 | 254.6952
| Stormwater Concerns | 5 | 12.2%
Environmental/Community Concerns | Animal Protection/Endangered Species | 3 | 9.375% | 32 | 1.47% | 514825.6191 | 7567.4873
| Avoid Historical Structure | 1 | 3.125%
| Construction Impacts | 2 | 6.25%
| Environmental Concerns-Unspecified | 8 | 25%
| Natural Disaster (Drought) | 1 | 3.125%
| Noise Control | 2 | 6.25%
| Vegetation Establishment | 13 | 40.62%
| Wetland Delineation | 2 | 6.25%
Erosion Control Problems | Erosion Control Problems-Unspecified | 52 | 96.3% | 54 | 2.48% | 14589.7044 | 361.8944
| Waste Site Erosion Control | 2 | 3.704%
Issues with Underground Utilities | Inability to Locate Utilities | 7 | 5.512% | 127 | 5.834% | 29096.6257 | 1697.4145
| Utilities not Relocated on Time | 7 | 5.512%
| Utility Conflict | 113 | 88.98%
M&R/Replacement | Damaged Objects | 6 | 3.846% | 156 | 7.166% | 42963.2381 | 3078.6703
| M&R/Replacement-Unspecified | 147 | 94.23%
| Vehicular Accident | 3 | 1.923%
Other | Contractor Error | 2 | 12.5% | 16 | 0.735% | 11380.925 | 83.6448
| Covid 19 Impact | 2 | 12.5%
| Equipment/Items Protection | 3 | 18.75%
| Permit Acquisition Issues | 1 | 6.25%
| Permit Requirements | 4 | 25%
| Permit Restrictions | 2 | 12.5%
| Site Security | 2 | 12.5%
Procurement Issues | Error in Bill of Materials | 2 | 6.667% | 30 | 1.378% | 14827.2033 | 204.3253
| Material Acquisition Delays/Long Lead Items | 5 | 16.67%
| Material Fabrication Delay | 1 | 3.333%
| Shop Drawing Error | 3 | 10%
| Unavailability of Materials/Material Shortage | 18 | 60%
| Wrong Order Placement | 1 | 3.333%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 48 | 96% | 50 | 2.297% | 84632.4362 | 1943.7859
| Waste Excessive Material | 2 | 4%
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 5 | 4.237% | 118 | 5.42% | 30830.5636 | 1671.11
| Hazardous Materials Removal | 8 | 6.78%
| Safety Concerns-Unspecified | 91 | 77.12%
| Sight Distance Concerns | 1 | 0.8475%
| Travelers/Public Safety | 12 | 10.17%
| Tripping Hazard | 1 | 0.8475%
Scheduling and Coordination Issues | Additional ICT Required | 1 | 2.941% | 34 | 1.562% | 230636.1443 | 3602.0344
| Availability Date Delays | 5 | 14.71%
| Conflict with Other Projects | 2 | 5.882%
| Conflict/Overlap with Adjacent Projects | 3 | 8.824%
| Early Project Completion | 14 | 41.18%
| Miscommunication (Construction Progress) | 1 | 2.941%
| Overtime Hour Request | 1 | 2.941%
| Project Phasing Problems | 3 | 8.824%
| Statewide Initiative to Accelerate Projects | 2 | 5.882%
| Timely Completion of Project | 2 | 5.882%
Stakeholder Request | DOT Request-Unspecified | 71 | 39.89% | 178 | 8.176% | 178200.6782 | 14570.3816
| Stakeholder Request-Future Development Concerns | 11 | 6.18%
| Stakeholder Request-Unspecified | 96 | 53.93%
Survey/Test Issues | Additional Survey/Test Required | 6 | 30% | 20 | 0.9187% | 23243.903 | 213.5407
| Survey Error-Staking | 5 | 25%
| Survey Error-Unspecified | 9 | 45%

## 3a. Design-Plan Issues
Return to Cover Page
Design/Plan Issues
1. Roadway Design: vertical/horizontal alignment, earthwork, pavement, grade, etc.
2. Hydraulic Design: flow control, criteria changes, drainage, irrigation, system design, etc.
3. Traffic Design: ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.).
4. Structural Design: bridge superstructure, bridge substructure, etc.
5. Geotechnical Design: foundations, retaining walls, pile driving, etc.
6. Utility: design, as-builts, etc.
7. Environmental: vegetation plans, habitat mitigation, etc.
8. Traffic Control & Staging: Maintenance of Traffic, Work Zone Traffic Control, etc.
(2) Based on claims related to design/plan issues--from WSDOT's Risk Breakdown Structure (RBS)
Design/Plan Issues for Claims (1) | Number | % | Cost ($) | Time (Days) | Summary of Causes
Utility | 51 | 25.37% | 34100 | 70 | The main problem themes identified in the summary are utility conflicts, delays in utility relocation, errors in utility construction plans, unexpected waterline replacements, and delays caused by power company responses. These issues have caused delays in the completion of the project, additional materials and grading, erosion measures, and idle costs for the contractor. Additional compensation has been requested for the idle equipment and revised completion dates have been set.
Environmental | 34 | 16.92% | 12450 | 62 | The main problem themes identified are delays in establishing permanent vegetation, insufficient time for vegetation establishment, unfavorable weather conditions, and contractor compensation issues. These issues have caused delays in completing the contract and meeting erosion control requirements. Additional drainage infrastructure and wildlife nesting have also caused delays. Recommendations include adding 180 days to the original completion date and granting time for the contractor to attain 80% permanent cover.
Roadway Design | 29 | 14.43% | 59900 | 46 | The main problem themes identified include non-compliance with paving regulations, drainage issues, delays in contract completion, poor quality materials, design issues, plan errors, utility relocations, material shortages, scheduling issues, guardrail installation and removal, and lack of ADA compliance. These issues have caused extra work, delays, and additional costs for the contractor.
Geotechnical Design | 29 | 14.43% | 24200 | 28 | The main problem themes identified include continuous maintenance due to severe weather damage, delays in construction due to various issues such as high-water levels and unexpected subsurface conditions, poor quality materials, and the need for shoring to prevent erosion and exposure of graves during excavation. Solutions include using sheet piling as coffer dams, improving material quality, and extending contract completion dates.
Hydraulic Design | 17 | 8.458% | 3880 | 49 | The main problem themes identified in the summary include drainage issues, delays in acquiring materials, additional work required by environmental officers, obstruction of work by other projects, collapsed drainage structures, and missing line items in the contract. These issues have caused delays and extra work for the contractor, and in some cases, compensation is required for additional materials or work not included in the original contract.
Structural Design | 15 | 7.463% | 28180 | 46 | The main problem themes identified in the project include scope changes, manufacturing issues, delays due to unforeseen circumstances, errors in plans and specifications, and additional costs incurred for materials and labor. The contractor was not at fault for some of the issues, but improvements in manufacturing and planning processes are needed to prevent future problems.
Traffic Design | 15 | 7.463% | 5300 | 48 | The main problem themes identified include non-uniform and unsymmetrical pavement markings, incorrect striping on roads, incomplete permanent pavement markings, sight distance design issues, delay in approval of installations, inadequate pavement markings, and the use of non-ADA compliant material. Low visibility of crosswalks and temporary paint required additional measures, and missing line items caused compensation issues.
Traffic Control & Staging | 11 | 5.473% | 26000 | 102 | The main problem themes identified are railroad delays, specifically related to flagging, obtaining a flagger, and coordinating with the railroad. Additionally, there were issues with overlooked work zone signs, modifying barricades, and safety concerns related to the absence of Truck Mounted Attenuators. Payment for railroad inspectors and compensation for delays were also problematic.
Total | 201 | 100%
Design/Plan Issues for Supplemental Agreements (1) | Number | % | Cost ($) | Time (Days) | Summary of Causes
Roadway Design | 261 | 27.83% | 90400 | NA | The main problem themes identified include severe potholes on roads, overrun of contract quantities, inadequate guardrail protection, deteriorating pavement, inconsistent asphalt grades, missing line items in the contract, and the need for additional compensation for extra work and materials. Other issues include inadequate tie downs, insufficient guardrail coverage, and the need for additional asphalt surface treatment. The solutions involve creating supplemental agreements, establishing unit prices, and providing compensation for extra work and materials.
Hydraulic Design | 160 | 17.06% | 22850 | NA | The main problem themes identified include insufficient drainage causing issues with truck traffic, uncontrollable high-water levels, lack of proper drainage and uneven pavement in proposed roundabouts, drainage concerns on bridge shoulders, availability issues with Ductile Iron pipe, and the need for additional drainage work including masonry structures, HDPE pipes, concrete islands, borrow excavation, rip rap, seeding and mulching, flaggers, and temporary traffic control. There are also issues with existing pipes, catch basins, and drainage structures that require repair or replacement, as well as the need for erosion control measures such as wattles and turbidity curtains. Some items were omitted from the original contract, requiring supplemental agreements for compensation and additional work.
Traffic Design | 155 | 16.52% | 17930 | NA | The main problem themes identified include missing line items in the contract for necessary work, inadequate pavement markings, insufficient compensation for additional work, damaged or missing equipment, and safety concerns. Solutions include establishing pricing for additional work items, revising plans to account for traffic, compensating for necessary equipment and materials, and installing new pavement markings and safety features.
Geotechnical Design | 115 | 12.26% | 27800 | NA | The main problem themes identified in the text include slope failure, contaminated soil, unexpected rock, poor soil conditions, erosion issues, inadequate contract planning, omission of payment for necessary materials, unstable toe of slope, and lack of established line items for necessary work. Solutions include compensation for necessary materials and labor, installation of geotextile fabric and rip rap, and additional mobilization for necessary work.
Traffic Control & Staging | 102 | 10.87% | 17900 | NA | The main problem themes identified in the summary include the need for portable changeable message signs, type E sign erection, removal and relocation, U-channel support disposal, and 3-lb steel U-channel supports. There is also a lack of compensation for various traffic control measures, such as flaggers, law enforcement, and temporary traffic control devices. Additionally, there are issues with plan omissions, conflicting pavement markings, and the need for additional safety measures.
Utility | 84 | 8.955% | 27000 | NA | The main problem themes identified include utility conflicts, need for compensation for extra work and materials, incorrect or omitted information on plans, damage to existing infrastructure, and delays in utility relocations. These issues involve water and sewer line relocation, fire hydrant and meter adjustments, manhole and valve adjustments, and exploratory excavation to locate utilities. Supplemental agreements and compensation are necessary to address these problems.
Structural Design | 37 | 3.945% | 48250 | NA | The main problem themes identified in the summary include bridge approach paving, overstresses in spans, concrete slab failure, missing bridge items, compensation for additional work and materials, plan errors, guardrail installation, and structural deficiencies. These issues resulted in delays, increased material costs, and the need for supplemental agreements to address the additional work and compensation.
Environmental | 24 | 2.559% | 14000 | NA | The main problem themes identified in the summary include: trees marked for removal instead of saving, asbestos removal, lack of permanent vegetation establishment, insufficient vegetative coverage, damaged asphalt and vegetation, missing line items in the contract, and non-native plant material. These issues require additional work and compensation to ensure compliance with regulations and project specifications.
Total | 938 | 100%
(1) Based on newer data (2021 to 2023)

## 3b. Other Issues
Return to Cover Page
Other Issues | Number | % | Cost | Time | Summary of Causes
Claims (mostly time granted) | 277 | 46.4% | 17100 | 56 | The main problem themes identified include delays in project completion due to incomplete previous projects, pandemic-related shutdowns and staffing shortages, delays in material acquisition, waiting for other entities to perform work, scheduling conflicts, delays in final inspection and punch list, and delays in contract execution. There were also delays caused by additional work, equipment malfunctions, and errors in sign fabrication.
Supplemental Agreements (mostly cost granted) | 320 | 53.6% | 32160 | 20 | The main problem themes identified in the summary include material acquisition delays, time-limited material cost escalation adjustments, missing line items in contracts, additional work requested, and extensions of maps causing overruns in contract amounts. Other issues include damage to structures, equipment mobilization, and traffic control.
Total | 597 | 100%

## 4a. Claim-Appalach Region Comm
Return to Cover Page
4a. -- Table 3 Claims - Appalachian Regional Commission | [9 empty] | 4a. -- Table 1 Claims - Appalachian Regional Commission
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 50% | 2 | 9.524% | 6509 | 619.9048 | 132 | 12.5714 | Design/Plan Issues | 8 | 38.1%
| Constructability Issues-Unspecified | 1 | 50% | [6 empty] | Contract Amendment | 3 | 14.29%
Contract Amendment | Settlement and Release Agreement | 2 | 66.67% | 3 | 14.29% | 51192.17 | 7313.1671 | 256.5 | 36.6429 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 2 | 9.524%
| Unavailability of Funds/Cash Flow Considerations | 1 | 33.33% | [6 empty] | Natural Disaster | 2 | 9.524%
Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals | 1 | 100% | 1 | 4.762% |  | 0 | 8 | 0.38095 | Design Approval Waiting Period/Indecision/Negotiation | 1 | 4.762%
Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 25% | 8 | 38.1% | 1842.32 | 701.8362 | 8.5714 | 3.2653 | Environmental/Community Concerns | 1 | 4.762%
| Design/Plan Revision-Unspecified | 6 | 75% | [6 empty] | Issues with Underground Utilities | 1 | 4.762%
Environmental/Community Concerns | Animal Protection/Endangered Species | 1 | 100% | 1 | 4.762% |  | 0 | 167 | 7.9524 | Project Closeout Issues | 1 | 4.762%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 100% | 1 | 4.762% | 2750 | 130.9524 | - | - | Quantities Overrun/Underrun | 1 | 4.762%
Natural Disaster | Natural Disaster-Slide | 2 | 100% | 2 | 9.524% | 8411 | 801.0476 | 156 | 14.8571 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 1 | 4.762%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 100% | 1 | 4.762% | 0 | 0 | 5 | 0.2381
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 100% | 1 | 4.762% | 1050 | 50 | - | - | 4a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 1 | 100% | 1 | 4.762% | 0 | 0 | 1 | 0.047619 | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 50%
[10 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 37.5%
[10 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 12.5%
[10 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
[10 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 0%
[10 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 0%
[10 empty] | Utility – design, as-builts, etc. | 0%
[10 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Unspecified | 0%
(1) Based on WSDOT's Risk Breakdown Structure

## 4b. SA-Appalach Region Comm
Return to Cover Page
4b. -- Table 3 Supplemental Agreements (Appalachian Regional Commission) | [7 empty] | 4b. -- Table 1 Supplemental Agreements (Appalachian Regional Commission)
Generic Cause | Specific Cause | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Providing Access to Site | 1 | 50% | 2 | 3.636% | 7640 | 277.8182 | Design/Plan Issues | 13 | 23.64%
| Traffic Access Point | 1 | 50% |  |  |  |  | Contract Amendment | 10 | 18.18%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 100% | 3 | 5.455% | 52120 | 2842.9091 | Differing Site Conditions (Except Utilities) | 5 | 9.091%
Construction Method Revision | Construction Method Revision-Unspecified | 2 | 100% | 2 | 3.636% | -2952.375 | -107.3591 | Quantities Overrun/Underrun | 4 | 7.273%
Contract Amendment | Issues with Previous SA | 1 | 10% | 10 | 18.18% | 17527.582 | 3186.8331 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 3 | 5.455%
| Line Item Omission | 8 | 80% |  |  |  |  | Drainage Issues | 3 | 5.455%
| Revise Measurement and Payment Method | 1 | 10% |  |  |  |  | Access/ROW/Easement | 2 | 3.636%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 23.08% | 13 | 23.64% | 42045.0085 | 9937.9111 | Construction Method Revision | 2 | 3.636%
| Construction Plans Error/Discrepancy | 1 | 7.692% |  |  |  |  | Environmental/Community Concerns | 2 | 3.636%
| Design Revision-Fix Impacts of Previous Revisions | 1 | 7.692% |  |  |  |  | Issues with Underground Utilities | 2 | 3.636%
| Design Revision-Unspecified | 8 | 61.54% |  |  |  |  | M&R/Replacement | 2 | 3.636%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 20% | 5 | 9.091% | 87577.282 | 7961.5711 | Procurement Issues | 2 | 3.636%
| Differing Site Conditions-Not Shown in Construction Plans | 1 | 20% |  |  |  |  | Safety Concerns (Except Contaminated Soil) | 2 | 3.636%
| Differing Site Conditions-Unsuitable Materials | 2 | 40% |  |  |  |  | Other | 1 | 1.818%
| Slope Protection/Soil Stabilization | 1 | 20% |  |  |  |  | Stakeholder Request | 1 | 1.818%
Drainage Issues | Stormwater Concerns | 3 | 100% | 3 | 5.455% | 5727.8333 | 312.4273 | Survey/Test Issues | 1 | 1.818%
Environmental/Community Concerns | Vegetation Establishment | 2 | 100% | 2 | 3.636% | 4362 | 158.6182
Issues with Underground Utilities | Utility Conflict | 2 | 100% | 2 | 3.636% | 17198.75 | 625.4091 | 4b. -- Table 2 Supplemental Agreements (Appalachian Regional Commission)
M&R/Replacement | Damaged Objects | 1 | 50% | 2 | 3.636% | 39508 | 1436.6545 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| M&R/Replacement-Unspecified | 1 | 50% |  |  |  |  | Pavement | 7 | 12.73% | 113999.8443 | 14509.0711
Other | Equipment/Items Protection | 1 | 100% | 1 | 1.818% | 302.6 | 5.5018 | Environmental | 6 | 10.91% | 9704.0683 | 1058.6256
Procurement Issues | Unavailability of Materials/Material Shortage | 2 | 100% | 2 | 3.636% | -675 | -24.5455 | Finishing and Interior Work | 5 | 9.091% | 2971.14 | 270.1036
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 4 | 100% | 4 | 7.273% | -97424.2333 | -7085.3988 | Geotechnical | 5 | 9.091% | 105896.8825 | 9626.9893
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 2 | 100% | 2 | 3.636% | 57283.8 | 2083.0473 | Utilities | 5 | 9.091% | 30066.7 | 2733.3364
Stakeholder Request | DOT Request-Unspecified | 1 | 100% | 1 | 1.818% | 540 | 9.8182 | Hydraulics | 4 | 7.273% | 6150.005 | 447.2731
Survey/Test Issues | Survey Error-Unspecified | 1 | 100% | 1 | 1.818% | 7416.52 | 134.8458 | Roadway Design | 4 | 7.273% | 2107 | 153.2364
[8 empty] | TCP (Construction Phase) | 4 | 7.273% | 2357.65 | 171.4655
[8 empty] | Contract | 3 | 5.455% | -182355.06 | -9946.6396
[8 empty] | Procurement | 3 | 5.455% | -675 | -36.8182
[8 empty] | Safety | 3 | 5.455% | 44248.44 | 2413.5513
[8 empty] | Structural | 3 | 5.455% | 26731.9333 | 1458.1055
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 2 | 3.636% | 3031.5 | 110.2364
[8 empty] | Roadway Alignment | 1 | 1.818% | 83840 | 1524.3636

## 5a. Claim-Bicycle & Pedestrian
Return to Cover Page
5a. -- Table 3 Claims - Bicycle and Pedestrian | [9 empty] | 5a. -- Table 1 Claims - Bicycle and Pedestrian
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Insufficient ROW | 1 | 100% | 1 | 2.857% |  | 0 | 1 | 0.028571 | Issues with Underground Utilities | 8 | 22.86%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 100% | 1 | 2.857% |  | 0 | 180 | 5.1429 | Design/Plan Issues | 7 | 20%
Contract Amendment | Line Item Omission | 2 | 100% | 2 | 5.714% |  | 0 | 1 | 0.057143 | Design Approval Waiting Period/Indecision/Negotiation | 4 | 11.43%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 3 | 75% | 4 | 11.43% |  | 0 | 68.5 | 7.8286 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 8.571%
| Untimely Review and Return of Submittals | 1 | 25% | [6 empty] | Contract Amendment | 2 | 5.714%
Design/Plan Issues | Design/Plan Revision-Unspecified | 6 | 85.71% | 7 | 20% | 10013.3333 | 2002.6667 | 78.1429 | 15.6286 | M&R/Replacement | 2 | 5.714%
| Increased Traffic Volume | 1 | 14.29% | [6 empty] | Project Closeout Issues | 2 | 5.714%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 1 | 100% | 1 | 2.857% | 25536 | 729.6 | - | - | Start Date Delays | 2 | 5.714%
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 25% | 8 | 22.86% | 185009.5033 | 42287.8865 | 107.8333 | 24.6476 | Access/ROW/Easement | 1 | 2.857%
| Utility Conflict | 6 | 75% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 1 | 2.857%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 5.714% | 32423.12 | 1852.7497 | - | - | Differing Site Conditions (Except Utilities) | 1 | 2.857%
Natural Disaster | Natural Disaster-Hurricane | 1 | 100% | 1 | 2.857% |  | 0 | 7 | 0.2 | Natural Disaster | 1 | 2.857%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 100% | 1 | 2.857% |  | 0 | 71 | 2.0286 | Procurement Issues | 1 | 2.857%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 50% | 2 | 5.714% |  | 0 | 7.5 | 0.42857
| Scheduling Conflicts-Final Inspection/Punchlist | 1 | 50% | [6 empty] | 5a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 3 | 100% | 3 | 8.571% |  | 0 | 43.3333 | 3.7143 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 14.29%
Start Date Delays | Delay in Contract Execution | 2 | 100% | 2 | 5.714% |  | 0 | 16 | 0.91429 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 14.29%
[10 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 14.29%
[10 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 14.29%
[10 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 14.29%
[10 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
[10 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 0%
[10 empty] | Utility – design, as-builts, etc. | 0%
[10 empty] | Unspecified | 28.57%
(1) Based on WSDOT's Risk Breakdown Structure

## 5b. SA-Bicycle and Pedestrian
Return to Cover Page
5b. -- Table 3 Supplemental Agreements (SA-Bicycle and Pedestrian) | [7 empty] | 5b. -- Table 1 Supplemental Agreements (SA-Bicycle and Pedestrian)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Property Owners Access | 1 | 100% | 1 | 2.778% | 4472 | 124.2222 | Stakeholder Request | 6 | 16.67%
Construction Method Revision | Construction Method Revision-Unspecified | 2 | 100% | 2 | 5.556% | 41899.59 | 2327.755 | Contract Amendment | 5 | 13.89%
Contract Amendment | Elimination of Contract Line Item | 1 | 20% | 5 | 13.89% | 3166.3625 | 439.7726 | Issues with Underground Utilities | 4 | 11.11%
| Line Item Omission | 3 | 60% |  |  |  |  | M&R/Replacement | 4 | 11.11%
| Revise Measurement and Payment Method | 1 | 20% |  |  |  |  | Differing Site Conditions (Except Utilities) | 3 | 8.333%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 50% | 2 | 5.556% | 3682.645 | 204.5914 | Drainage Issues | 3 | 8.333%
| Design Revision-Future Maintenance Concerns | 1 | 50% |  |  |  |  | Erosion Control Problems | 3 | 8.333%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Encountered Rock | 1 | 33.33% | 3 | 8.333% | 5707.7733 | 475.6478 | Construction Method Revision | 2 | 5.556%
| Differing Site Conditions-Not Shown in Construction Plans | 2 | 66.67% |  |  |  |  | Design/Plan Issues | 2 | 5.556%
Drainage Issues | Drainage Issues-Unspecified | 3 | 100% | 3 | 8.333% | 3719.58 | 309.965 | Safety Concerns (Except Contaminated Soil) | 2 | 5.556%
Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 100% | 3 | 8.333% | 2409.6 | 200.8 | Access/ROW/Easement | 1 | 2.778%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 25% | 4 | 11.11% | 16109.5 | 1789.9444 | Scheduling and Coordination Issues | 1 | 2.778%
| Utility Conflict | 3 | 75%
M&R/Replacement | M&R/Replacement-Unspecified | 4 | 100% | 4 | 11.11% | 4997 | 555.2222 | 5b. -- Table 2 Supplemental Agreements (SA-Bicycle and Pedestrian)
Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 2 | 100% | 2 | 5.556% | 2785 | 154.7222 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
Scheduling and Coordination Issues | Early Project Completion | 1 | 100% | 1 | 2.778% | 162710.89 | 4519.7469 | Utilities | 9 | 25% | 11718.1312 | 2929.5328
Stakeholder Request | DOT Request-Unspecified | 2 | 33.33% | 6 | 16.67% | 6144.5833 | 1024.0972 | Environmental | 6 | 16.67% | 3072.3 | 512.05
| Stakeholder Request-Future Development Concerns | 1 | 16.67% |  |  |  |  | Hydraulics | 4 | 11.11% | 3307.185 | 367.465
| Stakeholder Request-Unspecified | 3 | 50% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 4 | 11.11% | 7187.3225 | 798.5914
[8 empty] | Safety | 2 | 5.556% | 36102.24 | 2005.68
[8 empty] | TCP (Construction Phase) | 2 | 5.556% | 10647.35 | 591.5194
[8 empty] | Traffic Control Systems (pavement Markings) | 2 | 5.556% | 4297.25 | 238.7361
[8 empty] | Access/ROW/Easement | 1 | 2.778% | 4472 | 124.2222
[8 empty] | Geotechnical | 1 | 2.778% | 0 | 0
[8 empty] | Pavement | 1 | 2.778% | 6161.72 | 171.1589
[8 empty] | Railroad | 1 | 2.778% | 9075 | 252.0833
[8 empty] | Roadway Design | 1 | 2.778% | 1600 | 44.4444
[8 empty] | Schedule | 1 | 2.778% | 162710.89 | 4519.7469
[8 empty] | Survey | 1 | 2.778% | -11880 | -330

## 6a. Claim-Bridge Replacement
Return to Cover Page
6a. -- Table 3 Claims - Bridge Replacement | [9 empty] | 6a. -- Table 1 Claims - Bridge Replacement
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Issues with Underground Utilities | Utilities not Relocated on Time | 24 | 40.68% | 59 | 13.88% | 21739.2367 | 3017.9176 | 43.7925 | 6.0794 | Issues with Underground Utilities | 59 | 13.88%
| Utility Conflict | 35 | 59.32% | [6 empty] | Design/Plan Issues | 59 | 13.88%
Design/Plan Issues | Compliance with Standard Specifications | 5 | 8.475% | 59 | 13.88% | 14093.0672 | 1956.4493 | 52.9608 | 7.3522 | Natural Disaster | 40 | 9.412%
| Design/Plan Error-Unspecified | 14 | 23.73% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 36 | 8.471%
| Design/Plan Revision-Unspecified | 39 | 66.1% | [6 empty] | Project Closeout Issues | 33 | 7.765%
| Increased Traffic Volume | 1 | 1.695% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 32 | 7.529%
Natural Disaster | Natural Disaster-Hurricane | 39 | 97.5% | 40 | 9.412% | - | 0 | 22.5 | 2.1176 | Environmental/Community Concerns | 31 | 7.294%
| Natural Disaster-Tropical Depression | 1 | 2.5% | [6 empty] | Contract Amendment | 25 | 5.882%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 6 | 16.67% | 36 | 8.471% | 94214.79 | 7980.5469 | 28.7879 | 2.4385 | Differing Site Conditions (Except Utilities) | 23 | 5.412%
| Purposeful Limited Work Schedule | 11 | 30.56% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 19 | 4.471%
| Scheduling Conflicts-Inspection | 5 | 13.89% | [6 empty] | Survey/Test Issues | 12 | 2.824%
| Timely Completion of Project | 1 | 2.778% | [6 empty] | M&R/Replacement | 12 | 2.824%
| Waiting for Other Entities to Perform Work | 2 | 5.556% | [6 empty] | Procurement Issues | 11 | 2.588%
| Work Out of Sequence | 2 | 5.556% | [6 empty] | Permit | 10 | 2.353%
| Work Restriction-Social Event | 1 | 2.778% | [6 empty] | Quantities Overrun/Underrun | 9 | 2.118%
| Work Restriction-Unspecified | 8 | 22.22% | [6 empty] | Start Date Delays | 7 | 1.647%
Project Closeout Issues | Final Punchlist Extra Work | 2 | 6.061% | 33 | 7.765% | 2000 | 155.2941 | 10.6667 | 0.82824 | Access/ROW/Easement | 5 | 1.176%
| Scheduling Conflicts-Final Inspection/Punchlist | 31 | 93.94% | [6 empty] | Other | 2 | 0.4706%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 2 | 6.25% | 32 | 7.529% | 36691.385 | 2762.6455 | 77.6562 | 5.8471
| Constructability Issues-Seasonal Limitations (Weather) | 29 | 90.62%
| Constructability Issues-Unspecified | 1 | 3.125% | [6 empty] | 6a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
Environmental/Community Concerns | Animal Protection/Endangered Species | 1 | 3.226% | 31 | 7.294% | 913 | 66.5953 | 93.6667 | 6.8322 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 32.2%
| Environmental Concerns/Unspecified | 1 | 3.226% | [6 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 18.64%
| Erosion Control Problems | 1 | 3.226% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 13.56%
| Vegetation Establishment | 28 | 90.32% | [6 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 13.56%
Contract Amendment | Contract Time Adjustment | 4 | 16% | 25 | 5.882% | 555758.3686 | 32691.6687 | 36.5238 | 2.1485 | Utility – design, as-builts, etc. | 8.475%
| Contractor Replacement | 1 | 4% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 1.695%
| Elimination of Contract Line Item | 2 | 8% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
| Error in Entering Time Extensions in HiCAMS | 9 | 36% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
| Line Item Omission | 5 | 20% | [6 empty] | Unspecified | 11.86%
| Revise Measurement and Payment Method | 1 | 4% | [6 empty] | (1) Based on WSDOT's Risk Breakdown Structure
| Settlement and Release Agreement | 3 | 12%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 8 | 34.78% | 23 | 5.412% | 10137.471 | 548.6161 | 26.7 | 1.4449
| Differing Site Conditions-Contaminated Groundwater | 1 | 4.348%
| Differing Site Conditions-Contaminated Soil | 1 | 4.348%
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 7 | 30.43%
| Differing Site Conditions-Incomplete Work by Others | 3 | 13.04%
| Differing Site Conditions-Unspecified | 1 | 4.348%
| Differing Site Conditions-Unsuitable Materials | 2 | 8.696%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 11 | 57.89% | 19 | 4.471% | 12714.68 | 568.421 | 41.2778 | 1.8454
| Untimely Receipt of Design | 1 | 5.263%
| Untimely Review and Return of Submittals | 5 | 26.32%
| Untimely Review of Approvals | 2 | 10.53%
Survey/Test Issues | Additional Survey-Test Required | 4 | 33.33% | 12 | 2.824% | 14511.0583 | 409.724 | 14.125 | 0.39882
| Survey Error | 7 | 58.33%
| Survey Results Delays | 1 | 8.333%
M&R/Replacement | M&R/Replacement-Unspecified | 12 | 100% | 12 | 2.824% | 2963.5275 | 83.6761 | 49.1111 | 1.3867
Procurement Issues | DOT Furnished Materials/Equipment Delays | 2 | 18.18% | 11 | 2.588% | 77894.29 | 2016.0875 | 33 | 0.85412
| Material Acquisition Delays/Long Lead Items | 4 | 36.36%
| Power Supply Delays | 1 | 9.091%
| Unavailability of Materials/Material Shortage | 2 | 18.18%
| Wrong Order Placement | 2 | 18.18%
Permit | Permit Acquisition Waiting Period | 8 | 80% | 10 | 2.353% | 60042.665 | 1412.7686 | 61.3333 | 1.4431
| Permit Limitation | 2 | 20%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 9 | 100% | 9 | 2.118% | 11051.7243 | 234.0365 | 2.6667 | 0.056471
Start Date Delays | Delay in Contract Execution | 2 | 28.57% | 7 | 1.647% | - | 0 | 55.1429 | 0.90824
| Delay in Preconstruction Meeting | 2 | 28.57%
| Delay in Project Award | 1 | 14.29%
| Delay in Receipt of Contract Information and Bonds | 1 | 14.29%
| Start Date Delays-Unspecified | 1 | 14.29%
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 20% | 5 | 1.176% | - | 0 | 36.6 | 0.43059
| Insufficient ROW | 2 | 40%
| ROW Acquisition Delays-Unspecified | 2 | 40%
Other | Covid 19 Impact | 1 | 50% | 2 | 0.4706% | 107204.47 | 504.4916 | 3 | 0.014118
| Unforeseen Issues-Unspecified | 1 | 50%

## 6b. SA-Bridge Replacement
Return to Cover Page
6b. -- Table 3 Supplemental Agreements (Bridge Replacement) | [7 empty] | 6b. -- Table 1 Supplemental Agreements (Bridge Replacement)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 3 | 42.86% | 7 | 1.955% | 5455.8457 | 106.6785 | Design/Plan Issues | 96 | 26.82%
| Insufficient ROW | 1 | 14.29% |  |  |  |  | Contract Amendment | 56 | 15.64%
| Property Owners Access | 2 | 28.57% |  |  |  |  | Differing Site Conditions (Except Utilities) | 31 | 8.659%
| Providing Access to Site | 1 | 14.29% |  |  |  |  | Stakeholder Request | 24 | 6.704%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 3 | 15.79% | 19 | 5.307% | 8386.76 | 445.1074 | Erosion Control Problems | 20 | 5.587%
| Constructability Issues-Unspecified | 15 | 78.95% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 19 | 5.307%
| Height Clearance Issues | 1 | 5.263% |  |  |  |  | M&R/Replacement | 18 | 5.028%
Construction Method Revision | Construction Method Revision-Unspecified | 9 | 100% | 9 | 2.514% | 7465.8138 | 187.6881 | Issues with Underground Utilities | 17 | 4.749%
Contract Amendment | Insufficient Insurance | 1 | 1.786% | 56 | 15.64% | 6473.1693 | 1012.5628 | Safety Concerns (Except Contaminated Soil) | 16 | 4.469%
| Line Item Omission | 53 | 94.64% |  |  |  |  | Quantities Overrun/Underrun | 11 | 3.073%
| Material Substitution Allowance | 2 | 3.571% |  |  |  |  | Construction Method Revision | 9 | 2.514%
Design/Plan Issues | Compliance with Standard Specifications | 16 | 16.67% | 96 | 26.82% | 15665.0293 | 4200.6782 | Survey/Test Issues | 9 | 2.514%
| Construction Plans Error/Discrepancy | 7 | 7.292% |  |  |  |  | Access/ROW/Easement | 7 | 1.955%
| Design Error-Elevation Difference with Existing Objects | 4 | 4.167% |  |  |  |  | Drainage Issues | 6 | 1.676%
| Design Error-Unspecified | 14 | 14.58% |  |  |  |  | Procurement Issues | 6 | 1.676%
| Design Revision-Fix Impacts of Previous Revisions | 1 | 1.042% |  |  |  |  | Environmental/Community Concerns | 5 | 1.397%
| Design Revision-Functionality Issues | 2 | 2.083% |  |  |  |  | Other | 5 | 1.397%
| Design Revision-Future Maintenance Concerns | 2 | 2.083% |  |  |  |  | Scheduling and Coordination Issues | 3 | 0.838%
| Design Revision-per Contractor Request | 17 | 17.71%
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 1.042% |  |  |  |  | 6b. --Table 2 Supplemental Agreements (Bridge Replacement)
| Design Revision-Unspecified | 29 | 30.21% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Increased Traffic Volume | 2 | 2.083% |  |  |  |  | Utilities | 54 | 15.08% | 23812.8023 | 3591.8752
| Scope Change | 1 | 1.042% |  |  |  |  | Geotechnical | 46 | 12.85% | 55227.552 | 7096.2776
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 3.226% | 31 | 8.659% | 29960.8306 | 2594.3736 | Roadway Design | 41 | 11.45% | 8571.5076 | 981.6531
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 3 | 9.677% |  |  |  |  | Structural | 34 | 9.497% | 23328.9038 | 2215.5942
| Differing Site Conditions-Not Shown in Construction Plans | 5 | 16.13% |  |  |  |  | Hydraulics | 33 | 9.218% | 11869.0268 | 1094.0723
| Differing Site Conditions-Unspecified | 7 | 22.58% |  |  |  |  | Environmental | 31 | 8.659% | 348060.1471 | 30139.2865
| Differing Site Conditions-Unsuitable Materials | 4 | 12.9% |  |  |  |  | TCP (Construction Phase) | 21 | 5.866% | 3794.6111 | 222.5889
| Slope Protection/Soil Stabilization | 11 | 35.48% |  |  |  |  | Traffic Control Systems (pavement Markings) | 17 | 4.749% | 6133.0788 | 291.2356
Drainage Issues | Drainage Issues-Unspecified | 6 | 100% | 6 | 1.676% | 17626.76 | 295.4206 | Pavement | 14 | 3.911% | 24997.5589 | 977.5582
Environmental/Community Concerns | Environmental Concerns-Unspecified | 3 | 60% | 5 | 1.397% | 2133963.016 | 29803.9527 | Roadway Alignment | 11 | 3.073% | 19761.2991 | 607.1908
| Vegetation Establishment | 2 | 40% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 10 | 2.793% | 86025.364 | 2402.9431
Erosion Control Problems | Erosion Control Problems-Unspecified | 20 | 100% | 20 | 5.587% | 3244.832 | 181.2755 | Corridor/Traffic Design | 9 | 2.514% | 268158.7089 | 6741.4201
Issues with Underground Utilities | Inability to Locate Utilities | 1 | 5.882% | 17 | 4.749% | 12091.7682 | 574.1901 | Procurement | 7 | 1.955% | -3473.88 | -67.925
| Utilities not Relocated on Time | 1 | 5.882% |  |  |  |  | Access/ROW/Easement | 5 | 1.397% | 3771.06 | 52.6684
| Utility Conflict | 15 | 88.24% |  |  |  |  | Schedule | 5 | 1.397% | 251731.49 | 3515.8029
M&R/Replacement | Damaged Objects | 1 | 5.556% | 18 | 5.028% | 48245.0639 | 2425.7295 | Other | 4 | 1.117% | 46098.26 | 515.0644
| M&R/Replacement-Unspecified | 17 | 94.44% |  |  |  |  | Safety | 4 | 1.117% | 24655.765 | 275.4834
Other | Contractor Error | 1 | 20% | 5 | 1.397% | 8777.55 | 122.5915 | Contract | 3 | 0.838% | 1000 | 8.3799
| Covid 19 Impact | 2 | 40% |  |  |  |  | Security/Protection | 3 | 0.838% | 5527.8667 | 46.3229
| Equipment/Items Protection | 1 | 20% |  |  |  |  | Survey | 3 | 0.838% | 30903.3333 | 258.9665
| Permit Restrictions | 1 | 20% |  |  |  |  | Natural Disaster | 2 | 0.5587% | 3109.75 | 17.3729
Procurement Issues | Error in Bill of Materials | 2 | 33.33% | 6 | 1.676% | -4586.395 | -76.867 | Finishing and Interior Work | 1 | 0.2793% | 22225 | 62.081
| Unavailability of Materials/Material Shortage | 4 | 66.67%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 11 | 100% | 11 | 3.073% | 32226.8555 | 990.2106
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 2 | 12.5% | 16 | 4.469% | 13001.9025 | 581.0906
| Hazardous Materials Removal | 1 | 6.25%
| Safety Concerns-Unspecified | 11 | 68.75%
| Travelers/Public Safety | 2 | 12.5%
Scheduling and Coordination Issues | Availability Date Delays | 3 | 100% | 3 | 0.838% | 126590.245 | 1060.8121
Stakeholder Request | DOT Request-Unspecified | 8 | 33.33% | 24 | 6.704% | 194491.015 | 13038.5038
| Stakeholder Request-Future Development Concerns | 1 | 4.167%
| Stakeholder Request-Unspecified | 15 | 62.5%
Survey/Test Issues | Additional Survey/Test Required | 2 | 22.22% | 9 | 2.514% | 36203.4456 | 910.1425
| Survey Error-Staking | 2 | 22.22%
| Survey Error-Unspecified | 5 | 55.56%

## 7a. Claim-Ferry
Return to Cover Page
7a. -- Table 3 Claims - Ferry | [9 empty] | 7a. -- Table 1 Claims - Ferry
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Contract Amendment | Line Item Omission | 2 | 100% | 2 | 14.29% | 8004.73 | 1143.5329 | 236 | 33.7143 | Natural Disaster | 4 | 28.57%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 100% | 1 | 7.143% | 0 | 0 | 87 | 6.2143 | Contract Amendment | 2 | 14.29%
Design/Plan Issues | Design/Plan Error-Unspecified | 1 | 100% | 1 | 7.143% | 10517.15 | 751.225 | 95 | 6.7857 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 2 | 14.29%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 100% | 1 | 7.143% | 5571.87 | 397.9907 | 1 | 0.071429 | Design Approval Waiting Period/Indecision/Negotiation | 1 | 7.143%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 100% | 1 | 7.143% | 26127.93 | 1866.2807 | - | - | Design/Plan Issues | 1 | 7.143%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 7.143% | 0 | 0 | 6 | 0.42857 | Differing Site Conditions (Except Utilities) | 1 | 7.143%
Natural Disaster | Natural Disaster-Hurricane | 4 | 100% | 4 | 28.57% | 0 | 0 | 70 | 20 | Issues with Underground Utilities | 1 | 7.143%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 1 | 100% | 1 | 7.143% | 0 | 0 | 32 | 2.2857 | M&R/Replacement | 1 | 7.143%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 50% | 2 | 14.29% | 0 | 0 | 18 | 2.5714 | Procurement Issues | 1 | 7.143%
| Work Out of Sequence | 1 | 50%
[10 empty] | 7a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
[10 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 100%
[10 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 0%
[10 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
[10 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 0%
[10 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
[10 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
[10 empty] | Utility – design, as-builts, etc. | 0%
[10 empty] | Unspecified | 0%
(1) Based on WSDOT's Risk Breakdown Structure

## 7b. SA-Ferry
Return to Cover Page
7b. -- Table 3 Supplemental Agreements (Ferry) | [7 empty] | 7b. -- Table 1 Supplemental Agreements (Ferry)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Contract Amendment | Change in Contract Provisions | 1 | 25% | 4 | 8% | 158581.475 | 12686.518 | Design/Plan Issues | 36 | 72%
| Settlement and Release Agreement | 1 | 25% |  |  |  |  | Contract Amendment | 4 | 8%
| Unavailability of Funds/Cash Flow Considerations | 2 | 50% |  |  |  |  | Other | 3 | 6%
Design/Plan Issues | Design Error-Unspecified | 1 | 2.778% | 36 | 72% | 13983.5356 | 10068.1456 | Stakeholder Request | 3 | 6%
| Design Revision-Unspecified | 35 | 97.22% |  |  |  |  | Procurement Issues | 2 | 4%
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 100% | 1 | 2% | 44434.27 | 888.6854 | Issues with Underground Utilities | 1 | 2%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 2% | 17230.79 | 344.6158 | M&R/Replacement | 1 | 2%
Other | Permit Requirements | 3 | 100% | 3 | 6% | 20513 | 1230.78
Procurement Issues | Material Acquisition Delays/Long Lead Items | 2 | 100% | 2 | 4% | 80708.795 | 3228.3518 | 7b. -- Table 2 Supplemental Agreements (Ferry)
Stakeholder Request | DOT Request-Unspecified | 3 | 100% | 3 | 6% | 13005.2733 | 780.3164 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
[8 empty] | Ferry | 30 | 60% | 15212.5073 | 9127.5044
[8 empty] | Procurement | 7 | 14% | 31029.94 | 4344.1916
[8 empty] | Contract | 3 | 6% | 210933.5267 | 12656.0116
[8 empty] | Environmental | 2 | 4% | 1413.29 | 56.5316
[8 empty] | Finishing and Interior Work | 1 | 2% | 33391 | 667.82
[8 empty] | Geotechnical | 1 | 2% | 9280 | 185.6
[8 empty] | Hydraulics | 1 | 2% | 3805.3 | 76.106
[8 empty] | Natural Disaster | 1 | 2% | 23027.5 | 460.55
[8 empty] | Pavement | 1 | 2% | 23546.72 | 470.9344
[8 empty] | Structural | 1 | 2% | 17230.79 | 344.6158
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 1 | 2% | 2359 | 47.18
[8 empty] | Utilities | 1 | 2% | 44434.27 | 888.6854

## 8a, Claim-Highway Safety
Return to Cover Page
8a. -- Table 3 Claims - Highway Safety | [9 empty] | 8a. -- Table 1 Claims - Highway Safety
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Railroad Right of Entry | 1 | 25% | 4 | 2.703% | 0 | 0 | 95.75 | 2.5878 | Issues with Underground Utilities | 26 | 17.57%
| ROW Acquisition Delays-Unspecified | 3 | 75% | [6 empty] | Design/Plan Issues | 21 | 14.19%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 8 | 100% | 8 | 5.405% | 0 | 0 | 68.375 | 3.6959 | Project Closeout Issues | 21 | 14.19%
Contract Amendment | Elimination of Contract Line Item | 1 | 20% | 5 | 3.378% | 0 | 0 | 27.8 | 0.93919 | Natural Disaster | 18 | 12.16%
| Error in Entering Time Extensions in HiCAMS | 3 | 60% | [6 empty] | Quantities Overrun/Underrun | 11 | 7.432%
| Settlement and Release Agreement | 1 | 20% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 9 | 6.081%
Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement | 1 | 33.33% | 3 | 2.027% | 0 | 0 | 57.6667 | 1.1689 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 8 | 5.405%
| Indecision-Unspecified | 1 | 33.33% | [6 empty] | Environmental/Community Concerns | 7 | 4.73%
| Untimely Review and Return of Submittals | 1 | 33.33% | [6 empty] | M&R/Replacement | 6 | 4.054%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 4.762% | 21 | 14.19% | 6787.2 | 963.0486 | 109.5238 | 15.5405 | Contract Amendment | 5 | 3.378%
| Design/Plan Error-Unspecified | 4 | 19.05% | [6 empty] | Access/ROW/Easement | 4 | 2.703%
| Design/Plan Revision-Unspecified | 16 | 76.19% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 3 | 2.027%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 1 | 33.33% | 3 | 2.027% | 3668.49 | 74.3613 | 9 | 0.18243 | Differing Site Conditions (Except Utilities) | 3 | 2.027%
| Differing Site Conditions-Unspecified | 1 | 33.33% | [6 empty] | Procurement Issues | 3 | 2.027%
| Differing Site Conditions-Unsuitable Materials | 1 | 33.33% | [6 empty] | Start Date Delays | 2 | 1.351%
Environmental/Community Concerns | Vegetation Establishment | 6 | 85.71% | 7 | 4.73% | 0 | 0 | 104.2857 | 4.9324 | Survey/Test Issues | 1 | 0.6757%
| Wetland Discovery | 1 | 14.29%
Issues with Underground Utilities | Utilities not Relocated on Time | 8 | 30.77% | 26 | 17.57% | 5160.21 | 906.5234 | 133.44 | 23.4422 | Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
| Utility Conflict | 18 | 69.23% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 28.57%
M&R/Replacement | M&R/Replacement-Damaged Objects | 1 | 16.67% | 6 | 4.054% | 96211.03 | 3900.4472 | 191.4 | 7.7595 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 28.57%
| M&R/Replacement-Unspecified | 5 | 83.33% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 9.524%
Natural Disaster | Natural Disaster-Hurricane | 18 | 100% | 18 | 12.16% | 0 | 0 | 25.3333 | 3.0811 | Utility – design, as-builts, etc. | 4.762%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 1 | 33.33% | 3 | 2.027% | 0 | 0 | 24 | 0.48649 | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 4.762%
| Power Supply Delays | 2 | 66.67% | [6 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 0%
Project Closeout Issues | Final Punchlist Extra Work | 2 | 9.524% | 21 | 14.19% | 0 | 0 | 22.7143 | 3.223 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 0%
| Scheduling Conflicts-Final Inspection/Punchlist | 19 | 90.48% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 11 | 100% | 11 | 7.432% | 26369.47 | 1959.893 | 34.125 | 2.5363 | Unspecified | 23.81%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 1 | 11.11% | 9 | 6.081% | 0 | 0 | 63.7778 | 3.8784 | (1) Based on WSDOT's Risk Breakdown Structure
| Coordination Issues-DOT Personnel Unavailability | 1 | 11.11%
| Miscommunication (Construction Progress) | 1 | 11.11%
| Purposeful Limited Work Schedule | 2 | 22.22%
| Scheduling Conflicts-Inspection | 1 | 11.11%
| Work Restriction-Social Event | 2 | 22.22%
| Work Restriction-Unspecified | 1 | 11.11%
Start Date Delays | Delay in Contract Execution | 2 | 100% | 2 | 1.351% | 0 | 0 | 18.5 | 0.25
Survey/Test Issues | Survey Error | 1 | 100% | 1 | 0.6757% | 0 | 0 | 7 | 0.047297

## 8b. SA-Highway Safety
Return to Cover Page
8b. -- Table 3 Supplemental Agreements (Highway Safety) | [7 empty] | 8b. -- Table 1 Supplemental Agreements (Highway Safety)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Property Owners Access | 2 | 50% | 4 | 3.39% | 12502.6875 | 423.8199 | Design/Plan Issues | 33 | 27.97%
| Traffic Access Point | 2 | 50% |  |  |  |  | Contract Amendment | 17 | 14.41%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 100% | 3 | 2.542% | 9796.8 | 249.0712 | M&R/Replacement | 14 | 11.86%
Construction Method Revision | Construction Method Revision-Unspecified | 1 | 100% | 1 | 0.8475% | 8373 | 70.9576 | Differing Site Conditions (Except Utilities) | 12 | 10.17%
Contract Amendment | Line Item Omission | 17 | 100% | 17 | 14.41% | 14070.6259 | 2027.1241 | Issues with Underground Utilities | 11 | 9.322%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 9.091% | 33 | 27.97% | 8168.329 | 2284.3632 | Safety Concerns (Except Contaminated Soil) | 6 | 5.085%
| Construction Plans Error/Discrepancy | 1 | 3.03% |  |  |  |  | Stakeholder Request | 6 | 5.085%
| Design Error-Elevation Difference with Existing Objects | 2 | 6.061% |  |  |  |  | Access/ROW/Easement | 4 | 3.39%
| Design Error-Unspecified | 3 | 9.091% |  |  |  |  | Erosion Control Problems | 4 | 3.39%
| Design Revision-Achieve Higher/Acceptable Quality | 1 | 3.03% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 3 | 2.542%
| Design Revision-Future Maintenance Concerns | 1 | 3.03% |  |  |  |  | Quantities Overrun/Underrun | 3 | 2.542%
| Design Revision-per Contractor Request | 4 | 12.12% |  |  |  |  | Construction Method Revision | 1 | 0.8475%
| Design Revision-Unspecified | 15 | 45.45% |  |  |  |  | Drainage Issues | 1 | 0.8475%
| Increased Traffic Volume | 1 | 3.03% |  |  |  |  | Environmental/Community Concerns | 1 | 0.8475%
| Scope Change | 2 | 6.061% |  |  |  |  | Procurement Issues | 1 | 0.8475%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 8.333% | 12 | 10.17% | 45820.2667 | 4659.6881 | Scheduling and Coordination Issues | 1 | 0.8475%
| Differing Site Conditions-Unspecified | 8 | 66.67%
| Differing Site Conditions-Unsuitable Materials | 2 | 16.67% |  |  |  |  | 8b. -- Table 2 Supplemental Agreements (Highway Safety)
| Slope Protection/Soil Stabilization | 1 | 8.333% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
Drainage Issues | Drainage Issues-Unspecified | 1 | 100% | 1 | 0.8475% | 18990.19 | 160.9338 | Utilities | 27 | 22.88% | 13451.15 | 3077.8055
Environmental/Community Concerns | Vegetation Establishment | 1 | 100% | 1 | 0.8475% | 3601.4 | 30.5203 | Roadway Design | 15 | 12.71% | 12235.376 | 1555.3444
Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 75% | 4 | 3.39% | 2821.865 | 95.6564 | TCP (Construction Phase) | 15 | 12.71% | 7073.65 | 899.1928
| Waste Site Erosion Control | 1 | 25% |  |  |  |  | Pavement | 14 | 11.86% | 6938.0067 | 823.1533
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 9.091% | 11 | 9.322% | 17511.2978 | 1632.4091 | Geotechnical | 10 | 8.475% | 58368.45 | 4946.4788
| Utility Conflict | 10 | 90.91% |  |  |  |  | Hydraulics | 9 | 7.627% | 9323.5489 | 711.1181
M&R/Replacement | M&R/Replacement-Unspecified | 14 | 100% | 14 | 11.86% | 16164.43 | 1917.8137 | Environmental | 7 | 5.932% | 43382.8657 | 2573.5598
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 100% | 1 | 0.8475% | 0 | 0 | Traffic Control Systems (Except Pavement Markings) | 5 | 4.237% | 16780.75 | 711.0487
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 3 | 100% | 3 | 2.542% | 2823.6667 | 71.7881 | Traffic Control Systems (Pavement Markings) | 4 | 3.39% | -17674.8325 | -599.1469
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 1 | 16.67% | 6 | 5.085% | 20101.6833 | 1022.1195 | Corridor/Traffic Design | 3 | 2.542% | 87967 | 2236.4492
| Safety Concerns-Unspecified | 5 | 83.33% |  |  |  |  | Procurement | 2 | 1.695% | 8373 | 141.9153
Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 100% | 1 | 0.8475% | 37455 | 317.4153 | Roadway Alignment | 2 | 1.695% | 8734.5 | 148.0424
Stakeholder Request | DOT Request-Unspecified | 2 | 33.33% | 6 | 5.085% | 60929.9333 | 3098.1322 | Safety | 2 | 1.695% | 6815.275 | 115.5131
| Stakeholder Request-Future Development Concerns | 1 | 16.67% |  |  |  |  | Contract | 1 | 0.8475% | 61290.47 | 519.4108
| Stakeholder Request-Unspecified | 3 | 50% |  |  |  |  | Other | 1 | 0.8475% | 0 | 0
[8 empty] | Schedule | 1 | 0.8475% | 0 | 0

## 9a. Claim-Interstate
Return to Cover Page
9a. -- Table 3 Claims - Interstate | [9 empty] | 9a. -- Table 1 Claims - Interstate
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per Claim | Expected Cost per Claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Railroad Right of Entry | 1 | 25% | 4 | 2.186% | 4430869 | 96849.5956 | 67.25 | 1.4699 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 25 | 13.66%
| ROW Acquisition Delays-Property Owners Agreement | 1 | 25% | [6 empty] | Design/Plan Issues | 23 | 12.57%
| ROW Acquisition Delays-Unspecified | 2 | 50% | [6 empty] | Natural Disaster | 21 | 11.48%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 13 | 100% | 13 | 7.104% | 16000 | 1136.612 | 45.0769 | 3.2022 | M&R/Replacement | 19 | 10.38%
Contract Amendment | Elimination of Contract Line Item | 2 | 15.38% | 13 | 7.104% | 145875.0229 | 10362.7065 | 75 | 5.3279 | Quantities Overrun/Underrun | 18 | 9.836%
| Error in Entering Time Extensions in HiCAMS | 2 | 15.38% | [6 empty] | Project Closeout Issues | 15 | 8.197%
| Line Item Omission | 4 | 30.77% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 13 | 7.104%
| Settlement and Release Agreement | 3 | 23.08% | [6 empty] | Contract Amendment | 13 | 7.104%
| Unavailability of Funds/Cash Flow Considerations | 2 | 15.38% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 7 | 3.825%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 5 | 71.43% | 7 | 3.825% | 0 | 0 | 47.7143 | 1.8251 | Procurement Issues | 7 | 3.825%
| Negotiation Delays | 2 | 28.57% | [6 empty] | Issues with Underground Utilities | 6 | 3.279%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 13.04% | 23 | 12.57% | 43160.0382 | 5424.4857 | 46.75 | 5.8757 | Access/ROW/Easement | 4 | 2.186%
| Design/Plan Error-Unspecified | 7 | 30.43% | [6 empty] | Differing Site Conditions (Except Utilities) | 4 | 2.186%
| Design/Plan Revision-Unspecified | 12 | 52.17% | [6 empty] | Environmental/Community Concerns | 3 | 1.639%
| Increased Traffic Volume | 1 | 4.348% | [6 empty] | Permit | 1 | 0.5464%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 4 | 100% | 4 | 2.186% | 0 | 0 | 22.25 | 0.48634
Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 33.33% | 3 | 1.639% | 15778.545 | 258.6647 | 30 | 0.4918 | 9a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
| Historical Site | 1 | 33.33% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 26.09%
| Vegetation Establishment | 1 | 33.33% | [6 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 17.39%
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 33.33% | 6 | 3.279% | 173897.54 | 5701.5587 | 214.6667 | 7.0383 | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 13.04%
| Utility Conflict | 4 | 66.67% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 13.04%
M&R/Replacement | M&R/Replacement-Unspecified | 16 | 84.21% | 19 | 10.38% | 101177.8043 | 10504.7994 | 56.2857 | 5.8439 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 8.696%
| Vehicular Accident | 3 | 15.79% | [6 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 4.348%
Natural Disaster | Natural Disaster-Hurricane | 21 | 100% | 21 | 11.48% | 44523.09 | 5109.207 | 31.9048 | 3.6612 | Environmental – vegetation plans, habitat mitigation, etc. | 4.348%
Permit | Permit Acquisition Waiting Period | 1 | 100% | 1 | 0.5464% | 0 | 0 | 40 | 0.21858 | Utility – design, as-builts, etc. | 0%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 14.29% | 7 | 3.825% | 5142.2 | 196.6962 | 203.3333 | 7.7778 | Unspecified | 13.04%
| Material Fabrication Delay | 1 | 14.29% | [6 empty] | (1) Based on WSDOT's Risk Breakdown Structure
| Power Supply Delays | 4 | 57.14%
| Unavailability of Materials/Material Shortage | 1 | 14.29%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 6.667% | 15 | 8.197% | 0 | 0 | 28.4 | 2.3279
| Scheduling Conflicts-Final Inspection/Punchlist | 14 | 93.33%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 18 | 100% | 18 | 9.836% | 124312.6562 | 12227.4744 | 44.4545 | 4.3726
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 5 | 20% | 25 | 13.66% | 547.44 | 74.7869 | 61.7083 | 8.4301
| Purposeful Limited Work Schedule | 5 | 20%
| Scheduling Conflicts-Inspection | 1 | 4%
| Work Out of Sequence | 2 | 8%
| Work Restriction-Social Event | 8 | 32%
| Work Restriction-Unspecified | 4 | 16%
Start Date Delays | Delay in Contract Execution | 2 | 100% | 2 | 1.093% | 0 | 0 | 46.5 | 0.5082
Survey/Test Issues | Survey Error | 2 | 100% | 2 | 1.093% | 13851.33 | 151.3807 | 9 | 0.098361
Start Date Delays | 2 | 0.010929
Survey/Test Issues | 2 | 0.010929

## 9b. SA-Interstate
Return to Cover Page
9b. -- Table 3 Supplemental Agreements (Interstate) | [7 empty] | 9b. -- Table 1 Supplemental Agreements (Interstate)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 33.33% | 3 | 1.181% | 7518.3167 | 88.799 | Design/Plan Issues | 69 | 27.17%
| Railroad Right of Entry Delays | 1 | 33.33% |  |  |  |  | M&R/Replacement | 32 | 12.6%
| Traffic Access Point | 1 | 33.33% |  |  |  |  | Contract Amendment | 30 | 11.81%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 20 | 100% | 20 | 7.874% | 43401.4511 | 3417.4371 | Stakeholder Request | 26 | 10.24%
Construction Method Revision | Construction Method Revision-Unspecified | 9 | 100% | 9 | 3.543% | 720476.2 | 25528.6843 | Safety Concerns (Except Contaminated Soil) | 25 | 9.843%
Contract Amendment | Change in Contract Provisions | 1 | 3.333% | 30 | 11.81% | 34387.6804 | 4061.5371 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 20 | 7.874%
| Elimination of Contract Line Item | 2 | 6.667% |  |  |  |  | Differing Site Conditions (Except Utilities) | 14 | 5.512%
| Issues with Previous SA | 2 | 6.667% |  |  |  |  | Construction Method Revision | 9 | 3.543%
| Line Item Omission | 19 | 63.33% |  |  |  |  | Drainage Issues | 7 | 2.756%
| Mitigation of Potential Risk | 1 | 3.333% |  |  |  |  | Quantities Overrun/Underrun | 7 | 2.756%
| Revise Measurement and Payment Method | 1 | 3.333% |  |  |  |  | Erosion Control Problems | 5 | 1.969%
| Risk Management | 1 | 3.333% |  |  |  |  | Access/ROW/Easement | 3 | 1.181%
| Settlement and Release Agreement | 1 | 3.333% |  |  |  |  | Environmental/Community Concerns | 2 | 0.7874%
| Unavailability of Funds/Cash Flow Considerations | 2 | 6.667% |  |  |  |  | Issues with Underground Utilities | 2 | 0.7874%
Design/Plan Issues | Compliance with Standard Specifications | 8 | 11.59% | 69 | 27.17% | 67008.6668 | 18203.1418 | Procurement Issues | 1 | 0.3937%
| Design Error-Elevation Difference with Existing Objects | 3 | 4.348% |  |  |  |  | Scheduling and Coordination Issues | 1 | 0.3937%
| Design Error-Unspecified | 3 | 4.348% |  |  |  |  | Survey/Test Issues | 1 | 0.3937%
| Design Revision-Achieve Higher/Acceptable Quality | 3 | 4.348%
| Design Revision-Fix Impacts of Previous Revisions | 5 | 7.246% |  |  |  |  | 9b. -- Table 2 Supplemental Agreements (Interstate)
| Design Revision-Future Maintenance Concerns | 2 | 2.899% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Design Revision-per Contractor Request | 2 | 2.899% |  |  |  |  | Pavement | 36 | 14.17% | 119816.4685 | 16981.8617
| Design Revision-Uniformity with Adjacent Projects/Objects | 4 | 5.797% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 29 | 11.42% | 43860.8386 | 5007.7335
| Design Revision-Unspecified | 28 | 40.58% |  |  |  |  | Hydraulics | 26 | 10.24% | 35973.6577 | 3682.3429
| Design Revision-Value Engineering Proposal | 5 | 7.246% |  |  |  |  | Roadway Design | 22 | 8.661% | 41610.6557 | 3604.0725
| Incomplete Design | 1 | 1.449% |  |  |  |  | Geotechnical | 20 | 7.874% | -115143.5526 | -9066.4215
| Increased Traffic Volume | 2 | 2.899% |  |  |  |  | Structural | 19 | 7.48% | 64977.0437 | 4860.4875
| Scope Change | 3 | 4.348% |  |  |  |  | TCP (Construction Phase) | 18 | 7.087% | 32601.76 | 2310.3609
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 1 | 7.143% | 14 | 5.512% | 41633.19 | 2294.7428 | Utilities | 18 | 7.087% | 397953.2867 | 28201.414
| Differing Site Conditions-Extra Work from Previous Projects | 1 | 7.143% |  |  |  |  | Corridor/Traffic Design | 17 | 6.693% | 1032407.9265 | 69098.1683
| Differing Site Conditions-Not Shown in Construction Plans | 1 | 7.143% |  |  |  |  | Traffic Control Systems (Pavement Markings) | 13 | 5.118% | 28628.0246 | 1465.2139
| Differing Site Conditions-Unspecified | 7 | 50% |  |  |  |  | Environmental | 10 | 3.937% | 33126.463 | 1304.1915
| Differing Site Conditions-Unsuitable Materials | 3 | 21.43% |  |  |  |  | Safety | 7 | 2.756% | 4455.06 | 122.7772
| Slope Protection/Soil Stabilization | 1 | 7.143% |  |  |  |  | Contract | 4 | 1.575% | 5482.4933 | 86.3385
Drainage Issues | Drainage Issues-Unspecified | 7 | 100% | 7 | 2.756% | 24310.6586 | 669.9788 | Access/ROW/Easement | 3 | 1.181% | 496998.3167 | 5870.0589
Environmental/Community Concerns | Construction Impacts | 1 | 50% | 2 | 0.7874% | 363976.375 | 2865.9557 | Procurement | 3 | 1.181% | -156475 | -1848.1299
| Natural Disaster (Drought) | 1 | 50% |  |  |  |  | Roadway Alignment | 3 | 1.181% | 9675 | 114.2717
Erosion Control Problems | Erosion Control Problems-Unspecified | 5 | 100% | 5 | 1.969% | 52984.46 | 1043.0012 | Schedule | 3 | 1.181% | 10 | 0.11811
Issues with Underground Utilities | Utility Conflict | 2 | 100% | 2 | 0.7874% | 340905 | 2684.2913 | Other | 2 | 0.7874% | 796851.48 | 6274.4211
M&R/Replacement | Damaged Objects | 1 | 3.125% | 32 | 12.6% | 85994.8916 | 10834.0021 | Railroad | 1 | 0.3937% | 40124.43 | 157.9702
| M&R/Replacement-Unspecified | 28 | 87.5%
| Vehicular Accident | 3 | 9.375%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 100% | 1 | 0.3937% | 0 | 0
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 7 | 100% | 7 | 2.756% | 42956.3771 | 1183.8372
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 4% | 25 | 9.843% | 69669.3304 | 6857.2176
| Safety Concerns-Unspecified | 20 | 80%
| Travelers/Public Safety | 4 | 16%
Scheduling and Coordination Issues | Early Project Completion | 1 | 100% | 1 | 0.3937% | 10 | 0.03937
Stakeholder Request | DOT Request-Unspecified | 17 | 65.38% | 26 | 10.24% | 611870.6408 | 62632.4278
| Stakeholder Request-Future Development Concerns | 3 | 11.54%
| Stakeholder Request-Unspecified | 6 | 23.08%
Survey/Test Issues | Survey Error-Unspecified | 1 | 100% | 1 | 0.3937% | 1585.23 | 6.2411

## 10a. Claim-Other
Return to Cover Page
10a. -- Table 3 Claims - Other | [9 empty] | 10a. -- Table 1 Claims - Other
Generic Cause | Specific Cause | Count GC Level 2 | SC-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 2 | 100% | 2 | 3.774% | 0 | 0 | 153.5 | 5.7925 | Issues with Underground Utilities | 7 | 13.21%
Contract Amendment | Contract Error | 1 | 25% | 4 | 7.547% | 0 | 0 | 198.75 | 15 | Project Closeout Issues | 7 | 13.21%
| Error in Entering Time Extensions in HiCAMS | 3 | 75% | [6 empty] | Design/Plan Issues | 6 | 11.32%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 3 | 75% | 4 | 7.547% | 0 | 0 | 22.75 | 1.717 | Start Date Delays | 6 | 11.32%
| Untimely Review of Approvals | 1 | 25% | [6 empty] | Contract Amendment | 4 | 7.547%
Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 33.33% | 6 | 11.32% | 1916.875 | 217.0047 | 8 | 0.90566 | Design Approval Waiting Period/Indecision/Negotiation | 4 | 7.547%
| Design/Plan Revision-Unspecified | 4 | 66.67% | [6 empty] | Environmental/Community Concerns | 3 | 5.66%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 50% | 2 | 3.774% | 0 | 0 | 12 | 0.45283 | Natural Disaster | 3 | 5.66%
| Differing Site Conditions-Unsuitable Materials | 1 | 50% | [6 empty] | Procurement Issues | 3 | 5.66%
Environmental/Community Concerns | Vegetation Establishment | 3 | 100% | 3 | 5.66% | 0 | 0 | 36.3333 | 2.0566 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 5.66%
Issues with Underground Utilities | Utility Conflict | 7 | 100% | 7 | 13.21% | 0 | 0 | 45 | 5.9434 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 2 | 3.774%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 3.774% | 4576.005 | 172.6794 | - | - | Differing Site Conditions (Except Utilities) | 2 | 3.774%
Natural Disaster | Natural Disaster-Drought | 1 | 33.33% | 3 | 5.66% | 0 | 0 | 21 | 1.1887 | M&R/Replacement | 2 | 3.774%
| Natural Disaster-Flood | 1 | 33.33% | [6 empty] | Other | 1 | 1.887%
| Natural Disaster-Hurricane | 1 | 33.33%
Other | Covid 19 Impact | 1 | 100% | 1 | 1.887% | 0 | 0 | 269 | 5.0755 | 10a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 33.33% | 3 | 5.66% | 0 | 0 | 48.3333 | 2.7358 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 16.67%
| Unavailability of Materials/Material Shortage | 2 | 66.67% | [6 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 16.67%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 7 | 100% | 7 | 13.21% | 0 | 0 | 13.2857 | 1.7547 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 16.67%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 1 | 33.33% | 3 | 5.66% | 0 | 0 | 76.3333 | 4.3208 | Utility – design, as-builts, etc. | 16.67%
| Coordination Issues-DOT Personnel Unavailability | 1 | 33.33% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 16.67%
| Work Restriction-Social Event | 1 | 33.33% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
Start Date Delays | Delay in Contract Execution | 4 | 66.67% | 6 | 11.32% | 0 | 0 | 17.6667 | 2 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
| Delay in Preconstruction Meeting | 2 | 33.33% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
[10 empty] | Unspecified | 16.67%
(1) Based on WSDOT's Risk Breakdown Structure

## 10b. SA-Other
Return to Cover Page
10b. -- Table 3 Supplemental Agreements (Other) | [7 empty] | 10b. -- Table 1 Supplemental Agreements (Other)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Providing Access to Site | 1 | 100% | 1 | 2.703% | 20000 | 540.5405 | Design/Plan Issues | 8 | 21.62%
Contract Amendment | Line Item Omission | 7 | 100% | 7 | 18.92% | 3018.2857 | 571.027 | Contract Amendment | 7 | 18.92%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 12.5% | 8 | 21.62% | 9068.6063 | 1960.7797 | Differing Site Conditions (Except Utilities) | 7 | 18.92%
| Construction Plans Error/Discrepancy | 1 | 12.5% |  |  |  |  | Procurement Issues | 3 | 8.108%
| Design Revision-Achieve Higher/Acceptable Quality | 2 | 25% |  |  |  |  | Quantities Overrun/Underrun | 3 | 8.108%
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 12.5% |  |  |  |  | Erosion Control Problems | 2 | 5.405%
| Design Revision-Unspecified | 3 | 37.5% |  |  |  |  | Issues with Underground Utilities | 2 | 5.405%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 1 | 14.29% | 7 | 18.92% | -1863.7743 | -352.6059 | Access/ROW/Easement | 1 | 2.703%
| Differing Site Conditions-Unspecified | 3 | 42.86% |  |  |  |  | Drainage Issues | 1 | 2.703%
| Differing Site Conditions-Unsuitable Materials | 2 | 28.57% |  |  |  |  | Environmental/Community Concerns | 1 | 2.703%
| Slope Protection/Soil Stabilization | 1 | 14.29% |  |  |  |  | M&R/Replacement | 1 | 2.703%
Drainage Issues | Drainage Issues-Unspecified | 1 | 100% | 1 | 2.703% | 6100 | 164.8649 | Stakeholder Request | 1 | 2.703%
Environmental/Community Concerns | Environmental Concerns-Unspecified | 1 | 100% | 1 | 2.703% | 15584.25 | 421.1959
Erosion Control Problems | Erosion Control Problems-Unspecified | 2 | 100% | 2 | 5.405% | 3682 | 199.027 | 10b. -- Table 2 Supplemental Agreements (Other)
Issues with Underground Utilities | Utility Conflict | 2 | 100% | 2 | 5.405% | 2844.5 | 153.7568 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 2.703% | 16968.2 | 458.6 | Environmental | 10 | 27.03% | 6827.025 | 1845.1419
Procurement Issues | Unavailability of Materials/Material Shortage | 3 | 100% | 3 | 8.108% | 6148.375 | 498.5169 | TCP (Construction Phase) | 5 | 13.51% | 6165.6 | 833.1892
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 3 | 100% | 3 | 8.108% | 4254.3333 | 344.9459 | Geotechnical | 4 | 10.81% | 6777.405 | 732.6924
Stakeholder Request | DOT Request-Unspecified | 1 | 100% | 1 | 2.703% | 794 | 21.4595 | Roadway Design | 4 | 10.81% | -4460.285 | -482.193
[8 empty] | Pavement | 3 | 8.108% | 2933.3333 | 237.8378
[8 empty] | Procurement | 3 | 8.108% | 6148.375 | 498.5169
[8 empty] | Hydraulics | 2 | 5.405% | 5030 | 271.8919
[8 empty] | Traffic Control Systems (Pavement Markings) | 2 | 5.405% | 4240.675 | 229.2257
[8 empty] | Utilities | 2 | 5.405% | 2844.5 | 153.7568
[8 empty] | Other | 1 | 2.703% | 1528.3 | 41.3054
[8 empty] | Structural | 1 | 2.703% | 22967.5 | 620.7432

## 11a. Claim-Rail
Return to Cover Page
11a. -- Table 3 Claims - Rail | [9 empty] | 11a. -- Table 1 Claims - Rail
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Insufficient Right of Entry | 1 | 14.29% | 7 | 10% | 369355.015 | 36935.5015 | 117 | 11.7 | Issues with Underground Utilities | 26 | 37.14%
| Railroad Right of Entry | 6 | 85.71% | [6 empty] | Quantities Overrun/Underrun | 8 | 11.43%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 20% | 5 | 7.143% | 124500 | 8892.8571 | 132 | 9.4286 | Access/ROW/Easement | 7 | 10%
| Constructability Issues-Seasonal Limitations (Weather) | 4 | 80% | [6 empty] | Contract Amendment | 6 | 8.571%
Contract Amendment | Contract Error | 3 | 50% | 6 | 8.571% | 4542.235 | 389.3344 | 72.75 | 6.2357 | Design/Plan Issues | 6 | 8.571%
| Error in Entering Time Extensions in HiCAMS | 1 | 16.67% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 5 | 7.143%
| Line Item Omission | 1 | 16.67% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 4 | 5.714%
| Unavailability of Funds/Cash Flow Considerations | 1 | 16.67% | [6 empty] | Other | 3 | 4.286%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 100% | 1 | 1.429% | 20105.23 | 287.2176 | 21 | 0.3 | M&R/Replacement | 2 | 2.857%
Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 33.33% | 6 | 8.571% | 116321.4 | 9970.4057 | 49.6 | 4.2514 | Design Approval Waiting Period/Indecision/Negotiation | 1 | 1.429%
| Design/Plan Revision-Unspecified | 4 | 66.67% | [6 empty] | Procurement Issues | 1 | 1.429%
Issues with Underground Utilities | Utilities not Relocated on Time | 4 | 15.38% | 26 | 37.14% | 350556.8563 | 130206.8323 | 100.0909 | 37.1766 | Project Closeout Issues | 1 | 1.429%
| Utility Conflict | 22 | 84.62%
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 2.857% | 143896.62 | 4111.332 | 7 | 0.2 | 11a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
Other | Misinterpretation of Plans | 1 | 33.33% | 3 | 4.286% | 144300 | 6184.2857 | 226.5 | 9.7071 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 50%
| Unavailability of Labor | 2 | 66.67% | [6 empty] | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 16.67%
Procurement Issues | Power Supply Delays | 1 | 100% | 1 | 1.429% | 0 | 0 | 43 | 0.61429 | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 100% | 1 | 1.429% | 0 | 0 | 45 | 0.64286 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 0%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 8 | 100% | 8 | 11.43% | 276266.645 | 31573.3309 | 15.5 | 1.7714 | Structural Design – bridge superstructure, bridge substructure, etc. | 0%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 1 | 25% | 4 | 5.714% | 33838 | 1933.6 | 82 | 4.6857 | Utility – design, as-builts, etc. | 0%
| Coordination Issues-Unspecified | 1 | 25% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
| Waiting for Other Entities to Perform Work | 2 | 50% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Unspecified | 33.33%
(1) Based on WSDOT's Risk Breakdown Structure

## 11b. SA-Rail
Return to Cover Page
11b. -- Table 3 Supplemental Agreements (Rail) | [7 empty] | 11b. -- Table 1 Supplemental Agreements (Rail)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Insufficient ROW | 2 | 66.67% | 3 | 4.839% | 9118.39 | 441.2124 | Survey/Test Issues | 2 | 100%
| Providing Access to Site | 1 | 33.33% |  |  |  |  | Stakeholder Request | 5 | 71.43%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 4 | 66.67% | 6 | 10.17% | 14540.3783 | 1478.6825 | Design/Plan Issues | 13 | 28.26%
| Constructability Issues-Unspecified | 2 | 33.33% |  |  |  |  | Scheduling and Coordination Issues | 2 | 22.22%
Contract Amendment | Contingency Item | 1 | 14.29% | 7 | 13.21% | 2321.24 | 306.5789 | Differing Site Conditions (Except Utilities) | 7 | 21.21%
| Line Item Omission | 6 | 85.71% |  |  |  |  | Procurement Issues | 3 | 20%
Design/Plan Issues | Compliance with Standard Specifications | 3 | 23.08% | 13 | 28.26% | 17695.2185 | 5000.8226 | Safety Concerns (Except Contaminated Soil) | 2 | 18.18%
| Construction Plans Error/Discrepancy | 1 | 7.692% |  |  |  |  | Other | 3 | 16.67%
| Design Error-Unspecified | 3 | 23.08% |  |  |  |  | Contract Amendment | 7 | 13.21%
| Design Revision-per Contractor Request | 1 | 7.692% |  |  |  |  | Issues with Underground Utilities | 3 | 13.04%
| Design Revision-Unspecified | 5 | 38.46% |  |  |  |  | Erosion Control Problems | 3 | 11.54%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 3 | 42.86% | 7 | 21.21% | 14313.6571 | 3036.2303 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 6 | 10.17%
| Differing Site Conditions-Unspecified | 4 | 57.14% |  |  |  |  | M&R/Replacement | 2 | 10%
Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 100% | 3 | 11.54% | 9193.3667 | 1060.7731 | Quantities Overrun/Underrun | 1 | 8.333%
Issues with Underground Utilities | Utility Conflict | 3 | 100% | 3 | 13.04% | 15075.5 | 1966.3696
M&R/Replacement | M&R/Replacement-Unspecified | 2 | 100% | 2 | 10% | 20269 | 2026.9 | 11b. -- Table 2 Supplemental Agreements (Rail)
Other | Contractor Error | 1 | 33.33% | 3 | 16.67% | 17936.31 | 2989.385 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Site Security | 2 | 66.67% |  |  |  |  | Utilities | 10 | 16.13% | 18846.808 | 3039.8077
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 33.33% | 3 | 20% | 10636 | 2127.2 | Hydraulics | 9 | 14.52% | 14102.4267 | 2047.1265
| Unavailability of Materials/Material Shortage | 2 | 66.67% |  |  |  |  | Access/ROW/Easement | 5 | 8.065% | 17734.12 | 1430.171
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 100% | 1 | 8.333% | 21600 | 1800 | Environmental | 5 | 8.065% | 8468.658 | 682.9563
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 2 | 100% | 2 | 18.18% | 43208 | 7856 | Procurement | 5 | 8.065% | 20859.2 | 1682.1935
Scheduling and Coordination Issues | Availability Date Delays | 2 | 100% | 2 | 22.22% | 69903.3 | 15534.0667 | Traffic Control Systems (Except Pavement Markings) | 5 | 8.065% | 2494.574 | 201.1753
Stakeholder Request | DOT Request-Unspecified | 2 | 40% | 5 | 71.43% | 14913.888 | 10652.7771 | Geotechnical | 4 | 6.452% | 13709 | 884.4516
| Stakeholder Request-Unspecified | 3 | 60% |  |  |  |  | TCP (Construction Phase) | 4 | 6.452% | 5728 | 369.5484
Survey/Test Issues | Additional Survey/Test Required | 2 | 100% | 2 | 100% | 7851.4 | 7851.4 | Railroad | 3 | 4.839% | 4497.3333 | 217.6129
[8 empty] | Structural | 3 | 4.839% | 28825.03 | 1394.7595
[8 empty] | Finishing and Interior Work | 2 | 3.226% | 65581.425 | 2115.5298
[8 empty] | Safety | 2 | 3.226% | 43208 | 1393.8065
[8 empty] | Corridor/Traffic Design | 1 | 1.613% | 12032.67 | 194.0753
[8 empty] | Pavement | 1 | 1.613% | -32397.5 | -522.5403
[8 empty] | Roadway Design | 1 | 1.613% | 1000 | 16.129
[8 empty] | Security/Protection | 1 | 1.613% | 58041.64 | 936.1555
[8 empty] | Traffic Control Systems (Pavement Markings) | 1 | 1.613% | 1092.5 | 17.621

## 12a. Claim-Railroad - HW Crossi
Return to Cover Page
12a. -- Table 3 Claims - Railroad - Highway Crossings | [9 empty] | 12a. -- Table 1 Claims - Railroad - Highway Crossings
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 33.33% | 3 | 42.86% | 0 | 0 | 25.3333 | 10.8571 | Issues with Underground Utilities | 3 | 42.86%
| Utility Conflict | 2 | 66.67% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 42.86%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 100% | 1 | 14.29% | 0 | 0 | 12 | 1.7143 | Project Closeout Issues | 1 | 14.29%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 1 | 33.33% | 3 | 42.86% | 0 | 0 | 32 | 13.7143
| Work Restriction-Social Event | 1 | 33.33% | [6 empty] | 12a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
| Work Restriction-Unspecified | 1 | 33.33% | [6 empty] | No Design/Plan Issues
(1) Based on WSDOT's Risk Breakdown Structure

## 12b. SA-Railroad - HW Crossings
Return to Cover Page
12b. -- Table 3 Supplemental Agreements (Railroad - Highway Crossings) | [7 empty] | 12b. -- Table 1 Supplemental Agreements (Railroad - Highway Crossings)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Insufficient ROW | 1 | 100% | 1 | 4.545% | 850 | 38.6364 | Design/Plan Issues | 8 | 36.36%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 25% | 4 | 18.18% | 23587.25 | 4288.5909 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 4 | 18.18%
| Constructability Issues-Unspecified | 3 | 75% |  |  |  |  | Contract Amendment | 4 | 18.18%
Contract Amendment | Line Item Omission | 4 | 100% | 4 | 18.18% | 1538.3425 | 279.6986 | Differing Site Conditions (Except Utilities) | 2 | 9.091%
Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 12.5% | 8 | 36.36% | 4257.472 | 1548.1716 | Safety Concerns (Except Contaminated Soil) | 2 | 9.091%
| Design Error-Unspecified | 2 | 25% |  |  |  |  | Access/ROW/Easement | 1 | 4.545%
| Design Revision-Unspecified | 5 | 62.5% |  |  |  |  | Erosion Control Problems | 1 | 4.545%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 100% | 2 | 9.091% | 43404 | 3945.8182
Erosion Control Problems | Erosion Control Problems-Unspecified | 1 | 100% | 1 | 4.545% | 222.2 | 10.1 | 12b. -- Table 2 Supplemental Agreements (Railroad - Highway Crossings)
Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 2 | 100% | 2 | 9.091% | 8653.445 | 786.6768 | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
[8 empty] | Pavement | 6 | 27.27% | 23881.125 | 6513.0341
[8 empty] | Traffic Control Systems (pavement Markings) | 4 | 18.18% | 911.7075 | 165.765
[8 empty] | Geotechnical | 2 | 9.091% | 43404 | 3945.8182
[8 empty] | Hydraulics | 2 | 9.091% | 9760.07 | 887.2791
[8 empty] | Roadway Design | 2 | 9.091% | 2375 | 215.9091
[8 empty] | Access/ROW/Easement | 1 | 4.545% | 850 | 38.6364
[8 empty] | Environmental | 1 | 4.545% | 222.2 | 10.1
[8 empty] | Procurement | 1 | 4.545% | 0 | 0
[8 empty] | TCP (Construction Phase) | 1 | 4.545% | 16116.75 | 732.5795
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 1 | 4.545% | -1161.6 | -52.8
[8 empty] | Utilities | 1 | 4.545% | 700 | 31.8182

## 13a. Claim-Rest Area
Return to Cover Page
13a. -- Table 3 Claims - Rest Area | [9 empty] | 13a. -- Table 1 Claims - Rest Area
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 100% | 1 | 2.703% | 0 | 0 | 3 | 0.081081 | Design/Plan Issues | 8 | 21.62%
Contract Amendment | Error in Entering Time Extensions in HiCAMS | 3 | 60% | 5 | 13.51% | 220000 | 29729.7297 | 22 | 2.973 | Contract Amendment | 5 | 13.51%
| Line Item Omission | 1 | 20% | [6 empty] | Natural Disaster | 4 | 10.81%
| Settlement and Release Agreement | 1 | 20% | [6 empty] | Procurement Issues | 4 | 10.81%
Design/Plan Issues | Design/Plan Error-Unspecified | 1 | 12.5% | 8 | 21.62% | 0 | 0 | 45.625 | 9.8649 | Start Date Delays | 4 | 10.81%
| Design/Plan Revision-Unspecified | 7 | 87.5% | [6 empty] | Project Closeout Issues | 3 | 8.108%
Environmental/Community Concerns | Erosion Control Problems | 1 | 50% | 2 | 5.405% | 0 | 0 | 114 | 6.1622 | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 3 | 8.108%
| Vegetation Establishment | 1 | 50% | [6 empty] | Environmental/Community Concerns | 2 | 5.405%
Issues with Underground Utilities | Utility Conflict | 1 | 100% | 1 | 2.703% | 1881.07 | 50.8397 | 1 | 0.027027 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 1 | 2.703%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 2.703% | 0 | 0 | 65 | 1.7568 | Issues with Underground Utilities | 1 | 2.703%
Natural Disaster | Natural Disaster-Hurricane | 4 | 100% | 4 | 10.81% | 0 | 0 | 10.5 | 1.1351 | M&R/Replacement | 1 | 2.703%
Permit | Insufficient Permit | 1 | 100% | 1 | 2.703% | 0 | 0 | 10 | 0.27027 | Permit | 1 | 2.703%
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 25% | 4 | 10.81% | 9928.165 | 1073.3151 | 65.3333 | 7.0631
| Material Cost Fluctuation | 1 | 25% | [6 empty] | 13a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
| Unavailability of Materials/Material Shortage | 1 | 25% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 25%
| Wrong Order Placement | 1 | 25% | [6 empty] | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 25%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 3 | 100% | 3 | 8.108% | 0 | 0 | 16.6667 | 1.3514 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 12.5%
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-Unspecified | 2 | 66.67% | 3 | 8.108% | 0 | 0 | 11 | 0.89189 | Utility – design, as-builts, etc. | 12.5%
| Miscommunication (Construction Progress) | 1 | 33.33% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 0%
Start Date Delays | Delay in Contract Execution | 2 | 50% | 4 | 10.81% | 0 | 0 | 18.5 | 2 | Structural Design – bridge superstructure, bridge substructure, etc. | 0%
| Delay in Project Award | 1 | 25% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 0%
| Start Date Delays-Unspecified | 1 | 25% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
[10 empty] | Unspecified | 25%
(1) Based on WSDOT's Risk Breakdown Structure

## 13b. SA-Rest Area
Return to Cover Page
13b. -- Table 3 Supplemental Agreements (Rest Area) | [7 empty] | 13b. -- Table 1 Supplemental Agreements (Rest Area)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Providing Access to Site | 1 | 100% | 1 | 1.389% | 423.5 | 588.2% | Design/Plan Issues | 26 | 36.11%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 100% | 3 | 4.167% | 25421.55 | 105923% | M&R/Replacement | 10 | 13.89%
Construction Method Revision | Construction Method Revision-Unspecified | 2 | 100% | 2 | 2.778% | 28601.82 | 79450% | Stakeholder Request | 9 | 12.5%
Contract Amendment | Elimination of Contract Line Item | 1 | 14.29% | 7 | 9.722% | 7415.4143 | 72094% | Contract Amendment | 7 | 9.722%
| Line Item Omission | 5 | 71.43% |  |  |  |  | Differing Site Conditions (Except Utilities) | 5 | 6.944%
| Unavailability of Funds/Cash Flow Considerations | 1 | 14.29% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 3 | 4.167%
Design/Plan Issues | Construction Plans Error/Discrepancy | 3 | 11.54% | 26 | 36.11% | 5589.7723 | 201853% | Safety Concerns (Except Contaminated Soil) | 3 | 4.167%
| Design Error-Unspecified | 4 | 15.38% |  |  |  |  | Construction Method Revision | 2 | 2.778%
| Design Revision-Unspecified | 19 | 73.08% |  |  |  |  | Drainage Issues | 2 | 2.778%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 1 | 20% | 5 | 6.944% | 9833.11 | 68285% | Access/ROW/Easement | 1 | 1.389%
| Differing Site Conditions-Unspecified | 3 | 60% |  |  |  |  | Issues with Underground Utilities | 1 | 1.389%
| Differing Site Conditions-Unsuitable Materials | 1 | 20% |  |  |  |  | Procurement Issues | 1 | 1.389%
Drainage Issues | Drainage Issues-Unspecified | 1 | 50% | 2 | 2.778% | 5550 | 15417% | Quantities Overrun/Underrun | 1 | 1.389%
| Stormwater Concerns | 1 | 50% |  |  |  |  | Survey/Test Issues | 1 | 1.389%
Issues with Underground Utilities | Utility Conflict | 1 | 100% | 1 | 1.389% | 4935 | 6854%
M&R/Replacement | M&R/Replacement-Unspecified | 10 | 100% | 10 | 13.89% | 10956.802 | 152178% | 13b. -- Table 2 Supplemental Agreements (Rest Area)
Procurement Issues | Shop Drawing Error | 1 | 100% | 1 | 1.389% | 3597.96 | 4997% | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 100% | 1 | 1.389% | 115500 | 160417% | Finishing and Interior Work | 19 | 26.39% | 5683.5542 | 1499.8268
Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 2 | 66.67% | 3 | 4.167% | 1734.4 | 7227% | Utilities | 12 | 16.67% | 5139.3042 | 856.5507
| Tripping Hazard | 1 | 33.33% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 11 | 15.28% | 6414.5055 | 979.9939
Stakeholder Request | DOT Request-Unspecified | 2 | 22.22% | 9 | 12.5% | 7023.9022 | 87799% | Hydraulics | 7 | 9.722% | 4075.15 | 396.1951
| Stakeholder Request-Future Development Concerns | 1 | 11.11% |  |  |  |  | Structural | 6 | 8.333% | 17851.7333 | 1487.6444
| Stakeholder Request-Unspecified | 6 | 66.67% |  |  |  |  | Geotechnical | 4 | 5.556% | 42953.25 | 2386.2917
Survey/Test Issues | Additional Survey/Test Required | 1 | 100% | 1 | 1.389% | 38331 | 53238% | Environmental | 3 | 4.167% | 9047.7 | 376.9875
[8 empty] | Procurement | 3 | 4.167% | 7175.8967 | 298.9957
[8 empty] | Other | 2 | 2.778% | 960.25 | 26.6736
[8 empty] | Safety | 2 | 2.778% | 22702 | 630.6111
[8 empty] | Contract | 1 | 1.389% | 31267.5 | 434.2708
[8 empty] | Security/Protection | 1 | 1.389% | 880 | 12.2222
[8 empty] | TCP (Construction Phase) | 1 | 1.389% | 55938.64 | 776.9256

## 14a. Claim-Rural
Return to Cover Page
14a. -- Table 3 Claims - Rural | [9 empty] | 14a. -- Table 1 Claims - Rural
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Right of Entry Acquisition Delays | 1 | 14.29% | 7 | 2.035% | 15743.095 | 320.3537 | 97.8571 | 1.9913 | Access/ROW/Easement | 7 | 2.035%
| ROW Acquisition Delays-Unspecified | 6 | 85.71% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 22 | 6.395%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 4.545% | 22 | 6.395% | 21604.9075 | 1381.7092 | 83.2778 | 5.3259 | Contract Amendment | 39 | 11.34%
| Constructability Issues-Seasonal Limitations (Weather) | 20 | 90.91% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 7 | 2.035%
| Constructability Issues-Unspecified | 1 | 4.545% | [6 empty] | Design/Plan Issues | 63 | 18.31%
Contract Amendment | Contractor Replacement | 1 | 2.564% | 39 | 11.34% | 1330002.0672 | 150785.1181 | 94.9286 | 10.7623 | Differing Site Conditions (Except Utilities) | 8 | 2.326%
| Elimination of Contract Line Item | 3 | 7.692% | [6 empty] | Environmental/Community Concerns | 13 | 3.779%
| Error in Entering Time Extensions in HiCAMS | 16 | 41.03% | [6 empty] | Issues with Underground Utilities | 46 | 13.37%
| Line Item Omission | 3 | 7.692% | [6 empty] | M&R/Replacement | 22 | 6.395%
| Settlement and Release Agreement | 16 | 41.03% | [6 empty] | Natural Disaster | 30 | 8.721%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 4 | 57.14% | 7 | 2.035% | 0 | 0 | 54 | 1.0988 | Other | 5 | 1.453%
| Untimely Receipt of Design | 2 | 28.57% | [6 empty] | Permit | 4 | 1.163%
| Untimely Review and Return of Submittals | 1 | 14.29% | [6 empty] | Procurement Issues | 12 | 3.488%
Design/Plan Issues | Compliance with Standard Specifications | 1 | 1.587% | 63 | 18.31% | 132272.86 | 24224.3901 | 47.0435 | 8.6155 | Project Closeout Issues | 9 | 2.616%
| Design/Plan Error-Unspecified | 21 | 33.33% | [6 empty] | Quantities Overrun/Underrun | 12 | 3.488%
| Design/Plan Revision-Unspecified | 41 | 65.08% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 29 | 8.43%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 2 | 25% | 8 | 2.326% | 43123.0625 | 1002.8619 | 90 | 2.093 | Start Date Delays | 10 | 2.907%
| Differing Site Conditions-Unspecified | 1 | 12.5% | [6 empty] | Survey/Test Issues | 6 | 1.744%
| Differing Site Conditions-Unsuitable Materials | 5 | 62.5%
Environmental/Community Concerns | Environmental Concerns/Unspecified | 3 | 23.08% | 13 | 3.779% | 2207.0133 | 83.4046 | 238.5 | 9.0131 | 14a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
| Vegetation Establishment | 10 | 76.92% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 28.57%
Issues with Underground Utilities | Utilities not Relocated on Time | 17 | 36.96% | 46 | 13.37% | 368771.8191 | 49312.5107 | 108.1026 | 14.4556 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 23.81%
| Utility Conflict | 29 | 63.04% | [6 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 11.11%
M&R/Replacement | M&R/Replacement-Damaged Objects | 2 | 9.091% | 22 | 6.395% | 10843.1111 | 693.4548 | 70.4 | 4.5023 | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 9.524%
| M&R/Replacement-Unspecified | 20 | 90.91% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 7.937%
Natural Disaster | Natural Disaster-Hurricane | 30 | 100% | 30 | 8.721% | 48307.886 | 4212.897 | 17.1786 | 1.4981 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 4.762%
Other | Covid 19 Impact | 1 | 20% | 5 | 1.453% | 7047.8967 | 102.4404 | 56.5 | 0.82122 | Utility – design, as-builts, etc. | 4.762%
| Lawsuit Costs | 1 | 20% | [6 empty] | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 0%
| Misinterpretation of Plans | 1 | 20% | [6 empty] | Unspecified | 9.524%
| Unforeseen Issues-Unspecified | 2 | 40% | [6 empty] | (1) Based on WSDOT's Risk Breakdown Structure
Permit | Insufficient Permit | 1 | 25% | 4 | 1.163% | 12939.66 | 150.4612 | 31 | 0.36047
| Permit Acquisition Waiting Period | 1 | 25%
| Permit Expiration | 1 | 25%
| Permit Violation | 1 | 25%
Procurement Issues | DOT Furnished Materials/Equipment Delays | 2 | 16.67% | 12 | 3.488% | 9373.65 | 326.9878 | 67.6 | 2.3581
| Material Acquisition Delays/Long Lead Items | 2 | 16.67%
| Material Cost Fluctuation | 1 | 8.333%
| Power Supply Delays | 6 | 50%
| Unavailability of Materials/Material Shortage | 1 | 8.333%
Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 9 | 100% | 9 | 2.616% | 0 | 0 | 15.3333 | 0.40116
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 12 | 100% | 12 | 3.488% | 91413.6678 | 3188.8489 | 20.25 | 0.7064
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 4 | 13.79% | 29 | 8.43% | 12844.182 | 1082.7944 | 26.96 | 2.2728
| Miscommunication (Construction Progress) | 1 | 3.448%
| Purposeful Limited Work Schedule | 10 | 34.48%
| Scheduling Conflicts-Inspection | 1 | 3.448%
| Waiting for Other Entities to Perform Work | 4 | 13.79%
| Work Out of Sequence | 3 | 10.34%
| Work Restriction-Social Event | 4 | 13.79%
| Work Restriction-Unspecified | 2 | 6.897%
Start Date Delays | Delay in Availability of Project | 1 | 10% | 10 | 2.907% | 0 | 0 | 24.4 | 0.7093
| Delay in Contract Execution | 2 | 20%
| Delay in Preconstruction Meeting | 5 | 50%
| Delay in Project Award | 2 | 20%
Survey/Test Issues | Survey Error | 5 | 83.33% | 6 | 1.744% | 137254.3467 | 2393.9712 | 34.5 | 0.60174
| Survey Results Delays | 1 | 16.67%

## 14b. SA-Rural
Return to Cover Page
14b. -- Table 3 Supplemental Agreements (Rural) | [7 empty] | 14b. -- Table 1 Supplemental Agreements (Rural)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Design/Plan Issues | Compliance with Standard Specifications | 17 | 9.77% | 174 | 27.88% | 108614.5845 | 30286.7591 | Design/Plan Issues | 174 | 27.88%
| Construction Plans Error/Discrepancy | 11 | 6.322% |  |  |  |  | Contract Amendment | 101 | 16.19%
| Design Error-Elevation Difference with Existing Objects | 4 | 2.299% |  |  |  |  | Stakeholder Request | 48 | 7.692%
| Design Error-Unspecified | 13 | 7.471% |  |  |  |  | Differing Site Conditions (Except Utilities) | 43 | 6.891%
| Design Revision-Achieve Higher/Acceptable Quality | 5 | 2.874% |  |  |  |  | M&R/Replacement | 42 | 6.731%
| Design Revision-Change in Design Criteria | 1 | 0.5747% |  |  |  |  | Safety Concerns (Except Contaminated Soil) | 35 | 5.609%
| Design Revision-Functionality Issues | 1 | 0.5747% |  |  |  |  | Issues with Underground Utilities | 31 | 4.968%
| Design Revision-Future Maintenance Concerns | 6 | 3.448% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 31 | 4.968%
| Design Revision-per Contractor Request | 8 | 4.598% |  |  |  |  | Construction Method Revision | 28 | 4.487%
| Design Revision-Toll Collection | 1 | 0.5747% |  |  |  |  | Environmental/Community Concerns | 18 | 2.885%
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 0.5747% |  |  |  |  | Access/ROW/Easement | 16 | 2.564%
| Design Revision-Unspecified | 90 | 51.72% |  |  |  |  | Scheduling and Coordination Issues | 15 | 2.404%
| Design Revision-Value Engineering Proposal | 5 | 2.874% |  |  |  |  | Quantities Overrun/Underrun | 15 | 2.404%
| Increased Traffic Volume | 2 | 1.149% |  |  |  |  | Drainage Issues | 8 | 1.282%
| Scope Change | 9 | 5.172% |  |  |  |  | Erosion Control Problems | 8 | 1.282%
Contract Amendment | Change in Contract Provisions | 4 | 3.96% | 101 | 16.19% | 137159.8069 | 22200.5457 | Procurement Issues | 6 | 0.9615%
| Elimination of Contract Line Item | 1 | 0.9901% |  |  |  |  | Survey/Test Issues | 3 | 0.4808%
| Issues with Previous SA | 2 | 1.98% |  |  |  |  | Other | 2 | 0.3205%
| Line Item Omission | 84 | 83.17%
| Mitigation of Potential Risk | 1 | 0.9901% |  |  |  |  | 14b. -- Table 2 Supplemental Agreements (Rural)
| Permission to Hold Additional Retainage | 1 | 0.9901% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Revise Measurement and Payment Method | 8 | 7.921% |  |  |  |  | Utilities | 118 | 18.91% | 74738.669 | 14133.2739
Stakeholder Request | DOT Request-Unspecified | 18 | 37.5% | 48 | 7.692% | 175183.9472 | 13475.6882 | Hydraulics | 79 | 12.66% | 28685.1585 | 3631.6146
| Stakeholder Request-Future Development Concerns | 3 | 6.25% |  |  |  |  | Geotechnical | 56 | 8.974% | 40480.5862 | 3632.8731
| Stakeholder Request-Unspecified | 27 | 56.25% |  |  |  |  | Roadway Design | 50 | 8.013% | 69576.6432 | 5575.0515
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 2.326% | 43 | 6.891% | 20484.9567 | 1411.6236 | Traffic Control Systems (Except Pavement Markings) | 50 | 8.013% | 71441.8775 | 5724.5094
| Differing Site Conditions-Contaminated Soil | 2 | 4.651% |  |  |  |  | Pavement | 45 | 7.212% | 258137.305 | 18615.671
| Differing Site Conditions-Encountered Rock | 1 | 2.326% |  |  |  |  | Environmental | 37 | 5.929% | 38030.6684 | 2255.0236
| Differing Site Conditions-Extra Work from Previous Projects | 1 | 2.326% |  |  |  |  | TCP (Construction Phase) | 36 | 5.769% | 30323.0056 | 1749.4042
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 7 | 16.28% |  |  |  |  | Structural | 22 | 3.526% | 21832.0186 | 769.7186
| Differing Site Conditions-Not Shown in Construction Plans | 2 | 4.651% |  |  |  |  | Corridor/Traffic Design | 21 | 3.365% | 261163.0705 | 8789.1418
| Differing Site Conditions-Unspecified | 21 | 48.84% |  |  |  |  | Traffic Control Systems (pavement Markings) | 21 | 3.365% | 15760.3371 | 530.396
| Differing Site Conditions-Unsuitable Materials | 2 | 4.651% |  |  |  |  | Access/ROW/Easement | 13 | 2.083% | 19205.8962 | 400.1228
| Slope Protection/Soil Stabilization | 6 | 13.95% |  |  |  |  | Safety | 13 | 2.083% | 130893.7008 | 2726.9521
M&R/Replacement | Damaged Objects | 2 | 4.762% | 42 | 6.731% | 32528.4936 | 2189.4178 | Contract | 12 | 1.923% | 830505.2778 | 15971.2553
| M&R/Replacement-Unspecified | 40 | 95.24% |  |  |  |  | Roadway Alignment | 11 | 1.763% | 46769.3409 | 824.4595
Safety Concerns (Except Contaminated Soil) | Falling Hazard | 2 | 5.714% | 35 | 5.609% | 25495.8243 | 1430.0542 | Schedule | 10 | 1.603% | 1018010.5162 | 16314.2711
| Hazardous Materials Removal | 1 | 2.857% |  |  |  |  | Other | 9 | 1.442% | 6296.8244 | 90.8196
| Safety Concerns-Unspecified | 28 | 80% |  |  |  |  | Procurement | 8 | 1.282% | -3053.7575 | -39.1507
| Sight Distance Concerns | 1 | 2.857% |  |  |  |  | Natural Disaster | 3 | 0.4808% | 16856.32 | 81.04
| Travelers/Public Safety | 3 | 8.571% |  |  |  |  | Permit | 3 | 0.4808% | 24911.76 | 119.7681
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 6.452% | 31 | 4.968% | 51497.8733 | 2558.3879 | Security/Protection | 3 | 0.4808% | 9306.8333 | 44.7444
| Utility Conflict | 29 | 93.55% |  |  |  |  | Survey | 3 | 0.4808% | 3790.42 | 18.2232
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 7 | 22.58% | 31 | 4.968% | 68684.0374 | 3412.1878 | Finishing and Interior Work | 1 | 0.1603% | 2500 | 4.0064
| Constructability Issues-Unspecified | 24 | 77.42%
Construction Method Revision | Construction Method Revision-Unspecified | 28 | 100% | 28 | 4.487% | 16657.0792 | 747.433
Environmental/Community Concerns | Animal Protection/Endangered Species | 3 | 16.67% | 18 | 2.885% | 55171.8744 | 1591.4964
| Avoid Historical Structure | 1 | 5.556%
| Construction Impacts | 1 | 5.556%
| Environmental Concerns-Unspecified | 4 | 22.22%
| Vegetation Establishment | 7 | 38.89%
| Wetland Delineation | 2 | 11.11%
Access/ROW/Easement | Easement Acquisition Delays | 1 | 6.25% | 16 | 2.564% | 59033.6056 | 1513.6822
| Extra Work Associated with ROW Agreement | 3 | 18.75%
| Insufficient ROW | 2 | 12.5%
| Insufficient Utility Easement | 2 | 12.5%
| Property Owners Access | 5 | 31.25%
| Providing Access to Site | 1 | 6.25%
| Traffic Access Point | 2 | 12.5%
Scheduling and Coordination Issues | Additional ICT Required | 1 | 6.667% | 15 | 2.404% | 428955.2969 | 10311.4254
| Conflict with Other Projects | 2 | 13.33%
| Conflict/Overlap with Adjacent Projects | 1 | 6.667%
| Early Project Completion | 7 | 46.67%
| Overtime Hour Request | 1 | 6.667%
| Project Phasing Problems | 1 | 6.667%
| Statewide Initiative to Accelerate Projects | 1 | 6.667%
| Timely Completion of Project | 1 | 6.667%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 13 | 86.67% | 15 | 2.404% | 256152.7046 | 6157.5169
| Waste Excessive Material | 2 | 13.33%
Drainage Issues | Drainage Issues-Unspecified | 7 | 87.5% | 8 | 1.282% | 17283.875 | 221.5881
| Stormwater Concerns | 1 | 12.5%
Erosion Control Problems | Erosion Control Problems-Unspecified | 7 | 87.5% | 8 | 1.282% | 10811.6963 | 138.6115
| Waste Site Erosion Control | 1 | 12.5%
Procurement Issues | Shop Drawing Error | 1 | 16.67% | 6 | 0.9615% | 9710.5517 | 93.3707
| Unavailability of Materials/Material Shortage | 4 | 66.67%
| Wrong Order Placement | 1 | 16.67%
Survey/Test Issues | Survey Error-Staking | 1 | 33.33% | 3 | 0.4808% | 3790.42 | 18.2232
| Survey Error-Unspecified | 2 | 66.67%
Other | Permit Acquisition Issues | 1 | 50% | 2 | 0.3205% | 3420.025 | 10.9616
| Permit Requirements | 1 | 50%

## 15a. Claim-Safe Route to School
Return to Cover Page
15a. -- Table 3 Claims - Safe Routes to School | [9 empty] | 15a. -- Table 1 Claims - Safe Routes to School
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 1 | 1 | 6.667% | 0 | 0 | 118 | 7.8667 | Issues with Underground Utilities | 5 | 33.33%
Contract Amendment | Contract Error | 2 | 0.5 | 4 | 26.67% | 0 | 0 | 6.25 | 1.6667 | Contract Amendment | 4 | 26.67%
| Error in Entering Time Extensions in HiCAMS | 2 | 0.5 | [6 empty] | Project Closeout Issues | 2 | 13.33%
Environmental/Community Concerns | Vegetation Establishment | 1 | 1 | 1 | 6.667% | 0 | 0 | 84 | 5.6 | Constructability Issues (Except Geotechnical/Underground Conflicts) | 1 | 6.667%
Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 0.4 | 5 | 33.33% | 20533.28 | 6844.4267 | 118.6 | 39.5333 | Environmental/Community Concerns | 1 | 6.667%
| Utility Conflict | 3 | 0.6 | [6 empty] | Natural Disaster | 1 | 6.667%
Natural Disaster | Natural Disaster-Hurricane | 1 | 1 | 1 | 6.667% | 0 | 0 | 14 | 0.93333 | Quantities Overrun/Underrun | 1 | 6.667%
Project Closeout Issues | Final Punchlist Extra Work | 1 | 0.5 | 2 | 13.33% | 0 | 0 | 14 | 1.8667
| Scheduling Conflicts-Final Inspection/Punchlist | 1 | 0.5 | [6 empty] | 15a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 1 | 1 | 6.667% | 5655 | 377 | - | - | No Design/Plan Issues
(1) Based on WSDOT's Risk Breakdown Structure

## 15b. SA-Safe Route to School
Return to Cover Page
15b. -- Table 3 Supplemental Agreements (Safe Routes to School) | [7 empty] | 15b. -- Table 1 Supplemental Agreements (Safe Routes to School)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Contract Amendment | Line Item Omission | 2 | 100% | 2 | 20% | 11831.915 | 2366.383 | Contract Amendment | 2 | 20%
Design/Plan Issues | Design Error-Unspecified | 1 | 100% | 1 | 10% | 3212.05 | 321.205 | Differing Site Conditions (Except Utilities) | 2 | 20%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 50% | 2 | 20% | 12415 | 2483 | Stakeholder Request | 2 | 20%
| Differing Site Conditions-Unspecified | 1 | 50% |  |  |  |  | Design/Plan Issues | 1 | 10%
Issues with Underground Utilities | Utility Conflict | 1 | 100% | 1 | 10% | 3672 | 367.2 | Issues with Underground Utilities | 1 | 10%
M&R/Replacement | M&R/Replacement-Unspecified | 1 | 100% | 1 | 10% | 18025 | 1802.5 | M&R/Replacement | 1 | 10%
Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 1 | 100% | 1 | 10% | 7700 | 770 | Safety Concerns (Except Contaminated Soil) | 1 | 10%
Stakeholder Request | DOT Request-Unspecified | 2 | 100% | 2 | 20% | 6951.85 | 1390.37
15b. -- Table 2 Supplemental Agreements (Safe Routes to School)
[8 empty] | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
[8 empty] | Roadway Design | 3 | 30% | 8747.9333 | 2624.38
[8 empty] | Geotechnical | 2 | 20% | 13525.015 | 2705.003
[8 empty] | Hydraulics | 2 | 20% | 10618.525 | 2123.705
[8 empty] | TCP (Construction Phase) | 1 | 10% | 7700 | 770
[8 empty] | Traffic Control Systems (Except Pavement Markings) | 1 | 10% | 9103.7 | 910.37
[8 empty] | Utilities | 1 | 10% | 3672 | 367.2

## 16a. Claim-Urban
Return to Cover Page
16a. -- Table 3 Claims - Urban | [9 empty] | 16a. -- Table 1 Claims - Urban
Generic Cause | Generic Cause Level 2 | Count GC Level 2 | GC Level 2-GC Ratio | Total | % Total | Average Cost per claim | Expected Cost per claim | Average Time Granted per claim | Expected Time Granted per claim | Generic Cause | Count | % Total
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 16.67% | 6 | 2.459% | 95664.05 | 2352.3947 | 74.6667 | 1.8361 | Design/Plan Issues | 56 | 22.95%
| Railroad Right of Entry | 1 | 16.67% | [6 empty] | Issues with Underground Utilities | 46 | 18.85%
| ROW Acquisition Delays-Property Owners Agreement | 1 | 16.67% | [6 empty] | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | 23 | 9.426%
| ROW Acquisition Delays-Unspecified | 3 | 50% | [6 empty] | Contract Amendment | 19 | 7.787%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 7 | 100% | 7 | 2.869% | 0 | 0 | 92 | 2.6393 | Natural Disaster | 17 | 6.967%
Contract Amendment | Elimination of Contract Line Item | 1 | 5.263% | 19 | 7.787% | 16760.5 | 1305.1209 | 36.375 | 2.8325 | Quantities Overrun/Underrun | 16 | 6.557%
| Error in Entering Time Extensions in HiCAMS | 10 | 52.63% | [6 empty] | Project Closeout Issues | 14 | 5.738%
| Line Item Omission | 5 | 26.32% | [6 empty] | Design Approval Waiting Period/Indecision/Negotiation | 8 | 3.279%
| Revise Measurement and Payment Method | 1 | 5.263% | [6 empty] | M&R/Replacement | 8 | 3.279%
| Settlement and Release Agreement | 1 | 5.263% | [6 empty] | Constructability Issues (Except Geotechnical/Underground Conflicts) | 7 | 2.869%
| Unavailability of Funds/Cash Flow Considerations | 1 | 5.263% | [6 empty] | Differing Site Conditions (Except Utilities) | 7 | 2.869%
Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 2 | 25% | 8 | 3.279% | 0 | 0 | 86.5 | 2.8361 | Environmental/Community Concerns | 7 | 2.869%
| Untimely Review and Return of Submittals | 6 | 75% | [6 empty] | Access/ROW/Easement | 6 | 2.459%
Design/Plan Issues | Compliance with Standard Specifications | 2 | 3.571% | 56 | 22.95% | 72292.4639 | 16591.713 | 44.025 | 10.1041 | Procurement Issues | 5 | 2.049%
| Design/Plan Error-Unspecified | 17 | 30.36% | [6 empty] | Survey/Test Issues | 3 | 1.23%
| Design/Plan Revision-Unspecified | 37 | 66.07% | [6 empty] | Other | 1 | 0.4098%
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 14.29% | 7 | 2.869% | 19933.78 | 571.8707 | 42 | 1.2049 | Permit | 1 | 0.4098%
| Differing Site Conditions-Contaminated Soil | 1 | 14.29%
| Differing Site Conditions-Hazardous Materials | 4 | 57.14% | [6 empty] | 16a. -- Table 2 "Design/Plan Issues" Category (RBS) (1) | % (Design/Plan Issues)
| Differing Site Conditions-Incomplete Work by Others | 1 | 14.29% | [6 empty] | Roadway Design – vertical/horizontal alignment, earthwork, pavement, grade, etc. | 26.79%
Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 14.29% | 7 | 2.869% | 12551.2667 | 360.0773 | 98.4 | 2.823 | Traffic Design – ITS, illumination, signals, intersections, roadway signs, safety (concrete island, sight distance, etc.). | 19.64%
| Erosion Control Problems | 2 | 28.57% | [6 empty] | Hydraulic Design – flow control, criteria changes, drainage, irrigation, system design, etc. | 17.86%
| Vegetation Establishment | 3 | 42.86% | [6 empty] | Structural Design – bridge superstructure, bridge substructure, etc. | 7.143%
| Wetland Discovery | 1 | 14.29% | [6 empty] | Environmental – vegetation plans, habitat mitigation, etc. | 7.143%
Issues with Underground Utilities | Utilities not Relocated on Time | 10 | 21.74% | 46 | 18.85% | 42028.7289 | 7923.4489 | 118.4762 | 22.3357 | Geotechnical Design – foundations, retaining walls, pile driving, etc. | 5.357%
| Utility Conflict | 36 | 78.26% | [6 empty] | Utility – design, as-builts, etc. | 5.357%
M&R/Replacement | M&R/Replacement-Damaged Objects | 1 | 12.5% | 8 | 3.279% | 13509.9425 | 442.9489 | 31 | 1.0164 | Traffic Control & Staging – Maintenance of Traffic, Work Zone Traffic Control, etc. | 1.786%
| M&R/Replacement-Unspecified | 7 | 87.5% | [6 empty] | Unspecified | 8.929%
Natural Disaster | Natural Disaster-Drought | 1 | 5.882% | 17 | 6.967% | 3948.72 | 275.1157 | 41.375 | 2.8827 | (1) Based on WSDOT's Risk Breakdown Structure
| Natural Disaster-Hurricane | 14 | 82.35%
| Natural Disaster-Sinkhole | 1 | 5.882%
| Natural Disaster-Thunderstorm | 1 | 5.882%
Other | Unforeseen Issues-Unspecified | 1 | 100% | 1 | 0.4098% | 2742.05 | 11.2379 | 3 | 0.012295
Permit | Permit Acquisition Waiting Period | 1 | 100% | 1 | 0.4098% | 0 | 0 | 36 | 0.14754
Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 20% | 5 | 2.049% | 0 | 0 | 109.4 | 2.2418
| Power Supply Delays | 3 | 60%
| Unavailability of Materials/Material Shortage | 1 | 20%
Project Closeout Issues | Delay in Project Acceptance | 1 | 7.143% | 14 | 5.738% | 0 | 0 | 32 | 1.8361
| Delay in Receipt of Final Punchlist | 1 | 7.143%
| Final Punchlist Extra Work | 4 | 28.57%
| Scheduling Conflicts-Final Inspection/Punchlist | 8 | 57.14%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 16 | 100% | 16 | 6.557% | 102317.22 | 6709.3259 | 33.8889 | 2.2222
Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 3 | 13.04% | 23 | 9.426% | 732970.215 | 69091.4547 | 21.6667 | 2.0423
| Early Project Completion | 1 | 4.348%
| Purposeful Limited Work Schedule | 14 | 60.87%
| Scheduling Conflicts-Inspection | 1 | 4.348%
| Waiting for Other Entities to Perform Work | 1 | 4.348%
| Work Out of Sequence | 1 | 4.348%
| Work Restriction-Social Event | 2 | 8.696%
Survey/Test Issues | Survey Error | 3 | 100% | 3 | 1.23% | 0 | 0 | 3.3333 | 0.040984

## 16b. SA-Urban
Return to Cover Page
16b. -- Table 3 Supplemental Agreements (Urban) | [7 empty] | 16b. -- Table 1 Supplemental Agreements (Urban)
Generic Cause | Generic Cause Level 2 | Count (Generic Cause Level 2) | GC Level 2-GC Ratio | Count (Generic Cause) | % (Generic Cause) | Average Cost per SA | Expected Cost per SA | Generic Cause | Count | %
Access/ROW/Easement | Extra Work Associated with ROW Agreement | 4 | 26.67% | 15 | 3.132% | 21302.192 | 667.0833 | Design/Plan Issues | 104 | 21.71%
| Insufficient ROW | 4 | 26.67% |  |  |  |  | Contract Amendment | 74 | 15.45%
| Railroad Right of Entry Delays | 1 | 6.667% |  |  |  |  | Issues with Underground Utilities | 52 | 10.86%
| ROW Acquisition Delays | 1 | 6.667% |  |  |  |  | Stakeholder Request | 47 | 9.812%
| ROW Revision | 1 | 6.667% |  |  |  |  | Differing Site Conditions (Except Utilities) | 42 | 8.768%
| Traffic Access Point | 4 | 26.67% |  |  |  |  | M&R/Replacement | 29 | 6.054%
Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 9 | 39.13% | 23 | 4.802% | 12255.6952 | 588.4781 | Safety Concerns (Except Contaminated Soil) | 24 | 5.01%
| Constructability Issues-Unspecified | 14 | 60.87% |  |  |  |  | Constructability Issues (Except Geotechnical/Underground Conflicts) | 23 | 4.802%
Construction Method Revision | Construction Method Revision-Unspecified | 22 | 100% | 22 | 4.593% | 332088.6367 | 15252.5052 | Construction Method Revision | 22 | 4.593%
Contract Amendment | Elimination of Contract Line Item | 2 | 2.703% | 74 | 15.45% | 12720.0915 | 1965.1081 | Access/ROW/Easement | 15 | 3.132%
| Issues with Previous SA | 1 | 1.351% |  |  |  |  | Scheduling and Coordination Issues | 11 | 2.296%
| Line Item Omission | 61 | 82.43% |  |  |  |  | Drainage Issues | 10 | 2.088%
| Revise Measurement and Payment Method | 7 | 9.459% |  |  |  |  | Erosion Control Problems | 8 | 1.67%
| Settlement and Release Agreement | 3 | 4.054% |  |  |  |  | Procurement Issues | 5 | 1.044%
Design/Plan Issues | Compliance with Standard Specifications | 13 | 12.5% | 104 | 21.71% | 153708.1566 | 33372.9609 | Quantities Overrun/Underrun | 5 | 1.044%
| Construction Plans Error/Discrepancy | 14 | 13.46% |  |  |  |  | Environmental/Community Concerns | 3 | 0.6263%
| Design Error-Elevation Difference with Existing Objects | 6 | 5.769% |  |  |  |  | Survey/Test Issues | 3 | 0.6263%
| Design Error-Unspecified | 5 | 4.808% |  |  |  |  | Other | 2 | 0.4175%
| Design Revision-Achieve Higher/Acceptable Quality | 5 | 4.808%
| Design Revision-Fix Impacts of Previous Revisions | 3 | 2.885% |  |  |  |  | 16b. -- Table 2 Supplemental Agreements (Urban)
| Design Revision-Functionality Issues | 5 | 4.808% |  |  |  |  | Risk Area | Count | % | Average Cost per SA | Expected Cost per SA
| Design Revision-Future Maintenance Concerns | 4 | 3.846% |  |  |  |  | Utilities | 112 | 23.38% | 16122.0464 | 3769.6643
| Design Revision-per Contractor Request | 4 | 3.846% |  |  |  |  | Hydraulics | 63 | 13.15% | 10029.6526 | 1319.1401
| Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 0.9615% |  |  |  |  | Traffic Control Systems (Except Pavement Markings) | 41 | 8.559% | 21842.7178 | 1869.6272
| Design Revision-Unspecified | 38 | 36.54% |  |  |  |  | Geotechnical | 36 | 7.516% | 76279.8686 | 5732.9338
| Incomplete Design | 2 | 1.923% |  |  |  |  | TCP (Construction Phase) | 36 | 7.516% | 219074.3224 | 16464.876
| Increased Traffic Volume | 2 | 1.923% |  |  |  |  | Roadway Design | 35 | 7.307% | 318465.8223 | 23269.9453
| Scope Change | 2 | 1.923% |  |  |  |  | Pavement | 25 | 5.219% | 289761.7754 | 15123.2659
Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 3 | 7.143% | 42 | 8.768% | 49098.909 | 4305.1235 | Environmental | 20 | 4.175% | 22410.628 | 935.7256
| Differing Site Conditions-Encountered Rock | 1 | 2.381% |  |  |  |  | Corridor/Traffic Design | 19 | 3.967% | 112890.35 | 4477.9053
| Differing Site Conditions-Extra Work from Previous Projects | 1 | 2.381% |  |  |  |  | Access/ROW/Easement | 14 | 2.923% | 17121.8071 | 500.4286
| Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 2.381% |  |  |  |  | Traffic Control Systems (Pavement Markings) | 14 | 2.923% | 11595.7407 | 338.9152
| Differing Site Conditions-Incomplete Work by Others | 2 | 4.762% |  |  |  |  | Safety | 11 | 2.296% | 26435.6964 | 607.0828
| Differing Site Conditions-Not Shown in Construction Plans | 9 | 21.43% |  |  |  |  | Structural | 11 | 2.296% | 55317.6591 | 1270.3429
| Differing Site Conditions-Unspecified | 17 | 40.48% |  |  |  |  | Contract | 10 | 2.088% | 39736.6714 | 829.5756
| Differing Site Conditions-Unsuitable Materials | 2 | 4.762% |  |  |  |  | Roadway Alignment | 7 | 1.461% | 31018.0271 | 453.2906
| Slope Protection/Soil Stabilization | 6 | 14.29% |  |  |  |  | Other | 6 | 1.253% | 28581.5517 | 358.0153
Drainage Issues | Drainage Issues-Unspecified | 10 | 100% | 10 | 2.088% | 7573.286 | 158.1062 | Procurement | 5 | 1.044% | 13899.218 | 145.0858
Environmental/Community Concerns | Noise Control | 2 | 66.67% | 3 | 0.6263% | 1351882.8633 | 8466.9073 | Schedule | 5 | 1.044% | 53696.292 | 560.5041
| Vegetation Establishment | 1 | 33.33% |  |  |  |  | Finishing and Interior Work | 3 | 0.6263% | 14505.25 | 90.8471
Erosion Control Problems | Erosion Control Problems-Unspecified | 8 | 100% | 8 | 1.67% | 39731.1213 | 663.5678 | Survey | 3 | 0.6263% | 1546.9233 | 9.6885
Issues with Underground Utilities | Inability to Locate Utilities | 6 | 11.54% | 52 | 10.86% | 15415.3873 | 1673.4867 | Railroad | 2 | 0.4175% | 6964.9 | 29.081
| Utilities not Relocated on Time | 1 | 1.923% |  |  |  |  | Security/Protection | 1 | 0.2088% | 10279.72 | 21.4608
| Utility Conflict | 45 | 86.54%
M&R/Replacement | Damaged Objects | 1 | 3.448% | 29 | 6.054% | 39544.8293 | 2394.1546
| M&R/Replacement-Unspecified | 28 | 96.55%
Other | Equipment/Items Protection | 1 | 50% | 2 | 0.4175% | 5254.86 | 21.941
| Permit Restrictions | 1 | 50%
Procurement Issues | Material Fabrication Delay | 1 | 20% | 5 | 1.044% | 21477.97 | 224.1959
| Shop Drawing Error | 1 | 20%
| Unavailability of Materials/Material Shortage | 3 | 60%
Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 5 | 100% | 5 | 1.044% | 25297.598 | 264.0668
Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 4.167% | 24 | 5.01% | 19414.0596 | 972.7295
| Safety Concerns-Unspecified | 22 | 91.67%
| Travelers/Public Safety | 1 | 4.167%
Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 9.091% | 11 | 2.296% | 74950.249 | 1721.1957
| Early Project Completion | 5 | 45.45%
| Miscommunication (Construction Progress) | 1 | 9.091%
| Project Phasing Problems | 2 | 18.18%
| Statewide Initiative to Accelerate Projects | 1 | 9.091%
| Timely Completion of Project | 1 | 9.091%
Stakeholder Request | DOT Request-Unspecified | 13 | 27.66% | 47 | 9.812% | 42581.9054 | 4178.1828
| Stakeholder Request-Future Development Concerns | 1 | 2.128%
| Stakeholder Request-Unspecified | 33 | 70.21%
Survey/Test Issues | Additional Survey/Test Required | 1 | 33.33% | 3 | 0.6263% | 21546.7467 | 134.9483
| Survey Error-Staking | 2 | 66.67%

## 17a. Mitigation (Roadway)
Return to Cover Page
Roadway Risk Mitigation Strategies
Regulatory and Safety Requirements for Borrow and Waste Pits
Key Question(s):
Is extra work required for the Corps of Engineers to provide technical data?
Has the NC Department of Environmental Quality approved the land quality of the pits?
Have land costs been considered properly in the estimates?
Are high voltage lines present in the borrow pit area, which could lead to the possibility of less efficient hauling of unclassified excavation materials?
Has sufficient time been scheduled for the establishment of vegetation for the waste pit to avoid final acceptance delays by the NC Department of Natural Resources?
Will the contractor need to perform an environmental impact study as a prerequisite for reimbursement?
Mitigation Strategies:
Obtain written approval from local authorities for use of the proposed site.
Undertake a preliminary site assessment prior to excavation work.
Confirm the extent and quality of the materials within the proposed site by drilling boreholes and/or excavating test pits.
Ensure that high voltage lines will not interfere with hauling operations.
Substandard Subgrade Quality
Key Question(s):
Are subgrade properties that could impact future pavement performance adequately understood?
Mitigation Strategies:
Understand the soil properties, proper grading practices, and quality control testing requirements to achieve a high-quality subgrade.
Determine the non-uniform geotechnical conditions throughout the pavement that could contribute to local permanent deformation.
Conduct a geotechnical study to evaluate specific problems (e.g., excessive subgrade rutting, aggregate contamination or degeneration, subgrade pumping, poor drainage, frost action, and/or swelling soil) and recommend procedures to mitigate potential problems.
Test the soil to determine the bearing capacity that relates to moisture and density information, as the pavement and designed base course thickness depend on the resultant subgrade strength.
Perform quality control and quality assurance testing and compare actual performance with predicted performance.
Inadequate Understanding of Site Hydraulic Characteristics
Key Questions:
Have frames, pipes, and boxes been designed properly?
Have appropriate grates been considered for the intended use of the roadway (e.g., bicycle traffic)?
Mitigation Strategies:
Ensure that pipe ends, culvert wing walls, and headwalls adjacent to the roadway do not extend past the surrounding ground.
Install a grated inlet to prevent water ponding at access points.
Install flexible lining for ditches with heavy runoff.
Install safe bicycle grates when expecting bicycle traffic.
Clean the ditches regularly to prevent silting and forcing water back onto the roadway surface or into the sub-base of the pavement.
Restore eroded and silted areas around barrier posts, breakaway sign supports, and highway light supports to the desired ground level, and seed those areas. If the area continues to erode, install bituminous overlays.
Surveying Errors and Omissions
Key Questions:
Have probable sources of surveying errors been considered?
Has the survey equipment been maintained and calibrated properly?
Mitigation Strategies:
Use a terrestrial laser scanner (TLS) to create 3D site models.
Maintain routine care of equipment.
Acclimatize the survey instruments to outside conditions prior to final setup in cold or hot weather when using vehicle climate control.
Use mapping grade receivers to export collected data to an external database, such as a geographical information system (GIS).
Before commencing a GPS project, obtain the latest versions of all software, adjust all tribraches, and visually check all cables and connections.
Employ electronic distance measuring instruments, such as total stations.
Use hand levels for the quick location of turn and instrument points and conduct elevation checks during grading operations.
Use digital levels for all surveys that require elevations.
Analyze traverse closure errors to identify and mitigate specific types of error.
Use sight distances that best fit the terrain and are most comfortable for the instrument operator. Sight distances should not exceed 200 ft (60 m).
Set benchmarks prior to or during leveling. Check for all found monuments that are to be incorporated in the level line for stability.
Driveway Issues
Key Questions:
Have all driveways been identified and taken into account for roadway construction?
Has the possibility of driveway flooding been considered? From roadside ditch? From nearby stream?
Mitigation Strategies:
Using eco-friendly permeable pavers, such as TRUEGRID© pavers, to help solve flooded driveway problems.
Implement seal-coating, a cost-saving preventive maintenance process that can slow the natural degradation process.
Prevent future root intrusion by installing a root barrier between the planted area and asphalt surface.
Install a transition mill and asphalt overlay.
Install a modified concrete base where a high water table affects the surface or inadequate installation results in base failure.
Poorly Timed Installation of Pavement Markings
Key Questions:
Does the schedule accommodate the properly timed installation of pavement and markings?
Mitigation Strategies:
Ensure that activities such as the paving and installation of thermal markings are scheduled during appropriate times of the year. For example, the installation of thermoplastic pavement markings requires warm temperatures to establish proper bonding to the pavement surface.
Inadequate Planning for Signage and Signalization
Key Questions:
Are there any aerial utility conflicts that could affect the installation of overhead signs?
Have signage plans been reviewed and do they include all necessary dimensions?
Have power requirements for overhead sign structures and sources been identified to reduce the chance of delay?
Has sufficient ROW been acquired for the installation of signs?
Mitigation Strategies:
Check for all issues that pertain to the installation of overhead signs (e.g., utility conflicts, power availability, and dimensions).
Install lighting along horizontal curves or segments of high-speed rural roadways that have narrow lanes and/or shoulders and a history of lane departure crashes.
Install roadside delineators to help drivers see changes in the roadway geometry.
Install signs to warn drivers of an upcoming change in lane width.
Revisions to Project Limits
Key Questions:
Have project limits been extended beyond the study area?
Are the Location and Surveys (L&S) and Photogrammetry Units aware of the project’s mapping and surveying needs?
How likely is it that project limits will change?
When is the let date?
When is the final survey date?
Mitigation Strategies:
Communicate with planning staff and the Environmental Analysis Unit regarding any revisions to project limits.
Reach out to the L&S and Photogrammetry Units as soon as possible. Mapping during the leaf off-season (mid-December to mid-April) maximizes ground coverage.
Provide project limits information to the Photogrammetry Unit in good time for the Photogrammetry Unit to plan flights.
If limits are likely to be changed, then the Photogrammetry Unit can acquire additional imagery during the leaf off-season to reduce the risk of project delays or increase the cost of final surveys.
Because the let date typically determines when final surveys are due, be aware that it is a key date when determining the date for the Photogrammetry Unit to begin mapping.
Be aware that the date for the final surveys typically determines when shell mapping by the Photogrammetry Unit is due to the L&S Unit.
Inadequate Vegetation/Revegetation Plans
Key Questions:
Has a suitable vegetation/revegetation plan been developed?
Is the schedule favorable to achieve permanent vegetation (considering time of year and weather conditions)?
Mitigation Strategies:
Enlist experts from natural resource disciplines (e.g., botany, plant genetics, horticulture, etc.) to help with revegetation planning.
Incorporate revegetation planning early in the road project development process to benefit project coordination, schedule, and budget.
Define appropriate roles to help the designer coordinate work with appropriate personnel, follow protocols, and avoid duplicating efforts.
Ensure that the designer is the coordinator of the technical and organizational aspects of the revegetation project to enhance project quality and efficiency.
Prior to vegetation design, understand any new road alignments or major road widenings, which often involves extensive study of functional, cultural, environmental, and aesthetic issues.
Slope and Embankment Issues
Key Questions:
Has the quantity of required embankment materials been checked?
Is additional work required to control the erosion of existing channels, greenway trails, slopes, and base ditches?
Mitigation Strategies:
Verify the estimated quantity of embankment materials.
Check for additional erosion control requirements that may be needed for this project.
Inadequate Traffic Control
Key Questions:
Will high-volume traffic result in the suspension of work?
Is additional work required for lane closures and movable concrete barriers?
Is temporary shoring required for the control of traffic through the project site?
Mitigation Strategies:
Reduce project impacts on motorists and improve safety by implementing efficient and effective project phasing, construction sequencing, and control of traffic through the work zone.
Develop a traffic control plan to minimize traffic disruption and eliminate safety hazards typically associated with work zones.
Select pavement treatments, traffic management approaches, and contracting methods that will accelerate the work and minimize traffic disruption.
Select strategies for high-volume traffic conditions that require construction knowledge and experience input to ensure that each strategy is constructible and cost-effective, minimizes traffic delays, and provides a safe environment for workers and the traveling public.
Use a process modeling technique to formalize and structure the maintenance repair and rehabilitation (MRR) strategy selection.
Use Quick Zone, which is a traffic impact analysis spreadsheet-based tool that can be used for work zone delay estimation. Quick Zone is a tool being developed under the Strategic Work-Zone Analysis Tools (SWAT) program at the Federal Highway Administration’s Turner-Fairbanks Highway Research Center.
Install intelligent traffic systems with changeable message signs to provide real-time traffic information for drivers.
Segment full closures (4.8 km to 8 km in length) in one lane direction from one major ramp to another off-ramp during weekends and late weeknight hours.
Use media to inform the public about the project.
Analyze traffic alternatives and perform constructability reviews. These two distinct sub-steps should be iterative and include a collaborative effort among traffic engineers, construction engineers, constructability experts, project engineers, pavement engineers, and, as necessary, public information staff.
Coordinate tools and integrate construction staging and maintenance of traffic via multidisciplinary reviews.
Use appropriate road closure techniques, including directional closures, crossovers, reduced lane width, and temporary widening within existing right-of-way.
Do not set the design basis too early in the project development process to avoid suboptimal solutions for handling traffic.

## 17b. Mitigation (ROW)
Return to Cover Page
Right-of-Way Risk Mitigation Strategies
Land Purchase Delays
Key Questions:
How much will be paid for the land ultimately?
How many properties will need to be condemned? Rule of thumb: 1/3 of properties will experience a claim (settle for a higher price or condemnation).
Mitigation Strategies:
Involve ROW Unit early (pre-STIP is preferred).
Consider ROW costs carefully in the risk mitigation strategy approach.
Use the Utility lead to provide early coordination with utility owner. Consider 2- to 4-year lead time for utilities.
Implement a ‘right size’ resource assignment, as bigger projects require larger, more experienced consulting firms to assist with ROW analysis than smaller projects.
Implement an early acquisition program.
Establish early involvement and relationship building with property owner(s) (i.e., hold an adequate number of public hearings).
Insufficient ROW leading to possible utility relocation delays, redesign to accommodate existing easement, and/or purchase of additional easement
Key Questions:
Is the ROW too close to a structure or construction?
Is the ROW sufficient for temporary work zones, bridges, signage, and detours?
Is the ROW adequate to avoid utility encroachments?
Is the ROW sufficient for temporary work?
Mitigation Strategies:
Show correct existing ROW dimensions on the plans for ROW acquisition.
Confirm existing ROW dimensions throughout the entire project.
Consider changing the design to avoid high-risk locations.
Acquire ROW with future consideration for widening, improvements, and/or reconstruction to add additional lanes.
Complex Relocations
Key Questions:
Are gas stations, parking lots, septic systems, and utilities (e.g., power and telecom) present in the ROW?
Mitigation Strategies:
Conduct project inspections and take notes to identify issues such as “utility pole in the parking lot”.
Ensure adequate easement (consider temporary work zones, including traffic shifts, temporary bridges, signage, and utilities).
Consider making minor design changes to the grade or alignment to accommodate a utility relocation.
Hold utility relocation coordination meetings on an annual basis.
Provide notice and request that the utility company relocate the utility as soon as the need is determined.
Contamination within ROW
Key Questions:
Is there contamination (soil, asbestos, water, etc.) in the ROW that requires remediation?
Mitigation Strategies:
Clearly understand the nature of contaminants that require remediation.
Provide cap protection by interrupting an exposure pathway or controlling contaminant movement.
Allow contractors to inspect buildings for asbestos and/or other contaminants and perform remediation work.
Unforeseen Risks
Key Questions:
Is a gravesite or other unknown condition in the ROW that will need to be addressed?
Mitigation Strategies:
Consider in the estimate possible public concerns and possible litigation due to unforeseen ROW risks.
Ensure coordination between the NCDOT and the utility company regarding the control of ROW.
Have the contractor communicate all changes in the original construction schedule to the local government and all other affected stakeholders.
Develop a plan of action if unforeseen circumstances occur.
Inaccurate ROW estimate
Key Questions:
Is the ROW estimate reasonable for this project?
Have all costs been considered in the ROW estimate?
Mitigation Strategies:
Consider having a third party review the estimate.
Update ROW costs throughout the preconstruction stages, including all possible costs (e.g., costs associated with land acquisition or easement rights, relocation, asbestos abatement and demolition, consultant fees, and condemnation).
Involve the Photogrammetry Unit to help create more accurate ROW estimates through GIS software and parcel data from NC One Map.
Other Considerations
Key Questions:
How many parcels of land shall be purchased?
What is the project delivery approach (design-bid-build, design-build, etc.)?
Mitigation Strategies:
Increase cost estimate contingency for larger projects (> 40 parcels), as estimation accuracy decreases for larger projects. (Note that estimating ROW costs for small and medium-sized projects, i.e., 10 to 40 parcels, is less of an issue.)

## 17c. Mitigation (Structures)
Return to Cover Page
Structures Risk Mitigation Strategies
Bridge Structure Design Errors
Key Questions:
Are lift bents properly designed?
Mitigation Strategies:
Review and check the plans for completeness and accuracy with regard to lift bents.
Deck and Guardrail Omissions and Design Errors
Key Questions:
Have plans been reviewed to verify deck steel and dowels?
Are expansion/contraction joints shown on the plans?
Is additional epoxy-coated rebar required in the design that is not shown in the plans?
Are all guardrails included in the design?
Mitigation Strategies:
Review and check the plans for completeness and accuracy with regard to deck steel and dowels, expansion/contraction joints, epoxy-coated rebar, and guardrails.
Provide a detailed plan view and standard drawings for the various design elements of the bridge that include all important information.
Ensure that the bridge designer works with the Road Design Section to ensure compatibility between the guardrail-to-bridge-to-rail transition and the site.
Foundation Obstructions and/or Unsuitable Soil
Key Questions:
Have pile cut-off elevations been checked?
Does the pile design meet sufficient bearing load criteria?
Have natural and manmade objects been investigated for their possible interference with drilled shafts or piling operations?
Are soil nails sufficient in terms of number and type in the design?
Mitigation Strategies:
Understand the environmental, thermal, and loading conditions that are expected during the life of the proposed bridge.
Require close coordination between the Geotechnical Design Section (GDS) and the design team.
Ask GDS personnel to develop a soil exploration program and prepare a preliminary geotechnical report and bridge geotechnical report.
Perform a detailed subsurface soil investigation based on the bridge bent locations and anticipated foundation type after conducting a design field review.
Ensure that the drawings show the estimated and minimum pile tip elevations of the structural elements.
Examine individual boring logs and plots of the profiles of the various subsurface materials.
Temporary Construction Omissions
Key Questions:
Has sufficient easement been acquired to avoid utility encroachments and to address temporary construction?
Has traffic bearing shoring been considered in the contract?
Mitigation Strategies:
Review and check the plans for completeness and accuracy with regard to traffic bearing shoring and adequate easement for temporary construction.
Untimely or Late Permit Acquisition
Key Questions:
Have all required permits been acquired to ensure continual progress of the project?
Has a permit been considered for the possible impact of a stream during the construction phase?
Mitigation Strategies:
Ensure that all necessary permit applications are filed with the appropriate enforcement agencies and that they are filed in good time.
Surveying Errors
Key Questions:
Have survey data been verified as they pertain to the location of retaining walls?
Mitigation Strategies:
Review and check the plans for completeness and accuracy with regard to survey data and the location of structures.

## 17d. Mitigation (Utilities)
Return to Cover Page
Utilities Risk Mitigation Strategies
Relocation Delays
Key Questions:
What is the best way to reduce utility delays?
Mitigation Strategies:
Establish an appropriate schedule prior to construction. Use a phased contract approach if utilities will not be removed prior to construction.
Gather available information and perform preliminary field investigations.
Plan utility relocations prior to construction to identify their current location with respect to new utilities to avoid obstructions or constraints.
Review relocation plans with utility owners to ensure that the plans meet utility owner requirements.
Relocate utilities in advance (by the utility company or one of its prequalified contractors).
Avoid relocating existing utilities by redesigning or realigning a proposed structure during the design phase.
Conduct utility relocation coordination meetings on a regular basis.
Require that utility information is included with all roadway construction plans.
Encroachment on New Construction
Key Questions:
Are utilities too close to new construction?
Mitigation Strategies:
Ensure adequate easement to accommodate temporary work zones, including traffic shifts, temporary bridges, signage, etc.
Evaluate alternatives for the project and utilities to reduce impacts.
Utilities shown in different plan location
Key Questions:
Are utilities shown correctly in the plans?
Mitigation Strategies:
Review existing utilities records and information.
Perform subsurface utility investigation to map utility locations.
Conduct contract survey to map utilities, if necessary.
Survey and plot above-ground features and connecting points.
Create a 3D utility model.
Unforeseen Utilities
Key Questions:
Is the discovery of unanticipated utilities possible on this project?
Mitigation Strategies:
Identify unique constraints, such as nearby high voltage lines, specialized equipment or permits, power transmission easements, transcontinental gas lines, complex or phased installation of wet utilities, prior grading work, high water table, and/or contaminated soil.
Excavate, if necessary, to expose and survey utilities.
Tie-in delays due to existing utilities
Key Questions:
Are there any tie-ins to existing wet utilities?
Mitigation Strategies:
Identify any possible tie-ins to existing wet utilities in advance and ensure adequate coordination with all appropriate stakeholders (e.g., owners and municipalities).
Special Utility Requirements
Key Questions:
Are there any special requirements when dealing with utilities?
Mitigation Strategies:
Provide a utilities coordinator to be available throughout the project’s lifecycle.
Ensure that correct utility boxes are identified in the plans.
Locate any underground utilities that are inside the tolerance zone.
Damage of new utilities by others
Key Questions:
What is the best way to mitigate damage to new utilities made by others?
Mitigation Strategies:
Identify potential utility conflicts using a utility conflicts matrix (Clash Detections).
Conduct utility impact analysis.
Avoid sensitive environmental areas in the design stage of the project.

## 17e. Mitigation (Rail)
Return to Cover Page
Rail Risk Mitigation Strategies
Railroad Agreement Delay
Key Questions:
How can the time to establish a railroad agreement be reduced?
Mitigation Strategies:
Ensure early involvement and coordination between the NCDOT and railroad company.
Conduct periodic meetings between the NCDOT and railroad company.
Consider partnering with the railroad company to streamline the entire process.
Develop a master agreement.
Identify one NCDOT representative and one railroad company representative as the central points of contact and empower those persons to coordinate highway and railway project issues.
Establish a website with ROW requirements that are specific to each railroad company.
Right-of-Entry Delay
Key Questions:
What are the reasons for any encroachment delays (e.g., RR crossing not finished on time, the need to construct detour tracks to relocate train operations, or removing existing tracks where a new bridge is to be located)?
Mitigation Strategies:
Consider design changes to avoid high-risk locations.
Ensure adequate easement when working near railroad property.
Use third-party consultants to provide a design review of plan submittals.
Update standard bid specifications as they pertain to contractors working in a railway right- of-way.
Determine railroad company’s insurance requirements.
Railroad Bridge Clearance Issues
Key Questions:
Have minimum height requirements been considered for structures and overhead utilities?
Mitigation Strategies:
Check with railroad regarding suitable clearance requirements.
Railroad company’s specific requirements are more stringent than those of the NCDOT, resulting in extra work
Key Questions:
Does the railroad company have more stringent requirements than the NCDOT that may impact the project?
Mitigation Strategies:
Allow additional time for setting girders for any structure over railroad tracks.
Check with railroad company regarding suitable embankment materials (e.g., broken pavement might not meet the railroad company’s requirements).
Unforeseen Site Conditions within railway easement
Key Questions:
Is there contaminated soil or other site conditions (e.g., an underground storage tank) that could delay construction?
Mitigation Strategies:
Collect site information from the railroad company to help identify possible unforeseen site conditions.
Conduct subsurface investigations during the design phase.
Flagger Availability Delay
Key Questions:
Will flagger issues possibly delay construction?
Mitigation Strategies:
Make sure to have right-of-entry permits filed and railway flaggers present during encroachment.
Issue a Scope of Work worksheet to document flagging needs and the reimbursement method.
Identify one point of contact within the railroad company who is responsible for coordination of flagging.

## 17f. Mitigation (Other)
Return to Cover Page
Other Risk Mitigation Strategies
Suspension of work due to funding issues
Key Questions:
Are the cost estimations based on proper assumptions?
How should cash flow and cash reserve problems be addressed?
Mitigation Strategies:
Avoid late invoicing.
Hire a part-time bookkeeper or financial controller to help balance the workload.
Gather detailed financial data to make informed and strategic business decisions.
Include price adjustment clauses in the contract.
Allow contractors to make a change by requiring a 25% to 50% security deposit to avoid insufficient cash reserves.
Consider renegotiating vendor contracts to extend billing cycles or to pay some or all costs after the project is complete.
Issues with phased projects
Key Questions:
Is this project part of a larger phased project?
Mitigation Strategies:
Consider the impacts of completing one portion of the project and not others (e.g., consider potential hydraulic impacts on uncompleted sections).
Conflicts with nearby projects
Key Questions:
What is the best way to settle conflicts with nearby projects?
Mitigation Strategies:
Compromise so that each party’s interests are satisfied to a degree.
Solve the underlying problem, not the symptom.
Accept risks if they cannot be avoided, transferred, insured, eliminated, controlled, or mitigated.
Local tourism activity that may lead to schedule changes
Key Questions:
Has the tourist season been considered in the project schedule?
Mitigation Strategies:
Consider potential impacts of the tourist season when preparing the construction schedule.
Resource Limitations
Key Questions:
Does the NCDOT have the appropriate resources that could impact project performance?
Mitigation Strategies:
Consider hiring temporary staff in areas that may experience a shortage of resources.
Unexpected Risks
Key Questions:
How are unexpected risks identified in a timely fashion?
Mitigation Strategies:
Use Monte Carlo simulations to review all possible outcomes and probabilities of any given action in response to unexpected situations.
Try to identify conditions that are most conducive to detecting risk factors early in the project’s lifecycle.