## Sheet1
Category | Project Type | Generic Cause | Specific Cause | Count | Average Cost | Average Time Granted | Total Cost | Total Time
Claim | Appalachian Regional Commission | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 6509 | 132 | 6509 | 132
Claim | Appalachian Regional Commission | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 1 | 6509 | 132 | 6509 | 132
Claim | Appalachian Regional Commission | Contract Amendment | Settlement and Release Agreement | 2 | 51192.17 | 256.5 | 102384.34 | 513
Claim | Appalachian Regional Commission | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 1 | 51192.17 | 256.5 | 51192.17 | 256.5
Claim | Appalachian Regional Commission | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals | 1 | 0 | 8 | 0 | 8
Claim | Appalachian Regional Commission | Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 1842.32 | 8.5714 | 3684.64 | 17.1429
Claim | Appalachian Regional Commission | Design/Plan Issues | Design/Plan Revision-Unspecified | 6 | 1842.32 | 8.5714 | 11053.92 | 51.4286
Claim | Appalachian Regional Commission | Environmental/Community Concerns | Animal Protection/Endangered Species | 1 | 0 | 167 | 0 | 167
Claim | Appalachian Regional Commission | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 2750 | 0 | 2750 | 0
Claim | Appalachian Regional Commission | Natural Disaster | Natural Disaster-Slide | 2 | 8411 | 156 | 16822 | 312
Claim | Appalachian Regional Commission | Project Closeout Issues | Final Punchlist Extra Work | 1 | 0 | 5 | 0 | 5
Claim | Appalachian Regional Commission | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 1050 | 0 | 1050 | 0
Claim | Appalachian Regional Commission | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 1 | 0 | 1 | 0 | 1
Claim | Bicycle & Pedestrian | Access/ROW/Easement | Insufficient ROW | 1 | 0 | 1 | 0 | 1
Claim | Bicycle & Pedestrian | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 0 | 180 | 0 | 180
Claim | Bicycle & Pedestrian | Contract Amendment | Line Item Omission | 2 | 0 | 1 | 0 | 2
Claim | Bicycle & Pedestrian | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 3 | 0 | 68.5 | 0 | 205.5
Claim | Bicycle & Pedestrian | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals | 1 | 0 | 68.5 | 0 | 68.5
Claim | Bicycle & Pedestrian | Design/Plan Issues | Design/Plan Revision-Unspecified | 6 | 10013.3333 | 78.1429 | 60080 | 468.8571
Claim | Bicycle & Pedestrian | Design/Plan Issues | Increased Traffic Volume | 1 | 10013.3333 | 0 | 10013.3333 | 0
Claim | Bicycle & Pedestrian | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 1 | 25536 | 0 | 25536 | 0
Claim | Bicycle & Pedestrian | Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 185009.5033 | 107.8333 | 370019.0067 | 215.6667
Claim | Bicycle & Pedestrian | Issues with Underground Utilities | Utility Conflict | 6 | 185009.5033 | 107.8333 | 1110057.02 | 647
Claim | Bicycle & Pedestrian | M&R/Replacement | M&R/Replacement-Unspecified | 2 | 32423.12 | 0 | 64846.24 | 0
Claim | Bicycle & Pedestrian | Natural Disaster | Natural Disaster-Hurricane | 1 | 0 | 7 | 0 | 7
Claim | Bicycle & Pedestrian | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 0 | 71 | 0 | 71
Claim | Bicycle & Pedestrian | Project Closeout Issues | Final Punchlist Extra Work | 1 | 0 | 7.5 | 0 | 7.5
Claim | Bicycle & Pedestrian | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 0 | 7.5 | 0 | 7.5
Claim | Bicycle & Pedestrian | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 3 | 0 | 43.3333 | 0 | 130
Claim | Bicycle & Pedestrian | Start Date Delays | Delay in Contract Execution | 2 | 0 | 16 | 0 | 32
Claim | Bridge Replacement | Issues with Underground Utilities | Utilities not Relocated on Time | 24 | 21739.2367 | 43.7925 | 521741.68 | 1051.0189
Claim | Bridge Replacement | Issues with Underground Utilities | Utility Conflict | 35 | 21739.2367 | 43.7925 | 760873.2833 | 1532.7358
Claim | Bridge Replacement | Design/Plan Issues | Compliance with Standard Specifications | 5 | 14093.0672 | 52.9608 | 70465.3361 | 264.8039
Claim | Bridge Replacement | Design/Plan Issues | Design/Plan Error-Unspecified | 14 | 14093.0672 | 52.9608 | 197302.9411 | 741.451
Claim | Bridge Replacement | Design/Plan Issues | Design/Plan Revision-Unspecified | 39 | 14093.0672 | 52.9608 | 549629.6217 | 2065.4706
Claim | Bridge Replacement | Design/Plan Issues | Increased Traffic Volume | 1 | 14093.0672 | 52.9608 | 14093.0672 | 52.9608
Claim | Bridge Replacement | Natural Disaster | Natural Disaster-Hurricane | 39 | 0 | 22.5 | 0 | 877.5
Claim | Bridge Replacement | Natural Disaster | Natural Disaster-Tropical Depression | 1 | 0 | 22.5 | 0 | 22.5
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 6 | 94214.79 | 28.7879 | 565288.74 | 172.7273
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule | 11 | 94214.79 | 28.7879 | 1036362.69 | 316.6667
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 5 | 94214.79 | 28.7879 | 471073.95 | 143.9394
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Timely Completion of Project | 1 | 94214.79 | 28.7879 | 94214.79 | 28.7879
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 2 | 94214.79 | 28.7879 | 188429.58 | 57.5758
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence | 2 | 94214.79 | 28.7879 | 188429.58 | 57.5758
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 1 | 94214.79 | 28.7879 | 94214.79 | 28.7879
Claim | Bridge Replacement | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified | 8 | 94214.79 | 28.7879 | 753718.32 | 230.303
Claim | Bridge Replacement | Project Closeout Issues | Final Punchlist Extra Work | 2 | 2000 | 10.6667 | 4000 | 21.3333
Claim | Bridge Replacement | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 31 | 2000 | 10.6667 | 62000 | 330.6667
Claim | Bridge Replacement | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 2 | 36691.385 | 77.6562 | 73382.77 | 155.3125
Claim | Bridge Replacement | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 29 | 36691.385 | 77.6562 | 1064050.165 | 2252.0312
Claim | Bridge Replacement | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 1 | 36691.385 | 77.6562 | 36691.385 | 77.6562
Claim | Bridge Replacement | Environmental/Community Concerns | Animal Protection/Endangered Species | 1 | 913 | 93.6667 | 913 | 93.6667
Claim | Bridge Replacement | Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 913 | 93.6667 | 913 | 93.6667
Claim | Bridge Replacement | Environmental/Community Concerns | Erosion Control Problems | 1 | 913 | 93.6667 | 913 | 93.6667
Claim | Bridge Replacement | Environmental/Community Concerns | Vegetation Establishment | 28 | 913 | 93.6667 | 25564 | 2622.6667
Claim | Bridge Replacement | Contract Amendment | Contract Time Adjustment | 4 | 555758.3686 | 36.5238 | 2223033.4743 | 146.0952
Claim | Bridge Replacement | Contract Amendment | Contractor Replacement | 1 | 555758.3686 | 36.5238 | 555758.3686 | 36.5238
Claim | Bridge Replacement | Contract Amendment | Elimination of Contract Line Item | 2 | 555758.3686 | 36.5238 | 1111516.7371 | 73.0476
Claim | Bridge Replacement | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 9 | 555758.3686 | 36.5238 | 5001825.3171 | 328.7143
Claim | Bridge Replacement | Contract Amendment | Line Item Omission | 5 | 555758.3686 | 36.5238 | 2778791.8429 | 182.619
Claim | Bridge Replacement | Contract Amendment | Revise Measurement and Payment Method | 1 | 555758.3686 | 36.5238 | 555758.3686 | 36.5238
Claim | Bridge Replacement | Contract Amendment | Settlement and Release Agreement | 3 | 555758.3686 | 36.5238 | 1667275.1057 | 109.5714
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 8 | 10137.471 | 26.7 | 81099.768 | 213.6
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Groundwater | 1 | 10137.471 | 26.7 | 10137.471 | 26.7
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 1 | 10137.471 | 26.7 | 10137.471 | 26.7
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 7 | 10137.471 | 26.7 | 70962.297 | 186.9
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 3 | 10137.471 | 26.7 | 30412.413 | 80.1
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 1 | 10137.471 | 26.7 | 10137.471 | 26.7
Claim | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 10137.471 | 26.7 | 20274.942 | 53.4
Claim | Bridge Replacement | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 11 | 12714.68 | 41.2778 | 139861.48 | 454.0556
Claim | Bridge Replacement | Design Approval Waiting Period/Indecision/Negotiation | Untimely Receipt of Design | 1 | 12714.68 | 41.2778 | 12714.68 | 41.2778
Claim | Bridge Replacement | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals | 5 | 12714.68 | 41.2778 | 63573.4 | 206.3889
Claim | Bridge Replacement | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals | 2 | 12714.68 | 41.2778 | 25429.36 | 82.5556
Claim | Bridge Replacement | Survey/Test Issues | Additional Survey-Test Required | 4 | 14511.0583 | 14.125 | 58044.2333 | 56.5
Claim | Bridge Replacement | Survey/Test Issues | Survey Error | 7 | 14511.0583 | 14.125 | 101577.4083 | 98.875
Claim | Bridge Replacement | Survey/Test Issues | Survey Results Delays | 1 | 14511.0583 | 14.125 | 14511.0583 | 14.125
Claim | Bridge Replacement | M&R/Replacement | M&R/Replacement-Unspecified | 12 | 2963.5275 | 49.1111 | 35562.33 | 589.3333
Claim | Bridge Replacement | Procurement Issues | DOT Furnished Materials/Equipment Delays | 2 | 77894.29 | 33 | 155788.58 | 66
Claim | Bridge Replacement | Procurement Issues | Material Acquisition Delays/Long Lead Items | 4 | 77894.29 | 33 | 311577.16 | 132
Claim | Bridge Replacement | Procurement Issues | Power Supply Delays | 1 | 77894.29 | 33 | 77894.29 | 33
Claim | Bridge Replacement | Procurement Issues | Unavailability of Materials/Material Shortage | 2 | 77894.29 | 33 | 155788.58 | 66
Claim | Bridge Replacement | Procurement Issues | Wrong Order Placement | 2 | 77894.29 | 33 | 155788.58 | 66
Claim | Bridge Replacement | Permit | Permit Acquisition Waiting Period | 8 | 60042.665 | 61.3333 | 480341.32 | 490.6667
Claim | Bridge Replacement | Permit | Permit Limitation | 2 | 60042.665 | 61.3333 | 120085.33 | 122.6667
Claim | Bridge Replacement | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 9 | 11051.7243 | 2.6667 | 99465.5186 | 24
Claim | Bridge Replacement | Start Date Delays | Delay in Contract Execution | 2 | 0 | 55.1429 | 0 | 110.2857
Claim | Bridge Replacement | Start Date Delays | Delay in Preconstruction Meeting | 2 | 0 | 55.1429 | 0 | 110.2857
Claim | Bridge Replacement | Start Date Delays | Delay in Project Award | 1 | 0 | 55.1429 | 0 | 55.1429
Claim | Bridge Replacement | Start Date Delays | Delay in Receipt of Contract Information and Bonds | 1 | 0 | 55.1429 | 0 | 55.1429
Claim | Bridge Replacement | Start Date Delays | Start Date Delays-Unspecified | 1 | 0 | 55.1429 | 0 | 55.1429
Claim | Bridge Replacement | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 0 | 36.6 | 0 | 36.6
Claim | Bridge Replacement | Access/ROW/Easement | Insufficient ROW | 2 | 0 | 36.6 | 0 | 73.2
Claim | Bridge Replacement | Access/ROW/Easement | ROW Acquisition Delays-Unspecified | 2 | 0 | 36.6 | 0 | 73.2
Claim | Bridge Replacement | Other | Covid 19 Impact | 1 | 107204.47 | 3 | 107204.47 | 3
Claim | Bridge Replacement | Other | Unforeseen Issues-Unspecified | 1 | 107204.47 | 3 | 107204.47 | 3
Claim | Ferry | Contract Amendment | Line Item Omission | 2 | 8004.73 | 236 | 16009.46 | 472
Claim | Ferry | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 0 | 87 | 0 | 87
Claim | Ferry | Design/Plan Issues | Design/Plan Error-Unspecified | 1 | 10517.15 | 95 | 10517.15 | 95
Claim | Ferry | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 5571.87 | 1 | 5571.87 | 1
Claim | Ferry | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 26127.93 | 0 | 26127.93 | 0
Claim | Ferry | M&R/Replacement | M&R/Replacement-Unspecified | 1 | 0 | 6 | 0 | 6
Claim | Ferry | Natural Disaster | Natural Disaster-Hurricane | 4 | 0 | 70 | 0 | 280
Claim | Ferry | Procurement Issues | DOT Furnished Materials/Equipment Delays | 1 | 0 | 32 | 0 | 32
Claim | Ferry | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 0 | 18 | 0 | 18
Claim | Ferry | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence | 1 | 0 | 18 | 0 | 18
Claim | Highway Safety | Access/ROW/Easement | Railroad Right of Entry | 1 | 0 | 95.75 | 0 | 95.75
Claim | Highway Safety | Access/ROW/Easement | ROW Acquisition Delays-Unspecified | 3 | 0 | 95.75 | 0 | 287.25
Claim | Highway Safety | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 8 | 0 | 68.375 | 0 | 547
Claim | Highway Safety | Contract Amendment | Elimination of Contract Line Item | 1 | 0 | 27.8 | 0 | 27.8
Claim | Highway Safety | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 3 | 0 | 27.8 | 0 | 83.4
Claim | Highway Safety | Contract Amendment | Settlement and Release Agreement | 1 | 0 | 27.8 | 0 | 27.8
Claim | Highway Safety | Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement | 1 | 0 | 57.6667 | 0 | 57.6667
Claim | Highway Safety | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 0 | 57.6667 | 0 | 57.6667
Claim | Highway Safety | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals | 1 | 0 | 57.6667 | 0 | 57.6667
Claim | Highway Safety | Design/Plan Issues | Compliance with Standard Specifications | 1 | 6787.2 | 109.5238 | 6787.2 | 109.5238
Claim | Highway Safety | Design/Plan Issues | Design/Plan Error-Unspecified | 4 | 6787.2 | 109.5238 | 27148.8 | 438.0952
Claim | Highway Safety | Design/Plan Issues | Design/Plan Revision-Unspecified | 16 | 6787.2 | 109.5238 | 108595.2 | 1752.381
Claim | Highway Safety | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 1 | 3668.49 | 9 | 3668.49 | 9
Claim | Highway Safety | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 1 | 3668.49 | 9 | 3668.49 | 9
Claim | Highway Safety | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 1 | 3668.49 | 9 | 3668.49 | 9
Claim | Highway Safety | Environmental/Community Concerns | Vegetation Establishment | 6 | 0 | 104.2857 | 0 | 625.7143
Claim | Highway Safety | Environmental/Community Concerns | Wetland Discovery | 1 | 0 | 104.2857 | 0 | 104.2857
Claim | Highway Safety | Issues with Underground Utilities | Utilities not Relocated on Time | 8 | 5160.21 | 133.44 | 41281.68 | 1067.52
Claim | Highway Safety | Issues with Underground Utilities | Utility Conflict | 18 | 5160.21 | 133.44 | 92883.78 | 2401.92
Claim | Highway Safety | M&R/Replacement | M&R/Replacement-Damaged Objects | 1 | 96211.03 | 191.4 | 96211.03 | 191.4
Claim | Highway Safety | M&R/Replacement | M&R/Replacement-Unspecified | 5 | 96211.03 | 191.4 | 481055.15 | 957
Claim | Highway Safety | Natural Disaster | Natural Disaster-Hurricane | 18 | 0 | 25.3333 | 0 | 456
Claim | Highway Safety | Procurement Issues | DOT Furnished Materials/Equipment Delays | 1 | 0 | 24 | 0 | 24
Claim | Highway Safety | Procurement Issues | Power Supply Delays | 2 | 0 | 24 | 0 | 48
Claim | Highway Safety | Project Closeout Issues | Final Punchlist Extra Work | 2 | 0 | 22.7143 | 0 | 45.4286
Claim | Highway Safety | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 19 | 0 | 22.7143 | 0 | 431.5714
Claim | Highway Safety | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 11 | 26369.47 | 34.125 | 290064.17 | 375.375
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 1 | 0 | 63.7778 | 0 | 63.7778
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 1 | 0 | 63.7778 | 0 | 63.7778
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Miscommunication (Construction Progress) | 1 | 0 | 63.7778 | 0 | 63.7778
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule | 2 | 0 | 63.7778 | 0 | 127.5556
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 0 | 63.7778 | 0 | 63.7778
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 2 | 0 | 63.7778 | 0 | 127.5556
Claim | Highway Safety | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified | 1 | 0 | 63.7778 | 0 | 63.7778
Claim | Highway Safety | Start Date Delays | Delay in Contract Execution | 2 | 0 | 18.5 | 0 | 37
Claim | Highway Safety | Survey/Test Issues | Survey Error | 1 | 0 | 7 | 0 | 7
Claim | Interstate | Access/ROW/Easement | Railroad Right of Entry | 1 | 4430869 | 67.25 | 4430869 | 67.25
Claim | Interstate | Access/ROW/Easement | ROW Acquisition Delays-Property Owners Agreement | 1 | 4430869 | 67.25 | 4430869 | 67.25
Claim | Interstate | Access/ROW/Easement | ROW Acquisition Delays-Unspecified | 2 | 4430869 | 67.25 | 8861738 | 134.5
Claim | Interstate | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 13 | 16000 | 45.0769 | 208000 | 586
Claim | Interstate | Contract Amendment | Elimination of Contract Line Item | 2 | 145875.0229 | 75 | 291750.0457 | 150
Claim | Interstate | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 2 | 145875.0229 | 75 | 291750.0457 | 150
Claim | Interstate | Contract Amendment | Line Item Omission | 4 | 145875.0229 | 75 | 583500.0914 | 300
Claim | Interstate | Contract Amendment | Settlement and Release Agreement | 3 | 145875.0229 | 75 | 437625.0686 | 225
Claim | Interstate | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 2 | 145875.0229 | 75 | 291750.0457 | 150
Claim | Interstate | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 5 | 0 | 47.7143 | 0 | 238.5714
Claim | Interstate | Design Approval Waiting Period/Indecision/Negotiation | Negotiation Delays | 2 | 0 | 47.7143 | 0 | 95.4286
Claim | Interstate | Design/Plan Issues | Compliance with Standard Specifications | 3 | 43160.0382 | 46.75 | 129480.1145 | 140.25
Claim | Interstate | Design/Plan Issues | Design/Plan Error-Unspecified | 7 | 43160.0382 | 46.75 | 302120.2673 | 327.25
Claim | Interstate | Design/Plan Issues | Design/Plan Revision-Unspecified | 12 | 43160.0382 | 46.75 | 517920.4582 | 561
Claim | Interstate | Design/Plan Issues | Increased Traffic Volume | 1 | 43160.0382 | 46.75 | 43160.0382 | 46.75
Claim | Interstate | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 4 | 0 | 22.25 | 0 | 89
Claim | Interstate | Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 15778.545 | 30 | 15778.545 | 30
Claim | Interstate | Environmental/Community Concerns | Historical Site | 1 | 15778.545 | 30 | 15778.545 | 30
Claim | Interstate | Environmental/Community Concerns | Vegetation Establishment | 1 | 15778.545 | 30 | 15778.545 | 30
Claim | Interstate | Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 173897.54 | 214.6667 | 347795.08 | 429.3333
Claim | Interstate | Issues with Underground Utilities | Utility Conflict | 4 | 173897.54 | 214.6667 | 695590.16 | 858.6667
Claim | Interstate | M&R/Replacement | M&R/Replacement-Unspecified | 16 | 101177.8043 | 56.2857 | 1618844.8686 | 900.5714
Claim | Interstate | M&R/Replacement | Vehicular Accident | 3 | 101177.8043 | 56.2857 | 303533.4129 | 168.8571
Claim | Interstate | Natural Disaster | Natural Disaster-Hurricane | 21 | 44523.09 | 31.9048 | 934984.89 | 670
Claim | Interstate | Permit | Permit Acquisition Waiting Period | 1 | 0 | 40 | 0 | 40
Claim | Interstate | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 5142.2 | 203.3333 | 5142.2 | 203.3333
Claim | Interstate | Procurement Issues | Material Fabrication Delay | 1 | 5142.2 | 203.3333 | 5142.2 | 203.3333
Claim | Interstate | Procurement Issues | Power Supply Delays | 4 | 5142.2 | 203.3333 | 20568.8 | 813.3333
Claim | Interstate | Procurement Issues | Unavailability of Materials/Material Shortage | 1 | 5142.2 | 203.3333 | 5142.2 | 203.3333
Claim | Interstate | Project Closeout Issues | Final Punchlist Extra Work | 1 | 0 | 28.4 | 0 | 28.4
Claim | Interstate | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 14 | 0 | 28.4 | 0 | 397.6
Claim | Interstate | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 18 | 124312.6562 | 44.4545 | 2237627.8125 | 800.1818
Claim | Interstate | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 5 | 547.44 | 61.7083 | 2737.2 | 308.5417
Claim | Interstate | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule | 5 | 547.44 | 61.7083 | 2737.2 | 308.5417
Claim | Interstate | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 547.44 | 61.7083 | 547.44 | 61.7083
Claim | Interstate | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence | 2 | 547.44 | 61.7083 | 1094.88 | 123.4167
Claim | Interstate | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 8 | 547.44 | 61.7083 | 4379.52 | 493.6667
Claim | Interstate | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified | 4 | 547.44 | 61.7083 | 2189.76 | 246.8333
Claim | Interstate | Start Date Delays | Delay in Contract Execution | 2 | 0 | 46.5 | 0 | 93
Claim | Interstate | Survey/Test Issues | Survey Error | 2 | 13851.33 | 9 | 27702.66 | 18
Claim | Other | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 2 | 0 | 153.5 | 0 | 307
Claim | Other | Contract Amendment | Contract Error | 1 | 0 | 198.75 | 0 | 198.75
Claim | Other | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 3 | 0 | 198.75 | 0 | 596.25
Claim | Other | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 3 | 0 | 22.75 | 0 | 68.25
Claim | Other | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals | 1 | 0 | 22.75 | 0 | 22.75
Claim | Other | Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 1916.875 | 8 | 3833.75 | 16
Claim | Other | Design/Plan Issues | Design/Plan Revision-Unspecified | 4 | 1916.875 | 8 | 7667.5 | 32
Claim | Other | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 0 | 12 | 0 | 12
Claim | Other | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 1 | 0 | 12 | 0 | 12
Claim | Other | Environmental/Community Concerns | Vegetation Establishment | 3 | 0 | 36.3333 | 0 | 109
Claim | Other | Issues with Underground Utilities | Utility Conflict | 7 | 0 | 45 | 0 | 315
Claim | Other | M&R/Replacement | M&R/Replacement-Unspecified | 2 | 4576.005 | 0 | 9152.01 | 0
Claim | Other | Natural Disaster | Natural Disaster-Drought | 1 | 0 | 21 | 0 | 21
Claim | Other | Natural Disaster | natural Disaster-Flood | 1 | 0 | 21 | 0 | 21
Claim | Other | Natural Disaster | Natural Disaster-Hurricane | 1 | 0 | 21 | 0 | 21
Claim | Other | Other | Covid 19 Impact | 1 | 0 | 269 | 0 | 269
Claim | Other | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 0 | 48.3333 | 0 | 48.3333
Claim | Other | Procurement Issues | Unavailability of Materials/Material Shortage | 2 | 0 | 48.3333 | 0 | 96.6667
Claim | Other | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 7 | 0 | 13.2857 | 0 | 93
Claim | Other | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 1 | 0 | 76.3333 | 0 | 76.3333
Claim | Other | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 1 | 0 | 76.3333 | 0 | 76.3333
Claim | Other | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 1 | 0 | 76.3333 | 0 | 76.3333
Claim | Other | Start Date Delays | Delay in Contract Execution | 4 | 0 | 17.6667 | 0 | 70.6667
Claim | Other | Start Date Delays | Delay in Preconstruction Meeting | 2 | 0 | 17.6667 | 0 | 35.3333
Claim | Rail | Access/ROW/Easement | Insufficient Right of Entry | 1 | 369355.015 | 117 | 369355.015 | 117
Claim | Rail | Access/ROW/Easement | Railroad Right of Entry | 6 | 369355.015 | 117 | 2216130.09 | 702
Claim | Rail | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 124500 | 132 | 124500 | 132
Claim | Rail | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 4 | 124500 | 132 | 498000 | 528
Claim | Rail | Contract Amendment | Contract Error | 3 | 4542.235 | 72.75 | 13626.705 | 218.25
Claim | Rail | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 1 | 4542.235 | 72.75 | 4542.235 | 72.75
Claim | Rail | Contract Amendment | Line Item Omission | 1 | 4542.235 | 72.75 | 4542.235 | 72.75
Claim | Rail | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 1 | 4542.235 | 72.75 | 4542.235 | 72.75
Claim | Rail | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 1 | 20105.23 | 21 | 20105.23 | 21
Claim | Rail | Design/Plan Issues | Design/Plan Error-Unspecified | 2 | 116321.4 | 49.6 | 232642.8 | 99.2
Claim | Rail | Design/Plan Issues | Design/Plan Revision-Unspecified | 4 | 116321.4 | 49.6 | 465285.6 | 198.4
Claim | Rail | Issues with Underground Utilities | Utilities not Relocated on Time | 4 | 350556.8563 | 100.0909 | 1402227.425 | 400.3636
Claim | Rail | Issues with Underground Utilities | Utility Conflict | 22 | 350556.8563 | 100.0909 | 7712250.8375 | 2202
Claim | Rail | M&R/Replacement | M&R/Replacement-Unspecified | 2 | 143896.62 | 7 | 287793.24 | 14
Claim | Rail | Other | Misinterpretation of Plans | 1 | 144300 | 226.5 | 144300 | 226.5
Claim | Rail | Other | Unavailability of Labor | 2 | 144300 | 226.5 | 288600 | 453
Claim | Rail | Procurement Issues | Power Supply Delays | 1 | 0 | 43 | 0 | 43
Claim | Rail | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 0 | 45 | 0 | 45
Claim | Rail | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 8 | 276266.645 | 15.5 | 2210133.16 | 124
Claim | Rail | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 1 | 33838 | 82 | 33838 | 82
Claim | Rail | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-Unspecified | 1 | 33838 | 82 | 33838 | 82
Claim | Rail | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 2 | 33838 | 82 | 67676 | 164
Claim | Railroad Highway Crossing | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 0 | 25.3333 | 0 | 25.3333
Claim | Railroad Highway Crossing | Issues with Underground Utilities | Utility Conflict | 2 | 0 | 25.3333 | 0 | 50.6667
Claim | Railroad Highway Crossing | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 0 | 12 | 0 | 12
Claim | Railroad Highway Crossing | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 1 | 0 | 32 | 0 | 32
Claim | Railroad Highway Crossing | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 1 | 0 | 32 | 0 | 32
Claim | Railroad Highway Crossing | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified | 1 | 0 | 32 | 0 | 32
Claim | Rest Area | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 0 | 3 | 0 | 3
Claim | Rest Area | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 3 | 220000 | 22 | 660000 | 66
Claim | Rest Area | Contract Amendment | Line Item Omission | 1 | 220000 | 22 | 220000 | 22
Claim | Rest Area | Contract Amendment | Settlement and Release Agreement | 1 | 220000 | 22 | 220000 | 22
Claim | Rest Area | Design/Plan Issues | Design/Plan Error-Unspecified | 1 | 0 | 45.625 | 0 | 45.625
Claim | Rest Area | Design/Plan Issues | Design/Plan Revision-Unspecified | 7 | 0 | 45.625 | 0 | 319.375
Claim | Rest Area | Environmental/Community Concerns | Erosion Control Problems | 1 | 0 | 114 | 0 | 114
Claim | Rest Area | Environmental/Community Concerns | Vegetation Establishment | 1 | 0 | 114 | 0 | 114
Claim | Rest Area | Issues with Underground Utilities | Utility Conflict | 1 | 1881.07 | 1 | 1881.07 | 1
Claim | Rest Area | M&R/Replacement | M&R/Replacement-Unspecified | 1 | 0 | 65 | 0 | 65
Claim | Rest Area | Natural Disaster | Natural Disaster-Hurricane | 4 | 0 | 10.5 | 0 | 42
Claim | Rest Area | Permit | Insufficient Permit | 1 | 0 | 10 | 0 | 10
Claim | Rest Area | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 9928.165 | 65.3333 | 9928.165 | 65.3333
Claim | Rest Area | Procurement Issues | Material Cost Fluctuation | 1 | 9928.165 | 65.3333 | 9928.165 | 65.3333
Claim | Rest Area | Procurement Issues | Unavailability of Materials/Material Shortage | 1 | 9928.165 | 65.3333 | 9928.165 | 65.3333
Claim | Rest Area | Procurement Issues | Wrong Order Placement | 1 | 9928.165 | 65.3333 | 9928.165 | 65.3333
Claim | Rest Area | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 3 | 0 | 16.6667 | 0 | 50
Claim | Rest Area | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-Unspecified | 2 | 0 | 11 | 0 | 22
Claim | Rest Area | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Miscommunication (Construction Progress) | 1 | 0 | 11 | 0 | 11
Claim | Rest Area | Start Date Delays | Delay in Contract Execution | 2 | 0 | 18.5 | 0 | 37
Claim | Rest Area | Start Date Delays | Delay in Project Award | 1 | 0 | 18.5 | 0 | 18.5
Claim | Rest Area | Start Date Delays | Start Date Delays-Unspecified | 1 | 0 | 18.5 | 0 | 18.5
Claim | Rural | Access/ROW/Easement | Right of Entry Acquisition Delays | 1 | 15743.095 | 97.8571 | 15743.095 | 97.8571
Claim | Rural | Access/ROW/Easement | ROW Acquisition Delays-Unspecified | 6 | 15743.095 | 97.8571 | 94458.57 | 587.1429
Claim | Rural | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 21604.9075 | 83.2778 | 21604.9075 | 83.2778
Claim | Rural | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 20 | 21604.9075 | 83.2778 | 432098.15 | 1665.5556
Claim | Rural | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 1 | 21604.9075 | 83.2778 | 21604.9075 | 83.2778
Claim | Rural | Contract Amendment | Contractor Replacement | 1 | 1330002.0672 | 94.9286 | 1330002.0672 | 94.9286
Claim | Rural | Contract Amendment | Elimination of Contract Line Item | 3 | 1330002.0672 | 94.9286 | 3990006.2017 | 284.7857
Claim | Rural | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 16 | 1330002.0672 | 94.9286 | 21280033.0756 | 1518.8571
Claim | Rural | Contract Amendment | Line Item Omission | 3 | 1330002.0672 | 94.9286 | 3990006.2017 | 284.7857
Claim | Rural | Contract Amendment | Settlement and Release Agreement | 16 | 1330002.0672 | 94.9286 | 21280033.0756 | 1518.8571
Claim | Rural | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 4 | 0 | 54 | 0 | 216
Claim | Rural | Design Approval Waiting Period/Indecision/Negotiation | Untimely Receipt of Design | 2 | 0 | 54 | 0 | 108
Claim | Rural | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals | 1 | 0 | 54 | 0 | 54
Claim | Rural | Design/Plan Issues | Compliance with Standard Specifications | 1 | 132272.86 | 47.0435 | 132272.86 | 47.0435
Claim | Rural | Design/Plan Issues | Design/Plan Error-Unspecified | 21 | 132272.86 | 47.0435 | 2777730.06 | 987.913
Claim | Rural | Design/Plan Issues | Design/Plan Revision-Unspecified | 41 | 132272.86 | 47.0435 | 5423187.26 | 1928.7826
Claim | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 2 | 43123.0625 | 90 | 86246.125 | 180
Claim | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 1 | 43123.0625 | 90 | 43123.0625 | 90
Claim | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 5 | 43123.0625 | 90 | 215615.3125 | 450
Claim | Rural | Environmental/Community Concerns | Environmental Concerns/Unspecified | 3 | 2207.0133 | 238.5 | 6621.04 | 715.5
Claim | Rural | Environmental/Community Concerns | Vegetation Establishment | 10 | 2207.0133 | 238.5 | 22070.1333 | 2385
Claim | Rural | Issues with Underground Utilities | Utilities not Relocated on Time | 17 | 368771.8191 | 108.1026 | 6269120.9245 | 1837.7436
Claim | Rural | Issues with Underground Utilities | Utility Conflict | 29 | 368771.8191 | 108.1026 | 10694382.7536 | 3134.9744
Claim | Rural | M&R/Replacement | M&R/Replacement-Damaged Objects | 2 | 10843.1111 | 70.4 | 21686.2222 | 140.8
Claim | Rural | M&R/Replacement | M&R/Replacement-Unspecified | 20 | 10843.1111 | 70.4 | 216862.2222 | 1408
Claim | Rural | Natural Disaster | Natural Disaster-Hurricane | 30 | 48307.886 | 17.1786 | 1449236.58 | 515.3571
Claim | Rural | Other | Covid 19 Impact | 1 | 7047.8967 | 56.5 | 7047.8967 | 56.5
Claim | Rural | Other | Lawsuit Costs | 1 | 7047.8967 | 56.5 | 7047.8967 | 56.5
Claim | Rural | Other | Misinterpretation of Plans | 1 | 7047.8967 | 56.5 | 7047.8967 | 56.5
Claim | Rural | Other | Unforeseen Issues-Unspecified | 2 | 7047.8967 | 56.5 | 14095.7933 | 113
Claim | Rural | Permit | Insufficient Permit | 1 | 12939.66 | 31 | 12939.66 | 31
Claim | Rural | Permit | Permit Acquisition Waiting Period | 1 | 12939.66 | 31 | 12939.66 | 31
Claim | Rural | Permit | Permit Expiration | 1 | 12939.66 | 31 | 12939.66 | 31
Claim | Rural | Permit | Permit Violation | 1 | 12939.66 | 31 | 12939.66 | 31
Claim | Rural | Procurement Issues | DOT Furnished Materials/Equipment Delays | 2 | 9373.65 | 67.6 | 18747.3 | 135.2
Claim | Rural | Procurement Issues | Material Acquisition Delays/Long Lead Items | 2 | 9373.65 | 67.6 | 18747.3 | 135.2
Claim | Rural | Procurement Issues | Material Cost Fluctuation | 1 | 9373.65 | 67.6 | 9373.65 | 67.6
Claim | Rural | Procurement Issues | Power Supply Delays | 6 | 9373.65 | 67.6 | 56241.9 | 405.6
Claim | Rural | Procurement Issues | Unavailability of Materials/Material Shortage | 1 | 9373.65 | 67.6 | 9373.65 | 67.6
Claim | Rural | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 9 | 0 | 15.3333 | 0 | 138
Claim | Rural | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 12 | 91413.6678 | 20.25 | 1096964.0133 | 243
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects | 4 | 12844.182 | 26.96 | 51376.728 | 107.84
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Miscommunication (Construction Progress) | 1 | 12844.182 | 26.96 | 12844.182 | 26.96
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule | 10 | 12844.182 | 26.96 | 128441.82 | 269.6
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 12844.182 | 26.96 | 12844.182 | 26.96
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 4 | 12844.182 | 26.96 | 51376.728 | 107.84
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence | 3 | 12844.182 | 26.96 | 38532.546 | 80.88
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 4 | 12844.182 | 26.96 | 51376.728 | 107.84
Claim | Rural | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified | 2 | 12844.182 | 26.96 | 25688.364 | 53.92
Claim | Rural | Start Date Delays | Delay in Availability of Project | 1 | 0 | 24.4 | 0 | 24.4
Claim | Rural | Start Date Delays | Delay in Contract Execution | 2 | 0 | 24.4 | 0 | 48.8
Claim | Rural | Start Date Delays | Delay in Preconstruction Meeting | 5 | 0 | 24.4 | 0 | 122
Claim | Rural | Start Date Delays | Delay in Project Award | 2 | 0 | 24.4 | 0 | 48.8
Claim | Rural | Survey/Test Issues | Survey Error | 5 | 137254.3467 | 34.5 | 686271.7333 | 172.5
Claim | Rural | Survey/Test Issues | Survey Results Delays | 1 | 137254.3467 | 34.5 | 137254.3467 | 34.5
Claim | Safe Route to School | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 1 | 0 | 118 | 0 | 118
Claim | Safe Route to School | Contract Amendment | Contract Error | 2 | 0 | 6.25 | 0 | 12.5
Claim | Safe Route to School | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 2 | 0 | 6.25 | 0 | 12.5
Claim | Safe Route to School | Environmental/Community Concerns | Vegetation Establishment | 1 | 0 | 84 | 0 | 84
Claim | Safe Route to School | Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 20533.28 | 118.6 | 41066.56 | 237.2
Claim | Safe Route to School | Issues with Underground Utilities | Utility Conflict | 3 | 20533.28 | 118.6 | 61599.84 | 355.8
Claim | Safe Route to School | Natural Disaster | Natural Disaster-Hurricane | 1 | 0 | 14 | 0 | 14
Claim | Safe Route to School | Project Closeout Issues | Final Punchlist Extra Work | 1 | 0 | 14 | 0 | 14
Claim | Safe Route to School | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 1 | 0 | 14 | 0 | 14
Claim | Safe Route to School | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 5655 | 0 | 5655 | 0
Claim | Urban | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 95664.05 | 74.6667 | 95664.05 | 74.6667
Claim | Urban | Access/ROW/Easement | Railroad Right of Entry | 1 | 95664.05 | 74.6667 | 95664.05 | 74.6667
Claim | Urban | Access/ROW/Easement | ROW Acquisition Delays-Property Owners Agreement | 1 | 95664.05 | 74.6667 | 95664.05 | 74.6667
Claim | Urban | Access/ROW/Easement | ROW Acquisition Delays-Unspecified | 3 | 95664.05 | 74.6667 | 286992.15 | 224
Claim | Urban | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather) | 7 | 0 | 92 | 0 | 644
Claim | Urban | Contract Amendment | Elimination of Contract Line Item | 1 | 16760.5 | 36.375 | 16760.5 | 36.375
Claim | Urban | Contract Amendment | Error in Entering Time Extensions in HiCAMS | 10 | 16760.5 | 36.375 | 167605 | 363.75
Claim | Urban | Contract Amendment | Line Item Omission | 5 | 16760.5 | 36.375 | 83802.5 | 181.875
Claim | Urban | Contract Amendment | Revise Measurement and Payment Method | 1 | 16760.5 | 36.375 | 16760.5 | 36.375
Claim | Urban | Contract Amendment | Settlement and Release Agreement | 1 | 16760.5 | 36.375 | 16760.5 | 36.375
Claim | Urban | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 1 | 16760.5 | 36.375 | 16760.5 | 36.375
Claim | Urban | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified | 2 | 0 | 86.5 | 0 | 173
Claim | Urban | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals | 6 | 0 | 86.5 | 0 | 519
Claim | Urban | Design/Plan Issues | Compliance with Standard Specifications | 2 | 72292.4639 | 44.025 | 144584.9278 | 88.05
Claim | Urban | Design/Plan Issues | Design/Plan Error-Unspecified | 17 | 72292.4639 | 44.025 | 1228971.8861 | 748.425
Claim | Urban | Design/Plan Issues | Design/Plan Revision-Unspecified | 37 | 72292.4639 | 44.025 | 2674821.1639 | 1628.925
Claim | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 19933.78 | 42 | 19933.78 | 42
Claim | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 1 | 19933.78 | 42 | 19933.78 | 42
Claim | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Hazardous Materials | 4 | 19933.78 | 42 | 79735.12 | 168
Claim | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 1 | 19933.78 | 42 | 19933.78 | 42
Claim | Urban | Environmental/Community Concerns | Environmental Concerns/Unspecified | 1 | 12551.2667 | 98.4 | 12551.2667 | 98.4
Claim | Urban | Environmental/Community Concerns | Erosion Control Problems | 2 | 12551.2667 | 98.4 | 25102.5333 | 196.8
Claim | Urban | Environmental/Community Concerns | Vegetation Establishment | 3 | 12551.2667 | 98.4 | 37653.8 | 295.2
Claim | Urban | Environmental/Community Concerns | Wetland Discovery | 1 | 12551.2667 | 98.4 | 12551.2667 | 98.4
Claim | Urban | Issues with Underground Utilities | Utilities not Relocated on Time | 10 | 42028.7289 | 118.4762 | 420287.2889 | 1184.7619
Claim | Urban | Issues with Underground Utilities | Utility Conflict | 36 | 42028.7289 | 118.4762 | 1513034.24 | 4265.1429
Claim | Urban | M&R/Replacement | M&R/Replacement-Damaged Objects | 1 | 13509.9425 | 31 | 13509.9425 | 31
Claim | Urban | M&R/Replacement | M&R/Replacement-Unspecified | 7 | 13509.9425 | 31 | 94569.5975 | 217
Claim | Urban | Natural Disaster | Natural Disaster-Drought | 1 | 3948.72 | 41.375 | 3948.72 | 41.375
Claim | Urban | Natural Disaster | Natural Disaster-Hurricane | 14 | 3948.72 | 41.375 | 55282.08 | 579.25
Claim | Urban | Natural Disaster | Natural Disaster-Sinkhole | 1 | 3948.72 | 41.375 | 3948.72 | 41.375
Claim | Urban | Natural Disaster | Natural Disaster-Thunderstorm | 1 | 3948.72 | 41.375 | 3948.72 | 41.375
Claim | Urban | Other | Unforeseen Issues-Unspecified | 1 | 2742.05 | 3 | 2742.05 | 3
Claim | Urban | Permit | Permit Acquisition Waiting Period | 1 | 0 | 36 | 0 | 36
Claim | Urban | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 0 | 109.4 | 0 | 109.4
Claim | Urban | Procurement Issues | Power Supply Delays | 3 | 0 | 109.4 | 0 | 328.2
Claim | Urban | Procurement Issues | Unavailability of Materials/Material Shortage | 1 | 0 | 109.4 | 0 | 109.4
Claim | Urban | Project Closeout Issues | Delay in Project Acceptance | 1 | 0 | 32 | 0 | 32
Claim | Urban | Project Closeout Issues | Delay in Receipt of Final Punchlist | 1 | 0 | 32 | 0 | 32
Claim | Urban | Project Closeout Issues | Final Punchlist Extra Work | 4 | 0 | 32 | 0 | 128
Claim | Urban | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist | 8 | 0 | 32 | 0 | 256
Claim | Urban | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 16 | 102317.22 | 33.8889 | 1637075.52 | 542.2222
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability | 3 | 732970.215 | 21.6667 | 2198910.645 | 65
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Early Project Completion | 1 | 732970.215 | 21.6667 | 732970.215 | 21.6667
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule | 14 | 732970.215 | 21.6667 | 10261583.01 | 303.3333
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection | 1 | 732970.215 | 21.6667 | 732970.215 | 21.6667
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work | 1 | 732970.215 | 21.6667 | 732970.215 | 21.6667
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence | 1 | 732970.215 | 21.6667 | 732970.215 | 21.6667
Claim | Urban | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event | 2 | 732970.215 | 21.6667 | 1465940.43 | 43.3333
Claim | Urban | Survey/Test Issues | Survey Error | 3 | 0 | 3.3333 | 0 | 10
Supplemental Agreement | Appalachian Regional Commission | Access/ROW/Easement | Providing Access to Site | 1 | 7640 | 0 | 7640 | 0
Supplemental Agreement | Appalachian Regional Commission | Access/ROW/Easement | Traffic Access Point | 1 | 7640 | 0 | 7640 | 0
Supplemental Agreement | Appalachian Regional Commission | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 52120 | 0 | 156360 | 0
Supplemental Agreement | Appalachian Regional Commission | Construction Method Revision | Construction Method Revision-Unspecified | 2 | -2952.375 | 0 | -5904.75 | 0
Supplemental Agreement | Appalachian Regional Commission | Contract Amendment | Issues with Previous SA | 1 | 17527.582 | 0 | 17527.582 | 0
Supplemental Agreement | Appalachian Regional Commission | Contract Amendment | Line Item Omission | 8 | 17527.582 | 0 | 140220.656 | 0
Supplemental Agreement | Appalachian Regional Commission | Contract Amendment | Revise Measurement and Payment Method | 1 | 17527.582 | 0 | 17527.582 | 0
Supplemental Agreement | Appalachian Regional Commission | Design/Plan Issues | Compliance with Standard Specifications | 3 | 42045.0085 | 0 | 126135.0254 | 0
Supplemental Agreement | Appalachian Regional Commission | Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 42045.0085 | 0 | 42045.0085 | 0
Supplemental Agreement | Appalachian Regional Commission | Design/Plan Issues | Design Revision-Fix Impacts of Previous Revisions | 1 | 42045.0085 | 0 | 42045.0085 | 0
Supplemental Agreement | Appalachian Regional Commission | Design/Plan Issues | Design Revision-Unspecified | 8 | 42045.0085 | 0 | 336360.0677 | 0
Supplemental Agreement | Appalachian Regional Commission | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 87577.282 | 0 | 87577.282 | 0
Supplemental Agreement | Appalachian Regional Commission | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 87577.282 | 0 | 87577.282 | 0
Supplemental Agreement | Appalachian Regional Commission | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 87577.282 | 0 | 175154.564 | 0
Supplemental Agreement | Appalachian Regional Commission | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 1 | 87577.282 | 0 | 87577.282 | 0
Supplemental Agreement | Appalachian Regional Commission | Drainage Issues | Stormwater Concerns | 3 | 5727.8333 | 0 | 17183.5 | 0
Supplemental Agreement | Appalachian Regional Commission | Environmental/Community Concerns | Vegetation Establishment | 2 | 4362 | 0 | 8724 | 0
Supplemental Agreement | Appalachian Regional Commission | Issues with Underground Utilities | Utility Conflict | 2 | 17198.75 | 0 | 34397.5 | 0
Supplemental Agreement | Appalachian Regional Commission | M&R/Replacement | Damaged Objects | 1 | 39508 | 0 | 39508 | 0
Supplemental Agreement | Appalachian Regional Commission | M&R/Replacement | M&R/Replacement-Unspecified | 1 | 39508 | 0 | 39508 | 0
Supplemental Agreement | Appalachian Regional Commission | Other | Equipment/Items Protection | 1 | 302.6 | 0 | 302.6 | 0
Supplemental Agreement | Appalachian Regional Commission | Procurement Issues | Unavailability of Materials/Material Shortage | 2 | -675 | 0 | -1350 | 0
Supplemental Agreement | Appalachian Regional Commission | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 4 | -97424.2333 | 0 | -389696.9333 | 0
Supplemental Agreement | Appalachian Regional Commission | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 2 | 57283.8 | 0 | 114567.6 | 0
Supplemental Agreement | Appalachian Regional Commission | Stakeholder Request | DOT Request-Unspecified | 1 | 540 | 0 | 540 | 0
Supplemental Agreement | Appalachian Regional Commission | Survey/Test Issues | Survey Error-Unspecified | 1 | 7416.52 | 0 | 7416.52 | 0
Supplemental Agreement | Bicycle & Pedestrian | Access/ROW/Easement | Property Owners Access | 1 | 4472 | 0 | 4472 | 0
Supplemental Agreement | Bicycle & Pedestrian | Construction Method Revision | Construction Method Revision-Unspecified | 2 | 41899.59 | 0 | 83799.18 | 0
Supplemental Agreement | Bicycle & Pedestrian | Contract Amendment | Elimination of Contract Line Item | 1 | 3166.3625 | 0 | 3166.3625 | 0
Supplemental Agreement | Bicycle & Pedestrian | Contract Amendment | Line Item Omission | 3 | 3166.3625 | 0 | 9499.0875 | 0
Supplemental Agreement | Bicycle & Pedestrian | Contract Amendment | Revise Measurement and Payment Method | 1 | 3166.3625 | 0 | 3166.3625 | 0
Supplemental Agreement | Bicycle & Pedestrian | Design/Plan Issues | Compliance with Standard Specifications | 1 | 3682.645 | 0 | 3682.645 | 0
Supplemental Agreement | Bicycle & Pedestrian | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 1 | 3682.645 | 0 | 3682.645 | 0
Supplemental Agreement | Bicycle & Pedestrian | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Encountered Rock | 1 | 5707.7733 | 0 | 5707.7733 | 0
Supplemental Agreement | Bicycle & Pedestrian | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 2 | 5707.7733 | 0 | 11415.5467 | 0
Supplemental Agreement | Bicycle & Pedestrian | Drainage Issues | Drainage Issues-Unspecified | 3 | 3719.58 | 0 | 11158.74 | 0
Supplemental Agreement | Bicycle & Pedestrian | Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 2409.6 | 0 | 7228.8 | 0
Supplemental Agreement | Bicycle & Pedestrian | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 16109.5 | 0 | 16109.5 | 0
Supplemental Agreement | Bicycle & Pedestrian | Issues with Underground Utilities | Utility Conflict | 3 | 16109.5 | 0 | 48328.5 | 0
Supplemental Agreement | Bicycle & Pedestrian | M&R/Replacement | M&R/Replacement-Unspecified | 4 | 4997 | 0 | 19988 | 0
Supplemental Agreement | Bicycle & Pedestrian | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 2 | 2785 | 0 | 5570 | 0
Supplemental Agreement | Bicycle & Pedestrian | Scheduling and Coordination Issues | Early Project Completion | 1 | 162710.89 | 0 | 162710.89 | 0
Supplemental Agreement | Bicycle & Pedestrian | Stakeholder Request | DOT Request-Unspecified | 2 | 6144.5833 | 0 | 12289.1667 | 0
Supplemental Agreement | Bicycle & Pedestrian | Stakeholder Request | Stakeholder Request-Future Development Concerns | 1 | 6144.5833 | 0 | 6144.5833 | 0
Supplemental Agreement | Bicycle & Pedestrian | Stakeholder Request | Stakeholder Request-Unspecified | 3 | 6144.5833 | 0 | 18433.75 | 0
Supplemental Agreement | Bridge Replacement | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 3 | 5455.8457 | 0 | 16367.5371 | 0
Supplemental Agreement | Bridge Replacement | Access/ROW/Easement | Insufficient ROW | 1 | 5455.8457 | 0 | 5455.8457 | 0
Supplemental Agreement | Bridge Replacement | Access/ROW/Easement | Property Owners Access | 2 | 5455.8457 | 0 | 10911.6914 | 0
Supplemental Agreement | Bridge Replacement | Access/ROW/Easement | Providing Access to Site | 1 | 5455.8457 | 0 | 5455.8457 | 0
Supplemental Agreement | Bridge Replacement | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 3 | 8386.76 | 0 | 25160.28 | 0
Supplemental Agreement | Bridge Replacement | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 15 | 8386.76 | 0 | 125801.4 | 0
Supplemental Agreement | Bridge Replacement | Constructability Issues (Except Geotechnical/Underground Conflicts) | Height Clearance Issues | 1 | 8386.76 | 0 | 8386.76 | 0
Supplemental Agreement | Bridge Replacement | Construction Method Revision | Construction Method Revision-Unspecified | 9 | 7465.8138 | 0 | 67192.3237 | 0
Supplemental Agreement | Bridge Replacement | Contract Amendment | Insufficient Insurance | 1 | 6473.1693 | 0 | 6473.1693 | 0
Supplemental Agreement | Bridge Replacement | Contract Amendment | Line Item Omission | 53 | 6473.1693 | 0 | 343077.9707 | 0
Supplemental Agreement | Bridge Replacement | Contract Amendment | Material Substitution Allowance | 2 | 6473.1693 | 0 | 12946.3385 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Compliance with Standard Specifications | 16 | 15665.0293 | 0 | 250640.4687 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Construction Plans Error/Discrepancy | 7 | 15665.0293 | 0 | 109655.2051 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Error-Elevation Difference with Existing Objects | 4 | 15665.0293 | 0 | 62660.1172 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Error-Unspecified | 14 | 15665.0293 | 0 | 219310.4101 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Revision-Fix Impacts of Previous Revisions | 1 | 15665.0293 | 0 | 15665.0293 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Revision-Functionality Issues | 2 | 15665.0293 | 0 | 31330.0586 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 2 | 15665.0293 | 0 | 31330.0586 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Revision-per Contractor Request | 17 | 15665.0293 | 0 | 266305.498 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 15665.0293 | 0 | 15665.0293 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Design Revision-Unspecified | 29 | 15665.0293 | 0 | 454285.8495 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Increased Traffic Volume | 2 | 15665.0293 | 0 | 31330.0586 | 0
Supplemental Agreement | Bridge Replacement | Design/Plan Issues | Scope Change | 1 | 15665.0293 | 0 | 15665.0293 | 0
Supplemental Agreement | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 29960.8306 | 0 | 29960.8306 | 0
Supplemental Agreement | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 3 | 29960.8306 | 0 | 89882.4919 | 0
Supplemental Agreement | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 5 | 29960.8306 | 0 | 149804.1532 | 0
Supplemental Agreement | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 7 | 29960.8306 | 0 | 209725.8145 | 0
Supplemental Agreement | Bridge Replacement | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 4 | 29960.8306 | 0 | 119843.3226 | 0
Supplemental Agreement | Bridge Replacement | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 11 | 29960.8306 | 0 | 329569.1371 | 0
Supplemental Agreement | Bridge Replacement | Drainage Issues | Drainage Issues-Unspecified | 6 | 17626.76 | 0 | 105760.56 | 0
Supplemental Agreement | Bridge Replacement | Environmental/Community Concerns | Environmental Concerns-Unspecified | 3 | 2133963.016 | 0 | 6401889.048 | 0
Supplemental Agreement | Bridge Replacement | Environmental/Community Concerns | Vegetation Establishment | 2 | 2133963.016 | 0 | 4267926.032 | 0
Supplemental Agreement | Bridge Replacement | Erosion Control Problems | Erosion Control Problems-Unspecified | 20 | 3244.832 | 0 | 64896.64 | 0
Supplemental Agreement | Bridge Replacement | Issues with Underground Utilities | Inability to Locate Utilities | 1 | 12091.7682 | 0 | 12091.7682 | 0
Supplemental Agreement | Bridge Replacement | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 12091.7682 | 0 | 12091.7682 | 0
Supplemental Agreement | Bridge Replacement | Issues with Underground Utilities | Utility Conflict | 15 | 12091.7682 | 0 | 181376.5235 | 0
Supplemental Agreement | Bridge Replacement | M&R/Replacement | Damaged Objects | 1 | 48245.0639 | 0 | 48245.0639 | 0
Supplemental Agreement | Bridge Replacement | M&R/Replacement | M&R/Replacement-Unspecified | 17 | 48245.0639 | 0 | 820166.0861 | 0
Supplemental Agreement | Bridge Replacement | Other | Contractor Error | 1 | 8777.55 | 0 | 8777.55 | 0
Supplemental Agreement | Bridge Replacement | Other | Covid 19 Impact | 2 | 8777.55 | 0 | 17555.1 | 0
Supplemental Agreement | Bridge Replacement | Other | Equipment/Items Protection | 1 | 8777.55 | 0 | 8777.55 | 0
Supplemental Agreement | Bridge Replacement | Other | Permit Restrictions | 1 | 8777.55 | 0 | 8777.55 | 0
Supplemental Agreement | Bridge Replacement | Procurement Issues | Error in Bill of Materials | 2 | -4586.395 | 0 | -9172.79 | 0
Supplemental Agreement | Bridge Replacement | Procurement Issues | Unavailability of Materials/Material Shortage | 4 | -4586.395 | 0 | -18345.58 | 0
Supplemental Agreement | Bridge Replacement | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 11 | 32226.8555 | 0 | 354495.41 | 0
Supplemental Agreement | Bridge Replacement | Safety Concerns (Except Contaminated Soil) | Falling Hazard | 2 | 13001.9025 | 0 | 26003.805 | 0
Supplemental Agreement | Bridge Replacement | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 13001.9025 | 0 | 13001.9025 | 0
Supplemental Agreement | Bridge Replacement | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 11 | 13001.9025 | 0 | 143020.9275 | 0
Supplemental Agreement | Bridge Replacement | Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 2 | 13001.9025 | 0 | 26003.805 | 0
Supplemental Agreement | Bridge Replacement | Scheduling and Coordination Issues | Availability Date Delays | 3 | 126590.245 | 0 | 379770.735 | 0
Supplemental Agreement | Bridge Replacement | Stakeholder Request | DOT Request-Unspecified | 8 | 194491.015 | 0 | 1555928.12 | 0
Supplemental Agreement | Bridge Replacement | Stakeholder Request | Stakeholder Request-Future Development Concerns | 1 | 194491.015 | 0 | 194491.015 | 0
Supplemental Agreement | Bridge Replacement | Stakeholder Request | Stakeholder Request-Unspecified | 15 | 194491.015 | 0 | 2917365.225 | 0
Supplemental Agreement | Bridge Replacement | Survey/Test Issues | Additional Survey/Test Required | 2 | 36203.4456 | 0 | 72406.8911 | 0
Supplemental Agreement | Bridge Replacement | Survey/Test Issues | Survey Error-Staking | 2 | 36203.4456 | 0 | 72406.8911 | 0
Supplemental Agreement | Bridge Replacement | Survey/Test Issues | Survey Error-Unspecified | 5 | 36203.4456 | 0 | 181017.2278 | 0
Supplemental Agreement | Ferry | Contract Amendment | Change in Contract Provisions | 1 | 158581.475 | 0 | 158581.475 | 0
Supplemental Agreement | Ferry | Contract Amendment | Settlement and Release Agreement | 1 | 158581.475 | 0 | 158581.475 | 0
Supplemental Agreement | Ferry | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 2 | 158581.475 | 0 | 317162.95 | 0
Supplemental Agreement | Ferry | Design/Plan Issues | Design Error-Unspecified | 1 | 13983.5356 | 0 | 13983.5356 | 0
Supplemental Agreement | Ferry | Design/Plan Issues | Design Revision-Unspecified | 35 | 13983.5356 | 0 | 489423.7469 | 0
Supplemental Agreement | Ferry | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 44434.27 | 0 | 44434.27 | 0
Supplemental Agreement | Ferry | M&R/Replacement | M&R/Replacement-Unspecified | 1 | 17230.79 | 0 | 17230.79 | 0
Supplemental Agreement | Ferry | Other | Permit Requirements | 3 | 20513 | 0 | 61539 | 0
Supplemental Agreement | Ferry | Procurement Issues | Material Acquisition Delays/Long Lead Items | 2 | 80708.795 | 0 | 161417.59 | 0
Supplemental Agreement | Ferry | Stakeholder Request | DOT Request-Unspecified | 3 | 13005.2733 | 0 | 39015.82 | 0
Supplemental Agreement | Highway Safety | Access/ROW/Easement | Property Owners Access | 2 | 12502.6875 | 0 | 25005.375 | 0
Supplemental Agreement | Highway Safety | Access/ROW/Easement | Traffic Access Point | 2 | 12502.6875 | 0 | 25005.375 | 0
Supplemental Agreement | Highway Safety | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 9796.8 | 0 | 29390.4 | 0
Supplemental Agreement | Highway Safety | Construction Method Revision | Construction Method Revision-Unspecified | 1 | 8373 | 0 | 8373 | 0
Supplemental Agreement | Highway Safety | Contract Amendment | Line Item Omission | 17 | 14070.6259 | 0 | 239200.64 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Compliance with Standard Specifications | 3 | 8168.329 | 0 | 24504.987 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 8168.329 | 0 | 8168.329 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Design Error-Elevation Difference with Existing Objects | 2 | 8168.329 | 0 | 16336.658 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Design Error-Unspecified | 3 | 8168.329 | 0 | 24504.987 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Design Revision-Achieve Higher/Acceptable Quality | 1 | 8168.329 | 0 | 8168.329 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 1 | 8168.329 | 0 | 8168.329 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Design Revision-per Contractor Request | 4 | 8168.329 | 0 | 32673.316 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Design Revision-Unspecified | 15 | 8168.329 | 0 | 122524.935 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Increased Traffic Volume | 1 | 8168.329 | 0 | 8168.329 | 0
Supplemental Agreement | Highway Safety | Design/Plan Issues | Scope Change | 2 | 8168.329 | 0 | 16336.658 | 0
Supplemental Agreement | Highway Safety | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 45820.2667 | 0 | 45820.2667 | 0
Supplemental Agreement | Highway Safety | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 8 | 45820.2667 | 0 | 366562.1333 | 0
Supplemental Agreement | Highway Safety | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 45820.2667 | 0 | 91640.5333 | 0
Supplemental Agreement | Highway Safety | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 1 | 45820.2667 | 0 | 45820.2667 | 0
Supplemental Agreement | Highway Safety | Drainage Issues | Drainage Issues-Unspecified | 1 | 18990.19 | 0 | 18990.19 | 0
Supplemental Agreement | Highway Safety | Environmental/Community Concerns | Vegetation Establishment | 1 | 3601.4 | 0 | 3601.4 | 0
Supplemental Agreement | Highway Safety | Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 2821.865 | 0 | 8465.595 | 0
Supplemental Agreement | Highway Safety | Erosion Control Problems | Waste Site Erosion Control | 1 | 2821.865 | 0 | 2821.865 | 0
Supplemental Agreement | Highway Safety | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 17511.2978 | 0 | 17511.2978 | 0
Supplemental Agreement | Highway Safety | Issues with Underground Utilities | Utility Conflict | 10 | 17511.2978 | 0 | 175112.9778 | 0
Supplemental Agreement | Highway Safety | M&R/Replacement | M&R/Replacement-Unspecified | 14 | 16164.43 | 0 | 226302.02 | 0
Supplemental Agreement | Highway Safety | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 0 | 0 | 0 | 0
Supplemental Agreement | Highway Safety | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 3 | 2823.6667 | 0 | 8471 | 0
Supplemental Agreement | Highway Safety | Safety Concerns (Except Contaminated Soil) | Falling Hazard | 1 | 20101.6833 | 0 | 20101.6833 | 0
Supplemental Agreement | Highway Safety | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 5 | 20101.6833 | 0 | 100508.4167 | 0
Supplemental Agreement | Highway Safety | Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 37455 | 0 | 37455 | 0
Supplemental Agreement | Highway Safety | Stakeholder Request | DOT Request-Unspecified | 2 | 60929.9333 | 0 | 121859.8667 | 0
Supplemental Agreement | Highway Safety | Stakeholder Request | Stakeholder Request-Future Development Concerns | 1 | 60929.9333 | 0 | 60929.9333 | 0
Supplemental Agreement | Highway Safety | Stakeholder Request | Stakeholder Request-Unspecified | 3 | 60929.9333 | 0 | 182789.8 | 0
Supplemental Agreement | Interstate | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 1 | 7518.3167 | 0 | 7518.3167 | 0
Supplemental Agreement | Interstate | Access/ROW/Easement | Railroad Right of Entry Delays | 1 | 7518.3167 | 0 | 7518.3167 | 0
Supplemental Agreement | Interstate | Access/ROW/Easement | Traffic Access Point | 1 | 7518.3167 | 0 | 7518.3167 | 0
Supplemental Agreement | Interstate | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 20 | 43401.4511 | 0 | 868029.0222 | 0
Supplemental Agreement | Interstate | Construction Method Revision | Construction Method Revision-Unspecified | 9 | 720476.2 | 0 | 6484285.8 | 0
Supplemental Agreement | Interstate | Contract Amendment | Change in Contract Provisions | 1 | 34387.6804 | 0 | 34387.6804 | 0
Supplemental Agreement | Interstate | Contract Amendment | Elimination of Contract Line Item | 2 | 34387.6804 | 0 | 68775.3607 | 0
Supplemental Agreement | Interstate | Contract Amendment | Issues with Previous SA | 2 | 34387.6804 | 0 | 68775.3607 | 0
Supplemental Agreement | Interstate | Contract Amendment | Line Item Omission | 19 | 34387.6804 | 0 | 653365.9268 | 0
Supplemental Agreement | Interstate | Contract Amendment | Mitigation of Potential Risk | 1 | 34387.6804 | 0 | 34387.6804 | 0
Supplemental Agreement | Interstate | Contract Amendment | Revise Measurement and Payment Method | 1 | 34387.6804 | 0 | 34387.6804 | 0
Supplemental Agreement | Interstate | Contract Amendment | Risk Management | 1 | 34387.6804 | 0 | 34387.6804 | 0
Supplemental Agreement | Interstate | Contract Amendment | Settlement and Release Agreement | 1 | 34387.6804 | 0 | 34387.6804 | 0
Supplemental Agreement | Interstate | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 2 | 34387.6804 | 0 | 68775.3607 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Compliance with Standard Specifications | 8 | 67008.6668 | 0 | 536069.3342 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Error-Elevation Difference with Existing Objects | 3 | 67008.6668 | 0 | 201026.0003 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Error-Unspecified | 3 | 67008.6668 | 0 | 201026.0003 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-Achieve Higher/Acceptable Quality | 3 | 67008.6668 | 0 | 201026.0003 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-Fix Impacts of Previous Revisions | 5 | 67008.6668 | 0 | 335043.3338 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 2 | 67008.6668 | 0 | 134017.3335 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-per Contractor Request | 2 | 67008.6668 | 0 | 134017.3335 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-Uniformity with Adjacent Projects/Objects | 4 | 67008.6668 | 0 | 268034.6671 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-Unspecified | 28 | 67008.6668 | 0 | 1876242.6695 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Design Revision-Value Engineering Proposal | 5 | 67008.6668 | 0 | 335043.3338 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Incomplete Design | 1 | 67008.6668 | 0 | 67008.6668 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Increased Traffic Volume | 2 | 67008.6668 | 0 | 134017.3335 | 0
Supplemental Agreement | Interstate | Design/Plan Issues | Scope Change | 3 | 67008.6668 | 0 | 201026.0003 | 0
Supplemental Agreement | Interstate | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 1 | 41633.19 | 0 | 41633.19 | 0
Supplemental Agreement | Interstate | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 1 | 41633.19 | 0 | 41633.19 | 0
Supplemental Agreement | Interstate | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 41633.19 | 0 | 41633.19 | 0
Supplemental Agreement | Interstate | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 7 | 41633.19 | 0 | 291432.33 | 0
Supplemental Agreement | Interstate | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 3 | 41633.19 | 0 | 124899.57 | 0
Supplemental Agreement | Interstate | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 1 | 41633.19 | 0 | 41633.19 | 0
Supplemental Agreement | Interstate | Drainage Issues | Drainage Issues-Unspecified | 7 | 24310.6586 | 0 | 170174.61 | 0
Supplemental Agreement | Interstate | Environmental/Community Concerns | Construction Impacts | 1 | 363976.375 | 0 | 363976.375 | 0
Supplemental Agreement | Interstate | Environmental/Community Concerns | Natural Disaster (Drought) | 1 | 363976.375 | 0 | 363976.375 | 0
Supplemental Agreement | Interstate | Erosion Control Problems | Erosion Control Problems-Unspecified | 5 | 52984.46 | 0 | 264922.3 | 0
Supplemental Agreement | Interstate | Issues with Underground Utilities | Utility Conflict | 2 | 340905 | 0 | 681810 | 0
Supplemental Agreement | Interstate | M&R/Replacement | Damaged Objects | 1 | 85994.8916 | 0 | 85994.8916 | 0
Supplemental Agreement | Interstate | M&R/Replacement | M&R/Replacement-Unspecified | 28 | 85994.8916 | 0 | 2407856.9638 | 0
Supplemental Agreement | Interstate | M&R/Replacement | Vehicular Accident | 3 | 85994.8916 | 0 | 257984.6747 | 0
Supplemental Agreement | Interstate | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 0 | 0 | 0 | 0
Supplemental Agreement | Interstate | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 7 | 42956.3771 | 0 | 300694.64 | 0
Supplemental Agreement | Interstate | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 69669.3304 | 0 | 69669.3304 | 0
Supplemental Agreement | Interstate | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 20 | 69669.3304 | 0 | 1393386.6083 | 0
Supplemental Agreement | Interstate | Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 4 | 69669.3304 | 0 | 278677.3217 | 0
Supplemental Agreement | Interstate | Scheduling and Coordination Issues | Early Project Completion | 1 | 10 | 0 | 10 | 0
Supplemental Agreement | Interstate | Stakeholder Request | DOT Request-Unspecified | 17 | 611870.6408 | 0 | 10401800.8931 | 0
Supplemental Agreement | Interstate | Stakeholder Request | Stakeholder Request-Future Development Concerns | 3 | 611870.6408 | 0 | 1835611.9223 | 0
Supplemental Agreement | Interstate | Stakeholder Request | Stakeholder Request-Unspecified | 6 | 611870.6408 | 0 | 3671223.8446 | 0
Supplemental Agreement | Interstate | Survey/Test Issues | Survey Error-Unspecified | 1 | 1585.23 | 0 | 1585.23 | 0
Supplemental Agreement | Other | Access/ROW/Easement | Providing Access to Site | 1 | 20000 | 0 | 20000 | 0
Supplemental Agreement | Other | Contract Amendment | Line Item Omission | 7 | 3018.2857 | 0 | 21128 | 0
Supplemental Agreement | Other | Design/Plan Issues | Compliance with Standard Specifications | 1 | 9068.6063 | 0 | 9068.6063 | 0
Supplemental Agreement | Other | Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 9068.6063 | 0 | 9068.6063 | 0
Supplemental Agreement | Other | Design/Plan Issues | Design Revision-Achieve Higher/Acceptable Quality | 2 | 9068.6063 | 0 | 18137.2125 | 0
Supplemental Agreement | Other | Design/Plan Issues | Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 9068.6063 | 0 | 9068.6063 | 0
Supplemental Agreement | Other | Design/Plan Issues | Design Revision-Unspecified | 3 | 9068.6063 | 0 | 27205.8188 | 0
Supplemental Agreement | Other | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 1 | -1863.7743 | 0 | -1863.7743 | 0
Supplemental Agreement | Other | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 3 | -1863.7743 | 0 | -5591.3229 | 0
Supplemental Agreement | Other | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | -1863.7743 | 0 | -3727.5486 | 0
Supplemental Agreement | Other | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 1 | -1863.7743 | 0 | -1863.7743 | 0
Supplemental Agreement | Other | Drainage Issues | Drainage Issues-Unspecified | 1 | 6100 | 0 | 6100 | 0
Supplemental Agreement | Other | Environmental/Community Concerns | Environmental Concerns-Unspecified | 1 | 15584.25 | 0 | 15584.25 | 0
Supplemental Agreement | Other | Erosion Control Problems | Erosion Control Problems-Unspecified | 2 | 3682 | 0 | 7364 | 0
Supplemental Agreement | Other | Issues with Underground Utilities | Utility Conflict | 2 | 2844.5 | 0 | 5689 | 0
Supplemental Agreement | Other | M&R/Replacement | M&R/Replacement-Unspecified | 1 | 16968.2 | 0 | 16968.2 | 0
Supplemental Agreement | Other | Procurement Issues | Unavailability of Materials/Material Shortage | 3 | 6148.375 | 0 | 18445.125 | 0
Supplemental Agreement | Other | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 3 | 4254.3333 | 0 | 12763 | 0
Supplemental Agreement | Other | Stakeholder Request | DOT Request-Unspecified | 1 | 794 | 0 | 794 | 0
Supplemental Agreement | Rail | Access/ROW/Easement | Insufficient ROW | 2 | 9118.39 | 0 | 18236.78 | 0
Supplemental Agreement | Rail | Access/ROW/Easement | Providing Access to Site | 1 | 9118.39 | 0 | 9118.39 | 0
Supplemental Agreement | Rail | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 4 | 14540.3783 | 0 | 58161.5133 | 0
Supplemental Agreement | Rail | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 2 | 14540.3783 | 0 | 29080.7567 | 0
Supplemental Agreement | Rail | Contract Amendment | Contingency Item | 1 | 2321.24 | 0 | 2321.24 | 0
Supplemental Agreement | Rail | Contract Amendment | Line Item Omission | 6 | 2321.24 | 0 | 13927.44 | 0
Supplemental Agreement | Rail | Design/Plan Issues | Compliance with Standard Specifications | 3 | 17695.2185 | 0 | 53085.6554 | 0
Supplemental Agreement | Rail | Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 17695.2185 | 0 | 17695.2185 | 0
Supplemental Agreement | Rail | Design/Plan Issues | Design Error-Unspecified | 3 | 17695.2185 | 0 | 53085.6554 | 0
Supplemental Agreement | Rail | Design/Plan Issues | Design Revision-per Contractor Request | 1 | 17695.2185 | 0 | 17695.2185 | 0
Supplemental Agreement | Rail | Design/Plan Issues | Design Revision-Unspecified | 5 | 17695.2185 | 0 | 88476.0923 | 0
Supplemental Agreement | Rail | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 3 | 14313.6571 | 0 | 42940.9714 | 0
Supplemental Agreement | Rail | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 4 | 14313.6571 | 0 | 57254.6286 | 0
Supplemental Agreement | Rail | Erosion Control Problems | Erosion Control Problems-Unspecified | 3 | 9193.3667 | 0 | 27580.1 | 0
Supplemental Agreement | Rail | Issues with Underground Utilities | Utility Conflict | 3 | 15075.5 | 0 | 45226.5 | 0
Supplemental Agreement | Rail | M&R/Replacement | M&R/Replacement-Unspecified | 2 | 20269 | 0 | 40538 | 0
Supplemental Agreement | Rail | Other | Contractor Error | 1 | 17936.31 | 0 | 17936.31 | 0
Supplemental Agreement | Rail | Other | Site Security | 2 | 17936.31 | 0 | 35872.62 | 0
Supplemental Agreement | Rail | Procurement Issues | Material Acquisition Delays/Long Lead Items | 1 | 10636 | 0 | 10636 | 0
Supplemental Agreement | Rail | Procurement Issues | Unavailability of Materials/Material Shortage | 2 | 10636 | 0 | 21272 | 0
Supplemental Agreement | Rail | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 21600 | 0 | 21600 | 0
Supplemental Agreement | Rail | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 2 | 43208 | 0 | 86416 | 0
Supplemental Agreement | Rail | Scheduling and Coordination Issues | Availability Date Delays | 2 | 69903.3 | 0 | 139806.6 | 0
Supplemental Agreement | Rail | Stakeholder Request | DOT Request-Unspecified | 2 | 14913.888 | 0 | 29827.776 | 0
Supplemental Agreement | Rail | Stakeholder Request | Stakeholder Request-Unspecified | 3 | 14913.888 | 0 | 44741.664 | 0
Supplemental Agreement | Rail | Survey/Test Issues | Additional Survey/Test Required | 2 | 7851.4 | 0 | 15702.8 | 0
Supplemental Agreement | Railroad Highway Crossing | Access/ROW/Easement | Insufficient ROW | 1 | 850 | 0 | 850 | 0
Supplemental Agreement | Railroad Highway Crossing | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 1 | 23587.25 | 0 | 23587.25 | 0
Supplemental Agreement | Railroad Highway Crossing | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 23587.25 | 0 | 70761.75 | 0
Supplemental Agreement | Railroad Highway Crossing | Contract Amendment | Line Item Omission | 4 | 1538.3425 | 0 | 6153.37 | 0
Supplemental Agreement | Railroad Highway Crossing | Design/Plan Issues | Construction Plans Error/Discrepancy | 1 | 4257.472 | 0 | 4257.472 | 0
Supplemental Agreement | Railroad Highway Crossing | Design/Plan Issues | Design Error-Unspecified | 2 | 4257.472 | 0 | 8514.944 | 0
Supplemental Agreement | Railroad Highway Crossing | Design/Plan Issues | Design Revision-Unspecified | 5 | 4257.472 | 0 | 21287.36 | 0
Supplemental Agreement | Railroad Highway Crossing | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 43404 | 0 | 86808 | 0
Supplemental Agreement | Railroad Highway Crossing | Erosion Control Problems | Erosion Control Problems-Unspecified | 1 | 222.2 | 0 | 222.2 | 0
Supplemental Agreement | Railroad Highway Crossing | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 2 | 8653.445 | 0 | 17306.89 | 0
Supplemental Agreement | Rest Area | Access/ROW/Easement | Providing Access to Site | 1 | 423.5 | 0 | 423.5 | 0
Supplemental Agreement | Rest Area | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 3 | 25421.55 | 0 | 76264.65 | 0
Supplemental Agreement | Rest Area | Construction Method Revision | Construction Method Revision-Unspecified | 2 | 28601.82 | 0 | 57203.64 | 0
Supplemental Agreement | Rest Area | Contract Amendment | Elimination of Contract Line Item | 1 | 7415.4143 | 0 | 7415.4143 | 0
Supplemental Agreement | Rest Area | Contract Amendment | Line Item Omission | 5 | 7415.4143 | 0 | 37077.0714 | 0
Supplemental Agreement | Rest Area | Contract Amendment | Unavailability of Funds/Cash Flow Considerations | 1 | 7415.4143 | 0 | 7415.4143 | 0
Supplemental Agreement | Rest Area | Design/Plan Issues | Construction Plans Error/Discrepancy | 3 | 5589.7723 | 0 | 16769.3169 | 0
Supplemental Agreement | Rest Area | Design/Plan Issues | Design Error-Unspecified | 4 | 5589.7723 | 0 | 22359.0892 | 0
Supplemental Agreement | Rest Area | Design/Plan Issues | Design Revision-Unspecified | 19 | 5589.7723 | 0 | 106205.6738 | 0
Supplemental Agreement | Rest Area | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 1 | 9833.11 | 0 | 9833.11 | 0
Supplemental Agreement | Rest Area | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 3 | 9833.11 | 0 | 29499.33 | 0
Supplemental Agreement | Rest Area | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 1 | 9833.11 | 0 | 9833.11 | 0
Supplemental Agreement | Rest Area | Drainage Issues | Drainage Issues-Unspecified | 1 | 5550 | 0 | 5550 | 0
Supplemental Agreement | Rest Area | Drainage Issues | Stormwater Concerns | 1 | 5550 | 0 | 5550 | 0
Supplemental Agreement | Rest Area | Issues with Underground Utilities | Utility Conflict | 1 | 4935 | 0 | 4935 | 0
Supplemental Agreement | Rest Area | M&R/Replacement | M&R/Replacement-Unspecified | 10 | 10956.802 | 0 | 109568.02 | 0
Supplemental Agreement | Rest Area | Procurement Issues | Shop Drawing Error | 1 | 3597.96 | 0 | 3597.96 | 0
Supplemental Agreement | Rest Area | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 1 | 115500 | 0 | 115500 | 0
Supplemental Agreement | Rest Area | Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 2 | 1734.4 | 0 | 3468.8 | 0
Supplemental Agreement | Rest Area | Safety Concerns (Except Contaminated Soil) | Tripping Hazard | 1 | 1734.4 | 0 | 1734.4 | 0
Supplemental Agreement | Rest Area | Stakeholder Request | DOT Request-Unspecified | 2 | 7023.9022 | 0 | 14047.8044 | 0
Supplemental Agreement | Rest Area | Stakeholder Request | Stakeholder Request-Future Development Concerns | 1 | 7023.9022 | 0 | 7023.9022 | 0
Supplemental Agreement | Rest Area | Stakeholder Request | Stakeholder Request-Unspecified | 6 | 7023.9022 | 0 | 42143.4133 | 0
Supplemental Agreement | Rest Area | Survey/Test Issues | Additional Survey/Test Required | 1 | 38331 | 0 | 38331 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Compliance with Standard Specifications | 17 | 108614.5845 | 0 | 1846447.9358 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Construction Plans Error/Discrepancy | 11 | 108614.5845 | 0 | 1194760.429 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Error-Elevation Difference with Existing Objects | 4 | 108614.5845 | 0 | 434458.3378 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Error-Unspecified | 13 | 108614.5845 | 0 | 1411989.598 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Achieve Higher/Acceptable Quality | 5 | 108614.5845 | 0 | 543072.9223 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Change in Design Criteria | 1 | 108614.5845 | 0 | 108614.5845 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Functionality Issues | 1 | 108614.5845 | 0 | 108614.5845 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 6 | 108614.5845 | 0 | 651687.5067 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-per Contractor Request | 8 | 108614.5845 | 0 | 868916.6757 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Toll Collection | 1 | 108614.5845 | 0 | 108614.5845 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 108614.5845 | 0 | 108614.5845 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Unspecified | 90 | 108614.5845 | 0 | 9775312.6012 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Design Revision-Value Engineering Proposal | 5 | 108614.5845 | 0 | 543072.9223 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Increased Traffic Volume | 2 | 108614.5845 | 0 | 217229.1689 | 0
Supplemental Agreement | Rural | Design/Plan Issues | Scope Change | 9 | 108614.5845 | 0 | 977531.2601 | 0
Supplemental Agreement | Rural | Contract Amendment | Change in Contract Provisions | 4 | 137159.8069 | 0 | 548639.2276 | 0
Supplemental Agreement | Rural | Contract Amendment | Elimination of Contract Line Item | 1 | 137159.8069 | 0 | 137159.8069 | 0
Supplemental Agreement | Rural | Contract Amendment | Issues with Previous SA | 2 | 137159.8069 | 0 | 274319.6138 | 0
Supplemental Agreement | Rural | Contract Amendment | Line Item Omission | 84 | 137159.8069 | 0 | 11521423.7787 | 0
Supplemental Agreement | Rural | Contract Amendment | Mitigation of Potential Risk | 1 | 137159.8069 | 0 | 137159.8069 | 0
Supplemental Agreement | Rural | Contract Amendment | Permission to Hold Additional Retainage | 1 | 137159.8069 | 0 | 137159.8069 | 0
Supplemental Agreement | Rural | Contract Amendment | Revise Measurement and Payment Method | 8 | 137159.8069 | 0 | 1097278.4551 | 0
Supplemental Agreement | Rural | Stakeholder Request | DOT Request-Unspecified | 18 | 175183.9472 | 0 | 3153311.0502 | 0
Supplemental Agreement | Rural | Stakeholder Request | Stakeholder Request-Future Development Concerns | 3 | 175183.9472 | 0 | 525551.8417 | 0
Supplemental Agreement | Rural | Stakeholder Request | Stakeholder Request-Unspecified | 27 | 175183.9472 | 0 | 4729966.5753 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects | 1 | 20484.9567 | 0 | 20484.9567 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil | 2 | 20484.9567 | 0 | 40969.9135 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Encountered Rock | 1 | 20484.9567 | 0 | 20484.9567 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 1 | 20484.9567 | 0 | 20484.9567 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 7 | 20484.9567 | 0 | 143394.6972 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 2 | 20484.9567 | 0 | 40969.9135 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 21 | 20484.9567 | 0 | 430184.0916 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 20484.9567 | 0 | 40969.9135 | 0
Supplemental Agreement | Rural | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 6 | 20484.9567 | 0 | 122909.7405 | 0
Supplemental Agreement | Rural | M&R/Replacement | Damaged Objects | 2 | 32528.4936 | 0 | 65056.9871 | 0
Supplemental Agreement | Rural | M&R/Replacement | M&R/Replacement-Unspecified | 40 | 32528.4936 | 0 | 1301139.7429 | 0
Supplemental Agreement | Rural | Safety Concerns (Except Contaminated Soil) | Falling Hazard | 2 | 25495.8243 | 0 | 50991.6486 | 0
Supplemental Agreement | Rural | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 25495.8243 | 0 | 25495.8243 | 0
Supplemental Agreement | Rural | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 28 | 25495.8243 | 0 | 713883.08 | 0
Supplemental Agreement | Rural | Safety Concerns (Except Contaminated Soil) | Sight Distance Concerns | 1 | 25495.8243 | 0 | 25495.8243 | 0
Supplemental Agreement | Rural | Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 3 | 25495.8243 | 0 | 76487.4729 | 0
Supplemental Agreement | Rural | Issues with Underground Utilities | Utilities not Relocated on Time | 2 | 51497.8733 | 0 | 102995.7467 | 0
Supplemental Agreement | Rural | Issues with Underground Utilities | Utility Conflict | 29 | 51497.8733 | 0 | 1493438.3267 | 0
Supplemental Agreement | Rural | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 7 | 68684.0374 | 0 | 480788.2619 | 0
Supplemental Agreement | Rural | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 24 | 68684.0374 | 0 | 1648416.8981 | 0
Supplemental Agreement | Rural | Construction Method Revision | Construction Method Revision-Unspecified | 28 | 16657.0792 | 0 | 466398.2185 | 0
Supplemental Agreement | Rural | Environmental/Community Concerns | Animal Protection/Endangered Species | 3 | 55171.8744 | 0 | 165515.6233 | 0
Supplemental Agreement | Rural | Environmental/Community Concerns | Avoid Historical Structure | 1 | 55171.8744 | 0 | 55171.8744 | 0
Supplemental Agreement | Rural | Environmental/Community Concerns | Construction Impacts | 1 | 55171.8744 | 0 | 55171.8744 | 0
Supplemental Agreement | Rural | Environmental/Community Concerns | Environmental Concerns-Unspecified | 4 | 55171.8744 | 0 | 220687.4978 | 0
Supplemental Agreement | Rural | Environmental/Community Concerns | Vegetation Establishment | 7 | 55171.8744 | 0 | 386203.1211 | 0
Supplemental Agreement | Rural | Environmental/Community Concerns | Wetland Delineation | 2 | 55171.8744 | 0 | 110343.7489 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Easement Acquisition Delays | 1 | 59033.6056 | 0 | 59033.6056 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 3 | 59033.6056 | 0 | 177100.8169 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Insufficient ROW | 2 | 59033.6056 | 0 | 118067.2112 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Insufficient Utility Easement | 2 | 59033.6056 | 0 | 118067.2112 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Property Owners Access | 5 | 59033.6056 | 0 | 295168.0281 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Providing Access to Site | 1 | 59033.6056 | 0 | 59033.6056 | 0
Supplemental Agreement | Rural | Access/ROW/Easement | Traffic Access Point | 2 | 59033.6056 | 0 | 118067.2112 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Additional ICT Required | 1 | 428955.2969 | 0 | 428955.2969 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Conflict with Other Projects | 2 | 428955.2969 | 0 | 857910.5938 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 428955.2969 | 0 | 428955.2969 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Early Project Completion | 7 | 428955.2969 | 0 | 3002687.0785 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Overtime Hour Request | 1 | 428955.2969 | 0 | 428955.2969 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Project Phasing Problems | 1 | 428955.2969 | 0 | 428955.2969 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Statewide Initiative to Accelerate Projects | 1 | 428955.2969 | 0 | 428955.2969 | 0
Supplemental Agreement | Rural | Scheduling and Coordination Issues | Timely Completion of Project | 1 | 428955.2969 | 0 | 428955.2969 | 0
Supplemental Agreement | Rural | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 13 | 256152.7046 | 0 | 3329985.16 | 0
Supplemental Agreement | Rural | Quantities Overrun/Underrun | Waste Excessive Material | 2 | 256152.7046 | 0 | 512305.4092 | 0
Supplemental Agreement | Rural | Drainage Issues | Drainage Issues-Unspecified | 7 | 17283.875 | 0 | 120987.125 | 0
Supplemental Agreement | Rural | Drainage Issues | Stormwater Concerns | 1 | 17283.875 | 0 | 17283.875 | 0
Supplemental Agreement | Rural | Erosion Control Problems | Erosion Control Problems-Unspecified | 7 | 10811.6963 | 0 | 75681.8737 | 0
Supplemental Agreement | Rural | Erosion Control Problems | Waste Site Erosion Control | 1 | 10811.6963 | 0 | 10811.6963 | 0
Supplemental Agreement | Rural | Procurement Issues | Shop Drawing Error | 1 | 9710.5517 | 0 | 9710.5517 | 0
Supplemental Agreement | Rural | Procurement Issues | Unavailability of Materials/Material Shortage | 4 | 9710.5517 | 0 | 38842.2067 | 0
Supplemental Agreement | Rural | Procurement Issues | Wrong Order Placement | 1 | 9710.5517 | 0 | 9710.5517 | 0
Supplemental Agreement | Rural | Survey/Test Issues | Survey Error-Staking | 1 | 3790.42 | 0 | 3790.42 | 0
Supplemental Agreement | Rural | Survey/Test Issues | Survey Error-Unspecified | 2 | 3790.42 | 0 | 7580.84 | 0
Supplemental Agreement | Rural | Other | Permit Acquisition Issues | 1 | 3420.025 | 0 | 3420.025 | 0
Supplemental Agreement | Rural | Other | Permit Requirements | 1 | 3420.025 | 0 | 3420.025 | 0
Supplemental Agreement | Safe Route to School | Contract Amendment | Line Item Omission | 2 | 11831.915 | 0 | 23663.83 | 0
Supplemental Agreement | Safe Route to School | Design/Plan Issues | Design Error-Unspecified | 1 | 3212.05 | 0 | 3212.05 | 0
Supplemental Agreement | Safe Route to School | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 1 | 12415 | 0 | 12415 | 0
Supplemental Agreement | Safe Route to School | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 1 | 12415 | 0 | 12415 | 0
Supplemental Agreement | Safe Route to School | Issues with Underground Utilities | Utility Conflict | 1 | 3672 | 0 | 3672 | 0
Supplemental Agreement | Safe Route to School | M&R/Replacement | M&R/Replacement-Unspecified | 1 | 18025 | 0 | 18025 | 0
Supplemental Agreement | Safe Route to School | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 1 | 7700 | 0 | 7700 | 0
Supplemental Agreement | Safe Route to School | Stakeholder Request | DOT Request-Unspecified | 2 | 6951.85 | 0 | 13903.7 | 0
Supplemental Agreement | Urban | Access/ROW/Easement | Extra Work Associated with ROW Agreement | 4 | 21302.192 | 0 | 85208.768 | 0
Supplemental Agreement | Urban | Access/ROW/Easement | Insufficient ROW | 4 | 21302.192 | 0 | 85208.768 | 0
Supplemental Agreement | Urban | Access/ROW/Easement | Railroad Right of Entry Delays | 1 | 21302.192 | 0 | 21302.192 | 0
Supplemental Agreement | Urban | Access/ROW/Easement | ROW Acquisition Delays | 1 | 21302.192 | 0 | 21302.192 | 0
Supplemental Agreement | Urban | Access/ROW/Easement | ROW Revision | 1 | 21302.192 | 0 | 21302.192 | 0
Supplemental Agreement | Urban | Access/ROW/Easement | Traffic Access Point | 4 | 21302.192 | 0 | 85208.768 | 0
Supplemental Agreement | Urban | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects | 9 | 12255.6952 | 0 | 110301.257 | 0
Supplemental Agreement | Urban | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified | 14 | 12255.6952 | 0 | 171579.733 | 0
Supplemental Agreement | Urban | Construction Method Revision | Construction Method Revision-Unspecified | 22 | 332088.6367 | 0 | 7305950.0067 | 0
Supplemental Agreement | Urban | Contract Amendment | Elimination of Contract Line Item | 2 | 12720.0915 | 0 | 25440.1831 | 0
Supplemental Agreement | Urban | Contract Amendment | Issues with Previous SA | 1 | 12720.0915 | 0 | 12720.0915 | 0
Supplemental Agreement | Urban | Contract Amendment | Line Item Omission | 61 | 12720.0915 | 0 | 775925.5838 | 0
Supplemental Agreement | Urban | Contract Amendment | Revise Measurement and Payment Method | 7 | 12720.0915 | 0 | 89040.6408 | 0
Supplemental Agreement | Urban | Contract Amendment | Settlement and Release Agreement | 3 | 12720.0915 | 0 | 38160.2746 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Compliance with Standard Specifications | 13 | 153708.1566 | 0 | 1998206.0354 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Construction Plans Error/Discrepancy | 14 | 153708.1566 | 0 | 2151914.192 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Error-Elevation Difference with Existing Objects | 6 | 153708.1566 | 0 | 922248.9394 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Error-Unspecified | 5 | 153708.1566 | 0 | 768540.7828 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-Achieve Higher/Acceptable Quality | 5 | 153708.1566 | 0 | 768540.7828 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-Fix Impacts of Previous Revisions | 3 | 153708.1566 | 0 | 461124.4697 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-Functionality Issues | 5 | 153708.1566 | 0 | 768540.7828 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-Future Maintenance Concerns | 4 | 153708.1566 | 0 | 614832.6263 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-per Contractor Request | 4 | 153708.1566 | 0 | 614832.6263 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-Uniformity with Adjacent Projects/Objects | 1 | 153708.1566 | 0 | 153708.1566 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Design Revision-Unspecified | 38 | 153708.1566 | 0 | 5840909.9496 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Incomplete Design | 2 | 153708.1566 | 0 | 307416.3131 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Increased Traffic Volume | 2 | 153708.1566 | 0 | 307416.3131 | 0
Supplemental Agreement | Urban | Design/Plan Issues | Scope Change | 2 | 153708.1566 | 0 | 307416.3131 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Changes in Site After Bid/During Construction | 3 | 49098.909 | 0 | 147296.7271 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Encountered Rock | 1 | 49098.909 | 0 | 49098.909 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Extra Work from Previous Projects | 1 | 49098.909 | 0 | 49098.909 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level | 1 | 49098.909 | 0 | 49098.909 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others | 2 | 49098.909 | 0 | 98197.8181 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Not Shown in Construction Plans | 9 | 49098.909 | 0 | 441890.1814 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified | 17 | 49098.909 | 0 | 834681.4538 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials | 2 | 49098.909 | 0 | 98197.8181 | 0
Supplemental Agreement | Urban | Differing Site Conditions (Except Utilities) | Slope Protection/Soil Stabilization | 6 | 49098.909 | 0 | 294593.4543 | 0
Supplemental Agreement | Urban | Drainage Issues | Drainage Issues-Unspecified | 10 | 7573.286 | 0 | 75732.86 | 0
Supplemental Agreement | Urban | Environmental/Community Concerns | Noise Control | 2 | 1351882.8633 | 0 | 2703765.7267 | 0
Supplemental Agreement | Urban | Environmental/Community Concerns | Vegetation Establishment | 1 | 1351882.8633 | 0 | 1351882.8633 | 0
Supplemental Agreement | Urban | Erosion Control Problems | Erosion Control Problems-Unspecified | 8 | 39731.1213 | 0 | 317848.97 | 0
Supplemental Agreement | Urban | Issues with Underground Utilities | Inability to Locate Utilities | 6 | 15415.3873 | 0 | 92492.3235 | 0
Supplemental Agreement | Urban | Issues with Underground Utilities | Utilities not Relocated on Time | 1 | 15415.3873 | 0 | 15415.3873 | 0
Supplemental Agreement | Urban | Issues with Underground Utilities | Utility Conflict | 45 | 15415.3873 | 0 | 693692.4265 | 0
Supplemental Agreement | Urban | M&R/Replacement | Damaged Objects | 1 | 39544.8293 | 0 | 39544.8293 | 0
Supplemental Agreement | Urban | M&R/Replacement | M&R/Replacement-Unspecified | 28 | 39544.8293 | 0 | 1107255.22 | 0
Supplemental Agreement | Urban | Other | Equipment/Items Protection | 1 | 5254.86 | 0 | 5254.86 | 0
Supplemental Agreement | Urban | Other | Permit Restrictions | 1 | 5254.86 | 0 | 5254.86 | 0
Supplemental Agreement | Urban | Procurement Issues | Material Fabrication Delay | 1 | 21477.97 | 0 | 21477.97 | 0
Supplemental Agreement | Urban | Procurement Issues | Shop Drawing Error | 1 | 21477.97 | 0 | 21477.97 | 0
Supplemental Agreement | Urban | Procurement Issues | Unavailability of Materials/Material Shortage | 3 | 21477.97 | 0 | 64433.91 | 0
Supplemental Agreement | Urban | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified | 5 | 25297.598 | 0 | 126487.99 | 0
Supplemental Agreement | Urban | Safety Concerns (Except Contaminated Soil) | Hazardous Materials Removal | 1 | 19414.0596 | 0 | 19414.0596 | 0
Supplemental Agreement | Urban | Safety Concerns (Except Contaminated Soil) | Safety Concerns-Unspecified | 22 | 19414.0596 | 0 | 427109.3104 | 0
Supplemental Agreement | Urban | Safety Concerns (Except Contaminated Soil) | Travelers/Public Safety | 1 | 19414.0596 | 0 | 19414.0596 | 0
Supplemental Agreement | Urban | Scheduling and Coordination Issues | Conflict/Overlap with Adjacent Projects | 1 | 74950.249 | 0 | 74950.249 | 0
Supplemental Agreement | Urban | Scheduling and Coordination Issues | Early Project Completion | 5 | 74950.249 | 0 | 374751.245 | 0
Supplemental Agreement | Urban | Scheduling and Coordination Issues | Miscommunication (Construction Progress) | 1 | 74950.249 | 0 | 74950.249 | 0
Supplemental Agreement | Urban | Scheduling and Coordination Issues | Project Phasing Problems | 2 | 74950.249 | 0 | 149900.498 | 0
Supplemental Agreement | Urban | Scheduling and Coordination Issues | Statewide Initiative to Accelerate Projects | 1 | 74950.249 | 0 | 74950.249 | 0
Supplemental Agreement | Urban | Scheduling and Coordination Issues | Timely Completion of Project | 1 | 74950.249 | 0 | 74950.249 | 0
Supplemental Agreement | Urban | Stakeholder Request | DOT Request-Unspecified | 13 | 42581.9054 | 0 | 553564.7707 | 0
Supplemental Agreement | Urban | Stakeholder Request | Stakeholder Request-Future Development Concerns | 1 | 42581.9054 | 0 | 42581.9054 | 0
Supplemental Agreement | Urban | Stakeholder Request | Stakeholder Request-Unspecified | 33 | 42581.9054 | 0 | 1405202.8793 | 0
Supplemental Agreement | Urban | Survey/Test Issues | Additional Survey/Test Required | 1 | 21546.7467 | 0 | 21546.7467 | 0
Supplemental Agreement | Urban | Survey/Test Issues | Survey Error-Staking | 2 | 21546.7467 | 0 | 43093.4933 | 0