## Sheet1
Category | Generic Cause | Specific Cause
Claim | Design/Plan Issues | Compliance with Standard Specifications
Claim | Design/Plan Issues | Design/Plan Error-Unspecified
Claim | Design/Plan Issues | Design/Plan Revision-Unspecified
Claim | Design/Plan Issues | Increased Traffic Volume
Claim | Issues with Underground Utilities | Utilities not Relocated on Time
Claim | Issues with Underground Utilities | Utility Conflict
Claim | Natural Disaster | Natural Disaster-Drought
Claim | Natural Disaster | Natural Disaster-Flood
Claim | Natural Disaster | Natural Disaster-Hurricane
Claim | Natural Disaster | Natural Disaster-Sinkhole
Claim | Natural Disaster | Natural Disaster-Slide
Claim | Natural Disaster | Natural Disaster-Thunderstorm
Claim | Natural Disaster | Natural Disaster-Tropical Depression
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Conflict/Overlap with Other Projects
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-DOT Personnel Unavailability
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Coordination Issues-Unspecified
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Early Project Completion
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Miscommunication (Construction Progress)
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Purposeful Limited Work Schedule
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Scheduling Conflicts-Inspection
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Timely Completion of Project
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Waiting for Other Entities to Perform Work
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Out of Sequence
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Social Event
Claim | Scheduling and Coordination Issues (Except Start of Work and/or project closeout) | Work Restriction-Unspecified
Claim | Contract Amendment | Contract Error
Claim | Contract Amendment | Contract Time Adjustment
Claim | Contract Amendment | Contractor Replacement
Claim | Contract Amendment | Elimination of Contract Line Item
Claim | Contract Amendment | Error in Entering Time Extensions in HiCAMS
Claim | Contract Amendment | Line Item Omission
Claim | Contract Amendment | Revise Measurement and Payment Method
Claim | Contract Amendment | Settlement and Release Agreement
Claim | Contract Amendment | Unavailability of Funds/Cash Flow Considerations
Claim | Project Closeout Issues | Delay in Project Acceptance
Claim | Project Closeout Issues | Delay in Receipt of Final Punchlist
Claim | Project Closeout Issues | Final Punchlist Extra Work
Claim | Project Closeout Issues | Scheduling Conflicts-Final Inspection/Punchlist
Claim | Constructability Issues (Except Geotechnical/Underground Conflicts) | Conflict with Existing (Surface) Objects
Claim | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Seasonal Limitations (Weather)
Claim | Constructability Issues (Except Geotechnical/Underground Conflicts) | Constructability Issues-Unspecified
Claim | Quantities Overrun/Underrun | Quantities Overrun/Underrun-Unspecified
Claim | M&R/Replacement | M&R/Replacement-Damaged Objects
Claim | M&R/Replacement | M&R/Replacement-Unspecified
Claim | M&R/Replacement | Vehicular Accident
Claim | Environmental/Community Concerns | Animal Protection/Endangered Species
Claim | Environmental/Community Concerns | Environmental Concerns/Unspecified
Claim | Environmental/Community Concerns | Erosion Control Problems
Claim | Environmental/Community Concerns | Historical Site
Claim | Environmental/Community Concerns | Vegetation Establishment
Claim | Environmental/Community Concerns | Wetland Discovery
Claim | Design Approval Waiting Period/Indecision/Negotiation | Document Misplacement
Claim | Design Approval Waiting Period/Indecision/Negotiation | Indecision-Unspecified
Claim | Design Approval Waiting Period/Indecision/Negotiation | Negotiation Delays
Claim | Design Approval Waiting Period/Indecision/Negotiation | Untimely Receipt of Design
Claim | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review and Return of Submittals
Claim | Design Approval Waiting Period/Indecision/Negotiation | Untimely Review of Approvals
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Buried Objects
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Groundwater
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Contaminated Soil
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Groundwater Discovery/High Groundwater Level
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Hazardous Materials
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Incomplete Work by Others
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unspecified
Claim | Differing Site Conditions (Except Utilities) | Differing Site Conditions-Unsuitable Materials
Claim | Procurement Issues | DOT Furnished Materials/Equipment Delays
Claim | Procurement Issues | Material Acquisition Delays/Long Lead Items
Claim | Procurement Issues | Material Cost Fluctuation
Claim | Procurement Issues | Material Fabrication Delay
Claim | Procurement Issues | Power Supply Delays
Claim | Procurement Issues | Unavailability of Materials/Material Shortage
Claim | Procurement Issues | Wrong Order Placement
Claim | Access/ROW/Easement | Extra Work Associated with ROW Agreement
Claim | Access/ROW/Easement | Insufficient Right of Entry
Claim | Access/ROW/Easement | Insufficient ROW
Claim | Access/ROW/Easement | Railroad Right of Entry
Claim | Access/ROW/Easement | Right of Entry Acquisition Delays
Claim | Access/ROW/Easement | ROW Acquisition Delays-Property Owners Agreement
Claim | Access/ROW/Easement | ROW Acquisition Delays-Unspecified
Claim | Start Date Delays | Delay in Availability of Project
Claim | Start Date Delays | Delay in Contract Execution
Claim | Start Date Delays | Delay in Preconstruction Meeting
Claim | Start Date Delays | Delay in Project Award
Claim | Start Date Delays | Delay in Receipt of Contract Information and Bonds
Claim | Start Date Delays | Start Date Delays-Unspecified
Claim | Survey/Test Issues | Additional Survey-Test Required
Claim | Survey/Test Issues | Survey Error
Claim | Survey/Test Issues | Survey Results Delays
Claim | Permit Issues | Insufficient Permit
Claim | Permit Issues | Permit Acquisition Waiting Period
Claim | Permit Issues | Permit Expiration
Claim | Permit Issues | Permit Limitation
Claim | Permit Issues | Permit Violation
Claim | Other Issues | Covid 19 Impact
Claim | Other Issues | Lawsuit Costs
Claim | Other Issues | Misinterpretation of Plans
Claim | Other Issues | Unavailability of Labor
Claim | Other Issues | Unforeseen Issues-Unspecified