## Sheet1
Design Area | Design Issue | Count | Summary
Pavement | Plan Revision | 88 | Asphalt milling, pavement repairs, asphalt mix design, truck apron replacements, shoulder reconstruction, traffic control, asphalt slippage, pavement failures, bridge shoulder issues, inadequate asphalt depth, and additional paving work.
Pavement | Contract | 66 | Contract did not include key items such as asphalt, patching, and milling. Supplemental agreements were needed to address additional work and establish unit prices for compensation.
Pavement | Drainage | 4 | Drainage issues caused by asphalt-filled curbs, settled asphalt near catch basins, and concerns on bridge shoulders, requiring various repair and maintenance work.
Pavement | Paving | 4 | Weather-related delays in paving, non-compliance with regulations leading to removal and replacement of asphalt, rutting on sandy soils necessitating subgrade stabilization with Class IV aggregate.
Pavement | Quality | 4 | Safety issues from failing pavement, including open-graded friction course, debonded UTBWC, and reflective cracking. Solutions include milling and replacing asphalt, using Fibrecrete B, and installing pavement interlayer for reinforcement.
Pavement | Construction | 1 | Repairing road damage caused by quarry trucks, compensation for patching, using milling machine, 4' width patches, 19.0C intermediate course, and proper compaction equipment to ensure quality repairs.
Pavement | Other Project Delay | 1 | Contractor delay due to unnecessary testing, caused by NCDOT error. Theme: Communication breakdown, bureaucratic inefficiency.
Pavement | Specification | 1 | Improving pavement quality through compensation for using an MTV. Clarifying specifications for final surface paving to ensure uniformity and ride quality.
Pavement | Underlying Layer | 1 | Challenges of underlying layer issues causing placement issues and the necessity of using a 78m Mat Coat to improve asphalt bonding.
Traffic | Plan Revision | 86 | Improving road safety with rumble strips and thermoplastic markings, ADA compliant pedestrian devices, signal communication, and proper pavement markings. Addressing various issues to enhance visibility, safety, and compliance.
Traffic | Contract Issue | 66 | Omission of key items in the original contract, lack of compensation for necessary work, missing line items for essential components, and need for supplemental agreements to address additional work.
Traffic | Sign Fabrication | 5 | Costly delays and errors in sign fabrication by the Department resulted in additional expenses for the contractor. Use of overlays on existing markers proposed to prevent further delays and costs.
Traffic | Railroad | 4 | Missing pavement markings for railroad crossings, lack of line items for symbol replacement, supplemental agreement for unit pricing, labor, materials, and equipment for installation.
Traffic | Sight Distance | 3 | Sight distance design problems identified at ramps, bridge, and driveway access. Contractor instructed to address issues by adjusting vertical curvature and compensating for additional work. Paving and payment adjustments made.
Traffic | Accident | 1 | Replacing damaged signal cabinet with new one and salvaging controllers, emphasizing importance of maintaining traffic signal equipment for safety and efficiency at intersections.
Traffic | Other Project Delay | 1 | Delay in approval of RRFB installations, leading to potential safety concerns and hindering progress in implementing pedestrian safety measures.
Hydraulic | Contract | 41 | Omission of various items in the original contract, requiring supplemental agreements for compensation and additions. Focus on erosion and sediment control, drainage work, and construction materials.
Hydraulic | Drainage | 34 | Inadequate drainage systems, need for additional pipe and drainage structures, compensation for extra work, traffic control measures, and issues with existing drainage structures causing maintenance problems.
Hydraulic | Plan Revision | 34 | Pricing establishment, location adjustments, construction method alterations, drainage structure modifications, erosion prevention, safety concerns addressed, compensation for extra work, equipment replacement, drainage pipe installation, structure relocation, diversion of water flow, environmental impact mitigation.
Hydraulic | Construction | 6 | Issues with drainage structures, safety risks, compensation, erosion control, construction methods, damaged driveways, conflicts, standing water hindering construction.
Hydraulic | Crossline Pipe | 5 | Excavation, settlement, maintenance, compensation, rip rap, resurfacing, leveling, crossline pipes, manhole, drainage, shoulder widening, inlet protection.
Hydraulic | Turbidity | 5 | Compensation, environmental regulations, turbidity control, erosion control, extra work reimbursement, silt suspension, turbidity curtain installation.
Hydraulic | Culvert | 3 | Temporary pipe installation, use of Avanti products for water stopping, excessive debris in excavation, compensation for suitable backfill material, use of existing material for shoulders and slopes.
Hydraulic | Standing Water | 3 | Need for repaving intersections to improve drainage, addressing high accumulation of water at curb ramps, and paving roads to prevent settled water after resurfacing.
Hydraulic | Material Availability | 3 | Supply chain issues with Ductile Iron pipe and Coir Fiber Wattle, as well as planned location changes for Force Main Sewer and use of corrugated aluminized pipe, impacted project timeline.
Hydraulic | Catch Basin | 2 | Damaged catch basin, replacement with Type-E inlet frame grate, hood installation, and delay in adjusting the catch basin.
Hydraulic | Masonry Drainage Structure | 2 | Missing line items in contracts, supplemental agreements, lack of pricing for new construction elements, and the importance of using specific materials for backfilling.
Hydraulic | Deck Drain | 2 | Preventing erosion, maintenance issues, deck drains, protective coating application, adherence to specifications.
Hydraulic | Erosion Control | 2 | Runoff management, erosion control, culvert maintenance, and water conveyance improvement are the main themes identified in the case study, aiming to reduce erosion and enhance infrastructure durability.
Hydraulic | Unforeseen Subsurface Condition | 2 | Infrastructure maintenance, sidewalk retrofitting, steel plate installation, concrete pouring, rebar reinforcement, drainage structure replacement, curb ramp retrofitting, crossline replacement, project clearing, construction challenges.
Hydraulic | Manhole | 2 | Adjustment of manholes and valve boxes due to resurfacing, new line items for law enforcement, increased contract unit price for manhole adjustments, overrun in Contract Line Item.
Hydraulic | Utility Conflict | 1 | Planned drainage structures do not fit due to lack of right of way and power pole conflict.
Hydraulic | Headwall | 1 | Headwall washout due to design flaw. Supplemental agreement for full compensation of repair work, to be performed in accordance with specifications and directed by Engineer.
Hydraulic | Maintenance | 1 | Additional work required for vessel maintenance including antifouling paint, HVAC piping, window replacement, tailshaft and propeller repair, watertight door credit, access plate removal, and valve replacement. Contractor granted 6 additional days.
Hydraulic | Insufficient Cover | 1 | Insufficient cover on 15" RCP driveway pipe required contractor to remove and reinstall pipe at lower elevation and revise ditch grade.
Hydraulic | Concrete Island | 1 | Concrete island causing drainage issues.
Hydraulic | Groundwater | 1 | Excess groundwater in the center of a roundabout due to future plantings by the Town. Installation of a subsurface drain in accordance with NCDOT standards.
Hydraulic | Final Inspection/Punchlist | 1 | Special Stilling Basin was left out of the original inspection. Contractor compensated to perform the work as directed by the Engineer, including labor, materials, equipment, and incidentals
Hydraulic | Debris | 1 | Debris accumulation upstream of bridge
Hydraulic | Wetland | 1 | Ground disturbance in riparian areas and waste area not in compliance with environmental practices requiring addition of coir fiber matting as a contract line item.
Utility | Utility Conflict | 48 | Utility conflicts hindering restoration, accurate utility line location determination, conflicts with foundation locations, revisions to plans to address conflicts, delays caused by errors in utility construction plans.
Utility | Plan Revision | 24 | Utility infrastructure issues, including outdated water meters, incorrect utility plans, and misaligned manholes and valves, necessitated adjustments, relocations, and additional work to ensure proper function and safety.
Utility | Utility not Relocated on Time | 19 | Delays in relocating utilities caused setbacks in project timelines and hindered progress. Lack of timely response and action from utility companies impacted overall project efficiency and completion.
Utility | Water Line | 18 | Compensation for extra work, delays due to waterline issues, material availability problems, need for additional valves, and unexpected challenges in waterline relocation and installation.
Utility | Fire Hydrant | 5 | Compensation for additional work due to faulty valves, unexpected water line bend, and planning issues related to fire hydrant replacement, relocation, and adjusting manhole elevations.
Utility | Manhole | 5 | Manhole adjustments not accounted for in contract plans require additional work and compensation. Safety concerns arise, requiring temporary traffic control and supplemental agreement for proper adjustments and installation.
Utility | Meter or Valve Box | 5 | Lack of line items for adjusting meters or valve boxes, omitted adjustments in contract, need for valve box adjustments due to existing conditions, and meter relocation for new curb.
Utility | Power Supply | 5 | Delays in contractor operations due to waiting for power company to install new electrical service, scheduling final inspection, and power supply delays.
Utility | Contract | 3 | Missing contract details, inadequate provisions for water supply, and proper equipment use for RCP installation.
Utility | Unforeseen Subsurface Condition | 3 | Unexpected obstacles in construction, need for adaptability and problem-solving, importance of thorough investigation, decision-making based on safety and efficiency, collaboration with stakeholders for successful project completion.
Utility | Utility Location | 3 | Importance of exploratory excavation to locate utilities, the challenge of locating waterlines for a proposed project, and the potential cost and time savings by determining if the waterline can remain in operation.
Utility | Material Availability | 2 | Material shortages and delays in procuring precast manhole. Department approval of non-DOT approved precast manhole. Project schedule delays. Need for sewer installation for structure construction. Utility subcontractor unable to supply valve boxes and covers
Utility | Sewer | 2 | Need for a new pigging port with manhole for cleanout purposes, installation of the port, abandonment of existing port, and delay in installation.
Utility | Utility Preference | 1 | Utility not wanting underground power installed.
Geotechnical | Shoulder | 15 | Contractor performed additional shoulder reconstruction work outside original contract scope. Needed to prevent erosion, fix pavement drop-offs, and address shoulder damage. Budget verified, material hauling by department.
Geotechnical | Slope | 10 | Emergency repairs, slope failure, toe protection, saturation, wetland boundaries, rip rap, geotextile, traffic control, erosion, storm water run-off, rock plating, stabilization, concrete flume, additional work, drainage ditches, erosion control.
Geotechnical | Stone | 9 | Contract discrepancies regarding payment for stone materials and placement, leading to supplemental agreements to establish unit prices and increase bid prices for grading work.
Geotechnical | Poor Soil | 8 | Undercut excavation, removal and resetting of guardrail end units, additional mobilization for guardrail work, poor soil conditions requiring Class IV materials, inadequate space necessitating steel casings, and redesign of foundation for mast arm pole. Compensation for additional work is established in Supplemental Agreement.
Geotechnical | Rip Rap | 8 | Compensation for omitted Class II Rip Rap, establishment of unit prices, overrun of original bid quantity, stream relocation, prequalification of contractor, and compliance with NCDOT standards.
Geotechnical | Undercut | 7 | Compensation for shallow undercut and Class IV stabilization work, lack of established line items in contract, need for supplemental agreement, undercut excavation not included, payment in accordance with NCDOT standards.
Geotechnical | Backfill | 6 | Replacement of earth material with Flowable Fill and Class AA Concrete for drainage structures. Shortage of suitable backfill material, additional funds needed for stabilization and compaction. Compensation for using #57 Stone instead of specified material for culvert backfill.
Geotechnical | Erosion Control | 6 | Erosion control, lack of provisions in contract, ground disturbance, need for matting, slope erosion, streambank erosion, permit modification, rip rap for protection.
Geotechnical | Pile | 5 | Cost savings through unit pricing, avoiding delays through proper materials selection, lack of contract clarity leading to potential issues, contractor substitutions for specified materials, and errors in quantity and specifications causing additional testing and downtime.
Geotechnical | Rock | 5 | Unexpected rock encountered during pile excavation led to delays, additional costs, and changes in construction methods. Geotech guidance, exploration, and remobilization of equipment were necessary to address the challenges.
Geotechnical | High Water | 4 | Bridge construction delay due to high water levels, erosion issues addressed with rock berm and undercut excavation, cost-effective solutions like impervious dikes and rock embankments implemented to combat water seepage and siltation.
Geotechnical | Retaining Wall | 4 | Potential damage to retaining wall foundation, use of geotextile and rip rap for protection, delays and revisions due to unnecessary wall, lack of detail in contract plans, additional work required.
Geotechnical | Scour | 4 | Wingwall extension to prevent scour, additional work granted by contractor, significant scouring at end bents, installation of scour protection, excavation of river channel material.
Geotechnical | Subgrade | 4 | Roadway maintenance, subgrade failure, spring opening, subsurface drainage, payment omission, asphalt removal, undercut excavation, ABC stone placement, traffic control, subgrade stabilization.
Geotechnical | Unforeseen Subsurface Condition | 4 | Unforeseen subsurface conditions, abandoned footers, and end bents disrupt construction requiring additional excavation, removal, and disposal of materials, resulting in a supplemental agreement and temporary suspension of work.
Geotechnical | Base Course | 3 | Alteration of construction plans, supplemental agreements for ABC exchange, no pay item for ABC during wheelchair ramp construction, incorrect use of #57 stone on driveways, removal and replacement for safe traversal.
Geotechnical | Dewatering | 3 | Challenges with dewatering during construction, need for effective stilling basin, contractor compensation for special stilling basin installation and removal as directed by engineer.
Geotechnical | Geotextile Fabric | 3 | Issues with geotextile materials on the dam spillway and corrugated aluminum pipe, leading to the need for additional fabric for soil stabilization and a supplemental agreement for compensation.
Geotechnical | Bank Erosion | 2 | Bank stabilization, erosion prevention, mobilization costs, and infrastructure protection are the main themes identified in the scenario of erosion along a jurisdictional stream and under an end bent.
Geotechnical | Bridge Approach | 2 | Neglected bridge approach fills require geotextile layer to prevent erosion and settlement, avoiding costly repairs and ensuring stability for long-term infrastructure sustainability.
Geotechnical | Compaction | 2 | Construction delays, material non-compliance, cost implications, meeting specifications, geotechnical recommendations, deadline pressure, financial penalties, adherence to project requirements, importance of proper material testing and selection.
Geotechnical | Dike | 2 | Omission of the Impervious Dike from the original contract, lack of payment for it, and the need for a Supplemental Agreement to address these issues.
Geotechnical | Groundwater | 2 | Impact of groundwater on infrastructure, the need for proper drainage solutions, and the importance of following specifications to prevent issues like cracking and settlement.
Geotechnical | Hazardous Material | 2 | Contamination, compensation, disposal, removal, landfill, old culvert construction, creosote backwalls, soil hauling.
Geotechnical | Plan Revision | 2 | Inaccurate project plans led to challenges in placing ABC under a barrier wall. Class V stone used instead, with compensation to contractor. Unforeseen earthen berms and pipes affected site elevations.
Geotechnical | Shoring | 2 | Erosion prevention, grave protection, use of precast structures, shoring delays, NCDOT involvement, grouting on roadway.
Geotechnical | Soil Stabilization | 2 | Soil stabilization is necessary for grading operations due to various soil conditions and utilities. Geotextile fabric is used for stabilization, with compensation covering all related costs.
Geotechnical | Borrow | 1 | Significant borrow overrun.
Geotechnical | Drilling | 1 | Struck an 8" HDPE sludge line while drilling foundation for bent-1 shaft-1 required installing a 48" diameter casing inside the 54" diameter permanent casing to prevent concrete from damaging the line.
Geotechnical | Embankment | 1 | Undermining of embankment due to short concrete flume.
Geotechnical | Excavation Limit | 1 | Excavation limits were insufficient for bridge floodplain stabilization, leading to additional excavation, backfill, and rip rap placement.
Geotechnical | Finish Grading | 1 | Contractor removes ballast, brings in suitable material, and performs additional grading.
Geotechnical | Grade Tie-in | 1 | Hump in roadway due to difference in grades between old and new structure. Remove hump to create better tie-in between existing and new grades.
Geotechnical | Gravesite Protection | 1 | Need for shoring to prevent erosion and exposure of a grave during excavation.
Geotechnical | Grout Design | 1 | Delay in providing viable grout mix design and pumping procedure.
Geotechnical | Insufficient Cover | 1 | Soil depth on culvert not sufficient for guardrail post. Use Structure Anchor Units with Posts in accordance with NCDOT Standard Specifications for Roads and Structures.
Geotechnical | Maintenance | 1 | Continuous maintenance required on HW due to slide damage from severe weather.
Geotechnical | Rock Plating | 1 | Adjustments made to rock plating design to better suit actual conditions and achieve Regulator Agency concurrence.
Geotechnical | Saturated Subgrade | 1 | Saturated subgrade due to water from adjacent hillside.
Geotechnical | Sheet Pile | 1 | Sheet pile toe wall not included in original plans for box culvert construction. Supplemental agreement for compensation for installation of sheet pile toe wall, flowable fill, and additional mobilization.
Geotechnical | Sink Hole | 1 | Sink hole void in ditch line prior to cross line pipe. Use flowable fill to prevent water seepage and control drainage. Prime contractor purchases material, supplemental agreement provides payment method.
Geotechnical | Specification | 1 | Contract required 60 lbs. of cement per square yard for Soil Cement Base (Full Depth Reclamation) but investigation report recommended 75 lbs. Supplemental agreement to establish new price and procedure with 75 lbs. of cement per square yard
Geotechnical | Steel Casing | 1 | Overrun in Line Item 107 Permanent Steel Casing.
Geotechnical | Vibration | 1 | Preventing damage to residential structure from vibrations through pre-construction surveys, monitoring, and post-construction reports by contractor in accordance with contract and special provision.
Roadway | Plan Revision | 75 | Contract discrepancies identified include issues with maps, concrete sidewalks, guardrails, and road elevations. Modifications, additional funding, and compensation are required to address the discrepancies and ensure compliance with NCDOT standards.
Roadway | Contract | 25 | Contract scope expanded to include additional work such as guardrail placement, driveway reconstruction, and curb ramp installation. Various items not originally included required supplemental agreements for compensation and adjustments.
Roadway | Surveying | 7 | Missing payment for construction surveying, higher tie-in elevations requiring redesign, contractor compensation for extra surveying, omitted surveying in the contract, and staking errors causing grading issues.
Roadway | Construction | 6 | Road deterioration due to loaded trucks, severe surface damage from quarry haul trucks, compensation for patching and asphalt removal, tracking of tack onto new structures, and supplemental agreements for conflict resolution.
Roadway | Adjust Utility to Match Grade | 3 | Ensuring proper access to utility valves, adjusting manholes, and providing full compensation for necessary work are the main themes identified in the document.
Roadway | Railroad | 3 | Payment disputes, inadequate pavement markings, missing guardrail on east side of tracks. Importance of adhering to contract specifications in railroad infrastructure projects.
Roadway | Project Scope Change | 2 | Improving safety and reducing crash ratings through widening and pavement markings on Map. Establishing unit prices, following project provisions and specifications. Additional compensation required for grading and paving extension.
Roadway | Concrete Island | 1 | Traffic and drainage issues due to concrete islands not flush with road surface, need for installation of new monolithic concrete islands and patching/paving final asphalt surface.
Roadway | Deck Grade | 1 | Work suspension, deck grade errors, plan revisions, back wall modifications, approach slabs, roadway profile changes.
Roadway | Material Availability | 1 | Lack of B25.0C availability for asphalt concrete intermediate course. Contractor elected to use I19.0C, which was approved by the Engineer. Supplemental agreement established materials and payment for satisfactory completion.
Roadway | Quality | 1 | Delays caused by poor quality materials used to double seal roads. Operations halted to replace materials and repairs were necessary, causing further delays.
Roadway | Settlement | 1 | Settlement in roadway causing dips that cannot be compensated for by automatics on paver during planned mill and fill.
Traffic Control & Staging | Contract | 68 | Contractor did not include necessary items such as flaggers, law enforcement, and message boards in the original contract, leading to supplemental agreements for compensation and safety measures during construction.
Traffic Control & Staging | Plan Revision | 32 | Need for additional temporary traffic control, traffic signal, lane closures, safety measures, and markings. Extension of contract time, compensation for extra work, and adjustments to traffic control plans.
Traffic Control & Staging | Railroad | 14 | Railroad flagging delays and lack of compensation for flaggers in paving contracts are the main themes identified in the Map project, leading to a claim for compensation from the Department.
Traffic Control & Staging | Other Project Delay | 4 | Holiday restrictions impacting contractor delays, structural deficiencies causing detour hardship, and seasonal limitations delaying pavement markings placement. Access issues and project setbacks highlighted in the case study.
Traffic Control & Staging | Road Closure | 2 | Ramp closures, detours, weekend road closures, and traffic shifts for milling, paving, and tie-in work on bridge approaches and adjacent roadways due to project constraints and traffic maintenance challenges.
Traffic Control & Staging | Work Zone Sign Removal | 2 | Delay in removing advanced work zone signs Overlooked work zone signs, but the contractor returned to remove them and no damages were charge
Traffic Control & Staging | Steel Plate Cover | 1 | Unscheduled need for a temporary steel plate cover on a roadway, the requirement for Grade A36 steel, and payment measured in units.
Traffic Control & Staging | Traffic Volume | 1 | Higher than anticipated traffic volume experienced by contractor.
Environmental | Vegetation | 46 | Delays in vegetation establishment, inadequate soil cover, unfavorable weather conditions, and contractor failures led to extended completion dates, adjustments for permanent seeding and mulching, and supplemental agreements for vegetation work.
Environmental | Landscaping | 9 | Forest fire emergency shutdown, compensation for seeding and mulching, tree removal and replacement, non-native plant material, temporary mulching, safety risks, equipment use, notification issues, and tree planting damage.
Environmental | Hazardous Material | 6 | Missing removal and disposal line item for asbestos in contract, contractor seeks compensation for removal, supplemental agreement not approved, asbestos discovered during assessment, lack of compensation for abatement.
Environmental | Endangered Species | 3 | Environmental conservation, protection of wildlife habitats, and adherence to regulations for endangered species during construction projects. Balancing progress with respect for natural ecosystems and wildlife populations.
Environmental | Natural Disaster | 3 | Natural disasters impacting road infrastructure, road closures due to wildfires and tropical storms, damage from severe weather events, and the need for stream mitigation repair after heavy rain.
Environmental | Wetland | 3 | Environmental protection and mitigation during construction, including use of geotextile fabric, turbidity curtains, construction surveying, erosion control, stream protection, and temporary water diversion.
Environmental | Accident | 1 | Damaged asphalt due to fuel leak from truck wreck.
Structural | Plan Revision | 32 | Delays and extra costs due to plan errors, material discrepancies, structural issues, and design changes require supplemental agreements for compensation, additional work, and time extensions on the bridge project.
Structural | Contract | 8 | Omissions and errors in contract items, including concrete deck repair, diamond grinding, falsework compensation, steel casing, bridges, reinforcing steel, and temporary shoring, requiring additional compensation and adjustments.
Structural | Final Inspection/Punchlist | 1 | More bridge rehab work needed, found during punchlist. Added to final punchlist. Not previously discovered or shown on plans. Added to project due to proximity.
Structural | Quality | 1 | Manufacturing issues led to beam rejections by M&T, necessitating recasting. Contractor was not blamed, emphasizing the need to address manufacturing problems to prevent future rejections.
Structural | Scour | 1 | Beaver dam caused scour on bridge, delaying erosion control project closeout. Bridge maintenance unit to complete repairs, allowing for extra time to complete project.
Other | Inflation Adjustment | 233 | Time-limited material cost escalation adjustments and contractor reimbursement for fuel price and AC adjustments.
Other | Final Inspection/Punchlist | 60 | Scheduling conflicts, final inspection delays, punchlist items, supplemental agreements, added scope of work, and contractor repairs were the main themes identified in the project.
Other | Material Delay | 60 | Delays in manufacturing and delivery of materials such as metal poles, box beams, and culverts, as well as shortages of labor and equipment causing project setbacks. Alternative suppliers and adjustments to designs are necessary to address these issues.
Other | Other Project Delay | 23 | Delays in project completion due to conflict investigations, contractor issues, design diagnostic delays, demobilization for special events, utility relocations, material shortages, scheduling issues, and project extensions.
Other | Project Scope Change | 19 | Extension of project scope led to additional work, costs, and time. Use of contract unit prices and adherence to specifications for changes. Compensated for added maps, mobilization, and materials
Other | Contract | 16 | Fluctuating asphalt binder prices, missed maps, omitted line items, additional roads, compensation for missed work, specialized tasks, water valves, traffic control, pipe removal, mulching, sodding, structure removal, mast arm signal pole, inaccurate quantity breakdown.
Other | Material Availability | 16 | Shortages of materials and labor led to delays in completing various construction projects. Solutions included sourcing materials from different suppliers and adjusting project timelines.
Other | COVID Delay | 14 | COVID Impact Delay in material delivery (e.g., beams) due to pandemic-related shutdowns and staffing shortages.
Other | Scheduling Delay | 12 | Insufficient time, delays in subcontractor and NCDOT requests, scheduling conflicts, weather restrictions, limited work schedule, delayed completion due to rain and holidays.
Other | Contract Execution Delay | 10 | Negotiation delays, contract execution delays, scheduling issues, and availability date postponements were the main themes identified in the process of supplemental agreements for precast culvert construction.
Other | Accident | 5 | Vehicle incidents caused damage to newly resurfaced locations on NC HWY, including severe damage to OGFC mat. Delays in repairs due to special material and contractor fatality. Compensation provided for damaged structures and signs.
Other | Maintenance | 5 | Delayed maintenance of grass/vegetation impacted pavement markings, crosslines, and project completion date. Potential for poor plant survivability and establishment due to lack of monthly maintenance in contract.
Other | Construction | 4 | Damage to inductive loops during milling operations, the need for deeper cut loops and asphalt cover for protection, limited access due to a proposed fence, and construction delays affecting timely patching.
Other | HICAMS | 4 | Lack of a floating start date option in HiCAMS for ICT 4, 03, and 5 contracts, with a recommendation to add this feature to the system.
Other | Property Owner | 4 | Traffic safety concerns, signage effectiveness, private property issues, public notification needs, and road infrastructure improvements.
Other | ICT Delay | 3 | Delays in ICT projects due to incomplete previous projects, shortage of materials, and the importance of timely completion to avoid further delays.
Other | Striping Delay | 3 | Delays in striping due to fog seal completion, extension of overall contract time, and additional road sweeping before striping to ensure quality work.
Other | Takeover Agreement | 3 | Takeover Agreement considerations include establishing new contract completion dates, transferring responsibilities, and ensuring compliance with bonding company requirements.
Other | Waiting for Other Entities to Perform Work | 3 | Reliance on others to complete tasks, delegation of responsibilities, and the anticipation of external entities to carry out necessary work.
Other | Communication | 2 | Misinformation on project limits, mobilization costs, supplemental agreements for additional work, impact of skipping intersection work on project costs.
Other | Railroad | 2 | Delay due to railroad crossing requirements Railroad changed billing procedures for railroad flagger protection mid-contract.
Other | Material Ordering | 1 | Issues with incorrect frame and grates ordered and received. Need to establish unit price for revised items, consider restocking fees, and revise plans with suitable materials without contract time extensions.
Other | Plan Revision | 1 | Delay in bridge mounted noise wall panel installation. Address redesign, manufacturing, delivery, and installation issues.
Other | Quality | 1 | Work not completed per specification.
Other | Right-of-Way | 1 | Delay in acquiring right of way to complete connection with US Road.
Other | Shoring | 1 | Delays caused by shoring issues and waiting for NCDOT forces to fill and grout the roadway.
Other | Traffic Volume | 1 | Excessive traffic caused need for night work.
Other | Unavailability of Funds/Cash Flow | 1 | Unavailability of Funds/Cash Flow Considerations.
1649