## Sheet1
Mitigation Category | Issue to be Addressed | Mitigation Strategy
Roadway | Regulatory and safety requirements for borrow and waste pits | Obtain written approval from local authorities for use of the proposed site.
Roadway | Regulatory and safety requirements for borrow and waste pits | Undertake a preliminary site assessment prior to excavation work.
Roadway | Regulatory and safety requirements for borrow and waste pits | Confirm the extent and quality of the materials within the proposed site by drilling boreholes and/or excavating test pits.
Roadway | Regulatory and safety requirements for borrow and waste pits | Ensure that high voltage lines will not interfere with hauling operations.
Roadway | Substandard subgrade quality | Understand the soil properties, proper grading practices, and quality control testing requirements to achieve a high-quality subgrade.
Roadway | Substandard subgrade quality | Determine the non-uniform geotechnical conditions throughout the pavement that could contribute to local permanent deformation.
Roadway | Substandard subgrade quality | Conduct a geotechnical study to evaluate specific problems (e.g., excessive subgrade rutting, aggregate contamination or degeneration, subgrade pumping, poor drainage, frost action, and/or swelling soil) and recommend procedures to mitigate potential problems.
Roadway | Substandard subgrade quality | Test the soil to determine the bearing capacity that relates to moisture and density information, as the pavement and designed base course thickness depend on the resultant subgrade strength.
Roadway | Substandard subgrade quality | Perform quality control and quality assurance testing and compare actual performance with predicted performance.
Roadway | Inadequate understanding of site hydraulic characteristics | Ensure that pipe ends, culvert wing walls, and headwalls adjacent to the roadway do not extend past the surrounding ground.
Roadway | Inadequate understanding of site hydraulic characteristics | Install a grated inlet to prevent water ponding at access points.
Roadway | Inadequate understanding of site hydraulic characteristics | Install flexible lining for ditches with heavy runoff.
Roadway | Inadequate understanding of site hydraulic characteristics | Install safe bicycle grates when expecting bicycle traffic.
Roadway | Inadequate understanding of site hydraulic characteristics | Clean the ditches regularly to prevent silting and forcing water back onto the roadway surface or into the sub-base of the pavement.
Roadway | Inadequate understanding of site hydraulic characteristics | Restore eroded and silted areas around barrier posts, breakaway sign supports, and highway light supports to the desired ground level, and seed those areas. If the area continues to erode, install bituminous overlays.
Roadway | Surveying errors and omissions | Use a terrestrial laser scanner (TLS) to create 3D site models.
Roadway | Surveying errors and omissions | Maintain routine care of equipment.
Roadway | Surveying errors and omissions | Acclimatize the survey instruments to outside conditions prior to final setup in cold or hot weather when using vehicle climate control.
Roadway | Surveying errors and omissions | Use mapping grade receivers to export collected data to an external database, such as a geographical information system (GIS).
Roadway | Surveying errors and omissions | Before commencing a GPS project, obtain the latest versions of all software, adjust all tribraches, and visually check all cables and connections.
Roadway | Surveying errors and omissions | Employ electronic distance measuring instruments, such as total stations.
Roadway | Surveying errors and omissions | Use hand levels for the quick location of turn and instrument points and conduct elevation checks during grading operations.
Roadway | Surveying errors and omissions | Use digital levels for all surveys that require elevations.
Roadway | Surveying errors and omissions | Analyze traverse closure errors to identify and mitigate specific types of error.
Roadway | Surveying errors and omissions | Use sight distances that best fit the terrain and are most comfortable for the instrument operator. Sight distances should not exceed 200 ft (60 m).
Roadway | Surveying errors and omissions | Set benchmarks prior to or during leveling. Check for all found monuments that are to be incorporated in the level line for stability.
Roadway | Driveway Issues | Using eco-friendly permeable pavers, such as TRUEGRID© pavers, to help solve flooded driveway problems.
Roadway | Driveway Issues | Implement seal-coating, a cost-saving preventive maintenance process that can slow the natural degradation process.
Roadway | Driveway Issues | Prevent future root intrusion by installing a root barrier between the planted area and asphalt surface.
Roadway | Driveway Issues | Install a transition mill and asphalt overlay.
Roadway | Driveway Issues | Install a modified concrete base where a high water table affects the surface or inadequate installation results in base failure.
Roadway | Poorly Timed Installation of Pavement Markings | Ensure that activities such as the paving and installation of thermal markings are scheduled during appropriate times of the year. For example, the installation of thermoplastic pavement markings requires warm temperatures to establish proper bonding to the pavement surface.
Roadway | Inadequate Planning for Signage and Signalization | Check for all issues that pertain to the installation of overhead signs (e.g., utility conflicts, power availability, and dimensions).
Roadway | Inadequate Planning for Signage and Signalization | Install lighting along horizontal curves or segments of high-speed rural roadways that have narrow lanes and/or shoulders and a history of lane departure crashes.
Roadway | Inadequate Planning for Signage and Signalization | Install roadside delineators to help drivers see changes in the roadway geometry.
Roadway | Inadequate Planning for Signage and Signalization | Install signs to warn drivers of an upcoming change in lane width.
Roadway | Revisions to Project Limits | Communicate with planning staff and the Environmental Analysis Unit regarding any revisions to project limits.
Roadway | Revisions to Project Limits | Reach out to the L&S and Photogrammetry Units as soon as possible. Mapping during the leaf off-season (mid-December to mid-April) maximizes ground coverage.
Roadway | Revisions to Project Limits | Provide project limits information to the Photogrammetry Unit in good time for the Photogrammetry Unit to plan flights.
Roadway | Revisions to Project Limits | If limits are likely to be changed, then the Photogrammetry Unit can acquire additional imagery during the leaf off-season to reduce the risk of project delays or increase the cost of final surveys.
Roadway | Revisions to Project Limits | Because the let date typically determines when final surveys are due, be aware that it is a key date when determining the date for the Photogrammetry Unit to begin mapping.
Roadway | Revisions to Project Limits | Be aware that the date for the final surveys typically determines when shell mapping by the Photogrammetry Unit is due to the L&S Unit.
Roadway | Inadequate Vegetation/Revegetation Plans | Enlist experts from natural resource disciplines (e.g., botany, plant genetics, horticulture, etc.) to help with revegetation planning.
Roadway | Inadequate Vegetation/Revegetation Plans | Incorporate revegetation planning early in the road project development process to benefit project coordination, schedule, and budget.
Roadway | Inadequate Vegetation/Revegetation Plans | Define appropriate roles to help the designer coordinate work with appropriate personnel, follow protocols, and avoid duplicating efforts.
Roadway | Inadequate Vegetation/Revegetation Plans | Ensure that the designer is the coordinator of the technical and organizational aspects of the revegetation project to enhance project quality and efficiency.
Roadway | Inadequate Vegetation/Revegetation Plans | Prior to vegetation design, understand any new road alignments or major road widenings, which often involves extensive study of functional, cultural, environmental, and aesthetic issues.
Roadway | Slope and Embankment Issues | Verify the estimated quantity of embankment materials.
Roadway | Slope and Embankment Issues | Check for additional erosion control requirements that may be needed for this project.
Roadway | Inadequate Traffic Control | Reduce project impacts on motorists and improve safety by implementing efficient and effective project phasing, construction sequencing, and control of traffic through the work zone.
Roadway | Inadequate Traffic Control | Develop a traffic control plan to minimize traffic disruption and eliminate safety hazards typically associated with work zones.
Roadway | Inadequate Traffic Control | Select pavement treatments, traffic management approaches, and contracting methods that will accelerate the work and minimize traffic disruption.
Roadway | Inadequate Traffic Control | Select strategies for high-volume traffic conditions that require construction knowledge and experience input to ensure that each strategy is constructible and cost-effective, minimizes traffic delays, and provides a safe environment for workers and the traveling public.
Roadway | Inadequate Traffic Control | Use a process modeling technique to formalize and structure the maintenance repair and rehabilitation (MRR) strategy selection.
Roadway | Inadequate Traffic Control | Use Quick Zone, which is a traffic impact analysis spreadsheet-based tool that can be used for work zone delay estimation. Quick Zone is a tool being developed under the Strategic Work-Zone Analysis Tools (SWAT) program at the Federal Highway Administration’s Turner-Fairbanks Highway Research Center.
Roadway | Inadequate Traffic Control | Install intelligent traffic systems with changeable message signs to provide real-time traffic information for drivers.
Roadway | Inadequate Traffic Control | Segment full closures (4.8 km to 8 km in length) in one lane direction from one major ramp to another off-ramp during weekends and late weeknight hours.
Roadway | Inadequate Traffic Control | Use media to inform the public about the project.
Roadway | Inadequate Traffic Control | Analyze traffic alternatives and perform constructability reviews. These two distinct sub-steps should be iterative and include a collaborative effort among traffic engineers, construction engineers, constructability experts, project engineers, pavement engineers, and, as necessary, public information staff.
Roadway | Inadequate Traffic Control | Coordinate tools and integrate construction staging and maintenance of traffic via multidisciplinary reviews.
Roadway | Inadequate Traffic Control | Use appropriate road closure techniques, including directional closures, crossovers, reduced lane width, and temporary widening within existing right-of-way.
Roadway | Inadequate Traffic Control | Do not set the design basis too early in the project development process to avoid suboptimal solutions for handling traffic.
Right-of-Way | Land purchase delays | Involve ROW Unit early (pre-STIP is preferred).
Right-of-Way | Land purchase delays | Consider ROW costs carefully in the risk mitigation strategy approach.
Right-of-Way | Land purchase delays | Use the Utility lead to provide early coordination with utility owner. Consider 2- to 4-year lead time for utilities.
Right-of-Way | Land purchase delays | Implement a ‘right size’ resource assignment, as bigger projects require larger, more experienced consulting firms to assist with ROW analysis than smaller projects.
Right-of-Way | Land purchase delays | Implement an early acquisition program.
Right-of-Way | Land purchase delays | Establish early involvement and relationship building with property owner(s) (i.e., hold an adequate number of public hearings).
Right-of-Way | Insufficient ROW leading to possible utility relocation delays, redesign to accommodate existing easement, and/or purchase of additional easement | Show correct existing ROW dimensions on the plans for ROW acquisition.
Right-of-Way | Insufficient ROW leading to possible utility relocation delays, redesign to accommodate existing easement, and/or purchase of additional easement | Confirm existing ROW dimensions throughout the entire project.
Right-of-Way | Insufficient ROW leading to possible utility relocation delays, redesign to accommodate existing easement, and/or purchase of additional easement | Consider changing the design to avoid high-risk locations.
Right-of-Way | Insufficient ROW leading to possible utility relocation delays, redesign to accommodate existing easement, and/or purchase of additional easement | Acquire ROW with future consideration for widening, improvements, and/or reconstruction to add additional lanes.
Right-of-Way | Complex relocations | Conduct project inspections and take notes to identify issues such as “utility pole in the parking lot”.
Right-of-Way | Complex relocations | Ensure adequate easement (consider temporary work zones, including traffic shifts, temporary bridges, signage, and utilities).
Right-of-Way | Complex relocations | Consider making minor design changes to the grade or alignment to accommodate a utility relocation.
Right-of-Way | Complex relocations | Hold utility relocation coordination meetings on an annual basis.
Right-of-Way | Complex relocations | Provide notice and request that the utility company relocate the utility as soon as the need is determined.
Right-of-Way | Contamination within ROW | Clearly understand the nature of contaminants that require remediation.
Right-of-Way | Contamination within ROW | Provide cap protection by interrupting an exposure pathway or controlling contaminant movement.
Right-of-Way | Contamination within ROW | Allow contractors to inspect buildings for asbestos and/or other contaminants and perform remediation work.
Right-of-Way | Unforeseen risks | Consider in the estimate possible public concerns and possible litigation due to unforeseen ROW risks.
Right-of-Way | Unforeseen risks | Ensure coordination between the NCDOT and the utility company regarding the control of ROW.
Right-of-Way | Unforeseen risks | Have the contractor communicate all changes in the original construction schedule to the local government and all other affected stakeholders.
Right-of-Way | Unforeseen risks | Develop a plan of action if unforeseen circumstances occur.
Right-of-Way | Inaccurate ROW estimate | Consider having a third party review the estimate.
Right-of-Way | Inaccurate ROW estimate | Update ROW costs throughout the preconstruction stages, including all possible costs (e.g., costs associated with land acquisition or easement rights, relocation, asbestos abatement and demolition, consultant fees, and condemnation).
Right-of-Way | Inaccurate ROW estimate | Involve the Photogrammetry Unit to help create more accurate ROW estimates through GIS software and parcel data from NC One Map.
Right-of-Way | Other considerations | Increase cost estimate contingency for larger projects (> 40 parcels), as estimation accuracy decreases for larger projects. (Note that estimating ROW costs for small and medium-sized projects, i.e., 10 to 40 parcels, is less of an issue.)
Structures | Bridge structure design errors | Review and check the plans for completeness and accuracy with regard to lift bents.
Structures | Deck and guardrail omissions and design errors | Review and check the plans for completeness and accuracy with regard to deck steel and dowels, expansion/contraction joints, epoxy-coated rebar, and guardrails.
Structures | Deck and guardrail omissions and design errors | Provide a detailed plan view and standard drawings for the various design elements of the bridge that include all important information.
Structures | Deck and guardrail omissions and design errors | Ensure that the bridge designer works with the Road Design Section to ensure compatibility between the guardrail-to-bridge-to-rail transition and the site.
Structures | Foundation obstructions and/or unsuitable soil | Understand the environmental, thermal, and loading conditions that are expected during the life of the proposed bridge.
Structures | Foundation obstructions and/or unsuitable soil | Require close coordination between the Geotechnical Design Section (GDS) and the design team.
Structures | Foundation obstructions and/or unsuitable soil | Ask GDS personnel to develop a soil exploration program and prepare a preliminary geotechnical report and bridge geotechnical report.
Structures | Foundation obstructions and/or unsuitable soil | Perform a detailed subsurface soil investigation based on the bridge bent locations and anticipated foundation type after conducting a design field review.
Structures | Foundation obstructions and/or unsuitable soil | Ensure that the drawings show the estimated and minimum pile tip elevations of the structural elements.
Structures | Foundation obstructions and/or unsuitable soil | Examine individual boring logs and plots of the profiles of the various subsurface materials.
Structures | Temporary construction omissions | Review and check the plans for completeness and accuracy with regard to traffic bearing shoring and adequate easement for temporary construction.
Structures | Untimely or late permit acquisition | Ensure that all necessary permit applications are filed with the appropriate enforcement agencies and that they are filed in good time.
Structures | Surveying errors | Review and check the plans for completeness and accuracy with regard to survey data and the location of structures.
Utilities | Relocation delays | Establish an appropriate schedule prior to construction. Use a phased contract approach if utilities will not be removed prior to construction.
Utilities | Relocation delays | Gather available information and perform preliminary field investigations.
Utilities | Relocation delays | Plan utility relocations prior to construction to identify their current location with respect to new utilities to avoid obstructions or constraints.
Utilities | Relocation delays | Review relocation plans with utility owners to ensure that the plans meet utility owner requirements.
Utilities | Relocation delays | Relocate utilities in advance (by the utility company or one of its prequalified contractors).
Utilities | Relocation delays | Avoid relocating existing utilities by redesigning or realigning a proposed structure during the design phase.
Utilities | Relocation delays | Conduct utility relocation coordination meetings on a regular basis.
Utilities | Relocation delays | Require that utility information is included with all roadway construction plans.
Utilities | Encroachment on new construction | Ensure adequate easement to accommodate temporary work zones, including traffic shifts, temporary bridges, signage, etc.
Utilities | Encroachment on new construction | Evaluate alternatives for the project and utilities to reduce impacts.
Utilities | Utilities shown in different plan location | Review existing utilities records and information.
Utilities | Utilities shown in different plan location | Perform subsurface utility investigation to map utility locations.
Utilities | Utilities shown in different plan location | Conduct contract survey to map utilities, if necessary.
Utilities | Utilities shown in different plan location | Survey and plot above-ground features and connecting points.
Utilities | Utilities shown in different plan location | Create a 3D utility model.
Utilities | Unforeseen utilities | Identify unique constraints, such as nearby high voltage lines, specialized equipment or permits, power transmission easements, transcontinental gas lines, complex or phased installation of wet utilities, prior grading work, high water table, and/or contaminated soil.
Utilities | Unforeseen utilities | Excavate, if necessary, to expose and survey utilities.
Utilities | Tie-in delays due to existing utilities | Identify any possible tie-ins to existing wet utilities in advance and ensure adequate coordination with all appropriate stakeholders (e.g., owners and municipalities).
Utilities | Special utility requirements | Provide a utilities coordinator to be available throughout the project’s lifecycle.
Utilities | Special utility requirements | Ensure that correct utility boxes are identified in the plans.
Utilities | Special utility requirements | Locate any underground utilities that are inside the tolerance zone.
Utilities | Damage of new utilities by others | Identify potential utility conflicts using a utility conflicts matrix (Clash Detections).
Utilities | Damage of new utilities by others | Conduct utility impact analysis.
Utilities | Damage of new utilities by others | Avoid sensitive environmental areas in the design stage of the project.
Rail | Railroad agreement delay | Ensure early involvement and coordination between the NCDOT and railroad company.
Rail | Railroad agreement delay | Conduct periodic meetings between the NCDOT and railroad company.
Rail | Railroad agreement delay | Consider partnering with the railroad company to streamline the entire process.
Rail | Railroad agreement delay | Develop a master agreement.
Rail | Railroad agreement delay | Identify one NCDOT representative and one railroad company representative as the central points of contact and empower those persons to coordinate highway and railway project issues.
Rail | Railroad agreement delay | Establish a website with ROW requirements that are specific to each railroad company.
Rail | Right-of-entry delay | Consider design changes to avoid high-risk locations.
Rail | Right-of-entry delay | Ensure adequate easement when working near railroad property.
Rail | Right-of-entry delay | Use third-party consultants to provide a design review of plan submittals.
Rail | Right-of-entry delay | Update standard bid specifications as they pertain to contractors working in a railway right- of-way.
Rail | Right-of-entry delay | Determine railroad company’s insurance requirements.
Rail | Railroad bridge clearance issues | Check with railroad regarding suitable clearance requirements.
Rail | Railroad company’s specific requirements are more stringent than those of the NCDOT, resulting in extra work | Allow additional time for setting girders for any structure over railroad tracks.
Rail | Railroad company’s specific requirements are more stringent than those of the NCDOT, resulting in extra work | Check with railroad company regarding suitable embankment materials (e.g., broken pavement might not meet the railroad company’s requirements).
Rail | Unforeseen site conditions within railway easement | Collect site information from the railroad company to help identify possible unforeseen site conditions.
Rail | Unforeseen site conditions within railway easement | Conduct subsurface investigations during the design phase.
Rail | Flagger availability delay | Make sure to have right-of-entry permits filed and railway flaggers present during encroachment.
Rail | Flagger availability delay | Issue a Scope of Work worksheet to document flagging needs and the reimbursement method.
Rail | Flagger availability delay | Identify one point of contact within the railroad company who is responsible for coordination of flagging.
Other | Suspension of work due to funding issues | Avoid late invoicing.
Other | Suspension of work due to funding issues | Hire a part-time bookkeeper or financial controller to help balance the workload.
Other | Suspension of work due to funding issues | Gather detailed financial data to make informed and strategic business decisions.
Other | Suspension of work due to funding issues | Include price adjustment clauses in the contract.
Other | Suspension of work due to funding issues | Allow contractors to make a change by requiring a 25% to 50% security deposit to avoid insufficient cash reserves.
Other | Suspension of work due to funding issues | Consider renegotiating vendor contracts to extend billing cycles or to pay some or all costs after the project is complete.
Other | Issues with phased projects | Consider the impacts of completing one portion of the project and not others (e.g., consider potential hydraulic impacts on uncompleted sections).
Other | Conflicts with nearby projects | Compromise so that each party’s interests are satisfied to a degree.
Other | Conflicts with nearby projects | Solve the underlying problem, not the symptom.
Other | Conflicts with nearby projects | Accept risks if they cannot be avoided, transferred, insured, eliminated, controlled, or mitigated.
Other | Local tourism activity that may lead to schedule changes | Consider potential impacts of the tourist season when preparing the construction schedule.
Other | Resource limitations | Consider hiring temporary staff in areas that may experience a shortage of resources.
Other | Unexpected risks | Use Monte Carlo simulations to review all possible outcomes and probabilities of any given action in response to unexpected situations.
Other | Unexpected risks | Try to identify conditions that are most conducive to detecting risk factors early in the project’s lifecycle.