## Sheet1
Category | Area | Count | Average Cost ($) | Average Time (Days) | Issue Summary
Claim | Utility | 51 | 34100 | 70 | Utility conflicts, delays in utility relocation, errors in utility construction plans, unexpected waterline replacements, and delays caused by power company responses. These issues have caused delays in the completion of the project, additional materials and grading, erosion measures, and idle costs for the contractor. Additional compensation has been requested for the idle equipment and revised completion dates have been set.
Claim | Environmental | 34 | 12450 | 62 | Delays in establishing permanent vegetation, insufficient time for vegetation establishment, unfavorable weather conditions, and contractor compensation issues. These issues have caused delays in completing the contract and meeting erosion control requirements. Additional drainage infrastructure and wildlife nesting have also caused delays. Recommendations include adding 180 days to the original completion date and granting time for the contractor to attain 80% permanent cover.
Claim | Roadway | 29 | 59900 | 46 | Non-compliance with paving regulations, drainage issues, delays in contract completion, poor quality materials, design issues, plan errors, utility relocations, material shortages, scheduling issues, guardrail installation and removal, and lack of ADA compliance. These issues have caused extra work, delays, and additional costs for the contractor.
Claim | Geotechnical | 29 | 24200 | 28 | Continuous maintenance due to severe weather damage, delays in construction due to various issues such as high-water levels and unexpected subsurface conditions, poor quality materials, and the need for shoring to prevent erosion and exposure of graves during excavation. Solutions include using sheet piling as coffer dams, improving material quality, and extending contract completion dates.
Claim | Hydraulic | 17 | 3880 | 49 | Drainage issues, delays in acquiring materials, additional work required by environmental officers, obstruction of work by other projects, collapsed drainage structures, and missing line items in the contract. These issues have caused delays and extra work for the contractor, and in some cases, compensation is required for additional materials or work not included in the original contract.
Claim | Structural | 15 | 28180 | 46 | Scope changes, manufacturing issues, delays due to unforeseen circumstances, errors in plans and specifications, and additional costs incurred for materials and labor. The contractor was not at fault for some of the issues, but improvements in manufacturing and planning processes are needed to prevent future problems.
Claim | Traffic | 15 | 5300 | 48 | Non-uniform and unsymmetrical pavement markings, incorrect striping on roads, incomplete permanent pavement markings, sight distance design issues, delay in approval of installations, inadequate pavement markings, and the use of non-ADA compliant material. Low visibility of crosswalks and temporary paint required additional measures, and missing line items caused compensation issues.
Claim | Traffic Control & Staging | 11 | 26000 | 102 | Railroad delays, specifically related to flagging, obtaining a flagger, and coordinating with the railroad. Additionally, there were issues with overlooked work zone signs, modifying barricades, and safety concerns related to the absence of Truck Mounted Attenuators. Payment for railroad inspectors and compensation for delays were also problematic.
Claim | Other | 277 | 17100 | 56 | Delays in project completion due to incomplete previous projects, pandemic-related shutdowns and staffing shortages, delays in material acquisition, waiting for other entities to perform work, scheduling conflicts, delays in final inspection and punchlist, and delays in contract execution. There were also delays caused by additional work, equipment malfunctions, and errors in sign fabrication.
Supplemental Agreement | Roadway | 261 | 90400 | 0 | Severe potholes on roads, overrun of contract quantities, inadequate guardrail protection, deteriorating pavement, inconsistent asphalt grades, missing line items in the contract, and the need for additional compensation for extra work and materials. Other issues include inadequate tie downs, insufficient guardrail coverage, and the need for additional asphalt surface treatment. The solutions involve creating supplemental agreements, establishing unit prices, and providing compensation for extra work and materials.
Supplemental Agreement | Hydraulic | 160 | 22850 | 0 | Insufficient drainage causing issues with truck traffic, uncontrollable high-water levels, lack of proper drainage and uneven pavement in proposed roundabouts, drainage concerns on bridge shoulders, availability issues with Ductile Iron pipe, and the need for additional drainage work including masonry structures, HDPE pipes, concrete islands, borrow excavation, rip rap, seeding and mulching, flaggers, and temporary traffic control. There are also issues with existing pipes, catch basins, and drainage structures that require repair or replacement, as well as the need for erosion control measures such as wattles and turbidity curtains. Some items were omitted from the original contract, requiring supplemental agreements for compensation and additional work.
Supplemental Agreement | Traffic | 155 | 17930 | 0 | Missing line items in the contract for necessary work, inadequate pavement markings, insufficient compensation for additional work, damaged or missing equipment, and safety concerns. Solutions include establishing pricing for additional work items, revising plans to account for traffic, compensating for necessary equipment and materials, and installing new pavement markings and safety features.
Supplemental Agreement | Geotechnical | 115 | 27800 | 0 | Slope failure, contaminated soil, unexpected rock, poor soil conditions, erosion issues, inadequate contract planning, omission of payment for necessary materials, unstable toe of slope, and lack of established line items for necessary work. Solutions include compensation for necessary materials and labor, installation of geotextile fabric and rip rap, and additional mobilization for necessary work.
Supplemental Agreement | Traffic Control & Staging | 102 | 17900 | 0 | Need for portable changeable message signs, type E sign erection, removal and relocation, U-channel support disposal, and 3-lb steel U-channel supports. There is also a lack of compensation for various traffic control measures, such as flaggers, law enforcement, and temporary traffic control devices. Additionally, there are issues with plan omissions, conflicting pavement markings, and the need for additional safety measures.
Supplemental Agreement | Utility | 84 | 27000 | 0 | Utility conflicts, need for compensation for extra work and materials, incorrect or omitted information on plans, damage to existing infrastructure, and delays in utility relocations. These issues involve water and sewer line relocation, fire hydrant and meter adjustments, manhole and valve adjustments, and exploratory excavation to locate utilities. Supplemental agreements and compensation are necessary to address these problems.
Supplemental Agreement | Structural | 37 | 48250 | 0 | Bridge approach paving, overstresses in spans, concrete slab failure, missing bridge items, compensation for additional work and materials, plan errors, guardrail installation, and structural deficiencies. These issues resulted in delays, increased material costs, and the need for supplemental agreements to address the additional work and compensation.
Supplemental Agreement | Environmental | 24 | 14000 | 0 | Trees marked for removal instead of saving, asbestos removal, lack of permanent vegetation establishment, insufficient vegetative coverage, damaged asphalt and vegetation, missing line items in the contract, and non-native plant material. These issues require additional work and compensation to ensure compliance with regulations and project specifications.
Supplemental Agreement | Other | 320 | 32160 | 0 | Material acquisition delays, time-limited material cost escalation adjustments, missing line items in contracts, additional work requested, and extensions of maps causing overruns in contract amounts.