## Cost Calculation for Supp Mat
CONSTRUCTION COST OVERVIEW
| LENGTH | CONSTRUCTION COST 2024 DOLLARS | ROUGH/BALLPARK DESIGN COST (15% of construction cost) 2024 DOLLARS | CONSTRUCTION COST/MILE CHECK
MAINLINE (no contingency) | 3.834 | 5307407.4074 | 796000 | 1384300.3149
CONNECTORS (no contingency) | 2.28 | 3335555.5556 | 500000 | 1462962.963
TOTAL Costs (No Contingency) | 6.114 | 8642962.963 | 1296000 | 1413634.7666
TOTAL Costs (30% construction contingency) | 6.114 | 11236000 | 1685000 | 1837749.4275
TOTAL Costs (35% construction contingency) | 6.114 | 11668000 | 1750000 | 1908406.9349
Approx. Average of 30% and 35% Design Costs |  |  | 1700000
*Segment Crossing Railroad at S English street excluded from cost per mile calculations (part of NCDOT STIP Project)
DETAILED DESIGN COSTS |  |  |  |  | PROJECT COST SUMMARY
| Task Cost | 5% Escalation to 2025$ | Milestone/Deliverable |  |  | 30% Construction Contingency | 35% Construction Contingency
TASK 1: GRANT ADMINISTRATION + PROJECT MANAGEMENT | 50000 | 53000 | Duration of Project (Quarterly) |  | 2024 Construction Estimate | 11236000 | 11668000
TASK 2: SURVEY | 400000 | 420000 | NTP + 3 MONTHS |  | 2029 Escalated Construction Cost | 14340000 | 14892000
TASK 3: 25% DESIGN PLANS | 250000 | 263000 | NTP + 6 MONTHS |  | Design Cost | 1907000 | 1907000
TASK 4: 50% DESIGN PLANS | 300000 | 315000 | NTP + 10 MONTHS |  | CEI | 1720000 | 1785000
TASK 5: 75% DESIGN PLANS | 200000 | 210000 | NTP + 14 MONTHS |  | RW Acquisition | TBD | TBD
TASK 6: UTILITY + RAILROAD COORDINATION | 180000 | 189000 | NTP + 20 MONTHS |  | Project Contingency (5%) | 715000 | 745000
TASK 7: PERMITTING | 100000 | 105000 | NTP + 22 MONTHS |  | TOTAL RECOMMENDED CONSTRUCTION BUDGET | 18682000 | 19329000
TASK 8: COMMUNITY ENGAGEMENT | 75000 | 79000 | Duration of Project
TASK 9: 90% DESIGN PLANS | 150000 | 158000 | NTP + 20 MONTHS
TASK 10: 100% CONSTRUCTION DOCUMENTS | 25000 | 26000 | NTP + 24 MONTHS
DESIGN CONTINGENCY (5%) | 85000 | 89000 | n/a
TOTAL | 1815000 | 1907000
| Local Match (20%) | 381400
| Federal Share (80%) | 1525600