## Original
[10 empty] | Version: | 2020.01.21.RJS
TIP | B-1234
PROJECT DESCRIPTION | Survey and Evaluation
PREPARED BY | Archaeology Team
FIRM | Vandelay Industries
|  |  | TASK 1 |  | TASK 2 |  | TASK 3 |  | TASK 4 |  | TOTALS
|  |  | Consultation and |  | Research and |  |  |  | Draft and Final
|  |  | Project Management |  | Fieldwork |  | Lab Work |  | Report Preparation
LABOR CATEGORY | EMPLOYEE NAME | BILLING RATE | HOURS | COST | HOURS | COST | HOURS | COST | HOURS | COST | HOURS | COST
Contract/Project Manager | John Mayall |  | 16 | 0 | 44 | 0 |  | 0 | 32 | 0 | 92 | 0
Archaeologist |  |  | 12 | 0 | 325 | 0 | 20 | 0 | 280 | 0 | 637 | 0
Arcaheolgoical Technician |  |  |  | 0 | 240 | 0 | 300 | 0 | 20 | 0 | 560 | 0
Arcaheolgoical Technician | Jimi Hendrix |  | 8 | 0 | 240 | 0 | 300 | 0 |  | 0 | 548 | 0
Archaeological Technicians |  |  |  | 0 | 720 | 0 |  | 0 |  | 0 | 720 | 0
Lab Manager |  |  |  | 0 | 8 | 0 | 40 | 0 | 20 | 0 | 68 | 0
Lithic Analyst |  |  |  | 0 |  | 0 | 100 | 0 |  | 0 | 100 | 0
Editor/Peer Review |  |  |  | 0 |  | 0 |  | 0 | 16 | 0 | 16 | 0
GIS/Graphics | Carlos Santana |  | 6 | 0 |  | 0 |  | 0 | 120 | 0 | 126 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Direct Labor Subtotals |  |  | 42 | 0 | 1577 | 0 | 760 | 0 | 488 | 0 | 2867 | 0
Overhead @ 000.00% |  | 122% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fee Base Subtotals |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Net Fee |  | 9% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Facilities Cost of Capital @0.0000% |  | 0.23% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subtotals |  |  | 42 | 0 | 1577 | 0 | 760 | 0 | 488 | 0 | 2867 | 0
DIRECT COSTS |  | RATE | UNITS | COST | UNITS | COST | UNITS | COST | UNITS | COST | TOTALS | COST
Vehicle Mileage (Carry-All) |  | 0.595 | 120 | 71.4 | 4960 | 2951.2 |  | 0 |  | 0 | 5080 | 3022.6
Vehicle Mileage (Sedan) |  | 0.575 | 180 | 103.5 | 680 | 391 |  | 0 |  | 0 | 860 | 494.5
Car Rental |  | 45 |  | 0 | 45 | 2025 |  | 0 |  | 0 | 45 | 2025
Gas for Rental |  | 0.2 |  | 0 | 900 | 180 |  | 0 |  | 0 | 900 | 180
Film and Developing |  | 20 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Per diem |  | 39.4 |  | 0 | 210 | 8274 |  | 0 |  | 0 | 210 | 8274
Lodging |  | 80 |  | 0 | 210 | 16800 |  | 0 |  | 0 | 210 | 16800
Report b/w |  | 0.07 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Report color |  | 1.25 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Miscellaneaous Field Supplies |  | 100 |  | 0 | 15 | 1500 |  | 0 |  | 0 | 15 | 1500
Miscellaneaous Lab Supplies |  | 100 |  | 0 |  | 0 | 5 | 500 | 2 | 200 | 7 | 700
Miscellaneaous |  | 250 |  | 0 |  | 0 |  | 0 |  | 200 | 0 | 0
Subcontracted Services
Heavy Machinery w/ Operator |  | 125 |  | 0 | 196 | 24500 |  | 0 |  | 0 | 196 | 24500
Excavation Shelter |  | 650 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Outdoor Portable Heater |  | 100 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Porta-Johns |  | 80 |  | 0 | 6 | 480 |  | 0 |  | 0 | 6 | 480
Ground Penetrating Radar |  | 165 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Total Station Rental/Weekly |  | 550 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Chronometric Analysis |  | 695 |  | 0 |  | 0 | 10 | 6950 |  | 0 | 10 | 6950
Ethnobotanical Analysis |  | 225 |  | 0 |  | 0 | 15 | 3375 |  | 0 | 15 | 3375
Faunal Analysis |  | 250 |  | 0 |  | 0 | 10 | 2500 |  | 0 | 10 | 2500
Pollen/Phytolith Analysis |  | 225 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
INAA |  | 100 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Pottery Petrographic Analysis |  | 85 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Use Wear Analysis |  | 100 |  | 0 |  | 0 | 10 | 1000 |  | 0 | 10 | 1000
Subtotals |  |  |  | 174.9 |  | 57101.2 |  | 14325 |  | 400 |  | 71801.1
PROJECT TOTAL |  |  |  | 174.9 |  | 57101.2 |  | 14325 |  | 400 |  | 71801.1