## Sheet3
PROJECT_ID | ROUTE_CITY | COUNTY | IMPACTS | LET DATE | DIVISION | ECO-REGION | RIVER BASIN | CU | Warm Stream | Cool Stream | Cold Stream | TOTAL STREAM | Riparian Wetlands | Non-Riparian Wetlands | Coastal Marsh Wetlands | TOTAL WETLANDS | SOURCE | SOURCEDATE | LAST THREE YRS | STATUS | MITIGATION SOURCE | NOTE TO DMS
U-6143 | NC 7 (EAST CATAWBA STREET) | GASTON | X | 2024-06-18 | 12 | SP | CATAWBA | 03050101 | 50 |  |  | 50 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-6048 | SR 1812 (DIGGS ROAD) | Anson |  | 2024-04-16 | 10 | SP | YADKIN | 03040201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
HB-0002 | I-40 | Haywood |  | 2024-04-16 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | GIS | 2021-12-07 |  | Projected-STIP
P-5720 | CSX | Wake |  | 2024-04-16 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Projected-STIP
B-6054D | I-40 | Haywood |  | 2024-05-06 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
B-6054E | I-40 | Haywood |  | 2024-05-06 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
B-4636 | NC 24 | Sampson | X | 2024-06-18 | 3 | SICP | CAPE FEAR | 03030006 |  |  |  | 0 | 0.39 |  |  | 0.39 | Permit Drawings | 2022-10-10 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5847 | SR 1709 (ROCK BARN ROAD) | Catawba |  | 2024-05-21 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5871 | SR 1306 (BILLS CREEK ROAD) | Rutherford |  | 2024-05-21 | 13 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5791A | SR 2714 | Onslow | X | 2024-06-18 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 | 3 |  |  | 3 | Merger Materials | 2020-01-22 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HE-0002 | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | Wake | X | 2024-07-16 | 5 | CP | CAPE FEAR | 03030002 | 925 |  |  | 925 | 0.11 |  |  | 0.11 | EAU Review | 2022-02-03 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-5610 | NC 12 | Dare |  | 2024-06-18 | 1 | NOCP | TAR-PAMLICO | 03020105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5684 | US 401 (CAPITAL BOULEVARD) | Wake |  | 2024-06-18 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5716 | SR 1138 (LINDSEY BRIDGE ROAD) | Rockingham |  | 2024-06-18 | 7 | CP | ROANOKE | 03010103 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-6051 | US 29 / US 74 | Mecklenburg |  | 2024-06-18 | 10 | SP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
U-4700CA | US 321 | Caldwell |  | 2024-06-18 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-02-04 |  | Projected-STIP
U-4700CC | US 321 | Caldwell |  | 2024-06-18 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2018-02-01 |  | Projected-STIP
U-4709 | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | Cumberland |  | 2024-06-18 | 6 | SICP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5761 | NC 3 (DALE EARNHARDT BOULEVARD) | Cabarrus |  | 2024-06-18 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-6202 | SR 2048 (GORDON ROAD) | New Hanover | X | 2024-07-16 | 3 | SOCP | CAPE FEAR | 03030007 | 920 |  |  | 920 | 0.3 |  |  | 0.3 | Document | 2022-10-10 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5809 | US 601 (STATE STREET) | Yadkin |  | 2024-06-18 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
R-5854 | SR 1410 (FARMINGTON ROAD) | Davie |  | 2024-07-11 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-31 |  | Projected-STIP
U-5711 | SR 1712 (PINEVIEW STREET) | Randolph | X | 2024-07-16 | 8 | CP | CAPE FEAR | 03030003 | 121 |  |  | 121 |  |  |  | 0 | Preliminary Designs | 2021-01-26 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0003 | I-40 | Haywood |  | 2024-07-16 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | GIS | 2021-12-07 |  | Projected-STIP
P-5717 | NORFOLK SOUTHERN H LINE | Durham | X | 2024-08-20 | 5 | CP | CAPE FEAR | 03030002 | 440 |  |  | 440 | 0.18 |  |  | 0.18 | Rail Review | 2021-01-26 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5929 | NC 24 / NC 27 | Moore |  | 2024-07-16 | 8 | SP | Cape Fear | 03030003 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
U-5783 | US 64 | Henderson |  | 2024-07-16 | 14 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
U-6020 | NC 56 (EAST C STREET) | Granville |  | 2024-07-16 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP
HB-0021 | OXFORD ROAD | Pitt | X | 2024-09-11 | 2 | NICP | TAR-PAMLICO | 03020103 |  |  |  | 0 | 0.0004 |  |  | 0.0004 | GIS | 2022-08-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5809A | NC 45 | Bertie | X | 2024-09-17 | 1 | NOCP | CHOWAN | 03010203 | 272 |  |  | 272 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
P-5715 | CSX | Wake |  | 2024-08-20 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Projected-STIP
R-5714 | US 601 | Surry |  | 2024-08-20 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
U-5302 | US 401 | Wake |  | 2024-08-20 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP
U-6011 | US 70 (SOUTH CHURCH STREET) | Alamance |  | 2024-08-20 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
I-5979 | US 74 / FUTURE I-74 | Richmond |  | 2024-08-20 | 8 | SP | YADKIN | 03040201 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5809A | NC 45 | Bertie | X | 2024-09-17 | 1 | NOCP | ROANOKE | 03010107 | 41 |  |  | 41 | 1.5344 | 0.9118 |  | 2.4462 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6058 | US 70 (LIVE OAK STREET) | Carteret |  | 2024-09-11 | 2 | SOCP | WHITE OAK | 03020106 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP
R-5809A | NC 45 | Bertie | X | 2024-09-17 | 1 | NOCP | PASQUOTANK | 03010205 |  |  |  | 0 | 0.0332 | 0.1559 |  | 0.1891 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5759 | NC 115 | WILKES | X | 2024-10-15 | 11 | NM | YADKIN | 03040101 |  | 605 |  | 605 | 0.1 |  |  | 0.1 | Division Review | 2021-02-04 |  | Projected-STIP | NCDOT/DMS | Private bank credits for cool stream, cold stream and wetlands. DMS for warm stream credits.
U-4713A | SR 3440 (MCKEE ROAD) EXTENSION | Mecklenburg | X | 2024-10-15 | 10 | SP | CATAWBA | 03050103 | 60 |  |  | 60 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5986 | NC 231 | Wake |  | 2024-09-17 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
R-3430B | SR 1001 (CONNELLY SPRINGS ROAD) | Caldwell |  | 2024-09-17 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | NRTR | 2018-01-01 |  | Projected-STIP
R-5921 | US 276 (JONATHAN CREEK) | Haywood |  | 2024-09-17 | 14 | SM | French Broad | 06010106 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
U-5757 | NC 8 (WINSTON ROAD) | Davidson |  | 2024-09-17 | 9 | CP | YADKIN | 03040103 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-31 |  | Projected-STIP
B-5674 | US 15 / US 501 NORTHBOUND | Durham | X | 2024-10-15 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  | 0.003 |  | 0.003 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5739 | NC 46 | Northampton | X | 2024-11-19 | 1 | NICP | ROANOKE | 03010106 | 500 |  |  | 500 | 0.25 | 0.25 |  | 0.5 | Division Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5723 | SR 1158 (JACKSON LAKE ROAD) | Guilford | X | 2024-11-19 | 7 | CP | CAPE FEAR | 03030003 |  |  |  | 0 | 0.317 | 0.033 |  | 0.35 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-6044 | I-95 | Johnston |  | 2024-10-15 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-12-07 |  | Projected-STIP
U-3628 | NC 24 / NC 27 | MOORE |  | 2024-10-15 | 8 | SP | Cape Fear | 03030003 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-5536 | NEW ROUTE | Forsyth |  | 2024-10-15 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5835 | US 221 BUSINESS | McDowell | X | 2024-12-17 | 13 | NM | CATAWBA | 03050101 | 100 |  |  | 100 |  |  |  | 0 | Division Review | 2021-02-04 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-4758 | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | Guilford | X | 2024-12-17 | 7 | CP | CAPE FEAR | 03030003 | 69 |  |  | 69 | 0.01 |  |  | 0.01 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6044 | SR 2200 (COX ROAD) | Gaston |  | 2025-08-01 | 12 | SP | CATAWBA | 03050102 | [7 empty] | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5746 | US 401 | WAKE |  | 2024-11-19 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | Preliminary Designs | 2021-01-26 |  | Projected-STIP
HB-0009 | ROAD) SR 1800 (BLACKSMITH | Columbus | X | 2025-01-01 | 6 | SICP | LUMBER | 03040206 |  |  |  | 0 | 0.0132 |  |  | 0.0132 | GIS | 2022-08-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5768 | NC 49 & BACK CREEK CHURCH ROAD | Mecklenburg | X | 2025-01-21 | 10 | SP | YADKIN | 03040105 | 1600 |  |  | 1600 | 0.163 | 0.337 |  | 0.5 | Merger Materials | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5814 | US 15 / US 501 / NC 211 | Moore |  | 2024-12-17 | 8 | SP | LUMBER | 03040203 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5815B | US 1 (SANDHILLS BOULEVARD) | Moore |  | 2024-12-17 | 8 | SP | LUMBER | 03040203 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-6013 | NC 119 | Alamance |  | 2024-12-17 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6146 | US 29/74 (WILKINSON BOULEVARD) | Gaston | X | 2025-02-18 | 12 | SP | CATAWBA | 03050102 | 29 |  |  | 29 |  |  |  | 0 | GIS | 2018-12-07 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0010 | SR 1716 (JACKIE LEE ROAD) | Cumberland |  | 2025-01-01 | 6 | SICP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0022 | ROCK SPRINGS ROAD | Pitt |  | 2025-01-01 | 2 | NICP | TAR-PAMLICO | 03020103 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0027 | SR 1355 (PANTHER CREEK ROAD) | Haywood |  | 2025-01-01 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0046 | SR 1105 | Ashe |  | 2025-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0052 | SR 1104 | Ashe |  | 2025-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0055 | SR 1326 | Avery |  | 2025-01-01 | 11 | NM | WATAUGA | 06010103 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0057 | SR 1356 | Caldwell |  | 2025-01-01 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0058 | SR 1356 | Caldwell |  | 2025-01-01 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0059 | SR 1356 | Caldwell |  | 2025-01-01 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0060 | SR 1356 | Caldwell |  | 2025-01-01 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0062 | SR 1594 | Watauga |  | 2025-01-01 | 11 | NM | WATAUGA | 06010103 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0063 | SR 1559 | Wilkes |  | 2025-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0064 | SR 1567 | Wilkes |  | 2025-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0066 | SR 1355 | Wilkes |  | 2025-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0067 | SR 1433 | Alleghany |  | 2025-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HF-0005 | SR 1140 (MYERS CHAPEL ROAD) | Clay |  | 2025-01-01 | 14 | SM | HIWASSEE | 06020002 |  |  |  | 0 |  |  |  | 0 | GIS | 2024-02-12 |  | Projected-STIP
B-6026 | SR 1500 (WATAUGA ROAD) | Macon |  | 2025-01-14 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
B-5832 | SR 2080 (QUAKER CHURCH ROAD) | Surry |  | 2025-01-16 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
U-5750 | NC 54 | Wake | X | 2025-04-15 | 5 | CP | NEUSE | 03020201 | 140 |  |  | 140 |  | 0.02 |  | 0.02 | Preliminary Designs | 2021-01-26 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5833 | US 21 BUSINESS | Yadkin |  | 2025-01-21 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5944 | SR 1509 (QUEENS CREEK ROAD) | Onslow |  | 2025-01-21 | 3 | SOCP | WHITE OAK | 03020106 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5949 | NC 200 | Union |  | 2025-01-21 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
BR-0025 | SR 1639 (MEACHAM RD) | Iredell |  | 2025-01-21 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
HL-0025 | GREYLOCK RIDGE ROAD | Mecklenburg |  | 2025-01-21 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | GIS | 2021-12-16 |  | Projected-STIP
I-5880 | I-40 / US 311 | Forsyth |  | 2025-01-21 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-6041 | US 64 | Alexander |  | 2025-01-21 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-6034 | SR 1300 (PUMPKINTOWN ROAD) | Jackson |  | 2025-01-28 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
B-6036 | SR 1737 (CANEY FORK ROAD) | Jackson |  | 2025-01-28 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
U-5800 | NC 7 | Gaston |  | 2025-02-18 | 12 | SP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5852 | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | Guilford | X | 2025-05-20 | 7 | CP | CAPE FEAR | 03030002 | 240 |  |  | 240 |  |  |  | 0 | Draft MCDC | 2021-01-26 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-6038 | NC 14 / NC 87 | Rockingham |  | 2025-02-18 | 7 | CP | ROANOKE | 03010103 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
U-5730 | US 13 (MEMORIAL DRIVE) | Pitt |  | 2025-02-18 | 2 | NICP | TAR-PAMLICO | 03020103 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
B-6031 | SR 1300 (PUMPKINTOWN ROAD) | Jackson |  | 2025-02-25 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
U-5703B | US 74 (ROOSEVELT BLVD) | Union |  | 2025-03-05 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
R-5717B | SR 1224 (OLD SWAMP ROAD) | Camden |  | 2025-03-18 | 1 | NOCP | PASQUOTANK | 03010205 |  |  |  | 0 |  |  |  | 0 | GIS | 2024-02-12 |  | Projected-STIP
U-5844 | NC 62 | Alamance |  | 2025-03-18 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6248 | NC 75 | UNION |  | 2025-03-19 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | Division Review | 2020-09-24 |  | Projected-STIP
U-3609B | US 13 (BERKELEY BOULEVARD) | Wayne | X | 2025-05-20 | 4 | NICP | NEUSE | 03020202 | 195 |  |  | 195 | 0.1706 |  |  | 0.1706 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-5779 | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | Davidson |  | 2025-04-15 | 9 | CP | YADKIN | 03040103 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5747B | NC 54 | Wake |  | 2025-04-15 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
W-5704E | SR 1700 (COVERED BRIDGE ROAD) | Johnston |  | 2025-04-15 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2020-01-23 |  | Projected-STIP
U-6246 | NC 84 | UNION |  | 2025-04-16 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2020-09-24 |  | Projected-STIP
U-6247 | NC 84 | UNION |  | 2025-04-16 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | Division Review | 2020-09-24 |  | Projected-STIP
U-5728 | US 17 BUSINESS (MARINE BOULEVARD) | Onslow |  | 2025-05-01 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
B-5985B | NC 41/NC 72/SR 1600 | Robeson | X | 2025-05-20 | 6 | SICP | LUMBER | 03040203 |  |  |  | 0 | 0.2689 | 0.1194 |  | 0.3883 | GIS | 2024-02-12 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-6047 | SR 2125 (HARRIS HENRIETTA ROAD) | Rutherford | X | 2025-05-20 | 13 | SP | BROAD | 03050105 |  |  |  | 0 | 0.003 |  |  | 0.003 | GIS | 2019-10-11 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-2822B | NC 143 | Graham | X | 2025-06-17 | 14 | SM | LITTLE TENNESSEE | 06010204 |  |  | 3200 | 3200 | 0.08 |  |  | 0.08 | Merger Materials | 2021-02-04 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-4900 | NC 210 (MURCHISON ROAD) | Cumberland |  | 2025-05-20 | 6 | SICP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6004 | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | Forsyth |  | 2025-05-20 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
U-6014 | SR 1716 (GRAHAM- HOPEDALE ROAD) | Alamance |  | 2025-05-20 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6187 | NEW ROUTE | Davie | X | 2025-06-17 | 9 | CP | YADKIN | 03040101 | 2035 |  |  | 2035 | 0.262 |  |  | 0.262 | Division Review | 2022-04-13 |  | Projected-STIP | NCDOT/DMS | Private bank credits for cool stream, cold stream and wetlands. DMS for warm stream credits.
U-5834 | SR 3116 (MILLS GAP ROAD) | Buncombe | X | 2025-06-17 | 13 | SM | FRENCH BROAD | 06010105 |  |  | 750 | 750 | 0.12 |  |  | 0.12 | Division Review | 2021-02-04 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5824 | NC 690 (LOBELIA ROAD) | Moore | X | 2025-06-17 | 8 | SP | CAPE FEAR | 03030004 | 715 |  |  | 715 |  | 4.34 |  | 4.34 | MCDC | 2022-03-16 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-4409 | SR 2500 (BLUE RIDGE ROAD) | BUNCOMBE | X | 2025-06-17 | 13 | SM | FRENCH BROAD | 06010105 |  |  | 560 | 560 |  |  |  | 0 | NES Review | 2021-02-04 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5807 | NC 343 | Camden | X | 2025-06-17 | 1 | NOCP | PASQUOTANK | 03010205 | 500 |  |  | 500 | 0.5 |  |  | 0.5 | EAU Review | 2019-01-29 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-5831 | I-77 NORTHBOUND | Surry |  | 2025-06-17 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5876 | US 74 | Rutherford |  | 2025-06-17 | 13 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5809B | NC 45 | Bertie | X | 2025-06-17 | 1 | NOCP | CHOWAN | 03010203 | 469 |  |  | 469 | 0.0321 | 0.4763 |  | 0.5084 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
P-5707 | CSX S LINE | WAKE |  | 2025-06-17 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Projected-STIP
P-5725 | KANNAPOLIS | Cabarrus |  | 2025-06-17 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-10-05 |  | Projected-STIP
U-5817 | SR 1246 (FAIRVIEW ROAD) | Iredell | X | 2025-06-17 | 12 | CP | CATAWBA | 03050101 | 280 |  |  | 280 |  |  |  | 0 | Designs | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5100B | SR 1109 (WILLIAMSON ROAD) | Iredell |  | 2025-06-17 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5743 | NC 42 | Randolph | X | 2025-06-17 | 8 | CP | CAPE FEAR | 03030003 | 116 |  |  | 116 |  |  |  | 0 | Preliminary Designs | 2021-01-26 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5939 | US 17 BUSINESS | Pasquotank | X | 2025-06-17 | 1 | NOCP | PASQUOTANK | 03010205 | 100 |  |  | 100 | 0.5 |  |  | 0.5 | Division Review | 2018-02-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5796 | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | Hertford | X | 2025-06-17 | 1 | NOCP | CHOWAN | 03010203 |  |  |  | 0 |  | 0.15 |  | 0.15 | Division Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6043 | US 29/US 74 (FRANKLIN BOULEVARD) | Gaston | X | 2025-06-24 | 12 | SP | CATAWBA | 03050102 | 170 |  |  | 170 | 0.0476 | 0.1609 |  | 0.2085 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-3300A | US 17 | Pender | X | 2025-07-15 | 3 | SOCP | CAPE FEAR | 03030007 | 5400 |  |  | 5400 | 14.1 | 18.85 |  | 32.95 | Merger CP4A | 2021-02-04 |  | Projected-STIP | NCDOT/DMS | Onsite mitigation for riparian wetlands. DMS to provide stream and nonriparian mitigation.
U-5787 | SR 2715 (TRADE STREET) | Onslow |  | 2025-06-17 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
U-5799 | US 21 | Iredell |  | 2025-06-17 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | Merger Sceening | 1999-01-01 |  | Projected-STIP
U-5810 | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | Watauga |  | 2025-06-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
U-5899 | NEW ROUTE | FORSYTH |  | 2025-06-17 | 9 | CP | Yadkin | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-31 |  | Projected-STIP
U-5945 | WILSON | Wilson |  | 2025-06-17 | 4 | NICP | NEUSE | 03020203 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-6027 | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | Richmond |  | 2025-06-17 | 8 | SP | YADKIN | 03040201 |  |  |  | 0 |  |  |  | 0 | MCDC | 2022-08-04 |  | Projected-STIP
R-5600 | NC 107 (US 23 BUSINESS) | Jackson | X | 2025-07-15 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  | 650 | 650 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5771 | US 21 | Mecklenburg | X | 2025-07-15 | 10 | SP | CATAWBA | 03050101 | 347 |  |  | 347 | 0.05 |  |  | 0.05 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-5719 | I-85 | Gaston | X | 2025-08-01 | 12 | SP | CATAWBA | 03050102 | 1996 |  |  | 1996 | 0.1238 | 0.034 |  | 0.1578 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-3400 | SR 1577 / SR 1004 (ARCHDALE ROAD) | Randolph | X | 2025-08-19 | 8 | CP | CAPE FEAR | 03030003 | 1344 |  |  | 1344 | 0.29 |  |  | 0.29 | Preliminary Designs | 2022-01-06 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-6037 | NC 86 | Orange |  | 2025-07-15 | 7 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
P-5709 | NORFOLK SOUTHERN H LINE | GUILFORD |  | 2025-07-15 | 7 | CP | Cape Fear | 03030002 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Projected-STIP
P-5713 | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | Guilford |  | 2025-07-15 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Projected-STIP
R-5100A | SR 1109 (WILLIAMSON ROAD) | Iredell |  | 2025-07-15 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5857 | US 17 | Brunswick |  | 2025-07-15 | 3 | SOCP | LUMBER | 03040207 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6005 | NC 65 (BETHANIA-RURAL HALL ROAD) | Forsyth |  | 2025-07-15 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-31 |  | Projected-STIP
R-5840 | NC 9 | Polk | X | 2025-08-19 | 14 | SP | BROAD | 03050105 |  | 250 |  | 250 | 0.1 |  |  | 0.1 | Division Review | 2019-01-28 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5706A | NC 73 (DAVIDSON HIGHWAY) | Mecklenburg | X | 2025-08-19 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 | 0.19 |  |  | 0.19 | Merger Materials | 2020-09-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5763 | SR 1540 (WILSON ROAD) | TRANSYLVANIA | X | 2025-09-16 | 14 | SM | FRENCH BROAD | 06010105 |  | 3038 |  | 3038 | 0.4 |  |  | 0.4 | Merger Materials | 2021-02-04 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
HB-0024 | US-401 | Haywood |  | 2025-08-19 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0025 | SR 1004 (POORS FORD ROAD) | Polk |  | 2025-08-19 | 14 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
U-5727 | US 1 / US 15 / US 501 | Lee |  | 2025-08-19 | 8 | SP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5976 | US 15 / US 501 | Moore |  | 2025-08-19 | 8 | SP | Lumber | 03040203 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
R-5757 | NC 305 | NORTHAMPTON | X | 2025-09-16 | 1 | NICP | Chowan | 03010204 | 360 |  |  | 360 | 1 |  |  | 1 | Division Review | 2021-02-04 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5673 | SR 1630 (GREEN LEVEL CHURCH ROAD) | Wake | X | 2025-09-16 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 | 0.223 | 0.006 |  | 0.229 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
HB-0018 | I-40 | Catawba |  | 2025-09-16 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
U-6086 | NC 51 | Mecklenburg |  | 2025-09-16 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-10-24 |  | Projected-STIP
U-5307A | US 1 | Wake | X | 2025-10-21 | 5 | CP | NEUSE | 03020201 | 517 |  |  | 517 | 0.6585 | 0.8457 |  | 1.5042 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5709 | SR 1237 (CARTHAGE STREET) | Lee | X | 2025-10-21 | 8 | SP | CAPE FEAR | 03030003 | 319 |  |  | 319 | 0.26 |  |  | 0.26 | Preliminary Designs | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6105 | CORNELIUS | MECKLENBURG | X | 2025-10-21 | 10 | SP | Catawba | 03050101 | 315 |  |  | 315 |  |  |  | 0 | EAU Review | 2021-01-26 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5956 | US 29 | Cabarrus | X | 2025-11-18 | 10 | SP | YADKIN | 03040105 | 110 |  |  | 110 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5990 | SR 1138 WESTBOUND | Mecklenburg |  | 2025-10-21 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
I-5990 | I-40 | Burke | X | 2025-12-16 | 13 | NM | CATAWBA | 03050102 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 2022-08-30 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0026 | SR 1533 (EVERETT ROAD) | Transylvania | X | 2025-12-16 | 14 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 | 0.0006 | 0.0074 |  | 0.008 | GIS | 2022-08-24 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
HB-0030 | SR 1679 (PEEKS CREEK ROAD) | Macon | X | 2026-01-01 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 | 0.0907 | 0.0599 |  | 0.1506 | GIS | 2022-08-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5737 | US 64 (EAST 11TH STREET) | Chatham |  | 2025-12-16 | 8 | CP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5821 | NC 279 (NEW HOPE ROAD) | Gaston |  | 2025-12-16 | 12 | SP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-6003 | SR 1609 (BAPTIST CHURCH ROAD) | Franklin | X | 2026-01-20 | 5 | CP | TAR-PAMLICO | 03020101 | 494 |  |  | 494 | 0.6 | 0.02 |  | 0.62 | Division Review | 2022-10-09 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0033 | POLO ROAD | Forsyth |  | 2026-01-01 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0034 | SR 1007 (PLANK ROAD) | Chatham |  | 2026-01-01 | 8 | CP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0043 | SR 1523 | Ashe |  | 2026-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0047 | SR 1528 | Ashe |  | 2026-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0051 | SR 1159 | Ashe |  | 2026-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0054 | SR 1222 | Ashe |  | 2026-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0068 | SR 1527 | Ashe |  | 2026-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
U-6131 | NC 54 (WEST HARDEN STREET) | Alamance |  | 2026-01-15 | 7 | CP | Cape Fear | 03030002 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
B-4444 | US 19/23/25/70 | Buncombe |  | 2026-01-16 | 13 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5975 | US 1 / US 15 / US 501 | Lee | X | 2026-01-20 | 8 | SP | CAPE FEAR | 03030003 | 492 |  |  | 492 | 0.38 |  |  | 0.38 | Preliminary Designs | 2019-06-20 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5811 | SR 1434 (ROGERS ROAD) | Stanly | X | 2026-01-20 | 10 | SP | YADKIN | 03040105 | 331 |  |  | 331 | 0.011 |  |  | 0.011 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6134 | NC 16 BYPASS | LINCOLN | X | 2026-01-20 | 12 | SP | CATAWBA | 03050101 | 240 |  |  | 240 | 0.1 |  |  | 0.1 | EAU Review | 2018-10-27 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5725 | SR 1710 (GRIERS CHURCH ROAD) | Caswell | X | 2026-01-20 | 7 | CP | ROANOKE | 03010104 |  |  |  | 0 | 0.081 |  |  | 0.081 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-4566 | NC 903 | Lenoir | X | 2026-01-20 | 2 | SICP | NEUSE | 03020202 |  |  |  | 0 | 0.112 |  |  | 0.112 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-5713 | WILLOW ROAD | Guilford | X | 2026-01-20 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  | 0.123 |  | 0.123 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-4443 | US 19/US 23/US 25/ US 70 | Buncombe |  | 2026-01-20 | 13 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5826B | NC 109 | Montgomery | X | 2026-02-17 | 8 | SP | YADKIN | 03040104 | 200 |  |  | 200 |  |  |  | 0 | Division Review | 2022-11-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-4937 | I-95 | Johnston |  | 2026-01-20 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5130 | SR 1321 (AVENT FERRY ROAD) | Wake |  | 2026-01-20 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5976 | SR 1400 (CUMNOCK ROAD) | Lee |  | 2026-01-20 | 8 | SP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-6041 | I-40 | Catawba |  | 2026-01-20 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
B-6050 | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | JOHNSTON |  | 2026-01-20 | 4 | NICP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-02-13 |  | Projected-STIP
BR-0130 | I-40 | Burke |  | 2026-01-20 | 13 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2020-01-22 |  | Projected-STIP
U-4753 | SR 1556 (WAYNE MEMORIAL DRIVE) | Wayne |  | 2026-01-20 | 4 | NICP | NEUSE | 03020202 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-02-04 |  | Projected-STIP
B-6030 | SR 1351 (MATLOCK CREEK ROAD) | Macon |  | 2026-01-27 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
B-6033 | SR 1445 (LEE BUMGARNER ROAD) | Jackson |  | 2026-01-27 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Projected-STIP
R-3603A | NC 127 | Alexander | X | 2026-03-17 | 12 | CP | CATAWBA | 03050101 | 1000 |  |  | 1000 | 0.03 | 0.02 |  | 0.05 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5835 | SR 1306 (HICKS HOLLOW ROAD) | Avery |  | 2026-02-17 | 11 | NM | WATAUGA | 06010103 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
HB-0029 | SR 1179 (BRIDGE STREET) | Wake |  | 2026-02-17 | 5 | CP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
I-5708 | I-440 / US 1 | Wake | X | 2026-03-17 | 5 | CP | NEUSE | 03020201 | 320 |  |  | 320 | 0.109 |  |  | 0.109 | NES Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5959 | SR 1521 (KELLY DRIVE) | Lee | X | 2026-03-17 | 8 | SP | CAPE FEAR | 03030004 | 80 |  |  | 80 |  |  |  | 0 | GIS | 2019-01-25 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5518 | US 70 (GLENWOOD AVENUE) | Wake | X | 2026-04-21 | 5 | CP | NEUSE | 03020201 | 1549 |  |  | 1549 | 2.3 |  |  | 2.3 | PDEA Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5770B | SR 1009 (SOUTH MAIN STREET) | Randolph |  | 2026-03-17 | 8 | CP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5964 | US 64 (DAVIE AVENUE) | Iredell |  | 2026-03-17 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-2817 | SR 1700 (EVANS STREET/ OLD TAR ROAD) | Pitt | X | 2026-04-21 | 2 | NICP | NEUSE | 03020202 | 876 |  |  | 876 | 0.29 | 0.16 |  | 0.45 | Division Review | 2019-01-28 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-5753 | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | Hoke | X | 2026-04-21 | 8 | SICP | CAPE FEAR | 03030004 | 517 |  |  | 517 | 1 |  |  | 1 | NRTR | 2021-02-05 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5823 | NC 65 / NC 68 | Rockingham | X | 2026-05-19 | 7 | CP | ROANOKE | 03010103 | 783 |  |  | 783 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
P-5747 | NCRR NORFOLK SOUTHERN H LINE | Guilford |  | 2026-04-21 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Projected-STIP
R-5724B | US 15 / US 501 | Chatham |  | 2026-04-21 | 8 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5765 | NC 73 (SAM FURR ROAD) | Mecklenburg | X | 2026-05-19 | 10 | SP | CATAWBA | 03050101 | 340 |  |  | 340 | 0.17 |  |  | 0.17 | Merger Materials | 2018-06-06 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-5715 | I-77 | Mecklenburg | X | 2026-05-19 | 10 | SP | CATAWBA | 03050101 | 200 |  |  | 200 |  |  |  | 0 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-3415A | SR 1394 (POPLAR TENT ROAD) | Cabarrus | X | 2026-06-16 | 10 | SP | YADKIN | 03040105 | 915 |  |  | 915 | 0.06 |  |  | 0.06 | NES Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5721B | NC 73 | Mecklenburg |  | 2026-05-19 | 10 | SP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Merger Materials | 1999-01-01 |  | Projected-STIP
U-6034 | US 321 ALT | Caldwell |  | 2026-05-19 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
U-6138 | NC 279 (NORTH NEW HOPE ROAD) | GASTON |  | 2026-05-26 | 12 | SP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Projected-STIP
I-4759 | I-40 | Buncombe | X | 2026-06-16 | 13 | SM | FRENCH BROAD | 06010105 |  | 891 |  | 891 |  |  |  | 0 | Merger Materials | 2021-02-04 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5836 | US 601 | Surry | X | 2026-06-16 | 11 | CP | YADKIN | 03040101 |  | 500 |  | 500 |  |  |  | 0 | GIS | 2018-04-18 |  | Projected-STIP | NCDOT/DMS | Private bank credits for cool stream, cold stream and wetlands. DMS for warm stream credits.
R-5766C | NC 65 / NC 87 | Rockingham | X | 2026-06-16 | 7 | CP | ROANOKE | 03010103 | 407 |  |  | 407 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5798 | US 74 (ANDREW JACKSON HIGHWAY) | Anson | X | 2026-06-16 | 10 | SP | YADKIN | 03040201 | 309 |  |  | 309 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5917 | SR 1704 (FOURTEENTH STREET) | PITT | X | 2026-06-16 | 2 | NICP | Tar-Pamlico | 03020103 | 283 |  |  | 283 | 0.08 |  |  | 0.08 | Division Review | 2022-10-07 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5766A | NC 65 / NC 87 | ROCKINGHAM | X | 2026-06-16 | 7 | CP | ROANOKE | 03010103 | 260 |  |  | 260 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5962 | NC 16 BUSINESS | Lincoln | X | 2026-06-16 | 12 | SP | CATAWBA | 03050101 | 60 |  |  | 60 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-5716 | I-40 | Catawba |  | 2026-06-16 | 12 | CP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5792 | US 117 / NC 132 (COLLEGE ROAD) | New Hanover | X | 2026-06-16 | 3 | SOCP | CAPE FEAR | 03030007 |  |  |  | 0 | 0.75 |  |  | 0.75 | Division Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5766B | NC 65 / NC 87 | ROCKINGHAM |  | 2026-06-16 | 7 | CP | ROANOKE | 03010103 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
I-5707 | I-40 | Durham | X | 2026-06-16 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 | 0.006 |  |  | 0.006 | CE | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-2632AB | NC 73 | Mecklenburg | X | 2026-08-18 | 10 | SP | YADKIN | 03040105 | 409 |  |  | 409 | 0.02 |  |  | 0.02 | PDEA Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5832 | NC 88 | Ashe |  | 2026-06-16 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-04 |  | Projected-STIP
R-5858 | NC 24 | Carteret |  | 2026-06-16 | 2 | SOCP | WHITE OAK | 03020106 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP
HB-0035 | SR 1535 (PRICE ROAD) | Rockingham |  | 2026-07-21 | 7 | CP | ROANOKE | 03010103 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
U-2530A | NC 127 | Catawba |  | 2026-07-21 | 12 | CP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5717 | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | Camden | X | 2026-08-18 | 1 | NOCP | PASQUOTANK | 03010205 | 118 |  |  | 118 | 2.5 |  |  | 2.5 | Draft Permit Drawings | 2021-01-26 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
P-5730 | CLANTON ROAD | Mecklenburg |  | 2026-08-18 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Projected-STIP
U-5723 | US 74 | Union |  | 2026-08-18 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5893 | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | ROCKINGHAM |  | 2026-08-18 | 7 | CP | Roanoke | 03010103 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-6157 | SR 1130 (CAJAH MOUNTAIN ROAD) | Caldwell |  | 2026-08-18 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Projected-STIP
U-4712 | US 23 BUSINESS (SOUTH MAIN STREET) | Haywood | X | 2026-09-15 | 14 | SM | FRENCH BROAD | 06010106 |  |  | 194 | 194 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6163 | SR 3116 (MILLS GAP ROAD) | Buncombe |  | 2026-08-19 | 13 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-10-08 |  | Projected-STIP
U-6109 | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | Mecklenburg | X | 2026-09-15 | 10 | SP | CATAWBA | 03050103 | 152 |  |  | 152 |  |  |  | 0 | GIS | 2018-12-07 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5800 | US 64/ US 276 | Transylvania | X | 2026-10-20 | 14 | SM | FRENCH BROAD | 06010105 |  | 100 |  | 100 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
HB-0031 | THIRD STREET | Forsyth |  | 2026-09-15 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
U-5710 | US 74 (EASTWOOD ROAD) | NEW HANOVER |  | 2026-09-15 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-6049 | NC 225 (SOUTH MAIN STREET) | Henderson | X | 2026-10-20 | 14 | SM | FRENCH BROAD | 06010105 |  | 73 |  | 73 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5810 | US 17 | Martin | X | 2026-10-20 | 1 | NICP | ROANOKE | 03010107 | 66 |  |  | 66 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6065 | US 17 | Onslow | X | 2026-10-20 | 3 | SOCP | WHITE OAK | 03030001 | 60 |  |  | 60 | 0.3 |  |  | 0.3 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5961 | NC 274 (UNION ROAD) | Gaston | X | 2026-10-20 | 12 | SP | CATAWBA | 03050101 | 50 |  |  | 50 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5886 | SR 1170 (WHITE STREET) | HENDERSON | X | 2026-10-20 | 14 | SM | FRENCH BROAD | 06010105 |  | 35 |  | 35 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
HB-0020 | SR 1185 (CURTIS BRIDGE ROAD) | Wilkes |  | 2026-10-20 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
U-6006 | US 220 BUSINESS | Randolph | X | 2026-11-17 | 8 | CP | CAPE FEAR | 03030003 | 260 |  |  | 260 |  | 0.01 |  | 0.01 | MCDC | 2022-03-28 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5873 | US 74 | Polk |  | 2026-10-20 | 14 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | SPOT TSDS | 2018-08-08 |  | Projected-STIP
U-5717 | US 15 / US 501 | Durham |  | 2026-10-20 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
U-5911 | NC 48 | Nash |  | 2026-10-20 | 4 | NICP | TAR-PAMLICO | 03020101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-02-04 |  | Projected-STIP
B-5843 | SR 2402 (HOOVER ROAD) | Iredell |  | 2026-11-17 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6078 | NC 275 | Gaston | X | 2026-11-17 | 12 | SP | CATAWBA | 03050101 | 80 |  |  | 80 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6078 | NC 275 | Gaston | X | 2026-11-17 | 12 | SP | CATAWBA | 03050102 | 80 |  |  | 80 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6032 | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | Cabarrus | X | 2026-12-15 | 10 | SP | YADKIN | 03040105 | 148 |  |  | 148 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0038 | SR 1745 (BEND OF THE RIVER ROAD) | Nash |  | 2026-11-17 | 4 | NICP | TAR-PAMLICO | 03020101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
R-2555B | SR 5544 (WEST CATAWBA AVENUE) | MECKLENBURG |  | 2026-11-17 | 10 | SP | Catawba | 03050101 |  |  |  | 0 |  |  |  | 0 | Merger Materials | 1999-01-01 |  | Projected-STIP
I-5712 | I-40 / US 421 | Guilford | X | 2026-12-15 | 7 | CP | CAPE FEAR | 03030003 | 100 |  |  | 100 | 0.015 |  |  | 0.015 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5892 | US 220 (BATTLEGROUND AVENUE) | GUILFORD | X | 2026-12-15 | 7 | CP | CAPE FEAR | 03030002 | 100 |  |  | 100 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5830 | SR 1522 (DEERFIELD ROAD) | Watauga | X | 2026-12-15 | 11 | NM | NEW | 05050001 |  |  | 60 | 60 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0032 | SR 1004 (HUDSON CHAPEL ROAD) | Catawba |  | 2026-12-15 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
R-5878B | NEW ROUTE - WADESBORO BYPASS | Anson | X | 2027-01-19 | 10 | SP | YADKIN | 03040201 | 2891 |  |  | 2891 |  |  |  | 0 | GIS | 2018-12-07 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5907 | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | Jackson |  | 2026-12-15 | 14 | SM | Little Tennessee | 06010203 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
U-5998 | NC 42 | Johnston |  | 2026-12-15 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
HB-0036 | SIXTEENTH STREET | Forsyth |  | 2027-01-01 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0037 | SR 1679 (GOLD MINE ROAD) | Macon |  | 2027-01-01 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Projected-STIP
HB-0056 | SR 1514 | Caldwell |  | 2027-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0061 | SR 1574 | Caldwell |  | 2027-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0065 | SR 1170 | Wilkes |  | 2027-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0069 | US 421 BUSINESS | Wilkes |  | 2027-01-01 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
U-6017 | NC 54 (EAST HARDEN STREET) | Alamance |  | 2027-01-19 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6092 | DAVIDSON | Mecklenburg |  | 2027-01-19 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-10-24 |  | Projected-STIP
R-5878B | NEW ROUTE - WADESBORO BYPASS | Anson | X | 2027-01-19 | 10 | SP | YADKIN | 03040104 | 1567 |  |  | 1567 |  |  |  | 0 | GIS | 2018-12-07 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-5701 | I-40 / US 64 | Wake | X | 2027-01-19 | 5 | CP | NEUSE | 03020201 | 1399 |  |  | 1399 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-5308 | SR 1547 (FINCH FARM ROAD) | Randolph | X | 2027-01-19 | 8 | CP | YADKIN | 03040103 | 390 |  |  | 390 | 0.1 |  |  | 0.1 | Designs | 2022-10-10 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-4933 | NC 33 | Edgecombe |  | 2027-01-19 | 4 | NICP | TAR-PAMLICO | 03020101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
I-5703 | I-40 | WAKE | X | 2027-01-19 | 5 | CP | NEUSE | 03020201 | 300 |  |  | 300 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
B-5708 | NC 24 | Cumberland | X | 2027-01-19 | 6 | SICP | CAPE FEAR | 03030006 | 200 |  |  | 200 | 0.072 |  |  | 0.072 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5950 | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | Forsyth |  | 2027-01-19 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
P-5706 | NORFOLK SOUTHERN H LINE | Durham | X | 2027-01-19 | 5 | CP | CAPE FEAR | 03030002 | 150 |  |  | 150 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
B-5708 | NC 24 | Sampson | X | 2027-01-19 | 3 | SICP | CAPE FEAR | 03030006 |  |  |  | 0 | 0.02 |  |  | 0.02 | GIS | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-6011A | US 74 | ROBESON | X | 2027-01-19 | 6 | SICP | LUMBER | 03040203 |  |  |  | 0 |  |  |  | 0 | Division Review | 2020-09-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-5968 | I-540 | Wake | X | 2027-02-16 | 5 | CP | NEUSE | 03020201 | 992 |  |  | 992 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
R-5879 | US 13/US 17 | MARTIN |  | 2027-01-20 | 1 | NICP | ROANOKE | 03010107 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Projected-STIP
U-5815A | US 1 (SANDHILLS BOULEVARD) | Moore |  | 2027-01-26 | 8 | SP | LUMBER | 03040203 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5764 | US 74 | Union | X | 2027-03-16 | 10 | SP | YADKIN | 03040105 | 980 |  |  | 980 | 0.09 |  |  | 0.09 | Division Review | 2022-01-20 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6082 | SR 1308 (BELL FORK ROAD) | Onslow |  | 2027-02-18 | 3 | SOCP | White Oak | 03030001 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
B-4069 | SR 1326 | Cherokee | X | 2027-03-23 | 14 | SM | HIWASSEE | 06020002 |  |  | 100 | 100 | 0.1 |  |  | 0.1 | EAU Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5931 | US 74 | Union |  | 2027-03-16 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-01-20 |  | Projected-STIP
U-6110 | US 70 | Wayne |  | 2027-03-16 | 4 | NICP | Neuse | 03020202 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
U-6028 | SR 2467 (MALLARD CREEK ROAD) | Mecklenburg | X | 2027-04-20 | 10 | SP | YADKIN | 03040105 | 55 |  |  | 55 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5721A | NC 73 | Lincoln | X | 2027-05-18 | 12 | SP | CATAWBA | 03050101 | 2270 |  |  | 2270 | 0.41 |  |  | 0.41 | Merger Materials | 2018-05-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5701 | NC 53 | Pender |  | 2027-06-03 | 3 | SOCP | CAPE FEAR | 03030007 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
U-5766B | NC 160 | Mecklenburg | X | 2027-05-18 | 10 | SP | CATAWBA | 03050103 | 943 |  |  | 943 |  | 0.4 |  | 0.4 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5769A | NC 16 (PROVIDENCE ROAD SOUTH) | Union |  | 2027-06-15 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5769B | NC 16 (PROVIDENCE ROAD SOUTH) | Union |  | 2027-06-15 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-5950 | US 17 BUSINESS (MARINE BOULEVARD) | Onslow |  | 2027-06-15 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-5954 | NC 133 (CASTLE HAYNE ROAD) | New Hanover |  | 2027-06-15 | 3 | SOCP | CAPE FEAR | 03030007 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
R-2615 | US 421/US 321 | Watauga | X | 2027-06-15 | 11 | NM | WATAUGA | 06010103 |  |  | 4684 | 4684 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5971 | SR 1149 (ELK SPUR STREET) | Surry |  | 2027-07-20 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-01-04 |  | Projected-STIP
U-6059A | SR 2377 (OLD GREENSBORO ROAD NE) | Forsyth |  | 2027-08-25 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5356 | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | Guilford |  | 2027-10-19 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
B-5718 | PATTON AVENUE | Guilford |  | 2027-10-19 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-2307B | MCDONALD PARKWAY | CATAWBA | X | 2027-06-15 | 12 | CP | Catawba | 03050101 | 570 |  |  | 570 | 0.12 |  |  | 0.12 | NES Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5885A | NC 24 (WEST CORBETT AVENUE) | Onslow | X | 2027-06-17 | 3 | SOCP | WHITE OAK | 03020106 | 50 |  |  | 50 |  |  |  | 0 | GIS | 2019-02-15 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-2247EA | NEW ROUTE (FUTURE NC 452) | Forsyth | X | 2027-10-19 | 9 | CP | YADKIN | 03040101 | 6536 |  |  | 6536 | 0.57 |  |  | 0.57 | NES Review | 2018-11-13 |  | Projected-STIP | NCDOT | Potential Onsite Stream Mitigation being reviewed. Private bank credits for streams and wetlands
I-5974 | I-95 | Johnston | X | 2027-10-19 | 4 | NICP | NEUSE | 03020201 | 1311 |  |  | 1311 | 1.6 |  |  | 1.6 | Division Review | 2021-02-04 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-5934 | I-885 | Durham | X | 2027-10-19 | 5 | CP | CAPE FEAR | 03030002 | 559 |  |  | 559 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-6073 | FISHER ROAD | Cumberland | X | 2027-10-19 | 6 | SICP | CAPE FEAR | 03030004 | 56 |  |  | 56 | 0.1891 |  |  | 0.1891 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
HB-0041 | I-77 | Iredell |  | 2028-01-01 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | GIS | 2024-02-12 |  | Projected-STIP
HB-0044 | SR 1644 | Ashe |  | 2028-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0045 | SR 1609 | Ashe |  | 2028-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0048 | SR 1606 | Ashe |  | 2028-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0049 | SR 1602 | Ashe |  | 2028-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0050 | SR 1563 | Ashe |  | 2028-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
HB-0053 | SR 1126 | Ashe |  | 2028-01-01 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | GIS | 2023-09-06 |  | Projected-STIP
U-5101A | SR 1437 (SHAW ROAD) | Cumberland | X | 2027-11-16 | 6 | SICP | CAPE FEAR | 03030004 | 28 |  |  | 28 |  | 0.1821 |  | 0.1821 | GIS | 2019-10-11 |  | Projected-STIP | DMS | DMS to provide all mitigation.
B-5945 | NC 87 | Bladen |  | 2028-01-18 | 6 | SICP | CAPE FEAR | 03030005 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5909 | SR 1314 (EAST MAIN STREET) | Yadkin |  | 2028-02-15 | 11 | CP | Yadkin | 03040101 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP
U-5786 | SR 1508 (HICKORY TREE ROAD) | Davidson |  | 2028-02-15 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
R-5926 | US 158 / NC 86 | Caswell | X | 2027-11-16 | 7 | CP | ROANOKE | 03010104 | 10.25 |  |  | 10.25 |  |  |  | 0 | GIS | 2019-01-25 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5955B | NC 16 (BROOKSHIRE BOULEVARD) | Mecklenburg | X | 2028-01-01 | 10 | SP | CATAWBA | 03050103 | 1280 |  |  | 1280 |  |  |  | 0 | Division Review | 2022-08-30 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5736 | US 601 | Davie |  | 2028-04-18 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-31 |  | Projected-STIP
U-6161 | US 321 | CALDWELL | X | 2028-03-21 | 11 | NM | Catawba | 03050101 | 50 |  |  | 50 |  |  |  | 0 | GIS | 2019-02-15 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5905 | NC 89 (WEST PINE STREET) | Surry | X | 2028-03-21 | 11 | CP | YADKIN | 03040101 |  | 25 |  | 25 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
R-3403B | US 17 | Craven | X | 2028-05-16 | 2 | SOCP | NEUSE | 03020202 | 860 |  |  | 860 | 8.83 | 7.87 |  | 16.7 | Division Review | 2022-10-24 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-3618 | SR 1569 (CAREY ROAD EXTENSION) | Lenoir | X | 2028-05-16 | 2 | SICP | NEUSE | 03020202 | 626 |  |  | 626 | 1.0315 | 4.045 |  | 5.0765 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-2513A | US 17 | Craven | X | 2028-05-16 | 2 | SOCP | NEUSE | 03020202 | 280 |  |  | 280 | 1.65 |  |  | 1.65 | Division Review | 2019-01-28 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-3403B | US 17 | Craven | X | 2028-05-16 | 2 | SOCP | NEUSE | 03020204 |  |  |  | 0 | 3.12 | 8.05 |  | 11.17 | Division Review | 2022-10-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5936 | SR 1126 (ROPER NEWLAND ROAD) | Washington |  | 2028-06-20 | 1 | NOCP | PASQUOTANK | 03010205 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Projected-STIP
U-5731 | US 74 | New Hanover | X | 2028-05-16 | 3 | SOCP | CAPE FEAR | 03030005 |  |  |  | 0 | 2.04 |  | 0.75 | 2.79 | Draft Document | 2022-10-10 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-6047 | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | Buncombe | X | 2028-06-20 | 13 | SM | FRENCH BROAD | 06010105 |  | 281 |  | 281 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
R-5772 | SR 1001 (OAKWOODS ROAD) | WILKES | X | 2028-06-20 | 11 | NM | YADKIN | 03040101 |  | 80 |  | 80 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-5785 | SR 1708 (FIRETOWER ROAD) | Pitt | X | 2028-06-20 | 2 | NICP | TAR-PAMLICO | 03020103 | 60 |  |  | 60 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5940 | US 17 (HUGHES BOULEVARD) | Pasquotank | X | 2028-06-20 | 1 | NOCP | PASQUOTANK | 03010205 | 59 |  |  | 59 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-2523B | NC 279 | Gaston | X | 2028-06-20 | 12 | SP | CATAWBA | 03050102 | 56 |  |  | 56 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5870 | SR 1708 (FIRETOWER ROAD) | PITT | X | 2028-06-20 | 2 | NICP | Tar-Pamlico | 03020103 |  |  |  | 0 | 0.15 | 0.01 |  | 0.16 | Division Review | 2022-01-06 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5845 | SR 1009 (SOUTH CHURTON STREET) | Orange | X | 2028-07-18 | 7 | CP | NEUSE | 03020201 | 2320 |  |  | 2320 | 0.1 |  |  | 0.1 | EAU Review | 2018-02-01 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
R-5901 | NC 89 (WEST PINE STREET) | SURRY |  | 2028-07-20 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Projected-STIP
I-6061 | I-95 | Johnston |  | 2028-08-15 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Projected-STIP
U-5301 | US 64 | Wake | X | 2028-07-18 | 5 | CP | NEUSE | 03020201 | 535 |  |  | 535 | 0.2391 | 0.3877 |  | 0.6268 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-5974 | NC 68 | Guilford | X | 2028-07-18 | 7 | CP | CAPE FEAR | 03030003 | 472 |  |  | 472 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5864 | SR 1595 / SR 4053 (SURRETT DRIVE) | Randolph | X | 2028-08-15 | 8 | CP | YADKIN | 03040103 | 452 |  |  | 452 | 0.236 | 0.081 |  | 0.317 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-5962 | I-77 | Iredell |  | 2028-09-19 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-5864 | SR 1595 / SR 4053 (SURRETT DRIVE) | Guilford | X | 2028-08-15 | 7 | CP | CAPE FEAR | 03030003 | 206 |  |  | 206 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5927 | US 15 / US 501 | Moore | X | 2028-08-15 | 8 | SP | CAPE FEAR | 03030004 | 15.7 |  |  | 15.7 | 0.02865 | 0.0551 |  | 0.08375 | GIS | 2019-01-25 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-3431 | SR 1763 (MILLER BOULEVARD) | Craven | X | 2028-09-19 | 2 | SOCP | NEUSE | 03020204 | 600 |  |  | 600 | 0.3 | 0.3 |  | 0.6 | Division Review | 2022-10-07 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5716 | NC 24 | Onslow | X | 2028-09-19 | 3 | SOCP | WHITE OAK | 03030001 | 249 |  |  | 249 |  | 0.08 |  | 0.08 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5890 | SR 1162 (DABNEY DRIVE) | VANCE |  | 2028-09-19 | 5 | CP | Roanoke | 03010102 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Projected-STIP
U-5857 | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | Hoke | X | 2028-09-19 | 8 | SICP | CAPE FEAR | 03030004 | 170 |  |  | 170 | 0.313 |  |  | 0.313 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5739 | US 258/NC 24 (RICHLANDS HIGHWAY) | Onslow | X | 2028-09-19 | 3 | SOCP | WHITE OAK | 03030001 | 135 |  |  | 135 | 0.1 | 0.05 |  | 0.15 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-6203 | NC 210 | Johnston | X | 2028-09-19 | 4 | NICP | NEUSE | 03020201 | 28 |  |  | 28 | 0.2 |  |  | 0.2 | Division Review | 2019-01-25 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-2509AC | New location/connection of Independence Pointe Parkway | Mecklenburg | X | 2028-10-01 | 10 | SP | CATAWBA | 03050103 | 1976 |  |  | 1976 | 0.22 |  |  | 0.22 | EA Reevaluation | 2024-04-12 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-2307A | NC 150 | Catawba | X | 2028-10-17 | 12 | CP | CATAWBA | 03050101 | 1262 |  |  | 1032 | 1.52 |  |  | 1.52 | Merger CP3 Materials | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5906 | NC 268 | Wilkes | X | 2028-10-17 | 11 | NM | YADKIN | 03040101 |  | 150 |  | 150 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-6191 | NC 62 | Randolph | X | 2028-10-17 | 8 | CP | CAPE FEAR | 03030003 | 40 |  |  | 135 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5914 | NC 67 | Yadkin | X | 2028-10-17 | 11 | CP | YADKIN | 03040101 | 50 | 50 |  | 100 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
P-5736 | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | Wake |  | 2029-01-01 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Rail Review | 2024-02-14 |  | Projected-STIP
U-6191 | NC 62 | Randolph | X | 2028-10-17 | 8 | CP | YADKIN | 03040103 | 60 |  |  | 60 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-2901BA | NC 55 (WILLIAMS STREET) | Wake |  | 2029-01-01 | 5 | CP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 2024-02-12 |  | Projected-STIP
U-5729REG | US 421 | New Hanover |  | 2029-01-01 | 3 | SOCP | CAPE FEAR | 03030005 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
U-5729SW | US 421 | New Hanover |  | 2029-01-01 | 3 | SOCP | CAPE FEAR | 03030005 |  |  |  | 0 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP
R-5949 | US 258 | Edgecombe | X | 2028-11-21 | 4 | NICP | TAR-PAMLICO | 03020103 | 29 |  |  | 29 |  | 0.2235 |  | 0.2235 | GIS | 2019-01-25 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-3338C | SR 1175 (KERR AVENUE) | New Hanover | X | 2028-12-19 | 3 | SOCP | CAPE FEAR | 03030007 | 312 |  |  | 312 | 0.36 |  |  | 0.36 | Draft Permit Drawings | 2022-10-10 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5860A | US 52 | Rowan | X | 2029-01-01 | 9 | CP | YADKIN | 03040103 | 137 |  |  | 137 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-3410 | NC 42 | Johnston | X | 2029-01-16 | 4 | NICP | NEUSE | 03020201 | 1893 |  |  | 1893 | 0.96 |  |  | 0.96 | Division Review | 2021-02-04 |  | Projected-STIP | NCDOT | Private bank credits for streams and wetlands.
U-6008 | SR 2085 (BRYAN BOULEVARD) | Guilford |  | 2029-02-01 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-4403C | US 401 | Cumberland | X | 2029-01-16 | 6 | SICP | CAPE FEAR | 03030004 | 428 |  |  | 428 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-4729B | I-26 | Polk | X | 2029-01-16 | 14 | SP | BROAD | 03050105 |  | 200 |  | 200 |  |  |  | 0 | Division Review | 2019-01-28 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-4739 | SR 3556 (AMBOYROAD/ MEADOW ROAD) | Buncombe | X | 2029-01-16 | 13 | SM | FRENCH BROAD | 06010105 |  | 56 | 113 | 169 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-2509AA | Grade Separation at Sharon Forest Drive and Interchange at Village Lake Drive. | Mecklenburg | X | 2029-03-01 | 10 | SP | CATAWBA | 03050103 | 857 |  |  | 857 | 1.41 |  |  | 1.41 | EA Reevaluation | 2024-04-12 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-2509AD | New location/ connection of Matthews-Mint Hill Road Area. | Mecklenburg | X | 2029-03-01 | 10 | SP | CATAWBA | 03050103 | 135 |  |  | 135 | 0 |  |  | 0 | EA Reevaluation | 2024-04-12 |  | Projected-STIP | DMS | DMS to provide all mitigation.
I-6062 | I-95 | Johnston |  | 2029-04-17 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Projected-STIP
R-5853 | US 13 | Wayne | X | 2029-03-20 | 4 | NICP | NEUSE | 03020203 | 100 |  |  | 100 | 0.2 |  |  | 0.2 | Division Review | 2019-01-28 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-4007E | NC 53 | Onslow |  | 2029-05-15 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Projected-STIP
R-5853 | US 13 | Wayne | X | 2029-03-20 | 4 | NICP | NEUSE | 03020202 | 100 |  |  | 100 | 0.2 |  |  | 0.2 | Division Review | 2019-01-28 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-2509B | US 74 | Mecklenburg | X | 2029-04-17 | 10 | SP | CATAWBA | 03050103 | 2010 |  |  | 2010 | 1.29 |  |  | 1.29 | Merger Materials | 2020-09-24 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5816 | SR 1305 (OATES ROAD - MIDNIGHT LANE) | Iredell |  | 2029-05-15 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP
U-6103 | US 74 (INDEPENDENCE BOULEVARD) | Mecklenburg |  | 2029-04-17 | 10 | SP | CATAWBA | 03050103 | [7 empty] | 0 | GIS | 2024-04-14 |  | Projected-STIP
R-5869B | US 17 | PERQUIMANS | X | 2029-04-17 | 1 | NOCP | Pasquotank | 03010205 |  |  |  | 0 |  | 0.9 |  | 0.9 | GIS | 2019-02-19 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-5508 | NC 24 (LEJEUNE BOULEVARD) | Onslow | X | 2029-05-15 | 3 | SOCP | WHITE OAK | 03030001 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5736 | NC 53 (WESTERN BOULEVARD) | Onslow | X | 2029-05-15 | 3 | SOCP | WHITE OAK | 03030001 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 2018-02-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-2509AB | Construction of new interchanges and extensions in the Sardis and Sam Newell Road areas. | Mecklenburg | X | 2029-06-01 | 10 | SP | CATAWBA | 03050103 | 1032 |  |  | 1032 | 0.03 |  |  | 0.03 | EA Reevaluation | 2024-04-12 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-0204E | US 221 | McDowell | X | 2029-06-19 | 13 | NM | CATAWBA | 03050101 | 2111 |  |  | 2111 | 0.02 |  |  | 0.02 | Merger CP4 | 2021-02-04 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5311B | US 13/NC 11 | Hertford | X | 2029-06-19 | 1 | NOCP | CHOWAN | 03010203 | 799 |  |  | 799 |  | 45 |  | 45 | Merger Materials | 2018-11-13 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5311B | US 13/NC 11 | Hertford | X | 2029-06-19 | 1 | NOCP | CHOWAN | 03010204 | 327 |  |  | 327 |  | 49.4 |  | 49.4 | Merger Materials | 2018-11-13 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-3430C | SR 1001 (CONNELLY SPRINGS ROAD) | Caldwell | X | 2029-06-19 | 11 | NM | CATAWBA | 03050101 | 319 |  |  | 319 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-4902C | US 17 BUSINESS (MARKET STREET) | New Hanover | X | 2029-06-19 | 3 | SOCP | CAPE FEAR | 03030007 | 238 |  |  | 238 | 2.8 |  |  | 2.8 | Division Review | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5991 | NC 43 | Pitt | X | 2029-06-19 | 2 | NICP | TAR-PAMLICO | 03020103 | 171 |  |  | 171 |  |  |  | 0 | GIS | 1999-01-01 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5839BA | NC 28 | Graham | X | 2029-06-19 | 14 | SM | LITTLE TENNESSEE | 06010204 |  |  | 138 | 138 |  |  |  | 0 | GIS | 2020-01-22 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.
U-5735 | US 17 (WILMINGTON HIGHWAY) | Onslow | X | 2029-06-19 | 3 | SOCP | WHITE OAK | 03030001 | 50 |  |  | 50 | 0.14 | 2.38 |  | 2.52 | Draft Document | 2022-10-10 |  | Projected-STIP | DMS | DMS to provide all mitigation.
U-5836 | NC 181 | Burke | X | 2029-06-19 | 13 | NM | CATAWBA | 03050101 | 50 |  |  | 50 | 0.05 |  |  | 0.05 | Division Review | 2021-02-04 |  | Projected-STIP | DMS | DMS to provide all mitigation.
R-5839BA | NC 28 | Swain | X | 2029-06-19 | 14 | SM | LITTLE TENNESSEE | 06010204 |  |  | 33 | 33 |  |  |  | 0 | GIS | 2020-01-22 |  | Projected-STIP | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits.