## 2026_NCDOT_MitOrder
PROJECT ID | Alt ID | Route | County | Impacts | Let Date (as of 2/24/26) | Division | Ecoregion | River Basin | CU | Warm Stream | Cool Stream | Cold Stream | Total Stream | Riparian Wetland | Non-Riparian Wetland | Coastal Marsh Wetland | Total Wetland | Source | Source Date | QA / Comments | STIP Status | Mitigation Source | Note to DMS | 2025 YEAR Final List | 2025_List Let Date | Let Date change
U-5964 |  | US 64 (DAVIE AVENUE) | Iredell | NO | 2026-03-17 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-03-17 | no change
U-5302 |  | US 401 | Wake | NO | 2026-03-17 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-18 | No mitigable impacts | Delivery |  |  | DMS_List2025 | 2025-07-15 | pushed out
HL-0013 |  | 9TH STREET | Buncombe | YES | 2026-03-18 | 13 | SM | FRENCH BROAD | 06010105 |  |  | 56 | 56 | 0.05 |  |  | 0.05 | GIS | 2026-02-25 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-03-18 | no change
U-5730 |  | US 13 (MEMORIAL DRIVE) | Pitt | NO | 2026-04-15 | 2 | NICP | TAR-PAMLICO | 03020103 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Delivery |  |  |  |  | no change
51407 | 51407 | WBS 51407 Mimosa Street sidewalk | ROWAN | YES | 2026-04-16 | 9 | CP | Yadkin | 03040102 | 60 |  |  | 60 |  |  |  | 0 | Division Review | 2026-02-15 | updated 2026 (Atlas GIS, post NEPA/SEPA) |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-09-17 | moved in
HB-0048 |  | SR 1606 | Ashe | NO | 2026-04-16 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | permit | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2025-10-16 | pushed out
HB-0051 |  | SR 1159 | Ashe | NO | 2026-04-21 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | permit | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-01-20 | pushed out
U-4753 |  | SR 1556 (WAYNE MEMORIAL DRIVE) | Wayne | NO | 2026-04-21 | 4 | NICP | NEUSE | 03020202 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-02-04 |  | Delivery |  |  | DMS_List2025 | 2025-12-16 | pushed out
W-5704E |  | SR 1700 (COVERED BRIDGE ROAD) | Johnston | NO | 2026-04-28 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2020-01-23 |  | Delivery |  |  | DMS_List2025 | 2025-06-24 | pushed out
U-5945 |  | WILSON | Wilson | NO | 2026-05-19 | 4 | NICP | NEUSE | 03020203 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Delivery |  |  |  | 2026-05-19 | no change
B-6051 |  | US 29 / US 74 | Gaston | YES | 2026-05-19 | 12 | SP | Catawba | 03050101 | 440 |  |  | 440 |  | 0.289 |  | 0.289 | Permit Application | 2026-02-04 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-01-20 | pushed out
B-6047 |  | SR 2125 (HARRIS HENRIETTA ROAD) | Rutherford | YES | 2026-06-16 | 13 | SP | BROAD | 03050105 |  |  |  | 0 | 0.003 |  |  | 0.003 | GIS | 2019-10-11 |  | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-06-16 | no change
B-5995 |  | SR 1302 (JANIERO ROAD) | Pamlico | NO | 2026-06-16 | 2 | SOCP | NEUSE | 03020204 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Delivery |  |  |  | 2026-06-16 | no change
HE-0016 |  | New Route | Brunswick | YES | 2026-06-16 | 3 | SOCP | Cape Fear | 03030005 | 160 |  |  | 160 |  | 5.67 |  | 5.67 | Env Permit SAW | 2025-05-22 | Updated 2026-This is an industrial park, NCDOT is not on the hook for any mitigation. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-06-16 | no change
R-5858 |  | NC 24 | Carteret | NO | 2026-06-16 | 2 | SOCP | WHITE OAK | 03020106 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-01-28 |  | Delivery |  |  | Mitigation letter | 2026-06-16 | no change
U-5711 |  | SR 1712 (Pineview Street) | Randolph | YES | 2026-06-24 | 8 | CP | Cape Fear | 03030003 | 121 |  |  | 121 | 0.032996 | 0.032996 |  | 0.065992 | GIS | 2026-02-04 | New- tool did not pick up | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2025-10-21 | pushed out
B-5920 |  | SR 1216 (Steel Bridge Road) | Haywood | NO | 2026-07-14 | 14 | SM | French Broad | 06010106 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-19 | Proposed impacts will not require mitigation | Delivery |  |  |  | 2026-07-14 | no change
HB-0035 |  | SR 1535 (PRICE ROAD) | Rockingham | NO | 2026-07-21 | 7 | CP | ROANOKE | 03010103 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2026-07-21 | no change
I-5716 |  | I-40 | Catawba | NO | 2026-07-21 | 12 | CP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-24 | no impacts 2026 | Delivery |  |  | DMS_List2025 | 2026-06-16 | pushed out
R-5724B |  | US 15 / US 501 | Chatham | NO | 2026-07-21 | 8 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-04-21 | pushed out
U-4700CA |  | US 321 | Caldwell | NO | 2026-07-21 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | permit | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2025-08-19 | pushed out
P-5726A |  | NORFOLK SOUTHERN | ROWAN | YES | 2026-07-22 | 9 | CP | YADKIN | 03040103 | 132 |  |  | 132 |  |  |  | 0 | (3EN2) Apply for Permits | 2025-02-11 | This is updated based on the permit received in 2021. The permit verification is currently out of date, but I will contact the USACE and NC DEQ about getting them reissued. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2025-07-23 | pushed out
U-5950 |  | US 17 BUSINESS (MARINE BOULEVARD) | Onslow | NO | 2026-08-06 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-23 | 2026- No mitigation required/ impacts | Delivery |  |  | DMS_List2025 | 2026-08-06 | no change
B-5921 |  | SR 1120 (Cedar Creek Road) | Jackson | NO | 2026-08-11 | 14 | SM | Little Tennessee | 06010203 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-19 | Proposed impacts will not require mitigation | Delivery |  |  |  | 2026-08-11 | no change
I-6011A |  | US 74 | Columbus | NO | 2026-08-18 | 6 | SICP | LUMBER | 03040206 |  |  |  | 0 |  |  |  | 0 | CE | 2024-03-06 | no impacts 2026 | Delivery |  |  | DMS_List2025 | 2027-01-19 | moved in
I-6011A |  | US 74 | ROBESON | NO | 2026-08-18 | 6 | SICP | LUMBER | 03040203 |  |  |  | 0 |  |  |  | 0 | CE | 2024-03-06 |  | Delivery |  |  | DMS_List2025 | 2027-01-19 | moved in
U-5810 |  | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | Watauga | YES | 2026-08-18 | 11 | NM | NEW | 05050001 |  |  | 472 | 472 | 0.02 |  |  | 0.02 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-08-18 | no change
HB-0046 |  | SR 1105 | Ashe | YES | 2026-08-20 | 11 | NM | NEW | 05050001 |  |  | 13 | 13 |  | 0.02 |  | 0.02 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-08-20 | no change
HB-0052 |  | SR 1104 | Ashe | YES | 2026-08-20 | 11 | NM | NEW | 05050001 |  |  | 21 | 21 |  |  |  | 0 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-08-20 | no change
HB-0055 |  | SR 1326 | Avery | YES | 2026-08-20 | 11 | NM | WATAUGA | 06010103 |  |  | 30 | 30 |  | 0.25 |  | 0.25 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2026-08-20 | no change
HB-0057 |  | SR 1356 | Caldwell | NO | 2026-08-20 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0058 |  | SR 1356 | Caldwell | NO | 2026-08-20 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0059 |  | SR 1356 | Caldwell | NO | 2026-08-20 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0060 |  | SR 1356 | Caldwell | NO | 2026-08-20 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-23 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0062 |  | SR 1594 | Watauga | YES | 2026-08-20 | 11 | NM | WATAUGA | 06010103 |  |  | 180 | 180 |  |  |  | 0 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2026-08-20 | no change
HB-0063 |  | SR 1559 | Wilkes | NO | 2026-08-20 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0064 |  | SR 1567 | Wilkes | NO | 2026-08-20 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0066 |  | SR 1355 | Wilkes | NO | 2026-08-20 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | CFI Plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
HB-0067 |  | SR 1433 | Alleghany | NO | 2026-08-20 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | CFI plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-08-20 | no change
B-4676A |  | SR 1001 (Oakwoods Road) | Wilkes | YES | 2026-09-15 | 11 | NM | Yadkin | 03040101 |  | 106.9158 |  | 106.9158 |  |  |  | 0 | GIS | 2026-02-04 | updated 2026-permit drawings avialable soon | Delivery | NCDOT | Private bank credits for streams and wetlands. |  | 2026-09-15 | no change
I-4409A |  | I-40 | Buncombe | YES | 2026-09-15 | 13 | SM | French Broad | 06010105 |  |  | 660.3224 | 660.3224 |  |  |  | 0 | GIS | 2026-02-04 | New | Delivery | DMS | DMS to provide all mitigation. |  | 2026-09-15 | no change
R-5100B |  | SR 1109 (WILLIAMSON ROAD) | Iredell | NO | 2026-09-15 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-09-15 | no change
R-5717B |  | SR 1224 (OLD SWAMP ROAD) | Camden | NO | 2026-09-15 | 1 | NOCP | PASQUOTANK | 03010205 |  |  |  | 0 |  |  |  | 0 | GIS | 2024-02-12 |  | Delivery |  |  | DMS_List2025 | 2026-09-15 | no change
U-5834 |  | SR 3116 (MILLS GAP ROAD) | Buncombe | YES | 2026-09-15 | 13 | SM | FRENCH BROAD | 06010105 |  |  | 750 | 750 | 0.12 |  |  | 0.12 | Division Review | 2021-02-04 | requested update-No new records in SharePoint, 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-09-15 | no change
U-5728 |  | US 17 BUSINESS (MARINE BOULEVARD) | Onslow | NO | 2026-09-15 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-23 | 2026- No mitigation required/ impacts | Delivery |  |  | DMS_List2025 | 2026-07-21 | pushed out
HB-0044 |  | SR 1644 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | CFI plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0045 |  | SR 1609 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0049 |  | SR 1602 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | ROW plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0050 |  | SR 1563 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0053 |  | SR 1126 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | CFI plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0054 |  | SR 1222 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0056 |  | SR 1514 | Caldwell | NO | 2026-09-17 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-09-17 | no change
HB-0061 |  | SR 1574 | Caldwell | YES | 2026-09-17 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  | 0.25 |  | 0.25 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2026-09-17 | no change
HB-0065 |  | SR 1170 | Wilkes | YES | 2026-09-17 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  | 0.02 |  | 0.02 | CFI Plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2026-09-17 | no change
HB-0043 |  | SR 1523 | Ashe | YES | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  | 40 | 40 |  |  |  | 0 | CFI Plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2025-10-16 | pushed out
HB-0068 |  | SR 1527 | Ashe | NO | 2026-09-17 | 11 | NM | NEW | 05050001 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2025-09-04 | pushed out
I-4759A |  | I-40; SR 1228 (Liberty Road) | Buncombe | YES | 2026-10-07 | 13 | SM | French Broad | 06010105 |  | 1289.7103 |  | 1289.7103 |  |  |  | 0 | GIS | 2026-02-04 | Inactive - shelved - Waiting on reply | Delivery | DMS | DMS to provide all mitigation. |  | 2026-10-07 | no change
HB-0020 |  | SR 1185 (CURTIS BRIDGE ROAD) | Wilkes | YES | 2026-10-20 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 | 0.15 |  |  | 0.15 | Permit plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2026-10-20 | no change
HB-0037 |  | SR 1679 (GOLD MINE ROAD) | Macon | NO | 2026-11-17 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2026-11-17 | no change
HB-0038 |  | SR 1745 (BEND OF THE RIVER ROAD) | Nash | NO | 2026-11-17 | 4 | NICP | TAR-PAMLICO | 03020101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2026-11-17 | no change
I-2513AC |  | I-26 / I-240 | Buncombe | YES | 2026-11-17 | 13 | SM | French Broad | 06010105 |  | 3312 |  | 3312 | 2.24 |  |  | 2.24 | MRTF | 2026-02-11 | Permitted together with I-2513 AA, AB, & AC (asking 2/19/26) | Delivery | DMS | DMS to provide all mitigation. |  | 2026-11-17 | no change
U-6163 |  | SR 3116 (MILLS GAP ROAD) | Buncombe | NO | 2026-11-17 | 13 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2019-10-08 |  | Delivery |  |  | DMS_List2025 | 2026-11-17 | no change
P-5709 |  | NORFOLK SOUTHERN H LINE | GUILFORD | NO | 2026-11-17 | 7 | CP | Cape Fear | 03030002 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2025-10-21 | pushed out
HB-0069 |  | US 421 BUSINESS | Wilkes | NO | 2026-12-15 | 11 | NM | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Permit plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2027-09-21 | moved in
I-5701 |  | I-40 / US 64 | Wake | YES | 2026-12-15 | 5 | CP | NEUSE | 03020201 | 1290 |  |  | 1290 | 0.307 |  |  | 0.307 | (3EN2) Apply for Permits | 2025-11-24 05:00 | submitting to Alternative Design Unit, No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2027-01-19 | moved in
I-5703 |  | I-40 | WAKE | YES | 2026-12-15 | 5 | CP | NEUSE | 03020201 | 1386 |  |  | 1386 | 0.718 |  |  | 0.718 | (3EN2) Apply for Permits | 2025-11-24 05:00 | submitting to Alternative Design Unit, No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2027-01-19 | moved in
B-5876 |  | US 74 | Rutherford | NO | 2026-12-15 | 13 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-12-15 | no change
U-3422B |  | SR 1003 (Camden Road) | Cumberland | YES | 2026-12-15 | 6 | SICP | Cape Fear | 03030004 | 254 |  |  | 254 | 0.32 |  |  | 0.32 | Division Review | 2026-02-25 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. |  | 2026-12-15 | no change
R-5826B |  | NC 109 | Montgomery | YES | 2026-12-15 | 8 | SP | YADKIN | 03040104 | 65 |  |  | 65 | 0.02 |  |  | 0.02 | MCDC | 2022-05-18 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-02-17 | pushed out
U-6014 |  | SR 1716 (GRAHAM- HOPEDALE ROAD) | Alamance | NO | 2027-02-16 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 | no impact updates 2026 | Delivery |  |  | DMS_List2025 | 2026-08-18 | pushed out
B-6048 |  | SR 1812 (DIGGS ROAD) | Anson | YES | 2027-02-17 | 10 | SP | YADKIN | 03040201 | 40 |  |  | 40 |  |  |  | 0 | NRTM/Division Review | 2026-02-01 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-02-17 | no change
U-5761 |  | NC 3 (DALE EARNHARDT BOULEVARD) | Cabarrus | NO | 2027-03-16 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 | No update available 2026 | Delivery |  |  | DMS_List2025 | 2027-03-16 | no change
U-5844 |  | NC 62 | Alamance | NO | 2027-03-16 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2027-03-16 | no change
U-6110 |  | US 70 | Wayne | NO | 2027-03-16 | 4 | NICP | Neuse | 03020202 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  | DMS_List2025 | 2027-03-16 | no change
B-4069 |  | SR 1326 | Cherokee | YES | 2027-03-23 | 14 | SM | HIWASSEE | 06020002 |  |  | 120 | 120 |  |  |  | 0 | Permit Design | 2026-01-01 | Final permit plans depict 120’ culvert. Update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-03-23 | no change
BP9-C002 | BP9.C002.1 |  | DAVIE | YES | 2027-03-24 | 9 | CP | Yadkin | 03040101 | 100 |  |  | 100 |  |  |  | 0 | Division Review | 2026-02-15 | update 2026 add- 100’ warm stream, atlas GIS |  | NCDOT | Private bank credits for streams and wetlands. |  | 0 | pushed out
BP9-R008 | BP9.R008.1 |  | DAVIE | YES | 2027-04-14 | 9 | CP | Yadkin | 03040102 | 106 |  |  | 106 |  |  |  | 0 | Division Review | 2026-02-15 | update 2026 add- 106’ warm stream, permit plans, pre-permit application |  | DMS | DMS to provide all mitigation. |  | 0 | pushed out
HL-0006 |  | US 401 | Wake | YES | 2027-04-20 | 5 | CP | Neuse | 03020201 | 1729 |  |  | 1729 | 0.114 | 4.0927 |  | 4.2067 | Permit Drawings and Permit Application/DMS Acceptance Letter | 2026-02-04 | Individual 404 and Water Quality Certification 6965 and Buffer Authorization already obtained. | Delivery | NCDOT | Private bank credits for streams and wetlands. |  | 2027-01-19 | pushed out
U-5911 |  | NC 48 | Nash | NO | 2027-04-20 | 4 | NICP | TAR-PAMLICO | 03020101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-02-04 |  | Delivery |  |  | DMS_List2025 | 2026-10-20 | pushed out
R-5959 |  | SR 1521 (KELLY DRIVE) | Lee | YES | 2027-04-20 | 8 | SP | CAPE FEAR | 03030004 | 213 |  |  | 213 | 0.1 |  |  | 0.1 | Preliminary Plans | 2025-02-28 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-06-16 | pushed out
P-5725 |  | KANNAPOLIS | Cabarrus | NO | 2027-04-20 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2022-10-05 |  | Delivery |  |  | DMS_List2025 | 2025-10-21 | pushed out
R-5899 |  | NC 210 | PENDER | YES | 2027-05-18 | 3 | SOCP | WHITE OAK | 03030001 | 60 |  |  | 60 | 0.1 |  |  | 0.1 | 65Z% Design Plans | 2026-02-23 | 2026 update - Based on 65% Plans | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-03-18 | pushed out
U-5747B |  | NC 54 | Wake | NO | 2027-05-26 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-18 | No update available 2026 | Delivery |  |  |  | 0 | pushed out
BP9-C001 | BP9.C001.1 |  | DAVIE | YES | 2027-06-03 | 9 | CP | Yadkin | 03040102 | 70 |  |  | 70 |  |  |  | 0 | Division Review | 2026-02-15 | update 2026 -70’ warm stream, atlas GIS |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-06-03 | no change
R-5701 |  | NC 53 | Pender | NO | 2027-06-15 | 3 | SOCP | CAPE FEAR | 03030007 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-23 | 2026- No mitigation required/ impacts | Delivery |  |  |  | 2027-06-15 | no change
B-5925 |  | SR 1548 (Old Highway 64) | Cherokee | NO | 2027-06-15 | 14 | SM | Hiwassee | 06020002 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-19 | Proposed impacts will not require mitigation | Delivery |  |  |  | 2027-06-15 | no change
HB-0039 |  | US 17 / US 76 / US 421 | New Hanover | YES | 2027-06-15 | 3 | SOCP | Cape Fear | 03030005 | 0 |  |  | 0 | 10.4 |  |  | 10.4 | Division Review | 2026-02-04 | update 2026 -Based off CP2; slope stake + 40 ft., this # is for Alt 2, Alt 1 wetland impact is 1.1 which is movable alt. CP3 has not occurred. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-06-15 | no change
I-5707 |  | I-40 | Durham | NO | 2027-06-15 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | Permit Drawings | 2022-07-10 | No update available 2026 | Delivery |  |  | DMS_List2025 | 2027-06-15 | no change
R-5772 |  | SR 1001 (OAKWOODS ROAD) | WILKES | YES | 2027-06-15 | 11 | NM | Yadkin | 03040101 |  | 20 |  | 20 |  |  |  | 0 | Division review | 2026-02-23 | reduced, may end up zero | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2027-01-01 | pushed out
R-2822BB |  | NC143 | Graham | YES | 2027-06-17 | 14 | SM | Little Tennessee | 06010204 |  |  | 150 | 150 |  |  |  | 0 | GIS | 2025-02-06 | Update 2026 - TBD Permit Plans are not complete | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2027-06-17 | no change
R-5885A |  | NC 24 (WEST CORBETT AVENUE) | Onslow | YES | 2027-07-20 | 3 | SOCP | WHITE OAK | 03020106 | 30 |  |  | 30 |  |  |  | 0 | Draft Permit Drawings | 2025-01-01 | update 2026--No mitigation required; Permit Drawings | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-07-18 | moved in
R-5721B |  | NC 73 | Mecklenburg | NO | 2027-07-20 | 10 | SP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | Merger Materials | 1999-01-01 |  | Delivery |  |  |  | 2027-07-20 | no change
BR-0040 |  | NC 9 | Polk | YES | 2027-07-20 | 14 | SP | Broad | 03050105 |  | 89 |  | 89 | 0.01 |  |  | 0.01 | Permit Drawing | 2025-11-01 | Updated 2026 |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-01-19 | pushed out
B-5950 |  | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | Forsyth | NO | 2027-07-20 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | (2EP1) Advance NEPA/SEPA Doc | 2026-02-18 | No mitigable impacts | Delivery |  |  | DMS_List2025 | 2026-06-16 | pushed out
U-4900 |  | NC 210 (MURCHISON ROAD) | Cumberland | NO | 2027-07-20 | 6 | SICP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-05-19 | pushed out
B-6036 |  | SR 1737 (CANEY FORK ROAD) | Jackson | NO | 2027-08-17 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Delivery |  |  | DMS_List2025 | 2027-08-17 | no change
U-5821 |  | NC 279 (NEW HOPE ROAD) | Gaston | NO | 2027-08-17 | 12 | SP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2027-08-17 | no change
U-6006 |  | US 220 BUSINESS | Randolph | YES | 2027-08-17 | 8 | CP | CAPE FEAR | 03030003 | 260 |  |  | 260 |  | 0.01 |  | 0.01 | MCDC | 2022-03-28 | no change 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-02-16 | pushed out
U-6086 |  | NC 51 | Mecklenburg | NO | 2027-08-17 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | ROW Plans | 2026-02-01 | updated 2026 | Delivery |  |  | DMS_List2025 | 2026-12-15 | pushed out
U-5998 |  | NC 42 | Johnston | NO | 2027-09-21 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  | DMS_List2025 | 2027-09-21 | no change
HL-0135 |  | SR 1315 (New Town Road) | Union | NO | 2027-09-21 | 10 | SP | Catawba | 03050103 |  |  |  | 0 |  |  |  | 0 | CE | 2025-05-07 | updated 2026 | Delivery |  |  | DMS_List2025 | 2027-09-21 | no change
HB-0036 |  | SIXTEENTH STREET | Forsyth | NO | 2027-09-21 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | (2EP1) Advance NEPA/SEPA Doc | 2026-02-18 | No mitigable impacts | Delivery |  |  | DMS_List2025 | 2027-09-21 | no change
U-5710 |  | US 74 (EASTWOOD ROAD) | NEW HANOVER | YES | 2027-09-21 | 3 | SOCP | WHITE OAK | 03030001 | 40 |  |  | 40 |  |  |  | 0 | 65% Plans | 2026-02-01 | 2026 update - Based on 65% Plans | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-05-19 | pushed out
U-5817 |  | SR 1246 (FAIRVIEW ROAD) | Iredell | YES | 2027-09-21 | 12 | CP | CATAWBA | 03050101 | 226 |  |  | 226 | 0.02 |  |  | 0.02 | Permit Drawings | 2020-05-08 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2025-12-16 | pushed out
U-5709 |  | SR 1237 (CARTHAGE STREET) | Lee | YES | 2027-10-19 | 8 | SP | CAPE FEAR | 03030003 | 350 |  |  | 350 | 0.051 |  |  | 0.051 | ROW Plans | 2024-04-02 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. |  | 2027-10-19 | no change
I-5990 |  | I-40 | Burke | YES | 2027-10-19 | 13 | NM | CATAWBA | 03050102 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 2022-08-30 | 3/11/25 -Design change, new let date | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-10-19 | no change
BR-0145 |  | NC 208 | Madison | YES | 2027-10-19 | 13 | NM | French Broad | 06010105 |  |  | 329.2571 | 329.2571 |  |  |  | 0 | GIS | 2026-02-04 | New |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-10-19 | no change
HB-0026 |  | SR 1533 (EVERETT ROAD) | Transylvania | YES | 2027-10-19 | 14 | SM | FRENCH BROAD | 06010105 |  |  |  | 0 |  | 0.0074 |  | 0.0074 | Division Review | 2026-02-23 | Permit plans are not complete - update 2026 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2027-10-19 | no change
U-2509EA |  | SR 3156 (MARGARET WALLACE ROAD) | Mecklenburg | NO | 2027-10-19 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 |  |  | No update available 2026 | Delivery |  |  | DMS_List2025 | 2027-10-19 | no change
U-5308 |  | SR 1547 (FINCH FARM ROAD) | Randolph | YES | 2027-10-19 | 8 | CP | YADKIN | 03040103 | 290 |  |  | 290 | 0.076 |  |  | 0.076 | ROW Plans | 2025-03-06 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-03-16 | pushed out
U-6117 |  | VARIOUS | Wake | NO | 2027-10-19 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-18 | Resources in the study area but unsure of impacts at this time | Delivery |  |  | DMS_List2025 | 2027-03-16 | pushed out
R-5853 |  | US 13 | Wayne | YES | 2027-10-19 | 4 | NICP | NEUSE | 03020202 | 62 |  |  | 62 |  |  |  | 0 | Roadway & Drainage Plans | 2025-02-27 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-08-18 | pushed out
R-5853 |  | US 13 | Wayne | YES | 2027-10-20 | 4 | NICP | NEUSE | 03020203 | 266 |  |  | 266 | 0.22 |  |  | 0.22 | Roadway & Drainage Plans | 2025-02-27 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. |  | 2027-10-20 | no change
R-2632AB |  | NC 73 | Mecklenburg | YES | 2027-11-16 | 10 | SP | YADKIN | 03040105 | 735 |  |  | 735 | 0.02 |  |  | 0.02 | Draft Project Permit Drawing | 2025-03-19 | Stream impacts increased/wetland decreased- update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-11-16 | no change
B-5376 |  | SR 1681 (Old Camden Road) | Union | YES | 2027-12-21 | 10 | SP | Yadkin | 03040105 |  |  |  | 0 | 0.1 |  |  | 0.1 | NRTR | 2020-05-01 | Division Review- Estimate based on MCDC signed May 2019 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-12-21 | no change
U-5952 |  | GREENVILLE | Pitt | NO | 2027-12-21 | 2 | NICP | TAR-PAMLICO | 03020103 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-11-17 | pushed out
R-5807 |  | NC 343 | Camden | YES | 2028-01-18 | 1 | NOCP | PASQUOTANK | 03010205 | 500 |  |  | 500 | 0.5 |  |  | 0.5 | Permit Drawings | 2025-01-01 | updated 2025 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2027-01-19 | pushed out
R-2555B |  | SR 5544 (WEST CATAWBA AVENUE) | MECKLENBURG | NO | 2028-01-18 | 10 | SP | Catawba | 03050101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-24 | No Water Resources associated with this project- updated 2026 | Delivery |  |  | DMS_List2025 | 2027-01-19 | pushed out
U-5727 |  | US 1 / US 15 / US 501 | Lee | NO | 2028-01-25 | 8 | SP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2028-01-25 | no change
U-5975 |  | US 1 / US 15 / US 501 | Lee | YES | 2028-02-15 | 8 | SP | CAPE FEAR | 03030003 | 139 |  |  | 139 | 0.13 |  |  | 0.13 | Approved Permit Drawings | 2023-08-14 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-02-15 | no change
B-6026 |  | SR 1500 (WATAUGA ROAD) | Macon | NO | 2028-02-16 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Delivery |  |  |  | 2027-09-15 | pushed out
R-5824 |  | NC 690 (LOBELIA ROAD) | Moore | YES | 2028-03-01 | 8 | SP | CAPE FEAR | 03030004 | 275 |  |  | 275 | 0.53 |  |  | 0.53 | ROW Plans | 2024-10-23 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. |  | 2028-03-01 | no change
HB-0008 |  | SR 1214 (Mount Pisgah Church Road) | Harnett | YES | 2028-03-21 | 6 | SICP | Cape Fear | 03030004 | 35 |  |  | 35 |  |  |  | 0 | Division Review | 2026-02-25 | Updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | moved in
U-5967 |  | VARIOUS | Wake | NO | 2028-03-21 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 | no reply 2026 | Delivery |  |  | DMS_List2025 | 2028-03-21 | no change
R-5822 |  | NC 86 | Caswell | NO | 2028-03-21 | 7 | CP | ROANOKE | 03010104 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2028-03-21 | no change
U-2561C |  | NC 43 | Nash | YES | 2028-03-21 | 4 | NICP | TAR-PAMLICO | 03020101 | 82 |  |  | 82 |  |  |  | 0 | GIS | 1999-01-01 | PM waiting on PEF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-03-21 | no change
U-5939 |  | US 17 BUSINESS | Pasquotank | YES | 2028-03-21 | 1 | NOCP | PASQUOTANK | 03010205 | 100 |  |  | 100 | 0.5 |  |  | 0.5 | Division Review | 2018-02-01 | no impact update 2025 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2027-03-16 | pushed out
U-6161 |  | US 321 | CALDWELL | YES | 2028-03-21 | 11 | NM | Catawba | 03050101 | 80 |  |  | 80 |  |  |  | 0 | NRTR | 2026-02-23 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-01-19 | pushed out
U-5770B |  | SR 1009 (SOUTH MAIN STREET) | Randolph | NO | 2028-03-21 | 8 | CP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2026-09-15 | pushed out
U-5917 |  | SR 1704 (FOURTEENTH STREET) | PITT | YES | 2028-04-05 | 2 | NICP | Tar-Pamlico | 03020103 | 229 |  |  | 229 | 0.08 |  |  | 0.08 | Division Review | 2022-10-07 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-02-03 | pushed out
U-6246 |  | NC 84 | UNION | NO | 2028-04-18 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-24 | No Water Resources associated with this project- updated 2026 | Delivery |  |  | DMS_List2025 | 2028-04-18 | no change
R-5836 |  | US 601 | Surry | YES | 2028-04-19 | 11 | CP | YADKIN | 03040101 |  | 3560 |  | 3560 | 0.2 |  |  | 0.2 | Merger screening | 2026-02-26 | based on merger screening report from 7/21/22 (increased from 500LF) | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2027-04-07 | pushed out
U-6248 |  | NC 75 | UNION | NO | 2028-05-16 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-24 | No Water Resources associated with this project- updated 2026 | Delivery |  |  | DMS_List2025 | 2028-05-16 | no change
B-5871 |  | SR 1306 (BILLS CREEK ROAD) | Rutherford | NO | 2028-05-16 | 13 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2028-05-16 | no change
U-6013 |  | NC 119 | Alamance | NO | 2028-06-20 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 | no impact updates 2026 | Delivery |  |  | DMS_List2025 | 2028-06-21 | moved in
R-5943 |  | US 13 | Greene | NO | 2028-06-20 | 2 | NICP | Neuse | 03020203 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  |  | 2028-06-20 | no change
BR-0193 |  | Bridge 660007 over Northeast Creek | Onslow | YES | 2028-06-20 | 3 | SOCP | White Oak | 03020302 | 0 |  |  | 0 | 0.002 |  |  | 0.002 | Cat Excl. | 2026-02-04 | update 2026- asking division of NRTR CU discrepancy | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-06-20 | no change
U-5860 |  | SR 1306 (15TH STREET) | Beaufort | NO | 2028-06-20 | 2 | NOCP | TAR-PAMLICO | 03020104 |  |  |  | 0 |  |  |  | 0 | PDEA Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2028-06-20 | no change
U-6027 |  | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | Richmond | NO | 2028-06-20 | 8 | SP | YADKIN | 03040201 |  |  |  | 0 |  |  |  | 0 | MCDC | 2022-08-04 |  | Delivery |  |  | DMS_List2025 | 2028-06-20 | no change
U-6082 |  | SR 1308 (BELL FORK ROAD) | Onslow | NO | 2028-06-20 | 3 | SOCP | White Oak | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-23 | 2026 update - No update on impacts. Project scope being revised. | Delivery |  |  | DMS_List2025 | 2027-09-21 | pushed out
R-5830 |  | SR 1522 (DEERFIELD ROAD) | Watauga | YES | 2028-06-20 | 11 | NM | NEW | 05050001 |  |  | 60 | 60 |  |  |  | 0 | Division Review | 2026-02-23 | no impact update 2026 / working on project plans | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-04-20 | pushed out
B-6037 |  | NC 86 | Orange | NO | 2028-07-18 | 7 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Final CE NRTR Addend | 2025-01-10 | updated 2026 | Delivery |  |  |  | 2028-07-18 | no change
BR-0154 |  | NC 209 | Haywood | YES | 2028-07-18 | 14 | SM | French Broad | 06010106 |  |  | 270.7681 | 270.7681 |  |  |  | 0 | GIS | 2026-02-04 | NRTR says 739 for the study area |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-07-18 | no change
U-2901BA |  | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | Wake | NO | 2028-07-18 | 5 | CP | CAPE FEAR | 03030204 |  |  |  | 0 |  |  |  | 0 | GIS | 2025-03-13 | no impact | Delivery |  |  | DMS_List2025 | 2028-07-18 | no change
U-5974 |  | NC 68 | Guilford | YES | 2028-07-18 | 7 | CP | CAPE FEAR | 03030003 | 2005 |  |  | 2005 | 0.18 |  |  | 0.18 |  | 2026-02-25 | updated 2026 (requesting source, not listed on email increased from 472 LF & 0 ac. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-03-21 | pushed out
HB-0032 |  | SR 1004 (HUDSON CHAPEL ROAD) | Catawba | NO | 2028-07-18 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2028-02-15 | pushed out
U-6204 |  | SR 1556 (WAYNE MEMORIAL DRIVE) | Wayne | YES | 2028-07-18 | 4 | NICP | NEUSE | 03020202 | 25 |  |  | 25 | 0.00076 |  |  | 0.00076 | GIS | 2019-01-25 | not update 2025 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2027-08-17 | pushed out
B-5949 |  | NC 200 | Union | YES | 2028-07-18 | 10 | SP | YADKIN | 03040105 | 80 |  |  | 80 | 0.1 |  |  | 0.1 | NRTM/Division Review | 2026-02-01 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-02-16 | pushed out
R-5913 |  | NC 67 (Elm St) | Yadkin | NO | 2028-07-22 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | Division review | 2026-02-23 | no impacts | Delivery |  |  |  |  | pushed out
BP9-R005 | BP9.R005.1 |  | STOKES | YES | 2028-07-26 | 9 | CP | Yadkin | 03040103 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 2026-02-15 | update 2026 add- 50’ warm stream, 25% plans with PJD, pre NEPA/SEPA |  | DMS | DMS to provide all mitigation. |  |  | pushed out
BP9-R010 | BP9.R010.1 |  | FORSYTH | YES | 2028-08-15 | 9 | CP | Yadkin | 03040101 | 146 |  |  | 146 | 1.46 |  |  | 1.46 | Division Review | 2026-02-15 | update 2026 add- 146’ warm stream, 1.46 acres riparian wetland (will go down), calculated proposed ROW to proposed ROW at 25% plans with PJD |  | NCDOT | Private bank credits for streams and wetlands. |  | 2028-08-15 | no change
BR-0169 |  | NC 561 | Franklin | YES | 2028-08-15 | 5 | CP | Tar-Pamlico | 03020101 | 234 |  |  | 234 | 0.05 |  |  | 0.05 | Permit Drawing | 2026-02-04 | Most up to date Permit Drawings depict 234LF of permanent stream impact, 99LF of temporary stream impact, and 0.05ac of wetland impact (not all will require mitigation) |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-08-15 | no change
HB-0025 |  | SR 1004 (POORS FORD ROAD) | Polk | NO | 2028-08-15 | 14 | SP | BROAD | 03050105 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2028-08-15 | no change
R-5809B |  | NC 45 | Bertie | YES | 2028-08-15 | 1 | NOCP | CHOWAN | 03010203 | 469 |  |  | 469 | 0.0321 | 0.4763 |  | 0.5084 | In design | 2025-03-02 05:00 | no updates | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-08-15 | no change
R-5832 |  | NC 88 | Ashe | YES | 2028-08-15 | 11 | NM | NEW | 05050001 |  |  | 300 | 300 | 0.25 | 0.25 |  | 0.5 | CFI Plans | 2026-02-23 | updated 2026 - increased from 0LF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-08-15 | no change
U-6059A |  | SR 2377 (OLD GREENSBORO ROAD NE) | Forsyth | NO | 2028-08-15 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | (2EP1) Advance NEPA/SEPA Doc | 2026-01-27 05:00 | no impacts | Delivery |  |  | DMS_List2025 | 2028-02-15 | pushed out
B-6038 |  | NC 14 / NC 87 | Rockingham | NO | 2028-08-17 | 7 | CP | ROANOKE | 03010103 | 398 |  |  | 398 |  |  |  | 0 | CFI Meeting | 2026-02-25 | updated 3/5/26- was No Impacts | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-01-15 | pushed out
U-6131 |  | NC 54 (WEST HARDEN STREET) | Alamance | NO | 2028-08-22 | 7 | CP | Cape Fear | 03030002 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-25 | No impact update 2026 | Delivery |  |  | DMS_List2025 | 2028-08-15 | pushed out
HB-0027 |  | SR 1355 (PANTHER CREEK ROAD) | Haywood | NO | 2028-09-19 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2027-01-19 | pushed out
HA-0005 |  | New Route | Rutherford | YES | 2028-09-20 | 13 | SP | Broad | 03050105 |  | 339.7787 |  | 339.7787 |  |  |  | 0 | GIS | 2026-02-04 | Hannah smith - No updates 2/172026 | Delivery | DMS | DMS to provide all mitigation. |  | 2028-09-20 | no change
B-6044 |  | I-95 | Johnston | NO | 2028-10-17 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | Division Review | 2021-12-07 |  | Delivery |  |  | DMS_List2025 | 2028-10-17 | no change
HB-0029 |  | SR 1179 (BRIDGE STREET) | Wake | NO | 2028-10-17 | 5 | CP | CAPE FEAR | 03030004 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 | no reply 2026 | Delivery |  |  | DMS_List2025 | 2028-10-17 | no change
I-5718 |  | I-77 | Mecklenburg | YES | 2028-10-17 | 10 | SP | Catawba | 03050103 | 16911 |  |  | 16911 |  |  |  | 0 | CP2 meeting | 2025-12-21 | I-5718 B & A were dropped by TIP Unit | Delivery | DMS | DMS to provide all mitigation. |  | 2028-10-17 | no change
U-5301A |  | US64 | Wake | NO | 2028-10-17 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2025-02-06 | no reply 2026 | Delivery |  |  | DMS_List2025 | 2028-10-17 | no change
I-5974 |  | I-95 | Johnston | YES | 2028-10-17 | 4 | NICP | NEUSE | 03020201 | 1530 |  |  | 1530 | 1.75 |  |  | 1.75 | CE - ROW Consult | 2021-02-04 | updated 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2028-07-18 | pushed out
U-4407 |  | US 70 BUSINESS (EAST ASH STREET) | Wayne | NO | 2028-10-17 | 4 | NICP | NEUSE | 03020202 |  |  |  | 0 |  |  |  | 0 | NRTR | 2019-01-28 |  | Delivery |  |  | DMS_List2025 | 2027-10-19 | pushed out
HB-0031 |  | THIRD STREET | Forsyth | NO | 2028-10-17 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | (2EP1) Advance NEPA/SEPA Doc | 2026-02-18 | no impacts, updated 2026 | Delivery |  |  | DMS_List2025 | 2027-09-21 | pushed out
U-6157 |  | SR 1130 (CAJAH MOUNTAIN ROAD) | Caldwell | YES | 2028-10-17 | 11 | NM | CATAWBA | 03050101 | 40 |  |  | 40 | 0.1 |  |  | 0.1 | CFI Plans | 2026-02-25 | updated 2026 - increased from 0LF | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-08-17 | pushed out
U-5886 |  | SR 1170 (WHITE STREET) | HENDERSON | YES | 2028-10-17 | 14 | SM | French Broad | 06010105 |  | 35 |  | 35 |  |  |  | 0 | Division Review | 2026-02-19 | 2/23/26 - No update (permit plans not complete) | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2026-10-20 | pushed out
U-6049 |  | NC 225 (SOUTH MAIN STREET) | Henderson | YES | 2028-10-17 | 14 | SM | FRENCH BROAD | 06010105 |  | 73 |  | 73 |  |  |  | 0 | Division Review | 2026-02-19 | 2/23/26 - No update (permit plans not complete) | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2026-10-20 | pushed out
BP9-R011 | BP9.R011.1 |  | FORSYTH | NO | 2028-10-25 | 9 | CP | Yadkin | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-15 | No mitigable impacts | [5 empty] | pushed out
B-6031 |  | SR 1300 (PUMPKINTOWN ROAD) | Jackson | NO | 2028-11-14 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Delivery |  |  | DMS_List2025 | 2028-11-14 | no change
BR-0163 |  | NC 742 | Anson | YES | 2028-11-21 | 10 | SP | Yadkin | 03040105 | 115.6692 |  |  | 115.6692 |  |  |  | 0 | GIS | 2026-02-04 | New |  | DMS | DMS to provide all mitigation. |  | 2028-11-21 | no change
I-5719A |  | I-85 | Gaston | YES | 2028-11-21 | 12 | SP | Catawba | 03050102 | 4995 |  |  | 4995 | 0.1 |  |  | 0.1 | 2025 ROW Plans | 2026-02-11 | Parent record I-5719 had breaks for R/W | Delivery | DMS | DMS to provide all mitigation. |  | 2028-11-21 | no change
U-6044 |  | SR 2200 (COX ROAD) | Gaston | NO | 2028-11-21 | 12 | SP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2024-04-23 |  | Delivery |  |  | DMS_List2025 | 2028-11-21 | no change
U-6034 |  | US 321 ALT | Caldwell | NO | 2028-11-21 | 11 | NM | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | NRTR | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2027-09-21 | pushed out
B-6030 |  | SR 1351 (MATLOCK CREEK ROAD) | Macon | NO | 2029-01-23 | 14 | SM | LITTLE TENNESSEE | 06010202 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Delivery |  |  | DMS_List2025 | 2029-01-23 | no change
B-6033 |  | SR 1445 (LEE BUMGARNER ROAD) | Jackson | NO | 2029-01-23 | 14 | SM | LITTLE TENNESSEE | 06010203 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 |  | Delivery |  |  | DMS_List2025 | 2029-01-23 | no change
B-5976 |  | SR 1400 (CUMNOCK ROAD) | Lee | NO | 2029-02-20 | 8 | SP | CAPE FEAR | 03030003 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2029-02-20 | no change
U-5790 |  | US 421 (CAROLINA BEACH ROAD) | New Hanover | YES | 2029-03-20 | 3 | SOCP | CAPE FEAR | 03030005 | 200 |  |  | 200 |  | 0.217 |  | 0.217 | Division Review | 2026-02-23 | no impact update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | no change
U-5790 |  | US 421 (CAROLINA BEACH ROAD) | New Hanover | YES | 2029-03-20 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  | 0.22 |  | 0.22 | Division Review | 2026-02-23 | no impact update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | no change
U-5951 |  | US 17 | Onslow | YES | 2029-03-20 | 3 | SOCP | WHITE OAK | 03030001 | 150 |  |  | 150 | 0.35 |  |  | 0.35 | 25% Plans | 2024-09-25 | 2026 no update on impacts | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | no change
U-6205 |  | SR 1556 (WAYNE MEMORIAL DRIVE) | Wayne | YES | 2029-03-20 | 4 | NICP | NEUSE | 03020202 | 223 |  |  | 223 | 0.0565 | 2.0415 |  | 2.098 | GIS | 2019-01-25 | no impact update 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | no change
U-6205 |  | SR 1556 (WAYNE MEMORIAL DRIVE) | Wayne | YES | 2029-03-20 | 4 | NICP | NEUSE | 03020203 |  |  |  | 0 |  | 0.0325 |  | 0.0325 | GIS | 2019-01-25 | no reply | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | no change
U-2530A |  | NC 127 | Catawba | NO | 2029-03-20 | 12 | CP | CATAWBA | 03050102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2028-03-21 | pushed out
U-5726 |  | US 301/NC 39/NC 96 | Johnston | NO | 2029-03-20 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  | DMS_List2025 | 2028-03-21 | pushed out
U-5892 |  | US 220 (BATTLEGROUND AVENUE) | GUILFORD | YES | 2029-03-20 | 7 | CP | Cape Fear | 03030002 | 400 |  |  | 400 | 0.19 | 0.001 |  | 0.191 | 2019 WEX files | 1905-07-11 | Increased by 300 LF, and new wetlands- updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-12-15 | pushed out
U-6032 |  | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | Cabarrus | YES | 2029-05-15 | 10 | SP | YADKIN | 03040105 | 100 |  |  | 100 | 0.01 |  |  | 0.01 | 2020 Slope Stakes file | 1905-07-12 | Division Review- Estimate based on MCDC signed May 2019 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-05-15 | no change
I-5708 |  | I-440 / US 1 | Wake | NO | 2029-05-15 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | (3EN2) Apply for Permits | 2026-02-18 | Project Team has reviewed the stream and wetland impacts and assessed that none will be affected by this project | Delivery |  |  | DMS_List2025 | 2029-05-15 | no change
U-5816 |  | SR 1305 (OATES ROAD - MIDNIGHT LANE) | Iredell | NO | 2029-06-13 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2029-06-14 | moved in
U-6197 |  | SR 1711 (WORTHINGTON ROAD) | PITT | NO | 2029-06-19 | 2 | NICP | Neuse | 03020202 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-02-15 |  | Delivery |  |  | DMS_List2025 | 2029-06-19 | no change
I-6065 |  | I-77 | Mecklenburg | YES | 2029-06-19 | 10 | SP | CATAWBA | 03050103 | 4011 |  |  | 4011 | 1.1 | 1.1 |  | 2.2 | Division Review | 2020-01-23 | Div 10- updated with PJD, previously no impacts- 2/24/26 | Delivery | DMS | DMS to provide all mitigation. |  | 2029-06-19 | no change
U-2307B |  | MCDONALD PARKWAY | CATAWBA | YES | 2029-06-19 | 12 | CP | Catawba | 03050101 | 1000 |  |  | 1000 | 0.4 |  |  | 0.4 | CE_FHWA comments | 2025-07-22 | No reply, I looked up 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-06-19 | no change
U-5769A |  | NC 16 (PROVIDENCE ROAD SOUTH) | Union | YES | 2029-06-19 | 10 | SP | CATAWBA | 03050103 | 250 |  |  | 250 | 0.37 |  |  | 0.37 | NRTM | 2017-01-01 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-06-19 | no change
U-5769B |  | NC 16 (PROVIDENCE ROAD SOUTH) | Union | YES | 2029-06-19 | 10 | SP | CATAWBA | 03050103 | 250 |  |  | 250 |  |  |  | 0 | NRTM | 2017-01-01 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-06-19 | no change
U-5791A |  | SR 2714 | Onslow | YES | 2029-06-19 | 3 | SOCP | WHITE OAK | 03030001 | 1341 |  |  | 1341 | 3.63 | 16.27 |  | 19.9 | (2EP1) Advance NEPA/SEPA Doc | 2025-03-31 04:00 | Div 2026 No update on impacts. CP3 is this week (2/24/26)and can provide up dated afterwards. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-06-19 | no change
U-5792 |  | US 117 / NC 132 (COLLEGE ROAD) | New Hanover | YES | 2029-06-19 | 3 | SOCP | CAPE FEAR | 03030007 | 824 |  |  | 824 | 1.9 |  |  | 1.9 | Alt Design | 2025-01-01 | update 2026-Based on 2025 Alt. Analysis Comparison. Impacts slope stake plus 25 ft. Some onsite mitigation anticipated. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-10-17 | pushed out
R-5905 |  | NC 89 (WEST PINE STREET) | Surry | NO | 2029-06-19 | 11 | CP | Yadkin | 03040101 |  | 0 |  | 0 |  |  |  | 0 | Division review | 2026-02-23 | no impacts 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2027-07-20 | pushed out
R-5929 |  | NC 24 / NC 27 | Moore | NO | 2029-06-19 | 8 | SP | Cape Fear | 03030003 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 | Waiting for Kevin H get update by 2/26/26 | Delivery |  |  | DMS_List2025 | 2027-06-15 | pushed out
P-5713 |  | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | Guilford | NO | 2029-06-19 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | Rail Review | 1999-01-01 | Waiting for Kevin H get update by 2/26/26 | Delivery |  |  | DMS_List2025 | 2027-06-15 | pushed out
U-5734 |  | US 421 (SOUTH FRONT STREET) | New Hanover | YES | 2029-07-17 | 3 | SOCP | CAPE FEAR | 03030005 | 75 |  |  | 75 | 1.25 |  |  | 1.25 | 25% Plans | 2025-01-01 | Waiting for Kevin H get update by 2/26/26 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2030-01-01 | moved in
R-2822BA |  | NC143 | Graham | YES | 2029-07-17 | 14 | SM | Little Tennessee | 06010204 |  |  | 3220 | 3220 |  |  |  | 0 | MDC | 2022-06-02 | Update 2026 - TBD Permit Plans are not complete | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. |  | 2029-07-17 | no change
BR-0162 |  | US 19 W | Yancey | YES | 2029-07-17 | 13 | NM | French Broad | 06010108 |  |  | 196.7211 | 196.7211 |  |  |  | 0 | GIS | 2026-02-04 | New |  | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-07-17 | no change
U-2509AD |  | US 74 | Mecklenburg | YES | 2029-07-17 | 10 | SP | CATAWBA | 03050103 | 135 |  |  | 135 |  |  |  | 0 | EA Reevaluation | 2024-04-12 |  | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-07-17 | no change
U-3431 |  | SR 1763 (MILLER BOULEVARD) | Craven | YES | 2029-07-17 | 2 | SOCP | NEUSE | 03020204 | 600 |  |  | 600 | 0.3 | 0.47 |  | 0.77 | Division Review | 2024-11-01 | Changed due to a 4,000 LF Lake Road Extension in November 2024 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-07-17 | no change
U-5785 |  | SR 1708 (FIRETOWER ROAD) | Pitt | YES | 2029-07-17 | 2 | NICP | TAR-PAMLICO | 03020103 | 60 |  |  | 60 |  |  |  | 0 | Division Review | 2019-01-28 | no reply | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-07-17 | no change
U-5811 |  | SR 1002 (AVIATION PARKWAY) | Wake | YES | 2029-07-17 | 5 | CP | NEUSE | 03020201 | 445 |  |  | 445 | 0.57 |  |  | 0.57 | (2EP1) Advance NEPA/SEPA Doc | 2025-06-13 04:00 | Public Meeting Maps 3/31/25 Per Joel P. | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2029-07-17 | no change
U-5890 |  | SR 1162 (DABNEY DRIVE) | VANCE | YES | 2029-07-17 | 5 | CP | Roanoke | 03010102 | 840 |  |  | 840 | 0.38 |  |  | 0.38 | CE | 2025-11-01 | Impacts likely required according to CE Document signed November 2025 - depicting 840LF stream and 0.38ac wetland | Delivery | DMS | DMS to provide all mitigation. |  | 0 | pushed out
BR-0016 |  |  | DAVIDSON | YES | 2029-08-14 | 9 | CP | Yadkin | 03040103 | 82 |  |  | 82 |  |  |  | 0 | Division Review | 2026-02-15 | update 2026 -82’ warm stream impacts, NEPA/SEPA document |  | DMS | DMS to provide all mitigation. |  | 2029-08-14 | no change
B-5858 |  | SR 1607 (Eastridge Drive) | Cleveland | YES | 2029-08-21 | 12 | SP | Broad | 03050105 | 112.3321 |  |  | 112.3321 |  |  |  | 0 | GIS | 2026-02-04 | New | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-08-21 | no change
HB-0024 |  | US-401 | Haywood | NO | 2029-08-21 | 14 | SM | FRENCH BROAD | 06010106 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2028-08-15 | pushed out
R-5706A |  | NC 73 (DAVIDSON HIGHWAY) | Mecklenburg | YES | 2029-08-29 | 10 | SP | YADKIN | 03040105 |  |  |  | 0 | 0.11 |  |  | 0.11 | CE Document | 2025-05-30 | Impacts Decreased updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-07-19 | pushed out
U-6247 |  | NC 84 | UNION | NO | 2029-09-18 | 10 | SP | CATAWBA | 03050103 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-24 | No Water Resources associated with this project- updated 2026 | Delivery |  |  | DMS_List2025 | 2028-06-20 | pushed out
P-5747 |  | NCRR NORFOLK SOUTHERN H LINE | Guilford | NO | 2029-10-16 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Delivery |  |  | DMS_List2025 | 2029-10-16 | no change
R-2247EA |  | NEW ROUTE (FUTURE NC 452) | Forsyth | YES | 2029-10-16 | 9 | CP | YADKIN | 03040101 | 8448 |  |  | 8448 | 0.63 |  |  | 0.63 | ROW update | 2021-12-01 | estimated 2026 | Delivery | NCDOT/DMS | Potential Onsite Stream Mitigation being reviewed (of no more than 1,200 LF). DMS to provide other stream and wetland credits | DMS_List2025 | 2029-10-16 | no change
U-6203 |  | NC 210 | Johnston | YES | 2029-10-16 | 4 | NICP | NEUSE | 03020201 | 28 |  |  | 28 | 0.2 |  |  | 0.2 | Division Review | 2019-01-25 | 2/24/25 - No update, waiting on plan set | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2028-10-17 | pushed out
R-5936 |  | SR 1126 (ROPER NEWLAND ROAD) | Washington | NO | 2029-10-16 | 1 | NOCP | PASQUOTANK | 03010205 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-22 |  | Delivery |  |  | DMS_List2025 | 2027-10-19 | pushed out
U-5717 |  | US 15 / US 501 | Durham | NO | 2029-10-16 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-18 | Resources in the study area but unsure of impacts at this time | Delivery |  |  | DMS_List2025 | 2026-10-20 | pushed out
U-6004 |  | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | Forsyth | YES | 2029-11-14 | 9 | CP | YADKIN | 03040101 | 20 |  |  | 20 |  |  |  | 0 | (3EN2) Apply for Permits | 2026-02-18 | mitigated through private bank | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2029-11-14 | no change
HB-0022 |  | ROCK SPRINGS ROAD | Pitt | YES | 2030-01-02 | 2 | NICP | TAR-PAMLICO | 03020103 |  |  |  | 0 | 0.004 |  |  | 0.004 | 404/401 Permit Drawing | 2024-06-24 |  | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-02 | no change
HB-0009 |  | ROAD) SR 1800 (BLACKSMITH | Columbus | YES | 2030-01-10 | 6 | SICP | LUMBER | 03040206 | 35 |  |  | 35 |  |  |  | 0 | Division Review | 2026-02-25 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-10 | no change
B-5832 |  | SR 2080 (QUAKER CHURCH ROAD) | Surry | NO | 2030-01-15 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | No info | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2030-01-15 | no change
B-5811 |  | SR 1434 (ROGERS ROAD) | Stanly | YES | 2030-01-15 | 10 | SP | YADKIN | 03040105 | 331 |  |  | 331 | 0.011 |  |  | 0.011 | Division Review | 1999-01-01 | Division Review- information incomplete 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-15 | no change
R-5939 |  | SR 1300 (NEW HOPE ROAD) | Perquimans | YES | 2030-01-15 | 1 | NOCP | PASQUOTANK | 03010205 | 94 |  |  | 94 |  | 0.23 |  | 0.23 | GIS | 2019-01-25 |  | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2030-01-15 | no change
U-5304F |  | US 15 / US 501 | Orange | NO | 2030-01-15 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2030-01-15 | no change
U-5508 |  | NC 24 (LEJEUNE BOULEVARD) | Onslow | YES | 2030-01-15 | 3 | SOCP | WHITE OAK | 03030001 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 2026-02-23 | 2026 No impact update | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-15 | no change
U-6009 |  | US 70 (SOUTH CHURCH STREET) | Alamance | YES | 2030-01-15 | 7 | CP | CAPE FEAR | 03030002 | 51 |  |  | 51 |  |  |  | 0 | GIS | 1999-01-01 | no impact updates 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-01 | pushed out
U-5825B |  | US 1 | WAKE | YES | 2030-01-15 | 5 | CP | Neuse | 03020201 | 440 |  |  | 440 |  |  |  | 0 | Express Design | 2025-02-25 | No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2028-09-19 | pushed out
HB-0018 |  | I-40 | Catawba | NO | 2030-01-15 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 2022-08-24 |  | Delivery |  |  | DMS_List2025 | 2028-01-18 | pushed out
B-4566 |  | NC 903 | Lenoir | YES | 2030-01-15 | 2 | SICP | NEUSE | 03020202 |  |  |  | 0 | 0.112 |  |  | 0.112 | Division Review | 2026-02-20 | No update available 2026 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2028-01-18 | pushed out
P-5706 |  | NORFOLK SOUTHERN H LINE | Durham | YES | 2030-01-15 | 5 | CP | Cape Fear | 03030002 | 1345 |  |  | 1345 | 0.1 |  |  | 0.1 | Division Review | 2025-02-21 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-01-18 | pushed out
U-5723 |  | US 74 | Union | YES | 2030-01-15 | 10 | SP | YADKIN | 03040105 | 50 |  |  | 50 | 0.83 |  |  | 0.83 | Division Review | 2026-02-24 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-01-18 | pushed out
U-6119 |  | VARIOUS | Wake | NO | 2030-02-19 | 5 | CP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  | DMS_List2025 | 2030-02-19 | no change
U-5940 |  | US 17 (HUGHES BOULEVARD) | Pasquotank | YES | 2030-02-19 | 1 | NOCP | PASQUOTANK | 03010205 | 59 |  |  | 59 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2029-02-20 | pushed out
U-6188 |  | SR 1969 (PINEY GROVE ROAD) | Forsyth | YES | 2030-03-06 | 9 | CP | ROANOKE | 03010103 | 454 |  |  | 454 |  |  |  | 0 | GIS | 2026-02-18 | update 2026 -Atlas estimate with Study area | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-03-06 | no change
HB-0010 |  | SR 1716 (JACKIE LEE ROAD) | Cumberland | YES | 2030-03-19 | 6 | SICP | CAPE FEAR | 03030004 | 35 |  |  | 35 |  |  |  | 0 | Division Review | 2026-02-25 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-03-20 | pushed out
U-6190 |  | NC 65 (BETHANIA-RURAL HALL ROAD) | Forsyth | NO | 2030-04-16 | 9 | CP | ROANOKE | 03010103 |  |  |  | 0 |  |  |  | 0 | GIS | 2026-02-18 | update 2026 -atlas estimate without study area-too early | Delivery |  |  | DMS_List2025 | 2029-04-17 | pushed out
U-5934 |  | I-885 | Durham | YES | 2030-04-16 | 5 | CP | CAPE FEAR | 03030002 | 559 |  |  | 559 |  |  |  | 0 | GIS | 2026-02-18 | No alternative as been selected to date 2/2025. No update available 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-08-15 | pushed out
U-5766B |  | NC 160 | Mecklenburg | YES | 2030-04-16 | 10 | SP | CATAWBA | 03050103 | 360 |  |  | 360 |  | 0.4 |  | 0.4 | 2025 Design Plans | 2025-08-08 | Division Review- Estimate from Design Plans-update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-04-18 | pushed out
U-5518 |  | US 70 (GLENWOOD AVENUE) | Wake | YES | 2030-05-21 | 5 | CP | NEUSE | 03020201 | 7658 |  |  | 7658 | 1.78 |  |  | 1.78 | CP 3/4A | 2019-01-01 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-05-21 | no change
B-5843 |  | SR 2402 (HOOVER ROAD) | Iredell | NO | 2030-05-21 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2030-05-21 | no change
U-4739 |  | SR 3556 (AMBOYROAD/ MEADOW ROAD) | Buncombe | YES | 2030-05-21 | 13 | SM | FRENCH BROAD | 06010105 |  | 56 | 113 | 169 |  |  |  | 0 | GIS | 1999-01-01 | no reply | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2029-04-17 | pushed out
B-5987 |  | US 401 | WAKE | YES | 2030-05-21 | 5 | CP | Neuse | 03020201 | 171 |  |  | 171 | 0.3 |  |  | 0.3 | Division Review | 2026-02-18 | No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2028-12-19 | pushed out
U-5737 |  | US 64 (EAST 11TH STREET) | Chatham | Yes | 2030-05-21 | 8 | CP | CAPE FEAR | 03030003 | 700 |  |  | 700 |  |  |  | 0 | ROW Plans | 2025-01-15 | Update 2026 -email M.DeWit | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-10-17 | pushed out
R-5900 |  | NC 50/NC 210 | PENDER | NO | 2030-06-18 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-23 | update 2026-Based on new conceptual design, minor non- riparian wetland impacts & no mitigation required. | Delivery |  |  |  | 2031-06-17 | moved in
R-5889A |  | US 29 (FUTURE I-785) | GUILFORD | YES | 2030-06-18 | 7 | CP | Cape Fear | 03030002 | 7003 |  |  | 7003 | 0.17 |  |  | 0.17 | GIS | 2025-02-21 | Inactive - shelved - No impact update 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2030-06-18 | no change
U-2509AB |  | US 74 | Mecklenburg | YES | 2030-06-18 | 10 | SP | CATAWBA | 03050103 | 1032 |  |  | 1032 | 0.03 |  |  | 0.03 | EA Reevaluation | 2024-04-12 | no reply 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-06-18 | no change
U-5764 |  | US 74 | Union | YES | 2030-06-18 | 10 | SP | YADKIN | 03040105 | 375 |  |  | 375 | 0.06 |  |  | 0.06 | PJD | 2025-12-15 | Division Review- no update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-06-18 | no change
U-5931 |  | US 74 | Union | YES | 2030-06-18 | 10 | SP | YADKIN | 03040105 | 300 |  |  | 300 |  |  |  | 0 | 25% Roadway Design | 2026-02-01 | updated 2026, was 0 in 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-06-19 | pushed out
R-5909 |  | SR 1314 (EAST MAIN STREET) | Yadkin | NO | 2030-06-18 | 11 | CP | Yadkin | 03040101 |  |  |  | 0 |  |  |  | 0 | NRTR | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2029-06-19 | pushed out
U-5731 |  | US 74 | New Hanover | YES | 2030-06-18 | 3 | SOCP | CAPE FEAR | 03030005 |  |  |  | 0 | 2.04 |  | 0.75 | 2.79 | Draft Document | 2022-10-10 | No update on impacts; alternatives being developed.- 2026 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2029-06-19 | pushed out
U-5836 |  | NC 181 | Burke | YES | 2030-06-18 | 13 | NM | CATAWBA | 03050101 | 50 |  |  | 50 | 0.05 |  |  | 0.05 | Division Review | 2021-02-04 | no reply | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-07-18 | pushed out
U-3400 |  | SR 1577 / SR 1004 (ARCHDALE ROAD) | Randolph | YES | 2030-06-18 | 8 | CP | CAPE FEAR | 03030003 | 1090 |  |  | 1090 | 0.26 |  |  | 0.26 | (2EP1) Advance NEPA/SEPA Doc | 2025-06-13 04:00 | email received with update by Jeffery Stroder 4/2/25 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-06-20 | pushed out
U-3338C |  | SR 1175 (KERR AVENUE) | New Hanover | YES | 2030-06-18 | 3 | SOCP | CAPE FEAR | 03030007 | 312 |  |  | 312 | 0.36 |  |  | 0.36 | Draft Permit Drawings | 2022-10-10 | 2026 No impact update | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2027-06-15 | pushed out
I-4759 |  | I-40 | Buncombe | YES | 2030-06-20 | 13 | SM | FRENCH BROAD | 06010105 |  | 1048 |  | 1048 |  |  |  | 0 | Draft Permit Drawings | 2023-08-18 | No impact update 2026 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2029-06-21 | pushed out
U-6128 |  | US 76 (OLEANDER DRIVE) | New Hanover | NO | 2030-07-16 | 3 | SOCP | White Oak | 03030001 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 | 2026 No impact update | Delivery |  |  |  | 2030-07-16 | no change
U-2509EB |  | Independence Pointe Parkway | Mecklenburg | YES | 2030-07-16 | 10 | SP | Catawba | 03050103 | 827.988 |  |  | 827.988 |  |  |  | 0 | GIS | 2026-02-04 | New | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-07-16 | no change
U-2901B |  | NC 55 (WILLIAMS STREET) | Wake | YES | 2030-07-16 | 5 | CP | NEUSE | 03020201 | 225 |  |  | 225 | 0.19 |  |  | 0.19 | Environmental Document | 2018-12-20 | No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2030-07-16 | no change
U-2901B |  | NC 55 (WILLIAMS STREET) | Wake | YES | 2030-07-16 | 5 | CP | CAPE FEAR | 03030002 | 629 |  |  | 629 | 0.01 |  |  | 0.01 | Environmental Document | 2018-12-20 | No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2028-07-18 | pushed out
HB-0041 |  | I-77 | Iredell | NO | 2030-07-16 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | GIS | 2024-02-12 |  | Delivery |  |  |  |  | pushed out
B-5787 |  |  | DAVIDSON | YES | 2030-08-20 | 9 | CP | Yadkin | 03040103 | 130 |  |  | 130 |  |  |  | 0 | 65% plans | 2026-02-15 | update 2026 add- 130’ warm stream impacts, 65% plans | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-08-21 | pushed out
P-5718 |  | CSX | Wake | YES | 2030-08-20 | 5 | CP | Neuse | 03020201 |  |  |  | 0 | 0.1 |  |  | 0.1 | Division Review | 2025-02-21 | No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. |  |  | pushed out
B-5785 |  |  | DAVIDSON | YES | 2030-08-20 | 9 | CP | Yadkin | 03040103 | 110 |  |  | 110 |  |  |  | 0 | Division Review | 2026-02-15 | update 2026 add- 110’ warm stream impacts, , 0.21 acres riparian wetland, 65% | Delivery | DMS | DMS to provide all mitigation. |  |  | pushed out
BR-0184 |  |  | FORSYTH | NO | 2030-09-17 | 9 | CP | Yadkin | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-15 | No mitigable impacts | Delivery |  |  | DMS_List2025 | 2028-09-19 | pushed out
B-5674 |  | US 15 / US 501 NORTHBOUND | Durham | NO | 2030-09-17 | 5 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 | no change 2026 | Delivery |  |  | DMS_List2025 | 2028-09-19 | pushed out
B-5986 |  | NC 231 | Wake | NO | 2030-09-17 | 5 | CP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-10-11 | no reply 2026 | Delivery |  |  | DMS_List2025 | 2028-09-19 | pushed out
R-5950 |  | SR 1501 (SWIFT CREEK ROAD) | Johnston | NO | 2030-09-17 | 4 | NICP | NEUSE | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-01-25 |  | Delivery |  |  | DMS_List2025 | 2028-09-19 | pushed out
U-6111 |  | NC 58 (NASH STREET NW) | Wilson | NO | 2030-09-17 | 4 | NICP | Neuse | 03020203 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  | DMS_List2025 | 2028-09-19 | pushed out
U-6206 |  | SR 1713 (MILLER'S CHAPEL ROAD) | Wayne | YES | 2030-09-17 | 4 | NICP | NEUSE | 03020202 | 60 |  |  | 60 |  |  |  | 0 | Division Review | 2025-02-24 | updated 2025 | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2027-12-21 | pushed out
U-5706 |  | VARIOUS | Richmond | YES | 2030-10-15 | 8 | SP | YADKIN | 03040201 | 710 |  |  | 710 | 7.1 |  |  | 7.1 | DRPS | 2025-03-25 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. |  | 2032-10-19 | moved in
R-5879 |  | US 13/US 17 | MARTIN | NO | 2030-10-15 | 1 | NICP | ROANOKE | 03010107 |  |  |  | 0 |  |  |  | 0 | GIS | 2018-10-27 |  | Delivery |  |  | DMS_List2025 | 2030-10-15 | no change
I-5968 |  | I-540 | Wake | YES | 2030-10-15 | 5 | CP | NEUSE | 03020201 | 992 |  |  | 992 |  |  |  | 0 | Division Review | 2026-02-18 | No update available 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2029-10-16 | pushed out
I-6004 |  | I-40 / I-85 | Guilford | YES | 2030-10-15 | 7 | CP | Cape Fear | 03030002 | 61 |  |  | 61 | 0.01 |  |  | 0.01 | Permit Package | 2025-09-18 | updated 2026 (NWP) | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2029-10-16 | pushed out
R-5714 |  | US 601 | Surry | NO | 2030-10-15 | 11 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | EC plans | 2026-02-25 | updated 2026 | Delivery |  |  | DMS_List2025 | 2029-10-16 | pushed out
B-5718 |  | PATTON AVENUE | Guilford | NO | 2030-10-15 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | PM Review | 2026-02-25 | Have not progressed, may include the improvement as part of I-5965 | Delivery |  |  | DMS_List2025 | 2027-10-19 | pushed out
B-5768 |  |  | DAVIE | NO | 2030-10-23 | 9 | CP | Yadkin | 03040101 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-15 | No mitigable impacts | Delivery |  |  |  |  | pushed out
U-5835 |  | US 221 BUSINESS | McDowell | YES | 2030-11-19 | 13 | NM | CATAWBA | 03050101 | 100 |  |  | 100 |  |  |  | 0 | Division Review | 2021-02-04 | updated 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-11-19 | no change
U-5961 |  | NC 274 (UNION ROAD) | Gaston | YES | 2030-11-19 | 12 | SP | CATAWBA | 03050101 | 50 |  |  | 50 |  |  |  | 0 | GIS | 1999-01-01 | no reply | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-11-19 | no change
B-6050 |  | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | JOHNSTON | NO | 2030-11-19 | 4 | NICP | Neuse | 03020201 |  |  |  | 0 |  |  |  | 0 | GIS | 2019-02-13 |  | Delivery |  |  | DMS_List2025 | 2028-11-21 | pushed out
U-5766A |  | NC 160 | Mecklenburg | YES | 2030-11-19 | 10 | SP | CATAWBA | 03050103 | 113 |  |  | 113 |  |  |  | 0 | GIS | 1999-01-01 | Division Review- incomplete information 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2028-06-20 | pushed out
B-5723 |  | SR 1158 (JACKSON LAKE ROAD) | Guilford | YES | 2030-11-21 | 7 | CP | CAPE FEAR | 03030003 | 57 |  |  | 57 | 0 | 0 |  | 0 | Division Review | 2026-02-25 | Updated 2026 - removed wetland impact, added stream with 10% buffer | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-11-21 | no change
I-5712 |  | I-40 / US 421 | Guilford | YES | 2030-12-17 | 7 | CP | CAPE FEAR | 03030003 | 100 |  |  | 100 | 0.015 |  |  | 0.015 | PM Review | 2026-02-25 | ROW plans not complete yet, update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-12-17 | no change
U-5799 |  | US 21 | Iredell | NO | 2031-01-14 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-24 | no impacts 2026 | Delivery |  |  | DMS_List2025 | 2027-01-19 | pushed out
B-5725 |  | SR 1710 (GRIERS CHURCH ROAD) | Caswell | YES | 2031-01-16 | 7 | CP | ROANOKE | 03010104 | 27 |  |  | 27 | 0.081 |  |  | 0.081 | Division Review | 2026-02-26 | updated 2026 | Delivery | DMS | DMS to provide all mitigation. |  | 2031-01-16 | no change
B-5713 |  | WILLOW ROAD | Guilford | YES | 2031-01-21 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  | 0.123 |  | 0.123 | GIS | 1999-01-01 | no change to impacts 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. |  | 2031-01-21 | no change
U-5751 |  | US 401 | Wake | YES | 2031-01-21 | 5 | CP | NEUSE | 03020201 | 2000 |  |  | 2000 | 3.3 |  |  | 3.3 | Merger Materials | 2020-09-24 | emailed twice 2026 | Delivery | NCDOT | Private bank credits for streams and wetlands. |  | 2031-01-21 | no change
BR-0130 |  | I-40 | Burke | YES | 2031-01-21 | 13 | NM | CATAWBA | 03050101 | 550 |  |  | 550 |  |  |  | 0 | NRTR | 2025-09-10 | There may be non-mitigable impacts and most may be temporary over Silver cr. | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-15 | pushed out
U-4007E |  | NC 53 | Onslow | NO | 2031-01-21 | 3 | SOCP | WHITE OAK | 03030001 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-23 | No update available 2026 | Delivery |  |  | DMS_List2025 | 2030-01-15 | pushed out
U-5736 |  | NC 53 (WESTERN BOULEVARD) | Onslow | YES | 2031-01-21 | 3 | SOCP | WHITE OAK | 03030001 | 50 |  |  | 50 |  |  |  | 0 | Division Review | 2026-02-23 | no impact update 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-15 | pushed out
U-5739 |  | US 258/NC 24 (RICHLANDS HIGHWAY) | Onslow | YES | 2031-01-21 | 3 | SOCP | WHITE OAK | 03030001 | 135 |  |  | 135 | 0.1 | 0.05 |  | 0.15 | Division Review | 2026-02-23 | 2026 No impact update | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-01-15 | pushed out
BR-0025 |  | SR 1639 (MEACHAM RD) | Iredell | NO | 2031-01-21 | 12 | CP | YADKIN | 03040102 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2029-01-16 | pushed out
R-3410 |  | NC 42 | Johnston | YES | 2031-01-21 | 4 | NICP | NEUSE | 03020201 | 1893 |  |  | 1893 | 0.96 |  |  | 0.96 | Division Review | 2021-02-04 | no reply | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2029-01-16 | pushed out
B-4933 |  | NC 33 | Edgecombe | NO | 2031-01-21 | 4 | NICP | TAR-PAMLICO | 03020101 |  |  |  | 0 |  |  |  | 0 | GIS | 2026-02-19 | update 2026- currently in the process of finalizing our Hydraulic Design (BSR & Redlines) | Delivery |  |  | DMS_List2025 | 2028-01-18 | pushed out
U-6134 |  | NC 16 BYPASS | LINCOLN | YES | 2031-01-21 | 12 | SP | CATAWBA | 03050101 | 240 |  |  | 240 | 0.1 |  |  | 0.1 | EAU Review | 2018-10-27 | no reply | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2026-01-20 | pushed out
B-6003 |  | SR 1609 (BAPTIST CHURCH ROAD) | Franklin | YES | 2031-01-22 | 5 | CP | TAR-PAMLICO | 03020101 | 494 |  |  | 494 | 0.6 | 0.02 |  | 0.62 | Division Review | 2022-10-09 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. |  | 2031-01-22 | no change
U-2509AA |  | US 74 | Mecklenburg | YES | 2031-03-18 | 10 | SP | CATAWBA | 03050103 | 857 |  |  | 857 | 1.41 |  |  | 1.41 | EA Reevaluation | 2024-04-12 |  | Delivery | DMS | DMS to provide all mitigation. |  | 2031-03-18 | no change
U-5716 |  | NC 24 | Onslow | YES | 2031-03-18 | 3 | SOCP | WHITE OAK | 03030001 | 653 |  |  | 653 | 0.81 | 0.1 |  | 0.91 | EA/FONSI | 2019-01-04 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-03-19 | pushed out
U-5301 |  | US 64 | Wake | YES | 2031-04-15 | 5 | CP | NEUSE | 03020201 | 535 |  |  | 535 | 0.2391 | 0.3877 |  | 0.6268 | Division Review | 2026-02-18 | No update available 2026 | Delivery | NCDOT/DMS | Private bank credits for streams and wetlands. |  | 2031-04-15 | no change
U-3618 |  | SR 1569 (CAREY ROAD EXTENSION) | Lenoir | YES | 2031-05-20 | 2 | SICP | NEUSE | 03020202 | 626 |  |  | 626 | 1.0315 | 4.045 |  | 5.0765 | GIS | 1999-01-01 | no reply | Delivery | NCDOT/DMS | Private bank credits for streams. DMS to provide wetland credits. | DMS_List2025 | 2031-05-20 | no change
U-5941 |  | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | Wilson | YES | 2031-05-20 | 4 | NICP | NEUSE | 03020203 |  |  |  | 0 |  | 0.0466 |  | 0.0466 | GIS | 1999-01-01 | no reply | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2031-05-20 | no change
R-5927 |  | US 15 / US 501 | Moore | YES | 2031-05-20 | 8 | SP | CAPE FEAR | 03030004 | 3193.1 |  |  | 3193.1 | 4.682 |  |  | 4.682 | GIS | 2025-03-18 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-08-20 | pushed out
U-5976 |  | US 15 / US 501 | Moore | NO | 2031-05-20 | 8 | SP | Lumber | 03040203 |  |  |  | 0 |  |  |  | 0 | EAU Review | 2019-01-29 |  | Delivery |  |  | DMS_List2025 | 2030-08-20 | pushed out
B-5847 |  | SR 1709 (ROCK BARN ROAD) | Catawba | NO | 2031-05-20 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2030-05-21 | pushed out
U-5862 |  | US 17 (SHALLOTTE BYPASS) | Brunswick | YES | 2031-05-20 | 3 | SOCP | LUMBER | 03040207 | 100 |  |  | 100 | 1 | 1.15 |  | 2.15 | Division Review | 2022-10-10 | 2026 No impact update | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2030-05-21 | pushed out
HB-0033 |  | POLO ROAD | Forsyth | NO | 2031-05-20 | 9 | CP | YADKIN | 03040101 |  |  |  | 0 |  |  |  | 0 | GIS | 2026-02-18 | update 2026 -atlas estimate without study area | Delivery |  |  | DMS_List2025 | 2028-10-17 | pushed out
U-5307B |  | US 1 | Wake | YES | 2031-06-17 | 5 | CP | NEUSE | 03020201 | 1197 |  |  | 1197 | 0.79 | 0.15 |  | 0.94 | FONSI | 2026-02-18 | PM sent update 3/5/26 | Delivery | NCDOT/DMS | Private bank credits for streams and Riparian wetlands. DMS to provide Non-Riparian |  | 2040-01-01 | moved in
U-5969B |  | US 501 | Person | NO | 2031-06-17 | 5 | CP | ROANOKE | 03010104 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-18 | May contain stream impacts but no permit drawings yet developed in order to determine. | Delivery |  |  |  | 2040-01-01 | moved in
U-6114 |  | NC 62 (ALAMANCE ROAD) | Alamance | NO | 2031-06-17 | 7 | CP | Cape Fear | 03030002 |  |  |  | 0 |  |  |  | 0 | Division Review | 2026-02-25 | No impact update 2026 | Delivery |  |  |  | 2040-01-01 | moved in
B-5612 |  | NC 222 | Pitt | YES | 2031-06-17 | 2 | NICP | Tar-Pamlico | 03020103 | 216.0534 |  |  | 216.0534 | 0.086386 |  |  | 0.086386 | Division Review | 2026-02-20 | No update available 2026 | Delivery | DMS | DMS to provide all mitigation. |  | 2031-06-17 | no change
B-4636 |  | NC 24 | Sampson | YES | 2031-06-17 | 3 | SICP | CAPE FEAR | 03030006 |  |  |  | 0 | 0.39 |  |  | 0.39 | Permit Drawings | 2022-10-10 | no impact update 2025 | Delivery | DMS | DMS to provide all mitigation. | DMS_List2025 | 2029-06-19 | pushed out
A-0010AE | B-4444 | US 19/23/25/70 | Buncombe | YES | 2031-08-19 | 13 | SM | FRENCH BROAD | 06010105 |  |  | 5650 | 5650 | 0.21 |  |  | 0.21 | NRTR addendum | 2025-06-26 | No update available 2026 | Delivery | NCDOT/DMS | Private bank credits for cool streams. DMS to provide cold stream credits and wetland credits. | Now A-0010AE | 2031-01-01 | pushed out
B-4443 |  | US 19/US 23/US 25/ US 70 | Buncombe | YES | 2031-08-19 | 13 | SM | FRENCH BROAD | 06010105 |  |  | 1617 | 1617 | 0.25 | 0.02 |  | 0.27 | NRTR | 2024-04-23 | no reply 2026 |  | NCDOT/DMS | Private bank credits for cool streams. DMS to provide cold stream credits and wetland credits. | DMS_List2025 | 2029-04-17 | pushed out
I-5962 |  | I-77 | Iredell | NO | 2031-09-16 | 12 | CP | CATAWBA | 03050101 |  |  |  | 0 |  |  |  | 0 | NES Review | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2029-09-18 | pushed out
B-5356 |  | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | Guilford | NO | 2031-10-21 | 7 | CP | CAPE FEAR | 03030002 |  |  |  | 0 |  |  |  | 0 | GIS | 1999-01-01 |  | Delivery |  |  | DMS_List2025 | 2028-10-17 | pushed out
I-5966 |  | I-40 | Wake | YES | 2031-11-18 | 5 | CP | NEUSE | 03020201 | 9066 |  |  | 9066 | 2.84 |  |  | 2.84 | GIS / PJD | 2025-03-25 | The PJD submitted March 2025 is the most up to date information to pull info from - contains 9,066LF stream and 2.84ac wetland (increased from 2000 if) | Delivery | NCDOT | Private bank credits for streams and wetlands. | DMS_List2025 | 2030-11-19 | pushed out
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CPL 2/24/26
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CPL 3/25/25
Note on W79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stream note Payment into NCDOT mitigation bank(s) is proposed for permanet stream impacts associated with structures and channel relocations. 1,729LF of impacts has been mitigated for at 2:1 ratio and 260LF of impacts has been mitigated for at a 1:1 ratio. No mitigation required for remaining 839LF. Wetland Note Reply: Payment into NCDOT mitigation bank(s) is proposed for wetland impacts - mitigation has been provided for 0.114 ac of wetland impacts at a 2:1 ratio for wetlands with NCWAM score of high or medium (excluding Site 7 and 8 permanent fill in wetland amounts associated with utility maintenance corridor which is in included within the 1:1 mitigation totals). Mitigation provided for 0.405 ac of wetland impacts at a 1:1 ratio for wetlands with NCWAM rating of low. No mitigation needed for Sites 3, 7, or 8 temporary excavation as wetland soil will be retained on site and used to restore wetland areas.