## Active Merger Projects
NCDOT ACTIVE MERGER PROJECTS
TIP NO. | BRIEF DESCRIPTION | COUNTY | TIMELINE
|  |  | STIP | FUNDING AUTH. | INTERNAL | INTERNAL | EXTERNAL | SCOPING | POINT 1 | POINT 2 | POINT 2A | POINT 3 | POINT 4A | EA/DEIS | FNSI/FEIS | CP 4B/4C | CP 2A | Comments
|  |  | APPROVAL | REQUEST (PE) | SCREENING | SCOPING | SCOPING | NOTICE | DATE | DATE | DATE | DATE | DATE
A-0010AA | I-26 (US 19/US 23), SR 1781 to US 25 | Buncombe | [15 empty] | Federal Funding
A-10A | Major re-paving, bridge widening | Buncombe | [6 empty] | 2014-03-20 | 2014-03-20 | 2015-04-02
A-9-B/C | US 74, US 129 to SR 1277 | Graham | [6 empty] | 2000-04-08 | 2000-10-18 |  |  |  | DEIS - 4/81 | DSFEIS-8/08 |  | 2007-08-14 | Federal Funding
B-2500A | Bonner Bridge Phase II. PINWR | Dare | [6 empty] | 2002-07-31 | 2012-10-29 |  | 2012-10-30 | 1/30/13 : 1/14/16 | EA - 3/13 |  | 1/30/13:1/30/13 | 2012-10-29
B-2500B | Bonner Bridge Phase II. Rodanthe | Dare | [6 empty] | 2002-07-31 |  |  | 2015-06-17
B-3187 | Bridge No. 79, W. Fork Pigeon River | Haywood | [5 empty] | 2002-03-07 | 2004-04-20 | 2004-04-20 |  | N/A | N/A | CE - ?
B-4722B | US 70 Bridge | Carteret | [6 empty] | N/A | N/A |  | N/A | 2012-01-19 | CE - ?
B-4863 | Harkers Is Bridge Replacements | Carteret | [6 empty] | 2016-02-18
I-0911A | I-40, NC 801 to SR 1101 | Forsyth/Davie | [15 empty] | Federal Funding
I-2513A&B | Asheville 1-26 Connector | Buncombe | [6 empty] | 2002-01-23 | 2015-01-22 | 2015-04-02 |  |  | DEIS-10/15 |  |  | 2009-12-15 | Federal Funding
I-3306A | I-40 to Durham Co. line | Orange | [5 empty] | 2013-04-23 | 2014-09-11 | 2014-09-11 |  |  |  | CE ? |  |  |  | Federal Funding
I-3610/3802 | I-85 Improvements, incl Cabarrus Co | Rowan | [5 empty] | 2005-02-16 | 2011-01-19 | 2011-01-19 |  | 2014-03-13 | 2014-03-13 | CE - ? |  | 2014-08-13
I-3804 | I-85, Beatty Ford Rd Interchange | Rowan | [15 empty] | Federal Funding
I-3819B | I-40/I-77 Final Interchange Improvement | Irredell | [15 empty] | Federal Funding
I-4400/I4700 | I-26 Improvements, incl. Henderson County | Buncombe | [5 empty] | 2006-04-07 | 2013-06-20 | 2015-02-11 | [6 empty] | 2015-02-11 | Federal Funding
I-4409 | SR 2500, Widening and Interchange | Buncombe | [15 empty] | Federal Funding
I-4729 | I-26, Revised Interchange at US74 | Polk | [15 empty] | State Funding
I-4739 | I-40, Access Improvments at Exit 312 | Johnston | [15 empty] | Federal Funding
I-4759 | I-40/SR 1228 Grade Separation | Buncombe | [5 empty] | 2008-04-04 | 2015-10-14 | [8 empty] | Federal Funding
I-5000 | I-85/US 321 Interchange Improvements | Gaston | [13 empty] | 2015-12-09 |  | Federal Funding
I-5111 | I-40 Widening, incl. Johnston Co. | Wake | [5 empty] | 2009-02-24 | 2011-02-17 | 2011-02-17 | [6 empty] | N/A | Federal Funding
I-5506 | I-40, Aviation Prkwy Interchange Improvemt | Wake | [15 empty] | Federal Funding
I-5507 | I-485, Independ. Blvd Add Express Lanes | Mecklenburg | [15 empty] | State Funding
I-5700 | I-40, Airport Blvd. Interchange Improvemt. | Wake | [15 empty] | Federal Funding
I-5701 | I-40, I-440 to Lake Wheeler Rd Add Lanes | Wake | [15 empty] | Federal Funding
I-5702A | I-40, US 15/501 to NC 147 | Durham | [15 empty] | State Funding
I-5702B | I-40, NC147 to Wade Av. | Durham/Wake | [15 empty] | State Funding
I-5703 | I-40, I-440 Interchange Improvement | Wake | [15 empty] | Federal Funding
I-5704 | I-40, East of I-440 Add Lanes | Wake | [15 empty] | Federal Funding
I-5707 | I-40, NC 55 to NC 147 | Durham | [15 empty] | Federal Funding
I-5708 | I-440/US 1 Interchange Improvement | Wake | [15 empty] | Federal Funding
I-5710 | I-540, Leesville Rd to Falls/Neuse Ramp Mtrs | Wake | [15 empty] | Federal Funding
I-5711 | I-40/I-85, Mebane-Oaks Rd Interchange Imp | Alamance | [15 empty] | Federal Funding
I-5712 | I-40/US 421, Sandy Ridge Rd Interchange | Guilford | [15 empty] | Federal Funding
I-5714 | I-77, Gilead Road Interchange Improvement | Mecklenburg | [15 empty] | Federal Funding
I-5715 | I-77, NC73 Interchange to Split Diamond | Mecklenburg | [15 empty] | Federal Funding
I-5716 | I-40, Lenoir Rhyne Blvd Interchange | Catawba | [15 empty] | Federal Funding
I-5717 | I-77, NC 150 Interchange | Iredell | [15 empty] | Federal Funding
I-5718A-E | I-77, Add Lanes and Interchang Imprvmts. | Mecklenburg | [15 empty] | Federal Funding
I-5719 | I-85, US 321 to NC 273, Add Lanes | Gaston | [15 empty] | Federal Funding
I-5870 | I-440, New Interchange and Crabtree Impr. | Wake | [15 empty] | Federal Funding
I-5895 | I-85, US 321 to US 74 Widen Roadway | Gaston | [15 empty] | Federal Funding
I-5896 | I-85, Kivett Dr. Interchange Improvemt. | Guilford | [15 empty] | Federal Funding
I-5898 | Future I-73, US 311 Interchange Improvement | Rockingham | [15 empty] | Federal Funding
I-5899A | Future I-74, Rockinham Bypass to Laurenb. | Richmond/Scot. | [15 empty] | State Funding
I-911A | I-40/I-85 Widening, incl. Forsyth Co. | Davie | [5 empty] | 2005-11-16 | N/A | N/A |  | N/A | 2014-05-14 | EA - 7/11 |  | 2/11/15: | 2014-05-14
R-0211EC | I-485, Weddington Rd Interchange Const. | Mecklenburg | [15 empty] | State Funding
R-1015 | US 70, Havelock Bypass, incl. Pamlico Co. | Craven | [5 empty] | 1905-06-15 | N/A | N/A |  | N/A - 3/12 | 2014-08-20 | DEIS - 9/11 | FEIS: 12/15 | 2002-06-20 | 2012-07-17 | Federal Funding
R-2201 | SR 1611, Doral Drive | Forsyth | [6 empty] | N/A | N/A |  | N/A | N/A | EA -3/02 | FNSI -3/04 | 2004-05-19
R-2233B | US 221, Rutherfordton Bypass | Rutherford | [6 empty] | 2000-10-01 | 2002-04-17 |  | 2010-02-17 | 2011-04-14 | DEIS-10/08 | sFEIS - 5/11 |  | 2007-10-25 | State Funding
R-2247CD | Peace Haven Rd Interchange and Approach | Forsyth | [15 empty] | Federal Funding
R-2247EB | Winston Salem Northern Beltway | Forsyth | [15 empty] | State Funding
R-2247EC | no information | Forstyth | [15 empty] | Federal Funding
R-2307 | NC 150, incl. Catawba & Iredell Co. | Lincoln | [5 empty] | 2012-04-17 |  | 2014-08-13 | [7 empty] | Federal Funding
R-2307/I-5717 | NC 150, incl. Iredell County | Catawba | [6 empty] | 2012-12-17 | 2015-10-15 | 2015-06-10 | [6 empty] | Federal Funding
R-2310 | US 221 Upgrade | Ashe | [6 empty] | 2002-02-07 | 2002-12-11 | [6 empty] | 2004-02-13
R-2501B/C | US 1, Sandhill Road to Marston Road | Richmond | [6 empty] | 1997-10-02 | 2001-02-15 |  | 2001-02-15 | 2011-04-04 | DEIS - 9/99 | SDEIS -9/01 | 2004-02-18 | 2011-04-04
R-2507C | US 13, Eure Rd to VA | Gates | [15 empty] | State Funding
R-2511 | US 17, Beaufort/Martin Co. | Beaufort | [6 empty] | 1999-05-06 | 2011-02-17 |  | 2014-05-07 | 2014-05-07 | EA - 6/13 |  |  | 2013-04-11
R-2527/2530B | NC 24/27, incl. Stanly County, B-4974 | Montgomery | [5 empty] | 2006-01-31 | 2008-08-12 | 2008-12-11 |  | 2014-01-23 | 2014-06-18 | EA - 3/12
R-2530B | NC 24-27, Bird Rd to the Pee Dee River | Stanly | [15 empty] | State Funding
R-2544/45 | US 64, incl. Dare County | Tyrell | [5 empty] | 2006-10-30 | 2007-06-14 | 2009-10-15 |  | dnc/TBD | 2014-12-17 | DEIS - 3/12 |  |  | 2009-11-18
R-2549 | US 64/NC 18, Morganton | Burke | [6 empty] | 2001-05-16 | 2005-08-11
R-2553 | US 70, Kinston Bypass | Lenoir | [5 empty] | 2000-06-02 | 2010-10-13 | 16-Jan-14rev | 2014-04-16 | [5 empty] | 2014-04-17 | not in Merger
R-2561 | NC 87 Widening, incl. Bladen Co. | Columbus | [5 empty] | 2005-12-07 | 2007-05-24 | 2013-06-13 |  |  |  | sDEIS - 7/11 |  |  | 2010-11-09
R-2566 | NC 105, incl. Avery Co. | Watauga | [5 empty] | 2009-12-28 | 2014-08-13 | 2014-08-13 | 2015-10-14 | [6 empty] | Federal Funding
R-2568C/F | NC 109 incl. Forsyth Co. | Davidson | [5 empty] | 2003-10-14 | 2004-09-15 | 2006-08-15 |  | 2011-08-10 | 2011-08-10 | DEIS-10/10 |  |  | 2009-04-28
R-2574 | US 158, incl. Currituck Co. | Camden | [5 empty] | 2011-10-03 | 2013-09-19 | 2016-01-26
R-2576 | Mid-Currituck Bridge, Dare TBD | Currituck | [5 empty] | 2008-10-01 | 2003-09-15 | OUT |  | OUT | OUT | DEIS - 3/10 | FEIS - 2/12 |  |  | Federal Funding
R-2577AB | US 158, incl. Guilford Co. | Forsyth | [5 empty] | 2004-05-17 | 2007-08-14 | 2013-08-22 | [7 empty] | Federal Funding
R-2577C | US 158, incl. Guilford Co. | Forsyth | [5 empty] | 2004-05-17 | 2007-08-14 | 2009-02-17
R-2579 | US 158 Widening, incl. Pasquotank Co. | Gates | [5 empty] | 2005-08-18 | 2007-05-24 | 2011-11-16 |  |  |  | EA 5/29/2014 |  |  | 2012-11-06
R-2582/2584 | US 158, incl. Halifax Co. | Northampton | [5 empty] | 2002-10-17 | 2000-02-09 | 2005-08-18 |  | 2010-10-19 | 2011-02-01 | sDEIS-5/08 | sFEIS - 7/11 | 2014-10-22 | 2007-06-19
R-2593 | NC 71/211, Red Springs Bypass | Robeson | [6 empty] | 2000-04-19 | 2005-10-20 |  |  |  | EA-8/09 |  |  | 2009-03-17
R-2594 | NC 215, US 64 to SR 1326 | Transylvania | [6 empty] | 1997-08-29 | 2014-05-14 | 2014-07-02 |  |  | EA - 1/98 |  |  | 8/14/2007; 7/2/14 | State Funding
R-2597/204 | US 221, incl. McDowell Co./R-204D/E | Rutherford | [5 empty] | 2002-07-29 | 2002-10-16 | 2011-06-30 |  | 2012-11-02 | 2013-11-13 | sEA - 9/11 | sFNSI-11/13 | 8/22/13: | 2011-06-30
R-2609 | US 401, incl. Harnett & Wake Co. | Cumberland | [5 empty] | 2007-08-07 | 2010-04-20 | pending
R-2615 | US 421/321, Add Lanes | Watauga | [15 empty] | State Funding
R-2628 | Pittsboro Southern Bypass | Chatham | [6 empty] | 2002-03-14
R-2707C | Shelby Bypass, NC 226 to NC 150 | Cleveland | [15 empty] | State Funding
R-2707F | Shelby Bypass, SR 1318 to NC 226 | Cleveland | [15 empty] | State Funding
R-2721/R-2828/R-2829 | Complete 540 | Wake/Johnston | [11 empty] | DEIS: 12/15 |  |  |  | Federal and State
R-2814C | US 401, NC 96 to SR 1103 | Wake/Franklin | [15 empty] | Federal Funding
R-2822 B | NC 143 Robbinsville | Graham | [5 empty] | 2003-12-01 | 2007-01-23 | 2011-01-02 | [6 empty] | 2013-05-13
R-2828 | Future NC 540 | Wake | [15 empty] | Federal Funding
R-2829 | Future NC 540, I-40 to US 64/264 | Wake, Johnston | [15 empty] | State Funding
R-2915C | US 221, New River to NC 194 | Ashe | [15 empty] | Federal Funding
R-3100A/B/C | NC 16 Widening | Catawba | [5 empty] | 2008-09-02 | N/A | N/A |  | N/A | N/A | EA-1/26/98 | FNSI-12/7/98 | 6/19/13 : 7/22/15 |  | Federal Funding
R-3111 | US 64/601 Mocksville | Davie | [5 empty] | 2001-03-06 | 2001-09-13 | 2004-05-13
R-3116DEF | NC 12 - Hatteras | Dare | [5 empty] | 10/1//01 | 2002-07-31 | 2003-07-23
R-3300 | US 17 Hampstead Bypass, incl. Pender co. | New Hanover | [5 empty] | 2005-09-07 | 2006-09-21 | 2007-08-23 |  | 2012-05-17 | TBD | DEIS - 9/11 | SDEIS-12/13 |  | 2010-05-27
R-3302 | US 53, Burgaw Bypass | Pender | [6 empty] | 2001-10-17 | 2002-04-18 |  | 2005-07-21 |  | EA - 2/05 |  |  | 2004-07-14
R-3333 | US 401 Bus. Add Lanes | Hoke/Scotland | [15 empty] | Federal Funding
R-3407 | NC 33 Widening, incl. Pitt Co. | Edgecombe | [5 empty] | 2003-12-01 | 2005-02-17 | 2008-12-11 |  |  |  | EA-10/10 |  |  | 2008-12-11
R-3410A | NC 42, US 70 Bypass to 70 Bus. Add Lanes | Johnston | [15 empty] | State Funding
R-3410B | NC 42, NC 50 to 70 Bypass Add Lanes | Johnston | [15 empty] | State Funding
R-3419 | US 158, US 64/NC 12 to E. Currituck Add Lns | Dare | [15 empty] | State Funding
R-3434 | SR1500 Midway Road | Brunswick | [5 empty] | 2002-12-19 | 2012-09-19 | 2012-10-11 | [6 empty] | 2014-04-16
R-3603A | NC 127, SR 1400 to SR 1156 | Alex./Catawba | [15 empty] | State Funding
R-3618 | New Road, Sr1553 to NC 42 | Johnston | [15 empty] | State Funding
R-3825B | NC 42, Glen Laurel Rd to Buffaloe Road | Johnston | [15 empty] | State Funding
R-3826 | NC 125 | Martin | [5 empty] | 2002-03-03 | 2002-05-07 | 2005-10-05 |  | 2010-02-23 | 2010-02-23 | EA-5/09 | FNSI- 2/11 | 2012-07-26 | 2005-10-05 | Federal Funding
R-3830 | NC 42, Sanford to SR 1538 | Lee | [15 empty] | State Funding
R-4457 | US 158, Improve Intersection with NC12 | Dare | [15 empty] | State Funding
R-4467 | US 17 Bus - NC 37 w/B-4923 | Perquimans | [5 empty] | 2008-12-09 | 2009-07-16 | 2012-10-18 |  | 2015-01-15 | 2015-01-15 | EA - 4/13 |  |  | 2012-10-18 | State Funding
R-4707 | SR 2970, Reedy Fork Pkwy. | Guilford | [5 empty] | 2004-10-11 | 2006-09-21 | 2006-09-21 | [7 empty] | State Funding
R-4734 | Macy Grove Rd., incl. Guilford Co. | Forsyth | [5 empty] | 2008-02-02 | 2009-08-11 | 2009-08-11 |  | 2011-04-14 | 2011-04-14 | EA-10/10 | FNSI - 7/11 |  | 2009-09-16
R-4753 | NC 107, SR 1002 to NC 281 Upgrade | Jackson | [15 empty] | Federal Funding
R-4902 | I-485 Widening, US 521 to I-77 | Mecklenburg | [5 empty] | 2006-07-28 | N/A | N/A |  | N/A | N/A | ? | ? | 12/12/12:
R-5014 | Collington Rd | Dare | [15 empty] | Federal Funding
R-5020 | US 701 Bypass Widening | Columbus | [5 empty] | 2012-05-01 |  |  | 2015-03-17
R-5021 | NC 211 Widening | Brunswick | [5 empty] | 2007-07-25 | 2009-05-21 | 2009-05-21 |  | 2011-11-16 | 2012-02-09 | EA-3/11 | FNSI - 5/12 | 2014-08-21 | 2010-03-25
R-5100
R-5113 | Startown Rd Widening | Catawba | [15 empty] | State Funding
R-5311A, B | US 13/NC 11 | Hertford | [5 empty] | 2011-06-02 | 2011-09-14 | 2012-09-19 |  | 2015-04-13 |  | EA - 1/14 |  | 2016-02-18 | 2013-06-18 | Federal Funding
R-5516 | US 70 Interchange at Military Base | Craven | [15 empty] | Federal Funding
R-5705A | NC 55, Church St. To Angier Limits | Harnett | [15 empty] | State Funding
R-5705B | NC 55, Angier Limits to SR 2791 | Harnett | [15 empty] | State Funding
R-5706A | NC 73, SR 2693 to US 29 | Cabarrus | [15 empty] | State Funding
R-5706B | NC 73, SR 2693 to US 29 | Cabarrus/Meck | [15 empty] | State Funding
R-5709 | NC 211, US 15/501 to SR 1244 | Moore/Hoke | [15 empty] | State Funding
R-5721A | NC 73, NC 16 Bus. To Vance Road | Lincoln/Meck. | [15 empty] | State Funding
R-5721B | NC 73, Vance Road Extension | Mecklenburg | [15 empty] | State Funding
R-5726 | NC 211, SR 1241 to NC 73 Add Lanes | Moore | [15 empty] | State Funding
R-5731 | US 17, Chowan River to US 17 Upgrade | Bertie/Chowan | [15 empty] | State Funding
R-5743 | New Road from US 276 to US 64 | Transylvania | [15 empty] | State Funding
R-5744 | Balfour Parkway, NC 191 to US 64 | Henderson | [15 empty] | State Funding
R-5766 | NC 65/87, SR 2371 to US 158 Upgrades | Rockingham | [15 empty] | State Funding
R-5777 | US 70, SR 1124 to Proposed Havelock BP | Craven | [15 empty] | State Funding
R-616 | NC 18-268, Wilkesboro Bypass | Wilkes | [5 empty] | 1999-08-01 | 2002-08-15 | 2004-06-15
R-623 | NC 24/27, Troy Bypass | Montgomery | [6 empty] | 2001-03-08 | 2004-08-19 |  | 30-Jul-08e | 2009-01-12 | EA - 2/07 | FNSI - 4/09 | 5/16/12: 5/16/13 | 2005-03-22
U-2307B | New Road from SR 1453 to NC 127 | Catawba | [15 empty] | State Funding
U-2412A | US 311 Bypass to SR 4228 | Guilford | [15 empty] | Federal Funding
U-2509 | US 74 Independence Blvd. | Mecklenburg | [5 empty] | 2015-03-19 | 2015-03-19 | 2015-03-19 | [7 empty] | Federal Funding
U-2519AA | Fayetteville Outer Loop | Robeson | [15 empty] | State Funding
U-2519AB | Fayetteville Outer Loop | Robeson/Cumb. | [15 empty] | State Funding
U-2519BA | Fayetteville Outer Loop | Cumberland | [15 empty] | Federal Funding
U-2519BB | Fayetteville Outer Loop | Cumberland | [15 empty] | Federal Funding
U-2525 D | Greensboro Western Loop | Guilford | [6 empty] | N/A | N/A |  | N/A | 2002-07-18 | DEIS - 1/92 | FEIS - 2/95 |  |  | Federal Funding
U-2525C | Future I-840 | Guilford | [15 empty] | State Funding
U-2545 | New Road, Lexington | Davidson | [5 empty] | 2004-04-19 | 2004-05-18 | 2005-01-25 |  | 2009-04-21 | 2009-10-20 | EA-9/08 | FNSI - 5/10 |  | 2008-04-24
U-2551 | Enola Road, Morganton | Burke | [6 empty] | 2000-07-13 | 2000-07-31 |  | 2000-10-05 | N/A | EA-5/08 | FNSI-6/09
U-2579AA | Future I-74 | Forsyth | [15 empty] | Federal Funding
U-2579AB | Future I-74 | Forsyth | [15 empty] | Federal Funding
U-2579C | Future I-74 | Forsyth | [15 empty] | Federal Funding
U-2579D | Future I-74 | Forsyth | [15 empty] | State Funding
U-2579E | Future I-74 | Forsyth | [15 empty] | State Funding
U-2579F | Future I-74 | Forsyth | [15 empty] | State Funding
U-2581B | w/R-2910, US 70, incl. Alamance Co. | Guilford | [5 empty] | 2011-04-29 | 2011-10-19 | 2013-11-20 | [6 empty] | 2013-11-20
U-2703 | US 421 Relocation, Boone | Watauga | [5 empty] | 2002-09-18 | 2003-07-23 | 2006-10-23
U-2719 | I-440/US1 Improvements | Wake | [5 empty] | 2012-07-20 | 2012-08-22 | 2015-03-12 | [7 empty] | Federal Funding
U-2800/4734 | Macy Grove Rd., incl. Guilford Co. | Forsyth | [5 empty] | 2008-02-02 | 2009-08-11 | 2009-08-11 |  | 2011-04-14 | 2011-04-14 | EA-10/10 | FNSI - 7/11 | 11/8/12:1/16/13 | 2009-09-16
U-2801A | Sweeten Creek Road | Buncombe | [15 empty] | Federal Funding
U-2809A | SR 1132 (Legion Road) | Cumberland | [6 empty] | N/A | N/A |  | N/A | N/A | EA - ? | ? | 9/14/11:
U-2827B | US 158/US 421/NC 150/ Bus. 40 | Forsyth | [15 empty] | Federal Funding
U-3109 | NC 119 Relocation, Melbane | Alamance | [6 empty] | 2000-12-13 | 2002-06-13 |  | 2008-06-19 |  | DEIS - 10/07 | FEIS -7/09 | :5/14/2015 | 2006-03-16 | Federal Funding
U-3125 | US 117, Relocation and New Location | Wayne | [15 empty] | State Funding
U-3308 | NC 55 (Alston Av.) | Durham | [15 empty] | Federal Funding
U-3321 | Gaston East-West Tollway -TBD | Gaston | [5 empty] | 2002-04-04 | 2008-10-23 | 2008-10-23 |  | 10/09cond. | 2/10cond. | DEIS - 6/09 | FEIS-1/11 | 6/9/11:8/11/11 | 2008-03-03
U-3330 | US 301 Bypass | Nash | [5 empty] | 2005-03-21 | N/A | N/A |  | N/A | N/A | EA - 3/10 |  | 2014-05-08 |  | Federal Funding
U-3334B | Booker Dairy Road Extension | Johnston | [15 empty] | State Funding
U-3400 | Archdale Road, Add Lanes | Guilford/Randolph | [15 empty] | State Funding
U-3403B | NC 191 | Buncombe
U-3415 | SR 1394, Poplar Tent Road | Cabarrus | [5 empty] | 2011-12-08 | 2006-12-12 | OUT |  | OUT | OUT | CE - ?
U-3419 | NC 94 Bypass, Edenton | Chowan | [6 empty] | 2001-03-14 | 2003-03-26 |  |  |  | EA-6/08 |  |  | 2007-09-20 | not in merger (5/20/15)
U-3440 | NC 3, Kannapolis West Side Bypass | Cabarrus | [15 empty] | State Funding
U-3467 | NC 84, NC 16 to Sr 1008 | Union | [15 empty] | Federal Funding
U-3468 | US 421 Wilkesboro | Wilkes | [5 empty] | 2002-03-22 | 2002-08-15 | 2004-06-15
U-3608
U-3621A | SR 1604 (Hunter Hill Road) | Nash | [15 empty] | State Funding
U-3633 | NC 273, Mount Holly | Gaston | [5 empty] | 2004-11-10 | [7 empty] | 2014-09-17
U-3633 | NC 273, 5-lane Widening | Gaston | [5 empty] | 2008-06-06 | N/A | N/A |  | N/A | ? | ? | ? | 5/9/12:
U-3815 | US 64/264 & NC 345 | Dare | [6 empty] | 2002-07-18 | 2007-05-15 |  | 2008-09-18 | 2008-12-11 | EA - 12/07 | FNSI-7/09 | 4/15/09: | 2007-05-15
U-3831 | SR 2048 (Gordon Road) Add Lanes | New Hanover | [15 empty] | State Funding
U-4403B | 401 Bus. To 401 Bypass | Cumberland | [15 empty] | Federal FundIng
U-4403C | US 401 Bypass to I-295 | Cumberland | [15 empty] | Federal FundIng
U-4405A | US 401, Hampton Oaks Drive to US 401 Byp. | Cumberland | [15 empty] | Federal FundIng
U-4405B | US 401 Bypass to Fairway Drive | Cumberland | [15 empty] | Federal FundIng
U-4700 | US 321, incl. Caldwell & Catawba Counties | Burke | [5 empty] | 2006-03-28 | 2015-10-14 | 2015-10-14 | 2015-10-14 | [6 empty] | Federal FundIng
U-4714 | SR 1009, Trade St. to Wesley Chapel Add Ln | Meck/Union | [15 empty] | Federal FundIng
U-4738 | Cape Fear Skyway, New Road, 17 to Ind. Blvd | Brunswick/New Hanover
U-4739 | SR 3556, Add Lanes and Bridge | Buncombe | [15 empty] | State Funding
U-4751 | Military Cutoff Road Ext. | New Hanover | [5 empty] | 2005-09-07 | 2006-09-21 | 2007-08-23 |  | 2012-06-06 | 2012-08-08 | DEIS - 9/11 | SDEIS-12/13 | 2014-04-16 | 2010-05-27 | State Funding
U-4758 | Johnson St.,High Point | Guilford | [5 empty] | 2012-06-05 | ? | ? | ? | 2014-11-13 | [5 empty] | State Funding
U-4763B | Cape Fear Skyway, incl. N.H. | Brunswick | [5 empty] | 2006-01-13 | 2013-06-13 | 2013-06-13
U-4910A & B | Derita Road, Add Lanes | Cabarrus | [15 empty] | Federal FundIng
U-5006 | Firetower Rd Extension | Pitt | [5 empty] | 2012-01-03 | 2012-10-11 | 2012-10-11
U-5026 | I-95, Interchange Improvement | Nash | [15 empty] | Federal FundIng
U-5101 | Shaw Road, Widen and New Location | Cumberland | [15 empty] | Federal FundIng
U-5169 | US 311/NC 68 Interchange | Guilford | [5 empty] | 2010-12-10 | N/A | N/A |  | N/A | N/A | CE - ? |  | 10/22/15 : |  | Federal FundIng
U-5301A, B & C | US 64, Superstreet and Interchange Impr. | Wake | [15 empty] | Federal FundIng
U-5304A, B, D & E | US 15/501, Superstreet and Interchange Imp. | Orange | [15 empty] | State Funding
U-5307A, B & C | US 1, Cooridor Upgrades | Wake | [15 empty] | Federal FundIng
U-5317 | NW Judd Pkwy. Fuquay-Varina | Wake | [5 empty] | 2013-03-22 | 2013-05-15 | 2013-05-15 |  | 2015-07-16 |  |  |  |  | 2014-03-20
U-5518 | US 70 improvements | Wake | [6 empty] | 2016-03-10 | 2016-03-10 | [7 empty] | Federal FundIng
U-5526A | Independence Blvd., I-277 to Wallace Lane | Mecklenburg | [15 empty] | Federal FundIng
U-5605 | Odell Rd, Ft Bragg to NC24/NC87 Add Lns | Cumberland | [5 empty] | 2014-04-17 | 2015-12-21 | 2016-01-05 | [7 empty] | Federal FundIng
U-5606 | SR 1598, NC 11 to Reade Circle Improvement | Pitt | [15 empty] | Federal FundIng
U-5702A | NC 132, Gordan Rd to Shipyard Blvd Improv | New Hanover | [15 empty] | Federal FundIng
U-5702B | NC 132, Shipyard to US 421 Improv | New Hanover | [15 empty] | Federal FundIng
U-5704 | NC 132, Shipyard Blvd Imprvmts + 76 interch. | New Hanover | [15 empty] | Federal FundIng
U-5707 | SR 1420, Rockfish Rd to Lindsay Rd add lns | Hoke | [15 empty] | State Funding
U-5710 | US 74, Interchange with Military Cutoff Rd | New Hanover | [15 empty] | Federal FundIng
U-5713 | US 70, Grantham Rd to Neuse Rvr Br.-Freewy | Craven | [15 empty] | Federal FundIng
U-5716 | NC 24, Richland Highway Interchange | Onslow | [15 empty] | Federal FundIng
U-5720A | US 70, Lynn Rd to SR 1811 | Durham | [15 empty] | State Funding
U-5720B | US 70, Sr 1811 intersection | Durham | [15 empty] | State Funding
U-5722 | US 421 Bus. Make Complete Street | Lee | [15 empty] | State Funding
U-5727 | US1/15/501, Tramway to Pendergrass | Lee | [15 empty] | Federal FundIng
U-5731 | US 74, US17/421 Fly-Over Interchange | New Hanover | [15 empty] | State Funding
U-5733 | NC 111 Extension on New Location | Onslow | [15 empty] | State Funding
U-5735 | US 17 at Jacksonville, New Interchange | Onslow | [15 empty] | Federal FundIng
U-5740 | US 70, Morehead to Beaufort, Widen Br | Carteret | [15 empty] | State Funding
U-5741 | NC 24, NC 24 Bus. To Jacksonville Urban Area | Onslow | [15 empty] | State Funding
U-5742 | Fayetteville Comp Traffic Signal System | Cumberland | [15 empty] | Federal FundIng
U-5746 | US 401, Future 540 to SR 1010, Add Lanes | Wake | [15 empty] | State Funding
U-5748 | US 401, Ligon Mill Road Intersection Impr. | Wake | [15 empty] | State Funding
U-5751 | US 401, NC 55 Intersection Impr. | Wake | [15 empty] | Federal FundIng
U-5753 | SR 1305, Plank Rd to 401, Add Lanes | Hoke | [15 empty] | State Funding
U-5754 | US29/70/220, Florida Street Ramp Impr. | Guilford | [15 empty] | Federal FundIng
U-5765 | NC 73, SR 2316 (Northcross Av) Widening | Mecklenburg | [15 empty] | State Funding
U-5767 | US 21, Northcross Center Ct to SR 2147 | Mecklenburg | [15 empty] | State Funding
U-5768 | NC 49, John Kirk Dr to I-485, Widening | Mecklenburg | [15 empty] | State Funding
U-5771 | US 21, SR 2136 (Gilead Rd) to Holly | Mecklenburg | [15 empty] | State Funding
U-5774A | NC 54, US 15-501. Upgrade interchange | Orange | [15 empty] | Federal FundIng
U-5774B | NC 54, US 15-501 to SR 1110, Road/Insect. | Orange/Durham | [15 empty] | ?
U-5774C | NC 54, SR 1110 to I-40 | Orange/Durham | [15 empty] | Federal FundIng
U-5774E | NC 54, SR 1110 Intersec. Impr. | Durham | [15 empty] | Federal FundIng
U-5774F | I-40 and NC 54 Interchange Impr. | Durham | [15 empty] | Federal FundIng
U-5774H | NC 54, NC 751 to SR 1118 Upgrade Road | Durham | [15 empty] | State Funding
U-5790 | US 421, NC 132 to Sanders, Rd and Interch. | New Hanover | [15 empty] | Federal FundIng
U-5791 | SR 2714, NC 53 to US 17, Add Lanes | Onslow | [15 empty] | State Funding
U-5792 | US 74, College Road Interchange | New Hanover | [15 empty] | Federal FundIng
U-5793 | SR 1308, SR 1322 to Jacksonville | Onslow | [15 empty] | State Funding
U-5798 | SR 1102, US 401 to SR 1418, Add Lanes | Hoke/Cumberland | [15 empty] | State Funding
U-5799 | US 21, SR 1933 to Ft. Dobbs Rd, Add Lanes | Iredell | [15 empty] | State Funding
U-5802A | Spring Lake Bypass, Partly New Location | Cumberland | [15 empty] | State Funding
U-5802B | Spring Lake Bypass, Partly New Location | Cumberland | [15 empty] | State Funding
U-5806 | SR 2894, Intersection at Entrance 1 Kings Gr. | Cabarrus | [15 empty] | State Funding
U-5811 | SR 1002, NC 54 to I-40, Add Lanes | Wake | [15 empty] | State Funding
U-5813 | US 64, Ash. Bypass to NC 49, Add Lanes | Randolph | [15 empty] | Federal FundIng
U-5813A | US 64, Ash. Widen to 4-Lane | Randolph | [15 empty] | Federal FundIng
U-5813B | US 64, NC 49, Interchange Impr. With B-5363 | Randolph | [15 empty] | Federal FundIng
U-5816 | SR 1305, SR 1474, Add Lanes | Iredell | [15 empty] | State Funding
U-5817 | SR 1246, extension to SR 1206 w/Conn. Rds. | Iredell | [15 empty] | State Funding
U-5825A | SR 1010, Apex Peakway to Reliance | Wake | [15 empty] | State Funding
U-5825B | SR 1010, Reliance to Kildaire Farm | Wake | [15 empty] | State Funding
U-5845 | SR 1009, I-40 to Eno River, Add Lanes | Orange | [15 empty] | State Funding
U-5848 | SR 1006, Existing SR 1006 to US 70 | Orange | [15 empty] | State Funding
U-5851 | SR 1001, US 220 to E. Cone Blvd, Add Lanes | Guilford | [15 empty] | State Funding
U-5852 | SR 2085, Wendover to Holden Rd, Add Lanes | Guilford | [15 empty] | State Funding
U-5853 | SR 1301, SR 1228 to E. Lebanon Av. | Alamance | [15 empty] | State Funding
U-5857 | SR 1406, SR 1418 to Sr 1003, Add Lanes | Hoke | [15 empty] | State Funding
U-5858 | SR 1418, Fayetteville, Widen to Multilanes | Hoke | [15 empty] | State Funding
U-5862 | Shallotte Bypass, SR 1357, Upgrade Intersec. | Brunswick | [15 empty] | State Funding
U-5864 | SR 1595, I-85 to Eden Terr., Add Lanes | Randolph | [15 empty] | State Funding
U-5868 | SR 1477, SR 251/1781 to I-40, Widen Rd. | Buncombe | [15 empty] | State Funding
U-5876 | US 70, 4th St. to SR 1175, Add Lanes | Carteret | [15 empty] | State Funding
U-5881 | NC 132, SR 2048 to SR 1272, Upgrade Rd | New Hanover | [15 empty] | State Funding
U-5891 | NC 50, I-540 to NC 98, Add Lanes | Wake | [15 empty] | State Funding
U-5892 | US 220, Westridge Rd to Cotswold Av, Add Ln | Guilford | [15 empty] | Federal FundIng
U-5893 | US 311/NC14, SR 2066 Interchange Upgrade | Rockingham | [15 empty] | State Funding
U-5895 | SR 1114, to US 70, Add Lanes and Ped./Bike | Orange | [15 empty] | State Funding
U-5920 | New Route from US 17 Bus. to Sr 1349 | Brunswick | [15 empty] | State Funding
W-5522 | SR 1656, SR 1658 Ped. Tunnel at Interchange | Wake | [15 empty] | Federal Funding
W-5600 | US 70 Improvements | Johnston | [8 empty] | 2015-11-18
X-0002F | Fayetteville Outer Loop | Cumberland | [15 empty] | Federal Funding