Preliminary Hydraulic Design Deliverables for TIP Bridges

Please utilize the detailed schedule below for the delivery of Preliminary Hydraulic Design Information required for TIP Bridges that follow the Condensed Tri-Managed Bridge Process.

Submit 8 Weeks Prior to Field Scoping Meeting (FSM)

- Hydraulics Preliminary Design Report (PDR)

- Preliminary Field Visit Checklist with supporting information (i.e. sketch with bridge layout for review prior to the Pre-FSM Meeting)

- Appendix “D” (Preliminary Design and Assessment of Stream Crossings and Encroachments)

- Hydraulics portion of FSM Worksheet

Submit 4 Weeks Prior to Field Scoping Meeting (FSM)

- Draft of Final Preliminary Hydraulic Recommendations (spreadsheet and supporting information) for review

- Schedule and attend Pre-FSM with Roadway Design, Structures Management, and Hydraulics Unit

Submit 2 Weeks after the Field Scoping Meeting (FSM)

- Final Preliminary Hydraulic Recommendations (spreadsheet and supporting information)