## CustomReport
CONTRACT # | WBS ELEMENT | TIP | TYPE | DESC | COMMENTS | COUNTY | ASSIGNMENT DATE | REQUESTED COMPLETION DATE | EXTENDED COMPLETION DATE | DISTRIBUTION DATE | RESIDENT/MAINTENANCE ENG | OPERATION ENGINEER | REGION
| 48153.1.1 | P-5737 | RET WALL REVIEW | Propose to construction of grade seperation at SR 2018 (Millbrook Road) and closure of existing at-grade crossing (Crossing # 630605A) | [11/02/20 rec req from email from JRB, HDR-Beth Howey, MAW] | WAKE | 2020-11-02 | 2020-12-01 | 2024-12-20 |  |  |  | EASTERN
| 50124.1.FS1 | I-5708 | RET WALL REVIEW | I-440/US 1/ SR 2000 Interchange Conversion to a Diverging Diamond | [11/04/20 rec req from email from JRB MAW] | WAKE | 2020-11-04 | 2020-12-03 | 2024-06-21 |  |  |  | EASTERN
| 50167.1.1 | U-5747 | RET WALL REVIEW | McCrimmon Parkway Grade Separation and Widening | [03/22/2021 rec req from email from NTR Atkins - Robert Boot - MAW] | WAKE | 2021-03-22 | 2021-04-22 | 2024-12-20 |  |  |  | EASTERN
| 37512.1.5 | R-2566B | RET WALL REVIEW | NC 105 From SR 1136 in Watauga County to SR 1107 (NC 105 Bypass) | [05/26/2022 rec req from SCC email from gtaylor@rkk.com> MAW] | WATAUGA | 2022-05-26 | 2022-07-29 | 2024-05-31 |  |  |  | WESTERN
| 37512.1.5 | R-2566B | RET WALL REVIEW | NC 105 From SR 1136 in Watauga County to SR 1107 (NC 105 Bypass) | [08/22/2022 rec req from SCC email from MAW] | WATAUGA | 2022-08-22 | 2022-09-05 | 2024-05-31 |  |  |  | WESTERN
| 37512.1.5 | R-2566B | RET WALL REVIEW | NC 105 From SR 1136 in Watauga County to SR 1107 (NC 105 Bypass) | [08/22/2022 rec req from SCC email from MAW] | WATAUGA | 2022-08-22 | 2022-09-05 | 2024-05-31 |  |  |  | WESTERN
| 44369.1.3 | U-5798B | RET WALL REVIEW | Widening of SR 1420/ SR 1102 (Gillis Hill Road) From SR 1007 (Stoney Point Road) to SR 1418 (Lindsay Road) | [12/04/2023 rec req from NTR email from Riggs Jr, Abner F <Abner.RiggsJr@terracon.com> MAW] | CUMBERLAND | 2023-12-04 | 2024-01-02 | 2024-05-31 |  |  |  | EASTERN
| 47104.1.1 | R-5832 | RET WALL REVIEW | NC 88, FROM NC 88 TO NC 194. UPGRADE ROADWAY | [12/08/2023 rec req from ENW email from Div11 - J. Heath Slaughter MAW] | ASHE | 2023-12-11 | 2024-01-15 | 2024-07-31 |  |  |  | WESTERN
| ENCROACH | ENCROACH | TEMP SHORING REVIEW | TEMP SHRG for CONE MEDICAL WATER TAP ON SPERO RD | WKG DWG REVIEW -NEED PE STAMPED DWG | RANDOLPH | 2024-01-05 | 2024-01-19 | 2024-01-19 |  | J BRITT, EI | DH | WESTERN
| 44383.1.1 | U-5810 | RET WALL REVIEW | 1514 (BAMBOO ROAD) FROM US 421/US 221 TO SR 1522 (DEERFIELD ROAD). WIDEN ROADWAY TO 12-FEET LANESWITH 4-FEET PAVED SHOULDERS. | [02/06/2024 rec req from ENW email from Joey Daily <jdaily@smeinc.com> MAW] | WATAUGA | 2024-02-06 | 2024-03-05 | 2024-05-31 |  |  |  | WESTERN
| ENCROACH | ENCROACH | TEMP SHORING REVIEW | MK AT BILTMORE SOIL NAIL SHORING | REV01 WKG DWG TO SMU 3/27, FROM 3/28 -"ACCEPTED AS NOTED" | BUNCOMBE | 2024-03-18 | 2024-04-11 | 2024-04-11 | 2024-04-01 | C MEDLIN, PE | JA/DH | WESTERN
| 49907 | PO4300403995 | TEMP SHORING REVIEW | SLIDE RAIL SHRG for ALUM CULVERT ON BURNT MILL RD | WKG DWG REVIEW | FORSYTH | 2024-04-01 | 2024-04-12 | 2024-04-12 | 2024-04-02 | C WHITE | DH | WESTERN
| 44524.3.1 | ENCROACH | HAMMER | MCALPINE GREENWAY PED BRIDGE | DRVNG CRITERIA REVIEW | MECKLENBURG | 2024-04-02 | 2024-04-15 | 2024-04-15 | 2024-04-15 | B STEPHENSON, PE | CG/DH | WESTERN
| 46927.1.1 | P-5715 | RET WALL REVIEW | The project includes a bridge on New Hope Church Road over the CSX Railroad in Raleigh with an on-site detour to maintain traffic on New Hope Church Road | [04/18/2024 rec req from JP email from Smallwood, Steve <Steve.Smallwood@stantec.com> MAW] | WAKE | 2024-04-19 | 2024-05-17 |  |  |  |  | EASTERN
C203970 | 43609.3.2 | I-5507 | DB REVIEW | RW05 (SNW) AT 919+50 -L4 WEST- | NEW SNW SUB TO SMU 4/2, FROM 4/17 -"ACCEPTED AS NOTED" | MECKLENBURG | 2024-04-02 | 2024-04-15 | 2024-04-15 | 2024-04-15 | B DAVIS, PE | DH | WESTERN
C204716 | 48063.3.1 | B-5869 | HAMMER | BRIDGE #99 ON US 64 / US70 (FLEMING DR) OVER NORFOLK SOUTHERN RAILROAD | ALT HAMMER4 - INT BENT DETOUR | BURKE | 2024-04-01 | 2024-04-10 | 2024-04-10 | 2024-04-04 | T HENLEY, PE | DH | WESTERN
C204815 | 45738.3.1 | B-5783 | TEMP SHORING REVIEW | TEMP SNW for BRIDGE #164 & BRIDGE #168 ON US 29/US 70/BUS I-85 OVER NORFOLK SOUTHERN RAILROAD | WKG DWG REVIEW TO SMU 4/3, FROM 4/5 -"ACCEPTED AS NOTED" | DAVIDSON | 2024-03-21 | 2024-04-18 | 2024-04-18 | 2024-04-18 | L SHAVER | JA/DH | WESTERN
C204823 | 50230.3.1 | U-5839 | DRILLED PIER | BRIDGE #184 ON US 276 (RUSS AVE) OVER Y6 (BLUE RIDGE SOUTHERN RR) |  | HAYWOOD | 2024-03-25 | 2024-04-08 | 2024-04-08 | 2024-04-08 | M BUCHANAN, PE | JA/DH | WESTERN
C204823 | 50230.3.1 | U-5839 | HAMMER | BRIDGE #186 ON US 276 (RUSS AVE) OVER RICHLAND CREEK |  | HAYWOOD | 2024-03-18 | 2024-04-15 | 2024-04-15 | 2024-04-02 | M BUCHANAN, PE | JA/DH | WESTERN
C204828 | 17BP.14.R.204 | BRDG0032 | HAMMER | BRIDGE #32 ON NC 116 OVER SAVANNAH CREEK |  | JACKSON | 2024-03-27 | 2024-04-10 | 2024-04-10 | 2024-04-02 | N TANNER, PE | DH | WESTERN
C204828 | 17BP.14.R.204 | BRDG0032 | DRILLED PIER | BRIDGE #32 ON NC 116 OVER SAVANNAH CREEK |  | JACKSON | 2024-04-23 | 2024-05-06 | 2024-05-06 |  | N TANNER, PE | DH | WESTERN
C204851 | 34497.3.12 | R-2707D/E | HAMMER | BRIDGE #488 ON SR-2607 (FAIRVIEW RD) OVER US 74 BYPASS |  | CLEVELAND | 2024-03-14 | 2024-04-08 | 2024-04-08 | 2024-04-08 | A SCHLEY, PE | CG/DH | WESTERN
C204851 | 34497.3.12 | R-2707D/E | HAMMER | BRIDGE #101 & BRIDGE #102 OVER BUFFALO CREEK ON US 74 |  | CLEVELAND | 2024-03-14 | 2024-04-03 | 2024-04-03 | 2024-04-03 | A SCHLEY, PE | JA/DH | WESTERN
DK00346 | BP11.R005.3 | BRDG0015 | HAMMER | BRIDGE #15 ON SR-1315 (ZEPHYR MTN PARK RD) OVER MITCHELL RIVER |  | SURRY | 2024-03-28 | 2024-04-12 | 2024-04-12 | 2024-04-02 | R MILES | DH | WESTERN
DK00346 | BP11.R005.3 | BRDG0015 | DRILLED PIER | BRIDGE #15 ON SR-1315 (ZEPHYR MTN PARK RD) OVER MITCHELL RIVER |  | SURRY | 2024-04-12 | 2024-04-25 | 2024-04-25 | 2024-04-22 | R MILES | DH | WESTERN
DK00392 | BP11.R022.3 | BRDG0180 | HAMMER | BRIDGE #180 OVER TOMS CREEK ON SR-1953 (W. DODSON MILL RD) |  | SURRY | 2024-04-22 | 2024-05-10 | 2024-05-10 |  | R MILES | JA/DH | WESTERN
DK00392 | BP11.R022.3 | BRDG0180 | DRILLED PIER | BRIDGE #180 OVER TOMS CREEK ON SR-1953 (W. DODSON MILL RD) |  | SURRY | 2024-04-17 | 2024-04-30 | 2024-04-30 |  | R MILES | JA/DH | WESTERN
DM00327 | 17BP.13.R.172 | BRDG0145 | TEMP SHORING REVIEW | TEMP SNW for GRAVIX WALL CONSTRUCTION | WKG DWG REVIEW | MADISON | 2024-04-23 | 2024-05-20 | 2024-05-20 |  | C JUSTICE, PE | JA/DH | WESTERN
DM00344 | 17BP.13.R.183 | BRDG0144 | TEMP SHORING REVIEW | TEMP SHRG for BRIDGE #144 OVER BIG PINE CREEK ON BIG PINE RD (SR-1151) | REV01 for ANCHORED -"ACCEPTED" | MADISON | 2024-04-12 | 2024-04-18 | 2024-04-18 | 2024-04-16 | C JUSTICE, PE | CG/DH | WESTERN
DM00425 | BP13.R019.3 | BRDG0023 | TEMP SHORING REVIEW | TEMP SNW (TS #3) for BRIDGE #23 OVER PAINT FORK CREEK ON SR-1530 (PAINT FORK RD) | WKG DWG REVIEW TO SMU 4/18 | MADISON | 2024-04-12 | 2024-05-09 | 2024-05-09 |  | C JUSTICE, PE | JA/DH | WESTERN
DM00425 | BP13.R019.3 | BRDG0023 | TEMP SHORING REVIEW | TEMP SNW (TS #1) for BRIDGE #23 OVER PAINT FORK CREEK ON SR-1530 (PAINT FORK RD) | WKG DWG REVIEW TO SMU 4/8 | MADISON | 2024-04-04 | 2024-05-01 | 2024-05-01 |  | C JUSTICE, PE | JA/DH | WESTERN
DN01044 | 17BP.14.R.156 | BRDG0236 | HAMMER | BRIDGE #236 ON SR-1396 OVER L PRONG BURNINGTOWN CREEK |  | MACON | 2024-03-15 | 2024-04-02 | 2024-04-02 | 2024-04-02 | A DOCKERY, PE | CG/DH | WESTERN