## Sheet1
Task # | Start Date | Finish Date | Administrative Unit | External WBS# | Work Function | Inventory Element | NCDOT SYSTEM NAME | Route/County | Lane Direction | Lane | Offset | From MP | To MP | Asset Type | WORK ACCOMP | Labor Cost ($) | Equipment Cost ($) | Material Cost ($) | Other Cost | Total
225312 | 2006-03-20 | 2006-03-22 08:00 | 04 Bri Smithfield | 4B.105111 | 4533-MAINT DRAINAGE SYST | B051 0056 | Prim Paved Brdg (Maint) | [6 empty] | Bridge Inventory | 84 | 2301.72 | 322.8 | 93.24 | 53.06 | 2770.82
928212 | 2013-03-21 | 2015-01-05 | 04 Bri Smithfield | 17BP.4.P.3 | 2909-Manual Brush and Tree Control | B051 0056 | All (Any DOH Rd Syst) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 526.67 | 159.69 | 19.88 | 0 | 838.29 | 1017.86
1011133 | 2014-05-06 | 2014-09-05 | 04 Bri Smithfield | 4B.105111 | 3306-Maintain Concrete Superstructure Components | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 16 | 10537.85 | 7898.6 | 0 | 592.27 | 19028.72
1030758 | 2014-08-06 | 2014-09-05 | 04 Bri Smithfield | 4B.105111 | 3348-Maintain Concrete Substructure Components | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 32 | 4198.32 | 3525.75 | 0 | 876.4 | 8600.47
1275897 | 2017-06-30 | 2017-06-30 | 04 Bri Smithfield | 4B.205111 | 3309C-Replacement of Bridge Expansion Joints | B051 0056 | Sec Paved Brdg (Malnt) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 0
1362068 | 2018-08-14 | 2018-10-23 | 04 Bri Smithfield | 4BPR.10511 | 3352-Maint Slope Protection | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 0 | 3980.33 | 1268.8 | 0 | 1742.99 | 6992.12
1440652 | 2019-10-21 | 2019-10-21 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 1380 | 549.68 | 36.54 | 0 | 0 | 586.22
1441839 | 2019-10-30 | 2019-10-30 | 04 Bri Smithfield | 4B.105111 | 2714-Assessments and Inspections | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 9 | 353.78 | 18.6 | 0 | 0 | 372.38
1493836 | 2021-01-28 | 2021-01-28 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 0
1527671 | 2021-08-04 11:16 | 2021-08-04 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 0
1527842 | 2021-08-04 15:22 | 2021-08-04 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 0 | 1016.7 | 161.15 | 0 | 0 | 1177.85
1565461 | 2022-01-13 09:44 | 2022-01-13 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 6657 | 936.84 | 108 | 0 | 0 | 1044.84
1619101 | 2022-07-04 | 2022-09-26 | 04 Bri Smithfield | 4BPR.10511 | 3318-Maintenance of Concrete Barrier Rail | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 110 | 26262.01 | 11655.63 | 387.16 | 2403.84 | 40708.64
1623481 | 2022-07-13 17:02 | 2022-07-13 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 6657 | 630.44 | 41.5 | 0 | 0 | 671.94
1632502 | 2022-08-08 06:40 | 2022-08-08 | 04 Bri Smithfield | 4BPR.10511 | 3376-Clean / Wash Bridge Decks | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 6657 | 738.72 | 60.72 | 0 | 0 | 799.44
1632958 | 2022-08-08 15:44 | 2022-08-08 | 04 Bri Smithfield | 4BPR.10511 | 3310-Maintenance / Repair Bridge Expansion Joints | B051 0056 | Prim Paved Brdg (Maint) | 20000301051 | All | All | 0 | 12.939 | 12.939 | Bridge Inventory | 85 | 875.74 | 60.72 | 0 | 0 | 936.46
[19 empty] | Total: | 84707.76