## Projected 25-Year Spending
Maintenance/ Preservation Estimate - Existing 880007 Bridge
Year | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
Activity
Bridge Tender | 148100 | 152543 | 157119.29 | 161832.8687 | 166687.8548 | 171688.4904 | 176839.1451 | 182144.3195 | 187608.6491 | 193236.9085 | 199034.0158 | 205005.0363 | 211155.1873 | 217489.843 | 224014.5383 | 230734.9744 | 237657.0236 | 244786.7343 | 252130.3364 | 259694.2465 | 267485.0739 | 275509.6261 | 283774.9149 | 292288.1623 | 301056.8072
Routine Maintenance | 82000 | 84000 | 43000 | 44000 | 68000 | 93000 | 95000 | 49000 | 50000 | 77000 | 105000 | 108000 | 55000 | 57000 | 87000 | 119000 | 122000 | 62000 | 64000 | 98000 | 134000 | 138000 | 71000 | 72000 | 111000
Electrical/ Mechanical Routine Maintenance | 82000 | 84000 | 43000 | 44000 | 68000 | 93000 | 95000 | 49000 | 50000 | 77000 | 105000 | 108000 | 55000 | 57000 | 87000 | 119000 | 122000 | 62000 | 64000 | 98000 | 134000 | 138000 | 71000 | 72000 | 111000
Preservation Project - Pile Jackets |  |  | 13100000 | [14 empty] | 19000000
Preservation Project - Bent Caps | [7 empty] | 975000 | [9 empty] | 1200000
Preservation Project - Superstructure Repairs | [12 empty] | 900000 | [9 empty] | 1100000
Preservation Project - Deck Overlay and Joint Seals | [7 empty] | 6700000 | [9 empty] | 8800000
Preservation Project - Electrical/ Mechanical/ Swing Span | [19 empty] | 14200000
Yearly Total: | 312100 | 320543 | 13343119.29 | 249832.8687 | 302687.8548 | 357688.4904 | 366839.1451 | 7955144.3195 | 287608.6491 | 347236.9085 | 409034.0158 | 421005.0363 | 1221155.1873 | 331489.843 | 398014.5383 | 468734.9744 | 481657.0236 | 29368786.7343 | 380130.3364 | 14655694.2465 | 535485.0739 | 551509.6261 | 1525774.9149 | 436288.1623 | 523056.8072
[24 empty] | 25-Year Total: | 75550617.0461
Maintenance/ Preservation Estimate - Replacement 880007 Bridge
Year | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
Activity
Bridge Complete in 2025 |  |  |  | 6647 | 6813 | 6984 | 7158 | 7337 | 7521 | 7709 | 7901 | 8099 | 8301 | 8509 | 8722 | 8940 | 9163 | 9392 | 9627 | 9868 | 10114 | 10367 | 10626 | 10892 | 11164
Silane Deck Treatment | [12 empty] | 7300000 | [9 empty] | 9000000
Modular Joint replacement | [24 empty] | 1600000
Yearly Total: | 0 | 0 | 0 | 6647 | 6813 | 6984 | 7158 | 7337 | 7521 | 7709 | 7901 | 8099 | 7308301 | 8509 | 8722 | 8940 | 9163 | 9392 | 9627 | 9868 | 10114 | 10367 | 9010626 | 10892 | 1611164
[24 empty] | 25-Year Total: | 18091854

## Bridge Maintenance History
Task # | Administrative Unit | Work Function | WBS | Comments | Start Date | Finish Date | Plan Amount | Work Accomplished | Labor Cost ($) | Equipment Cost ($) | Material Cost ($) | Other Cost | Total Cost ($) | Yearly Cost ($) | SFY | Status | Completion Date | User Update | Date Update | Att. | Asset Type | DC LAB EXISTS | DC EQP EXISTS | DC MAT EXISTS | DC ACC EXISTS | DC CST EXISTS | WO LOCATION EXISTS
1522747 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1BPR.10891 |  | 2021-07-12 | 2022-06-15 | 500 | 308 | 12321.03 | 2106.62 | 0 | 32.75 | 14460.4 | 126079.3057 | 2022 | Active |  | CCBANTOS | 2021-07-15 13:30 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
1593617 | 01 Bri Creswell | 3376-Clean / Wash Bridge Decks (SFT) | 1B.108911 |  | 2022-04-18 10:30 | 2022-04-29 | 4333.3333 | 2000 | 1271.8233 | 168.845 | 0 | 0 | 1440.6683 |  |  | Active |  | JSHASSELL1 | 2022-04-18 10:31 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1582200 | 01 Bridge Office | 3338C-Moveable Bridges (Operations) (DOL) | 1B.108914.2 | Bridge Tending | 2022-03-05 | 2022-04-01 | 61000 | 61000 | 0 | 0 | 0 | 61000 | 61000 |  |  | Active |  | CCBANTOS | 2022-03-15 08:41 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
1533431 | 01 Bridge Office | 3376C-Clean / Wash Bridge Decks (SFT) | 1BPR.10891 |  | 2021-08-25 07:57 | 2022-03-31 | 3959250.5806 | 20029.9355 | 0 | 0 | 0 | 400.5987 | 400.5987 |  |  | Active |  | BAHARRISON | 2021-08-25 07:58 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
1527128 | 01 Bridge Office | 3338C-Moveable Bridges (Operations) (DOL) | 1B.108911 | Alligator | 2021-07-31 | 2022-03-29 | 140904 | 48377.04 | 0 | 0 | 0 | 48377.04 | 48377.04 |  |  | Active |  | CCBANTOS | 2021-08-03 08:36 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
1532585 | 01 Bridge Office | 3376C-Clean / Wash Bridge Decks (SFT) | 1BPR.10891 |  | 2021-08-20 12:01 | 2021-11-17 | 3959250.5806 | 20029.9355 | 0 | 0 | 0 | 400.5987 | 400.5987 |  |  | Active |  | CCBANTOS | 2021-08-20 12:11 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
1511326 | 01 Bri Creswell | 3318-Maintenance of Concrete Barrier Rail (LFT) | 1BPR.10891 | RAIL REPLACEMENT | 2021-05-15 | 2021-07-30 | 16 | 32 | 8044.1 | 6178.34 | 152.35 | 0 | 14374.79 | 27780.26 | 2021 | Active |  | JSHASSELL1 | 2021-05-17 11:45 |  | Bridge Inventory | 1 | 1 | 1 | 1 | 0 | 1
1437051 | 01 Bri Creswell | 3318-Maintenance of Concrete Barrier Rail (LFT) | 1BPR.10891 | Fixing rail that was hit | 2019-09-25 | 2021-06-25 | 25 | 25 | 8602.95 | 4387.02 | 0 | 0 | 12989.97 |  |  | Active |  | MGWHITE | 2019-09-26 08:39 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1481454 | 01 Bri Creswell | 2914-Vegetation Management at Stationary Objects (LFT) | 1B.108911 | BUSHING BRIDGES | 2020-10-06 | 2021-03-18 | 950 | 950 | 365.9 | 49.6 | 0 | 0 | 415.5 |  |  | Active |  | JSHASSELL1 | 2020-10-06 14:45 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1533433 | 01 Bridge Office | 3376C-Clean / Wash Bridge Decks (SFT) | 1BPR.10891 | Tyrell # 07,02 | 2021-08-25 07:59 |  | 3959250.5806 |  | 0 | 0 | 0 |  | 0 |  |  | Active |  | BAHARRISON | 2021-08-25 08:01 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
1311281 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1BPR.10891 | Working on draw and house. | 2017-12-12 | 2020-08-14 | 100 | 1311 | 48117.96 | 6601.3 | 0 | 674 | 55393.26 | 55393.26 | 2019 | Completed | 2019-02-14 10:27 | MGWHITE | 2019-02-14 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
1296633 | 01 Bri Creswell | 2724-Construction Inspection (HR) | 46478.3.1 | Bridge was hit. | 2017-10-01 | 2017-10-02 | 40 | 53 | 2753.53 | 551.9 | 0 | 0 | 3305.43 |  |  | Completed | 2019-02-14 | MGWHITE | 2019-02-14 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1277354 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Working on draw. | 2017-07-09 | 2017-12-08 | 100 | 337.5 | 10480.44 | 1781.97 | 0 | 246.94 | 12509.35 | 96931.79 | 2018 | Completed | 2017-12-12 | MGWHITE | 2017-12-12 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
911135 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Maint. to Draw | 2013-01-03 | 2017-08-18 | 500 | 2364.5 | 67835.03 | 15234.46 | 6.42 | 1346.53 | 84422.44 |  |  | Completed | 2017-07-10 06:21 | MGWHITE | 2017-07-10 |  | Bridge Inventory | 1 | 1 | 1 | 1 | 1 | 1
1181025 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Truck hit gates. | 2016-07-03 | 2016-07-05 | 8 | 34 | 979.66 | 244.05 | 0 | 0 | 1223.71 | 1223.71 | 2017 | Completed | 2017-03-22 10:44 | MGWHITE | 2017-03-22 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1146118 | 01 Bri Creswell | 3318-Maintenance of Concrete Barrier Rail (LFT) | 1B.108911 | Remove truck,clean up oil repair rail. | 2016-02-16 | 2016-02-29 | 5 |  | 7379.51 | 2183.83 | 65.82 | 20.25 | 9649.41 | 16032.06 | 2016 | Completed | 2016-06-28 07:49 | MGWHITE | 2016-06-28 |  | Bridge Inventory | 1 | 1 | 1 | 0 | 1 | 1
1118625 | 01 Bri Creswell | 3326-Maintain Concrete Deck (SFT) | 1B.108911 | Patching holes in deck. | 2015-10-07 | 2015-12-08 | 50 | 9 | 3216.18 | 641.2 | 0 | 0 | 3857.38 |  |  | Completed | 2016-06-28 07:39 | MGWHITE | 2016-06-28 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1058314 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Car hit gate. | 2015-01-20 | 2015-01-20 | 4 | 28 | 751.04 | 83.6 | 0 | 0 | 834.64 |  |  | Completed | 2016-04-25 11:15 | MGWHITE | 2016-04-25 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1047959 | 01 Bri Creswell | 3102-Removal of Hazards/Debris From ROW (HR) | 1B.108911 | Picking up debris | 2014-10-31 | 2014-12-19 | 8 | 37 | 871.35 | 292.32 | 0 | 0 | 1163.67 |  |  | Completed | 2016-04-25 11:13 | MGWHITE | 2016-04-25 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1046690 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Replace gate that was hit. | 2014-10-25 | 2014-10-27 | 5 | 16 | 425.52 | 101.44 | 0 | 0 | 526.96 |  |  | Completed | 2016-04-25 11:11 | MGWHITE | 2016-04-25 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
984402 | 01 Bri Creswell | 3362-Maintenance and Repair of Fender System (LFT) | 1B.108911 | Repair fender system | 2013-11-20 | 2014-07-01 | 100 |  | 103934.75 | 11481.42 | 18598.58 | 1500.54 | 135515.29 | 155700.65 | 2015 | Completed | 2014-09-03 13:51 | MGWHITE | 2014-09-03 |  | Bridge Inventory | 1 | 1 | 1 | 0 | 1 | 1
965752 | 01 Bri Creswell | 3348-Maintain Concrete Substructure Components (SFT) | 1B.108911 | Repair of bent | 2013-08-21 | 2013-08-28 | 3 | 80 | 7777.39 | 5148.98 | 0 | 0 | 12926.37 |  |  | Completed | 2014-09-03 13:38 | MGWHITE | 2014-09-03 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
965751 | 01 Bri Creswell | 3306-Maintain Concrete Superstructure Components (SFT) | 1B.108911 | Repair girder and pier | 2013-08-21 | 2013-12-02 | 10 | 15 | 3759.01 | 1375.42 | 0 | 0 | 5134.43 |  |  | Completed | 2014-09-03 13:38 | MGWHITE | 2014-09-03 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
965749 | 01 Bri Creswell | 3326-Maintain Concrete Deck (SFT) | 1B.108911 | Repair concrete deck | 2013-08-21 | 2013-08-30 | 5 | 3 | 1591.82 | 532.74 | 0 | 0 | 2124.56 |  |  | Completed | 2014-09-03 13:38 | MGWHITE | 2014-09-03 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
965747 | 01 Bri Creswell | 3348-Maintain Concrete Substructure Components (SFT) | 1B.108911 | Repair concrete piles | 2013-08-21 | 2013-08-21 | 50 |  | 0 | 0 | 0 | 0 | 0 |  |  | Completed | 2014-09-03 13:37 | MGWHITE | 2014-09-03 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
1005934 | 01 Bridge Office | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1B.108911 | Concrete Asphalt Deck Repair | 2014-03-28 | 2014-04-10 | 64 | 3076 | 0 | 0 | 0 | 6767.2 | 6767.2 | 6767.2 | 2014 | Completed | 2014-04-22 12:47 | CCSPRUILL | 2014-04-22 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
700277 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Move contractor barge | 2010-08-31 | 2010-09-08 | 8 | 114 | 2297.01 | 1433.58 | 0 | 0 | 3730.59 | 86661.01 | 2013 | Completed | 2013-01-07 12:29 | MGWHITE | 2013-01-07 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
865773 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Fix gate | 2012-05-30 | 2012-06-01 | 4 | 28 | 626.12 | 123.2 | 0 | 0 | 749.32 |  |  | Completed | 2012-11-27 12:35 | MGWHITE | 2012-11-27 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
693298 | 01 Bri Creswell | 2714-Assessments and Inspections (HR) | 1B.102811 | Inspection steel | 2010-08-13 | 2010-08-18 | 8 | 131 | 2817.19 | 3015 | 0 | 0 | 5832.19 |  |  | Completed | 2012-11-27 12:31 | MGWHITE | 2012-11-27 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
633632 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Maint. to draw | 2010-01-22 | 2012-12-18 | 40 | 2493 | 55734.45 | 11163.99 | 2.97 | 1308.32 | 68209.73 |  |  | Completed | 2012-08-28 14:17 | MGWHITE | 2012-08-28 |  | Bridge Inventory | 1 | 1 | 1 | 1 | 1 | 1
580489 | 01 Bri Creswell | 3318-Maintenance of Concrete Barrier Rail (LFT) | 1B.108911 | Hit by car | 2009-06-22 | 2009-06-23 08:00 | 5 |  | 110.97 | 18.9 | 0 | 0 | 129.87 |  |  | Completed | 2012-07-20 13:29 | MGWHITE | 2012-07-20 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
460264 | 01 Bri Creswell | 3326-Maintain Concrete Deck (SFT) | 1B.108911 | Patching deck on top side | 2008-03-25 | 2008-03-27 08:00 | 50 |  | 3630.12 | 752.51 | 0 | 0 | 4382.63 |  |  | Completed | 2012-07-19 14:22 | MGWHITE | 2012-07-19 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
450563 | 01 Bri Creswell | 3362-Maintenance and Repair of Fender System (LFT) | 1B.108911 | Fix walkway on fender system | 2008-02-22 | 2008-02-25 | 40 |  | 2846.6 | 780.08 | 0 | 0 | 3626.68 |  |  | Completed | 2012-07-19 14:15 | MGWHITE | 2012-07-19 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
632262 | 01 Bri Harbinger | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1SP.10894.1 | Exp. Jt. Maint. Tyrrell Primary & Secondary | 2010-01-19 | 2010-01-19 08:00 | 1500 |  | 0 | 0 | 0 | 0 | 0 | 552.9797 | 2012 | Completed | 2011-08-02 08:48 | JCRANK | 2011-08-02 |  | Sections | 0 | 0 | 0 | 0 | 0 | 1
632537 | 01 Bri Harbinger | 3102-Removal of Hazards/Debris From ROW (HR) | 1B.108911 | Remove Hazards Tyrrell Primary | 2010-01-20 | 2011-05-17 | 15 | 4.5 | 111.153 | 48.2 | 0 | 0 | 159.353 |  |  | Completed | 2011-07-29 12:41 | JCRANK | 2011-07-29 |  | Sections | 1 | 1 | 0 | 1 | 0 | 1
632238 | 01 Bri Harbinger | 3376-Clean / Wash Bridge Decks (SFT) | 1SP.10894.1 | Clean/Wash Bridge Decks Tyrrell Primary & Secondary | 2010-01-19 | 2011-06-15 | 6000 | 10101.3 | 214.0272 | 179.5995 | 0 | 0 | 393.6267 |  |  | Completed | 2011-07-29 11:23 | JCRANK | 2011-07-29 |  | Sections | 1 | 1 | 0 | 1 | 0 | 1
632224 | 01 Bri Harbinger | 3314-Maintain / Repair Steel Superstructure Components (LFT) | 1SP.10894.1 | Tyrrell Co Maintain Steel Superstr Components - Washing | 2010-01-19 | 2010-01-19 08:00 | 1040 |  | 0 | 0 | 0 | 0 | 0 |  |  | Completed | 2011-07-29 10:38 | JCRANK | 2011-07-29 |  | Sections | 0 | 0 | 0 | 0 | 0 | 1
684086 | 01 Bridge Office | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1SP.10894.1 | New Joints & E-Crete Placed | 2010-04-30 | 2010-07-29 | 8250 |  | 0 | 0 | 0 | 346536.1 | 346536.1 | 346536.1 | 2011 | Completed | 2010-07-29 | JABEL | 2011-09-29 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 1 | 1
599860 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Doing maint to draw | 2009-09-02 | 2010-01-03 | 40 | 382.5 | 9939.06 | 3137.13 | 0 | 0 | 13076.19 | 39929.3454 | 2010 | Completed | 2010-01-22 | MGWHITE | 2010-01-22 10:45 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
573135 | 01 Bri Creswell | 3318-Maintenance of Concrete Barrier Rail (LFT) | 1B.108911 | Car hit rail | 2009-05-24 | 2009-06-10 | 10 | 18 | 7584.13 | 770.19 | 84.5 | 0 | 8438.82 |  |  | Completed | 2010-01-22 | MGWHITE | 2010-01-22 10:39 |  | Bridge Inventory | 1 | 1 | 1 | 1 | 1 | 1
575214 | 01 Bri Creswell | 3336-Moveable Bridges (Maintenance) (HR) | 1B.108911 | Car hit gate | 2009-06-02 | 2009-06-02 08:00 | 1 | 35 | 929.15 | 148.45 | 0 | 0 | 1077.6 |  |  | Completed | 2010-01-22 | MGWHITE | 2010-01-22 10:41 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
550438 | 01 Bri Harbinger | 3376-Clean / Wash Bridge Decks (SFT) | 1SP.10894.1 | Clean/Wash Bridge Decks Tyrrell Primary & Secondary | 2009-02-11 | 2010-01-19 | 17647.0588 | 2468.2588 | 173.5235 | 161.0954 | 0 | 2.0753 | 336.6942 |  |  | Completed | 2010-01-19 | JCRANK | 2010-01-19 12:36 |  | Sections | 1 | 1 | 0 | 1 | 1 | 1
568193 | 01 Bri Harbinger | 3314-Maintain / Repair Steel Superstructure Components (LFT) | 1SP.10894.1 | Tyrrell Co Maintain Steel Superstr Components - Washing | 2009-06-25 | 2009-10-05 08:00 | 130 | 921.31 | 672.3067 | 213.2845 | 0 | 0 | 885.5912 |  |  | Completed | 2010-01-19 | JCRANK | 2010-01-19 11:34 |  | Sections | 1 | 1 | 0 | 1 | 0 | 1
551066 | 01 Bri Harbinger | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1SP.10894.1 | Exp. Jt. Maint. Tyrrell Primary & Secondary | 2009-02-16 | 2009-02-16 08:00 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Completed | 2010-01-19 | JCRANK | 2010-01-19 14:56 |  | Sections | 0 | 0 | 0 | 0 | 0 | 1
288351 | 01 Bri Creswell | 4622-MAINT RC COL & PILES (LFT) | 1B.108911 | concrete work to piling and girders | 2006-10-03 | 2007-07-03 08:00 | 0 | 0 | 8754.97 | 3845.61 | 0 | 0 | 12600.58 |  |  | Completed | 2010-01-13 | MGWHITE | 2010-01-13 15:47 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
282500 | 01 Bri Creswell | 4591-MAINT DRAW SPAN (HR) | 39423 | Prompt Action (Gear # 58 ) | 2006-09-05 | 2006-09-09 | 0 | 91 | 1999.41 | 1514.46 | 0 | 0 | 3513.87 |  |  | Completed | 2010-01-13 | MGWHITE | 2010-01-13 16:26 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
471011 | 01 Bri Harbinger | 3376-Clean / Wash Bridge Decks (SFT) | 1B.108911 | Clean/Wash Bridge Deck Tyrrell Primary Bridges | 2008-05-06 | 2009-01-29 | 105000 | 48026.16 | 983.4405 | 719.4852 | 0 | 0 | 1702.9257 | 1702.9257 | 2009 | Completed | 2008-12-16 | JCRANK | 2009-02-12 22:22 |  | Sections | 1 | 1 | 0 | 1 | 0 | 1
146543 | 01 Bri Creswell | 4591-MAINT DRAW SPAN (HR) | 1B.108911 |  | 2005-06-27 | 2005-06-27 08:00 | 18 | 18 | 332.1 | 0 | 0 | 0 | 332.1 | 332.1 | 2006 | Completed | 2005-08-11 | GWOODLEY | 2005-08-11 15:06 |  | Bridge Inventory | 1 | 0 | 0 | 1 | 0 | 1
86383 | 01 Bri Creswell | 4591-MAINT DRAW SPAN (HR) | 1B.108911 | Maintennace to bridge superstructure ( repair to girders) | 2004-10-29 | 2004-10-29 05:00 | 25 | 25 | 545.35 | 152.25 | 0 | 0 | 697.6 | 4821.89 | 2005 | Completed | 2004-11-03 | DBARNES | 2004-11-03 11:31 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
86361 | 01 Bri Creswell | 4688-REPL BRIDGE SUPERSTRUC (SFT) | 1B.108911 | Maintenance to bridge superstructure ( repair to girders) | 2004-10-28 | 2004-10-28 08:00 | 0 | 0 | 1066.08 | 92.8 | 0 | 0 | 1158.88 |  |  | Completed | 2004-11-03 | DBARNES | 2004-11-03 11:31 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
86065 | 01 Bri Creswell | 4591-MAINT DRAW SPAN (HR) | 1B.108911 | Draw span maintenance | 2004-10-27 | 2004-10-27 08:00 | 24 | 24 | 471.84 | 136.53 | 0 | 0 | 608.37 |  |  | Completed | 2004-11-03 | DBARNES | 2004-11-03 11:31 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
86064 | 01 Bri Creswell | 4688-REPL BRIDGE SUPERSTRUC (SFT) | 1B.108911 | Maintenance to bridge superstructure (repair to girders) | 2004-10-27 | 2004-10-27 08:00 | 0 | 0 | 594.24 | 328.88 | 0 | 0 | 923.12 |  |  | Completed | 2004-11-03 | DBARNES | 2004-11-03 11:31 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
86063 | 01 Bri Creswell | 4688-REPL BRIDGE SUPERSTRUC (SFT) | 1B.108911 | Maintenance of bridge superstructure (repair to girder) | 2004-10-26 | 2004-10-26 08:00 | 0 | 0 | 1226.44 | 207.48 | 0 | 0 | 1433.92 |  |  | Completed | 2004-11-03 | DBARNES | 2004-11-03 14:42 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
19606 | 01 Bri Creswell | 4661-MAINT FENDER SYST (HR) | 1B.108911 |  | 2004-02-06 01:00 | 2004-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2004 | Completed | 2004-02-03 | GWOODLEY | 2004-02-03 10:04 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
[14 empty] | 840365.2808 | 60026.0915

## Preservation Work
Pile Repairs in 2025
From 03/23/2022 Inspection Report: |  |  |  | Cracking, spalls, delaminations, exposed strand and reinforcing
1268 piles in CS3
Assume pile jackets for all CS3 piles
Assume 8-foot length per jacket; structural jacket
| Qty. of Piles | Length/ Pile | Cost/ LF | Total
Cost: | 1268 | 8 | 1000 | 10144000
|  |  | Add 20% for contingency: | 12172800 | in 2022
|  |  |  | 13100000 | in 2025
Anticipate additional pile work at 15 years after this work, similar quantity; say, $ 19.0M
Cap repairs in 2030
From 03/23/2022 Inspection Report: |  |  |  | Cracking, spalls, delaminations, exposed reinforcing
Assume all of cracking and delam/ spall areas will need repair - say 123' crack injection; say 433' x 3' x 0.5' - 650 CF spall repairs
| Inject Length | Cost/ LF | Subtotal
Cost: | 123 | 130 | 15990
| Shotcrete Area | Cost/ SF | Subtotal
Cost: | 650 | 1000 | 650000
|  | Total: | 665990
|  | Add 20% for contingency: | 799188 | in 2022
|  |  | 975000 | in 2030
Anticipate additional pile work at 10 years after this work, similar quantity; say, $ 1.2M
Super Repairs in 2035
From 03/23/2022 Inspection Report: |  |  |  | Cracking, spalls, delaminations, exposed strand and reinforcing
Assume all of cracking and delam/ spall areas will need repair - say 66' crack injection; say 888' x 2' x 0.25' - 444 CF spall repairs
| Inject Length | Cost/ LF | Subtotal
Cost: | 66 | 130 | 8580
| Shotcrete Area | Cost/ SF | Subtotal
Cost: | 444 | 1200 | 532800
|  | Total: | 541380
|  | Add 20% for contingency: | 649656 | in 2022
|  |  | 900000 | in 2035
Anticipate additional pile work at 10 years after this work, similar quantity; say, $ 1.1K
New Overlay and joints in 2030
Recent thin epoxy overlay completed in approximately 2019; lifespan of thin epoxy overlay is 8-10 years; replace every 10 years
Epoxy | Length | Width | Cost/ SF | Subtotal
Cost: | 14961 | 26 | 10 | 3889860
| Joint Length | # of Joints | Cost/ SF | Subtotal
Cost: | 26 | 344 | 70 | 626080
|  |  | Total: | 4515940
|  |  | Add 20% for contingency: | 5419128 | Current costs
|  |  |  | 6700000 | Costs in 2030
|  |  |  | 8800000 | Costs in 2040

## Mech-Elec Work 2017
BID PRICES FROM 2017 REHABILITATION OF MECHANICAL, ELECTRICAL, CONTROLS OF SWING SPAN:
AUXILIARY OPERATING SYSTEM |  | 909000
BRIDGE CONTROL SYSTEM |  | 350000
CENTER WEDGE MACHINERY |  | 145000
CENTERING DEVICE MACHINERY |  | 100000
CONTROL HOUSE RENOVATIONS |  | 330000
DISCONNECT SWITCHES |  | 14000
DRY TYPE TRANSFORMER |  | 4500
ELECTRICAL DEMOLITION |  | 57000
ELECTRICAL REFURBISHING |  | 73000
END WEDGE MACHINERY |  | 500000
FIELD MEASURING |  | 75000
GROUNDING |  | 10000
HVAC UNIT |  | 14000
JUNCTION AND PULL BOXES |  | 26000
LIGHTING |  | 13000
MOTOR CONTROL CENTER |  | 125000
MOTORS |  | 90000
OPERATION & MAINT MANUALS, TRAINING & AS-BUILT |  | 100000
DOCUMENTA-TION
PANELBOARD |  | 5000
RACEWAY |  | 250000
SIREN |  | 5000
STABILIZING MACHINERY |  | 275000
START UP & COMMISSIONING |  | 75000
SUBMARINE CABLE |  | 150000
SWITCHES AND RECEPTACLES |  | 7500
TURNING MACHINERY |  | 2820000
UTIL SER, MED VOLT EQUIP, AUTO TRANSFER SWITCH & |  | 1500000
GENERATOR
WIRE AND CABLE |  | 75000
| TOTAL: | 8098000
ANTICIPATE MECH/ ELEC. CONT REHABILITATION AT 25 YEARS; SIMILAR SCOPE, SAY $ 14M FOR INFLATION
1.7784
8000000
14226920

## 270054 Maintenance
Task # | Administrative Unit | Work Function | WBS | Comments | Start Date | Finish Date | Plan Amount | Work Accomplished | Labor Cost ($) | Equipment Cost ($) | Material Cost ($) | Other Cost | Total | Status | Completion Date | User Update | Date Update | Att. | Asset Type | DC LAB EXISTS | DC EQP EXISTS | DC MAT EXISTS | DC ACC EXISTS | DC CST EXISTS | WO LOCATION EXISTS
1552185 | 01 Bri Creswell | 3376-Clean / Wash Bridge Decks (SFT) | 1BPR.10281 |  | 2021-11-09 08:09 | 2022-04-08 | 208333.3333 | 50616.6667 | 1215.6867 | 210.5233 | 0 | 0 | 1426.21 | Active |  | CCBANTOS | 2021-11-09 08:15 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1548758 | 01 Bridge Office | 3376C-Clean / Wash Bridge Decks (SFT) | 1BPR.10281 |  | 2021-10-26 09:56 | 2022-03-21 | 2697511.3846 | 925705.8462 | 0 | 0 | 0 | 18514.1169 | 18514.1169 | Active |  | BAHARRISON | 2021-10-26 10:03 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
1532574 | 01 Bridge Office | 3376C-Clean / Wash Bridge Decks (SFT) | 1BPR.10281 |  | 2021-08-20 11:05 | 2021-11-17 | 2697511.3846 | 925705.8462 | 0 | 0 | 0 | 18514.1169 | 18514.1169 | Active |  | CCBANTOS | 2021-08-20 11:08 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
1481440 | 01 Bri Creswell | 2914-Vegetation Management at Stationary Objects (LFT) | 1B.102811 | BUSHING BRIDGES | 2020-10-06 | 2021-03-11 | 521.4286 | 521.4286 | 99.2879 | 14.4914 | 0 | 0 | 113.7793 | Active |  | JSHASSELL1 | 2020-10-06 14:18 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
1500416 | 01 Bri Creswell | 3348-Maintain Concrete Substructure Components (SFT) | 1BPR.10281 | PATCHING CONCRETE | 2021-03-10 | 2021-03-10 | 600 |  | 0 | 0 | 0 |  | 0 | Completed | 2022-03-14 13:47 | JSHASSELL1 | 2021-03-10 15:03 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
1363780 | 01 Bri Creswell | 3332-Maintenance Drainage System - Bridge (LFT) | 1BPR.10281 | Cleaning drainage system | 2018-08-21 | 2018-08-22 | 100 | 0 | 3230.9 | 1245.25 | 0 |  | 4476.15 | Active |  | MGWHITE | 2018-08-21 13:50 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
1255789 | 01 Bri Creswell | 3376-Clean / Wash Bridge Decks (SFT) | 1B.102811 | Sweeping bridges | 2017-05-24 | 2017-06-27 | 650000 | 1657920 | 4348.71 | 1544.94 | 0 | 652 | 6545.65 | Completed | 2019-02-14 10:28 | MGWHITE | 2019-02-14 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
1261885 | 01 /1 Dare Mnt | 3120C-Install / Repair / Maintain Barriers (LFT) | 1.102820 | 25 ft of steel beam, 8 post | 2017-04-12 | 2017-05-10 | 25 |  | 0 | 0 | 0 |  | 0 | Active |  | JWHOADLEY | 2017-06-06 10:31 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
1239888 | 01 Bri Creswell | 3306-Maintain Concrete Superstructure Components (SFT) | 1B.102811 | Patching concrete | 2017-05-01 | 2017-05-09 | 15 | 0 | 6337.11 | 3729.39 | 0 |  | 10066.5 | Active |  | JSHASSELL1 | 2017-05-02 11:46 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
1192122 | 01 Bri Elizabeth City | 3376-Clean / Wash Bridge Decks (SFT) | 1B.102811 | sweep deck | 2016-08-16 | 2016-09-15 | 5 | 1737540 | 3239.07 | 1035.24 | 0 | 38.35 | 4312.66 | Completed | 2017-01-03 11:18 | JPLANE | 2017-01-03 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
1010566 | 01 Bri Creswell | 3376-Clean / Wash Bridge Decks (SFT) | 1B.102811 | Cleaning bridge decks | 2014-05-02 | 2014-05-21 | 100 | 7500 | 19383.09 | 8182.3 | 0 | 42.45 | 27607.84 | Completed | 2014-09-03 13:53 | MGWHITE | 2014-09-03 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
1005931 | 01 Bridge Office | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1B.102811 | Concrete | 2014-03-15 | 2014-04-10 | 6 | 684 | 0 | 0 | 0 | 1504.8 | 1504.8 | Completed | 2014-04-22 12:47 | CCSPRUILL | 2014-04-22 |  | Bridge Inventory | 0 | 0 | 0 | 1 | 1 | 1
632250 | 01 Bri Harbinger | 3376-Clean / Wash Bridge Decks (SFT) | 1SP.10284.1 | Clean/Wash Br. Decks Dare Primary & Secondary | 2010-01-19 | 2011-07-29 | 12000 | 66622.99 | 530.9696 | 662.435 | 0 | 7.4128 | 1200.8174 | Completed | 2011-07-29 11:24 | JCRANK | 2011-07-29 |  | Sections | 1 | 1 | 0 | 1 | 1 | 1
632694 | 01 Bri Harbinger | 3102-Removal of Hazards/Debris From ROW (HR) | 1B.102811 | Remove Hazards Dare Primary | 2010-01-20 | 2011-07-22 | 35 | 24.185 | 602.1967 | 224.6335 | 0 | 0 | 826.8302 | Completed | 2011-07-29 12:43 | JCRANK | 2011-07-29 |  | Sections | 1 | 1 | 0 | 1 | 0 | 1
680764 | 01 Bri Creswell | 3334-Bridge Bearings (EA) | 1B.102811 | Putting pad back under bearing | 2010-07-06 | 2010-08-02 | 1 | 1 | 3963.69 | 1914.68 | 0 | 1800 | 7678.37 | Completed | 2012-11-27 11:13 | MGWHITE | 2012-11-27 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 1 | 1
550429 | 01 Bri Harbinger | 3376-Clean / Wash Bridge Decks (SFT) | 1SP.10284.1 | Clean/Wash Br. Decks Dare Primary & Secondary | 2009-04-08 | 2010-01-28 | 65000 | 73828.56 | 1073.9599 | 759.7707 | 0 | 36.7133 | 1870.4439 | Completed | 2010-01-19 | JCRANK | 2010-01-19 12:36 |  | Sections | 1 | 1 | 0 | 1 | 1 | 1
632281 | 01 Bri Harbinger | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1SP.10284.1 | Exp.Jt. Maint. Dare Primary & Secondary | 2010-01-19 | 2010-01-19 08:00 | 100 |  | 0 | 0 | 0 | 0 | 0 | Completed | 2011-08-02 08:49 | JCRANK | 2011-08-02 |  | Sections | 0 | 0 | 0 | 0 | 0 | 1
628480 | 01 Bri Creswell | 3100-Snow and Ice (HR) | 1B.102811 | Put brine on bridges | 2010-01-08 | 2010-01-08 08:00 | 10 |  | 0 | 0 | 0 | 0 | 0 | Completed | 2012-07-20 13:30 | MGWHITE | 2012-07-20 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
551083 | 01 Bri Harbinger | 3310-Maintenance / Repair Bridge Expansion Joints (LFT) | 1SP.10284.1 | Exp.Jt. Maint. Dare Primary & Secondary | 2009-07-28 | 2009-08-18 08:00 | 7692.3077 | 107.6923 | 465.2488 | 400.48 | 0 | 0 | 865.7288 | Completed | 2010-01-19 | JCRANK | 2010-01-19 14:55 |  | Sections | 1 | 1 | 0 | 1 | 0 | 1
470935 | 01 Bri Harbinger | 3376-Clean / Wash Bridge Decks (SFT) | 1B.102811 | Clean/Wash Bridge Deck Dare Primary Bridges | 2008-04-29 | 2009-01-07 | 277500 | 589980.54 | 4238.683 | 2378.2453 | 0 | 76.849 | 6693.7773 | Completed | 2008-12-16 | JCRANK | 2009-02-12 22:23 |  | Sections | 1 | 1 | 0 | 1 | 1 | 1
473179 | 01 Bri Creswell | 3334-Bridge Bearings (EA) | 1B.102811 | Pa on bridge bearing pads | 2008-05-06 | 2008-09-16 | 4 |  | 12462.31 | 3527.19 | 0 | 1497.8 | 17487.3 | Completed | 2012-07-19 14:23 | MGWHITE | 2012-07-19 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 1 | 1
495833 | 01 Bri Harbinger | 3312-Maint/Replace/Repair Modular Bridge Joints (LFT) | 1B.102811 | Maintenance to Modular Exp. Jts. - Cleaning Jts. Va. Dare Bridge | 2008-07-21 | 2008-09-10 08:00 | 15000 | 3140 | 12130.74 | 6737.95 | 0 | 0 | 18868.69 | Completed | 2010-01-19 | JCRANK | 2010-01-19 12:37 |  | Bridge Inventory | 1 | 1 | 0 | 1 | 0 | 1
481617 | 01 Bri Creswell | 3326-Maintain Concrete Deck (SFT) | 1B.102811 | Doing P.A. | 2008-06-03 | 2008-07-15 | 10 |  | 5051.55 | 2075.85 | 0 | 0 | 7127.4 | Completed | 2012-07-19 14:23 | MGWHITE | 2012-07-19 |  | Bridge Inventory | 1 | 1 | 0 | 0 | 0 | 1
465514 | 01 Bri Harbinger | 3132-Sweep / Wash Roadway (SHM) | 1B.102811 | Sweep VA. Dare Bridge # 54 Dare (Croatan Sound) | 2008-04-11 | 2008-04-11 08:00 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | Completed | 2008-04-29 | JCRANK | 2008-04-29 08:29 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
1548760 | 01 Bridge Office | 3376C-Clean / Wash Bridge Decks (SFT) | 1BPR.10281 |  | 2021-10-26 10:03 |  | 2697511.3846 |  | 0 | 0 | 0 |  | 0 | Active |  | BAHARRISON | 2021-10-26 10:06 |  | Bridge Inventory | 0 | 0 | 0 | 0 | 0 | 1
[12 empty] | Total: | 155701.1807
[12 empty] | Annual Average: | 10380.0787
[12 empty] | Length: | 27580
[12 empty] | Width: | 63
[12 empty] | Area: | 1737540
[12 empty] | Annual Average/ SF: | 0.005974

## Preserv-Maint on New Bridge
Consider:
Length: | 16000
Width: | 63
Assume: | 100 spans
25 modular joints
4' closure for each modular joint
Replace modulars in 20 years
Silane Deck
Area | Cost/ SF | Cost
1008000 | 5 | 5100000 | 2022 | Apply 10 years after bridge completion in 2025 - includes re-striping
|  | 7030000 | 2035
|  | 9000000 | 2045
Modular Replacement
Area | Cost/ SY | Cost
700 | 1300 | 910000 | in 2022
|  | 1600000 | in 2042
Annual Maintenance
|  |  | 270054 Annual Average/ SF: | 0.005974
|  |  | 880007 Projected Annual Average: | 6021.8006 | in 2022