## Construction Cashflow
MID-CURRITUCK BRIDGE
QUARTERLY CASH FLOW ($M) - ANTICIPATED EXPENDITURES THROUGHOUT CONSTRUCTION | [25 empty] | 2024-04-15
|  |  |  | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031
| DESCRIPTION/YEAR | Cost Estimate ($M) | Prior Expenditures | Apr-Jun 26 | Jul-Sept 26 | Oct-Dec 26 | Jan-Mar 27 | Apr-Jun 27 | Jul-Sept 27 | Oct-Dec 27 | Jan-Mar 28 | Apr-Jun 28 | Jul-Sept 28 | Oct-Dec 28 | Jan-Mar 29 | Apr-Jun 29 | Jul-Sept 29 | Oct-Dec 29 | Jan-Mar 30 | Apr-Jun 30 | Jul-Sept 30 | Oct-Dec 30 | Jan-Mar 31 | Apr-Jun 31 | Jul-Sept 31 | Oct-Dec 31
|  |  |  | Q4 FY26 | Q1 FY27 | Q2 FY27 | Q3 FY27 | Q4 FY27 | Q1 FY28 | Q2 FY28 | Q3 FY28 | Q4 FY28 | Q1 FY29 | Q2 FY29 | Q3 FY29 | Q4 FY29 | Q1 FY30 | Q2 FY30 | Q3 FY30 | Q4 FY30 | Q1 FY31 | Q2 FY31 | Q3 FY31 | Q4 FY31 | Q1 FY32 | Q2 FY32
MID-CURRITUCK BRIDGE | Construction | 795.009 | 0 | 3.975 | 7.9501 | 7.9501 | 15.9002 | 15.9002 | 43.7255 | 39.7505 | 39.7505 | 47.7005 | 47.7005 | 39.7505 | 39.7505 | 47.7005 | 47.7005 | 39.7505 | 39.7505 | 47.7005 | 39.7505 | 39.7505 | 39.7505 | 39.7505 | 39.7505 | 23.8503
| Toll Integration | 6.157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18471 | 0.30785 | 0.6157 | 0.6157 | 1.2314 | 1.2314 | 1.2314 | 0.43099 | 0.30785 | 0
| Landscaping | 0.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2725 | 0.2725
| Right of Way | 20.673 | 0 | 0.20673 | 0.41346 | 2.0673 | 4.1346 | 4.1346 | 4.1346 | 3.5144 | 2.0673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Utilities | 20.448 | 0 | 0.20448 | 0.40896 | 2.0448 | 4.0896 | 4.0896 | 4.0896 | 3.4762 | 2.0448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agency Costs:
| NCDOT Labor and Expenses | 25.654 | 0 | 0.25654 | 0.51308 | 0.51308 | 0.51308 | 0.51308 | 1.0262 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.2827 | 1.5392 | 1.5392
| Change Order Allowance | 42.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42756 | 0.42756 | 2.1378 | 2.1378 | 2.1378 | 2.1378 | 2.1378 | 2.1378 | 4.2756 | 2.1378 | 2.1378 | 4.2756 | 4.2756 | 2.1378 | 2.1378 | 3.4205 | 2.1378 | 2.1378
| Public Education / Outreach | 0.164 | 0 | 0 | 0 | 0 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082 | 0.0082
| CEI and Materials Testing | 41.855 | 0 | 0 | 0 | 0 | 0.8371 | 0.8371 | 0.8371 | 1.6742 | 1.6742 | 2.0928 | 2.5113 | 2.0928 | 2.0928 | 2.5113 | 2.5113 | 2.0928 | 2.0928 | 2.5113 | 2.5113 | 2.0928 | 2.0928 | 2.5113 | 3.3484 | 2.9299
| Stipends / Incentives | 3.43 | 0 | 0 | 3.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Environmental Mitigation | 4.389 | 0 | 0 | 4.389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surcharges | 33.768 | 0 | 0.33768 | 0.67536 | 0.67536 | 0.67536 | 1.013 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884 | 1.6884
| Fuel Reserve | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0.06 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| AC Reserve | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0.045 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.15 | 0.15 | 0.075 | 0.075 | 0.15 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075
| Engineering Reserve Fund | 8.552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4276 | 0.4276 | 0.4276 | 0.4276 | 0.4276 | 0.4276 | 0.8552 | 0.4276 | 0.4276 | 0.8552 | 0.8552 | 0.4276 | 0.4276 | 0.8552 | 0.4276 | 0.4276
| Agency Reserve Fund | 8.552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4276 | 0.4276 | 0.4276 | 0.4276 | 0.4276 | 0.4276 | 0.8552 | 0.4276 | 0.4276 | 0.8552 | 0.8552 | 0.4276 | 0.4276 | 0.8552 | 0.4276 | 0.4276
| PROJECT SUB-TOTAL | 1015.452 | 0 | 4.9805 | 17.78 | 13.2506 | 26.1581 | 26.4958 | 56.0071 | 51.9271 | 51.6841 | 55.9406 | 56.3591 | 47.9905 | 47.9905 | 56.5341 | 59.7118 | 48.2984 | 48.6062 | 60.1428 | 52.6334 | 49.2219 | 49.2219 | 50.9779 | 50.083 | 33.4565
| PROJECT COST FOR FINANCING | 1015.452 | 0 | 4.9805 | 17.78 | 13.2506 | 26.1581 | 26.4958 | 56.0071 | 51.9271 | 51.6841 | 55.9406 | 56.3591 | 47.9905 | 47.9905 | 56.5341 | 59.7118 | 48.2984 | 48.6062 | 60.1428 | 52.6334 | 49.2219 | 49.2219 | 50.9779 | 50.083 | 33.4565
P/E | Additional P/E | 72.8896 |  | 3.6445 | 7.289 | 10.9334 | 10.9334 | 7.289 | 3.6445 | 3.6445 | 2.9156 | 2.9156 | 2.9156 | 2.9156 | 2.9156 | 2.9156 | 2.9156 | 2.9156 | 2.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prior Expenditures | 50.6475 | 50.6475
| PROJECT TOTAL (TIFIA ELIGIBLE) | 1138.9891 | 50.6475 | 8.625 | 25.0689 | 24.1841 | 37.0916 | 33.7848 | 59.6516 | 55.5716 | 54.5996 | 58.8562 | 59.2747 | 50.9061 | 50.9061 | 59.4497 | 62.6274 | 51.2139 | 50.7929 | 60.1428 | 52.6334 | 49.2219 | 49.2219 | 50.9779 | 50.083 | 33.4565
| DESCRIPTION/YEAR | Cost Estimate ($M) | Prior Expenditures | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
MID-CURRITUCK BRIDGE | Construction | 795.009 | 0 | 19.8752 | 115.2763 | 174.902 | 174.902 | 166.9519 | 143.1016 | 0
| Toll Integration | 6.157 | 0 | 0 | 0 | 0 | 0.49256 | 3.6942 | 1.9702 | 0
| Landscaping | 0.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0.545 | 0
| Right of Way | 20.673 | 0 | 2.6875 | 15.9182 | 2.0673 | 0 | 0 | 0 | 0
| Utilities | 20.448 | 0 | 2.6582 | 15.745 | 2.0448 | 0 | 0 | 0 | 0
| Agency Costs: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NCDOT Labor and Expenses | 25.654 | 0 | 1.2827 | 3.335 | 5.1308 | 5.1308 | 5.1308 | 5.6439 | 0
| Change Order Allowance | 42.756 | 0 | 0 | 0.85512 | 8.5512 | 10.689 | 12.8268 | 9.8339 | 0
| Public Education / Outreach | 0.164 | 0 | 0 | 0.0328 | 0.0328 | 0.0328 | 0.0328 | 0.0328 | 0
| CEI and Materials Testing | 41.855 | 0 | 0 | 4.1855 | 8.371 | 9.2081 | 9.2081 | 10.8823 | 0
| Stipends / Incentives | 3.43 | 0 | 3.43 | 0 | 0 | 0 | 0 | 0 | 0
| Environmental Mitigation | 4.389 | 0 | 4.389 | 0 | 0 | 0 | 0 | 0 | 0
| Surcharges | 33.768 | 0 | 1.6884 | 5.0652 | 6.7536 | 6.7536 | 6.7536 | 6.7536 | 0
| Fuel Reserve | 2 | 0 | 0 | 0.1 | 0.4 | 0.6 | 0.5 | 0.4 | 0
| AC Reserve | 1.5 | 0 | 0 | 0.075 | 0.3 | 0.45 | 0.375 | 0.3 | 0
| Engineering Reserve Fund | 8.552 | 0 | 0 | 0 | 1.7104 | 2.138 | 2.5656 | 2.138 | 0
| Agency Reserve Fund | 8.552 | 0 | 0 | 0 | 1.7104 | 2.138 | 2.5656 | 2.138 | 0
| PROJECT SUB-TOTAL | 1015.452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PROJECT COST FOR FINANCING | 1015.452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P/E | Additional P/E | 72.8896 |  | 21.8669 | 25.5114 | 11.6623 | 11.6623 | 2.1867 | 0 | 0
| Prior Expenditures | 50.6475 | 50.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PROJECT TOTAL (TIFIA ELIGIBLE) | 1138.9891 | 50.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Aggregate | Prior | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
| NCTA Costs | 842.832 |  | 25.221 | 146.9395 | 179.0141 | 175.3945 | 170.6461 | 145.6169 | 0
| Agency Costs | 172.62 |  | 10.7901 | 13.6486 | 32.9602 | 37.1403 | 39.9583 | 38.1225 | 0
| Additional P/E | 72.8896 |  | 21.8669 | 25.5114 | 11.6623 | 11.6623 | 2.1867 | 0 | 0
| Prior Costs | 50.6475 | 50.6475
| Grand Total | 1138.9891 | 50.6475 | 57.8779 | 186.0995 | 223.6366 | 224.1972 | 212.7911 | 183.7393 | 0