## R-2576
TIP No. R-2576 |  | R/W |  | County: | Currituck & Dare
Route: Mid-Currituck Bridge From US 158 South of Coinjock
| To NC 12 South of Corolla |  |  |  | CONSTR. COST
Typical Section: 2-Lane |  |  |  |  | 761700000
Design-Build
914100000
Prepared By: Lochner |  |  | Date | 2024-02-07
Requested By: | HNTB/Turnpike (Travis Feltes) |  | Date | 2024-02-07
Priced By: | Dan Shuller, Sherry Sockwell/Forrest Dungan (Struc), Greg Hall (Lighting), Todd Lapham (UC), |  | Date | unit price updates 3/4/2024
| Zach Little (Signals), Mitch Eaton (Sign), Alla Lyudmirskaya and Zachary Clark (TC), David Jones (ITS, Tolling) |  |  | ITS/Tolling update 3/7/2024
Sec No. | Description | Quantity | Unit | Price | Amount
| Mobilization | 1 | LS | 29361431.25 | 29361431.25
ROADWAY | Clearing and Grubbing | 21.3 | Acre | 45000 | 958500
| Supplemental Clearing and Grubbing | 3 | Acre | 10000 | 30000
| Unclassified Excavation | 57040 | CY | 20 | 1140800
| Borrow Excavation | 1001230 | CY | 16 | 16019680
| Drainage Ditch Excavation | 1380 | CY | 18 | 24840
| Removal of Existing Asphalt Pavement | 7810 | SY | 10.5 | 82005
| Breaking of Existing Asphalt Pavement | 23740 | SY | 4.5 | 106830
| Temporary Shoring | 26320 | SF | 57 | 1500240
| Foundation Conditioning Material, Minor Structures | 1180 | Tons | 67 | 79060
| Foundation Conditioning Geotextile | 3660 | SY | 4.1 | 15006
| 15" Side Drain Pipe | 760 | LF | 95 | 72200
| 18" Side Drain Pipe | 194 | LF | 115 | 22310
| 24" Side Drain Pipe | 20 | LF | 175 | 3500
| 15" Side Drain Pipe Elbows | 12 | Each | 765 | 9180
| 15" CAA Pipe Culverts, 0.064" Thick | 156 | LF | 125 | 19500
| 42" X 29" CAA Structural Platepipe Arch, 0.105" Thick | 272 | LF | 500 | 136000
| 15" Rc Pipe Culverts, Class III | 460 | LF | 80 | 36800
| 18" Rc Pipe Culverts, Class III | 360 | LF | 100 | 36000
| 24" Rc Pipe Culverts, Class III | 840 | LF | 120 | 100800
| 30" Rc Pipe Culverts, Class III | 268 | LF | 178 | 47704
| 15" RC Pipe Culverts, Class IV | 4464 | LF | 105 | 468720
| 18" RC Pipe Culverts, Class IV | 464 | LF | 130 | 60320
| 24" RC Pipe Culverts, Class IV | 560 | LF | 150 | 84000
| 36" RC Pipe Culverts, Class IV | 88 | LF | 300 | 26400
| 42" RC Pipe Culverts, Class IV | 308 | LF | 325 | 100100
| 18" RC Pipe Culverts, Class V | 820 | LF | 120 | 98400
| 24" RC Pipe Culverts, Class V | 556 | LF | 165 | 91740
| 30" RC Pipe Culverts, Class V | 380 | LF | 210 | 79800
| Pipe Removal | 1965 | LF | 33 | 64845
| Fine Grading | 148070 | SY | 2.5 | 370175
| Aggregate Base Course | 34500 | Tons | 57 | 1966500
| Shoulder Borrow | 14640 | CY | 20 | 292800
| Asphalt Conc Base Course, Type B25.0C | 40100 | Tons | 75 | 3007500
| Asphalt Conc Binder Course, Type I19.0C | 27300 | Tons | 80 | 2184000
| Asphalt Conc Surface Course, Type S9.5B | 8300 | Tons | 80 | 664000
| Asphalt Conc Surface Course, Type S9.5C | 22800 | Tons | 80 | 1824000
| Asphalt Binder for Plant Mix | 5050 | Tons | 700 | 3535000
| Permeable Asphalt Drainage Course | 300 | Tons | 144 | 43200
| 12" Port Cem Conc Pavement, Through Lanes (With Dowels) | 1636 | SY | 210 | 343560
| 7" Jointed Concrete Pavement (Reinforced) | 550 | SY | 130 | 71500
| Number 57 Stone | 770 | CY | 70 | 53900
| 8" Pervious Concrete Pavement | 1000 | CY | 110 | 110000
| Masonry Drainage Structures | 69 | Each | 4200 | 289800
| Masonry Drainage Structures | 4 | LF | 950 | 3800
| Frame with Two Grates, 840.16 | 14 | Each | 1300 | 18200
| Frame with Two Grates, 840.20 | 42 | Each | 1300 | 54600
| Frame with Two Grates, 840.22 | 6 | Each | 1300 | 7800
| Frame with Two Grates, 840.29 | 4 | Each | 1300 | 5200
| Frame with Cover, Std 840.54 | 2 | Each | 1050 | 2100
| Steel Frame with Two Grates, 840.37 | 16 | Each | 3450 | 55200
| Frame with Grate and Hood 840.03, Type G | 1 | Each | 1250 | 1250
| 8"x18" Concrete Curb | 360 | LF | 47 | 16920
| 1'-6" Concrete Curb and Gutter | 440 | LF | 40 | 17600
| 2'-6" Concrete Curb and Gutter | 450 | LF | 50 | 22500
| Shoulder Berm Gutter | 3610 | LF | 41 | 148010
| 4" Concrete Paved Ditch | 30 | SY | 225 | 6750
| 5" Monolithic Concrete Islands (Surface Mounted) | 2460 | SY | 90 | 221400
| Concrete Barrier, Type T | 1510 | LF | 200 | 302000
| Variable Height Concrete Barrier, Type T1 | 3330 | LF | 230 | 765900
| Precast Reinforced Concrete Barrier, Single Faced | 1850 | LF | 120 | 222000
| Impact Attenuator Units, Type TL-3 | 8 | Each | 20000 | 160000
| Steel Beam Guardrail | 4900 | LF | 27 | 132300
| Steel Beam Guardrail Terminal Sections | 8 | Each | 100 | 800
| Additional Guardrail Posts | 5 | Each | 55 | 275
| Guardrail Anchor Units, Type II | 2 | Each | 3300 | 6600
| Guardrail Anchor Units, Type III | 13 | Each | 3650 | 47450
| Guardrail End Units, Type CAT-1 | 9 | Each | 1050 | 9450
| Guardrail Anchor Units, Type B-77 | 18 | Each | 3000 | 54000
| Temporary Steel Beam Guardrail | 300 | LF | 12 | 3600
| Temporary Guardrail Anchor Units, Impact Attenuator | 1 | Each | 13500 | 13500
| Temporary Guardrail End Units, Type III | 2 | Each | 1275 | 2550
| Double Faced Cable Guiderail | 810 | LF | 12 | 9720
| Cable Guiderail Anchor Units | 2 | Each | 4000 | 8000
| Woven Wire Fence, 47" Fabric | 21770 | LF | 5.25 | 114292.5
| 4" Timber Fence Posts, 7'-6" Long | 1391 | Each | 35 | 48685
| 5" Timber Fence Posts, 8'-0" Long | 300 | Each | 45 | 13500
| Preformed Scour Holes With Level Spreader Apron | 2 | Each | 3000 | 6000
| Rip Rap, Class I | 550 | Tons | 80 | 44000
| Rip Rap, Class II | 680 | Tons | 80 | 54400
| Rip Rap, Class VII | 630 | Tons | 100 | 63000
| Rip Rap, Class A | 5 | Tons | 120 | 600
| Rip Rap, Class B | 1770 | Tons | 80 | 141600
| Geotextitle for Drainage | 5795 | SY | 3.5 | 20282.5
| Enclosed Drainage System: Bridge over Currituck Sound | 0 | SF |  | 0
| Signing - Toll Entrance | 1 | LS | 500000 | 500000
| Type I Reinforced Approach Fill, L over Maple Swamp (Avg. 84' W) | 1 | LS | 150000 | 150000
| Type III Reinforced Approach Fill, Y-NB over RPBD and LPB (70' W) | 1 | LS | 160000 | 160000
| Type III Reinforced Approach Fill, L Begin over Currituck Sound (39' W)(1/2 Fill for Shore End) | 1 | LS | 50000 | 50000
| Type I Reinforced Approach Fill, L End over Currituck Sound (67' W)(1/2 Fill for Island End) | 1 | LS | 80000 | 80000
| Traffic Control | 1 | LS | 1000000 | 1000000
| Traffic Control (Existing Location - US 158 Interchange/Ramp Ties) | 1.7 | Miles |  | 0
| Traffic Control (Existing Location - US 158 Widening) | 0.4 | Miles |  | 0
| Traffic Control (Existing Location - Y-Line) | 1.12 | Miles |  | 0
| Temporary Portable Traffic Signal System | 1 | Each | 30000 | 30000
| Upgrade Traffic Signal | 1 | Each | 250000 | 250000
| Thermo and Markers (1 Ln Ramp) | 0.5 | Miles | 20000 | 10000
| Thermo and Markers (2 Ln Ramp) | 1.5 | Miles | 25000 | 37500
| Thermo and Markers (3 Ln Ramp) | 0.5 | Miles | 35000 | 17500
| Thermo and Markers (2 Lanes) | 7.9 | Miles | 25000 | 197500
| Thermo and Markers (3 Lanes) | 0.7 | Miles | 35000 | 24500
| Thermo and Markers (4 Lanes) | 0.5 | Miles | 45000 | 22500
| Thermo and Markers (5 Lanes) | 1 | Miles | 50000 | 50000
| Thermo and Markers (6 Lanes) | 0.7 | Miles | 60000 | 42000
| Interchange Lighting (per NCDOT, Lighting) | 1 | LS | 500000 | 500000
| Toll Plaza Lighting (per NCDOT Lighting) | 1 | LS | 175000 | 175000
| Roundabout Lighting (per NCDOT Lighting) | 1 | LS | 95000 | 95000
| Pedestrian Lighting on Bridge Rail (per NCDOT Lighting) | 1 | LS |  | 0
Structures
| -Y_NB- over -RPBD- and -LPB- (69'-3" x 132' on tangent) | 9146 | SF | 235 | 2149310
| -L- over Maple Swamp (42'-7" x 7,843' on tangent) | 391782 | SF | 275 | 107740050
| -L- over -Y3- and Currituck Sound (42'-7" x 24,665' on tangent) | 1062804 | SF | 325 | 345411300
| Trestle 1 (Closed Trestle on West side of Currituck Sound) (2040' x 40') | 81600 | SF | 115 | 9384000
| Trestle 2 (Closed Trestle on West side of Currituck Sound) (2040' x 40') + (120' x 40') | 86400 | SF | 115 | 9936000
| Trestle 3 (Open Trestle on East side of Currituck Sound) (8800' x 40') | 352000 | SF | 85 | 29920000
| Trestle 4 (Open Trestle on East side of Currituck Sound) (560' x 40') | 22400 | SF | 145 | 3248000
| Trestle over Maple Swamp (6000' x 40') + (60 x 30' x 30') (per Firm 6/28/2021) | 294000 | SF | 85 | 24990000
Retaining Walls
| -Y_NB- Sta 22+50 to 24+50 Av.5.23' x 200' | 1046 | SF | 200 | 209200
| -Y_NB- Sta 28+60 to 33+20 Av.6.65' x 460' | 3059 | SF | 130 | 397670
| -Y_NB- Sta 29+00 to 29+90 Av.9.96' x 90' | 896 | SF | 150 | 134400
| -Y4- Sta 39+80 to 40+60 Av.5.49' x 80' | 439 | SF | 200 | 87800
| -Y7- Sta 52+75 to 55+00 Av.2.98' x 225' | 671 | SF | 200 | 134200
Utility Construction
| Relocate Existing 6" Water Line | 2640 | LF | 80 | 211200
| Relocate Existing 10" Water Line | 1000 | LF | 103 | 103000
| Relocate Existing 8" DIP Water Line | 1800 | LF | 122 | 219600
| Relocate Existing 12" DIP Water Line | 1000 | LF | 122 | 122000
| Relocate Existing 6" Sewer Line | 3400 | LF | 60 | 204000
| Relocate Existing 8" Sewer Line | 3400 | LF | 100 | 340000
| Relocate Fire Hydrant/Cut Pavement etc | 5 | EA | 7904 | 39520
| Clearing | 3 | Acre | 2433 | 7299
| Manhole | 4 | EA | 4256 | 17024
| Lift Station | 1 | EA | 257777 | 257777
| Water Meter Relocation | 25 | EA | 1800 | 45000
| Valves | 25 | EA | 1069 | 26725
Tolling Equipment and ITS
| Aesthetic Gantry Infrastructure | 2 | TZ | 400000 | 800000
| Generator/Propane Tank | 1 | TZ | 75000 | 75000
| NCDOT/NCTA Traffic Management CCTV System | 11 | MI | 75000 | 825000
| Toll Rate Sign DMS and Toll Rate CCTV | 0 | MI |  | 0
| Traffic Management DMS | 4 | EA | 250000 | 1000000
| Bridge-Mounted Mini-DMS | 10 | EA | 50000 | 500000
| Fiber Optic Conduit System (In ground) | 4 | MI | 150000 | 600000
| Fiber Optic Conduit System (Bridge-Mounted) | 7 | MI | 250000 | 1750000
| Fiber Optic Hub | 2 | EA | 35000 | 70000
| Mainline Detection System | 2 | EA | 35000 | 70000
| Ramp Detection System | 2 | EA | 100000 | 200000
| Head-End Communications Equipment | 1 | LS | 100000 | 100000
Toll Plaza Maintenance Compound
| Maintenance & Administration Building | 5700 | SF | 150 | 855000
| Fuel Storage Canopy | 1 | LS | 400000 | 400000
| Septic System | 1 | EA | 15000 | 15000
| Perimeter Fencing with gate | 1400 | LF | 50 | 70000
Toll Booth Facilities
| Main Toll Plaza Building | 1400 | SF | 400 | 560000
| Toll Canopies and Booths | 1 | Plaza | 1500000 | 1500000
| Septic System, 1000 gal. | 1 | EA | 15000 | 15000
| Misc. (5% Str & Utilities) | 5% | LS |  | 27237000 | 544740075 | 0.05
| Misc. (30% Rdwy) | 30% | LS |  | 12747000 | 42488550 | 0.3
656574000
[5 empty] | 105126000 |  | 1.16
[5 empty] | 761700000 |  | 100000
| Design Build Factor (20%) |  |  |  | 152400000
| Design Build Cost |  |  |  | 914100000

## bridge calcs
Maple Swamp
24" Conc Piles | LF | 51555 | 221 | 11393655
Pile Exc | 25% | 12888.75 | 400 | 5155500
24" Conc Piles Setup | EA | 491 | 9000 | 4419000
Deck | SF | 392383.6667 | 65 | 25504938.3333
Class A Conc x 1.25 factor for reinforcements | CY | 6000 | 2000 | 12000000
54" Girders | LF | 6770 | 650 | 4400500
72" MBT Girders | LF | 39100 | 700 | 27370000
Railings | LF | 15688 | 180 | 2823840
Tug Support (2 crews) | Days | 327.3333 | 8000 | 2618666.6667
Sub Total |  |  |  | 95686100
Misc | 10% |  |  | 9568610
Total |  |  |  | 105254710
/SF |  |  |  | 268.2444
Currituck Sound
20" Conc Piles | LF | 5760 | 200 | 1152000
Pile Exc | 25% | 1440 | 300 | 432000
20" Conc Piles Setup | EA | 72 | 8000 | 576000
30" Conc Piles | LF | 126792.5 | 300 | 38037750
Pile Exc | 25% | 31698.125 | 750 | 23773593.75
30" Conc Piles Setup | EA | 1237 | 10000 | 12370000
Deck | SF | 1062785.4167 | 65 | 69081052.0833
Class A Conc x 1.25 factor for reinforcements | CY | 18000 | 2000 | 36000000
54" Girders | LF | 8330 | 650 | 5414500
72" MBT Girders | LF | 123075 | 700 | 86152500
Railings | LF | 49330 | 180 | 8879400
Tug Support (4 crews) | Days | 872.6667 | 16000 | 13962666.6667
Sub Total |  |  |  | 295831462.5
Misc | 10% |  |  | 29583146.25
Total |  |  |  | 325414608.75
/SF |  |  |  | 306.1903

## bridge data
Maple Swamp Bridge
Bents | End bent 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | End bent 2 | number of piles | total length of all piles
Number of 24" square concrete piles | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 10 | 10 | 8 | 8 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 491 | 51555 | total length of all piles (average length of piles is 105')
Spans |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81
Span Len |  | 88 | 89 | 89 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 73 | 73 | 73 | 70 |  |  | 7844
Span Width |  | 124.5833 | 124.5833 | 124.5833 | 124.5833 | 124.5833 | 101.0833 | 101.0833 | 77.6667 | 77.6667 | 54.25 | 54.25 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 | 42.5833 |  |  | 392383.6667
54" concrete girders per span |  | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 |  | 6770
72" modified bulb tee girders per span |  | 0 | 0 | 0 | 0 | 12 | 12 | 10 | 10 | 8 | 8 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 |  | 39100
Currituck Sound Bridge
Bents | End bent 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79
Number of 30" square concrete piles | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Number of 20" square concrete piles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spans |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79
72" modified bulb girders per span |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
54" Type IV girders per span |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159
Number of 30" square concrete piles | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Number of 20" square concrete piles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spans | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159
72" modified bulb girders per span | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
54" Type IV girders per span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239
Number of 30" square concrete piles | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6
Number of 20" square concrete piles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spans | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239
72" modified bulb girders per span | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6
54" Type IV girders per span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 240 | 1: 241; 2: 242; 3: 243; 4: 244; 5: 245; 6: 246; 7: End bent 2; 9: number of piles; 11: total length of all piles
Number of 30" square concrete piles | 6 | 1: 7; 2: 7; 3: 7; 4: 7; 5: 7; 6: 7; 7: 7; 9: 1237; 11: 126792.5; 16: 30" piles (average length of piles is 102.5')
Number of 20" square concrete piles | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 9: 72; 11: 5760; 16: 20" piles (average length of piles is 80')
Spans | 240 | 1: 241; 2: 242; 3: 243; 4: 244; 5: 245; 6: 246; 7: 247; 11: 24565
72" modified bulb girders per span | 6 | 1: 7; 2: 7; 3: 7; 4: 7; 5: 0; 6: 0; 7: 0
54" Type IV girders per span | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 7; 6: 7; 7: 7