## Original
DIT-T Unit: EBS |  |  | Methodology Owner/Contact: Marnie Lockard/Jose Berdiel |  |  |  | Date Methodology Initially Added: 03/02/2021 |  |  | Project Name:
Methodology Name: SAP Solution Manager |  |  | Quality Management Plan Used: Follow the Enperprise Quality Management Plan |  |  |  | Date Last Updated: 03/02/2021 |  |  | Project Manager:
Methodology Type: SAP Activate Methodology - This methology is a modular and agile framework for implementation or migration of SAP solutions that provides content and guidance for project teams. |  |  | Deliverable Repository: SAP Solution Manager |  |  |  | Comments: The repository for the EBS templates/artifacts is located on the EBS MS Teams Channel |  |  | Comments:
[6 empty] | Operational |  | Mapping Red Text = Differences from E-SDLC |  | Exceptions to Methodology
Phase | ID | Key Deliverable | Minimum Requirement | Req'd for Audit | Audit Control | Change Request (Low Risk) | Req'd | Phase | Key Deliverable | Exception Reason N/A = Deliverable completed Blank = Deliverable is pending
Business Concept | 1 | Work Request |  | Y | ITGC03 | Y | Y | Business Concept - Business Request - received via phone call to the EBS Support Team or EBS management, email or in person. | Complete Section 1 of the Enterprise Business Service Work Request Form - Form document is located at the SAP Solution Manager, Problem screen.
Business Concept | 2 | Alternatives Analysis | If required |  | ITGC03 |  |  | Business Concept - If needed, the EBS Team will take a look at the issue in question or the business opportunity to identify possible options/solutions to the issue or about how to maximize the business opprtunity identified by the business. | Complete Section 2 of the Enterprise Business Service Work Request Form. Form document is located on the SAP Solution Manager, Problem screen. Design Authority Board (DAB) Approval/Denial of the Enterprise Business Service Work Request Form - the role of the DAB is to provide assurance that solution design is the appropriate solution for the issue or opportunity; ensure that each component meets business and technical requirements, integrates and works within the existing enterprise architecture.
Business Concept | 3 | Preliminary Business Case | Min: Scope of Work, Resource Plan, Cost Plan, Start/End Dates |  | ITGC03 |  | Y | Business Concept | Included on SAP Solution Management software as fields on the Problem Message screen.
Business Concept | 4 | Business Concept Exit Quality Review
Initiation | 5 | Scope of Work | Min: Work Definition, Resources, Estimated Cost, Start/End Dates | Y | ITGC03 | Y | Y | Initiation | Create the Request for Change (RC) on SAP Solution Manager and map-out Scope of Work - Admin. Change (Internal change with no transports) or a Normal Change ( transports using SAP Transport Management System).
Initiation | 6 | Scope of Work Approval | DOT Business & DIT-T approval required | Y | ITGC03 | Y | Y | Initiation | EBS management reviews and approves the RC on SAP Solution Manager, RC screen.
Initiation | 7 | Business Case |  |  | ITGC03
Initiation | 8 | Benefits |  |  | ITGC03
Initiation | 9 | Business Case Quality Review
Initiation | 10 | EPMO Business Case DP Approval | DIT EPMO & OSBM approved required
Initiation | 11 | Cost Plan |  |  | ITGC03
Initiation | 12 | Schedule |  |  | ITGC03
Initiation | 13 | Change Management Plan |  |  | ITGC03
Initiation | 14 | Procurement Plan | If procuring resources, products, services |  | ITGC03
Initiation | 15 | Communication Plan |  |  | ITGC03
Initiation | 16 | Organization Chart |  |  | ITGC03
Initiation | 17 | Quality Management Plan |  | Y | ITGC03 | Y | Y |  | The Quality Mangement Plan is not required for none PMO work-efforts.
Initiation | 18 | Risk Assessment/Mitigation Plan |  |  | ITGC03
Initiation | 19 | Issues Log |  |  | ITGC03
Initiation | 20 | Privacy Threshold Analysis (PTA) | Required if application not previously documented and/or if changing any privacy information. DIT-T Security & DIT Approval required. | Y | ITGC01 | Y | Y | Initiation | Follow the Enterprise Privacy Threshold Analysis and the process provided by the CISO office.
Initiation | 21 | Initiation Exit Quality Review |  |  | ITGC04
Planning & Design | 22 | Project Change Request Log
Planning & Design | 23 | Project Change Request | DIT-T and Business Approval |  | ITGC03
Planning & Design | 24 | Project Change Request Quality Review
Planning & Design | 25 | EPMO Change Request DP Approval | EPMO and/or OSBM approval (if required)
Planning & Design | 26 | SAP Cost Exception Report
Planning & Design | 27 | Requirements Management Plan |  |  | ITGC03
Planning & Design | 28 | Requirements | Must be approved by Business and other stakeholders, including Architecture, Security, Infrastructure, etc. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | Planning & Design | As required by the work-effort being performed by the EBS Team, the EBS Team prepares the following requirements documents (Repository of these templates is located on the EBS Teams Channel) and attached them to the Request for Change screen on SAP Solution Manager: BASIS and Infractructure Specifications Functional Specifications Development Specifications Business Warehouse Specifications Portal Specifications Security Specifications OpenText Specifications Training Specifications
Planning & Design | 29 | Requirements Approval | Required on all sizes of work except on small operational work, this may be included in Work Definition. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | Planning & Design | EBS Management Team, Functional and Technical Leads review and approve requirements documents
Planning & Design | 30 | Requirements Traceability Matrix
Planning & Design | 32 | Architecture Design |  |  | ITGC01 ITGC02
Planning & Design | 33 | Architecture DP Quality Review | If required by EPMO
Planning & Design | 34 | EPMO Architecture DP Approval | If required by EPMO DIT Architecture Approval required |  | ITGC01 ITGC02
Planning & Design | 35 | Security DP Quality Review | If required by EPMO
Planning & Design | 36 | EPMO Security DP Approval | If required by EPMO DIT Approval Required |  | ITGC01 ITGC02
Planning & Design | 37 | Architecture Exception Request | If required, complete DIT Approval Required
Planning & Design | 38 | NCID Exception Request | If required, complete DIT Approval Required |  | ITGC01
Planning & Design | 39 | Security Exception Request | If required, complete DIT Approval Required |  | ITGC01
Planning & Design | 40 | Design Document |  | Y | ITGC03 | Y | Y |  | The Design Document is not required for none PMO work-efforts.
Planning & Design | 41 | Design Approval | Business and other stakeholders approvals | Y | ITGC03 | Y | Y |  | The Design Approval is not required for none PMO work-efforts.
Planning & Design | 42 | Business Continuity Plan | If required |  | ITGC03
Planning & Design | 43 | Disaster Recovery Plan | If required |  | ITGC03
Planning & Design | 44 | Training Plan | If required |  | ITGC03
Planning & Design | 45 | Test Plan
Planning & Design | 46 | Acceptance Process and Criteria | Required if there are changes to the current OLA. |  | ITGC03
Planning & Design | 47 | Acceptance Process and Criteria Approval | Must be approved by Business and other stakeholders |  | ITGC03
Planning & Design | 48 | Operational Level Agreement (OLA) | Required if there are changes to the current OLA. |  | ITGC04
Planning & Design | 49 | Operational Level Agreement (OLA) Approval | If required Must be approved by IT Stakeholders |  | ITGC04
Planning & Design | 50 | Business Approval to Exit P&D |  |  | ITGC03
Planning & Design | 51 | P&D Exit Quality Review |  |  | ITGC04
Planning & Design |  | If RFP required, deliverables below: | [6 empty] | If RFP required, deliverables below: | If RFP required, deliverables below:
Planning & Design | 52 | RFP Request for Commodity/Service Form |  |  | ITGC04
Planning & Design | 53 | RFP Disaster Recovery Assessment |  |  | ITGC04
Planning & Design | 54 | RFP Sourcing Exception Request | If required for the RFP |  | ITGC04
Planning & Design | 55 | RFP Hosting Exception Request | If required for the RFP |  | ITGC04
Planning & Design | 56 | RFP and Attachments |  |  | ITGC03 ITGC04
Planning & Design | 57 | RFP Proposal Evaluation Plan |  |  | ITGC03 ITGC04
Planning & Design | 58 | RFP Content Submission
Planning & Design | 59 | RFP Individual Evaluation Workbooks |  |  | ITGC03 ITGC04
Planning & Design | 60 | RFP Oral Presentation/Demonstration Guide |  |  | ITGC03 ITGC04
Planning & Design | 61 | RFP Consensus Evaluation Workbook |  |  | ITGC03
Planning & Design | 62 | RFP Evaluation Report with Award Recommendation |  |  | ITGC03 ITGC04
Planning & Design | 63 | RFP Evaluation Report Approvals | Business and other stakeholders approvals required. |  | ITGC03 ITGC04
Planning & Design | 64 | RFP CIO Presentation
Planning & Design | 65 | RFP Evaluation Review Checklist
Planning & Design | 66 | EPMO RFP Review DP Approval | DPMO Approval Required
Planning & Design | 67 | EPMO Contract Award Review DP Approval | DPMO Approval Required
Planning & Design |  | If Invitation for Bid (IFB) required, deliverables below: | [6 empty] | If Invitation for Bid (IFB) required, deliverables below: | If Invitation for Bid (IFB) required, deliverables below:
Planning & Design | 68 | IFB Request for Commodity/Service Form |  |  | ITGC03 ITGC04
Planning & Design | 69 | IFB Disaster Recovery Assessment | If required for IFB |  | ITGC03 ITGC04
Planning & Design | 70 | IFB Sourcing Exception Request | If required for IFB |  | ITGC04
Planning & Design | 71 | IFB Hosting Exception Request | If required for IFB |  | ITGC04
Planning & Design | 72 | IFB and Attachments |  |  | ITGC03 ITGC04
Planning & Design | 73 | IFB Statement of Work | May be required for Extensive Services |  | ITGC03 ITGC04
Planning & Design | 74 | IFB Bid Review Checklist
Planning & Design | 75 | IFB Award Approval | Business and other stakeholders approvals required. |  | ITGC04
Planning & Design |  | IF Request for Quote (RFQ) required, deliverables below: | [6 empty] | IF Request for Quote (RFQ) required, deliverables below: | IF Request for Quote (RFQ) required, deliverables below:
Planning & Design | 76 | RFQ Request for Commodity/Service Form |  |  | ITGC03 ITGC04
Planning & Design | 77 | RFQ Disaster Recovery Assessment | If required for RFQ |  | ITGC03 ITGC04
Planning & Design | 78 | RFQ Sourcing Exception Request | If required for RFQ |  | ITGC04
Planning & Design | 79 | RFQ Hosting Exception Request | If required for RFQ |  | ITGC04
Planning & Design | 80 | RFQ and Attachments |  |  | ITGC03 ITGC04
Planning & Design | 81 | RFQ Market Research |  |  | ITGC03 ITGC04
Planning & Design | 82 | RFQ Estimate or Unofficial Quote |  |  | ITGC04
Planning & Design | 83 | RFQ Statement of Work |  |  | ITGC03 ITGC04
Planning & Design | 84 | RFQ Quote Review Document |  |  | ITGC03 ITGC04
Planning & Design | 85 | RFQ Award Approval | Business and other stakeholders approvals required. |  | ITGC04
Planning & Design |  | If Contract Modifications through Amendment required, deliverables below: | [6 empty] | If Contract Modifications through Amendment required, deliverables below: | If Contract Modifications through Amendment required, deliverables below:
Planning & Design | 86 | Amendment Request for Commodity/Service Form |  |  | ITGC03 ITGC04
Planning & Design | 87 | Amendment Disaster Recovery Assessment | May be required if change in scope of work |  | ITGC03 ITGC04
Planning & Design | 88 | Amendment Sourcing Exception Request | If required for Amendment |  | ITGC04
Planning & Design | 89 | Amendment Hosting Exception Request | If required for Amendment |  | ITGC04
Planning & Design | 90 | Amendment and Attachments |  |  | ITGC03 ITGC04
Planning & Design | 91 | Amendment Market Research |  |  | ITGC03 ITGC04
Planning & Design | 92 | Amendment Estimate or Unofficial Quote |  |  | ITGC03 ITGC04
Planning & Design | 93 | Amendment Statement of Work | May be required for additional work within scope of work in existing contract |  | ITGC03 ITGC04
Planning & Design | 94 | Amendment Approval | Business and other stakeholders approvals required. |  | ITGC04
Planning & Design |  | IF Request for Information (RFI), deliverables below: | [6 empty] | IF Request for Information (RFI), deliverables below: | IF Request for Information (RFI), deliverables below:
Planning & Design | 95 | RFI |  |  | ITGC03 ITGC04
Excecute & Build | 31 | Application Architecture Design (AAD) | DIT-T Architecture Approval Required | Y | ITGC01 ITGC02 | Y | Y | Excecute & Build | Design Authority Board (DAB) Approval/Denial. The role of the DAB is to provide assurance that solution design is the appropriate solution for the issue or opportunity; ensure that each component meets business and technical requirements, integrates and works within the existing enterprise architecture.
Execute & Build | 96 | Code Structural Quality Analysis (CAST) Report | If required
Execute & Build | 97 | Component Integration Test (CIT) Approved |  | Y | ITGC02 | Y | Y | Excecute & Build | Test Scripts - document is located on SAP Solution Manager, Change Document screen.
Execute & Build | 98 | System Integration Test (SIT) Approved |  | Y | ITGC02 | Y | Y | Excecute & Build | Test Scripts - document is located on SAP Solution Manager, Change Document screen
Execute & Build | 99 | Performance Testing Approved | If required
Execute & Build | 100 | IT Testing Complete Approval |  | Y | ITGC02 | Y | Y | Excecute & Build | EBS Management, Technical Leads and Subject Matter Experts, the business (UT) review and approve the Test Script document.
Execute & Build | 101 | User Acceptance Plan and Script | IT management involves users in the design of applications, selection of packaged software and testing thereof. | Y | ITGC03 | Y | Y | Excecute & Build | EBS staff includes the business and business users in the design of applications, testing and validation. This is performed in Quality system and documented on SAP Solution Manager, Change Document screen.
Execute & Build | 102 | Sponsor Approved UAT |  | Y | ITGC03 | Y | Y | Excecute & Build | EBS staff and business users are involved in testing and validation. Approval is documented on SAP Solution Manager, Change Document screen.
Execute & Build | 103 | Implementation Plan
Execute & Build | 104 | Go Live Readiness Assessment |  | Y | ITGC03 | Y | Y | Excecute & Build | Ready for Production Check List attached on SAP Solution Manager, Change Document screen.
Execute & Build | 105 | Go Live Approval | Business and other Stakeholders approval | Y | ITGC03 | Y | Y | Excecute & Build | EBS CAB reviews and approves Project GO Live. Approval is documented on SAP Solution Manager, Change Document screen.
Execute & Build | 106 | Project Go Live Readiness DP Quality Review | If required
Execute & Build | 107 | EPMO Go Live Readiness DP Approval | If required. EPMO approval
Execute & Build | 108 | E&B Exit Quality Review
Implementation | 109 | Business Approval to Close the Project |  |  | ITGC03
Implementation | 110 | Implementation Exit Quality Review
Closeout | 111 | SAP Commitments Reconciled
Closeout | 112 | Lessons Learned Survey
Closeout | 113 | EPMO Lessons Learned
Closeout | 114 | EPMO Closeout Report
Closeout | 115 | Closeout Quality Review
Note on A1: Enter the name of the unit that owns the mapped methodology
Note on D1: Enter person to contact if there are questions about the mapped methodology.
Note on J1: Enter the date approved and added to the DIT-T Enterprise SDLC site on Connect.
Note on M1: Enter Project Name.
Note on A2: Enter the name the unit refers to their methodology by.
Note on D2: Enter the name of the Quality Management Plan used; most units will use the DIT-T Enterprise Quality Management Plan. If not, provide the name of your plan and include in that plan that you are following the DIT-T Enterprise Quality Management Plan and this plan includes additional quality requirements.
Note on J2: Enter the date the methodology was last updated and approved.
Note on M2: Enter person responsible for managing the project.
Note on A3: Enter the industry type of methodology mapped, such as Agile, Iterative, Waterfall, etc.
Note on D3: Enter the location where deliverable artifacts are stored.
Note on J3: Enter additional information about the methodology, if needed.
Note on K4: For the process to be mapped, review the DIT-T SDLC Key Deliverable in column C to determine if the deliverable is created, if it is called by a different name, and the name of the phase initiated in. Deliverables on all projects and required for audit should not be deleted (see column E).
Note on J5: Enter a 'Y' for required deliverables. The column is prepopulated with the project type values (H) to be mapped to. If additional deliverables in the Key Deliverables column (C) are required by the mapped methodology, enter a ‘Y’ in this column, enter phase name and key deliverable name. Use red text to indicate different from the DIT-T Enterprise SDLC Deliverables.
Note on K5: Enter the phase name for the phase the deliverable is initiated in.
Note on L5: Enter the name of the deliverable (this is the name that will be used for the document artifact name). If the deliverable is located in another system, such as a Work Request is located in ServiceNow, indicate how to find the deliverable and the System Name where it can be found. Examples can be found in the 'Approved Methodologies' folder, document name 'PMO_Enterprise Project (Waterfall)'.
Note on M5: For each Key Deliverable in the column highlighted in blue, enter either: - N/A for deliverable produced or - Exception Reason if deliverable is not produced.