## combined Prj and Chg
DIT-T Unit: GIS Unit |  |  | Methodology Owner/Contact: Jun Wu |  |  |  | Date Metholdology Initially Added: 03/02/2021 |  |  | Project Name:
Methodology Name: GIS Change Request |  |  | Quality Management Plan Used: Operational Change Request |  |  |  | Date Last Updated: 03/02/2021 |  |  | Project Manager:
Methodology Type: Agile |  |  | Deliverables Repository: GIS Project Team Site |  |  |  | Comments: Link to description of methodology |  |  | Comments:
[6 empty] | Operational |  | Mapping Red Text = Differences from E-SDLC |  | Exceptions to Methodology
Phase | ID | Key Deliverable | Minimum Requirement | Req'd for Audit | Audit Control | Change Request (Low Risk) | Req'd | Phase | Key Deliverable | Exception Reason N/A = Deliverable completed Blank = Deliverable is pending
Business Concept | 1 | Work Request |  | Y | ITGC03 | Y | Y | 1 Concept (ITR- neg 1) | GIS EMS Work Effort Request (or ServiceNow Request) or High Level Work Request
Business Concept | 2 | Alternatives Analysis | If required |  | ITGC03 |  |  | 1 Concept (ITR- neg 1)
Business Concept | 3 | Preliminary Business Case | Min: Scope of Work, Resource Plan, Cost Plan, Start/End Dates |  | ITGC03 |  | Y | 1 Concept (ITR- neg 1) | Customer's Business Case
Business Concept | 4 | Business Concept Exit Quality Review | [5 empty] | 1 Concept (ITR- neg 1)
Initiation | 5 | Scope of Work | Min: Work Definition, Resources, Estimated Cost, Start/End Dates | Y | ITGC03 | Y | Y | Inception (ITR - 0) | Statement of Work - Scope of Work
Initiation | 6 | Scope of Work Approval | DOT Business & DIT-T approval required | Y | ITGC03 | Y | Y | Inception (ITR - 0) | Statement of Work - Scope of Work Approval
Initiation | 7 | Business Case |  |  | ITGC03 |  |  | Inception (ITR - 0) | Customer's Business Case (Revised)
Initiation | 8 | Benefits |  |  | ITGC03 |  |  | Inception (ITR - 0)
Initiation | 9 | Business Case Quality Review | [5 empty] | Inception (ITR - 0)
Initiation | 10 | EPMO Business Case DP Approval | DIT EPMO & OSBM approved required |  |  |  |  | Inception (ITR - 0)
Initiation | 11 | Cost Plan |  |  | ITGC03 |  | Y | Inception (ITR - 0) | Customer's Cost Plan
Initiation | 12 | Schedule |  |  | ITGC03 | Y | Y | Inception (ITR - 0) | Project Schedule or Schedule maintained in DevOps (Exportable)
Initiation | 13 | Change Management Plan |  |  | ITGC03 |  |  | Inception (ITR - 0)
Initiation | 14 | Procurement Plan | If procuring resources, products, services |  | ITGC03 |  |  | Inception (ITR - 0)
Initiation | 15 | Communication Plan |  |  | ITGC03 |  |  | Inception (ITR - 0)
Initiation | 16 | Organization Chart |  |  | ITGC03 |  |  | Inception (ITR - 0)
Initiation | 17 | Quality Management Plan |  | Y | ITGC03 | Y | Y | Inception (ITR - 0) | Quality Management Plan
Initiation | 18 | Risk Assessment/Mitigation Plan |  |  | ITGC03 |  |  | Inception (ITR - 0)
Initiation | 19 | Issues Log |  |  | ITGC03 |  |  | Inception (ITR - 0) | RAID Log or ServiceNow Issues Log or GIS Mantis or DevOps
Initiation | 20 | Privacy Threshold Analysis (PTA) | Required if application not previously documented and/or if changing any privacy information. DIT-T Security & DIT Approval required. | Y | ITGC01 | Y | Y | Inception (ITR - 0) | Privacy Threshold Analysis (PTA)
Initiation | 21 | Initiation Exit Quality Review |  |  | ITGC04 |  |  | Inception (ITR - 0)
Planning & Design | 22 | Project Change Request Log | [5 empty] | Inception (ITR - 0) | RAID Log - Decisions or GIS Mantis or DevOps
Planning & Design | 23 | Project Change Request | DIT-T and Business Approval |  | ITGC03 |  |  | Inception (ITR - 0)
Planning & Design | 24 | Project Change Request Quality Review | [5 empty] | Inception (ITR - 0)
Planning & Design | 25 | EPMO Change Request DP Approval | EPMO and/or OSBM approval (if required) |  |  |  |  | Inception (ITR - 0)
Planning & Design | 26 | SAP Cost Exception Report | [5 empty] | Inception (ITR - 0)
Planning & Design | 27 | Requirements Management Plan |  |  | ITGC03 |  |  | Inception (ITR - 0)
Planning & Design | 28 | Requirements | Must be approved by Business and other stakeholders, including Architecture, Security, Infrastructure, etc. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | Inception (ITR - 0) | Requirements
Planning & Design | 29 | Requirements Approval | Required on all sizes of work except on small operational work, this may be included in Work Definition. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | Inception (ITR - 0) | Requirements Approval
Planning & Design | 30 | Requirements Traceability Matrix | [5 empty] | Inception (ITR - 0)
Planning & Design | 32 | Architecture Design |  |  | ITGC01 ITGC02 |  |  | Inception (ITR - 0)
Planning & Design | 33 | Architecture DP Quality Review | If required by EPMO |  |  |  |  | Inception (ITR - 0)
Planning & Design | 34 | EPMO Architecture DP Approval | If required by EPMO DIT Architecture Approval required |  | ITGC01 ITGC02 |  |  | Inception (ITR - 0)
Planning & Design | 35 | Security DP Quality Review | If required by EPMO |  |  |  |  | Inception (ITR - 0)
Planning & Design | 36 | EPMO Security DP Approval | If required by EPMO DIT Approval Required |  | ITGC01 ITGC02 |  |  | Inception (ITR - 0)
Planning & Design | 37 | Architecture Exception Request | If required, complete DIT Approval Required |  |  | Y | Y | Inception (ITR - 0) | Architecture Exception Request
Planning & Design | 38 | NCID Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y | Inception (ITR - 0) | NCID Exception Request
Planning & Design | 39 | Security Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y | Inception (ITR - 0) | Security Exception Request
Planning & Design | 40 | Design Document |  | Y | ITGC03 | Y | Y | Inception (ITR - 0) | Design Document
Planning & Design | 41 | Design Approval | Business and other stakeholders approvals | Y | ITGC03 | Y | Y | Inception (ITR - 0) | Design Approval
Planning & Design | 42 | Business Continuity Plan | If required |  | ITGC03 |  |  | Inception (ITR - 0)
Planning & Design | 43 | Disaster Recovery Plan | If required |  | ITGC03 |  |  | Inception (ITR - 0)
Planning & Design | 44 | Training Plan | If required |  | ITGC03 |  |  | Inception (ITR - 0)
Planning & Design | 45 | Test Plan |  |  |  | Y | Y | Inception (ITR - 0) | Test Plan or Test Plan in TestLink
Planning & Design | 46 | Acceptance Process and Criteria |  |  | ITGC03 | Y | Y | Inception (ITR - 0) | UAT Plan
Planning & Design | 47 | Acceptance Process and Criteria Approval | Must be approved by Business and other stakeholders |  | ITGC03 | Y | Y | Inception (ITR - 0) | UAT Plan Approval
Planning & Design | 48 | Operational Level Agreement (OLA) | Required if there are changes to the current OLA. |  | ITGC04 | Y | Y | Inception (ITR - 0) | O&M Manual Update
Planning & Design | 49 | Operational Level Agreement (OLA) Approval | If required Must be approved by IT Stakeholders |  | ITGC04 | Y | Y | Inception (ITR - 0) | O&M Manual Update
Planning & Design | 50 | Business Approval to Exit P&D |  |  | ITGC03 |  |  | Inception (ITR - 0)
Planning & Design | 51 | P&D Exit Quality Review |  |  | ITGC04 |  |  | Inception (ITR - 0)
|  | If RFP required, deliverables below: |  |  |  |  | Exception Request for whole section for RFPs: GISU does not manage RFPs. We involve PMO if this type of procurement is needed, so these don't apply to us |  |  | If RFP required, deliverables below:
Planning & Design | 52 | RFP Request for Commodity/Service Form |  |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 53 | RFP Disaster Recovery Assessment |  |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 54 | RFP Sourcing Exception Request | If required for the RFP |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 55 | RFP Hosting Exception Request | If required for the RFP |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 56 | RFP and Attachments |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 57 | RFP Proposal Evaluation Plan |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 58 | RFP Content Submission | [5 empty] | Inception (ITR - 0)
Planning & Design | 59 | RFP Individual Evaluation Workbooks |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 60 | RFP Oral Presentation/Demonstration Guide |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 61 | RFP Consensus Evaluation Workbook |  |  | ITGC03 | Y |  | Inception (ITR - 0)
Planning & Design | 62 | RFP Evaluation Report with Award Recommendation |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 63 | RFP Evaluation Report Approvals | Business and other stakeholders approvals required. |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 64 | RFP CIO Presentation |  |  |  | Y |  | Inception (ITR - 0)
Planning & Design | 65 | RFP Evaluation Review Checklist | [5 empty] | Inception (ITR - 0)
Planning & Design | 66 | EPMO RFP Review DP Approval | DPMO Approval Required |  |  |  |  | Inception (ITR - 0)
Planning & Design | 67 | EPMO Contract Award Review DP Approval | DPMO Approval Required |  |  |  |  | Inception (ITR - 0)
Planning & Design |  | If Invitation for Bid (IFB) required, deliverables below: |  |  |  |  | Exception Request for whole section for IFBs:GISU does not manage IFBs. We involve PMO if this type of procurement is needed, so these don't apply to us |  |  | If Invitation for Bid (IFB) required, deliverables below:
Planning & Design | 68 | IFB Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 69 | IFB Disaster Recovery Assessment | If required for IFB |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 70 | IFB Sourcing Exception Request | If required for IFB |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 71 | IFB Hosting Exception Request | If required for IFB |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 72 | IFB and Attachments |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 73 | IFB Statement of Work | May be required for Extensive Services |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 74 | IFB Bid Review Checklist |  |  |  | Y |  | Inception (ITR - 0)
Planning & Design | 75 | IFB Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design |  | IF Request for Quote (RFQ) required, deliverables below: |  |  |  |  | Exception Request for whole section for RFQs: GISU does not manage RFQs. We involve PMO if this type of procurement is needed, so these don't apply to us |  |  | IF Request for Quote (RFQ) required, deliverables below:
Planning & Design | 76 | RFQ Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 77 | RFQ Disaster Recovery Assessment | If required for RFQ |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 78 | RFQ Sourcing Exception Request | If required for RFQ |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 79 | RFQ Hosting Exception Request | If required for RFQ |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 80 | RFQ and Attachments |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 81 | RFQ Market Research |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 82 | RFQ Estimate or Unofficial Quote |  |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 83 | RFQ Statement of Work |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 84 | RFQ Quote Review Document |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design | 85 | RFQ Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y |  | Inception (ITR - 0)
Planning & Design |  | If Contract Modifications through Amendment required, deliverables below: |  |  |  |  | Exception Request for item# 91 due to the fact that the Statements of Work and Supplemental Staffing contracts GISU typically uses for projects do not require doing additional market research mid-contract. This need would be addressed with a fresh statement of work if the SOW amendment approval was declined or by hiring a new staff under the Supplemental Staffing Contract. Recommend keeping items 101 & 91 as 'if required for Amendment' in case there are unique situations. |  |  | If Contract Modifications through Amendment required, deliverables below:
Planning & Design | 86 | Amendment Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Exception Request | Inception (ITR - 0)
Planning & Design | 87 | Amendment Disaster Recovery Assessment | May be required if change in scope of work |  | ITGC03 ITGC04 | Y | Y | Inception (ITR - 0)
Planning & Design | 88 | Amendment Sourcing Exception Request | If required for Amendment |  | ITGC04 | Y | Y | Inception (ITR - 0)
Planning & Design | 89 | Amendment Hosting Exception Request | If required for Amendment |  | ITGC04 | Y | Y | Inception (ITR - 0)
Planning & Design | 90 | Amendment and Attachments |  |  | ITGC03 ITGC04 | Y | Y | Inception (ITR - 0) | Ammendment and Attachments
Planning & Design | 91 | Amendment Market Research |  |  | ITGC03 ITGC04 | Y | Exception Request | Inception (ITR - 0)
Planning & Design | 92 | Amendment Estimate or Unofficial Quote |  |  | ITGC03 ITGC04 | Y | Y | Inception (ITR - 0)
Planning & Design | 93 | Amendment Statement of Work | May be required for additional work within scope of work in existing contract |  | ITGC03 ITGC04 | Y | Y | Inception (ITR - 0) | Ammendment Statement of Work
Planning & Design | 94 | Amendment Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y | Inception (ITR - 0) | Amendment Approval
|  | IF Request for Information (RFI), deliverables below: |  |  |  |  | Exception Request for whole section for RFIs: GISU does not manage RFIs. We involve PMO if this type of solicitation is needed, so these don't apply to us |  |  | IF Request for Information (RFI), deliverables below:
Planning & Design | 95 | RFI |  |  | ITGC03 ITGC04 | Y |  | Inception (ITR - 0)
Exception Request for all EPMO Approval items. GIS Unit does not required EPMO review or approval for our projects.
Execute & Build | 31 | Application Architecture Design (AAD) | DIT-T Architecture Approval Required | Y | ITGC01 ITGC02 | Y | Y | Construction ITRs | Application Architecture Design (AAD)
Execute & Build | 96 | Code Structural Quality Analysis (CAST) Report | If required |  |  |  |  | Construction ITRs
Execute & Build | 97 | Component Integration Test (CIT) Approved |  | Y | ITGC02 | Y |  | Construction ITRs
Execute & Build | 98 | System Integration Test (SIT) Approved |  | Y | ITGC02 | Y |  | Construction ITRs
Execute & Build | 99 | Performance Testing Approved | If required |  |  | Y |  | Construction ITRs
Execute & Build | 100 | IT Testing Complete Approval |  | Y | ITGC02 | Y |  | Construction ITRs
Execute & Build | 101 | User Acceptance Plan and Script | IT management involves users in the design of applications, selection of packaged software and testing thereof. | Y | ITGC03 | Y |  | Construction ITRs
Execute & Build | 102 | Sponsor Approved UAT |  | Y | ITGC03 | Y | Y | Construction ITRs | Sponsor Approved UAT
Execute & Build | 103 | Implementation Plan | [5 empty] | Construction ITRs
Execute & Build | 104 | Go Live Readiness Assessment |  | Y | ITGC03 | Y |  | 4 Transition
Execute & Build | 105 | Go Live Approval | Business and other Stakeholders approval | Y | ITGC03 | Y | Y | Transition (Release) | Go Live Approval
Execute & Build | 106 | Project Go Live Readiness DP Quality Review | If required |  |  |  |  | Transition (Release)
Execute & Build | 107 | EPMO Go Live Readiness DP Approval | If required. EPMO approval |  |  |  |  | Transition (Release)
Execute & Build | 108 | E&B Exit Quality Review | [5 empty] | Transition (Release)
Implementation | 109 | Business Approval to Close the Project |  |  | ITGC03 |  |  | Transition (Release)
Implementation | 110 | Implementation Exit Quality Review | [5 empty] | Transition (Release)
Exception Request for whole section for RFIs: GISU does not manage RFIs. We involve PMO if this type of solicitation is needed, so these don't apply to us
Closeout | 111 | SAP Commitments Reconciled | [5 empty] | Production
Closeout | 112 | Lessons Learned Survey | [5 empty] | Production
Closeout | 113 | EPMO Lessons Learned | [5 empty] | Production
Closeout | 114 | EPMO Closeout Report | [5 empty] | Production
Closeout | 115 | Closeout Quality Review | [5 empty] | Production
|  | No PMO item ID# identified | [6 empty] | IF GIS Master Contract Statements of Work (SOW), additional deliverables below: | IF GIS Master Contract Statements of Work (SOW), additional deliverables below:
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Budget approval and WBS Number Assignment
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Master Contract Statement of Work
3 Inception (ITR-0)
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Vendor Responses
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Evaluation Workbook
Planning & Design | ## | Not in PMO QMP | [6 empty] | Clarifications issued to all vendor
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Sponsor Approval of Selected Vendor
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Award Recommendation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Statewide IT Procurement Office Award Authorization
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Commodity Service Request
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | ITBO Executed Purchase Order
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | NCID Account Approval
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | DOT Email Approval
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | ID/Security Badge Approval
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | NCID Account Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | DOT Email Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | ID/Security Badge Deactivation?
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Retirement Analysis Document
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Retirement Plan
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Retirement Cost Plan
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Removal of System Approval
Planning & Design | [8 empty] | IF IT Supplemental Staffing Contract, additional deliverables below: | IF IT Supplemental Staffing Contract, additional deliverables below:
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Business Request
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | WBS Number/SAP Number Communication
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | NCID Accout Approval
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | DOT Email Approval
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | ID/Security Badge Approval
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | New Contractor Onboarding Quality Checklist?
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | NCID Account Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | DOT Email Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | ID/Security Badge Deactivation?
Planning & Design | ## | Not in PMO QMP | [5 empty] | 2 Inception (ITR-0) | Contractor Offboarding Quality Checklist
Note on A1: Enter the name of the unit that owns the mapped methodology
Note on D1: Enter person to contact if there are questions about the mapped methodology.
Note on J1: Enter the date approved and added to the DIT-T Enterprise SDLC site on Connect.
Note on M1: Enter Project Name.
Note on A2: Enter the name the unit refers to their methodology by.
Note on D2: Enter the name of the Quality Management Plan used; most units will use the DIT-T Enterprise Quality Management Plan. If not, provide the name of your plan and include in that plan that you are following the DIT-T Enterprise Quality Management Plan and this plan includes additional quality requirements.
Note on J2: Enter the date the methodology was last updated and approved.
Note on M2: Enter person responsible for managing the project.
Note on A3: Enter the industry type of methodology mapped, such as Agile, Iterative, Waterfall, etc.
Note on D3: Enter the location where deliverable artifacts are stored.
Note on J3: Enter additional information about the methodology, if needed.
Note on K4: For the process to be mapped, review the DIT-T SDLC Key Deliverable in column C to determine if the deliverable is created, if it is called by a different name, and the name of the phase initiated in. Deliverables on all projects and required for audit should not be deleted (see column E).
Note on J5: Enter a 'Y' for required deliverables. The column is prepopulated with the project type values (H) to be mapped to. If additional deliverables in the Key Deliverables column (C) are required by the mapped methodology, enter a ‘Y’ in this column, enter phase name and key deliverable name. Use red text to indicate different from the DIT-T Enterprise SDLC Deliverables.
Note on K5: Enter the phase name for the phase the deliverable is initiated in.
Note on L5: Enter the name of the deliverable (this is the name that will be used for the document artifact name). If the deliverable is located in another system, such as a Work Request is located in ServiceNow, indicate how to find the deliverable and the System Name where it can be found. Examples can be found in the 'Approved Methodologies' folder, document name 'PMO_Enterprise Project (Waterfall)'.
Note on M5: For each Key Deliverable in the column highlighted in blue, enter either: - N/A for deliverable produced or - Exception Reason if deliverable is not produced.