## combined Prj and Chg
DIT-T Unit: GIS Unit |  |  | Methodology Owner/Contact: Jun Wu |  |  |  | Date Metholdology Initially Added: 03/02/2021 |  |  | Project Name:
Methodology Name: GIS Disciplined Agile Delivery (DAD) |  |  | Quality Management Plan Used: Operational Non-PMO Project |  |  |  | Date Last Updated: 03/02/2021 |  |  | Project Manager:
Methodology Type: Agile |  |  | Deliverables Repository: GIS Project Team Site |  |  |  | Comments: Link to description of methodology |  |  | Comments:
[6 empty] | Operational |  | Mapping Red Text = Differences from E-SDLC |  | Exceptions to Methodology
Phase | ID | Key Deliverable | Minimum Requirement | Req'd for Audit | Audit Control | Non-PMO Project (Medium Risk) | Req'd | Phase | Key Deliverable | Exception Reason N/A = Deliverable completed Blank = Deliverable is pending
Business Concept | 1 | Work Request |  | Y | ITGC03 | Y | Y | 1 Concept (ITR- neg 1) | GIS EMS Work Effort Request (or ServiceNow Request) or High Level Work Request
Business Concept | 2 | Alternatives Analysis | If required |  | ITGC03 |  |  | 1 Concept (ITR- neg 1) | High Level Requirements
Business Concept | 3 | Preliminary Business Case | Min: Scope of Work, Resource Plan, Cost Plan, Start/End Dates |  | ITGC03 |  |  | 1 Concept (ITR- neg 1) | Project Charter -Preliminary Business Case Section
Business Concept | 4 | Business Concept Exit Quality Review | [5 empty] | 1 Concept (ITR- neg 1) | Concept Exit Quality Review
Initiation | 5 | Scope of Work | Min: Work Definition, Resources, Estimated Cost, Start/End Dates | Y | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Project Charter -Scope of Work
Initiation | 6 | Scope of Work Approval | DOT Business & DIT-T approval required | Y | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Project Charter -Approvals Section
Initiation | 7 | Business Case |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Project Charter -Preliminary Business Case Section
Initiation | 8 | Benefits |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Project Charter -Goals Section
Initiation | 9 | Business Case Quality Review | [5 empty] | 2 Inception (ITR - 0) | Business Case Quality Review
Initiation | 10 | EPMO Business Case DP Approval | DIT EPMO & OSBM approved required |  |  |  |  | 2 Inception (ITR - 0) | Exception-GISU Projects don't require EPMO approval
Initiation | 11 | Cost Plan |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Project Charter - Project Budget Section
Initiation | 12 | Schedule |  |  | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Project Charter -Preliminary Target Milestones or Project Schedule or Schedule maintained in DevOps (Exportable)
Initiation | 13 | Change Management Plan |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Change Management Plan
Initiation | 14 | Procurement Plan | If procuring resources, products, services |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Procurement Plan
Initiation | 15 | Communication Plan |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Communication Plan
Initiation | 16 | Organization Chart |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | High-Level Requirements - Organization Chart
Initiation | 17 | Quality Management Plan |  | Y | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Quality Management Plan
Initiation | 18 | Risk Assessment/Mitigation Plan |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Project Charter - Assumptions, Restrictions, and External Dependencies & RAID Log
Initiation | 19 | Issues Log |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | RAID Log or ServiceNow Issues Log or GIS Mantis or DevOps
Initiation | 20 | Privacy Threshold Analysis (PTA) | Required if application not previously documented and/or if changing any privacy information. DIT-T Security & DIT Approval required. | Y | ITGC01 | Y | Y | 2 Inception (ITR - 0) | Privacy Threshold Analysis (PTA)
Initiation | 21 | Initiation Exit Quality Review |  |  | ITGC04 |  |  | 2 Inception (ITR - 0) | Initiation Exit Quality Review
Planning & Design | 22 | Project Change Request Log | [5 empty] | 2 Inception (ITR - 0) | RAID Log - Decisions or GIS Mantis or DevOps
Planning & Design | 23 | Project Change Request | DIT-T and Business Approval |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Project Change Request
Planning & Design | 24 | Project Change Request Quality Review | [5 empty] | 2 Inception (ITR - 0) | Project Change Request Quality Review
Planning & Design | 25 | EPMO Change Request DP Approval | EPMO and/or OSBM approval (if required) |  |  |  |  | 2 Inception (ITR - 0) | Exception Request-GISU Projects don't require EPMO approval
Planning & Design | 26 | SAP Cost Exception Report | [5 empty] | 2 Inception (ITR - 0) | SAP Cost Exception Report
Planning & Design | 27 | Requirements Management Plan |  |  | ITGC03 |  |  | 2 Inception (ITR - 0)
Planning & Design | 28 | Requirements | Must be approved by Business and other stakeholders, including Architecture, Security, Infrastructure, etc. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | 2 Inception (ITR - 0) | Requirements
Planning & Design | 29 | Requirements Approval | Required on all sizes of work except on small operational work, this may be included in Work Definition. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | 2 Inception (ITR - 0) | Requirements Approval
Planning & Design | 30 | Requirements Traceability Matrix | [5 empty] | 2 Inception (ITR - 0) | High-Level Requirements Document
Planning & Design | 32 | Architecture Design |  |  | ITGC01 ITGC02 |  |  | 2 Inception (ITR - 0) | Technical Architecture System Design (TASD)
Planning & Design | 33 | Architecture DP Quality Review | If required by EPMO |  |  |  |  | 2 Inception (ITR - 0) | Architecture DP Quality Review
Planning & Design | 34 | EPMO Architecture DP Approval | If required by EPMO DIT Architecture Approval required |  | ITGC01 ITGC02 |  |  | 2 Inception (ITR - 0) | EPMO Architecture DP Approval
Planning & Design | 35 | Security DP Quality Review | If required by EPMO |  |  |  |  | 2 Inception (ITR - 0) | Security DP Quality Review
Planning & Design | 36 | EPMO Security DP Approval | If required by EPMO DIT Approval Required |  | ITGC01 ITGC02 |  |  | 2 Inception (ITR - 0) | EPMO Security DP Approval
Planning & Design | 37 | Architecture Exception Request | If required, complete DIT Approval Required |  |  | Y | Y | 2 Inception (ITR - 0) | Architecture Exception Request
Planning & Design | 38 | NCID Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y | 2 Inception (ITR - 0) | NCID Exception Request
Planning & Design | 39 | Security Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y | 2 Inception (ITR - 0) | Security Exception Request
Planning & Design | 40 | Design Document |  | Y | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Design Document
Planning & Design | 41 | Design Approval | Business and other stakeholders approvals | Y | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Design Approval
Planning & Design | 42 | Business Continuity Plan | If required |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Business Continuity Plan
Planning & Design | 43 | Disaster Recovery Plan | If required |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Disaster Recovery Plan
Planning & Design | 44 | Training Plan | If required |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Training Plan
Planning & Design | 45 | Test Plan |  |  |  | Y | Y | 2 Inception (ITR - 0) | Test Plan or Test Plan in TestLink
Planning & Design | 46 | Acceptance Process and Criteria |  |  | ITGC03 | Y | Y | 2 Inception (ITR - 0) | Project Charter - Project Success Criteria Section & User Acceptance Test Plan
Planning & Design | 47 | Acceptance Process and Criteria Approval | Must be approved by Business and other stakeholders |  | ITGC03 | Y | Y | 2 Inception (ITR - 0) | User Acceptance Testing (UAT) Plan Approval
Planning & Design | 48 | Operational Level Agreement (OLA) | Required if there are changes to the current OLA. |  | ITGC04 | Y | Y | 2 Inception (ITR - 0) | Operations & Maintenance (O&M) Plan
Planning & Design | 49 | Operational Level Agreement (OLA) Approval | If required Must be approved by IT Stakeholders |  | ITGC04 | Y | Y | 2 Inception (ITR - 0) | Operations & Maintenance Plan (O&M) Approval
Planning & Design | 50 | Business Approval to Exit P&D |  |  | ITGC03 |  |  | 2 Inception (ITR - 0) | Business Approval to Exit P&D
Planning & Design | 51 | P&D Exit Quality Review |  |  | ITGC04 |  |  | 2 Inception (ITR - 0) | Inception Exit Quality Review
|  | If RFP required, deliverables below: |  |  |  |  | Exception Request for whole section for RFPs: GISU does not manage RFPs. We involve PMO if this type of procurement is needed, so these don't apply to us |  |  | If RFP required, deliverables below:
Planning & Design | 52 | RFP Request for Commodity/Service Form |  |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Request for Commodity/Service Form
Planning & Design | 53 | RFP Disaster Recovery Assessment |  |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Disaster Recovery Assessment
Planning & Design | 54 | RFP Sourcing Exception Request | If required for the RFP |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Sourcing Exception Request
Planning & Design | 55 | RFP Hosting Exception Request | If required for the RFP |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Hosting Exception Request
Planning & Design | 56 | RFP and Attachments |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP and Attachments
Planning & Design | 57 | RFP Proposal Evaluation Plan |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Proposal Evaluation Plan
Planning & Design | 58 | RFP Content Submission | [5 empty] | 2 Inception (ITR - 0) | RFP Content Submission
Planning & Design | 59 | RFP Individual Evaluation Workbooks |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Individual Evaluation Workbooks
Planning & Design | 60 | RFP Oral Presentation/Demonstration Guide |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Oral Presentation/Demonstration Guide
Planning & Design | 61 | RFP Consensus Evaluation Workbook |  |  | ITGC03 | Y |  | 2 Inception (ITR - 0) | RFP Consensus Evaluation Workbook
Planning & Design | 62 | RFP Evaluation Report with Award Recommendation |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Evaluation Report with Award Recommendation
Planning & Design | 63 | RFP Evaluation Report Approvals | Business and other stakeholders approvals required. |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFP Evaluation Report Approvals
Planning & Design | 64 | RFP CIO Presentation |  |  |  | Y |  | 2 Inception (ITR - 0) | RFP CIO Presentation
Planning & Design | 65 | RFP Evaluation Review Checklist | [5 empty] | 2 Inception (ITR - 0) | RFP Evaluation Review Checklist
Planning & Design | 66 | EPMO RFP Review DP Approval | DPMO Approval Required |  |  |  |  | 2 Inception (ITR - 0) | EPMO RFP Review DP Approval
Planning & Design | 67 | EPMO Contract Award Review DP Approval | DPMO Approval Required |  |  |  |  | 2 Inception (ITR - 0) | EPMO Contract Award Review DP Approval
Planning & Design |  | If Invitation for Bid (IFB) required, deliverables below: |  |  |  |  | Exception Request for whole section for IFBs:GISU does not manage IFBs. We involve PMO if this type of procurement is needed, so these don't apply to us |  |  | If Invitation for Bid (IFB) required, deliverables below:
Planning & Design | 68 | IFB Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB Request for Commodity/Service Form
Planning & Design | 69 | IFB Disaster Recovery Assessment | If required for IFB |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB Disaster Recovery Assessment
Planning & Design | 70 | IFB Sourcing Exception Request | If required for IFB |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB Sourcing Exception Request
Planning & Design | 71 | IFB Hosting Exception Request | If required for IFB |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB Hosting Exception Request
Planning & Design | 72 | IFB and Attachments |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB and Attachments
Planning & Design | 73 | IFB Statement of Work | May be required for Extensive Services |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB Statement of Work
Planning & Design | 74 | IFB Bid Review Checklist |  |  |  | Y |  | 2 Inception (ITR - 0) | IFB Bid Review Checklist
Planning & Design | 75 | IFB Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | IFB Award Approval
Planning & Design |  | IF Request for Quote (RFQ) required, deliverables below: |  |  |  |  | Exception Request for whole section for RFQs: GISU does not manage RFQs. We involve PMO if this type of procurement is needed, so these don't apply to us |  |  | IF Request for Quote (RFQ) required, deliverables below:
Planning & Design | 76 | RFQ Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Request for Commodity/Service Form
Planning & Design | 77 | RFQ Disaster Recovery Assessment | If required for RFQ |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Disaster Recovery Assessment
Planning & Design | 78 | RFQ Sourcing Exception Request | If required for RFQ |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Sourcing Exception Request
Planning & Design | 79 | RFQ Hosting Exception Request | If required for RFQ |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Hosting Exception Request
Planning & Design | 80 | RFQ and Attachments |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ and Attachments
Planning & Design | 81 | RFQ Market Research |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Market Research
Planning & Design | 82 | RFQ Estimate or Unofficial Quote |  |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Estimate or Unofficial Quote
Planning & Design | 83 | RFQ Statement of Work |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Statement of Work
Planning & Design | 84 | RFQ Quote Review Document |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Quote Review Document
Planning & Design | 85 | RFQ Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y |  | 2 Inception (ITR - 0) | RFQ Award Approval
Planning & Design |  | If Contract Modifications through Amendment required, deliverables below: |  |  |  |  | Exception Request for item# 91 due to the fact that the Statements of Work and Supplemental Staffing contracts GISU typically uses for projects do not require doing additional market research mid-contract. This need would be addressed with a fresh statement of work if the SOW amendment approval was declined or by hiring a new staff under the Supplemental Staffing Contract. Recommend keeping items 101 & 91 as 'if required for Amendment' in case there are unique situations. |  |  | If Contract Modifications through Amendment required, deliverables below:
Planning & Design | 86 | Amendment Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Exception Request | 3 Construction thru Transition | Amendment Request for Commodity/Service Form
Planning & Design | 87 | Amendment Disaster Recovery Assessment | May be required if change in scope of work |  | ITGC03 ITGC04 | Y | Y | 3 Construction thru Transition | Amendment Disaster Recovery Assessment
Planning & Design | 88 | Amendment Sourcing Exception Request | If required for Amendment |  | ITGC04 | Y | Y | 3 Construction thru Transition | Amendment Sourcing Exception Request
Planning & Design | 89 | Amendment Hosting Exception Request | If required for Amendment |  | ITGC04 | Y | Y | 3 Construction thru Transition | Amendment Hosting Exception Request
Planning & Design | 90 | Amendment and Attachments |  |  | ITGC03 ITGC04 | Y | Y | 3 Construction thru Transition | Amendment and Attachments
Planning & Design | 91 | Amendment Market Research |  |  | ITGC03 ITGC04 | Y | Exception Request | 3 Construction thru Transition | Amendment Market Research
Planning & Design | 92 | Amendment Estimate or Unofficial Quote |  |  | ITGC03 ITGC04 | Y | Y | 3 Construction thru Transition | Amendment Estimate or Unofficial Quote
Planning & Design | 93 | Amendment Statement of Work | May be required for additional work within scope of work in existing contract |  | ITGC03 ITGC04 | Y | Y | 3 Construction thru Transition | Amendment Statement of Work
Planning & Design | 94 | Amendment Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y | 3 Construction thru Transition | Amendment Approval
|  | IF Request for Information (RFI), deliverables below: |  |  |  |  | Exception Request for whole section for RFIs: GISU does not manage RFIs. We involve PMO if this type of solicitation is needed, so these don't apply to us |  |  | IF Request for Information (RFI), deliverables below:
Planning & Design | 95 | RFI |  |  | ITGC03 ITGC04 | Y |  | 2 Inception (ITR - 0) | RFI
Exception Request for all EPMO Approval items. GIS Unit does not required EPMO review or approval for our projects.
Execute & Build | 31 | Application Architecture Design (AAD) | DIT-T Architecture Approval Required | Y | ITGC01 ITGC02 | Y | Y | 3 Construction | Application Architecture Design (AAD)
Execute & Build | 96 | Code Structural Quality Analysis (CAST) Report | If required |  |  |  |  | 3 Construction | Code Structural Quality Analysis (CAST) Report
Execute & Build | 97 | Component Integration Test (CIT) Approved |  | Y | ITGC02 | Y | Y | 3 Construction | Component Integration Test (CIT) Approved
Execute & Build | 98 | System Integration Test (SIT) Approved |  | Y | ITGC02 | Y | Y | 3 Construction | System Integration Test (SIT) Approved
Execute & Build | 99 | Performance Testing Approved | If required |  |  | Y | Y | 3 Construction | Performance Testing Approved
Execute & Build | 100 | IT Testing Complete Approval |  | Y | ITGC02 | Y | Y | 3 Construction | IT Testing Complete Approval
Execute & Build | 101 | User Acceptance Plan and Script | IT management involves users in the design of applications, selection of packaged software and testing thereof. | Y | ITGC03 | Y | Y | 4 Transition | User Acceptance Plan and Script
Execute & Build | 102 | Sponsor Approved UAT |  | Y | ITGC03 | Y | Y | 4 Transition | Sponsor Approved UAT
Execute & Build | 103 | Implementation Plan |  |  |  |  | Y | 4 Transition | Implementation Plan
Execute & Build | 104 | Go Live Readiness Assessment |  | Y | ITGC03 | Y | Y | 4 Transition | Go Live Readiness Assessment
Execute & Build | 105 | Go Live Approval | Business and other Stakeholders approval | Y | ITGC03 | Y | Y | 4 Transition | Go Live Approval
Execute & Build | 106 | Project Go Live Readiness DP Quality Review | If required |  |  |  |  | 4 Transition | Project Go Live Readiness DP Quality Review
Execute & Build | 107 | EPMO Go Live Readiness DP Approval | If required. EPMO approval |  |  |  |  | 4 Transition
Execute & Build | 108 | E&B Exit Quality Review | [5 empty] | 4 Transition | Construction Exit Quality Review
Implementation | 109 | Business Approval to Close the Project |  |  | ITGC03 |  |  | 4 Transition | Business Approval to Close the Project
Implementation | 110 | Implementation Exit Quality Review | [5 empty] | 4 Transition | Implementation Exit Quality Review
Exception Request for whole section for RFIs: GISU does not manage RFIs. We involve PMO if this type of solicitation is needed, so these don't apply to us
Closeout | 111 | SAP Commitments Reconciled | [5 empty] | 4 Transition | SAP Commitments Reconciled
Closeout | 112 | Lessons Learned Survey | [5 empty] | 4 Transition | Lessons Learned Survey
Closeout | 113 | EPMO Lessons Learned | [5 empty] | 4 Transition | Lessons Learned Document & Team Recommendations
Closeout | 114 | EPMO Closeout Report | [5 empty] | 4 Transition
Closeout | 115 | Closeout Quality Review | [5 empty] | 4 Transition | Transition Quality Review
|  | No PMO item ID# identified | [6 empty] | IF GIS Master Contract Statements of Work (SOW), additional deliverables below: | IF GIS Master Contract Statements of Work (SOW), additional deliverables below:
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Budget approval and WBS Number Assignment
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Master Contract Statement of Work
[8 empty] | 3 Inception (ITR-0) | Hosting Exception Request
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Vendor Responses
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Evaluation Workbook
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Clarifications issued to all vendor
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Sponsor Approval of Selected Vendor
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Award Recommendation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Statewide IT Procurement Office Award Authorization
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Commodity Service Request
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | ITBO Executed Purchase Order
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | NCID Account Approval
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | DOT Email Approval
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | ID/Security Badge Approval
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | NCID Account Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | DOT Email Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | ID Security Badge Deactivation Confirmation
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Retirement Analysis Document
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Retirement Plan
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Retirement Cost Plan
Unsure of PMO phase | ## | Not in PMO QMP |  |  |  |  | Y | Retirement | Removal of System Approval
Planning & Design | [8 empty] | IF IT Supplemental Staffing Contract, additional deliverables below: | IF IT Supplemental Staffing Contract, additional deliverables below:
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Business Supplemental Staff Request
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Business WBS Number_Other SAP Number
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | NCID Accout Approval
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | DOT Email Approval
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | ID/Security Badge Approval
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | New Contractor Onboarding Quality Checklist
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | NCID Account Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | DOT Email Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | ID/Security Badge Deactivation Confirmation
Planning & Design | ## | Not in PMO QMP |  |  |  |  | Y | 2 Inception (ITR-0) | Contractor Offboarding Quality Checklist
Note on A1: Enter the name of the unit that owns the mapped methodology
Note on D1: Enter person to contact if there are questions about the mapped methodology.
Note on J1: Enter the date approved and added to the DIT-T Enterprise SDLC site on Connect.
Note on M1: Enter Project Name.
Note on A2: Enter the name the unit refers to their methodology by.
Note on D2: Enter the name of the Quality Management Plan used; most units will use the DIT-T Enterprise Quality Management Plan. If not, provide the name of your plan and include in that plan that you are following the DIT-T Enterprise Quality Management Plan and this plan includes additional quality requirements.
Note on J2: Enter the date the methodology was last updated and approved.
Note on M2: Enter person responsible for managing the project.
Note on A3: Enter the industry type of methodology mapped, such as Agile, Iterative, Waterfall, etc.
Note on D3: Enter the location where deliverable artifacts are stored.
Note on J3: Enter additional information about the methodology, if needed.
Note on K4: For the process to be mapped, review the DIT-T SDLC Key Deliverable in column C to determine if the deliverable is created, if it is called by a different name, and the name of the phase initiated in. Deliverables on all projects and required for audit should not be deleted (see column E).
Note on J5: Enter a 'Y' for required deliverables. The column is prepopulated with the project type values (H) to be mapped to. If additional deliverables in the Key Deliverables column (C) are required by the mapped methodology, enter a ‘Y’ in this column, enter phase name and key deliverable name. Use red text to indicate different from the DIT-T Enterprise SDLC Deliverables.
Note on K5: Enter the phase name for the phase the deliverable is initiated in.
Note on L5: Enter the name of the deliverable (this is the name that will be used for the document artifact name). If the deliverable is located in another system, such as a Work Request is located in ServiceNow, indicate how to find the deliverable and the System Name where it can be found. Examples can be found in the 'Approved Methodologies' folder, document name 'PMO_Enterprise Project (Waterfall)'.
Note on M5: For each Key Deliverable in the column highlighted in blue, enter either: - N/A for deliverable produced or - Exception Reason if deliverable is not produced.