## Original
DIT-T Unit: Web Applications Team |  |  | Process Owner/Contact: James Merricks |  |  |  | Date Process Initially Added: 03/02/2021 |  |  | Project Name:
Process Name: Small Agile Application |  |  | Quality Management Plan Used: Enterprise |  |  |  | Date Last Updated: 03/02/2021 |  |  | Project Manager:
Methodology Type: Agile |  |  | Document Repository: Project's Team Site |  |  |  | Comments: |  |  | Comments:
[6 empty] | Operational |  | Mapping Red Text = Differences from E-SDLC |  | Exceptions to Methodology
Phase | ID | Key Deliverable | Minimum Requirement | Req'd for Audit | Audit Control | Non-PMO Project (Medium Risk) | Req'd | Phase | Key Deliverable | Exception Reason N/A = Deliverable completed Blank = Deliverable is pending
Business Concept | 1 | Work Request |  | Y | ITGC03 | Y | Y | Business Concept | Work Request
Business Concept | 2 | Alternatives Analysis | If required |  | ITGC03
Business Concept | 3 | Preliminary Business Case | Min: Scope of Work, Resource Plan, Cost Plan, Start/End Dates |  | ITGC03 |  |  | Business Concept | Preliminary Business Case
Business Concept | 4 | Business Concept Exit Quality Review
Initiation | 5 | Scope of Work | Min: Work Definition, Resources, Estimated Cost, Start/End Dates | Y | ITGC03 | Y | Y | Initiation | Scope of Work
Initiation | 6 | Scope of Work Approval | DOT Business & DIT-T approval required | Y | ITGC03 | Y | Y | Initiation | Scope of Work Approval
Initiation | 7 | Business Case |  |  | ITGC03 |  |  | Initiation | Business Case
Initiation | 8 | Benefits |  |  | ITGC03
Initiation | 9 | Business Case Quality Review
Initiation | 10 | EPMO Business Case DP Approval | DIT EPMO & OSBM approved required
Initiation | 11 | Cost Plan |  |  | ITGC03
Initiation | 12 | Schedule |  |  | ITGC03 | Y | Y | Initiation | Schedule
Initiation | 13 | Change Management Plan |  |  | ITGC03
Initiation | 14 | Procurement Plan | If procuring resources, products, services |  | ITGC03 |  |  | Initiation | Procurement Plan
Initiation | 15 | Communication Plan |  |  | ITGC03
Initiation | 16 | Organization Chart |  |  | ITGC03
Initiation | 17 | Quality Management Plan |  | Y | ITGC03 | Y | Y | Initiation | Quality Management Plan
Initiation | 18 | Risk Assessment/Mitigation Plan |  |  | ITGC03
Initiation | 19 | Issues Log |  |  | ITGC03 |  |  | Initiation | Issues Log
Initiation | 20 | Privacy Threshold Analysis (PTA) | Required if application not previously documented and/or if changing any privacy information. DIT-T Security & DIT Approval required. | Y | ITGC01 | Y | Y | Initiation | Privacy Threshold Analysis (PTA)
Initiation | 21 | Initiation Exit Quality Review |  |  | ITGC04
Planning & Design | 22 | Project Change Request Log
Planning & Design | 23 | Project Change Request | DIT-T and Business Approval |  | ITGC03
Planning & Design | 24 | Project Change Request Quality Review
Planning & Design | 25 | EPMO Change Request DP Approval | EPMO and/or OSBM approval (if required)
Planning & Design | 26 | SAP Cost Exception Report
Planning & Design | 27 | Requirements Management Plan |  |  | ITGC03
Planning & Design | 28 | Requirements | Must be approved by Business and other stakeholders, including Architecture, Security, Infrastructure, etc. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | Planning & Design | Requirements
Planning & Design | 29 | Requirements Approval | Required on all sizes of work except on small operational work, this may be included in Work Definition. | Y | ITGC01 ITGC02 ITGC03 | Y | Y | Planning & Design | Requirements Approval
Planning & Design | 30 | Requirements Traceability Matrix
Planning & Design | 32 | Architecture Design |  |  | ITGC01 ITGC02 |  |  | Planning & Design | Technical Architecture System Design (TASD)
Planning & Design | 33 | Architecture DP Quality Review | If required by EPMO
Planning & Design | 34 | EPMO Architecture DP Approval | If required by EPMO DIT Architecture Approval required |  | ITGC01 ITGC02
Planning & Design | 35 | Security DP Quality Review | If required by EPMO
Planning & Design | 36 | EPMO Security DP Approval | If required by EPMO DIT Approval Required |  | ITGC01 ITGC02
Planning & Design | 37 | Architecture Exception Request | If required, complete DIT Approval Required |  |  | Y | Y | Planning & Design | Architecture Exception Request
Planning & Design | 38 | NCID Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y | Planning & Design | NCID Exception Request
Planning & Design | 39 | Security Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y | Planning & Design | Security Exception Request
Planning & Design | 40 | Design Document |  | Y | ITGC03 | Y | Y | Planning & Design | Design Document
Planning & Design | 41 | Design Approval | Business and other stakeholders approvals | Y | ITGC03 | Y | Y | Planning & Design | Design Approval
Planning & Design | 42 | Business Continuity Plan | If required |  | ITGC03
Planning & Design | 43 | Disaster Recovery Plan | If required |  | ITGC03
Planning & Design | 44 | Training Plan | If required |  | ITGC03
Planning & Design | 45 | Test Plan |  |  |  | Y | Y | Planning & Design | Test Plan
Planning & Design | 46 | Acceptance Process and Criteria |  |  | ITGC03 | Y | Y | Planning & Design | Acceptance Process and Criteria
Planning & Design | 47 | Acceptance Process and Criteria Approval | Must be approved by Business and other stakeholders |  | ITGC03 | Y | Y | Planning & Design | Acceptance Process and Criteria Approval
Planning & Design | 48 | Operational Level Agreement (OLA) | Required if there are changes to the current OLA. |  | ITGC04 | Y | Y | Planning & Design | Operational Level Agreement (OLA)
Planning & Design | 49 | Operational Level Agreement (OLA) Approval | If required Must be approved by IT Stakeholders |  | ITGC04 | Y | Y | Planning & Design | Operational Level Agreement (OLA) Approval
Planning & Design | 50 | Business Approval to Exit P&D |  |  | ITGC03 |  |  | Planning & Design | Business Approval to Exit P&D
Planning & Design | 51 | P&D Exit Quality Review |  |  | ITGC04
Planning & Design |  | If RFP required, deliverables below: | [5 empty] | Planning & Design | If RFP required, deliverables below: | If RFP required, deliverables below:
Planning & Design | 52 | RFP Request for Commodity/Service Form |  |  | ITGC04 | Y | Y | Planning & Design | RFP Request for Commodity/Service Form
Planning & Design | 53 | RFP Disaster Recovery Assessment |  |  | ITGC04 | Y | Y | Planning & Design | RFP Disaster Recovery Assessment
Planning & Design | 54 | RFP Sourcing Exception Request | If required for the RFP |  | ITGC04 | Y | Y | Planning & Design | RFP Sourcing Exception Request
Planning & Design | 55 | RFP Hosting Exception Request | If required for the RFP |  | ITGC04 | Y | Y | Planning & Design | RFP Hosting Exception Request
Planning & Design | 56 | RFP and Attachments |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFP and Attachments
Planning & Design | 57 | RFP Proposal Evaluation Plan |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFP Proposal Evaluation Plan
Planning & Design | 58 | RFP Content Submission | [5 empty] | Planning & Design | RFP Content Submission
Planning & Design | 59 | RFP Individual Evaluation Workbooks |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFP Individual Evaluation Workbooks
Planning & Design | 60 | RFP Oral Presentation/Demonstration Guide |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFP Oral Presentation/Demonstration Guide
Planning & Design | 61 | RFP Consensus Evaluation Workbook |  |  | ITGC03 | Y | Y | Planning & Design | RFP Consensus Evaluation Workbook
Planning & Design | 62 | RFP Evaluation Report with Award Recommendation |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFP Evaluation Report with Award Recommendation
Planning & Design | 63 | RFP Evaluation Report Approvals | Business and other stakeholders approvals required. |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFP Evaluation Report Approvals
Planning & Design | 64 | RFP CIO Presentation |  |  |  | Y | Y | Planning & Design | RFP CIO Presentation
Planning & Design | 65 | RFP Evaluation Review Checklist | [5 empty] | Planning & Design | RFP Evaluation Review Checklist
Planning & Design | 66 | EPMO RFP Review DP Approval | DPMO Approval Required |  |  |  |  | Planning & Design | EPMO RFP Review DP Approval
Planning & Design | 67 | EPMO Contract Award Review DP Approval | DPMO Approval Required |  |  |  |  | Planning & Design | EPMO Contract Award Review DP Approval
Planning & Design |  | If Invitation for Bid (IFB) required, deliverables below: | [5 empty] | Planning & Design | If Invitation for Bid (IFB) required, deliverables below: | If Invitation for Bid (IFB) required, deliverables below:
Planning & Design | 68 | IFB Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | IFB Request for Commodity/Service Form
Planning & Design | 69 | IFB Disaster Recovery Assessment | If required for IFB |  | ITGC03 ITGC04 | Y | Y | Planning & Design | IFB Disaster Recovery Assessment
Planning & Design | 70 | IFB Sourcing Exception Request | If required for IFB |  | ITGC04 | Y | Y | Planning & Design | IFB Sourcing Exception Request
Planning & Design | 71 | IFB Hosting Exception Request | If required for IFB |  | ITGC04 | Y | Y | Planning & Design | IFB Hosting Exception Request
Planning & Design | 72 | IFB and Attachments |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | IFB and Attachments
Planning & Design | 73 | IFB Statement of Work | May be required for Extensive Services |  | ITGC03 ITGC04 | Y | Y | Planning & Design | IFB Statement of Work
Planning & Design | 74 | IFB Bid Review Checklist |  |  |  | Y | Y | Planning & Design | IFB Bid Review Checklist
Planning & Design | 75 | IFB Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y | Planning & Design | IFB Award Approval
Planning & Design |  | IF Request for Quote (RFQ) required, deliverables below: | [5 empty] | Planning & Design | IF Request for Quote (RFQ) required, deliverables below: | IF Request for Quote (RFQ) required, deliverables below:
Planning & Design | 76 | RFQ Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFQ Request for Commodity/Service Form
Planning & Design | 77 | RFQ Disaster Recovery Assessment | If required for RFQ |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFQ Disaster Recovery Assessment
Planning & Design | 78 | RFQ Sourcing Exception Request | If required for RFQ |  | ITGC04 | Y | Y | Planning & Design | RFQ Sourcing Exception Request
Planning & Design | 79 | RFQ Hosting Exception Request | If required for RFQ |  | ITGC04 | Y | Y | Planning & Design | RFQ Hosting Exception Request
Planning & Design | 80 | RFQ and Attachments |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFQ and Attachments
Planning & Design | 81 | RFQ Market Research |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFQ Market Research
Planning & Design | 82 | RFQ Estimate or Unofficial Quote |  |  | ITGC04 | Y | Y | Planning & Design | RFQ Estimate or Unofficial Quote
Planning & Design | 83 | RFQ Statement of Work |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFQ Statement of Work
Planning & Design | 84 | RFQ Quote Review Document |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFQ Quote Review Document
Planning & Design | 85 | RFQ Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y | Planning & Design | RFQ Award Approval
Planning & Design |  | If Contract Modifications through Amendment required, deliverables below: | [5 empty] | Planning & Design | If Contract Modifications through Amendment required, deliverables below: | If Contract Modifications through Amendment required, deliverables below:
Planning & Design | 86 | Amendment Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | Amendment Request for Commodity/Service Form
Planning & Design | 87 | Amendment Disaster Recovery Assessment | May be required if change in scope of work |  | ITGC03 ITGC04 | Y | Y | Planning & Design | Amendment Disaster Recovery Assessment
Planning & Design | 88 | Amendment Sourcing Exception Request | If required for Amendment |  | ITGC04 | Y | Y | Planning & Design | Amendment Sourcing Exception Request
Planning & Design | 89 | Amendment Hosting Exception Request | If required for Amendment |  | ITGC04 | Y | Y | Planning & Design | Amendment Hosting Exception Request
Planning & Design | 90 | Amendment and Attachments |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | Amendment and Attachments
Planning & Design | 91 | Amendment Market Research |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | Amendment Market Research
Planning & Design | 92 | Amendment Estimate or Unofficial Quote |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | Amendment Estimate or Unofficial Quote
Planning & Design | 93 | Amendment Statement of Work | May be required for additional work within scope of work in existing contract |  | ITGC03 ITGC04 | Y | Y | Planning & Design | Amendment Statement of Work
Planning & Design | 94 | Amendment Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y | Planning & Design | Amendment Approval
Planning & Design |  | IF Request for Information (RFI), deliverables below: | [5 empty] | Planning & Design | IF Request for Information (RFI), deliverables below: | IF Request for Information (RFI), deliverables below:
Planning & Design | 95 | RFI |  |  | ITGC03 ITGC04 | Y | Y | Planning & Design | RFI
Execute & Build | 31 | Application Architecture Design (AAD) | DIT-T Architecture Approval Required | Y | ITGC01 ITGC02 | Y | Y | Execute & Build | Application Architecture Design (AAD)
Execute & Build | 96 | Code Structural Quality Analysis (CAST) Report | If required
Execute & Build | 97 | Component Integration Test (CIT) Approved |  | Y | ITGC02 | Y | Y | Execute & Build | Component Integration Test (CIT) Approved
Execute & Build | 98 | System Integration Test (SIT) Approved |  | Y | ITGC02 | Y | Y | Execute & Build | System Integration Test (SIT) Approved
Execute & Build | 99 | Performance Testing Approved | If required |  |  | Y | Y | Execute & Build | Performance Testing Approved
Execute & Build | 100 | IT Testing Complete Approval |  | Y | ITGC02 | Y | Y | Execute & Build | IT Testing Complete Approval
Execute & Build | 101 | User Acceptance Plan and Script | IT management involves users in the design of applications, selection of packaged software and testing thereof. | Y | ITGC03 | Y | Y | Execute & Build | User Acceptance Plan and Script
Execute & Build | 102 | Sponsor Approved UAT |  | Y | ITGC03 | Y | Y | Execute & Build | Sponsor Approved UAT
Execute & Build | 103 | Implementation Plan | [5 empty] | Execute & Build | Implementation Plan
Execute & Build | 104 | Go Live Readiness Assessment |  | Y | ITGC03 | Y | Y | Execute & Build | Go Live Readiness Assessment
Execute & Build | 105 | Go Live Approval | Business and other Stakeholders approval | Y | ITGC03 | Y | Y | Execute & Build | Go Live Approval
Execute & Build | 106 | Project Go Live Readiness DP Quality Review | If required
Execute & Build | 107 | EPMO Go Live Readiness DP Approval | If required. EPMO approval
Execute & Build | 108 | E&B Exit Quality Review | [5 empty] | Execute & Build | E&B Exit Quality Review
Implementation | 109 | Business Approval to Close the Project |  |  | ITGC03 |  |  | Implementation | Business Approval to Close the Project
Implementation | 110 | Implementation Exit Quality Review
Closeout | 111 | SAP Commitments Reconciled | [5 empty] | Closeout | SAP Commitments Reconciled
Closeout | 112 | Lessons Learned Survey
Closeout | 113 | EPMO Lessons Learned
Closeout | 114 | EPMO Closeout Report
Closeout | 115 | Closeout Quality Review | [5 empty] | Closeout | Closeout Quality Review
Note on A1: Enter the name of the unit that owns the mapped methodology.
Note on D1: Enter person to contact if there are questions about the mapped methodology.
Note on J1: Enter the date approved and added to the DIT-T Enterprise SDLC site on Connect.
Note on M1: Enter Project Name.
Note on A2: Enter the name the unit refers to their methodology by.
Note on D2: Enter the name of the Quality Management Plan used; most units will use the DIT-T Enterprise Quality Management Plan. If not, provide the name of your plan and include in that plan that you are following the DIT-T Enterprise Quality Management Plan and this plan includes additional quality requirements.
Note on J2: Enter the date the methodology was last updated and approved.
Note on M2: Enter person responsible for managing the project.
Note on A3: Enter the industry type of methodology mapped, such as Agile, Iterative, Waterfall, etc.
Note on D3: Enter the location where deliverable artifacts are stored.
Note on J3: Enter additional information about the methodology, if needed.
Note on K4: For the process to be mapped, review the DIT-T SDLC Key Deliverable in column C to determine if the deliverable is created, if it is called by a different name, and the name of the phase initiated in. Deliverables on all projects and required for audit should not be deleted (see column E).
Note on J5: Enter a 'Y' for required deliverables. The column is prepopulated with the project type values (H) to be mapped to. If additional deliverables in the Key Deliverables column (C) are required by the mapped methodology, enter a ‘Y’ in this column, enter phase name and key deliverable name. Use red text to indicate different from the DIT-T Enterprise SDLC Deliverables.
Note on K5: Enter the phase name for the phase the deliverable is initiated in.
Note on L5: Enter the name of the deliverable (this is the name that will be used for the document artifact name). If the deliverable is located in another system, such as a Work Request is located in ServiceNow, indicate how to find the deliverable and the System Name where it can be found. Examples can be found in the 'Approved Methodologies' folder, document name 'PMO_Enterprise Project (Waterfall)'.
Note on M5: For each Key Deliverable in the column highlighted in blue, enter either: - N/A for deliverable produced or - Exception Reason if deliverable is not produced.