## Original
DIT-T Unit: |  |  | Process Owner/Contact: |  |  |  | Date Process Initially Added:
Process Name: |  |  | Quality Management Plan Used: |  |  |  | Date Last Updated:
Methodology Type: |  |  | Document Repository: |  |  |  | Comments:
[6 empty] | PMO |  | Mapping Red Text = Differences from E-SDLC
Phase | ID | Key Deliverable | Minimum Requirement | Req'd for Audit | Audit Control | Lite (Medium Risk) | Req'd | Phase | Key Deliverable
Business Concept | 1 | Work Request |  | Y | ITGC03 | Y | Y
Business Concept | 2 | Alternatives Analysis | If required |  | ITGC03
Business Concept | 3 | Preliminary Business Case | Min: Scope of Work, Resource Plan, Cost Plan, Start/End Dates |  | ITGC03 | Y | Y
Business Concept | 4 | Business Concept Exit Quality Review |  |  |  | Y | Y
Initiation | 5 | Scope of Work | Min: Work Definition, Resources, Estimated Cost, Start/End Dates | Y | ITGC03 | Y | Y
Initiation | 6 | Scope of Work Approval | DOT Business & DIT-T approval required | Y | ITGC03 | Y | Y
Initiation | 7 | Business Case |  |  | ITGC03 | Y | Y
Initiation | 8 | Benefits |  |  | ITGC03 | Y | Y
Initiation | 9 | Business Case Quality Review |  |  |  | Y | Y
Initiation | 10 | EPMO Business Case DP Approval | DIT EPMO & OSBM approved required |  |  | Y | Y
Initiation | 11 | Cost Plan |  |  | ITGC03 | Y | Y
Initiation | 12 | Schedule |  |  | ITGC03 | Y | Y
Initiation | 13 | Change Management Plan |  |  | ITGC03 | Y | Y
Initiation | 14 | Procurement Plan | If procuring resources, products, services |  | ITGC03 | Y | Y
Initiation | 15 | Communication Plan |  |  | ITGC03 | Y | Y
Initiation | 16 | Organization Chart |  |  | ITGC03 | Y | Y
Initiation | 17 | Enterprise Quality Management Plan |  | Y | ITGC03 | Y | Y
Initiation | 18 | Risk Assessment/Mitigation Plan |  |  | ITGC03 | Y | Y
Initiation | 19 | Issues Log |  |  | ITGC03 | Y | Y
Initiation | 20 | Privacy Threshold Analysis (PTA) | Required if application not previously documented and/or if changing any privacy information. DIT-T Security & DIT Approval required. | Y | ITGC01 | Y | Y
Initiation | 21 | Initiation Exit Quality Review |  |  | ITGC04 | Y | Y
Planning & Design | 22 | Project Change Request Log |  |  |  | Y | Y
Planning & Design | 23 | Project Change Request | DIT-T and Business Approval |  | ITGC03 | Y | Y
Planning & Design | 24 | Project Change Request Quality Review |  |  |  | Y | Y
Planning & Design | 25 | EPMO Change Request DP Approval | EPMO and/or OSBM approval (if required) |  |  | Y | Y
Planning & Design | 26 | SAP Cost Exception Report |  |  |  | Y | Y
Planning & Design | 27 | Requirements Management Plan |  |  | ITGC03 | Y | Y
Planning & Design | 28 | Requirements | Must be approved by Business and other stakeholders, including Architecture, Security, Infrastructure, etc. | Y | ITGC01 ITGC02 ITGC03 | Y | Y
Planning & Design | 29 | Requirements Approval | Required on all sizes of work except on small operational work, this may be included in Work Definition. | Y | ITGC01 ITGC02 ITGC03 | Y | Y
Planning & Design | 30 | Requirements Traceability Matrix |  |  |  | Y | Y
Planning & Design | 32 | Architecture Design |  |  | ITGC01 ITGC02 | Y | Y
Planning & Design | 33 | Architecture DP Quality Review | If required by EPMO |  |  | Y | Y
Planning & Design | 34 | EPMO Architecture DP Approval | If required by EPMO DIT Architecture Approval required |  | ITGC01 ITGC02 | Y | Y
Planning & Design | 35 | Security DP Quality Review | If required by EPMO |  |  | Y | Y
Planning & Design | 36 | EPMO Security DP Approval | If required by EPMO DIT Approval Required |  | ITGC01 ITGC02 | Y | Y
Planning & Design | 37 | Architecture Exception Request | If required, complete DIT Approval Required |  |  | Y | Y
Planning & Design | 38 | NCID Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y
Planning & Design | 39 | Security Exception Request | If required, complete DIT Approval Required |  | ITGC01 | Y | Y
Planning & Design | 40 | Design Document |  | Y | ITGC03 | Y | Y
Planning & Design | 41 | Design Approval | Business and other stakeholders approvals | Y | ITGC03 | Y | Y
Planning & Design | 42 | Business Continuity Plan | If required |  | ITGC03 | Y | Y
Planning & Design | 43 | Disaster Recovery Plan | If required |  | ITGC03 | Y | Y
Planning & Design | 44 | Training Plan | If required |  | ITGC03 | Y | Y
Planning & Design | 45 | Test Plan |  |  |  | Y | Y
Planning & Design | 46 | Acceptance Process and Criteria |  |  | ITGC03 | Y | Y
Planning & Design | 47 | Acceptance Process and Criteria Approval | Must be approved by Business and other stakeholders |  | ITGC03 | Y | Y
Planning & Design | 48 | Operational Level Agreement (OLA) | Required if there are changes to the current OLA. |  | ITGC04 | Y | Y
Planning & Design | 49 | Operational Level Agreement (OLA) Approval | If required Must be approved by IT Stakeholders |  | ITGC04 | Y | Y
Planning & Design | 50 | Business Approval to Exit P&D |  |  | ITGC03 | Y | Y
Planning & Design | 51 | P&D Exit Quality Review |  |  | ITGC04 | Y | Y
Planning & Design |  | If RFP required, deliverables below: | [6 empty] | If RFP required, deliverables below:
Planning & Design | 52 | RFP Request for Commodity/Service Form |  |  | ITGC04 | Y | Y
Planning & Design | 53 | RFP Disaster Recovery Assessment |  |  | ITGC04 | Y | Y
Planning & Design | 54 | RFP Sourcing Exception Request | If required for the RFP |  | ITGC04 | Y | Y
Planning & Design | 55 | RFP Hosting Exception Request | If required for the RFP |  | ITGC04 | Y | Y
Planning & Design | 56 | RFP and Attachments |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 57 | RFP Proposal Evaluation Plan |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 58 | RFP Content Submission |  |  |  | Y | Y
Planning & Design | 59 | RFP Individual Evaluation Workbooks |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 60 | RFP Oral Presentation/Demonstration Guide |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 61 | RFP Consensus Evaluation Workbook |  |  | ITGC03 | Y | Y
Planning & Design | 62 | RFP Evaluation Report with Award Recommendation |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 63 | RFP Evaluation Report Approvals | Business and other stakeholders approvals required. |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 64 | RFP CIO Presentation |  |  |  | Y | Y
Planning & Design | 65 | RFP Evaluation Review Checklist |  |  |  | Y | Y
Planning & Design | 66 | EPMO RFP Review DP Approval | DPMO Approval Required |  |  | Y | Y
Planning & Design | 67 | EPMO Contract Award Review DP Approval | DPMO Approval Required |  |  | Y | Y
Planning & Design |  | If Invitation for Bid (IFB) required, deliverables below: | [6 empty] | If Invitation for Bid (IFB) required, deliverables below:
Planning & Design | 68 | IFB Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 69 | IFB Disaster Recovery Assessment | If required for IFB |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 70 | IFB Sourcing Exception Request | If required for IFB |  | ITGC04 | Y | Y
Planning & Design | 71 | IFB Hosting Exception Request | If required for IFB |  | ITGC04 | Y | Y
Planning & Design | 72 | IFB and Attachments |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 73 | IFB Statement of Work | May be required for Extensive Services |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 74 | IFB Bid Review Checklist |  |  |  | Y | Y
Planning & Design | 75 | IFB Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y
Planning & Design |  | IF Request for Quote (RFQ) required, deliverables below: | [6 empty] | IF Request for Quote (RFQ) required, deliverables below:
Planning & Design | 76 | RFQ Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 77 | RFQ Disaster Recovery Assessment | If required for RFQ |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 78 | RFQ Sourcing Exception Request | If required for RFQ |  | ITGC04 | Y | Y
Planning & Design | 79 | RFQ Hosting Exception Request | If required for RFQ |  | ITGC04 | Y | Y
Planning & Design | 80 | RFQ and Attachments |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 81 | RFQ Market Research |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 82 | RFQ Estimate or Unofficial Quote |  |  | ITGC04 | Y | Y
Planning & Design | 83 | RFQ Statement of Work |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 84 | RFQ Quote Review Document |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 85 | RFQ Award Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y
Planning & Design |  | If Contract Modifications through Amendment required, deliverables below: | [6 empty] | If Contract Modifications through Amendment required, deliverables below:
Planning & Design | 86 | Amendment Request for Commodity/Service Form |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 87 | Amendment Disaster Recovery Assessment | May be required if change in scope of work |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 88 | Amendment Sourcing Exception Request | If required for Amendment |  | ITGC04 | Y | Y
Planning & Design | 89 | Amendment Hosting Exception Request | If required for Amendment |  | ITGC04 | Y | Y
Planning & Design | 90 | Amendment and Attachments |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 91 | Amendment Market Research |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 92 | Amendment Estimate or Unofficial Quote |  |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 93 | Amendment Statement of Work | May be required for additional work within scope of work in existing contract |  | ITGC03 ITGC04 | Y | Y
Planning & Design | 94 | Amendment Approval | Business and other stakeholders approvals required. |  | ITGC04 | Y | Y
Planning & Design |  | IF Request for Information (RFI), deliverables below: | [6 empty] | IF Request for Information (RFI), deliverables below:
Planning & Design | 95 | RFI |  |  | ITGC03 ITGC04 | Y | Y
Execute & Build | 31 | Application Architecture Design (AAD) | DIT-T Architecture Approval Required | Y | ITGC01 ITGC02 | Y | Y
Execute & Build | 96 | Code Structural Quality Analysis (CAST) Report | If required |  |  | Y | Y
Execute & Build | 97 | Component Integration Test (CIT) Approved |  |  |  | Y | Y
Execute & Build | 98 | System Integration Test (SIT) Approved |  |  |  | Y | Y
Execute & Build | 99 | Performance Testing Approved | If required |  |  | Y | Y
Execute & Build | 100 | IT Testing Complete Approval |  |  |  | Y | Y
Execute & Build | 101 | User Acceptance Plan and Script | IT management involves users in the design of applications, selection of packaged software and testing thereof. | Y | ITGC03 | Y | Y
Execute & Build | 102 | Sponsor Approved UAT |  | Y | ITGC03 | Y | Y
Execute & Build | 103 | Implementation Plan |  |  |  | Y | Y
Execute & Build | 104 | Go Live Readiness Assessment |  | Y | ITGC03 | Y | Y
Execute & Build | 105 | Go Live Approval | Business and other Stakeholders approval | Y | ITGC03 | Y | Y
Execute & Build | 106 | Project Go Live Readiness DP Quality Review | If required
Execute & Build | 107 | EPMO Go Live Readiness DP Approval | If required. EPMO approval
Execute & Build | 108 | E&B Exit Quality Review |  |  |  | Y | Y
Implementation | 109 | Business Approval to Close the Project |  |  | ITGC03 | Y | Y
Implementation | 110 | Implementation Exit Quality Review |  |  |  | Y | Y
Closeout | 111 | SAP Commitments Reconciled |  |  |  | Y | Y
Closeout | 112 | Lessons Learned Survey |  |  |  | Y | Y
Closeout | 113 | EPMO Lessons Learned |  |  |  | Y | Y
Closeout | 114 | EPMO Closeout Report |  |  |  | Y | Y
Closeout | 115 | Closeout Quality Review |  |  |  | Y | Y
Note on A1: Enter the name of the unit that owns the mapped methodology.
Note on D1: Enter person to contact if there are questions about the mapped methodology.
Note on J1: Enter the date approved and added to the DIT-T Enterprise SDLC site on Connect.
Note on A2: Enter the name the unit refers to their methodology by.
Note on D2: Enter the name of the Quality Management Plan used; most units will use the DIT-T Enterprise Quality Management Plan. If not, provide the name of your plan and include in that plan that you are following the DIT-T Enterprise Quality Management Plan and this plan includes additional quality requirements.
Note on J2: Enter the date the methodology was last updated and approved.
Note on A3: Enter the industry type of methodology mapped, such as Agile, Iterative, Waterfall, etc.
Note on D3: Enter the location where deliverable artifacts are stored.
Note on J3: Enter additional information about the methodology, if needed.
Note on K4: For the process to be mapped, review the DIT-T SDLC Key Deliverable in column C to determine if the deliverable is created, if it is called by a different name, and the name of the phase initiated in. Deliverables on all projects and required for audit should not be deleted (see column E).
Note on J5: Enter a 'Y' for required deliverables. The column is prepopulated with the project type values (H) to be mapped to. If additional deliverables in the Key Deliverables column (C) are required by the mapped methodology, enter a ‘Y’ in this column, enter phase name and key deliverable name. Use red text to indicate different from the DIT-T Enterprise SDLC Deliverables.
Note on K5: Enter the phase name for the phase the deliverable is initiated in.
Note on L5: Enter the name of the deliverable (this is the name that will be used for the document artifact name found in the Deliverables Repository specified above). If the deliverable is located in another system, such as a Work Request is located in ServiceNow, indicate how to find the deliverable and the System Name where it can be found. Examples can be found in the 'Approved Methodologies' folder, document name 'PMO_Enterprise Project (Waterfall)'.