## INTERMEDIATE CONTRACT TIME NUMBER AND LIQUIDATED DAMAGES:

|  |  |  |
| --- | --- | --- |
| (2-20-07) | 108 | SP1 G14 B |

The Contractor shall not narrow or close a lane of traffic on **[road name]**, detain and /or alter the traffic flow on or during holiday weekends, special events, or any other time when traffic is unusually heavy, including the following schedules:

HOLIDAY AND HOLIDAY WEEKEND LANE CLOSURE RESTRICTIONS

1. For **unexpected occurrence** that creates unusually high traffic volumes, as directed by the Engineer.

2. For **New Year's Day**, between the hours of **[hour]** December 31st and **[hour]** January 2nd. If New Year's Day is on a Friday, Saturday, Sunday or Monday, then until **[hour]** the following Tuesday.

3. For **Easter**, between the hours of **[hour]** Thursday and **[hour]** Monday.

4. For **Memorial Day**, between the hours of **[hour]** Friday and **[hour]** Tuesday.

5. For **Independence Day**, between the hours of **[hour]** the day before Independence Day and **[hour]** the day after Independence Day.

If **Independence Day** is on a Friday, Saturday, Sunday or Monday, then between the hours of **[hour]** the Thursday before Independence Day and **[hour]** the Tuesday after Independence Day.

6. For **Labor Day**, between the hours of **[hour]** Friday and **[hour]** Tuesday.

7. For **Thanksgiving Day**, between the hours of **[hour]** Tuesday and **[hour]** Monday.

8. For **Christmas**, between the hours of **[hour]** the Friday before the week of Christmas Day and **[hour]** the following Tuesday after the week of Christmas Day.

9. For **[Event Name]**, between the hours of (Time) the (Day) of the week of the **(Event Name)** and (time) the following (Day) after the week of the **[Event Name]**.

And/or

For **[Event Name]**, occurring at **[Location]** between **[number]** hours before the start and **[number]** hours after the end of the **[Event Name]**.

Holidays and holiday weekends shall include New Year's, Easter, Memorial Day, Independence Day, Labor Day, Thanksgiving, and Christmas. The Contractor shall schedule his work so that lane closures are not required during these periods, unless otherwise directed by the Engineer.

The time of availability for this intermediate contract work shall be the time the Contractor begins to install all traffic control devices for lane closures according to the time restrictions listed herein.

The completion time for this intermediate contract work shall be the time the Contractor is required to complete the removal of all traffic control devices for lane closures according to the time restrictions stated herein and place traffic in the existing traffic pattern.

The liquidated damages are **[words] Dollars** ($**(number).00**) per hour.