
INTERMEDIATE CONTRACT TIME NUMBER [number]
INCENTIVE PAYMENT AND LIQUIDATED DAMAGES (RAILROAD FLAGGERS):
	   (8-19-08)(Rev.1-16-24)
	108
	SPI 1-01A



The Contractor shall complete all work included in this contract which requires a railroad flagger within an aggregate total of ________ days of flagger use.

The day of availability for this intermediate contract time will be the first day on which a railroad flagger is used. 

The work requiring a railroad flagger is hereinafter referred to as "intermediate contract work".

It is mutually agreed that time is of the essence in completing all of this "intermediate contract work".  It is further mutually agreed a delay in completing this work will result in damage due to increased engineering and flagger costs to the Department of Transportation.

By reason of the necessity of completing this "intermediate contract work", it is mutually agreed the Contractor will receive an incentive payment of $ (Dollars) ___________________ per flagger day fewer than an aggregate total of ________ flagger days that this "intermediate contract work" is completed.  Incentive payment will be limited to a maximum of $ (Dollars) ___________________.  Incentive payment determined to be due the Contractor will be paid by the Department within forty-five (45) calendar days after completion of all of this "intermediate contract work".  No incentive payment will be allowed if the contract is terminated under the provisions of Article 108-13 of the Standard Specifications.

Liquidated damages of $ (Dollars) ___________________ per flagger day will be assessed the Contractor for each flagger day the “intermediate contract work” exceeds an aggregate total of ________ flagger days. 

The Engineer will withhold the liquidated damages as they accrue from the amount of monies due on work performed in the contract.  

Upon apparent satisfactory completion of this “intermediate contract work”, a final inspection will be held on this “intermediate contract work” in accordance with Article 105-17 of the Standard Specifications and upon acceptance, the State will assume responsibility for the costs of other railroad flagging.

Flagger days will be granted for authorized time extensions in accordance with Article 108-10 of the Standard Specifications.

