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Except for that work required under the Project Special Provisions entitled Planting, Reforestation and/or Permanent Vegetation Establishment included elsewhere in this proposal, the Contractor shall complete all work included in this contract and shall place and maintain traffic on same. 
	
The date of availability for this intermediate contract time is (Date______________________).

The completion date for this intermediate contract time is (Date________________________).

It is mutually agreed that time is of the essence in completing Intermediate Contract Time Number {#__} and opening same to traffic.  It is further mutually agreed a delay in completing this work will result in damage due to increased engineering and inspection costs to the Department of Transportation, great hardship to the general public, public inconvenience, obstruction of traffic, interference with business, and increased cost of maintaining traffic.  

By reason of the necessity of expeditious completion of the work included in Intermediate Contract Time {#__}, and placing and maintaining traffic on same, it is mutually agreed, the Contractor shall receive an incentive payment of (words______________________) Dollars ($________________) per calendar day for each day prior to (Date or Completion Date___________________) that this work is completed.  Incentive payment shall be limited to a maximum of (words________________________) Dollars ($________________).  No incentive payment shall be allowed for any calendar day after (Date__________________) that this work remains incomplete.  This (Date__________________) date shall be utilized in determining incentive payments and it shall not be revised for any reason whatsoever.  Incentive payment determined to be due the Contractor shall be paid by the Department within forty-five (45) calendar days after completion of all work.  No incentive payment shall be allowed if the contract is terminated under the provisions of Article 108-13 of the Standard Specifications.

Disincentive of (words___________________) Dollars ($________________) per calendar day shall be assessed the Contractor for each day beyond (Date or Completion Date___________________) for Intermediate Contract Time {#__}  that the work is not completed.

The Engineer shall withhold the disincentives as they accrue from the amount of monies due on work performed in the contract.  

Upon apparent completion of all work required to be completed by this intermediate date, a final inspection will be held in accordance with Article 105-17 and upon acceptance, the Department will assume responsibility for maintenance of all work except Planting, Reforestation and/or Permanent Vegetation Establishment.  The Contractor will be responsible for and shall make corrections of all damages to the completed roadway caused by planting operations, whether occurring prior to or after placing traffic through the project.  
