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Revise the Standard Specifications as follows:

Page 1-47, Article 105-17, line 27, insert the following after the last paragraph:

When the special provisions provide for a reduction in the rate of liquidated damages for the contract time or an intermediate contract time after the work is substantially complete, the work will be considered substantially complete when the following requirements are satisfied:

1. Through traffic has been placed along the project or along the work required by an intermediate contract time and the work is complete to the extent specified below, and all lanes and shoulders are open such that traffic can move unimpeded at the posted speed.  Intersecting roads and service roads are complete to the extent that they provide the safe and convenient use of the facility by the public.

1. The final layers of pavement for all lanes and shoulders along the project or along the work required by an intermediate contract time are complete.

1. All signs are complete and accepted except for the signs on intersecting roadways.

1. All guardrails, drainage devices, ditches, excavation and embankment are complete.

1. Remaining work along the project consists of permanent pavement markings, permanent pavement markers or incidental construction that is away from the paved portion of the roadway.

Upon apparent substantial completion of the entire project or the work required by an intermediate contract time, the Engineer will make an inspection of the work.  If the inspection discloses the entire project or the work required by an intermediate contract time is substantially complete, the Engineer will notify the Contractor in writing that the work is substantially complete.  If the inspection discloses the entire project or the work required by an intermediate contract time is not substantially complete, the Engineer will notify the Contractor in writing of the work that is not substantially complete.  The entire project or the work required by an intermediate contract time will not be considered substantially complete until all of the recommendations made at the time of the inspection have been satisfactorily completed.

