## Slide 1: Division & Central Best Practices
Contract Standards & Development
(Jon Weathersbee, Ken Kennedy, Jeff Renn, Allen Fowler, Nicole Hackler)
October 6, 2026

## Slide 2: Agenda
Division & Central Best Practices
Division Let Increase for Eligible Bridge Projects
Contract Time Guidance for Divisions on Bridge Replacement Projects
Lump Sum Grading
Major Contract and Specialty Items
Steel Price Adjustment
Common Errors and Omissions
(Closed Caption Video of this Presentation is available upon request.)
Notes: https://ncconnect-my.sharepoint.com/personal/arfowler1_ncdot_gov/_layouts/15/stream.aspx?id=%2Fpersonal%2Farfowler1%5Fncdot%5Fgov%2FDocuments%2FRecordings%2FCS%5FD%20Division%20Let%20Increase%20Discussion%2D20261006%5F090208%2DMeeting%20Recording%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2Ef37af208%2D5c42%2D4a28%2Db888%2D5d2a1e44a2f5&xsdata=MDV8MDJ8bGVwZW5ueUBuY2RvdC5nb3Z8MjI0ZGQyNjZkMjk3NGViNGE3MWMwOGRmMjg3MjlhNmV8N2E3NjgxZGNiOWQwNDQ5YTg1YzNlY2MyNmNkN2VkMTl8MHwwfDYzOTI3NDE0NDgyNzQxODIwMXxVbmtub3dufFRXRnBiR1pzYjNkOGV5SkZiWEIwZVUxaGNHa2lPblJ5ZFdVc0lsWWlPaUl3TGpBdU1EQXdNQ0lzSWxBaU9pSlhhVzR6TWlJc0lrRk9Jam9pVFdGcGJDSXNJbGRVSWpveWZRPT18MHx8fA%3D%3D&sdata=WmZYVk92Ym1MMDVZeUhrN2tXdy80Zyt0MExQc3ZzeXEvd2hEVkdaZ3pkcz0%3D&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMjAzMjYuMjAxNDQiLCAiT1MiIDogIldpbmRvd3MiIH0%3D

## Slide 3: Division Let Increase for Eligible Bridge Projects
Jon Weathersbee
October 6, 2026
Notes: Thanks for the intro; as mentioned my name is Allen Fowler, and I serve as the Division Contracts Liaison. I have previous Division experience in maintenance, construction, and district offices in various roles and my last four years in Central, primarily contract standards unit.

## Slide 4: Where we’ve been, where we’re going:
DPOC projects capped at $5M since 2016
Bridge Replacements now allowed up to $10M
CSDU hosting meetings with Divisions:
      Goal is consistency
      Meetings via Teams twice per year
      Multiple topics per session
Division / Contractor feedback to help guide future topics

## Slide 5: background
Background:
    Bridge projects reviewed in 2025:
        Central - 3 projects ($6M to $16M)
        Divisions - 1 from each Division (< $5M)
    Overall good, some differences noted:
  - lump sum grading - shallow undercut
  - major contract items - restrikes for pile driving
  - contract times / ICTs - UBO / UC provisions, plans, items
  - steel price adjustment - provisions, std drawings, addenda
    Chief’s office and Industry foresee minimal issues

## Slide 6: Memo authorizing the increase

## Slide 7: Eligible projects
Bridge Replacement DPOC projects up to $10M
Multiple Bridges in one contract allowed <$10M
Culvert replacements allowed
CSDU Review required – send Plans & Proposal two weeks before advertisement (DivisionLetReviews@ncdot.gov)
SMU Reviews required – Preliminary General Design and 90% plans (Trey Carroll – thcarroll1@ncdot.gov)
No bridges/culverts on interstates (Central let only)
No other project types over $5M at this time

## Slide 8: Topics for meeting
Topics for today’s meeting:
Contract Time Development
Major and Specialty Items
Steel Price Adjustment
PS&E Packages
Lump Sum Grading

## Slide 9: Contact us
Jon Weathersbee
jweathersbee@ncdot.gov
919-707-6901

## Slide 10: CONTRACT TIME GUIDANCE FOR DIVISIONS ON BRIDGE REPLACEMENT PROJECTS
Ken Kennedy, PE
October 6, 2026

## Slide 11: CONTRACT TIME RECOMMENDATION
CONTRACT TIME GUIDANCE FOR DIVISIONS
Setting a Date of Availability (DOA)
Using Production Rates
Checking the Completion Date

## Slide 12: SETTING A DATE OF AVAILABILITY (DOA)
CONTRACT TIME GUIDANCE FOR DIVISIONS
Let Milestone Generator
Right of Way Field Certification
Utility by Others Special Provision
Material Acquisitions

## Slide 13: PRODUCTION RATES
CONTRACT TIME GUIDANCE FOR DIVISIONS
Plan & Estimate Review
Selecting a Production Rate
Provisions / Recommendations

## Slide 14: PRODUCTION RATES (CONT.)
CONTRACT TIME GUIDANCE FOR DIVISIONS
Plan & Estimate Review
Selecting the Correct Production Rate

## Slide 15: CONTRACT TIME GUIDELINES
CONTRACT TIME GUIDANCE FOR DIVISIONS

## Slide 16: PRODUCTION RATES (CONT.)
CONTRACT TIME GUIDANCE FOR DIVISIONS
Rate
“Overlap Except”

## Slide 17: STRUCTURE WORKING DAYS
CONTRACT TIME GUIDANCE FOR DIVISIONS
Guidelines
Provided by SMU (or PEF)

## Slide 18: DOA AND COMPLETION DATE
CONTRACT TIME GUIDANCE FOR DIVISIONS
Assign DOA and Completion Date

## Slide 19: CHECKING THE COMPLETION DATE
CONTRACT TIME GUIDANCE FOR DIVISIONS
Account to Winter Working Conditions
Account for temperature or seasonal requirements per the SPECS
SO, WHAT ARE WE MISSING?

## Slide 20: CHECK THE DOA
CONTRACT TIME GUIDANCE FOR DIVISIONS
Green Sheet Commitments
Permits
Local Notes

## Slide 21: ACCELERATED CONSTRUCTION
CONTRACT TIME GUIDANCE FOR DIVISIONS
Justification
User Costs

## Slide 22: ACCELERATED CONSTRUCTION – RULE OF THUMB
CONTRACT TIME GUIDANCE FOR DIVISIONS
If the User Cost (UC) < $1,000, do not use Accelerated Construction.
If the UC > $1,000, accelerate construction to (17) working days.
If the UC > $10,000, accelerate construction to (18) working days.
If the UC > $30,000, accelerate construction to (19) working days.
If the UC > $50,000, accelerate construction to (20) working days.

## Slide 23: ACCELERATED CONSTRUCTION (CONT.)
CONTRACT TIME GUIDANCE FOR DIVISIONS
Assign DOA and Completion Date
How do Material Acquisitions impact the project’s duration?
Assign Final Date and acquire Concurrence

## Slide 24: MATERIAL ACQUISITION
CONTRACT TIME GUIDANCE FOR DIVISIONS
Assign DOA and Completion Date
How do Material Acquisitions impact the project’s duration?
Assign Final Date and acquire Concurrence

## Slide 25: Contact us – Lump Sum Grading, Major Contract Items, Specialty Items
Ken Kennedy, PE
drkennedy1@ncdot.gov
919-707-6910
Josh Sellers, PE
jcsellers1@ncdot.gov
919-707-6908
Marsha Sample
mmsample@ncdot.gov
919-707-6915
Notes: I appreciate the time and interest in participating in our discussion. Our intent was to cover easily fixed or common omissions that had been identified. If there are any questions on the steel price adjustment provision or any future division needs related to contract consistency or additional outreach, please feel free to email me directly or copy me on any questions. Thanks.

## Slide 26: Lump Sum Grading
Jeff Renn
October 6, 2026
Notes: Thanks for the intro; as mentioned my name is Allen Fowler, and I serve as the Division Contracts Liaison. I have previous Division experience in maintenance, construction, and district offices in various roles and my last four years in Central, primarily contract standards unit.

## Slide 27: Lump Sum Grading Worksheet
Lump Sum Grading
Link for the Lump Sum Grading work sheet below; it’s provided by Contract Standards under our Contracts Resources tab:
Lump Sum Grading work sheet
Notes: This is a snapshot of the large fluctuations and increases in steel prices experienced during the years of 2021 through 2022. These type market conditions helped lead to the need for a Steel Price Adjustment Provision. The steel price adjustment can insulate our bidders against the fluctuations in the raw price of steel for products incorporated permanently into our projects. The Department and our bidders have an expectation that the provision will be uniformly included under our criteria to protect bidding activities from future supply and tariff impacts and general market fluctuations.

## Slide 28: Lump Sum Grading Worksheet Instructions
Lump Sum Grading
Link for the Lump Sum Grading work sheet below; it’s provided by Contract Standards under our Contracts Resources tab:
Lump Sum Grading work sheet
Notes: This is a snapshot of the large fluctuations and increases in steel prices experienced during the years of 2021 through 2022. These type market conditions helped lead to the need for a Steel Price Adjustment Provision. The steel price adjustment can insulate our bidders against the fluctuations in the raw price of steel for products incorporated permanently into our projects. The Department and our bidders have an expectation that the provision will be uniformly included under our criteria to protect bidding activities from future supply and tariff impacts and general market fluctuations.

## Slide 29: Lump Sum Grading SP02 R016 and Pay Items
Lump Sum Grading
Automated Proposal Application, Line Up Sheet (see this link below for the location of the application and current line up sheets):
Automated Proposal Application website
See Contract Resources Additional Resources section
for the latest
Pay Item List
Notes: This is a snapshot of the large fluctuations and increases in steel prices experienced during the years of 2021 through 2022. These type market conditions helped lead to the need for a Steel Price Adjustment Provision. The steel price adjustment can insulate our bidders against the fluctuations in the raw price of steel for products incorporated permanently into our projects. The Department and our bidders have an expectation that the provision will be uniformly included under our criteria to protect bidding activities from future supply and tariff impacts and general market fluctuations.

## Slide 30: Major Contract and Specialty Items
Jeff Renn
October 6, 2026
Notes: Thanks for the intro; as mentioned my name is Allen Fowler, and I serve as the Division Contracts Liaison. I have previous Division experience in maintenance, construction, and district offices in various roles and my last four years in Central, primarily contract standards unit.

## Slide 31: Major Contract Items Article 104-5
Major Contract and Specialty Items
Discussion of Specifications, Provision, and determination of use for Major Contract Items.
Standard Specifications Article 104-5
General and Overruns Increase in Unit Price

## Slide 32: Major Contract Items Article 104-5 (Subarticle 104-5(C))
Major Contract and Specialty Items
Discussion of Specifications, Provision, and determination of use for Major Contract Items.
Standard Specifications Article 104-5
Underruns Increase in Unit Price

## Slide 33: Major Contract Items Article 104-5 (Subarticle 104-5(C) and (D))
Major Contract and Specialty Items
Discussion of Specifications, Provision, and determination of use for Major Contract Items.
Standard Specifications Article 104-5
Underruns Increase in Unit Price continued and Overruns and Underruns Reduction in Unit Price

## Slide 34: Major Contract Items SP01 G028
Major Contract and Specialty Items
Discussion of Specifications, Provision, and determination of use for Major Contract Items.
Automated Proposal Application, Line Up Sheet (see this link below for the location of the application and current line up sheets):
Automated Proposal Application website

## Slide 35: Major Contract Items SP01 G028 Special Provision
Major Contract and Specialty Items
Discussion of Specifications, Provision, and determination of use for Major Contract Items.
Special Provision SP01 G028

## Slide 36: Specialty Items Article 108-6
Major Contract and Specialty Items
Discussion of Specifications, Specialty Items provisions and APA text for use; relationship to determining percentage of contract sublet.
Standard Specifications Article 108-6

## Slide 37: Specialty Items SP01 G037
Major Contract and Specialty Items
Discussion of Specifications, Specialty Items provisions and APA text for use; relationship to determining percentage of contract sublet.
Automated Proposal Application, Line Up Sheet (see this link below for the location of the application and current line up sheets):
Automated Proposal Application website

## Slide 38: Specialty Items SP01 G037 Special Provision
Major Contract and Specialty Items
Discussion of Specifications, Specialty Items provisions and APA text for use; relationship to determining percentage of contract sublet.
Special Provision SP01 G037

## Slide 39: Contact us – Lump Sum Grading, Major Contract Items, and Specialty Items
Jeff Renn
ext-jjrenn@ncdot.gov
Notes: I appreciate the time and interest in participating in our discussion. Our intent was to cover easily fixed or common omissions that had been identified. If there are any questions on the steel price adjustment provision or any future division needs related to contract consistency or additional outreach, please feel free to email me directly or copy me on any questions. Thanks.

## Slide 40: Steel Price Adjustment
Allen Fowler
October 6, 2026
Notes: Thanks for the intro; as mentioned my name is Allen Fowler, and I serve as the Division Contracts Liaison. I have previous Division experience in maintenance, construction, and district offices in various roles and my last four years in Central, primarily contract standards unit.

## Slide 41: Steel Price Adjustment SP01 G047
Division & Central Consistency
Notes: I will be sharing a brief overview of the departments steel price adjustment provision SP1 G47 and a discussion of determining when it should be included in our proposals. Please hold questions until the end since the answer may be offered by a later slide. I remember before this provision discussing with contractors and I was doubtful we would have an adjustment, but there came a time when it was sorely needed.

## Slide 42: Steel Price Adjustment SP01 G047
Steel Price Adjustment
Steel price increase in 2021
Steel price fluctuations
Notes: This is a snapshot of the large fluctuations and increases in steel prices experienced during the years of 2021 through 2022. These type market conditions helped lead to the need for a Steel Price Adjustment Provision. The steel price adjustment can insulate our bidders against the fluctuations in the raw price of steel for products incorporated permanently into our projects. The Department and our bidders have an expectation that the provision will be uniformly included under our criteria to protect bidding activities from future supply and tariff impacts and general market fluctuations.

## Slide 43: Steel Price Adjustment SP01 G047
Steel Price Adjustment
Special provisions website
Special Provision SP01 G047
Notes: The steel price adjustment provision is stored and maintained with our other standard provisions; starting at the top the tab for Resources, down to Contract Standards, then Specifications and Special Provisions. It is also provided in the APA – the automated proposal application – to be reviewed and inserted by the contract officer when the criteria are met during development of the letting and proposal document. The APA also includes instructions for use on the provision.

## Slide 44: Steel Price Adjustment SP01 G047 Provision
Steel Price Adjustment
Notes: The provision includes 11 pages of information, links, and examples of how the adjustment is applied and the proper steps for the contractor to submit documentation. A lot of the information covers post let activities and although important, <next slide> our discussion is concerned primarily with the first two highlighted headings.

## Slide 45: Steel Price Adjustment Provision Overview
Steel Price Adjustment
Notes: They are the description and purpose followed by the eligible items. These two sections provide the basis for when the provision is applicable, and the list of items covered and the limitations.

## Slide 46: Steel Price Adjustment Details
Steel Price Adjustment
Description and Purpose
Steel price adjustments will be made to the payments due the Contractor for items as defined herein that are permanently incorporated into the work, when the price of raw steel mill products utilized on the contract have fluctuated. The Department will adjust monthly progress payments up or down as appropriate for cost changes in steel according to this provision.
Note the adjustment criteria defines products incorporated permanently into the project.
Notes: The first section states that we will apply the adjustment to the defined appropriate items, and the restriction that the adjustment is only to items permanently incorporated into the work. The adjustment will be applied to the monthly payments when the price fluctuates on applicable products that are utilized on the project, and the adjustment will be up or down as appropriate. <next>

## Slide 47: Steel Price Adjustment Eligible Items
Steel Price Adjustment
Eligible Items
The list of eligible bid items for steel price adjustment can be found on the Departments website at the following address:
https://connect.ncdot.gov/letting/LetCentral/Eligible Bid Items for Steel Price Adjustment.xlsx
Nuts, bolts, anchor bolts, rebar chairs, connecting bands and other miscellaneous hardware associated with these items shall not be included in the price adjustment.
Adjustments will only be made for fluctuations in the material cost of the steel used in the above products as specified in the Product Relationship Table below. The producing mill is defined as the source of steel product before any fabrication has occurred (e.g., coil, plate, rebar, hot rolled shapes, etc.). No adjustment will be made for changes in the cost of fabrication, coating, shipping, storage, etc.
No steel price adjustments will be made for any products manufactured from steel having an adjustment date, as defined by the Product Relationship Table below, prior to the letting date.
Notes: The second section details eligible items and provides the important eligible items list link that defines what pay items are covered by the provision. The provision does not cover all steel items; miscellaneous hardware and fabrication, shipping, coating, and items not included on the list are not part of the adjustment. The adjustment will not apply to products manufactured from steel having a determined adjustment date prior to the letting date.

## Slide 48: Steel Price Adjustment
Steel Price Adjustment
Criteria for SP01 G047
There are two basic criteria to determine when to include the steel price adjustment:
All Centrally let projects and Division projects with a duration greater than one year. This is from letting to completion date, excluding permanent vegetation establishment. Projects that are less than 1 year in duration should not include this provision.
When project steel pay items are listed in the current eligible bid items for steel adjustment; link to eligible bid items for the adjustment ; Pay items in the list range from guardrail, concrete pavement, fence, utilities, signal, bridge and additional.
Project exceeds one year and includes eligible steel items
Notes: Based on the provision text there are two basic criteria for when to include the steel adjustment provision. Initially you must determine if the duration of the project will exceed one year. <next slide >This would be from the letting or bid opening date until the completion date, not counting the permanent vegetation establishment. Outside the scope of this discussion but be aware this first criteria will exempt the majority of ID/IQ and Maintenance type contracts that are limited to durations of 1 year. <next slide> Second, you must determine if the project items include any of the pay items from the eligible bid items list for steel adjustment. <next slide> Currently this list includes roughly 140 pay items under various disciplines; numerous guardrail items, sign supports, metal fence items, encasement pipes, signal poles, and structure items that incorporate steel. The list is provided through the link in the provision itself.

## Slide 49: Steel Price Adjustment Resources
Steel Price Adjustment
Criteria for SP01 G047
Central Let Resources Website
Eligible Bid Items for Steel Price Adjustment
Notes: Outside the provision link you can directly access that list file of eligible items; it is stored on the connect site under Bidding and Letting at Central Letting Resources. The Eligible Bid Items for Steel Price Adjustment and forms SPA-1 and SPA-1DB (Design Build) can also be accessed here.

## Slide 50: Steel Price Adjustment SP01 G047 and resurfacing contracts
Steel Price Adjustment
Resurfacing Contracts
Resurfacing projects (by definition) would not normally meet the criteria for the adjustment. Standard resurfacing contracts will include asphalt, aggregate, and pavement materials with associated pay items, and not normally include permanently installed steel items. However, a resurfacing project exceeding the one-year timeframe and including eligible items (such as guardrail, lighting, or signals items) will meet the criteria and trigger the need to include the provision.
Criteria for SP01 G047
Notes: As previously mentioned, standard maintenance and ID/IQ contracts will not meet the criteria for the provision; and the items are often covered under separate escalation clauses. Traditionally, resurfacing contracts would include primarily asphalt, pavement, and limited aggregate materials and these items also fail to meet the criteria. However, due to various challenges the divisions occasionally expand their resurfacing work scope to accomplish needed roadway items under their resurfacing projects, as shown in this example resurfacing that included the adjustment. Although not expected, if a resurfacing project meets the provisions two criteria and exceeds1 year with eligible items, it would be necessary to include the steel adjustment provision.

## Slide 51: Steel Price Adjustment Recap
Steel Price Adjustment
Recap
Provision will be included when:
Project has a duration greater than one year, excluding permanent vegetation establishment.
Project includes steel pay items listed in the eligible bid items sheet.
The adjustment is not to be applied retroactively and does not apply to:
Items not permanently incorporated into the project.
Products manufactured from steel having an adjustment date prior to the letting date.
Additional notes:
Includes a link for form SPA-1 to be submitted in accordance with the provision listing line items the contractor selects to have adjustments applied link for form SPA-1 .
Includes a link for the steel price adjustment calculator with monthly reference data to determine the steel adjustment monthly total link for monthly steel adjustment calculator.
Notes: Now for a quick recap of the Steel Price Adjustment.
Be aware this should be considered a non-discretionary provision; from the first bullet set policy is to Include this provision when project duration is greater than one year and pay items include steel items from the eligible items list.
The second bullet set the adjustment is not applied retroactively, does not apply to items that are not permanently incorporated into the project, or products manufactured from steel having an adjustment date prior to the letting date; and note the provision includes details for determining this steel product adjustment date.

## Slide 52: Contact us – Steel Price Adjustment
Allen Fowler
arfowler1@ncdot.gov
919-707-6927
Notes: I appreciate the time and interest in participating in our discussion. Our intent was to cover easily fixed or common omissions that had been identified. If there are any questions on the steel price adjustment provision or any future division needs related to contract consistency or additional outreach, please feel free to email me directly or copy me on any questions. Thanks.

## Slide 53: Common Errors and Omissions
Nicole Hackler
October 6, 2026
Notes: Thanks for the intro; as mentioned my name is Allen Fowler, and I serve as the Division Contracts Liaison. I have previous Division experience in maintenance, construction, and district offices in various roles and my last four years in Central, primarily contract standards unit.

## Slide 54: Common Errors & Omissions
Earthwork
  Balance Sheet ≠ Earthwork Summary ≠ X-Section Summary/Report
  Detour Removal missing from Earthwork Summary
  Earthwork does not correctly account for Traffic Control phasing (NEW)
  Confusion or Omission of Shoulder Borrow / Shoulder Construction
  Undercut Excavation missing from Profiles / X-Sections
  NEW GUIDANCE COMING – Soon to be on the 3-G1 Sheet
Drainage
  Drainage Summary Sheets ≠ Drainage Design on Plan Sheets
  Drainage Details ≠ Drainage Design on Plan Sheets
Other Omissions
  Temporary Guardrail shown on TMP; missing from GR summary, and
  Temporary GR pay items missing
  Temporary Pavement shown on TMP; Temporary Pavement Typical Sections missing, and Temporary Pavement pay items missing
  Temporary Shoring notes missing from TMP
  Temporary Shoring quantities per site missing from plans
  Shallow Undercut by Station Range missing from X-Sections
  CURRENTLY UNDER REVIEW
ncdot.gov
54
Notes: Good morning everyone. I’m Nicole Hackler, the State Plans and Standards Engineer, and I’ve been asked to briefly touch on common errors and omissions we often see in centrally let projects, so that the Divisions can also be on the lookout for these items in Division Let projects.
If any of you attended the presentation on Quality PS&E packages at the ACEC conference a few years ago, some forthcoming items on this slide might look familiar to you. Although many of the same errors and omissions are still occurring today as back then, there are other issues that have either evolved or been eliminated by new platforms we are using, while new issues have come to light. So keep in mind that although some of these bullets are the same as before, other information has been added or changed, but I have tried to indicate all items that have undergone revisions or updates.
The number one thing, and probably one of the most common errors we still see is that Earthwork is rarely correct.
The volumes listed on the balance sheet, earthwork summary, and the cross section summary or report should all match, but rarely do. This is an easy fix with quality control. Make one last check prior to advertisement to compare all of these items and make sure everything aligns.
If you have a detour on your project, you must also have detour removal accounted for in your earthwork summary.
Earthwork does not correctly take into account Traffic Control phasing. Although this is not a new problem, it has become such an issue lately, that we have added it as a new item to this list.
Confusion or omission of shoulder borrow and shoulder construction is another common error we still see. Know the difference between the two. Shoulder borrow should typically only be used on a waste job. Shoulder Construction and shoulder material is used when you have a borrow pit.
(You can’t have borrow and shoulder borrow on the same job.)
Undercut excavation missing from Profiles and X-sections.
New guidance on this bullet, though, is expected in the November 2026 RDM update. Up until now, undercut excavation was supposed to be shown on Profiles and X-sections, but this has evolved with the new ORD platform. Soon, undercut will no longer be required on the aforementioned sheets, but instead an earthwork report will be generated by ORD, and will replace the X-section summary. The Geotechnical Unit has already begun to include these undercut excavation tables on the 3-G1 Sheets. The take-away is that undercut excavation often gets omitted, so this is simply a reminder to make sure that it is included SOMEWHERE, although it may no longer be in the X-Sections and profiles as you were previously accustomed, but might be found instead on the 3G-1 sheet, and in the Geotechnical report. And I actually received a draft email this morning on this issue, laying out the new expectations, so I expect you will be receiving official notification of these changes very soon.
The 2nd most common place we see mistakes are in DRAINAGE: The exact same errors and omissions are occurring today as the last time I gave this presentation: drainage summary sheets very rarely match the plans. (For instance, plan sheets show a TBDI and the summary sheet shows a DI). Again, this is low hanging fruit and easily fixed – you’ll want to perform one final quality control comparison between the plans and the drainage summaries before you advertise, to make sure everything matches.
Additionally, check that all needed drainage details have been included, and that they are also the correct ones to match what’s shown in the plans.
Other omissions – READ
I would like to note, however, that shallow undercut by station range on X-sections is currently being evaluated. This requirement may change in the future, similar to what we have seen with undercut excavation that we discussed earlier – but for now shallow undercut by station should still be shown on X-sections, so you will want to double check that information is there.

## Slide 55: Common Errors & Omissions (Continued…)
100% PS&E Packages
PET Files (NEW)
  Generic or items with asterisks (**) require a supplemental description
  When adding supplemental descriptions, use ALL CAPS
  BE CONSISTENT WITH ENTRIES (e.g. 1-1/2” milling vs. 1.5” milling)
  The supplemental descriptions should match the Pay Items shown in
  the corresponding Special Provisions
Questions or comments can be emailed to: AWPHelp@ncdot.gov
?
?
?
55
Notes: And lastly, one of the new issues we have seen arise has to do with the PET files, and incorrect entries in these files.
As you know, we have transitioned over to PET files as the new way to input pay items and quantities. Unfortunately, PET file entry is extremely picky, and does not like any deviations from the proscribed methods.
For instance, when you have a generic item,or an item with asterisks in parenthesis, these require supplemental descriptions.
When inputting these supplemental descriptions, you must use all caps.
And you need to make SURE to be consistent in your entries. For instance, using 1-1/2” Milling as an example: if you enter 1 - dash – 1- slash 2 inch-mark milling, and then say another person from a different firm later enters 1.5” milling, these will come in as two separate pay items. Even something as simple as using the dash one time, and omitting it the next will create duplications. Having multiple pay items for the same thing is not only confusing, but it also throws off your bid averages. SO CONSISTENCY IS KEY.
Make sure your supplemental descriptions match the pay items shown in the corresponding Special Provisions.
These are just a few of the seemingly small things that if done incorrectly can give you import or export issues, and quickly derail a project. But in order to help with this, our estimating group has compiled a detailed set of instructions for your use, and I cannot emphasize enough the importance of following the guidelines. These can be found on a separate tab labeled “Instructions” embedded in the PET Excel sheets on the Contracts Resources webpage…Under Additional Resources shown here.
There are directions written specifically for Division Let projects, so you will want to follow these closely. The one good thing about PET files for Division Let projects is that only two files are required for each WBS – one for Roadway and one for Structures. This is different from Centrally let projects, who require a separate tab for each discipline. The guidance provided for Division let projects will help to ensure your estimates capture all items correctly. These instructions are routinely updated, so please always check back to the website for the newest version. Any changes made from the previous version will be denoted in red.
And if you need any assistance with PET file entry, do not hesitate to reach out to AWPhelp…
Thanks so much for your time!

## Slide 56: Contact us – Common Errors and Omissions
Nicole Hackler
nmhackler@ncdot.gov
919-707-6950
Notes: I appreciate the time and interest in participating in our discussion. Our intent was to cover easily fixed or common omissions that had been identified. If there are any questions on the steel price adjustment provision or any future division needs related to contract consistency or additional outreach, please feel free to email me directly or copy me on any questions. Thanks.