## Lead Times
MONTHLY MATERIAL SUPPLY CHAIN ISSUES REPORT | Updated: | 2022-07-05
MATERIAL | LEAD TIMES
Aggregates | 1 - 4 weeks (see notes)
Asphalt Mix | No known issues.
Cement | Cement on Allocation.
Emulsions | No known issues.
Ready-Mixed Concrete | 1 - 3 weeks (see notes)
Pavement Markings (Paint, Thermoplastic) | 2 weeks (see notes)
Fencing Items | (see notes)
Guardrail | No known issues.
Culvert Pipe, Reinforced Concrete | 4 - 12 weeks (see notes)
Culvert Pipe, Plastic | 4 - 8 weeks (see notes)
Culvert Pipe, Corrugated Metal | 4 weeks
Culvert Pipe, Welded Steel | 6 weeks
Utility Pipe, Ductile Iron | 24" & Smaller = 52 weeks; 30" & Larger = 36 Weeks
Utility Pipe, PVC | No known issues.
Precast Units | 3 - 8 weeks (see notes)
Prestress Units, Cored Slabs & Box Beams | 4 - 8 weeks (see notes)
Prestressed Units, Girders | 4 - 8 weeks (see notes)
Structural Steel, Girders | No known issues.
Structural Steel, Piles | No known issues.
Stay-In-Place (SIP) Forms | 16 weeks
Notes:
Aggregates: | General Size Aggregates – (ABC, 78M, 57, 67, 5, 467, screenings, etc.)
1 week – Sandhills / Charlotte Area / West
2 weeks - Piedmont / East
Other Aggregate Sizes (14M, #9)
3 weeks – Piedmont
4 weeks – West
Rip Rap
[Made as needed] – East / Piedmont
4 weeks – West
1 week - Sandhills / Charlotte Area
Ready Mix Concrete & Cement: | Lead times ranging from 1 – 3 weeks depending on region: Eastern and Western parts of the state running closer to 1 week; Piedmont running at 2 – 3 weeks.
Cement allocations across the board: one large supplier is about out of Type I cement and is moving all customers to Type IL (M&T working with Producers on Mix Design changes)
Allocations make Lead Times very specific to the plant location, size of order, and/or if speciality items/mixes are requested.
No Fly Ash supply issues.
Pavement Markings (Paint, Thermoplastic): | Typical lead times have resumed but are expected to increase into late summer.
Fencing Items: | See memo dated May 26, 2022 from E. Boyd Tharrington on Wood Post Availability.
Memo allows temporary modifications to fencing Standards in limited cases.
Culvert Pipe, Reinforced Concrete & Prestressed/Precast: | Concrete Pipe
Biggest issues for concrete pipe producers is availability of reinforcing steel for the pipe and availability of labor.
Precast Units
3 – 8 weeks for standard stock items; special order items may have greater lead times of 4 – 12 weeks. Labor still an issue.
Prestress Units, Girders
4 – 8 weeks from signed PO. Most plants have scheduled work on the books; new items must be worked in as scheduling allows.
Turnaround time for trucking permits has been a minor issue for some producers but it causes major scheduling issues when permitting delays do occur.
Deliveries/Trucking are still an issue with limited drivers and resources.
Cement allocations are regional and unpredictable, but most prestress producers have not been affected by the allocations.
Reinforcing steel availability has improved some but still seeing 3 – 6 week lead times and increasing cost.
Prestress Units, Cored Slabs & Box Beams
Cored Slabs = 4 – 8 weeks; Box Beams = 16 weeks from time of order to time of delivery.
Deliveries/Trucking are still an issue with limited drivers and resources. Labor issues affecting all levels of production.
Cement allocations are regional and unpredictable, but most prestress producers have not been affected by the allocations.
Reinforcing steel availability has improved some but still seeing 3 – 6 week lead times and increasing cost.
[NOTE: New Prestress facility - MST Concrete (PS30) - started production of cored slabs and box beams in June 2022]
Culvert Pipe, Plastic: | Pipe sizes 30" and above -- little to no inventory until late summer or early fall.