MOBILIZATION AND LIQUIDATED DAMAGES (Guardrail):

| (4-8-09) (Rev. 2-22-11) | 800 | SPD 08-100 |
| --- | --- | --- |

Description

“Routine mobilization” is defined as the cost of mobilizing for routine guardrail repair or installation. The Department may or may not provide the Contractor a list of locations to be repaired or installed at each notification.  Guardrail installation and routine repairs for damaged guardrail will have no minimum limits and the Contractor shall consider this when submitting his bid.  The Contractor shall report to the specified location within 30 calendar days after notification.

Revise the 2018 Standard Specifications as follows:

Page 8-1, add the following as new Article 800-1.5:

800-1.5	EMERGENCY MOBILIZATION

The Contractor shall arrive on site within 48 hours of notification.

Page 8-1, Article 800-2 MEASUREMENT AND PAYMENT, replace the first paragraph with the following:

Routine Mobilization will be paid at the contract unit price per each initial mobilization. Relocation within the District is considered incidental to the contract bid price.

Emergency Mobilization will be paid as the contract price per each emergency mobilization notification.  Once mobilized for an emergency repair, relocation for emergency or routine installation and repairs within the District is considered incidental to the initial notification.

The Contractor will only be paid one mobilization (routine or emergency) for each notification.

Liquidated damages for failure to report to or begin work within the above specified time will be charged according to the following:

Liquidated damages for routine mobilization are One Hundred Dollars ($100.00) per day per each notification beginning at the end of the thirty day routine notification time period.

Liquidated damages for emergency mobilizations are Three Hundred Dollars ($300.00) per day per each notification beginning at the end of the forty-eight hour emergency notification time period.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| Emergency Mobilization | Each |
| Routine Mobilization | Each |