## Sheet1
Signing and Delineation Project Coordination
Project Phase | Roadway Prerequisite | Milestone/Submittal | Action | Coordination | Deliverable | Performed By | Approval | S&D Subsequent Event
Planning | Project Identification | Preliminary Scoping Meeting | Attendance & Input | Project Development Team | Document Meeting Minutes | Managing Office |  | Final Scoping Meeting
Planning | Preliminary Scoping Meeting | Final Scoping Meeting | Attendance & Input | Project Development Team | Document Meeting Minutes | Managing Office
Planning | Functional Design | Routing change (US or Interstate) proposed as part of a project. | Develop Routing Concept Plan | NEPA PM | Map depicting existing and proposed routing for interstate, US, and NC routes | Managing Office or PEF | SDU, DTE, RTE | Proof of Concept or 25% Plans Begin route change coordination and approvals
Planning | Functional Design | Interchange Access Request (IAR) | Develop IAR Signing Concept for inclusion in IAR report | NEPA PM, Congestion Mgmt, Roadway Design | IAR Signing Concept by SDU or Consultant | Managing Office or PEF | SDU, DTE, RTE | Proof of Concept or 25% Plans
Planning | Functional Design | Proof of Concept: NEPA phase for complex projects: Interstate projects Urban Loops Toll Roads and Bridges Express Lane Projects | Develop Preliminary Signing Concept | NEPA PM, Congestion Mgmt, Roadway Design | Preliminary Signing Roll Plot | Managing Office or PEF | SDU, DTE, RTE | 25% Plans
Preliminary Design | Approved 25% Roadway Plans | Project Concept (25% plans) | Develop 25% Signing & Delineation Plans | Roadway Design for Geometry, RTE for Signal Recommendations | Signing and Delineation Roll Plot per SDU Procedure Manual | PEF | SDU, DTE, RTE | Approved 25% Signing needed prior to FDFI for coordination
Preliminary Design | Approved 65% Roadway Plans | Final Design or Combined Field Inspection | Attendance & Input | Project Development Team | Document Meeting Minutes | Managing Office or PEF |  | 50% Design Plans
Final Design | Approved Right-Of-Way Plans | 50% Design Plans | Develop 50% Signing & Delineation Plans | Roadway, Hydro, Utilities for OH sign locations | 50% Plans | PEF | SDU, DTE, RTE | 90% Design Plans
Final Design | Approved 90% Plans | Pre-Let field inspection | Attendance & Input | Project Development Team | Document Meeting Minutes | Managing Office or PEF |  | 90% Design Plans
Final Design | PLFI Occurrence | 90% Design Plans | Develop 90% Signing & Delineation Plans | Roadway, Hydro, Utilities for OH sign locations | 90% Plans | PEF | SDU, DTE, RTE | 100% Plans
Final Design | Approved 90% Plans | 100% Plans | Develop 100% Signing & Delineation Plans | Roadway, Hydro, Utilities for OH sign locations | 100% Unsealed Plans | PEF | SDU, DTE, RTE | Final Plans
Final Design | Approved 100% Plans | Final Plans | Develop Final Signing & Delineation Plans | Roadway, Hydro, Utilities for OH sign locations | Final Signing and Delineation Plans | PEF | SDU, DTE, RTE, Plan Checking | Final Sealed Plans
Final Design | Approved Final Plan | Final Sealed Plans | Develop Final Sealed Signing & Delineation Plans | Roadway, Hydro, Utilities for OH sign locations | Final Sealed Signing and Delineation Plans | PEF | SDU, DTE, RTE, Plan Checking | Project Letting
Construction | Final Grade | Construction Support Verification | Construction Unit to provide support/section verification information. Develop construction revision plans. | Resident Engineer | Sealed Construction Revision Plans | PEF | SDU or Division PM | Sign Requisition
Construction | Field Verification of Type A &B OHSA and Supports | Sign Requisition | Requisition Type A&B signs following support verification. Requisition Type D, E, F & mile marker signs 4 months prior to completion | Resident Engineer | Sign Requisitions | Managing Office | SDU or Division PM | Sign Installation
Construction | Construction Completion | Final Construction Inspection | Inspect installed signing against Final Sealed Plans for completeness and accuracy. | Resident Engineer |  | CEI | Division Construction | Project Open to traffic